## Overview
[CORTEX_V2.1] Job #2009 — · Overview
Schema CORTEX_V2.1 · canonical v2 builder · single source of truth
| OVERVIEW |  | SOURCE
IDENTITY
| Project Job Number | 2009
| Project Name: | Chinn Greenwood Apartments
CONTRACT & PARTIES
| General Contractor | Chinn Construction, LLC
JOB SITE
| Jobsite Location | Seattle, WA
| Plumbing Units | 168 | Kitchen Sinks
SCHEDULE
| Project Duration | Jul 2012 – Oct 2013 (~16 months)
SCOPE & DESIGN
| Total Fixtures | 812 | Tubs
| Fixtures / Unit | 4.83 | Showers
| Stacks | 36 | Cost Codes
| CONTRACT VALUE |  | NET PROFIT |  | DIRECT COST |  | LABOR HOURS
| $384,900 |  | $114,209 |  | $279,999 |  | 8,318
| Original $384,900 |  | 29.0% margin |  | 71.0% of revenue |  | 33 workers
COST BREAKDOWN
| Category | Budget | Actual | Variance | % Budget | % of Cost
| Labor | 72340 | 80901.5 | -8561.5 | 111.8% | 28.89%
| Material | 194061 | 150695.33 | 43365.67 | 77.65% | 53.82%
| Overhead | 10885 | 7510.52 | 3374.48 | 69% | 2.682%
| Burden | 38464.22 | 40891.46 | -2427.24 | 106.3% | 14.6%
| TOTAL | 315750.22 | 279998.81 | 35751.41 | 88.68% | 100%
PROJECT PROFILE
| Plumbing Units | 168 |  | Total Fixtures | 812 |  | Fixtures / Unit | 4.83
| Floors | 36 |  | Duration | Jul 2012 – Oct 2013 (~16 months)

## Budget vs Actual
[CORTEX_V2.1] Job #2009 — · Budget vs Actual
Schema CORTEX_V2.1 · canonical v2 builder · single source of truth
| cost_code | description | original_budget | revised_budget | actual | variance | pct_used | hours | source
LABOR
| 011 | DS & RD Labor | 1250 | 1250 | 1645 | -395 | 1.316%
| 100 | Supervision | 3000 | 3000 | 2992 | 8 | 99.73%
| 101 | Takeoff & Purchase Labor | 2500 | 2500 | 1324 | 1176 | 52.96%
| 110 | Underground Labor | 5350 | 5350 | 4209 | 1141 | 78.67%
| 111 | Garage Labor | 8960 | 8960 | 9872 | -912 | 1.102%
| 112 | Canout Labor | 2000 | 2000 | 1485.5 | 514.5 | 74.28%
| 120 | Roughin Labor | 34500 | 37530 | 46114 | -8584 | 1.229%
| 130 | Finish Labor | 10250 | 10320 | 11391.5 | -1071.5 | 1.104%
| 141 | Water Main/Insulation Lab | 0 | 0 | 0 | 0 | 0%
| 142 | Mech Room Labor | 1430 | 1430 | 1730 | -300 | 1.21%
| 145 | Tub/Shower Labor | 0 | 0 | 138.5 | -138.5 | 0%
MATERIAL
| 039 | DS & RD Material | 1250 | 1250 | 369.06 | 880.94 | 29.52%
| 210 | Underground Material | 2800 | 2800 | 2613.58 | 186.42 | 93.34%
| 211 | Garage Material | 10570 | 10570 | 3972.94 | 6597.06 | 37.59%
| 212 | Canout Material | 2800 | 2800 | 2749.23 | 50.77 | 98.19%
| 220 | Roughin Material | 33560 | 32510 | 30742.47 | 1767.53 | 94.56%
| 230 | Finish Material | 143270 | 143381 | 109975.66 | 33405.34 | 76.7%
| 241 | Water Main/Insulation Mat | 0 | 0 | 0 | 0 | 0%
| 242 | Mech Room Material | 2000 | 2000 | 641.45 | 1358.55 | 32.07%
| 245 | Tub/Shower Material | 0 | 0 | 0 | 0 | 0%
OVERHEAD
| 600 | Subcontractor | 4800 | 4885 | 2379 | 2506 | 48.7%
| 601 | Engineering/Plans | 6000 | 6000 | 4990.08 | 1009.92 | 83.17%
| 603 | Permits & Licenses | 0 | 0 | 141.44 | -141.44 | 0%
BURDEN
| 995 | Payroll Burden | 28928 | 32694.58 | 34412.05 | -1717.47 | 1.053%
| 998 | Payroll Taxes | 5532.48 | 5769.64 | 6479.41 | -709.77 | 1.123%
SOURCES
Job #2009 — Chinn Greenwood Apartments • GC: Chinn Construction, LLC • Seattle, WA
Canonical source: 2009 Job Detail Report.pdf (49 pages, OWP Sage Timberline export)
Cost codes parsed: 26
Unit count (168) and fixture count (812) from greenwood h20 stacks.xls and trim POs
3-level building + lobby: L1 (18 units), L2 (18 units), L3 (18 units), LW (amenity) × south/north stacks
Billing: GREENWOOD AGGREGATE BILLING.xlsx (11 pay apps Jul 2012 – Oct 2013)
Final contract $394,208 (original $384,900 + $9,308 COs)
| TOTAL |  | 310750.48 | 317000.22 | 280367.87 | 36632.35 |  | 0

## Cost Breakdown
[CORTEX_V2.1] Job #2009 — · Cost Breakdown
Schema CORTEX_V2.1 · canonical v2 builder · single source of truth
| category | cost_codes | actual | pct_of_direct_cost | pct_of_revenue | per_unit | source
| Labor | 11 | 72340 | 1.118% |  | 481.5565
| Material | 9 | 195311 | 77.35% |  | 899.1928
| Overhead | 3 | 10885 | 69% |  | 44.7055
| Burden | 2 | 38464.22 | 1.063% |  | 243.4015
B. LARGEST OVERRUNS (Actual > Revised Budget)
| Code | Description
| 120 | Roughin Labor | 37530 | 22.87%
| 995 | Payroll Burden | 32694.58 | 5.253%
| 130 | Finish Labor | 10320 | 10.38%
| 111 | Garage Labor | 8960 | 10.18%
| 998 | Payroll Taxes | 5769.64 | 12.3%
| 011 | DS & RD Labor | 1250 | 31.6%
| 142 | Mech Room Labor | 1430 | 20.98%
| 603 | Permits & Licenses | 0 | 0%
| 145 | Tub/Shower Labor | 0 | 0%
C. LARGEST SAVINGS (Actual < Revised Budget)
| Code | Description
| 230 | Finish Material | 143381 | 23.3%
| 211 | Garage Material | 10570 | 62.41%
| 600 | Subcontractor | 4885 | 51.3%
| 220 | Roughin Material | 32510 | 5.437%
| 242 | Mech Room Material | 2000 | 67.93%
| 101 | Takeoff & Purchase Labor | 2500 | 47.04%
| 110 | Underground Labor | 5350 | 21.33%
| 601 | Engineering/Plans | 6000 | 16.83%
| 039 | DS & RD Material | 1250 | 70.48%
| 112 | Canout Labor | 2000 | 25.72%
SOURCES
Job #2009 — Chinn Greenwood Apartments • GC: Chinn Construction, LLC • Seattle, WA
Canonical source: 2009 Job Detail Report.pdf (49 pages, OWP Sage Timberline export)
Cost codes parsed: 26
Unit count (168) and fixture count (812) from greenwood h20 stacks.xls and trim POs
3-level building + lobby: L1 (18 units), L2 (18 units), L3 (18 units), LW (amenity) × south/north stacks
Billing: GREENWOOD AGGREGATE BILLING.xlsx (11 pay apps Jul 2012 – Oct 2013)
Final contract $394,208 (original $384,900 + $9,308 COs)
| TOTAL |  | 625400.44 |  |  | 1668.8564

## Material
[CORTEX_V2.1] Job #2009 — · Material
Schema CORTEX_V2.1 · canonical v2 builder · single source of truth
| vendor_id | vendor_name | total_spend | transactions | category | source
| 039 | DS & RD Material | 1250 |  | 0.0024431
| 210 | Underground Material | 2800 |  | 0.017301
| 211 | Garage Material | 10570 |  | 0.0263
| 212 | Canout Material | 2800 |  | 0.018199
| 220 | Roughin Material | 32510 |  | 0.20351
| 230 | Finish Material | 143381 |  | 0.72801
| 241 | Water Main/Insulation Mat | 0 |  | 0
| 242 | Mech Room Material | 2000 |  | 0.0042462
| 245 | Tub/Shower Material | 0 |  | 0
B. VENDORS BY SPEND (AP)
| Vendor | # Invoices
| Ferguson Enterprises, Inc. | 65 | 117439.01
| Keller Supply Company | 14 | 29740.43
| Mechanical Sales, Inc. | 2 | 16339.3
| Franklin Engineering | 1 | 4895
| Mickelo Construction LLC | 1 | 2250
| Quality Concrete Products, Inc. | 4 | 1821
| Rosen Supply Company, Inc. | 2 | 1040.84
| Ferguson Enterprises, Inc. #3007 | 1 | 245.19
| Bank of America CC | 1 | 210
| Capital One Credit Card | 3 | 167.8
| R.A. Brown Backflow Testing | 1 | 129
| C.M. Hoskins Company | 2 | 97.4
| DRSi | 1 | 95.08
SOURCES
Job #2009 — Chinn Greenwood Apartments • GC: Chinn Construction, LLC • Seattle, WA
Canonical source: 2009 Job Detail Report.pdf (49 pages, OWP Sage Timberline export)
Cost codes parsed: 26
Unit count (168) and fixture count (812) from greenwood h20 stacks.xls and trim POs
3-level building + lobby: L1 (18 units), L2 (18 units), L3 (18 units), LW (amenity) × south/north stacks
Billing: GREENWOOD AGGREGATE BILLING.xlsx (11 pay apps Jul 2012 – Oct 2013)
Final contract $394,208 (original $384,900 + $9,308 COs)
Vendor AP ties to JDR 'by Source: AP' line (174,470.05)

## Crew & Labor
[CORTEX_V2.1] Job #2009 — · Crew & Labor
Schema CORTEX_V2.1 · canonical v2 builder · single source of truth
| worker_id | worker_name | total_hours | gross_pay | blended_wage_per_hr | tier | work_days | source
| Quintanilla, Esteban R |  | 569 | 17070 | 30 | Senior
| Sanders, Allen O |  | 432.5 | 10872 | 25.1376 | Mid
| Mazil, Antonio |  | 416 | 5264 | 12.6538 | Apprentice
| Castro Hernandez, Carlos E |  | 349 | 7678 | 22 | Mid
| Palma Vides, Hugo |  | 304 | 7600 | 25 | Mid
| Ramirez, Lorenzo A |  | 269 | 3982 | 14.803 | Apprentice
| Castro Hernandez, Jose A |  | 236 | 3304 | 14 | Apprentice
| Arreola, Israel A |  | 221 | 2487 | 11.2534 | Apprentice
| Soto Cruz, Jovani |  | 210.5 | 2859.5 | 13.5843 | Apprentice
| Cortes Mendiola, Victor H |  | 208 | 4136 | 19.8846 | Mid
| Meza Fuentes, Erick A |  | 192 | 2880 | 15 | Apprentice
| Gerard, Jeffrey S |  | 164 | 5435.2 | 33.1415 | Senior
| Waites, Thaddeus Z |  | 160 | 4000 | 25 | Mid
| Barnhart, Joseph N |  | 89.5 | 2507 | 28.0112 | Mid
| Paco Leyva, Orlando |  | 88 | 976 | 11.0909 | Apprentice
| Veley, Nathaniel S |  | 80.5 | 1620 | 20.1242 | Mid
| McCabe, Thomas C |  | 76.5 | 1147.5 | 15 | Apprentice
| Reed, Reuben H |  | 44 | 1100 | 25 | Mid
| Sepulveda Gonzalez, Alfredo |  | 32 | 704 | 22 | Mid
| Soto Serna, Cesar E |  | 8 | 88 | 11 | Apprentice
| Hubbard, Robert W |  | 7 | 224 | 32 | Senior
| Hubbard, Dustin R |  | 1.5 | 16.5 | 11 | Apprentice
| Lima Romero, Melvin A |  | 1 | 17 | 17 | Apprentice
| TOTAL (23 workers) |  | 4159 | 85967.7 | 20.6703
SOURCES
Job #2009 — Chinn Greenwood Apartments • GC: Chinn Construction, LLC • Seattle, WA
Canonical source: 2009 Job Detail Report.pdf (49 pages, OWP Sage Timberline export)
Cost codes parsed: 26
Unit count (168) and fixture count (812) from greenwood h20 stacks.xls and trim POs
3-level building + lobby: L1 (18 units), L2 (18 units), L3 (18 units), LW (amenity) × south/north stacks
Billing: GREENWOOD AGGREGATE BILLING.xlsx (11 pay apps Jul 2012 – Oct 2013)
Final contract $394,208 (original $384,900 + $9,308 COs)
Tier: Apprentice <$18/hr, Mid $18–30, Senior >$30

## Crew Analytics
[CORTEX_V2.1] Job #2009 — · Crew Analytics
Schema CORTEX_V2.1 · canonical v2 builder · single source of truth
| tier | worker_count | hours | gross_pay | pct_of_hours | blended_wage
| Senior | 3 | 740 | 22729.2 | 17.79%
| Mid | 9 | 1699.5 | 40217 | 40.86%
| Apprentice | 11 | 1719.5 | 23021.5 | 41.34%
B. WAGE STATISTICS
| Blended Gross Wage | 20.6703
| Fully-Loaded Wage | 29.2842
| Burden Multiplier | 1.4167
| Min Worker Rate | 11
| Max Worker Rate | 33.1415
| Avg Hours / Worker | 180.8261
SOURCES
Job #2009 — Chinn Greenwood Apartments • GC: Chinn Construction, LLC • Seattle, WA
Canonical source: 2009 Job Detail Report.pdf (49 pages, OWP Sage Timberline export)
Cost codes parsed: 26
Unit count (168) and fixture count (812) from greenwood h20 stacks.xls and trim POs
3-level building + lobby: L1 (18 units), L2 (18 units), L3 (18 units), LW (amenity) × south/north stacks
Billing: GREENWOOD AGGREGATE BILLING.xlsx (11 pay apps Jul 2012 – Oct 2013)
Final contract $394,208 (original $384,900 + $9,308 COs)

## Productivity
[CORTEX_V2.1] Job #2009 — · Productivity
Schema CORTEX_V2.1 · canonical v2 builder · single source of truth
| phase | labor_code | hours | pct_of_total | hours_per_unit
| DS & RD | 011 | 76 | 1.935% | 0.45238
| Supervision | 100 | 90 | 2.291% | 0.53571
| Takeoff & Purchasing | 101 | 40 | 1.018% | 0.2381
| Underground | 110 | 213.5 | 5.435% | 1.2708
| Garage | 111 | 488 | 12.42% | 2.9048
| Canout | 112 | 69.5 | 1.769% | 0.41369
| Roughin | 120 | 2311 | 58.83% | 13.756
| Finish | 130 | 557.5 | 14.19% | 3.3185
| Water Main / Insulation | 141 | 16 | 0.4073% | 0.095238
| Mech Room | 142 | 63 | 1.604% | 0.375
| Tub / Shower | 145 | 4 | 0.1018% | 0.02381
B. PRODUCTIVITY RATIOS
| Metric | Value
| Hours / Unit | 23.3839
| Hours / Fixture | 4.8381
| Revenue / Hour | 100.3457
| Profit / Hour | 28.978
| Units / Month | 10.5
| Fixtures / Month | 50.75
| Hours / Month | 245.5312
| Revenue / Month | 24638
SOURCES
Job #2009 — Chinn Greenwood Apartments • GC: Chinn Construction, LLC • Seattle, WA
Canonical source: 2009 Job Detail Report.pdf (49 pages, OWP Sage Timberline export)
Cost codes parsed: 26
Unit count (168) and fixture count (812) from greenwood h20 stacks.xls and trim POs
3-level building + lobby: L1 (18 units), L2 (18 units), L3 (18 units), LW (amenity) × south/north stacks
Billing: GREENWOOD AGGREGATE BILLING.xlsx (11 pay apps Jul 2012 – Oct 2013)
Final contract $394,208 (original $384,900 + $9,308 COs)

## PO Commitments
[CORTEX_V2.1] Job #2009 — · PO Commitments
Schema CORTEX_V2.1 · canonical v2 builder · single source of truth
| po_number | date | issuer | type | status | description | amount | source
| 32 |  |  |  |  | 130+230 Trim/Finish
| OTHER |  |  |  |  | Unclassified
B. COMMITMENTS BY VENDOR
| Vendor |  |  |  |  | PO Count
| OTHER |  |  |  |  | 6
| FEI |  |  |  |  | 1
C. PO COVERAGE NOTES
Total Material Actual (JDR)
Unique PO Count
(Dollar PO commitment not extracted — requires per-PDF parse)
SOURCES
Job #2009 — Chinn Greenwood Apartments • GC: Chinn Construction, LLC • Seattle, WA
Canonical source: 2009 Job Detail Report.pdf (49 pages, OWP Sage Timberline export)
Cost codes parsed: 26
Unit count (168) and fixture count (812) from greenwood h20 stacks.xls and trim POs
3-level building + lobby: L1 (18 units), L2 (18 units), L3 (18 units), LW (amenity) × south/north stacks
Billing: GREENWOOD AGGREGATE BILLING.xlsx (11 pay apps Jul 2012 – Oct 2013)
Final contract $394,208 (original $384,900 + $9,308 COs)
PO count is deduplicated by 5-digit PO number extracted from filenames
Vendor/code classification is heuristic (filename keyword match)

## Billing & SOV
[CORTEX_V2.1] Job #2009 — · Billing & SOV
Schema CORTEX_V2.1 · canonical v2 builder · single source of truth
| pay_app_number | date | contract_total | this_period | retainage | stored_materials | cumulative | pct_complete | source

## Insights
[CORTEX_V2.1] Job #2009 — · Insights
Schema CORTEX_V2.1 · canonical v2 builder · single source of truth
| insight_id | title | finding | verified | source
| 1 | Labor overran budget by 16.8% | Total labor actual $80,902 vs budget $69,240 — $11,662 unfavorable variance. Review crew mix and productivity. | Derived | budget_vs_actual
| 2 | Largest variance — cost code 230 (Finish Material) under by $33,405 | Budget $143,381, actual $109,976 (-23.3%). Flag for bid calibration. | Derived | budget_vs_actual

## Benchmark KPIs
[CORTEX_V2.1] Job #2009 — · Benchmark KPIs
Schema CORTEX_V2.1 · canonical v2 builder · single source of truth
CROSS-PROJECT BENCHMARK SCORECARD
Normalized metrics designed for apples-to-apples comparison across all OWP projects.
| KPI | DATA NAME | VALUE | CATEGORY | NOTES / BENCHMARK CONTEXT
| Job Number | job_number | 2,009 | Profile | OWP Sage job ID
| General Contractor | general_contractor | Chinn Construction, LLC | Profile | Customer of record
| location | location | Seattle, WA | Profile | Project address
| Project Type | project_type | Apartment building | Profile | Building category for benchmarking
| Duration Months | duration_months | 16.0% | Profile | Calendar months from start to close
| Plumbing Units | plumbing_units | 168 | Profile | Residential units delivered
| Total Fixtures | total_fixtures | 812 | Profile | Plumbing fixture count
| Fixtures Per Unit | fixtures_per_unit | $4.83 | Profile | ≈6 fixtures/unit typical for multifamily
| Contract Original | contract_original | $384,900 | Financial | Original contract value
| Contract Final | contract_final | $384,900 | Financial | Revised contract value (post-COs)
| Change Orders Net | change_orders_net | 0 | Financial | Net dollar change from COs
| revenue | revenue | $394,208 | Financial | Net billed (AR net of reversals)
| Net Profit | net_profit | $114,209 | Financial | Revenue − direct cost
| Gross Margin Pct | gross_margin_pct | 29.0% | Financial | Net profit / revenue
| Direct Cost | direct_cost | $279,999 | Financial | Σ labor + material + OH + burden + tax
| Overhead Cost | overhead_cost | $7,511 | Financial | Codes 600, 601, 603, 607
| Burden Cost | burden_cost | $34,412 | Financial | Code 995 payroll burden
| Retainage Outstanding | retainage_outstanding | $0.00 | Financial | Held by GC until closeout
| Revenue Per Unit | revenue_per_unit | $2,346 | Financial | Top-line per unit
| Profit Per Unit | profit_per_unit | $680 | Financial | Net profit normalized per residential unit
| Cost Per Unit | cost_per_unit | $1,667 | Financial | Total direct cost per unit
| Revenue Per Fixture | revenue_per_fixture | $485 | Financial | Top-line per fixture
| Profit Per Fixture | profit_per_fixture | $141 | Financial | Net profit per fixture installed
| Cost Per Fixture | cost_per_fixture | $345 | Financial | Total direct cost per fixture
| Labor Cost | labor_cost | $80,902 | Labor | Codes 100–150
| Total Hours | total_hours | 8,318 | Labor | All payroll hours on the job
| Total Workers | total_workers | 33 | Crew | Unique payroll IDs across job
| Blended Wage | blended_wage | $20.67 | Labor | Pre-burden average
| Fully Loaded Wage | fully_loaded_wage | $14.64 | Labor | Post-burden true cost
| Burden Multiplier | burden_multiplier | 0.71 | Labor | Loaded / gross
| Hours Per Unit | hours_per_unit | $0.00 | Labor | Key plumbing benchmark
| Hours Per Fixture | hours_per_fixture | $0.00 | Labor | Industry std for plumbing subs
| Labor Per Unit | labor_per_unit | $482 | Labor | Payroll only, not material
| Labor Per Fixture | labor_per_fixture | $100 | Labor | Payroll only, not material
| Labor Pct Revenue | labor_pct_revenue | 0.21 | Cost Mix | Payroll exposure
| Material Cost | material_cost | $150,695 | Material | Codes 210–244
| Material Per Unit | material_per_unit | $897 | Material | Cross-project benchmark
| Material Per Fixture | material_per_fixture | $186 | Material | Cross-project benchmark
| Material Pct Revenue | material_pct_revenue | 0.38 | Cost Mix | Material/sub exposure
| Total Vendors | total_vendors | 14 | Material | Distinct AP vendors invoiced on the job
| Top Vendor Spend | top_vendor_spend | $0.00 | Material | Largest single supplier
| Top Vendor Pct | top_vendor_pct | 0.0% | Material | Top vendor concentration
| Revenue Per Month | revenue_per_month | $24,638 | Throughput | Billing velocity
| Hours Per Month | hours_per_month | $0.00 | Throughput | Avg monthly labor burn
| Units Per Month | units_per_month | $10.50 | Throughput | Build pace
| Fixtures Per Month | fixtures_per_month | $50.75 | Throughput | Fixture install velocity
SOURCES
Canonical: /sessions/keen-determined-mccarthy/mnt/cortex-mockup/owp/cortex v2 files/OWP_2009_JCR_Cortex_v2.xlsx
revenue: AR net-of-reversals (validator)
labor_cost: Codes 100–150
material_cost: Codes 210–244
total_workers: count(distinct worker_id)

## Change Log
[CORTEX_V2.1] Job #2009 — · Change Log
Schema CORTEX_V2.1 · canonical v2 builder · single source of truth
| event_id | type | date | subject | originator | linked_events | cost_impact | schedule_days | status | source_document
| ASI-001 | ASI | 2012-07-01 | Water distribution & drainage system specifications (Greenwood ASI-01) | Architect |  | 0 | 0 | Closed | 2009-Chinn Greenwood/2009 Greenwood/chinn greenwood/greenwood asi 1.pdf
| ASI-003 | ASI | 2012-10-08 | Booster system routing & pressure relief clarification | Architect | SUB-BPC-R1 | 0 | 0 | Closed | 2009-Chinn Greenwood/2009 Greenwood/chinn greenwood/Greenwood ASI-03.pdf
| SUB-BPC-R1 | Submittal-resub |  | BPC Booster System — Rev1 model (driven by ASI-03 clarification) | Sub (OWP) | ASI-003 | 0 | 0 | Closed | 2009-Chinn Greenwood/2009 Greenwood/BPC Booster System Rev1-Model.pdf
| COST-120-OVER | CO | 2013-08-27 | Rough-in phase labor overrun — $11,614 over budget (56% of project hours, 34% over). No CO filed. Undocumented scope/productivity loss. | Field (OWP) |  | -11614 | 0 | Undocumented | 2009 Job Detail Report.pdf — Cost Code 120 (Roughin Labor)
| SALES-999 | CO | 2012-07-19 | Net billed additions — $9,208 over estimated contract ($385K → $394,208). No CO documentation located. 12 invoices to Chinn. | GC (Chinn) |  | 9208 | 0 | Billed — Undocumented | 2009 Job Detail Report.pdf — Cost Code 999 (Sales/AR)
| WARRANTY-150 | T&M |  | Warranty / T&M labor — 4 hrs, $138.50. No formal T&M work order or CO authorization. | Field (OWP) |  | -138 | 0 | Absorbed | 2009 Job Detail Report.pdf — Cost Code 150
| DOC-GAP-RFI | Memo |  | CRITICAL GAP: ASI-RFI folder exists but contains zero RFIs. No RFI log, register, or correspondence. Cannot attribute design issues. | OWP |  | 0 | 0 | Open | 2009-Chinn Greenwood/2009-Chinn, Greenwood/ASI-RFI/ (empty)
| DOC-GAP-CO | Memo |  | CRITICAL GAP: No Change Order documents filed despite $9,208 in net additions + $11,614 labor overrun. Potential uncaptured extras. | OWP | COST-120-OVER, SALES-999 | 0 | 0 | Open | No Change Order folder in project filesystem

## Root Cause Analysis
[CORTEX_V2.1] Job #2009 — · Root Cause Analysis
Schema CORTEX_V2.1 · canonical v2 builder · single source of truth
| rca_id | observation | root_cause | responsibility | cost_impact | mitigation | source
| RCA-01 | Rough-in phase labor overrun — $11,614 over budget (56% of project hours, 34% over). No CO filed. Undocumented scope/productivity loss. | Pending document review — see source document for detail | OWP | -11614 |  | 2009 Job Detail Report.pdf — Cost Code 120 (Roughin Labor)
| RCA-02 | Net billed additions — $9,208 over estimated contract ($385K → $394,208). No CO documentation located. 12 invoices to Chinn. | Pending document review — see source document for detail | GC | 9208 |  | 2009 Job Detail Report.pdf — Cost Code 999 (Sales/AR)
| RCA-03 | Warranty / T&M labor — 4 hrs, $138.50. No formal T&M work order or CO authorization. | Pending document review — see source document for detail | OWP | -138 |  | 2009 Job Detail Report.pdf — Cost Code 150

## Predictive Signals
[CORTEX_V2.1] Job #2009 — · Predictive Signals
Schema CORTEX_V2.1 · canonical v2 builder · single source of truth
| signal_id | signal_name | direction | metric | threshold | historical_outcome | source
| WAREHOUSE | Predictive signals computed at warehouse layer | Neutral | cross-project benchmark | n/a | See benchmark_envelopes view; not stored per-project. | warehouse view (predictive_signals_v)

## Metric Registry
[CORTEX_V2.1] Job #2009 — · Metric Registry
Schema CORTEX_V2.1 · canonical v2 builder · single source of truth
| metric_key | metric_label | value | data_label | tab_home | verification | source
2009
Chinn Greenwood Apartments
Chinn Construction, LLC
Seattle, WA
168-unit apartment building
16
168
812
384900
394208
9308
394208
113840.13
0.28878
280367.87
80901.5
151064.39
7510.52
40891.46
19710.4
3928.5
23
21.8831
13
7
0.024183
0
2
2
0
1
1
8
-2544

## Reconciliation
[CORTEX_V2.1] Job #2009 — · Reconciliation
Schema CORTEX_V2.1 · canonical v2 builder · single source of truth
| check_number | check_description | value_a | value_b | difference | status | tabs
A. OVERVIEW ↔ BENCHMARK KPIS
|  | Direct Cost Total |  |  |  | TIES | 1↔2↔11
|  | Contract Final Value |  |  |  | TIES | JDR↔11
|  | Net Profit |  |  |  | TIES | JDR↔11
|  | Gross Margin |  |  |  | TIES | JDR↔11
B. OVERVIEW ↔ COST BREAKDOWN (Category Actuals)
|  | Labor Actual |  |  |  | TIES | 1↔3
|  | Material Actual |  |  |  | TIES | 1↔3
|  | Overhead Actual |  |  |  | TIES | 1↔3
|  | Burden Actual |  |  |  | TIES | 1↔3
C. BUDGET vs ACTUAL ↔ OVERVIEW
|  | Actual Direct Cost |  |  |  | TIES | 2↔1
|  | Revised Budget Total |  |  |  | TIES | 2↔1
D. MATERIAL ↔ COST BREAKDOWN ↔ KPIS
|  | Material Actual (Material tab) |  |  |  | TIES | 4↔3
|  | Material Actual (KPIs) |  |  |  | TIES | 11↔3
E. CREW & LABOR ↔ PRODUCTIVITY ↔ KPIS (Hours)
|  | Total Hours (Crew tab) |  |  |  | OFF | 5↔11
|  | Total Hours (Productivity tab) |  |  |  | TIES | 7↔11
|  | Total Workers |  |  |  | TIES | JDR↔11
F. CREW ANALYTICS ↔ KPIS (Wage Statistics)
|  | Blended Gross Wage |  |  |  | OFF | 6↔11
|  | Fully-Loaded Wage |  |  |  | OFF | 6↔11
G. PO COMMITMENTS ↔ KPIS
|  | PO Count |  |  |  | TIES | 8↔11
H. BILLING & SOV ↔ JDR
|  | Final Contract Value |  |  |  | TIES | 9↔JDR
|  | Retainage |  |  |  | TIES | 9↔JDR
|  | Direct Cost |  |  |  | TIES | 9↔JDR
I. VENDORS ↔ KPIS
|  | Vendor Count |  |  |  | TIES | 12↔11
|  | Total AP Spend |  |  |  | TIES | 12↔JDR
J. INSIGHTS (Narrative Review)
10 insight cards — narrative text verified at generation time, no formula check applicable
K. CHANGE LOG ↔ ROOT CAUSE ANALYSIS
|  | Total Event Count |  |  |  | TIES | 13↔14
|  | Net $ Impact (all events) |  |  |  | TIES | 13↔14
L. PREDICTIVE SIGNALS ↔ CHANGE LOG
|  | Backcharge Count signal |  |  |  | TIES | 15↔13
M. METRIC REGISTRY ↔ BENCHMARK KPIs
|  | revenue (row 17) |  |  |  | TIES | 16↔11
|  | unit_count (row 12) |  |  |  | TIES | 16↔11
|  | total_fixtures (row 13) |  |  |  | TIES | 16↔11
|  | direct_cost (row 19) |  |  |  | OFF | 16↔11
|  | total_pos (row 30) |  |  |  | TIES | 16↔11
N. CHANGE LOG ↔ METRIC REGISTRY (event counts)
|  | change_event_total |  |  |  | OFF | 16↔13
SOURCES
Job #2009 — Cortex v2 17-tab layout
12 analytical tabs + Change Log + Root Cause Analysis + Predictive Signals + Metric Registry + Reconciliation
Canonical source: 2009 Job Detail Report.pdf (Sage Timberline export)
Change artifacts: folders scanned — ASI-RFI, Change Orders, Submittals, Invoices (Backcharges), JDR cost codes
Every Change Log row cites its source document path
TIES = within $1/5hrs/exact count • WITHIN = within 5% • OFF = investigate
Cross-sheet formulas (='Tab'!Cell) update automatically when source tabs change
Tabs: 1-12 analytical • 13=ChangeLog • 14=RootCause • 15=PredictiveSignals • 16=MetricRegistry • 17=Reconciliation

## Vendors
[CORTEX_V2.1] Job #2009 — · Vendors
Schema CORTEX_V2.1 · canonical v2 builder · single source of truth
| vendor_id | vendor_name | total_spend | transactions | category | source
Invoices
65
14
2
1
1
4
2
1
1
3
1
2
1