## Overview
[CORTEX_V2.1] Job #2010 — · Overview
Schema CORTEX_V2.1 · canonical v2 builder · single source of truth
| OVERVIEW |  | SOURCE
IDENTITY
| Project Job Number | 2010
| Project Name: | Chinn Old Town Mixed Use
CONTRACT & PARTIES
| General Contractor | Chinn Construction, LLC
JOB SITE
| Jobsite Location | Seattle, WA
| Plumbing Units | 165 | Kitchen Sinks
SCHEDULE
| Project Duration | Sep 2012 – Sep 2014 (~24 months)
SCOPE & DESIGN
| Total Fixtures | 803 | Showers
| Fixtures / Unit | 4.87 | Auto Washers
| Stacks | 30 | Cost Codes
| CONTRACT VALUE |  | NET PROFIT |  | DIRECT COST |  | LABOR HOURS
| $1,469,800 |  | $801,609 |  | $584,810 |  | 19,847
| Original $1,469,800 |  | 57.8% margin |  | 42.2% of revenue |  | 32 workers
COST BREAKDOWN
| Category | Budget | Actual | Variance | % Budget | % of Cost
| Labor | 303565 | 196271.13 | 107293.87 | 64.66% | 33.56%
| Material | 493180 | 281473.91 | 211706.09 | 57.07% | 48.13%
| Overhead | 8000 | 3650.67 | 4349.33 | 45.63% | 0.6242%
| Burden | 161672.55 | 103414.01 | 58258.54 | 63.97% | 17.68%
| TOTAL | 966417.55 | 584809.72 | 381607.83 | 60.51% | 100%
PROJECT PROFILE
| Plumbing Units | 165 |  | Total Fixtures | 803 |  | Fixtures / Unit | 4.87
| Floors | 30 |  | Duration | Sep 2012 – Sep 2014 (~24 months)

## Budget vs Actual
[CORTEX_V2.1] Job #2010 — · Budget vs Actual
Schema CORTEX_V2.1 · canonical v2 builder · single source of truth
| cost_code | description | original_budget | revised_budget | actual | variance | pct_used | hours | source
LABOR
| 011 | DS & RD Labor | 7590 | 7590 | 2137 | 5453 | 28.16%
| 100 | Supervision | 10430 | 10430 | 4944 | 5486 | 47.4%
| 101 | Takeoff & Purchase Labor | 7450 | 7450 | 4286 | 3164 | 57.53%
| 110 | Underground Labor | 3820 | 3820 | 959 | 2861 | 25.1%
| 111 | Garage Labor | 39100 | 39100 | 28821.5 | 10278.5 | 73.71%
| 112 | Canout Labor | 6650 | 6650 | 2982.25 | 3667.75 | 44.85%
| 120 | Roughin Labor | 204925 | 159525 | 114688.38 | 44836.62 | 71.89%
| 130 | Finish Labor | 31000 | 31500 | 29825 | 1675 | 94.68%
| 140 | Gas Labor | 3600 | 3600 | 1712 | 1888 | 47.56%
| 141 | Water Main/Insulation Lab | 14900 | 33900 | 3672 | 30228 | 10.83%
| 142 | Mech Room Labor | 0 | 0 | 1871 | -1871 | 0%
| 145 | Tub/Shower Labor | 0 | 0 | 373 | -373 | 0%
MATERIAL
| 039 | DS & RD Material | 11500 | 11500 | 1188.86 | 10311.14 | 10.34%
| 210 | Underground Material | 3000 | 3000 | 1514.24 | 1485.76 | 50.47%
| 211 | Garage Material | 63370 | 63370 | 11302.9 | 52067.1 | 17.84%
| 212 | Canout Material | 7980 | 7980 | 5720.08 | 2259.92 | 71.68%
| 220 | Roughin Material | 204925 | 130025 | 66457.52 | 63567.48 | 51.11%
| 230 | Finish Material | 261700 | 251305 | 173652.72 | 77652.28 | 69.1%
| 240 | Gas Material | 3600 | 3600 | 1080.05 | 2519.95 | 30%
| 241 | Water Main/Insulation Mat | 14900 | 33900 | 20000.49 | 13899.51 | 59%
| 242 | Mech Room Material | 0 | 0 | 1098.46 | -1098.46 | 0%
| 245 | Tub/Shower Material | 0 | 0 | 647.45 | -647.45 | 0%
OVERHEAD
| 600 | Subcontractor | 1000 | 1000 | 1212 | -212 | 1.212%
| 601 | Engineering/Plans | 4000 | 4000 | 2404.21 | 1595.79 | 60.11%
| 603 | Permits & Licenses | 3000 | 3000 | 34.46 | 2965.54 | 1.149%
BURDEN
| 995 | Payroll Burden | 145220.27 | 137421.67 | 87883.44 | 49538.23 | 63.95%
| 998 | Payroll Taxes | 26232.23 | 24250.88 | 15530.57 | 8720.31 | 64.04%
SOURCES
Job #2010 — Chinn Old Town Mixed Use • GC: Chinn Construction, LLC • Seattle, WA
Canonical source: 2010 Job Detail Report.pdf (123 pages, OWP Sage Timberline export)
Cost codes parsed: 28
Unit count (165) and fixture count (803) confirmed from existing project data
Mixed-use: 165 plumbing units, 175 lavatories (suggests 10 powder-room units) + 15 shower-only units
Billing: OLD TOWN AGGREGATE BILLING.xlsx (18 pay apps Sep 2012 – Sep 2014)
Final contract $1,386,419 (original $1,469,800 + $-83,381 COs)
| TOTAL |  | 1079892.5 | 977917.55 | 585998.58 | 391918.97 |  | 0

## Cost Breakdown
[CORTEX_V2.1] Job #2010 — · Cost Breakdown
Schema CORTEX_V2.1 · canonical v2 builder · single source of truth
| category | cost_codes | actual | pct_of_direct_cost | pct_of_revenue | per_unit | source
| Labor | 12 | 303565 | 64.66% |  | 1189.522
| Material | 10 | 504680 | 56.01% |  | 1713.1077
| Overhead | 3 | 8000 | 45.63% |  | 22.1253
| Burden | 2 | 161672.55 | 63.97% |  | 626.7516
B. LARGEST OVERRUNS (Actual > Revised Budget)
| Code | Description
| 142 | Mech Room Labor | 0 | 0%
| 242 | Mech Room Material | 0 | 0%
| 245 | Tub/Shower Material | 0 | 0%
| 145 | Tub/Shower Labor | 0 | 0%
| 600 | Subcontractor | 1000 | 21.2%
C. LARGEST SAVINGS (Actual < Revised Budget)
| Code | Description
| 230 | Finish Material | 251305 | 30.9%
| 220 | Roughin Material | 130025 | 48.89%
| 211 | Garage Material | 63370 | 82.16%
| 995 | Payroll Burden | 137421.67 | 36.05%
| 120 | Roughin Labor | 159525 | 28.11%
| 141 | Water Main/Insulation Lab | 33900 | 89.17%
| 241 | Water Main/Insulation Mat | 33900 | 41%
| 039 | DS & RD Material | 11500 | 89.66%
| 111 | Garage Labor | 39100 | 26.29%
| 998 | Payroll Taxes | 24250.88 | 35.96%
SOURCES
Job #2010 — Chinn Old Town Mixed Use • GC: Chinn Construction, LLC • Seattle, WA
Canonical source: 2010 Job Detail Report.pdf (123 pages, OWP Sage Timberline export)
Cost codes parsed: 28
Unit count (165) and fixture count (803) confirmed from existing project data
Mixed-use: 165 plumbing units, 175 lavatories (suggests 10 powder-room units) + 15 shower-only units
Billing: OLD TOWN AGGREGATE BILLING.xlsx (18 pay apps Sep 2012 – Sep 2014)
Final contract $1,386,419 (original $1,469,800 + $-83,381 COs)
| TOTAL |  | 1863215.1 |  |  | 3551.5065

## Material
[CORTEX_V2.1] Job #2010 — · Material
Schema CORTEX_V2.1 · canonical v2 builder · single source of truth
| vendor_id | vendor_name | total_spend | transactions | category | source
| 039 | DS & RD Material | 11500 |  | 0.0042059
| 210 | Underground Material | 3000 |  | 0.0053571
| 211 | Garage Material | 63370 |  | 0.039987
| 212 | Canout Material | 7980 |  | 0.020236
| 220 | Roughin Material | 130025 |  | 0.23511
| 230 | Finish Material | 251305 |  | 0.61435
| 240 | Gas Material | 3600 |  | 0.003821
| 241 | Water Main/Insulation Mat | 33900 |  | 0.070757
| 242 | Mech Room Material | 0 |  | 0.0038861
| 245 | Tub/Shower Material | 0 |  | 0.0022905
B. VENDORS BY SPEND (AP)
| Vendor | # Invoices
| Rosen Supply Company, Inc. | 73 | 215859.94
| Ferguson Enterprises, Inc. | 58 | 84342.57
| Bank of America CC | 3 | 30892.62
| Franklin Engineering | 4 | 10463
| Keller Supply Company | 7 | 10106.67
| Quality Concrete Products, Inc. | 2 | 2414
| United Rentals, Inc. | 6 | 2404.21
| Ferguson Enterprises, Inc. #3007 | 7 | 2271.7
| Rosen Supply Kirkland | 3 | 1831.58
| Duraseal, Inc. | 1 | 950
| DRSi | 2 | 265.36
| R.A. Brown Backflow Testing | 1 | 212
| Manor Hardware & Construction Supply | 1 | 197.5
| Consolidated Supply Co. | 1 | 168.54
| Pacific Plumbing Supply Co., LLC | 2 | 121.4
| Fastenal Company | 2 | 96.67
| Kele, Inc | 1 | 69.69
| C.M. Hoskins Company | 1 | 54.4
SOURCES
Job #2010 — Chinn Old Town Mixed Use • GC: Chinn Construction, LLC • Seattle, WA
Canonical source: 2010 Job Detail Report.pdf (123 pages, OWP Sage Timberline export)
Cost codes parsed: 28
Unit count (165) and fixture count (803) confirmed from existing project data
Mixed-use: 165 plumbing units, 175 lavatories (suggests 10 powder-room units) + 15 shower-only units
Billing: OLD TOWN AGGREGATE BILLING.xlsx (18 pay apps Sep 2012 – Sep 2014)
Final contract $1,386,419 (original $1,469,800 + $-83,381 COs)
Vendor AP ties to JDR 'by Source: AP' line (362,721.85)

## Crew & Labor
[CORTEX_V2.1] Job #2010 — · Crew & Labor
Schema CORTEX_V2.1 · canonical v2 builder · single source of truth
| worker_id | worker_name | total_hours | gross_pay | blended_wage_per_hr | tier | work_days | source
| Anderson, Richard P |  | 1681 | 42050 | 25.0149 | Mid
| Barnhart, Joseph N |  | 1588 | 46498.5 | 29.2812 | Mid
| Hayton, Evan R |  | 1465 | 19207 | 13.1106 | Apprentice
| Garcia, Jordan X |  | 1192 | 15781 | 13.2391 | Apprentice
| Wilson, Garret A |  | 833.5 | 11129.5 | 13.3527 | Apprentice
| Kinssies, Jr, John E |  | 727.5 | 9796.5 | 13.466 | Apprentice
| Waites, Thaddeus Z |  | 680 | 18200 | 26.7647 | Mid
| Mayfield, Elijah S |  | 366 | 4758 | 13 | Apprentice
| Soto Serna, Cesar E |  | 366 | 4114 | 11.2404 | Apprentice
| Gerard, Jeffrey S |  | 314.5 | 10992.5 | 34.9523 | Senior
| Holmes, Anthony R |  | 301 | 3660 | 12.1595 | Apprentice
| Nabbefeld, Maxwell B |  | 112 | 1344 | 12 | Apprentice
| Leone, Jared S |  | 91 | 1092 | 12 | Apprentice
| Meza Fuentes, Erick A |  | 59.5 | 892.5 | 15 | Apprentice
| Salazar, Hajdar L |  | 47 | 525 | 11.1702 | Apprentice
| Pennington, Patrick S |  | 40 | 480 | 12 | Apprentice
| McCabe, Thomas C |  | 24 | 414 | 17.25 | Apprentice
| Hubbard, Robert W |  | 11 | 358 | 32.5455 | Senior
| Lima Romero, Melvin A |  | 9 | 153 | 17 | Apprentice
| Sanders, Allen O |  | 7 | 203 | 29 | Mid
| Paco Leyva, Orlando |  | 6.5 | 87.75 | 13.5 | Apprentice
| Arreola, Israel A |  | 2 | 24 | 12 | Apprentice
| TOTAL (22 workers) |  | 9923.5 | 191760.25 | 19.3239
SOURCES
Job #2010 — Chinn Old Town Mixed Use • GC: Chinn Construction, LLC • Seattle, WA
Canonical source: 2010 Job Detail Report.pdf (123 pages, OWP Sage Timberline export)
Cost codes parsed: 28
Unit count (165) and fixture count (803) confirmed from existing project data
Mixed-use: 165 plumbing units, 175 lavatories (suggests 10 powder-room units) + 15 shower-only units
Billing: OLD TOWN AGGREGATE BILLING.xlsx (18 pay apps Sep 2012 – Sep 2014)
Final contract $1,386,419 (original $1,469,800 + $-83,381 COs)
Tier: Apprentice <$18/hr, Mid $18–30, Senior >$30

## Crew Analytics
[CORTEX_V2.1] Job #2010 — · Crew Analytics
Schema CORTEX_V2.1 · canonical v2 builder · single source of truth
| tier | worker_count | hours | gross_pay | pct_of_hours | blended_wage
| Senior | 2 | 325.5 | 11350.5 | 3.28%
| Mid | 4 | 3956 | 106951.5 | 39.86%
| Apprentice | 16 | 5642 | 73458.25 | 56.85%
B. WAGE STATISTICS
| Blended Gross Wage | 19.3239
| Fully-Loaded Wage | 30.1995
| Burden Multiplier | 1.5628
| Min Worker Rate | 11.1702
| Max Worker Rate | 34.9523
| Avg Hours / Worker | 451.0682
SOURCES
Job #2010 — Chinn Old Town Mixed Use • GC: Chinn Construction, LLC • Seattle, WA
Canonical source: 2010 Job Detail Report.pdf (123 pages, OWP Sage Timberline export)
Cost codes parsed: 28
Unit count (165) and fixture count (803) confirmed from existing project data
Mixed-use: 165 plumbing units, 175 lavatories (suggests 10 powder-room units) + 15 shower-only units
Billing: OLD TOWN AGGREGATE BILLING.xlsx (18 pay apps Sep 2012 – Sep 2014)
Final contract $1,386,419 (original $1,469,800 + $-83,381 COs)

## Productivity
[CORTEX_V2.1] Job #2010 — · Productivity
Schema CORTEX_V2.1 · canonical v2 builder · single source of truth
| phase | labor_code | hours | pct_of_total | hours_per_unit
| DS & RD | 011 | 90 | 0.9007% | 0.54545
| Supervision | 100 | 138 | 1.381% | 0.83636
| Takeoff & Purchasing | 101 | 124 | 1.241% | 0.75152
| Underground | 110 | 30 | 0.3002% | 0.18182
| Garage | 111 | 1345 | 13.46% | 8.1515
| Canout | 112 | 122.5 | 1.226% | 0.74242
| Roughin | 120 | 6202.25 | 62.07% | 37.5894
| Finish | 130 | 1569 | 15.7% | 9.5091
| Gas | 140 | 79 | 0.7906% | 0.47879
| Water Main / Insulation | 141 | 189.5 | 1.896% | 1.1485
| Mech Room | 142 | 89 | 0.8907% | 0.53939
| Tub / Shower | 145 | 14 | 0.1401% | 0.084848
B. PRODUCTIVITY RATIOS
| Metric | Value
| Hours / Unit | 60.5591
| Hours / Fixture | 12.4436
| Revenue / Hour | 138.7494
| Profit / Hour | 80.1041
| Units / Month | 6.875
| Fixtures / Month | 33.4583
| Hours / Month | 416.3438
| Revenue / Month | 57767.4583
SOURCES
Job #2010 — Chinn Old Town Mixed Use • GC: Chinn Construction, LLC • Seattle, WA
Canonical source: 2010 Job Detail Report.pdf (123 pages, OWP Sage Timberline export)
Cost codes parsed: 28
Unit count (165) and fixture count (803) confirmed from existing project data
Mixed-use: 165 plumbing units, 175 lavatories (suggests 10 powder-room units) + 15 shower-only units
Billing: OLD TOWN AGGREGATE BILLING.xlsx (18 pay apps Sep 2012 – Sep 2014)
Final contract $1,386,419 (original $1,469,800 + $-83,381 COs)

## PO Commitments
[CORTEX_V2.1] Job #2010 — · PO Commitments
Schema CORTEX_V2.1 · canonical v2 builder · single source of truth
| po_number | date | issuer | type | status | description | amount | source
| 30 |  |  |  |  | 110+210 Underground
| 31 |  |  |  |  | 120+220 Roughin
| 32 |  |  |  |  | 130+230 Trim/Finish
| 40 |  |  |  |  | 141+241 Water Main/Ins
| 41 |  |  |  |  | 140+240 Gas
| OTHER |  |  |  |  | Unclassified
B. COMMITMENTS BY VENDOR
| Vendor |  |  |  |  | PO Count
| OTHER |  |  |  |  | 60
| ROSEN |  |  |  |  | 8
| FEI |  |  |  |  | 3
| CONSOLIDATED |  |  |  |  | 1
| SIOUX CHIEF |  |  |  |  | 1
C. PO COVERAGE NOTES
Total Material Actual (JDR)
Unique PO Count
(Dollar PO commitment not extracted — requires per-PDF parse)
SOURCES
Job #2010 — Chinn Old Town Mixed Use • GC: Chinn Construction, LLC • Seattle, WA
Canonical source: 2010 Job Detail Report.pdf (123 pages, OWP Sage Timberline export)
Cost codes parsed: 28
Unit count (165) and fixture count (803) confirmed from existing project data
Mixed-use: 165 plumbing units, 175 lavatories (suggests 10 powder-room units) + 15 shower-only units
Billing: OLD TOWN AGGREGATE BILLING.xlsx (18 pay apps Sep 2012 – Sep 2014)
Final contract $1,386,419 (original $1,469,800 + $-83,381 COs)
PO count is deduplicated by 5-digit PO number extracted from filenames
Vendor/code classification is heuristic (filename keyword match)

## Billing & SOV
[CORTEX_V2.1] Job #2010 — · Billing & SOV
Schema CORTEX_V2.1 · canonical v2 builder · single source of truth
| pay_app_number | date | contract_total | this_period | retainage | stored_materials | cumulative | pct_complete | source

## Insights
[CORTEX_V2.1] Job #2010 — · Insights
Schema CORTEX_V2.1 · canonical v2 builder · single source of truth
| insight_id | title | finding | verified | source
| 1 | Labor came in 40.4% under budget | Total labor actual $196,271 vs budget $329,465 — $133,194 favorable variance. | Derived | budget_vs_actual
| 2 | Largest variance — cost code 230 (Finish Material) under by $77,652 | Budget $251,305, actual $173,653 (-30.9%). Flag for bid calibration. | Derived | budget_vs_actual

## Benchmark KPIs
[CORTEX_V2.1] Job #2010 — · Benchmark KPIs
Schema CORTEX_V2.1 · canonical v2 builder · single source of truth
CROSS-PROJECT BENCHMARK SCORECARD
Normalized metrics designed for apples-to-apples comparison across all OWP projects.
| KPI | DATA NAME | VALUE | CATEGORY | NOTES / BENCHMARK CONTEXT
| Job Number | job_number | 2,010 | Profile | OWP Sage job ID
| General Contractor | general_contractor | Chinn Construction, LLC | Profile | Customer of record
| location | location | Seattle, WA | Profile | Project address
| Project Type | project_type | Apartment building | Profile | Building category for benchmarking
| Duration Months | duration_months | 24.0% | Profile | Calendar months from start to close
| Plumbing Units | plumbing_units | 165 | Profile | Residential units delivered
| Total Fixtures | total_fixtures | 803 | Profile | Plumbing fixture count
| Fixtures Per Unit | fixtures_per_unit | $4.87 | Profile | ≈6 fixtures/unit typical for multifamily
| Contract Original | contract_original | $1,469,800 | Financial | Original contract value
| Contract Final | contract_final | $1,469,800 | Financial | Revised contract value (post-COs)
| Change Orders Net | change_orders_net | 0 | Financial | Net dollar change from COs
| revenue | revenue | $1,386,419 | Financial | Net billed (AR net of reversals)
| Net Profit | net_profit | $801,609 | Financial | Revenue − direct cost
| Gross Margin Pct | gross_margin_pct | 57.8% | Financial | Net profit / revenue
| Direct Cost | direct_cost | $584,810 | Financial | Σ labor + material + OH + burden + tax
| Overhead Cost | overhead_cost | $3,651 | Financial | Codes 600, 601, 603, 607
| Burden Cost | burden_cost | $87,883 | Financial | Code 995 payroll burden
| Retainage Outstanding | retainage_outstanding | $0.00 | Financial | Held by GC until closeout
| Revenue Per Unit | revenue_per_unit | $8,403 | Financial | Top-line per unit
| Profit Per Unit | profit_per_unit | $4,858 | Financial | Net profit normalized per residential unit
| Cost Per Unit | cost_per_unit | $3,544 | Financial | Total direct cost per unit
| Revenue Per Fixture | revenue_per_fixture | $1,727 | Financial | Top-line per fixture
| Profit Per Fixture | profit_per_fixture | $998 | Financial | Net profit per fixture installed
| Cost Per Fixture | cost_per_fixture | $728 | Financial | Total direct cost per fixture
| Labor Cost | labor_cost | $196,271 | Labor | Codes 100–150
| Total Hours | total_hours | 19,847 | Labor | All payroll hours on the job
| Total Workers | total_workers | 32 | Crew | Unique payroll IDs across job
| Blended Wage | blended_wage | $19.32 | Labor | Pre-burden average
| Fully Loaded Wage | fully_loaded_wage | $15.10 | Labor | Post-burden true cost
| Burden Multiplier | burden_multiplier | 0.78 | Labor | Loaded / gross
| Hours Per Unit | hours_per_unit | $0.00 | Labor | Key plumbing benchmark
| Hours Per Fixture | hours_per_fixture | $0.00 | Labor | Industry std for plumbing subs
| Labor Per Unit | labor_per_unit | $1,190 | Labor | Payroll only, not material
| Labor Per Fixture | labor_per_fixture | $244 | Labor | Payroll only, not material
| Labor Pct Revenue | labor_pct_revenue | 0.14 | Cost Mix | Payroll exposure
| Material Cost | material_cost | $281,474 | Material | Codes 210–244
| Material Per Unit | material_per_unit | $1,706 | Material | Cross-project benchmark
| Material Per Fixture | material_per_fixture | $351 | Material | Cross-project benchmark
| Material Pct Revenue | material_pct_revenue | 0.20 | Cost Mix | Material/sub exposure
| Total Vendors | total_vendors | 19 | Material | Distinct AP vendors invoiced on the job
| Top Vendor Spend | top_vendor_spend | $0.00 | Material | Largest single supplier
| Top Vendor Pct | top_vendor_pct | 0.0% | Material | Top vendor concentration
| Revenue Per Month | revenue_per_month | $57,767 | Throughput | Billing velocity
| Hours Per Month | hours_per_month | $0.00 | Throughput | Avg monthly labor burn
| Units Per Month | units_per_month | $6.88 | Throughput | Build pace
| Fixtures Per Month | fixtures_per_month | $33.46 | Throughput | Fixture install velocity
SOURCES
Canonical: /sessions/keen-determined-mccarthy/mnt/cortex-mockup/owp/cortex v2 files/OWP_2010_JCR_Cortex_v2.xlsx
revenue: AR net-of-reversals (validator)
labor_cost: Codes 100–150
material_cost: Codes 210–244
total_workers: count(distinct worker_id)

## Change Log
[CORTEX_V2.1] Job #2010 — · Change Log
Schema CORTEX_V2.1 · canonical v2 builder · single source of truth
| event_id | type | date | subject | originator | linked_events | cost_impact | schedule_days | status | source_document
| CO-003 | CO | 2013-12-12 | Change Order #3 — embedded in schedule of values | GC (WPM) |  | 0 | 0 | Active | 2010-Chinn, Old Town/Oldtown billing/Chinn Old Town schedule of values- 13 -12-12-13 co#3.xlsx
| CO-004 | CO | 2014-05-20 | Change Order #4 — embedded in schedule of values | GC (WPM) |  | 0 | 0 | Active | 2010-Chinn, Old Town/Oldtown billing/Chinn Old Town schedule of values- 17 -5-20-14 co#4.xlsx
| ASI-001 | ASI | 2012-05-31 | Landscape for construction drawings | Architect (Weber Thompson) |  | 0 | 0 | Closed | 2010-Chinn, Old Town/ASI-RFI/ASI No 1 Narrative.pdf
| ASI-002 | ASI | 2012-06-19 | Structural Drawings Revision 7 — transformer cable room, wall replacement 8→6, dimensions, column repositioning | Architect (Weber Thompson) |  | 0 | 0 | Closed | 2010-Chinn, Old Town/ASI-RFI/ASI No 2 Narratives.pdf
| ASI-006 | ASI |  | Architectural revisions — Level L011 | Architect (Weber Thompson) |  | 0 | 0 | Closed | 2010-Chinn, Old Town/ASI-RFI/old town RFI-ASI/ASI 6 Architectural Revisions Level L011.pdf
| ASI-008 | ASI |  | Courtyard & street level irrigation plan details | Landscape Architect |  | 0 | 0 | Closed | 2010-Chinn, Old Town/ASI-RFI/old town RFI-ASI/Old Town ASI#8.pdf
| ASI-023.R1 | ASI |  | ASI 23 Revision 1 — resubmission | Architect (Weber Thompson) |  | 0 | 0 | Closed | 2010-Chinn, Old Town/ASI-RFI/ASI No 23R1 Complete.pdf
| ASI-024 | ASI |  | ASI 24 — design clarification | Architect (Weber Thompson) |  | 0 | 0 | Closed | 2010-Chinn, Old Town/ASI-RFI/ASI No 24 Complete.pdf
| ASI-NARR | ASI |  | ID Revisions Narrative — design revisions summary | Architect (Weber Thompson) |  | 0 | 0 | Closed | 2010-Chinn, Old Town/ASI-RFI/Narrative for ID Revisions.pdf
| RFI-004 | RFI |  | PSE Transformer Relocation | GC (OTMU) |  | 0 | 0 | Closed | 2010-Chinn, Old Town/ASI-RFI/old town RFI-ASI/RFI 4 PSE Transformer Relocation_Response.pdf
| RFI-016 | RFI |  | Oil/water separator relocation | GC (OTMU) |  | 0 | 0 | Closed | 2010-Chinn, Old Town/ASI-RFI/old town RFI-ASI/Response - OTMU RFI #016 - oil water location relocation_.pdf
| RFI-026 | RFI |  | Vault room wall and footing details | GC (OTMU) |  | 0 | 0 | Closed | 2010-Chinn, Old Town/ASI-RFI/old town RFI-ASI/RFI 026 - Response - Vault room wall and footing details.pdf
| RFI-063 | RFI |  | Crane blockout pourback | GC (OTMU) |  | 0 | 0 | Closed | 2010-Chinn, Old Town/ASI-RFI/old town RFI-ASI/OTMU RFI #63 - crane blockout pourback_Response.pdf
| RFI-086 | RFI |  | Dog wash sleeve locations (plumbing coordination) | GC (OTMU) |  | 0 | 0 | Closed | 2010-Chinn, Old Town/ASI-RFI/old town RFI-ASI/RFI 086 Dog Wash Sleeve Locations_WT Response.pdf
| RFI-091 | RFI |  | New location for backflow protection assembly | GC (OTMU) |  | 0 | 0 | Closed | 2010-Chinn, Old Town/ASI-RFI/old town RFI-ASI/OTMU RFI 091 - New location for backflow protection assembly_Response.pdf
| RFI-092 | RFI |  | Water/sewer sleeves in PT slab for tenant spaces | GC (OTMU) |  | 0 | 0 | Closed | 2010-Chinn, Old Town/ASI-RFI/old town RFI-ASI/OTMU RESPONSE RFI 092 - Watersewer sleeves in PT slab for tenant spaces.pdf
| RFI-093 | RFI |  | Elevation & location of fixtures in stairwells | GC (OTMU) |  | 0 | 0 | Closed | 2010-Chinn, Old Town/ASI-RFI/old town RFI-ASI/OTMU RFI 093 - Elevation and location of fixtures in stairwells_Response.pdf
| RFI-095 | RFI |  | Water vault pump change (equipment substitution) | GC (OTMU) |  | 0 | 0 | Closed | 2010-Chinn, Old Town/ASI-RFI/old town RFI-ASI/OTMU RFI 095 - Water vault pump change_Response.pdf
| RFI-096 | RFI | 2013-03-01 | ERRCS head end equipment location | GC (OTMU) |  | 0 | 0 | Closed | 2010-Chinn, Old Town/ASI-RFI/old town RFI-ASI/OTMU RFI 096 - ERRCS head end equipment location-AWA WT Response-3-1-13.pdf
| RFI-099 | RFI |  | L01 PT pour east design changes | GC (OTMU) |  | 0 | 0 | Closed | 2010-Chinn, Old Town/ASI-RFI/old town RFI-ASI/OTMU RESPONSE RFI 99 L01 PT pour east design changes.pdf
| RFI-104 | RFI |  | PT deck at grid A level LM | GC (OTMU) |  | 0 | 0 | Closed | 2010-Chinn, Old Town/ASI-RFI/old town RFI-ASI/OTMU RFI 104 - PT deck at grid A level LM_Response1.pdf
| RFI-107 | RFI |  | Warning horn or light at garage exits | GC (OTMU) |  | 0 | 0 | Closed | 2010-Chinn, Old Town/ASI-RFI/old town RFI-ASI/OTMU RFI 107 - Warning Horn or Light at Garage Exits_Response1.pdf
| RFI-115 | RFI |  | Water repeater | GC (OTMU) |  | 0 | 0 | Closed | 2010-Chinn, Old Town/ASI-RFI/old town RFI-ASI/OTMU RFI 115 - Water repeater_Response.pdf

## Root Cause Analysis
[CORTEX_V2.1] Job #2010 — · Root Cause Analysis
Schema CORTEX_V2.1 · canonical v2 builder · single source of truth
| rca_id | observation | root_cause | responsibility | cost_impact | mitigation | source

## Predictive Signals
[CORTEX_V2.1] Job #2010 — · Predictive Signals
Schema CORTEX_V2.1 · canonical v2 builder · single source of truth
| signal_id | signal_name | direction | metric | threshold | historical_outcome | source
| WAREHOUSE | Predictive signals computed at warehouse layer | Neutral | cross-project benchmark | n/a | See benchmark_envelopes view; not stored per-project. | warehouse view (predictive_signals_v)

## Metric Registry
[CORTEX_V2.1] Job #2010 — · Metric Registry
Schema CORTEX_V2.1 · canonical v2 builder · single source of truth
| metric_key | metric_label | value | data_label | tab_home | verification | source
2010
Chinn Old Town Mixed Use
Chinn Construction, LLC
Seattle, WA
165-unit mixed-use multifamily apartments + ground-floor retail
24
165
803
1469800
1386419
-83381
1386419
800420.42
0.57733
585998.58
196271.13
282662.77
3650.67
103414.01
69320.95
9992.25
22
19.1909
18
73
-0.056729
14
7
2
0
0
0
23
0

## Reconciliation
[CORTEX_V2.1] Job #2010 — · Reconciliation
Schema CORTEX_V2.1 · canonical v2 builder · single source of truth
| check_number | check_description | value_a | value_b | difference | status | tabs
A. OVERVIEW ↔ BENCHMARK KPIS
|  | Direct Cost Total |  |  |  | TIES | 1↔2↔11
|  | Contract Final Value |  |  |  | TIES | JDR↔11
|  | Net Profit |  |  |  | TIES | JDR↔11
|  | Gross Margin |  |  |  | TIES | JDR↔11
B. OVERVIEW ↔ COST BREAKDOWN (Category Actuals)
|  | Labor Actual |  |  |  | TIES | 1↔3
|  | Material Actual |  |  |  | TIES | 1↔3
|  | Overhead Actual |  |  |  | TIES | 1↔3
|  | Burden Actual |  |  |  | TIES | 1↔3
C. BUDGET vs ACTUAL ↔ OVERVIEW
|  | Actual Direct Cost |  |  |  | TIES | 2↔1
|  | Revised Budget Total |  |  |  | TIES | 2↔1
D. MATERIAL ↔ COST BREAKDOWN ↔ KPIS
|  | Material Actual (Material tab) |  |  |  | TIES | 4↔3
|  | Material Actual (KPIs) |  |  |  | TIES | 11↔3
E. CREW & LABOR ↔ PRODUCTIVITY ↔ KPIS (Hours)
|  | Total Hours (Crew tab) |  |  |  | WITHIN | 5↔11
|  | Total Hours (Productivity tab) |  |  |  | TIES | 7↔11
|  | Total Workers |  |  |  | TIES | JDR↔11
F. CREW ANALYTICS ↔ KPIS (Wage Statistics)
|  | Blended Gross Wage |  |  |  | TIES | 6↔11
|  | Fully-Loaded Wage |  |  |  | TIES | 6↔11
G. PO COMMITMENTS ↔ KPIS
|  | PO Count |  |  |  | TIES | 8↔11
H. BILLING & SOV ↔ JDR
|  | Final Contract Value |  |  |  | TIES | 9↔JDR
|  | Retainage |  |  |  | TIES | 9↔JDR
|  | Direct Cost |  |  |  | TIES | 9↔JDR
I. VENDORS ↔ KPIS
|  | Vendor Count |  |  |  | TIES | 12↔11
|  | Total AP Spend |  |  |  | TIES | 12↔JDR
J. INSIGHTS (Narrative Review)
10 insight cards — narrative text verified at generation time, no formula check applicable
K. CHANGE LOG ↔ ROOT CAUSE ANALYSIS
|  | Total Event Count |  |  |  | TIES | 13↔14
|  | Net $ Impact (all events) |  |  |  | TIES | 13↔14
L. PREDICTIVE SIGNALS ↔ CHANGE LOG
|  | Backcharge Count signal |  |  |  | TIES | 15↔13
M. METRIC REGISTRY ↔ BENCHMARK KPIs
|  | revenue (row 17) |  |  |  | TIES | 16↔11
|  | unit_count (row 12) |  |  |  | TIES | 16↔11
|  | total_fixtures (row 13) |  |  |  | TIES | 16↔11
|  | direct_cost (row 19) |  |  |  | OFF | 16↔11
|  | total_pos (row 30) |  |  |  | TIES | 16↔11
N. CHANGE LOG ↔ METRIC REGISTRY (event counts)
|  | change_event_total |  |  |  | OFF | 16↔13
SOURCES
Job #2010 — Cortex v2 17-tab layout
12 analytical tabs + Change Log + Root Cause Analysis + Predictive Signals + Metric Registry + Reconciliation
Canonical source: 2010 Job Detail Report.pdf (Sage Timberline export)
Change artifacts: folders scanned — ASI-RFI, Change Orders, Submittals, Invoices (Backcharges), JDR cost codes
Every Change Log row cites its source document path
TIES = within $1/5hrs/exact count • WITHIN = within 5% • OFF = investigate
Cross-sheet formulas (='Tab'!Cell) update automatically when source tabs change
Tabs: 1-12 analytical • 13=ChangeLog • 14=RootCause • 15=PredictiveSignals • 16=MetricRegistry • 17=Reconciliation

## Vendors
[CORTEX_V2.1] Job #2010 — · Vendors
Schema CORTEX_V2.1 · canonical v2 builder · single source of truth
| vendor_id | vendor_name | total_spend | transactions | category | source
Invoices
73
58
3
4
7
2
6
7
3
1
2
1
1
1
2
2
1
1