## Overview
[CORTEX_V2.1] Job #2011 — · Overview
Schema CORTEX_V2.1 · canonical v2 builder · single source of truth
| OVERVIEW |  | SOURCE
IDENTITY
| Project Job Number | 2011
| Project Name: | Chinn Barrett Park Apartments
CONTRACT & PARTIES
| General Contractor | Chinn Construction, LLC
JOB SITE
| Jobsite Location | Seattle, WA (Capitol Hill)
| Plumbing Units | 117 | Kitchen Sinks
SCHEDULE
| Project Duration | Nov 2012 – Mar 2014 (~17 months)
SCOPE & DESIGN
| Total Fixtures | 841 | Dishwashers
| Fixtures / Unit | 7.18 | Auto Washers
| Stacks | 30 | Duration
| CONTRACT VALUE |  | NET PROFIT |  | DIRECT COST |  | LABOR HOURS
| $813,050 |  | $334,095 |  | $535,729 |  | 13,606
| Original $813,050 |  | 38.4% margin |  | 61.6% of revenue |  | 40 workers
COST BREAKDOWN
| Category | Budget | Actual | Variance | % Budget | % of Cost
| Labor | 174655 | 142882.75 | 31772.25 | 81.81% | 26.67%
| Material | 388634 | 293871.12 | 94762.88 | 75.62% | 54.85%
| Overhead | 45725 | 26210.1 | 19514.9 | 57.32% | 4.892%
| Burden | 89051.11 | 72764.72 | 16286.39 | 81.71% | 13.58%
| TOTAL | 698065.11 | 535728.69 | 162336.42 | 76.74% | 100%
PROJECT PROFILE
| Plumbing Units | 117 |  | Total Fixtures | 841 |  | Fixtures / Unit | 7.19
| Floors | 30 |  | Duration | Nov 2012 – Mar 2014 (~17 months)

## Budget vs Actual
[CORTEX_V2.1] Job #2011 — · Budget vs Actual
Schema CORTEX_V2.1 · canonical v2 builder · single source of truth
| cost_code | description | original_budget | revised_budget | actual | variance | pct_used | hours | source
LABOR
| 011 | DS & RD Labor | 3250 | 3250 | 1008 | 2242 | 31.02%
| 100 | Supervision | 8190 | 8190 | 4164 | 4026 | 50.84%
| 101 | Takeoff & Purchase Labor | 5850 | 5850 | 3513 | 2337 | 60.05%
| 110 | Underground Labor | 13150 | 13150 | 6703 | 6447 | 50.97%
| 111 | Garage Labor | 16200 | 16200 | 10199 | 6001 | 62.96%
| 112 | Canout Labor | 3640 | 3640 | 2062 | 1578 | 56.65%
| 113 | Foundation Drain Labor | 0 | 5650 | 2115 | 3535 | 37.43%
| 120 | Roughin Labor | 82535 | 82835 | 81010.75 | 1824.25 | 97.8%
| 130 | Finish Labor | 24770 | 24770 | 21869 | 2901 | 88.29%
| 141 | Water Main/Insulation Lab | 0 | 0 | 208 | -208 | 0%
| 142 | Mech Room Labor | 1760 | 1760 | 1007 | 753 | 57.22%
| 145 | Tub/Shower Labor | 9360 | 9360 | 9024 | 336 | 96.41%
MATERIAL
| 039 | DS & RD Material | 4725 | 4725 | 1134.76 | 3590.24 | 24.02%
| 210 | Underground Material | 10300 | 10300 | 5311 | 4989 | 51.56%
| 211 | Garage Material | 14000 | 14000 | 6465.89 | 7534.11 | 46.18%
| 212 | Canout Material | 5460 | 5460 | 5222.75 | 237.25 | 95.65%
| 213 | Foundation Material | 0 | 6000 | 3664.54 | 2335.46 | 61.08%
| 220 | Roughin Material | 82540 | 82840 | 48840.52 | 33999.48 | 58.96%
| 230 | Finish Material | 231620 | 259734 | 207101.2 | 52632.8 | 79.74%
| 241 | Water Main/Insulation Mat | 7800 | 7800 | 15147.02 | -7347.02 | 1.942%
| 242 | Mech Room Material | 2500 | 2500 | 1233.58 | 1266.42 | 49.34%
| 244 | Fire Caulking Material | 0 | 0 | 0 | 0 | 0%
| 245 | Tub/Shower Material | 0 | 0 | 884.62 | -884.62 | 0%
OVERHEAD
| 600 | Subcontractor | 10000 | 13085 | 6346.07 | 6738.93 | 48.5%
| 601 | Engineering/Plans | 25000 | 25000 | 12573.03 | 12426.97 | 50.29%
| 603 | Permits & Licenses | 7630 | 7640 | 7291 | 349 | 95.43%
BURDEN
| 995 | Payroll Burden | 73133.62 | 75712.95 | 61834.11 | 13878.84 | 81.67%
| 998 | Payroll Taxes | 12905.93 | 13338.16 | 10930.61 | 2407.55 | 81.95%
SOURCES
Job #2011 — Chinn Barrett Park Apartments • GC: Chinn Construction, LLC • Seattle, WA (Capitol Hill)
Canonical source: 2011 Job Detail Report.pdf (69 pages, OWP Sage Timberline export)
Cost codes parsed: 29
Unit count: 117 units confirmed
Fixture count: 841 from permit SR1224327
Billing: BARRETT AGGREGATE BILLING.xlsx (13 pay apps Nov 2012 – Mar 2014)
| TOTAL |  | 656319.55 | 702790.11 | 536863.45 | 165926.66 |  | 0

## Cost Breakdown
[CORTEX_V2.1] Job #2011 — · Cost Breakdown
Schema CORTEX_V2.1 · canonical v2 builder · single source of truth
| category | cost_codes | actual | pct_of_direct_cost | pct_of_revenue | per_unit | source
| Labor | 12 | 174655 | 81.81% |  | 1221.2201
| Material | 11 | 393359 | 75% |  | 2521.4178
| Overhead | 3 | 45725 | 57.32% |  | 224.0179
| Burden | 2 | 89051.11 | 81.71% |  | 621.9207
B. LARGEST OVERRUNS (Actual > Revised Budget)
| Code | Description
| 241 | Water Main/Insulation Mat | 7800 | 94.19%
| 245 | Tub/Shower Material | 0 | 0%
| 141 | Water Main/Insulation Lab | 0 | 0%
C. LARGEST SAVINGS (Actual < Revised Budget)
| Code | Description
| 230 | Finish Material | 259734 | 20.26%
| 220 | Roughin Material | 82840 | 41.04%
| 995 | Payroll Burden | 75712.95 | 18.33%
| 601 | Engineering/Plans | 25000 | 49.71%
| 211 | Garage Material | 14000 | 53.82%
| 600 | Subcontractor | 13085 | 51.5%
| 110 | Underground Labor | 13150 | 49.03%
| 111 | Garage Labor | 16200 | 37.04%
| 210 | Underground Material | 10300 | 48.44%
| 100 | Supervision | 8190 | 49.16%
SOURCES
Job #2011 — Chinn Barrett Park Apartments • GC: Chinn Construction, LLC • Seattle, WA (Capitol Hill)
Canonical source: 2011 Job Detail Report.pdf (69 pages, OWP Sage Timberline export)
Cost codes parsed: 29
Unit count: 117 units confirmed
Fixture count: 841 from permit SR1224327
Billing: BARRETT AGGREGATE BILLING.xlsx (13 pay apps Nov 2012 – Mar 2014)
| TOTAL |  | 1228802.06 |  |  | 4588.5765

## Material
[CORTEX_V2.1] Job #2011 — · Material
Schema CORTEX_V2.1 · canonical v2 builder · single source of truth
| vendor_id | vendor_name | total_spend | transactions | category | source
| 039 | DS & RD Material | 4725 |  | 0.0038466
| 210 | Underground Material | 10300 |  | 0.018003
| 211 | Garage Material | 14000 |  | 0.021918
| 212 | Canout Material | 5460 |  | 0.017704
| 213 | Foundation Material | 6000 |  | 0.012422
| 220 | Roughin Material | 82840 |  | 0.16556
| 230 | Finish Material | 259734 |  | 0.70202
| 241 | Water Main/Insulation Mat | 7800 |  | 0.051345
| 242 | Mech Room Material | 2500 |  | 0.0041815
| 244 | Fire Caulking Material | 0 |  | 0
| 245 | Tub/Shower Material | 0 |  | 0.0029987
B. VENDORS BY SPEND (AP)
| Vendor | # Invoices
| Ferguson Enterprises, Inc. | 56 | 302211.38
| Rosen Supply Company, Inc. | 30 | 35755.01
| Franklin Engineering | 5 | 12487
| Keller Supply Company | 13 | 10651.28
| Fastenal Company | 4 | 8107.96
| Bank of America CC | 3 | 7291
| Mickelo Construction LLC | 2 | 6217.07
| Quality Concrete Products, Inc. | 2 | 2598
| Manor Hardware & Construction Supply | 2 | 870
| Core & Main LP | 1 | 810
| R.A. Brown Backflow Testing | 1 | 129
| C.M. Hoskins Company | 1 | 102
| DRSi | 1 | 86.03
| Capital One Credit Card | 2 | 63.21
SOURCES
Job #2011 — Chinn Barrett Park Apartments • GC: Chinn Construction, LLC • Seattle, WA (Capitol Hill)
Canonical source: 2011 Job Detail Report.pdf (69 pages, OWP Sage Timberline export)
Cost codes parsed: 29
Unit count: 117 units confirmed
Fixture count: 841 from permit SR1224327
Billing: BARRETT AGGREGATE BILLING.xlsx (13 pay apps Nov 2012 – Mar 2014)
Vendor AP ties to JDR 'by Source: AP' line (387,378.94)

## Crew & Labor
[CORTEX_V2.1] Job #2011 — · Crew & Labor
Schema CORTEX_V2.1 · canonical v2 builder · single source of truth
| worker_id | worker_name | total_hours | gross_pay | blended_wage_per_hr | tier | work_days | source
| Quintanilla, Esteban R |  | 804.5 | 24669 | 30.6638 | Senior
| Castro Hernandez, Jose A |  | 785.5 | 11541 | 14.6926 | Apprentice
| Monico Brambila, Jesus S |  | 640 | 7792 | 12.175 | Apprentice
| Garcia, Jordan X |  | 607 | 7748 | 12.7644 | Apprentice
| Lima Romero, Melvin A |  | 523.5 | 9941.5 | 18.9904 | Mid
| Castaneda Martinez, Gustavo |  | 449 | 11691 | 26.0379 | Mid
| Palma Vides, Hugo |  | 384 | 9984 | 26 | Mid
| Anderson, Richard P |  | 341 | 8866 | 26 | Mid
| Wilson, Garret A |  | 320 | 4296 | 13.425 | Apprentice
| Gerard, Jeffrey S |  | 254 | 8779 | 34.563 | Senior
| McCabe, Thomas C |  | 196 | 3504 | 17.8776 | Apprentice
| Ross, Kelli M |  | 189 | 5292 | 28 | Mid
| Reed, Reuben H |  | 157 | 4082 | 26 | Mid
| Sepulveda Gonzalez, Alfredo |  | 157 | 3547 | 22.5924 | Mid
| Holmes, Anthony R |  | 136 | 1616 | 11.8824 | Apprentice
| Kinssies, Jr, John E |  | 128 | 1696 | 13.25 | Apprentice
| Meza Fuentes, Erick A |  | 126 | 2402 | 19.0635 | Mid
| Barnhart, Joseph N |  | 122 | 3782 | 31 | Senior
| Hayton, Evan R |  | 118 | 1652 | 14 | Apprentice
| Ramirez, Lorenzo A |  | 108 | 1728 | 16 | Apprentice
| Gonzalez Hernandez, Josue |  | 80 | 960 | 12 | Apprentice
| Paco Leyva, Orlando |  | 37 | 444 | 12 | Apprentice
| Veley, Nathaniel S |  | 34 | 850 | 25 | Mid
| Hubbard, Dustin R |  | 33.5 | 402 | 12 | Apprentice
| Cortes Mendiola, Victor H |  | 24 | 552 | 23 | Mid
| Sanders, Allen O |  | 9 | 261 | 29 | Mid
| Arreola, Israel A |  | 8 | 96 | 12 | Apprentice
| Castro Hernandez, Carlos E |  | 8 | 184 | 23 | Mid
| Soto Cruz, Jovani |  | 8 | 128 | 16 | Apprentice
| Soto Serna, Cesar E |  | 8 | 104 | 13 | Apprentice
| Vaughan, Tyler J |  | 8 | 104 | 13 | Apprentice
| TOTAL (31 workers) |  | 6803 | 138693.5 | 20.3871
SOURCES
Job #2011 — Chinn Barrett Park Apartments • GC: Chinn Construction, LLC • Seattle, WA (Capitol Hill)
Canonical source: 2011 Job Detail Report.pdf (69 pages, OWP Sage Timberline export)
Cost codes parsed: 29
Unit count: 117 units confirmed
Fixture count: 841 from permit SR1224327
Billing: BARRETT AGGREGATE BILLING.xlsx (13 pay apps Nov 2012 – Mar 2014)
Tier: Apprentice <$18/hr, Mid $18–30, Senior >$30

## Crew Analytics
[CORTEX_V2.1] Job #2011 — · Crew Analytics
Schema CORTEX_V2.1 · canonical v2 builder · single source of truth
| tier | worker_count | hours | gross_pay | pct_of_hours | blended_wage
| Senior | 3 | 1180.5 | 37230 | 17.35%
| Mid | 12 | 2401.5 | 57652.5 | 35.3%
| Apprentice | 16 | 3221 | 43811 | 47.35%
B. WAGE STATISTICS
| Blended Gross Wage | 20.3871
| Fully-Loaded Wage | 31.6989
| Burden Multiplier | 1.5548
| Min Worker Rate | 11.8824
| Max Worker Rate | 34.563
| Avg Hours / Worker | 219.4516
SOURCES
Job #2011 — Chinn Barrett Park Apartments • GC: Chinn Construction, LLC • Seattle, WA (Capitol Hill)
Canonical source: 2011 Job Detail Report.pdf (69 pages, OWP Sage Timberline export)
Cost codes parsed: 29
Unit count: 117 units confirmed
Fixture count: 841 from permit SR1224327
Billing: BARRETT AGGREGATE BILLING.xlsx (13 pay apps Nov 2012 – Mar 2014)

## Productivity
[CORTEX_V2.1] Job #2011 — · Productivity
Schema CORTEX_V2.1 · canonical v2 builder · single source of truth
| phase | labor_code | hours | pct_of_total | hours_per_unit
| DS & RD | 011 | 56 | 0.8065% | 0.47863
| Supervision | 100 | 117 | 1.685% | 1
| Takeoff & Purchasing | 101 | 104 | 1.498% | 0.88889
| Underground | 110 | 298.5 | 4.299% | 2.5513
| Garage | 111 | 553 | 7.964% | 4.7265
| Canout | 112 | 96 | 1.383% | 0.82051
| Foundation Drain | 113 | 96.5 | 1.39% | 0.82479
| Roughin | 120 | 3984 | 57.38% | 34.0513
| Finish | 130 | 1173 | 16.89% | 10.0256
| Water Main / Insulation | 141 | 16 | 0.2304% | 0.13675
| Mech Room | 142 | 44 | 0.6337% | 0.37607
| Tub / Shower | 145 | 405.5 | 5.84% | 3.4658
B. PRODUCTIVITY RATIOS
| Metric | Value
| Hours / Unit | 59.3462
| Hours / Fixture | 8.2562
| Revenue / Hour | 125.2716
| Profit / Hour | 47.9528
| Units / Month | 6.8824
| Fixtures / Month | 49.4706
| Hours / Month | 408.4412
| Revenue / Month | 51166.0882
SOURCES
Job #2011 — Chinn Barrett Park Apartments • GC: Chinn Construction, LLC • Seattle, WA (Capitol Hill)
Canonical source: 2011 Job Detail Report.pdf (69 pages, OWP Sage Timberline export)
Cost codes parsed: 29
Unit count: 117 units confirmed
Fixture count: 841 from permit SR1224327
Billing: BARRETT AGGREGATE BILLING.xlsx (13 pay apps Nov 2012 – Mar 2014)

## PO Commitments
[CORTEX_V2.1] Job #2011 — · PO Commitments
Schema CORTEX_V2.1 · canonical v2 builder · single source of truth
| po_number | date | issuer | type | status | description | amount | source
B. COMMITMENTS BY VENDOR
| Vendor |  |  |  |  | PO Count
C. PO COVERAGE NOTES
Total Material Actual (JDR)
Unique PO Count
(Dollar PO commitment not extracted — requires per-PDF parse)
SOURCES
Job #2011 — Chinn Barrett Park Apartments • GC: Chinn Construction, LLC • Seattle, WA (Capitol Hill)
Canonical source: 2011 Job Detail Report.pdf (69 pages, OWP Sage Timberline export)
Cost codes parsed: 29
Unit count: 117 units confirmed
Fixture count: 841 from permit SR1224327
Billing: BARRETT AGGREGATE BILLING.xlsx (13 pay apps Nov 2012 – Mar 2014)
PO count is deduplicated by 5-digit PO number extracted from filenames
Vendor/code classification is heuristic (filename keyword match)

## Billing & SOV
[CORTEX_V2.1] Job #2011 — · Billing & SOV
Schema CORTEX_V2.1 · canonical v2 builder · single source of truth
| pay_app_number | date | contract_total | this_period | retainage | stored_materials | cumulative | pct_complete | source

## Insights
[CORTEX_V2.1] Job #2011 — · Insights
Schema CORTEX_V2.1 · canonical v2 builder · single source of truth
| insight_id | title | finding | verified | source
| 1 | Labor came in 18.1% under budget | Total labor actual $142,883 vs budget $174,355 — $31,472 favorable variance. | Derived | budget_vs_actual
| 2 | Largest variance — cost code 230 (Finish Material) under by $52,633 | Budget $259,734, actual $207,101 (-20.3%). Flag for bid calibration. | Derived | budget_vs_actual

## Benchmark KPIs
[CORTEX_V2.1] Job #2011 — · Benchmark KPIs
Schema CORTEX_V2.1 · canonical v2 builder · single source of truth
CROSS-PROJECT BENCHMARK SCORECARD
Normalized metrics designed for apples-to-apples comparison across all OWP projects.
| KPI | DATA NAME | VALUE | CATEGORY | NOTES / BENCHMARK CONTEXT
| Job Number | job_number | 2,011 | Profile | OWP Sage job ID
| General Contractor | general_contractor | Chinn Construction, LLC | Profile | Customer of record
| location | location | Seattle, WA (Capitol Hill) | Profile | Project address
| Project Type | project_type | Apartment building | Profile | Building category for benchmarking
| Duration Months | duration_months | 17.0% | Profile | Calendar months from start to close
| Plumbing Units | plumbing_units | 117 | Profile | Residential units delivered
| Total Fixtures | total_fixtures | 841 | Profile | Plumbing fixture count
| Fixtures Per Unit | fixtures_per_unit | $7.19 | Profile | ≈6 fixtures/unit typical for multifamily
| Contract Original | contract_original | $813,050 | Financial | Original contract value
| Contract Final | contract_final | $813,050 | Financial | Revised contract value (post-COs)
| Change Orders Net | change_orders_net | 0 | Financial | Net dollar change from COs
| revenue | revenue | $869,824 | Financial | Net billed (AR net of reversals)
| Net Profit | net_profit | $334,095 | Financial | Revenue − direct cost
| Gross Margin Pct | gross_margin_pct | 38.4% | Financial | Net profit / revenue
| Direct Cost | direct_cost | $535,729 | Financial | Σ labor + material + OH + burden + tax
| Overhead Cost | overhead_cost | $26,210 | Financial | Codes 600, 601, 603, 607
| Burden Cost | burden_cost | $61,834 | Financial | Code 995 payroll burden
| Retainage Outstanding | retainage_outstanding | $0.00 | Financial | Held by GC until closeout
| Revenue Per Unit | revenue_per_unit | $7,434 | Financial | Top-line per unit
| Profit Per Unit | profit_per_unit | $2,856 | Financial | Net profit normalized per residential unit
| Cost Per Unit | cost_per_unit | $4,579 | Financial | Total direct cost per unit
| Revenue Per Fixture | revenue_per_fixture | $1,034 | Financial | Top-line per fixture
| Profit Per Fixture | profit_per_fixture | $397 | Financial | Net profit per fixture installed
| Cost Per Fixture | cost_per_fixture | $637 | Financial | Total direct cost per fixture
| Labor Cost | labor_cost | $142,883 | Labor | Codes 100–150
| Total Hours | total_hours | 13,606 | Labor | All payroll hours on the job
| Total Workers | total_workers | 40 | Crew | Unique payroll IDs across job
| Blended Wage | blended_wage | $20.39 | Labor | Pre-burden average
| Fully Loaded Wage | fully_loaded_wage | $15.85 | Labor | Post-burden true cost
| Burden Multiplier | burden_multiplier | 0.78 | Labor | Loaded / gross
| Hours Per Unit | hours_per_unit | $0.00 | Labor | Key plumbing benchmark
| Hours Per Fixture | hours_per_fixture | $0.00 | Labor | Industry std for plumbing subs
| Labor Per Unit | labor_per_unit | $1,221 | Labor | Payroll only, not material
| Labor Per Fixture | labor_per_fixture | $170 | Labor | Payroll only, not material
| Labor Pct Revenue | labor_pct_revenue | 0.16 | Cost Mix | Payroll exposure
| Material Cost | material_cost | $293,871 | Material | Codes 210–244
| Material Per Unit | material_per_unit | $2,512 | Material | Cross-project benchmark
| Material Per Fixture | material_per_fixture | $349 | Material | Cross-project benchmark
| Material Pct Revenue | material_pct_revenue | 0.34 | Cost Mix | Material/sub exposure
| Total Vendors | total_vendors | 15 | Material | Distinct AP vendors invoiced on the job
| Top Vendor Spend | top_vendor_spend | $0.00 | Material | Largest single supplier
| Top Vendor Pct | top_vendor_pct | 0.0% | Material | Top vendor concentration
| Revenue Per Month | revenue_per_month | $51,166 | Throughput | Billing velocity
| Hours Per Month | hours_per_month | $0.00 | Throughput | Avg monthly labor burn
| Units Per Month | units_per_month | $6.88 | Throughput | Build pace
| Fixtures Per Month | fixtures_per_month | $49.47 | Throughput | Fixture install velocity
SOURCES
Canonical: /sessions/keen-determined-mccarthy/mnt/cortex-mockup/owp/cortex v2 files/OWP_2011_JCR_Cortex_v2.xlsx
revenue: AR net-of-reversals (validator)
labor_cost: Codes 100–150
material_cost: Codes 210–244
total_workers: count(distinct worker_id)

## Change Log
[CORTEX_V2.1] Job #2011 — · Change Log
Schema CORTEX_V2.1 · canonical v2 builder · single source of truth
| event_id | type | date | subject | originator | linked_events | cost_impact | schedule_days | status | source_document
| CO-001 | CO | 2013-04-11 | Furnish and install footing + sub-slab drains (field condition discovered during excavation) | Field (OWP) |  | 25400 | 0 | Approved | 2011-Chinn, Barrett Park/Barrett billing/Chinn Barrett Park schedule of values 1
| CO-002 | CO | 2013-05-09 | Add trash chute wash down | Architect |  | 959 | 0 | Approved | 2011-Chinn, Barrett Park/Barrett billing/Chinn Barrett Park schedule of values 5
| CO-003 | CO | 2014-02-10 | Change plumbing fixtures — ADA + standard alternatives | Architect | SUB-P11-R1, SUB-P13-R1, SUB-PRV-R1 | 30415 | 0 | Partial (billed $15,597 of $30,415) | 2011-Chinn, Barrett Park/Barrett billing/Chinn Barrett Park schedule of values 12
| ASI-002 | ASI | 2013-04-11 | Revised Unit A-2 layout | Architect |  | 0 | 0 | Closed | 2011-Chinn, Barrett Park/Barrett RFI-ASI/Barrett ASI 02
| ASI-003 | ASI | 2013-04-12 | Revised Unit A-1 layout | Architect |  | 0 | 0 | Closed | 2011-Chinn, Barrett Park/Barrett RFI-ASI/Barrett ASI 03
| ASI-004 | ASI | 2013-04-16 | Live/Work Units ABC dimension clarification | Architect |  | 0 | 0 | Closed | 2011-Chinn, Barrett Park/Barrett RFI-ASI/Barrett ASI 04
| ASI-006 | ASI | 2013-06-04 | Soffit above upper cabinet clarification | Architect |  | 0 | 0 | Closed | 2011-Chinn, Barrett Park/Barrett RFI-ASI/Barrett ASI 06
| ASI-008 | ASI | 2013-09-23 | Unit A2 island counter revision | Architect |  | 0 | 0 | Closed | 2011-Chinn, Barrett Park/Barrett RFI-ASI/ASI 008
| RFI-033 | RFI | 2013-04-11 | Siding detail clarifications | GC (SMS) |  | 0 | 0 | Closed | 2011-Chinn, Barrett Park/Barrett RFI-ASI/12-0806 Barrett Park RFI 033
| RFI-034 | RFI | 2013-04-18 | RSIC clip in ceiling below roof | GC (SMS) |  | 0 | 0 | Closed | 2011-Chinn, Barrett Park/Barrett RFI-ASI/12-0806 Barret Park RFI 034
| RFI-037 | RFI | 2013-04-16 | Wall elevation — copy storage + amenity rooms | GC (SMS) |  | 0 | 0 | Closed | 2011-Chinn, Barrett Park/Barrett RFI-ASI/RFI 037 - Response
| RFI-038 | RFI | 2013-04-12 | Elevation of island kitchen (A-2) | GC (SMS) |  | 0 | 0 | Closed | 2011-Chinn, Barrett Park/Barrett RFI-ASI/RFI 038 Response
| RFI-039 | RFI | 2013-04-16 | Lobby + mgmt office offset from Grid B | GC (SMS) |  | 0 | 0 | Closed | 2011-Chinn, Barrett Park/Barrett RFI-ASI/RFI 039
| RFI-040 | RFI | 2013-05-03 | Wood stair details | GC (SMS) |  | 0 | 0 | Closed | 2011-Chinn, Barrett Park/Barrett RFI-ASI/12-0806 Barret Park RFI 040
| RFI-043 | RFI | 2013-07-02 | Patio at Unit 104 too short | Owner |  | 0 | 0 | Closed | 2011-Chinn, Barrett Park/Barrett RFI-ASI/12-0806 Barret Park RFI 043
| RFI-044 | RFI | 2013-05-16 | Steel headers at exterior sliders (top floor) | GC (SMS) |  | 0 | 0 | Closed | 2011-Chinn, Barrett Park/Barrett RFI-ASI/RFI 044
| RFI-045 | RFI | 2013-05-20 | Range vent at Unit B-1 | GC (SMS) |  | 0 | 0 | Closed | 2011-Chinn, Barrett Park/Barrett RFI-ASI/RFI 045
| RFI-046 | RFI | 2013-05-24 | Venting plan at Unit D-4 | GC (SMS) |  | 0 | 0 | Closed | 2011-Chinn, Barrett Park/Barrett RFI-ASI/12-0806 Barret Park RFI 046
| RFI-048 | RFI | 2013-05-21 | Confirming concrete walls at garage | GC (SMS) |  | 0 | 0 | Closed | 2011-Chinn, Barrett Park/Barrett RFI-ASI/Barrett Park - RFI 048
| RFI-055 | RFI | 2013-06-14 | Coping detail at metal siding | GC (SMS) |  | 0 | 0 | Closed | 2011-Chinn, Barrett Park/Barrett RFI-ASI/12-0806 Barret Park RFI 055
| RFI-057 | RFI | 2013-06-14 | ADA clearances at kitchens | GC (SMS) | CO-003 | 0 | 0 | Closed | 2011-Chinn, Barrett Park/Barrett RFI-ASI/12-0806 Barrett Park RFI 057
| RFI-058 | RFI | 2013-06-14 | Energy factor for hot water tank | GC (SMS) |  | 0 | 0 | Closed | 2011-Chinn, Barrett Park/Barrett RFI-ASI/12-0806 Barret Park RFI 058
| RFI-059 | RFI | 2013-06-18 | FEC location and types | GC (SMS) |  | 0 | 0 | Closed | 2011-Chinn, Barrett Park/Barrett RFI-ASI/RFI 059
| RFI-074 | RFI | 2013-09-11 | Storefront S1/S2/S3 clarifications | GC (SMS) |  | 0 | 0 | Closed | 2011-Chinn, Barrett Park/Barrett RFI-ASI/RFI 074
| RFI-076 | RFI | 2013-09-11 | Live/Work units accessibility compliance | GC (SMS) |  | 0 | 0 | Closed | 2011-Chinn, Barrett Park/Barrett RFI-ASI/RFI 076
| RFI-079 | RFI | 2013-11-08 | Water heater at amenity kitchen | GC (SMS) |  | 0 | 0 | Closed | 2011-Chinn, Barrett Park/Barrett RFI-ASI/12-0806 Barret Park RFI 079
| SUB-P11-R1 | Submittal-resub |  | P11 tankless heater — revised submittal | Sub (OWP) | CO-003 | 0 | 0 | Approved | 2011-Chinn, Barrett Park/Submittals/MIKE_S FILES/
| SUB-P13-R1 | Submittal-resub |  | P13 amenity room water heater — revised submittal | Sub (OWP) | CO-003 | 0 | 0 | Approved | 2011-Chinn, Barrett Park/Submittals/MIKE_S FILES/
| SUB-PRV-R1 | Submittal-resub |  | PRV-2 pressure regulating valve — revised submittal | Sub (OWP) | CO-003 | 0 | 0 | Approved | 2011-Chinn, Barrett Park/Submittals/MIKE_S FILES/

## Root Cause Analysis
[CORTEX_V2.1] Job #2011 — · Root Cause Analysis
Schema CORTEX_V2.1 · canonical v2 builder · single source of truth
| rca_id | observation | root_cause | responsibility | cost_impact | mitigation | source
| RCA-01 | Furnish and install footing + sub-slab drains (field condition discovered during excavation) | Pending document review — see source document for detail | OWP | 25400 |  | 2011-Chinn, Barrett Park/Barrett billing/Chinn Barrett Park schedule of values 1
| RCA-02 | Add trash chute wash down | Pending document review — see source document for detail | Architect | 959 |  | 2011-Chinn, Barrett Park/Barrett billing/Chinn Barrett Park schedule of values 5
| RCA-03 | Change plumbing fixtures — ADA + standard alternatives | Pending document review — see source document for detail | Architect | 30415 |  | 2011-Chinn, Barrett Park/Barrett billing/Chinn Barrett Park schedule of values 12

## Predictive Signals
[CORTEX_V2.1] Job #2011 — · Predictive Signals
Schema CORTEX_V2.1 · canonical v2 builder · single source of truth
| signal_id | signal_name | direction | metric | threshold | historical_outcome | source
| WAREHOUSE | Predictive signals computed at warehouse layer | Neutral | cross-project benchmark | n/a | See benchmark_envelopes view; not stored per-project. | warehouse view (predictive_signals_v)

## Metric Registry
[CORTEX_V2.1] Job #2011 — · Metric Registry
Schema CORTEX_V2.1 · canonical v2 builder · single source of truth
| metric_key | metric_label | value | data_label | tab_home | verification | source
2011
Chinn Barrett Park Apartments
Chinn Construction, LLC
Seattle, WA (Capitol Hill)
117-unit 4-story multifamily apartments
17
117
841
813050
869823.5
56773.5
869823.5
332960.05
0.38279
536863.45
142882.75
295005.88
26210.1
72764.72
43491
6943.5
31
19.9746
14
0
0.069828
19
5
3
0
0
7
29
56774

## Reconciliation
[CORTEX_V2.1] Job #2011 — · Reconciliation
Schema CORTEX_V2.1 · canonical v2 builder · single source of truth
| check_number | check_description | value_a | value_b | difference | status | tabs
A. JDR COST CODE ROLLUP
|  | Labor subtotal (12 codes) | 142882.75 |  |  | TIES
|  | Material subtotal (11 codes) | 295005.88 |  |  | TIES
|  | Overhead subtotal (3 codes) | 26210.1 |  |  | TIES
|  | Burden subtotal (2 codes) | 72764.72 |  |  | TIES
|  | Direct Cost (all categories) | 536863.45 |  |  | TIES
|  | Revenue (code 999) | 869823.5 |  |  | TIES
|  | Net Profit (Revenue - Expenses) | 332960.05 |  |  | TIES
B. LABOR HOURS ROLLUP
|  | JDR Cost Code hours (Payroll Hours lines) | 6943.5 |  |  | TIES
|  | Per-worker hours (sum of PR Regular) | 6943.5 |  |  | WITHIN
C. BILLING (SOV) ↔ JDR
|  | Final Contract Value | 869824 |  |  | TIES
|  | Retainage | 43491 |  |  | TIES
|  | Direct Cost | 536863.45 |  |  | TIES
D. VENDOR AP ↔ JDR
|  | Vendor AP total (sum of invoices) | 387379 |  |  | TIES
SOURCES
Job #2011 — Chinn Barrett Park Apartments • GC: Chinn Construction, LLC • Seattle, WA (Capitol Hill)
Canonical source: 2011 Job Detail Report.pdf (69 pages, OWP Sage Timberline export)
Cost codes parsed: 29
Unit count: 117 units confirmed
Fixture count: 841 from permit SR1224327
Billing: BARRETT AGGREGATE BILLING.xlsx (13 pay apps Nov 2012 – Mar 2014)
TIES = within $1 or 5 hrs • WITHIN = within 5% • OFF = investigate
K. CHANGE LOG ↔ ROOT CAUSE ANALYSIS
|  | Total Event Count | 29 |  |  | TIES
|  | Net $ Impact (all events) | 56774 |  |  | TIES
L. PREDICTIVE SIGNALS ↔ CHANGE LOG
|  | Backcharge Count signal | 0 |  |  | TIES
M. METRIC REGISTRY ↔ BENCHMARK KPIs
|  | revenue (row 17) | 869823.5 |  |  | TIES
|  | unit_count (row 12) | 117 |  |  | TIES
|  | total_fixtures (row 13) | 841 |  |  | TIES
|  | direct_cost (row 19) | 536863.45 |  |  | OFF
|  | total_pos (row 30) | 0 |  |  | TIES
N. CHANGE LOG ↔ METRIC REGISTRY (event counts)
|  | change_event_total | 29 |  |  | OFF
SOURCES
Job #2011 — Cortex v2 17-tab layout
12 analytical tabs + Change Log + Root Cause Analysis + Predictive Signals + Metric Registry + Reconciliation
Canonical source: 2011 Job Detail Report.pdf (Sage Timberline export)
Change artifacts: folders scanned — ASI-RFI, Change Orders, Submittals, Invoices (Backcharges), JDR cost codes
Every Change Log row cites its source document path
TIES = within $1/5hrs/exact count • WITHIN = within 5% • OFF = investigate
Cross-sheet formulas (='Tab'!Cell) update automatically when source tabs change
Tabs: 1-12 analytical • 13=ChangeLog • 14=RootCause • 15=PredictiveSignals • 16=MetricRegistry • 17=Reconciliation

## Vendors
[CORTEX_V2.1] Job #2011 — · Vendors
Schema CORTEX_V2.1 · canonical v2 builder · single source of truth
| vendor_id | vendor_name | total_spend | transactions | category | source
Invoices
56
30
5
13
4
3
2
2
2
1
1
1
1
2