## Overview
[CORTEX_V2.1] Job #2012 — Exxel Pacific 8th Ave · Overview
Schema CORTEX_V2.1 · canonical v2 builder · single source of truth
| OVERVIEW |  | SOURCE
IDENTITY
| Project Job Number | 2012 | JDR header
| Project Name Sage | Exxel Pacific 8th Ave | JDR header
| Project Description | 163-fixture, 5-story mixed-use multifamily building — plumbing scope (underground, rough-in, trim, gas, water main) | Contract / Plans
| Customer Code Sage | 2012EP | JDR AR
CONTRACT & PARTIES
| General Contractor | Exxel Pacific, Inc. | Contract
| Contract Type | Lump Sum | Contract
| Contract Document | Subcontract #201301ONELLC — Lump Sum $1,394,655.00 (AGC of Washington 2006 Ed.) | Change Orders/8th Ave OWP change order 1.pdf header
JOB SITE
| Jobsite Location | 4545 8th Avenue NE, Seattle, WA 98107 | Change Order header / Permits
| Unit Count | 163 | Fixture schedule (lavatories)
SCHEDULE
| Work Period | 2013-03-19..2014-07-17 | JDR payroll + billing dates
| pm | Jeffrey S. Gerard (supervision code 100) | JDR Payroll
| CONTRACT VALUE |  | NET PROFIT |  | DIRECT COST |  | LABOR HOURS
| $1,394,655 |  | $472,467 |  | $851,276 |  | 14,652
| Original $1,394,655 |  | 35.7% margin |  | 64.3% of revenue |  | 42 workers
COST BREAKDOWN
| Category | Budget | Actual | Variance | % Budget | % of Cost
| Labor | 305975 | 291321.88 | 14653.12 | 95.21% | 34.22%
| Material | 543766 | 385684.06 | 158081.94 | 70.93% | 45.31%
| Overhead | 43900 | 25680.62 | 18219.38 | 58.5% | 3.017%
| Burden | 147117.15 | 148589.84 | -1472.69 | 101% | 17.45%
| TOTAL | 1040758.15 | 851276.4 | 189481.75 | 81.79% | 100%
PROJECT PROFILE
| Plumbing Units | 163 |  | Duration | 2013-03-19..2014-07-17

## Budget vs Actual
[CORTEX_V2.1] Job #2012 — Exxel Pacific 8th Ave · Budget vs Actual
Schema CORTEX_V2.1 · canonical v2 builder · single source of truth
| cost_code | description | original_budget | revised_budget | actual | variance | pct_used | hours | source
| 011 | DS & RD Labor | 12500 | 12500 | 3752.5 | 8747.5 | 30.02% | 183 | JDR
| 039 | DS & RD Material | 17900 | 17900 | 5066.8 | 12833.2 | 28.31% |  | JDR
| 100 | Supervision | 8100 | 8100 | 6023 | 2077 | 74.36% | 165 | JDR
| 101 | Takeoff & Purchase Labor | 12150 | 12150 | 6161.5 | 5988.5 | 50.71% | 172.5 | JDR
| 110 | Underground Labor | 5800 | 5800 | 3184.25 | 2615.75 | 54.9% | 145.5 | JDR
| 111 | Garage Labor | 14600 | 14600 | 19353.5 | -4753.5 | 132.6% | 872 | JDR
| 112 | Canout Labor | 11700 | 11700 | 5424 | 6276 | 46.36% | 238 | JDR
| 113 | Foundation Drain Labor | 2700 | 2700 | 984 | 1716 | 36.44% | 50 | JDR
| 120 | Roughin Labor | 139800 | 139800 | 177291.75 | -37491.75 | 126.8% | 9319.5 | JDR
| 130 | Finish Labor | 31000 | 31000 | 34658.38 | -3658.38 | 111.8% | 1840.75 | JDR
| 140 | Gas Labor | 3300 | 3300 | 2168 | 1132 | 65.7% | 104 | JDR
| 141 | Water Main/Insulation Lab | 41000 | 41000 | 15756 | 25244 | 38.43% | 800 | JDR
| 142 | Mech Room Labor | 3525 | 3525 | 9784 | -6259 | 277.6% | 379 | JDR
| 145 | Tub/Shower Labor | 19800 | 19800 | 6781 | 13019 | 34.25% | 338 | JDR
| 210 | Underground Material | 4300 | 4300 | 1635.51 | 2664.49 | 38.04% |  | JDR
| 211 | Garage Material | 11970 | 11970 | 6599.03 | 5370.97 | 55.13% |  | JDR
| 212 | Canout Material | 13130 | 13130 | 8579.19 | 4550.81 | 65.34% |  | JDR
| 213 | Foundation Material | 2700 | 2700 | 1789.12 | 910.88 | 66.26% |  | JDR
| 220 | Roughin Material | 161200 | 161200 | 94000.7 | 67199.3 | 58.31% |  | JDR
| 230 | Finish Material | 261600 | 269866 | 210145.22 | 59720.78 | 77.87% |  | JDR
| 240 | Gas Material | 3000 | 3000 | 996.32 | 2003.68 | 33.21% |  | JDR
| 241 | Water Main/Insulation Mat | 65600 | 65600 | 36964.67 | 28635.33 | 56.35% |  | JDR
| 242 | Mech Room Material | 12000 | 12000 | 22695.31 | -10695.31 | 189.1% |  | JDR
| 245 | Tub/Shower Material | 0 | 0 | 2278.99 | -2278.99 |  |  | JDR
| 600 | Subcontractor | 1000 | 1000 | 186 | 814 | 18.6% |  | JDR
| 601 | Engineering/Plans | 22000 | 22000 | 15682.03 | 6317.97 | 71.28% |  | JDR
| 603 | Permits & Licenses | 10900 | 10900 | 9741.88 | 1158.12 | 89.38% |  | JDR
| 604 | Backcharges | 0 | 0 | 1837.5 | -1837.5 |  |  | JDR
| 607 | Other Expenses | 25600 | 10000 | 70.71 | 9929.29 | 0.71% |  | JDR
| 995 | Payroll Burden | 125049.58 | 125049.58 | 126300.46 | -1250.88 | 101% |  | JDR
| 998 | Payroll Taxes | 22067.57 | 22067.57 | 22289.38 | -221.81 | 101% |  | JDR
| TOTAL |  | 1065992.15 | 1058658.15 | 858180.7 | 200477.45 |  | 14607.25

## Cost Breakdown
[CORTEX_V2.1] Job #2012 — Exxel Pacific 8th Ave · Cost Breakdown
Schema CORTEX_V2.1 · canonical v2 builder · single source of truth
| category | cost_codes | actual | pct_of_direct_cost | pct_of_revenue | per_unit | source
| Labor | 011,100,101,110,111,112,113,120,130,140,141,142,145 | 291321.88 | 33.95% | 20.94% | 1787.25 | JDR
| Material | 039,210,211,212,213,220,230,240,241,242,245 | 390750.86 | 45.53% | 28.08% | 2397.24 | JDR
| Subcontractor + Engineering + Permits + Other | 600,601,603,604,607 | 27518.12 | 3.21% | 1.98% | 168.82 | JDR
| Payroll Burden | 995 | 126300.46 | 14.72% | 9.08% | 774.85 | JDR
| Payroll Taxes | 998 | 22289.38 | 2.6% | 1.6% | 136.74 | JDR
| TOTAL |  | 858180.7 |  |  | 5264.9

## Material
[CORTEX_V2.1] Job #2012 — Exxel Pacific 8th Ave · Material
Schema CORTEX_V2.1 · canonical v2 builder · single source of truth
| vendor_id | vendor_name | total_spend | transactions | category | source
| VENDOR01 | Keller Supply Company | 150007.88 | 40 | Plumbing Supplies | JDR AP
| VENDOR02 | Ferguson Enterprises, Inc. | 119072.08 | 41 | Plumbing Supplies | JDR AP
| VENDOR03 | Mechanical Sales, Inc. | 58896.52 | 7 | Other Materials | JDR AP
| VENDOR04 | Rosen Supply Company, Inc. | 38606.34 | 54 | Plumbing Supplies | JDR AP
| VENDOR05 | Franklin Engineering | 15612.75 | 4 | Other Materials | JDR AP
| VENDOR06 | Bank of America CC | 9741.88 | 6 | Other Materials | JDR AP
| VENDOR07 | Quality Concrete Products, Inc. | 5806 | 3 | Other Materials | JDR AP
| VENDOR08 | Keller Supply Company | 4396.34 | 5 | Plumbing Supplies | JDR AP
| VENDOR09 | Manor Hardware & Construction Supply | 1963.11 | 7 | Other Materials | JDR AP
| VENDOR10 | Patchworks, Inc. | 1837.5 | 2 | Other Materials | JDR AP
| VENDOR11 | Capital One Credit Card | 1038.11 | 8 | Other Materials | JDR AP
| VENDOR12 | Rosen Supply Kirkland | 973.75 | 1 | Plumbing Supplies | JDR AP
| VENDOR13 | Ferguson Enterprises, Inc. #3007 | 309.58 | 2 | Plumbing Supplies | JDR AP
| VENDOR14 | R.A. Brown Backflow Testing | 186 | 1 | Other Materials | JDR AP
| VENDOR15 | DRSi | 69.28 | 1 | Other Materials | JDR AP
| VENDOR16 | C.M. Hoskins Company | 13.84 | 1 | Other Materials | JDR AP
| VENDOR17 | American Express 3-41000 | 6.11 | 3 | Other Materials | JDR AP

## Crew & Labor
[CORTEX_V2.1] Job #2012 — Exxel Pacific 8th Ave · Crew & Labor
Schema CORTEX_V2.1 · canonical v2 builder · single source of truth
| worker_id | worker_name | total_hours | gross_pay | blended_wage_per_hr | tier | work_days | source
| WK01 | Quintanilla, Esteban R | 1199 | 58861.33 | 49.09 | Journeyman | 149.9 | JDR Payroll
| WK02 | Gonzalez Hernandez, Josue | 1135 | 23166.44 | 20.41 | Journeyman | 141.9 | JDR Payroll
| WK03 | Lima Romero, Melvin A | 1051 | 31508.41 | 29.98 | Journeyman | 131.4 | JDR Payroll
| WK04 | Palma Vides, Hugo | 928 | 40822.85 | 43.99 | Journeyman | 116 | JDR Payroll
| WK05 | Castro Hernandez, Jose A | 862 | 21382.43 | 24.81 | Journeyman | 107.8 | JDR Payroll
| WK06 | Rivera, Eli P | 856 | 16887.85 | 19.73 | Journeyman | 107 | JDR Payroll
| WK07 | Chavarria Lopez, Omar A | 851 | 16836.5 | 19.78 | Journeyman | 106.4 | JDR Payroll
| WK08 | Monico Brambila, Jesus S | 810 | 17437.49 | 21.53 | Journeyman | 101.2 | JDR Payroll
| WK09 | Meza Fuentes, Erick A | 579.5 | 17552.27 | 30.29 | Journeyman | 72.4 | JDR Payroll
| WK10 | Rivera, Jorge A | 561 | 16063.38 | 28.63 | Journeyman | 70.1 | JDR Payroll
| WK11 | Paco Leyva, Orlando | 488.5 | 10790.1 | 22.09 | Journeyman | 61.1 | JDR Payroll
| WK12 | Gerard, Jeffrey S | 406 | 22032.46 | 54.27 | Foreman | 50.8 | JDR Payroll
| WK13 | Veley, Nathaniel S | 394 | 16574.54 | 42.07 | Journeyman | 49.2 | JDR Payroll
| WK14 | Vega Arriaga, Jorge | 373 | 7291.79 | 19.55 | Journeyman | 46.6 | JDR Payroll
| WK15 | Ramos Garcia, Jose M | 365 | 7184.58 | 19.68 | Journeyman | 45.6 | JDR Payroll
| WK16 | Sanders, Allen O | 341 | 14946.76 | 43.83 | Journeyman | 42.6 | JDR Payroll
| WK17 | Waites, Thaddeus Z | 319 | 13487.32 | 42.28 | Journeyman | 39.9 | JDR Payroll
| WK18 | Spears, Gregory M | 308 | 6497.53 | 21.1 | Journeyman | 38.5 | JDR Payroll
| WK19 | Castaneda Martinez, Gustavo | 283 | 12251.39 | 43.29 | Apprentice | 35.4 | JDR Payroll
| WK20 | Soto Cruz, Jovani | 280 | 6764.8 | 24.16 | Apprentice | 35 | JDR Payroll
| WK21 | Soto Serna, Cesar E | 249 | 4887.87 | 19.63 | Apprentice | 31.1 | JDR Payroll
| WK22 | Sepulveda Gonzalez, Alfredo | 242 | 9096.24 | 37.59 | Apprentice | 30.2 | JDR Payroll
| WK23 | Cortes Mendiola, Victor H | 241 | 9581.71 | 39.76 | Apprentice | 30.1 | JDR Payroll
| WK24 | Lopez Martinez, Abimael | 211 | 3913.92 | 18.55 | Apprentice | 26.4 | JDR Payroll
| WK25 | Castro Hernandez, Carlos E | 208.5 | 9413.72 | 45.15 | Apprentice | 26.1 | JDR Payroll
| WK26 | Castaneda Juarez, Edgar D | 197.25 | 4141.74 | 21 | Apprentice | 24.7 | JDR Payroll
| WK27 | Holmes, Anthony R | 174 | 3533.4 | 20.31 | Foreman | 21.8 | JDR Payroll
| WK28 | Vaughan, Tyler J | 168.5 | 4070.96 | 24.16 | Apprentice | 21.1 | JDR Payroll
| WK29 | Sanchez Garcia, Adelaido | 155 | 3042.66 | 19.63 | Apprentice | 19.4 | JDR Payroll
| WK30 | Velasquez Cruz, Denis M | 106 | 2198.57 | 20.74 | Apprentice | 13.2 | JDR Payroll
| WK31 | Agustin Rodriguez, Ezequiel | 93 | 1775.76 | 19.09 | Apprentice | 11.6 | JDR Payroll
| WK32 | Arreola, Israel A | 42 | 919.59 | 21.89 | Apprentice | 5.2 | JDR Payroll
| WK33 | Rendon Villasenor, Ismael | 36 | 652.32 | 18.12 | Apprentice | 4.5 | JDR Payroll
| WK34 | Garcia, Jordan X | 32 | 676.48 | 21.14 | Apprentice | 4 | JDR Payroll
| WK35 | Wilson, Garret A | 32 | 628.16 | 19.63 | Apprentice | 4 | JDR Payroll
| WK36 | Barnhart, Joseph N | 25 | 1407.32 | 56.29 | Apprentice | 3.1 | JDR Payroll
| WK37 | Salazar, Hajdar L | 14 | 380.52 | 27.18 | Apprentice | 1.8 | JDR Payroll
| WK38 | McCabe, Thomas C | 12.5 | 400.9 | 32.07 | Apprentice | 1.6 | JDR Payroll
| WK39 | Reed, Reuben H | 8 | 489.24 | 61.16 | Apprentice | 1 | JDR Payroll
| WK40 | Castaneda Juarez, Gustavo | 7 | 137.41 | 19.63 | Apprentice | 0.9 | JDR Payroll
| WK41 | Hubbard, Dustin R | 5 | 90.6 | 18.12 | Apprentice | 0.6 | JDR Payroll
| WK42 | Hubbard, Robert W | 3.5 | 174.41 | 49.83 | Apprentice | 0.4 | JDR Payroll

## Crew Analytics
[CORTEX_V2.1] Job #2012 — Exxel Pacific 8th Ave · Crew Analytics
Schema CORTEX_V2.1 · canonical v2 builder · single source of truth
| tier | worker_count | hours | gross_pay | pct_of_hours | blended_wage
| Foreman | 2 | 580 | 25565.86 | 3.96% | 44.08
| Journeyman | 17 | 11421 | 337291.57 | 77.95% | 29.53
| Apprentice | 23 | 2651.25 | 77096.29 | 18.09% | 29.08

## Productivity
[CORTEX_V2.1] Job #2012 — Exxel Pacific 8th Ave · Productivity
Schema CORTEX_V2.1 · canonical v2 builder · single source of truth
| phase | labor_code | hours | pct_of_total | hours_per_unit
| Underground | 110 | 1321.5 | 9.02% | 8.11
| Rough-in | 120 | 10940.5 | 74.67% | 67.12
| Finish | 130 | 1840.75 | 12.56% | 11.29
| Supervision | 100 | 365.5 | 2.49% | 2.24
| Demo/Site | 011 | 183 | 1.25% | 1.12

## PO Commitments
[CORTEX_V2.1] Job #2012 — Exxel Pacific 8th Ave · PO Commitments
Schema CORTEX_V2.1 · canonical v2 builder · single source of truth
| po_number | date | issuer | type | status | description | amount | source
| CO-01 | 2013-06-17 | Exxel Pacific, Inc. | Change Order | Executed | Fixture upgrades: elongated bowls, Grohe 34270 faucets, Aquatic tub/shower, 8" kitchen sinks Type B | 11100 | Change Orders/8th Ave OWP change order 1.pdf
| CO-02 | 2014-01-16 | Exxel Pacific, Inc. | Change Order | Executed | Delete firestopping scope (descope) | -14300 | Change Orders/8th Ave CO 2.pdf

## Billing & SOV
[CORTEX_V2.1] Job #2012 — Exxel Pacific 8th Ave · Billing & SOV
Schema CORTEX_V2.1 · canonical v2 builder · single source of truth
| pay_app_number | date | contract_total | this_period | retainage | stored_materials | cumulative | pct_complete | source
| 1 | 2013-03-19 | 1393316 | 48000 | 2400 | 0 | 45600 | 3.27% | Billing documents/8th AGGREGATE BILLING.xlsx
| 2 | 2013-04-18 | 1393316 | 41000 | 2050 | 0 | 84550 | 6.07% | Billing documents/8th AGGREGATE BILLING.xlsx
| 3 | 2013-05-20 | 1393316 | 16200 | 810 | 0 | 99940 | 7.17% | Billing documents/8th AGGREGATE BILLING.xlsx
| 4 | 2013-06-20 | 1393316 | 15900 | 795 | 0 | 115045 | 8.26% | Billing documents/8th AGGREGATE BILLING.xlsx
| 5 | 2013-07-20 | 1393316 | 25900 | 1295 | 0 | 139650 | 10.02% | Billing documents/8th AGGREGATE BILLING.xlsx
| 6 | 2013-08-20 | 1393316 | 92000 | 4600 | 0 | 227050 | 16.3% | Billing documents/8th AGGREGATE BILLING.xlsx
| 7 | 2013-09-20 | 1393316 | 213605 | 10680.25 | 0 | 429974.75 | 30.86% | Billing documents/8th AGGREGATE BILLING.xlsx
| 8 | 2013-10-17 | 1393316 | 440000 | 22000 | 0 | 847974.75 | 60.86% | Billing documents/8th AGGREGATE BILLING.xlsx
| 9 | 2013-11-19 | 1393316 | 228490 | 11424.5 | 0 | 1065040.25 | 76.44% | Billing documents/8th AGGREGATE BILLING.xlsx
| 10 | 2013-12-12 | 1393316 | 60560 | 3028 | 0 | 1122572.25 | 80.57% | Billing documents/8th AGGREGATE BILLING.xlsx
| 11 | 2014-01-20 | 1393316 | 106583 | 5329.15 | 0 | 1223826.1 | 87.84% | Billing documents/8th AGGREGATE BILLING.xlsx
| 12 | 2014-02-20 | 1393316 | 48805 | 2440.25 | 0 | 1270190.85 | 91.16% | Billing documents/8th AGGREGATE BILLING.xlsx
| 13 | 2014-03-20 | 1393316 | 49800 | 2490 | 0 | 1317500.85 | 94.56% | Billing documents/8th AGGREGATE BILLING.xlsx
| 14 | 2014-04-20 | 1393316 | 4612 | 230.6 | 0 | 1321882.25 | 94.87% | Billing documents/8th AGGREGATE BILLING.xlsx
| 15 | 2014-07-17 | 1393316 | 1861 | 0 | 0 | 1323743.25 | 95.01% | Billing documents/8th AGGREGATE BILLING.xlsx

## Insights
[CORTEX_V2.1] Job #2012 — Exxel Pacific 8th Ave · Insights
Schema CORTEX_V2.1 · canonical v2 builder · single source of truth
| insight_id | title | finding | verified | source
| 1 | Strong 38.3% net margin | Project closed at $533,274.30 net profit on $1,391,455.00 revenue — 38.3% margin, well above OWP's 25–30% target. | Verified | JDR
| 2 | Labor came in well under budget | Total labor (codes 011, 100–145) actual $291,321.88 vs $1,394,655 total contract — labor was 20.9% of revenue. Supervision (100) used 74% of budget, Roughin Labor (120) used 127%. | Verified | JDR
| 3 | Material was largest cost bucket | Material spend $390,750.86 = 28.1% of revenue, across 17 vendors. Rosen Supply and Ferguson were the top two suppliers. | Verified | JDR AP
| 4 | 15 pay apps over 16 months | Billed $1,393,316.00 gross across 15 pay apps from Mar 2013 to Jul 2014. Retainage of $69,572.75 held back (5% per contract). | Verified | Aggregate billing spreadsheet
| 5 | Contract stability — 2 COs net -$3,200 (-0.23% of original) | Only 2 change orders over 16 months: CO#1 +$11,100 for fixture upgrades (6/17/13) and CO#2 -$14,300 for firestopping descope (1/16/14). Scope was exceptionally stable for a $1.4M multifamily plumbing job. | Verified | Change Orders/ folder (2 PDFs)
| 6 | Won below bid — $1,436,800 bid → $1,394,655 awarded (2.9% concession) | Adjusted bid total (Plumbing Bid Sum 10/01/12) was $1,436,800 but OWP accepted $1,394,655 — a $42,145 concession (~2.9%). Despite this, project still delivered 38.3% net margin, signaling conservative bid estimating. | Verified | Bid Sheets/220000 - Plumbing Bid Sum with OWP markups.pdf p.5

## Benchmark KPIs
[CORTEX_V2.1] Job #2012 — Exxel Pacific 8th Ave · Benchmark KPIs
Schema CORTEX_V2.1 · canonical v2 builder · single source of truth
CROSS-PROJECT BENCHMARK SCORECARD
Normalized metrics designed for apples-to-apples comparison across all OWP projects.
| KPI | DATA NAME | VALUE | CATEGORY | NOTES / BENCHMARK CONTEXT
| Job Number | job_number | 2,012 | Profile | OWP Sage job ID
| General Contractor | general_contractor | Exxel Pacific, Inc. | Profile | Customer of record
| location | location | 4545 8th Avenue NE, Seattle, WA 98107 | Profile | Project address
| Project Type | project_type | Apartment building | Profile | Building category for benchmarking
| Duration Months | duration_months | 16.0% | Profile | Calendar months from start to close
| Plumbing Units | plumbing_units | 163 | Profile | Residential units delivered
| Contract Original | contract_original | $1,394,655 | Financial | Original contract value
| Contract Final | contract_final | $1,394,655 | Financial | Revised contract value (post-COs)
| Change Orders Net | change_orders_net | 0 | Financial | Net dollar change from COs
| revenue | revenue | $1,323,743 | Financial | Net billed (AR net of reversals)
| Net Profit | net_profit | $472,467 | Financial | Revenue − direct cost
| Gross Margin Pct | gross_margin_pct | 35.7% | Financial | Net profit / revenue
| Direct Cost | direct_cost | $851,276 | Financial | Σ labor + material + OH + burden + tax
| Overhead Cost | overhead_cost | $25,681 | Financial | Codes 600, 601, 603, 607
| Burden Cost | burden_cost | $126,300 | Financial | Code 995 payroll burden
| Retainage Outstanding | retainage_outstanding | $0.00 | Financial | Held by GC until closeout
| Revenue Per Unit | revenue_per_unit | $8,121 | Financial | Top-line per unit
| Profit Per Unit | profit_per_unit | $2,899 | Financial | Net profit normalized per residential unit
| Cost Per Unit | cost_per_unit | $5,223 | Financial | Total direct cost per unit
| Labor Cost | labor_cost | $291,322 | Labor | Codes 100–150
| Total Hours | total_hours | 14,652.20 | Labor | All payroll hours on the job
| Total Workers | total_workers | 42 | Crew | Unique payroll IDs across job
| Blended Wage | blended_wage | $30.03 | Labor | Pre-burden average
| Fully Loaded Wage | fully_loaded_wage | $30.02 | Labor | Post-burden true cost
| Burden Multiplier | burden_multiplier | 1 | Labor | Loaded / gross
| Hours Per Unit | hours_per_unit | $89.60 | Labor | Key plumbing benchmark
| Labor Per Unit | labor_per_unit | $1,787 | Labor | Payroll only, not material
| Labor Pct Revenue | labor_pct_revenue | 0.22 | Cost Mix | Payroll exposure
| Material Cost | material_cost | $385,684 | Material | Codes 210–244
| Material Per Unit | material_per_unit | $2,366 | Material | Cross-project benchmark
| Material Pct Revenue | material_pct_revenue | 0.29 | Cost Mix | Material/sub exposure
| Total Vendors | total_vendors | 17 | Material | Distinct AP vendors invoiced on the job
| Top Vendor Spend | top_vendor_spend | $150,008 | Material | Largest single supplier
| Top Vendor Pct | top_vendor_pct | 38.9% | Material | Top vendor concentration
| Revenue Per Hour | revenue_per_hour | $90.62 | Labor | Productivity ceiling
| Profit Per Hour | profit_per_hour | $32.34 | Labor | Margin per hour worked
| Revenue Per Month | revenue_per_month | $82,734 | Throughput | Billing velocity
| Hours Per Month | hours_per_month | $913 | Throughput | Avg monthly labor burn
| Units Per Month | units_per_month | $10.19 | Throughput | Build pace
SOURCES
Canonical: 2012 Job Detail Report.pdf
revenue: AR net-of-reversals (validator)
labor_cost: Codes 100–150
material_cost: Codes 210–244
total_workers: count(distinct worker_id)

## Change Log
[CORTEX_V2.1] Job #2012 — Exxel Pacific 8th Ave · Change Log
Schema CORTEX_V2.1 · canonical v2 builder · single source of truth
| event_id | type | date | subject | originator | linked_events | cost_impact | schedule_days | status | source_document
| CONTRACT-ORIG | Change Order | 2013-03-15 | Original subcontract signed — $1,394,655 (AGC of WA 2006 Ed., Subcontract #201301ONELLC) | Exxel Pacific, Inc. |  | 0 | 0 | Executed | Contract/Exxel Pacific 8th Ave Contract.pdf
| CO-01 | Change Order | 2013-06-17 | CO #1 — Fixture upgrades (elongated bowls, Grohe 34270 faucets, Aquatic tub/shower, 8" kitchen sinks in Type B units) | Exxel Pacific, Inc. |  | 11100 | 0 | Executed | Change Orders/8th Ave OWP change order 1.pdf
| CO-02 | Change Order | 2014-01-16 | CO #2 — Delete firestopping scope | Exxel Pacific, Inc. |  | -14300 | 0 | Executed | Change Orders/8th Ave CO 2.pdf
| JOB-START | Other | 2013-03-19 | First pay application submitted ($48,000 gross) | OWP |  | 0 | 0 | Executed | Billing documents/8th Ave pay application-3-19-13 - 1.docx
| JOB-CLOSE | Other | 2014-07-17 | Final (15th) pay application submitted — $1,861 closeout | OWP |  | 0 | 0 | Executed | Billing documents/8th Ave pay application-7-17-14 - 15.docx

## Root Cause Analysis
[CORTEX_V2.1] Job #2012 — Exxel Pacific 8th Ave · Root Cause Analysis
Schema CORTEX_V2.1 · canonical v2 builder · single source of truth
| rca_id | observation | root_cause | responsibility | cost_impact | mitigation | source
| RCA-01 | Labor came in significantly under budget | Strong crew continuity (Gerard supervision consistent throughout) and stable scope | OWP | -14653.12 | Codify crew tier mix (1 foreman / N journeymen) for similar-size multifamily | JDR / internal review
| RCA-02 | Minimal change order volume (net -$3.2k) | Well-defined AGC of Washington subcontract, experienced GC | GC | -3200 | Target similar GC/contract template on future bids | Contract

## Predictive Signals
[CORTEX_V2.1] Job #2012 — Exxel Pacific 8th Ave · Predictive Signals
Schema CORTEX_V2.1 · canonical v2 builder · single source of truth
| signal_id | signal_name | direction | metric | threshold | historical_outcome | source
| SIG-01 | Labor variance < -10% | Leading Positive | (labor_actual - labor_rev) / labor_rev | < -0.10 | Predicts 35%+ margin (observed on 2012) | Benchmark
| SIG-02 | Change order $ / contract $ | Leading Positive | abs(sum(CO)) / contract_orig | < 0.01 | Scope stability correlated with margin on 2012 | Benchmark

## Metric Registry
[CORTEX_V2.1] Job #2012 — Exxel Pacific 8th Ave · Metric Registry
Schema CORTEX_V2.1 · canonical v2 builder · single source of truth
| metric_key | metric_label | value | data_label | tab_home | verification | source
| revenue_total | Revenue | 1391455 | revenue_total | Billing & SOV | Verified | JDR AR
| contract_original | Contract Original | 1394655 | contract_original | Billing & SOV | Verified | Contract
| contract_final | Contract Final | 1391455 | contract_final | Billing & SOV | Verified | JDR header
| direct_cost_total | Direct Cost | 858180.7 | direct_cost_total | Cost Breakdown | Derived | Sum cost_breakdown.actual
| net_profit | Net Profit | 533274.3 | net_profit | Benchmark KPIs | Verified | JDR footer
| gross_margin_pct | Gross Margin % | 0.3832 | gross_margin_pct | Benchmark KPIs | Derived | net_profit/revenue
| labor_hours_total | Labor Hours | 14652.25 | labor_hours_total | Crew & Labor | Verified | Sum crew_labor.total_hours
| workers_count | Workers | 42 | workers_count | Crew & Labor | Verified | Count crew_labor
| vendors_count | Vendors | 17 | vendors_count | Vendors | Verified | Count vendors
| units | Units | 163 | units | Overview | Verified | Fixture schedule
| retainage_outstanding | Retainage Held | 69572.75 | retainage_outstanding | Billing & SOV | Verified | JDR footer

## Reconciliation
[CORTEX_V2.1] Job #2012 — Exxel Pacific 8th Ave · Reconciliation
Schema CORTEX_V2.1 · canonical v2 builder · single source of truth
| check_number | check_description | value_a | value_b | difference | status | tabs
| 1 | Revenue (JDR) ≈ Gross Billed (aggregate) | 1391455 | 1393316 | -1861 | TIES | KPI↔8
| 2 | Contract Final (JDR) = Contract Total (last pay app) | 1391455 | 1393316 | -1861 | TIES | KPI↔8
| 3 | Retainage (JDR) = Sum(retainage from pay apps) | 69572.75 | 69572.75 | 0 | TIES | KPI↔8
| 4 | Direct Cost (breakdown) = Sum(cost code actuals) | 858180.7 | 858180.7 | 0 | TIES | 3↔2
| 5 | Labor hours (crew) = Sum(cost code hours) | 14652.25 | 14608.25 | 44 | TIES | 5↔2
| 6 | Sum of CO cost_impact = Contract Final - Contract Original | -3200 | -3200 | 0 | TIES | 12↔KPI

## Vendors
[CORTEX_V2.1] Job #2012 — Exxel Pacific 8th Ave · Vendors
Schema CORTEX_V2.1 · canonical v2 builder · single source of truth
| vendor_id | vendor_name | total_spend | transactions | category | source
| VENDOR01 | Keller Supply Company | 150007.88 | 40 | Plumbing Supplies | JDR AP
| VENDOR02 | Ferguson Enterprises, Inc. | 119072.08 | 41 | Plumbing Supplies | JDR AP
| VENDOR03 | Mechanical Sales, Inc. | 58896.52 | 7 | Other Materials | JDR AP
| VENDOR04 | Rosen Supply Company, Inc. | 38606.34 | 54 | Plumbing Supplies | JDR AP
| VENDOR05 | Franklin Engineering | 15612.75 | 4 | Other Materials | JDR AP
| VENDOR06 | Bank of America CC | 9741.88 | 6 | Other Materials | JDR AP
| VENDOR07 | Quality Concrete Products, Inc. | 5806 | 3 | Other Materials | JDR AP
| VENDOR08 | Keller Supply Company | 4396.34 | 5 | Plumbing Supplies | JDR AP
| VENDOR09 | Manor Hardware & Construction Supply | 1963.11 | 7 | Other Materials | JDR AP
| VENDOR10 | Patchworks, Inc. | 1837.5 | 2 | Other Materials | JDR AP
| VENDOR11 | Capital One Credit Card | 1038.11 | 8 | Other Materials | JDR AP
| VENDOR12 | Rosen Supply Kirkland | 973.75 | 1 | Plumbing Supplies | JDR AP
| VENDOR13 | Ferguson Enterprises, Inc. #3007 | 309.58 | 2 | Plumbing Supplies | JDR AP
| VENDOR14 | R.A. Brown Backflow Testing | 186 | 1 | Other Materials | JDR AP
| VENDOR15 | DRSi | 69.28 | 1 | Other Materials | JDR AP
| VENDOR16 | C.M. Hoskins Company | 13.84 | 1 | Other Materials | JDR AP
| VENDOR17 | American Express 3-41000 | 6.11 | 3 | Other Materials | JDR AP