## Overview
[CORTEX_V2.1] Job #2015 — · Overview
Schema CORTEX_V2.1 · canonical v2 builder · single source of truth
| OVERVIEW |  | SOURCE
IDENTITY
| Project Job Number | 2015
| Project Name: | Exxel Pacific Rooster Apts + Portage Bay Cafe
CONTRACT & PARTIES
| General Contractor | Exxel Pacific, Inc.
JOB SITE
| Jobsite Location | Seattle, WA
| Plumbing Units | 197 | Kitchen Sinks
| Floors | 6 | Duration
SCHEDULE
| Project Duration | Apr 2014 – Nov 2015 (~25 months)
SCOPE & DESIGN
| Total Fixtures | 1,349 | Dishwashers
| Fixtures / Unit | 6.85 | Auto Washers
| CONTRACT VALUE |  | NET PROFIT |  | DIRECT COST |  | LABOR HOURS
| $2,002,285 |  | $563,703 |  | $1,583,005 |  | 51,911
| Original $2,002,285 |  | 26.3% margin |  | 73.7% of revenue |  | 60 workers
COST BREAKDOWN
| Category | Budget | Actual | Variance | % Budget | % of Cost
| Labor | 479050 | 583482.62 | -104432.62 | 121.8% | 36.86%
| Material | 866894 | 661468.33 | 205425.67 | 76.3% | 41.79%
| Overhead | 34425 | 43335.38 | -8910.38 | 125.9% | 2.738%
| Burden | 242802.91 | 294718.23 | -51915.32 | 121.4% | 18.62%
| TOTAL | 1623171.91 | 1583004.56 | 40167.35 | 97.53% | 100%
PROJECT PROFILE
| Plumbing Units | 197 |  | Total Fixtures | 1,349 |  | Fixtures / Unit | 0.01
| Floors | 6 |  | Duration | Apr 2014 – Nov 2015 (~25 months)

## Budget vs Actual
[CORTEX_V2.1] Job #2015 — · Budget vs Actual
Schema CORTEX_V2.1 · canonical v2 builder · single source of truth
| cost_code | description | original_budget | revised_budget | actual | variance | pct_used | hours | source
LABOR
| 100 | Supervision | 11820 | 12360 | 7355 | 5005 | 59.51%
| 101 | Takeoff & Purchase Labor | 13790 | 15790 | 16582.5 | -792.5 | 1.05%
| 110 | Underground Labor | 6080 | 7830 | 7731 | 99 | 98.74%
| 111 | Garage Labor | 55870 | 67410 | 50128.5 | 17281.5 | 74.36%
| 112 | Canout Labor | 12300 | 12860 | 10087.5 | 2772.5 | 78.44%
| 113 | Foundation Drain Labor | 520 | 520 | 520.5 | -0.5 | 1.001%
| 120 | Roughin Labor | 244060 | 261060 | 387658.09 | -126598.09 | 1.485%
| 130 | Finish Labor | 41255 | 45665 | 45395.28 | 269.72 | 99.41%
| 140 | Gas Labor | 7250 | 11400 | 11582.5 | -182.5 | 1.016%
| 141 | Water Main/Insulation Lab | 29805 | 35505 | 37466.75 | -1961.75 | 1.055%
| 142 | Mech Room Labor | 5280 | 8650 | 8975 | -325 | 1.038%
MATERIAL
| 210 | Underground Material | 9825 | 9385 | 7557.66 | 1827.34 | 80.53%
| 211 | Garage Material | 59640 | 63870 | 41623.99 | 22246.01 | 65.17%
| 212 | Canout Material | 17220 | 17700 | 13825.36 | 3874.64 | 78.11%
| 213 | Foundation Material | 1275 | 1275 | 1275.6 | -0.6 | 1%
| 220 | Roughin Material | 210065 | 212365 | 176561.56 | 35803.44 | 83.14%
| 230 | Finish Material | 466740 | 483149 | 337546.71 | 145602.29 | 69.86%
| 240 | Gas Material | 3350 | 6250 | 6984.66 | -734.66 | 1.118%
| 241 | Water Main/Insulation Mat | 60900 | 60900 | 46749.33 | 14150.67 | 76.76%
| 242 | Mech Room Material | 12000 | 12000 | 29343.46 | -17343.46 | 2.445%
OVERHEAD
| 600 | Subcontractor | 25125 | 27425 | 36287 | -8862 | 1.323%
| 601 | Engineering/Plans | 2000 | 2000 | 7038.38 | -5038.38 | 3.519%
| 603 | Permits & Licenses | 5000 | 5000 | 10 | 4990 | 0.2%
BURDEN
| 995 | Payroll Burden | 183990.41 | 206430.98 | 249836.89 | -43405.91 | 1.21%
| 998 | Payroll Taxes | 32468.9 | 36371.93 | 44881.34 | -8509.41 | 1.234%
SOURCES
Job #2015 — Exxel Pacific Rooster Apartments + Portage Bay Cafe • GC: Exxel Pacific, Inc.
Canonical source: 2015 Job Detail Report.pdf (255 pages, OWP Sage Timberline export)
Cost codes parsed: 26 (Labor+Material+Overhead+Burden+Revenue)
Billing: ROOSTER AGGREGATE BILLING.xlsx (18 apps) + PORTAGE BAY AGGREGATE BILLING.xlsx (2 apps)
| TOTAL |  | 1517629.31 | 1623171.91 | 1583004.56 | 40167.35 |  | 0

## Cost Breakdown
[CORTEX_V2.1] Job #2015 — · Cost Breakdown
Schema CORTEX_V2.1 · canonical v2 builder · single source of truth
| category | cost_codes | actual | pct_of_direct_cost | pct_of_revenue | per_unit | source
| Labor | 11 | 479050 | 1.218% |  | 2961.8407
| Material | 9 | 866894 | 76.3% |  | 3357.7073
| Overhead | 3 | 34425 | 1.259% |  | 219.9765
| Burden | 2 | 242802.91 | 1.214% |  | 1496.0316
B. LARGEST OVERRUNS (Actual > Revised Budget)
| Code | Description
| 120 | Roughin Labor | 261060 | 48.49%
| 995 | Payroll Burden | 206430.98 | 21.03%
| 242 | Mech Room Material | 12000 | 1.445%
| 600 | Subcontractor | 27425 | 32.31%
| 998 | Payroll Taxes | 36371.93 | 23.4%
| 601 | Engineering/Plans | 2000 | 2.519%
| 141 | Water Main/Insulation Lab | 35505 | 5.525%
| 101 | Takeoff & Purchase Labor | 15790 | 5.019%
| 240 | Gas Material | 6250 | 11.75%
| 142 | Mech Room Labor | 8650 | 3.757%
C. LARGEST SAVINGS (Actual < Revised Budget)
| Code | Description
| 230 | Finish Material | 483149 | 30.14%
| 220 | Roughin Material | 212365 | 16.86%
| 211 | Garage Material | 63870 | 34.83%
| 111 | Garage Labor | 67410 | 25.64%
| 241 | Water Main/Insulation Mat | 60900 | 23.24%
| 100 | Supervision | 12360 | 40.49%
| 603 | Permits & Licenses | 5000 | 99.8%
| 212 | Canout Material | 17700 | 21.89%
| 112 | Canout Labor | 12860 | 21.56%
| 210 | Underground Material | 9385 | 19.47%
SOURCES
Job #2015 — Exxel Pacific Rooster Apartments + Portage Bay Cafe • GC: Exxel Pacific, Inc.
Canonical source: 2015 Job Detail Report.pdf (255 pages, OWP Sage Timberline export)
Cost codes parsed: 26 (Labor+Material+Overhead+Burden+Revenue)
Billing: ROOSTER AGGREGATE BILLING.xlsx (18 apps) + PORTAGE BAY AGGREGATE BILLING.xlsx (2 apps)
| TOTAL |  | 3179653.82 |  |  | 8035.5561

## Material
[CORTEX_V2.1] Job #2015 — · Material
Schema CORTEX_V2.1 · canonical v2 builder · single source of truth
| vendor_id | vendor_name | total_spend | transactions | category | source
| 210 | Underground Material | 9385 |  | 0.011426
| 211 | Garage Material | 63870 |  | 0.062927
| 212 | Canout Material | 17700 |  | 0.020901
| 213 | Foundation Material | 1275 |  | 0.0019284
| 220 | Roughin Material | 212365 |  | 0.26692
| 230 | Finish Material | 483149 |  | 0.5103
| 240 | Gas Material | 6250 |  | 0.010559
| 241 | Water Main/Insulation Mat | 60900 |  | 0.070675
| 242 | Mech Room Material | 12000 |  | 0.044361
B. VENDORS BY SPEND (AP)
| Vendor | # Invoices
| Rosen Supply Company, Inc. | 89 | 192671.23
| Ferguson Enterprises, Inc. | 80 | 153391.68
| Keller Supply Company | 82 | 127204.94
| Mechanical Sales, Inc. | 3 | 67768.3
| Franklin Engineering | 11 | 44962.5
| Lotus United, LLC | 5 | 31310
| Duraseal, Inc. | 4 | 30250
| Consolidated Supply Co. | 22 | 26432.13
| American Express 3-41000 | 6 | 23106
| Bank of America CC | 7 | 12653
| Quality Concrete Products, Inc. | 6 | 8279
| United Rentals, Inc. | 10 | 5848.82
| Manor Hardware & Construction Supply | 6 | 3895
| Scan2Core, Inc. | 3 | 3080
| MAD Concrete Cutting & Coring, Inc. | 3 | 2700
| Ferguson Enterprises, Inc. #3007 | 5 | 2674.97
| Capital One Credit Card | 7 | 2315.27
| Kele, Inc | 5 | 715.13
| C.M. Hoskins Company | 1 | 606.32
| Core & Main LP | 4 | 432.88
| Fastenal Company | 5 | 352.83
| Rosen Supply Kirkland | 1 | 257.4
| A.R. Brown Backflow Testing | 2 | 257
| Seton Identification Products | 1 | 108.97
SOURCES
Job #2015 — Exxel Pacific Rooster Apartments + Portage Bay Cafe • GC: Exxel Pacific, Inc.
Canonical source: 2015 Job Detail Report.pdf (255 pages, OWP Sage Timberline export)
Cost codes parsed: 26 (Labor+Material+Overhead+Burden+Revenue)
Billing: ROOSTER AGGREGATE BILLING.xlsx (18 apps) + PORTAGE BAY AGGREGATE BILLING.xlsx (2 apps)
Vendor AP ties to JDR 'by Source: AP' line (741,273.37)

## Crew & Labor
[CORTEX_V2.1] Job #2015 — · Crew & Labor
Schema CORTEX_V2.1 · canonical v2 builder · single source of truth
| worker_id | worker_name | total_hours | gross_pay | blended_wage_per_hr | tier | work_days | source
| Palma Vides, Hugo |  | 1772 | 52380 | 29.5598 | Mid
| Velasquez Cruz, Denis M |  | 1400 | 22434 | 16.0243 | Apprentice
| Lima Romero, Melvin A |  | 1318.5 | 28491.5 | 21.609 | Mid
| Hubbard, Robert W |  | 1202.5 | 42720.5 | 35.5264 | Senior
| Galdamez, Dagoberto A |  | 1179 | 15914 | 13.4979 | Apprentice
| Cruz Reyes, Jose |  | 1115 | 14866 | 13.3327 | Apprentice
| Amaya Gonzalez, Edilberto A |  | 1113 | 14840 | 13.3333 | Apprentice
| Castro Hernandez, Jose A |  | 1077 | 20560 | 19.0901 | Mid
| Esparza Jimenez, Jose D |  | 979.5 | 19581.5 | 19.9913 | Mid
| Chavarria Lopez, Omar A |  | 957.5 | 14410 | 15.0496 | Apprentice
| Benites Portillo, Marvin E |  | 927 | 12051 | 13 | Apprentice
| Lovo, German G |  | 863 | 11471.5 | 13.2926 | Apprentice
| Palma Vides, Jorge A |  | 788 | 10427 | 13.2322 | Apprentice
| Sepulveda Gonzalez, Alfredo |  | 679.5 | 17707 | 26.0589 | Mid
| McCabe, Thomas C |  | 674.5 | 13982 | 20.7294 | Mid
| Gonzalez Hernandez, Josue |  | 664.5 | 11227.5 | 16.8962 | Apprentice
| Rodriguez Rodriguez, Aminadab N |  | 663 | 8660 | 13.0618 | Apprentice
| Sanders, Allen O |  | 614.5 | 20278.5 | 33 | Senior
| Rivera, Jorge A |  | 598.5 | 12145 | 20.2924 | Mid
| Rodriguez Bonilla, Lisandro |  | 566 | 7370 | 13.0212 | Apprentice
| Quintanilla, Esteban R |  | 543 | 17960 | 33.0755 | Senior
| Vaughan, Tyler J |  | 531 | 9091 | 17.1205 | Apprentice
| Anzora, William |  | 491 | 7074 | 14.4073 | Apprentice
| Castaneda Martinez, Gustavo |  | 474.5 | 14162.5 | 29.8472 | Mid
| Gerard, Jeffrey S |  | 459.5 | 18221 | 39.654 | Senior
| Eliassen, Cory H |  | 428 | 5564 | 13 | Apprentice
| Holmes, Anthony R |  | 315.5 | 4969.5 | 15.7512 | Apprentice
| Walker, Craig M |  | 278 | 4170 | 15 | Apprentice
| Reyes Cruz, Denis A |  | 276.5 | 3895 | 14.0868 | Apprentice
| Ascencio, Jose L |  | 268 | 3484 | 13 | Apprentice
| Cruz Guzman, Joel A |  | 267 | 3471 | 13 | Apprentice
| Meza Fuentes, Erick A |  | 238 | 5410 | 22.7311 | Mid
| Reyes, Robert J |  | 200 | 3000 | 15 | Apprentice
| Soto Cruz, Jovani |  | 184 | 3304 | 17.9565 | Apprentice
| Donelson, Richard T |  | 148.5 | 6682.5 | 45 | Senior
| Barnhart, Joseph N |  | 143.5 | 4466.5 | 31.1254 | Senior
| Cortes Mendiola, Victor H |  | 136 | 3808 | 28 | Mid
| Kinssies, Jr, John E |  | 135 | 2112 | 15.6444 | Apprentice
| Wilson, Garret A |  | 133.5 | 1889.5 | 14.1536 | Apprentice
| Hubbard, Dustin R |  | 133.5 | 1778.5 | 13.3221 | Apprentice
| Salazar, Hajdar L |  | 130 | 2080 | 16 | Apprentice
| Ayers, Jordan L |  | 128 | 1912 | 14.9375 | Apprentice
| Montenegro, Carlos E |  | 122 | 1952 | 16 | Apprentice
| Monico Brambila, Jesus S |  | 104 | 1768 | 17 | Apprentice
| Castaneda Juarez, Edgar D |  | 98 | 1568 | 16 | Apprentice
| Taylor, Evan R |  | 96 | 1248 | 13 | Apprentice
| Castaneda Juarez, Gustavo |  | 82.5 | 1320 | 16 | Apprentice
| Gerard, Mitchell J |  | 66 | 885 | 13.4091 | Apprentice
| Whitaker, Daniel J |  | 55.5 | 721.5 | 13 | Apprentice
| Veley, Nathaniel S |  | 52 | 1508 | 29 | Mid
| Aguilar, Tony A |  | 48 | 624 | 13 | Apprentice
| Paco Leyva, Orlando |  | 25 | 425 | 17 | Apprentice
| Gerard, Jordan E |  | 12 | 156 | 13 | Apprentice
| TOTAL (53 workers) |  | 25955.5 | 512197.5 | 19.7337
SOURCES
Job #2015 — Exxel Pacific Rooster Apartments + Portage Bay Cafe • GC: Exxel Pacific, Inc.
Canonical source: 2015 Job Detail Report.pdf (255 pages, OWP Sage Timberline export)
Cost codes parsed: 26 (Labor+Material+Overhead+Burden+Revenue)
Billing: ROOSTER AGGREGATE BILLING.xlsx (18 apps) + PORTAGE BAY AGGREGATE BILLING.xlsx (2 apps)
Tier: Apprentice <$18/hr, Mid $18–30, Senior >$30

## Crew Analytics
[CORTEX_V2.1] Job #2015 — · Crew Analytics
Schema CORTEX_V2.1 · canonical v2 builder · single source of truth
| tier | worker_count | hours | gross_pay | pct_of_hours | blended_wage
| Senior | 6 | 3111.5 | 110329 | 11.99%
| Mid | 11 | 8000 | 189735.5 | 30.82%
| Apprentice | 36 | 14844 | 212133 | 57.19%
B. WAGE STATISTICS
| Blended Gross Wage | 19.7337
| Fully-Loaded Wage | 33.8349
| Burden Multiplier | 1.7146
| Min Worker Rate | 13
| Max Worker Rate | 45
| Avg Hours / Worker | 489.7264
SOURCES
Job #2015 — Exxel Pacific Rooster Apartments + Portage Bay Cafe • GC: Exxel Pacific, Inc.
Canonical source: 2015 Job Detail Report.pdf (255 pages, OWP Sage Timberline export)
Cost codes parsed: 26 (Labor+Material+Overhead+Burden+Revenue)
Billing: ROOSTER AGGREGATE BILLING.xlsx (18 apps) + PORTAGE BAY AGGREGATE BILLING.xlsx (2 apps)

## Productivity
[CORTEX_V2.1] Job #2015 — · Productivity
Schema CORTEX_V2.1 · canonical v2 builder · single source of truth
| phase | labor_code | hours | pct_of_total | hours_per_unit
| Supervision | 100 | 181.5 | 0.6333% | 0.92132
| Takeoff & Purchasing | 101 | 401.5 | 1.401% | 2.0381
| Underground | 110 | 338 | 1.179% | 1.7157
| Garage | 111 | 2333.5 | 8.142% | 11.8452
| Canout | 112 | 407 | 1.42% | 2.066
| Foundation Drain | 113 | 21 | 0.07327% | 0.1066
| Roughin | 120 | 19733.75 | 68.85% | 100.1713
| Finish | 130 | 2328.5 | 8.124% | 11.8198
| Gas | 140 | 529 | 1.846% | 2.6853
| Water Main / Insulation | 141 | 2007 | 7.003% | 10.1878
| Mech Room | 142 | 380 | 1.326% | 1.9289
B. PRODUCTIVITY RATIOS
| Metric | Value
| Hours / Unit | 145.486
| Hours / Fixture | 21.2459
| Revenue / Hour | 74.9006
| Profit / Hour | 19.6681
| Units / Month | 7.88
| Fixtures / Month | 53.96
| Hours / Month | 1146.43
| Revenue / Month | 85868.32
SOURCES
Job #2015 — Exxel Pacific Rooster Apartments + Portage Bay Cafe • GC: Exxel Pacific, Inc.
Canonical source: 2015 Job Detail Report.pdf (255 pages, OWP Sage Timberline export)
Cost codes parsed: 26 (Labor+Material+Overhead+Burden+Revenue)
Billing: ROOSTER AGGREGATE BILLING.xlsx (18 apps) + PORTAGE BAY AGGREGATE BILLING.xlsx (2 apps)

## PO Commitments
[CORTEX_V2.1] Job #2015 — · PO Commitments
Schema CORTEX_V2.1 · canonical v2 builder · single source of truth
| po_number | date | issuer | type | status | description | amount | source
| 30 |  |  |  |  | 110+210 Underground
| 31 |  |  |  |  | 120+220 Roughin
| 32 |  |  |  |  | 130+230 Trim/Finish
| 40 |  |  |  |  | 141+241 Water Main/Ins
| 41 |  |  |  |  | 140+240 Gas
| OTHER |  |  |  |  | Unclassified
B. COMMITMENTS BY VENDOR
| Vendor |  |  |  |  | PO Count
| ROSEN |  |  |  |  | 66
| KELLER |  |  |  |  | 49
| FEI |  |  |  |  | 42
| OTHER |  |  |  |  | 21
| CONSOLIDATED |  |  |  |  | 7
| MANOR |  |  |  |  | 6
| MECH SALES |  |  |  |  | 3
| FASTENAL |  |  |  |  | 3
| PIKE |  |  |  |  | 1
C. PO COVERAGE NOTES
Total Material Actual (JDR)
Unique PO Count
(Dollar PO commitment not extracted — requires per-PDF parse)
SOURCES
Job #2015 — Exxel Pacific Rooster Apartments + Portage Bay Cafe • GC: Exxel Pacific, Inc.
Canonical source: 2015 Job Detail Report.pdf (255 pages, OWP Sage Timberline export)
Cost codes parsed: 26 (Labor+Material+Overhead+Burden+Revenue)
Billing: ROOSTER AGGREGATE BILLING.xlsx (18 apps) + PORTAGE BAY AGGREGATE BILLING.xlsx (2 apps)
PO count is deduplicated by 5-digit PO number extracted from filenames
Vendor/code classification is heuristic (filename keyword match)

## Billing & SOV
[CORTEX_V2.1] Job #2015 — · Billing & SOV
Schema CORTEX_V2.1 · canonical v2 builder · single source of truth
| pay_app_number | date | contract_total | this_period | retainage | stored_materials | cumulative | pct_complete | source

## Insights
[CORTEX_V2.1] Job #2015 — · Insights
Schema CORTEX_V2.1 · canonical v2 builder · single source of truth
| insight_id | title | finding | verified | source
| 1 | Labor overran budget by 36.3% | Total labor actual $583,483 vs budget $428,030 — $155,453 unfavorable variance. Review crew mix and productivity. | Derived | budget_vs_actual
| 2 | Largest variance — cost code 230 (Finish Material) under by $145,602 | Budget $483,149, actual $337,547 (-30.1%). Flag for bid calibration. | Derived | budget_vs_actual

## Benchmark KPIs
[CORTEX_V2.1] Job #2015 — · Benchmark KPIs
Schema CORTEX_V2.1 · canonical v2 builder · single source of truth
CROSS-PROJECT BENCHMARK SCORECARD
Normalized metrics designed for apples-to-apples comparison across all OWP projects.
| KPI | DATA NAME | VALUE | CATEGORY | NOTES / BENCHMARK CONTEXT
| Job Number | job_number | 2,015 | Profile | OWP Sage job ID
| General Contractor | general_contractor | Exxel Pacific, Inc. | Profile | Customer of record
| location | location | Seattle, WA | Profile | Project address
| Project Type | project_type | Apartment building | Profile | Building category for benchmarking
| Duration Months | duration_months | 25.0% | Profile | Calendar months from start to close
| Plumbing Units | plumbing_units | 197 | Profile | Residential units delivered
| Total Fixtures | total_fixtures | 1 | Profile | Plumbing fixture count
| Fixtures Per Unit | fixtures_per_unit | $0.01 | Profile | ≈6 fixtures/unit typical for multifamily
| Contract Original | contract_original | $2,002,285 | Financial | Original contract value
| Contract Final | contract_final | $2,002,285 | Financial | Revised contract value (post-COs)
| Change Orders Net | change_orders_net | 0 | Financial | Net dollar change from COs
| revenue | revenue | $2,146,708 | Financial | Net billed (AR net of reversals)
| Net Profit | net_profit | $563,703 | Financial | Revenue − direct cost
| Gross Margin Pct | gross_margin_pct | 26.3% | Financial | Net profit / revenue
| Direct Cost | direct_cost | $1,583,005 | Financial | Σ labor + material + OH + burden + tax
| Overhead Cost | overhead_cost | $43,335 | Financial | Codes 600, 601, 603, 607
| Burden Cost | burden_cost | $249,837 | Financial | Code 995 payroll burden
| Retainage Outstanding | retainage_outstanding | $0.00 | Financial | Held by GC until closeout
| Revenue Per Unit | revenue_per_unit | $10,897 | Financial | Top-line per unit
| Profit Per Unit | profit_per_unit | $2,861 | Financial | Net profit normalized per residential unit
| Cost Per Unit | cost_per_unit | $8,036 | Financial | Total direct cost per unit
| Revenue Per Fixture | revenue_per_fixture | $2,146,708 | Financial | Top-line per fixture
| Profit Per Fixture | profit_per_fixture | $563,703 | Financial | Net profit per fixture installed
| Cost Per Fixture | cost_per_fixture | $1,583,005 | Financial | Total direct cost per fixture
| Labor Cost | labor_cost | $583,483 | Labor | Codes 100–150
| Total Hours | total_hours | 51,911 | Labor | All payroll hours on the job
| Total Workers | total_workers | 60 | Crew | Unique payroll IDs across job
| Blended Wage | blended_wage | $19.73 | Labor | Pre-burden average
| Fully Loaded Wage | fully_loaded_wage | $16.92 | Labor | Post-burden true cost
| Burden Multiplier | burden_multiplier | 0.86 | Labor | Loaded / gross
| Hours Per Unit | hours_per_unit | $0.00 | Labor | Key plumbing benchmark
| Hours Per Fixture | hours_per_fixture | $0.00 | Labor | Industry std for plumbing subs
| Labor Per Unit | labor_per_unit | $2,962 | Labor | Payroll only, not material
| Labor Per Fixture | labor_per_fixture | $583,483 | Labor | Payroll only, not material
| Labor Pct Revenue | labor_pct_revenue | 0.27 | Cost Mix | Payroll exposure
| Material Cost | material_cost | $661,468 | Material | Codes 210–244
| Material Per Unit | material_per_unit | $3,358 | Material | Cross-project benchmark
| Material Per Fixture | material_per_fixture | $661,468 | Material | Cross-project benchmark
| Material Pct Revenue | material_pct_revenue | 0.31 | Cost Mix | Material/sub exposure
| Total Vendors | total_vendors | 25 | Material | Distinct AP vendors invoiced on the job
| Top Vendor Spend | top_vendor_spend | $0.00 | Material | Largest single supplier
| Top Vendor Pct | top_vendor_pct | 0.0% | Material | Top vendor concentration
| Revenue Per Month | revenue_per_month | $85,868 | Throughput | Billing velocity
| Hours Per Month | hours_per_month | $0.00 | Throughput | Avg monthly labor burn
| Units Per Month | units_per_month | $7.88 | Throughput | Build pace
| Fixtures Per Month | fixtures_per_month | $0.04 | Throughput | Fixture install velocity
SOURCES
Canonical: /sessions/keen-determined-mccarthy/mnt/cortex-mockup/owp/cortex v2 files/OWP_2015_JCR_Cortex_v2.xlsx
revenue: AR net-of-reversals (validator)
labor_cost: Codes 100–150
material_cost: Codes 210–244
total_workers: count(distinct worker_id)

## Change Log
[CORTEX_V2.1] Job #2015 — · Change Log
Schema CORTEX_V2.1 · canonical v2 builder · single source of truth
| event_id | type | date | subject | originator | linked_events | cost_impact | schedule_days | status | source_document
| COP-ASI02 | COP | 2014-10-24 | Shower type changes — delete (4) 32" + (10) 36" showers, add (14) 42x34 non-adaptable showers | Architect/Owner | ASI-002 | 793 | 0 | Approved | 2015-Exxel, Rooster/Change Orders/COR_s/Rooster - OWP COP ASI #02.pdf
| COP-ASI04 | COP | 2014-12-11 | Portage Bay Café additions — 8 items: dishwasher/prep relocation, gas piping, grease interceptor, food service rough-in, water heater, circ pump, floor drains, fixture spec updates | Architect/Owner | ASI-004 | 47149 | 0 | Approved | 2015-Exxel, Rooster/Change Orders/COR_s/Rooster - OWP COP ASI #04 Portage Bay Additions.pdf
| COP-ASI05 | COP |  | Bike room plumbing move | Architect | ASI-005 | 0 | 0 | Approved | 2015-Exxel, Rooster/Change Orders/COR_s/Rooster - OWP COP ASI-05 Bike Room.pdf
| COP-FRAME | COP |  | Replumbing due to framing conflicts (revised version issued) | Field (OWP) |  | 0 | 0 | Approved | 2015-Exxel, Rooster/Change Orders/COR_s/Rooster - OWP COP Replumbing Due to Framing REVISED.pdf
| COP-RFI247 | COP |  | Move plumbing Unit 114 driven by RFI-247 | GC (Exxel) | RFI-247 | 0 | 0 | Approved | 2015-Exxel, Rooster/Change Orders/COR_s/Rooster - OWP COP Replumbing Due to RFI-247.pdf
| COP-PBC-HOOD | COP |  | Move plumbing for Portage Bay Café exhaust hood | GC (Exxel) |  | 0 | 0 | Approved | 2015-Exxel, Rooster/Change Orders/COR_s/Rooster - OWP COP Move Plumbing for PBC Exhaust Hood.pdf
| COP-FLEX-GAS | COP |  | Flexible connections to exterior gas heaters | Architect |  | 0 | 0 | Approved | 2015-Exxel, Rooster/Change Orders/COR_s/Rooster - OWP COP Flex Connections to Exterior Gas Heaters.pdf
| COP-GAS-HTR | COP |  | Gas heater system scope | Architect |  | 0 | 0 | Approved | 2015-Exxel, Rooster/Change Orders/COR_s/Rooster - OWP COP Gas Heaters.pdf
| COP-HOOKUP-HTR | COP |  | Hook up heaters | GC (Exxel) |  | 0 | 0 | Approved | 2015-Exxel, Rooster/Change Orders/COR_s/Rooster - OWP COP Hook Up Heaters.pdf
| COP-TEMP-SINK | T&M |  | Temporary sink installation (T&M ticket) | Field (OWP) |  | 0 | 0 | Approved | 2015-Exxel, Rooster/Change Orders/COR_s/Rooster - Temp Sink T&M Ticket.pdf
| COP-RFI097 | COP | 2014-11-03 | Hose bibs — RFI-097 driven (3 pricing revisions) | GC (Exxel) | RFI-097 | 0 | 0 | Approved | 2015-Exxel, Rooster/Change Orders/COR_s/COR Pricing - RFI-097 HOSE BIBS.xlsx
| COP-RFI213 | COP | 2015-06-15 | Move water mains — RFI-213 (delete bedroom partitions) | Architect | RFI-213 | 0 | 0 | Approved | 2015-Exxel, Rooster/Change Orders/COR_s/COR Pricing - RFI-213 MOVE WATER MAINS.xlsx
| COP-FIT-DF | COP |  | Added drinking fountain in fitness room | Owner |  | 0 | 0 | Approved | 2015-Exxel, Rooster/Change Orders/COR_s/COR Pricing - Added Drinking Fountain Fitness Room.xlsx
| COP-IDSI02 | COP |  | IDSI-02 coffee maker connection | Interior Designer | IDSI-002 | 0 | 0 | Approved | 2015-Exxel, Rooster/Change Orders/COR_s/COR Pricing - IDSI-02 Coffee Maker Connection.xlsx
| COP-GAS-ROOF | COP |  | Single shot gas line to roof | Architect |  | 0 | 0 | Approved | 2015-Exxel, Rooster/Change Orders/COR_s/COR Pricing - Single Shot Gas to Roof.xlsx
| COP-MTR125 | COP |  | Move unit water meter Unit 125 (PBC) | GC (Exxel) |  | 0 | 0 | Approved | 2015-Exxel, Rooster 2/Rooster - OWP COP Move Unit Water Meter Unit 125.pdf
| COP-WM123 | COP |  | Move water main Unit 123 (PBC) | GC (Exxel) |  | 0 | 0 | Approved | 2015-Exxel, Rooster 2/Rooster - OWP COP Move Water Main Unit 123.pdf
| ASI-002 | ASI |  | Shower type revision | Architect (WAU) | COP-ASI02 | 0 | 0 | Closed | 2015-Exxel, Rooster/ASI-RFI/ASI-002
| ASI-004 | ASI |  | Portage Bay Café scope additions | Architect (WAU) | COP-ASI04 | 0 | 0 | Closed | 2015-Exxel, Rooster/ASI-RFI/ASI-004
| ASI-005 | ASI |  | Bike room revision | Architect (WAU) | COP-ASI05 | 0 | 0 | Closed | 2015-Exxel, Rooster/ASI-RFI/ASI-005
| ASI-006 | ASI |  | Design clarification ASI #06 | Architect (WAU) |  | 0 | 0 | Closed | 2015-Exxel, Rooster/ASI-RFI/ASI-006
| ASI-007 | ASI |  | Design clarification ASI #07 | Architect (WAU) |  | 0 | 0 | Closed | 2015-Exxel, Rooster/ASI-RFI/ASI-007
| IDSI-002 | ASI |  | Interior design supplemental — coffee maker connection | Interior Designer | COP-IDSI02 | 0 | 0 | Closed | 2015-Exxel, Rooster/ASI-RFI/IDSI-002
| RFI-097 | RFI | 2014-11-03 | Hose bib locations (revised response) | GC (Exxel) | COP-RFI097 | 0 | 0 | Closed | 2015-Exxel, Rooster/ASI-RFI/RFI-097
| RFI-213 | RFI | 2015-06-15 | Delete bedroom partitions — move water mains | GC (Exxel) | COP-RFI213 | 0 | 0 | Closed | 2015-Exxel, Rooster/ASI-RFI/RFI-213
| RFI-247 | RFI |  | Unit 114 plumbing move | GC (Exxel) | COP-RFI247 | 0 | 0 | Closed | 2015-Exxel, Rooster/ASI-RFI/RFI-247
| RFI-SUMMARY | Memo |  | RFI log — 90+ RFIs spanning Apr 2014–Jun 2015 (range RFI-008 to RFI-223+). Responders: WAU, CPL, Rushing, Vida. SCOR letters issued on subset. | GC (Exxel) |  | 0 | 0 | Informational | 2015-Exxel, Rooster/ASI-RFI/ (90+ PDFs)
| SUB-22-01-R1 | Submittal-resub |  | Underground Plumbing Package — R1 revision | Sub (OWP) |  | 0 | 0 | Approved | 2015-Exxel, Rooster/Submittals/#22 0000-01 R1
| SUB-FIX-R1 | Submittal-resub |  | Fixture submittal resubmissions — multiple iterations for Kohler/Sloan/HansGrohe/Duravit (PBC spec updates) | Sub (OWP) | COP-ASI04 | 0 | 0 | Approved | 2015-Exxel, Rooster/Submittals/FIXTURE SUBMITTALS/RESPONSE/
| DOC-GAP-RFI-LOG | Memo |  | GAP: No consolidated RFI log/summary spreadsheet despite 90+ RFIs. Cycle-day + resubmission metrics not computable without reconstruction. | OWP |  | 0 | 0 | Open | 2015-Exxel, Rooster/ASI-RFI/ (no log file)
| DOC-GAP-COR-OUT | Memo |  | GAP: Outstanding COR trackers exist (8-18-15, 10-5-15) but final resolution/billed amounts unreconciled vs signed CO totals. | OWP |  | 0 | 0 | Open | 2015-Exxel, Rooster/Change Orders/Outstanding COR_s as of 08-18-15.xlsx

## Root Cause Analysis
[CORTEX_V2.1] Job #2015 — · Root Cause Analysis
Schema CORTEX_V2.1 · canonical v2 builder · single source of truth
| rca_id | observation | root_cause | responsibility | cost_impact | mitigation | source

## Predictive Signals
[CORTEX_V2.1] Job #2015 — · Predictive Signals
Schema CORTEX_V2.1 · canonical v2 builder · single source of truth
| signal_id | signal_name | direction | metric | threshold | historical_outcome | source
| WAREHOUSE | Predictive signals computed at warehouse layer | Neutral | cross-project benchmark | n/a | See benchmark_envelopes view; not stored per-project. | warehouse view (predictive_signals_v)

## Metric Registry
[CORTEX_V2.1] Job #2015 — · Metric Registry
Schema CORTEX_V2.1 · canonical v2 builder · single source of truth
| metric_key | metric_label | value | data_label | tab_home | verification | source
2015
Exxel Pacific Rooster Apts + Portage Bay Cafe
Exxel Pacific, Inc.
Seattle, WA
Mixed-use 6-story apartments + ground-floor restaurant TI
25
197
1349
2002285
2146708
144423
2146708
563703.44
0.26259
1583004.56
583482.62
661468.33
43335.38
294718.23
103985
28660.75
53
17.871
24
198
0.072129
90
6
16
0
1
7
31
47942

## Reconciliation
[CORTEX_V2.1] Job #2015 — · Reconciliation
Schema CORTEX_V2.1 · canonical v2 builder · single source of truth
| check_number | check_description | value_a | value_b | difference | status | tabs
A. JDR COST CODE ROLLUP
|  | Labor subtotal (11 codes) | 583482.62 |  |  | TIES
|  | Material subtotal (9 codes) | 661468.33 |  |  | TIES
|  | Overhead subtotal (3 codes) | 43335.38 |  |  | TIES
|  | Burden subtotal (2 codes) | 294718.23 |  |  | TIES
|  | Direct Cost (all categories) | 1583004.56 |  |  | TIES
|  | Revenue (code 999) | 2146708 |  |  | TIES
|  | Net Profit (Revenue - Expenses) | 563703.44 |  |  | TIES
B. LABOR HOURS ROLLUP
|  | JDR Cost Code hours (Payroll Hours lines) | 28660.75 |  |  | TIES
|  | Per-worker hours (sum of PR Regular) | 28660.75 |  |  | OFF
C. BILLING (SOV) ↔ JDR
|  | Final Contract Value | 2146708 |  |  | WITHIN
|  | Retainage | 103985 |  |  | TIES
|  | Direct Cost | 1641584 |  |  | WITHIN
D. VENDOR AP ↔ JDR
|  | Vendor AP total (sum of invoices) | 690359 |  |  | OFF
SOURCES
Job #2015 — Exxel Pacific Rooster Apartments + Portage Bay Cafe • GC: Exxel Pacific, Inc.
Canonical source: 2015 Job Detail Report.pdf (255 pages, OWP Sage Timberline export)
Cost codes parsed: 26 (Labor+Material+Overhead+Burden+Revenue)
Billing: ROOSTER AGGREGATE BILLING.xlsx (18 apps) + PORTAGE BAY AGGREGATE BILLING.xlsx (2 apps)
TIES = within $1 or 5 hrs • WITHIN = within 5% • OFF = investigate
K. CHANGE LOG ↔ ROOT CAUSE ANALYSIS
|  | Total Event Count | 31 |  |  | TIES
|  | Net $ Impact (all events) | 47942 |  |  | TIES
L. PREDICTIVE SIGNALS ↔ CHANGE LOG
|  | Backcharge Count signal | 0 |  |  | TIES
M. METRIC REGISTRY ↔ BENCHMARK KPIs
|  | revenue (row 17) | 2146708 |  |  | TIES
|  | unit_count (row 12) | 197 |  |  | TIES
|  | total_fixtures (row 13) | 1349 |  |  | TIES
|  | direct_cost (row 19) | 1583004.56 |  |  | OFF
|  | total_pos (row 30) | 198 |  |  | TIES
N. CHANGE LOG ↔ METRIC REGISTRY (event counts)
|  | change_event_total | 31 |  |  | OFF
SOURCES
Job #2015 — Cortex v2 17-tab layout
12 analytical tabs + Change Log + Root Cause Analysis + Predictive Signals + Metric Registry + Reconciliation
Canonical source: 2015 Job Detail Report.pdf (Sage Timberline export)
Change artifacts: folders scanned — ASI-RFI, Change Orders, Submittals, Invoices (Backcharges), JDR cost codes
Every Change Log row cites its source document path
TIES = within $1/5hrs/exact count • WITHIN = within 5% • OFF = investigate
Cross-sheet formulas (='Tab'!Cell) update automatically when source tabs change
Tabs: 1-12 analytical • 13=ChangeLog • 14=RootCause • 15=PredictiveSignals • 16=MetricRegistry • 17=Reconciliation

## Vendors
[CORTEX_V2.1] Job #2015 — · Vendors
Schema CORTEX_V2.1 · canonical v2 builder · single source of truth
| vendor_id | vendor_name | total_spend | transactions | category | source
Invoices
89
80
82
3
11
5
4
22
6
7
6
10
6
3
3
5
7
5
1
4
5
1
2
1