## Overview
[CORTEX_V2.1] Job #2017 — · Overview
Schema CORTEX_V2.1 · canonical v2 builder · single source of truth
| OVERVIEW |  | SOURCE
IDENTITY
| Project Job Number | 2017
| Project Name: | Exxel Pacific 3636 Stone Way Apartments
CONTRACT & PARTIES
| General Contractor | Exxel Pacific, Inc.
JOB SITE
| Jobsite Location | Seattle, WA (3636 Stone Way N)
| Plumbing Units | 119 | Kitchen Sinks
| Floors | 4 + P1 | Duration
SCHEDULE
| Project Duration | Feb 2014 – May 2015 (~16 months)
SCOPE & DESIGN
| Total Fixtures | 801 | Dishwashers
| Fixtures / Unit | 6.73 | Auto Washers
| CONTRACT VALUE |  | NET PROFIT |  | DIRECT COST |  | LABOR HOURS
| $1,373,148 |  | $513,186 |  | $856,803 |  | 29,950
| Original $1,373,148 |  | 37.5% margin |  | 62.5% of revenue |  | 54 workers
COST BREAKDOWN
| Category | Budget | Actual | Variance | % Budget | % of Cost
| Labor | 272340 | 292755.75 | -20415.75 | 107.5% | 34.17%
| Material | 502391 | 375932.8 | 126458.2 | 74.83% | 43.88%
| Overhead | 42470 | 33855.5 | 8614.5 | 79.72% | 3.951%
| Burden | 139796.75 | 154259.34 | -14462.59 | 110.3% | 18%
| TOTAL | 956997.75 | 856803.39 | 100194.36 | 89.53% | 100%
PROJECT PROFILE
| Plumbing Units | 119 |  | Total Fixtures | 801 |  | Fixtures / Unit | 6.73
| Floors | 4 + P1 |  | Duration | Feb 2014 – May 2015 (~16 months)

## Budget vs Actual
[CORTEX_V2.1] Job #2017 — · Budget vs Actual
Schema CORTEX_V2.1 · canonical v2 builder · single source of truth
| cost_code | description | original_budget | revised_budget | actual | variance | pct_used | hours | source
LABOR
| 100 | Supervision | 6500 | 6500 | 4744 | 1756 | 72.98%
| 101 | Takeoff & Purchase Labor | 6500 | 7300 | 7873 | -573 | 1.078%
| 110 | Underground Labor | 8538 | 8538 | 6900 | 1638 | 80.82%
| 111 | Garage Labor | 38180 | 38670 | 29981 | 8689 | 77.53%
| 112 | Canout Labor | 5130 | 5130 | 4602 | 528 | 89.71%
| 113 | Foundation Drain Labor | 2012 | 2012 | 2012 | 0 | 100%
| 120 | Roughin Labor | 138760 | 140370 | 173312.75 | -32942.75 | 1.235%
| 130 | Finish Labor | 23400 | 25520 | 36292.5 | -10772.5 | 1.422%
| 140 | Gas Labor | 6000 | 6300 | 7448 | -1148 | 1.182%
| 141 | Water Main/Insulation Lab | 32000 | 32000 | 19505.5 | 12494.5 | 60.95%
| 142 | Mech Room Labor | 0 | 0 | 85 | -85 | 0%
MATERIAL
| 039 | DS & RD Material | 0 | 0 | 2380.94 | -2380.94 | 0%
| 210 | Underground Material | 5685 | 5685 | 3861 | 1824 | 67.92%
| 211 | Garage Material | 29760 | 29800 | 3724.79 | 26075.21 | 12.5%
| 212 | Canout Material | 5700 | 5740 | 6453.36 | -713.36 | 1.124%
| 213 | Foundation Material | 15065 | 13365 | 13364.65 | 0.35 | 100%
| 220 | Roughin Material | 138250 | 132050 | 98571.05 | 33478.95 | 74.65%
| 230 | Finish Material | 273100 | 248951 | 192296.61 | 56654.39 | 77.24%
| 240 | Gas Material | 3600 | 3600 | 2769 | 831 | 76.92%
| 241 | Water Main/Insulation Mat | 51200 | 51200 | 45904.61 | 5295.39 | 89.66%
| 242 | Mech Room Material | 12000 | 12000 | 8987.73 | 3012.27 | 74.9%
OVERHEAD
| 600 | Subcontractor | 15970 | 16970 | 15635 | 1335 | 92.13%
| 601 | Engineering/Plans | 22000 | 22500 | 17974.5 | 4525.5 | 79.89%
| 603 | Permits & Licenses | 3000 | 3000 | 246 | 2754 | 8.2%
BURDEN
| 995 | Payroll Burden | 116366.6 | 118687.33 | 131106.33 | -12419 | 1.105%
| 998 | Payroll Taxes | 20702.43 | 21109.42 | 23153.01 | -2043.59 | 1.097%
SOURCES
Job #2017 — Exxel Pacific 3636 Stone Way Apartments • GC: Exxel Pacific, Inc. • Seattle, WA
Canonical source: 2017 Job Detail Report.pdf (124 pages, OWP Sage Timberline export)
Cost codes parsed: 27 (Labor+Material+Overhead+Burden+Revenue)
Unit count: 119 from Job Ticket (119 DWs, 119 washers)
Fixture count: Toto WCs 122, Grohe lavs 137, Aquatic tubs 122, Lenova/Elkay sinks 119 + common area
Billing: 36 STONE AGGREGATE BILLING.xlsx (14 pay apps, Feb 2014 – May 2015)
| TOTAL |  | 979419.03 | 956997.75 | 859184.33 | 97813.42 |  | 0

## Cost Breakdown
[CORTEX_V2.1] Job #2017 — · Cost Breakdown
Schema CORTEX_V2.1 · canonical v2 builder · single source of truth
| category | cost_codes | actual | pct_of_direct_cost | pct_of_revenue | per_unit | source
| Labor | 11 | 272340 | 1.075% |  | 2460.1324
| Material | 10 | 502391 | 75.3% |  | 3179.1071
| Overhead | 3 | 42470 | 79.72% |  | 284.5
| Burden | 2 | 139796.75 | 1.103% |  | 1296.297
B. LARGEST OVERRUNS (Actual > Revised Budget)
| Code | Description
| 120 | Roughin Labor | 140370 | 23.47%
| 995 | Payroll Burden | 118687.33 | 10.46%
| 130 | Finish Labor | 25520 | 42.21%
| 039 | DS & RD Material | 0 | 0%
| 998 | Payroll Taxes | 21109.42 | 9.681%
| 140 | Gas Labor | 6300 | 18.22%
| 212 | Canout Material | 5740 | 12.43%
| 101 | Takeoff & Purchase Labor | 7300 | 7.849%
C. LARGEST SAVINGS (Actual < Revised Budget)
| Code | Description
| 230 | Finish Material | 248951 | 22.76%
| 220 | Roughin Material | 132050 | 25.35%
| 211 | Garage Material | 29800 | 87.5%
| 141 | Water Main/Insulation Lab | 32000 | 39.05%
| 111 | Garage Labor | 38670 | 22.47%
| 241 | Water Main/Insulation Mat | 51200 | 10.34%
| 601 | Engineering/Plans | 22500 | 20.11%
| 242 | Mech Room Material | 12000 | 25.1%
| 603 | Permits & Licenses | 3000 | 91.8%
| 210 | Underground Material | 5685 | 32.08%
SOURCES
Job #2017 — Exxel Pacific 3636 Stone Way Apartments • GC: Exxel Pacific, Inc. • Seattle, WA
Canonical source: 2017 Job Detail Report.pdf (124 pages, OWP Sage Timberline export)
Cost codes parsed: 27 (Labor+Material+Overhead+Burden+Revenue)
Unit count: 119 from Job Ticket (119 DWs, 119 washers)
Fixture count: Toto WCs 122, Grohe lavs 137, Aquatic tubs 122, Lenova/Elkay sinks 119 + common area
Billing: 36 STONE AGGREGATE BILLING.xlsx (14 pay apps, Feb 2014 – May 2015)
| TOTAL |  | 1857880.5 |  |  | 7220.0364

## Material
[CORTEX_V2.1] Job #2017 — · Material
Schema CORTEX_V2.1 · canonical v2 builder · single source of truth
| vendor_id | vendor_name | total_spend | transactions | category | source
| 039 | DS & RD Material | 0 |  | 0.0062936
| 210 | Underground Material | 5685 |  | 0.010206
| 211 | Garage Material | 29800 |  | 0.0098458
| 212 | Canout Material | 5740 |  | 0.017058
| 213 | Foundation Material | 13365 |  | 0.035327
| 220 | Roughin Material | 132050 |  | 0.26055
| 230 | Finish Material | 248951 |  | 0.5083
| 240 | Gas Material | 3600 |  | 0.0073193
| 241 | Water Main/Insulation Mat | 51200 |  | 0.12134
| 242 | Mech Room Material | 12000 |  | 0.023757
B. VENDORS BY SPEND (AP)
| Vendor | # Invoices
| Consolidated Supply Co. | 102 | 176571.46
| Rosen Supply Company, Inc. | 85 | 139209.01
| Ferguson Enterprises, Inc. | 18 | 72780.98
| Franklin Engineering | 5 | 17974.5
| Duraseal, Inc. | 2 | 12800
| Keller Supply Company | 11 | 8131.24
| Bank of America CC | 6 | 8076
| Quality Concrete Products, Inc. | 3 | 5921
| Rosen Supply Kirkland | 6 | 4412.21
| Mechanical Sales, Inc. | 2 | 2840
| Manor Hardware & Construction Supply | 3 | 2465
| Cascade Restoration Co. | 2 | 2140
| Kele, Inc | 4 | 1340.48
| Core & Main LP | 2 | 1134.15
| Ferguson Enterprises, Inc. #3007 | 3 | 811.46
| C.M. Hoskins Company | 3 | 702.97
| Structural Imaging, LLC | 1 | 500
| Fastenal Company | 4 | 258.11
| R.A. Brown Backflow Testing | 2 | 195
| Capital One Credit Card | 2 | 112.8
SOURCES
Job #2017 — Exxel Pacific 3636 Stone Way Apartments • GC: Exxel Pacific, Inc. • Seattle, WA
Canonical source: 2017 Job Detail Report.pdf (124 pages, OWP Sage Timberline export)
Cost codes parsed: 27 (Labor+Material+Overhead+Burden+Revenue)
Unit count: 119 from Job Ticket (119 DWs, 119 washers)
Fixture count: Toto WCs 122, Grohe lavs 137, Aquatic tubs 122, Lenova/Elkay sinks 119 + common area
Billing: 36 STONE AGGREGATE BILLING.xlsx (14 pay apps, Feb 2014 – May 2015)
Vendor AP ties to JDR 'by Source: AP' line (458,376.37)

## Crew & Labor
[CORTEX_V2.1] Job #2017 — · Crew & Labor
Schema CORTEX_V2.1 · canonical v2 builder · single source of truth
| worker_id | worker_name | total_hours | gross_pay | blended_wage_per_hr | tier | work_days | source
| Gonzalez Hernandez, Josue |  | 1282 | 19700 | 15.3666 | Apprentice
| Montenegro, Carlos E |  | 1186 | 16982 | 14.3187 | Apprentice
| Castro Hernandez, Carlos E |  | 1176 | 33725 | 28.6777 | Mid
| Reyes Cruz, Denis A |  | 1006.5 | 13658 | 13.5698 | Apprentice
| Quintanilla, Esteban R |  | 1002 | 32471 | 32.4062 | Senior
| Lima Romero, Melvin A |  | 921 | 18933 | 20.557 | Mid
| Rivera, Jorge A |  | 909 | 17124 | 18.8383 | Mid
| Esparza Jimenez, Jose D |  | 784 | 14896 | 19 | Mid
| Castro Hernandez, Jose A |  | 687.5 | 12177 | 17.712 | Apprentice
| Reyes, Robert J |  | 606 | 8164 | 13.4719 | Apprentice
| Ramirez, Lorenzo A |  | 490 | 8061 | 16.451 | Apprentice
| Soto Cruz, Jovani |  | 442.5 | 7471 | 16.8836 | Apprentice
| Monico Brambila, Jesus S |  | 408 | 6352 | 15.5686 | Apprentice
| Ramos Banegas, Noel O |  | 405.5 | 5930.5 | 14.6252 | Apprentice
| Sepulveda Gonzalez, Alfredo |  | 401 | 10159 | 25.3342 | Mid
| Rivera, Eli P |  | 397 | 5811 | 14.6373 | Apprentice
| Castaneda Martinez, Gustavo |  | 394 | 11269 | 28.6015 | Mid
| Gerard, Jeffrey S |  | 331.5 | 12927 | 38.9955 | Senior
| Anzora, William |  | 312 | 4216 | 13.5128 | Apprentice
| Kinssies, Jr, John E |  | 220.5 | 3420 | 15.5102 | Apprentice
| Salazar, Hajdar L |  | 216.5 | 3312 | 15.2979 | Apprentice
| Castaneda Juarez, Edgar D |  | 214 | 3340.75 | 15.611 | Apprentice
| Sanders, Allen O |  | 156 | 4809 | 30.8269 | Senior
| Vaughan, Tyler J |  | 150.5 | 2468.5 | 16.402 | Apprentice
| Anderson, Richard P |  | 140 | 3920 | 28 | Mid
| Rico-Gomez, Angel A |  | 114.5 | 1488.5 | 13 | Apprentice
| Castaneda Juarez, Gustavo |  | 111.5 | 1641 | 14.7175 | Apprentice
| Veley, Nathaniel S |  | 107 | 3103 | 29 | Mid
| Rodriguez Bonilla, Lisandro |  | 88 | 1144 | 13 | Apprentice
| Gerard, Mitchell J |  | 73 | 936 | 12.8219 | Apprentice
| Paco Leyva, Orlando |  | 59 | 1003 | 17 | Apprentice
| Donelson, Richard T |  | 29 | 1305 | 45 | Senior
| Meza Fuentes, Erick A |  | 24 | 488 | 20.3333 | Mid
| Palma Vides, Hugo |  | 16 | 464 | 29 | Mid
| Amaya Gonzalez, Edilberto A |  | 16 | 208 | 13 | Apprentice
| Arreola, Israel A |  | 16 | 272 | 17 | Apprentice
| Garcia, Jordan X |  | 16 | 272 | 17 | Apprentice
| Hubbard, Dustin R |  | 16 | 208 | 13 | Apprentice
| Nishiyama, Joshua K |  | 13 | 169 | 13 | Apprentice
| Rodriguez Rodriguez, Aminadab N |  | 8 | 104 | 13 | Apprentice
| Ascencio, Jose L |  | 8 | 104 | 13 | Apprentice
| Cruz Reyes, Jose |  | 8 | 104 | 13 | Apprentice
| McCabe, Thomas C |  | 6 | 120 | 20 | Mid
| Velasquez Cruz, Denis M |  | 6 | 90 | 15 | Apprentice
| Barnhart, Joseph N |  | 1 | 31 | 31 | Senior
| TOTAL (45 workers) |  | 14975 | 294551.25 | 19.6695
SOURCES
Job #2017 — Exxel Pacific 3636 Stone Way Apartments • GC: Exxel Pacific, Inc. • Seattle, WA
Canonical source: 2017 Job Detail Report.pdf (124 pages, OWP Sage Timberline export)
Cost codes parsed: 27 (Labor+Material+Overhead+Burden+Revenue)
Unit count: 119 from Job Ticket (119 DWs, 119 washers)
Fixture count: Toto WCs 122, Grohe lavs 137, Aquatic tubs 122, Lenova/Elkay sinks 119 + common area
Billing: 36 STONE AGGREGATE BILLING.xlsx (14 pay apps, Feb 2014 – May 2015)
Tier: Apprentice <$18/hr, Mid $18–30, Senior >$30

## Crew Analytics
[CORTEX_V2.1] Job #2017 — · Crew Analytics
Schema CORTEX_V2.1 · canonical v2 builder · single source of truth
| tier | worker_count | hours | gross_pay | pct_of_hours | blended_wage
| Senior | 5 | 1519.5 | 51543 | 10.15%
| Mid | 11 | 4878 | 114201 | 32.57%
| Apprentice | 29 | 8577.5 | 128807.25 | 57.28%
B. WAGE STATISTICS
| Blended Gross Wage | 19.6695
| Fully-Loaded Wage | 29.8508
| Burden Multiplier | 1.5176
| Min Worker Rate | 12.8219
| Max Worker Rate | 45
| Avg Hours / Worker | 332.7778
SOURCES
Job #2017 — Exxel Pacific 3636 Stone Way Apartments • GC: Exxel Pacific, Inc. • Seattle, WA
Canonical source: 2017 Job Detail Report.pdf (124 pages, OWP Sage Timberline export)
Cost codes parsed: 27 (Labor+Material+Overhead+Burden+Revenue)
Unit count: 119 from Job Ticket (119 DWs, 119 washers)
Fixture count: Toto WCs 122, Grohe lavs 137, Aquatic tubs 122, Lenova/Elkay sinks 119 + common area
Billing: 36 STONE AGGREGATE BILLING.xlsx (14 pay apps, Feb 2014 – May 2015)

## Productivity
[CORTEX_V2.1] Job #2017 — · Productivity
Schema CORTEX_V2.1 · canonical v2 builder · single source of truth
| phase | labor_code | hours | pct_of_total | hours_per_unit
| Supervision | 100 | 119.5 | 0.8062% | 1.0042
| Takeoff & Purchasing | 101 | 198.5 | 1.339% | 1.6681
| Underground | 110 | 288 | 1.943% | 2.4202
| Garage | 111 | 1485 | 10.02% | 12.479
| Canout | 112 | 177.5 | 1.198% | 1.4916
| Foundation Drain | 113 | 97 | 0.6544% | 0.81513
| Roughin | 120 | 9126.5 | 61.57% | 76.6933
| Finish | 130 | 1926 | 12.99% | 16.1849
| Gas | 140 | 352 | 2.375% | 2.958
| Water Main / Insulation | 141 | 1047 | 7.064% | 8.7983
| Mech Room | 142 | 5 | 0.03373% | 0.042017
B. PRODUCTIVITY RATIOS
| Metric | Value
| Hours / Unit | 124.5546
| Hours / Fixture | 18.5044
| Revenue / Hour | 92.4294
| Profit / Hour | 34.4626
| Units / Month | 7.4375
| Fixtures / Month | 50.0625
| Hours / Month | 926.375
| Revenue / Month | 85624.3125
SOURCES
Job #2017 — Exxel Pacific 3636 Stone Way Apartments • GC: Exxel Pacific, Inc. • Seattle, WA
Canonical source: 2017 Job Detail Report.pdf (124 pages, OWP Sage Timberline export)
Cost codes parsed: 27 (Labor+Material+Overhead+Burden+Revenue)
Unit count: 119 from Job Ticket (119 DWs, 119 washers)
Fixture count: Toto WCs 122, Grohe lavs 137, Aquatic tubs 122, Lenova/Elkay sinks 119 + common area
Billing: 36 STONE AGGREGATE BILLING.xlsx (14 pay apps, Feb 2014 – May 2015)

## PO Commitments
[CORTEX_V2.1] Job #2017 — · PO Commitments
Schema CORTEX_V2.1 · canonical v2 builder · single source of truth
| po_number | date | issuer | type | status | description | amount | source
| 30 |  |  |  |  | 110+210 Underground
| 31 |  |  |  |  | 120+220 Roughin
| 32 |  |  |  |  | 130+230 Trim/Finish
| 34 |  |  |  |  | 111+211 Garage
| 40 |  |  |  |  | 141+241 Water Main/Ins
| 41 |  |  |  |  | 140+240 Gas
| OTHER |  |  |  |  | Unclassified
B. COMMITMENTS BY VENDOR
| Vendor |  |  |  |  | PO Count
| ROSEN |  |  |  |  | 62
| CONSOLIDATED |  |  |  |  | 31
| OTHER |  |  |  |  | 18
| KELLER |  |  |  |  | 11
| FEI |  |  |  |  | 11
| MANOR |  |  |  |  | 3
| FASTENAL |  |  |  |  | 3
| SIOUX CHIEF |  |  |  |  | 1
| PIKE |  |  |  |  | 1
| MECH SALES |  |  |  |  | 1
C. PO COVERAGE NOTES
Total Material Actual (JDR)
Unique PO Count
(Dollar PO commitment not extracted — requires per-PDF parse)
SOURCES
Job #2017 — Exxel Pacific 3636 Stone Way Apartments • GC: Exxel Pacific, Inc. • Seattle, WA
Canonical source: 2017 Job Detail Report.pdf (124 pages, OWP Sage Timberline export)
Cost codes parsed: 27 (Labor+Material+Overhead+Burden+Revenue)
Unit count: 119 from Job Ticket (119 DWs, 119 washers)
Fixture count: Toto WCs 122, Grohe lavs 137, Aquatic tubs 122, Lenova/Elkay sinks 119 + common area
Billing: 36 STONE AGGREGATE BILLING.xlsx (14 pay apps, Feb 2014 – May 2015)
PO count is deduplicated by 5-digit PO number extracted from filenames
Vendor/code classification is heuristic (filename keyword match)

## Billing & SOV
[CORTEX_V2.1] Job #2017 — · Billing & SOV
Schema CORTEX_V2.1 · canonical v2 builder · single source of truth
| pay_app_number | date | contract_total | this_period | retainage | stored_materials | cumulative | pct_complete | source
| 11 | 2015-01-20 | 1365227 | 32880 | 0 | 0 | 1251338 | 91.66%
| 8 | 2014-10-20 | 1365227 | 213650 | 0 | 0 | 1110513 | 81.34%
| 9 | 2014-11-17 | 1365227 | 83445 | 0 | 0 | 1193958 | 87.45%
| 10 | 2014-12-15 | 1365227 | 24500 | 0 | 0 | 1218458 | 89.25%
| 12 | 2015-02-19 | 1365227 | 53430 | 0 | 0 | 1304768 | 95.57%
| 1 | 2014-02-20 | 1373148 | 70000 | 0 | 0 | 70000 | 5.1%
| 13 | 2015-03-19 | 1368712 | 63944 | 0 | 0 | 1368712 | 100%
| 2 | 2014-04-17 | 1358932 | 43000 | 0 | 0 | 113000 | 8.32%
| 14 | 2015-05-19 | 1369989 | 1277 | 0 | 0 | 1369989 | 100%
| 3 | 2014-05-20 | 1358932 | 72350 | 0 | 0 | 185350 | 13.64%
| 4 | 2014-06-20 | 1349920 | 21643 | 0 | 0 | 206993 | 15.33%
| 5 | 2014-07-20 | 1351542 | 111749 | 0 | 0 | 318742 | 23.58%
| 6 | 2014-08-19 | 1351542 | 229700 | 0 | 0 | 548442 | 40.58%
| 7 | 2014-09-18 | 1365227 | 348421 | 0 | 0 | 896863 | 65.69%

## Insights
[CORTEX_V2.1] Job #2017 — · Insights
Schema CORTEX_V2.1 · canonical v2 builder · single source of truth
| insight_id | title | finding | verified | source
| 1 | Labor overran budget by 9.6% | Total labor actual $292,756 vs budget $267,020 — $25,736 unfavorable variance. Review crew mix and productivity. | Derived | budget_vs_actual
| 2 | Scope stability — 9 executed COs net $15,852 (+0.00% of contract) | Minimal scope churn indicates well-defined contract and experienced GC. Candidate GC profile for future similar bids. | Derived | change_log
| 3 | Largest variance — cost code 230 (Finish Material) under by $56,654 | Budget $248,951, actual $192,297 (-22.8%). Flag for bid calibration. | Derived | budget_vs_actual

## Benchmark KPIs
[CORTEX_V2.1] Job #2017 — · Benchmark KPIs
Schema CORTEX_V2.1 · canonical v2 builder · single source of truth
CROSS-PROJECT BENCHMARK SCORECARD
Normalized metrics designed for apples-to-apples comparison across all OWP projects.
| KPI | DATA NAME | VALUE | CATEGORY | NOTES / BENCHMARK CONTEXT
| Job Number | job_number | 2,017 | Profile | OWP Sage job ID
| General Contractor | general_contractor | Exxel Pacific, Inc. | Profile | Customer of record
| location | location | Seattle, WA (3636 Stone Way N) | Profile | Project address
| Project Type | project_type | Apartment building | Profile | Building category for benchmarking
| Duration Months | duration_months | 16.0% | Profile | Calendar months from start to close
| Plumbing Units | plumbing_units | 119 | Profile | Residential units delivered
| Total Fixtures | total_fixtures | 801 | Profile | Plumbing fixture count
| Fixtures Per Unit | fixtures_per_unit | $6.73 | Profile | ≈6 fixtures/unit typical for multifamily
| Contract Original | contract_original | $1,373,148 | Financial | Original contract value
| Contract Final | contract_final | $1,373,148 | Financial | Revised contract value (post-COs)
| Change Orders Net | change_orders_net | 0 | Financial | Net dollar change from COs
| revenue | revenue | $1,369,989 | Financial | Net billed (AR net of reversals)
| Net Profit | net_profit | $513,186 | Financial | Revenue − direct cost
| Gross Margin Pct | gross_margin_pct | 37.5% | Financial | Net profit / revenue
| Direct Cost | direct_cost | $856,803 | Financial | Σ labor + material + OH + burden + tax
| Overhead Cost | overhead_cost | $33,856 | Financial | Codes 600, 601, 603, 607
| Burden Cost | burden_cost | $131,106 | Financial | Code 995 payroll burden
| Retainage Outstanding | retainage_outstanding | $0.00 | Financial | Held by GC until closeout
| Revenue Per Unit | revenue_per_unit | $11,513 | Financial | Top-line per unit
| Profit Per Unit | profit_per_unit | $4,312 | Financial | Net profit normalized per residential unit
| Cost Per Unit | cost_per_unit | $7,200 | Financial | Total direct cost per unit
| Revenue Per Fixture | revenue_per_fixture | $1,710 | Financial | Top-line per fixture
| Profit Per Fixture | profit_per_fixture | $641 | Financial | Net profit per fixture installed
| Cost Per Fixture | cost_per_fixture | $1,070 | Financial | Total direct cost per fixture
| Labor Cost | labor_cost | $292,756 | Labor | Codes 100–150
| Total Hours | total_hours | 29,950 | Labor | All payroll hours on the job
| Total Workers | total_workers | 54 | Crew | Unique payroll IDs across job
| Blended Wage | blended_wage | $19.67 | Labor | Pre-burden average
| Fully Loaded Wage | fully_loaded_wage | $14.93 | Labor | Post-burden true cost
| Burden Multiplier | burden_multiplier | 0.76 | Labor | Loaded / gross
| Hours Per Unit | hours_per_unit | $0.00 | Labor | Key plumbing benchmark
| Hours Per Fixture | hours_per_fixture | $0.00 | Labor | Industry std for plumbing subs
| Labor Per Unit | labor_per_unit | $2,460 | Labor | Payroll only, not material
| Labor Per Fixture | labor_per_fixture | $365 | Labor | Payroll only, not material
| Labor Pct Revenue | labor_pct_revenue | 0.21 | Cost Mix | Payroll exposure
| Material Cost | material_cost | $375,933 | Material | Codes 210–244
| Material Per Unit | material_per_unit | $3,159 | Material | Cross-project benchmark
| Material Per Fixture | material_per_fixture | $469 | Material | Cross-project benchmark
| Material Pct Revenue | material_pct_revenue | 0.27 | Cost Mix | Material/sub exposure
| Total Vendors | total_vendors | 21 | Material | Distinct AP vendors invoiced on the job
| Top Vendor Spend | top_vendor_spend | $0.00 | Material | Largest single supplier
| Top Vendor Pct | top_vendor_pct | 0.0% | Material | Top vendor concentration
| Revenue Per Month | revenue_per_month | $85,624 | Throughput | Billing velocity
| Hours Per Month | hours_per_month | $0.00 | Throughput | Avg monthly labor burn
| Units Per Month | units_per_month | $7.44 | Throughput | Build pace
| Fixtures Per Month | fixtures_per_month | $50.06 | Throughput | Fixture install velocity
SOURCES
Canonical: /sessions/keen-determined-mccarthy/mnt/cortex-mockup/owp/cortex v2 files/OWP_2017_JCR_Cortex_v2.xlsx
revenue: AR net-of-reversals (validator)
labor_cost: Codes 100–150
material_cost: Codes 210–244
total_workers: count(distinct worker_id)

## Change Log
[CORTEX_V2.1] Job #2017 — · Change Log
Schema CORTEX_V2.1 · canonical v2 builder · single source of truth
| event_id | type | date | subject | originator | linked_events | cost_impact | schedule_days | status | source_document
| COR-001 | COR | 2014-05-30 | Delete filter fabric from footing drains contract | Sub (OWP) | RFI-123 | -2100 | 0 | Accepted | 2017-Exxel, 36 Stone/Change Orders/COR_s/36 Stone - OWP COR #01.pdf
| COR-002 | COR | 2014-05-30 | Fitness Room bathroom sink — Kohler K-2084-0 in lieu of Elkay ELUH12V | Sub (OWP) | RFI-115 | 495 | 0 | Accepted | 2017-Exxel, 36 Stone/Change Orders/COR_s/36 Stone - OWP COR #02.pdf
| CO-003 | CO | 2014-06-12 | Eliminate sewer vault + pumps (gravity drain to SW corner) | GC (Exxel) |  | -6872 | 0 | Signed | 2017-Exxel, 36 Stone/Change Orders/CO_s/3636 change orders 3 through 6.pdf
| CO-004 | CO | 2014-06-12 | Wall-mount sink Fitness Room (in lieu of countertop) | GC (Exxel) | RFI-115 | 495 | 0 | Signed | 2017-Exxel, 36 Stone/Change Orders/CO_s/3636 change orders 3 through 6.pdf
| CO-005 | CO | 2014-06-12 | Delete filter fabric at footing drains | GC (Exxel) | RFI-123 | -2100 | 0 | Signed | 2017-Exxel, 36 Stone/Change Orders/CO_s/3636 change orders 3 through 6.pdf
| CO-006 | CO | 2014-06-12 | Catch basin in lieu of trench drain at P1 garage ramp | GC (Exxel) | RFI-132 | -535 | 0 | Signed | 2017-Exxel, 36 Stone/Change Orders/CO_s/3636 change orders 3 through 6.pdf
| CO-007 | CO | 2014-06-26 | 2 drains south residential patio + Type B→A ADA lavatory sink | GC (Exxel) | RFI-018 | 1622 | 0 | Signed | 2017-Exxel, 36 Stone/Change Orders/CO_s/Stoneway CO 7.pdf
| COR-005 | COR | 2014-06-10 | Kitchen sink upgrades — Lenova/Elkay + Grohe pull-down faucet | Sub (OWP) |  | 7790 | 0 | Accepted | 2017-Exxel, 36 Stone/Change Orders/COR_s/36 Stone - OWP COR #05.pdf
| COR-006 | COR | 2014-06-11 | Rated washer connection boxes all 119 units | Sub (OWP) |  | 2685 | 0 | Accepted | 2017-Exxel, 36 Stone/Change Orders/COR_s/36 Stone - OWP COR #06.pdf
| COR-007 | COR | 2014-08-12 | Coffee maker water connection in lobby | Sub (OWP) | RFI-176 | 335 | 0 | Accepted | 2017-Exxel, 36 Stone/Change Orders/COR_s/36 Stone - OWP COR #07.pdf
| COR-008 | COR | 2014-08-20 | 1st floor leasing parcel undercounter sink + Grohe faucet | Sub (OWP) |  | 1885 | 0 | Accepted | 2017-Exxel, 36 Stone/Change Orders/COR_s/36 Stone - OWP COR #08.pdf
| COR-009 | COR | 2015-01-07 | Irrigation Point-of-Connection per RFI-234R2 | Sub (OWP) | RFI-234 | 2703 | 0 | Accepted | 2017-Exxel, 36 Stone/Change Orders/COR_s/36 Stone - OWP COR #09 RFI-234R2 Irrigation POC.pdf
| COR-010 | COR | 2015-01-26 | Gas fireplace POC on 2nd floor lounge per RFI-228 | Sub (OWP) | RFI-228 | 782 | 0 | Accepted | 2017-Exxel, 36 Stone/Change Orders/COR_s/36 Stone - OWP COR #10 RFI-228 Gas Fireplace POC.pdf
| COR-011 | COR | 2015-04-30 | Repair damaged tubs in units 423, 428, 426, 318, 319, 301, 207, 208 | Sub (OWP) |  | 1277 | 0 | Accepted | 2017-Exxel, 36 Stone/Change Orders/COR_s/36 Stone - OWP COR #11 Tub Repairs.pdf

## Root Cause Analysis
[CORTEX_V2.1] Job #2017 — · Root Cause Analysis
Schema CORTEX_V2.1 · canonical v2 builder · single source of truth
| rca_id | observation | root_cause | responsibility | cost_impact | mitigation | source
| RCA-01 | Delete filter fabric from footing drains contract | Pending document review — see source document for detail | OWP | -2100 |  | 2017-Exxel, 36 Stone/Change Orders/COR_s/36 Stone - OWP COR #01.pdf
| RCA-02 | Fitness Room bathroom sink — Kohler K-2084-0 in lieu of Elkay ELUH12V | Pending document review — see source document for detail | OWP | 495 |  | 2017-Exxel, 36 Stone/Change Orders/COR_s/36 Stone - OWP COR #02.pdf
| RCA-03 | Eliminate sewer vault + pumps (gravity drain to SW corner) | Pending document review — see source document for detail | GC | -6872 |  | 2017-Exxel, 36 Stone/Change Orders/CO_s/3636 change orders 3 through 6.pdf
| RCA-04 | Wall-mount sink Fitness Room (in lieu of countertop) | Pending document review — see source document for detail | GC | 495 |  | 2017-Exxel, 36 Stone/Change Orders/CO_s/3636 change orders 3 through 6.pdf
| RCA-05 | Delete filter fabric at footing drains | Pending document review — see source document for detail | GC | -2100 |  | 2017-Exxel, 36 Stone/Change Orders/CO_s/3636 change orders 3 through 6.pdf
| RCA-06 | Catch basin in lieu of trench drain at P1 garage ramp | Pending document review — see source document for detail | GC | -535 |  | 2017-Exxel, 36 Stone/Change Orders/CO_s/3636 change orders 3 through 6.pdf
| RCA-07 | 2 drains south residential patio + Type B→A ADA lavatory sink | Pending document review — see source document for detail | GC | 1622 |  | 2017-Exxel, 36 Stone/Change Orders/CO_s/Stoneway CO 7.pdf
| RCA-08 | Kitchen sink upgrades — Lenova/Elkay + Grohe pull-down faucet | Pending document review — see source document for detail | OWP | 7790 |  | 2017-Exxel, 36 Stone/Change Orders/COR_s/36 Stone - OWP COR #05.pdf
| RCA-09 | Rated washer connection boxes all 119 units | Pending document review — see source document for detail | OWP | 2685 |  | 2017-Exxel, 36 Stone/Change Orders/COR_s/36 Stone - OWP COR #06.pdf
| RCA-10 | Coffee maker water connection in lobby | Pending document review — see source document for detail | OWP | 335 |  | 2017-Exxel, 36 Stone/Change Orders/COR_s/36 Stone - OWP COR #07.pdf
| RCA-11 | 1st floor leasing parcel undercounter sink + Grohe faucet | Pending document review — see source document for detail | OWP | 1885 |  | 2017-Exxel, 36 Stone/Change Orders/COR_s/36 Stone - OWP COR #08.pdf
| RCA-12 | Irrigation Point-of-Connection per RFI-234R2 | Pending document review — see source document for detail | OWP | 2703 |  | 2017-Exxel, 36 Stone/Change Orders/COR_s/36 Stone - OWP COR #09 RFI-234R2 Irrigation POC.pdf
| RCA-13 | Gas fireplace POC on 2nd floor lounge per RFI-228 | Pending document review — see source document for detail | OWP | 782 |  | 2017-Exxel, 36 Stone/Change Orders/COR_s/36 Stone - OWP COR #10 RFI-228 Gas Fireplace POC.pdf
| RCA-14 | Repair damaged tubs in units 423, 428, 426, 318, 319, 301, 207, 208 | Pending document review — see source document for detail | OWP | 1277 |  | 2017-Exxel, 36 Stone/Change Orders/COR_s/36 Stone - OWP COR #11 Tub Repairs.pdf

## Predictive Signals
[CORTEX_V2.1] Job #2017 — · Predictive Signals
Schema CORTEX_V2.1 · canonical v2 builder · single source of truth
| signal_id | signal_name | direction | metric | threshold | historical_outcome | source
| WAREHOUSE | Predictive signals computed at warehouse layer | Neutral | cross-project benchmark | n/a | See benchmark_envelopes view; not stored per-project. | warehouse view (predictive_signals_v)

## Metric Registry
[CORTEX_V2.1] Job #2017 — · Metric Registry
Schema CORTEX_V2.1 · canonical v2 builder · single source of truth
| metric_key | metric_label | value | data_label | tab_home | verification | source
2017
Exxel Pacific 3636 Stone Way Apartments
Exxel Pacific, Inc.
Seattle, WA (3636 Stone Way N)
119-unit 4-story mixed-use apartments + ground-floor retail
16
119
801
1373148
1369989
-3159
1369989
510804.67
0.37285
859184.33
292755.75
378313.74
33855.5
154259.34
68499
14822
45
19.8726
20
142
-0.0023006
32
0
14
0
0
11
14
8462

## Reconciliation
[CORTEX_V2.1] Job #2017 — · Reconciliation
Schema CORTEX_V2.1 · canonical v2 builder · single source of truth
| check_number | check_description | value_a | value_b | difference | status | tabs
A. JDR COST CODE ROLLUP
|  | Labor subtotal (11 codes) | 292755.75 |  |  | TIES
|  | Material subtotal (10 codes) | 378313.74 |  |  | TIES
|  | Overhead subtotal (3 codes) | 33855.5 |  |  | TIES
|  | Burden subtotal (2 codes) | 154259.34 |  |  | TIES
|  | Direct Cost (all categories) | 859184.33 |  |  | TIES
|  | Revenue (code 999) | 1369989 |  |  | TIES
|  | Net Profit (Revenue - Expenses) | 510804.67 |  |  | TIES
B. LABOR HOURS ROLLUP
|  | JDR Cost Code hours (Payroll Hours lines) | 14822 |  |  | TIES
|  | Per-worker hours (sum of PR Regular) | 14822 |  |  | WITHIN
C. BILLING (SOV) ↔ JDR
|  | Final Contract Value | 1369989 |  |  | WITHIN
|  | Retainage | 68499 |  |  | TIES
|  | Direct Cost | 859184.33 |  |  | TIES
D. VENDOR AP ↔ JDR
|  | Vendor AP total (sum of invoices) | 401446 |  |  | OFF
SOURCES
Job #2017 — Exxel Pacific 3636 Stone Way Apartments • GC: Exxel Pacific, Inc. • Seattle, WA
Canonical source: 2017 Job Detail Report.pdf (124 pages, OWP Sage Timberline export)
Cost codes parsed: 27 (Labor+Material+Overhead+Burden+Revenue)
Unit count: 119 from Job Ticket (119 DWs, 119 washers)
Fixture count: Toto WCs 122, Grohe lavs 137, Aquatic tubs 122, Lenova/Elkay sinks 119 + common area
Billing: 36 STONE AGGREGATE BILLING.xlsx (14 pay apps, Feb 2014 – May 2015)
TIES = within $1 or 5 hrs • WITHIN = within 5% • OFF = investigate
K. CHANGE LOG ↔ ROOT CAUSE ANALYSIS
|  | Total Event Count | 14 |  |  | TIES
|  | Net $ Impact (all events) | 8462 |  |  | TIES
L. PREDICTIVE SIGNALS ↔ CHANGE LOG
|  | Backcharge Count signal | 0 |  |  | TIES
M. METRIC REGISTRY ↔ BENCHMARK KPIs
|  | revenue (row 17) | 1369989 |  |  | TIES
|  | unit_count (row 12) | 119 |  |  | TIES
|  | total_fixtures (row 13) | 801 |  |  | TIES
|  | direct_cost (row 19) | 859184.33 |  |  | OFF
|  | total_pos (row 30) | 142 |  |  | TIES
N. CHANGE LOG ↔ METRIC REGISTRY (event counts)
|  | change_event_total | 14 |  |  | OFF
SOURCES
Job #2017 — Cortex v2 17-tab layout
12 analytical tabs + Change Log + Root Cause Analysis + Predictive Signals + Metric Registry + Reconciliation
Canonical source: 2017 Job Detail Report.pdf (Sage Timberline export)
Change artifacts: folders scanned — ASI-RFI, Change Orders, Submittals, Invoices (Backcharges), JDR cost codes
Every Change Log row cites its source document path
TIES = within $1/5hrs/exact count • WITHIN = within 5% • OFF = investigate
Cross-sheet formulas (='Tab'!Cell) update automatically when source tabs change
Tabs: 1-12 analytical • 13=ChangeLog • 14=RootCause • 15=PredictiveSignals • 16=MetricRegistry • 17=Reconciliation

## Vendors
[CORTEX_V2.1] Job #2017 — · Vendors
Schema CORTEX_V2.1 · canonical v2 builder · single source of truth
| vendor_id | vendor_name | total_spend | transactions | category | source
Invoices
102
85
18
5
2
11
6
3
6
2
3
2
4
2
3
3
1
4
2
2