## Overview
[CORTEX_V2.1] Job #2018 — · Overview
Schema CORTEX_V2.1 · canonical v2 builder · single source of truth
| OVERVIEW |  | SOURCE
IDENTITY
| Project Job Number | 2018
| Project Name: | SRM Astro Apartments
CONTRACT & PARTIES
| General Contractor | SRMQA, LLC (SRM Development)
JOB SITE
| Jobsite Location | Seattle, WA
| Plumbing Units | 212 | Kitchen Sinks
| Levels | L2–L6 residential (N+S wings) + L1 retail/amenity + P1/P2/P3 parking | Below-grade
SCHEDULE
| Project Duration | Dec 2013 – Feb 2015 (~15 months)
SCOPE & DESIGN
| Total Fixtures | ~1,144 | Dishwashers
| Fixtures / Unit | 5.4 | Auto Washers
| CONTRACT VALUE |  | NET PROFIT |  | DIRECT COST |  | LABOR HOURS
| $2,282,726 |  | $1,072,788 |  | $1,232,270 |  | 47,132
| Original $2,282,726 |  | 46.5% margin |  | 53.5% of revenue |  | 58 workers
COST BREAKDOWN
| Category | Budget | Actual | Variance | % Budget | % of Cost
| Labor | 468235 | 440392.94 | 27842.06 | 94.05% | 35.74%
| Material | 722677 | 556906.77 | 165770.23 | 77.06% | 45.19%
| Overhead | 8150 | 4943.28 | 3206.72 | 60.65% | 0.4012%
| Burden | 243900.6 | 230026.81 | 13873.79 | 94.31% | 18.67%
| TOTAL | 1442962.6 | 1232269.8 | 210692.8 | 85.4% | 100%
PROJECT PROFILE
| Plumbing Units | 212 |  | Total Fixtures | ~1,144 |  | Fixtures / Unit | 5.4
| Floors | L2–L6 residential (N+S wings) + L1 retail/amenity + P1/P2/P3 parking |  | Duration | Dec 2013 – Feb 2015 (~15 months)

## Budget vs Actual
[CORTEX_V2.1] Job #2018 — · Budget vs Actual
Schema CORTEX_V2.1 · canonical v2 builder · single source of truth
| cost_code | description | original_budget | revised_budget | actual | variance | pct_used | hours | source
LABOR
| 011 | DS & RD Labor | 17545 | 19105 | 4039 | 15066 | 21.14%
| 100 | Supervision | 10000 | 10000 | 7795 | 2205 | 77.95%
| 101 | Takeoff & Purchase Labor | 10000 | 10440 | 9680 | 760 | 92.72%
| 110 | Underground Labor | 9330 | 9330 | 8108.75 | 1221.25 | 86.91%
| 111 | Garage Labor | 71700 | 71700 | 33852.25 | 37847.75 | 47.21%
| 112 | Canout Labor | 10400 | 10400 | 5609.75 | 4790.25 | 53.94%
| 113 | Foundation Drain Labor | 6625 | 6625 | 952 | 5673 | 14.37%
| 120 | Roughin Labor | 207140 | 208010 | 256945.47 | -48935.47 | 1.235%
| 130 | Finish Labor | 43900 | 44800 | 58292.75 | -13492.75 | 1.301%
| 140 | Gas Labor | 7200 | 8390 | 8626.5 | -236.5 | 1.028%
| 141 | Water Main/Insulation Lab | 40550 | 40550 | 31534.47 | 9015.53 | 77.77%
| 142 | Mech Room Labor | 8400 | 8400 | 14152 | -5752 | 1.685%
| 145 | Tub/Shower Labor | 20485 | 20485 | 805 | 19680 | 3.93%
MATERIAL
| 210 | Underground Material | 5900 | 5900 | 3233.67 | 2666.33 | 54.81%
| 211 | Garage Material | 45820 | 45820 | 74066.35 | -28246.35 | 1.616%
| 212 | Canout Material | 18200 | 18200 | 5771.34 | 12428.66 | 31.71%
| 213 | Foundation Material | 10600 | 10600 | 5372.56 | 5227.44 | 50.68%
| 220 | Roughin Material | 201680 | 201680 | 141396.65 | 60283.35 | 70.11%
| 230 | Finish Material | 390477 | 336907 | 272549.22 | 64357.78 | 80.9%
| 240 | Gas Material | 10800 | 10800 | 3578.52 | 7221.48 | 33.13%
| 241 | Water Main/Insulation Mat | 87250 | 87250 | 48338.27 | 38911.73 | 55.4%
| 242 | Mech Room Material | 5520 | 5520 | 1947.18 | 3572.82 | 35.27%
| 245 | Tub/Shower Material | 0 | 0 | 653.01 | -653.01 | 0%
OVERHEAD
| 600 | Subcontractor | 3000 | 3000 | 691.7 | 2308.3 | 23.06%
| 601 | Engineering/Plans | 3000 | 3000 | 2252.62 | 747.38 | 75.09%
| 603 | Permits & Licenses | 2000 | 2150 | 1998.96 | 151.04 | 92.97%
BURDEN
| 995 | Payroll Burden | 205165 | 207315.16 | 195501.68 | 11813.48 | 94.3%
| 998 | Payroll Taxes | 36206 | 36585.44 | 34525.13 | 2060.31 | 94.37%
SOURCES
Job #2018 — SRM Astro Apartments • GC: SRMQA, LLC (SRM Development) • Seattle, WA
Canonical source: 2018 Job Detail Report.pdf (183 pages, OWP Sage Timberline export)
Cost codes parsed: 29 (Labor+Material+Overhead+Burden+Revenue)
Unit count (212) from 11 Keller Supply per-level trim POs (L1N, L2N/S, L3N/S, L4N/S, L5N/S, L6N/S)
Per-level residential WCs: L2N=25, L2S=24, L3N=25, L3S=23, L4N=25, L4S=23, L5N=25, L5S=23, L6N=25, L6S=21 = 239 res + 3 common (L1N)
Billing: ASTRO AGGREGATE BILLING.xlsx (15 pay apps, Dec 2013 – Feb 2015) + 15 underlying SOV files
Change orders: 5 COs net +$22,332 (roof deck, ASK 40, sky lounge, trench drain, tub liners)
| TOTAL |  | 1488893 | 1442962.6 | 1232269.8 | 210692.8 |  | 0

## Cost Breakdown
[CORTEX_V2.1] Job #2018 — · Cost Breakdown
Schema CORTEX_V2.1 · canonical v2 builder · single source of truth
| category | cost_codes | actual | pct_of_direct_cost | pct_of_revenue | per_unit | source
| Labor | 13 | 468235 | 94.05% |  | 2077.3252
| Material | 10 | 722677 | 77.06% |  | 2626.9187
| Overhead | 3 | 8150 | 60.65% |  | 23.3174
| Burden | 2 | 243900.6 | 94.31% |  | 1085.0321
B. LARGEST OVERRUNS (Actual > Revised Budget)
| Code | Description
| 120 | Roughin Labor | 208010 | 23.53%
| 211 | Garage Material | 45820 | 61.65%
| 130 | Finish Labor | 44800 | 30.12%
| 142 | Mech Room Labor | 8400 | 68.48%
| 245 | Tub/Shower Material | 0 | 0%
| 140 | Gas Labor | 8390 | 2.819%
C. LARGEST SAVINGS (Actual < Revised Budget)
| Code | Description
| 230 | Finish Material | 336907 | 19.1%
| 220 | Roughin Material | 201680 | 29.89%
| 241 | Water Main/Insulation Mat | 87250 | 44.6%
| 111 | Garage Labor | 71700 | 52.79%
| 145 | Tub/Shower Labor | 20485 | 96.07%
| 011 | DS & RD Labor | 19105 | 78.86%
| 212 | Canout Material | 18200 | 68.29%
| 995 | Payroll Burden | 207315.16 | 5.698%
| 141 | Water Main/Insulation Lab | 40550 | 22.23%
| 240 | Gas Material | 10800 | 66.87%
SOURCES
Job #2018 — SRM Astro Apartments • GC: SRMQA, LLC (SRM Development) • Seattle, WA
Canonical source: 2018 Job Detail Report.pdf (183 pages, OWP Sage Timberline export)
Cost codes parsed: 29 (Labor+Material+Overhead+Burden+Revenue)
Unit count (212) from 11 Keller Supply per-level trim POs (L1N, L2N/S, L3N/S, L4N/S, L5N/S, L6N/S)
Per-level residential WCs: L2N=25, L2S=24, L3N=25, L3S=23, L4N=25, L4S=23, L5N=25, L5S=23, L6N=25, L6S=21 = 239 res + 3 common (L1N)
Billing: ASTRO AGGREGATE BILLING.xlsx (15 pay apps, Dec 2013 – Feb 2015) + 15 underlying SOV files
Change orders: 5 COs net +$22,332 (roof deck, ASK 40, sky lounge, trench drain, tub liners)
| TOTAL |  | 2772374.76 |  |  | 5812.5934

## Material
[CORTEX_V2.1] Job #2018 — · Material
Schema CORTEX_V2.1 · canonical v2 builder · single source of truth
| vendor_id | vendor_name | total_spend | transactions | category | source
| 210 | Underground Material | 5900 |  | 0.0058065
| 211 | Garage Material | 45820 |  | 0.133
| 212 | Canout Material | 18200 |  | 0.010363
| 213 | Foundation Material | 10600 |  | 0.0096471
| 220 | Roughin Material | 201680 |  | 0.2539
| 230 | Finish Material | 336907 |  | 0.4894
| 240 | Gas Material | 10800 |  | 0.0064257
| 241 | Water Main/Insulation Mat | 87250 |  | 0.086798
| 242 | Mech Room Material | 5520 |  | 0.0034964
| 245 | Tub/Shower Material | 0 |  | 0.0011726
B. VENDORS BY SPEND (AP)
| Vendor | # Invoices
| Rosen Supply Company, Inc. | 87 | 187929.87
| Keller Supply Company | 64 | 141063.76
| Ferguson Enterprises, Inc. | 45 | 65193.3
| Mechanical Sales, Inc. | 4 | 47527.77
| Consolidated Supply Co. | 21 | 43369.79
| Franklin Engineering | 6 | 23133.75
| Bank of America CC | 3 | 11633
| Quality Concrete Products, Inc. | 4 | 8875
| United Rentals, Inc. | 4 | 2252.62
| Ferguson Enterprises, Inc. #3007 | 3 | 934.77
| C.M. Hoskins Company | 4 | 654.66
| Kele, Inc | 2 | 637.54
| MAD Concrete Cutting & Coring, Inc. | 1 | 500
| Capital One Credit Card | 44 | 431.75
| Fastenal Company | 3 | 372.77
| DRSi | 2 | 354.99
| R.A. Brown Backflow Testing | 1 | 191.7
| Rosen Supply Kirkland | 2 | 111.82
| Core & Main LP | 1 | 29.39
SOURCES
Job #2018 — SRM Astro Apartments • GC: SRMQA, LLC (SRM Development) • Seattle, WA
Canonical source: 2018 Job Detail Report.pdf (183 pages, OWP Sage Timberline export)
Cost codes parsed: 29 (Labor+Material+Overhead+Burden+Revenue)
Unit count (212) from 11 Keller Supply per-level trim POs (L1N, L2N/S, L3N/S, L4N/S, L5N/S, L6N/S)
Per-level residential WCs: L2N=25, L2S=24, L3N=25, L3S=23, L4N=25, L4S=23, L5N=25, L5S=23, L6N=25, L6S=21 = 239 res + 3 common (L1N)
Billing: ASTRO AGGREGATE BILLING.xlsx (15 pay apps, Dec 2013 – Feb 2015) + 15 underlying SOV files
Change orders: 5 COs net +$22,332 (roof deck, ASK 40, sky lounge, trench drain, tub liners)
Vendor AP ties to JDR 'by Source: AP' line (535,198.25)

## Crew & Labor
[CORTEX_V2.1] Job #2018 — · Crew & Labor
Schema CORTEX_V2.1 · canonical v2 builder · single source of truth
| worker_id | worker_name | total_hours | gross_pay | blended_wage_per_hr | tier | work_days | source
| Waites, Thaddeus Z |  | 1056 | 29568 | 28 | Mid
| Reyes, Robert J |  | 1006.25 | 13441.25 | 13.3578 | Apprentice
| Cortes Mendiola, Victor H |  | 978.5 | 24497.5 | 25.0358 | Mid
| Sanders, Allen O |  | 941 | 28383.5 | 30.1631 | Senior
| Vaughan, Tyler J |  | 857.5 | 13751 | 16.0362 | Apprentice
| Castaneda Juarez, Edgar D |  | 855.5 | 12404.75 | 14.5 | Apprentice
| Anzora, William |  | 835.75 | 10864.75 | 13 | Apprentice
| Palma Vides, Hugo |  | 825.5 | 23138 | 28.0291 | Mid
| Arreola, Israel A |  | 824 | 13248 | 16.0777 | Apprentice
| Kinssies, Jr, John E |  | 762.5 | 12099.5 | 15.8682 | Apprentice
| Castaneda Martinez, Gustavo |  | 740 | 20720 | 28 | Mid
| Rivera, Eli P |  | 699.5 | 9417.5 | 13.4632 | Apprentice
| Ramos Banegas, Noel O |  | 686.25 | 9218.25 | 13.4328 | Apprentice
| Holmes, Anthony R |  | 639.5 | 9225 | 14.4253 | Apprentice
| Hubbard, Robert W |  | 636 | 21627 | 34.0047 | Senior
| Garcia, Jordan X |  | 636 | 9237 | 14.5236 | Apprentice
| Balderas Ortiz, Ricardo I |  | 624 | 8568 | 13.7308 | Apprentice
| Castro Hernandez, Jose A |  | 620.5 | 10548.5 | 17 | Apprentice
| Castaneda Juarez, Gustavo |  | 611 | 8554 | 14 | Apprentice
| Spears, Gregory M |  | 591.5 | 8281 | 14 | Apprentice
| Paco Leyva, Orlando |  | 589.5 | 10021.5 | 17 | Apprentice
| Monico Brambila, Jesus S |  | 581 | 8390 | 14.4406 | Apprentice
| McCabe, Thomas C |  | 580.5 | 10980 | 18.9147 | Mid
| Alba Martinez, Santiago |  | 571.5 | 8620.5 | 15.084 | Apprentice
| Meza Fuentes, Erick A |  | 506.75 | 10135 | 20 | Mid
| Reed, Reuben H |  | 495 | 13860 | 28 | Mid
| Gerard, Jeffrey S |  | 493.5 | 19039 | 38.5795 | Senior
| Lopez Martinez, Abimael |  | 479.25 | 5990.75 | 12.5003 | Apprentice
| Agustin Rodriguez, Ezequiel |  | 472 | 5664 | 12 | Apprentice
| Bateman, Rohan O |  | 367 | 4404 | 12 | Apprentice
| Velasquez Cruz, Denis M |  | 363 | 5453 | 15.022 | Apprentice
| Ross, Kelli M |  | 320 | 9280 | 29 | Mid
| Ramirez, Lorenzo A |  | 314.25 | 5028 | 16 | Apprentice
| Hubbard, Dustin R |  | 310 | 4030 | 13 | Apprentice
| Veley, Nathaniel S |  | 281.5 | 8163.5 | 29 | Mid
| Soto Cruz, Jovani |  | 226 | 3616 | 16 | Apprentice
| Salazar, Hajdar L |  | 208 | 3112 | 14.9615 | Apprentice
| Sepulveda Gonzalez, Alfredo |  | 202 | 5077 | 25.1337 | Mid
| Gonzalez Hernandez, Josue |  | 158.5 | 2219 | 14 | Apprentice
| Soto Serna, Cesar E |  | 134 | 1742 | 13 | Apprentice
| Reyes Cruz, Denis A |  | 133.5 | 1602 | 12 | Apprentice
| Ramos Garcia, Jose M |  | 88 | 1144 | 13 | Apprentice
| Gerard, Mitchell J |  | 74 | 898 | 12.1351 | Apprentice
| Nishiyama, Joshua K |  | 61 | 793 | 13 | Apprentice
| Sanchez Garcia, Adelaido |  | 56 | 728 | 13 | Apprentice
| Wilson, Garret A |  | 33 | 470 | 14.2424 | Apprentice
| Barnhart, Joseph N |  | 20.5 | 635.5 | 31 | Senior
| Donelson, Richard T |  | 20 | 900 | 45 | Senior
| TOTAL (48 workers) |  | 23566 | 448788.25 | 19.0439
SOURCES
Job #2018 — SRM Astro Apartments • GC: SRMQA, LLC (SRM Development) • Seattle, WA
Canonical source: 2018 Job Detail Report.pdf (183 pages, OWP Sage Timberline export)
Cost codes parsed: 29 (Labor+Material+Overhead+Burden+Revenue)
Unit count (212) from 11 Keller Supply per-level trim POs (L1N, L2N/S, L3N/S, L4N/S, L5N/S, L6N/S)
Per-level residential WCs: L2N=25, L2S=24, L3N=25, L3S=23, L4N=25, L4S=23, L5N=25, L5S=23, L6N=25, L6S=21 = 239 res + 3 common (L1N)
Billing: ASTRO AGGREGATE BILLING.xlsx (15 pay apps, Dec 2013 – Feb 2015) + 15 underlying SOV files
Change orders: 5 COs net +$22,332 (roof deck, ASK 40, sky lounge, trench drain, tub liners)
Tier: Apprentice <$18/hr, Mid $18–30, Senior >$30

## Crew Analytics
[CORTEX_V2.1] Job #2018 — · Crew Analytics
Schema CORTEX_V2.1 · canonical v2 builder · single source of truth
| tier | worker_count | hours | gross_pay | pct_of_hours | blended_wage
| Senior | 5 | 2111 | 70585 | 8.958%
| Mid | 10 | 5985.75 | 155419 | 25.4%
| Apprentice | 33 | 15469.25 | 222784.25 | 65.64%
B. WAGE STATISTICS
| Blended Gross Wage | 19.0439
| Fully-Loaded Wage | 28.4486
| Burden Multiplier | 1.4938
| Min Worker Rate | 12
| Max Worker Rate | 45
| Avg Hours / Worker | 490.9583
SOURCES
Job #2018 — SRM Astro Apartments • GC: SRMQA, LLC (SRM Development) • Seattle, WA
Canonical source: 2018 Job Detail Report.pdf (183 pages, OWP Sage Timberline export)
Cost codes parsed: 29 (Labor+Material+Overhead+Burden+Revenue)
Unit count (212) from 11 Keller Supply per-level trim POs (L1N, L2N/S, L3N/S, L4N/S, L5N/S, L6N/S)
Per-level residential WCs: L2N=25, L2S=24, L3N=25, L3S=23, L4N=25, L4S=23, L5N=25, L5S=23, L6N=25, L6S=21 = 239 res + 3 common (L1N)
Billing: ASTRO AGGREGATE BILLING.xlsx (15 pay apps, Dec 2013 – Feb 2015) + 15 underlying SOV files
Change orders: 5 COs net +$22,332 (roof deck, ASK 40, sky lounge, trench drain, tub liners)

## Productivity
[CORTEX_V2.1] Job #2018 — · Productivity
Schema CORTEX_V2.1 · canonical v2 builder · single source of truth
| phase | labor_code | hours | pct_of_total | hours_per_unit
| DS & RD | 011 | 258 | 1.107% | 1.217
| Supervision | 100 | 203 | 0.8712% | 0.95755
| Takeoff & Purchasing | 101 | 250.5 | 1.075% | 1.1816
| Underground | 110 | 340.5 | 1.461% | 1.6061
| Garage | 111 | 1616 | 6.935% | 7.6226
| Canout | 112 | 238 | 1.021% | 1.1226
| Foundation Drain | 113 | 49 | 0.2103% | 0.23113
| Roughin | 120 | 14241 | 61.12% | 67.1745
| Finish | 130 | 2845 | 12.21% | 13.4198
| Gas | 140 | 429.5 | 1.843% | 2.0259
| Water Main / Insulation | 141 | 1935.5 | 8.307% | 9.1297
| Mech Room | 142 | 856 | 3.674% | 4.0377
| Tub / Shower | 145 | 38.5 | 0.1652% | 0.1816
B. PRODUCTIVITY RATIOS
| Metric | Value
| Hours / Unit | 109.908
| Hours / Fixture | 20.3676
| Revenue / Hour | 98.9274
| Profit / Hour | 46.0414
| Units / Month | 14.1333
| Fixtures / Month | 76.2667
| Hours / Month | 1553.3667
| Revenue / Month | 153670.5333
SOURCES
Job #2018 — SRM Astro Apartments • GC: SRMQA, LLC (SRM Development) • Seattle, WA
Canonical source: 2018 Job Detail Report.pdf (183 pages, OWP Sage Timberline export)
Cost codes parsed: 29 (Labor+Material+Overhead+Burden+Revenue)
Unit count (212) from 11 Keller Supply per-level trim POs (L1N, L2N/S, L3N/S, L4N/S, L5N/S, L6N/S)
Per-level residential WCs: L2N=25, L2S=24, L3N=25, L3S=23, L4N=25, L4S=23, L5N=25, L5S=23, L6N=25, L6S=21 = 239 res + 3 common (L1N)
Billing: ASTRO AGGREGATE BILLING.xlsx (15 pay apps, Dec 2013 – Feb 2015) + 15 underlying SOV files
Change orders: 5 COs net +$22,332 (roof deck, ASK 40, sky lounge, trench drain, tub liners)

## PO Commitments
[CORTEX_V2.1] Job #2018 — · PO Commitments
Schema CORTEX_V2.1 · canonical v2 builder · single source of truth
| po_number | date | issuer | type | status | description | amount | source
| 30 |  |  |  |  | 110+210 Underground
| 31 |  |  |  |  | 120+220 Roughin
| 32 |  |  |  |  | 130+230 Trim/Finish
| 40 |  |  |  |  | 141+241 Water Main/Ins
| 41 |  |  |  |  | 140+240 Gas
| OTHER |  |  |  |  | Unclassified
B. COMMITMENTS BY VENDOR
| Vendor |  |  |  |  | PO Count
| ROSEN |  |  |  |  | 49
| KELLER |  |  |  |  | 38
| OTHER |  |  |  |  | 23
| FEI |  |  |  |  | 19
| CONSOLIDATED |  |  |  |  | 13
| MECH SALES |  |  |  |  | 2
| FASTENAL |  |  |  |  | 2
| SIOUX CHIEF |  |  |  |  | 1
C. PO COVERAGE NOTES
Total Material Actual (JDR)
Unique PO Count
(Dollar PO commitment not extracted — requires per-PDF parse)
SOURCES
Job #2018 — SRM Astro Apartments • GC: SRMQA, LLC (SRM Development) • Seattle, WA
Canonical source: 2018 Job Detail Report.pdf (183 pages, OWP Sage Timberline export)
Cost codes parsed: 29 (Labor+Material+Overhead+Burden+Revenue)
Unit count (212) from 11 Keller Supply per-level trim POs (L1N, L2N/S, L3N/S, L4N/S, L5N/S, L6N/S)
Per-level residential WCs: L2N=25, L2S=24, L3N=25, L3S=23, L4N=25, L4S=23, L5N=25, L5S=23, L6N=25, L6S=21 = 239 res + 3 common (L1N)
Billing: ASTRO AGGREGATE BILLING.xlsx (15 pay apps, Dec 2013 – Feb 2015) + 15 underlying SOV files
Change orders: 5 COs net +$22,332 (roof deck, ASK 40, sky lounge, trench drain, tub liners)
PO count is deduplicated by 5-digit PO number extracted from filenames
Vendor/code classification is heuristic (filename keyword match)

## Billing & SOV
[CORTEX_V2.1] Job #2018 — · Billing & SOV
Schema CORTEX_V2.1 · canonical v2 builder · single source of truth
| pay_app_number | date | contract_total | this_period | retainage | stored_materials | cumulative | pct_complete | source
| 13 | 2014-12-15 | 2298765 | 52000 | 0 | 0 | 2248539 | 97.82%
| 14 | 2015-01-22 | 2298765 | 32410 | 0 | 0 | 2280949 | 99.22%
| 15 | 2015-02-25 | 2305058 | 24109 | 0 | 0 | 2305058 | 100%
| 2 | 2014-01-23 | 2282726 | 69200 | 0 | 0 | 133200 | 5.84%
| 11 | 2014-10-23 | 2298765 | 53690 | 0 | 0 | 2118139 | 92.14%
| 1 | 2013-12-19 | 2282726 | 64000 | 0 | 0 | 64000 | 2.8%
| 12 | 2014-11-18 | 2298765 | 78400 | 0 | 0 | 2196539 | 95.55%
| 3 | 2014-02-25 | 2285319 | 21900 | 0 | 0 | 155100 | 6.79%
| 4 | 2014-03-25 | 2285319 | 71500 | 0 | 0 | 226600 | 9.92%
| 5 | 2014-04-25 | 2285319 | 152200 | 0 | 0 | 378800 | 16.58%
| 6 | 2014-05-22 | 2285319 | 526600 | 0 | 0 | 905400 | 39.62%
| 7 | 2014-06-24 | 2285319 | 766800 | 0 | 0 | 1672200 | 73.17%
| 8 | 2014-07-24 | 2285319 | 245793 | 0 | 0 | 1917993 | 83.93%
| 9 | 2014-08-25 | 2285875 | 77356 | 0 | 0 | 1995349 | 87.29%
| 10 | 2014-09-25 | 2298765 | 69100 | 0 | 0 | 2064449 | 89.81%
| 13 | 2014-12-15 | 2298765 | 52000 | 0 | 0 | 2248539 | 97.82%
| 14 | 2015-01-22 | 2298765 | 32410 | 0 | 0 | 2280949 | 99.22%
| 15 | 2015-02-25 | 2305058 | 24109 | 0 | 0 | 2305058 | 100%
| 2 | 2014-01-23 | 2282726 | 69200 | 0 | 0 | 133200 | 5.84%
| 11 | 2014-10-23 | 2298765 | 53690 | 0 | 0 | 2118139 | 92.14%
| 1 | 2013-12-19 | 2282726 | 64000 | 0 | 0 | 64000 | 2.8%
| 12 | 2014-11-18 | 2298765 | 78400 | 0 | 0 | 2196539 | 95.55%
| 3 | 2014-02-25 | 2285319 | 21900 | 0 | 0 | 155100 | 6.79%
| 4 | 2014-03-25 | 2285319 | 71500 | 0 | 0 | 226600 | 9.92%
| 5 | 2014-04-25 | 2285319 | 152200 | 0 | 0 | 378800 | 16.58%
| 6 | 2014-05-22 | 2285319 | 526600 | 0 | 0 | 905400 | 39.62%
| 7 | 2014-06-24 | 2285319 | 766800 | 0 | 0 | 1672200 | 73.17%
| 8 | 2014-07-24 | 2285319 | 245793 | 0 | 0 | 1917993 | 83.93%
| 9 | 2014-08-25 | 2285875 | 77356 | 0 | 0 | 1995349 | 87.29%
| 10 | 2014-09-25 | 2298765 | 69100 | 0 | 0 | 2064449 | 89.81%

## Insights
[CORTEX_V2.1] Job #2018 — · Insights
Schema CORTEX_V2.1 · canonical v2 builder · single source of truth
| insight_id | title | finding | verified | source
| 1 | Labor tracked within 5% of budget | Total labor actual $440,393 vs budget $463,275 — -$22,882 variance. | Derived | budget_vs_actual
| 2 | Scope stability — 6 executed COs net $23,638 (+0.00% of contract) | Minimal scope churn indicates well-defined contract and experienced GC. Candidate GC profile for future similar bids. | Derived | change_log
| 3 | Largest variance — cost code 230 (Finish Material) under by $64,358 | Budget $336,907, actual $272,549 (-19.1%). Flag for bid calibration. | Derived | budget_vs_actual

## Benchmark KPIs
[CORTEX_V2.1] Job #2018 — · Benchmark KPIs
Schema CORTEX_V2.1 · canonical v2 builder · single source of truth
CROSS-PROJECT BENCHMARK SCORECARD
Normalized metrics designed for apples-to-apples comparison across all OWP projects.
| KPI | DATA NAME | VALUE | CATEGORY | NOTES / BENCHMARK CONTEXT
| Job Number | job_number | 2,018 | Profile | OWP Sage job ID
| General Contractor | general_contractor | SRMQA, LLC (SRM Development) | Profile | Customer of record
| location | location | Seattle, WA | Profile | Project address
| Project Type | project_type | Apartment building | Profile | Building category for benchmarking
| Duration Months | duration_months | 15.0% | Profile | Calendar months from start to close
| Plumbing Units | plumbing_units | 212 | Profile | Residential units delivered
| Total Fixtures | total_fixtures | 1 | Profile | Plumbing fixture count
| Fixtures Per Unit | fixtures_per_unit | $0.00 | Profile | ≈6 fixtures/unit typical for multifamily
| Contract Original | contract_original | $2,282,726 | Financial | Original contract value
| Contract Final | contract_final | $2,282,726 | Financial | Revised contract value (post-COs)
| Change Orders Net | change_orders_net | 0 | Financial | Net dollar change from COs
| revenue | revenue | $2,305,058 | Financial | Net billed (AR net of reversals)
| Net Profit | net_profit | $1,072,788 | Financial | Revenue − direct cost
| Gross Margin Pct | gross_margin_pct | 46.5% | Financial | Net profit / revenue
| Direct Cost | direct_cost | $1,232,270 | Financial | Σ labor + material + OH + burden + tax
| Overhead Cost | overhead_cost | $4,943 | Financial | Codes 600, 601, 603, 607
| Burden Cost | burden_cost | $195,502 | Financial | Code 995 payroll burden
| Retainage Outstanding | retainage_outstanding | $0.00 | Financial | Held by GC until closeout
| Revenue Per Unit | revenue_per_unit | $10,873 | Financial | Top-line per unit
| Profit Per Unit | profit_per_unit | $5,060 | Financial | Net profit normalized per residential unit
| Cost Per Unit | cost_per_unit | $5,813 | Financial | Total direct cost per unit
| Revenue Per Fixture | revenue_per_fixture | $2,305,058 | Financial | Top-line per fixture
| Profit Per Fixture | profit_per_fixture | $1,072,788 | Financial | Net profit per fixture installed
| Cost Per Fixture | cost_per_fixture | $1,232,270 | Financial | Total direct cost per fixture
| Labor Cost | labor_cost | $440,393 | Labor | Codes 100–150
| Total Hours | total_hours | 47,132 | Labor | All payroll hours on the job
| Total Workers | total_workers | 58 | Crew | Unique payroll IDs across job
| Blended Wage | blended_wage | $19.04 | Labor | Pre-burden average
| Fully Loaded Wage | fully_loaded_wage | $14.22 | Labor | Post-burden true cost
| Burden Multiplier | burden_multiplier | 0.75 | Labor | Loaded / gross
| Hours Per Unit | hours_per_unit | $0.00 | Labor | Key plumbing benchmark
| Hours Per Fixture | hours_per_fixture | $0.00 | Labor | Industry std for plumbing subs
| Labor Per Unit | labor_per_unit | $2,077 | Labor | Payroll only, not material
| Labor Per Fixture | labor_per_fixture | $440,393 | Labor | Payroll only, not material
| Labor Pct Revenue | labor_pct_revenue | 0.19 | Cost Mix | Payroll exposure
| Material Cost | material_cost | $556,907 | Material | Codes 210–244
| Material Per Unit | material_per_unit | $2,627 | Material | Cross-project benchmark
| Material Per Fixture | material_per_fixture | $556,907 | Material | Cross-project benchmark
| Material Pct Revenue | material_pct_revenue | 0.24 | Cost Mix | Material/sub exposure
| Total Vendors | total_vendors | 20 | Material | Distinct AP vendors invoiced on the job
| Top Vendor Spend | top_vendor_spend | $0.00 | Material | Largest single supplier
| Top Vendor Pct | top_vendor_pct | 0.0% | Material | Top vendor concentration
| Revenue Per Month | revenue_per_month | $153,671 | Throughput | Billing velocity
| Hours Per Month | hours_per_month | $0.00 | Throughput | Avg monthly labor burn
| Units Per Month | units_per_month | $14.13 | Throughput | Build pace
| Fixtures Per Month | fixtures_per_month | $0.07 | Throughput | Fixture install velocity
SOURCES
Canonical: /sessions/keen-determined-mccarthy/mnt/cortex-mockup/owp/cortex v2 files/OWP_2018_JCR_Cortex_v2.xlsx
revenue: AR net-of-reversals (validator)
labor_cost: Codes 100–150
material_cost: Codes 210–244
total_workers: count(distinct worker_id)

## Change Log
[CORTEX_V2.1] Job #2018 — · Change Log
Schema CORTEX_V2.1 · canonical v2 builder · single source of truth
| event_id | type | date | subject | originator | linked_events | cost_impact | schedule_days | status | source_document
| COR-001 | COR | 2014-07-29 | Rooftop items — trench drain dog run + 6 gas heaters + BBQ + waste/water piping BBQ sinks | Sub (OWP) |  | 8985 | 0 | Approved | 2018-SRM, Astro/Change Orders/COR_s/Astro - OWP COR #01 Rooftop Items.pdf
| COR-002 | COR | 2014-09-19 | ASI-020 replumb washer/dryer — maintenance access to courtyards (demo+recore+replumb) | Sub (OWP) | ASI-020 | 3905 | 0 | Approved | 2018-SRM, Astro/Change Orders/COR_s/Astro - OWP COR #02 ASI-020 Replumbing.pdf
| COR-003 | COR | 2014-10-22 | ASI-024 Common & Media Lounge sinks (move + add) | Sub (OWP) | ASI-024 | 2374 | 0 | Approved | 2018-SRM, Astro/Change Orders/COR_s/Astro - OWP COR #03 ASI-024.pdf
| COR-004 | COR | 2015-01-23 | Added trench drain at north entrance | Sub (OWP) |  | 2037 | 0 | Approved | 2018-SRM, Astro/Change Orders/COR_s/Astro - OWP COR #04 ADDED TRENCH DRAIN.pdf
| COR-005 | COR | 2015-01-23 | Added drinking fountain Elkay EEZSDL | Sub (OWP) |  | 1882 | 0 | Approved | 2018-SRM, Astro/Change Orders/COR_s/Astro - OWP COR #05 ADDED DRINKING FOUNTAIN.pdf
| COR-006 | COR | 2015-06-19 | ASI-042 BBQ gas system mod — pull pavers, demo, install, test, restore (40 hrs) | Sub (OWP) | ASI-042 | 4455 | 0 | Approved | 2018-SRM, Astro/Change Orders/COR_s/Astro - OWP COR #06 ASI-042 ADDED BARBECUES.pdf
| ASI-001 | ASI | 2014-01-13 | Residential garage entry widened + Media room wall relocation + mech layout revisions | Runberg (Eric Blank) |  | 0 | 0 | Closed | 2018-SRM, Astro/ASI-RFI/ASI 01 - Residential Garage Entry Reconfiguration.pdf
| ASI-002 | ASI | 2014-02-05 | Commercial garage entry reconfiguration | Runberg |  | 0 | 0 | Closed | 2018-SRM, Astro/ASI-RFI/ASI 02 - Commercial Garage Entry Reconfiguration.pdf
| ASI-003 | ASI | 2014-02-19 | Grand lobby stair redesign + structural column relocation (SBC 2406.4.11) | Runberg (Eric Blank) | ASK-08 | 0 | 0 | Closed | 2018-SRM, Astro/ASI-RFI/ASI 03 - Lobby Stair Redesign.pdf
| ASI-004 | ASI |  | VTHP louvers in x06 stack | Runberg |  | 0 | 0 | Closed | 2018-SRM, Astro/ASI-RFI/ASI 04 - VTHP Louvers in x06 Stack.pdf
| ASI-005 | ASI |  | 2 Hour walls at electrical shafts (code) | Runberg |  | 0 | 0 | Closed | 2018-SRM, Astro/ASI-RFI/ASI 05 - 2 Hour Walls at Electrical Shafts.pdf
| ASI-007 | ASI |  | AV closet at media room | Runberg |  | 0 | 0 | Closed | 2018-SRM, Astro/ASI-RFI/ASI 07 - AV Closet at Media Room.pdf
| ASI-010 | ASI |  | Common area ID changes | Runberg |  | 0 | 0 | Closed | 2018-SRM, Astro/ASI-RFI/ASI 10 - Common Area ID Changes.pdf
| ASI-013 | ASI |  | Final roof deck revisions | Runberg |  | 0 | 0 | Closed | 2018-SRM, Astro/ASI-RFI/ASI 13 - Final Roof Deck Revisions.pdf
| RFI-031 | RFI |  | Structural — mail room wall concrete curb | Sub |  | 0 | 0 | Closed | 2018-SRM, Astro/ASI-RFI/RFI # 31 - STRUCTURAL - MAIL ROOM WALL CONCRETE CURB- Response.pdf
| RFI-032 | RFI |  | Architectural — adaptable showers in Unit Types L and F | Sub |  | 0 | 0 | Closed | 2018-SRM, Astro/ASI-RFI/RFI # 32 - ARCHITECTURAL - ADAPTABLE SHOWERS IN UNIT TYPES L AND F - Response.pdf
| RFI-036 | RFI |  | Architectural — concrete feature strips at alley wall | Sub |  | 0 | 0 | Closed | 2018-SRM, Astro/ASI-RFI/RFI # 36 - ARCHITECTURAL - CONCRETE FEATURE STRIPS AT ALLEY WALL- Response.pdf
| RFI-049 | RFI |  | Architectural — retail blade sign locations | Sub |  | 0 | 0 | Closed | 2018-SRM, Astro/ASI-RFI/RFI # 49 - ARCHITECTURAL - RETAIL BLADE SIGN LOCATIONS- Response.pdf
| RFI-057 | RFI |  | Architectural — shower head heights (accessibility) | Sub |  | 0 | 0 | Closed | 2018-SRM, Astro/ASI-RFI/RFI # 57 -ARCHITECTURAL - SHOWER HEAD HEIGHTS-Response.pdf
| DOC-GAP-CONTRACT | Memo |  | GAP: original/final contract $ not stated in reviewed docs; 6 CORs total $25,338 but baseline unknown. Schedule_days = 0 on all CORs likely understated. | OWP |  | 0 | 0 | Open | 2018-SRM, Astro/Contract/astro contrct.pdf

## Root Cause Analysis
[CORTEX_V2.1] Job #2018 — · Root Cause Analysis
Schema CORTEX_V2.1 · canonical v2 builder · single source of truth
| rca_id | observation | root_cause | responsibility | cost_impact | mitigation | source
| RCA-01 | Rooftop items — trench drain dog run + 6 gas heaters + BBQ + waste/water piping BBQ sinks | Pending document review — see source document for detail | OWP | 8985 |  | 2018-SRM, Astro/Change Orders/COR_s/Astro - OWP COR #01 Rooftop Items.pdf
| RCA-02 | ASI-020 replumb washer/dryer — maintenance access to courtyards (demo+recore+replumb) | Pending document review — see source document for detail | OWP | 3905 |  | 2018-SRM, Astro/Change Orders/COR_s/Astro - OWP COR #02 ASI-020 Replumbing.pdf
| RCA-03 | ASI-024 Common & Media Lounge sinks (move + add) | Pending document review — see source document for detail | OWP | 2374 |  | 2018-SRM, Astro/Change Orders/COR_s/Astro - OWP COR #03 ASI-024.pdf
| RCA-04 | Added trench drain at north entrance | Pending document review — see source document for detail | OWP | 2037 |  | 2018-SRM, Astro/Change Orders/COR_s/Astro - OWP COR #04 ADDED TRENCH DRAIN.pdf
| RCA-05 | Added drinking fountain Elkay EEZSDL | Pending document review — see source document for detail | OWP | 1882 |  | 2018-SRM, Astro/Change Orders/COR_s/Astro - OWP COR #05 ADDED DRINKING FOUNTAIN.pdf
| RCA-06 | ASI-042 BBQ gas system mod — pull pavers, demo, install, test, restore (40 hrs) | Pending document review — see source document for detail | OWP | 4455 |  | 2018-SRM, Astro/Change Orders/COR_s/Astro - OWP COR #06 ASI-042 ADDED BARBECUES.pdf

## Predictive Signals
[CORTEX_V2.1] Job #2018 — · Predictive Signals
Schema CORTEX_V2.1 · canonical v2 builder · single source of truth
| signal_id | signal_name | direction | metric | threshold | historical_outcome | source
| WAREHOUSE | Predictive signals computed at warehouse layer | Neutral | cross-project benchmark | n/a | See benchmark_envelopes view; not stored per-project. | warehouse view (predictive_signals_v)

## Metric Registry
[CORTEX_V2.1] Job #2018 — · Metric Registry
Schema CORTEX_V2.1 · canonical v2 builder · single source of truth
| metric_key | metric_label | value | data_label | tab_home | verification | source
2018
SRM Astro Apartments
SRMQA, LLC (SRM Development)
Seattle, WA
6-story multifamily apartments + 3 levels below-grade parking + retail/amenity
15
212
1144
2282726
2305058
22332
2305058
1072788.2
0.46541
1232269.8
440392.94
556906.77
4943.28
230026.81
115253
23300.5
48
19.2609
19
147
0.009783
5
8
6
0
0
8
20
23638

## Reconciliation
[CORTEX_V2.1] Job #2018 — · Reconciliation
Schema CORTEX_V2.1 · canonical v2 builder · single source of truth
| check_number | check_description | value_a | value_b | difference | status | tabs
A. JDR COST CODE ROLLUP
|  | Labor subtotal (13 codes) | 440392.94 |  |  | TIES
|  | Material subtotal (10 codes) | 556906.77 |  |  | TIES
|  | Overhead subtotal (3 codes) | 4943.28 |  |  | TIES
|  | Burden subtotal (2 codes) | 230026.81 |  |  | TIES
|  | Direct Cost (all categories) | 1232269.8 |  |  | TIES
|  | Revenue (code 999) | 2305058 |  |  | TIES
|  | Net Profit (Revenue - Expenses) | 1072788.2 |  |  | TIES
B. LABOR HOURS ROLLUP
|  | JDR Cost Code hours (Payroll Hours lines) | 23300.5 |  |  | TIES
|  | Per-worker hours (sum of PR Regular) | 23300.5 |  |  | WITHIN
C. BILLING (SOV) ↔ JDR
|  | Final Contract Value | 2305058 |  |  | TIES
|  | Retainage | 115253 |  |  | TIES
|  | Direct Cost | 1232269.8 |  |  | TIES
D. VENDOR AP ↔ JDR
|  | Vendor AP total (sum of invoices) | 529698 |  |  | WITHIN
SOURCES
Job #2018 — SRM Astro Apartments • GC: SRMQA, LLC (SRM Development) • Seattle, WA
Canonical source: 2018 Job Detail Report.pdf (183 pages, OWP Sage Timberline export)
Cost codes parsed: 29 (Labor+Material+Overhead+Burden+Revenue)
Unit count (212) from 11 Keller Supply per-level trim POs (L1N, L2N/S, L3N/S, L4N/S, L5N/S, L6N/S)
Per-level residential WCs: L2N=25, L2S=24, L3N=25, L3S=23, L4N=25, L4S=23, L5N=25, L5S=23, L6N=25, L6S=21 = 239 res + 3 common (L1N)
Billing: ASTRO AGGREGATE BILLING.xlsx (15 pay apps, Dec 2013 – Feb 2015) + 15 underlying SOV files
Change orders: 5 COs net +$22,332 (roof deck, ASK 40, sky lounge, trench drain, tub liners)
TIES = within $1 or 5 hrs • WITHIN = within 5% • OFF = investigate
K. CHANGE LOG ↔ ROOT CAUSE ANALYSIS
|  | Total Event Count | 20 |  |  | TIES
|  | Net $ Impact (all events) | 23638 |  |  | TIES
L. PREDICTIVE SIGNALS ↔ CHANGE LOG
|  | Backcharge Count signal | 0 |  |  | TIES
M. METRIC REGISTRY ↔ BENCHMARK KPIs
|  | revenue (row 17) | 2305058 |  |  | TIES
|  | unit_count (row 12) | 212 |  |  | TIES
|  | total_fixtures (row 13) | 1144 |  |  | TIES
|  | direct_cost (row 19) | 1232269.8 |  |  | OFF
|  | total_pos (row 30) | 147 |  |  | TIES
N. CHANGE LOG ↔ METRIC REGISTRY (event counts)
|  | change_event_total | 20 |  |  | OFF
SOURCES
Job #2018 — Cortex v2 17-tab layout
12 analytical tabs + Change Log + Root Cause Analysis + Predictive Signals + Metric Registry + Reconciliation
Canonical source: 2018 Job Detail Report.pdf (Sage Timberline export)
Change artifacts: folders scanned — ASI-RFI, Change Orders, Submittals, Invoices (Backcharges), JDR cost codes
Every Change Log row cites its source document path
TIES = within $1/5hrs/exact count • WITHIN = within 5% • OFF = investigate
Cross-sheet formulas (='Tab'!Cell) update automatically when source tabs change
Tabs: 1-12 analytical • 13=ChangeLog • 14=RootCause • 15=PredictiveSignals • 16=MetricRegistry • 17=Reconciliation

## Vendors
[CORTEX_V2.1] Job #2018 — · Vendors
Schema CORTEX_V2.1 · canonical v2 builder · single source of truth
| vendor_id | vendor_name | total_spend | transactions | category | source
Invoices
87
64
45
4
21
6
3
4
4
3
4
2
1
44
3
2
1
2
1