## Overview
[CORTEX_V2.1] Job #2019 — · Overview
Schema CORTEX_V2.1 · canonical v2 builder · single source of truth
| OVERVIEW |  | SOURCE
IDENTITY
| Project Job Number | 2019
| Project Name: | Exxel Pacific 8th & Republican Apartments
CONTRACT & PARTIES
| General Contractor | Exxel Pacific, Inc. (Owner: The Wolff Company)
JOB SITE
| Jobsite Location | Seattle, WA (430 8th Ave N)
| Plumbing Units | 211 | Kitchen Sinks
| Floors | L1 retail/amenity + L2–L8 residential | Urinals
SCHEDULE
| Project Duration | Sep 2014 – Jul 2016 (~22 months)
SCOPE & DESIGN
| Total Fixtures | 1,196 | Dishwashers
| Fixtures / Unit | 5.67 | Auto Washers
| Roof Drains | 10
| CONTRACT VALUE |  | NET PROFIT |  | DIRECT COST |  | LABOR HOURS
| $2,721,210 |  | $1,353,160 |  | $1,524,059 |  | 52,897
| Original $2,721,210 |  | 47.0% margin |  | 53.0% of revenue |  | 68 workers
COST BREAKDOWN
| Category | Budget | Actual | Variance | % Budget | % of Cost
| Labor | 630261 | 550832.62 | 79428.38 | 87.4% | 36.14%
| Material | 974017 | 660548.93 | 313468.07 | 67.82% | 43.34%
| Overhead | 65850 | 59981.3 | 5868.7 | 91.09% | 3.936%
| Burden | 297111.35 | 252695.88 | 44415.47 | 85.05% | 16.58%
| TOTAL | 1967239.35 | 1524058.73 | 443180.62 | 77.47% | 100%
PROJECT PROFILE
| Plumbing Units | 211 |  | Total Fixtures | 1,196 |  | Fixtures / Unit | 5.67
| Roof Drains | 10 |  | Floors | L1 retail/amenity + L2–L8 residential |  | Duration | Sep 2014 – Jul 2016 (~22 months)

## Budget vs Actual
[CORTEX_V2.1] Job #2019 — · Budget vs Actual
Schema CORTEX_V2.1 · canonical v2 builder · single source of truth
| cost_code | description | original_budget | revised_budget | actual | variance | pct_used | hours | source
LABOR
| 100 | Supervision | 14700 | 18480 | 13841.5 | 4638.5 | 74.9%
| 101 | Takeoff & Purchase Labor | 14700 | 26068 | 27212.5 | -1144.5 | 1.044%
| 110 | Underground Labor | 12700 | 12700 | 11835 | 865 | 93.19%
| 111 | Garage Labor | 80400 | 84100 | 65168.5 | 18931.5 | 77.49%
| 112 | Canout Labor | 44800 | 48150 | 47229 | 921 | 98.09%
| 120 | Roughin Labor | 281500 | 294635 | 301244.35 | -6609.35 | 1.022%
| 130 | Finish Labor | 54000 | 55373 | 36001.25 | 19371.75 | 65.02%
| 140 | Gas Labor | 14700 | 15325 | 7665 | 7660 | 50.02%
| 141 | Water Main/Insulation Lab | 74800 | 75430 | 39821.52 | 35608.48 | 52.79%
| 142 | Mech Room Labor | 0 | 0 | 814 | -814 | 0%
MATERIAL
| 210 | Underground Material | 16500 | 16500 | 9932.16 | 6567.84 | 60.19%
| 211 | Garage Material | 55800 | 57063 | 22168.78 | 34894.22 | 38.85%
| 212 | Canout Material | 69200 | 69350 | 40231.97 | 29118.03 | 58.01%
| 220 | Roughin Material | 212400 | 215686 | 176444.92 | 39241.08 | 81.81%
| 230 | Finish Material | 461500 | 488611 | 313722.19 | 174888.81 | 64.21%
| 240 | Gas Material | 10300 | 10532 | 4568.01 | 5963.99 | 43.37%
| 241 | Water Main/Insulation Mat | 83500 | 83775 | 69305.69 | 14469.31 | 82.73%
| 242 | Mech Room Material | 32500 | 32500 | 24175.21 | 8324.79 | 74.39%
| 244 | Fire Caulking Material | 0 | 0 | 0 | 0 | 0%
OVERHEAD
| 600 | Subcontractor | 21600 | 45850 | 31086.35 | 14763.65 | 67.8%
| 601 | Engineering/Plans | 5000 | 5000 | 10226 | -5226 | 2.045%
| 603 | Permits & Licenses | 15000 | 15000 | 18668.95 | -3668.95 | 1.245%
BURDEN
| 995 | Payroll Burden | 262831.05 | 247825.38 | 209946.79 | 37878.59 | 84.72%
| 998 | Payroll Taxes | 46381.95 | 49285.97 | 42749.09 | 6536.88 | 86.74%
SOURCES
Job #2019 — Exxel Pacific 8th & Republican Apartments • GC: Exxel Pacific, Inc. (Owner: The Wolff Company) • Seattle, WA
Canonical source: 2019 Job Detail Report.pdf (249 pages, OWP Sage Timberline export)
Cost codes parsed: 25 (Labor+Material+Overhead+Burden+Revenue)
Unit count (211) confirmed by two independent sources:
1) Keller Supply consolidated trim PO (8TH REP TRIM - KELLER.xlsx): 211 Delta 4159-DST kitchen faucets
2) Seattle/King County plumbing permit #1459 ($11,925 fee, 10/23/2014): Water Closet field = 211
Fixture breakdown from same permit: Lavs 255, Tubs/Showers 214, Kitchen 211, DW 211, Floor Drains 49, Urinals 2, Sump 8, Roof Drains 10, + misc = ~1,196
Billing: REPUBLICAN AGGREGATE BILLING.xlsx (20 pay apps, Sep 2014 – Jun 2016) + 20 underlying SOV files
Change orders: 10 COs net +$156,008.60 (can layout, acoustical wrap, added boilers, ASI 15/48, premium time, etc.)
| TOTAL |  | 1884813 | 1967239.35 | 1524058.73 | 443180.62 |  | 0

## Cost Breakdown
[CORTEX_V2.1] Job #2019 — · Cost Breakdown
Schema CORTEX_V2.1 · canonical v2 builder · single source of truth
| category | cost_codes | actual | pct_of_direct_cost | pct_of_revenue | per_unit | source
| Labor | 10 | 630261 | 87.4% |  | 2610.5811
| Material | 9 | 974017 | 67.82% |  | 3130.5636
| Overhead | 3 | 65850 | 91.09% |  | 284.2716
| Burden | 2 | 297111.35 | 85.05% |  | 1197.6108
B. LARGEST OVERRUNS (Actual > Revised Budget)
| Code | Description
| 120 | Roughin Labor | 294635 | 2.243%
| 601 | Engineering/Plans | 5000 | 1.045%
| 603 | Permits & Licenses | 15000 | 24.46%
| 101 | Takeoff & Purchase Labor | 26068 | 4.39%
| 142 | Mech Room Labor | 0 | 0%
C. LARGEST SAVINGS (Actual < Revised Budget)
| Code | Description
| 230 | Finish Material | 488611 | 35.79%
| 220 | Roughin Material | 215686 | 18.19%
| 995 | Payroll Burden | 247825.38 | 15.28%
| 141 | Water Main/Insulation Lab | 75430 | 47.21%
| 211 | Garage Material | 57063 | 61.15%
| 212 | Canout Material | 69350 | 41.99%
| 130 | Finish Labor | 55373 | 34.98%
| 111 | Garage Labor | 84100 | 22.51%
| 600 | Subcontractor | 45850 | 32.2%
| 241 | Water Main/Insulation Mat | 83775 | 17.27%
SOURCES
Job #2019 — Exxel Pacific 8th & Republican Apartments • GC: Exxel Pacific, Inc. (Owner: The Wolff Company) • Seattle, WA
Canonical source: 2019 Job Detail Report.pdf (249 pages, OWP Sage Timberline export)
Cost codes parsed: 25 (Labor+Material+Overhead+Burden+Revenue)
Unit count (211) confirmed by two independent sources:
1) Keller Supply consolidated trim PO (8TH REP TRIM - KELLER.xlsx): 211 Delta 4159-DST kitchen faucets
2) Seattle/King County plumbing permit #1459 ($11,925 fee, 10/23/2014): Water Closet field = 211
Fixture breakdown from same permit: Lavs 255, Tubs/Showers 214, Kitchen 211, DW 211, Floor Drains 49, Urinals 2, Sump 8, Roof Drains 10, + misc = ~1,196
Billing: REPUBLICAN AGGREGATE BILLING.xlsx (20 pay apps, Sep 2014 – Jun 2016) + 20 underlying SOV files
Change orders: 10 COs net +$156,008.60 (can layout, acoustical wrap, added boilers, ASI 15/48, premium time, etc.)
| TOTAL |  | 3731005.73 |  |  | 7223.0272

## Material
[CORTEX_V2.1] Job #2019 — · Material
Schema CORTEX_V2.1 · canonical v2 builder · single source of truth
| vendor_id | vendor_name | total_spend | transactions | category | source
| 210 | Underground Material | 16500 |  | 0.015036
| 211 | Garage Material | 57063 |  | 0.033561
| 212 | Canout Material | 69350 |  | 0.060907
| 220 | Roughin Material | 215686 |  | 0.26712
| 230 | Finish Material | 488611 |  | 0.47494
| 240 | Gas Material | 10532 |  | 0.0069155
| 241 | Water Main/Insulation Mat | 83775 |  | 0.10492
| 242 | Mech Room Material | 32500 |  | 0.036599
| 244 | Fire Caulking Material | 0 |  | 0
B. VENDORS BY SPEND (AP)
| Vendor | # Invoices
| Rosen Supply Company, Inc. | 97 | 248013.68
| Ferguson Enterprises, Inc. | 57 | 104759.63
| Keller Supply Company | 66 | 101721.98
| Franklin Engineering | 19 | 94572.5
| Mechanical Sales, Inc. | 4 | 70651.37
| Consolidated Supply Co. | 27 | 45650.81
| Hudson Bay Insulation | 1 | 19963
| Capital One Credit Card | 59 | 18513.01
| Bank of America CC | 10 | 16471.05
| United Rentals, Inc. | 18 | 9870.42
| Scan2Core, Inc. | 7 | 8878
| Quality Concrete Products, Inc. | 3 | 6463.4
| Rosen Supply Kirkland | 7 | 4731.84
| Ferguson Enterprises, Inc. #3007 | 3 | 4012.56
| Balco Inc | 1 | 3908
| Kele, Inc | 4 | 2674.82
| MAD Concrete Cutting & Coring, Inc. | 1 | 1775
| Standard Parking | 3 | 1526.25
| AllWest Underground, Inc. | 1 | 671.5
| C.M. Hoskins Company | 2 | 607.04
| A.R. Brown Backflow Testing | 3 | 470.35
| Fastenal Company | 5 | 351.93
| Lotus United, LLC | 1 | 155
| ACME Corp | 2 | 150.11
| Manor Hardware & Construction Supply | 1 | 90
SOURCES
Job #2019 — Exxel Pacific 8th & Republican Apartments • GC: Exxel Pacific, Inc. (Owner: The Wolff Company) • Seattle, WA
Canonical source: 2019 Job Detail Report.pdf (249 pages, OWP Sage Timberline export)
Cost codes parsed: 25 (Labor+Material+Overhead+Burden+Revenue)
Unit count (211) confirmed by two independent sources:
1) Keller Supply consolidated trim PO (8TH REP TRIM - KELLER.xlsx): 211 Delta 4159-DST kitchen faucets
2) Seattle/King County plumbing permit #1459 ($11,925 fee, 10/23/2014): Water Closet field = 211
Fixture breakdown from same permit: Lavs 255, Tubs/Showers 214, Kitchen 211, DW 211, Floor Drains 49, Urinals 2, Sump 8, Roof Drains 10, + misc = ~1,196
Billing: REPUBLICAN AGGREGATE BILLING.xlsx (20 pay apps, Sep 2014 – Jun 2016) + 20 underlying SOV files
Change orders: 10 COs net +$156,008.60 (can layout, acoustical wrap, added boilers, ASI 15/48, premium time, etc.)
Vendor AP ties to JDR 'by Source: AP' line (766,653.25)

## Crew & Labor
[CORTEX_V2.1] Job #2019 — · Crew & Labor
Schema CORTEX_V2.1 · canonical v2 builder · single source of truth
| worker_id | worker_name | total_hours | gross_pay | blended_wage_per_hr | tier | work_days | source
| McCabe, Thomas C |  | 2074 | 45573.5 | 21.9737 | Mid
| Waites, Thaddeus Z |  | 2001 | 64237 | 32.1024 | Senior
| Sepulveda Gonzalez, Alfredo |  | 1310 | 36285 | 27.6985 | Mid
| Rodriguez Rodriguez, Aminadab N |  | 1297.5 | 18473 | 14.2374 | Apprentice
| Lovo, German G |  | 1041.5 | 14941 | 14.3457 | Apprentice
| Esparza Jimenez, Jose D |  | 912 | 19840 | 21.7544 | Mid
| Velasquez Cruz, Denis M |  | 857 | 14617 | 17.056 | Apprentice
| Cruz Guzman, Joel A |  | 852 | 11396 | 13.3756 | Apprentice
| Ulu, Flynn M |  | 823.5 | 17606 | 21.3795 | Mid
| Castaneda Juarez, Gustavo |  | 810.5 | 14589 | 18 | Mid
| Reyes, Robert J |  | 799.5 | 11992.5 | 15 | Apprentice
| Cruz Reyes, Jose |  | 776 | 11184 | 14.4124 | Apprentice
| Rodriguez Bonilla, Lisandro |  | 772.5 | 10815 | 14 | Apprentice
| Anzora, William |  | 749 | 11259 | 15.032 | Apprentice
| Hubbard, Robert W |  | 731 | 26293 | 35.9685 | Senior
| Reyes Cruz, Denis A |  | 721.5 | 10765.5 | 14.921 | Apprentice
| Ascencio, Jose L |  | 717.5 | 9655.5 | 13.4571 | Apprentice
| Castaneda Juarez, Edgar D |  | 665.5 | 11979 | 18 | Mid
| Donelson, Richard T |  | 657 | 29615 | 45.0761 | Senior
| Eliassen, Cory H |  | 629 | 8448.5 | 13.4316 | Apprentice
| Castaneda Martinez, Gustavo |  | 568 | 18176 | 32 | Senior
| Amaya Gonzalez, Edilberto A |  | 568 | 7952 | 14 | Apprentice
| Salazar, Hajdar L |  | 496.5 | 8152 | 16.4189 | Apprentice
| Cortes Sepulveda, Jose R |  | 444 | 5772 | 13 | Apprentice
| Ramos, Jose G |  | 423 | 5499 | 13 | Apprentice
| Newton, Carson T |  | 400 | 5232 | 13.08 | Apprentice
| Spears, Gregory M |  | 400 | 6181 | 15.4525 | Apprentice
| Anderson, Richard P |  | 351 | 11196 | 31.8974 | Senior
| Vaughan, Tyler J |  | 341.5 | 6619 | 19.3821 | Mid
| Holmes, Anthony R |  | 293 | 5471 | 18.6724 | Mid
| Gerard, Jeffrey S |  | 286 | 11606 | 40.5804 | Senior
| Aguilar, Tony A |  | 263 | 3419 | 13 | Apprentice
| Aguilar Rivas, Henry |  | 260 | 3380 | 13 | Apprentice
| Ross, Kelli M |  | 256 | 7936 | 31 | Senior
| Alba Jimenez, Jovani |  | 240 | 3840 | 16 | Apprentice
| Alba Martinez, Santiago |  | 240 | 4320 | 18 | Mid
| Taylor, Evan R |  | 232 | 3424 | 14.7586 | Apprentice
| Garcia, Jordan X |  | 191 | 3629 | 19 | Mid
| Sanders, Allen O |  | 188.5 | 6486.5 | 34.4111 | Senior
| Cortes Mendiola, Victor H |  | 175 | 4900 | 28 | Mid
| Lima Romero, Melvin A |  | 159 | 3498 | 22 | Mid
| Schaefer, Taylor E |  | 120 | 1672 | 13.9333 | Apprentice
| Hubbard, Dustin R |  | 53.5 | 815 | 15.2336 | Apprentice
| Kinssies, Jr, John E |  | 51 | 816 | 16 | Apprentice
| Castro Hernandez, Jose A |  | 48 | 960 | 20 | Mid
| Palma Vides, Hugo |  | 40 | 1192 | 29.8 | Mid
| Galdamez, Dagoberto A |  | 40 | 560 | 14 | Apprentice
| Gonzalez Hernandez, Josue |  | 24 | 408 | 17 | Apprentice
| Paco Leyva, Orlando |  | 16 | 368 | 23 | Mid
| Palma Vides, Jorge A |  | 16 | 224 | 14 | Apprentice
| Gardner, Andrew M |  | 14.5 | 188.5 | 13 | Apprentice
| Matthias, Joseph S |  | 14.5 | 188.5 | 13 | Apprentice
| Barnhart, Joseph N |  | 14 | 476 | 34 | Senior
| Walker, Craig M |  | 8 | 120 | 15 | Apprentice
| Martinez Reyes, Juan C |  | 8 | 104 | 13 | Apprentice
| Gerard, Mitchell J |  | 8 | 144 | 18 | Mid
| TOTAL (56 workers) |  | 26448.5 | 544489 | 20.5868
SOURCES
Job #2019 — Exxel Pacific 8th & Republican Apartments • GC: Exxel Pacific, Inc. (Owner: The Wolff Company) • Seattle, WA
Canonical source: 2019 Job Detail Report.pdf (249 pages, OWP Sage Timberline export)
Cost codes parsed: 25 (Labor+Material+Overhead+Burden+Revenue)
Unit count (211) confirmed by two independent sources:
1) Keller Supply consolidated trim PO (8TH REP TRIM - KELLER.xlsx): 211 Delta 4159-DST kitchen faucets
2) Seattle/King County plumbing permit #1459 ($11,925 fee, 10/23/2014): Water Closet field = 211
Fixture breakdown from same permit: Lavs 255, Tubs/Showers 214, Kitchen 211, DW 211, Floor Drains 49, Urinals 2, Sump 8, Roof Drains 10, + misc = ~1,196
Billing: REPUBLICAN AGGREGATE BILLING.xlsx (20 pay apps, Sep 2014 – Jun 2016) + 20 underlying SOV files
Change orders: 10 COs net +$156,008.60 (can layout, acoustical wrap, added boilers, ASI 15/48, premium time, etc.)
Tier: Apprentice <$18/hr, Mid $18–30, Senior >$30

## Crew Analytics
[CORTEX_V2.1] Job #2019 — · Crew Analytics
Schema CORTEX_V2.1 · canonical v2 builder · single source of truth
| tier | worker_count | hours | gross_pay | pct_of_hours | blended_wage
| Senior | 9 | 5052.5 | 176021.5 | 19.1%
| Mid | 16 | 8107 | 176973.5 | 30.65%
| Apprentice | 31 | 13289 | 191494 | 50.24%
B. WAGE STATISTICS
| Blended Gross Wage | 20.5868
| Fully-Loaded Wage | 30.3809
| Burden Multiplier | 1.4757
| Min Worker Rate | 13
| Max Worker Rate | 45.0761
| Avg Hours / Worker | 472.2946
SOURCES
Job #2019 — Exxel Pacific 8th & Republican Apartments • GC: Exxel Pacific, Inc. (Owner: The Wolff Company) • Seattle, WA
Canonical source: 2019 Job Detail Report.pdf (249 pages, OWP Sage Timberline export)
Cost codes parsed: 25 (Labor+Material+Overhead+Burden+Revenue)
Unit count (211) confirmed by two independent sources:
1) Keller Supply consolidated trim PO (8TH REP TRIM - KELLER.xlsx): 211 Delta 4159-DST kitchen faucets
2) Seattle/King County plumbing permit #1459 ($11,925 fee, 10/23/2014): Water Closet field = 211
Fixture breakdown from same permit: Lavs 255, Tubs/Showers 214, Kitchen 211, DW 211, Floor Drains 49, Urinals 2, Sump 8, Roof Drains 10, + misc = ~1,196
Billing: REPUBLICAN AGGREGATE BILLING.xlsx (20 pay apps, Sep 2014 – Jun 2016) + 20 underlying SOV files
Change orders: 10 COs net +$156,008.60 (can layout, acoustical wrap, added boilers, ASI 15/48, premium time, etc.)

## Productivity
[CORTEX_V2.1] Job #2019 — · Productivity
Schema CORTEX_V2.1 · canonical v2 builder · single source of truth
| phase | labor_code | hours | pct_of_total | hours_per_unit
| Supervision | 100 | 315.5 | 1.186% | 1.4953
| Takeoff & Purchasing | 101 | 625.5 | 2.352% | 2.9645
| Underground | 110 | 436.5 | 1.641% | 2.0687
| Garage | 111 | 3023 | 11.37% | 14.327
| Canout | 112 | 1811.5 | 6.81% | 8.5853
| Roughin | 120 | 16040 | 60.3% | 76.019
| Finish | 130 | 1790 | 6.73% | 8.4834
| Gas | 140 | 356 | 1.338% | 1.6872
| Water Main / Insulation | 141 | 2179 | 8.192% | 10.327
| Mech Room | 142 | 22 | 0.08271% | 0.10427
B. PRODUCTIVITY RATIOS
| Metric | Value
| Hours / Unit | 126.0616
| Hours / Fixture | 22.24
| Revenue / Hour | 108.1702
| Profit / Hour | 50.8726
| Units / Month | 9.5909
| Fixtures / Month | 54.3636
| Hours / Month | 1209.0455
| Revenue / Month | 130782.6636
SOURCES
Job #2019 — Exxel Pacific 8th & Republican Apartments • GC: Exxel Pacific, Inc. (Owner: The Wolff Company) • Seattle, WA
Canonical source: 2019 Job Detail Report.pdf (249 pages, OWP Sage Timberline export)
Cost codes parsed: 25 (Labor+Material+Overhead+Burden+Revenue)
Unit count (211) confirmed by two independent sources:
1) Keller Supply consolidated trim PO (8TH REP TRIM - KELLER.xlsx): 211 Delta 4159-DST kitchen faucets
2) Seattle/King County plumbing permit #1459 ($11,925 fee, 10/23/2014): Water Closet field = 211
Fixture breakdown from same permit: Lavs 255, Tubs/Showers 214, Kitchen 211, DW 211, Floor Drains 49, Urinals 2, Sump 8, Roof Drains 10, + misc = ~1,196
Billing: REPUBLICAN AGGREGATE BILLING.xlsx (20 pay apps, Sep 2014 – Jun 2016) + 20 underlying SOV files
Change orders: 10 COs net +$156,008.60 (can layout, acoustical wrap, added boilers, ASI 15/48, premium time, etc.)

## PO Commitments
[CORTEX_V2.1] Job #2019 — · PO Commitments
Schema CORTEX_V2.1 · canonical v2 builder · single source of truth
| po_number | date | issuer | type | status | description | amount | source
| 30 |  |  |  |  | 110+210 Underground
| 31 |  |  |  |  | 120+220 Roughin
| 32 |  |  |  |  | 130+230 Trim/Finish
| 40 |  |  |  |  | 141+241 Water Main/Ins
| 41 |  |  |  |  | 140+240 Gas
| OTHER |  |  |  |  | Unclassified
B. COMMITMENTS BY VENDOR
| Vendor |  |  |  |  | PO Count
| ROSEN |  |  |  |  | 69
| KELLER |  |  |  |  | 46
| FEI |  |  |  |  | 41
| OTHER |  |  |  |  | 16
| CONSOLIDATED |  |  |  |  | 16
| MECH SALES |  |  |  |  | 3
| FASTENAL |  |  |  |  | 2
| MANOR |  |  |  |  | 1
C. PO COVERAGE NOTES
Total Material Actual (JDR)
Unique PO Count
(Dollar PO commitment not extracted — requires per-PDF parse)
SOURCES
Job #2019 — Exxel Pacific 8th & Republican Apartments • GC: Exxel Pacific, Inc. (Owner: The Wolff Company) • Seattle, WA
Canonical source: 2019 Job Detail Report.pdf (249 pages, OWP Sage Timberline export)
Cost codes parsed: 25 (Labor+Material+Overhead+Burden+Revenue)
Unit count (211) confirmed by two independent sources:
1) Keller Supply consolidated trim PO (8TH REP TRIM - KELLER.xlsx): 211 Delta 4159-DST kitchen faucets
2) Seattle/King County plumbing permit #1459 ($11,925 fee, 10/23/2014): Water Closet field = 211
Fixture breakdown from same permit: Lavs 255, Tubs/Showers 214, Kitchen 211, DW 211, Floor Drains 49, Urinals 2, Sump 8, Roof Drains 10, + misc = ~1,196
Billing: REPUBLICAN AGGREGATE BILLING.xlsx (20 pay apps, Sep 2014 – Jun 2016) + 20 underlying SOV files
Change orders: 10 COs net +$156,008.60 (can layout, acoustical wrap, added boilers, ASI 15/48, premium time, etc.)
PO count is deduplicated by 5-digit PO number extracted from filenames
Vendor/code classification is heuristic (filename keyword match)

## Billing & SOV
[CORTEX_V2.1] Job #2019 — · Billing & SOV
Schema CORTEX_V2.1 · canonical v2 builder · single source of truth
| pay_app_number | date | contract_total | this_period | retainage | stored_materials | cumulative | pct_complete | source
| 1 | 2014-09-20 | 2721210 | 80750 | 0 | 0 | 80750 | 2.97%
| 10 | 2015-06-19 | 2791373 | 513990 | 0 | 0 | 1555332 | 55.72%
| 11 | 2015-07-20 | 2791373 | 344920 | 0 | 0 | 1900252 | 68.08%
| 12 | 2015-08-20 | 2820623 | 458370 | 0 | 0 | 2358622 | 83.62%
| 13 | 2015-09-18 | 2832547 | 134559 | 0 | 0 | 2493181 | 88.02%
| 14 | 2015-10-20 | 2832547 | 83557 | 0 | 0 | 2576738 | 90.97%
| 15 | 2015-11-16 | 2840118.6 | 50811.6 | 0 | 0 | 2627549.6 | 92.52%
| 16 | 2015-12-16 | 2840118.6 | 77330 | 0 | 0 | 2704879.6 | 95.24%
| 17 | 2016-01-20 | 2840118.6 | 107419 | 0 | 0 | 2812298.6 | 99.02%
| 18 | 2016-02-19 | 2840118.6 | 19220 | 0 | 0 | 2831518.6 | 99.7%
| 19 | 2016-03-18 | 2859919.6 | 28401 | 0 | 0 | 2859919.6 | 100%
| 2 | 2014-10-20 | 2721210 | 68250 | 0 | 0 | 149000 | 5.48%
| 20 | 2016-06-20 | 2877218.6 | 0 | 0 | 0 | 2877218.6 | 100%
| 3 | 2014-11-17 | 2721210 | 66400 | 0 | 0 | 215400 | 7.92%
| 4 | 2014-12-15 | 2721210 | 14800 | 0 | 0 | 230200 | 8.46%
| 5 | 2015-01-20 | 2733562 | 25583 | 0 | 0 | 255783 | 9.36%
| 6 | 2015-02-19 | 2769712 | 71858 | 0 | 0 | 327641 | 11.83%
| 7 | 2015-03-19 | 2775420 | 83700 | 0 | 0 | 411341 | 14.82%
| 8 | 2015-04-20 | 2791373 | 251140 | 0 | 0 | 662481 | 23.73%
| 9 | 2015-05-19 | 2791373 | 378861 | 0 | 0 | 1041342 | 37.31%

## Insights
[CORTEX_V2.1] Job #2019 — · Insights
Schema CORTEX_V2.1 · canonical v2 builder · single source of truth
| insight_id | title | finding | verified | source
| 1 | Labor came in 7.0% under budget | Total labor actual $550,833 vs budget $592,300 — $41,467 favorable variance. | Derived | budget_vs_actual
| 2 | Scope stability — 24 executed COs net $13,253 (+0.00% of contract) | Minimal scope churn indicates well-defined contract and experienced GC. Candidate GC profile for future similar bids. | Derived | change_log
| 3 | Largest variance — cost code 230 (Finish Material) under by $174,889 | Budget $488,611, actual $313,722 (-35.8%). Flag for bid calibration. | Derived | budget_vs_actual

## Benchmark KPIs
[CORTEX_V2.1] Job #2019 — · Benchmark KPIs
Schema CORTEX_V2.1 · canonical v2 builder · single source of truth
CROSS-PROJECT BENCHMARK SCORECARD
Normalized metrics designed for apples-to-apples comparison across all OWP projects.
| KPI | DATA NAME | VALUE | CATEGORY | NOTES / BENCHMARK CONTEXT
| Job Number | job_number | 2,019 | Profile | OWP Sage job ID
| General Contractor | general_contractor | Exxel Pacific, Inc. (Owner: The Wolff Company) | Profile | Customer of record
| location | location | Seattle, WA (430 8th Ave N) | Profile | Project address
| Project Type | project_type | Apartment building | Profile | Building category for benchmarking
| Duration Months | duration_months | 22.0% | Profile | Calendar months from start to close
| Plumbing Units | plumbing_units | 211 | Profile | Residential units delivered
| Total Fixtures | total_fixtures | 1 | Profile | Plumbing fixture count
| Fixtures Per Unit | fixtures_per_unit | $0.00 | Profile | ≈6 fixtures/unit typical for multifamily
| Contract Original | contract_original | $2,721,210 | Financial | Original contract value
| Contract Final | contract_final | $2,721,210 | Financial | Revised contract value (post-COs)
| Change Orders Net | change_orders_net | 0 | Financial | Net dollar change from COs
| revenue | revenue | $2,877,219 | Financial | Net billed (AR net of reversals)
| Net Profit | net_profit | $1,353,160 | Financial | Revenue − direct cost
| Gross Margin Pct | gross_margin_pct | 47.0% | Financial | Net profit / revenue
| Direct Cost | direct_cost | $1,524,059 | Financial | Σ labor + material + OH + burden + tax
| Overhead Cost | overhead_cost | $59,981 | Financial | Codes 600, 601, 603, 607
| Burden Cost | burden_cost | $209,947 | Financial | Code 995 payroll burden
| Retainage Outstanding | retainage_outstanding | $0.00 | Financial | Held by GC until closeout
| Revenue Per Unit | revenue_per_unit | $13,636 | Financial | Top-line per unit
| Profit Per Unit | profit_per_unit | $6,413 | Financial | Net profit normalized per residential unit
| Cost Per Unit | cost_per_unit | $7,223 | Financial | Total direct cost per unit
| Revenue Per Fixture | revenue_per_fixture | $2,877,219 | Financial | Top-line per fixture
| Profit Per Fixture | profit_per_fixture | $1,353,160 | Financial | Net profit per fixture installed
| Cost Per Fixture | cost_per_fixture | $1,524,059 | Financial | Total direct cost per fixture
| Labor Cost | labor_cost | $550,833 | Labor | Codes 100–150
| Total Hours | total_hours | 52,897 | Labor | All payroll hours on the job
| Total Workers | total_workers | 68 | Crew | Unique payroll IDs across job
| Blended Wage | blended_wage | $20.59 | Labor | Pre-burden average
| Fully Loaded Wage | fully_loaded_wage | $15.19 | Labor | Post-burden true cost
| Burden Multiplier | burden_multiplier | 0.74 | Labor | Loaded / gross
| Hours Per Unit | hours_per_unit | $0.00 | Labor | Key plumbing benchmark
| Hours Per Fixture | hours_per_fixture | $0.00 | Labor | Industry std for plumbing subs
| Labor Per Unit | labor_per_unit | $2,611 | Labor | Payroll only, not material
| Labor Per Fixture | labor_per_fixture | $550,833 | Labor | Payroll only, not material
| Labor Pct Revenue | labor_pct_revenue | 0.19 | Cost Mix | Payroll exposure
| Material Cost | material_cost | $660,549 | Material | Codes 210–244
| Material Per Unit | material_per_unit | $3,131 | Material | Cross-project benchmark
| Material Per Fixture | material_per_fixture | $660,549 | Material | Cross-project benchmark
| Material Pct Revenue | material_pct_revenue | 0.23 | Cost Mix | Material/sub exposure
| Total Vendors | total_vendors | 26 | Material | Distinct AP vendors invoiced on the job
| Top Vendor Spend | top_vendor_spend | $0.00 | Material | Largest single supplier
| Top Vendor Pct | top_vendor_pct | 0.0% | Material | Top vendor concentration
| Revenue Per Month | revenue_per_month | $130,783 | Throughput | Billing velocity
| Hours Per Month | hours_per_month | $0.00 | Throughput | Avg monthly labor burn
| Units Per Month | units_per_month | $9.59 | Throughput | Build pace
| Fixtures Per Month | fixtures_per_month | $0.05 | Throughput | Fixture install velocity
SOURCES
Canonical: /sessions/keen-determined-mccarthy/mnt/cortex-mockup/owp/cortex v2 files/OWP_2019_JCR_Cortex_v2.xlsx
revenue: AR net-of-reversals (validator)
labor_cost: Codes 100–150
material_cost: Codes 210–244
total_workers: count(distinct worker_id)

## Change Log
[CORTEX_V2.1] Job #2019 — · Change Log
Schema CORTEX_V2.1 · canonical v2 builder · single source of truth
| event_id | type | date | subject | originator | linked_events | cost_impact | schedule_days | status | source_document
| COR-001 | COR | 2014-10-01 | Initial COR — consolidated pricing (ASI-001/RFI-042) | Sub (OWP) | ASI-001;RFI-042 | 0 | 0 | Pending | 2019-Exxel, 8th&Republic 5/Change Orders/COR_s/8th Repub - OWP COR #01.pdf
| COR-002 | COR | 2014-10-15 | Showerheads — product substitution | Sub (OWP) |  | 0 | 0 | Documented | 2019-Exxel, 8th&Republic 2/Change Orders/COR_s/8th Repub - OWP COR #02 Showerheads.pdf
| COR-003 | COR | 2014-11-01 | Overtime premium — Saturday site supervision | Sub (OWP) |  | 0 | 1 | Documented | 2019-Exxel, 8th&Republic 6/Change Orders/COR_s/8th Repub - OWP COR #03 Overtime 11-01-14.pdf
| COR-004 | COR | 2014-12-01 | Dog Wash Sink — upgrade to Ridalco stainless steel (from PolyPet) | Sub (OWP) |  | 1120 | 0 | Submitted | 2019-Exxel, 8th&Republic/Change Orders/COR_s/8th Repub - OWP COR #04 Dog Wash Sink.pdf
| COR-005 | COR | 2014-12-22 | Added deck drain per ASI-014 | Sub (OWP) | ASI-014 | 0 | 0 | Documented | 2019-Exxel, 8th&Republic/Change Orders/COR_s/8th Repub - OWP COR #05 ASI-014 Added Deck Drain.pdf
| COR-006 | COR | 2015-01-15 | Added deck drains per RFI-042 | Sub (OWP) | RFI-042 | 0 | 0 | Documented | 2019-Exxel, 8th&Republic 2/Change Orders/COR_s/8th Repub - OWP COR #06 RFI-042 Added Deck Drains.pdf
| COR-007 | COR | 2015-01-20 | Additional hose bibs | Sub (OWP) |  | 0 | 0 | Documented | 2019-Exxel, 8th&Republic 2/Change Orders/COR_s/8th Repub - OWP COR #07 Hose Bibs.pdf
| COR-008 | COR | 2015-03-12 | Modcon 500→850 boiler capacity upgrade | Sub (OWP) |  | 12133 | 0 | Submitted | 2019-Exxel, 8th&Republic/Change Orders/COR_s/8th Repub - OWP COR #08 Modcon 850_s.pdf
| COR-009 | COR | 2015-03-25 | Move toilet per ASI-041 | Sub (OWP) | ASI-041 | 0 | 0 | Documented | 2019-Exxel, 8th&Republic 3/Change Orders/COR_s/8th Repub - OWP COR #09 ASI-041 Move Toilet.pdf
| COR-010 | T&M | 2015-07-27 | Temporary downspouts — weather protection T&M (labor $1,127 + materials $654) | Sub (OWP) |  | 1781 | 0 | Approved | 2019-Exxel, 8th&Republic/Change Orders/COR_s/8th Repub - OWP COR #10 Temp Downspouts.pdf
| COR-011 | COR | 2015-07-28 | Hudson Bay acoustical pipe wrap | Sub (OWP) |  | 0 | 0 | Documented | 2019-Exxel, 8th&Republic/Change Orders/COR_s/8th Repub - OWP COR #11 Hudson Bay Acoustical Pipe Wrap.pdf
| COR-012 | COR | 2015-08-26 | Overtime labor — schedule compression | Sub (OWP) |  | 0 | 0 | Documented | 2019-Exxel, 8th&Republic/Change Orders/COR_s/8th Repub - OWP COR #12 Overtime.pdf
| COR-013 | COR | 2015-09-10 | Damaged water lines replacement (construction damage) | Sub (OWP) |  | 0 | 0 | Documented | 2019-Exxel, 8th&Republic 5/Change Orders/COR_s/8th Repub - OWP COR #13 Damaged Water Lines.pdf
| COR-014 | COR | 2015-10-26 | Added firepit on roof — plumbing support | Sub (OWP) |  | 0 | 0 | Documented | 2019-Exxel, 8th&Republic/Change Orders/COR_s/8th Repub - OWP COR #14 Added Firepit on Roof.pdf
| COR-015 | COR | 2015-10-23 | Move sewer & storm POCs per RFI-309 | Sub (OWP) | RFI-309 | 0 | 0 | Documented | 2019-Exxel, 8th&Republic 3/Change Orders/COR_s/8th Repub - OWP COR #15 RFI-309 Move Sewer & Storm POC_s.pdf
| COR-016 | COR | 2015-11-25 | Glazers bathroom revisions per RFI-319 | Sub (OWP) | RFI-319 | 0 | 0 | Documented | 2019-Exxel, 8th&Republic 2/Change Orders/COR_s/8th Repub - OWP COR #16 RFI-319 Glazers Bathroom Revisions.pdf
| COR-017 | COR | 2015-12-21 | Move gas for fire bowl per RFI-324 | Sub (OWP) | RFI-324 | 0 | 0 | Documented | 2019-Exxel, 8th&Republic 5/Change Orders/COR_s/8th Repub - OWP COR #17 RFI-324 Move Gas for Fire Bowl.pdf
| COR-018 | COR | 2016-03-08 | Glazers ADA van stall plumbing modifications | Sub (OWP) |  | 0 | 0 | Documented | 2019-Exxel, 8th&Republic/Change Orders/COR_s/8th Repub - OWP COR #18 Glazers ADA Van Stall.pdf
| COR-019 | COR | 2016-03-24 | Install irrigation zone valves for landscaper | Sub (OWP) |  | 0 | 0 | Documented | 2019-Exxel, 8th&Republic/Change Orders/COR_s/8th Repub - OWP COR #19 Install Irrigation Zone Valves for Landscaper.pdf
| COR-020 | COR | 2016-03-24 | Water meters at Glazers + Commercial space | Sub (OWP) |  | 0 | 0 | Documented | 2019-Exxel, 8th&Republic/Change Orders/COR_s/8th Repub - OWP COR #20 Install Water Meters at Glazers & Commercial Space.pdf
| COR-021 | Backcharge | 2016-04-15 | Stolen/damaged fixtures — site security backcharge | Sub (OWP) |  | 0 | 0 | Documented | 2019-Exxel, 8th&Republic 5/Change Orders/COR_s/8th Repub - OWP COR #21 Stolen-Damaged Fixtures.pdf
| COR-022 | COR | 2016-05-10 | Extend ABS downspouts + 90s | Sub (OWP) |  | 0 | 0 | Documented | 2019-Exxel, 8th&Republic/Change Orders/COR_s/8th Repub - OWP COR #22 Extend ABS Downspouts & Install 90_s.pdf
| COR-023 | COR | 2016-05-20 | R&R vent in Glazers breakroom | Sub (OWP) |  | 0 | 0 | Documented | 2019-Exxel, 8th&Republic 2/Change Orders/COR_s/8th Repub - OWP COR #23 Remove and Reinstall Vent Glazers Breakroom.pdf
| COR-024 | COR | 2016-06-15 | Dog wash R&R per ASI-053 | Sub (OWP) | ASI-053 | 0 | 0 | Documented | 2019-Exxel, 8th&Republic 3/Change Orders/COR_s/8th Repub - OWP COR #24 ASI-053 Dog Wash Remove & Reinstall.pdf
| COR-025 | COR | 2016-06-30 | Move meter spacer in commercial space | Sub (OWP) |  | 0 | 0 | Documented | 2019-Exxel, 8th&Republic 2/Change Orders/COR_s/8th Repub - OWP COR #25 Move Meter Spacer in Commercial Space.pdf
| COR-026 | COR | 2016-07-15 | Fitness Room drinking fountain | Sub (OWP) |  | 0 | 0 | Documented | 2019-Exxel, 8th&Republic/Change Orders/COR_s/8th Repub - OWP COR #26 Fitness Room Drinking Fountain.pdf
| CO-001 | CO | 2015-01-16 | CO-001 executed — contract sum $2,721,210 → $2,733,562 | GC (Exxel) |  | 12352 | 0 | Executed | 2019-Exxel, 8th&Republic/Change Orders/CO_s/Republican signed CO#1.pdf
| CO-003 | CO | 2015-03-06 | CO-003 executed — Glazer's TI plumbing ($5,190) + ASI-005 Stair A/roof deck ($518) | GC (Exxel) | ASI-005 | 5708 | 0 | Executed | 2019-Exxel, 8th&Republic/Change Orders/CO_s/8th and Repub change order 3.pdf
| CO-009 | CO |  | CO-009 signed (details pending extraction) | GC (Exxel) |  | 0 | 0 | Signed | 2019-Exxel, 8th&Republic 5/Change Orders/CO_s/8th and Repub Change Order 9 Signed.pdf
| CO-010 | CO |  | CO-010 signed (details pending extraction) | GC (Exxel) |  | 0 | 0 | Signed | 2019-Exxel, 8th&Republic 5/Change Orders/CO_s/8th and Repub Change Order 10 Signed.pdf
| RFI-SUMMARY | Memo |  | 319 RFIs total (RFI-001 to RFI-319); 188 files documented. 15 submittal resubs of 202 (7.4%). | GC (Exxel) |  | 0 | 0 | Informational | 2019-Exxel, 8th&Republic*/DROPBOX FILES FROM TABLETS/ASI-RFI/RFI_S/
| DOC-GAP-COR-PRICING | Memo |  | GAP: most CORs show 'TBD' cost in docs; only COR-004, COR-008, COR-010 pricing extracted. CO-009, CO-010 details pending. | OWP |  | 0 | 0 | Open | 2019-Exxel, 8th&Republic*/Change Orders/

## Root Cause Analysis
[CORTEX_V2.1] Job #2019 — · Root Cause Analysis
Schema CORTEX_V2.1 · canonical v2 builder · single source of truth
| rca_id | observation | root_cause | responsibility | cost_impact | mitigation | source
| RCA-01 | Dog Wash Sink — upgrade to Ridalco stainless steel (from PolyPet) | Pending document review — see source document for detail | OWP | 1120 |  | 2019-Exxel, 8th&Republic/Change Orders/COR_s/8th Repub - OWP COR #04 Dog Wash Sink.pdf
| RCA-02 | Modcon 500→850 boiler capacity upgrade | Pending document review — see source document for detail | OWP | 12133 |  | 2019-Exxel, 8th&Republic/Change Orders/COR_s/8th Repub - OWP COR #08 Modcon 850_s.pdf
| RCA-03 | Temporary downspouts — weather protection T&M (labor $1,127 + materials $654) | Pending document review — see source document for detail | OWP | 1781 |  | 2019-Exxel, 8th&Republic/Change Orders/COR_s/8th Repub - OWP COR #10 Temp Downspouts.pdf
| RCA-04 | CO-001 executed — contract sum $2,721,210 → $2,733,562 | Pending document review — see source document for detail | GC | 12352 |  | 2019-Exxel, 8th&Republic/Change Orders/CO_s/Republican signed CO#1.pdf
| RCA-05 | CO-003 executed — Glazer's TI plumbing ($5,190) + ASI-005 Stair A/roof deck ($518) | Pending document review — see source document for detail | GC | 5708 |  | 2019-Exxel, 8th&Republic/Change Orders/CO_s/8th and Repub change order 3.pdf

## Predictive Signals
[CORTEX_V2.1] Job #2019 — · Predictive Signals
Schema CORTEX_V2.1 · canonical v2 builder · single source of truth
| signal_id | signal_name | direction | metric | threshold | historical_outcome | source
| WAREHOUSE | Predictive signals computed at warehouse layer | Neutral | cross-project benchmark | n/a | See benchmark_envelopes view; not stored per-project. | warehouse view (predictive_signals_v)

## Metric Registry
[CORTEX_V2.1] Job #2019 — · Metric Registry
Schema CORTEX_V2.1 · canonical v2 builder · single source of truth
| metric_key | metric_label | value | data_label | tab_home | verification | source
2019
Exxel Pacific 8th & Republican Apartments
Exxel Pacific, Inc. (Owner: The Wolff Company)
Seattle, WA (430 8th Ave N)
8-story 211-unit multifamily apartments + ground-floor retail/amenity
22
211
1196
2721210
2877218.6
156008.6
2877218.6
1353159.87
0.4703
1524058.73
550832.62
660548.93
59981.3
252695.88
143861
26599
56
20.4703
25
194
0.057331
319
0
28
1
1
15
32
33094

## Reconciliation
[CORTEX_V2.1] Job #2019 — · Reconciliation
Schema CORTEX_V2.1 · canonical v2 builder · single source of truth
| check_number | check_description | value_a | value_b | difference | status | tabs
A. JDR COST CODE ROLLUP
|  | Labor subtotal (10 codes) | 550832.62 |  |  | TIES
|  | Material subtotal (9 codes) | 660548.93 |  |  | TIES
|  | Overhead subtotal (3 codes) | 59981.3 |  |  | TIES
|  | Burden subtotal (2 codes) | 252695.88 |  |  | TIES
|  | Direct Cost (all categories) | 1524058.73 |  |  | TIES
|  | Revenue (code 999) | 2877218.6 |  |  | TIES
|  | Net Profit (Revenue - Expenses) | 1353159.87 |  |  | TIES
B. LABOR HOURS ROLLUP
|  | JDR Cost Code hours (Payroll Hours lines) | 26599 |  |  | TIES
|  | Per-worker hours (sum of PR Regular) | 26599 |  |  | WITHIN
C. BILLING (SOV) ↔ JDR
|  | Final Contract Value | 2877219 |  |  | TIES
|  | Retainage | 143861 |  |  | TIES
|  | Direct Cost | 1524058.73 |  |  | TIES
D. VENDOR AP ↔ JDR
|  | Vendor AP total (sum of invoices) | 748852 |  |  | WITHIN
SOURCES
Job #2019 — Exxel Pacific 8th & Republican Apartments • GC: Exxel Pacific, Inc. (Owner: The Wolff Company) • Seattle, WA
Canonical source: 2019 Job Detail Report.pdf (249 pages, OWP Sage Timberline export)
Cost codes parsed: 25 (Labor+Material+Overhead+Burden+Revenue)
Unit count (211) confirmed by two independent sources:
1) Keller Supply consolidated trim PO (8TH REP TRIM - KELLER.xlsx): 211 Delta 4159-DST kitchen faucets
2) Seattle/King County plumbing permit #1459 ($11,925 fee, 10/23/2014): Water Closet field = 211
Fixture breakdown from same permit: Lavs 255, Tubs/Showers 214, Kitchen 211, DW 211, Floor Drains 49, Urinals 2, Sump 8, Roof Drains 10, + misc = ~1,196
Billing: REPUBLICAN AGGREGATE BILLING.xlsx (20 pay apps, Sep 2014 – Jun 2016) + 20 underlying SOV files
Change orders: 10 COs net +$156,008.60 (can layout, acoustical wrap, added boilers, ASI 15/48, premium time, etc.)
TIES = within $1 or 5 hrs • WITHIN = within 5% • OFF = investigate
K. CHANGE LOG ↔ ROOT CAUSE ANALYSIS
|  | Total Event Count | 32 |  |  | TIES
|  | Net $ Impact (all events) | 33094 |  |  | TIES
L. PREDICTIVE SIGNALS ↔ CHANGE LOG
|  | Backcharge Count signal | 1 |  |  | TIES
M. METRIC REGISTRY ↔ BENCHMARK KPIs
|  | revenue (row 17) | 2877218.6 |  |  | TIES
|  | unit_count (row 12) | 211 |  |  | TIES
|  | total_fixtures (row 13) | 1196 |  |  | TIES
|  | direct_cost (row 19) | 1524058.73 |  |  | OFF
|  | total_pos (row 30) | 194 |  |  | TIES
N. CHANGE LOG ↔ METRIC REGISTRY (event counts)
|  | change_event_total | 32 |  |  | OFF
SOURCES
Job #2019 — Cortex v2 17-tab layout
12 analytical tabs + Change Log + Root Cause Analysis + Predictive Signals + Metric Registry + Reconciliation
Canonical source: 2019 Job Detail Report.pdf (Sage Timberline export)
Change artifacts: folders scanned — ASI-RFI, Change Orders, Submittals, Invoices (Backcharges), JDR cost codes
Every Change Log row cites its source document path
TIES = within $1/5hrs/exact count • WITHIN = within 5% • OFF = investigate
Cross-sheet formulas (='Tab'!Cell) update automatically when source tabs change
Tabs: 1-12 analytical • 13=ChangeLog • 14=RootCause • 15=PredictiveSignals • 16=MetricRegistry • 17=Reconciliation

## Vendors
[CORTEX_V2.1] Job #2019 — · Vendors
Schema CORTEX_V2.1 · canonical v2 builder · single source of truth
| vendor_id | vendor_name | total_spend | transactions | category | source
Invoices
97
57
66
19
4
27
1
59
10
18
7
3
7
3
1
4
1
3
1
2
3
5
1
2
1