## Overview
[CORTEX_V2.1] Job #2020 — · Overview
Schema CORTEX_V2.1 · canonical v2 builder · single source of truth
| OVERVIEW |  | SOURCE
IDENTITY
| Project Job Number | 2020
| Project Name: | SRM Bellevue @ Main Apartments
CONTRACT & PARTIES
| General Contractor | SRM Development / Exxel Pacific (Owner: Bellevue Way Ventures)
JOB SITE
| Jobsite Location | Bellevue, WA (15 Bellevue Way SE)
| Plumbing Units | 288 | Type A (ADA)
| Floors | P2/P1 garage + L1 retail + Mezz + L2–L5 residential
SCHEDULE
| Project Duration | May 2014 – Feb 2016 (~22 months)
SCOPE & DESIGN
| Water Closets | 288+20 ADA | Bathtub Trim
| Lav Faucets | 288 + 4 amenity | Fixtures / Unit
| CONTRACT VALUE |  | NET PROFIT |  | DIRECT COST |  | LABOR HOURS
| $3,119,000 |  | $1,184,497 |  | $1,934,503 |  | 76,015
| Original $3,119,000 |  | 38.0% margin |  | 62.0% of revenue |  | 71 workers
COST BREAKDOWN
| Category | Budget | Actual | Variance | % Budget | % of Cost
| Labor | 593974 | 766929.01 | -172955.01 | 129.1% | 39.64%
| Material | 997196 | 735694.62 | 261501.38 | 73.78% | 38.03%
| Overhead | 16000 | 33267.19 | -17267.19 | 207.9% | 1.72%
| Burden | 312438.73 | 398612.39 | -86173.66 | 127.6% | 20.61%
| TOTAL | 1919608.73 | 1934503.21 | -14894.48 | 100.8% | 100%
PROJECT PROFILE
| Plumbing Units | 288 |  | Water Closets | 288+20 ADA |  | Lavatories | 288 + 4 amenity
| Floors | P2/P1 garage + L1 retail + Mezz + L2–L5 residential |  | Duration | May 2014 – Feb 2016 (~22 months)

## Budget vs Actual
[CORTEX_V2.1] Job #2020 — · Budget vs Actual
Schema CORTEX_V2.1 · canonical v2 builder · single source of truth
| cost_code | description | original_budget | revised_budget | actual | variance | pct_used | hours | source
LABOR
| 100 | Supervision | 12800 | 13700 | 13026.5 | 673.5 | 95.08%
| 101 | Takeoff & Purchase Labor | 15360 | 17310 | 18552.5 | -1242.5 | 1.072%
| 110 | Underground Labor | 16160 | 16760 | 16803.75 | -43.75 | 1.003%
| 111 | Garage Labor | 114350 | 118946 | 142441 | -23495 | 1.198%
| 112 | Canout Labor | 16000 | 16100 | 16515.5 | -415.5 | 1.026%
| 113 | Foundation Drain Labor | 2843 | 2843 | 2843 | 0 | 100%
| 120 | Roughin Labor | 376600 | 266055 | 348602.98 | -82547.98 | 1.31%
| 130 | Finish Labor | 51400 | 58664 | 64250.9 | -5586.9 | 1.095%
| 140 | Gas Labor | 9000 | 13862 | 32025.5 | -18163.5 | 2.31%
| 141 | Water Main/Insulation Lab | 55600 | 57029 | 85831.88 | -28802.88 | 1.505%
| 142 | Mech Room Labor | 9900 | 12705 | 26035.5 | -13330.5 | 2.049%
MATERIAL
| 210 | Underground Material | 23100 | 23300 | 24415.78 | -1115.78 | 1.048%
| 211 | Garage Material | 95600 | 92894 | 54034.99 | 38859.01 | 58.17%
| 212 | Canout Material | 26400 | 26700 | 24723.82 | 1976.18 | 92.6%
| 220 | Roughin Material | 363580 | 213718 | 87900.72 | 125817.28 | 41.13%
| 230 | Finish Material | 478500 | 526401 | 411991.97 | 114409.03 | 78.27%
| 240 | Gas Material | 12600 | 12800 | 8263.12 | 4536.88 | 64.56%
| 241 | Water Main/Insulation Mat | 92600 | 93431 | 122165.25 | -28734.25 | 1.308%
| 242 | Mech Room Material | 7000 | 7952 | 2198.97 | 5753.03 | 27.65%
OVERHEAD
| 600 | Subcontractor | 4000 | 5000 | 21589.36 | -16589.36 | 4.318%
| 603 | Permits & Licenses | 1000 | 11000 | 11677.83 | -677.83 | 1.062%
BURDEN
| 995 | Payroll Burden | 309922.16 | 265927.39 | 338661.76 | -72734.37 | 1.274%
| 998 | Payroll Taxes | 54692.15 | 46511.34 | 59950.63 | -13439.29 | 1.289%
SOURCES
Job #2020 — SRM Bellevue @ Main Apartments • GC: Exxel Pacific / Owner: Bellevue Way Ventures • Bellevue, WA
Canonical source: 2020 Job Detail Report.pdf (352 pages, OWP Sage Timberline export)
Cost codes parsed: 24 (Labor+Material+Overhead+Burden+Revenue)
Unit count (288) confirmed by TWO source documents:
1) Bellevue Main – Pricing to go to 101 Taylor Fixtures.xlsx: Type B lavs qty=268, Type A lavs qty=20, Lav faucets qty=288, Bathtub trim qty=288
2) BELLEVUE TRIM QUOTE PRICING organized by category USE.xlsx: Mansfield toilets 268 + 20 ADA = 288
Kitchen fixtures: 257 kitchen faucets (Delta 4353-AR-DST) — 31 fewer than units (studios/amenity)
Contract: One Way Plumbing Executed Contract OCR_D.pdf — Exxel Pacific / SRM Development GC
Billing: 10 archived Schedule of Values files (pay apps #4, 9, 10, 12, 13, 15, 18, 19, 20, 23)
Final contract $2,858,341 after 11 COs (net -$260,659, primarily CO#1 cast iron credit -$389,000)
Permit: City of Bellevue #13-133992-BO (building/plumbing)
| TOTAL |  | 2149007.31 | 1919608.73 | 1934503.21 | -14894.48 |  | 0

## Cost Breakdown
[CORTEX_V2.1] Job #2020 — · Cost Breakdown
Schema CORTEX_V2.1 · canonical v2 builder · single source of truth
| category | cost_codes | actual | pct_of_direct_cost | pct_of_revenue | per_unit | source
| Labor | 11 | 593974 | 1.291% |  | 2662.948
| Material | 8 | 997196 | 73.78% |  | 2554.4952
| Overhead | 2 | 16000 | 2.079% |  | 115.5111
| Burden | 2 | 312438.73 | 1.276% |  | 1384.0708
B. LARGEST OVERRUNS (Actual > Revised Budget)
| Code | Description
| 120 | Roughin Labor | 266055 | 31.03%
| 995 | Payroll Burden | 265927.39 | 27.35%
| 141 | Water Main/Insulation Lab | 57029 | 50.51%
| 241 | Water Main/Insulation Mat | 93431 | 30.75%
| 111 | Garage Labor | 118946 | 19.75%
| 140 | Gas Labor | 13862 | 1.31%
| 600 | Subcontractor | 5000 | 3.318%
| 998 | Payroll Taxes | 46511.34 | 28.89%
| 142 | Mech Room Labor | 12705 | 1.049%
| 130 | Finish Labor | 58664 | 9.524%
C. LARGEST SAVINGS (Actual < Revised Budget)
| Code | Description
| 220 | Roughin Material | 213718 | 58.87%
| 230 | Finish Material | 526401 | 21.73%
| 211 | Garage Material | 92894 | 41.83%
| 242 | Mech Room Material | 7952 | 72.35%
| 240 | Gas Material | 12800 | 35.44%
| 212 | Canout Material | 26700 | 7.401%
| 100 | Supervision | 13700 | 4.916%
SOURCES
Job #2020 — SRM Bellevue @ Main Apartments • GC: Exxel Pacific / Owner: Bellevue Way Ventures • Bellevue, WA
Canonical source: 2020 Job Detail Report.pdf (352 pages, OWP Sage Timberline export)
Cost codes parsed: 24 (Labor+Material+Overhead+Burden+Revenue)
Unit count (288) confirmed by TWO source documents:
1) Bellevue Main – Pricing to go to 101 Taylor Fixtures.xlsx: Type B lavs qty=268, Type A lavs qty=20, Lav faucets qty=288, Bathtub trim qty=288
2) BELLEVUE TRIM QUOTE PRICING organized by category USE.xlsx: Mansfield toilets 268 + 20 ADA = 288
Kitchen fixtures: 257 kitchen faucets (Delta 4353-AR-DST) — 31 fewer than units (studios/amenity)
Contract: One Way Plumbing Executed Contract OCR_D.pdf — Exxel Pacific / SRM Development GC
Billing: 10 archived Schedule of Values files (pay apps #4, 9, 10, 12, 13, 15, 18, 19, 20, 23)
Final contract $2,858,341 after 11 COs (net -$260,659, primarily CO#1 cast iron credit -$389,000)
Permit: City of Bellevue #13-133992-BO (building/plumbing)
| TOTAL |  | 3751904.46 |  |  | 6717.025

## Material
[CORTEX_V2.1] Job #2020 — · Material
Schema CORTEX_V2.1 · canonical v2 builder · single source of truth
| vendor_id | vendor_name | total_spend | transactions | category | source
| 210 | Underground Material | 23300 |  | 0.033187
| 211 | Garage Material | 92894 |  | 0.073448
| 212 | Canout Material | 26700 |  | 0.033606
| 220 | Roughin Material | 213718 |  | 0.11948
| 230 | Finish Material | 526401 |  | 0.56
| 240 | Gas Material | 12800 |  | 0.011232
| 241 | Water Main/Insulation Mat | 93431 |  | 0.16605
| 242 | Mech Room Material | 7952 |  | 0.002989
B. VENDORS BY SPEND (AP)
| Vendor | # Invoices
| Ferguson Enterprises, Inc. | 121 | 216177.2
| Keller Supply Company | 101 | 204979.52
| Rosen Supply Company | 172 | 188562.66
| Mechanical Sales, Inc. | 4 | 67935.82
| Consolidated Supply Co. | 11 | 47819.57
| United Rentals, Inc. | 40 | 23301.34
| Quality Concrete Products, Inc. | 5 | 15202
| Scan2Core, Inc. | 13 | 8585
| MAD Concrete Cutting & Coring, Inc. | 5 | 4605
| Kele, Inc | 6 | 3172.33
| C.M. Hoskins Company | 5 | 2334.26
| Rosen Supply Kirkland | 8 | 2331.87
| Capital One Credit Card | 16 | 2040.76
| Shirley Dennison | 17 | 1700
| Seton Identification Products | 3 | 1302.22
| American Express 3-41000 | 1 | 945
| NRP-Meydenbauer | 4 | 474
| Ferguson Enterprises, Inc. #3007 | 2 | 458.5
| Fastenal Company | 5 | 456.5
| A.R. Brown Backflow Testing | 3 | 304
| Rosen Supply Company, Inc. | 3 | 47.32
SOURCES
Job #2020 — SRM Bellevue @ Main Apartments • GC: Exxel Pacific / Owner: Bellevue Way Ventures • Bellevue, WA
Canonical source: 2020 Job Detail Report.pdf (352 pages, OWP Sage Timberline export)
Cost codes parsed: 24 (Labor+Material+Overhead+Burden+Revenue)
Unit count (288) confirmed by TWO source documents:
1) Bellevue Main – Pricing to go to 101 Taylor Fixtures.xlsx: Type B lavs qty=268, Type A lavs qty=20, Lav faucets qty=288, Bathtub trim qty=288
2) BELLEVUE TRIM QUOTE PRICING organized by category USE.xlsx: Mansfield toilets 268 + 20 ADA = 288
Kitchen fixtures: 257 kitchen faucets (Delta 4353-AR-DST) — 31 fewer than units (studios/amenity)
Contract: One Way Plumbing Executed Contract OCR_D.pdf — Exxel Pacific / SRM Development GC
Billing: 10 archived Schedule of Values files (pay apps #4, 9, 10, 12, 13, 15, 18, 19, 20, 23)
Final contract $2,858,341 after 11 COs (net -$260,659, primarily CO#1 cast iron credit -$389,000)
Permit: City of Bellevue #13-133992-BO (building/plumbing)
Vendor AP ties to JDR 'by Source: AP' line (792,734.87)

## Crew & Labor
[CORTEX_V2.1] Job #2020 — · Crew & Labor
Schema CORTEX_V2.1 · canonical v2 builder · single source of truth
| worker_id | worker_name | total_hours | gross_pay | blended_wage_per_hr | tier | work_days | source
| Veley, Nathaniel S |  | 2965.5 | 93837.5 | 31.6431 | Senior
| Paco Leyva, Orlando |  | 2928.5 | 58335.5 | 19.9199 | Mid
| Gerard, Mitchell J |  | 2472 | 37490 | 15.1659 | Apprentice
| Moran Fernandez, Jose |  | 2334.5 | 37020 | 15.8578 | Apprentice
| Reed, Reuben H |  | 2246 | 67320 | 29.9733 | Mid
| Rodriguez, Fernando V |  | 1869.5 | 28508 | 15.249 | Apprentice
| Meza Fuentes, Erick A |  | 1472.5 | 32385.5 | 21.9935 | Mid
| Monico Brambila, Jesus S |  | 1389 | 22908.5 | 16.4928 | Apprentice
| Taylor, Evan R |  | 1342.5 | 18092.5 | 13.4767 | Apprentice
| Ayers, Jordan L |  | 1335.5 | 20429.5 | 15.2973 | Apprentice
| Holmes, Anthony R |  | 990.5 | 15385.5 | 15.5331 | Apprentice
| Wennig, Johnathan M |  | 978 | 14097.5 | 14.4146 | Apprentice
| Barbosa, Michael S |  | 973.5 | 12783.5 | 13.1315 | Apprentice
| Salazar, Hajdar L |  | 857 | 13712 | 16 | Apprentice
| Cruz Jimenez, Adalberto |  | 857 | 11998 | 14 | Apprentice
| Gonzalez Guzman, Rigoberto A |  | 856.5 | 11286.5 | 13.1775 | Apprentice
| Gerard, Jordan E |  | 824 | 11312 | 13.7282 | Apprentice
| Waites, Thaddeus Z |  | 784 | 23440 | 29.898 | Mid
| Walker, Craig M |  | 730.5 | 10406 | 14.245 | Apprentice
| Sanders, Allen O |  | 712 | 23807.5 | 33.4375 | Senior
| Kinssies, Jr, John E |  | 673 | 10985 | 16.3224 | Apprentice
| Ramos, Jose G |  | 540 | 7020 | 13 | Apprentice
| Donelson, Richard T |  | 477 | 21465 | 45 | Senior
| Galdamez, Dagoberto A |  | 448 | 6368 | 14.2143 | Apprentice
| Lopez Barrios, Luis F |  | 444.5 | 5778.5 | 13 | Apprentice
| Vaughan, Tyler J |  | 412 | 7940.5 | 19.2731 | Mid
| Castro Hernandez, Jose A |  | 411.5 | 8323 | 20.226 | Mid
| Lopez Martinez, Abimael |  | 397 | 5955 | 15 | Apprentice
| Alba Jimenez, Jovani |  | 366 | 5856 | 16 | Apprentice
| Garcia, Jordan X |  | 365.5 | 6024.5 | 16.4829 | Apprentice
| Alba Martinez, Santiago |  | 361 | 6498 | 18 | Mid
| Hubbard, Robert W |  | 359.5 | 13363.5 | 37.1725 | Senior
| Ross, Kelli M |  | 348 | 10788 | 31 | Senior
| Ramos Banegas, Noel O |  | 341.5 | 5464 | 16 | Apprentice
| Ramirez, Lorenzo A |  | 297 | 5049 | 17 | Apprentice
| Santiago, William T |  | 286.5 | 3724.5 | 13 | Apprentice
| Gerard, Jeffrey S |  | 279.5 | 11102.5 | 39.7227 | Senior
| Soto Cruz, Jovani |  | 274 | 4384 | 16 | Apprentice
| Reyes, Robert J |  | 199.5 | 2793 | 14 | Apprentice
| Eliassen, Cory H |  | 192.5 | 2502.5 | 13 | Apprentice
| Palma Vides, Jorge A |  | 176 | 2464 | 14 | Apprentice
| Lima Romero, Melvin A |  | 176 | 4032 | 22.9091 | Mid
| Cortes Mendiola, Victor H |  | 173 | 4844 | 28 | Mid
| Cruz Reyes, Jose |  | 144 | 2016 | 14 | Apprentice
| Palma Vides, Hugo |  | 144 | 4464 | 31 | Senior
| Soto Serna, Cesar E |  | 140 | 1820 | 13 | Apprentice
| Whitaker, Daniel J |  | 110 | 1430 | 13 | Apprentice
| Trump, Norman W |  | 108 | 1836 | 17 | Apprentice
| Hubbard, Dustin R |  | 95 | 1406 | 14.8 | Apprentice
| Schaefer, Taylor E |  | 88 | 1232 | 14 | Apprentice
| Cruz Guzman, Joel A |  | 80 | 1040 | 13 | Apprentice
| Ruiz, Hugo |  | 56 | 784 | 14 | Apprentice
| Gonzalez Hernandez, Josue |  | 46 | 736 | 16 | Apprentice
| Cortes Sepulveda, Jose R |  | 40 | 520 | 13 | Apprentice
| Sepulveda Gonzalez, Alfredo |  | 24 | 640 | 26.6667 | Mid
| Ascencio, Jose L |  | 8 | 112 | 14 | Apprentice
| Anderson, Richard P |  | 7.5 | 230 | 30.6667 | Senior
| TOTAL (57 workers) |  | 38007.5 | 745546 | 19.6158
SOURCES
Job #2020 — SRM Bellevue @ Main Apartments • GC: Exxel Pacific / Owner: Bellevue Way Ventures • Bellevue, WA
Canonical source: 2020 Job Detail Report.pdf (352 pages, OWP Sage Timberline export)
Cost codes parsed: 24 (Labor+Material+Overhead+Burden+Revenue)
Unit count (288) confirmed by TWO source documents:
1) Bellevue Main – Pricing to go to 101 Taylor Fixtures.xlsx: Type B lavs qty=268, Type A lavs qty=20, Lav faucets qty=288, Bathtub trim qty=288
2) BELLEVUE TRIM QUOTE PRICING organized by category USE.xlsx: Mansfield toilets 268 + 20 ADA = 288
Kitchen fixtures: 257 kitchen faucets (Delta 4353-AR-DST) — 31 fewer than units (studios/amenity)
Contract: One Way Plumbing Executed Contract OCR_D.pdf — Exxel Pacific / SRM Development GC
Billing: 10 archived Schedule of Values files (pay apps #4, 9, 10, 12, 13, 15, 18, 19, 20, 23)
Final contract $2,858,341 after 11 COs (net -$260,659, primarily CO#1 cast iron credit -$389,000)
Permit: City of Bellevue #13-133992-BO (building/plumbing)
Tier: Apprentice <$18/hr, Mid $18–30, Senior >$30

## Crew Analytics
[CORTEX_V2.1] Job #2020 — · Crew Analytics
Schema CORTEX_V2.1 · canonical v2 builder · single source of truth
| tier | worker_count | hours | gross_pay | pct_of_hours | blended_wage
| Senior | 8 | 5293 | 179058 | 13.93%
| Mid | 10 | 8988.5 | 213758.5 | 23.65%
| Apprentice | 39 | 23726 | 352729.5 | 62.42%
B. WAGE STATISTICS
| Blended Gross Wage | 19.6158
| Fully-Loaded Wage | 30.6661
| Burden Multiplier | 1.5633
| Min Worker Rate | 13
| Max Worker Rate | 45
| Avg Hours / Worker | 666.7982
SOURCES
Job #2020 — SRM Bellevue @ Main Apartments • GC: Exxel Pacific / Owner: Bellevue Way Ventures • Bellevue, WA
Canonical source: 2020 Job Detail Report.pdf (352 pages, OWP Sage Timberline export)
Cost codes parsed: 24 (Labor+Material+Overhead+Burden+Revenue)
Unit count (288) confirmed by TWO source documents:
1) Bellevue Main – Pricing to go to 101 Taylor Fixtures.xlsx: Type B lavs qty=268, Type A lavs qty=20, Lav faucets qty=288, Bathtub trim qty=288
2) BELLEVUE TRIM QUOTE PRICING organized by category USE.xlsx: Mansfield toilets 268 + 20 ADA = 288
Kitchen fixtures: 257 kitchen faucets (Delta 4353-AR-DST) — 31 fewer than units (studios/amenity)
Contract: One Way Plumbing Executed Contract OCR_D.pdf — Exxel Pacific / SRM Development GC
Billing: 10 archived Schedule of Values files (pay apps #4, 9, 10, 12, 13, 15, 18, 19, 20, 23)
Final contract $2,858,341 after 11 COs (net -$260,659, primarily CO#1 cast iron credit -$389,000)
Permit: City of Bellevue #13-133992-BO (building/plumbing)

## Productivity
[CORTEX_V2.1] Job #2020 — · Productivity
Schema CORTEX_V2.1 · canonical v2 builder · single source of truth
| phase | labor_code | hours | pct_of_total | hours_per_unit
| Supervision | 100 | 301 | 0.7768% | 1.0451
| Takeoff & Purchasing | 101 | 434 | 1.12% | 1.5069
| Underground | 110 | 775 | 2% | 2.691
| Garage | 111 | 6414 | 16.55% | 22.2708
| Canout | 112 | 776.5 | 2.004% | 2.6962
| Foundation Drain | 113 | 144 | 0.3716% | 0.5
| Roughin | 120 | 18980.5 | 48.98% | 65.9045
| Finish | 130 | 3322 | 8.573% | 11.5347
| Gas | 140 | 1515.5 | 3.911% | 5.2622
| Water Main / Insulation | 141 | 4519 | 11.66% | 15.691
| Mech Room | 142 | 1567.5 | 4.045% | 5.4427
B. PRODUCTIVITY RATIOS
| Metric | Value
| Hours / Unit | 134.5451
| Hours / Fixture | 24.7756
| Revenue / Hour | 73.7655
| Profit / Hour | 23.8416
| Units / Month | 13.0909
| Fixtures / Month | 71.0909
| Hours / Month | 1761.3182
| Revenue / Month | 129924.5909
SOURCES
Job #2020 — SRM Bellevue @ Main Apartments • GC: Exxel Pacific / Owner: Bellevue Way Ventures • Bellevue, WA
Canonical source: 2020 Job Detail Report.pdf (352 pages, OWP Sage Timberline export)
Cost codes parsed: 24 (Labor+Material+Overhead+Burden+Revenue)
Unit count (288) confirmed by TWO source documents:
1) Bellevue Main – Pricing to go to 101 Taylor Fixtures.xlsx: Type B lavs qty=268, Type A lavs qty=20, Lav faucets qty=288, Bathtub trim qty=288
2) BELLEVUE TRIM QUOTE PRICING organized by category USE.xlsx: Mansfield toilets 268 + 20 ADA = 288
Kitchen fixtures: 257 kitchen faucets (Delta 4353-AR-DST) — 31 fewer than units (studios/amenity)
Contract: One Way Plumbing Executed Contract OCR_D.pdf — Exxel Pacific / SRM Development GC
Billing: 10 archived Schedule of Values files (pay apps #4, 9, 10, 12, 13, 15, 18, 19, 20, 23)
Final contract $2,858,341 after 11 COs (net -$260,659, primarily CO#1 cast iron credit -$389,000)
Permit: City of Bellevue #13-133992-BO (building/plumbing)

## PO Commitments
[CORTEX_V2.1] Job #2020 — · PO Commitments
Schema CORTEX_V2.1 · canonical v2 builder · single source of truth
| po_number | date | issuer | type | status | description | amount | source
| 30 |  |  |  |  | 110+210 Underground
| 31 |  |  |  |  | 120+220 Roughin
| 32 |  |  |  |  | 130+230 Trim/Finish
| 34 |  |  |  |  | 111+211 Garage
| 40 |  |  |  |  | 141+241 Water Main/Ins
| 41 |  |  |  |  | 140+240 Gas
| OTHER |  |  |  |  | Unclassified
B. COMMITMENTS BY VENDOR
| Vendor |  |  |  |  | PO Count
| ROSEN |  |  |  |  | 96
| FEI |  |  |  |  | 71
| KELLER |  |  |  |  | 60
| OTHER |  |  |  |  | 38
| FASTENAL |  |  |  |  | 6
| MECH SALES |  |  |  |  | 4
| CONSOLIDATED |  |  |  |  | 2
| PIKE |  |  |  |  | 1
| SIOUX CHIEF |  |  |  |  | 1
C. PO COVERAGE NOTES
Total Material Actual (JDR)
Unique PO Count
(Dollar PO commitment not extracted — requires per-PDF parse)
SOURCES
Job #2020 — SRM Bellevue @ Main Apartments • GC: Exxel Pacific / Owner: Bellevue Way Ventures • Bellevue, WA
Canonical source: 2020 Job Detail Report.pdf (352 pages, OWP Sage Timberline export)
Cost codes parsed: 24 (Labor+Material+Overhead+Burden+Revenue)
Unit count (288) confirmed by TWO source documents:
1) Bellevue Main – Pricing to go to 101 Taylor Fixtures.xlsx: Type B lavs qty=268, Type A lavs qty=20, Lav faucets qty=288, Bathtub trim qty=288
2) BELLEVUE TRIM QUOTE PRICING organized by category USE.xlsx: Mansfield toilets 268 + 20 ADA = 288
Kitchen fixtures: 257 kitchen faucets (Delta 4353-AR-DST) — 31 fewer than units (studios/amenity)
Contract: One Way Plumbing Executed Contract OCR_D.pdf — Exxel Pacific / SRM Development GC
Billing: 10 archived Schedule of Values files (pay apps #4, 9, 10, 12, 13, 15, 18, 19, 20, 23)
Final contract $2,858,341 after 11 COs (net -$260,659, primarily CO#1 cast iron credit -$389,000)
Permit: City of Bellevue #13-133992-BO (building/plumbing)
PO count is deduplicated by 5-digit PO number extracted from filenames
Vendor/code classification is heuristic (filename keyword match)

## Billing & SOV
[CORTEX_V2.1] Job #2020 — · Billing & SOV
Schema CORTEX_V2.1 · canonical v2 builder · single source of truth
| pay_app_number | date | contract_total | this_period | retainage | stored_materials | cumulative | pct_complete | source
| 8 | 2014-11-18 | 2770591 | 233070 | 0 | 0 | 667921 | 24.11%
| 8 | 2014-11-18 | 2770591 | 233070 | 0 | 0 | 667921 | 24.11%

## Insights
[CORTEX_V2.1] Job #2020 — · Insights
Schema CORTEX_V2.1 · canonical v2 builder · single source of truth
| insight_id | title | finding | verified | source
| 1 | Labor overran budget by 12.8% | Total labor actual $766,929 vs budget $680,013 — $86,916 unfavorable variance. Review crew mix and productivity. | Derived | budget_vs_actual
| 2 | Largest variance — cost code 220 (Roughin Material) under by $125,817 | Budget $213,718, actual $87,901 (-58.9%). Flag for bid calibration. | Derived | budget_vs_actual

## Benchmark KPIs
[CORTEX_V2.1] Job #2020 — · Benchmark KPIs
Schema CORTEX_V2.1 · canonical v2 builder · single source of truth
CROSS-PROJECT BENCHMARK SCORECARD
Normalized metrics designed for apples-to-apples comparison across all OWP projects.
| KPI | DATA NAME | VALUE | CATEGORY | NOTES / BENCHMARK CONTEXT
| Job Number | job_number | 2,020 | Profile | OWP Sage job ID
| General Contractor | general_contractor | SRM Development / Exxel Pacific (Owner: Bellevue Way Ventures) | Profile | Customer of record
| location | location | Bellevue, WA (15 Bellevue Way SE) | Profile | Project address
| Project Type | project_type | Apartment building | Profile | Building category for benchmarking
| Duration Months | duration_months | 22.0% | Profile | Calendar months from start to close
| Plumbing Units | plumbing_units | 288 | Profile | Residential units delivered
| Contract Original | contract_original | $3,119,000 | Financial | Original contract value
| Contract Final | contract_final | $3,119,000 | Financial | Revised contract value (post-COs)
| Change Orders Net | change_orders_net | 0 | Financial | Net dollar change from COs
| revenue | revenue | $3,119,000 | Financial | Net billed (AR net of reversals)
| Net Profit | net_profit | $1,184,497 | Financial | Revenue − direct cost
| Gross Margin Pct | gross_margin_pct | 38.0% | Financial | Net profit / revenue
| Direct Cost | direct_cost | $1,934,503 | Financial | Σ labor + material + OH + burden + tax
| Overhead Cost | overhead_cost | $33,267 | Financial | Codes 600, 601, 603, 607
| Burden Cost | burden_cost | $338,662 | Financial | Code 995 payroll burden
| Retainage Outstanding | retainage_outstanding | $0.00 | Financial | Held by GC until closeout
| Revenue Per Unit | revenue_per_unit | $10,830 | Financial | Top-line per unit
| Profit Per Unit | profit_per_unit | $4,113 | Financial | Net profit normalized per residential unit
| Cost Per Unit | cost_per_unit | $6,717 | Financial | Total direct cost per unit
| Labor Cost | labor_cost | $766,929 | Labor | Codes 100–150
| Total Hours | total_hours | 76,015 | Labor | All payroll hours on the job
| Total Workers | total_workers | 71 | Crew | Unique payroll IDs across job
| Blended Wage | blended_wage | $19.62 | Labor | Pre-burden average
| Fully Loaded Wage | fully_loaded_wage | $15.33 | Labor | Post-burden true cost
| Burden Multiplier | burden_multiplier | 0.78 | Labor | Loaded / gross
| Hours Per Unit | hours_per_unit | $0.00 | Labor | Key plumbing benchmark
| Labor Per Unit | labor_per_unit | $2,663 | Labor | Payroll only, not material
| Labor Pct Revenue | labor_pct_revenue | 0.25 | Cost Mix | Payroll exposure
| Material Cost | material_cost | $735,695 | Material | Codes 210–244
| Material Per Unit | material_per_unit | $2,554 | Material | Cross-project benchmark
| Material Pct Revenue | material_pct_revenue | 0.24 | Cost Mix | Material/sub exposure
| Total Vendors | total_vendors | 22 | Material | Distinct AP vendors invoiced on the job
| Top Vendor Spend | top_vendor_spend | $0.00 | Material | Largest single supplier
| Top Vendor Pct | top_vendor_pct | 0.0% | Material | Top vendor concentration
| Revenue Per Month | revenue_per_month | $141,773 | Throughput | Billing velocity
| Hours Per Month | hours_per_month | $0.00 | Throughput | Avg monthly labor burn
| Units Per Month | units_per_month | $13.09 | Throughput | Build pace
SOURCES
Canonical: /sessions/keen-determined-mccarthy/mnt/cortex-mockup/owp/cortex v2 files/OWP_2020_JCR_Cortex_v2.xlsx
revenue: AR net-of-reversals (validator)
labor_cost: Codes 100–150
material_cost: Codes 210–244
total_workers: count(distinct worker_id)

## Change Log
[CORTEX_V2.1] Job #2020 — · Change Log
Schema CORTEX_V2.1 · canonical v2 builder · single source of truth
| event_id | type | date | subject | originator | linked_events | cost_impact | schedule_days | status | source_document
| CO-003-UNEXEC | COR | 2014-10-07 | CR #1092 Upgrade plumbing fixture package to match 101 Taylor (UNEXECUTED) | Owner (SRM) | CR-1092 | 37931 | 0 | Unexecuted | 2020-SRM, Bellevue @ Main/Change Orders/CO_s/ONEWAY UNEXECUTED CO 3.pdf
| CO-004 | CO | 2014-11-14 | CR #1102 Undercounter vanity sinks — Kohler K2214 Ladena Type A/B | Owner (SRM) | CR-1102 | 31418 | 0 | Executed | 2020-SRM, Bellevue @ Main/Change Orders/CO_s/One Way signed change order 4.pdf
| CO-005-UNEXEC | COR | 2014-12-02 | CR #1106 Water cooler upgrades (Elkay LZSTL8WSS3K, LZS8WSS2K) — UNEXECUTED | Owner (SRM) | CR-1106 | 5085 | 0 | Unexecuted | 2020-SRM, Bellevue @ Main/Change Orders/CO_s/UNEXECUTED OWP CO 5.pdf
| CO-006 | CO | 2015-01-19 | CR #1121 Misc plumbing revisions — 9 planter drains, sports lounge, mop sinks, drains, grease interceptor, RPBA, hose bibb, FD deletes | Owner (SRM) | CR-1121 | 4756 | 0 | Executed | 2020-SRM, Bellevue @ Main/Change Orders/CO_s/One Way signed change order 6.pdf
| CO-007 | CO | 2015-09-23 | CR #1235 Eyewash station w/ mixing valve @ Maintenance Shop | Owner (SRM) | CR-1235 | 2852 | 0 | Executed | 2020-SRM, Bellevue @ Main/Change Orders/CO_s/One Way signed change order 7.pdf
| CO-008 | CO | 2015-10-26 | CR #1253 Hose bibbs (courtyard + decks) + 3 BBQ sinks + 1-1/4" gas to Whisk retail | Owner (SRM) | CR-1253 | 22671 | 0 | Executed | 2020-SRM, Bellevue @ Main/Change Orders/CO_s/One Way signed change order 8.pdf
| CO-009 | CO | 2015-11-23 | CR #1277 Theater sink + relocate ice maker boxes L4-5 + courtyard water feature piping + CBV consolidation | Owner (SRM) | CR-1277 | 9131 | 0 | Executed | 2020-SRM, Bellevue @ Main/Change Orders/CO_s/One Way signed change order 9.pdf
| CO-010 | CO | 2016-01-18 | CR #1305 Attic stock + ADA toilet flange relocations units 327/331/231/450/461 | Owner (SRM) / Todd Rankin | CR-1305 | 4210 | 0 | Executed | 2020-SRM, Bellevue @ Main/Change Orders/CO_s/One Way signed change order 10.pdf
| CO-011 | CO | 2016-02-25 | CR #1361 Barber waste extension + vanity sink replacements (trade damage) + condensate drains + retail/gas deduct meters + two-stage drains | Owner (SRM) | CR-1361 | 15963 | 0 | Executed | 2020-SRM, Bellevue @ Main/Change Orders/CO_s/One Way signed change order 11.pdf
| CO-012 | Backcharge | 2016-03-11 | CR #1396 Water damage repair — OWP uncapped pipe (CREDIT) | GC | CR-1396 | -6655 | 0 | Executed | 2020-SRM, Bellevue @ Main/Change Orders/CO_s/One Way signed change order 12.pdf
| DOC-GAP-CO-1-2 | Memo |  | GAP: CO #1 and CO #2 not found in any extracted folder; may exist in archived OLD DROPBOX FILES subdirectories. | OWP |  | 0 | 0 | Open | 2020-SRM, Bellevue @ Main/Change Orders/CO_s/ (CO1+CO2 missing)
| DOC-GAP-RESUB | Memo |  | GAP: 206+ submittal documents but no formal resubmission log; tracked only by ORIGINAL/RESPONSE folder structure. | OWP |  | 0 | 0 | Open | 2020-SRM, Bellevue @ Main/Submittals/
| RFI-SUMMARY | Memo |  | 56 RFIs in primary folder (duplicates across 4 extracted instances totaling 282 occurrences). RFI range #027-#258. Focus: structural, concrete, shearwall, countertop, column conflicts, drainage, flashing. | GC |  | 0 | 0 | Informational | 2020-SRM, Bellevue @ Main/ASI-RFI/

## Root Cause Analysis
[CORTEX_V2.1] Job #2020 — · Root Cause Analysis
Schema CORTEX_V2.1 · canonical v2 builder · single source of truth
| rca_id | observation | root_cause | responsibility | cost_impact | mitigation | source
| RCA-01 | CR #1092 Upgrade plumbing fixture package to match 101 Taylor (UNEXECUTED) | Pending document review — see source document for detail | Owner | 37931 |  | 2020-SRM, Bellevue @ Main/Change Orders/CO_s/ONEWAY UNEXECUTED CO 3.pdf
| RCA-02 | CR #1102 Undercounter vanity sinks — Kohler K2214 Ladena Type A/B | Pending document review — see source document for detail | Owner | 31418 |  | 2020-SRM, Bellevue @ Main/Change Orders/CO_s/One Way signed change order 4.pdf
| RCA-03 | CR #1106 Water cooler upgrades (Elkay LZSTL8WSS3K, LZS8WSS2K) — UNEXECUTED | Pending document review — see source document for detail | Owner | 5085 |  | 2020-SRM, Bellevue @ Main/Change Orders/CO_s/UNEXECUTED OWP CO 5.pdf
| RCA-04 | CR #1121 Misc plumbing revisions — 9 planter drains, sports lounge, mop sinks, drains, grease interceptor, RPBA, hose bibb, FD deletes | Pending document review — see source document for detail | Owner | 4756 |  | 2020-SRM, Bellevue @ Main/Change Orders/CO_s/One Way signed change order 6.pdf
| RCA-05 | CR #1235 Eyewash station w/ mixing valve @ Maintenance Shop | Pending document review — see source document for detail | Owner | 2852 |  | 2020-SRM, Bellevue @ Main/Change Orders/CO_s/One Way signed change order 7.pdf
| RCA-06 | CR #1253 Hose bibbs (courtyard + decks) + 3 BBQ sinks + 1-1/4" gas to Whisk retail | Pending document review — see source document for detail | Owner | 22671 |  | 2020-SRM, Bellevue @ Main/Change Orders/CO_s/One Way signed change order 8.pdf
| RCA-07 | CR #1277 Theater sink + relocate ice maker boxes L4-5 + courtyard water feature piping + CBV consolidation | Pending document review — see source document for detail | Owner | 9131 |  | 2020-SRM, Bellevue @ Main/Change Orders/CO_s/One Way signed change order 9.pdf
| RCA-08 | CR #1305 Attic stock + ADA toilet flange relocations units 327/331/231/450/461 | Pending document review — see source document for detail | Owner | 4210 |  | 2020-SRM, Bellevue @ Main/Change Orders/CO_s/One Way signed change order 10.pdf
| RCA-09 | CR #1361 Barber waste extension + vanity sink replacements (trade damage) + condensate drains + retail/gas deduct meters + two-stage drains | Pending document review — see source document for detail | Owner | 15963 |  | 2020-SRM, Bellevue @ Main/Change Orders/CO_s/One Way signed change order 11.pdf

## Predictive Signals
[CORTEX_V2.1] Job #2020 — · Predictive Signals
Schema CORTEX_V2.1 · canonical v2 builder · single source of truth
| signal_id | signal_name | direction | metric | threshold | historical_outcome | source
| WAREHOUSE | Predictive signals computed at warehouse layer | Neutral | cross-project benchmark | n/a | See benchmark_envelopes view; not stored per-project. | warehouse view (predictive_signals_v)

## Metric Registry
[CORTEX_V2.1] Job #2020 — · Metric Registry
Schema CORTEX_V2.1 · canonical v2 builder · single source of truth
| metric_key | metric_label | value | data_label | tab_home | verification | source
2020
SRM Bellevue @ Main Apartments
SRM Development / Exxel Pacific (Owner: Bellevue Way Ventures)
Bellevue, WA (15 Bellevue Way SE)
6-story 288-unit luxury multifamily + retail (268 Type B + 20 Type A ADA)
22
288
1564
3119000
2858341
-260659
2858341
923837.79
0.32321
1934503.21
766929.01
735694.62
33267.19
398612.39
142517
38749
57
19.2404
21
279
-0.083571
56
0
9
1
0
12
13
127362

## Reconciliation
[CORTEX_V2.1] Job #2020 — · Reconciliation
Schema CORTEX_V2.1 · canonical v2 builder · single source of truth
| check_number | check_description | value_a | value_b | difference | status | tabs
A. JDR COST CODE ROLLUP
|  | Labor subtotal (11 codes) | 766929.01 |  |  | TIES
|  | Material subtotal (8 codes) | 735694.62 |  |  | TIES
|  | Overhead subtotal (2 codes) | 33267.19 |  |  | TIES
|  | Burden subtotal (2 codes) | 398612.39 |  |  | TIES
|  | Direct Cost (all categories) | 1934503.21 |  |  | TIES
|  | Revenue (code 999) | 2858341 |  |  | WITHIN
|  | Net Profit (Revenue - Expenses) | 923837.79 |  |  | WITHIN
B. LABOR HOURS ROLLUP
|  | JDR Cost Code hours (Payroll Hours lines) | 38749 |  |  | TIES
|  | Per-worker hours (sum of PR Regular) | 38749 |  |  | WITHIN
C. BILLING (SOV) ↔ JDR
|  | Final Contract Value | 2858341 |  |  | TIES
|  | Retainage | 142517 |  |  | TIES
|  | Direct Cost | 1934503.21 |  |  | TIES
D. VENDOR AP ↔ JDR
|  | Vendor AP total (sum of invoices) | 792735 |  |  | TIES
SOURCES
Job #2020 — SRM Bellevue @ Main Apartments • GC: Exxel Pacific / Owner: Bellevue Way Ventures • Bellevue, WA
Canonical source: 2020 Job Detail Report.pdf (352 pages, OWP Sage Timberline export)
Cost codes parsed: 24 (Labor+Material+Overhead+Burden+Revenue)
Unit count (288) confirmed by TWO source documents:
1) Bellevue Main – Pricing to go to 101 Taylor Fixtures.xlsx: Type B lavs qty=268, Type A lavs qty=20, Lav faucets qty=288, Bathtub trim qty=288
2) BELLEVUE TRIM QUOTE PRICING organized by category USE.xlsx: Mansfield toilets 268 + 20 ADA = 288
Kitchen fixtures: 257 kitchen faucets (Delta 4353-AR-DST) — 31 fewer than units (studios/amenity)
Contract: One Way Plumbing Executed Contract OCR_D.pdf — Exxel Pacific / SRM Development GC
Billing: 10 archived Schedule of Values files (pay apps #4, 9, 10, 12, 13, 15, 18, 19, 20, 23)
Final contract $2,858,341 after 11 COs (net -$260,659, primarily CO#1 cast iron credit -$389,000)
Permit: City of Bellevue #13-133992-BO (building/plumbing)
TIES = within $1 or 5 hrs • WITHIN = within 5% • OFF = investigate
K. CHANGE LOG ↔ ROOT CAUSE ANALYSIS
|  | Total Event Count | 13 |  |  | TIES
|  | Net $ Impact (all events) | 127362 |  |  | TIES
L. PREDICTIVE SIGNALS ↔ CHANGE LOG
|  | Backcharge Count signal | 1 |  |  | TIES
M. METRIC REGISTRY ↔ BENCHMARK KPIs
|  | revenue (row 17) | 2858341 |  |  | TIES
|  | unit_count (row 12) | 288 |  |  | TIES
|  | total_fixtures (row 13) | 1564 |  |  | TIES
|  | direct_cost (row 19) | 1934503.21 |  |  | OFF
|  | total_pos (row 30) | 279 |  |  | TIES
N. CHANGE LOG ↔ METRIC REGISTRY (event counts)
|  | change_event_total | 13 |  |  | OFF
SOURCES
Job #2020 — Cortex v2 17-tab layout
12 analytical tabs + Change Log + Root Cause Analysis + Predictive Signals + Metric Registry + Reconciliation
Canonical source: 2020 Job Detail Report.pdf (Sage Timberline export)
Change artifacts: folders scanned — ASI-RFI, Change Orders, Submittals, Invoices (Backcharges), JDR cost codes
Every Change Log row cites its source document path
TIES = within $1/5hrs/exact count • WITHIN = within 5% • OFF = investigate
Cross-sheet formulas (='Tab'!Cell) update automatically when source tabs change
Tabs: 1-12 analytical • 13=ChangeLog • 14=RootCause • 15=PredictiveSignals • 16=MetricRegistry • 17=Reconciliation

## Vendors
[CORTEX_V2.1] Job #2020 — · Vendors
Schema CORTEX_V2.1 · canonical v2 builder · single source of truth
| vendor_id | vendor_name | total_spend | transactions | category | source
Invoices
121
101
172
4
11
40
5
13
5
6
5
8
16
17
3
1
4
2
5
3
3