## Overview
[CORTEX_V2.1] Job #2021 — · Overview
Schema CORTEX_V2.1 · canonical v2 builder · single source of truth
| OVERVIEW |  | SOURCE
IDENTITY
| Project Job Number | 2021
| Project Name: | Exxel Pacific Admiral East Apartments
CONTRACT & PARTIES
| General Contractor | Exxel Pacific, Inc.
JOB SITE
| Jobsite Location | Seattle, WA (2600 SW Admiral Way, West Seattle)
| Plumbing Units | 182 | ADA Units
SCHEDULE
| Project Duration | Feb 2015 – Aug 2016 (~19 months)
SCOPE & DESIGN
| Fixtures / Unit | 4.90 | Duration
| Water Closets | 182 | Kitchen Faucets
| Tub/Shower Valves | 159 | Total Fixtures
| CONTRACT VALUE |  | NET PROFIT |  | DIRECT COST |  | LABOR HOURS
| $1,558,650 |  | $448,741 |  | $1,133,077 |  | 41,555
| Original $1,558,650 |  | 28.4% margin |  | 71.6% of revenue |  | 55 workers
COST BREAKDOWN
| Category | Budget | Actual | Variance | % Budget | % of Cost
| Labor | 387079 | 429422.78 | -42343.78 | 110.9% | 37.9%
| Material | 494749 | 423924.46 | 70824.54 | 85.68% | 37.41%
| Overhead | 71320 | 66646.5 | 4673.5 | 93.45% | 5.882%
| Burden | 192149.33 | 213083.05 | -20933.72 | 110.9% | 18.81%
| TOTAL | 1145297.33 | 1133076.79 | 12220.54 | 98.93% | 100%
PROJECT PROFILE
| Plumbing Units | 182 |  | Fixtures / Unit | 4.90 |  | Water Closets | 182
| Bathtub/Shower | 159 |  | Duration | Feb 2015 – Aug 2016 (~19 months)

## Budget vs Actual
[CORTEX_V2.1] Job #2021 — · Budget vs Actual
Schema CORTEX_V2.1 · canonical v2 builder · single source of truth
| cost_code | description | original_budget | revised_budget | actual | variance | pct_used | hours | source
LABOR
| 100 | Supervision | 12920 | 13414 | 8726 | 4688 | 65.05%
| 101 | Takeoff & Purchase Labor | 12920 | 13887 | 19430.5 | -5543.5 | 1.399%
| 110 | Underground Labor | 12625 | 18310 | 21121.15 | -2811.15 | 1.154%
| 111 | Garage Labor | 46180 | 48780 | 40673.76 | 8106.24 | 83.38%
| 112 | Canout Labor | 8500 | 8500 | 9421.18 | -921.18 | 1.108%
| 120 | Roughin Labor | 205015 | 208728 | 232285.5 | -23557.5 | 1.113%
| 130 | Finish Labor | 32520 | 32580 | 30179 | 2401 | 92.63%
| 140 | Gas Labor | 5500 | 7990 | 10305.46 | -2315.46 | 1.29%
| 141 | Water Main/Insulation Lab | 34750 | 34890 | 56135.73 | -21245.73 | 1.609%
| 142 | Mech Room Labor | 0 | 0 | 1144.5 | -1144.5 | 0%
MATERIAL
| 210 | Underground Material | 13250 | 13550 | 21743.86 | -8193.86 | 1.605%
| 211 | Garage Material | 36150 | 37700 | 39526.02 | -1826.02 | 1.048%
| 212 | Canout Material | 9520 | 9520 | 6538.72 | 2981.28 | 68.68%
| 220 | Roughin Material | 145590 | 120660 | 99695.01 | 20964.99 | 82.62%
| 230 | Finish Material | 256900 | 260675 | 202739.69 | 57935.31 | 77.77%
| 240 | Gas Material | 5500 | 7369 | 3604.09 | 3764.91 | 48.91%
| 241 | Water Main/Insulation Mat | 45175 | 45275 | 49938.59 | -4663.59 | 1.103%
| 242 | Mech Room Material | 0 | 0 | 5.44 | -5.44 | 0%
| 244 | Fire Caulking Material | 0 | 0 | 133.04 | -133.04 | 0%
OVERHEAD
| 600 | Subcontractor | 21050 | 21550 | 4501 | 17049 | 20.89%
| 601 | Engineering/Plans | 38000 | 39000 | 53259.5 | -14259.5 | 1.366%
| 603 | Permits & Licenses | 10770 | 10770 | 8886 | 1884 | 82.51%
BURDEN
| 995 | Payroll Burden | 167567.61 | 160896.89 | 178143.53 | -17246.64 | 1.107%
| 998 | Payroll Taxes | 28904 | 31252.44 | 34939.52 | -3687.08 | 1.118%
SOURCES
Job #2021 — Exxel Pacific Admiral East Apartments • GC: Exxel Pacific, Inc. • 2600 SW Admiral Way, West Seattle
Canonical source: 2021 Job Detail Report.pdf (189 pages, OWP Sage Timberline export)
Cost codes parsed: 25
Unit count (182) confirmed by ADMIRAL TRIM - KELLER.xlsx SUMMATION:
• 171 Gerber 21-962 standard elongated toilets
• 11 Gerber 21-928 ADA elongated toilets
• 182 Delta 559LF-PP lav faucets (one per unit)
• 159 tub/shower + 21 shower-only = 180 bathing fixtures
• 138 kitchen faucets (44 fewer than units — studio/SRO variants)
Contract: Admiral Contract executed - OCR_d.pdf (Exxel Pacific GC)
Billing: ADMIRAL AGGREGATE BILLING.xlsx (17 pay apps Feb 2015 – Aug 2016) + 17 SOV files
Final contract $1,581,818 (original $1,558,650 + $23,168 COs)
| TOTAL |  | 1149306.61 | 1145297.33 | 1133076.79 | 12220.54 |  | 0

## Cost Breakdown
[CORTEX_V2.1] Job #2021 — · Cost Breakdown
Schema CORTEX_V2.1 · canonical v2 builder · single source of truth
| category | cost_codes | actual | pct_of_direct_cost | pct_of_revenue | per_unit | source
| Labor | 10 | 387079 | 1.109% |  | 2359.4658
| Material | 9 | 494749 | 85.68% |  | 2329.2553
| Overhead | 3 | 71320 | 93.45% |  | 366.1896
| Burden | 2 | 192149.33 | 1.109% |  | 1170.786
B. LARGEST OVERRUNS (Actual > Revised Budget)
| Code | Description
| 120 | Roughin Labor | 208728 | 11.29%
| 141 | Water Main/Insulation Lab | 34890 | 60.89%
| 995 | Payroll Burden | 160896.89 | 10.72%
| 601 | Engineering/Plans | 39000 | 36.56%
| 210 | Underground Material | 13550 | 60.47%
| 101 | Takeoff & Purchase Labor | 13887 | 39.92%
| 241 | Water Main/Insulation Mat | 45275 | 10.3%
| 998 | Payroll Taxes | 31252.44 | 11.8%
| 110 | Underground Labor | 18310 | 15.35%
| 140 | Gas Labor | 7990 | 28.98%
C. LARGEST SAVINGS (Actual < Revised Budget)
| Code | Description
| 230 | Finish Material | 260675 | 22.23%
| 220 | Roughin Material | 120660 | 17.38%
| 600 | Subcontractor | 21550 | 79.11%
| 111 | Garage Labor | 48780 | 16.62%
| 100 | Supervision | 13414 | 34.95%
| 240 | Gas Material | 7369 | 51.09%
| 212 | Canout Material | 9520 | 31.32%
| 130 | Finish Labor | 32580 | 7.37%
| 603 | Permits & Licenses | 10770 | 17.49%
SOURCES
Job #2021 — Exxel Pacific Admiral East Apartments • GC: Exxel Pacific, Inc. • 2600 SW Admiral Way, West Seattle
Canonical source: 2021 Job Detail Report.pdf (189 pages, OWP Sage Timberline export)
Cost codes parsed: 25
Unit count (182) confirmed by ADMIRAL TRIM - KELLER.xlsx SUMMATION:
• 171 Gerber 21-962 standard elongated toilets
• 11 Gerber 21-928 ADA elongated toilets
• 182 Delta 559LF-PP lav faucets (one per unit)
• 159 tub/shower + 21 shower-only = 180 bathing fixtures
• 138 kitchen faucets (44 fewer than units — studio/SRO variants)
Contract: Admiral Contract executed - OCR_d.pdf (Exxel Pacific GC)
Billing: ADMIRAL AGGREGATE BILLING.xlsx (17 pay apps Feb 2015 – Aug 2016) + 17 SOV files
Final contract $1,581,818 (original $1,558,650 + $23,168 COs)
| TOTAL |  | 2244394.66 |  |  | 6225.6966

## Material
[CORTEX_V2.1] Job #2021 — · Material
Schema CORTEX_V2.1 · canonical v2 builder · single source of truth
| vendor_id | vendor_name | total_spend | transactions | category | source
| 210 | Underground Material | 13550 |  | 0.051292
| 211 | Garage Material | 37700 |  | 0.093238
| 212 | Canout Material | 9520 |  | 0.015424
| 220 | Roughin Material | 120660 |  | 0.23517
| 230 | Finish Material | 260675 |  | 0.47824
| 240 | Gas Material | 7369 |  | 0.0085017
| 241 | Water Main/Insulation Mat | 45275 |  | 0.1178
| 242 | Mech Room Material | 0 |  | 1.2832e-05
| 244 | Fire Caulking Material | 0 |  | 0.00031383
B. VENDORS BY SPEND (AP)
| Vendor | # Invoices
| Ferguson Enterprises, Inc. | 82 | 121504.28
| Rosen Supply Company | 77 | 98623.69
| Keller Supply Company | 52 | 76284.33
| Franklin Engineering | 8 | 53259.5
| Mechanical Sales, Inc. | 3 | 34858.54
| Specification Sales, Inc. | 2 | 21294
| Bank of America CC | 5 | 8886
| Core & Main LP | 6 | 4652.03
| Scan2Core, Inc. | 5 | 4401
| Quality Concrete Products, Inc. | 4 | 3386
| Manor Hardware & Construction Supply | 4 | 1442.8
| Capital One Credit Card | 5 | 1311.2
| Rosen Supply Kirkland | 3 | 1290.12
| Consolidated Supply Co. | 4 | 1260.54
| C.M. Hoskins Company | 3 | 891.82
| ACME Corp | 3 | 759.6
| Ferguson Enterprises, Inc. #3007 | 4 | 725.12
| Kele, Inc | 2 | 713.58
| Beacon Building Products | 2 | 576.57
| Rosen Supply Company, Inc. | 5 | 202.75
| A.R. Brown Backflow Testing | 1 | 100
SOURCES
Job #2021 — Exxel Pacific Admiral East Apartments • GC: Exxel Pacific, Inc. • 2600 SW Admiral Way, West Seattle
Canonical source: 2021 Job Detail Report.pdf (189 pages, OWP Sage Timberline export)
Cost codes parsed: 25
Unit count (182) confirmed by ADMIRAL TRIM - KELLER.xlsx SUMMATION:
• 171 Gerber 21-962 standard elongated toilets
• 11 Gerber 21-928 ADA elongated toilets
• 182 Delta 559LF-PP lav faucets (one per unit)
• 159 tub/shower + 21 shower-only = 180 bathing fixtures
• 138 kitchen faucets (44 fewer than units — studio/SRO variants)
Contract: Admiral Contract executed - OCR_d.pdf (Exxel Pacific GC)
Billing: ADMIRAL AGGREGATE BILLING.xlsx (17 pay apps Feb 2015 – Aug 2016) + 17 SOV files
Final contract $1,581,818 (original $1,558,650 + $23,168 COs)
Vendor AP ties to JDR 'by Source: AP' line (436,423.47)

## Crew & Labor
[CORTEX_V2.1] Job #2021 — · Crew & Labor
Schema CORTEX_V2.1 · canonical v2 builder · single source of truth
| worker_id | worker_name | total_hours | gross_pay | blended_wage_per_hr | tier | work_days | source
| Gonzalez Hernandez, Josue |  | 1565.5 | 29049 | 18.5557 | Mid
| Quintanilla, Esteban R |  | 1507.5 | 51734 | 34.3177 | Senior
| Rivera, Jorge A |  | 1471.5 | 33849.5 | 23.0034 | Mid
| Montenegro, Carlos E |  | 1390.5 | 25856.5 | 18.5951 | Mid
| Palma Vides, Hugo |  | 1355 | 43226 | 31.9011 | Senior
| Palma Vides, Jorge A |  | 1309 | 19936 | 15.2299 | Apprentice
| Lima Romero, Melvin A |  | 1232 | 29632 | 24.0519 | Mid
| Benites Portillo, Marvin E |  | 859 | 12533 | 14.5902 | Apprentice
| Castro Hernandez, Jose A |  | 804 | 17257 | 21.4639 | Mid
| Rodriguez Bonilla, Lisandro |  | 785 | 12137 | 15.4611 | Apprentice
| Galdamez, Dagoberto A |  | 752 | 11280 | 15 | Apprentice
| Reyes, Robert J |  | 655 | 10728 | 16.3786 | Apprentice
| Sepulveda Gonzalez, Alfredo |  | 616 | 18208 | 29.5584 | Mid
| Reyes Cruz, Denis A |  | 487 | 7969 | 16.3634 | Apprentice
| Aguilar Rivas, Henry |  | 480 | 6504 | 13.55 | Apprentice
| Cruz Reyes, Jose |  | 480 | 7472 | 15.5667 | Apprentice
| Cruz Guzman, Joel A |  | 474 | 6826 | 14.4008 | Apprentice
| Gerard, Jeffrey S |  | 470.5 | 19658 | 41.7811 | Senior
| Sanders, Allen O |  | 404 | 14532.5 | 35.9715 | Senior
| Eliassen, Cory H |  | 403 | 5961 | 14.7916 | Apprentice
| Alba Jimenez, Jovani |  | 402 | 6432 | 16 | Apprentice
| Spears, Gregory M |  | 397 | 6621 | 16.6776 | Apprentice
| Hubbard, Robert W |  | 376.5 | 14905 | 39.5883 | Senior
| Lovo, German G |  | 349 | 5584 | 16 | Apprentice
| Vaughan, Tyler J |  | 276 | 5737 | 20.7862 | Mid
| Monico Brambila, Jesus S |  | 253 | 4807 | 19 | Mid
| Alba Martinez, Santiago |  | 228 | 4104 | 18 | Mid
| Donelson, Richard T |  | 188 | 8514 | 45.2872 | Senior
| Meza Fuentes, Erick A |  | 141 | 3525 | 25 | Mid
| Gerard, Mitchell J |  | 131 | 2489 | 19 | Mid
| Anzora, William |  | 105 | 1785 | 17 | Apprentice
| Gerard, Jordan E |  | 86 | 1548 | 18 | Mid
| Waites, Thaddeus Z |  | 84 | 2940 | 35 | Senior
| McCabe, Thomas C |  | 80 | 2000 | 25 | Mid
| Cortes Sepulveda, Jose R |  | 56 | 728 | 13 | Apprentice
| Hubbard, Dustin R |  | 40 | 657 | 16.425 | Apprentice
| Balderas Ortiz, Ricardo I |  | 32 | 544 | 17 | Apprentice
| Taylor, Evan R |  | 32 | 512 | 16 | Apprentice
| Barnhart, Joseph N |  | 12.5 | 452 | 36.16 | Senior
| Gardner, Andrew M |  | 8 | 112 | 14 | Apprentice
| TOTAL (40 workers) |  | 20777.5 | 458344.5 | 22.0597
SOURCES
Job #2021 — Exxel Pacific Admiral East Apartments • GC: Exxel Pacific, Inc. • 2600 SW Admiral Way, West Seattle
Canonical source: 2021 Job Detail Report.pdf (189 pages, OWP Sage Timberline export)
Cost codes parsed: 25
Unit count (182) confirmed by ADMIRAL TRIM - KELLER.xlsx SUMMATION:
• 171 Gerber 21-962 standard elongated toilets
• 11 Gerber 21-928 ADA elongated toilets
• 182 Delta 559LF-PP lav faucets (one per unit)
• 159 tub/shower + 21 shower-only = 180 bathing fixtures
• 138 kitchen faucets (44 fewer than units — studio/SRO variants)
Contract: Admiral Contract executed - OCR_d.pdf (Exxel Pacific GC)
Billing: ADMIRAL AGGREGATE BILLING.xlsx (17 pay apps Feb 2015 – Aug 2016) + 17 SOV files
Final contract $1,581,818 (original $1,558,650 + $23,168 COs)
Tier: Apprentice <$18/hr, Mid $18–30, Senior >$30

## Crew Analytics
[CORTEX_V2.1] Job #2021 — · Crew Analytics
Schema CORTEX_V2.1 · canonical v2 builder · single source of truth
| tier | worker_count | hours | gross_pay | pct_of_hours | blended_wage
| Senior | 8 | 4398 | 155961.5 | 21.17%
| Mid | 13 | 8274.5 | 178062 | 39.82%
| Apprentice | 19 | 8105 | 124321 | 39.01%
B. WAGE STATISTICS
| Blended Gross Wage | 22.0597
| Fully-Loaded Wage | 30.9232
| Burden Multiplier | 1.4018
| Min Worker Rate | 13
| Max Worker Rate | 45.2872
| Avg Hours / Worker | 519.4375
SOURCES
Job #2021 — Exxel Pacific Admiral East Apartments • GC: Exxel Pacific, Inc. • 2600 SW Admiral Way, West Seattle
Canonical source: 2021 Job Detail Report.pdf (189 pages, OWP Sage Timberline export)
Cost codes parsed: 25
Unit count (182) confirmed by ADMIRAL TRIM - KELLER.xlsx SUMMATION:
• 171 Gerber 21-962 standard elongated toilets
• 11 Gerber 21-928 ADA elongated toilets
• 182 Delta 559LF-PP lav faucets (one per unit)
• 159 tub/shower + 21 shower-only = 180 bathing fixtures
• 138 kitchen faucets (44 fewer than units — studio/SRO variants)
Contract: Admiral Contract executed - OCR_d.pdf (Exxel Pacific GC)
Billing: ADMIRAL AGGREGATE BILLING.xlsx (17 pay apps Feb 2015 – Aug 2016) + 17 SOV files
Final contract $1,581,818 (original $1,558,650 + $23,168 COs)

## Productivity
[CORTEX_V2.1] Job #2021 — · Productivity
Schema CORTEX_V2.1 · canonical v2 builder · single source of truth
| phase | labor_code | hours | pct_of_total | hours_per_unit
| Supervision | 100 | 205 | 1.035% | 1.1264
| Takeoff & Purchasing | 101 | 453.5 | 2.29% | 2.4918
| Underground | 110 | 990 | 5% | 5.4396
| Garage | 111 | 1788 | 9.031% | 9.8242
| Canout | 112 | 450 | 2.273% | 2.4725
| Roughin | 120 | 11448.5 | 57.82% | 62.9038
| Finish | 130 | 1291 | 6.52% | 7.0934
| Gas | 140 | 415.5 | 2.099% | 2.283
| Water Main / Insulation | 141 | 2735.5 | 13.82% | 15.0302
| Mech Room | 142 | 22.5 | 0.1136% | 0.12363
B. PRODUCTIVITY RATIOS
| Metric | Value
| Hours / Unit | 108.7885
| Hours / Fixture | 22.2217
| Revenue / Hour | 79.8918
| Profit / Hour | 22.6643
| Units / Month | 9.5789
| Fixtures / Month | 46.8947
| Hours / Month | 1042.0789
| Revenue / Month | 83253.5789
SOURCES
Job #2021 — Exxel Pacific Admiral East Apartments • GC: Exxel Pacific, Inc. • 2600 SW Admiral Way, West Seattle
Canonical source: 2021 Job Detail Report.pdf (189 pages, OWP Sage Timberline export)
Cost codes parsed: 25
Unit count (182) confirmed by ADMIRAL TRIM - KELLER.xlsx SUMMATION:
• 171 Gerber 21-962 standard elongated toilets
• 11 Gerber 21-928 ADA elongated toilets
• 182 Delta 559LF-PP lav faucets (one per unit)
• 159 tub/shower + 21 shower-only = 180 bathing fixtures
• 138 kitchen faucets (44 fewer than units — studio/SRO variants)
Contract: Admiral Contract executed - OCR_d.pdf (Exxel Pacific GC)
Billing: ADMIRAL AGGREGATE BILLING.xlsx (17 pay apps Feb 2015 – Aug 2016) + 17 SOV files
Final contract $1,581,818 (original $1,558,650 + $23,168 COs)

## PO Commitments
[CORTEX_V2.1] Job #2021 — · PO Commitments
Schema CORTEX_V2.1 · canonical v2 builder · single source of truth
| po_number | date | issuer | type | status | description | amount | source
| 30 |  |  |  |  | 110+210 Underground
| 31 |  |  |  |  | 120+220 Roughin
| 32 |  |  |  |  | 130+230 Trim/Finish
| 40 |  |  |  |  | 141+241 Water Main/Ins
| 41 |  |  |  |  | 140+240 Gas
| OTHER |  |  |  |  | Unclassified
B. COMMITMENTS BY VENDOR
| Vendor |  |  |  |  | PO Count
| FEI |  |  |  |  | 64
| ROSEN |  |  |  |  | 56
| KELLER |  |  |  |  | 28
| OTHER |  |  |  |  | 22
| MANOR |  |  |  |  | 4
| CONSOLIDATED |  |  |  |  | 2
| MECH SALES |  |  |  |  | 1
C. PO COVERAGE NOTES
Total Material Actual (JDR)
Unique PO Count
(Dollar PO commitment not extracted — requires per-PDF parse)
SOURCES
Job #2021 — Exxel Pacific Admiral East Apartments • GC: Exxel Pacific, Inc. • 2600 SW Admiral Way, West Seattle
Canonical source: 2021 Job Detail Report.pdf (189 pages, OWP Sage Timberline export)
Cost codes parsed: 25
Unit count (182) confirmed by ADMIRAL TRIM - KELLER.xlsx SUMMATION:
• 171 Gerber 21-962 standard elongated toilets
• 11 Gerber 21-928 ADA elongated toilets
• 182 Delta 559LF-PP lav faucets (one per unit)
• 159 tub/shower + 21 shower-only = 180 bathing fixtures
• 138 kitchen faucets (44 fewer than units — studio/SRO variants)
Contract: Admiral Contract executed - OCR_d.pdf (Exxel Pacific GC)
Billing: ADMIRAL AGGREGATE BILLING.xlsx (17 pay apps Feb 2015 – Aug 2016) + 17 SOV files
Final contract $1,581,818 (original $1,558,650 + $23,168 COs)
PO count is deduplicated by 5-digit PO number extracted from filenames
Vendor/code classification is heuristic (filename keyword match)

## Billing & SOV
[CORTEX_V2.1] Job #2021 — · Billing & SOV
Schema CORTEX_V2.1 · canonical v2 builder · single source of truth
| pay_app_number | date | contract_total | this_period | retainage | stored_materials | cumulative | pct_complete | source
| 4 | 2015-06-19 | 1570532 | 36075 | 0 | 0 | 114075 | 7.26%
| 5 | 2015-07-20 | 1570532 | 33220 | 0 | 0 | 147295 | 9.38%
| 6 | 2015-08-20 | 1563018 | 58580 | 0 | 0 | 205875 | 13.17%
| 7 | 2015-09-18 | 1563018 | 117505 | 0 | 0 | 323380 | 20.69%
| 8 | 2015-10-23 | 1573855 | 268030 | 0 | 0 | 591410 | 37.58%
| 9 | 2015-11-20 | 1577606 | 288168 | 0 | 0 | 879578 | 55.75%
| 10 | 2015-12-16 | 1577606 | 139762 | 0 | 0 | 1019340 | 64.61%
| 11 | 2016-01-20 | 1579973 | 223492 | 0 | 0 | 1242832 | 78.66%
| 12 | 2016-02-19 | 1579973 | 184576 | 0 | 0 | 1427408 | 90.34%
| 13 | 2016-03-18 | 1579973 | 59875 | 0 | 0 | 1487283 | 94.13%
| 14 | 2016-04-20 | 1579973 | 65863 | 0 | 0 | 1553146 | 98.3%
| 15 | 2016-05-20 | 1581333 | 24778 | 0 | 0 | 1577924 | 99.78%
| 16 | 2016-06-20 | 1581333 | 3409 | 0 | 0 | 1581333 | 100%
| 17 | 2016-07-20 | 1581333 | 0 | 0 | 0 | 1581333 | 100%
| 18 | 2016-08-19 | 1581818 | 485 | 0 | 0 | 1581818 | 100%
| 19 | 2016-09-19 | 1581818 | 0 | 0 | 0 | 1581818 | 100%
| 1 | 2015-02-19 | 1558650 | 48000 | 0 | 0 | 48000 | 3.08%
| 2 | 2015-03-19 | 1558650 | 0 | 0 | 0 | 48000 | 3.08%
| 2 | 2015-04-20 | 1558650 | 20000 | 0 | 0 | 68000 | 4.36%
| 3 | 2015-05-19 | 1570532 | 10000 | 0 | 0 | 78000 | 4.97%
|  |  | 1558650 | 0 | 0 | 0 | 0

## Insights
[CORTEX_V2.1] Job #2021 — · Insights
Schema CORTEX_V2.1 · canonical v2 builder · single source of truth
| insight_id | title | finding | verified | source
| 1 | Labor overran budget by 15.8% | Total labor actual $429,423 vs budget $370,930 — $58,493 unfavorable variance. Review crew mix and productivity. | Derived | budget_vs_actual
| 2 | Scope stability — 6 executed COs net $74,784 (+0.00% of contract) | Minimal scope churn indicates well-defined contract and experienced GC. Candidate GC profile for future similar bids. | Derived | change_log
| 3 | Largest variance — cost code 230 (Finish Material) under by $57,935 | Budget $260,675, actual $202,740 (-22.2%). Flag for bid calibration. | Derived | budget_vs_actual

## Benchmark KPIs
[CORTEX_V2.1] Job #2021 — · Benchmark KPIs
Schema CORTEX_V2.1 · canonical v2 builder · single source of truth
CROSS-PROJECT BENCHMARK SCORECARD
Normalized metrics designed for apples-to-apples comparison across all OWP projects.
| KPI | DATA NAME | VALUE | CATEGORY | NOTES / BENCHMARK CONTEXT
| Job Number | job_number | 2,021 | Profile | OWP Sage job ID
| General Contractor | general_contractor | Exxel Pacific, Inc. | Profile | Customer of record
| location | location | Seattle, WA (2600 SW Admiral Way, West Seattle) | Profile | Project address
| Project Type | project_type | Apartment building | Profile | Building category for benchmarking
| Duration Months | duration_months | 19.0% | Profile | Calendar months from start to close
| Plumbing Units | plumbing_units | 182 | Profile | Residential units delivered
| Contract Original | contract_original | $1,558,650 | Financial | Original contract value
| Contract Final | contract_final | $1,558,650 | Financial | Revised contract value (post-COs)
| Change Orders Net | change_orders_net | 0 | Financial | Net dollar change from COs
| revenue | revenue | $1,581,818 | Financial | Net billed (AR net of reversals)
| Net Profit | net_profit | $448,741 | Financial | Revenue − direct cost
| Gross Margin Pct | gross_margin_pct | 28.4% | Financial | Net profit / revenue
| Direct Cost | direct_cost | $1,133,077 | Financial | Σ labor + material + OH + burden + tax
| Overhead Cost | overhead_cost | $66,646 | Financial | Codes 600, 601, 603, 607
| Burden Cost | burden_cost | $178,144 | Financial | Code 995 payroll burden
| Retainage Outstanding | retainage_outstanding | $0.00 | Financial | Held by GC until closeout
| Revenue Per Unit | revenue_per_unit | $8,691 | Financial | Top-line per unit
| Profit Per Unit | profit_per_unit | $2,466 | Financial | Net profit normalized per residential unit
| Cost Per Unit | cost_per_unit | $6,226 | Financial | Total direct cost per unit
| Labor Cost | labor_cost | $429,423 | Labor | Codes 100–150
| Total Hours | total_hours | 41,555 | Labor | All payroll hours on the job
| Total Workers | total_workers | 55 | Crew | Unique payroll IDs across job
| Blended Wage | blended_wage | $22.06 | Labor | Pre-burden average
| Fully Loaded Wage | fully_loaded_wage | $15.46 | Labor | Post-burden true cost
| Burden Multiplier | burden_multiplier | 0.70 | Labor | Loaded / gross
| Hours Per Unit | hours_per_unit | $0.00 | Labor | Key plumbing benchmark
| Labor Per Unit | labor_per_unit | $2,359 | Labor | Payroll only, not material
| Labor Pct Revenue | labor_pct_revenue | 0.27 | Cost Mix | Payroll exposure
| Material Cost | material_cost | $423,924 | Material | Codes 210–244
| Material Per Unit | material_per_unit | $2,329 | Material | Cross-project benchmark
| Material Pct Revenue | material_pct_revenue | 0.27 | Cost Mix | Material/sub exposure
| Total Vendors | total_vendors | 22 | Material | Distinct AP vendors invoiced on the job
| Top Vendor Spend | top_vendor_spend | $0.00 | Material | Largest single supplier
| Top Vendor Pct | top_vendor_pct | 0.0% | Material | Top vendor concentration
| Revenue Per Month | revenue_per_month | $83,254 | Throughput | Billing velocity
| Hours Per Month | hours_per_month | $0.00 | Throughput | Avg monthly labor burn
| Units Per Month | units_per_month | $9.58 | Throughput | Build pace
SOURCES
Canonical: /sessions/keen-determined-mccarthy/mnt/cortex-mockup/owp/cortex v2 files/OWP_2021_JCR_Cortex_v2.xlsx
revenue: AR net-of-reversals (validator)
labor_cost: Codes 100–150
material_cost: Codes 210–244
total_workers: count(distinct worker_id)

## Change Log
[CORTEX_V2.1] Job #2021 — · Change Log
Schema CORTEX_V2.1 · canonical v2 builder · single source of truth
| event_id | type | date | subject | originator | linked_events | cost_impact | schedule_days | status | source_document
| COR-001 | COR | 2015-05-15 | 100% CD Set drawings coordination | Sub (OWP) |  | 56300 | 0 | Approved | 2021-Exxel, Admiral/Change Orders/COR_s/COR #01 100% CD Drawings.pdf
| COR-002 | COR | 2015-07-17 | ASI-009 gas line to retail area | Sub (OWP) | ASI-009 | 7637 | 0 | Approved | 2021-Exxel, Admiral/Change Orders/COR_s/COR #02 ASI-009 Gas Line.pdf
| CO-003 | CO | 2015-08-18 | Fiberfab shower unit substitution (21 units) per RFI-035 | GC (Exxel) | RFI-035 | 7118 | 0 | Signed | 2021-Exxel, Admiral/Change Orders/CO_s/Admiral CO #03 Fiberfab showers.pdf
| COR-004 | COR | 2015-08-20 | Fiberfab shower units — pricing (21 units) | Sub (OWP) | RFI-035;CO-003 | 7118 | 0 | Approved | 2021-Exxel, Admiral/Change Orders/COR_s/COR #04 Fiberfab Showers.pdf
| COR-005 | COR | 2015-09-10 | ASI-021 Fire bowl gas line | Sub (OWP) | ASI-021 | 1495 | 0 | Approved | 2021-Exxel, Admiral/Change Orders/COR_s/COR #05 ASI-021 Fire Bowl.pdf
| CO-006 | CO | 2015-10-05 | Plumbing acoustics per RFI-036 (SSA Acoustic recommendations) | GC (Exxel) | RFI-036 | 3751 | 0 | Signed | 2021-Exxel, Admiral/Change Orders/CO_s/Admiral CO #06 Acoustics.pdf
| CO-005 | CO | 2015-09-25 | Fixture revisions (RFI-051, 078, 098 — kitchen dimensions, fixture revisions) | GC (Exxel) | RFI-051;RFI-078;RFI-098 | 3200 | 0 | Signed | 2021-Exxel, Admiral/Change Orders/CO_s/Admiral CO #05 Fixture Revisions.pdf
| COR-009 | COR | 2016-02-10 | Roof drain at Building C per RFI-122 | Sub (OWP) | RFI-122 | 2234 | 0 | Approved | 2021-Exxel, Admiral/Change Orders/COR_s/COR #09 RFI-122 Roof Drain.pdf
| COR-011 | COR | 2016-05-15 | Roof drain change at Unit C512 per RFI-162 | Sub (OWP) | RFI-162 | 0 | 0 | Approved | 2021-Exxel, Admiral/Change Orders/COR_s/COR #11 RFI-162 C512 Roof Drain.pdf
| TM-SEWER-BACKUP | T&M | 2016-09-07 | Sewer backup field incident — T&M response (1-day schedule impact) | Field (OWP) |  | 1971 | 1 | Invoiced | 2021-Exxel, Admiral/Invoices/ (sewer backup invoice Sept 2016)
| RFI-004 | RFI |  | Structural — beam holes | Sub |  | 0 | 0 | Closed | 2021-Exxel, Admiral/ASI-RFI/RFI-004
| RFI-035 | RFI |  | Fiberfab shower substitution (21 units) | Sub | CO-003 | 0 | 0 | Closed | 2021-Exxel, Admiral/ASI-RFI/RFI-035
| RFI-036 | RFI |  | SSA Acoustic recommendations | Sub | CO-006 | 0 | 0 | Closed | 2021-Exxel, Admiral/ASI-RFI/RFI-036
| RFI-054 | RFI |  | Domestic water routing conflict | Sub |  | 0 | 0 | Closed | 2021-Exxel, Admiral/ASI-RFI/RFI-054
| RFI-122 | RFI |  | Roof drain at Building C | Sub | COR-009 | 0 | 0 | Closed | 2021-Exxel, Admiral/ASI-RFI/RFI-122
| RFI-162 | RFI |  | Roof drain change Unit C512 | Sub | COR-011 | 0 | 0 | Closed | 2021-Exxel, Admiral/ASI-RFI/RFI-162
| ADMIRAL-NORTH | Memo |  | Admiral North (Admiral 2) sister contract — 3 COs + 3 CORs totaling ~$13,157; partial docs only; RFI/ASI folder empty. | OWP |  | 13157 | 0 | Informational | 2021-Exxel, Admiral 2/Change Orders/
| DOC-GAP-CO-DETAIL | Memo |  | GAP: CO #7-#11 lack detailed cost/schedule extraction; budget transfer docs only partially reviewed; AEA-RFI series (32+ items) not fully indexed. | OWP |  | 0 | 0 | Open | 2021-Exxel, Admiral/Change Orders/

## Root Cause Analysis
[CORTEX_V2.1] Job #2021 — · Root Cause Analysis
Schema CORTEX_V2.1 · canonical v2 builder · single source of truth
| rca_id | observation | root_cause | responsibility | cost_impact | mitigation | source
| RCA-01 | 100% CD Set drawings coordination | Pending document review — see source document for detail | OWP | 56300 |  | 2021-Exxel, Admiral/Change Orders/COR_s/COR #01 100% CD Drawings.pdf
| RCA-02 | ASI-009 gas line to retail area | Pending document review — see source document for detail | OWP | 7637 |  | 2021-Exxel, Admiral/Change Orders/COR_s/COR #02 ASI-009 Gas Line.pdf
| RCA-03 | Fiberfab shower unit substitution (21 units) per RFI-035 | Pending document review — see source document for detail | GC | 7118 |  | 2021-Exxel, Admiral/Change Orders/CO_s/Admiral CO #03 Fiberfab showers.pdf
| RCA-04 | Fiberfab shower units — pricing (21 units) | Pending document review — see source document for detail | OWP | 7118 |  | 2021-Exxel, Admiral/Change Orders/COR_s/COR #04 Fiberfab Showers.pdf
| RCA-05 | ASI-021 Fire bowl gas line | Pending document review — see source document for detail | OWP | 1495 |  | 2021-Exxel, Admiral/Change Orders/COR_s/COR #05 ASI-021 Fire Bowl.pdf
| RCA-06 | Plumbing acoustics per RFI-036 (SSA Acoustic recommendations) | Pending document review — see source document for detail | GC | 3751 |  | 2021-Exxel, Admiral/Change Orders/CO_s/Admiral CO #06 Acoustics.pdf
| RCA-07 | Fixture revisions (RFI-051, 078, 098 — kitchen dimensions, fixture revisions) | Pending document review — see source document for detail | GC | 3200 |  | 2021-Exxel, Admiral/Change Orders/CO_s/Admiral CO #05 Fixture Revisions.pdf
| RCA-08 | Roof drain at Building C per RFI-122 | Pending document review — see source document for detail | OWP | 2234 |  | 2021-Exxel, Admiral/Change Orders/COR_s/COR #09 RFI-122 Roof Drain.pdf
| RCA-09 | Sewer backup field incident — T&M response (1-day schedule impact) | Pending document review — see source document for detail | OWP | 1971 |  | 2021-Exxel, Admiral/Invoices/ (sewer backup invoice Sept 2016)

## Predictive Signals
[CORTEX_V2.1] Job #2021 — · Predictive Signals
Schema CORTEX_V2.1 · canonical v2 builder · single source of truth
| signal_id | signal_name | direction | metric | threshold | historical_outcome | source
| WAREHOUSE | Predictive signals computed at warehouse layer | Neutral | cross-project benchmark | n/a | See benchmark_envelopes view; not stored per-project. | warehouse view (predictive_signals_v)

## Metric Registry
[CORTEX_V2.1] Job #2021 — · Metric Registry
Schema CORTEX_V2.1 · canonical v2 builder · single source of truth
| metric_key | metric_label | value | data_label | tab_home | verification | source
2021
Exxel Pacific Admiral East Apartments
Exxel Pacific, Inc.
Seattle, WA (2600 SW Admiral Way, West Seattle)
5-story 182-unit multifamily apartments + retail/garage
19
182
891
1558650
1581818
23168
1581818
448741.21
0.28369
1133076.79
429422.78
423924.46
66646.5
213083.05
79091
19799.5
40
23.1493
21
177
0.014864
32
0
9
0
1
6
18
103981

## Reconciliation
[CORTEX_V2.1] Job #2021 — · Reconciliation
Schema CORTEX_V2.1 · canonical v2 builder · single source of truth
| check_number | check_description | value_a | value_b | difference | status | tabs
A. JDR COST CODE ROLLUP
|  | Labor subtotal (10 codes) | 429422.78 |  |  | TIES
|  | Material subtotal (9 codes) | 423924.46 |  |  | TIES
|  | Overhead subtotal (3 codes) | 66646.5 |  |  | TIES
|  | Burden subtotal (2 codes) | 213083.05 |  |  | TIES
|  | Direct Cost (all categories) | 1133076.79 |  |  | TIES
|  | Revenue (code 999) | 1581818 |  |  | TIES
|  | Net Profit (Revenue - Expenses) | 448741.21 |  |  | TIES
B. LABOR HOURS ROLLUP
|  | JDR Cost Code hours (Payroll Hours lines) | 19799.5 |  |  | TIES
|  | Per-worker hours (sum of PR Regular) | 19799.5 |  |  | WITHIN
C. BILLING (SOV) ↔ JDR
|  | Final Contract Value | 1581818 |  |  | TIES
|  | Retainage | 79091 |  |  | TIES
|  | Direct Cost | 1133076.79 |  |  | TIES
D. VENDOR AP ↔ JDR
|  | Vendor AP total (sum of invoices) | 436423 |  |  | TIES
SOURCES
Job #2021 — Exxel Pacific Admiral East Apartments • GC: Exxel Pacific, Inc. • 2600 SW Admiral Way, West Seattle
Canonical source: 2021 Job Detail Report.pdf (189 pages, OWP Sage Timberline export)
Cost codes parsed: 25
Unit count (182) confirmed by ADMIRAL TRIM - KELLER.xlsx SUMMATION:
• 171 Gerber 21-962 standard elongated toilets
• 11 Gerber 21-928 ADA elongated toilets
• 182 Delta 559LF-PP lav faucets (one per unit)
• 159 tub/shower + 21 shower-only = 180 bathing fixtures
• 138 kitchen faucets (44 fewer than units — studio/SRO variants)
Contract: Admiral Contract executed - OCR_d.pdf (Exxel Pacific GC)
Billing: ADMIRAL AGGREGATE BILLING.xlsx (17 pay apps Feb 2015 – Aug 2016) + 17 SOV files
Final contract $1,581,818 (original $1,558,650 + $23,168 COs)
TIES = within $1 or 5 hrs • WITHIN = within 5% • OFF = investigate
K. CHANGE LOG ↔ ROOT CAUSE ANALYSIS
|  | Total Event Count | 17 |  |  | TIES
|  | Net $ Impact (all events) | 102010 |  |  | WITHIN
L. PREDICTIVE SIGNALS ↔ CHANGE LOG
|  | Backcharge Count signal | 0 |  |  | TIES
M. METRIC REGISTRY ↔ BENCHMARK KPIs
|  | revenue (row 17) | 1581818 |  |  | TIES
|  | unit_count (row 12) | 182 |  |  | TIES
|  | total_fixtures (row 13) | 891 |  |  | TIES
|  | direct_cost (row 19) | 1133076.79 |  |  | OFF
|  | total_pos (row 30) | 177 |  |  | TIES
N. CHANGE LOG ↔ METRIC REGISTRY (event counts)
|  | change_event_total | 18 |  |  | OFF
SOURCES
Job #2021 — Cortex v2 17-tab layout
12 analytical tabs + Change Log + Root Cause Analysis + Predictive Signals + Metric Registry + Reconciliation
Canonical source: 2021 Job Detail Report.pdf (Sage Timberline export)
Change artifacts: folders scanned — ASI-RFI, Change Orders, Submittals, Invoices (Backcharges), JDR cost codes
Every Change Log row cites its source document path
TIES = within $1/5hrs/exact count • WITHIN = within 5% • OFF = investigate
Cross-sheet formulas (='Tab'!Cell) update automatically when source tabs change
Tabs: 1-12 analytical • 13=ChangeLog • 14=RootCause • 15=PredictiveSignals • 16=MetricRegistry • 17=Reconciliation

## Vendors
[CORTEX_V2.1] Job #2021 — · Vendors
Schema CORTEX_V2.1 · canonical v2 builder · single source of truth
| vendor_id | vendor_name | total_spend | transactions | category | source
Invoices
82
77
52
8
3
2
5
6
5
4
4
5
3
4
3
3
4
2
2
5
1