## Overview
[CORTEX_V2.1] Job #2022 — · Overview
Schema CORTEX_V2.1 · canonical v2 builder · single source of truth
| OVERVIEW |  | SOURCE
IDENTITY
| Project Job Number | 2022
| Project Name: | Exxel Pacific 3651 Interlake Apartments
CONTRACT & PARTIES
| General Contractor | Exxel Pacific, Inc.
JOB SITE
| Jobsite Location | Seattle, WA (3651 Interlake Ave N)
| Plumbing Units | 20 | ADA Units
SCHEDULE
| Project Duration | Oct 2014 – Aug 2015 (~11 months)
SCOPE & DESIGN
| Fixtures / Unit | 7.00
| Water Closets | 20 | Kitchen Faucets
| Tub/Shower Valves | 18 + 1 shower | Total Fixtures
| CONTRACT VALUE |  | NET PROFIT |  | DIRECT COST |  | LABOR HOURS
| $232,454 |  | $87,162 |  | $155,475 |  | 3,952
| Original $232,454 |  | 35.9% margin |  | 64.1% of revenue |  | 36 workers
COST BREAKDOWN
| Category | Budget | Actual | Variance | % Budget | % of Cost
| Labor | 52240 | 57917.75 | -5677.75 | 110.9% | 37.25%
| Material | 89109 | 60804.36 | 28304.64 | 68.24% | 39.11%
| Overhead | 12250 | 7289.5 | 4960.5 | 59.51% | 4.689%
| Burden | 27142.52 | 29463.76 | -2321.24 | 108.6% | 18.95%
| TOTAL | 180741.52 | 155475.37 | 25266.15 | 86.02% | 100%
PROJECT PROFILE
| Plumbing Units | 20 |  | Fixtures / Unit | 7.00 |  | Water Closets | 20
| Bathtub/Shower | 18 + 1 shower |  | Duration | Oct 2014 – Aug 2015 (~11 months)

## Budget vs Actual
[CORTEX_V2.1] Job #2022 — · Budget vs Actual
Schema CORTEX_V2.1 · canonical v2 builder · single source of truth
| cost_code | description | original_budget | revised_budget | actual | variance | pct_used | hours | source
LABOR
| 100 | Supervision | 3000 | 3000 | 1042 | 1958 | 34.73%
| 101 | Takeoff & Purchase Labor | 5100 | 5450 | 2957.5 | 2492.5 | 54.27%
| 110 | Underground Labor | 6210 | 6910 | 8667 | -1757 | 1.254%
| 120 | Roughin Labor | 32400 | 32400 | 39476.75 | -7076.75 | 1.218%
| 130 | Finish Labor | 4480 | 4480 | 5302 | -822 | 1.183%
| 141 | Water Main/Insulation Lab | 0 | 0 | 472.5 | -472.5 | 0%
MATERIAL
| 210 | Underground Material | 5550 | 5550 | 3879.67 | 1670.33 | 69.9%
| 213 | Foundation Material | 0 | 0 | 829 | -829 | 0%
| 220 | Roughin Material | 24340 | 24340 | 20929.54 | 3410.46 | 85.99%
| 230 | Finish Material | 52590 | 59219 | 32656.07 | 26562.93 | 55.14%
| 242 | Mech Room Material | 0 | 0 | 2510.08 | -2510.08 | 0%
OVERHEAD
| 600 | Subcontractor | 3400 | 3400 | 950 | 2450 | 27.94%
| 601 | Engineering/Plans | 7000 | 7000 | 4756.5 | 2243.5 | 67.95%
| 603 | Permits & Licenses | 1850 | 1850 | 1583 | 267 | 85.57%
BURDEN
| 995 | Payroll Burden | 22607.03 | 23072.71 | 25033.08 | -1960.37 | 1.085%
| 998 | Payroll Taxes | 3989.48 | 4069.81 | 4430.68 | -360.87 | 1.089%
SOURCES
Job #2022 — Exxel Pacific 3651 Interlake Apartments • GC: Exxel Pacific, Inc. • 3651 Interlake Ave N, Seattle
Canonical source: 2022 Job Detail Report.pdf (33 pages, OWP Sage Timberline export)
Cost codes parsed: 17
Unit count (20) confirmed by 3651 INTERLAKE TRIM - CONSOLIDATED.xlsx SUMMATION:
• 18 TOTO C744E standard elongated toilets + 2 TOTO C744EL ADA elongated = 20 toilets
• 19 TOTO lav sinks + 1 Kohler K-2007 ADA wall-hung = 20 lavs
• 20 GROHE 34.270.001 chrome lav faucets (one per unit)
• 18 GROHE 19.457 tub valve trimsets + 1 shower-only = 19 bathing fixtures
• 16 Lenova LS18304 undercounter kitchens + 2 Elkay ADA = 18 kitchen sinks
Contract: L1 220000 One Way Plumbing Executed.pdf (Exxel Pacific)
Billing: 6+ archived Schedule of Values files (Nov 2014 – Jun 2015)
Final contract $242,637 (original $232,454 + $10,183 COs)
Small project — 20 units, 4 stories, ~11 months
| TOTAL |  | 172516.51 | 180741.52 | 155475.37 | 25266.15 |  | 0

## Cost Breakdown
[CORTEX_V2.1] Job #2022 — · Cost Breakdown
Schema CORTEX_V2.1 · canonical v2 builder · single source of truth
| category | cost_codes | actual | pct_of_direct_cost | pct_of_revenue | per_unit | source
| Labor | 6 | 52240 | 1.109% |  | 2895.8875
| Material | 5 | 89109 | 68.24% |  | 3040.218
| Overhead | 3 | 12250 | 59.51% |  | 364.475
| Burden | 2 | 27142.52 | 1.086% |  | 1473.188
B. LARGEST OVERRUNS (Actual > Revised Budget)
| Code | Description
| 120 | Roughin Labor | 32400 | 21.84%
| 242 | Mech Room Material | 0 | 0%
| 995 | Payroll Burden | 23072.71 | 8.496%
| 110 | Underground Labor | 6910 | 25.43%
| 213 | Foundation Material | 0 | 0%
| 130 | Finish Labor | 4480 | 18.35%
| 141 | Water Main/Insulation Lab | 0 | 0%
| 998 | Payroll Taxes | 4069.81 | 8.867%
C. LARGEST SAVINGS (Actual < Revised Budget)
| Code | Description
| 230 | Finish Material | 59219 | 44.86%
| 220 | Roughin Material | 24340 | 14.01%
| 101 | Takeoff & Purchase Labor | 5450 | 45.73%
| 600 | Subcontractor | 3400 | 72.06%
| 601 | Engineering/Plans | 7000 | 32.05%
| 100 | Supervision | 3000 | 65.27%
| 210 | Underground Material | 5550 | 30.1%
| 603 | Permits & Licenses | 1850 | 14.43%
SOURCES
Job #2022 — Exxel Pacific 3651 Interlake Apartments • GC: Exxel Pacific, Inc. • 3651 Interlake Ave N, Seattle
Canonical source: 2022 Job Detail Report.pdf (33 pages, OWP Sage Timberline export)
Cost codes parsed: 17
Unit count (20) confirmed by 3651 INTERLAKE TRIM - CONSOLIDATED.xlsx SUMMATION:
• 18 TOTO C744E standard elongated toilets + 2 TOTO C744EL ADA elongated = 20 toilets
• 19 TOTO lav sinks + 1 Kohler K-2007 ADA wall-hung = 20 lavs
• 20 GROHE 34.270.001 chrome lav faucets (one per unit)
• 18 GROHE 19.457 tub valve trimsets + 1 shower-only = 19 bathing fixtures
• 16 Lenova LS18304 undercounter kitchens + 2 Elkay ADA = 18 kitchen sinks
Contract: L1 220000 One Way Plumbing Executed.pdf (Exxel Pacific)
Billing: 6+ archived Schedule of Values files (Nov 2014 – Jun 2015)
Final contract $242,637 (original $232,454 + $10,183 COs)
Small project — 20 units, 4 stories, ~11 months
| TOTAL |  | 361483.04 |  |  | 7773.7685

## Material
[CORTEX_V2.1] Job #2022 — · Material
Schema CORTEX_V2.1 · canonical v2 builder · single source of truth
| vendor_id | vendor_name | total_spend | transactions | category | source
| 210 | Underground Material | 5550 |  | 0.063806
| 213 | Foundation Material | 0 |  | 0.013634
| 220 | Roughin Material | 24340 |  | 0.34421
| 230 | Finish Material | 59219 |  | 0.53707
| 242 | Mech Room Material | 0 |  | 0.041281
B. VENDORS BY SPEND (AP)
| Vendor | # Invoices
| Consolidated Supply Co. | 22 | 23840.61
| Rosen Supply Company | 13 | 17213.91
| Ferguson Enterprises, Inc. | 14 | 10598.72
| Franklin Engineering | 2 | 4756.5
| Bank of America CC | 2 | 1583
| Quality Concrete Products, Inc. | 1 | 829
| Keller Supply Company | 1 | 665.76
| Cascade Restoration Co. | 1 | 545
| Rosen Supply Kirkland | 1 | 531.44
| Rosen Supply Company, Inc. | 3 | 435.54
| Patchworks, Inc. | 1 | 405
| Hilti, Inc. | 1 | 143.8
| Capital One Credit Card | 1 | 99.37
SOURCES
Job #2022 — Exxel Pacific 3651 Interlake Apartments • GC: Exxel Pacific, Inc. • 3651 Interlake Ave N, Seattle
Canonical source: 2022 Job Detail Report.pdf (33 pages, OWP Sage Timberline export)
Cost codes parsed: 17
Unit count (20) confirmed by 3651 INTERLAKE TRIM - CONSOLIDATED.xlsx SUMMATION:
• 18 TOTO C744E standard elongated toilets + 2 TOTO C744EL ADA elongated = 20 toilets
• 19 TOTO lav sinks + 1 Kohler K-2007 ADA wall-hung = 20 lavs
• 20 GROHE 34.270.001 chrome lav faucets (one per unit)
• 18 GROHE 19.457 tub valve trimsets + 1 shower-only = 19 bathing fixtures
• 16 Lenova LS18304 undercounter kitchens + 2 Elkay ADA = 18 kitchen sinks
Contract: L1 220000 One Way Plumbing Executed.pdf (Exxel Pacific)
Billing: 6+ archived Schedule of Values files (Nov 2014 – Jun 2015)
Final contract $242,637 (original $232,454 + $10,183 COs)
Small project — 20 units, 4 stories, ~11 months
Vendor AP ties to JDR 'by Source: AP' line (61,647.65)

## Crew & Labor
[CORTEX_V2.1] Job #2022 — · Crew & Labor
Schema CORTEX_V2.1 · canonical v2 builder · single source of truth
| worker_id | worker_name | total_hours | gross_pay | blended_wage_per_hr | tier | work_days | source
| Castaneda Martinez, Gustavo |  | 361.5 | 11568 | 32 | Senior
| Castaneda Juarez, Edgar D |  | 273.5 | 4659 | 17.0347 | Apprentice
| Ascencio, Jose L |  | 255 | 3315 | 13 | Apprentice
| Rodriguez Bonilla, Lisandro |  | 242 | 3220 | 13.3058 | Apprentice
| Castaneda Juarez, Gustavo |  | 139.5 | 2511 | 18 | Mid
| Quintanilla, Esteban R |  | 104 | 3432 | 33 | Senior
| Castro Hernandez, Carlos E |  | 99 | 2871 | 29 | Mid
| Sanders, Allen O |  | 93.5 | 3085.5 | 33 | Senior
| Vaughan, Tyler J |  | 84 | 1428 | 17 | Apprentice
| Reyes Cruz, Denis A |  | 75 | 1050 | 14 | Apprentice
| Gerard, Jeffrey S |  | 69 | 2762 | 40.029 | Senior
| Eliassen, Cory H |  | 46.5 | 604.5 | 13 | Apprentice
| Montenegro, Carlos E |  | 38 | 570 | 15 | Apprentice
| Salazar, Hajdar L |  | 28 | 448 | 16 | Apprentice
| Donelson, Richard T |  | 27.5 | 1237.5 | 45 | Senior
| Castro Hernandez, Jose A |  | 20 | 360 | 18 | Mid
| Reyes, Robert J |  | 8 | 120 | 15 | Apprentice
| Holmes, Anthony R |  | 6 | 96 | 16 | Apprentice
| Kinssies, Jr, John E |  | 5 | 80 | 16 | Apprentice
| Hubbard, Dustin R |  | 1 | 14 | 14 | Apprentice
| TOTAL (20 workers) |  | 1976 | 43431.5 | 21.9795
SOURCES
Job #2022 — Exxel Pacific 3651 Interlake Apartments • GC: Exxel Pacific, Inc. • 3651 Interlake Ave N, Seattle
Canonical source: 2022 Job Detail Report.pdf (33 pages, OWP Sage Timberline export)
Cost codes parsed: 17
Unit count (20) confirmed by 3651 INTERLAKE TRIM - CONSOLIDATED.xlsx SUMMATION:
• 18 TOTO C744E standard elongated toilets + 2 TOTO C744EL ADA elongated = 20 toilets
• 19 TOTO lav sinks + 1 Kohler K-2007 ADA wall-hung = 20 lavs
• 20 GROHE 34.270.001 chrome lav faucets (one per unit)
• 18 GROHE 19.457 tub valve trimsets + 1 shower-only = 19 bathing fixtures
• 16 Lenova LS18304 undercounter kitchens + 2 Elkay ADA = 18 kitchen sinks
Contract: L1 220000 One Way Plumbing Executed.pdf (Exxel Pacific)
Billing: 6+ archived Schedule of Values files (Nov 2014 – Jun 2015)
Final contract $242,637 (original $232,454 + $10,183 COs)
Small project — 20 units, 4 stories, ~11 months
Tier: Apprentice <$18/hr, Mid $18–30, Senior >$30

## Crew Analytics
[CORTEX_V2.1] Job #2022 — · Crew Analytics
Schema CORTEX_V2.1 · canonical v2 builder · single source of truth
| tier | worker_count | hours | gross_pay | pct_of_hours | blended_wage
| Senior | 5 | 655.5 | 22085 | 33.17%
| Mid | 3 | 258.5 | 5742 | 13.08%
| Apprentice | 12 | 1062 | 15604.5 | 53.74%
B. WAGE STATISTICS
| Blended Gross Wage | 21.9795
| Fully-Loaded Wage | 44.2214
| Burden Multiplier | 2.0119
| Min Worker Rate | 13
| Max Worker Rate | 45
| Avg Hours / Worker | 98.8
SOURCES
Job #2022 — Exxel Pacific 3651 Interlake Apartments • GC: Exxel Pacific, Inc. • 3651 Interlake Ave N, Seattle
Canonical source: 2022 Job Detail Report.pdf (33 pages, OWP Sage Timberline export)
Cost codes parsed: 17
Unit count (20) confirmed by 3651 INTERLAKE TRIM - CONSOLIDATED.xlsx SUMMATION:
• 18 TOTO C744E standard elongated toilets + 2 TOTO C744EL ADA elongated = 20 toilets
• 19 TOTO lav sinks + 1 Kohler K-2007 ADA wall-hung = 20 lavs
• 20 GROHE 34.270.001 chrome lav faucets (one per unit)
• 18 GROHE 19.457 tub valve trimsets + 1 shower-only = 19 bathing fixtures
• 16 Lenova LS18304 undercounter kitchens + 2 Elkay ADA = 18 kitchen sinks
Contract: L1 220000 One Way Plumbing Executed.pdf (Exxel Pacific)
Billing: 6+ archived Schedule of Values files (Nov 2014 – Jun 2015)
Final contract $242,637 (original $232,454 + $10,183 COs)
Small project — 20 units, 4 stories, ~11 months

## Productivity
[CORTEX_V2.1] Job #2022 — · Productivity
Schema CORTEX_V2.1 · canonical v2 builder · single source of truth
| phase | labor_code | hours | pct_of_total | hours_per_unit
| Supervision | 100 | 25.5 | 1.039% | 1.275
| Takeoff & Purchasing | 101 | 71 | 2.893% | 3.55
| Underground | 110 | 349 | 14.22% | 17.45
| Roughin | 120 | 1757.5 | 71.62% | 87.875
| Finish | 130 | 233 | 9.495% | 11.65
| Water Main / Insulation | 141 | 18 | 0.7335% | 0.9
B. PRODUCTIVITY RATIOS
| Metric | Value
| Hours / Unit | 122.7
| Hours / Fixture | 17.5286
| Revenue / Hour | 98.8741
| Profit / Hour | 35.5182
| Units / Month | 1.8182
| Fixtures / Month | 12.7273
| Hours / Month | 223.0909
| Revenue / Month | 22057.9091
SOURCES
Job #2022 — Exxel Pacific 3651 Interlake Apartments • GC: Exxel Pacific, Inc. • 3651 Interlake Ave N, Seattle
Canonical source: 2022 Job Detail Report.pdf (33 pages, OWP Sage Timberline export)
Cost codes parsed: 17
Unit count (20) confirmed by 3651 INTERLAKE TRIM - CONSOLIDATED.xlsx SUMMATION:
• 18 TOTO C744E standard elongated toilets + 2 TOTO C744EL ADA elongated = 20 toilets
• 19 TOTO lav sinks + 1 Kohler K-2007 ADA wall-hung = 20 lavs
• 20 GROHE 34.270.001 chrome lav faucets (one per unit)
• 18 GROHE 19.457 tub valve trimsets + 1 shower-only = 19 bathing fixtures
• 16 Lenova LS18304 undercounter kitchens + 2 Elkay ADA = 18 kitchen sinks
Contract: L1 220000 One Way Plumbing Executed.pdf (Exxel Pacific)
Billing: 6+ archived Schedule of Values files (Nov 2014 – Jun 2015)
Final contract $242,637 (original $232,454 + $10,183 COs)
Small project — 20 units, 4 stories, ~11 months

## PO Commitments
[CORTEX_V2.1] Job #2022 — · PO Commitments
Schema CORTEX_V2.1 · canonical v2 builder · single source of truth
| po_number | date | issuer | type | status | description | amount | source
| 30 |  |  |  |  | 110+210 Underground
| 31 |  |  |  |  | 120+220 Roughin
| 32 |  |  |  |  | 130+230 Trim/Finish
| OTHER |  |  |  |  | Unclassified
B. COMMITMENTS BY VENDOR
| Vendor |  |  |  |  | PO Count
| ROSEN |  |  |  |  | 12
| FEI |  |  |  |  | 10
| OTHER |  |  |  |  | 6
| CONSOLIDATED |  |  |  |  | 5
| KELLER |  |  |  |  | 2
| PIKE |  |  |  |  | 1
C. PO COVERAGE NOTES
Total Material Actual (JDR)
Unique PO Count
(Dollar PO commitment not extracted — requires per-PDF parse)
SOURCES
Job #2022 — Exxel Pacific 3651 Interlake Apartments • GC: Exxel Pacific, Inc. • 3651 Interlake Ave N, Seattle
Canonical source: 2022 Job Detail Report.pdf (33 pages, OWP Sage Timberline export)
Cost codes parsed: 17
Unit count (20) confirmed by 3651 INTERLAKE TRIM - CONSOLIDATED.xlsx SUMMATION:
• 18 TOTO C744E standard elongated toilets + 2 TOTO C744EL ADA elongated = 20 toilets
• 19 TOTO lav sinks + 1 Kohler K-2007 ADA wall-hung = 20 lavs
• 20 GROHE 34.270.001 chrome lav faucets (one per unit)
• 18 GROHE 19.457 tub valve trimsets + 1 shower-only = 19 bathing fixtures
• 16 Lenova LS18304 undercounter kitchens + 2 Elkay ADA = 18 kitchen sinks
Contract: L1 220000 One Way Plumbing Executed.pdf (Exxel Pacific)
Billing: 6+ archived Schedule of Values files (Nov 2014 – Jun 2015)
Final contract $242,637 (original $232,454 + $10,183 COs)
Small project — 20 units, 4 stories, ~11 months
PO count is deduplicated by 5-digit PO number extracted from filenames
Vendor/code classification is heuristic (filename keyword match)

## Billing & SOV
[CORTEX_V2.1] Job #2022 — · Billing & SOV
Schema CORTEX_V2.1 · canonical v2 builder · single source of truth
| pay_app_number | date | contract_total | this_period | retainage | stored_materials | cumulative | pct_complete | source

## Insights
[CORTEX_V2.1] Job #2022 — · Insights
Schema CORTEX_V2.1 · canonical v2 builder · single source of truth
| insight_id | title | finding | verified | source
| 1 | Labor overran budget by 13.1% | Total labor actual $57,918 vs budget $51,190 — $6,728 unfavorable variance. Review crew mix and productivity. | Derived | budget_vs_actual
| 2 | Scope stability — 4 executed COs net $10,183 (+0.00% of contract) | Minimal scope churn indicates well-defined contract and experienced GC. Candidate GC profile for future similar bids. | Derived | change_log
| 3 | Largest variance — cost code 230 (Finish Material) under by $26,563 | Budget $59,219, actual $32,656 (-44.9%). Flag for bid calibration. | Derived | budget_vs_actual

## Benchmark KPIs
[CORTEX_V2.1] Job #2022 — · Benchmark KPIs
Schema CORTEX_V2.1 · canonical v2 builder · single source of truth
CROSS-PROJECT BENCHMARK SCORECARD
Normalized metrics designed for apples-to-apples comparison across all OWP projects.
| KPI | DATA NAME | VALUE | CATEGORY | NOTES / BENCHMARK CONTEXT
| Job Number | job_number | 2,022 | Profile | OWP Sage job ID
| General Contractor | general_contractor | Exxel Pacific, Inc. | Profile | Customer of record
| location | location | Seattle, WA (3651 Interlake Ave N) | Profile | Project address
| Project Type | project_type | Apartment building | Profile | Building category for benchmarking
| Duration Months | duration_months | 11.0% | Profile | Calendar months from start to close
| Plumbing Units | plumbing_units | 20 | Profile | Residential units delivered
| Contract Original | contract_original | $232,454 | Financial | Original contract value
| Contract Final | contract_final | $232,454 | Financial | Revised contract value (post-COs)
| Change Orders Net | change_orders_net | 0 | Financial | Net dollar change from COs
| revenue | revenue | $242,637 | Financial | Net billed (AR net of reversals)
| Net Profit | net_profit | $87,162 | Financial | Revenue − direct cost
| Gross Margin Pct | gross_margin_pct | 35.9% | Financial | Net profit / revenue
| Direct Cost | direct_cost | $155,475 | Financial | Σ labor + material + OH + burden + tax
| Overhead Cost | overhead_cost | $7,290 | Financial | Codes 600, 601, 603, 607
| Burden Cost | burden_cost | $25,033 | Financial | Code 995 payroll burden
| Retainage Outstanding | retainage_outstanding | $0.00 | Financial | Held by GC until closeout
| Revenue Per Unit | revenue_per_unit | $12,132 | Financial | Top-line per unit
| Profit Per Unit | profit_per_unit | $4,358 | Financial | Net profit normalized per residential unit
| Cost Per Unit | cost_per_unit | $7,774 | Financial | Total direct cost per unit
| Labor Cost | labor_cost | $57,918 | Labor | Codes 100–150
| Total Hours | total_hours | 3,952 | Labor | All payroll hours on the job
| Total Workers | total_workers | 36 | Crew | Unique payroll IDs across job
| Blended Wage | blended_wage | $21.98 | Labor | Pre-burden average
| Fully Loaded Wage | fully_loaded_wage | $22.11 | Labor | Post-burden true cost
| Burden Multiplier | burden_multiplier | 1.01 | Labor | Loaded / gross
| Hours Per Unit | hours_per_unit | $0.00 | Labor | Key plumbing benchmark
| Labor Per Unit | labor_per_unit | $2,896 | Labor | Payroll only, not material
| Labor Pct Revenue | labor_pct_revenue | 0.24 | Cost Mix | Payroll exposure
| Material Cost | material_cost | $60,804 | Material | Codes 210–244
| Material Per Unit | material_per_unit | $3,040 | Material | Cross-project benchmark
| Material Pct Revenue | material_pct_revenue | 0.25 | Cost Mix | Material/sub exposure
| Total Vendors | total_vendors | 14 | Material | Distinct AP vendors invoiced on the job
| Top Vendor Spend | top_vendor_spend | $0.00 | Material | Largest single supplier
| Top Vendor Pct | top_vendor_pct | 0.0% | Material | Top vendor concentration
| Revenue Per Month | revenue_per_month | $22,058 | Throughput | Billing velocity
| Hours Per Month | hours_per_month | $0.00 | Throughput | Avg monthly labor burn
| Units Per Month | units_per_month | $1.82 | Throughput | Build pace
SOURCES
Canonical: /sessions/keen-determined-mccarthy/mnt/cortex-mockup/owp/cortex v2 files/OWP_2022_JCR_Cortex_v2.xlsx
revenue: AR net-of-reversals (validator)
labor_cost: Codes 100–150
material_cost: Codes 210–244
total_workers: count(distinct worker_id)

## Change Log
[CORTEX_V2.1] Job #2022 — · Change Log
Schema CORTEX_V2.1 · canonical v2 builder · single source of truth
| event_id | type | date | subject | originator | linked_events | cost_impact | schedule_days | status | source_document
| COR-001 | COR | 2014-10-27 | Best Bath shower stalls in lieu of FiberFab per RFI-011 (Type A/B units) | Sub (OWP) | RFI-011 | 5667 | 0 | Authorized | 2022-Exxel, 3651 Interlake/Change Orders/COR_s/3651 Interlake - OWP COR #01.pdf
| COR-002 | COR | 2015-01-06 | 2" PEX domestic water main (meter to water room) | Sub (OWP) |  | 546 | 0 | Authorized | 2022-Exxel, 3651 Interlake/Change Orders/COR_s/3651 Interlake - OWP COR #02.pdf
| COR-003 | COR | 2015-02-03 | Fixture package change to match 36 Stone project per RFI-053 | Sub (OWP) | RFI-053 | 2976 | 0 | Authorized | 2022-Exxel, 3651 Interlake/Change Orders/COR_s/3651 Interlake - OWP COR #03 RFI-053 Fixture Change.pdf
| COR-004 | COR | 2015-02-03 | Add 2 area drains at Level B1 walkway per RFI-057 | Sub (OWP) | RFI-057 | 994 | 2 | Authorized | 2022-Exxel, 3651 Interlake/Change Orders/COR_s/3651 Interlake - OWP COR #04 RFI-057 Area Drains.pdf
| CO-001 | CO | 2014-10-31 | Best Bath shower installation (ties to COR-001); contract $232,454 → $238,121 | GC (Exxel) | COR-001 | 5667 | 0 | Signed | 2022-Exxel, 3651 Interlake/Change Orders/CO_s/interlake change order#1.pdf
| CO-002 | CO | 2015-01-21 | 2" PEX water main install (ties to COR-002); $238,121 → $238,667 | GC (Exxel) | COR-002 | 546 | 0 | Signed | 2022-Exxel, 3651 Interlake/Change Orders/CO_s/3651 Interlake - One Way Change order 2 signed.pdf
| CO-003 | CO | 2015-03-17 | CO-003 combined — RFI-053 fixture package ($2,976) + RFI-057 area drains ($994); $238,667 → $242,637 | GC (Exxel) | COR-003;COR-004 | 3970 | 0 | Signed | 2022-Exxel, 3651 Interlake/Change Orders/CO_s/3651 Interlake change order 3.pdf
| RFI-013 | RFI | 2014-10-21 | Shutoff and panel locations | Sub |  | 0 | 0 | Closed | 2022-Exxel, 3651 Interlake/ASI-RFI/RFI-013
| RFI-016 | RFI | 2014-10-28 | Stair A steel-to-wood connections at 1st floor | Sub |  | 0 | 0 | Closed | 2022-Exxel, 3651 Interlake/ASI-RFI/RFI-016
| RFI-019 | RFI | 2014-10-30 | Interlake Ave sewer main elevation (CPL response) | Sub |  | 0 | 0 | Closed | 2022-Exxel, 3651 Interlake/ASI-RFI/RFI-019
| RFI-030 | RFI | 2014-12-11 | Perimeter footing drainage | Sub |  | 0 | 0 | Closed | 2022-Exxel, 3651 Interlake/ASI-RFI/RFI-030
| RFI-053 | RFI | 2015-01-26 | Plumbing fixture package | Sub | COR-003 | 0 | 0 | Closed | 2022-Exxel, 3651 Interlake/ASI-RFI/RFI-053
| RFI-057 | RFI | 2015-01-30 | Level B1 walkway drainage | Sub | COR-004 | 0 | 0 | Closed | 2022-Exxel, 3651 Interlake/ASI-RFI/RFI-057
| RFI-062 | RFI | 2015-02-17 | Plumbing pipe in shear wall | Sub |  | 0 | 0 | Closed | 2022-Exxel, 3651 Interlake/ASI-RFI/RFI-062
| RFI-064 | RFI | 2015-02-26 | Double TGIs below plumbing walls | Sub |  | 0 | 0 | Closed | 2022-Exxel, 3651 Interlake/ASI-RFI/RFI-064
| RFI-071 | RFI | 2015-03-10 | Unit water closet dimensions | Sub |  | 0 | 0 | Closed | 2022-Exxel, 3651 Interlake/ASI-RFI/RFI-071
| RFI-089 | RFI | 2015-04-15 | Add vent boxes in washer/dryer closets | Sub |  | 0 | 0 | Closed | 2022-Exxel, 3651 Interlake/ASI-RFI/RFI-089
| RFI-109 | RFI | 2015-05-28 | Level 1 exterior corridor piping soffit | Sub |  | 0 | 0 | Closed | 2022-Exxel, 3651 Interlake/ASI-RFI/RFI-109
| ASI-001 | ASI |  | Roof access and corridor revisions | Architect |  | 0 | 0 | Closed | 2022-Exxel, 3651 Interlake/ASI-RFI/ASI-001
| SUB-22-01A-R | Submittal-resub | 2014-12-05 | 220000-01A Plumbing Underground — Make Corrections Noted (resubmit) | Sub (OWP) |  | 0 | 0 | Approved | 2022-Exxel, 3651 Interlake/Submittals/RESPONSES/3651 Interlake Submittal 220000-01 Plumbing Underground (Make Corrections Noted).pdf
| SUB-22-04-R | Submittal-resub |  | 220000-04 Plumbing Fixtures — Revise & Resubmit (2 iterations driven by RFI-011 + RFI-053) | Sub (OWP) | RFI-011;RFI-053 | 0 | 0 | Approved | 2022-Exxel, 3651 Interlake/Submittals/RESPONSES/

## Root Cause Analysis
[CORTEX_V2.1] Job #2022 — · Root Cause Analysis
Schema CORTEX_V2.1 · canonical v2 builder · single source of truth
| rca_id | observation | root_cause | responsibility | cost_impact | mitigation | source
| RCA-01 | Best Bath shower stalls in lieu of FiberFab per RFI-011 (Type A/B units) | Pending document review — see source document for detail | OWP | 5667 |  | 2022-Exxel, 3651 Interlake/Change Orders/COR_s/3651 Interlake - OWP COR #01.pdf
| RCA-02 | 2" PEX domestic water main (meter to water room) | Pending document review — see source document for detail | OWP | 546 |  | 2022-Exxel, 3651 Interlake/Change Orders/COR_s/3651 Interlake - OWP COR #02.pdf
| RCA-03 | Fixture package change to match 36 Stone project per RFI-053 | Pending document review — see source document for detail | OWP | 2976 |  | 2022-Exxel, 3651 Interlake/Change Orders/COR_s/3651 Interlake - OWP COR #03 RFI-053 Fixture Change.pdf
| RCA-04 | Add 2 area drains at Level B1 walkway per RFI-057 | Pending document review — see source document for detail | OWP | 994 |  | 2022-Exxel, 3651 Interlake/Change Orders/COR_s/3651 Interlake - OWP COR #04 RFI-057 Area Drains.pdf
| RCA-05 | Best Bath shower installation (ties to COR-001); contract $232,454 → $238,121 | Pending document review — see source document for detail | GC | 5667 |  | 2022-Exxel, 3651 Interlake/Change Orders/CO_s/interlake change order#1.pdf
| RCA-06 | 2" PEX water main install (ties to COR-002); $238,121 → $238,667 | Pending document review — see source document for detail | GC | 546 |  | 2022-Exxel, 3651 Interlake/Change Orders/CO_s/3651 Interlake - One Way Change order 2 signed.pdf
| RCA-07 | CO-003 combined — RFI-053 fixture package ($2,976) + RFI-057 area drains ($994); $238,667 → $242,637 | Pending document review — see source document for detail | GC | 3970 |  | 2022-Exxel, 3651 Interlake/Change Orders/CO_s/3651 Interlake change order 3.pdf

## Predictive Signals
[CORTEX_V2.1] Job #2022 — · Predictive Signals
Schema CORTEX_V2.1 · canonical v2 builder · single source of truth
| signal_id | signal_name | direction | metric | threshold | historical_outcome | source
| WAREHOUSE | Predictive signals computed at warehouse layer | Neutral | cross-project benchmark | n/a | See benchmark_envelopes view; not stored per-project. | warehouse view (predictive_signals_v)

## Metric Registry
[CORTEX_V2.1] Job #2022 — · Metric Registry
Schema CORTEX_V2.1 · canonical v2 builder · single source of truth
| metric_key | metric_label | value | data_label | tab_home | verification | source
2022
Exxel Pacific 3651 Interlake Apartments
Exxel Pacific, Inc.
Seattle, WA (3651 Interlake Ave N)
4-story 20-unit small multifamily (18 standard + 2 ADA)
11
20
140
232454
242637
10183
242637
87161.63
0.35923
155475.37
57917.75
60804.36
7289.5
29463.76
12132
2454
20
17.6982
13
36
0.043807
14
1
7
0
0
2
21
20366

## Reconciliation
[CORTEX_V2.1] Job #2022 — · Reconciliation
Schema CORTEX_V2.1 · canonical v2 builder · single source of truth
| check_number | check_description | value_a | value_b | difference | status | tabs
A. JDR COST CODE ROLLUP
|  | Labor subtotal (6 codes) | 57917.75 |  |  | TIES
|  | Material subtotal (5 codes) | 60804.36 |  |  | TIES
|  | Overhead subtotal (3 codes) | 7289.5 |  |  | TIES
|  | Burden subtotal (2 codes) | 29463.76 |  |  | TIES
|  | Direct Cost (all categories) | 155475.37 |  |  | TIES
|  | Revenue (code 999) | 242637 |  |  | TIES
|  | Net Profit (Revenue - Expenses) | 87161.63 |  |  | TIES
B. LABOR HOURS ROLLUP
|  | JDR Cost Code hours (Payroll Hours lines) | 2454 |  |  | TIES
|  | Per-worker hours (sum of PR Regular) | 2454 |  |  | OFF
C. BILLING (SOV) ↔ JDR
|  | Final Contract Value | 242637 |  |  | TIES
|  | Retainage | 12132 |  |  | TIES
|  | Direct Cost | 155475.37 |  |  | TIES
D. VENDOR AP ↔ JDR
|  | Vendor AP total (sum of invoices) | 61648 |  |  | TIES
SOURCES
Job #2022 — Exxel Pacific 3651 Interlake Apartments • GC: Exxel Pacific, Inc. • 3651 Interlake Ave N, Seattle
Canonical source: 2022 Job Detail Report.pdf (33 pages, OWP Sage Timberline export)
Cost codes parsed: 17
Unit count (20) confirmed by 3651 INTERLAKE TRIM - CONSOLIDATED.xlsx SUMMATION:
• 18 TOTO C744E standard elongated toilets + 2 TOTO C744EL ADA elongated = 20 toilets
• 19 TOTO lav sinks + 1 Kohler K-2007 ADA wall-hung = 20 lavs
• 20 GROHE 34.270.001 chrome lav faucets (one per unit)
• 18 GROHE 19.457 tub valve trimsets + 1 shower-only = 19 bathing fixtures
• 16 Lenova LS18304 undercounter kitchens + 2 Elkay ADA = 18 kitchen sinks
Contract: L1 220000 One Way Plumbing Executed.pdf (Exxel Pacific)
Billing: 6+ archived Schedule of Values files (Nov 2014 – Jun 2015)
Final contract $242,637 (original $232,454 + $10,183 COs)
Small project — 20 units, 4 stories, ~11 months
TIES = within $1 or 5 hrs • WITHIN = within 5% • OFF = investigate
K. CHANGE LOG ↔ ROOT CAUSE ANALYSIS
|  | Total Event Count | 21 |  |  | TIES
|  | Net $ Impact (all events) | 20366 |  |  | TIES
L. PREDICTIVE SIGNALS ↔ CHANGE LOG
|  | Backcharge Count signal | 0 |  |  | TIES
M. METRIC REGISTRY ↔ BENCHMARK KPIs
|  | revenue (row 17) | 242637 |  |  | TIES
|  | unit_count (row 12) | 20 |  |  | TIES
|  | total_fixtures (row 13) | 140 |  |  | TIES
|  | direct_cost (row 19) | 155475.37 |  |  | OFF
|  | total_pos (row 30) | 36 |  |  | TIES
N. CHANGE LOG ↔ METRIC REGISTRY (event counts)
|  | change_event_total | 21 |  |  | OFF
SOURCES
Job #2022 — Cortex v2 17-tab layout
12 analytical tabs + Change Log + Root Cause Analysis + Predictive Signals + Metric Registry + Reconciliation
Canonical source: 2022 Job Detail Report.pdf (Sage Timberline export)
Change artifacts: folders scanned — ASI-RFI, Change Orders, Submittals, Invoices (Backcharges), JDR cost codes
Every Change Log row cites its source document path
TIES = within $1/5hrs/exact count • WITHIN = within 5% • OFF = investigate
Cross-sheet formulas (='Tab'!Cell) update automatically when source tabs change
Tabs: 1-12 analytical • 13=ChangeLog • 14=RootCause • 15=PredictiveSignals • 16=MetricRegistry • 17=Reconciliation

## Vendors
[CORTEX_V2.1] Job #2022 — · Vendors
Schema CORTEX_V2.1 · canonical v2 builder · single source of truth
| vendor_id | vendor_name | total_spend | transactions | category | source
Invoices
22
13
14
2
2
1
1
1
1
3
1
1
1