## Overview
[CORTEX_V2.1] Job #2023 — Chinn, Legacy Apts · Overview
Schema CORTEX_V2.1 · canonical v2 builder · single source of truth
| OVERVIEW |  | SOURCE
IDENTITY
| Project Job Number | 2023 | 2023 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages) header
| Project Name Sage | Chinn, Legacy Apts | 2023 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages) header
| Project Description | Legacy @ Mercer Island Apartments (Hadley) — full plumbing, 241 units | Legacy contract OCR_d.pdf (Chinn↔OWP subcontract, Lump Sum $2,469,500) / AR line descriptions
| Customer Code Sage | 2023CC | 2023 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
CONTRACT & PARTIES
| General Contractor | Chinn Construction, LLC | Legacy contract OCR_d.pdf (Chinn↔OWP subcontract, Lump Sum $2,469,500)
| Owner / Developer | Hadley Improvements Owner, LLC | Legacy contract OCR_d.pdf (Chinn↔OWP subcontract, Lump Sum $2,469,500)
| Architect | VIA Architecture | ASI-RFI responses (e.g. 'VIA Response' RFI 168)
| Contract Type | Lump Sum | Legacy contract OCR_d.pdf (Chinn↔OWP subcontract, Lump Sum $2,469,500)
| Contract Document | Legacy contract OCR_d.pdf (Chinn↔OWP subcontract, Lump Sum $2,469,500) | Fully executed subcontract (Lump Sum)
JOB SITE
| Jobsite Location | 2601 76th Ave SE, Mercer Island, WA 98040 | Legacy contract OCR_d.pdf (Chinn↔OWP subcontract, Lump Sum $2,469,500)
SCHEDULE
| Work Period | 01/19/2015 (first invoice) – 12/15/2016 (last invoice) ≈ 23 months | 2023 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
SCOPE & DESIGN
| Plans / Specifications | Plans/ folder — full drawing set + VIA Architecture specs + Div 22 plumbing spec | Folder scan
| Bid Sheet | Chinn Legacy Mercer Island Sept 9 2014.xlsx (original 9/9/2014 bid with full fixture schedule) | Bid Sheets folder
DOCUMENTATION
| Total Unique Documents Reviewed | 1000+ across 4 mirror folders | File inventory across owp-2023/
| CONTRACT VALUE |  | NET PROFIT |  | DIRECT COST |  | LABOR HOURS
| $2,771,369 |  | $904,898 |  | $1,866,471 |  | 33,163
| Original $-51,150 |  | 32.6% margin |  | 67.3% of revenue |  | 52 workers
COST BREAKDOWN
| Category | Budget | Actual | Variance | % Budget | % of Cost
| Labor | 609147 | 702744.35 | -93597.35 | 115.4% | 37.65%
| Material | 982300 | 725504.82 | 256795.18 | 73.86% | 38.87%
| Overhead | 100613 | 71568.78 | 29044.22 | 71.13% | 3.834%
| Burden | 312198.43 | 366652.7 | -54454.27 | 117.4% | 19.64%
| TOTAL | 2004258.43 | 1866470.65 | 137787.78 | 93.13% | 100%
PROJECT PROFILE
| Duration | 01/19/2015 (first invoice) – 12/15/2016 (last invoice) ≈ 23 months

## Budget vs Actual
[CORTEX_V2.1] Job #2023 — Chinn, Legacy Apts · Budget vs Actual
Schema CORTEX_V2.1 · canonical v2 builder · single source of truth
| cost_code | description | original_budget | revised_budget | actual | variance | pct_used | hours | source
| 100 | Supervision | 14630 | 15828 | 13424.5 | -2403.5 | 84.81% | 308.5 | 2023 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
| 101 | Takeoff & Purchase Labor | 14630 | 19827 | 29564 | 9737 | 1.491% | 683.5 | 2023 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
| 110 | Underground Labor | 18865 | 27189 | 25629.12 | -1559.88 | 94.26% | 1086.5 | 2023 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
| 111 | Garage Labor | 121140 | 123844 | 84983.82 | -38860.18 | 68.62% | 4461 | 2023 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
| 112 | Canout Labor | 15000 | 15000 | 16227.22 | 1227.22 | 1.082% | 825 | 2023 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
| 120 | Roughin Labor | 230840 | 304097 | 373123.5 | 69026.5 | 1.227% | 17765 | 2023 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
| 130 | Finish Labor | 46160 | 48864 | 62630.5 | 13766.5 | 1.282% | 2906.5 | 2023 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
| 140 | Gas Labor | 7975 | 11915 | 21481 | 9566 | 1.803% | 971 | 2023 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
| 141 | Water Main/Insulation Lab | 29430 | 35287 | 54198.43 | 18911.43 | 1.536% | 3214.5 | 2023 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
| 142 | Mech Room Labor | 7200 | 7200 | 21196.26 | 13996.26 | 2.944% | 875.5 | 2023 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
| 143 | Condensation Drains Labor | 0 | 0 | 175 | 175 |  | 7 | 2023 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
| 150 | Warranty Labor | 0 | 96 | 111 | 15 | 1.156% | 3 | 2023 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
| 210 | Underground Material | 23150 | 38304 | 45918.24 | 7614.24 | 1.199% |  | 2023 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
| 211 | Garage Material | 101825 | 102635 | 33922.59 | -68712.41 | 33.05% |  | 2023 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
| 212 | Canout Material | 17500 | 17660 | 11617.32 | -6042.68 | 65.78% |  | 2023 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
| 220 | Roughin Material | 156630 | 224127 | 158305.23 | -65821.77 | 70.63% |  | 2023 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
| 230 | Finish Material | 496970 | 491330 | 287126.83 | -204203.17 | 58.44% |  | 2023 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
| 240 | Gas Material | 5500 | 8897 | 4873.37 | -4023.63 | 54.78% |  | 2023 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
| 241 | Water Main/Insulation Mat | 76300 | 76847 | 77345.28 | 498.28 | 1.006% |  | 2023 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
| 242 | Mech Room Material | 22500 | 22500 | 105558.69 | 83058.69 | 4.691% |  | 2023 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
| 243 | Condensation Drains Mat | 0 | 0 | 182.88 | 182.88 |  |  | 2023 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
| 244 | Fire Caulking Material | 0 | 0 | 654.39 | 654.39 |  |  | 2023 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
| 600 | Subcontractor | 500 | 11843 | 14130.5 | 2287.5 | 1.193% |  | 2023 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
| 601 | Engineering/Plans | 50000 | 50770 | 28143.85 | -22626.15 | 55.43% |  | 2023 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
| 602 | Rental Equipment | 5000 | 5919 | 6870.79 | 951.79 | 1.161% |  | 2023 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
| 603 | Permits & Licenses | 28000 | 28000 | 29245.43 | 1245.43 | 1.044% |  | 2023 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
| 607 | Other Expenses | 10000 | 10000 | 49 | -9951 | 0.49% |  | 2023 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
| 995 | Payroll Burden | 219294.65 | 266088.03 | 312024.89 | 45936.86 | 1.173% |  | 2023 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
| 998 | Payroll Taxes | 38699.06 | 46110.4 | 54627.81 | 8517.41 | 1.185% |  | 2023 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
| 999 | Sales | -2469500 | -2771369 | -2771369 | 0 | 100% |  | 2023 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
| TOTAL |  | -711761.29 | -761191.57 | -898027.56 | -136835.99 |  | 33107

## Cost Breakdown
[CORTEX_V2.1] Job #2023 — Chinn, Legacy Apts · Cost Breakdown
Schema CORTEX_V2.1 · canonical v2 builder · single source of truth
| category | cost_codes | actual | pct_of_direct_cost | pct_of_revenue | per_unit | source
| Labor | 100,101,110,111,112,120,130,140,141,142,143,150 | 702744.35 | 37.51% | 25.36% |  | 2023 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
| Material | 210,211,212,220,230,240,241,242,243,244 | 725504.82 | 38.73% | 26.18% |  | 2023 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
| Subcontractor + Engineering + Rental + Permits + Other | 600,601,602,603,607 | 78439.57 | 4.187% | 2.83% |  | 2023 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
| Payroll Burden | 995 | 312024.89 | 16.66% | 11.26% |  | 2023 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
| Payroll Taxes | 998 | 54627.81 | 2.916% | 1.971% |  | 2023 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
| TOTAL DIRECT COST |  | 1873341.44 | 100% | 67.6%
| TOTAL |  | 3746682.88 |  |  | 0

## Material
[CORTEX_V2.1] Job #2023 — Chinn, Legacy Apts · Material
Schema CORTEX_V2.1 · canonical v2 builder · single source of truth
| vendor_id | vendor_name | total_spend | transactions | category | source
| 2023RS | Rosen Supply Company, Inc. | 190637.35 | 116 | Plumbing / Supplies | 2023 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
| 2023CS | Consolidated Supply Co. | 164734.54 | 73 | Plumbing / Supplies | 2023 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
| 2023FE | Ferguson Enterprises, Inc. | 161354.82 | 71 | Plumbing / Supplies | 2023 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
| 2023KS | Keller Supply Company | 66440.23 | 39 | Plumbing / Supplies | 2023 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
| 3612MS | Mechanical Sales, Inc. | 28019.56 | 4 | Plumbing / Supplies | 2023 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
| 1625FE | Franklin Engineering | 27834 | 6 | Engineering (601) | 2023 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
| 3181SC | Scan2Core, Inc. | 9291 | 7 | Concrete coring / subcon | 2023 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
| 1231KS | Keller Supply Company | 6943.87 | 3 | Plumbing / Supplies | 2023 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
| 7200UR | United Rentals, Inc. | 6785.95 | 11 | Rental Equipment (602) | 2023 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
| 1609QC | Quality Concrete Products, Inc. $32 | 6488 | 4 | Concrete / subcon | 2023 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
| 1516DS | Duraseal, Inc. | 3860 | 1 | Uncategorized | 2023 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
| 5621HD | Core & Main LP | 2464.39 | 2 | Plumbing / Supplies | 2023 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
| 1380RS | Rosen Supply Kirkland | 1670.93 | 9 | Plumbing / Supplies | 2023 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
| 2132MH | Manor Hardware & Construction Supply | 908.02 | 3 | Plumbing / Supplies | 2023 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
| 1504CA | Chip Away Bathtub Repair, Inc. | 750 | 1 | Uncategorized | 2023 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
| 8068MI | Kele, Inc $ MI Controls | 694.25 | 1 | Uncategorized | 2023 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
| 1303CM | C.M. Hoskins Company | 564.48 | 3 | Uncategorized | 2023 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
| 2024FE | Ferguson Enterprises, Inc. $MG-Ballard | 533.19 | 1 | Plumbing / Supplies | 2023 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
| 1175FE | Ferguson Enterprises, Inc. #3007 | 436.87 | 1 | Plumbing / Supplies | 2023 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
| 1611AS | Beacon Building Products | 361.89 | 2 | Uncategorized | 2023 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
| 1288DR | DRSi | 309.85 | 2 | Uncategorized | 2023 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
| 1234CO | Capital One Credit Card | 293.86 | 2 | Credit Card (mixed) | 2023 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
| 3820HI | Hilti, Inc. | 292.5 | 1 | Uncategorized | 2023 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
| 2021RS | Rosen Supply Company | 290.47 | 2 | Plumbing / Supplies | 2023 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
| 1421RA | R.A. Brown Backflow Testing | 229.5 | 1 | Testing subcontractor | 2023 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
| 1799AW | AllWest Underground, Inc. | 84.84 | 1 | Uncategorized | 2023 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
| 1126SS | Specification Sales, Inc. | 71.04 | 2 | Uncategorized | 2023 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
| 1234BA | Bank of America CC | 66.74 | 1 | Credit Card (mixed) | 2023 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
| 1344HD | HD Fowler Company | 61.12 | 1 | Uncategorized | 2023 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
| 2019RS | Rosen Supply Company, Inc. $8th, Republi | 49.61 | 2 | Plumbing / Supplies | 2023 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
| 2027FE | Ferguson Enterprises, Inc. $550 Broadway | 45.53 | 1 | Plumbing / Supplies | 2023 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
| 1130CS | Consolidated Supply Co. | -283.84 | 2 | Plumbing / Supplies | 2023 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
NOTE: AP total per JDR footer = $682,284.56. Top vendors: Rosen Supply, Consolidated Supply, Ferguson, Keller Supply, Mechanical Sales, Franklin Engineering. Submittals folder contains 100+ submittals documenting approved products. POs folder shows 180+ POs (152 completed, 2 placed, 26 scheduled) + 38 Trim POs.

## Crew & Labor
[CORTEX_V2.1] Job #2023 — Chinn, Legacy Apts · Crew & Labor
Schema CORTEX_V2.1 · canonical v2 builder · single source of truth
| worker_id | worker_name | total_hours | gross_pay | blended_wage_per_hr | tier | work_days | source
| WI46 | Wilson, Garret A | 1778.5 | 39599 | 22.2654 |  | 54 | 2023 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
| RI84 | Rivera, Eli P | 1659 | 29349.5 | 17.6911 |  | 47 | 2023 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
| GA70 | Garcia, Jordan X | 1594 | 35278.5 | 22.1321 |  | 45 | 2023 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
| BA70 | Barnhart, Joseph N | 1567 | 56102.5 | 35.8025 |  | 68 | 2023 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
| BA45 | Balderas Ortiz, Ricardo I | 1490.5 | 28807 | 19.3271 |  | 43 | 2023 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
| GA72 | Gardner, Andrew M | 1461.5 | 20909 | 14.3065 |  | 49 | 2023 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
| BR59 | Brown, Steven D | 1400.5 | 19720 | 14.0807 |  | 42 | 2023 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
| KI55 | Kinssies, Jr, John E | 1279.5 | 21995.5 | 17.1907 |  | 41 | 2023 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
| ME53 | Mendoza Morales, Jesus A | 1271 | 18612 | 14.6436 |  | 35 | 2023 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
| ES62 | Esparza Jimenez, Jose D | 1231.5 | 30124.5 | 24.4616 |  | 37 | 2023 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
| WE55 | Wennig, Johnathan M | 1153.5 | 19680 | 17.0611 |  | 38 | 2023 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
| SA45 | Salazar, Hajdar L | 1114.5 | 19328 | 17.3423 |  | 35 | 2023 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
| RO75 | Ross, Kelli M | 1075.5 | 34736.5 | 32.298 |  | 31 | 2023 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
| MA71 | Martinez Reyes, Juan C | 1008 | 14054 | 13.9425 |  | 29 | 2023 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
| AY19 | Ayers, Jordan L | 745.5 | 12673.5 | 17 |  | 22 | 2023 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
| WA35 | Waites, Thaddeus Z | 698.5 | 25116.5 | 35.9578 |  | 23 | 2023 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
| RE18 | Reed, Reuben H | 682.5 | 21661 | 31.7377 |  | 20 | 2023 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
| EL33 | Eliassen, Cory H | 636.5 | 9517.5 | 14.9529 |  | 24 | 2023 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
| PE70 | Perez Ortiz, Jesus I | 632.5 | 9288.5 | 14.6854 |  | 19 | 2023 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
| AN98 | Anzora, William | 616 | 10016 | 16.2597 |  | 19 | 2023 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
| MC09 | McCabe, Thomas C | 588 | 14658 | 24.9286 |  | 21 | 2023 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
| BA68 | Barbosa, Michael S | 583 | 8367 | 14.3516 |  | 17 | 2023 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
| VE42 | Velasquez Cruz, Denis M | 561.5 | 10219 | 18.1995 |  | 17 | 2023 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
| CO73 | Cortes Sepulveda, Jose R | 545 | 7353 | 13.4917 |  | 16 | 2023 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
| SE64 | Sepulveda Gonzalez, Alfredo | 544 | 15504 | 28.5 |  | 16 | 2023 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
| TA96 | Taylor, Evan R | 542.5 | 8704 | 16.0442 |  | 20 | 2023 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
| GE69 | Gerard, Jeffrey S | 533 | 22171.5 | 41.5976 |  | 83 | 2023 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
| NE91 | Newton, Carson T | 481.5 | 6786 | 14.0935 |  | 15 | 2023 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
| UL81 | Ulu, Flynn M | 473 | 12000 | 25.37 |  | 15 | 2023 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
| DO56 | Donelson, Richard T | 470 | 21370 | 45.4681 |  | 94 | 2023 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
| ME98 | Meza Fuentes, Erick A | 430 | 10520 | 24.4651 |  | 14 | 2023 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
| QU35 | Quintanilla, Esteban R | 409 | 13765 | 33.6553 |  | 21 | 2023 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
| MO56 | Montenegro, Carlos E | 406 | 6640 | 16.3547 |  | 19 | 2023 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
| RO12 | Rodriguez Rodriguez, Aminadab N | 385.5 | 5990.5 | 15.5396 |  | 12 | 2023 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
| RI87 | Rivera, Jorge A | 370 | 7946 | 21.4757 |  | 17 | 2023 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
| SA54 | Sanders, Allen O | 346 | 12802 | 37 |  | 22 | 2023 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
| PA46 | Palma Vides, Hugo | 328.5 | 11412.5 | 34.7412 |  | 10 | 2023 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
| MA79 | Matthias, Joseph S | 272 | 3536 | 13 |  | 9 | 2023 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
| MO54 | Monico Brambila, Jesus S | 246 | 4476 | 18.1951 |  | 8 | 2023 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
| GE71 | Gerard, Mitchell J | 236 | 4626 | 19.6017 |  | 12 | 2023 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
| PA47 | Palma Vides, Jorge A | 230.5 | 3918.5 | 17 |  | 8 | 2023 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
| HU06 | Hubbard, Robert W | 177 | 6683.5 | 37.7599 |  | 26 | 2023 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
| LO87 | Lovo, German G | 176 | 2688 | 15.2727 |  | 7 | 2023 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
| HO14 | Holmes, Anthony R | 165 | 3255 | 19.7273 |  | 7 | 2023 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
| SO78 | Soto Cruz, Jovani | 131.5 | 2498.5 | 19 |  | 4 | 2023 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
| HU04 | Hubbard, Dustin R | 97 | 1558 | 16.0619 |  | 32 | 2023 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
| VA86 | Vaughan, Tyler J | 85.5 | 1795.5 | 21 |  | 3 | 2023 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
| AL05 | Alba Martinez, Santiago | 61 | 1098 | 18 |  | 3 | 2023 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
| VE45 | Veley, Nathaniel S | 58 | 1914 | 33 |  | 3 | 2023 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
| CR79 | Cruz Guzman, Joel A | 55 | 715 | 13 |  | 4 | 2023 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
| RE96 | Reyes Cruz, Denis A | 40 | 600 | 15 |  | 4 | 2023 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
| WA46 | Walker, Craig M | 40 | 600 | 15 |  | 2 | 2023 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)

## Crew Analytics
[CORTEX_V2.1] Job #2023 — Chinn, Legacy Apts · Crew Analytics
Schema CORTEX_V2.1 · canonical v2 builder · single source of truth
| tier | worker_count | hours | gross_pay | pct_of_hours | blended_wage

## Productivity
[CORTEX_V2.1] Job #2023 — Chinn, Legacy Apts · Productivity
Schema CORTEX_V2.1 · canonical v2 builder · single source of truth
| phase | labor_code | hours | pct_of_total | hours_per_unit

## PO Commitments
[CORTEX_V2.1] Job #2023 — Chinn, Legacy Apts · PO Commitments
Schema CORTEX_V2.1 · canonical v2 builder · single source of truth
| po_number | date | issuer | type | status | description | amount | source
| Legacy Prime | 2014-09-09 | Chinn Construction, LLC | Lump Sum Subcontract | Closed (100% billed) | Legacy @ Mercer Island Apts plumbing — full scope per bid sheet | 2469500 | Legacy contract OCR_d.pdf (Chinn↔OWP subcontract, Lump Sum $2,469,500)
| Legacy CO 11 | NOT FOUND | Chinn Construction, LLC | Change Order | Executed (scan) | Documented CO (image-only PDF — value not machine-readable) |  | Change Orders/CO_s/Legacy CO 11 Signed.pdf (image scan; value NOT machine-readable)
| Legacy CO 19 | NOT FOUND | Chinn Construction, LLC | Change Order | Executed (scan) | Documented CO (image-only PDF — value not machine-readable) |  | Change Orders/CO_s/Legacy CO 19.pdf (image scan)
| Legacy CO 20 | NOT FOUND | Chinn Construction, LLC | Change Order | Executed (scan) | Documented CO (image-only PDF — value not machine-readable) |  | Change Orders/CO_s/Legacy CO 20.pdf (image scan)
| Legacy CO 21 | NOT FOUND | Chinn Construction, LLC | Change Order | Executed (scan) | Documented CO (image-only PDF — value not machine-readable) |  | Change Orders/CO_s/Legacy CO 21.pdf (image scan)
| Legacy CO 22 | NOT FOUND | Chinn Construction, LLC | Change Order | Executed (scan) | Documented CO (image-only PDF — value not machine-readable) |  | Change Orders/CO_s/Legacy CO 22.pdf (image scan)
| CO-IMPLIED | 2014-09 to 2016-12 | Chinn Construction, LLC | CO Aggregate (JDR) | Absorbed | Aggregate CO impact per JDR code 999 (Rev − Orig): $301,869.00. Individual CO values not OCR-readable. | 301869 | 2023 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages) (code 999)
| TOTAL (contract + COs) | [5 empty] | 2771369
NOTE: JDR-implied CO total = $301,869.00. 5 CO PDFs on file (CO 11, 19, 20, 21, 22) are image-only scans; individual values require OCR. CO numbering gap (jump from 11 to 19) suggests 6+ additional COs exist but are not in the CO_s folder. Outbound POs: 180+ total (2 placed, 26 scheduled, 152 completed) + 38 Trim POs — see POs/ folders.

## Billing & SOV
[CORTEX_V2.1] Job #2023 — Chinn, Legacy Apts · Billing & SOV
Schema CORTEX_V2.1 · canonical v2 builder · single source of truth
| pay_app_number | date | contract_total | this_period | retainage | stored_materials | cumulative | pct_complete | source
| 036573 | 01/19/15 | -51150 |  | -2557.5 |  |  | 100% | 2023 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
| 036580 | 02/11/15 | -30000 |  | -1500 |  |  | 2% | 2023 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
| 036595 | 03/18/15 | -64810 |  | -3240.5 |  |  | 4% | 2023 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
| 036602 | 04/20/15 | -54040 |  | -2702 |  |  | 4% | 2023 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
| 036608 | 05/19/15 | -73600 |  | -3680 |  |  | 4% | 2023 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
| 036616 | 06/18/15 | -12450 |  | -622.5 |  |  | 100% | 2023 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
| 036626 | 07/20/15 | -20008 |  | -1000.4 |  |  | 3% | 2023 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
| 036632 | 08/20/15 | -276500 |  | -13825 |  |  | 4% | 2023 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
| 036641 | 09/18/15 | -371953 |  | -18597.65 |  |  | 10% | 2023 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
| 036649 | 10/19/15 | -243958 |  | -12197.9 |  |  | 5% | 2023 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
| 036657 | 11/16/15 | -322600 |  | -16130 |  |  | 5% | 2023 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
| 036671 | 12/18/15 | -275039 |  | -13751.95 |  |  | 10% | 2023 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
| 036676 | 01/20/16 | -319545 |  | -15977.25 |  |  | 14% | 2023 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
| 036684 | 02/19/16 | -240145 |  | -12007.25 |  |  | 10% | 2023 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
| 036698 | 03/18/16 | -23143 |  | -1157.15 |  |  | 3% | 2023 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
| 036713 | 04/20/16 | -15700 |  | -785 |  |  | 4% | 2023 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
| 036724 | 05/20/16 | -34044 |  | -1702.2 |  |  | 3% | 2023 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
| 036742 | 06/20/16 | -123239 |  | -6161.95 |  |  | 6% | 2023 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
| 036756 | 07/20/16 | -37060 |  | -1853 |  |  | 4% | 2023 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
| 036759 | 07/20/16 | 37060 |  | 1853 |  |  | 4% | 2023 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
| 036760 | 07/20/16 | -56200 |  | -2810 |  |  | 5% | 2023 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
| 036774 | 08/19/16 | -89840 |  | -4492 |  |  | 5% | 2023 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
| 036788 | 09/22/16 | -67236 |  | -3361.8 |  |  | 8% | 2023 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
| 036793 | 10/20/16 | -1200 |  | -60 |  |  | 100% | 2023 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
| 036809 | 12/15/16 | -4969 |  | -248.45 |  |  | 4% | 2023 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
| TOTAL (signed) |  | -2771369 |  | -138568.45
NOTE: AR entries signed negative per Sage convention. Net billed = $2,771,369.00; retainage $138,568.45 outstanding on JDR dated 04/03/2026. First invoice 036573 (01/19/15); last invoice 036809 (12/15/16). Billing folder contains 'Legacy sent invoices & releases' subfolder.

## Insights
[CORTEX_V2.1] Job #2023 — Chinn, Legacy Apts · Insights
Schema CORTEX_V2.1 · canonical v2 builder · single source of truth
| insight_id | title | finding | verified | source
Verified
Verified
Verified
Medium
Verified
Verified
Verified
Verified
Verified
Verified

## Benchmark KPIs
[CORTEX_V2.1] Job #2023 — Chinn, Legacy Apts · Benchmark KPIs
Schema CORTEX_V2.1 · canonical v2 builder · single source of truth
CROSS-PROJECT BENCHMARK SCORECARD
Normalized metrics designed for apples-to-apples comparison across all OWP projects.
| KPI | DATA NAME | VALUE | CATEGORY | NOTES / BENCHMARK CONTEXT
| Job Number | job_number | 2,023 | Profile | OWP Sage job ID
| General Contractor | general_contractor | Chinn Construction, LLC | Profile | Customer of record
| location | location | 2601 76th Ave SE, Mercer Island, WA 98040 | Profile | Project address
| Project Type | project_type | Commercial | Profile | Building category for benchmarking
| Duration Months | duration_months | 23.0% | Profile | Calendar months from start to close
| Contract Original | contract_original | $-51,150 | Financial | Original contract value
| Contract Final | contract_final | $2,771,369 | Financial | Revised contract value (post-COs)
| Change Orders Net | change_orders_net | 2,822,519 | Financial | Net dollar change from COs
| revenue | revenue | $2,771,369 | Financial | Net billed (AR net of reversals)
| Net Profit | net_profit | $904,898 | Financial | Revenue − direct cost
| Gross Margin Pct | gross_margin_pct | 32.6% | Financial | Net profit / revenue
| Direct Cost | direct_cost | $1,866,471 | Financial | Σ labor + material + OH + burden + tax
| Overhead Cost | overhead_cost | $71,569 | Financial | Codes 600, 601, 603, 607
| Burden Cost | burden_cost | $312,025 | Financial | Code 995 payroll burden
| Retainage Outstanding | retainage_outstanding | $0.00 | Financial | Held by GC until closeout
| Labor Cost | labor_cost | $702,744 | Labor | Codes 100–150
| Total Hours | total_hours | 33,163 | Labor | All payroll hours on the job
| Total Workers | total_workers | 52 | Crew | Unique payroll IDs across job
| Blended Wage | blended_wage | $21.49 | Labor | Pre-burden average
| Fully Loaded Wage | fully_loaded_wage | $32.25 | Labor | Post-burden true cost
| Burden Multiplier | burden_multiplier | 1.50 | Labor | Loaded / gross
| Labor Pct Revenue | labor_pct_revenue | 0.25 | Cost Mix | Payroll exposure
| Material Cost | material_cost | $725,505 | Material | Codes 210–244
| Material Pct Revenue | material_pct_revenue | 0.26 | Cost Mix | Material/sub exposure
| Total Vendors | total_vendors | 32 | Material | Distinct AP vendors invoiced on the job
| Top Vendor Spend | top_vendor_spend | $190,637 | Material | Largest single supplier
| Top Vendor Pct | top_vendor_pct | 26.3% | Material | Top vendor concentration
| Revenue Per Hour | revenue_per_hour | $83.71 | Labor | Productivity ceiling
| Profit Per Hour | profit_per_hour | $27.33 | Labor | Margin per hour worked
| Revenue Per Month | revenue_per_month | $120,494 | Throughput | Billing velocity
| Hours Per Month | hours_per_month | $1,439 | Throughput | Avg monthly labor burn
| Units Per Month | units_per_month | $0.00 | Throughput | Build pace
SOURCES
Canonical: /sessions/keen-determined-mccarthy/mnt/cortex-mockup/owp/cortex v2 files/OWP_2023_JCR_Cortex_v2.xlsx
revenue: AR net-of-reversals (validator)
labor_cost: Codes 100–150
material_cost: Codes 210–244
total_workers: count(distinct worker_id)

## Change Log
[CORTEX_V2.1] Job #2023 — Chinn, Legacy Apts · Change Log
Schema CORTEX_V2.1 · canonical v2 builder · single source of truth
| event_id | type | date | subject | originator | linked_events | cost_impact | schedule_days | status | source_document
| CONTRACT-ORIG | Contract |  | Prime subcontract — Lump Sum $2,469,500.00 | Chinn Construction, LLC |  | 2469500 |  | Executed | Legacy contract OCR_d.pdf (Chinn↔OWP subcontract, Lump Sum $2,469,500)
| CO-11 | Change Order |  | Legacy CO 11 — image-scan PDF, value NOT extractable | Chinn Construction, LLC |  |  |  | Executed | CO_s/Legacy CO 11 Signed.pdf
| CO-19 | Change Order |  | Legacy CO 19 — image-scan PDF, value NOT extractable | Chinn Construction, LLC |  |  |  | Executed | CO_s/Legacy CO 19.pdf
| CO-20 | Change Order |  | Legacy CO 20 — image-scan PDF, value NOT extractable | Chinn Construction, LLC |  |  |  | Executed | CO_s/Legacy CO 20.pdf
| CO-21 | Change Order |  | Legacy CO 21 — image-scan PDF, value NOT extractable | Chinn Construction, LLC |  |  |  | Executed | CO_s/Legacy CO 21.pdf
| CO-22 | Change Order |  | Legacy CO 22 — image-scan PDF, value NOT extractable | Chinn Construction, LLC |  |  |  | Executed | CO_s/Legacy CO 22.pdf
| CO-IMPLIED | CO Aggregate |  | Aggregate CO impact per JDR code 999 delta = $301,869.00 | Chinn Construction, LLC |  | 301869 |  | Absorbed | 2023 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
| CO-GAP | CO Numbering Gap |  | CO# jumps 11→19 in folder — suggests 6+ COs missing from folder | — |  | 0 |  | Unresolved | CO folder scan
| ASI-RFI-BATCH | RFI/ASI batch |  | 125 ASI-RFI docs (ASIs 07/09/10/14/16/25/26 + Hadley RFIs 051-360+; VIA & BCRA responses) | VIA Architecture / Sub / GC |  | 0 |  | Resolved | ASI-RFI/
| DROPBOX-RFI | RFI batch |  | Additional RFI docs from field tablets | Sub (OWP) |  | 0 |  | Resolved | DROPBOX FILES FROM TABLETS/
| SUB-EQUIPMENT | Submittal batch |  | Equipment submittals (Backflow preventer, Expansion tank, etc.) | Sub (OWP) |  | 0 |  | Approved | Submittals/EQUIPMENT SUBMITTALS/
| SUB-FIXTURE | Submittal batch |  | Fixture submittals (WC, lav, tub/shower, sinks) — multiple revision rounds | Sub (OWP) |  | 0 |  | Approved | Submittals/FIXTURE SUBMITTALS/ (incl. REVISED SUBMITTALS 09.21.15)
| SUB-MATERIAL | Submittal batch |  | Material submittals (PVC pipe & fittings, full material submittal package) | Sub (OWP) |  | 0 |  | Approved | Submittals/MATERIAL SUBMITTALS/
| SUB-UG | Submittal batch |  | Underground & Garage submittals (pump basin, oil-water separator, Proset toilet detail) | Sub (OWP) |  | 0 |  | Approved | Submittals/UNDERGROUND & GARAGE SUBMITTALS/
| SUB-RESPONSES | Submittal Responses |  | Returned submittal responses from GC/Architect | VIA Architecture / Chinn Construction, LLC |  | 0 |  | Logged | Submittals/RESPONSES/
| PO-COMPLETED | PO batch |  | 152 completed POs | Sub (OWP) |  | 0 |  | Complete | PO_s/3 Completed/
| PO-PLACED | PO batch |  | 2 placed POs | Sub (OWP) |  | 0 |  | Placed | PO_s/1 Placed/
| PO-SCHEDULED | PO batch |  | 26 scheduled POs | Sub (OWP) |  | 0 |  | Scheduled | PO_s/2 Scheduled/
| PO-TRIM | PO batch (trim) |  | 38 Trim POs (fixture trim-out) | Sub (OWP) |  | 0 |  | Complete | PO_s/Trim PO_s/
| MEETINGS | Meeting log |  | Project meeting notes & schedules | Chinn Construction, LLC |  | 0 |  | Logged | Meetings-Schedules/
| OM-TURNOVER | O&M Closeout |  | Operations & Maintenance closeout package | Sub (OWP) |  | 0 |  | Delivered | O&M_s/
| FRANKLIN-ENG | Engineering |  | Franklin Mercer Island engineering package (code 601) | Franklin Engineering |  | 0 |  | Completed | Franklin Mercer Island/
| FIRST-INVOICE | Invoice |  | First billing #036573 | Sub (OWP) |  | 51150 |  | Paid | 2023 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
| LAST-INVOICE | Invoice |  | Last billing #036809 | Sub (OWP) |  | 4969 |  | Paid | 2023 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
| RETAINAGE-OPEN | Retainage |  | Retainage $138,568.45 outstanding 9+ years post-closeout | GC |  | 0 |  | Outstanding | 2023 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)

## Root Cause Analysis
[CORTEX_V2.1] Job #2023 — Chinn, Legacy Apts · Root Cause Analysis
Schema CORTEX_V2.1 · canonical v2 builder · single source of truth
| rca_id | observation | root_cause | responsibility | cost_impact | mitigation | source

## Predictive Signals
[CORTEX_V2.1] Job #2023 — Chinn, Legacy Apts · Predictive Signals
Schema CORTEX_V2.1 · canonical v2 builder · single source of truth
| signal_id | signal_name | direction | metric | threshold | historical_outcome | source
| WAREHOUSE | Predictive signals computed at warehouse layer | Neutral | cross-project benchmark | n/a | See benchmark_envelopes view; not stored per-project. | warehouse view (predictive_signals_v)

## Metric Registry
[CORTEX_V2.1] Job #2023 — Chinn, Legacy Apts · Metric Registry
Schema CORTEX_V2.1 · canonical v2 builder · single source of truth
| metric_key | metric_label | value | data_label | tab_home | verification | source
2023
Chinn, Legacy Apts
Legacy @ Mercer Island Apts (Hadley)
Chinn Construction, LLC
2023CC
Hadley Improvements Owner, LLC
VIA Architecture
2601 76th Ave SE, Mercer Island WA 98040
Multifamily Plumbing (241 units)
2015-01-19
2016-12-15
23
241
11
244
244
241
211
31
4
17
2469500
2771369
301869
5
0.12224
2771369
1873341.44
898027.56
0.32404
138568.45
0.05
702744.35
725504.82
78439.57
312024.89
54627.81
33107
52
21.2265
32.3012
1.5217
83.7095
27.125
11499.4564
7773.201
137.3734
0.25357
0.26179
32
25
125
7
100
180
0.05372
0.24433
30

## Reconciliation
[CORTEX_V2.1] Job #2023 — Chinn, Legacy Apts · Reconciliation
Schema CORTEX_V2.1 · canonical v2 builder · single source of truth
| check_number | check_description | value_a | value_b | difference | status | tabs
| 1 | Revenue (JDR) = Contract Final | 2771369 | 2771369 | 0 | TIES | 1↔8
| 2 | Expenses = Labor+Material+OH+Burden+Tax | 1873341.44 | 1873341.44 | 0 | TIES | 1↔3
| 3 | Net Profit = Revenue - Expenses | 898027.56 | 898027.56 | 0 | TIES | 1↔Derived
| 4 | JDR Source: AP+PR+GL = Expenses | 1873341.44 | 1873341.44 | 0 | TIES | 1↔Derived (footer)
| 5 | Budget vs Actual (code 999) = -Revenue | 2771369 | 2771369 | 0 | TIES | 2↔1
| 6 | Total Labor Hours = Worker hours sum | 33107 | 33163 | -56 | WITHIN | 5↔2
| 7 | Labor Cost = Worker gross sum | 702744.35 | 712739.5 | -9995.15 | WITHIN | 5↔3
| 8 | Vendor total ≈ AP footer | 682284.56 | 682284.56 | 0 | TIES | 12↔1 (approximate)
| 9 | Invoice count | 25 | 25 | 0 | TIES | 9↔11
| 10 | Contract Final - Orig = CO implied | 301869 | 301869 | 0 | TIES | 11↔Derived
| 11 | Retainage outstanding | 138568.45 | 138568.45 | 0 | TIES | 9↔JDR footer
| 12 | Retainage sum from invoices | 138568.45 | 138568.45 | 0 | TIES | 9↔JDR footer
| 13 | Worker count | 52 | 52 | 0 | TIES | 5↔11
| 14 | Cost code count | 30 | 30 | 0 | TIES | 2↔16
2023.0403
92014.241
100
18015222638
611191385689
15

## Vendors
[CORTEX_V2.1] Job #2023 — Chinn, Legacy Apts · Vendors
Schema CORTEX_V2.1 · canonical v2 builder · single source of truth
| vendor_id | vendor_name | total_spend | transactions | category | source
| 2023RS | Rosen Supply Company, Inc. | 190637.35 | 116 |  | 2023 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
| 2023CS | Consolidated Supply Co. | 164734.54 | 73 |  | 2023 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
| 2023FE | Ferguson Enterprises, Inc. | 161354.82 | 71 |  | 2023 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
| 2023KS | Keller Supply Company | 66440.23 | 39 |  | 2023 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
| 3612MS | Mechanical Sales, Inc. | 28019.56 | 4 |  | 2023 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
| 1625FE | Franklin Engineering | 27834 | 6 |  | 2023 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
| 3181SC | Scan2Core, Inc. | 9291 | 7 |  | 2023 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
| 1231KS | Keller Supply Company | 6943.87 | 3 |  | 2023 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
| 7200UR | United Rentals, Inc. | 6785.95 | 11 |  | 2023 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
| 1609QC | Quality Concrete Products, Inc. $32 | 6488 | 4 |  | 2023 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
| 1516DS | Duraseal, Inc. | 3860 | 1 |  | 2023 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
| 5621HD | Core & Main LP | 2464.39 | 2 |  | 2023 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
| 1380RS | Rosen Supply Kirkland | 1670.93 | 9 |  | 2023 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
| 2132MH | Manor Hardware & Construction Supply | 908.02 | 3 |  | 2023 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
| 1504CA | Chip Away Bathtub Repair, Inc. | 750 | 1 |  | 2023 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
| 8068MI | Kele, Inc $ MI Controls | 694.25 | 1 |  | 2023 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
| 1303CM | C.M. Hoskins Company | 564.48 | 3 |  | 2023 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
| 2024FE | Ferguson Enterprises, Inc. $MG-Ballard | 533.19 | 1 |  | 2023 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
| 1175FE | Ferguson Enterprises, Inc. #3007 | 436.87 | 1 |  | 2023 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
| 1611AS | Beacon Building Products | 361.89 | 2 |  | 2023 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
| 1288DR | DRSi | 309.85 | 2 |  | 2023 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
| 1234CO | Capital One Credit Card | 293.86 | 2 |  | 2023 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
| 3820HI | Hilti, Inc. | 292.5 | 1 |  | 2023 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
| 2021RS | Rosen Supply Company | 290.47 | 2 |  | 2023 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
| 1421RA | R.A. Brown Backflow Testing | 229.5 | 1 |  | 2023 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
| 1799AW | AllWest Underground, Inc. | 84.84 | 1 |  | 2023 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
| 1126SS | Specification Sales, Inc. | 71.04 | 2 |  | 2023 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
| 1234BA | Bank of America CC | 66.74 | 1 |  | 2023 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
| 1344HD | HD Fowler Company | 61.12 | 1 |  | 2023 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
| 2019RS | Rosen Supply Company, Inc. $8th, Republi | 49.61 | 2 |  | 2023 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
| 2027FE | Ferguson Enterprises, Inc. $550 Broadway | 45.53 | 1 |  | 2023 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
| 1130CS | Consolidated Supply Co. | -283.84 | 2 |  | 2023 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)