## Overview
[CORTEX_V2.1] Job #2024 — SRM, Ballard Merrill Gardens · Overview
Schema CORTEX_V2.1 · canonical v2 builder · single source of truth
| OVERVIEW |  | SOURCE
IDENTITY
| Project Job Number | 2024 | 2024 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages) header
| Project Name Sage | SRM, Ballard Merrill Gardens | 2024 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages) header
| Project Description | Merrill Gardens at Ballard — senior-living plumbing, ~116 residential units + amenity | mgb contract brett signed OCR_D.pdf (21-Apr-2015, Lump Sum $1,932,774.08 gross incl $169,294 WSST = $1,763,480 net) + trim PO fixture count
| Customer Code Sage | 2024MG | 2024 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
CONTRACT & PARTIES
| Contract Counterparty | Merrill Gardens at Ballard, LLC | mgb contract brett signed OCR_D.pdf (21-Apr-2015, Lump Sum $1,932,774.08 gross incl $169,294 WSST = $1,763,480 net)
| Parent Owner / Developer | SRM Development Corp / Merrill Gardens (Spokane) | mgb contract brett signed OCR_D.pdf (21-Apr-2015, Lump Sum $1,932,774.08 gross incl $169,294 WSST = $1,763,480 net) (111 N. Post, Suite 200, Spokane, WA)
| Architect | Urbal Architecture (Seattle) | Per contract § 'Main Contract' documents
| Contract Type | Lump Sum | mgb contract brett signed OCR_D.pdf (21-Apr-2015, Lump Sum $1,932,774.08 gross incl $169,294 WSST = $1,763,480 net)
| Contract Document | mgb contract brett signed OCR_D.pdf (21-Apr-2015, Lump Sum $1,932,774.08 gross incl $169,294 WSST = $1,763,480 net) | Fully executed 4/21/2015, Lump Sum + WSST 9.6%
JOB SITE
| Jobsite Location | 5601 24th Ave NW, Seattle, WA 98107 | mgb contract brett signed OCR_D.pdf (21-Apr-2015, Lump Sum $1,932,774.08 gross incl $169,294 WSST = $1,763,480 net)
SCHEDULE
| Work Period | 05/19/15 – 08/22/16 ≈ 15 months (first→last invoice) | 2024 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
SCOPE & DESIGN
| Fixture Schedule | Submittals/FIXTURE SUBMITTALS/BALLARD MERRILL GARDENS FIXTURE SUBMITTAL CONTENTS.xlsx | Residential (P-1/P-2/P-5/P-7) + Common/Amenity/Staff (P-1A/P-2A/P-2B/P-5/P-5A/P-6/P-8/P-9/P-10/P-12/P-13)
| Plans / Specifications | Plans/ folder — 8 subfolders (Current / Contract / Misc / MEF / Old / CADD / Bid / As-Built) | Folder scan
| Bid Documents | Plans/7 - Bid Documents/14-11-14 Merrill Gardens at Ballard Specifications.pdf | Bid Documents subfolder
DOCUMENTATION
| Total Unique Documents Reviewed | 1000+ across 2 mirror folders | File inventory across owp-2024/
| CONTRACT VALUE |  | NET PROFIT |  | DIRECT COST |  | LABOR HOURS
| $1,811,843 |  | $888,611 |  | $923,232 |  | 17,061
| Original $-114,100 |  | 49.0% margin |  | 51.0% of revenue |  | 40 workers
COST BREAKDOWN
| Category | Budget | Actual | Variance | % Budget | % of Cost
| Labor | 414758 | 379757.5 | 35000.5 | 91.56% | 41.13%
| Material | 587857 | 336538.34 | 251318.66 | 57.25% | 36.45%
| Overhead | 42123 | 10200.98 | 31922.02 | 24.22% | 1.105%
| Burden | 212023 | 196735.22 | 15287.78 | 92.79% | 21.31%
| TOTAL | 1256761 | 923232.04 | 333528.96 | 73.46% | 100%
PROJECT PROFILE
| Duration | 05/19/15 – 08/22/16 ≈ 15 months (first→last invoice)

## Budget vs Actual
[CORTEX_V2.1] Job #2024 — SRM, Ballard Merrill Gardens · Budget vs Actual
Schema CORTEX_V2.1 · canonical v2 builder · single source of truth
| cost_code | description | original_budget | revised_budget | actual | variance | pct_used | hours | source
| 100 | Supervision | 14000 | 14800 | 12228.5 | -2571.5 | 82.62% | 295 | 2024 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
| 101 | Takeoff & Purchase Labor | 20800 | 21407 | 20381.5 | -1025.5 | 95.21% | 471.5 | 2024 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
| 110 | Underground Labor | 13300 | 13300 | 7558 | -5742 | 56.83% | 297 | 2024 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
| 111 | Garage Labor | 85500 | 91072 | 66691 | -24381 | 73.23% | 2754 | 2024 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
| 112 | Canout Labor | 9400 | 9400 | 5878.5 | -3521.5 | 62.54% | 231 | 2024 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
| 120 | Roughin Labor | 183700 | 190647 | 164177 | -26470 | 86.12% | 8731 | 2024 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
| 130 | Finish Labor | 29900 | 31289 | 28250.5 | -3038.5 | 90.29% | 1150.5 | 2024 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
| 140 | Gas Labor | 8700 | 8700 | 9547 | 847 | 1.097% | 406.5 | 2024 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
| 141 | Water Main/Insulation Lab | 27000 | 27000 | 33366.5 | 6366.5 | 1.236% | 1554.5 | 2024 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
| 142 | Mech Room Labor | 7000 | 7097 | 10740.5 | 3643.5 | 1.513% | 343.5 | 2024 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
| 143 | Condensation Drains Labor | 0 | 46 | 20595.5 | 20549.5 | 447.7% | 854.5 | 2024 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
| 150 | Warranty Labor | 0 | 0 | 343 | 343 |  | 9 | 2024 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
| 210 | Underground Material | 17800 | 17800 | 22920.93 | 5120.93 | 1.288% |  | 2024 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
| 211 | Garage Material | 57600 | 57951 | 25579.57 | -32371.43 | 44.14% |  | 2024 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
| 212 | Canout Material | 14100 | 14100 | 8927.31 | -5172.69 | 63.31% |  | 2024 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
| 213 | Foundation Material | 0 | 0 | 9.84 | 9.84 |  |  | 2024 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
| 220 | Roughin Material | 122600 | 124334 | 75249.36 | -49084.64 | 60.52% |  | 2024 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
| 230 | Finish Material | 267000 | 276405 | 70943.89 | -205461.11 | 25.67% |  | 2024 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
| 240 | Gas Material | 7200 | 7200 | 4159.94 | -3040.06 | 57.78% |  | 2024 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
| 241 | Water Main/Insulation Mat | 59400 | 59400 | 50657.33 | -8742.67 | 85.28% |  | 2024 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
| 242 | Mech Room Material | 29000 | 30622 | 76386.17 | 45764.17 | 2.494% |  | 2024 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
| 243 | Condensation Drains Mat | 0 | 45 | 1704 | 1659 | 37.87% |  | 2024 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
| 600 | Subcontractor | 1000 | 1000 | 1711 | 711 | 1.711% |  | 2024 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
| 601 | Engineering/Plans | 20000 | 20000 | 1218.23 | -18781.77 | 6.091% |  | 2024 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
| 602 | Rental Equipment | 5000 | 5000 | 2202.92 | -2797.08 | 44.06% |  | 2024 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
| 603 | Permits & Licenses | 11000 | 11123 | 7148 | -3975 | 64.26% |  | 2024 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
| 607 | Other Expenses | 10000 | 10000 | 123.75 | -9876.25 | 1.238% |  | 2024 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
| 995 | Payroll Burden | 173096.55 | 180294 | 167598.54 | -12695.46 | 92.96% |  | 2024 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
| 998 | Payroll Taxes | 30546.45 | 31729 | 29136.68 | -2592.32 | 91.83% |  | 2024 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
| 999 | Sales | -1763480 | -1811843 | -1811843 | 0 | 100% |  | 2024 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
| TOTAL |  | -538837 | -550082 | -886408.04 | -336326.04 |  | 17098

## Cost Breakdown
[CORTEX_V2.1] Job #2024 — SRM, Ballard Merrill Gardens · Cost Breakdown
Schema CORTEX_V2.1 · canonical v2 builder · single source of truth
| category | cost_codes | actual | pct_of_direct_cost | pct_of_revenue | per_unit | source
| Labor | 100,101,110,111,112,120,130,140,141,142,143,150 | 379757.5 | 41.04% | 20.96% |  | 2024 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
| Material | 210,211,212,213,220,230,240,241,242,243 | 336538.34 | 36.37% | 18.57% |  | 2024 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
| Subcontractor + Engineering + Rental + Permits + Other | 600,601,602,603,607 | 12403.9 | 1.34% | 0.6846% |  | 2024 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
| Payroll Burden | 995 | 167598.54 | 18.11% | 9.25% |  | 2024 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
| Payroll Taxes | 998 | 29136.68 | 3.148% | 1.608% |  | 2024 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
| TOTAL DIRECT COST |  | 925434.96 | 100% | 51.08%
| TOTAL |  | 1850869.92 |  |  | 0

## Material
[CORTEX_V2.1] Job #2024 — SRM, Ballard Merrill Gardens · Material
Schema CORTEX_V2.1 · canonical v2 builder · single source of truth
| vendor_id | vendor_name | total_spend | transactions | category | source
| 2024RS | Rosen Supply Company, Inc. $MG-Ballard | 102072.49 | 99 | Plumbing / Supplies | 2024 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
| 2024KS | Keller Supply Company $MG-Ballard | 80438.14 | 90 | Plumbing / Supplies | 2024 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
| 3612MS | Mechanical Sales, Inc. | 37098.89 | 6 | Plumbing / Supplies | 2024 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
| 2024FE | Ferguson Enterprises, Inc. $MG-Ballard | 22824.24 | 29 | Plumbing / Supplies | 2024 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
| 2024CS | Consolidated Supply Co. $MG-Ballard | 21645.04 | 9 | Plumbing / Supplies | 2024 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
| 1609QC | Quality Concrete Products, Inc. $32 | 11655 | 4 | Concrete / subcon | 2024 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
| 1234BA | Bank of America CC | 7148 | 9 | Credit Card (mixed) | 2024 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
| 1231KS | Keller Supply Company | 5234.3 | 7 | Plumbing / Supplies | 2024 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
| 1344HD | HD Fowler Company | 3590.93 | 1 | Plumbing / Supplies | 2024 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
| 7200UR | United Rentals, Inc. | 1948.38 | 3 | Rental Equipment (602) | 2024 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
| 3181SC | Scan2Core, Inc. | 1514 | 2 | Concrete coring / subcon | 2024 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
| 1625FE | Franklin Engineering | 1021 | 1 | Engineering (601) | 2024 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
| 8068MI | Kele, Inc $ MI Controls | 847.74 | 1 | Controls | 2024 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
| 1303CM | C.M. Hoskins Company | 716 | 2 | Service / subcon | 2024 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
| 1175FE | Ferguson Enterprises, Inc. #3007 | 390.48 | 1 | Plumbing / Supplies | 2024 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
| 1130CS | Consolidated Supply Co. | 348.12 | 3 | Plumbing / Supplies | 2024 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
| 1234CO | Capital One Credit Card | 315.62 | 5 | Credit Card (mixed) | 2024 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
| 5621HD | Core & Main LP | 256 | 1 | Plumbing / Supplies | 2024 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
| 1799AW | AllWest Underground, Inc. | 254.54 | 2 | Uncategorized | 2024 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
| 1421RA | R.A. Brown Backflow Testing | 197 | 1 | Testing subcontractor | 2024 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
| 1380RS | Rosen Supply Kirkland | 123.14 | 2 | Plumbing / Supplies | 2024 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
| 1978FC | Fastenal Company | 36.18 | 1 | Uncategorized | 2024 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
| 1233AE | American Express 3-41000 | 2 | 1 | Uncategorized | 2024 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
| 2020RS | Rosen Supply Company | 0 | 2 | Plumbing / Supplies | 2024 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
NOTE: AP total per JDR footer = $299,677.23. Top vendors: Rosen Supply (MG-Ballard), Mechanical Sales, Ferguson, Consolidated Supply, Quality Concrete. Submittals folder contains 80+ submittals documenting approved products. POs folder shows 138+ POs (102 completed, 0 placed, 36 scheduled) + Trim PO_s subfolder (toilets, faucets/lavs, kitchen sinks, attic stock, utility/mop sink).

## Crew & Labor
[CORTEX_V2.1] Job #2024 — SRM, Ballard Merrill Gardens · Crew & Labor
Schema CORTEX_V2.1 · canonical v2 builder · single source of truth
| worker_id | worker_name | total_hours | gross_pay | blended_wage_per_hr | tier | work_days | source
| CA74 | Castaneda Martinez, Gustavo | 1735 | 58252 | 33.5746 |  | 49 | 2024 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
| CO71 | Cortes Mendiola, Victor H | 1221 | 36239 | 29.6798 |  | 32 | 2024 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
| CA72 | Castaneda Juarez, Edgar D | 1189.5 | 23273.5 | 19.5658 |  | 37 | 2024 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
| GU19 | Guerrero, Jorge A | 1128 | 17608 | 15.6099 |  | 32 | 2024 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
| CA73 | Castaneda Juarez, Gustavo | 1113.5 | 20874 | 18.7463 |  | 33 | 2024 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
| AS10 | Ascencio, Jose L | 1104 | 16272 | 14.7391 |  | 32 | 2024 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
| AM03 | Amaya Gonzalez, Edilberto A | 981 | 15104 | 15.3965 |  | 27 | 2024 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
| PA11 | Paco Leyva, Orlando | 933 | 22813 | 24.4512 |  | 24 | 2024 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
| RA52 | Ramos Banegas, Noel O | 932 | 15170 | 16.2768 |  | 27 | 2024 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
| GE70 | Gerard, Jordan E | 787 | 13221 | 16.7992 |  | 25 | 2024 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
| PO71 | Portillo, Kevin J | 714 | 9535 | 13.3543 |  | 20 | 2024 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
| HU06 | Hubbard, Robert W | 612.5 | 23388 | 38.1845 |  | 60 | 2024 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
| GE69 | Gerard, Jeffrey S | 544 | 22874 | 42.0478 |  | 68 | 2024 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
| GE71 | Gerard, Mitchell J | 492 | 9632 | 19.5772 |  | 18 | 2024 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
| RE96 | Reyes Cruz, Denis A | 489 | 7754 | 15.8569 |  | 14 | 2024 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
| MO54 | Monico Brambila, Jesus S | 408 | 7264 | 17.8039 |  | 13 | 2024 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
| SA54 | Sanders, Allen O | 341.5 | 12463.5 | 36.4963 |  | 28 | 2024 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
| AG51 | Aguilar Rivas, Henry | 340.5 | 4426.5 | 13 |  | 9 | 2024 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
| ME98 | Meza Fuentes, Erick A | 277 | 6632 | 23.9422 |  | 8 | 2024 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
| DO56 | Donelson, Richard T | 221 | 10049 | 45.4706 |  | 63 | 2024 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
| TA96 | Taylor, Evan R | 216 | 3408 | 15.7778 |  | 9 | 2024 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
| BE54 | Benites Portillo, Marvin E | 210.5 | 2820 | 13.3967 |  | 9 | 2024 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
| NE91 | Newton, Carson T | 156.5 | 2347.5 | 15 |  | 6 | 2024 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
| VA86 | Vaughan, Tyler J | 137 | 2877 | 21 |  | 9 | 2024 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
| MO69 | Moran Fernandez, Jose | 104 | 1872 | 18 |  | 4 | 2024 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
| RO16 | Rodriguez Bonilla, Lisandro | 104 | 1520 | 14.6154 |  | 3 | 2024 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
| MO56 | Montenegro, Carlos E | 91.5 | 1555.5 | 17 |  | 5 | 2024 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
| QU35 | Quintanilla, Esteban R | 91.5 | 3111 | 34 |  | 4 | 2024 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
| MC09 | McCabe, Thomas C | 76 | 1596 | 21 |  | 8 | 2024 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
| RI87 | Rivera, Jorge A | 64 | 1408 | 22 |  | 4 | 2024 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
| HO14 | Holmes, Anthony R | 62 | 1178 | 19 |  | 2 | 2024 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
| EL33 | Eliassen, Cory H | 49.5 | 693 | 14 |  | 3 | 2024 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
| HU04 | Hubbard, Dustin R | 43 | 682.5 | 15.8721 |  | 20 | 2024 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
| AL03 | Alba Jimenez, Jovani | 24 | 384 | 16 |  | 1 | 2024 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
| GO56 | Gonzalez Hernandez, Josue | 21 | 357 | 17 |  | 2 | 2024 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
| CR79 | Cruz Guzman, Joel A | 16 | 208 | 13 |  | 1 | 2024 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
| WE55 | Wennig, Johnathan M | 16 | 288 | 18 |  | 1 | 2024 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
| CR87 | Cruz Reyes, Jose | 8 | 120 | 15 |  | 1 | 2024 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
| BA70 | Barnhart, Joseph N | 5 | 191 | 38.2 |  | 2 | 2024 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
| GA70 | Garcia, Jordan X | 2 | 48 | 24 |  | 1 | 2024 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)

## Crew Analytics
[CORTEX_V2.1] Job #2024 — SRM, Ballard Merrill Gardens · Crew Analytics
Schema CORTEX_V2.1 · canonical v2 builder · single source of truth
| tier | worker_count | hours | gross_pay | pct_of_hours | blended_wage

## Productivity
[CORTEX_V2.1] Job #2024 — SRM, Ballard Merrill Gardens · Productivity
Schema CORTEX_V2.1 · canonical v2 builder · single source of truth
| phase | labor_code | hours | pct_of_total | hours_per_unit

## PO Commitments
[CORTEX_V2.1] Job #2024 — SRM, Ballard Merrill Gardens · PO Commitments
Schema CORTEX_V2.1 · canonical v2 builder · single source of truth
| po_number | date | issuer | type | status | description | amount | source
| 100-220002 | 2015-04-21 | Merrill Gardens at Ballard, LLC | Lump Sum Subcontract | Closed (100% billed) | Merrill Gardens at Ballard plumbing (5601 24th Ave NW) — full scope | 1763480 | mgb contract brett signed OCR_D.pdf (21-Apr-2015, Lump Sum $1,932,774.08 gross incl $169,294 WSST = $1,763,480 net)
| COR-02 (CO#1) | 2016-01-11 | Merrill Gardens at Ballard, LLC | Change Order (COR) | Executed | RFI-061 ADDED EYEWASH STATIONS | 3015 | Change Orders/COR_s/Ballard MG - Outstanding COR_s.xlsx
| COR-FX (CO#1) | 2016-01-11 | Merrill Gardens at Ballard, LLC | Change Order (COR) | Executed | ALTERNATE FIXTURE PRICING | 653 | Change Orders/COR_s/Ballard MG - Outstanding COR_s.xlsx
| COR-05 (CO#1) | 2016-01-11 | Merrill Gardens at Ballard, LLC | Change Order (COR) | Executed | UPGRADED P-17 SINK | 161 | Change Orders/COR_s/Ballard MG - Outstanding COR_s.xlsx
| COR-06-R1 (CO#2) | 2016-02-18 | Merrill Gardens at Ballard, LLC | Change Order (COR) | Executed | ASI-039-R1 Kitchen Equipment Changes | 1107 | Change Orders/COR_s/Ballard MG - Outstanding COR_s.xlsx
| COR-04 (CO#3) | 2016-02-18 | Merrill Gardens at Ballard, LLC | Change Order (COR) | Executed | CHANGE OUT CAST IRON 90'S | 9302 | Change Orders/COR_s/Ballard MG - Outstanding COR_s.xlsx
| COR-09 (CO#3) | 2016-02-18 | Merrill Gardens at Ballard, LLC | Change Order (COR) | Executed | Undermount Kitchen & Bar Sinks | 6842 | Change Orders/COR_s/Ballard MG - Outstanding COR_s.xlsx
| COR-01 (CO#4) | 2016-04-20 | Merrill Gardens at Ballard, LLC | Change Order (COR) | Executed | RFI-074 ADD AUTOWASH BOX | 637 | Change Orders/COR_s/Ballard MG - Outstanding COR_s.xlsx
| COR-03 (CO#4) | 2016-04-20 | Merrill Gardens at Ballard, LLC | Change Order (COR) | Executed | RFI-122 MOVE KITCHEN STACKS | 2012 | Change Orders/COR_s/Ballard MG - Outstanding COR_s.xlsx
| COR-07 (CO#4) | 2016-04-20 | Merrill Gardens at Ballard, LLC | Change Order (COR) | Executed | RFI-159 Condenser Rack Drain | 271 | Change Orders/COR_s/Ballard MG - Outstanding COR_s.xlsx
| COR-08 (CO#4) | 2016-04-20 | Merrill Gardens at Ballard, LLC | Change Order (COR) | Executed | RFI-162 Added Drinking Fountain | 2020 | Change Orders/COR_s/Ballard MG - Outstanding COR_s.xlsx
| COR-10 (CO#4) | 2016-04-20 | Merrill Gardens at Ballard, LLC | Change Order (COR) | Executed | RFI-175 Added Sink | 933 | Change Orders/COR_s/Ballard MG - Outstanding COR_s.xlsx
| COR-11 (CO#4) | 2016-04-20 | Merrill Gardens at Ballard, LLC | Change Order (COR) | Executed | Stolen Fittings & Valves | 1772 | Change Orders/COR_s/Ballard MG - Outstanding COR_s.xlsx
| COR-12 (CO#4) | 2016-04-20 | Merrill Gardens at Ballard, LLC | Change Order (COR) | Executed | ASI-045 Level 7 Suite Revision | 21954 | Change Orders/COR_s/Ballard MG - Outstanding COR_s.xlsx
| COR-Kitchen Vent (CO#6) | 2016-06-24 | Merrill Gardens at Ballard, LLC | Change Order (COR) | Executed | Move Vent for Kitchen Exhaust | 517 | Change Orders/COR_s/Ballard MG - Outstanding COR_s.xlsx
| COR-15 (CO#7) | 2016-07-14 | Merrill Gardens at Ballard, LLC | Change Order (COR) | Executed | Sink Changes | 732 | Change Orders/COR_s/Ballard MG - Outstanding COR_s.xlsx
| COR-14 (CO#8) | 2016-08-19 | Merrill Gardens at Ballard, LLC | Change Order (COR) | Executed | Attic Stock | 690 | Change Orders/COR_s/Ballard MG - Outstanding COR_s.xlsx
| COR-16 (CO#8) | 2016-08-19 | Merrill Gardens at Ballard, LLC | Change Order (COR) | Executed | Eyewash Stations | 2045 | Change Orders/COR_s/Ballard MG - Outstanding COR_s.xlsx
| TOTAL (contract + documented COs) | [5 empty] | 1818143
NOTE: Documented COs sum to $54,663.00; JDR-implied COs = $48,363.00 (diff $6,300.00 — documented CORs exceed JDR delta by ~$6,300, likely due to CORs that were re-priced or cancelled, and WSST-exclusive pricing vs contract-net figures). Outbound POs: 138+ total (102 completed + 36 scheduled) + extensive Trim PO subfolder.

## Billing & SOV
[CORTEX_V2.1] Job #2024 — SRM, Ballard Merrill Gardens · Billing & SOV
Schema CORTEX_V2.1 · canonical v2 builder · single source of truth
| pay_app_number | date | contract_total | this_period | retainage | stored_materials | cumulative | pct_complete | source
| 036614 | 05/19/15 | -114100 |  | -5705 |  |  | 4% | 2024 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
| 036622 | 06/25/15 | -19000 |  | -950 |  |  | 100% | 2024 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
| 036629 | 07/23/15 | -25700 |  | -1285 |  |  | 100% | 2024 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
| 036638 | 08/25/15 | -89950 |  | -4497.5 |  |  | 3% | 2024 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
| 036648 | 09/25/15 | -321150 |  | -16057.5 |  |  | 5% | 2024 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
| 036656 | 10/22/15 | -446910 |  | -22345.5 |  |  | 9% | 2024 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
| 036663 | 11/23/15 | -156760 |  | -7838 |  |  | 6% | 2024 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
| 036672 | 12/18/15 | -231660 |  | -11583 |  |  | 10% | 2024 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
| 036679 | 01/22/16 | -141050 |  | -7052.5 |  |  | 6% | 2024 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
| 036687 | 02/25/16 | -59829 |  | -2991.45 |  |  | 10% | 2024 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
| 036699 | 03/18/16 | -49480 |  | -2474 |  |  | 6% | 2024 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
| 036714 | 04/25/16 | -56998 |  | -2849.9 |  |  | 10% | 2024 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
| 036728 | 05/24/16 | -55020 |  | -2751 |  |  | 5% | 2024 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
| 036744 | 06/24/16 | -40252 |  | -2012.6 |  |  | 7% | 2024 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
| 036745 | 06/24/16 | 40252 |  | 2012.6 |  |  | 7% | 2024 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
| 036746 | 06/24/16 | -40769 |  | -2038.45 |  |  | 8% | 2024 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
| 036758 | 07/20/16 | -732 |  | -36.6 |  |  | 100% | 2024 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
| 036777 | 08/22/16 | -2735 |  | -136.75 |  |  | 2% | 2024 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
| TOTAL (signed) |  | -1811843 |  | -90592.15
NOTE: AR entries signed negative per Sage convention. Net billed = $1,811,843.00; retainage $90,592.15 outstanding on JDR dated 04/03/2026. First invoice 036614 (05/19/15); last invoice 036777 (08/22/16). Aggregate billing log (MGB AGGREGATE BILLING.xlsx (16 billings + retainage release row, ties to JDR)) shows 16 billings + retainage-release line, 5% retention, 9.6% WSST add-on, with running aggregate ties to the contract ledger.

## Insights
[CORTEX_V2.1] Job #2024 — SRM, Ballard Merrill Gardens · Insights
Schema CORTEX_V2.1 · canonical v2 builder · single source of truth
| insight_id | title | finding | verified | source
Verified
Verified
Verified
Verified
Verified
Verified
Verified
Verified
Verified
Verified

## Benchmark KPIs
[CORTEX_V2.1] Job #2024 — SRM, Ballard Merrill Gardens · Benchmark KPIs
Schema CORTEX_V2.1 · canonical v2 builder · single source of truth
CROSS-PROJECT BENCHMARK SCORECARD
Normalized metrics designed for apples-to-apples comparison across all OWP projects.
| KPI | DATA NAME | VALUE | CATEGORY | NOTES / BENCHMARK CONTEXT
| Job Number | job_number | 2,024 | Profile | OWP Sage job ID
| location | location | 5601 24th Ave NW, Seattle, WA 98107 | Profile | Project address
| Project Type | project_type | Commercial | Profile | Building category for benchmarking
| Duration Months | duration_months | 15.0% | Profile | Calendar months from start to close
| Contract Original | contract_original | $-114,100 | Financial | Original contract value
| Contract Final | contract_final | $1,811,843 | Financial | Revised contract value (post-COs)
| Change Orders Net | change_orders_net | 1,925,943 | Financial | Net dollar change from COs
| revenue | revenue | $1,811,843 | Financial | Net billed (AR net of reversals)
| Net Profit | net_profit | $888,611 | Financial | Revenue − direct cost
| Gross Margin Pct | gross_margin_pct | 49.0% | Financial | Net profit / revenue
| Direct Cost | direct_cost | $923,232 | Financial | Σ labor + material + OH + burden + tax
| Overhead Cost | overhead_cost | $10,201 | Financial | Codes 600, 601, 603, 607
| Burden Cost | burden_cost | $167,599 | Financial | Code 995 payroll burden
| Retainage Outstanding | retainage_outstanding | $0.00 | Financial | Held by GC until closeout
| Labor Cost | labor_cost | $379,758 | Labor | Codes 100–150
| Total Hours | total_hours | 17,061 | Labor | All payroll hours on the job
| Total Workers | total_workers | 40 | Crew | Unique payroll IDs across job
| Blended Wage | blended_wage | $22.24 | Labor | Pre-burden average
| Fully Loaded Wage | fully_loaded_wage | $33.79 | Labor | Post-burden true cost
| Burden Multiplier | burden_multiplier | 1.52 | Labor | Loaded / gross
| Labor Pct Revenue | labor_pct_revenue | 0.21 | Cost Mix | Payroll exposure
| Material Cost | material_cost | $336,538 | Material | Codes 210–244
| Material Pct Revenue | material_pct_revenue | 0.19 | Cost Mix | Material/sub exposure
| Total Vendors | total_vendors | 24 | Material | Distinct AP vendors invoiced on the job
| Top Vendor Spend | top_vendor_spend | $102,072 | Material | Largest single supplier
| Top Vendor Pct | top_vendor_pct | 30.3% | Material | Top vendor concentration
| Revenue Per Hour | revenue_per_hour | $106 | Labor | Productivity ceiling
| Profit Per Hour | profit_per_hour | $51.97 | Labor | Margin per hour worked
| Revenue Per Month | revenue_per_month | $120,790 | Throughput | Billing velocity
| Hours Per Month | hours_per_month | $1,140 | Throughput | Avg monthly labor burn
| Units Per Month | units_per_month | $0.00 | Throughput | Build pace
SOURCES
Canonical: /sessions/keen-determined-mccarthy/mnt/cortex-mockup/owp/cortex v2 files/OWP_2024_JCR_Cortex_v2.xlsx
revenue: AR net-of-reversals (validator)
labor_cost: Codes 100–150
material_cost: Codes 210–244
total_workers: count(distinct worker_id)

## Change Log
[CORTEX_V2.1] Job #2024 — SRM, Ballard Merrill Gardens · Change Log
Schema CORTEX_V2.1 · canonical v2 builder · single source of truth
| event_id | type | date | subject | originator | linked_events | cost_impact | schedule_days | status | source_document
| CONTRACT-ORIG | Contract | 2015-04-21 | Prime subcontract — Lump Sum $1,763,480.00 (+9.6% WSST = $1,932,774.08 gross) | Merrill Gardens at Ballard, LLC |  | 1763480 |  | Executed | mgb contract brett signed OCR_D.pdf (21-Apr-2015, Lump Sum $1,932,774.08 gross incl $169,294 WSST = $1,763,480 net)
| COR-02 | Change Order (COR) | 2016-01-11 | COR-02: RFI-061 ADDED EYEWASH STATIONS (rolled into CO#1) | Merrill Gardens at Ballard, LLC |  | 3015 |  | Executed | Change Orders/COR_s/Ballard MG - Outstanding COR_s.xlsx
| COR-FX | Change Order (COR) | 2016-01-11 | COR-FX: ALTERNATE FIXTURE PRICING (rolled into CO#1) | Merrill Gardens at Ballard, LLC |  | 653 |  | Executed | Change Orders/COR_s/Ballard MG - Outstanding COR_s.xlsx
| COR-05 | Change Order (COR) | 2016-01-11 | COR-05: UPGRADED P-17 SINK (rolled into CO#1) | Merrill Gardens at Ballard, LLC |  | 161 |  | Executed | Change Orders/COR_s/Ballard MG - Outstanding COR_s.xlsx
| COR-06-R1 | Change Order (COR) | 2016-02-18 | COR-06-R1: ASI-039-R1 Kitchen Equipment Changes (rolled into CO#2) | Merrill Gardens at Ballard, LLC |  | 1107 |  | Executed | Change Orders/COR_s/Ballard MG - Outstanding COR_s.xlsx
| COR-04 | Change Order (COR) | 2016-02-18 | COR-04: CHANGE OUT CAST IRON 90'S (rolled into CO#3) | Merrill Gardens at Ballard, LLC |  | 9302 |  | Executed | Change Orders/COR_s/Ballard MG - Outstanding COR_s.xlsx
| COR-09 | Change Order (COR) | 2016-02-18 | COR-09: Undermount Kitchen & Bar Sinks (rolled into CO#3) | Merrill Gardens at Ballard, LLC |  | 6842 |  | Executed | Change Orders/COR_s/Ballard MG - Outstanding COR_s.xlsx
| COR-01 | Change Order (COR) | 2016-04-20 | COR-01: RFI-074 ADD AUTOWASH BOX (rolled into CO#4) | Merrill Gardens at Ballard, LLC |  | 637 |  | Executed | Change Orders/COR_s/Ballard MG - Outstanding COR_s.xlsx
| COR-03 | Change Order (COR) | 2016-04-20 | COR-03: RFI-122 MOVE KITCHEN STACKS (rolled into CO#4) | Merrill Gardens at Ballard, LLC |  | 2012 |  | Executed | Change Orders/COR_s/Ballard MG - Outstanding COR_s.xlsx
| COR-07 | Change Order (COR) | 2016-04-20 | COR-07: RFI-159 Condenser Rack Drain (rolled into CO#4) | Merrill Gardens at Ballard, LLC |  | 271 |  | Executed | Change Orders/COR_s/Ballard MG - Outstanding COR_s.xlsx
| COR-08 | Change Order (COR) | 2016-04-20 | COR-08: RFI-162 Added Drinking Fountain (rolled into CO#4) | Merrill Gardens at Ballard, LLC |  | 2020 |  | Executed | Change Orders/COR_s/Ballard MG - Outstanding COR_s.xlsx
| COR-10 | Change Order (COR) | 2016-04-20 | COR-10: RFI-175 Added Sink (rolled into CO#4) | Merrill Gardens at Ballard, LLC |  | 933 |  | Executed | Change Orders/COR_s/Ballard MG - Outstanding COR_s.xlsx
| COR-11 | Change Order (COR) | 2016-04-20 | COR-11: Stolen Fittings & Valves (rolled into CO#4) | Merrill Gardens at Ballard, LLC |  | 1772 |  | Executed | Change Orders/COR_s/Ballard MG - Outstanding COR_s.xlsx
| COR-12 | Change Order (COR) | 2016-04-20 | COR-12: ASI-045 Level 7 Suite Revision (rolled into CO#4) | Merrill Gardens at Ballard, LLC |  | 21954 |  | Executed | Change Orders/COR_s/Ballard MG - Outstanding COR_s.xlsx
| COR-Kitchen Vent | Change Order (COR) | 2016-06-24 | COR-Kitchen Vent: Move Vent for Kitchen Exhaust (rolled into CO#6) | Merrill Gardens at Ballard, LLC |  | 517 |  | Executed | Change Orders/COR_s/Ballard MG - Outstanding COR_s.xlsx
| COR-15 | Change Order (COR) | 2016-07-14 | COR-15: Sink Changes (rolled into CO#7) | Merrill Gardens at Ballard, LLC |  | 732 |  | Executed | Change Orders/COR_s/Ballard MG - Outstanding COR_s.xlsx
| COR-14 | Change Order (COR) | 2016-08-19 | COR-14: Attic Stock (rolled into CO#8) | Merrill Gardens at Ballard, LLC |  | 690 |  | Executed | Change Orders/COR_s/Ballard MG - Outstanding COR_s.xlsx
| COR-16 | Change Order (COR) | 2016-08-19 | COR-16: Eyewash Stations (rolled into CO#8) | Merrill Gardens at Ballard, LLC |  | 2045 |  | Executed | Change Orders/COR_s/Ballard MG - Outstanding COR_s.xlsx
| CO-CANCELLED | COR (cancelled) | 2015-12-11 | MGB - COR-06 ASI-039 Kitchen Equipment (superseded by COR-06-R1) | Merrill Gardens at Ballard, LLC |  | 1480 |  | Cancelled | Change Orders/COR_s/Ballard MG - Outstanding COR_s.xlsx
| CO-GAP | CO Reconciliation |  | Documented CORs $54,663 > JDR-implied $48,363 by $6,300; includes WSST net/gross variance & repriced/cancelled items | — |  | 6300 |  | Reconciled (note) | 2024 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages) + Change Orders/COR_s/Ballard MG - Outstanding COR_s.xlsx
| ASI-007 | ASI |  | Package Lockers (Hadley Ballard note: also appears in 2023) | Urbal Architecture (Seattle) |  | 0 |  | Resolved | ASI-RFI/
| ASI-024 | ASI |  | Overtime — Joe Barnhart (gas main relocation) | Urbal Architecture (Seattle) |  | 4232 |  | Resolved | ASI-RFI/ + COR outstanding sheet2
| ASI-039 | ASI |  | Kitchen Equipment Changes (revised to -R1, COR-06-R1) | Urbal Architecture (Seattle) |  | 1107 |  | Resolved | ASI-RFI/ + CO#2
| ASI-045 | ASI |  | Level 7 Suite Revision | Urbal Architecture (Seattle) |  | 21954 |  | Resolved | ASI-RFI/ + CO#4
| RFI-BATCH | RFI batch |  | 52 ASI-RFI PDFs: RFI-051 through RFI-491+ (Urbal Architecture responses) | Urbal Architecture (Seattle)/Sub/GC |  | 0 |  | Resolved | ASI-RFI/
| DROPBOX-RFI | RFI batch |  | Additional RFI docs from field tablets | Sub (OWP) |  | 0 |  | Resolved | DROPBOX FILES FROM TABLETS/
| SUB-EQUIPMENT | Submittal batch |  | Equipment submittals (Backflow preventer Watts LF009/957/SS009, Expansion tank, boilers, pumps) | Sub (OWP) |  | 0 |  | Approved | Submittals/EQUIPMENT SUBMITTALS/
| SUB-FIXTURE | Submittal batch |  | Fixture submittals (WC, lav, tub/shower, sinks, faucets) — original + revised | Sub (OWP) |  | 0 |  | Approved | Submittals/FIXTURE SUBMITTALS/
| SUB-MATERIAL | Submittal batch |  | Material submittals (PVC, cast iron, valves, insulation, trap seals) | Sub (OWP) |  | 0 |  | Approved | Submittals/MATERIAL SUBMITTALS/
| SUB-UG | Submittal batch |  | Underground & Garage submittals (trench drains, pump basins, oil-water separator) | Sub (OWP) |  | 0 |  | Approved | Submittals/UNDERGROUND & GARAGE SUBMITTALS/
| SUB-ALTKS | Submittal batch |  | Alternate Kitchen Sinks submittals (undermount kitchen & bar sinks) | Sub (OWP) |  | 0 |  | Approved | Submittals/ALTERNATE KITCHEN SINKS/
| SUB-SUMP | Submittal batch |  | Sump pumps submittals | Sub (OWP) |  | 0 |  | Approved | Submittals/SUMP PUMPS/
| SUB-RESPONSES | Submittal Responses |  | Returned submittal responses from Architect | Urbal Architecture (Seattle) |  | 0 |  | Logged | Submittals/RESPONSES/
| PERMIT-PLUMBING | Permit | 2016-04-21 | Plumbing permit (MGB ApplicationPlumbingPermit + MGB plumbing permit) | Seattle DPD |  | 0 |  | Issued | Permits/
| PERMIT-PLUMBING-REN | Permit |  | Plumbing permit renewed | Seattle DPD |  | 0 |  | Issued | Permits/
| PERMIT-BACKFLOW | Permit |  | Backflow permit (+ renewal) | Seattle DPD |  | 0 |  | Issued | Permits/
| PERMIT-BOILER | Permit | 2016-04-21 | Boiler permit | WA L&I |  | 0 |  | Issued | Permits/
| PERMIT-GAS | Permit |  | Gas permit | Seattle DPD |  | 0 |  | Issued | Permits/
| PO-COMPLETED | PO batch |  | 102 completed POs (including key Rosen/Keller/Mech Sales/QCP orders) | Sub (OWP) |  | 0 |  | Complete | PO_S/3 Completed/
| PO-SCHEDULED | PO batch |  | 36 scheduled POs | Sub (OWP) |  | 0 |  | Scheduled | PO_S/2 Scheduled/
| PO-TRIM | PO batch (trim) |  | Trim PO_s: toilets (116 WP B872), faucets/lavs, kitchen sinks, attic stock, utility/mop sinks | Sub (OWP) |  | 0 |  | Complete | PO_S/Trim PO_s/
| BILLING-REGISTER | SOV register | 2015-05-19 | MGB AGGREGATE BILLING.xlsx — 16 billings + retainage-release row, 5% retention, 9.6% WSST | Sub (OWP) |  | 0 |  | Closed | MGB AGGREGATE BILLING.xlsx (16 billings + retainage release row, ties to JDR)
| LIEN-WAIVERS | Closeout docs |  | 12+ MGB INTERIM LIEN WAIVER PDFs + FINAL 9-21-16 | Sub (OWP) |  | 0 |  | Delivered | Billing/ + vendor lien waivers/
| WARRANTY-UPONOR | Warranty | 2013-05-25 | 2016 Uponor Warranty 130525.pdf | Uponor |  | 0 |  | Active | Root doc
| WARRANTY-OWP | Warranty |  | OWP Ballard warranty doc.docx | Sub (OWP) |  | 0 |  | Active | Root doc
| STARTUP-ZOELLER | Startup Report |  | Zoeller Startup Report.pdf | Zoeller |  | 0 |  | Complete | Root doc
| OM-TURNOVER | O&M Closeout |  | Operations & Maintenance closeout package | Sub (OWP) |  | 0 |  | Delivered | O&M_s/
| FRANKLIN-ENG | Engineering |  | Franklin Merrill Gardens Ballard engineering package (code 601) | Franklin Engineering |  | 0 |  | Completed | Franklin Merrill Gardens Ballard/
| INSURANCE | Insurance |  | Certificate of Insurance 2016 + Insurance compliance form | OWP |  | 0 |  | Active | Contract/ + Insurance/
| MEETINGS | Meeting log |  | Project meeting notes & schedules | Merrill Gardens at Ballard, LLC |  | 0 |  | Logged | Meetings-Schedules/
| DAMAGED-FIXTURES | Incident log |  | Damaged Fixtures.pdf (scope/remedy tracking) | Sub (OWP) |  | 0 |  | Logged | Root doc
| FIRST-INVOICE | Invoice |  | First billing #036614 | Sub (OWP) |  | 114100 |  | Paid | 2024 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
| LAST-INVOICE | Invoice |  | Last billing #036777 | Sub (OWP) |  | 2735 |  | Paid | 2024 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
| RETAINAGE-OPEN | Retainage |  | Retainage $90,592.15 outstanding 9+ years post-closeout | GC |  | 0 |  | Outstanding | 2024 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)

## Root Cause Analysis
[CORTEX_V2.1] Job #2024 — SRM, Ballard Merrill Gardens · Root Cause Analysis
Schema CORTEX_V2.1 · canonical v2 builder · single source of truth
| rca_id | observation | root_cause | responsibility | cost_impact | mitigation | source
| RCA-01 | Overtime — Joe Barnhart (gas main relocation) | Pending document review — see source document for detail | Architect | 4232 |  | ASI-RFI/ + COR outstanding sheet2
| RCA-02 | Kitchen Equipment Changes (revised to -R1, COR-06-R1) | Pending document review — see source document for detail | Architect | 1107 |  | ASI-RFI/ + CO#2
| RCA-03 | Level 7 Suite Revision | Pending document review — see source document for detail | Architect | 21954 |  | ASI-RFI/ + CO#4

## Predictive Signals
[CORTEX_V2.1] Job #2024 — SRM, Ballard Merrill Gardens · Predictive Signals
Schema CORTEX_V2.1 · canonical v2 builder · single source of truth
| signal_id | signal_name | direction | metric | threshold | historical_outcome | source
| WAREHOUSE | Predictive signals computed at warehouse layer | Neutral | cross-project benchmark | n/a | See benchmark_envelopes view; not stored per-project. | warehouse view (predictive_signals_v)

## Metric Registry
[CORTEX_V2.1] Job #2024 — SRM, Ballard Merrill Gardens · Metric Registry
Schema CORTEX_V2.1 · canonical v2 builder · single source of truth
| metric_key | metric_label | value | data_label | tab_home | verification | source
2024
SRM, Ballard Merrill Gardens
Merrill Gardens at Ballard (senior living)
Merrill Gardens at Ballard, LLC
2024MG
SRM Development Corp / Merrill Gardens (Spokane)
Urbal Architecture (Seattle)
5601 24th Ave NW, Seattle WA 98107
Senior Living Plumbing (116 units)
2015-04-21
2016-08-22
15.1
116
1763480
1932774.08
0.096
1811843
48363
54663
17
8
0.027425
1811843
925434.96
886408.04
0.48923
90592.15
0.05
379757.5
336538.34
12403.9
167598.54
29136.68
17098
40
22.2106
33.717
1.5181
105.9681
51.8428
15619.3362
7977.8876
147.3966
0.2096
0.18574
24
18
52
7
80
138
8
0.10147
0.37355
30

## Reconciliation
[CORTEX_V2.1] Job #2024 — SRM, Ballard Merrill Gardens · Reconciliation
Schema CORTEX_V2.1 · canonical v2 builder · single source of truth
| check_number | check_description | value_a | value_b | difference | status | tabs
| 1 | Revenue (JDR) = Contract Final | 1811843 | 1811843 | 0 | TIES | 1↔8
| 2 | Expenses = Labor+Material+OH+Burden+Tax | 925434.96 | 925434.96 | 0 | TIES | 1↔3
| 3 | Net Profit = Revenue - Expenses | 886408.04 | 886408.04 | 0 | TIES | 1↔Derived
| 4 | JDR Source: AP+PR+GL = Expenses | 925434.96 | 925434.96 | 0 | TIES | 1↔Derived (footer)
| 5 | Budget vs Actual (code 999) = -Revenue | 1811843 | 1811843 | 0 | TIES | 2↔1
| 6 | Total Labor Hours = Worker hours sum | 17098 | 17061 | 37 | WITHIN | 5↔2
| 7 | Labor Cost = Worker gross sum | 379757.5 | 379509 | 248.5 | WITHIN | 5↔3
| 8 | Vendor total ≈ AP footer | 299677.23 | 299677.23 | 0 | TIES | 12↔1 (approximate)
| 9 | Invoice count | 18 | 18 | 0 | TIES | 9↔11
| 10 | Contract Final - Orig = CO implied | 48363 | 48363 | 0 | TIES | 11↔Derived
| 11 | Retainage outstanding | 90592.15 | 90592.15 | 0 | TIES | 9↔JDR footer
| 12 | Retainage sum from invoices | 90592.15 | 90592.15 | 0 | TIES | 9↔JDR footer
| 13 | Aggregate billing Total before retention = Revenue | 1811843 | 1811843 | 0 | TIES | 9↔Billing XLSX
| 14 | Aggregate billing Retention = JDR Retainage | 90592.15 | 90592.15 | 0 | TIES | 9↔Billing XLSX
| 15 | Contract net + WSST = Contract gross | 1932774.08 | 1932774.08 | 0 | TIES | Contract header
| 16 | Worker count | 40 | 40 | 0 | TIES | 5↔11
| 17 | Cost code count | 30 | 30 | 0 | TIES | 2↔16
| 18 | COR documented ≈ CO implied | 54663 | 48363 | 6300 | NEAR | 8↔13
2024.0403
0.16
806
138102036
1515

## Vendors
[CORTEX_V2.1] Job #2024 — SRM, Ballard Merrill Gardens · Vendors
Schema CORTEX_V2.1 · canonical v2 builder · single source of truth
| vendor_id | vendor_name | total_spend | transactions | category | source
| 2024RS | Rosen Supply Company, Inc. $MG-Ballard | 102072.49 | 99 |  | 2024 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
| 2024KS | Keller Supply Company $MG-Ballard | 80438.14 | 90 |  | 2024 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
| 3612MS | Mechanical Sales, Inc. | 37098.89 | 6 |  | 2024 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
| 2024FE | Ferguson Enterprises, Inc. $MG-Ballard | 22824.24 | 29 |  | 2024 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
| 2024CS | Consolidated Supply Co. $MG-Ballard | 21645.04 | 9 |  | 2024 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
| 1609QC | Quality Concrete Products, Inc. $32 | 11655 | 4 |  | 2024 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
| 1234BA | Bank of America CC | 7148 | 9 |  | 2024 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
| 1231KS | Keller Supply Company | 5234.3 | 7 |  | 2024 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
| 1344HD | HD Fowler Company | 3590.93 | 1 |  | 2024 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
| 7200UR | United Rentals, Inc. | 1948.38 | 3 |  | 2024 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
| 3181SC | Scan2Core, Inc. | 1514 | 2 |  | 2024 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
| 1625FE | Franklin Engineering | 1021 | 1 |  | 2024 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
| 8068MI | Kele, Inc $ MI Controls | 847.74 | 1 |  | 2024 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
| 1303CM | C.M. Hoskins Company | 716 | 2 |  | 2024 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
| 1175FE | Ferguson Enterprises, Inc. #3007 | 390.48 | 1 |  | 2024 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
| 1130CS | Consolidated Supply Co. | 348.12 | 3 |  | 2024 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
| 1234CO | Capital One Credit Card | 315.62 | 5 |  | 2024 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
| 5621HD | Core & Main LP | 256 | 1 |  | 2024 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
| 1799AW | AllWest Underground, Inc. | 254.54 | 2 |  | 2024 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
| 1421RA | R.A. Brown Backflow Testing | 197 | 1 |  | 2024 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
| 1380RS | Rosen Supply Kirkland | 123.14 | 2 |  | 2024 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
| 1978FC | Fastenal Company | 36.18 | 1 |  | 2024 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
| 1233AE | American Express 3-41000 | 2 | 1 |  | 2024 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
| 2020RS | Rosen Supply Company | 0 | 2 |  | 2024 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)