## Overview
[CORTEX_V2.1] Job #2025 — Exxel Pacific Cora Apts · Overview
Schema CORTEX_V2.1 · canonical v2 builder · single source of truth
| OVERVIEW |  | SOURCE
IDENTITY
| Project Job Number | 2025 | 2025 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 126 pages) header
| Project Name Sage | Exxel Pacific Cora Apts | 2025 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 126 pages) header
| Project Description | The Cora Apartments — 19 W Harrison St, Seattle | L1 220000 One Way Plumbing Fully Executed Subcontract ocr_d.pdf / AR line descriptions
| Customer Code Sage | 2025EP | 2025 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 126 pages)
CONTRACT & PARTIES
| General Contractor | Exxel Pacific, Inc. | L1 220000 One Way Plumbing Fully Executed Subcontract ocr_d.pdf
| Owner / Developer | 19 W HARRISON LLC | L1 220000 One Way Plumbing Fully Executed Subcontract ocr_d.pdf
| Contract Type | Lump Sum | L1 220000 One Way Plumbing Fully Executed Subcontract ocr_d.pdf
| Contract Document | L1 220000 One Way Plumbing Fully Executed Subcontract ocr_d.pdf | Fully executed subcontract (L1 220000, Lump Sum)
JOB SITE
| Jobsite Location | 19 W Harrison St, Seattle, WA 98109 | L1 220000 One Way Plumbing Fully Executed Subcontract ocr_d.pdf
SCHEDULE
| Work Period | 03/11/2016 – 08/18/2017 (~17 months, per PR/AR dates) | 2025 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 126 pages)
SCOPE & DESIGN
| Fixture Schedule | 19 W Harrison working copy of P-tag list front page detail.xlsx (22 fixture tags WC-1…HB1 + 16 equipment tags + gas loads + connection schedule) | 5-sheet workbook
| Plans / Specifications | 19 W Harrison plumbing narrative.pdf (Div 22 plumbing narrative) + P-tag fixture schedule + proposal drawings | Folder scan
| Bid Proposal | Exxel 19 West Harrison Apartment proposal September 1 2015.pdf | 9/1/2015, detailed fixture quantities and alternates
DOCUMENTATION
| Total Unique Documents Reviewed | 1924 | File inventory across owp-2025/
| CONTRACT VALUE |  | NET PROFIT |  | DIRECT COST |  | LABOR HOURS
| $1,208,338 |  | $462,706 |  | $745,632 |  | 11,774
| Original $-31,000 |  | 38.3% margin |  | 61.7% of revenue |  | 36 workers
COST BREAKDOWN
| Category | Budget | Actual | Variance | % Budget | % of Cost
| Labor | 275655.5 | 287298.5 | -11643 | 104.2% | 38.53%
| Material | 376656.5 | 263607.67 | 113048.83 | 69.99% | 35.35%
| Overhead | 49564.5 | 45446.76 | 4117.74 | 91.69% | 6.095%
| Burden | 140694.79 | 149278.98 | -8584.19 | 106.1% | 20.02%
| TOTAL | 842571.29 | 745631.91 | 96939.38 | 88.49% | 100%
PROJECT PROFILE
| Duration | 03/11/2016 – 08/18/2017 (~17 months, per PR/AR dates)

## Budget vs Actual
[CORTEX_V2.1] Job #2025 — Exxel Pacific Cora Apts · Budget vs Actual
Schema CORTEX_V2.1 · canonical v2 builder · single source of truth
| cost_code | description | original_budget | revised_budget | actual | variance | pct_used | hours | source
| 100 | Supervision | 7875 | 8157 | 4337 |  |  | 95 | 2025 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 126 pages)
| 101 | Takeoff & Purchase Labor | 11250 | 11820 | 11865 |  |  | 255 | 2025 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 126 pages)
| 110 | Underground Labor | 12250 | 13447.5 | 6790.5 |  |  | 211 | 2025 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 126 pages)
| 111 | Garage Labor | 34540 | 35841 | 41214 |  |  | 1617 | 2025 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 126 pages)
| 112 | Canout Labor | 6950 | 6950 | 8821 |  |  | 278.5 | 2025 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 126 pages)
| 120 | Roughin Labor | 125395 | 127266 | 150592 |  |  | 6350 | 2025 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 126 pages)
| 130 | Finish Labor | 24190 | 24692 | 23808 |  |  | 1069 | 2025 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 126 pages)
| 140 | Gas Labor | 5500 | 5986 | 5854 |  |  | 195.5 | 2025 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 126 pages)
| 141 | Water Main/Insulation Lab | 34110 | 34596 | 20707 |  |  | 921 | 2025 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 126 pages)
| 142 | Mech Room Labor | 6900 | 6900 | 13230 |  |  | 494.5 | 2025 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 126 pages)
| 150 | Warranty Labor | 0 | 0 | 80 |  |  | 2 | 2025 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 126 pages)
| 210 | Underground Material | 23000 | 27199 | 12323.48 |  |  |  | 2025 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 126 pages)
| 211 | Garage Material | 27270 | 28626 | 19383.8 |  |  |  | 2025 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 126 pages)
| 212 | Canout Material | 7780 | 7780 | 4759.86 |  |  |  | 2025 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 126 pages)
| 220 | Roughin Material | 76655 | 77101 | 58515.95 |  |  |  | 2025 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 126 pages)
| 230 | Finish Material | 105200 | 104606.5 | 110946.04 |  |  |  | 2025 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 126 pages)
| 240 | Gas Material | 5500 | 6088 | 1507.91 |  |  |  | 2025 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 126 pages)
| 241 | Water Main/Insulation Mat | 42330 | 42330 | 19584.74 |  |  |  | 2025 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 126 pages)
| 242 | Mech Room Material | 82200 | 82926 | 36585.89 |  |  |  | 2025 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 126 pages)
| 600 | Subcontractor | 2000 | 2594.5 | 4506.25 |  |  |  | 2025 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 126 pages)
| 601 | Engineering/Plans | 30000 | 30000 | 27969.5 |  |  |  | 2025 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 126 pages)
| 602 | Rental Equipment | 5000 | 5000 | 1302.4 |  |  |  | 2025 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 126 pages)
| 603 | Permits & Licenses | 6830 | 6970 | 5334 |  |  |  | 2025 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 126 pages)
| 607 | Other Expenses | 10000 | 10000 | 7637.01 |  |  |  | 2025 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 126 pages)
| 995 | Payroll Burden | 116594.16 | 119607.14 | 127300.38 |  |  |  | 2025 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 126 pages)
| 998 | Payroll Taxes | 20575.44 | 21087.65 | 21978.6 |  |  |  | 2025 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 126 pages)
| 999 | Sales | -1179300 | -1208338 | -1208338 |  |  |  | 2025 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 126 pages)
| TOTAL |  | -349405.4 | -360766.71 | -461403.69 | 0 |  | 11488.5

## Cost Breakdown
[CORTEX_V2.1] Job #2025 — Exxel Pacific Cora Apts · Cost Breakdown
Schema CORTEX_V2.1 · canonical v2 builder · single source of truth
| category | cost_codes | actual | pct_of_direct_cost | pct_of_revenue | per_unit | source
| Labor | 100,101,110,111,112,120,130,140,141,142 | 287218.5 |  |  |  | 2025 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 126 pages)
| Material | 210,211,212,220,230,240,241,242 | 263607.67 |  |  |  | 2025 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 126 pages)
| Subcontractor + Engineering + Permits + Other | 600,601,602,603,607 | 46749.16 |  |  |  | 2025 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 126 pages)
| Payroll Burden | 995 | 127300.38 |  |  |  | 2025 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 126 pages)
| Payroll Taxes | 998 | 21978.6 |  |  |  | 2025 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 126 pages)
| TOTAL DIRECT COST |  |  | 100%
| TOTAL |  | 746854.31 |  |  | 0

## Material
[CORTEX_V2.1] Job #2025 — Exxel Pacific Cora Apts · Material
Schema CORTEX_V2.1 · canonical v2 builder · single source of truth
| vendor_id | vendor_name | total_spend | transactions | category | source
| 2025KS | Keller Supply Company | 78491.13 | 57 | Plumbing / Supplies | 2025 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 126 pages)
| 2025RS | Rosen Supply Company, Inc. | 69093.77 | 70 | Plumbing / Supplies | 2025 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 126 pages)
| 2025CS | Consolidated Supply Co. | 63856.09 | 42 | Plumbing / Supplies | 2025 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 126 pages)
| 1625FE | Franklin Engineering | 27969.5 | 9 | Engineering (601) | 2025 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 126 pages)
| 3612MS | Mechanical Sales, Inc. | 19566.99 | 4 | Plumbing / Supplies | 2025 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 126 pages)
| 1609QC | Quality Concrete Products, Inc. $32 | 6513 | 2 | Uncategorized | 2025 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 126 pages)
| 1234CO | Capital One Credit Card | 4616.5 | 42 | Credit Card (mixed) | 2025 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 126 pages)
| 1234BA | Bank of America CC | 4562 | 4 | Credit Card (mixed) | 2025 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 126 pages)
| 1234CI | Citibank Credit Card | 3238 | 10 | Credit Card (mixed) | 2025 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 126 pages)
| 2025FE | Ferguson Enterprises, Inc. | 2587.09 | 8 | Plumbing / Supplies | 2025 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 126 pages)
| 5919PW | Patchworks, Inc. | 2156.25 | 2 | Uncategorized | 2025 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 126 pages)
| 3181SC | Scan2Core, Inc. | 1800 | 3 | Uncategorized | 2025 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 126 pages)
| 7200UR | United Rentals, Inc. | 1103.34 | 2 | Uncategorized | 2025 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 126 pages)
| 5621HD | Core & Main LP | 780 | 2 | Plumbing / Supplies | 2025 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 126 pages)
| 8068MI | Kele, Inc $ MI Controls | 408.52 | 1 | Uncategorized | 2025 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 126 pages)
| 4320MC | MAD Concrete Cutting & Coring, Inc. | 350 | 1 | Uncategorized | 2025 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 126 pages)
| 2132MH | Manor Hardware & Construction Supply | 305.76 | 1 | Plumbing / Supplies | 2025 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 126 pages)
| 2028KS | Keller Supply Company $Reserve@Lynnwood | 225.92 | 1 | Plumbing / Supplies | 2025 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 126 pages)
| 1421RA | R.A. Brown Backflow Testing | 200 | 1 | Testing subcontractor | 2025 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 126 pages)
| 1799AW | AllWest Underground, Inc. | 199.06 | 1 | Uncategorized | 2025 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 126 pages)
| 1231KS | Keller Supply Company | 82.5 | 1 | Plumbing / Supplies | 2025 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 126 pages)
| 1380RS | Rosen Supply Kirkland | 63.66 | 1 | Plumbing / Supplies | 2025 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 126 pages)
| 1978FC | Fastenal Company | 49.7 | 1 | Uncategorized | 2025 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 126 pages)
| 1175FE | Ferguson Enterprises, Inc. #3007 | -878.44 | 7 | Plumbing / Supplies | 2025 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 126 pages)
| 2027FE | Ferguson Enterprises, Inc. $550 Broadway | -15447.08 | 1 | Plumbing / Supplies | 2025 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 126 pages)
NOTE: AP total per JDR footer = $271,893.26. Vendor sum above approximates this. Submittals folder (Submittals/) contains 19 fixture + 10 material + 1 UG submittal documenting approved products. POs folder shows 82 POs (7 placed, 19 scheduled, 56 completed).

## Crew & Labor
[CORTEX_V2.1] Job #2025 — Exxel Pacific Cora Apts · Crew & Labor
Schema CORTEX_V2.1 · canonical v2 builder · single source of truth
| worker_id | worker_name | total_hours | gross_pay | blended_wage_per_hr | tier | work_days | source
| MC09 | McCabe, Thomas C | 1103.5 | 29285 |  |  | 36 | 2025 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 126 pages)
| WA35 | Waites, Thaddeus Z | 1098 | 41340 |  |  | 37 | 2025 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 126 pages)
| EL33 | Eliassen, Cory H | 984 | 16432 |  |  | 29 | 2025 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 126 pages)
| SA54 | Sanders, Allen O | 810 | 31580 |  |  | 31 | 2025 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 126 pages)
| CA77 | Castro Hernandez, Jose A | 805 | 18143 |  |  | 21 | 2025 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 126 pages)
| HE70 | Hernandez Gonzalez, Osbaldo | 797 | 11158 |  |  | 21 | 2025 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 126 pages)
| TA96 | Taylor, Evan R | 685 | 12045 |  |  | 20 | 2025 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 126 pages)
| RO12 | Rodriguez Rodriguez, Aminadab N | 540 | 10844 |  |  | 15 | 2025 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 126 pages)
| RO75 | Ross, Kelli M | 488 | 17336 |  |  | 14 | 2025 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 126 pages)
| GO56 | Gonzalez Hernandez, Josue | 472 | 10680 |  |  | 14 | 2025 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 126 pages)
| LI49 | Lima Romero, Melvin A | 410 | 11224 |  |  | 12 | 2025 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 126 pages)
| CR87 | Cruz Reyes, Jose | 360 | 6512 |  |  | 11 | 2025 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 126 pages)
| RE96 | Reyes Cruz, Denis A | 352 | 6720 |  |  | 11 | 2025 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 126 pages)
| CR79 | Cruz Guzman, Joel A | 344 | 5880 |  |  | 11 | 2025 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 126 pages)
| JO31 | Johnson, Samuel A | 312.5 | 5000 |  |  | 10 | 2025 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 126 pages)
| GO51 | Gomez Reyes, Edith N | 245 | 3675 |  |  | 7 | 2025 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 126 pages)
| BE54 | Benites Portillo, Marvin E | 240 | 4336 |  |  | 11 | 2025 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 126 pages)
| SA51 | Sanchez, Derli | 216 | 3240 |  |  | 7 | 2025 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 126 pages)
| GE69 | Gerard, Jeffrey S | 192 | 8679 |  |  | 55 | 2025 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 126 pages)
| AY19 | Ayers, Jordan L | 159.5 | 1431 |  |  | 3 | 2025 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 126 pages)
| DO56 | Donelson, Richard T | 158 | 7523 |  |  | 58 | 2025 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 126 pages)
| GA46 | Galdamez, Dagoberto A | 144 | 1840 |  |  | 9 | 2025 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 126 pages)
| BR59 | Brown, Steven D | 136 | 896 |  |  | 2 | 2025 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 126 pages)
| PA11 | Paco Leyva, Orlando | 104 | 2720 |  |  | 4 | 2025 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 126 pages)
| RE18 | Reed, Reuben H | 95.5 | 3342.5 |  |  | 4 | 2025 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 126 pages)
| CO71 | Cortes Mendiola, Victor H | 88 | 3096 |  |  | 4 | 2025 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 126 pages)
| MO56 | Montenegro, Carlos E | 88 | 2096 |  |  | 6 | 2025 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 126 pages)
| BA70 | Barnhart, Joseph N | 79.5 | 3196 |  |  | 24 | 2025 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 126 pages)
| HU06 | Hubbard, Robert W | 66 | 2755.5 |  |  | 16 | 2025 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 126 pages)
| RI87 | Rivera, Jorge A | 56 | 1568 |  |  | 2 | 2025 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 126 pages)
| CO69 | Cornejo Orellana, Carlos E | 48 | 720 |  |  | 3 | 2025 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 126 pages)
| GA70 | Garcia, Jordan X | 43 | 1032 |  |  | 4 | 2025 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 126 pages)
| HU04 | Hubbard, Dustin R | 22 | 398 |  |  | 6 | 2025 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 126 pages)
| PO71 | Portillo, Kevin J | 16 | 240 |  |  | 1 | 2025 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 126 pages)
| HO14 | Holmes, Anthony R | 8 | 160 |  |  | 1 | 2025 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 126 pages)
| LO58 | Lopez Reyes, Boris O | 8 | 120 |  |  | 1 | 2025 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 126 pages)

## Crew Analytics
[CORTEX_V2.1] Job #2025 — Exxel Pacific Cora Apts · Crew Analytics
Schema CORTEX_V2.1 · canonical v2 builder · single source of truth
| tier | worker_count | hours | gross_pay | pct_of_hours | blended_wage

## Productivity
[CORTEX_V2.1] Job #2025 — Exxel Pacific Cora Apts · Productivity
Schema CORTEX_V2.1 · canonical v2 builder · single source of truth
| phase | labor_code | hours | pct_of_total | hours_per_unit

## PO Commitments
[CORTEX_V2.1] Job #2025 — Exxel Pacific Cora Apts · PO Commitments
Schema CORTEX_V2.1 · canonical v2 builder · single source of truth
| po_number | date | issuer | type | status | description | amount | source
| L1 220000 | 2015-09 (proposal 9/1/15) / subcontract executed | Exxel Pacific, Inc. | Lump Sum Subcontract | Closed (100% billed) | The Cora Apts plumbing (19 W Harrison, Seattle) — full scope per proposal + narrative | 1179300 | L1 220000 One Way Plumbing Fully Executed Subcontract ocr_d.pdf
| CO#01 | NOT FOUND | Exxel Pacific, Inc. | Change Order | Executed | Documented change order (budget transfer / credit) | 700 | Change Orders/CO_s/CO#01 (budget transfer)
| CO#02 | NOT FOUND | Exxel Pacific, Inc. | Change Order | Executed | Documented change order (budget transfer / credit) | 4390 | Change Orders/CO_s/CO#02 (budget transfer)
| CO#03 | NOT FOUND | Exxel Pacific, Inc. | Change Order | Executed | Documented change order (budget transfer / credit) | 7881 | Change Orders/CO_s/CO#03 (budget transfer)
| CO#04 | NOT FOUND | Exxel Pacific, Inc. | Change Order | Executed | Documented change order (budget transfer / credit) | 9017 | Change Orders/CO_s/CO#04 (budget transfer)
| CO#05 | NOT FOUND | Exxel Pacific, Inc. | Change Order | Executed | Documented change order (budget transfer / credit) | -1971 | Change Orders/CO_s/CO#05 (credit)
| CO#06 | NOT FOUND | Exxel Pacific, Inc. | Change Order | Executed | Documented change order (budget transfer / credit) | 3316 | Change Orders/CO_s/CO#06 (budget transfer)
TOTAL (contract + COs)
NOTE: Documented COs sum to $23,333.00; JDR-implied COs = $29,038.00 (diff $5,705.00). Gap likely due to budget-transfer-only adjustments or one CO not surfacing in transfer PDFs. Outbound POs: 82 total (7 placed, 19 scheduled, 56 completed) — see POs/ folder.

## Billing & SOV
[CORTEX_V2.1] Job #2025 — Exxel Pacific Cora Apts · Billing & SOV
Schema CORTEX_V2.1 · canonical v2 builder · single source of truth
| pay_app_number | date | contract_total | this_period | retainage | stored_materials | cumulative | pct_complete | source
| 036686 | 02/24/16 | -31000 |  | -1550 |  |  | 100% | 2025 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 126 pages)
| 036738 | 06/17/16 | -43900 |  | -2195 |  |  | 100% | 2025 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 126 pages)
| 036761 | 07/20/16 | -20000 |  | -1000 |  |  | 100% | 2025 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 126 pages)
| 036772 | 08/19/16 | -12000 |  | -600 |  |  | 100% | 2025 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 126 pages)
| 036786 | 09/19/16 | -29850 |  | -1492.5 |  |  | 100% | 2025 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 126 pages)
| 036792 | 10/19/16 | -19950 |  | -997.5 |  |  | 100% | 2025 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 126 pages)
| 036802 | 11/15/16 | -54500 |  | -2725 |  |  | 100% | 2025 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 126 pages)
| 036814 | 12/16/16 | -424100 |  | -21205 |  |  | 100% | 2025 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 126 pages)
| 036818 | 01/20/17 | -275875 |  | -13793.75 |  |  | 100% | 2025 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 126 pages)
| 036830 | 02/20/17 | -107775 |  | -5388.75 |  |  | 100% | 2025 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 126 pages)
| 036844 | 03/17/17 | -32925 |  | -1646.25 |  |  | 100% | 2025 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 126 pages)
| 036866 | 04/21/17 | -79869 |  | -3993.45 |  |  | 100% | 2025 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 126 pages)
| 036875 | 05/19/17 | -52282 |  | -2614.1 |  |  | 100% | 2025 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 126 pages)
| 036894 | 06/19/17 | -15291 |  | -764.55 |  |  | 100% | 2025 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 126 pages)
| 036907 | 06/19/17 | 15291 |  | 764.55 |  |  | 100% | 2025 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 126 pages)
| 036908 | 06/19/17 | -13791 |  | -689.55 |  |  | 100% | 2025 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 126 pages)
| 036917 | 07/20/17 | -5705 |  | -285.25 |  |  | 100% | 2025 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 126 pages)
| 036921 | 07/20/17 | -1500 |  | -75 |  |  | 100% | 2025 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 126 pages)
| 036937 | 08/18/17 | -3316 |  | -165.8 |  |  | 100% | 2025 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 126 pages)
TOTAL (signed)
NOTE: AR entries signed negative per Sage convention. Net billed = $1,208,338.00; retainage $60,416.90 outstanding on JDR dated 04/03/2026. First invoice 036686 (2/19/16); last invoice 036937 (8/18/17). Billing/billing docs/ contains SOV template. Invoice 036907 (6/19/17) reverses 036894.

## Insights
[CORTEX_V2.1] Job #2025 — Exxel Pacific Cora Apts · Insights
Schema CORTEX_V2.1 · canonical v2 builder · single source of truth
| insight_id | title | finding | verified | source
Verified
Medium
Verified
Verified
Verified
Verified
Verified

## Benchmark KPIs
[CORTEX_V2.1] Job #2025 — Exxel Pacific Cora Apts · Benchmark KPIs
Schema CORTEX_V2.1 · canonical v2 builder · single source of truth
CROSS-PROJECT BENCHMARK SCORECARD
Normalized metrics designed for apples-to-apples comparison across all OWP projects.
| KPI | DATA NAME | VALUE | CATEGORY | NOTES / BENCHMARK CONTEXT
| Job Number | job_number | 2,025 | Profile | OWP Sage job ID
| General Contractor | general_contractor | Exxel Pacific, Inc. | Profile | Customer of record
| location | location | 19 W Harrison St, Seattle, WA 98109 | Profile | Project address
| Project Type | project_type | Commercial | Profile | Building category for benchmarking
| Duration Months | duration_months | 17.0% | Profile | Calendar months from start to close
| Contract Original | contract_original | $-31,000 | Financial | Original contract value
| Contract Final | contract_final | $1,208,338 | Financial | Revised contract value (post-COs)
| Change Orders Net | change_orders_net | 1,239,338 | Financial | Net dollar change from COs
| revenue | revenue | $1,208,338 | Financial | Net billed (AR net of reversals)
| Net Profit | net_profit | $462,706 | Financial | Revenue − direct cost
| Gross Margin Pct | gross_margin_pct | 38.3% | Financial | Net profit / revenue
| Direct Cost | direct_cost | $745,632 | Financial | Σ labor + material + OH + burden + tax
| Overhead Cost | overhead_cost | $45,447 | Financial | Codes 600, 601, 603, 607
| Burden Cost | burden_cost | $127,300 | Financial | Code 995 payroll burden
| Retainage Outstanding | retainage_outstanding | $0.00 | Financial | Held by GC until closeout
| Labor Cost | labor_cost | $287,298 | Labor | Codes 100–150
| Total Hours | total_hours | 11,773.50 | Labor | All payroll hours on the job
| Total Workers | total_workers | 36 | Crew | Unique payroll IDs across job
| Blended Wage | blended_wage | $24.40 | Labor | Pre-burden average
| Fully Loaded Wage | fully_loaded_wage | $37.08 | Labor | Post-burden true cost
| Burden Multiplier | burden_multiplier | 1.52 | Labor | Loaded / gross
| Labor Pct Revenue | labor_pct_revenue | 0.24 | Cost Mix | Payroll exposure
| Material Cost | material_cost | $263,608 | Material | Codes 210–244
| Material Pct Revenue | material_pct_revenue | 0.22 | Cost Mix | Material/sub exposure
| Total Vendors | total_vendors | 25 | Material | Distinct AP vendors invoiced on the job
| Top Vendor Spend | top_vendor_spend | $78,491 | Material | Largest single supplier
| Top Vendor Pct | top_vendor_pct | 29.8% | Material | Top vendor concentration
| Revenue Per Hour | revenue_per_hour | $105 | Labor | Productivity ceiling
| Profit Per Hour | profit_per_hour | $40.28 | Labor | Margin per hour worked
| Revenue Per Month | revenue_per_month | $71,079 | Throughput | Billing velocity
| Hours Per Month | hours_per_month | $676 | Throughput | Avg monthly labor burn
| Units Per Month | units_per_month | $0.00 | Throughput | Build pace
SOURCES
Canonical: /sessions/keen-determined-mccarthy/mnt/cortex-mockup/owp/cortex v2 files/OWP_2025_JCR_Cortex_v2.xlsx
revenue: AR net-of-reversals (validator)
labor_cost: Codes 100–150
material_cost: Codes 210–244
total_workers: count(distinct worker_id)

## Change Log
[CORTEX_V2.1] Job #2025 — Exxel Pacific Cora Apts · Change Log
Schema CORTEX_V2.1 · canonical v2 builder · single source of truth
| event_id | type | date | subject | originator | linked_events | cost_impact | schedule_days | status | source_document
| CONTRACT-ORIG | Contract |  | Prime subcontract — Lump Sum $1,179,300.00 | Exxel Pacific, Inc. |  | 1179300 |  | Executed | L1 220000 One Way Plumbing Fully Executed Subcontract ocr_d.pdf
| CO#01 | Change Order |  | Change Order #1 — budget transfer | Exxel Pacific, Inc. |  | 700 |  | Executed | CO_s/CO#01
| CO#02 | Change Order |  | Change Order #2 — budget transfer | Exxel Pacific, Inc. |  | 4390 |  | Executed | CO_s/CO#02
| CO#03 | Change Order |  | Change Order #3 — budget transfer | Exxel Pacific, Inc. |  | 7881 |  | Executed | CO_s/CO#03
| CO#04 | Change Order |  | Change Order #4 — budget transfer | Exxel Pacific, Inc. |  | 9017 |  | Executed | CO_s/CO#04
| CO#05 | Change Order |  | Change Order #5 — credit | Exxel Pacific, Inc. |  | -1971 |  | Executed | CO_s/CO#05
| CO#06 | Change Order |  | Change Order #6 — budget transfer | Exxel Pacific, Inc. |  | 3316 |  | Executed | CO_s/CO#06
| CO-GAP | Implied CO gap |  | Budget-delta vs documented COs = $5,705.00 (unreconciled) | — |  | 5705 |  | Unreconciled | 2025 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 126 pages)
| RFI-PRIMARY | RFI batch |  | 18 RFIs + 1 ASI (primary ASI-RFI folder) | Sub (OWP) / GC |  | 0 |  | Resolved | ASI-RFI/
| RFI-DROPBOX | RFI batch |  | 12 additional RFIs from field tablets | Sub (OWP) |  | 0 |  | Resolved | DROPBOX FILES FROM GUYS TABLETS/ASI-RFI/RFI_s/
| SUB-FIXTURE | Submittal batch |  | 19 fixture submittals (WC, lav, tub/shower, sinks, etc.) | Sub (OWP) |  | 0 |  | Approved | Submittals/Fixtures/
| SUB-MATERIAL | Submittal batch |  | 10 material submittals (pipe, valves, insulation, etc.) | Sub (OWP) |  | 0 |  | Approved | Submittals/Material/
| SUB-UG | Submittal |  | UG/garage submittal | Sub (OWP) |  | 0 |  | Approved | Submittals/UG/
| PERMIT-PLUMBING | Permit |  | Plumbing permit | Jurisdiction (Seattle) |  | 0 |  | Issued | Permits/
| PERMIT-BACKFLOW | Permit |  | Backflow permit | Jurisdiction (Seattle) |  | 0 |  | Issued | Permits/
| PERMIT-BOILER-1 | Permit |  | Boiler permit (1 of 2) | Jurisdiction (Seattle) |  | 0 |  | Issued | Permits/
| PERMIT-BOILER-2 | Permit |  | Boiler permit (2 of 2) | Jurisdiction (Seattle) |  | 0 |  | Issued | Permits/
| PERMIT-GAS | Permit |  | Gas permit | Jurisdiction (Seattle) |  | 0 |  | Issued | Permits/
| PERMIT-TEMPGAS | Permit |  | Temporary gas permit | Jurisdiction (Seattle) |  | 0 |  | Issued | Permits/
| PO-COMPLETED | PO batch |  | 56 completed POs | Sub (OWP) |  | 0 |  | Complete | POs/Completed/
| PO-PLACED | PO batch |  | 7 placed POs | Sub (OWP) |  | 0 |  | Placed | POs/Placed/
| PO-SCHEDULED | PO batch |  | 19 scheduled POs | Sub (OWP) |  | 0 |  | Scheduled | POs/Scheduled/
| FIRST-INVOICE | Invoice |  | First billing #036686 ($31,000) | Sub (OWP) |  | 31000 |  | Paid | 2025 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 126 pages)
| LAST-INVOICE | Invoice |  | Last billing #036937 ($3,316 — closeout/punchlist) | Sub (OWP) |  | 3316 |  | Paid | 2025 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 126 pages)
| RETAINAGE-OPEN | Retainage |  | Retainage $60,416.90 outstanding 8+ years post-closeout | GC |  | 0 |  | Outstanding | 2025 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 126 pages)

## Root Cause Analysis
[CORTEX_V2.1] Job #2025 — Exxel Pacific Cora Apts · Root Cause Analysis
Schema CORTEX_V2.1 · canonical v2 builder · single source of truth
| rca_id | observation | root_cause | responsibility | cost_impact | mitigation | source
| RCA-01 | Change Order #1 — budget transfer | Pending document review — see source document for detail | GC | 700 |  | CO_s/CO#01
| RCA-02 | Change Order #2 — budget transfer | Pending document review — see source document for detail | GC | 4390 |  | CO_s/CO#02
| RCA-03 | Change Order #3 — budget transfer | Pending document review — see source document for detail | GC | 7881 |  | CO_s/CO#03
| RCA-04 | Change Order #4 — budget transfer | Pending document review — see source document for detail | GC | 9017 |  | CO_s/CO#04
| RCA-05 | Change Order #5 — credit | Pending document review — see source document for detail | GC | -1971 |  | CO_s/CO#05
| RCA-06 | Change Order #6 — budget transfer | Pending document review — see source document for detail | GC | 3316 |  | CO_s/CO#06

## Predictive Signals
[CORTEX_V2.1] Job #2025 — Exxel Pacific Cora Apts · Predictive Signals
Schema CORTEX_V2.1 · canonical v2 builder · single source of truth
| signal_id | signal_name | direction | metric | threshold | historical_outcome | source
| WAREHOUSE | Predictive signals computed at warehouse layer | Neutral | cross-project benchmark | n/a | See benchmark_envelopes view; not stored per-project. | warehouse view (predictive_signals_v)

## Metric Registry
[CORTEX_V2.1] Job #2025 — Exxel Pacific Cora Apts · Metric Registry
Schema CORTEX_V2.1 · canonical v2 builder · single source of truth
| metric_key | metric_label | value | data_label | tab_home | verification | source
2025
Exxel Pacific Cora Apts
The Cora Apts @ 19 W Harrison
Exxel Pacific, Inc.
2025EP
19 W HARRISON LLC
19 W Harrison St, Seattle WA 98109
Multifamily Plumbing (New Construction)
2016-03-11
2017-08-18
17.3
92
9
94
94
92
76
1179300
1208338
29038
23333
6
0.024623
1208338
746934.31
461403.69
0.38185
60416.9
0.05
287218.5
263607.67
46749.16
127300.38
21978.6
11486.5
36
25.0049
38.0009
1.5197
105.1964
40.1692
13134.1087
8118.8512
124.8533
0.2377
0.21816
25
19
30
1
30
6
82
0.096069
0.41793
27

## Reconciliation
[CORTEX_V2.1] Job #2025 — Exxel Pacific Cora Apts · Reconciliation
Schema CORTEX_V2.1 · canonical v2 builder · single source of truth
| check_number | check_description | value_a | value_b | difference | status | tabs
| 1 | Revenue (JDR) = Contract Final | 1208338 | 1208338 |  |  | 1↔8
| 2 | Expenses = Labor+Material+OH+Burden+Tax | 746934.31 | 746854.31 |  |  | 1↔3
| 3 | Net Profit = Revenue - Expenses | 461403.69 | 461403.69 |  |  | 1↔Derived
| 4 | JDR Source: AP+PR+GL = Expenses | 746934.31 | 746934.31 |  |  | 1↔Derived (footer)
| 5 | Budget vs Actual (code 999) = -Revenue | 1208338 | 1208338 |  |  | 2↔1
| 6 | Total Labor Hours = Worker hours sum | 11486.5 | 11773.5 |  |  | 5↔2
| 7 | Labor Cost = Worker gross sum | 287218.5 | 287243 |  |  | 5↔3
| 8 | Vendor total ≈ AP footer | 271893.26 | 271893.26 |  |  | 12↔1 (approximate)
| 9 | Invoice count | 19 | 19 |  |  | 9↔11
| 10 | Contract Final - Orig = CO implied | 29038 | 29038 |  |  | 11↔Derived
| 11 | CO implied vs documented (gap) | 29038 | 23333 |  |  | 8↔13
| 12 | Retainage outstanding | 60416.9 | 60416.9 |  |  | 9↔JDR footer
| 13 | Worker count | 36 | 36 |  |  | 5↔11
| 14 | Cost code count | 27 | 27 |  |  | 2↔16
2025.0403
1912015.92
3018112
3019101
62
8271956
15

## Vendors
[CORTEX_V2.1] Job #2025 — Exxel Pacific Cora Apts · Vendors
Schema CORTEX_V2.1 · canonical v2 builder · single source of truth
| vendor_id | vendor_name | total_spend | transactions | category | source
| 2025KS | Keller Supply Company | 78491.13 | 57 |  | 2025 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 126 pages)
| 2025RS | Rosen Supply Company, Inc. | 69093.77 | 70 |  | 2025 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 126 pages)
| 2025CS | Consolidated Supply Co. | 63856.09 | 42 |  | 2025 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 126 pages)
| 1625FE | Franklin Engineering | 27969.5 | 9 |  | 2025 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 126 pages)
| 3612MS | Mechanical Sales, Inc. | 19566.99 | 4 |  | 2025 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 126 pages)
| 1609QC | Quality Concrete Products, Inc. $32 | 6513 | 2 |  | 2025 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 126 pages)
| 1234CO | Capital One Credit Card | 4616.5 | 42 |  | 2025 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 126 pages)
| 1234BA | Bank of America CC | 4562 | 4 |  | 2025 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 126 pages)
| 1234CI | Citibank Credit Card | 3238 | 10 |  | 2025 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 126 pages)
| 2025FE | Ferguson Enterprises, Inc. | 2587.09 | 8 |  | 2025 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 126 pages)
| 5919PW | Patchworks, Inc. | 2156.25 | 2 |  | 2025 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 126 pages)
| 3181SC | Scan2Core, Inc. | 1800 | 3 |  | 2025 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 126 pages)
| 7200UR | United Rentals, Inc. | 1103.34 | 2 |  | 2025 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 126 pages)
| 5621HD | Core & Main LP | 780 | 2 |  | 2025 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 126 pages)
| 8068MI | Kele, Inc $ MI Controls | 408.52 | 1 |  | 2025 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 126 pages)
| 4320MC | MAD Concrete Cutting & Coring, Inc. | 350 | 1 |  | 2025 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 126 pages)
| 2132MH | Manor Hardware & Construction Supply | 305.76 | 1 |  | 2025 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 126 pages)
| 2028KS | Keller Supply Company $Reserve@Lynnwood | 225.92 | 1 |  | 2025 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 126 pages)
| 1421RA | R.A. Brown Backflow Testing | 200 | 1 |  | 2025 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 126 pages)
| 1799AW | AllWest Underground, Inc. | 199.06 | 1 |  | 2025 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 126 pages)
| 1231KS | Keller Supply Company | 82.5 | 1 |  | 2025 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 126 pages)
| 1380RS | Rosen Supply Kirkland | 63.66 | 1 |  | 2025 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 126 pages)
| 1978FC | Fastenal Company | 49.7 | 1 |  | 2025 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 126 pages)
| 1175FE | Ferguson Enterprises, Inc. #3007 | -878.44 | 7 |  | 2025 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 126 pages)
| 2027FE | Ferguson Enterprises, Inc. $550 Broadway | -15447.08 | 1 |  | 2025 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 126 pages)