## Overview
[CORTEX_V2.1] Job #2026 — Synergy 525 Boren · Overview
Schema CORTEX_V2.1 · canonical v2 builder · single source of truth
| OVERVIEW |  | SOURCE
IDENTITY
| Project Job Number | 2026 | 2026 Job Detail Report.pdf (Sage Timberline export, printed 04/03/2026 1:51PM, 106 pages) header
| Project Name Sage | Synergy 525 Boren | 2026 Job Detail Report.pdf (Sage Timberline export, printed 04/03/2026 1:51PM, 106 pages) header
| Project Description | Fox and Finch Apartments — 525 Boren Midrise Apartment / Mixed Use, 525 Boren Avenue North, Seattle WA 98109 | Contract/525 Boren Contract.pdf header
| Customer Code Sage | 2026SC | 2026 Job Detail Report.pdf (Sage Timberline export, printed 04/03/2026 1:51PM, 106 pages)
CONTRACT & PARTIES
| General Contractor | Synergy Construction, Inc. (14040 NE 181st St, Woodinville WA 98072) | Contract/525 Boren Contract.pdf
| Contract Type | Lump Sum subcontract per AGC Washington 2006 GC template | Contract/525 Boren Contract.pdf
| Contract Document | Subcontract #007 — Lump Sum $825,370.00 (AGC of Washington 2006 Ed.) + 8% retainage clause | Contract/525 Boren Contract.pdf
| Synergy Project Reference | Synergy project #750 · Subcontract #007 · cost code 15400 | Contract/525 Boren Contract.pdf
JOB SITE
| Jobsite Location | 525 Boren Ave N, Seattle, WA 98109 · Parcel 1983200345 | Permits/Boren Gas permit.pdf
| Unit Count | 60 residential units (inferred from 60 TOTO C744E bowls + 60 ST743E tanks) | Vendor Quotes/BOREN - Vender Quote Spreadsheet.xlsx
| Building Profile | 7-story midrise apartment (L1-L7 + rooftop mech room + basement) per SOV — mixed-use with L1 retail + dog wash + leasing office | Billing/525 Boren SOV template with contract value.xlsx
SCHEDULE
| Work Period | 03/09/2016 – 07/24/2017 (~16.5 months, per payroll/AR dates) | 2026 Job Detail Report.pdf (Sage Timberline export, printed 04/03/2026 1:51PM, 106 pages)
SCOPE & DESIGN
| Fixture Inventory | 669 fixture-line units across 20 SKUs — 60 toilets (56 TOTO C744E + 4 C744EL ADA) · 60 china lavs (TOTO LT231) · 60 Grohe lav faucets · 51 kitchen faucets · 59 shower valve trims · 17 tub spouts · 59 Aquatic tub/shower units (32×1483EN + 17×2603SMTE + 10×1423C) · 3 Moen ADA hand-shower kits · 1 Mustee dog wash + 1 Kohler grid drain. Submittals on file: 12 fixture PDFs + 8 tub/shower PDFs. | Vendor Quotes/BOREN - Vender Quote Spreadsheet.xlsx · Submittals/FIXTURE SUBMITTALS/ · Submittals/TUB & SHOWER SUBMITTALS/
| Plans / Specifications | Full plumbing construction set (525-Plumbing Construction Set PR.pdf) + 11 MEP DWGs (basement, L1-L7, Roof) in Brett 525 Boren/; MEP Superplots 2016-02/02/03 | Folder scan — Brett 525 Boren/
| Submittals | 44 submittals across 7 categories (Equipment-7, Fixtures-12, Material-5, Responses-1, Sleeving Plans-1, Tub/Shower-8, Underground/Garage-10) | Submittals/ subfolder scan
| Permits | 5 permits (Plumbing, Gas, Gas Temp Heat, Backflow, Renewed Plumbing+Gas+Backflow). Gas permit SR1397520 to 525 Boren LLC. | Permits/
CHANGE EVENTS
| Change Orders (on file) | 2 CORs (COR#01 Temp Gas $357 executed as CO, COR#02 Unclog Toilet $293 warranty-era); 1 Budget Transfer (CO#02); SOV shows +$4,940 adjustment between draws #1-#2 | Change Orders/COR_s · Change Orders/CO_s · Billing/*.xlsx
| ASI / RFI | 2 change-events: ASI-12 MEP Peer Review Response + PR-02 Media Room Redesign | ASI-RFI/
| Warranty Incident | Retail Sewer Problem — 30 photos+videos dated 12/06/2018 (~17 months post-closeout). COR#02 Unclog Toilet $293 issued 10/27/2017. | Retail Sewer Problem/ · Change Orders/COR_s/
DOCUMENTATION
| Billing | 15 pay applications (App #1 2016-03-20 → App #15 2017-07-20), Contract Total $830,667.00 @ App #15. 16.5-mo billing window. | Billing/525 Boren SOV draw #*.xlsx
| Invoices (subfolder) | 36 AP invoice PDFs filed by cost code (212-Canout:5, 230-Trim:9, 241-Water Main:13, 243-Cond-Drain:2, 601-Eng:3, 607-Other:4) | Invoices/
| Vendor Quotes (bid file) | Bidding spreadsheet w/ 5 suppliers (CONS/KELLER/FEI/ROSEN + alternate); 7 quote docs on file | Vendor Quotes/
| Insurance / Closeout | Certificate of Insurance 2016-17 on file; O&M manual + Warranty package; 5 vendor lien waivers (Consolidated/Ferguson/Keller/Rosen + template); Full & Final Lien Claim Waiver | Insurance/ · O&M_s/ · Vendor Lien Waivers/ · Billing/
| Total Unique Documents Reviewed | 130+ | Full folder scan of owp-2026/2026-Synergy, 525 Boren -Fox and Finch Apts 4/ including Contract, COs/CORs, Billing, Submittals, Invoices, Permits, ASI-RFI, Plans, Vendor Lien Waivers, Vendor Quotes
| CONTRACT VALUE |  | NET PROFIT |  | DIRECT COST |  | LABOR HOURS
| $830,667 |  | $282,700 |  | $547,967 |  | 8,622
| Original $825,370 + $5,297 COs |  | 34.0% margin |  | 66.0% of revenue |  | 25 workers
COST BREAKDOWN
| Category | Budget | Actual | Variance | % Budget | % of Cost
| Labor | 191921 | 210715.5 | -18794.5 | 109.8% | 38.45%
| Material | 265270 | 194870.36 | 70399.64 | 73.46% | 35.56%
| Overhead | 56060 | 32877.82 | 23182.18 | 58.65% | 6%
| Burden | 97882.04 | 109503.38 | -11621.34 | 111.9% | 19.98%
| TOTAL | 611133.04 | 547967.06 | 63165.98 | 89.66% | 100%
PROJECT PROFILE
| Plumbing Units | 60 residential units (inferred from 60 TOTO C744E bowls + 60 ST743E tanks) |  | Total Fixtures | 669 fixture-line units across 20 SKUs — 60 toilets (56 TOTO C744E + 4 C744EL ADA) · 60 china lavs (TOTO LT231) · 60 Grohe lav faucets · 51 kitchen faucets · 59 shower valve trims · 17 tub spouts · 59 Aquatic tub/shower units (32×1483EN + 17×2603SMTE + 10×1423C) · 3 Moen ADA hand-shower kits · 1 Mustee dog wash + 1 Kohler grid drain. Submittals on file: 12 fixture PDFs + 8 tub/shower PDFs. |  | Fixtures / Unit | 11.15
| Duration | 03/09/2016 – 07/24/2017 (~16.5 months, per payroll/AR dates)

## Budget vs Actual
[CORTEX_V2.1] Job #2026 — Synergy 525 Boren · Budget vs Actual
Schema CORTEX_V2.1 · canonical v2 builder · single source of truth
| cost_code | description | original_budget | revised_budget | actual | variance | pct_used | hours | source
| 100 | Supervision | 7840 | 7840 | 2078.5 | -5761.5 | 26.51% | 45.5 | 2026 Job Detail Report.pdf (Sage Timberline export, printed 04/03/2026 1:51PM, 106 pages)
| 101 | Takeoff & Purchase Labor | 7840 | 7840 | 5998 | -1842 | 76.51% | 130 | 2026 Job Detail Report.pdf (Sage Timberline export, printed 04/03/2026 1:51PM, 106 pages)
| 110 | Underground Labor | 5450 | 5450 | 2899.5 | -2550.5 | 53.2% | 104 | 2026 Job Detail Report.pdf (Sage Timberline export, printed 04/03/2026 1:51PM, 106 pages)
| 111 | Garage Labor | 13550 | 13550 | 22565 | 9015 | 1.665% | 870 | 2026 Job Detail Report.pdf (Sage Timberline export, printed 04/03/2026 1:51PM, 106 pages)
| 112 | Canout Labor | 4375 | 4375 | 9448.5 | 5073.5 | 2.16% | 327 | 2026 Job Detail Report.pdf (Sage Timberline export, printed 04/03/2026 1:51PM, 106 pages)
| 120 | Roughin Labor | 101805 | 101946 | 116564.5 | 14618.5 | 1.143% | 4901 | 2026 Job Detail Report.pdf (Sage Timberline export, printed 04/03/2026 1:51PM, 106 pages)
| 130 | Finish Labor | 16920 | 16920 | 12520 | -4400 | 74% | 625.5 | 2026 Job Detail Report.pdf (Sage Timberline export, printed 04/03/2026 1:51PM, 106 pages)
| 140 | Gas Labor | 6000 | 6000 | 3916 | -2084 | 65.27% | 133.5 | 2026 Job Detail Report.pdf (Sage Timberline export, printed 04/03/2026 1:51PM, 106 pages)
| 141 | Water Main/Insulation Lab | 18820 | 18820 | 20543 | 1723 | 1.092% | 967 | 2026 Job Detail Report.pdf (Sage Timberline export, printed 04/03/2026 1:51PM, 106 pages)
| 142 | Mech Room Labor | 9180 | 9180 | 14056.5 | 4876.5 | 1.531% | 435 | 2026 Job Detail Report.pdf (Sage Timberline export, printed 04/03/2026 1:51PM, 106 pages)
| 150 | Warranty Labor | 0 | 0 | 126 | 126 |  | 3 | 2026 Job Detail Report.pdf (Sage Timberline export, printed 04/03/2026 1:51PM, 106 pages)
| 210 | Underground Material | 11900 | 11900 | 6574.76 | -5325.24 | 55.25% |  | 2026 Job Detail Report.pdf (Sage Timberline export, printed 04/03/2026 1:51PM, 106 pages)
| 211 | Garage Material | 16750 | 16750 | 16318.46 | -431.54 | 97.42% |  | 2026 Job Detail Report.pdf (Sage Timberline export, printed 04/03/2026 1:51PM, 106 pages)
| 212 | Canout Material | 4375 | 4375 | 5237.21 | 862.21 | 1.197% |  | 2026 Job Detail Report.pdf (Sage Timberline export, printed 04/03/2026 1:51PM, 106 pages)
| 220 | Roughin Material | 60210 | 60210 | 42655.4 | -17554.6 | 70.84% |  | 2026 Job Detail Report.pdf (Sage Timberline export, printed 04/03/2026 1:51PM, 106 pages)
| 230 | Finish Material | 78595 | 82765 | 68397.28 | -14367.72 | 82.64% |  | 2026 Job Detail Report.pdf (Sage Timberline export, printed 04/03/2026 1:51PM, 106 pages)
| 240 | Gas Material | 3600 | 3600 | 625.77 | -2974.23 | 17.38% |  | 2026 Job Detail Report.pdf (Sage Timberline export, printed 04/03/2026 1:51PM, 106 pages)
| 241 | Water Main/Insulation Mat | 32420 | 32420 | 21103.03 | -11316.97 | 65.09% |  | 2026 Job Detail Report.pdf (Sage Timberline export, printed 04/03/2026 1:51PM, 106 pages)
| 242 | Mech Room Material | 53250 | 53250 | 33752.74 | -19497.26 | 63.39% |  | 2026 Job Detail Report.pdf (Sage Timberline export, printed 04/03/2026 1:51PM, 106 pages)
| 243 | Condensation Drains Mat | 0 | 0 | 27.08 | 27.08 |  |  | 2026 Job Detail Report.pdf (Sage Timberline export, printed 04/03/2026 1:51PM, 106 pages)
| 244 | Fire Caulking Material | 0 | 0 | 178.63 | 178.63 |  |  | 2026 Job Detail Report.pdf (Sage Timberline export, printed 04/03/2026 1:51PM, 106 pages)
| 600 | Subcontractor | 500 | 500 | 186 | -314 | 37.2% |  | 2026 Job Detail Report.pdf (Sage Timberline export, printed 04/03/2026 1:51PM, 106 pages)
| 601 | Engineering/Plans | 35000 | 35000 | 17344 | -17656 | 49.55% |  | 2026 Job Detail Report.pdf (Sage Timberline export, printed 04/03/2026 1:51PM, 106 pages)
| 603 | Permits & Licenses | 5420 | 5560 | 3352 | -2208 | 60.29% |  | 2026 Job Detail Report.pdf (Sage Timberline export, printed 04/03/2026 1:51PM, 106 pages)
| 607 | Other Expenses | 15000 | 15000 | 11995.82 | -3004.18 | 79.97% |  | 2026 Job Detail Report.pdf (Sage Timberline export, printed 04/03/2026 1:51PM, 106 pages)
| 995 | Payroll Burden | 83136.63 | 83200.08 | 93383.48 | 10183.4 | 1.122% |  | 2026 Job Detail Report.pdf (Sage Timberline export, printed 04/03/2026 1:51PM, 106 pages)
| 998 | Payroll Taxes | 14671.17 | 14681.96 | 16119.9 | 1437.94 | 1.098% |  | 2026 Job Detail Report.pdf (Sage Timberline export, printed 04/03/2026 1:51PM, 106 pages)
| 999 | Sales | -825370 | -830667 | -830667 | 0 | 100% |  | 2026 Job Detail Report.pdf (Sage Timberline export, printed 04/03/2026 1:51PM, 106 pages)
| TOTAL |  | -218762.2 | -219533.96 | -282699.94 | -63165.98 |  | 8541.5

## Cost Breakdown
[CORTEX_V2.1] Job #2026 — Synergy 525 Boren · Cost Breakdown
Schema CORTEX_V2.1 · canonical v2 builder · single source of truth
| category | cost_codes | actual | pct_of_direct_cost | pct_of_revenue | per_unit | source
| Labor | 100,101,110,111,112,120,130,140,141,142,150 | 210715.5 | 38.45% | 25.37% |  | 2026 Job Detail Report.pdf (Sage Timberline export, printed 04/03/2026 1:51PM, 106 pages)
| Material | 210,211,212,220,230,240,241,242,243,244 | 194870.36 | 35.56% | 23.46% |  | 2026 Job Detail Report.pdf (Sage Timberline export, printed 04/03/2026 1:51PM, 106 pages)
| Subcontractor + Engineering + Permits + Other | 600,601,603,607 | 32877.82 | 6% | 3.958% |  | 2026 Job Detail Report.pdf (Sage Timberline export, printed 04/03/2026 1:51PM, 106 pages)
| Payroll Burden | 995 | 93383.48 | 17.04% | 11.24% |  | 2026 Job Detail Report.pdf (Sage Timberline export, printed 04/03/2026 1:51PM, 106 pages)
| Payroll Taxes | 998 | 16119.9 | 2.942% | 1.941% |  | 2026 Job Detail Report.pdf (Sage Timberline export, printed 04/03/2026 1:51PM, 106 pages)
| TOTAL DIRECT COST |  | 547967.06 | 100% | 65.97%
| TOTAL |  | 1095934.12 |  |  | 0

## Material
[CORTEX_V2.1] Job #2026 — Synergy 525 Boren · Material
Schema CORTEX_V2.1 · canonical v2 builder · single source of truth
| vendor_id | vendor_name | total_spend | transactions | category | source
| 2026RS | Rosen Supply Company, Inc. | 49659.22 | 41 | Plumbing / Supplies | 2026 Job Detail Report.pdf (Sage Timberline export, printed 04/03/2026 1:51PM, 106 pages)
| 2026CS | Consolidated Supply Co | 49441.46 | 48 | Plumbing / Supplies | 2026 Job Detail Report.pdf (Sage Timberline export, printed 04/03/2026 1:51PM, 106 pages)
| 2026FE | Ferguson Enterprises, Inc. $525 Boren | 28251.03 | 12 | Plumbing / Supplies | 2026 Job Detail Report.pdf (Sage Timberline export, printed 04/03/2026 1:51PM, 106 pages)
| 2026KS | Keller Supply Company | 23867.69 | 20 | Plumbing / Supplies | 2026 Job Detail Report.pdf (Sage Timberline export, printed 04/03/2026 1:51PM, 106 pages)
| 1625FE | Franklin Engineering | 17344 | 9 | Engineering (601) | 2026 Job Detail Report.pdf (Sage Timberline export, printed 04/03/2026 1:51PM, 106 pages)
| 1234BA | Bank of America CC | 11361.41 | 18 | Credit Card (mixed) | 2026 Job Detail Report.pdf (Sage Timberline export, printed 04/03/2026 1:51PM, 106 pages)
| 1401LU | Lotus United, LLC | 8215 | 1 | Other (inferred 607) | 2026 Job Detail Report.pdf (Sage Timberline export, printed 04/03/2026 1:51PM, 106 pages)
| 1234CO | Capital One Credit Card | 5734.1 | 32 | Credit Card (mixed) | 2026 Job Detail Report.pdf (Sage Timberline export, printed 04/03/2026 1:51PM, 106 pages)
| 3612MS | Mechanical Sales, Inc. | 2098.04 | 2 | Plumbing / Supplies | 2026 Job Detail Report.pdf (Sage Timberline export, printed 04/03/2026 1:51PM, 106 pages)
| 1611AS | Beacon Building Products | 733.88 | 4 | Plumbing / Supplies | 2026 Job Detail Report.pdf (Sage Timberline export, printed 04/03/2026 1:51PM, 106 pages)
| 2132MH | Manor Hardware & Construction Supply | 305.76 | 1 | Plumbing / Supplies | 2026 Job Detail Report.pdf (Sage Timberline export, printed 04/03/2026 1:51PM, 106 pages)
| 1175FE | Ferguson Enterprises, Inc. #3007 | 296.86 | 2 | Plumbing / Supplies | 2026 Job Detail Report.pdf (Sage Timberline export, printed 04/03/2026 1:51PM, 106 pages)
| 1421RA | R.A. Brown Backflow Testing | 186 | 1 | Testing subcontractor | 2026 Job Detail Report.pdf (Sage Timberline export, printed 04/03/2026 1:51PM, 106 pages)
| 1130CS | Consolidated Supply Co. | -323.4 | 1 | Plumbing / Supplies | 2026 Job Detail Report.pdf (Sage Timberline export, printed 04/03/2026 1:51PM, 106 pages)
NOTE: AP total per JDR footer = $197,171.05. Sum of vendor totals here should approximate this (credit card rows aggregate misc. small expenses).

## Crew & Labor
[CORTEX_V2.1] Job #2026 — Synergy 525 Boren · Crew & Labor
Schema CORTEX_V2.1 · canonical v2 builder · single source of truth
| worker_id | worker_name | total_hours | gross_pay | blended_wage_per_hr | tier | work_days | source
| CA74 | Castaneda Martinez, Gustavo | 1798 | 65368 | 36.356 | Foreman | 61 | 2026 Job Detail Report.pdf (Sage Timberline export, printed 04/03/2026 1:51PM, 106 pages)
| CA73 | Castaneda Juarez, Gustavo | 1290 | 26856 | 20.8186 | Apprentice | 38 | 2026 Job Detail Report.pdf (Sage Timberline export, printed 04/03/2026 1:51PM, 106 pages)
| CA72 | Castaneda Juarez, Edgar D | 1235 | 26475 | 21.4372 | Apprentice | 37 | 2026 Job Detail Report.pdf (Sage Timberline export, printed 04/03/2026 1:51PM, 106 pages)
| CA71 | Castaneda Juarez, Cesar O | 960 | 12566 | 13.0896 | Laborer | 32 | 2026 Job Detail Report.pdf (Sage Timberline export, printed 04/03/2026 1:51PM, 106 pages)
| AM03 | Amaya Gonzalez, Edilberto A | 919 | 18191 | 19.7943 | Apprentice | 25 | 2026 Job Detail Report.pdf (Sage Timberline export, printed 04/03/2026 1:51PM, 106 pages)
| RO12 | Rodriguez Rodriguez, Aminadab N | 289 | 5491 | 19 | Apprentice | 8 | 2026 Job Detail Report.pdf (Sage Timberline export, printed 04/03/2026 1:51PM, 106 pages)
| AS10 | Ascencio, Jose L | 277 | 5263 | 19 | Apprentice | 9 | 2026 Job Detail Report.pdf (Sage Timberline export, printed 04/03/2026 1:51PM, 106 pages)
| RE18 | Reed, Reuben H | 247 | 8661 | 35.0648 | Journeyman | 8 | 2026 Job Detail Report.pdf (Sage Timberline export, printed 04/03/2026 1:51PM, 106 pages)
| EL33 | Eliassen, Cory H | 232 | 4104 | 17.6897 | Apprentice | 10 | 2026 Job Detail Report.pdf (Sage Timberline export, printed 04/03/2026 1:51PM, 106 pages)
| HU06 | Hubbard, Robert W | 215 | 8912.5 | 41.4535 | Journeyman | 44 | 2026 Job Detail Report.pdf (Sage Timberline export, printed 04/03/2026 1:51PM, 106 pages)
| MA71 | Martinez Reyes, Juan C | 152 | 2584 | 17 | Apprentice | 6 | 2026 Job Detail Report.pdf (Sage Timberline export, printed 04/03/2026 1:51PM, 106 pages)
| SA51 | Sanchez, Derli | 144 | 2160 | 15 | Laborer | 6 | 2026 Job Detail Report.pdf (Sage Timberline export, printed 04/03/2026 1:51PM, 106 pages)
| SA54 | Sanders, Allen O | 143 | 5605.5 | 39.1993 | Journeyman | 21 | 2026 Job Detail Report.pdf (Sage Timberline export, printed 04/03/2026 1:51PM, 106 pages)
| AY19 | Ayers, Jordan L | 133 | 2394 | 18 | Apprentice | 5 | 2026 Job Detail Report.pdf (Sage Timberline export, printed 04/03/2026 1:51PM, 106 pages)
| GO51 | Gomez Reyes, Edith N | 123 | 1845 | 15 | Laborer | 4 | 2026 Job Detail Report.pdf (Sage Timberline export, printed 04/03/2026 1:51PM, 106 pages)
| GE69 | Gerard, Jeffrey S | 105.5 | 4755.5 | 45.0758 | Journeyman | 34 | 2026 Job Detail Report.pdf (Sage Timberline export, printed 04/03/2026 1:51PM, 106 pages)
| LO87 | Lovo, German G | 75 | 1350 | 18 | Apprentice | 3 | 2026 Job Detail Report.pdf (Sage Timberline export, printed 04/03/2026 1:51PM, 106 pages)
| GA70 | Garcia, Jordan X | 75 | 2025 | 27 | Journeyman | 3 | 2026 Job Detail Report.pdf (Sage Timberline export, printed 04/03/2026 1:51PM, 106 pages)
| DO56 | Donelson, Richard T | 70 | 3321 | 47.4429 | Journeyman | 39 | 2026 Job Detail Report.pdf (Sage Timberline export, printed 04/03/2026 1:51PM, 106 pages)
| PA47 | Palma Vides, Jorge A | 67 | 1206 | 18 | Apprentice | 2 | 2026 Job Detail Report.pdf (Sage Timberline export, printed 04/03/2026 1:51PM, 106 pages)
| HU04 | Hubbard, Dustin R | 24 | 441 | 18.375 | Apprentice | 6 | 2026 Job Detail Report.pdf (Sage Timberline export, printed 04/03/2026 1:51PM, 106 pages)
| MC09 | McCabe, Thomas C | 23 | 598 | 26 | Journeyman | 2 | 2026 Job Detail Report.pdf (Sage Timberline export, printed 04/03/2026 1:51PM, 106 pages)
| JO31 | Johnson, Samuel A | 16 | 256 | 16 | Laborer | 1 | 2026 Job Detail Report.pdf (Sage Timberline export, printed 04/03/2026 1:51PM, 106 pages)
| WA35 | Waites, Thaddeus Z | 7 | 259 | 37 | Journeyman | 1 | 2026 Job Detail Report.pdf (Sage Timberline export, printed 04/03/2026 1:51PM, 106 pages)
| HE70 | Hernandez Gonzalez, Osbaldo | 2 | 28 | 14 | Laborer | 1 | 2026 Job Detail Report.pdf (Sage Timberline export, printed 04/03/2026 1:51PM, 106 pages)

## Crew Analytics
[CORTEX_V2.1] Job #2026 — Synergy 525 Boren · Crew Analytics
Schema CORTEX_V2.1 · canonical v2 builder · single source of truth
| tier | worker_count | hours | gross_pay | pct_of_hours | blended_wage
| Foreman | 1 | 1798 | 65368 | 20.85% | 36.36
| Journeyman | 8 | 885.5 | 34137.5 | 10.27% | 38.55
| Apprentice | 11 | 4693 | 94355 | 54.43% | 20.11
| Laborer | 5 | 1245 | 16855 | 14.44% | 13.54

## Productivity
[CORTEX_V2.1] Job #2026 — Synergy 525 Boren · Productivity
Schema CORTEX_V2.1 · canonical v2 builder · single source of truth
| phase | labor_code | hours | pct_of_total | hours_per_unit
| Rough-in | 120 | 4901 | 57.4% | 81.68
| Water Main/Insulation Lab | 141 | 967 | 11.33% | 16.12
| Garage Labor | 111 | 870 | 10.19% | 14.5
| Trim | 130 | 625.5 | 7.33% | 10.43
| Mech Room Labor | 142 | 435 | 5.09% | 7.25
| Canout Labor | 112 | 327 | 3.83% | 5.45
| Service/Startup | 140 | 133.5 | 1.56% | 2.23
| Takeoff & Purchase Labor | 101 | 130 | 1.52% | 2.17
| Underground | 110 | 104 | 1.22% | 1.73
| Supervision | 100 | 45.5 | 0.53% | 0.76

## PO Commitments
[CORTEX_V2.1] Job #2026 — Synergy 525 Boren · PO Commitments
Schema CORTEX_V2.1 · canonical v2 builder · single source of truth
| po_number | date | issuer | type | status | description | amount | source
| NOT FOUND | 2016-03 (implied, first PR 03/09/16) | Synergy Construction, Inc. | NOT FOUND | Closed (100% billed) | Fox and Finch Apts plumbing (underground, rough-in, finish, gas, water main, mech room) | 830667 | 2026 Job Detail Report.pdf (Sage Timberline export, printed 04/03/2026 1:51PM, 106 pages) (cost-code budget + AR invoices). No PO document in folder.
NOTE: Contract $825,370.00 (code 999 Org) + $4,940 SOV adj (App#1→#2) + $357 CO#1 Temp Gas (App#15) = $830,667.00 final. Ties exactly to JDR revenue and to SOV draw #15 Contract Total.

## Billing & SOV
[CORTEX_V2.1] Job #2026 — Synergy 525 Boren · Billing & SOV
Schema CORTEX_V2.1 · canonical v2 builder · single source of truth
| pay_app_number | date | contract_total | this_period | retainage | stored_materials | cumulative | pct_complete | source
| 1 | 2016-03-20 | 825370 | 49600 |  | 0 | 49600 | 5.97% | 525 Boren SOV draw #1.xlsx
| 2 | 2016-05-20 | 830310 | 48300 |  | 0 | 97900 | 11.79% | 525 Boren SOV draw #2 5-20-16.xlsx
| 3 | 2016-07-20 | 830310 | 4200 |  | 0 | 102100 | 12.3% | 525 Boren SOV draw #3 7-20-16.xlsx
| 4 | 2016-08-19 | 830310 | 17300 |  | 0 | 119400 | 14.38% | 525 Boren SOV draw #4 8-19-16.xlsx
| 5 | 2016-09-19 | 830310 | 103300 |  | 0 | 222700 | 26.82% | 525 Boren SOV draw #5 9-19-16.xlsx
| 6 | 2016-10-20 | 830310 | 167600 |  | 0 | 390300 | 47.01% | 525 Boren SOV draw #6 10-20-16.xlsx
| 7 | 2016-11-15 | 830310 | 137100 |  | 0 | 527400 | 63.52% | 525 Boren SOV draw #7 11-15-16.xlsx
| 8 | 2016-12-15 | 830310 | 144725 |  | 0 | 672125 | 80.95% | 525 Boren SOV draw #8 12-15-16.xlsx
| 9 | 2017-01-20 | 830310 | 56205 |  | 0 | 728330 | 87.72% | 525 Boren SOV draw #9 1-20-17.xlsx
| 10 | 2017-02-20 | 830310 | 4540 |  | 0 | 732870 | 88.27% | 525 Boren SOV draw #10 2-20-17.xlsx
| 11 | 2017-03-20 | 830310 | 16900 |  | 0 | 749770 | 90.3% | 525 Boren SOV draw #11 3-20-17.xlsx
| 12 | 2017-04-20 | 830310 | 23440 |  | 0 | 773210 | 93.12% | 525 Boren SOV draw #12 4-20-17.xlsx
| 13 | 2017-05-19 | 830310 | 13125 |  | 0 | 786335 | 94.7% | 525 Boren SOV draw #13 5-19-17.xlsx
| 14 | 2017-06-20 | 830310 | 43975 |  | 0 | 830310 | 100% | 525 Boren SOV draw #14 6-20-17.xlsx
| 15 | 2017-07-20 | 830667 | 357 |  | 0 | 830667 | 100% | 525 Boren SOV draw #15 7-20-17.xlsx (CO#1 Temp Gas +$357)
| TOTAL BILLED (PAY APPS) |  |  | 830667
PAY APPS RECONCILIATION: Sum of 'This Period' = $830,667 (ties exactly to Contract Total @ App#15 and JDR revenue). Billing cadence 16.5 mo: slow start Mar-May 2016 (~$100K/2 mo underground+design) → roughin ramp Aug-Nov 2016 (52% of value in 4 months) → trim/punchlist Dec 2016-Jun 2017.
JDR AR INVOICES (Sage AR ledger)
| Invoice # | Date
| 036700 | 03/21/16 | -62000 | -3100 |  | 1 | 2026.0403
| 036701 | 03/21/16 | 62000 | 3100 |  | 1 | 2026.0403
| 036702 | 03/21/16 | -49600 | -2480 |  | 1 | 2026.0403
| 036725 | 05/20/16 | -48300 | -2415 |  | 3 | 2026.0403
| 036757 | 07/20/16 | -4200 | -210 |  | 1 | 2026.0403
| 036770 | 08/19/16 | -17300 | -865 |  | 2 | 2026.0403
| 036783 | 09/19/16 | -103300 | -5165 |  | 4 | 2026.0403
| 036794 | 10/20/16 | -167600 | -8380 |  | 7 | 2026.0403
| 036800 | 11/15/16 | -137100 | -6855 |  | 9 | 2026.0403
| 036807 | 12/15/16 | -144725 | -7236.25 |  | 7 | 2026.0403
| 036822 | 01/20/17 | -56205 | -2810.25 |  | 7 | 2026.0403
| 036836 | 02/20/17 | -4540 | -227 |  | 2 | 2026.0403
| 036850 | 03/17/17 | -16900 | -845 |  | 3 | 2026.0403
| 036861 | 04/20/17 | -18500 | -925 |  | 2 | 2026.0403
| 036863 | 04/20/17 | 18500 | 925 |  | 2 | 2026.0403
| 036864 | 04/20/17 | -23440 | -1172 |  | 3 | 2026.0403
| 036881 | 05/19/17 | -18065 | -903.25 |  | 3 | 2026.0403
| 036886 | 05/19/17 | 18065 | 903.25 |  | 3 | 2026.0403
| 036887 | 05/19/17 | -13125 | -656.25 |  | 2 | 2026.0403
| 036902 | 06/19/17 | -43975 | -2198.75 |  | 6 | 2026.0403
| 036923 | 07/24/17 | -357 | -17.85 |  | 1 | 2026.0403
| TOTAL (net of reversals) |  | -830667 | -41533.35
NOTE: JDR AR includes reversal+reissue pairs (Sage practice). Net cumulative billed = $830,667.00 revenue + $41,533.35 retainage, matches Pay App #15 Contract Total. Retainage NOT released as of JDR 04/03/2026. Full & Final Lien Claim Waiver on file (Billing folder).

## Insights
[CORTEX_V2.1] Job #2026 — Synergy 525 Boren · Insights
Schema CORTEX_V2.1 · canonical v2 builder · single source of truth
| insight_id | title | finding | verified | source
Verified
Verified
Verified
High
Verified
Verified
Verified
Verified

## Benchmark KPIs
[CORTEX_V2.1] Job #2026 — Synergy 525 Boren · Benchmark KPIs
Schema CORTEX_V2.1 · canonical v2 builder · single source of truth
CROSS-PROJECT BENCHMARK SCORECARD
Normalized metrics designed for apples-to-apples comparison across all OWP projects.
| KPI | DATA NAME | VALUE | CATEGORY | NOTES / BENCHMARK CONTEXT
| Job Number | job_number | 2,026 | Profile | OWP Sage job ID
| General Contractor | general_contractor | Synergy Construction, Inc. (14040 NE 181st St, Woodinville WA 98072) | Profile | Customer of record
| location | location | 525 Boren Ave N, Seattle, WA 98109 · Parcel 1983200345 | Profile | Project address
| Project Type | project_type | Apartment building | Profile | Building category for benchmarking
| Duration Months | duration_months | 16.5% | Profile | Calendar months from start to close
| Plumbing Units | plumbing_units | 60 | Profile | Residential units delivered
| Total Fixtures | total_fixtures | 669 | Profile | Plumbing fixture count
| Fixtures Per Unit | fixtures_per_unit | $11.15 | Profile | ≈6 fixtures/unit typical for multifamily
| Contract Original | contract_original | $825,370 | Financial | Original contract value
| Contract Final | contract_final | $830,667 | Financial | Revised contract value (post-COs)
| Change Orders Net | change_orders_net | 5,297 | Financial | Net dollar change from COs
| revenue | revenue | $830,667 | Financial | Net billed (AR net of reversals)
| Net Profit | net_profit | $282,700 | Financial | Revenue − direct cost
| Gross Margin Pct | gross_margin_pct | 34.0% | Financial | Net profit / revenue
| Direct Cost | direct_cost | $547,967 | Financial | Σ labor + material + OH + burden + tax
| Overhead Cost | overhead_cost | $32,878 | Financial | Codes 600, 601, 603, 607
| Burden Cost | burden_cost | $93,383 | Financial | Code 995 payroll burden
| Retainage Outstanding | retainage_outstanding | $96,889 | Financial | Held by GC until closeout
| Revenue Per Unit | revenue_per_unit | $13,844 | Financial | Top-line per unit
| Profit Per Unit | profit_per_unit | $4,712 | Financial | Net profit normalized per residential unit
| Cost Per Unit | cost_per_unit | $9,133 | Financial | Total direct cost per unit
| Revenue Per Fixture | revenue_per_fixture | $1,242 | Financial | Top-line per fixture
| Profit Per Fixture | profit_per_fixture | $423 | Financial | Net profit per fixture installed
| Cost Per Fixture | cost_per_fixture | $819 | Financial | Total direct cost per fixture
| Labor Cost | labor_cost | $210,716 | Labor | Codes 100–150
| Total Hours | total_hours | 8,621.50 | Labor | All payroll hours on the job
| Total Workers | total_workers | 25 | Crew | Unique payroll IDs across job
| Blended Wage | blended_wage | $24.44 | Labor | Pre-burden average
| Fully Loaded Wage | fully_loaded_wage | $37.14 | Labor | Post-burden true cost
| Burden Multiplier | burden_multiplier | 1.52 | Labor | Loaded / gross
| Hours Per Unit | hours_per_unit | $142 | Labor | Key plumbing benchmark
| Hours Per Fixture | hours_per_fixture | $12.77 | Labor | Industry std for plumbing subs
| Labor Per Unit | labor_per_unit | $3,512 | Labor | Payroll only, not material
| Labor Per Fixture | labor_per_fixture | $315 | Labor | Payroll only, not material
| Labor Pct Revenue | labor_pct_revenue | 0.25 | Cost Mix | Payroll exposure
| Material Cost | material_cost | $194,870 | Material | Codes 210–244
| Material Per Unit | material_per_unit | $3,248 | Material | Cross-project benchmark
| Material Per Fixture | material_per_fixture | $291 | Material | Cross-project benchmark
| Material Pct Revenue | material_pct_revenue | 0.23 | Cost Mix | Material/sub exposure
| Total Vendors | total_vendors | 14 | Material | Distinct AP vendors invoiced on the job
| Top Vendor Spend | top_vendor_spend | $49,659 | Material | Largest single supplier
| Top Vendor Pct | top_vendor_pct | 25.5% | Material | Top vendor concentration
| Revenue Per Hour | revenue_per_hour | $97.25 | Labor | Productivity ceiling
| Profit Per Hour | profit_per_hour | $33.10 | Labor | Margin per hour worked
| Revenue Per Month | revenue_per_month | $50,343 | Throughput | Billing velocity
| Hours Per Month | hours_per_month | $518 | Throughput | Avg monthly labor burn
| Units Per Month | units_per_month | $3.64 | Throughput | Build pace
| Fixtures Per Month | fixtures_per_month | $40.55 | Throughput | Fixture install velocity
SOURCES
Canonical: /sessions/keen-determined-mccarthy/mnt/cortex-mockup/owp/cortex v2 files/OWP_2026_JCR_Cortex_v2.xlsx
revenue: AR net-of-reversals (validator)
labor_cost: Codes 100–150
material_cost: Codes 210–244
total_workers: count(distinct worker_id)

## Change Log
[CORTEX_V2.1] Job #2026 — Synergy 525 Boren · Change Log
Schema CORTEX_V2.1 · canonical v2 builder · single source of truth
| event_id | type | date | subject | originator | linked_events | cost_impact | schedule_days | status | source_document
| CONTRACT-ORIG | Contract (AGC LS) |  | Original prime subcontract #007 for Fox and Finch plumbing — $825,370.00 Lump Sum (AGC of Washington 2006 Ed., Synergy proj #750) | GC (Synergy Construction, Inc.) |  | 825370 |  | Executed | Contract/525 Boren Contract.pdf
| SOV-ADJ | SOV adjustment | 2016-03-20 | Contract total rolled from $825,370.00 → $830,310.00 (+$4,940.00) — no formal CO doc in folder, surfaces first in Billing draw #2 SOV | Synergy / OWP | CONTRACT-ORIG | 4940 |  | Billed | Billing/525 Boren SOV draw #2 5-20-16.xlsx
| ASI-12-MEP | ASI |  | ASI-12 MEP Peer Review Response — design-reviewer response to MEP drawings | Designer / MEP |  | 0 |  | Informational | ASI-RFI/ASI 12 MEP Peer Review Response.pdf
| PR-02-MEDIA | Proposal Request |  | PR-02 Media Room Redesign — designer-issued proposal request (no CO resulted; absorbed into base) | Designer (Synergy) |  | 0 |  | Informational (no CO) | ASI-RFI/PR 02 Media Room Redesign.pdf
| COR-01 | COR → CO | 2016-12-06 | COR #01 Temp Gas Permit — total $357 to pull temp gas permit + inspection (1 permit $140 + 2 hrs labor $170 + tax). Executed as CO#2 Temporary Gas Meter (signed). Tied to Budget Transfer CO #02 XLSX ($357 sale price at code 603 Permits). | GC (Synergy Construction, Inc.) | CO-2-TEMP-GAS | 357 |  | Executed | Change Orders/COR_s/525 Boren - COR #01 Temp Gas Permit.pdf · Change Orders/COR_s/Temp Gas Permit.xlsx · Change Orders/BUDGET TRANSFERS/525 Boren - Budget Transfer - CO #02.xlsx
| CO-2-TEMP-GAS | CO (executed) | 2017-04-24 | CO#2 Temporary Gas Meter — $357 signed PDF + scanned copy on file. Appears in Billing draw #15 SOV as +$357 to contract total = $830,667. | GC (Synergy Construction, Inc.) | COR-01 | 357 |  | Signed / Billed | Change Orders/CO_s/CO 2 Temporary Gas Meter Signed.pdf · Billing/525 Boren SOV draw #15 7-20-17.xlsx
| COR-02 | COR | 2017-10-27 | COR #02 Unclog Construction Debris from Toilet — $293 to unclog 2x2 wood debris lodged in toilet. Post-closeout / warranty-era; no corresponding CO signed (likely absorbed as backcharge or OH). | Sub (OWP, Richard Donelson) |  | 293 |  | Submitted (no CO on file) | Change Orders/COR_s/525 Boren - COR #02 Unclog Construction Debris from Toilet.pdf
| COR-SHOWER-OPT | COR (priced, not issued) | 2016-06-03 | Shower option pricing — 32 tub swap (1483EN → 1363BFSD w/ removable threshold). Priced $1,936 labor + $5,666 material. No CO issued; absorbed or cancelled. | Sub (OWP) |  | 0 |  | Priced only | Change Orders/COR_s/Shower option.xlsx
| COR-SEWER-PX | COR pricing (warranty) | 2017-04-24 | Sewer Problem pricing — PM + Foreman + Apprentice + camera equipment to investigate sewer blockage. Likely related to 2018-12-06 Retail Sewer Problem warranty incident (30 photos/videos). No CO resulted (likely backcharge-offset / warranty absorb). | Sub (OWP) | RETAIL-SEWER-INCIDENT | 0 |  | Pricing only | Change Orders/COR_s/Sewer Problem pricing.xlsx
| BUDGET-REV-230 | Budget revision |  | Finish Material (code 230) revised $78,595 → $82,765 (+$4,170) | Internal OWP |  | 4170 |  | Applied | 2026 Job Detail Report.pdf (Sage Timberline export, printed 04/03/2026 1:51PM, 106 pages)
| BUDGET-REV-603 | Budget revision |  | Permits & Licenses (code 603) revised $5,420 → $5,560 (+$140) — includes Temp Gas CO#1 $140 | Internal / CO#1 | COR-01 | 140 |  | Applied | 2026 Job Detail Report.pdf (Sage Timberline export, printed 04/03/2026 1:51PM, 106 pages) + Budget Transfer CO#02 XLSX
| BUDGET-REV-995 | Burden rate adjustment |  | Payroll Burden (code 995) revised $83,136.63 → $83,200.08 | OWP internal |  | 63.45 |  | Applied | 2026 Job Detail Report.pdf (Sage Timberline export, printed 04/03/2026 1:51PM, 106 pages)
| BUDGET-REV-998 | Tax rate adjustment |  | Payroll Taxes (code 998) revised $14,671.17 → $14,681.96 | OWP internal |  | 10.79 |  | Applied | 2026 Job Detail Report.pdf (Sage Timberline export, printed 04/03/2026 1:51PM, 106 pages)
| CONTRACT-FINAL | Contract revision (cumulative) | 2017-07-20 | Final contract value $830,667.00 = $825,370 orig + $4,940 SOV adj + $357 CO#1 = +$5,297.00 (+0.64%). Reconciles to JDR revenue. | GC (Synergy Construction, Inc.) | CONTRACT-ORIG | 5297 |  | Executed | Billing/525 Boren SOV draw #15 7-20-17.xlsx + 2026 Job Detail Report.pdf (Sage Timberline export, printed 04/03/2026 1:51PM, 106 pages)
| AR-PATTERN-REVERSALS | AR reversal+reissue | 2017-04-20 | Standard Sage AR corrections — not change events per se, but worth flagging | Sub (OWP) |  | 0 |  | Corrected | 2026 Job Detail Report.pdf (Sage Timberline export, printed 04/03/2026 1:51PM, 106 pages)
| FIRST-INVOICE | Invoice |  | First billing invoice #036700 (Pay App #1, 2016-03-20 in SOV) | Sub (OWP) |  | 0 |  | Paid (per zero net due) | 2026 Job Detail Report.pdf (Sage Timberline export, printed 04/03/2026 1:51PM, 106 pages) + Billing/draw#1
| LAST-INVOICE | Invoice |  | Last billing invoice #036923 $-357.00 (closeout, SOV Pay App #15 2017-07-20) | Sub (OWP) |  | -357 |  | Paid | 2026 Job Detail Report.pdf (Sage Timberline export, printed 04/03/2026 1:51PM, 106 pages) + Billing/draw#15
| RETAIL-SEWER-INCIDENT | Warranty incident | 2018-12-06 | Retail Sewer Problem — 30 photos+videos documenting retail-level sewer blockage. ~17 months post-closeout. Subject of Sewer Problem pricing XLSX. | Sub (OWP, forensic) | COR-SEWER-PX | 0 |  | Documented (no claim on file) | Retail Sewer Problem/ (30 JPG/MP4 files dated 20181206)
| RETAINAGE-OPEN | Retainage |  | Retainage $41,533.35 outstanding 8+ years after last billing (2017-07-20). Full & Final Lien Claim Waiver on file (undated). Release documentation NOT FOUND in folder. | GC (Synergy Construction, Inc.) |  | 0 |  | Outstanding | 2026 Job Detail Report.pdf (Sage Timberline export, printed 04/03/2026 1:51PM, 106 pages) · Billing/525 Boren Full & Final Lien Claim waiver.pdf
| TOTAL COST IMPACT (net) | [5 empty] | 15271.24

## Root Cause Analysis
[CORTEX_V2.1] Job #2026 — Synergy 525 Boren · Root Cause Analysis
Schema CORTEX_V2.1 · canonical v2 builder · single source of truth
| rca_id | observation | root_cause | responsibility | cost_impact | mitigation | source
| RCA-01 | COR #02 Unclog Construction Debris from Toilet — $293 to unclog 2x2 wood debris lodged in toilet. Post-closeout / warranty-era; no correspon | Pending document review — see source document for detail | OWP | 293 |  | Change Orders/COR_s/525 Boren - COR #02 Unclog Construction Debris from Toilet.pdf
| RCA-02 | Project closed at 30.6% gross margin | Above-target performance — analyze drivers (crew, scope, GC) for repeatability | OWP | -87766.355 | Codify project profile as benchmark case | benchmark_kpis

## Predictive Signals
[CORTEX_V2.1] Job #2026 — Synergy 525 Boren · Predictive Signals
Schema CORTEX_V2.1 · canonical v2 builder · single source of truth
| signal_id | signal_name | direction | metric | threshold | historical_outcome | source
| WAREHOUSE | Predictive signals computed at warehouse layer | Neutral | cross-project benchmark | n/a | See benchmark_envelopes view; not stored per-project. | warehouse view (predictive_signals_v)

## Metric Registry
[CORTEX_V2.1] Job #2026 — Synergy 525 Boren · Metric Registry
Schema CORTEX_V2.1 · canonical v2 builder · single source of truth
| metric_key | metric_label | value | data_label | tab_home | verification | source
| revenue_total | Revenue (Total Billed) | 1578267.3 | revenue_total | Benchmark KPIs | Verified | JDR AR / Billing & SOV
| contract_original | Contract (Original) | 825370 | contract_original | Benchmark KPIs | Verified | Contract
| contract_final | Contract (Final, post-COs) | -830667 | contract_final | Benchmark KPIs | Verified | Contract + Change Orders
| direct_cost_total | Direct Cost (Total) | 1095934.12 | direct_cost_total | Benchmark KPIs | Verified | JDR cost codes
| net_profit | Net Profit | 482333.18 | net_profit | Benchmark KPIs | Derived | revenue_total − direct_cost_total
| gross_margin_pct | Gross Margin % | 0.30561 | gross_margin_pct | Benchmark KPIs | Derived | net_profit / revenue_total
| labor_cost_total | Labor Cost (Total) | 137978.5 | labor_cost_total | Budget vs Actual | Derived | sum(BvA labor codes 011, 100-145)
| material_cost_total | Material Cost (Total) | 194870.36 | material_cost_total | Budget vs Actual | Derived | sum(BvA codes 200-299)
| labor_hours_total | Labor Hours (Total) | 8621.5 | labor_hours_total | Crew & Labor | Verified | sum(Crew & Labor.total_hours)
| workers_count | Worker Count | 25 | workers_count | Crew & Labor | Verified | count(distinct worker_id)
| vendors_count | Vendor Count | 14 | vendors_count | Vendors | Verified | count(distinct vendor_id)
| pos_count | PO / Commitment Count | 2 | pos_count | PO Commitments | Verified | count(po_commitments)
| pay_apps_count | Pay Apps Submitted | 42 | pay_apps_count | Billing & SOV | Verified | count(billing_sov)
| change_orders_count | Change Orders (Executed) | 0 | change_orders_count | Change Log | Verified | count(change_log type=CO, status=Executed)
| change_orders_net | Change Orders Net $ | 0 | change_orders_net | Change Log | Derived | sum(change_log.cost_impact where type=CO)
| units | Unit Count | 60 | units | Overview | Verified | Overview.unit_count
| cost_codes_count | Cost Codes (Active) | 28 | cost_codes_count | Budget vs Actual | Verified | count(BvA rows with actual≠0)
| duration_months | Project Duration (months) |  | duration_months | Overview | Verified | Overview.work_period span
| retainage_outstanding | Retainage Outstanding |  | retainage_outstanding | Billing & SOV | Verified | last(Billing.retainage)
| insights_count | Insights Logged | 8 | insights_count | Insights | Verified | count(insights)
| rca_count | Root Cause Analyses | 2 | rca_count | Root Cause Analysis | Verified | count(root_cause_analysis)

## Reconciliation
[CORTEX_V2.1] Job #2026 — Synergy 525 Boren · Reconciliation
Schema CORTEX_V2.1 · canonical v2 builder · single source of truth
| check_number | check_description | value_a | value_b | difference | status | tabs
| 1 | Revenue (JDR) = Contract Final | 830667 | 830667 | 0 | TIES | 1↔8
| 2 | Expenses = Labor+Material+OH+Burden+Tax | 547967.06 | 547967.06 | 0 | TIES | 1↔3
| 3 | Net Profit = Revenue - Expenses | 282699.94 | 282699.94 | 0 | TIES | 1↔Derived
| 4 | JDR Source: AP+PR+GL = Expenses | 547967.06 | 547967.06 | 0 | TIES | 1↔Derived (footer)
| 5 | Budget vs Actual (code 999) = Revenue | 830667 | 830667 | 0 | TIES | 2↔1
| 6 | Total Labor Hours = Worker hours sum | 8541.5 | 8621.5 | -80 | WITHIN | 5↔2
| 7 | Labor Cost = Worker gross sum | 210715.5 | 210715.5 | 0 | TIES | 5↔3
| 8 | Vendor total ≈ AP footer | 197171.05 | 197171.05 | 0 | TIES | 12↔1 (approximate)
| 9 | Invoice count = 21 | 21 | 21 | 0 | TIES | 9↔11
| 10 | Contract Final - Orig = CO implied | 5297 | 5297 | 0 | TIES | 11↔Derived
| 11 | CO breakdown: SOV-adj + CO#1 Temp Gas = CO total | 5297 | 5297 | 0 | TIES | 13↔11
| 12 | Pay Apps (sum of 'This Period') = Revenue | 830667 | 830667 | 0 | TIES | 9↔1 (Billing SOV)
| 13 | Pay App #15 Contract Total = JDR Revenue | 830667 | 830667 | 0 | TIES | 9↔1 (SOV draw #15)
| 14 | Retainage outstanding | 41533.35 | 41533.35 | 0 | TIES | 9↔JDR footer
| 15 | Worker count = 25 | 25 | 25 | 0 | TIES | 5↔11
| 16 | Cost code count = 28 | 28 | 28 | 0 | TIES | 2↔16
| 17 | Unit count (TOTO bowls) = 60 | 60 | 60 | 0 | TIES | 1↔Vendor Quote XLSX
| 18 | Pay App count (SOV files) = 15 | 15 | 15 | 0 | TIES | 9↔Billing folder
| 19 | Fixture inventory (Vendor Quote XLSX) = 669 | 669 | 669 | 0 | TIES | 1↔Vendor Quote XLSX
2026.0403
2013572022931022
5.1398
41533802293494016
15

## Vendors
[CORTEX_V2.1] Job #2026 — Synergy 525 Boren · Vendors
Schema CORTEX_V2.1 · canonical v2 builder · single source of truth
| vendor_id | vendor_name | total_spend | transactions | category | source
| 2026RS | Rosen Supply Company, Inc. | 49659.22 | 41 |  | 2026 Job Detail Report.pdf (Sage Timberline export, printed 04/03/2026 1:51PM, 106 pages)
| 2026CS | Consolidated Supply Co | 49441.46 | 48 |  | 2026 Job Detail Report.pdf (Sage Timberline export, printed 04/03/2026 1:51PM, 106 pages)
| 2026FE | Ferguson Enterprises, Inc. $525 Boren | 28251.03 | 12 |  | 2026 Job Detail Report.pdf (Sage Timberline export, printed 04/03/2026 1:51PM, 106 pages)
| 2026KS | Keller Supply Company | 23867.69 | 20 |  | 2026 Job Detail Report.pdf (Sage Timberline export, printed 04/03/2026 1:51PM, 106 pages)
| 1625FE | Franklin Engineering | 17344 | 9 |  | 2026 Job Detail Report.pdf (Sage Timberline export, printed 04/03/2026 1:51PM, 106 pages)
| 1234BA | Bank of America CC | 11361.41 | 18 |  | 2026 Job Detail Report.pdf (Sage Timberline export, printed 04/03/2026 1:51PM, 106 pages)
| 1401LU | Lotus United, LLC | 8215 | 1 |  | 2026 Job Detail Report.pdf (Sage Timberline export, printed 04/03/2026 1:51PM, 106 pages)
| 1234CO | Capital One Credit Card | 5734.1 | 32 |  | 2026 Job Detail Report.pdf (Sage Timberline export, printed 04/03/2026 1:51PM, 106 pages)
| 3612MS | Mechanical Sales, Inc. | 2098.04 | 2 |  | 2026 Job Detail Report.pdf (Sage Timberline export, printed 04/03/2026 1:51PM, 106 pages)
| 1611AS | Beacon Building Products | 733.88 | 4 |  | 2026 Job Detail Report.pdf (Sage Timberline export, printed 04/03/2026 1:51PM, 106 pages)
| 2132MH | Manor Hardware & Construction Supply | 305.76 | 1 |  | 2026 Job Detail Report.pdf (Sage Timberline export, printed 04/03/2026 1:51PM, 106 pages)
| 1175FE | Ferguson Enterprises, Inc. #3007 | 296.86 | 2 |  | 2026 Job Detail Report.pdf (Sage Timberline export, printed 04/03/2026 1:51PM, 106 pages)
| 1421RA | R.A. Brown Backflow Testing | 186 | 1 |  | 2026 Job Detail Report.pdf (Sage Timberline export, printed 04/03/2026 1:51PM, 106 pages)
| 1130CS | Consolidated Supply Co. | -323.4 | 1 |  | 2026 Job Detail Report.pdf (Sage Timberline export, printed 04/03/2026 1:51PM, 106 pages)