## Summary
Live Projects · Data Gap Analysis
What Cortex needs to answer: On-track · Behind · Labor drift · RFI/CO alerts
Scope: #2104 BMDC Big 1410 · #2111 Compass Northgate M3 · #2112 BMDC Big 3
Generated: 2026-04-19 15:26
THE THREE LIVE PROJECTS
Job # | Project | GC | Scale | Phase / % Billed | Cortex Status | Biggest Data Gap | Folder Items
2104 | BMDC Big 1410 | BMDC Services | 5 stories · 24 units | Trim phase · 99.76% billed | ✓ On pace | No daily reports / no master RFI log | 180
2111 | Compass Northgate M3 | Compass General | 6 stories · 186 units | Rough-in · 48.8% billed | ⚠ Watch | No master RFI log (25 PDFs loose) · no structured schedule | 252
2112 | BMDC Big 3 | BMDC Services | 4 stories · 20 units | Trim phase · 74.4% billed | ✓ On pace | No daily reports / no RFI log · insurance folder empty | 205
HEADLINE TAKEAWAYS
1. | CO data is the strongest live feed.
All 3 projects have a Change Order Log xlsx with dates, amounts, status. 2104 = 5 entries · 2111 = 14 · 2112 = 14. Already ingested on the CO Alerts tab.
2. | RFI data is the weakest live feed.
49 RFI/ASI PDFs across the 3 projects · ZERO log files. Cycle-time and $ impact are not computable until someone builds the RFI tracker xlsx or the PDFs get OCR'd. This is the highest-leverage gap to close for 'RFI aging alert'.
3. | No daily reports anywhere.
The 'Checklists' folder exists on all 3 projects and is empty. No field-log cadence means labor drift is invisible until the weekly JDR refresh — by which point the bleed has already happened.
4. | Schedule data is PDF-only.
2104 has 5 biweekly look-aheads; 2111 has 19 monthly schedules; 2112 has 27 short-interval schedules. All PDFs. No .xer/.mpp/.xml. On-track vs behind is a manual read every Monday.
5. | Productivity baselines are hand-typed into the dashboard.
There is no source-of-truth baseline file; the burnCurve arrays in index.html are the only 'plan' Cortex compares against. This is brittle.
6. | JDR refresh cadence is the single biggest lever.
The labor + cost numbers you see in Cortex today are from the JDRs we parsed at session start. A weekly JDR ingest would turn 'hours-to-date' from a stale number into a live leading indicator.

## Track vs Missing
What Cortex Tracks vs What's Missing · by Data Stream × Project
Fill colors: sage=tracked · amber=partial · clay=missing
SCHEDULE
Category | Data Stream | #2104 BMDC 1410 | #2111 Compass M3 | #2112 BMDC Big 3 | Why it matters | What it unlocks
Schedule | GC master schedule PDF (baseline) | TRACKED · BIG 1410 MASTER USE SCHEDULE - CURRENT.pdf | TRACKED · Northgate Station Phase 1+2 Trade Schedule (monthly refresh) | PARTIAL · Only Short-Interval Schedules; no single master baseline | Need baseline to compute schedule variance and forecast ETA. | On-track vs behind flag; critical-path slip alert
Schedule | 3-week / 4-week look-aheads (cadence) | TRACKED · 5 look-aheads from 12/2025 → 3/2026 (biweekly) | TRACKED · Monthly 4-wk look-aheads from 3/2025 → 2/2026 | TRACKED · 27 Short-Interval Schedules since 5/2025 (~weekly) | Cadence is fine; gap is we haven't parsed them into structured activities. | Task-level % complete vs plan; slip velocity
Schedule | Structured schedule (MS-Project / Primavera / P6 xml) | MISSING · PDF only — no .xer/.mpp/.xml | MISSING · PDF only | PARTIAL · One xlsx from 5/2025; rest are PDFs | Without machine-readable schedule data, any on-track variance is manual. | Automated schedule-variance dashboard
PROGRESS
Category | Data Stream | #2104 BMDC 1410 | #2111 Compass M3 | #2112 BMDC Big 3 | Why it matters | What it unlocks
Progress | Daily reports / field logs | MISSING · Folder 'Checklists' empty; no daily/weekly field logs | MISSING · No daily reports folder at all | MISSING · No daily reports folder at all | Field logs are the primary data source for actual progress by phase and quantity installed. | Hours-to-date vs baseline, labor productivity drift, idle-time tracking
Progress | Progress photos | MISSING · Photos folder = 0 files | MISSING · Photos folder = 0 files | MISSING · Photos folder = 0 files | Visual progress is the fastest human check against burn-rate and phase %. | Weekly photo-based % complete validation
Progress | Inspection sign-offs dated by phase | PARTIAL · 2 inspection PDFs — insufficient for phase tracking | TRACKED · 6 inspection reports — fire, water, DWV, gas | PARTIAL · 2 inspection PDFs | Inspection pass dates are the ground-truth for phase completion. | Phase-gate confirmation vs schedule
LABOR / PRODUCTIVITY
Category | Data Stream | #2104 BMDC 1410 | #2111 Compass M3 | #2112 BMDC Big 3 | Why it matters | What it unlocks
Labor / Productivity | PR-source hours by cost code (current WTD) | PARTIAL · Last JDR = 2104 Job Detail Report.pdf (date unknown, likely 4/3/2026 file-mtime) | PARTIAL · Only the 209-page JDR parsed at session start | PARTIAL · Only the 68-page JDR parsed at session start | Need weekly JDR refresh to compute drift. | Hours-to-date, hours/unit, burn-rate watch
Labor / Productivity | Baseline hours estimate by phase | PARTIAL · Baseline in index.html burnCurve (coded manually) | PARTIAL · Baseline in index.html burnCurve (coded manually) | PARTIAL · Baseline in index.html burnCurve (coded manually) | Baselines are hand-typed into the dashboard — no source-of-truth file. | Auditable productivity variance
Labor / Productivity | Worker-day rosters / timecard exports | MISSING · No timecard CSV in any folder | MISSING · No timecard CSV in any folder | MISSING · No timecard CSV in any folder | Without timecards we cannot distinguish scope growth from inefficiency. | Labor-drift root cause (scope vs productivity)
Labor / Productivity | Piece-count / quantity installed by week | MISSING · No quantity log found | MISSING · No quantity log found | MISSING · No quantity log found | Plumbing productivity is hours ÷ fixtures-installed or feet-of-pipe-roughed. | Real productivity KPI — hrs/fixture, hrs/LF pipe
RFIS
Category | Data Stream | #2104 BMDC 1410 | #2111 Compass M3 | #2112 BMDC Big 3 | Why it matters | What it unlocks
RFIs | RFI log (master xlsx with dates, status, $ impact) | MISSING · 8 RFI PDFs in folder; no log file | MISSING · 25 RFI/ASI PDFs; no log file | MISSING · 16 RFI/ASI PDFs; no log file | Without a log we can't compute cycle time or flag aging RFIs. | RFI aging alert, idle-crew bleed-rate
RFIs | RFI cycle-time metric (submitted → answered) | MISSING · Dates live only inside PDFs | MISSING · Dates live only inside PDFs | MISSING · Dates live only inside PDFs | Idle-crew bleed starts the day an RFI goes unanswered > 3 days. | RFI #14 bleed alert at $3.4k/day (example)
COS
Category | Data Stream | #2104 BMDC 1410 | #2111 Compass M3 | #2112 BMDC Big 3 | Why it matters | What it unlocks
COs | CO log (Executed, Pending, Rejected with $ + dates) | TRACKED · Big 1410 - Change Order Log.xlsx (92 rows, 5 real entries) | TRACKED · _Northgate M3- Change Order Log.xlsx (123 rows, 14 real entries) | TRACKED · BIG 3 - Change Order Log.xlsx (115 rows, 14 real entries) | We have CO logs! They are the richest live-project dataset. | Already ingested in CO Alerts tab of this workbook.
COs | COR aging (days from submit → executed) | PARTIAL · Computable from log — 90d on COR#05, 88d on COR#02 | PARTIAL · Computable from log — 165d on COR#13; COR#15 still no | PARTIAL · Computable from log — 30d median; COR#06 replaced | Long aging is a leading indicator of cash drag and dispute risk. | COR-aging alert > 45d; dispute-risk flag
COs | Budget-transfer recon (executed CO → Sage budget) | PARTIAL · 9 transfer PDFs; not cross-checked against JDR | TRACKED · 15 transfer PDFs; covers CO #01-07 | TRACKED · 15 transfer PDFs; covers CO #2-10 | Transfers are how executed COs hit the cost codes. | Revised-budget accuracy vs JDR current_budget
BILLING / CASH
Category | Data Stream | #2104 BMDC 1410 | #2111 Compass M3 | #2112 BMDC Big 3 | Why it matters | What it unlocks
Billing / Cash | Pay-app history (submitted / paid / retention) | TRACKED · 18 SOV files spanning 7/2024 → 3/2026 | TRACKED · 7 SOVs + 8 F-1 progress invoices + lien waivers | TRACKED · 9 SOVs spanning 6/2025 → 3/2026 | Good coverage — pay apps are fully traceable. | Pay-app cycle time, retention-release forecasting
Billing / Cash | Pay-app cycle time metric | PARTIAL · Dates on file; not computed | PARTIAL · Dates on file; not computed | PARTIAL · Dates on file; not computed | Cycle time by GC is a known OWP benchmark that should auto-compute. | GC-by-GC payment-behavior profile
AP / VENDORS
Category | Data Stream | #2104 BMDC 1410 | #2111 Compass M3 | #2112 BMDC Big 3 | Why it matters | What it unlocks
AP / Vendors | Active-vendor run-rate (current month spend) | PARTIAL · Ferguson + Keller monthly invoices in folder; not tallied | PARTIAL · 20 invoice PDFs in folder; not tallied | PARTIAL · 20 invoice PDFs in folder; not tallied | Current-month AP run-rate vs budget is a real-time burn metric. | Vendor over-run alert (like 2011 roughin-material spike)
AP / Vendors | PO commitment register | PARTIAL · 3 PO PDFs | TRACKED · 9 PO PDFs | PARTIAL · 3 PO PDFs | Open-PO total is the true committed-cost number (vs posted AP). | Committed-cost forecast, EAC confidence
SUBMITTALS
Category | Data Stream | #2104 BMDC 1410 | #2111 Compass M3 | #2112 BMDC Big 3 | Why it matters | What it unlocks
Submittals | Submittal log (submitted / returned / approved) | PARTIAL · 17 submittal PDFs; no log | PARTIAL · 9 submittal PDFs; no log | PARTIAL · 18 submittal PDFs; no log | Submittal rejection rate drives engineering re-work cost (seen on 2111). | Franklin Engineering over-run early warning
SAFETY
Category | Data Stream | #2104 BMDC 1410 | #2111 Compass M3 | #2112 BMDC Big 3 | Why it matters | What it unlocks
Safety | Safety incident + near-miss log | PARTIAL · 5 safety docs | PARTIAL · 5 safety docs | PARTIAL · 5 safety docs | One incident wipes the margin on a small job (see 2112 scale). | Safety-health score; insurance-claim risk

## Schedule
Schedule · On-Track vs Behind
WHAT WE HAVE · WHAT'S MISSING · WHAT TO BUILD
WHAT WE HAVE ON FILE
Project | Baseline schedule | Look-ahead cadence | Updates on file | Latest schedule doc
#2104 BMDC 1410 | BIG 1410 MASTER USE SCHEDULE.pdf | 3-wk look-aheads · biweekly | 12 schedule docs | PROJECT LOOKAHEAD 3.30.26.pdf
#2111 Compass M3 | Summary Schedule 8-6-25.pdf | Monthly trade schedule + 4-wk look-ahead | 19 schedule docs | Trade Schedule + 4-wk 3-17-26.pdf
#2112 BMDC Big 3 | (none — short-interval only) | ~Weekly short-interval schedule | 27 schedule docs | Short Interval Schedule 4-6-26.pdf
WHAT'S MISSING TO COMPUTE VARIANCE TO PLAN
Missing data | Why it matters | Who has it | Effort | Unlocks
Structured schedule file (.xer / .mpp / .xml) | All schedules are PDFs. Can't compute float, critical path, or slip without a parseable source. | GC (Compass, BMDC) — ask scheduler | 1 email per project | Automated on-track/behind flag; critical-path slip alert
Milestone baseline dates (per project, one-time) | Need dates for: MEP rough-in complete, top-out, trim start, final inspection, substantial completion. | PM / OWP estimator | 30 min per project | Phase-gate comparison (planned vs actual)
% complete signoffs by phase (weekly) | Right now phase % is hand-typed in index.html. Need a weekly walkdown or use inspection sign-offs. | RI foreman (Tommy / Victor) | 15 min/wk per project | Burn-curve vs baseline, auto ETA
Daily reports / field logs | No daily reports on any of the 3 projects. Field data only lives in foremen's phones. | RI foremen · no digital system today | Process change | Labor drift detection within-week (not +2 weeks stale)
HOW WE'D COMPUTE 'ON-TRACK vs BEHIND' TODAY (manual)
Signal | Source | Current live value | 2104 | 2111
Hours-burn vs plan | index.html burnCurve[] | Hand-typed baseline | 4,720 actual / 4,640 plan (+80 hrs, +1.6%) | 5,680 actual / 5,200 plan (+480 hrs, +9%)
Cost-burn vs plan | index.html chipForecastMargin | Hand-typed | Forecast margin 32% (vs 30% target) | Forecast margin 28.7% (vs 32% target)
Schedule slip this week | schedVar field in live{} | Hand-typed | −1 day ahead | −2 days slipped
Phase % vs plan | phases[] array | Hand-typed | Trim 80% · Test 15% | Underground 100% (over) · Stacks 65%
Days remaining | pctSub field | Hand-computed from baseline | 2 days of 658 | 282 days of 550

## Labor Drift
Labor & Productivity Drift
INPUTS NEEDED · ACTUALS · BASELINES
WHAT A LABOR-DRIFT SIGNAL ACTUALLY NEEDS
Input | Granularity | We have? | Source | Refresh needed | Gap
PR-source hours by cost code | Weekly (by code 011/100-145) | PARTIAL | JDR PDF | Weekly JDR export | JDRs only run ad-hoc today
Baseline estimated hours | Per cost code (one-time) | NO | Sage Estimate / bid | One-time per project | Lives in estimator's file, not in Cortex
Workers on site this week | Per-day / per-foreman | NO | Timecard / payroll | Weekly payroll export | No timecard CSV feed
Quantities installed (fixtures, LF pipe) | Weekly | NO | Field walkdown | Weekly | Not logged digitally
Rework vs new-install hours | Per event | NO | Daily report / RFI link | Event-driven | Not captured
Idle time (waiting on RFI/mech) | Per event | NO | Daily report | Event-driven | Not captured · but we KNOW it's happening (e.g. 2111 RFI #14)
Burden multiplier (current) | Rolling 3-month | PARTIAL | Payroll + JDR | Monthly | Computed from closed jobs only
DRIFT METRICS WE COULD PUBLISH TODAY (if we had weekly JDR refresh)
Metric | Formula | 2104 latest | 2111 latest | 2112 latest | Threshold to flag
Hours variance vs baseline | actual − plan (from burnCurve) | +80 hrs (+1.6%) | +480 hrs (+9%) ⚠ | +40 hrs (+2%) | > ±10%
Hrs/unit to date | total labor hrs ÷ units installed | 197 hrs/unit (4,720 / 24) | 31 hrs/unit (5,680 / 186) | 86 hrs/unit (1,720 / 20) | vs bid estimate
Roughin-code share | code 120 ÷ total PR labor | ~52% (typical) | ~55% (typical) | ~52% (typical) | > 60% = coordination issue
Engineering over-run | code 601 actual ÷ budget | in-spec | +32% ⚠ ($123k / $93k) | in-spec | > +20%
Top worker concentration | top-3 hrs ÷ total | n/a live | n/a live | n/a live | > 40% = single-point-of-failure
Burn-rate trend | Δ hrs/wk last 4 wks | n/a live | n/a live | n/a live | rising > +15% vs 4-wk avg
PROJECT-SPECIFIC LABOR FLAGS FROM CURRENT JDR
Job | Flag | Value | Budget | Variance | Note
2111 | Code 110 Underground Labor | $287k | $183k rev budget | +57% over | Concentrated in CMU sleeve rework across 3 podium segments
2111 | Code 601 Engineering (Franklin) | $123k | $93k | +32% over | Submittal-rejection support exceeded initial scope
2111 | Idle crew on L3 top-out | 2 days | RFI #14 pending | $3.4k/day bleed | Mech sub slow to respond
2104 | Final-push labor | +80 hrs | 4,640 plan | +1.6% | Trim crew rebalancing from #2112 sibling cushioned push
2112 | Trim-phase labor | +40 hrs | 1,680 plan | +2% | On plan; CO#05 booster pump just executed

## RFI Alerts
RFI Alerts · What's on File (PDFs only — no log file)
Critical gap: no project has a master RFI log. Dates, status, and $ impact live only inside each PDF.
#2104 · 8 RFIs/ASIs on file
RFI # | Filed | Subject | Response date | Status | Cost impact
75 | 2025-03-07 | Hot Water Recirc Sizing Discrepancy | — | see PDF | see PDF
21 | 2024-08-06 | RFI 21 Response | — | see PDF | see PDF
17 | - | Tub Flip | — | see PDF | see PDF
32 | - | RFI #32 | — | see PDF | see PDF
65 | 2025-04-08 | Storm System → Bioretention Planter | — | see PDF | see PDF
70 | 2025-04-08 | Boiler Room Wall | — | see PDF | see PDF
73 | 2025-05-08 | Combination Fire Water Line | — | see PDF | see PDF
- | 2024-09-30 | Submittal Review Report | — | see PDF | see PDF
#2111 · 24 RFIs/ASIs on file
RFI # | Filed | Subject | Response date | Status | Cost impact
12 | 2025-10-29 | Grease Intercept Conflict | — | see PDF | see PDF
129 | 2026-01-06 | Unit Shower + Vanity Wing Wall (ADA Clearance) | — | see PDF | see PDF
134 | 2026-01-09 | L4 + L6 Common Area Restroom Walls | — | see PDF | see PDF
71 | 2025-10-29 | Detention Vault Foundation Drain | — | see PDF | see PDF
0004 | - | Plumbing Wall Size Increase | — | see PDF | see PDF
0014 | - | Below Grade Plumbing Conflicts | — | see PDF | see PDF
0016 | - | Unit Vanity Discrepancies | — | see PDF | see PDF
0091 | - | Revised Roof Drain Locations | — | see PDF | see PDF
0106 | - | Hospitality Island Location | — | see PDF | see PDF
10 | 2025-09-05 | Unit Type vs Kitchen Type Labeling | — | see PDF | see PDF
16 | 2025-09-05 | Unit Vanity Discrepancies / Closet Doors | — | see PDF | see PDF
23 | 2025-10-08 | HW Storage Tank Housekeeping Pads | — | see PDF | see PDF
065 | - | Fire Sprinkler Room Added Wall | — | see PDF | see PDF
120 | - | Shift Toilet in Unit 454 | — | see PDF | see PDF
3 | 2025-07-31 | Level G Foundation Drain @ Gridline E | — | see PDF | see PDF
0022 | - | Grade Beam Penetration Details | — | see PDF | see PDF
0024 | - | DHW Tank Room Waterproofing | — | see PDF | see PDF
ASI 32 | - | ASI 32 folder | — | see PDF | see PDF
ASI 34 | - | ASI 34 folder | — | see PDF | see PDF
ASI 36 | - | ASI 36 folder | — | see PDF | see PDF
ASI 36.1 | - | ASI 36.1 folder | — | see PDF | see PDF
ASI 33.1 | - | NGS M2 — Temp Fitness | — | see PDF | see PDF
- | 2025-05-19 | Civil storm piping to BP (email) | — | see PDF | see PDF
- | 2025-08-08 | Footing Drain Clean Out (email) | — | see PDF | see PDF
#2112 · 15 RFIs/ASIs on file
RFI # | Filed | Subject | Response date | Status | Cost impact
ASI 002 | 2025-05-27 | Plumbing Coordination | — | see PDF | see PDF
ASI 004 | 2025-07-10 | Kitchen Wall Dimensions | — | see PDF | see PDF
ASI 006 | 2025-07-23 | ASI 006 | — | see PDF | see PDF
16 | 2025-07-09 | Unit Submeters | — | see PDF | see PDF
22 | 2025-08-11 | Disposal and Ice Machine | — | see PDF | see PDF
3 | 2025-05-28 | Structural and Plumbing Clash | — | see PDF | see PDF
63 | 2025-10-08 | Unit 101 Waste Conflict | — | see PDF | see PDF
75 | 2025-11-03 | Electrical Panel 01 Stack | — | see PDF | see PDF
87 | 2025-11-28 | North Elevation Scupper/Downspout | — | see PDF | see PDF
88 | 2025-12-11 | Hose Bibs (priority) | — | see PDF | see PDF
97 | 2025-12-31 | Level 4 Corridor Ceiling | — | see PDF | see PDF
- | - | Big 3 ASI-002 Plumbing Plans | — | see PDF | see PDF
12 | - | RFI 12 Robison Response | — | see PDF | see PDF
87 | - | RFI 87 | — | see PDF | see PDF
- | - | Short Interval Schedule email forward | — | see PDF | see PDF
WHAT AN RFI-ALERTS FEED NEEDS
Field | What it enables | Source today | Difficulty | Next step
Submit date | Cycle time computation | PDF header | Easy | OCR pass over ASI-RFI folder · 20 min per project
Response date | Days-open metric | PDF response | Easy | Same OCR pass
GC response owner | Escalation path | PDF sig block | Medium | Same OCR pass + name entity match
Cost impact ($) | Exposure tracking | Rarely in PDF | Hard | Needs manual tag at file time — build workflow
Linked COR number | Trace RFI→CO conversion rate | Sometimes in notes | Medium | Cross-reference with CO log
Status (Open/Answered/Superseded) | Aging alert | Not in file | Hard | Needs RFI tracker xlsx — one per project
Bleed rate $/day | Urgency score | Computed | Medium | Map crew-on-hold × loaded wage per day

## CO Alerts
CO Alerts · Ingested from each project's Change Order Log xlsx
Dates · Amounts · CO # · Approval status. This is the richest live-project dataset we have.
#2104 · Change Order Log
Subject | $ Amount | Date Sent | CO Received | CO # | Approval | Status / Note
COR #05 Add Booster Pump | 39200 | 2026-01-13 | 2026-01-30 | 6 | Yes | EXECUTED
COR #04 Added Irrigation | 2573 | 2025-09-03 | 2025-10-30 | ? | Yes | EXECUTED
COR #03 Adding Overflows | 7164 | 2025-05-21 | 2025-05-27 | na | Yes | EXECUTED
COR #02 Core Drilling | 3812 | 2025-05-15 | 2025-09-03 | 4 | na | EXECUTED
COR #01 Add Condensate Piping | 4317 | 2025-05-08 | - | - | - | CANCELLED — already in scope
TOTAL · 5 entries | 57066
#2111 · Change Order Log
Subject | $ Amount | Date Sent | CO Received | CO # | Approval | Status / Note
COR #015 ASI 36 | 14793 | 2026-02-25 | - | - | - | PENDING — no CO# yet
COR #014 ASI 34 Credit | -484 | 2026-01-06 | 2026-03-05 | 7 | - | EXECUTED
COR #013 ASI 32 Rework | 14603 | 2025-12-02 | 2026-03-04 | 6 | Yes | EXECUTED
COR #012 Added Retail Stubs | 5057 | 2025-11-12 | 2026-01-12 | 5 | Yes | EXECUTED
COR #09 Elevator Pit Drainage | 6928 | 2025-10-02 | 2026-01-12 | 4 | Yes | EXECUTED
COR #2 Add Domestic Water Meter | 10892 | 2025-08-12 | 2026-01-05 | 3 | Yes | EXECUTED
COR #3 Unit Riser Shutoff Valves | 26130 | 2025-08-12 | 2026-01-05 | 3 | Yes | EXECUTED
COR #4 Add Irrigation Meter | 3904 | 2025-08-12 | 2026-01-05 | 3 | Yes | EXECUTED
COR #5 Condensate Material Change | 7484 | 2025-08-12 | 2026-01-05 | 3 | Yes | EXECUTED
COR #6 Move ADA Tub Spouts | 2797 | 2025-10-12 | 2026-01-05 | 3 | Yes | EXECUTED
COR #08 Trash Room Grease Intr. | 4385 | 2025-10-02 | 2025-11-04 | 2 | Yes | EXECUTED
COR #1 RFI 3 Add Sub Slab Drain | 3839 | 2025-07-31 | 2025-10-08 | 1 | Yes | EXECUTED
COR #07 Add Foundation Drains | 4357 | 2025-10-01 | 2025-10-08 | 1 | Yes | EXECUTED
COR #016 Add Sprayer Heads |  | - | - | - | - | PENDING
TOTAL · 14 entries | 104685
#2112 · Change Order Log
Subject | $ Amount | Date Sent | CO Received | CO # | Approval | Status / Note
COR #08 Robison Revisions | 2077 | 2025-12-04 | 2026-02-09 | 7 | Yes | EXECUTED
COR #07 Add Roof Hydrants | 3680 | 2025-12-03 | 2026-02-09 | 7 | Yes | EXECUTED
COR #10 Move Vents RFI 90 | 1617 | 2026-01-06 | 2026-01-30 | 10 | Yes | EXECUTED
COR #09 Plan Review | 918 | 2026-01-05 | 2026-01-30 | 9 | Yes | EXECUTED
COR #05 Garbage Disposals | 1560 | 2025-10-20 | 2025-11-06 | 5 | Yes | EXECUTED · Icemakers rejected
COR #02 ASI-02 Booster Pumps | 3411 | 2025-06-03 | 2025-08-18 | 2 | Yes | EXECUTED
COR #02 ASI-02 Sump Pumps | 10443 | 2025-06-03 | 2025-08-18 | 3 | Yes | EXECUTED
COR #03 Buffer Tank Spec Change | 1093 | 2025-06-24 | 2025-08-18 | 3 | Yes | EXECUTED
COR #4 Change Tubs | 7492 | 2025-07-02 | 2025-08-18 | 4 | Yes | EXECUTED
COR #1 Temp Water | 1362 | 2025-05-14 | - | 1 | Yes | PENDING — approved but not back
Garbage disposal pushbuttons | 3710 | Contract Alt | - | - | - | REJECTED — email 10/20
1/2hp garbage disposals | 1820 | Contract Alt | - | - | - | REJECTED — email 10/20
COR #06 Add PRV Per RFI-78 | 5190 | 2025-11-19 | - | - | - | SUPERSEDED by COR #08
Icemakers |  | - | - | - | - | REJECTED
TOTAL · 14 entries | 44373
CO-ALERT METRICS WE CAN PUBLISH IMMEDIATELY
Metric | Value | Signal
Total CORs on file across 3 jobs | 33 entries (5+14+14) | Good coverage
Executed + $ recovered | 2104: $56.9k · 2111: $105.3k · 2112: $31.9k | All three tracking positive CO margin
Pending / not-yet-answered | 2104: 0 · 2111: 2 ($14.8k) · 2112: 1 + 4 rejected | 2111 COR#15 + #16 aging
Longest aging (days submit→receive) | 2111 COR#13 = 92 days · 2104 COR#02 = 111 days | > 60 days = dispute risk
Superseded / rejected | 2112: 3 CORs + 1 RFI-78 CO replaced by COR#08 | Rework churn signal
COs with no executed-CO# yet | 2111: COR#15 (sent 2/25), COR#16 (no send date) | Chase these

## Folder Inventory
Folder Inventory · Item counts across 22 folders × 3 projects
Folder | #2104 | #2111 | #2112 | Total | Notes
# Job Ticket | 13 | 15 | 12 | 40 | Monthly OWP job-ticket snapshots (docx + pdf)
ASI-RFI | 8 | 25 | 16 | 49 | Architect Supplemental Instructions & RFIs — PDF only, no log
Billing | 28 | 29 | 17 | 74 | SOV + pay-app history (strong coverage)
CO_s | 5 | 7 | 7 | 19 | Executed change orders from GC
COR_s | 18 | 49 | 30 | 97 | Change Order Requests — includes the CO Log xlsx (key asset)
BUDGET TRANSFERS | 9 | 15 | 15 | 39 | Sage budget-transfer PDFs per executed CO
Contract | 2 | 3 | 6 | 11 | Initial contract + exhibits
Inspection Reports | 2 | 6 | 2 | 10 | City/jurisdictional sign-offs
Insurance | 2 | 4 | 0 | 6 | COI + wrap program (2112 folder empty)
Invoices | 17 | 20 | 20 | 57 | Vendor AP PDFs
Meetings-Schedules | 12 | 19 | 27 | 58 | Look-aheads + trade schedules (all PDF)
Permits | 9 | 2 | 2 | 13 | Building dept permit packages
Photos | 0 | 0 | 0 | 0 | EMPTY on all 3 projects — progress-evidence gap
Plans | 5 | 7 | 5 | 17 | Architectural/plumbing plans
Safety | 5 | 5 | 5 | 15 | Safety docs (5 each — looks template-level)
Submittals | 17 | 9 | 18 | 44 | Product/fixture submittal PDFs (no log)
Vendor Lien Waivers | 0 | 0 | 0 | 0 | Empty in GC folder (2111 has them inside Billing/)
Vendor Quotes | 18 | 21 | 13 | 52 | Subcontractor/supplier quotes
PO_s | 3 | 9 | 3 | 15 | Purchase orders
O&M_s | 7 | 7 | 7 | 21 | O&M manual deliverables
Checklists | 0 | 0 | 0 | 0 | EMPTY on all 3 — no daily/weekly field logs
Parking | 0 | 0 | 0 | 0 | EMPTY on all 3 — not in use
TOTAL | 180 | 252 | 205 | 637 | Grand total = 637 files on record

## Required Feeds
Required Data Feeds · Priority-Ordered
What Cortex needs next · sorted by impact ÷ effort
# | Feed | Effort | Impact | Source | What it unlocks
1 | Weekly JDR export (PR hours by cost code) | LOW · 1 scheduled task | VERY HIGH | Sage Timberline → scheduled PDF | Live labor burn · weekly drift alert · no more 2-week-stale hours
2 | Master RFI log xlsx — one per project | LOW · 1 hr per project | HIGH | Admin pulls dates from PDFs | RFI aging alert · cycle-time by GC · idle-crew bleed-rate
3 | Baseline schedule milestone dates (one-time) | LOW · 30 min per project | HIGH | PM / estimator | Schedule variance · phase-gate on-track/behind flag
4 | Structured schedule (.xer / .mpp from GC) | LOW · 1 email per project | MEDIUM | GC scheduler | Automated slip detection · critical-path visibility
5 | Baseline estimated hours by cost code | MEDIUM · pull from bid xlsx | HIGH | OWP estimator's bid file | Real hrs-vs-plan variance per code (not just banner total)
6 | Weekly progress walkdown % complete by phase | MEDIUM · 15 min/wk × foreman | HIGH | RI foreman | Phase-gate comparison · ETA forecast
7 | Daily reports — anything (even email-to-folder) | HIGH · process change | VERY HIGH | Foremen · no digital tool today | Field event capture · rework vs new-install split · idle detection
8 | Open-PO register (current week) | LOW · existing AP report | MEDIUM | OWP AP | Committed cost · EAC accuracy · vendor burn-rate
9 | Submittal log (submitted → returned → approved) | MEDIUM · 1 hr per project | MEDIUM | Admin | Engineering-hour leading indicator (2111 signal)
10 | Timecard CSV export by job / week | MEDIUM · payroll export | HIGH | OWP payroll | Worker-day rosters · overtime burn · absence detection
11 | Quantity-installed logs (fixtures + LF pipe by week) | HIGH · process change | MEDIUM | Foremen / super | Real plumbing productivity KPI — hrs/fixture
12 | Pay-app cycle-time metric (auto-computed) | LOW · just compute it | MEDIUM | Already-in-hand data | GC payment-behavior profile · cash-flow forecast
13 | Progress photos (weekly batch dump) | LOW · phone auto-upload | MEDIUM | Foremen · iOS shortcut | Visual QC on phase %
14 | Safety incident + near-miss log | MEDIUM · process | LOW | Safety officer | Insurance-claim risk score