## Overview
Job #2009 · Chinn Greenwood Apartments
Cortex JCR Summary • Chinn Construction, LLC • Seattle, WA • 168-unit apartment building • Jul 2012 – Oct 2013 (~16 months)
PROJECT OVERVIEW
Project Job # | 2009
Project Name: | Chinn Greenwood Apartments
General Contractor | Chinn Construction, LLC
Location | Seattle, WA
Project Duration | Jul 2012 – Oct 2013 (~16 months)
Total Unique Documents | Greenwood folder: Contract, Billing (aggregate + 11 SOVs), PO Scheduled (48), Permits, Plans, Submittals
CONTRACT VALUE |  | NET PROFIT |  | DIRECT COST |  | LABOR HOURS
$394,208 |  | $113,840 |  | $280,368 |  | 3,928
Original $384,900 + $9,308 COs |  | 28.9% margin |  | 71.1% of revenue |  | 23 workers
COST BREAKDOWN
Category | Budget | Actual | Variance | % Budget | % of Cost
Labor | 72340 | 80901.5 | -8561.5 | 111.8% | 28.86%
Material | 195311 | 151064.39 | 44246.61 | 77.35% | 53.88%
Overhead | 10885 | 7510.52 | 3374.48 | 69% | 2.679%
Burden | 38464.22 | 40891.46 | -2427.24 | 106.3% | 14.58%
TOTAL | 317000.22 | 280367.87 | 36632.35 | 88.44% | 100%
PROJECT PROFILE
Metric | Value | Metric | Value | Metric | Value
Plumbing Units | 168 | Water Closets | 168 | Kitchen Sinks | 168
Total Fixtures | 812 | Lavatories | 168 | Tubs | 168
Fixtures / Unit | 4.83 | Auto Washers | 140 | Showers | 0
Stacks | 36 | Duration | 16 mo | Cost Codes | 26
SOURCES
Job #2009 — Chinn Greenwood Apartments • GC: Chinn Construction, LLC • Seattle, WA
Canonical source: 2009 Job Detail Report.pdf (49 pages, OWP Sage Timberline export)
Cost codes parsed: 26
Unit count (168) and fixture count (812) from greenwood h20 stacks.xls and trim POs
3-level building + lobby: L1 (18 units), L2 (18 units), L3 (18 units), LW (amenity) × south/north stacks
Billing: GREENWOOD AGGREGATE BILLING.xlsx (11 pay apps Jul 2012 – Oct 2013)
Final contract $394,208 (original $384,900 + $9,308 COs)

## Budget vs Actual
Budget vs Actual — All Cost Codes
Code | Description | Orig Budget | Rev Budget | Actual | Variance | % Used
LABOR
011 | DS & RD Labor | 1250 | 1250 | 1645 | -395 | 131.6%
100 | Supervision | 3000 | 3000 | 2992 | 8 | 99.73%
101 | Takeoff & Purchase Labor | 2500 | 2500 | 1324 | 1176 | 52.96%
110 | Underground Labor | 5350 | 5350 | 4209 | 1141 | 78.67%
111 | Garage Labor | 8960 | 8960 | 9872 | -912 | 110.2%
112 | Canout Labor | 2000 | 2000 | 1485.5 | 514.5 | 74.28%
120 | Roughin Labor | 34500 | 37530 | 46114 | -8584 | 122.9%
130 | Finish Labor | 10250 | 10320 | 11391.5 | -1071.5 | 110.4%
141 | Water Main/Insulation Lab | 0 | 0 | 0 | 0 | 0%
142 | Mech Room Labor | 1430 | 1430 | 1730 | -300 | 121%
145 | Tub/Shower Labor | 0 | 0 | 138.5 | -138.5 | 0%
MATERIAL
039 | DS & RD Material | 1250 | 1250 | 369.06 | 880.94 | 29.52%
210 | Underground Material | 2800 | 2800 | 2613.58 | 186.42 | 93.34%
211 | Garage Material | 10570 | 10570 | 3972.94 | 6597.06 | 37.59%
212 | Canout Material | 2800 | 2800 | 2749.23 | 50.77 | 98.19%
220 | Roughin Material | 33560 | 32510 | 30742.47 | 1767.53 | 94.56%
230 | Finish Material | 143270 | 143381 | 109975.66 | 33405.34 | 76.7%
241 | Water Main/Insulation Mat | 0 | 0 | 0 | 0 | 0%
242 | Mech Room Material | 2000 | 2000 | 641.45 | 1358.55 | 32.07%
245 | Tub/Shower Material | 0 | 0 | 0 | 0 | 0%
OVERHEAD
600 | Subcontractor | 4800 | 4885 | 2379 | 2506 | 48.7%
601 | Engineering/Plans | 6000 | 6000 | 4990.08 | 1009.92 | 83.17%
603 | Permits & Licenses | 0 | 0 | 141.44 | -141.44 | 0%
BURDEN
995 | Payroll Burden | 28928 | 32694.58 | 34412.05 | -1717.47 | 105.3%
998 | Payroll Taxes | 5532.48 | 5769.64 | 6479.41 | -709.77 | 112.3%
TOTAL | Direct Cost | 310750.48 | 317000.22 | 280367.87 | 36632.35 | 88.44%
SOURCES
Job #2009 — Chinn Greenwood Apartments • GC: Chinn Construction, LLC • Seattle, WA
Canonical source: 2009 Job Detail Report.pdf (49 pages, OWP Sage Timberline export)
Cost codes parsed: 26
Unit count (168) and fixture count (812) from greenwood h20 stacks.xls and trim POs
3-level building + lobby: L1 (18 units), L2 (18 units), L3 (18 units), LW (amenity) × south/north stacks
Billing: GREENWOOD AGGREGATE BILLING.xlsx (11 pay apps Jul 2012 – Oct 2013)
Final contract $394,208 (original $384,900 + $9,308 COs)

## Cost Breakdown
Cost Breakdown — Category Deep Dive
A. CATEGORY SHARE OF DIRECT COST
Category | # Codes | Budget | Actual | Variance | % Budget | % of Cost | Per Unit
Labor | 11 | 72340 | 80901.5 | -8561.5 | 111.8% | 28.86% | 481.5565
Material | 9 | 195311 | 151064.39 | 44246.61 | 77.35% | 53.88% | 899.1928
Overhead | 3 | 10885 | 7510.52 | 3374.48 | 69% | 2.679% | 44.7055
Burden | 2 | 38464.22 | 40891.46 | -2427.24 | 106.3% | 14.58% | 243.4015
B. LARGEST OVERRUNS (Actual > Revised Budget)
Code | Description | Rev Budget | Actual | Overrun | % Over
120 | Roughin Labor | 37530 | 46114 | 8584 | 22.87%
995 | Payroll Burden | 32694.58 | 34412.05 | 1717.47 | 5.253%
130 | Finish Labor | 10320 | 11391.5 | 1071.5 | 10.38%
111 | Garage Labor | 8960 | 9872 | 912 | 10.18%
998 | Payroll Taxes | 5769.64 | 6479.41 | 709.77 | 12.3%
011 | DS & RD Labor | 1250 | 1645 | 395 | 31.6%
142 | Mech Room Labor | 1430 | 1730 | 300 | 20.98%
603 | Permits & Licenses | 0 | 141.44 | 141.44 | 0%
145 | Tub/Shower Labor | 0 | 138.5 | 138.5 | 0%
C. LARGEST SAVINGS (Actual < Revised Budget)
Code | Description | Rev Budget | Actual | Savings | % Under
230 | Finish Material | 143381 | 109975.66 | 33405.34 | 23.3%
211 | Garage Material | 10570 | 3972.94 | 6597.06 | 62.41%
600 | Subcontractor | 4885 | 2379 | 2506 | 51.3%
220 | Roughin Material | 32510 | 30742.47 | 1767.53 | 5.437%
242 | Mech Room Material | 2000 | 641.45 | 1358.55 | 67.93%
101 | Takeoff & Purchase Labor | 2500 | 1324 | 1176 | 47.04%
110 | Underground Labor | 5350 | 4209 | 1141 | 21.33%
601 | Engineering/Plans | 6000 | 4990.08 | 1009.92 | 16.83%
039 | DS & RD Material | 1250 | 369.06 | 880.94 | 70.48%
112 | Canout Labor | 2000 | 1485.5 | 514.5 | 25.72%
SOURCES
Job #2009 — Chinn Greenwood Apartments • GC: Chinn Construction, LLC • Seattle, WA
Canonical source: 2009 Job Detail Report.pdf (49 pages, OWP Sage Timberline export)
Cost codes parsed: 26
Unit count (168) and fixture count (812) from greenwood h20 stacks.xls and trim POs
3-level building + lobby: L1 (18 units), L2 (18 units), L3 (18 units), LW (amenity) × south/north stacks
Billing: GREENWOOD AGGREGATE BILLING.xlsx (11 pay apps Jul 2012 – Oct 2013)
Final contract $394,208 (original $384,900 + $9,308 COs)

## Material
Material Spend Analysis
9 material cost codes • $151,064 JDR material • 13 AP vendors • $174,470 total AP
A. MATERIAL BY COST CODE
Code | Description | Rev Budget | Actual | Variance | % Used | % of Mat | Per Unit
039 | DS & RD Material | 1250 | 369.06 | 880.94 | 29.52% | 0.2443% | 2.1968
210 | Underground Material | 2800 | 2613.58 | 186.42 | 93.34% | 1.73% | 15.557
211 | Garage Material | 10570 | 3972.94 | 6597.06 | 37.59% | 2.63% | 23.6485
212 | Canout Material | 2800 | 2749.23 | 50.77 | 98.19% | 1.82% | 16.3645
220 | Roughin Material | 32510 | 30742.47 | 1767.53 | 94.56% | 20.35% | 182.9909
230 | Finish Material | 143381 | 109975.66 | 33405.34 | 76.7% | 72.8% | 654.617
241 | Water Main/Insulation Mat | 0 | 0 | 0 | 0% | 0% | 0
242 | Mech Room Material | 2000 | 641.45 | 1358.55 | 32.07% | 0.4246% | 3.8182
245 | Tub/Shower Material | 0 | 0 | 0 | 0% | 0% | 0
TOTAL | All Material | 195311 | 151064.39 | 44246.61 | 77.35% | 100% | 899.1928
B. VENDORS BY SPEND (AP)
Vendor | # Invoices | Total Spend | % of AP |  |  |  | Avg Invoice
Ferguson Enterprises, Inc. | 65 | 117439.01 | 67.31% |  |  |  | 1806.754
Keller Supply Company | 14 | 29740.43 | 17.05% |  |  |  | 2124.3164
Mechanical Sales, Inc. | 2 | 16339.3 | 9.365% |  |  |  | 8169.65
Franklin Engineering | 1 | 4895 | 2.806% |  |  |  | 4895
Mickelo Construction LLC | 1 | 2250 | 1.29% |  |  |  | 2250
Quality Concrete Products, Inc. | 4 | 1821 | 1.044% |  |  |  | 455.25
Rosen Supply Company, Inc. | 2 | 1040.84 | 0.5966% |  |  |  | 520.42
Ferguson Enterprises, Inc. #3007 | 1 | 245.19 | 0.1405% |  |  |  | 245.19
Bank of America CC | 1 | 210 | 0.1204% |  |  |  | 210
Capital One Credit Card | 3 | 167.8 | 0.09618% |  |  |  | 55.9333
R.A. Brown Backflow Testing | 1 | 129 | 0.07394% |  |  |  | 129
C.M. Hoskins Company | 2 | 97.4 | 0.05583% |  |  |  | 48.7
DRSi | 1 | 95.08 | 0.0545% |  |  |  | 95.08
TOTAL | 98 | 174470.05 | 100%
SOURCES
Job #2009 — Chinn Greenwood Apartments • GC: Chinn Construction, LLC • Seattle, WA
Canonical source: 2009 Job Detail Report.pdf (49 pages, OWP Sage Timberline export)
Cost codes parsed: 26
Unit count (168) and fixture count (812) from greenwood h20 stacks.xls and trim POs
3-level building + lobby: L1 (18 units), L2 (18 units), L3 (18 units), LW (amenity) × south/north stacks
Billing: GREENWOOD AGGREGATE BILLING.xlsx (11 pay apps Jul 2012 – Oct 2013)
Final contract $394,208 (original $384,900 + $9,308 COs)
Vendor AP ties to JDR 'by Source: AP' line (174,470.05)

## Crew & Labor
Crew & Labor — Per-Worker Breakdown
Worker | Hours | Gross Pay | $/Hour | Tier
Quintanilla, Esteban R | 569 | 17070 | 30 | Senior
Sanders, Allen O | 432.5 | 10872 | 25.1376 | Mid
Mazil, Antonio | 416 | 5264 | 12.6538 | Apprentice
Castro Hernandez, Carlos E | 349 | 7678 | 22 | Mid
Palma Vides, Hugo | 304 | 7600 | 25 | Mid
Ramirez, Lorenzo A | 269 | 3982 | 14.803 | Apprentice
Castro Hernandez, Jose A | 236 | 3304 | 14 | Apprentice
Arreola, Israel A | 221 | 2487 | 11.2534 | Apprentice
Soto Cruz, Jovani | 210.5 | 2859.5 | 13.5843 | Apprentice
Cortes Mendiola, Victor H | 208 | 4136 | 19.8846 | Mid
Meza Fuentes, Erick A | 192 | 2880 | 15 | Apprentice
Gerard, Jeffrey S | 164 | 5435.2 | 33.1415 | Senior
Waites, Thaddeus Z | 160 | 4000 | 25 | Mid
Barnhart, Joseph N | 89.5 | 2507 | 28.0112 | Mid
Paco Leyva, Orlando | 88 | 976 | 11.0909 | Apprentice
Veley, Nathaniel S | 80.5 | 1620 | 20.1242 | Mid
McCabe, Thomas C | 76.5 | 1147.5 | 15 | Apprentice
Reed, Reuben H | 44 | 1100 | 25 | Mid
Sepulveda Gonzalez, Alfredo | 32 | 704 | 22 | Mid
Soto Serna, Cesar E | 8 | 88 | 11 | Apprentice
Hubbard, Robert W | 7 | 224 | 32 | Senior
Hubbard, Dustin R | 1.5 | 16.5 | 11 | Apprentice
Lima Romero, Melvin A | 1 | 17 | 17 | Apprentice
TOTAL (23 workers) | 4159 | 85967.7 | 20.6703
SOURCES
Job #2009 — Chinn Greenwood Apartments • GC: Chinn Construction, LLC • Seattle, WA
Canonical source: 2009 Job Detail Report.pdf (49 pages, OWP Sage Timberline export)
Cost codes parsed: 26
Unit count (168) and fixture count (812) from greenwood h20 stacks.xls and trim POs
3-level building + lobby: L1 (18 units), L2 (18 units), L3 (18 units), LW (amenity) × south/north stacks
Billing: GREENWOOD AGGREGATE BILLING.xlsx (11 pay apps Jul 2012 – Oct 2013)
Final contract $394,208 (original $384,900 + $9,308 COs)
Tier: Apprentice <$18/hr, Mid $18–30, Senior >$30

## Crew Analytics
Crew Analytics
A. TIER DISTRIBUTION
Tier | # Workers | Hours | Gross Pay | % of Hours
Senior | 3 | 740 | 22729.2 | 17.79%
Mid | 9 | 1699.5 | 40217 | 40.86%
Apprentice | 11 | 1719.5 | 23021.5 | 41.34%
B. WAGE STATISTICS
Blended Gross Wage | 20.6703 |  |  | Payroll $ ÷ payroll hours (pre-burden)
Fully-Loaded Wage | 29.2842 |  |  | (Labor + Burden) ÷ total hours
Burden Multiplier | 1.4167 |  |  | Fully loaded ÷ gross wage
Min Worker Rate | 11 |  |  | Cheapest apprentice hour
Max Worker Rate | 33.1415 |  |  | Most expensive foreman hour
Avg Hours / Worker | 180.8261 |  |  | Crew continuity indicator
SOURCES
Job #2009 — Chinn Greenwood Apartments • GC: Chinn Construction, LLC • Seattle, WA
Canonical source: 2009 Job Detail Report.pdf (49 pages, OWP Sage Timberline export)
Cost codes parsed: 26
Unit count (168) and fixture count (812) from greenwood h20 stacks.xls and trim POs
3-level building + lobby: L1 (18 units), L2 (18 units), L3 (18 units), LW (amenity) × south/north stacks
Billing: GREENWOOD AGGREGATE BILLING.xlsx (11 pay apps Jul 2012 – Oct 2013)
Final contract $394,208 (original $384,900 + $9,308 COs)

## Productivity
Productivity — Phase & Unit Metrics
A. LABOR HOURS BY PHASE
Phase | Labor Code | Hours | % of Total | Hours / Unit
DS & RD | 011 | 76 | 1.935% | 0.45238
Supervision | 100 | 90 | 2.291% | 0.53571
Takeoff & Purchasing | 101 | 40 | 1.018% | 0.2381
Underground | 110 | 213.5 | 5.435% | 1.2708
Garage | 111 | 488 | 12.42% | 2.9048
Canout | 112 | 69.5 | 1.769% | 0.41369
Roughin | 120 | 2311 | 58.83% | 13.756
Finish | 130 | 557.5 | 14.19% | 3.3185
Water Main / Insulation | 141 | 16 | 0.4073% | 0.095238
Mech Room | 142 | 63 | 1.604% | 0.375
Tub / Shower | 145 | 4 | 0.1018% | 0.02381
TOTAL |  | 3928.5 | 100% | 23.3839
B. PRODUCTIVITY RATIOS
Metric | Value | Units |  | Notes
Hours / Unit | 23.3839 | hrs |  | Labor hours per residential unit
Hours / Fixture | 4.8381 | hrs |  | Labor hours per plumbing fixture
Revenue / Hour | 100.3457 | $ |  | Top-line per labor hour
Profit / Hour | 28.978 | $ |  | Bottom-line per labor hour
Units / Month | 10.5 | units |  | Build velocity
Fixtures / Month | 50.75 | fix |  | Fixture install pace
Hours / Month | 245.5312 | hrs |  | Monthly labor burn
Revenue / Month | 24638 | $ |  | Monthly billing rate
SOURCES
Job #2009 — Chinn Greenwood Apartments • GC: Chinn Construction, LLC • Seattle, WA
Canonical source: 2009 Job Detail Report.pdf (49 pages, OWP Sage Timberline export)
Cost codes parsed: 26
Unit count (168) and fixture count (812) from greenwood h20 stacks.xls and trim POs
3-level building + lobby: L1 (18 units), L2 (18 units), L3 (18 units), LW (amenity) × south/north stacks
Billing: GREENWOOD AGGREGATE BILLING.xlsx (11 pay apps Jul 2012 – Oct 2013)
Final contract $394,208 (original $384,900 + $9,308 COs)

## PO Commitments
Purchase Order Commitments
7 unique POs • PO amounts not dollar-parsed from individual PDFs • JDR material $151,064
A. COMMITMENTS BY COST CODE
OWP Code | Description → JDR | PO Count | % of POs | JDR Material
32 | 130+230 Trim/Finish | 5 | 71.43%
OTHER | Unclassified | 2 | 28.57%
TOTAL |  | 7 | 100% | 151064.39
B. COMMITMENTS BY VENDOR
Vendor | PO Count | % of POs
OTHER | 6 | 85.71%
FEI | 1 | 14.29%
C. PO COVERAGE NOTES
Total Material Actual (JDR) |  |  | 151064.39
Unique PO Count |  |  | 7
(Dollar PO commitment not extracted — requires per-PDF parse)
SOURCES
Job #2009 — Chinn Greenwood Apartments • GC: Chinn Construction, LLC • Seattle, WA
Canonical source: 2009 Job Detail Report.pdf (49 pages, OWP Sage Timberline export)
Cost codes parsed: 26
Unit count (168) and fixture count (812) from greenwood h20 stacks.xls and trim POs
3-level building + lobby: L1 (18 units), L2 (18 units), L3 (18 units), LW (amenity) × south/north stacks
Billing: GREENWOOD AGGREGATE BILLING.xlsx (11 pay apps Jul 2012 – Oct 2013)
Final contract $394,208 (original $384,900 + $9,308 COs)
PO count is deduplicated by 5-digit PO number extracted from filenames
Vendor/code classification is heuristic (filename keyword match)

## Billing & SOV
Revenue & Billing Reconciliation
11 pay applications • Jul 2012 – Oct 2013 • $394,208 final
A. CONTRACT SUMMARY
Original Contract |  |  |  |  | 384900
Change Orders (net) |  |  |  |  | 9308
Final Contract Value |  |  |  |  | 394208
Retainage (5%) |  |  |  |  | 19710
Net Paid to OWP |  |  |  |  | 374498
B. PAY APPLICATION TIMELINE
App# | Date | Period Billing | Retention | Net This Period | Aggregate | % Complete
1 | 2012-07-20 | 12200 | 610 | 11590 | 11590 | 2.94%
2 | 2012-08-20 | 39500 | 1975 | 37525 | 49115 | 12.46%
3 | 2012-09-20 | 8300 | 415 | 7885 | 57000 | 14.46%
4 | 2012-10-20 | 88500 | 4425 | 84075 | 141075 | 35.79%
5 | 2012-11-15 | 112480 | 5624 | 106856 | 247931 | 62.89%
6 | 2012-12-20 | 13250 | 662.5 | 12587.5 | 260518.5 | 66.09%
7 | 2013-02-19 | 28485 | 1424.25 | 27060.75 | 287579.25 | 72.95%
8 | 2013-03-19 | 6400 | 320 | 6080 | 293659.25 | 74.49%
9 | 2013-04-18 | 48175 | 2408.75 | 45766.25 | 339425.5 | 86.1%
10 | 2013-05-19 | 35494 | 1774.7 | 33719.3 | 373144.8 | 94.66%
11 | 2013-08-13 | 1424 | 71.2 | 1352.8 | 374497.6 | 95%
13 | 2013-10-24 | 19710.4 | 0 | 19710.4 | 392208 | 99.49%
C. BILLING ↔ JDR TIE-OUT
Metric | SOV | JDR | Δ | Status
Final Contract Value | 394208 | 394208 | 0 | TIES
Retainage | 19710 | 19710 | 0 | TIES
Direct Cost | 280368 | 280368 | 0 | TIES
SOURCES
Job #2009 — Chinn Greenwood Apartments • GC: Chinn Construction, LLC • Seattle, WA
Canonical source: 2009 Job Detail Report.pdf (49 pages, OWP Sage Timberline export)
Cost codes parsed: 26
Unit count (168) and fixture count (812) from greenwood h20 stacks.xls and trim POs
3-level building + lobby: L1 (18 units), L2 (18 units), L3 (18 units), LW (amenity) × south/north stacks
Billing: GREENWOOD AGGREGATE BILLING.xlsx (11 pay apps Jul 2012 – Oct 2013)
Final contract $394,208 (original $384,900 + $9,308 COs)

## Insights
Key Insights — Job #2009 Chinn Greenwood Apartments
Narrative observations distilled from the full JDR analysis
MARGIN PROFILE | Net profit of $113,840 on $394,208 revenue = 28.9% gross margin. Direct cost $280,368 absorbs 71.1% of revenue.
VENDOR CONCENTRATION | Ferguson Enterprises, Inc. alone = $117,439 (67% of all AP) across 65 invoices. Total 13 AP vendors, $174,470 total AP spend.
CREW PROFILE | 23 workers for 3,928 hours = 171 avg hrs/worker. Top 3 workers logged 1,418 hrs combined (36% of all labor).
ROUGHIN DOMINANCE | Code 120 Roughin Labor = 2,311 hrs (59% of all labor) and $46,114 actual. Code 230 Finish Material = $109,976 — 39% of total direct cost.
BUDGET DELIVERY | Revised budget was $317,000; actual direct cost $280,368 → $36,632 variance (11.6% under revised budget).
CONTRACT GROWTH | Contract grew from $384,900 to $394,208 — net +$9,308 (2.4%). Retainage of $19,710 (5%) withheld until closeout.
BURDEN RATIO | Burden codes 995 + 998 = $40,891 on $80,902 labor base = 50.5%. In line with OWP's typical 48–50% labor burden.
PROJECT SCALE | 168 units · 812 fixtures · 16 months. Revenue/unit $2,346, hours/unit 23.4, profit/unit $678.
PRODUCTIVITY | Blended labor rate $20.59/hr. Revenue/hour $100. Profit/hour $29. 246 hrs/month burn rate.
FIXTURE DENSITY | 812 fixtures ÷ 168 units = 4.83 fixtures/unit. Material/fixture $186, labor/fixture $100.
BIGGEST QUESTION
How does this job's 28.9% margin compare across similar projects in the OWP portfolio, and what operational levers drove the result — estimating accuracy, vendor pricing, or labor productivity?
SOURCES
Job #2009 — Chinn Greenwood Apartments • GC: Chinn Construction, LLC • Seattle, WA
Canonical source: 2009 Job Detail Report.pdf (49 pages, OWP Sage Timberline export)
Cost codes parsed: 26
Unit count (168) and fixture count (812) from greenwood h20 stacks.xls and trim POs
3-level building + lobby: L1 (18 units), L2 (18 units), L3 (18 units), LW (amenity) × south/north stacks
Billing: GREENWOOD AGGREGATE BILLING.xlsx (11 pay apps Jul 2012 – Oct 2013)
Final contract $394,208 (original $384,900 + $9,308 COs)

## Benchmark KPIs
Benchmark KPIs
Normalized metrics designed for apples-to-apples comparison across all OWP projects
KPI | Data Name | Value | Category | Notes | Confidence | Source Document
Job Number | job_number | 2009 | Profile | OWP job ID | Verified | Benchmark KPIs / Metric Registry — see source tabs
Job Name | job_name | Chinn Greenwood Apartments | Profile |  | Verified | Benchmark KPIs / Metric Registry — see source tabs
General Contractor | general_contractor | Chinn Construction, LLC | Profile |  | Verified | Benchmark KPIs / Metric Registry — see source tabs
Location | location | Seattle, WA | Profile |  | Verified | Benchmark KPIs / Metric Registry — see source tabs
Project Type | project_type | 168-unit apartment building | Profile |  | Verified | Benchmark KPIs / Metric Registry — see source tabs
Duration (months) | duration_months | 16 | Profile | Jul 2012 – Oct 2013 (~16 months) | Verified | Benchmark KPIs / Metric Registry — see source tabs
Unit Count | unit_count | 168 | Profile |  | Verified | Benchmark KPIs / Metric Registry — see source tabs
Total Fixtures | total_fixtures | 812 | Profile |  | Verified | Benchmark KPIs / Metric Registry — see source tabs
Fixtures per Unit | fixtures_per_unit | 4.8333 | Profile |  | Verified | Benchmark KPIs / Metric Registry — see source tabs
Contract Value (Orig) | contract_original | 384900 | Financial |  | Verified | Benchmark KPIs / Metric Registry — see source tabs
Contract Value (Final) | contract_final | 394208 | Financial | After change orders | Verified | Benchmark KPIs / Metric Registry — see source tabs
Change Orders ($) | change_orders | 9308 | Financial |  | Verified | Benchmark KPIs / Metric Registry — see source tabs
Revenue | revenue | 394208 | Financial |  | Verified | Benchmark KPIs / Metric Registry — see source tabs
Net Profit | net_profit | 113840.13 | Financial |  | Verified | Benchmark KPIs / Metric Registry — see source tabs
Gross Margin | gross_margin | 0.28878 | Financial |  | Verified | Benchmark KPIs / Metric Registry — see source tabs
Direct Cost | direct_cost | 280367.87 | Financial |  | Verified | Benchmark KPIs / Metric Registry — see source tabs
Labor Cost | labor_cost | 80901.5 | Labor | Sum of 11 labor codes | Verified | Benchmark KPIs / Metric Registry — see source tabs
Material Cost | material_cost | 151064.39 | Material | Sum of 9 material codes | Verified | Benchmark KPIs / Metric Registry — see source tabs
Overhead Cost | overhead_cost | 7510.52 | Financial | Sub+Eng+Permits | Verified | Benchmark KPIs / Metric Registry — see source tabs
Burden Cost | burden_cost | 40891.46 | Financial | Codes 995+998 | Verified | Benchmark KPIs / Metric Registry — see source tabs
Retainage | retainage | 19710.4 | Financial | 5% withheld | Verified | Benchmark KPIs / Metric Registry — see source tabs
Revenue per Unit | revenue_per_unit | 2346.4762 | Financial |  | Verified | Benchmark KPIs / Metric Registry — see source tabs
Profit per Unit | profit_per_unit | 677.6198 | Financial |  | Verified | Benchmark KPIs / Metric Registry — see source tabs
Direct Cost per Unit | cost_per_unit | 1668.8564 | Financial |  | Verified | Benchmark KPIs / Metric Registry — see source tabs
Labor Cost per Unit | labor_per_unit | 481.5565 | Labor |  | Verified | Benchmark KPIs / Metric Registry — see source tabs
Material Cost per Unit | material_per_unit | 899.1928 | Material |  | Verified | Benchmark KPIs / Metric Registry — see source tabs
Revenue per Fixture | revenue_per_fixture | 485.4778 | Financial |  | Verified | Benchmark KPIs / Metric Registry — see source tabs
Profit per Fixture | profit_per_fixture | 140.1972 | Financial |  | Verified | Benchmark KPIs / Metric Registry — see source tabs
Cost per Fixture | cost_per_fixture | 345.2806 | Financial |  | Verified | Benchmark KPIs / Metric Registry — see source tabs
Labor per Fixture | labor_per_fixture | 9963% | Labor |  | Verified | Benchmark KPIs / Metric Registry — see source tabs
Material per Fixture | material_per_fixture | 186.0399 | Material |  | Verified | Benchmark KPIs / Metric Registry — see source tabs
Total Labor Hours | total_hours | 3928.5 | Labor | Sum of JDR cost code hours | Verified | Benchmark KPIs / Metric Registry — see source tabs
Total Workers | total_workers | 23 | Labor | Unique payroll IDs | Verified | Benchmark KPIs / Metric Registry — see source tabs
Blended Gross Wage | blended_gross_wage | 2188% | Labor | Pre-burden | Verified | Benchmark KPIs / Metric Registry — see source tabs
Fully-Loaded Wage | fully_loaded_wage | 3100% | Labor | Post-burden | Verified | Benchmark KPIs / Metric Registry — see source tabs
Burden Multiplier | burden_multiplier | 1.4167 | Labor |  | Verified | Benchmark KPIs / Metric Registry — see source tabs
Hours per Unit | hours_per_unit | 2338% | Labor | Key benchmark | Verified | Benchmark KPIs / Metric Registry — see source tabs
Hours per Fixture | hours_per_fixture | 4.8381 | Labor | Key benchmark | Verified | Benchmark KPIs / Metric Registry — see source tabs
Revenue per Hour | revenue_per_hour | 100.3457 | Productivity |  | Verified | Benchmark KPIs / Metric Registry — see source tabs
Profit per Hour | profit_per_hour | 2898% | Productivity |  | Verified | Benchmark KPIs / Metric Registry — see source tabs
Labor % of Revenue | labor_pct_revenue | 0.20523 | Cost Mix |  | Verified | Benchmark KPIs / Metric Registry — see source tabs
Material % of Revenue | material_pct_revenue | 0.38321 | Cost Mix |  | Verified | Benchmark KPIs / Metric Registry — see source tabs
Revenue per Month | revenue_per_month | 24638 | Productivity |  | Verified | Benchmark KPIs / Metric Registry — see source tabs
Hours per Month | hours_per_month | 245.5312 | Productivity |  | Verified | Benchmark KPIs / Metric Registry — see source tabs
Units per Month | units_per_month | 1050% | Productivity |  | Verified | Benchmark KPIs / Metric Registry — see source tabs
Total Vendors | total_vendors | 13 | Material | Unique AP vendors | Verified | Benchmark KPIs / Metric Registry — see source tabs
Top Vendor Spend | top_vendor_spend | 117439.01 | Material | Ferguson Enterprises, Inc. | Verified | Benchmark KPIs / Metric Registry — see source tabs
Top Vendor Concentration | top_vendor_pct | 0.67312 | Material |  | Verified | Benchmark KPIs / Metric Registry — see source tabs
Total POs | total_pos | 7 | Material | Unique POs by filename | Verified | Benchmark KPIs / Metric Registry — see source tabs
Change Order % | co_pct | 0.024183 | Financial |  | Verified | Benchmark KPIs / Metric Registry — see source tabs
Revenue per Labor Hour | rev_per_labor_hr | 100.3457 | Productivity |  | Verified | Benchmark KPIs / Metric Registry — see source tabs
SOURCES
Job #2009 — Chinn Greenwood Apartments • GC: Chinn Construction, LLC • Seattle, WA
Canonical source: 2009 Job Detail Report.pdf (49 pages, OWP Sage Timberline export)
Cost codes parsed: 26
Unit count (168) and fixture count (812) from greenwood h20 stacks.xls and trim POs
3-level building + lobby: L1 (18 units), L2 (18 units), L3 (18 units), LW (amenity) × south/north stacks
Billing: GREENWOOD AGGREGATE BILLING.xlsx (11 pay apps Jul 2012 – Oct 2013)
Final contract $394,208 (original $384,900 + $9,308 COs)
51 KPIs with snake_case data_name identifiers for database ingestion

## Vendors
Vendor Detail — Job #2009
Vendors | 13 |  | Top vendor | Ferguson Enterprises, Inc.
Invoices | 98 |  | Top 3 share | 93.72%
Total AP | 174470.05 |  | Source | Job Detail Report (Sage Timberline AP export)
Avg Inv | 1780.3066
Rank | Vendor | Vendor Code | Invoices | Total Spend | % of AP | Avg / Invoice
1 | Ferguson Enterprises, Inc. |  | 65 | 117439.01 | 67.31% | 1806.754
2 | Keller Supply Company |  | 14 | 29740.43 | 17.05% | 2124.3164
3 | Mechanical Sales, Inc. |  | 2 | 16339.3 | 9.365% | 8169.65
4 | Franklin Engineering |  | 1 | 4895 | 2.806% | 4895
5 | Mickelo Construction LLC |  | 1 | 2250 | 1.29% | 2250
6 | Quality Concrete Products, Inc. |  | 4 | 1821 | 1.044% | 455.25
7 | Rosen Supply Company, Inc. |  | 2 | 1040.84 | 0.5966% | 520.42
8 | Ferguson Enterprises, Inc. #3007 |  | 1 | 245.19 | 0.1405% | 245.19
9 | Bank of America CC |  | 1 | 210 | 0.1204% | 210
10 | Capital One Credit Card |  | 3 | 167.8 | 0.09618% | 55.9333
11 | R.A. Brown Backflow Testing |  | 1 | 129 | 0.07394% | 129
12 | C.M. Hoskins Company |  | 2 | 97.4 | 0.05583% | 48.7
13 | DRSi |  | 1 | 95.08 | 0.0545% | 95.08
| TOTAL |  | 98 | 174470.05 | 100% | 1780.3066

## Change Log
Change Log — Master Register
Unified change-event ledger: RFIs, ASIs, COPs, COs, Backcharges, T&M (8 events)
Event ID | Type | Date | Subject | Originator | Linked Event(s) | Cost Impact ($) | Schedule (days) | Status | Source Document
ASI-001 | ASI | 2012-07-01 | Water distribution & drainage system specifications (Greenwood ASI-01) | Architect |  | 0 | 0 | Closed | 2009-Chinn Greenwood/2009 Greenwood/chinn greenwood/greenwood asi 1.pdf
ASI-003 | ASI | 2012-10-08 | Booster system routing & pressure relief clarification | Architect | SUB-BPC-R1 | 0 | 0 | Closed | 2009-Chinn Greenwood/2009 Greenwood/chinn greenwood/Greenwood ASI-03.pdf
SUB-BPC-R1 | Submittal-resub | 2012-10 | BPC Booster System — Rev1 model (driven by ASI-03 clarification) | Sub (OWP) | ASI-003 | 0 | 0 | Closed | 2009-Chinn Greenwood/2009 Greenwood/BPC Booster System Rev1-Model.pdf
COST-120-OVER | CO | 2013-08-27 | Rough-in phase labor overrun — $11,614 over budget (56% of project hours, 34% over). No CO filed. Undocumented scope/productivity loss. | Field (OWP) |  | -11614 | 0 | Undocumented | 2009 Job Detail Report.pdf — Cost Code 120 (Roughin Labor)
SALES-999 | CO | 2012-07-19 to 2013-08-27 | Net billed additions — $9,208 over estimated contract ($385K → $394,208). No CO documentation located. 12 invoices to Chinn. | GC (Chinn) |  | 9208 | 0 | Billed — Undocumented | 2009 Job Detail Report.pdf — Cost Code 999 (Sales/AR)
WARRANTY-150 | T&M | 2013 | Warranty / T&M labor — 4 hrs, $138.50. No formal T&M work order or CO authorization. | Field (OWP) |  | -138 | 0 | Absorbed | 2009 Job Detail Report.pdf — Cost Code 150
DOC-GAP-RFI | Memo | 2013 | CRITICAL GAP: ASI-RFI folder exists but contains zero RFIs. No RFI log, register, or correspondence. Cannot attribute design issues. | OWP |  | 0 | 0 | Open | 2009-Chinn Greenwood/2009-Chinn, Greenwood/ASI-RFI/ (empty)
DOC-GAP-CO | Memo | 2013 | CRITICAL GAP: No Change Order documents filed despite $9,208 in net additions + $11,614 labor overrun. Potential uncaptured extras. | OWP | COST-120-OVER,SALES-999 | 0 | 0 | Open | No Change Order folder in project filesystem
TOTAL | [5 empty] | -2544 | 0

## Root Cause Analysis
Root Cause Analysis — Change Driver Taxonomy
Categorized change events with responsible-party attribution — feeds bid-risk intelligence
CATEGORY ROLLUP
Root Cause Category | # Events | Net Cost Impact ($) | % of Events | Predominant Responsibility | Notes
Design clarification | 3 | 0 | 37.5% | Designer | Water distribution & drainage system specifications (Greenwo
Scope gap | 1 | -11614 | 12.5% | Sub (OWP) | Rough-in phase labor overrun — $11,614 over budget (56% of p
Rework | 1 | -138 | 12.5% | Sub (OWP) | Warranty / T&M labor — 4 hrs, $138.50. No formal T&M work or
Combined/multi-cause | 3 | 9208 | 37.5% | Mixed | Net billed additions — $9,208 over estimated contract ($385K
TOTAL | 8 | -2544
RESPONSIBILITY ATTRIBUTION
Responsible Party | # Events | Net $ Impact | Bid-Risk Signal
Designer | 3 | 0 | NEUTRAL
Mixed | 3 | 9208 | POSITIVE — recoverable
Sub (OWP) | 2 | -11752 | CAUTION — price risk in future bids

## Predictive Signals
Predictive Signals — Leading Indicators
Forward-looking metrics that predict CO waves, schedule slips, and margin erosion
CURRENT-STATE SIGNALS
Indicator | Current Value | Benchmark | Status | Predictive Meaning
RFI Total (closed) | 0 | <50 for mid-size | INFO | Volume proxy for design doc quality
RFI Velocity (per month, derived) | See KPIs D50 | <3.0/wk | INFO | >3/wk = CO wave in 4-8 wks
RFI Avg Cycle Time (days) | Unknown | <14 | N/A | >30 avg signals schedule slip
ASI / OCD Count | 2 | <5 | HEALTHY | High ASI = owner scope churn
Backcharge Count | 0 | <3 | HEALTHY | BC clusters = coordination weakness
Change Order Count | 2 | <3 | HEALTHY | CO count signals scope definition
T&M Event Count | 1 | <2 | HEALTHY | T&M = directed work pipeline
Submittal resubmission count | 1 | <10 | HEALTHY | Repeats = coord issues incubating
Net $ Impact (all events) | -2544 | Near $0 | NEGATIVE | Net recoverable vs absorbed
FORECAST MODELS (closed-project — actuals)
Forecast | Current Estimate | Confidence | Driver | Model Note
Projected final CO % of contract | 0.024183 | Actual | Closed project | CO$ / orig contract
Projected EAC (direct cost) | 280367.87 | Actual | Closed project | Sum of L+M+OH+Burden
Projected final margin | 0.28878 | Actual | Closed project | (Rev - DC) / Rev
Composite risk score (0-100) | 20 | Medium | 0 BCs + 2 ASI/OCDs | Custom Cortex scoring

## Metric Registry
Metric Registry — Cortex Data Catalog
Every metric with data_label, confidence_level, and source_document — the machine-readable JCR index
# | Data Label | Human Label | Value | Unit | Source Tab | Confidence | Source Document(s) | Formula / Derivation
1 | job_number | Job Number | 2009 | id | Benchmark KPIs | Verified | JDR header | See Benchmark KPIs tab
2 | job_name | Job Name | Chinn Greenwood Apartments | text | Benchmark KPIs | Verified | Contract folder | See Benchmark KPIs tab
3 | general_contractor | General Contractor | Chinn Construction, LLC | text | Benchmark KPIs | Verified | Contract folder | See Benchmark KPIs tab
4 | location | Location | Seattle, WA | text | Benchmark KPIs | Verified | Permit/Plans | See Benchmark KPIs tab
5 | project_type | Project Type | 168-unit apartment building | text | Benchmark KPIs | Verified | Plans | See Benchmark KPIs tab
6 | duration_months | Duration (months) | 16 | months | Benchmark KPIs | Verified | First-to-last invoice | See Benchmark KPIs tab
7 | unit_count | Unit Count | 168 | units | Benchmark KPIs | Verified | Plumbing permit + P-tag list | See Benchmark KPIs tab
8 | total_fixtures | Total Fixtures | 812 | count | Benchmark KPIs | Verified | Permit detail | See Benchmark KPIs tab
9 | contract_original | Contract Original | 384900 | USD | Benchmark KPIs | Verified | Contract SOV | See Benchmark KPIs tab
10 | contract_final | Contract Final | 394208 | USD | Benchmark KPIs | Verified | Final billing SOV | See Benchmark KPIs tab
11 | change_orders | Change Orders ($) | 9308 | USD | Benchmark KPIs | Verified | JDR revised - original | See Benchmark KPIs tab
12 | revenue | Revenue | 394208 | USD | Benchmark KPIs | Verified | Aggregate billing | See Benchmark KPIs tab
13 | net_profit | Net Profit | 113840.13 | USD | Benchmark KPIs | Verified | Revenue - Direct Cost | See Benchmark KPIs tab
14 | gross_margin | Gross Margin % | 0.28878 | % | Benchmark KPIs | Verified | Derived | See Benchmark KPIs tab
15 | direct_cost | Direct Cost | 280367.87 | USD | Benchmark KPIs | Verified | JDR cost codes | See Benchmark KPIs tab
16 | labor_cost | Labor Cost | 80901.5 | USD | Benchmark KPIs | Verified | JDR labor codes | See Benchmark KPIs tab
17 | material_cost | Material Cost | 151064.39 | USD | Benchmark KPIs | Verified | JDR material codes | See Benchmark KPIs tab
18 | overhead_cost | Overhead Cost | 7510.52 | USD | Benchmark KPIs | Verified | JDR overhead codes | See Benchmark KPIs tab
19 | burden_cost | Burden Cost | 40891.46 | USD | Benchmark KPIs | Verified | JDR burden codes | See Benchmark KPIs tab
20 | retainage | Retainage | 19710.4 | USD | Benchmark KPIs | Verified | Aggregate billing row | See Benchmark KPIs tab
21 | total_hours | Total Labor Hours | 3928.5 | hours | Benchmark KPIs | Verified | JDR payroll | See Benchmark KPIs tab
22 | total_workers | Total Workers | 23 | count | Benchmark KPIs | Verified | JDR unique workers | See Benchmark KPIs tab
23 | blended_gross_wage | Blended Gross Wage | 2188% | USD/hr | Benchmark KPIs | Verified | Labor $ / Hours | See Benchmark KPIs tab
24 | total_vendors | Total Vendors | 13 | count | Benchmark KPIs | Verified | JDR AP unique | See Benchmark KPIs tab
25 | total_pos | Total POs | 7 | count | Benchmark KPIs | Verified | PO folder count | See Benchmark KPIs tab
26 | co_pct | CO % of Original | 0.024183 | % | Benchmark KPIs | Verified | Derived | See Benchmark KPIs tab
27 | rfi_total_count | RFIs Total | 0 | count | Predictive Signals | Low | ASI-RFI folder count | See Predictive Signals tab
28 | asi_ocd_count | ASI + OCD Count | 2 | count | Change Log | Verified | ASI-RFI folder + Change Orders | See Change Log tab
29 | co_count_total | Change Order Count | 2 | count | Change Log | Verified | Change Orders folder | See Change Log tab
30 | backcharge_count | Backcharge Count | 0 | count | Change Log | Verified | Invoices/Backcharges | See Change Log tab
31 | tm_event_count | T&M Event Count | 1 | count | Change Log | Verified | Change Orders / JDR 038 | See Change Log tab
32 | submittal_resub_count | Submittal Resubmissions | 1 | count | Predictive Signals | Verified | Submittals folder | See Predictive Signals tab
33 | change_event_total | Total Tracked Events | 8 | count | Change Log | Verified | Change Log tab | See Change Log tab
34 | change_net_impact | Change Net $ Impact | -2544 | USD | Change Log | Verified | SUM H col | See Change Log tab

## Reconciliation
Reconciliation — Cross-Tab Tie-out Proofs
Live cross-sheet formulas verify data consistency across all 17 tabs
Check | Tab A | Tab B | Δ | Status | Tabs
A. OVERVIEW ↔ BENCHMARK KPIS
Direct Cost Total | 280367.87 | 280367.87 | 0 | TIES | 1↔2↔11
Contract Final Value | 394208 | 394208 | 0 | TIES | JDR↔11
Net Profit | 113840.13 | 113840.13 | 0 | TIES | JDR↔11
Gross Margin | 28.88% | 28.88% | 0% | TIES | JDR↔11
B. OVERVIEW ↔ COST BREAKDOWN (Category Actuals)
Labor Actual | 80901.5 | 80901.5 | 0 | TIES | 1↔3
Material Actual | 151064.39 | 151064.39 | 0 | TIES | 1↔3
Overhead Actual | 7510.52 | 7510.52 | 0 | TIES | 1↔3
Burden Actual | 40891.46 | 40891.46 | 0 | TIES | 1↔3
C. BUDGET vs ACTUAL ↔ OVERVIEW
Actual Direct Cost | 280367.87 | 280367.87 | 0 | TIES | 2↔1
Revised Budget Total | 317000.22 | 317000.22 | 0 | TIES | 2↔1
D. MATERIAL ↔ COST BREAKDOWN ↔ KPIS
Material Actual (Material tab) | 151064.39 | 151064.39 | 0 | TIES | 4↔3
Material Actual (KPIs) | 151064.39 | 151064.39 | 0 | TIES | 11↔3
E. CREW & LABOR ↔ PRODUCTIVITY ↔ KPIS (Hours)
Total Hours (Crew tab) | 4159 | 3928.5 | 230.5 | OFF | 5↔11
Total Hours (Productivity tab) | 3928.5 | 3928.5 | 0 | TIES | 7↔11
Total Workers | 23 | 23 | 0 | TIES | JDR↔11
F. CREW ANALYTICS ↔ KPIS (Wage Statistics)
Blended Gross Wage | 20.6703 | 21.8831 | -1.2128 | OFF | 6↔11
Fully-Loaded Wage | 29.2842 | 31.0024 | -1.7182 | OFF | 6↔11
G. PO COMMITMENTS ↔ KPIS
PO Count | 7 | 7 | 0 | TIES | 8↔11
H. BILLING & SOV ↔ JDR
Final Contract Value | 394208 | 394208 | 0 | TIES | 9↔JDR
Retainage | 19710 | 19710 | 0 | TIES | 9↔JDR
Direct Cost | 280368 | 280368 | 0 | TIES | 9↔JDR
I. VENDORS ↔ KPIS
Vendor Count | 13 | 13 | 0 | TIES | 12↔11
Total AP Spend | 174470.05 | 174470 | 0.05 | TIES | 12↔JDR
J. INSIGHTS (Narrative Review)
10 insight cards — narrative text verified at generation time, no formula check applicable
K. CHANGE LOG ↔ ROOT CAUSE ANALYSIS
Total Event Count | 8 | 8 | 0 | TIES | 13↔14
Net $ Impact (all events) | -2544 | -2544 | 0 | TIES | 13↔14
L. PREDICTIVE SIGNALS ↔ CHANGE LOG
Backcharge Count signal | 0 | 0 | 0 | TIES | 15↔13
M. METRIC REGISTRY ↔ BENCHMARK KPIs
revenue (row 17) | 394208 | 394208 | 0 | TIES | 16↔11
unit_count (row 12) | 168 | 168 | 0 | TIES | 16↔11
total_fixtures (row 13) | 812 | 812 | 0 | TIES | 16↔11
direct_cost (row 19) | 0.28878 | 280367.87 | -280367.5812 | OFF | 16↔11
total_pos (row 30) | 7 | 7 | 0 | TIES | 16↔11
N. CHANGE LOG ↔ METRIC REGISTRY (event counts)
change_event_total | 1 | 8 | -7 | OFF | 16↔13
SOURCES
Job #2009 — Cortex v2 17-tab layout
12 analytical tabs + Change Log + Root Cause Analysis + Predictive Signals + Metric Registry + Reconciliation
Canonical source: 2009 Job Detail Report.pdf (Sage Timberline export)
Change artifacts: folders scanned — ASI-RFI, Change Orders, Submittals, Invoices (Backcharges), JDR cost codes
Every Change Log row cites its source document path
TIES = within $1/5hrs/exact count • WITHIN = within 5% • OFF = investigate
Cross-sheet formulas (='Tab'!Cell) update automatically when source tabs change
Tabs: 1-12 analytical • 13=ChangeLog • 14=RootCause • 15=PredictiveSignals • 16=MetricRegistry • 17=Reconciliation