## Overview
Job #2009 · Chinn Greenwood Apartments
Cortex JCR Summary • Chinn Construction, LLC • Seattle, WA • 168-unit apartment building • Jul 2012 – Oct 2013 (~16 months)
PROJECT OVERVIEW
Project Job # | 2009
Project Name: | Chinn Greenwood Apartments
General Contractor | Chinn Construction, LLC
Location | Seattle, WA
Project Duration | Jul 2012 – Oct 2013 (~16 months)
Total Unique Documents | Greenwood folder: Contract, Billing (aggregate + 11 SOVs), PO Scheduled (48), Permits, Plans, Submittals
CONTRACT VALUE |  | NET PROFIT |  | DIRECT COST |  | LABOR HOURS
$394,208 |  | $113,840 |  | $280,368 |  | 3,928
Original $384,900 + $9,308 COs |  | 28.9% margin |  | 71.1% of revenue |  | 23 workers
COST BREAKDOWN
Category | Budget | Actual | Variance | % Budget | % of Cost
Labor | 72340 | 80901.5
Material | 195311 | 151064.39
Overhead | 10885 | 7510.52
Burden | 38464.22 | 40891.46
TOTAL |  |  |  |  | 100%
PROJECT PROFILE
Metric | Value | Metric | Value | Metric | Value
Plumbing Units | 168 | Water Closets | 168 | Kitchen Sinks | 168
Total Fixtures | 812 | Lavatories | 168 | Tubs | 168
Fixtures / Unit | 4.83 | Auto Washers | 140 | Showers | 0
Stacks | 36 | Duration | 16 mo | Cost Codes | 26
SOURCES
Job #2009 — Chinn Greenwood Apartments • GC: Chinn Construction, LLC • Seattle, WA
Canonical source: 2009 Job Detail Report.pdf (49 pages, OWP Sage Timberline export)
Cost codes parsed: 26
Unit count (168) and fixture count (812) from greenwood h20 stacks.xls and trim POs
3-level building + lobby: L1 (18 units), L2 (18 units), L3 (18 units), LW (amenity) × south/north stacks
Billing: GREENWOOD AGGREGATE BILLING.xlsx (11 pay apps Jul 2012 – Oct 2013)
Final contract $394,208 (original $384,900 + $9,308 COs)

## Budget vs Actual
Budget vs Actual — All Cost Codes
Code | Description | Orig Budget | Rev Budget | Actual | Variance | % Used
LABOR
011 | DS & RD Labor | 1250 | 1250 | 1645
100 | Supervision | 3000 | 3000 | 2992
101 | Takeoff & Purchase Labor | 2500 | 2500 | 1324
110 | Underground Labor | 5350 | 5350 | 4209
111 | Garage Labor | 8960 | 8960 | 9872
112 | Canout Labor | 2000 | 2000 | 1485.5
120 | Roughin Labor | 34500 | 37530 | 46114
130 | Finish Labor | 10250 | 10320 | 11391.5
141 | Water Main/Insulation Lab | 0 | 0 | 0
142 | Mech Room Labor | 1430 | 1430 | 1730
145 | Tub/Shower Labor | 0 | 0 | 138.5
MATERIAL
039 | DS & RD Material | 1250 | 1250 | 369.06
210 | Underground Material | 2800 | 2800 | 2613.58
211 | Garage Material | 10570 | 10570 | 3972.94
212 | Canout Material | 2800 | 2800 | 2749.23
220 | Roughin Material | 33560 | 32510 | 30742.47
230 | Finish Material | 143270 | 143381 | 109975.66
241 | Water Main/Insulation Mat | 0 | 0 | 0
242 | Mech Room Material | 2000 | 2000 | 641.45
245 | Tub/Shower Material | 0 | 0 | 0
OVERHEAD
600 | Subcontractor | 4800 | 4885 | 2379
601 | Engineering/Plans | 6000 | 6000 | 4990.08
603 | Permits & Licenses | 0 | 0 | 141.44
BURDEN
995 | Payroll Burden | 28928 | 32694.58 | 34412.05
998 | Payroll Taxes | 5532.48 | 5769.64 | 6479.41
TOTAL | Direct Cost | 310750.48 | 317000.22 | 280367.87
SOURCES
Job #2009 — Chinn Greenwood Apartments • GC: Chinn Construction, LLC • Seattle, WA
Canonical source: 2009 Job Detail Report.pdf (49 pages, OWP Sage Timberline export)
Cost codes parsed: 26
Unit count (168) and fixture count (812) from greenwood h20 stacks.xls and trim POs
3-level building + lobby: L1 (18 units), L2 (18 units), L3 (18 units), LW (amenity) × south/north stacks
Billing: GREENWOOD AGGREGATE BILLING.xlsx (11 pay apps Jul 2012 – Oct 2013)
Final contract $394,208 (original $384,900 + $9,308 COs)

## Cost Breakdown
Cost Breakdown — Category Deep Dive
A. CATEGORY SHARE OF DIRECT COST
Category | # Codes | Budget | Actual | Variance | % Budget | % of Cost | Per Unit
Labor | 11 | 72340 | 80901.5
Material | 9 | 195311 | 151064.39
Overhead | 3 | 10885 | 7510.52
Burden | 2 | 38464.22 | 40891.46
B. LARGEST OVERRUNS (Actual > Revised Budget)
Code | Description | Rev Budget | Actual | Overrun | % Over
120 | Roughin Labor | 37530 | 46114
995 | Payroll Burden | 32694.58 | 34412.05
130 | Finish Labor | 10320 | 11391.5
111 | Garage Labor | 8960 | 9872
998 | Payroll Taxes | 5769.64 | 6479.41
011 | DS & RD Labor | 1250 | 1645
142 | Mech Room Labor | 1430 | 1730
603 | Permits & Licenses | 0 | 141.44
145 | Tub/Shower Labor | 0 | 138.5
C. LARGEST SAVINGS (Actual < Revised Budget)
Code | Description | Rev Budget | Actual | Savings | % Under
230 | Finish Material | 143381 | 109975.66
211 | Garage Material | 10570 | 3972.94
600 | Subcontractor | 4885 | 2379
220 | Roughin Material | 32510 | 30742.47
242 | Mech Room Material | 2000 | 641.45
101 | Takeoff & Purchase Labor | 2500 | 1324
110 | Underground Labor | 5350 | 4209
601 | Engineering/Plans | 6000 | 4990.08
039 | DS & RD Material | 1250 | 369.06
112 | Canout Labor | 2000 | 1485.5
SOURCES
Job #2009 — Chinn Greenwood Apartments • GC: Chinn Construction, LLC • Seattle, WA
Canonical source: 2009 Job Detail Report.pdf (49 pages, OWP Sage Timberline export)
Cost codes parsed: 26
Unit count (168) and fixture count (812) from greenwood h20 stacks.xls and trim POs
3-level building + lobby: L1 (18 units), L2 (18 units), L3 (18 units), LW (amenity) × south/north stacks
Billing: GREENWOOD AGGREGATE BILLING.xlsx (11 pay apps Jul 2012 – Oct 2013)
Final contract $394,208 (original $384,900 + $9,308 COs)

## Material
Material Spend Analysis
9 material cost codes • $151,064 JDR material • 13 AP vendors • $174,470 total AP
A. MATERIAL BY COST CODE
Code | Description | Rev Budget | Actual | Variance | % Used | % of Mat | Per Unit
039 | DS & RD Material | 1250 | 369.06
210 | Underground Material | 2800 | 2613.58
211 | Garage Material | 10570 | 3972.94
212 | Canout Material | 2800 | 2749.23
220 | Roughin Material | 32510 | 30742.47
230 | Finish Material | 143381 | 109975.66
241 | Water Main/Insulation Mat | 0 | 0
242 | Mech Room Material | 2000 | 641.45
245 | Tub/Shower Material | 0 | 0
TOTAL | All Material |  |  |  |  | 100%
B. VENDORS BY SPEND (AP)
Vendor | # Invoices | Total Spend | % of AP |  |  |  | Avg Invoice
Ferguson Enterprises, Inc. | 65 | 117439.01
Keller Supply Company | 14 | 29740.43
Mechanical Sales, Inc. | 2 | 16339.3
Franklin Engineering | 1 | 4895
Mickelo Construction LLC | 1 | 2250
Quality Concrete Products, Inc. | 4 | 1821
Rosen Supply Company, Inc. | 2 | 1040.84
Ferguson Enterprises, Inc. #3007 | 1 | 245.19
Bank of America CC | 1 | 210
Capital One Credit Card | 3 | 167.8
R.A. Brown Backflow Testing | 1 | 129
C.M. Hoskins Company | 2 | 97.4
DRSi | 1 | 95.08
TOTAL |  |  | 100%
SOURCES
Job #2009 — Chinn Greenwood Apartments • GC: Chinn Construction, LLC • Seattle, WA
Canonical source: 2009 Job Detail Report.pdf (49 pages, OWP Sage Timberline export)
Cost codes parsed: 26
Unit count (168) and fixture count (812) from greenwood h20 stacks.xls and trim POs
3-level building + lobby: L1 (18 units), L2 (18 units), L3 (18 units), LW (amenity) × south/north stacks
Billing: GREENWOOD AGGREGATE BILLING.xlsx (11 pay apps Jul 2012 – Oct 2013)
Final contract $394,208 (original $384,900 + $9,308 COs)
Vendor AP ties to JDR 'by Source: AP' line (174,470.05)

## Crew & Labor
Crew & Labor — Per-Worker Breakdown
Worker | Hours | Gross Pay | $/Hour | Tier
Quintanilla, Esteban R | 569 | 17070 |  | Senior
Sanders, Allen O | 432.5 | 10872 |  | Mid
Mazil, Antonio | 416 | 5264 |  | Apprentice
Castro Hernandez, Carlos E | 349 | 7678 |  | Mid
Palma Vides, Hugo | 304 | 7600 |  | Mid
Ramirez, Lorenzo A | 269 | 3982 |  | Apprentice
Castro Hernandez, Jose A | 236 | 3304 |  | Apprentice
Arreola, Israel A | 221 | 2487 |  | Apprentice
Soto Cruz, Jovani | 210.5 | 2859.5 |  | Apprentice
Cortes Mendiola, Victor H | 208 | 4136 |  | Mid
Meza Fuentes, Erick A | 192 | 2880 |  | Apprentice
Gerard, Jeffrey S | 164 | 5435.2 |  | Senior
Waites, Thaddeus Z | 160 | 4000 |  | Mid
Barnhart, Joseph N | 89.5 | 2507 |  | Mid
Paco Leyva, Orlando | 88 | 976 |  | Apprentice
Veley, Nathaniel S | 80.5 | 1620 |  | Mid
McCabe, Thomas C | 76.5 | 1147.5 |  | Apprentice
Reed, Reuben H | 44 | 1100 |  | Mid
Sepulveda Gonzalez, Alfredo | 32 | 704 |  | Mid
Soto Serna, Cesar E | 8 | 88 |  | Apprentice
Hubbard, Robert W | 7 | 224 |  | Senior
Hubbard, Dustin R | 1.5 | 16.5 |  | Apprentice
Lima Romero, Melvin A | 1 | 17 |  | Apprentice
TOTAL (23 workers)
SOURCES
Job #2009 — Chinn Greenwood Apartments • GC: Chinn Construction, LLC • Seattle, WA
Canonical source: 2009 Job Detail Report.pdf (49 pages, OWP Sage Timberline export)
Cost codes parsed: 26
Unit count (168) and fixture count (812) from greenwood h20 stacks.xls and trim POs
3-level building + lobby: L1 (18 units), L2 (18 units), L3 (18 units), LW (amenity) × south/north stacks
Billing: GREENWOOD AGGREGATE BILLING.xlsx (11 pay apps Jul 2012 – Oct 2013)
Final contract $394,208 (original $384,900 + $9,308 COs)
Tier: Apprentice <$18/hr, Mid $18–30, Senior >$30

## Crew Analytics
Crew Analytics
A. TIER DISTRIBUTION
Tier | # Workers | Hours | Gross Pay | % of Hours
Senior | 3 | 740 | 22729.2
Mid | 9 | 1699.5 | 40217
Apprentice | 11 | 1719.5 | 23021.5
B. WAGE STATISTICS
Blended Gross Wage | 20.6703 |  |  | Payroll $ ÷ payroll hours (pre-burden)
Fully-Loaded Wage | 29.2842 |  |  | (Labor + Burden) ÷ total hours
Burden Multiplier | 1.4167 |  |  | Fully loaded ÷ gross wage
Min Worker Rate | 11 |  |  | Cheapest apprentice hour
Max Worker Rate | 33.1415 |  |  | Most expensive foreman hour
Avg Hours / Worker | 180.8261 |  |  | Crew continuity indicator
SOURCES
Job #2009 — Chinn Greenwood Apartments • GC: Chinn Construction, LLC • Seattle, WA
Canonical source: 2009 Job Detail Report.pdf (49 pages, OWP Sage Timberline export)
Cost codes parsed: 26
Unit count (168) and fixture count (812) from greenwood h20 stacks.xls and trim POs
3-level building + lobby: L1 (18 units), L2 (18 units), L3 (18 units), LW (amenity) × south/north stacks
Billing: GREENWOOD AGGREGATE BILLING.xlsx (11 pay apps Jul 2012 – Oct 2013)
Final contract $394,208 (original $384,900 + $9,308 COs)

## Productivity
Productivity — Phase & Unit Metrics
A. LABOR HOURS BY PHASE
Phase | Labor Code | Hours | % of Total | Hours / Unit
DS & RD | 011 | 76
Supervision | 100 | 90
Takeoff & Purchasing | 101 | 40
Underground | 110 | 213.5
Garage | 111 | 488
Canout | 112 | 69.5
Roughin | 120 | 2311
Finish | 130 | 557.5
Water Main / Insulation | 141 | 16
Mech Room | 142 | 63
Tub / Shower | 145 | 4
TOTAL |  |  | 100%
B. PRODUCTIVITY RATIOS
Metric | Value | Units |  | Notes
Hours / Unit | 23.3839 | hrs |  | Labor hours per residential unit
Hours / Fixture | 4.8381 | hrs |  | Labor hours per plumbing fixture
Revenue / Hour | 100.3457 | $ |  | Top-line per labor hour
Profit / Hour | 28.978 | $ |  | Bottom-line per labor hour
Units / Month | 10.5 | units |  | Build velocity
Fixtures / Month | 50.75 | fix |  | Fixture install pace
Hours / Month | 245.5312 | hrs |  | Monthly labor burn
Revenue / Month | 24638 | $ |  | Monthly billing rate
SOURCES
Job #2009 — Chinn Greenwood Apartments • GC: Chinn Construction, LLC • Seattle, WA
Canonical source: 2009 Job Detail Report.pdf (49 pages, OWP Sage Timberline export)
Cost codes parsed: 26
Unit count (168) and fixture count (812) from greenwood h20 stacks.xls and trim POs
3-level building + lobby: L1 (18 units), L2 (18 units), L3 (18 units), LW (amenity) × south/north stacks
Billing: GREENWOOD AGGREGATE BILLING.xlsx (11 pay apps Jul 2012 – Oct 2013)
Final contract $394,208 (original $384,900 + $9,308 COs)

## PO Commitments
Purchase Order Commitments
7 unique POs • PO amounts not dollar-parsed from individual PDFs • JDR material $151,064
A. COMMITMENTS BY COST CODE
OWP Code | Description → JDR | PO Count | % of POs | JDR Material
32 | 130+230 Trim/Finish | 5
OTHER | Unclassified | 2
TOTAL |  |  | 100% | 151064.39
B. COMMITMENTS BY VENDOR
Vendor | PO Count | % of POs
OTHER | 6
FEI | 1
C. PO COVERAGE NOTES
Total Material Actual (JDR) |  |  | 151064.39
Unique PO Count |  |  | 7
(Dollar PO commitment not extracted — requires per-PDF parse)
SOURCES
Job #2009 — Chinn Greenwood Apartments • GC: Chinn Construction, LLC • Seattle, WA
Canonical source: 2009 Job Detail Report.pdf (49 pages, OWP Sage Timberline export)
Cost codes parsed: 26
Unit count (168) and fixture count (812) from greenwood h20 stacks.xls and trim POs
3-level building + lobby: L1 (18 units), L2 (18 units), L3 (18 units), LW (amenity) × south/north stacks
Billing: GREENWOOD AGGREGATE BILLING.xlsx (11 pay apps Jul 2012 – Oct 2013)
Final contract $394,208 (original $384,900 + $9,308 COs)
PO count is deduplicated by 5-digit PO number extracted from filenames
Vendor/code classification is heuristic (filename keyword match)

## Billing & SOV
Revenue & Billing Reconciliation
11 pay applications • Jul 2012 – Oct 2013 • $394,208 final
A. CONTRACT SUMMARY
Original Contract |  |  |  |  | 384900
Change Orders (net) |  |  |  |  | 9308
Final Contract Value |  |  |  |  | 394208
Retainage (5%) |  |  |  |  | 19710
Net Paid to OWP |  |  |  |  | 374498
B. PAY APPLICATION TIMELINE
App# | Date | Period Billing | Retention | Net This Period | Aggregate | % Complete
1 | 2012-07-20 | 12200 | 610 |  | 11590
2 | 2012-08-20 | 39500 | 1975 |  | 49115
3 | 2012-09-20 | 8300 | 415 |  | 57000
4 | 2012-10-20 | 88500 | 4425 |  | 141075
5 | 2012-11-15 | 112480 | 5624 |  | 247931
6 | 2012-12-20 | 13250 | 662.5 |  | 260518.5
7 | 2013-02-19 | 28485 | 1424.25 |  | 287579.25
8 | 2013-03-19 | 6400 | 320 |  | 293659.25
9 | 2013-04-18 | 48175 | 2408.75 |  | 339425.5
10 | 2013-05-19 | 35494 | 1774.7 |  | 373144.8
11 | 2013-08-13 | 1424 | 71.2 |  | 374497.6
13 | 2013-10-24 | 19710.4 | 0 |  | 392208
C. BILLING ↔ JDR TIE-OUT
Metric | SOV | JDR | Δ | Status
Final Contract Value | 394208 | 394208
Retainage | 19710 | 19710
Direct Cost | 280368 | 280368
SOURCES
Job #2009 — Chinn Greenwood Apartments • GC: Chinn Construction, LLC • Seattle, WA
Canonical source: 2009 Job Detail Report.pdf (49 pages, OWP Sage Timberline export)
Cost codes parsed: 26
Unit count (168) and fixture count (812) from greenwood h20 stacks.xls and trim POs
3-level building + lobby: L1 (18 units), L2 (18 units), L3 (18 units), LW (amenity) × south/north stacks
Billing: GREENWOOD AGGREGATE BILLING.xlsx (11 pay apps Jul 2012 – Oct 2013)
Final contract $394,208 (original $384,900 + $9,308 COs)

## Insights
Key Insights — Job #2009 Chinn Greenwood Apartments
Narrative observations distilled from the full JDR analysis
MARGIN PROFILE | Net profit of $113,840 on $394,208 revenue = 28.9% gross margin. Direct cost $280,368 absorbs 71.1% of revenue.
VENDOR CONCENTRATION | Ferguson Enterprises, Inc. alone = $117,439 (67% of all AP) across 65 invoices. Total 13 AP vendors, $174,470 total AP spend.
CREW PROFILE | 23 workers for 3,928 hours = 171 avg hrs/worker. Top 3 workers logged 1,418 hrs combined (36% of all labor).
ROUGHIN DOMINANCE | Code 120 Roughin Labor = 2,311 hrs (59% of all labor) and $46,114 actual. Code 230 Finish Material = $109,976 — 39% of total direct cost.
BUDGET DELIVERY | Revised budget was $317,000; actual direct cost $280,368 → $36,632 variance (11.6% under revised budget).
CONTRACT GROWTH | Contract grew from $384,900 to $394,208 — net +$9,308 (2.4%). Retainage of $19,710 (5%) withheld until closeout.
BURDEN RATIO | Burden codes 995 + 998 = $40,891 on $80,902 labor base = 50.5%. In line with OWP's typical 48–50% labor burden.
PROJECT SCALE | 168 units · 812 fixtures · 16 months. Revenue/unit $2,346, hours/unit 23.4, profit/unit $678.
PRODUCTIVITY | Blended labor rate $20.59/hr. Revenue/hour $100. Profit/hour $29. 246 hrs/month burn rate.
FIXTURE DENSITY | 812 fixtures ÷ 168 units = 4.83 fixtures/unit. Material/fixture $186, labor/fixture $100.
BIGGEST QUESTION
How does this job's 28.9% margin compare across similar projects in the OWP portfolio, and what operational levers drove the result — estimating accuracy, vendor pricing, or labor productivity?
SOURCES
Job #2009 — Chinn Greenwood Apartments • GC: Chinn Construction, LLC • Seattle, WA
Canonical source: 2009 Job Detail Report.pdf (49 pages, OWP Sage Timberline export)
Cost codes parsed: 26
Unit count (168) and fixture count (812) from greenwood h20 stacks.xls and trim POs
3-level building + lobby: L1 (18 units), L2 (18 units), L3 (18 units), LW (amenity) × south/north stacks
Billing: GREENWOOD AGGREGATE BILLING.xlsx (11 pay apps Jul 2012 – Oct 2013)
Final contract $394,208 (original $384,900 + $9,308 COs)

## Benchmark KPIs
Benchmark KPIs
Normalized metrics designed for apples-to-apples comparison across all OWP projects
KPI | Data Name | Value | Category | Notes
Job Number | job_number | 2009 | Profile | OWP job ID
Job Name | job_name | Chinn Greenwood Apartments | Profile
General Contractor | general_contractor | Chinn Construction, LLC | Profile
Location | location | Seattle, WA | Profile
Project Type | project_type | 168-unit apartment building | Profile
Duration (months) | duration_months | 16 | Profile | Jul 2012 – Oct 2013 (~16 months)
Unit Count | unit_count | 168 | Profile
Total Fixtures | total_fixtures | 812 | Profile
Fixtures per Unit | fixtures_per_unit | 4.8333 | Profile
Contract Value (Orig) | contract_original | 384900 | Financial
Contract Value (Final) | contract_final | 394208 | Financial | After change orders
Change Orders ($) | change_orders | 9308 | Financial
Revenue | revenue | 394208 | Financial
Net Profit | net_profit | 113840.13 | Financial
Gross Margin | gross_margin | 0.28878 | Financial
Direct Cost | direct_cost | 280367.87 | Financial
Labor Cost | labor_cost | 80901.5 | Labor | Sum of 11 labor codes
Material Cost | material_cost | 151064.39 | Material | Sum of 9 material codes
Overhead Cost | overhead_cost | 7510.52 | Financial | Sub+Eng+Permits
Burden Cost | burden_cost | 40891.46 | Financial | Codes 995+998
Retainage | retainage | 19710.4 | Financial | 5% withheld
Revenue per Unit | revenue_per_unit | 2346.4762 | Financial
Profit per Unit | profit_per_unit | 677.6198 | Financial
Direct Cost per Unit | cost_per_unit | 1668.8564 | Financial
Labor Cost per Unit | labor_per_unit | 481.5565 | Labor
Material Cost per Unit | material_per_unit | 899.1928 | Material
Revenue per Fixture | revenue_per_fixture | 485.4778 | Financial
Profit per Fixture | profit_per_fixture | 140.1972 | Financial
Cost per Fixture | cost_per_fixture | 345.2806 | Financial
Labor per Fixture | labor_per_fixture | 9963% | Labor
Material per Fixture | material_per_fixture | 186.0399 | Material
Total Labor Hours | total_hours | 3928.5 | Labor | Sum of JDR cost code hours
Total Workers | total_workers | 23 | Labor | Unique payroll IDs
Blended Gross Wage | blended_gross_wage | 2188% | Labor | Pre-burden
Fully-Loaded Wage | fully_loaded_wage | 3100% | Labor | Post-burden
Burden Multiplier | burden_multiplier | 1.4167 | Labor
Hours per Unit | hours_per_unit | 2338% | Labor | Key benchmark
Hours per Fixture | hours_per_fixture | 4.8381 | Labor | Key benchmark
Revenue per Hour | revenue_per_hour | 100.3457 | Productivity
Profit per Hour | profit_per_hour | 2898% | Productivity
Labor % of Revenue | labor_pct_revenue | 0.20523 | Cost Mix
Material % of Revenue | material_pct_revenue | 0.38321 | Cost Mix
Revenue per Month | revenue_per_month | 24638 | Productivity
Hours per Month | hours_per_month | 245.5312 | Productivity
Units per Month | units_per_month | 1050% | Productivity
Total Vendors | total_vendors | 13 | Material | Unique AP vendors
Top Vendor Spend | top_vendor_spend | 117439.01 | Material | Ferguson Enterprises, Inc.
Top Vendor Concentration | top_vendor_pct | 0.67312 | Material
Total POs | total_pos | 7 | Material | Unique POs by filename
Change Order % | co_pct | 0.024183 | Financial
Revenue per Labor Hour | rev_per_labor_hr | 100.3457 | Productivity
SOURCES
Job #2009 — Chinn Greenwood Apartments • GC: Chinn Construction, LLC • Seattle, WA
Canonical source: 2009 Job Detail Report.pdf (49 pages, OWP Sage Timberline export)
Cost codes parsed: 26
Unit count (168) and fixture count (812) from greenwood h20 stacks.xls and trim POs
3-level building + lobby: L1 (18 units), L2 (18 units), L3 (18 units), LW (amenity) × south/north stacks
Billing: GREENWOOD AGGREGATE BILLING.xlsx (11 pay apps Jul 2012 – Oct 2013)
Final contract $394,208 (original $384,900 + $9,308 COs)
51 KPIs with snake_case data_name identifiers for database ingestion

## Vendors
Vendor Detail — Job #2009
Vendors | 13 |  | Top vendor | Ferguson Enterprises, Inc.
Invoices | 98 |  | Top 3 share
Total AP | 174470.05 |  | Source | Job Detail Report (Sage Timberline AP export)
Avg Inv
Rank | Vendor | Vendor Code | Invoices | Total Spend | % of AP | Avg / Invoice
1 | Ferguson Enterprises, Inc. |  | 65 | 117439.01
2 | Keller Supply Company |  | 14 | 29740.43
3 | Mechanical Sales, Inc. |  | 2 | 16339.3
4 | Franklin Engineering |  | 1 | 4895
5 | Mickelo Construction LLC |  | 1 | 2250
6 | Quality Concrete Products, Inc. |  | 4 | 1821
7 | Rosen Supply Company, Inc. |  | 2 | 1040.84
8 | Ferguson Enterprises, Inc. #3007 |  | 1 | 245.19
9 | Bank of America CC |  | 1 | 210
10 | Capital One Credit Card |  | 3 | 167.8
11 | R.A. Brown Backflow Testing |  | 1 | 129
12 | C.M. Hoskins Company |  | 2 | 97.4
13 | DRSi |  | 1 | 95.08
TOTAL

## Reconciliation
Reconciliation — Cross-Tab Tie-out Proofs
Live cross-sheet formulas verify data consistency across all 12 source tabs
Check | Tab A | Tab B | Δ | Status | Tabs
A. OVERVIEW ↔ BENCHMARK KPIS
Direct Cost Total |  |  |  |  | 1↔2↔11
Contract Final Value | 394208 |  |  |  | JDR↔11
Net Profit | 113840.13 |  |  |  | JDR↔11
Gross Margin | 28.88% |  |  |  | JDR↔11
B. OVERVIEW ↔ COST BREAKDOWN (Category Actuals)
Labor Actual |  |  |  |  | 1↔3
Material Actual |  |  |  |  | 1↔3
Overhead Actual |  |  |  |  | 1↔3
Burden Actual |  |  |  |  | 1↔3
C. BUDGET vs ACTUAL ↔ OVERVIEW
Actual Direct Cost |  |  |  |  | 2↔1
Revised Budget Total |  |  |  |  | 2↔1
D. MATERIAL ↔ COST BREAKDOWN ↔ KPIS
Material Actual (Material tab) |  |  |  |  | 4↔3
Material Actual (KPIs) |  |  |  |  | 11↔3
E. CREW & LABOR ↔ PRODUCTIVITY ↔ KPIS (Hours)
Total Hours (Crew tab) |  |  |  |  | 5↔11
Total Hours (Productivity tab) |  |  |  |  | 7↔11
Total Workers | 23 |  |  |  | JDR↔11
F. CREW ANALYTICS ↔ KPIS (Wage Statistics)
Blended Gross Wage |  |  |  |  | 6↔11
Fully-Loaded Wage |  |  |  |  | 6↔11
G. PO COMMITMENTS ↔ KPIS
PO Count |  |  |  |  | 8↔11
H. BILLING & SOV ↔ JDR
Final Contract Value | 394208 | 394208 |  |  | 9↔JDR
Retainage | 19710 | 19710 |  |  | 9↔JDR
Direct Cost | 280368 | 280368 |  |  | 9↔JDR
I. VENDORS ↔ KPIS
Vendor Count |  |  |  |  | 12↔11
Total AP Spend |  | 174470 |  |  | 12↔JDR
J. INSIGHTS (Narrative Review)
10 insight cards — narrative text verified at generation time, no formula check applicable
SOURCES
Job #2009 — Chinn Greenwood Apartments • GC: Chinn Construction, LLC • Seattle, WA
Canonical source: 2009 Job Detail Report.pdf (49 pages, OWP Sage Timberline export)
Cost codes parsed: 26
Unit count (168) and fixture count (812) from greenwood h20 stacks.xls and trim POs
3-level building + lobby: L1 (18 units), L2 (18 units), L3 (18 units), LW (amenity) × south/north stacks
Billing: GREENWOOD AGGREGATE BILLING.xlsx (11 pay apps Jul 2012 – Oct 2013)
Final contract $394,208 (original $384,900 + $9,308 COs)
TIES = within $1 / 5 hrs / exact count • WITHIN = within 5% • OFF = investigate
Cross-sheet formulas (='Tab'!Cell) update automatically when source tabs change
Tabs: 1=Overview 2=BvA 3=CostBkdn 4=Material 5=Crew 6=CrewAnalytics 7=Productivity
8=PO 9=Billing 10=Insights 11=KPIs 12=Vendors 13=Reconciliation (this tab)