## Overview
Job #2012 · Exxel Pacific 8th Ave Apartments
Cortex JCR Summary · Schema v3 (Reconciled) · Exxel Pacific, Inc. · Seattle, WA · 163-unit multifamily · Mar 2013–Jul 2014
SCHEMA VERSION & RECONCILIATION
Schema Version | notion_v3
Reconciliation Date | 2026-04-18
Canonical Budget | revised_budget (see Reconciliation Proofs tab)
Canonical Wage Basis | pr_src_cost_per_hr (fully-loaded) + per_worker_gross_wage (disambiguated)
Transactions Grain | 2,740 line items (PR/AP/GL) — matches Sam v3 grain
OT/REG/DT Split | per cost code (see Budget vs Actual tab)
Net Due + Retainage | per cost code (see Budget vs Actual tab)
Insights Structure | 10 narrative cards with category tags (see Insights tab)
CONTRACT | DIRECT COST | NET PROFIT | PR-SRC / HR | PER-WORKER WAGE
$1,391,455 | $858,181 | $533,274 | $30.03 | $19.89
final | JDR totals | 38.3% margin | Sam basis | Crew-tab basis
TAB INDEX (11 tabs · reconciled schema)
Overview | This tab — schema provenance + KPIs
Budget vs Actual | Per-code budget/actual + REG/OT/DT hours + Net Due + Retainage (Actions #5, #6)
Transactions | 2,740 PR/AP/GL line items (Action #4 — matches Sam v3 grain)
Crew & Labor | 40 workers with hours + gross pay + per-worker wage (Crew-tab basis)
Wage Basis Canonicals | Three wage rates published side-by-side (Action #3)
Vendors | 16 AP vendors with invoices + spend
Billing & SOV | 15 pay apps · retainage $69,573 · SOV tie-out
Change Log | 8 change events (CO, ASI, T&M, Backcharges)
Insights | 10 structured narrative cards with category tags (Action #10)
Metric Registry | Notion ↔ Sam v3 schema crosswalk with canonical names
Reconciliation Proofs | BOTH-sided canonicals: budget basis (Action #2) + wage basis (Action #3)

## Budget vs Actual
Budget vs Actual — Per-Code Detail (Schema v3)
Canonical budget = revised_budget. OT/REG/DT hours split per code. Retainage prorated. 31 non-Sales cost codes. Orig total $1,065,992 · Rev total $1,058,658 (Δ $7,334) · Actual $858,181.
Code | Category | Description | Orig Budget | Rev Budget (canonical) | Actual | Variance ($) | % Used | Reg Hrs | OT Hrs | DT Hrs | Total Hrs | Net Due (remaining) | Retainage (prorated) | Notes
011 | Labor | DS & RD Labor | 12500 | 12500 | 3752.5 | -8747.5 | 30.02% | 155 | 28 | 0 | 183 | 8747.5 | 304.2154 | Under-utilized
100 | Labor | Supervision | 8100 | 8100 | 6023 | -2077 | 74.36% | 179 | 0 | 0 | 179 | 2077 | 488.2849 | Under budget
101 | Labor | Takeoff & Purchase Labor | 12150 | 12150 | 6161.5 | -5988.5 | 50.71% | 186.5 | 0 | 0 | 186.5 | 5988.5 | 499.5131 | Under budget
110 | Labor | Underground Labor | 5800 | 5800 | 3184.25 | -2615.75 | 54.9% | 145.5 | 0 | 0 | 145.5 | 2615.75 | 258.1473 | Under budget
111 | Labor | Garage Labor | 14600 | 14600 | 19353.5 | 4753.5 | 132.6% | 808 | 80 | 0 | 888 | -4753.5 | 1568.9892 | Overrun
112 | Labor | Canout Labor | 11700 | 11700 | 5424 | -6276 | 46.36% | 236 | 2 | 0 | 238 | 6276 | 439.7239 | Under-utilized
113 | Labor | Foundation Drain Labor | 2700 | 2700 | 984 | -1716 | 36.44% | 50 | 0 | 0 | 50 | 1716 | 79.7729 | Under-utilized
120 | Labor | Roughin Labor | 139800 | 139800 | 177291.75 | 37491.75 | 126.8% | 8058 | 1261.5 | 0 | 9319.5 | -37491.75 | 14373.0506 | Overrun
130 | Labor | Finish Labor | 31000 | 31000 | 34658.38 | 3658.38 | 111.8% | 1840.75 | 0 | 0 | 1840.75 | -3658.38 | 2809.7565 | Overrun
140 | Labor | Gas Labor | 3300 | 3300 | 2168 | -1132 | 65.7% | 104 | 0 | 0 | 104 | 1132 | 175.7599 | Under budget
141 | Labor | Water Main/Insulation Lab | 41000 | 41000 | 15756 | -25244 | 38.43% | 800 | 0 | 0 | 800 | 25244 | 1277.3397 | Under-utilized
142 | Labor | Mech Room Labor | 3525 | 3525 | 9784 | 6259 | 277.6% | 379 | 0 | 0 | 379 | -6259 | 793.1893 | CRITICAL overrun
145 | Labor | Tub/Shower Labor | 19800 | 19800 | 6781 | -13019 | 34.25% | 279 | 59 | 0 | 338 | 13019 | 549.736 | Under-utilized
039 | Material | DS & RD Material | 17900 | 17900 | 5066.8 | -12833.2 | 28.31% | 0 | 0 | 0 | 0 | 12833.2 | 410.7657 | Under-utilized
210 | Material | Underground Material | 4300 | 4300 | 1635.51 | -2664.49 | 38.04% | 0 | 0 | 0 | 0 | 2664.49 | 132.5909 | Under-utilized
211 | Material | Garage Material | 11970 | 11970 | 6599.03 | -5370.97 | 55.13% | 0 | 0 | 0 | 0 | 5370.97 | 534.9837 | Under budget
212 | Material | Canout Material | 13130 | 13130 | 8579.19 | -4550.81 | 65.34% | 0 | 0 | 0 | 0 | 4550.81 | 695.5153 | Under budget
213 | Material | Foundation Material | 2700 | 2700 | 1789.12 | -910.88 | 66.26% | 0 | 0 | 0 | 0 | 910.88 | 145.044 | Under budget
220 | Material | Roughin Material | 161200 | 161200 | 94000.7 | -67199.3 | 58.31% | 0 | 1 | 0 | 1 | 67199.3 | 7620.6412 | Under budget
230 | Material | Finish Material | 261600 | 269866 | 210145.22 | -59720.78 | 77.87% | 0 | 0 | 0 | 0 | 59720.78 | 17036.4829 | Under budgetBudget revised -8,266
240 | Material | Gas Material | 3000 | 3000 | 996.32 | -2003.68 | 33.21% | 0 | 0 | 0 | 0 | 2003.68 | 80.7717 | Under-utilized
241 | Material | Water Main/Insulation Mat | 65600 | 65600 | 36964.67 | -28635.33 | 56.35% | 0 | 0 | 0 | 0 | 28635.33 | 2996.7275 | Under budget
242 | Material | Mech Room Material | 12000 | 12000 | 22695.31 | 10695.31 | 189.1% | 0 | 0 | 0 | 0 | -10695.31 | 1839.9099 | CRITICAL overrun
245 | Material | Tub/Shower Material | 0 | 0 | 2278.99 | 2278.99 | 0% | 0 | 0 | 0 | 0 | -2278.99 | 184.7578
600 | Overhead | Subcontractor | 1000 | 1000 | 186 | -814 | 18.6% | 0 | 0 | 0 | 0 | 814 | 15.079 | Under-utilized
601 | Overhead | Engineering/Plans | 22000 | 22000 | 15682.03 | -6317.97 | 71.28% | 0 | 0 | 0 | 0 | 6317.97 | 1271.3429 | Under budget
603 | Overhead | Permits & Licenses | 10900 | 10900 | 9741.88 | -1158.12 | 89.38% | 0 | 0 | 0 | 0 | 1158.12 | 789.7747 | Under budget
604 | Overhead | Backcharges | 0 | 0 | 1837.5 | 1837.5 | 0% | 0 | 0 | 0 | 0 | -1837.5 | 148.9662
607 | Overhead | Other Expenses | 25600 | 10000 | 70.71 | -9929.29 | 0.7071% | 0 | 0 | 0 | 0 | 9929.29 | 5.7325 | Under-utilizedBudget revised +15,600
995 | Burden | Payroll Burden | 125049.58 | 125049.58 | 126300.46 | 1250.88 | 101% | 0 | 0 | 0 | 0 | -1250.88 | 0
998 | Burden | Payroll Taxes | 22067.57 | 22067.57 | 22289.38 | 221.81 | 101% | 0 | 0 | 0 | 0 | -221.81 | 0
TOTAL |  | All non-Sales codes | 1065992.15 | 1058658.15 | 858180.7 | -200477.45 | 81.06% | 13220.75 | 1431.5 | 0 | 14652.25 | 200477.45 | 57526.5646

## Transactions
Transactions — JDR Line-Item Detail (Action #4)
2,740 line items from Sage Timberline JDR · PR=2,415 · AP=186 · GL=139 · Matches Sam v3 schema grain.
Txn ID | Src | Ref # | Post Date | Code | Description | Party Code | Party Name | Work/Inv Date | Hour Type | Hours | Amount | Net Due | Retainage | Check/Inv #
T0001 | PR | 166 | 09/13/13 | 011 | DS & RD Labor | CA75 | Castro Hernandez, Carlos E | 09/11/13 | Regular | 7 | 175 |  |  | 4235
T0002 | PR | 175 | 09/13/13 | 011 | DS & RD Labor | HO14 | Holmes, Anthony R | 09/11/13 | Overtime | 4 | 78 |  |  | 4244
T0003 | PR | 175 | 09/13/13 | 011 | DS & RD Labor | HO14 | Holmes, Anthony R | 09/11/13 | Regular | 16 | 208 |  |  | 4244
T0004 | PR | 185 | 09/13/13 | 011 | DS & RD Labor | PA46 | Palma Vides, Hugo | 09/11/13 | Overtime | 4 | 162 |  |  | 4254
T0005 | PR | 185 | 09/13/13 | 011 | DS & RD Labor | PA46 | Palma Vides, Hugo | 09/11/13 | Regular | 6 | 162 |  |  | 4254
T0006 | PR | 270 | 09/20/13 | 011 | DS & RD Labor | HO14 | Holmes, Anthony R | 09/18/13 | Regular | 38 | 494 |  |  | 4283
T0007 | PR | 280 | 09/20/13 | 011 | DS & RD Labor | PA11 | Paco Leyva, Orlando | 09/18/13 | Overtime | 6 | 130.5 |  |  | 4293
T0008 | PR | 280 | 09/20/13 | 011 | DS & RD Labor | PA11 | Paco Leyva, Orlando | 09/18/13 | Regular | 24 | 348 |  |  | 4293
T0009 | PR | 281 | 09/20/13 | 011 | DS & RD Labor | PA46 | Palma Vides, Hugo | 09/18/13 | Overtime | 6 | 243 |  |  | 4294
T0010 | PR | 281 | 09/20/13 | 011 | DS & RD Labor | PA46 | Palma Vides, Hugo | 09/18/13 | Regular | 32 | 864 |  |  | 4294
T0011 | PR | 404 | 09/27/13 | 011 | DS & RD Labor | PA46 | Palma Vides, Hugo | 09/25/13 | Overtime | 6 | 243 |  |  | 4335
T0012 | PR | 25 | 10/04/13 | 011 | DS & RD Labor | PA11 | Paco Leyva, Orlando | 10/02/13 | Regular | 24 | 348 |  |  | 4375
T0013 | PR | 91 | 10/11/13 | 011 | DS & RD Labor | PA46 | Palma Vides, Hugo | 10/09/13 | Overtime | 2 | 81 |  |  | 4418
T0014 | PR | 91 | 10/11/13 | 011 | DS & RD Labor | PA46 | Palma Vides, Hugo | 10/09/13 | Regular | 8 | 216 |  |  | 4418
T0015 | AP | 269 | 08/20/13 | 039 | DS & RD Material | 2012RS | Rosen Supply Company, Inc. $8th Ave | 08/13/13 | Inv |  | 479.84 |  |  | 4175052-00
T0016 | AP | 270 | 08/20/13 | 039 | DS & RD Material | 2012RS | Rosen Supply Company, Inc. $8th Ave | 08/13/13 | Inv |  | 677.58 |  |  | 4175054-00
T0017 | AP | 448 | 09/30/13 | 039 | DS & RD Material | 2012FE | Ferguson Enterprises, Inc. $8th Ave | 09/23/13 | Inv |  | 3991.47 |  |  | 2731677
T0018 | AP | 144 | 10/10/13 | 039 | DS & RD Material | 2012RS | Rosen Supply Company, Inc. $8th Ave | 09/27/13 | Inv |  | -82.09 |  |  | 4184849-00
T0019 | PR | 286 | 03/29/13 | 100 | Supervision | GE69 | Gerard, Jeffrey S | 03/27/13 | Regular | 1 | 33 |  |  | 3486
T0020 | PR | 153 | 04/19/13 | 100 | Supervision | GE69 | Gerard, Jeffrey S | 04/17/13 | Regular | 1.5 | 49.5 |  |  | 3569
T0021 | PR | 232 | 04/26/13 | 100 | Supervision | GE69 | Gerard, Jeffrey S | 04/24/13 | Regular | 2 | 66 |  |  | 3595
T0022 | PR | 9 | 05/03/13 | 100 | Supervision | GE69 | Gerard, Jeffrey S | 05/01/13 | Regular | 2 | 66 |  |  | 3622
T0023 | PR | 85 | 05/10/13 | 100 | Supervision | GE69 | Gerard, Jeffrey S | 05/08/13 | Regular | 2 | 66 |  |  | 3649
T0024 | PR | 88 | 05/10/13 | 100 | Supervision | LI49 | Lima Romero, Melvin A | 05/08/13 | Regular | 7 | 119 |  |  | 3652
T0025 | PR | 176 | 05/17/13 | 100 | Supervision | LI49 | Lima Romero, Melvin A | 05/15/13 | Regular | 7 | -133 |  |  | 3679
T0026 | PR | 264 | 05/24/13 | 100 | Supervision | GE69 | Gerard, Jeffrey S | 05/22/13 | Regular | 4 | 140 |  |  | 3703
T0027 | PR | 325 | 05/31/13 | 100 | Supervision | GE69 | Gerard, Jeffrey S | 05/29/13 | Regular | 1.5 | 52.5 |  |  | 3730
T0028 | PR | 97 | 06/14/13 | 100 | Supervision | GE69 | Gerard, Jeffrey S | 06/12/13 | Regular | 3 | 105 |  |  | 3787
T0029 | PR | 247 | 06/28/13 | 100 | Supervision | GE69 | Gerard, Jeffrey S | 06/26/13 | Regular | 4.5 | 157.5 |  |  | 3851
T0030 | PR | 12 | 07/03/13 | 100 | Supervision | GE69 | Gerard, Jeffrey S | 07/02/13 | Regular | 4.5 | 157.5 |  |  | 3884
T0031 | PR | 210 | 07/19/13 | 100 | Supervision | GE69 | Gerard, Jeffrey S | 07/17/13 | Regular | 1 | 35 |  |  | 3951
T0032 | PR | 283 | 07/26/13 | 100 | Supervision | GE69 | Gerard, Jeffrey S | 07/24/13 | Regular | 3.5 | 122.5 |  |  | 3984
T0033 | PR | 11 | 08/02/13 | 100 | Supervision | GE69 | Gerard, Jeffrey S | 07/31/13 | Regular | 1 | 35 |  |  | 4019
T0034 | PR | 93 | 08/09/13 | 100 | Supervision | GE69 | Gerard, Jeffrey S | 08/07/13 | Regular | 4 | 140 |  |  | 4055
T0035 | PR | 206 | 08/16/13 | 100 | Supervision | GE69 | Gerard, Jeffrey S | 08/14/13 | Regular | 5.5 | 192.5 |  |  | 4096
T0036 | PR | 287 | 08/23/13 | 100 | Supervision | GE69 | Gerard, Jeffrey S | 08/21/13 | Regular | 6.5 | 227.5 |  |  | 4132
T0037 | PR | 397 | 08/30/13 | 100 | Supervision | GE69 | Gerard, Jeffrey S | 08/28/13 | Regular | 13.5 | 472.5 |  |  | 4168
T0038 | PR | 60 | 09/06/13 | 100 | Supervision | GE69 | Gerard, Jeffrey S | 09/04/13 | Regular | 11 | 385 |  |  | 4204
T0039 | PR | 172 | 09/13/13 | 100 | Supervision | GE69 | Gerard, Jeffrey S | 09/11/13 | Regular | 5.5 | 209 |  |  | 4241
T0040 | PR | 267 | 09/20/13 | 100 | Supervision | GE69 | Gerard, Jeffrey S | 09/18/13 | Regular | 9 | 342 |  |  | 4280
T0041 | PR | 391 | 09/27/13 | 100 | Supervision | GE69 | Gerard, Jeffrey S | 09/25/13 | Regular | 3 | 114 |  |  | 4322
T0042 | PR | 13 | 10/04/13 | 100 | Supervision | GE69 | Gerard, Jeffrey S | 10/02/13 | Regular | 2 | 76 |  |  | 4363
T0043 | PR | 79 | 10/11/13 | 100 | Supervision | GE69 | Gerard, Jeffrey S | 10/09/13 | Regular | 3 | 114 |  |  | 4406
T0044 | PR | 214 | 10/18/13 | 100 | Supervision | GE69 | Gerard, Jeffrey S | 10/16/13 | Regular | 4 | 152 |  |  | 4448
T0045 | PR | 308 | 10/25/13 | 100 | Supervision | GE69 | Gerard, Jeffrey S | 10/23/13 | Regular | 5.5 | 209 |  |  | 4491
T0046 | PR | 407 | 10/31/13 | 100 | Supervision | GE69 | Gerard, Jeffrey S | 10/30/13 | Regular | 2 | 76 |  |  | 4535
T0047 | PR | 109 | 11/08/13 | 100 | Supervision | GE69 | Gerard, Jeffrey S | 11/06/13 | Regular | 4.5 | 171 |  |  | 4579
T0048 | PR | 196 | 11/15/13 | 100 | Supervision | GE69 | Gerard, Jeffrey S | 11/13/13 | Regular | 5.5 | 209 |  |  | 4624
T0049 | PR | 276 | 11/22/13 | 100 | Supervision | GE69 | Gerard, Jeffrey S | 11/20/13 | Regular | 3 | 114 |  |  | 4670
T0050 | PR | 397 | 11/27/13 | 100 | Supervision | GE69 | Gerard, Jeffrey S | 11/26/13 | Regular | 2 | 76 |  |  | 4715
T0051 | PR | 452 | 11/30/13 | 100 | Supervision | GE69 | Gerard, Jeffrey S | 11/30/13 | Regular | 1 | 38 |  |  | 4764
T0052 | PR | 61 | 12/13/13 | 100 | Supervision | GE69 | Gerard, Jeffrey S | 12/11/13 | Regular | 1 | 38 |  |  | 4808
T0053 | PR | 245 | 12/20/13 | 100 | Supervision | GE69 | Gerard, Jeffrey S | 12/18/13 | Regular | 1 | 38 |  |  | 4903
T0054 | PR | 148 | 01/10/14 | 100 | Supervision | GE69 | Gerard, Jeffrey S | 01/08/14 | Regular | 2.5 | 95 |  |  | 1153
T0055 | PR | 293 | 01/17/14 | 100 | Supervision | GE69 | Gerard, Jeffrey S | 01/15/14 | Regular | 1 | 38 |  |  | 5017
T0056 | PR | 383 | 01/24/14 | 100 | Supervision | GE69 | Gerard, Jeffrey S | 01/22/14 | Regular | 1.5 | 57 |  |  | 5065
T0057 | PR | 581 | 01/31/14 | 100 | Supervision | GE69 | Gerard, Jeffrey S | 01/29/14 | Regular | 2 | 76 |  |  | 5114
T0058 | PR | 31 | 02/07/14 | 100 | Supervision | GE69 | Gerard, Jeffrey S | 02/05/14 | Regular | 1 | 38 |  |  | 5163
T0059 | PR | 178 | 02/14/14 | 100 | Supervision | GE69 | Gerard, Jeffrey S | 02/12/14 | Regular | 1 | 38 |  |  | 5214
T0060 | PR | 287 | 02/21/14 | 100 | Supervision | GE69 | Gerard, Jeffrey S | 02/19/14 | Regular | 1 | 38 |  |  | 5264
T0061 | PR | 379 | 02/28/14 | 100 | Supervision | GE69 | Gerard, Jeffrey S | 02/26/14 | Regular | 4 | 152 |  |  | 5314
T0062 | PR | 16 | 03/07/14 | 100 | Supervision | GE69 | Gerard, Jeffrey S | 03/05/14 | Regular | 4.5 | 171 |  |  | 5364
T0063 | PR | 196 | 03/14/14 | 100 | Supervision | GE69 | Gerard, Jeffrey S | 03/12/14 | Regular | 2 | 76 |  |  | 5415
T0064 | PR | 337 | 03/21/14 | 100 | Supervision | GE69 | Gerard, Jeffrey S | 03/19/14 | Regular | 3 | 114 |  |  | 5466
T0065 | PR | 478 | 03/28/14 | 100 | Supervision | GE69 | Gerard, Jeffrey S | 03/26/14 | Regular | 4 | 152 |  |  | 5516
T0066 | PR | 18 | 04/04/14 | 100 | Supervision | GE69 | Gerard, Jeffrey S | 04/02/14 | Regular | 7.5 | 285 |  |  | 5567
T0067 | PR | 141 | 04/11/14 | 100 | Supervision | GE69 | Gerard, Jeffrey S | 04/09/14 | Regular | 3 | 114 |  |  | 5620
T0068 | PR | 260 | 04/18/14 | 100 | Supervision | GE69 | Gerard, Jeffrey S | 04/16/14 | Regular | 2 | 76 |  |  | 5674
T0069 | PR | 398 | 04/25/14 | 100 | Supervision | GE69 | Gerard, Jeffrey S | 04/23/14 | Regular | 1 | 38 |  |  | 5727
T0070 | PR | 207 | 01/25/13 | 101 | Takeoff & Purchase Labor | GE69 | Gerard, Jeffrey S | 01/23/13 | Regular | 5.5 | 181.5 |  |  | 3226
T0071 | PR | 9 | 03/01/13 | 101 | Takeoff & Purchase Labor | GE69 | Gerard, Jeffrey S | 02/27/13 | Regular | 2.5 | 82.5 |  |  | 3355
T0072 | PR | 194 | 03/22/13 | 101 | Takeoff & Purchase Labor | GE69 | Gerard, Jeffrey S | 03/20/13 | Regular | 3 | 99 |  |  | 3456
T0073 | PR | 20 | 04/05/13 | 101 | Takeoff & Purchase Labor | GE69 | Gerard, Jeffrey S | 04/03/13 | Regular | 1.5 | 49.5 |  |  | 3513
T0074 | PR | 90 | 04/12/13 | 101 | Takeoff & Purchase Labor | GE69 | Gerard, Jeffrey S | 04/10/13 | Regular | 10 | 330 |  |  | 3540
T0075 | PR | 153 | 04/19/13 | 101 | Takeoff & Purchase Labor | GE69 | Gerard, Jeffrey S | 04/17/13 | Regular | 2.5 | 82.5 |  |  | 3569
T0076 | PR | 232 | 04/26/13 | 101 | Takeoff & Purchase Labor | GE69 | Gerard, Jeffrey S | 04/24/13 | Regular | 2 | 66 |  |  | 3595
T0077 | PR | 9 | 05/03/13 | 101 | Takeoff & Purchase Labor | GE69 | Gerard, Jeffrey S | 05/01/13 | Regular | 6 | 198 |  |  | 3622
T0078 | PR | 85 | 05/10/13 | 101 | Takeoff & Purchase Labor | GE69 | Gerard, Jeffrey S | 05/08/13 | Regular | 6 | 198 |  |  | 3649
T0079 | PR | 88 | 05/10/13 | 101 | Takeoff & Purchase Labor | LI49 | Lima Romero, Melvin A | 05/08/13 | Regular | 7 | 119 |  |  | 3652
T0080 | PR | 176 | 05/17/13 | 101 | Takeoff & Purchase Labor | LI49 | Lima Romero, Melvin A | 05/15/13 | Regular | 7 | -133 |  |  | 3679
T0081 | PR | 325 | 05/31/13 | 101 | Takeoff & Purchase Labor | GE69 | Gerard, Jeffrey S | 05/29/13 | Regular | 3 | 105 |  |  | 3730
T0082 | PR | 13 | 06/07/13 | 101 | Takeoff & Purchase Labor | GE69 | Gerard, Jeffrey S | 06/05/13 | Regular | 12 | 420 |  |  | 3757
T0083 | PR | 97 | 06/14/13 | 101 | Takeoff & Purchase Labor | GE69 | Gerard, Jeffrey S | 06/12/13 | Regular | 10 | 350 |  |  | 3787
T0084 | PR | 182 | 06/21/13 | 101 | Takeoff & Purchase Labor | GE69 | Gerard, Jeffrey S | 06/19/13 | Regular | 2 | 70 |  |  | 3818
T0085 | PR | 12 | 07/03/13 | 101 | Takeoff & Purchase Labor | GE69 | Gerard, Jeffrey S | 07/02/13 | Regular | 3 | 105 |  |  | 3884
T0086 | PR | 81 | 07/12/13 | 101 | Takeoff & Purchase Labor | GE69 | Gerard, Jeffrey S | 07/10/13 | Regular | 11 | 385 |  |  | 3917
T0087 | PR | 210 | 07/19/13 | 101 | Takeoff & Purchase Labor | GE69 | Gerard, Jeffrey S | 07/17/13 | Regular | 9 | 315 |  |  | 3951
T0088 | PR | 11 | 08/02/13 | 101 | Takeoff & Purchase Labor | GE69 | Gerard, Jeffrey S | 07/31/13 | Regular | 4.5 | 157.5 |  |  | 4019
T0089 | PR | 93 | 08/09/13 | 101 | Takeoff & Purchase Labor | GE69 | Gerard, Jeffrey S | 08/07/13 | Regular | 2.5 | 87.5 |  |  | 4055
T0090 | PR | 206 | 08/16/13 | 101 | Takeoff & Purchase Labor | GE69 | Gerard, Jeffrey S | 08/14/13 | Regular | 1.5 | 52.5 |  |  | 4096
T0091 | PR | 287 | 08/23/13 | 101 | Takeoff & Purchase Labor | GE69 | Gerard, Jeffrey S | 08/21/13 | Regular | 1 | 35 |  |  | 4132
T0092 | PR | 397 | 08/30/13 | 101 | Takeoff & Purchase Labor | GE69 | Gerard, Jeffrey S | 08/28/13 | Regular | 2 | 70 |  |  | 4168
T0093 | PR | 172 | 09/13/13 | 101 | Takeoff & Purchase Labor | GE69 | Gerard, Jeffrey S | 09/11/13 | Regular | 2 | 76 |  |  | 4241
T0094 | PR | 267 | 09/20/13 | 101 | Takeoff & Purchase Labor | GE69 | Gerard, Jeffrey S | 09/18/13 | Regular | 3 | 114 |  |  | 4280
T0095 | PR | 214 | 10/18/13 | 101 | Takeoff & Purchase Labor | GE69 | Gerard, Jeffrey S | 10/16/13 | Regular | 1 | 38 |  |  | 4448
T0096 | PR | 308 | 10/25/13 | 101 | Takeoff & Purchase Labor | GE69 | Gerard, Jeffrey S | 10/23/13 | Regular | 9.5 | 361 |  |  | 4491
T0097 | PR | 407 | 10/31/13 | 101 | Takeoff & Purchase Labor | GE69 | Gerard, Jeffrey S | 10/30/13 | Regular | 2 | 76 |  |  | 4535
T0098 | PR | 109 | 11/08/13 | 101 | Takeoff & Purchase Labor | GE69 | Gerard, Jeffrey S | 11/06/13 | Regular | 8 | 304 |  |  | 4579
T0099 | PR | 196 | 11/15/13 | 101 | Takeoff & Purchase Labor | GE69 | Gerard, Jeffrey S | 11/13/13 | Regular | 5.5 | 209 |  |  | 4624
T0100 | PR | 276 | 11/22/13 | 101 | Takeoff & Purchase Labor | GE69 | Gerard, Jeffrey S | 11/20/13 | Regular | 3.5 | 133 |  |  | 4670
T0101 | PR | 397 | 11/27/13 | 101 | Takeoff & Purchase Labor | GE69 | Gerard, Jeffrey S | 11/26/13 | Regular | 4.5 | 171 |  |  | 4715
T0102 | PR | 341 | 12/27/13 | 101 | Takeoff & Purchase Labor | GE69 | Gerard, Jeffrey S | 12/25/13 | Regular | 1 | 38 |  |  | 4949
T0103 | PR | 581 | 01/31/14 | 101 | Takeoff & Purchase Labor | GE69 | Gerard, Jeffrey S | 01/29/14 | Regular | 4 | 152 |  |  | 5114
T0104 | PR | 31 | 02/07/14 | 101 | Takeoff & Purchase Labor | GE69 | Gerard, Jeffrey S | 02/05/14 | Regular | 5 | 190 |  |  | 5163
T0105 | PR | 178 | 02/14/14 | 101 | Takeoff & Purchase Labor | GE69 | Gerard, Jeffrey S | 02/12/14 | Regular | 2.5 | 95 |  |  | 5214
T0106 | PR | 287 | 02/21/14 | 101 | Takeoff & Purchase Labor | GE69 | Gerard, Jeffrey S | 02/19/14 | Regular | 6.5 | 247 |  |  | 5264
T0107 | PR | 379 | 02/28/14 | 101 | Takeoff & Purchase Labor | GE69 | Gerard, Jeffrey S | 02/26/14 | Regular | 1 | 38 |  |  | 5314
T0108 | PR | 16 | 03/07/14 | 101 | Takeoff & Purchase Labor | GE69 | Gerard, Jeffrey S | 03/05/14 | Regular | 5 | 190 |  |  | 5364
T0109 | PR | 196 | 03/14/14 | 101 | Takeoff & Purchase Labor | GE69 | Gerard, Jeffrey S | 03/12/14 | Regular | 5 | 190 |  |  | 5415
T0110 | PR | 337 | 03/21/14 | 101 | Takeoff & Purchase Labor | GE69 | Gerard, Jeffrey S | 03/19/14 | Regular | 1 | 38 |  |  | 5466
T0111 | PR | 260 | 04/18/14 | 101 | Takeoff & Purchase Labor | GE69 | Gerard, Jeffrey S | 04/16/14 | Regular | 2 | 76 |  |  | 5674
T0112 | PR | 71 | 03/08/13 | 110 | Underground Labor | GE69 | Gerard, Jeffrey S | 03/06/13 | Regular | 2 | 66 |  |  | 3381
T0113 | PR | 153 | 04/19/13 | 110 | Underground Labor | GE69 | Gerard, Jeffrey S | 04/17/13 | Regular | 2 | 66 |  |  | 3569
T0114 | PR | 225 | 04/26/13 | 110 | Underground Labor | BA70 | Barnhart, Joseph N | 04/24/13 | Regular | 3 | 84 |  |  | 3588
T0115 | PR | 227 | 04/26/13 | 110 | Underground Labor | CA77 | Castro Hernandez, Jose A | 04/24/13 | Regular | 3 | 42 |  |  | 3590
T0116 | PR | 232 | 04/26/13 | 110 | Underground Labor | GE69 | Gerard, Jeffrey S | 04/24/13 | Regular | 5 | 165 |  |  | 3595
T0117 | PR | 242 | 04/26/13 | 110 | Underground Labor | QU35 | Quintanilla, Esteban R | 04/24/13 | Regular | 7 | 210 |  |  | 3605
T0118 | PR | 4 | 05/03/13 | 110 | Underground Labor | CA77 | Castro Hernandez, Jose A | 05/01/13 | Regular | 4 | 56 |  |  | 3617
T0119 | PR | 9 | 05/03/13 | 110 | Underground Labor | GE69 | Gerard, Jeffrey S | 05/01/13 | Regular | 3 | 99 |  |  | 3622
T0120 | PR | 19 | 05/03/13 | 110 | Underground Labor | QU35 | Quintanilla, Esteban R | 05/01/13 | Regular | 8 | 240 |  |  | 3632
T0121 | PR | 26 | 05/03/13 | 110 | Underground Labor | VE45 | Veley, Nathaniel S | 05/01/13 | Regular | 4 | 100 |  |  | 3639
T0122 | PR | 85 | 05/10/13 | 110 | Underground Labor | GE69 | Gerard, Jeffrey S | 05/08/13 | Regular | 3 | 99 |  |  | 3649
T0123 | PR | 93 | 05/10/13 | 110 | Underground Labor | PA11 | Paco Leyva, Orlando | 05/08/13 | Regular | 24 | 288 |  |  | 3657
T0124 | PR | 102 | 05/10/13 | 110 | Underground Labor | VE45 | Veley, Nathaniel S | 05/08/13 | Regular | 26 | 650 |  |  | 3666
T0125 | PR | 181 | 05/17/13 | 110 | Underground Labor | PA11 | Paco Leyva, Orlando | 05/15/13 | Regular | 20 | 270 |  |  | 3684
T0126 | PR | 190 | 05/17/13 | 110 | Underground Labor | VE45 | Veley, Nathaniel S | 05/15/13 | Regular | 16 | 432 |  |  | 3693
T0127 | PR | 272 | 05/24/13 | 110 | Underground Labor | PA11 | Paco Leyva, Orlando | 05/22/13 | Regular | 7.5 | 101.25 |  |  | 3711
T0128 | PR | 281 | 05/24/13 | 110 | Underground Labor | VE45 | Veley, Nathaniel S | 05/22/13 | Regular | 8 | 216 |  |  | 3720
T0129 | PR | 30 | 06/07/13 | 111 | Garage Labor | VE45 | Veley, Nathaniel S | 06/05/13 | Regular | 4 | 108 |  |  | 3774
T0130 | PR | 11 | 08/02/13 | 111 | Garage Labor | GE69 | Gerard, Jeffrey S | 07/31/13 | Regular | 4 | 140 |  |  | 4019
T0131 | PR | 14 | 08/02/13 | 111 | Garage Labor | HU04 | Hubbard, Dustin R | 07/31/13 | Regular | 3 | 36 |  |  | 4022
T0132 | PR | 84 | 08/09/13 | 111 | Garage Labor | AR70 | Arreola, Israel A | 08/07/13 | Regular | 8 | 116 |  |  | 4046
T0133 | PR | 105 | 08/09/13 | 111 | Garage Labor | PA11 | Paco Leyva, Orlando | 08/07/13 | Regular | 8 | 116 |  |  | 4067
T0134 | PR | 113 | 08/09/13 | 111 | Garage Labor | SE64 | Sepulveda Gonzalez, Alfredo | 08/07/13 | Overtime | 8 | 276 |  |  | 4075
T0135 | PR | 126 | 08/09/13 | 111 | Garage Labor | SE64 | Sepulveda Gonzalez, Alfredo | 08/07/13 | Overtime | 8 | -276 |  |  | 4075
T0136 | PR | 131 | 08/09/13 | 111 | Garage Labor | SE64 | Sepulveda Gonzalez, Alfredo | 08/07/13 | Overtime | 8 | 288 |  |  | 4085
T0137 | PR | 218 | 08/16/13 | 111 | Garage Labor | PA11 | Paco Leyva, Orlando | 08/14/13 | Regular | 24 | 348 |  |  | 4108
T0138 | PR | 230 | 08/16/13 | 111 | Garage Labor | VE45 | Veley, Nathaniel S | 08/14/13 | Regular | 24 | 672 |  |  | 4120
T0139 | PR | 284 | 08/23/13 | 111 | Garage Labor | CO71 | Cortes Mendiola, Victor H | 08/21/13 | Regular | 24 | 576 |  |  | 4129
T0140 | PR | 299 | 08/23/13 | 111 | Garage Labor | PA11 | Paco Leyva, Orlando | 08/21/13 | Regular | 32 | 464 |  |  | 4144
T0141 | PR | 307 | 08/23/13 | 111 | Garage Labor | SE64 | Sepulveda Gonzalez, Alfredo | 08/21/13 | Regular | 20 | 480 |  |  | 4152
T0142 | PR | 310 | 08/23/13 | 111 | Garage Labor | SP17 | Spears, Gregory M | 08/21/13 | Regular | 24 | 312 |  |  | 4155
T0143 | PR | 311 | 08/23/13 | 111 | Garage Labor | VE45 | Veley, Nathaniel S | 08/21/13 | Regular | 36 | 1008 |  |  | 4156
T0144 | PR | 394 | 08/30/13 | 111 | Garage Labor | CO71 | Cortes Mendiola, Victor H | 08/28/13 | Overtime | 6 | 216 |  |  | 4165
T0145 | PR | 394 | 08/30/13 | 111 | Garage Labor | CO71 | Cortes Mendiola, Victor H | 08/28/13 | Regular | 40 | 960 |  |  | 4165
T0146 | PR | 400 | 08/30/13 | 111 | Garage Labor | HO14 | Holmes, Anthony R | 08/28/13 | Regular | 20 | 260 |  |  | 4171
T0147 | PR | 409 | 08/30/13 | 111 | Garage Labor | PA11 | Paco Leyva, Orlando | 08/28/13 | Overtime | 3 | 65.25 |  |  | 4180
T0148 | PR | 409 | 08/30/13 | 111 | Garage Labor | PA11 | Paco Leyva, Orlando | 08/28/13 | Regular | 43 | 623.5 |  |  | 4180
T0149 | PR | 410 | 08/30/13 | 111 | Garage Labor | PA46 | Palma Vides, Hugo | 08/28/13 | Overtime | 6 | 243 |  |  | 4181
T0150 | PR | 410 | 08/30/13 | 111 | Garage Labor | PA46 | Palma Vides, Hugo | 08/28/13 | Regular | 24 | 648 |  |  | 4181
T0151 | PR | 419 | 08/30/13 | 111 | Garage Labor | SP17 | Spears, Gregory M | 08/28/13 | Overtime | 4 | 78 |  |  | 4190
T0152 | PR | 419 | 08/30/13 | 111 | Garage Labor | SP17 | Spears, Gregory M | 08/28/13 | Regular | 37 | 481 |  |  | 4190
T0153 | PR | 420 | 08/30/13 | 111 | Garage Labor | VE45 | Veley, Nathaniel S | 08/28/13 | Overtime | 2 | 84 |  |  | 4191
T0154 | PR | 420 | 08/30/13 | 111 | Garage Labor | VE45 | Veley, Nathaniel S | 08/28/13 | Regular | 40 | 1120 |  |  | 4191
T0155 | PR | 422 | 08/30/13 | 111 | Garage Labor | SE64 | Sepulveda Gonzalez, Alfredo | 08/28/13 | Overtime | 6 | 216 |  |  | 4193
T0156 | PR | 422 | 08/30/13 | 111 | Garage Labor | SE64 | Sepulveda Gonzalez, Alfredo | 08/28/13 | Regular | 40 | 960 |  |  | 4193
T0157 | PR | 57 | 09/06/13 | 111 | Garage Labor | CO71 | Cortes Mendiola, Victor H | 09/04/13 | Regular | 28 | 672 |  |  | 4201
T0158 | PR | 72 | 09/06/13 | 111 | Garage Labor | PA11 | Paco Leyva, Orlando | 09/04/13 | Regular | 38 | 551 |  |  | 4216
T0159 | PR | 73 | 09/06/13 | 111 | Garage Labor | PA46 | Palma Vides, Hugo | 09/04/13 | Regular | 38 | 1026 |  |  | 4217
T0160 | PR | 80 | 09/06/13 | 111 | Garage Labor | SE64 | Sepulveda Gonzalez, Alfredo | 09/04/13 | Regular | 28 | 672 |  |  | 4224
T0161 | PR | 84 | 09/06/13 | 111 | Garage Labor | VE45 | Veley, Nathaniel S | 09/04/13 | Regular | 37 | 1036 |  |  | 4228
T0162 | PR | 184 | 09/13/13 | 111 | Garage Labor | PA11 | Paco Leyva, Orlando | 09/11/13 | Overtime | 13 | 282.75 |  |  | 4253
T0163 | PR | 184 | 09/13/13 | 111 | Garage Labor | PA11 | Paco Leyva, Orlando | 09/11/13 | Regular | 40 | 580 |  |  | 4253
T0164 | PR | 185 | 09/13/13 | 111 | Garage Labor | PA46 | Palma Vides, Hugo | 09/11/13 | Overtime | 2 | 81 |  |  | 4254
T0165 | PR | 185 | 09/13/13 | 111 | Garage Labor | PA46 | Palma Vides, Hugo | 09/11/13 | Regular | 34 | 918 |  |  | 4254
T0166 | PR | 198 | 09/13/13 | 111 | Garage Labor | VE45 | Veley, Nathaniel S | 09/11/13 | Regular | 14 | 392 |  |  | 4267
T0167 | PR | 280 | 09/20/13 | 111 | Garage Labor | PA11 | Paco Leyva, Orlando | 09/18/13 | Overtime | 8 | 174 |  |  | 4293
T0168 | PR | 280 | 09/20/13 | 111 | Garage Labor | PA11 | Paco Leyva, Orlando | 09/18/13 | Regular | 16 | 232 |  |  | 4293
T0169 | PR | 281 | 09/20/13 | 111 | Garage Labor | PA46 | Palma Vides, Hugo | 09/18/13 | Overtime | 2 | 81 |  |  | 4294
T0170 | PR | 281 | 09/20/13 | 111 | Garage Labor | PA46 | Palma Vides, Hugo | 09/18/13 | Regular | 8 | 216 |  |  | 4294
T0171 | PR | 295 | 09/20/13 | 111 | Garage Labor | VE45 | Veley, Nathaniel S | 09/18/13 | Overtime | 2 | 84 |  |  | 4308
T0172 | PR | 295 | 09/20/13 | 111 | Garage Labor | VE45 | Veley, Nathaniel S | 09/18/13 | Regular | 16 | 448 |  |  | 4308
T0173 | PR | 238 | 12/20/13 | 111 | Garage Labor | CA75 | Castro Hernandez, Carlos E | 12/18/13 | Overtime | 2 | 81 |  |  | 4896
T0174 | PR | 238 | 12/20/13 | 111 | Garage Labor | CA75 | Castro Hernandez, Carlos E | 12/18/13 | Regular | 8 | 216 |  |  | 4896
T0175 | PR | 17 | 03/07/14 | 111 | Garage Labor | GO56 | Gonzalez Hernandez, Josue | 03/05/14 | Regular | 8 | 112 |  |  | 5365
T0176 | PR | 49 | 03/07/14 | 111 | Garage Labor | WA35 | Waites, Thaddeus Z | 03/05/14 | Regular | 16 | 448 |  |  | 5397
T0177 | PR | 197 | 03/14/14 | 111 | Garage Labor | GO56 | Gonzalez Hernandez, Josue | 03/12/14 | Regular | 8 | 112 |  |  | 5416
T0178 | PR | 202 | 03/14/14 | 111 | Garage Labor | LI49 | Lima Romero, Melvin A | 03/12/14 | Regular | 16 | 320 |  |  | 5421
T0179 | PR | 266 | 05/24/13 | 112 | Canout Labor | HU06 | Hubbard, Robert W | 05/22/13 | Regular | 3.5 | 115.5 |  |  | 3705
T0180 | PR | 272 | 05/24/13 | 112 | Canout Labor | PA11 | Paco Leyva, Orlando | 05/22/13 | Regular | 4 | 54 |  |  | 3711
T0181 | PR | 281 | 05/24/13 | 112 | Canout Labor | VE45 | Veley, Nathaniel S | 05/22/13 | Regular | 4 | 108 |  |  | 3720
T0182 | PR | 325 | 05/31/13 | 112 | Canout Labor | GE69 | Gerard, Jeffrey S | 05/29/13 | Regular | 1 | 35 |  |  | 3730
T0183 | PR | 333 | 05/31/13 | 112 | Canout Labor | PA11 | Paco Leyva, Orlando | 05/29/13 | Regular | 9 | 121.5 |  |  | 3738
T0184 | PR | 342 | 05/31/13 | 112 | Canout Labor | VE45 | Veley, Nathaniel S | 05/29/13 | Regular | 23 | 621 |  |  | 3747
T0185 | PR | 21 | 06/07/13 | 112 | Canout Labor | PA11 | Paco Leyva, Orlando | 06/05/13 | Regular | 14 | 189 |  |  | 3765
T0186 | PR | 30 | 06/07/13 | 112 | Canout Labor | VE45 | Veley, Nathaniel S | 06/05/13 | Regular | 8 | 216 |  |  | 3774
T0187 | PR | 97 | 06/14/13 | 112 | Canout Labor | GE69 | Gerard, Jeffrey S | 06/12/13 | Regular | 3 | 105 |  |  | 3787
T0188 | PR | 182 | 06/21/13 | 112 | Canout Labor | GE69 | Gerard, Jeffrey S | 06/19/13 | Regular | 4 | 140 |  |  | 3818
T0189 | PR | 191 | 06/21/13 | 112 | Canout Labor | PA11 | Paco Leyva, Orlando | 06/19/13 | Regular | 8 | 108 |  |  | 3827
T0190 | PR | 202 | 06/21/13 | 112 | Canout Labor | VE45 | Veley, Nathaniel S | 06/19/13 | Regular | 16 | 432 |  |  | 3838
T0191 | PR | 247 | 06/28/13 | 112 | Canout Labor | GE69 | Gerard, Jeffrey S | 06/26/13 | Regular | 5.5 | 192.5 |  |  | 3851
T0192 | PR | 257 | 06/28/13 | 112 | Canout Labor | PA11 | Paco Leyva, Orlando | 06/26/13 | Regular | 17 | 229.5 |  |  | 3861
T0193 | PR | 267 | 06/28/13 | 112 | Canout Labor | VE45 | Veley, Nathaniel S | 06/26/13 | Regular | 19 | 513 |  |  | 3871
T0194 | PR | 12 | 07/03/13 | 112 | Canout Labor | GE69 | Gerard, Jeffrey S | 07/02/13 | Regular | 2.5 | 87.5 |  |  | 3884
T0195 | PR | 22 | 07/03/13 | 112 | Canout Labor | PA11 | Paco Leyva, Orlando | 07/02/13 | Regular | 4 | 54 |  |  | 3894
T0196 | PR | 32 | 07/03/13 | 112 | Canout Labor | VE45 | Veley, Nathaniel S | 07/02/13 | Regular | 9 | 243 |  |  | 3904
T0197 | PR | 81 | 07/12/13 | 112 | Canout Labor | GE69 | Gerard, Jeffrey S | 07/10/13 | Regular | 4 | 140 |  |  | 3917
T0198 | PR | 210 | 07/19/13 | 112 | Canout Labor | GE69 | Gerard, Jeffrey S | 07/17/13 | Regular | 11 | 385 |  |  | 3951
T0199 | PR | 213 | 07/19/13 | 112 | Canout Labor | HU04 | Hubbard, Dustin R | 07/17/13 | Regular | 2 | 24 |  |  | 3954
T0200 | PR | 220 | 07/19/13 | 112 | Canout Labor | PA11 | Paco Leyva, Orlando | 07/17/13 | Regular | 12 | 162 |  |  | 3961
T0201 | PR | 231 | 07/19/13 | 112 | Canout Labor | VE45 | Veley, Nathaniel S | 07/17/13 | Overtime | 1 | 40.5 |  |  | 3972
T0202 | PR | 231 | 07/19/13 | 112 | Canout Labor | VE45 | Veley, Nathaniel S | 07/17/13 | Regular | 12 | 324 |  |  | 3972
T0203 | PR | 280 | 07/26/13 | 112 | Canout Labor | CO71 | Cortes Mendiola, Victor H | 07/24/13 | Overtime | 1 | 34.5 |  |  | 3981
T0204 | PR | 280 | 07/26/13 | 112 | Canout Labor | CO71 | Cortes Mendiola, Victor H | 07/24/13 | Regular | 13 | 299 |  |  | 3981
T0205 | PR | 283 | 07/26/13 | 112 | Canout Labor | GE69 | Gerard, Jeffrey S | 07/24/13 | Regular | 3.5 | 122.5 |  |  | 3984
T0206 | PR | 293 | 07/26/13 | 112 | Canout Labor | PA11 | Paco Leyva, Orlando | 07/24/13 | Regular | 20 | 270 |  |  | 3994
T0207 | PR | 21 | 08/02/13 | 112 | Canout Labor | PA11 | Paco Leyva, Orlando | 07/31/13 | Regular | 4 | 58 |  |  | 4029
T0208 | PR | 4 | 05/03/13 | 113 | Foundation Drain Labor | CA77 | Castro Hernandez, Jose A | 05/01/13 | Regular | 15 | 210 |  |  | 3617
T0209 | PR | 17 | 05/03/13 | 113 | Foundation Drain Labor | PA11 | Paco Leyva, Orlando | 05/01/13 | Regular | 5 | 60 |  |  | 3630
T0210 | PR | 19 | 05/03/13 | 113 | Foundation Drain Labor | QU35 | Quintanilla, Esteban R | 05/01/13 | Regular | 12 | 360 |  |  | 3632
T0211 | PR | 93 | 05/10/13 | 113 | Foundation Drain Labor | PA11 | Paco Leyva, Orlando | 05/08/13 | Regular | 8 | 96 |  |  | 3657
T0212 | PR | 102 | 05/10/13 | 113 | Foundation Drain Labor | VE45 | Veley, Nathaniel S | 05/08/13 | Regular | 6 | 150 |  |  | 3666
T0213 | PR | 190 | 05/17/13 | 113 | Foundation Drain Labor | VE45 | Veley, Nathaniel S | 05/15/13 | Regular | 4 | 108 |  |  | 3693
T0214 | PR | 279 | 03/29/13 | 120 | Roughin Labor | BA70 | Barnhart, Joseph N | 03/27/13 | Regular | 3 | 84 |  |  | 3479
T0215 | PR | 300 | 03/29/13 | 120 | Roughin Labor | SA54 | Sanders, Allen O | 03/27/13 | Regular | 4 | 104 |  |  | 3500
T0216 | PR | 22 | 07/03/13 | 120 | Roughin Labor | PA11 | Paco Leyva, Orlando | 07/02/13 | Regular | 5 | 67.5 |  |  | 3894
T0217 | PR | 32 | 07/03/13 | 120 | Roughin Labor | VE45 | Veley, Nathaniel S | 07/02/13 | Regular | 5 | 135 |  |  | 3904
T0218 | PR | 210 | 07/19/13 | 120 | Roughin Labor | GE69 | Gerard, Jeffrey S | 07/17/13 | Regular | 4 | 140 |  |  | 3951
T0219 | PR | 227 | 07/19/13 | 120 | Roughin Labor | SA54 | Sanders, Allen O | 07/17/13 | Regular | 8 | 208 |  |  | 3968
T0220 | PR | 11 | 08/02/13 | 120 | Roughin Labor | GE69 | Gerard, Jeffrey S | 07/31/13 | Regular | 6 | 210 |  |  | 4019
T0221 | PR | 419 | 08/30/13 | 120 | Roughin Labor | SP17 | Spears, Gregory M | 08/28/13 | Overtime | 2 | 39 |  |  | 4190
T0222 | PR | 419 | 08/30/13 | 120 | Roughin Labor | SP17 | Spears, Gregory M | 08/28/13 | Regular | 3 | 39 |  |  | 4190
T0223 | PR | 63 | 09/06/13 | 120 | Roughin Labor | HO14 | Holmes, Anthony R | 09/04/13 | Regular | 38 | 494 |  |  | 4207
T0224 | PR | 70 | 09/06/13 | 120 | Roughin Labor | MO54 | Monico Brambila, Jesus S | 09/04/13 | Regular | 10 | 130 |  |  | 4214
T0225 | PR | 83 | 09/06/13 | 120 | Roughin Labor | SP17 | Spears, Gregory M | 09/04/13 | Regular | 38 | 494 |  |  | 4227
T0226 | PR | 165 | 09/13/13 | 120 | Roughin Labor | CA74 | Castaneda Martinez, Gustavo | 09/11/13 | Overtime | 7 | 283.5 |  |  | 4234
T0227 | PR | 169 | 09/13/13 | 120 | Roughin Labor | CO71 | Cortes Mendiola, Victor H | 09/11/13 | Overtime | 7 | 252 |  |  | 4238
T0228 | PR | 173 | 09/13/13 | 120 | Roughin Labor | GO56 | Gonzalez Hernandez, Josue | 09/11/13 | Overtime | 7 | 126 |  |  | 4242
T0229 | PR | 175 | 09/13/13 | 120 | Roughin Labor | HO14 | Holmes, Anthony R | 09/11/13 | Overtime | 2 | 39 |  |  | 4244
T0230 | PR | 175 | 09/13/13 | 120 | Roughin Labor | HO14 | Holmes, Anthony R | 09/11/13 | Regular | 24 | 312 |  |  | 4244
T0231 | PR | 178 | 09/13/13 | 120 | Roughin Labor | LI49 | Lima Romero, Melvin A | 09/11/13 | Overtime | 7 | 199.5 |  |  | 4247
T0232 | PR | 182 | 09/13/13 | 120 | Roughin Labor | MO54 | Monico Brambila, Jesus S | 09/11/13 | Overtime | 13 | 253.5 |  |  | 4251
T0233 | PR | 182 | 09/13/13 | 120 | Roughin Labor | MO54 | Monico Brambila, Jesus S | 09/11/13 | Regular | 40 | 520 |  |  | 4251
T0234 | PR | 186 | 09/13/13 | 120 | Roughin Labor | QU35 | Quintanilla, Esteban R | 09/11/13 | Regular | 11 | 341 |  |  | 4255
T0235 | PR | 193 | 09/13/13 | 120 | Roughin Labor | SE64 | Sepulveda Gonzalez, Alfredo | 09/11/13 | Overtime | 8 | 288 |  |  | 4262
T0236 | PR | 196 | 09/13/13 | 120 | Roughin Labor | SP17 | Spears, Gregory M | 09/11/13 | Overtime | 13 | 253.5 |  |  | 4265
T0237 | PR | 196 | 09/13/13 | 120 | Roughin Labor | SP17 | Spears, Gregory M | 09/11/13 | Regular | 40 | 520 |  |  | 4265
T0238 | PR | 197 | 09/13/13 | 120 | Roughin Labor | VE25 | Vega Arriaga, Jorge | 09/11/13 | Overtime | 13 | 234 |  |  | 4266
T0239 | PR | 197 | 09/13/13 | 120 | Roughin Labor | VE25 | Vega Arriaga, Jorge | 09/11/13 | Regular | 40 | 480 |  |  | 4266
T0240 | PR | 198 | 09/13/13 | 120 | Roughin Labor | VE45 | Veley, Nathaniel S | 09/11/13 | Overtime | 4 | 168 |  |  | 4267
T0241 | PR | 198 | 09/13/13 | 120 | Roughin Labor | VE45 | Veley, Nathaniel S | 09/11/13 | Regular | 26 | 728 |  |  | 4267
T0242 | PR | 257 | 09/20/13 | 120 | Roughin Labor | AR70 | Arreola, Israel A | 09/18/13 | Regular | 28 | 406 |  |  | 4270
T0243 | PR | 268 | 09/20/13 | 120 | Roughin Labor | GO56 | Gonzalez Hernandez, Josue | 09/18/13 | Overtime | 8 | 144 |  |  | 4281
T0244 | PR | 268 | 09/20/13 | 120 | Roughin Labor | GO56 | Gonzalez Hernandez, Josue | 09/18/13 | Regular | 2 | 24 |  |  | 4281
T0245 | PR | 270 | 09/20/13 | 120 | Roughin Labor | HO14 | Holmes, Anthony R | 09/18/13 | Overtime | 4 | 78 |  |  | 4283
T0246 | PR | 270 | 09/20/13 | 120 | Roughin Labor | HO14 | Holmes, Anthony R | 09/18/13 | Regular | 2 | 26 |  |  | 4283
T0247 | PR | 277 | 09/20/13 | 120 | Roughin Labor | MO54 | Monico Brambila, Jesus S | 09/18/13 | Overtime | 14 | 273 |  |  | 4290
T0248 | PR | 277 | 09/20/13 | 120 | Roughin Labor | MO54 | Monico Brambila, Jesus S | 09/18/13 | Regular | 40 | 520 |  |  | 4290
T0249 | PR | 282 | 09/20/13 | 120 | Roughin Labor | QU35 | Quintanilla, Esteban R | 09/18/13 | Regular | 14 | 434 |  |  | 4295
T0250 | PR | 285 | 09/20/13 | 120 | Roughin Labor | RE54 | Rendon Villasenor, Ismael | 09/18/13 | Regular | 16.5 | 198 |  |  | 4298
T0251 | PR | 288 | 09/20/13 | 120 | Roughin Labor | SA45 | Salazar, Hajdar L | 09/18/13 | Overtime | 6 | 108 |  |  | 4301
T0252 | PR | 293 | 09/20/13 | 120 | Roughin Labor | SP17 | Spears, Gregory M | 09/18/13 | Overtime | 8 | 156 |  |  | 4306
T0253 | PR | 293 | 09/20/13 | 120 | Roughin Labor | SP17 | Spears, Gregory M | 09/18/13 | Regular | 40 | 520 |  |  | 4306
T0254 | PR | 294 | 09/20/13 | 120 | Roughin Labor | VE25 | Vega Arriaga, Jorge | 09/18/13 | Overtime | 14 | 252 |  |  | 4307
T0255 | PR | 294 | 09/20/13 | 120 | Roughin Labor | VE25 | Vega Arriaga, Jorge | 09/18/13 | Regular | 40 | 480 |  |  | 4307
T0256 | PR | 295 | 09/20/13 | 120 | Roughin Labor | VE45 | Veley, Nathaniel S | 09/18/13 | Overtime | 4 | 168 |  |  | 4308
T0257 | PR | 295 | 09/20/13 | 120 | Roughin Labor | VE45 | Veley, Nathaniel S | 09/18/13 | Regular | 24 | 672 |  |  | 4308
T0258 | PR | 381 | 09/27/13 | 120 | Roughin Labor | AR70 | Arreola, Israel A | 09/25/13 | Regular | 6 | 87 |  |  | 4312
T0259 | PR | 382 | 09/27/13 | 120 | Roughin Labor | BA70 | Barnhart, Joseph N | 09/25/13 | Overtime | 6 | 261 |  |  | 4313
T0260 | PR | 388 | 09/27/13 | 120 | Roughin Labor | CO71 | Cortes Mendiola, Victor H | 09/25/13 | Overtime | 6 | 216 |  |  | 4319
T0261 | PR | 392 | 09/27/13 | 120 | Roughin Labor | GO56 | Gonzalez Hernandez, Josue | 09/25/13 | Overtime | 6 | 108 |  |  | 4323
T0262 | PR | 392 | 09/27/13 | 120 | Roughin Labor | GO56 | Gonzalez Hernandez, Josue | 09/25/13 | Regular | 40 | 480 |  |  | 4323
T0263 | PR | 394 | 09/27/13 | 120 | Roughin Labor | HO14 | Holmes, Anthony R | 09/25/13 | Overtime | 2 | 39 |  |  | 4325
T0264 | PR | 394 | 09/27/13 | 120 | Roughin Labor | HO14 | Holmes, Anthony R | 09/25/13 | Regular | 24 | 312 |  |  | 4325
T0265 | PR | 396 | 09/27/13 | 120 | Roughin Labor | LI49 | Lima Romero, Melvin A | 09/25/13 | Overtime | 6 | 171 |  |  | 4327
T0266 | PR | 400 | 09/27/13 | 120 | Roughin Labor | MO54 | Monico Brambila, Jesus S | 09/25/13 | Overtime | 8 | 156 |  |  | 4331
T0267 | PR | 400 | 09/27/13 | 120 | Roughin Labor | MO54 | Monico Brambila, Jesus S | 09/25/13 | Regular | 40 | 520 |  |  | 4331
T0268 | PR | 403 | 09/27/13 | 120 | Roughin Labor | PA11 | Paco Leyva, Orlando | 09/25/13 | Overtime | 8 | 174 |  |  | 4334
T0269 | PR | 403 | 09/27/13 | 120 | Roughin Labor | PA11 | Paco Leyva, Orlando | 09/25/13 | Regular | 40 | 580 |  |  | 4334
T0270 | PR | 404 | 09/27/13 | 120 | Roughin Labor | PA46 | Palma Vides, Hugo | 09/25/13 | Overtime | 2 | 81 |  |  | 4335
T0271 | PR | 404 | 09/27/13 | 120 | Roughin Labor | PA46 | Palma Vides, Hugo | 09/25/13 | Regular | 40 | 1080 |  |  | 4335
T0272 | PR | 405 | 09/27/13 | 120 | Roughin Labor | QU35 | Quintanilla, Esteban R | 09/25/13 | Regular | 48 | 1488 |  |  | 4336
T0273 | PR | 408 | 09/27/13 | 120 | Roughin Labor | RE54 | Rendon Villasenor, Ismael | 09/25/13 | Regular | 19.5 | 234 |  |  | 4339
T0274 | PR | 413 | 09/27/13 | 120 | Roughin Labor | SE64 | Sepulveda Gonzalez, Alfredo | 09/25/13 | Overtime | 6 | 216 |  |  | 4344
T0275 | PR | 416 | 09/27/13 | 120 | Roughin Labor | SP17 | Spears, Gregory M | 09/25/13 | Overtime | 8 | 156 |  |  | 4347
T0276 | PR | 416 | 09/27/13 | 120 | Roughin Labor | SP17 | Spears, Gregory M | 09/25/13 | Regular | 40 | 520 |  |  | 4347
T0277 | PR | 417 | 09/27/13 | 120 | Roughin Labor | VE25 | Vega Arriaga, Jorge | 09/25/13 | Overtime | 8 | 144 |  |  | 4348
T0278 | PR | 417 | 09/27/13 | 120 | Roughin Labor | VE25 | Vega Arriaga, Jorge | 09/25/13 | Regular | 40 | 480 |  |  | 4348
T0279 | PR | 6 | 10/04/13 | 120 | Roughin Labor | CA75 | Castro Hernandez, Carlos E | 10/02/13 | Overtime | 4 | 162 |  |  | 4356
T0280 | PR | 7 | 10/04/13 | 120 | Roughin Labor | CA77 | Castro Hernandez, Jose A | 10/02/13 | Overtime | 3 | 67.5 |  |  | 4357
T0281 | PR | 7 | 10/04/13 | 120 | Roughin Labor | CA77 | Castro Hernandez, Jose A | 10/02/13 | Regular | 40 | 600 |  |  | 4357
T0282 | PR | 8 | 10/04/13 | 120 | Roughin Labor | CH04 | Chavarria Lopez, Omar A | 10/02/13 | Overtime | 3 | 54 |  |  | 4358
T0283 | PR | 8 | 10/04/13 | 120 | Roughin Labor | CH04 | Chavarria Lopez, Omar A | 10/02/13 | Regular | 40 | 480 |  |  | 4358
T0284 | PR | 14 | 10/04/13 | 120 | Roughin Labor | GO56 | Gonzalez Hernandez, Josue | 10/02/13 | Overtime | 3 | 54 |  |  | 4364
T0285 | PR | 14 | 10/04/13 | 120 | Roughin Labor | GO56 | Gonzalez Hernandez, Josue | 10/02/13 | Regular | 40 | 480 |  |  | 4364
T0286 | PR | 22 | 10/04/13 | 120 | Roughin Labor | MO54 | Monico Brambila, Jesus S | 10/02/13 | Overtime | 2.5 | 48.75 |  |  | 4372
T0287 | PR | 22 | 10/04/13 | 120 | Roughin Labor | MO54 | Monico Brambila, Jesus S | 10/02/13 | Regular | 40 | 520 |  |  | 4372
T0288 | PR | 26 | 10/04/13 | 120 | Roughin Labor | PA46 | Palma Vides, Hugo | 10/02/13 | Regular | 40 | 1080 |  |  | 4376
T0289 | PR | 27 | 10/04/13 | 120 | Roughin Labor | QU35 | Quintanilla, Esteban R | 10/02/13 | Overtime | 1 | 46.5 |  |  | 4377
T0290 | PR | 27 | 10/04/13 | 120 | Roughin Labor | QU35 | Quintanilla, Esteban R | 10/02/13 | Regular | 42 | 1302 |  |  | 4377
T0291 | PR | 30 | 10/04/13 | 120 | Roughin Labor | RI84 | Rivera, Eli P | 10/02/13 | Overtime | 3 | 54 |  |  | 4380
T0292 | PR | 30 | 10/04/13 | 120 | Roughin Labor | RI84 | Rivera, Eli P | 10/02/13 | Regular | 40 | 480 |  |  | 4380
T0293 | PR | 31 | 10/04/13 | 120 | Roughin Labor | RI87 | Rivera, Jorge A | 10/02/13 | Overtime | 2 | 54 |  |  | 4381
T0294 | PR | 31 | 10/04/13 | 120 | Roughin Labor | RI87 | Rivera, Jorge A | 10/02/13 | Regular | 16 | 288 |  |  | 4381
T0295 | PR | 38 | 10/04/13 | 120 | Roughin Labor | SP17 | Spears, Gregory M | 10/02/13 | Overtime | 3 | 58.5 |  |  | 4388
T0296 | PR | 38 | 10/04/13 | 120 | Roughin Labor | SP17 | Spears, Gregory M | 10/02/13 | Regular | 40 | 520 |  |  | 4388
T0297 | PR | 39 | 10/04/13 | 120 | Roughin Labor | VE25 | Vega Arriaga, Jorge | 10/02/13 | Overtime | 8 | 144 |  |  | 4389
T0298 | PR | 39 | 10/04/13 | 120 | Roughin Labor | VE25 | Vega Arriaga, Jorge | 10/02/13 | Regular | 40 | 480 |  |  | 4389
T0299 | PR | 68 | 10/11/13 | 120 | Roughin Labor | BA70 | Barnhart, Joseph N | 10/09/13 | Overtime | 8 | 348 |  |  | 4395
T0300 | PR | 71 | 10/11/13 | 120 | Roughin Labor | CA74 | Castaneda Martinez, Gustavo | 10/09/13 | Overtime | 4 | 162 |  |  | 4398
T0301 | PR | 71 | 10/11/13 | 120 | Roughin Labor | CA74 | Castaneda Martinez, Gustavo | 10/09/13 | Regular | 32 | 864 |  |  | 4398
T0302 | PR | 72 | 10/11/13 | 120 | Roughin Labor | CA75 | Castro Hernandez, Carlos E | 10/09/13 | Overtime | 6 | 243 |  |  | 4399
T0303 | PR | 73 | 10/11/13 | 120 | Roughin Labor | CA77 | Castro Hernandez, Jose A | 10/09/13 | Overtime | 8 | 180 |  |  | 4400
T0304 | PR | 73 | 10/11/13 | 120 | Roughin Labor | CA77 | Castro Hernandez, Jose A | 10/09/13 | Regular | 40 | 600 |  |  | 4400
T0305 | PR | 74 | 10/11/13 | 120 | Roughin Labor | CH04 | Chavarria Lopez, Omar A | 10/09/13 | Overtime | 14.5 | 261 |  |  | 4401
T0306 | PR | 74 | 10/11/13 | 120 | Roughin Labor | CH04 | Chavarria Lopez, Omar A | 10/09/13 | Regular | 40 | 480 |  |  | 4401
T0307 | PR | 76 | 10/11/13 | 120 | Roughin Labor | CO71 | Cortes Mendiola, Victor H | 10/09/13 | Overtime | 6 | 216 |  |  | 4403
T0308 | PR | 80 | 10/11/13 | 120 | Roughin Labor | GO56 | Gonzalez Hernandez, Josue | 10/09/13 | Overtime | 14 | 252 |  |  | 4407
T0309 | PR | 80 | 10/11/13 | 120 | Roughin Labor | GO56 | Gonzalez Hernandez, Josue | 10/09/13 | Regular | 40 | 480 |  |  | 4407
T0310 | PR | 84 | 10/11/13 | 120 | Roughin Labor | LI49 | Lima Romero, Melvin A | 10/09/13 | Overtime | 6 | 171 |  |  | 4411
T0311 | PR | 84 | 10/11/13 | 120 | Roughin Labor | LI49 | Lima Romero, Melvin A | 10/09/13 | Regular | 40 | 760 |  |  | 4411
T0312 | PR | 88 | 10/11/13 | 120 | Roughin Labor | MO54 | Monico Brambila, Jesus S | 10/09/13 | Overtime | 14 | 273 |  |  | 4415
T0313 | PR | 88 | 10/11/13 | 120 | Roughin Labor | MO54 | Monico Brambila, Jesus S | 10/09/13 | Regular | 40 | 520 |  |  | 4415
T0314 | PR | 91 | 10/11/13 | 120 | Roughin Labor | PA46 | Palma Vides, Hugo | 10/09/13 | Overtime | 4 | 162 |  |  | 4418
T0315 | PR | 91 | 10/11/13 | 120 | Roughin Labor | PA46 | Palma Vides, Hugo | 10/09/13 | Regular | 32 | 864 |  |  | 4418
T0316 | PR | 92 | 10/11/13 | 120 | Roughin Labor | QU35 | Quintanilla, Esteban R | 10/09/13 | Overtime | 15 | 697.5 |  |  | 4419
T0317 | PR | 92 | 10/11/13 | 120 | Roughin Labor | QU35 | Quintanilla, Esteban R | 10/09/13 | Regular | 40 | 1240 |  |  | 4419
T0318 | PR | 94 | 10/11/13 | 120 | Roughin Labor | RE18 | Reed, Reuben H | 10/09/13 | Overtime | 8 | 324 |  |  | 4421
T0319 | PR | 95 | 10/11/13 | 120 | Roughin Labor | RI84 | Rivera, Eli P | 10/09/13 | Overtime | 12.5 | 225 |  |  | 4422
T0320 | PR | 95 | 10/11/13 | 120 | Roughin Labor | RI84 | Rivera, Eli P | 10/09/13 | Regular | 40 | 480 |  |  | 4422
T0321 | PR | 96 | 10/11/13 | 120 | Roughin Labor | RI87 | Rivera, Jorge A | 10/09/13 | Overtime | 6 | 162 |  |  | 4423
T0322 | PR | 96 | 10/11/13 | 120 | Roughin Labor | RI87 | Rivera, Jorge A | 10/09/13 | Regular | 24 | 432 |  |  | 4423
T0323 | PR | 98 | 10/11/13 | 120 | Roughin Labor | SA45 | Salazar, Hajdar L | 10/09/13 | Overtime | 8 | 144 |  |  | 4425
T0324 | PR | 100 | 10/11/13 | 120 | Roughin Labor | SE64 | Sepulveda Gonzalez, Alfredo | 10/09/13 | Overtime | 6 | 216 |  |  | 4427
T0325 | PR | 103 | 10/11/13 | 120 | Roughin Labor | SP17 | Spears, Gregory M | 10/09/13 | Overtime | 8 | 156 |  |  | 4430
T0326 | PR | 104 | 10/11/13 | 120 | Roughin Labor | VE25 | Vega Arriaga, Jorge | 10/09/13 | Overtime | 6 | 108 |  |  | 4431
T0327 | PR | 104 | 10/11/13 | 120 | Roughin Labor | VE25 | Vega Arriaga, Jorge | 10/09/13 | Regular | 40 | 480 |  |  | 4431
T0328 | PR | 206 | 10/18/13 | 120 | Roughin Labor | CA74 | Castaneda Martinez, Gustavo | 10/16/13 | Regular | 36 | 972 |  |  | 4440
T0329 | PR | 208 | 10/18/13 | 120 | Roughin Labor | CA77 | Castro Hernandez, Jose A | 10/16/13 | Overtime | 12 | 270 |  |  | 4442
T0330 | PR | 208 | 10/18/13 | 120 | Roughin Labor | CA77 | Castro Hernandez, Jose A | 10/16/13 | Regular | 40 | 600 |  |  | 4442
T0331 | PR | 209 | 10/18/13 | 120 | Roughin Labor | CH04 | Chavarria Lopez, Omar A | 10/16/13 | Overtime | 12 | 216 |  |  | 4443
T0332 | PR | 209 | 10/18/13 | 120 | Roughin Labor | CH04 | Chavarria Lopez, Omar A | 10/16/13 | Regular | 40 | 480 |  |  | 4443
T0333 | PR | 211 | 10/18/13 | 120 | Roughin Labor | CO71 | Cortes Mendiola, Victor H | 10/16/13 | Overtime | 6 | 216 |  |  | 4445
T0334 | PR | 211 | 10/18/13 | 120 | Roughin Labor | CO71 | Cortes Mendiola, Victor H | 10/16/13 | Regular | 32 | 768 |  |  | 4445
T0335 | PR | 215 | 10/18/13 | 120 | Roughin Labor | GO56 | Gonzalez Hernandez, Josue | 10/16/13 | Overtime | 12 | 216 |  |  | 4449
T0336 | PR | 215 | 10/18/13 | 120 | Roughin Labor | GO56 | Gonzalez Hernandez, Josue | 10/16/13 | Regular | 40 | 480 |  |  | 4449
T0337 | PR | 219 | 10/18/13 | 120 | Roughin Labor | LI49 | Lima Romero, Melvin A | 10/16/13 | Overtime | 12 | 342 |  |  | 4453
T0338 | PR | 219 | 10/18/13 | 120 | Roughin Labor | LI49 | Lima Romero, Melvin A | 10/16/13 | Regular | 40 | 760 |  |  | 4453
T0339 | PR | 223 | 10/18/13 | 120 | Roughin Labor | MO54 | Monico Brambila, Jesus S | 10/16/13 | Overtime | 12 | 234 |  |  | 4457
T0340 | PR | 223 | 10/18/13 | 120 | Roughin Labor | MO54 | Monico Brambila, Jesus S | 10/16/13 | Regular | 40 | 520 |  |  | 4457
T0341 | PR | 226 | 10/18/13 | 120 | Roughin Labor | PA46 | Palma Vides, Hugo | 10/16/13 | Overtime | 12 | 486 |  |  | 4460
T0342 | PR | 226 | 10/18/13 | 120 | Roughin Labor | PA46 | Palma Vides, Hugo | 10/16/13 | Regular | 40 | 1080 |  |  | 4460
T0343 | PR | 227 | 10/18/13 | 120 | Roughin Labor | QU35 | Quintanilla, Esteban R | 10/16/13 | Overtime | 12 | 558 |  |  | 4461
T0344 | PR | 227 | 10/18/13 | 120 | Roughin Labor | QU35 | Quintanilla, Esteban R | 10/16/13 | Regular | 40 | 1240 |  |  | 4461
T0345 | PR | 230 | 10/18/13 | 120 | Roughin Labor | RI84 | Rivera, Eli P | 10/16/13 | Overtime | 12 | 216 |  |  | 4464
T0346 | PR | 230 | 10/18/13 | 120 | Roughin Labor | RI84 | Rivera, Eli P | 10/16/13 | Regular | 40 | 480 |  |  | 4464
T0347 | PR | 231 | 10/18/13 | 120 | Roughin Labor | RI87 | Rivera, Jorge A | 10/16/13 | Overtime | 6 | 162 |  |  | 4465
T0348 | PR | 231 | 10/18/13 | 120 | Roughin Labor | RI87 | Rivera, Jorge A | 10/16/13 | Regular | 40 | 720 |  |  | 4465
T0349 | PR | 235 | 10/18/13 | 120 | Roughin Labor | SE64 | Sepulveda Gonzalez, Alfredo | 10/16/13 | Overtime | 6 | 216 |  |  | 4469
T0350 | PR | 235 | 10/18/13 | 120 | Roughin Labor | SE64 | Sepulveda Gonzalez, Alfredo | 10/16/13 | Regular | 32 | 768 |  |  | 4469
T0351 | PR | 239 | 10/18/13 | 120 | Roughin Labor | VE25 | Vega Arriaga, Jorge | 10/16/13 | Regular | 36 | 432 |  |  | 4473
T0352 | PR | 300 | 10/25/13 | 120 | Roughin Labor | CA74 | Castaneda Martinez, Gustavo | 10/23/13 | Overtime | 4 | 162 |  |  | 4483
T0353 | PR | 300 | 10/25/13 | 120 | Roughin Labor | CA74 | Castaneda Martinez, Gustavo | 10/23/13 | Regular | 40 | 1080 |  |  | 4483
T0354 | PR | 302 | 10/25/13 | 120 | Roughin Labor | CA77 | Castro Hernandez, Jose A | 10/23/13 | Overtime | 8 | 180 |  |  | 4485
T0355 | PR | 302 | 10/25/13 | 120 | Roughin Labor | CA77 | Castro Hernandez, Jose A | 10/23/13 | Regular | 40 | 600 |  |  | 4485
T0356 | PR | 303 | 10/25/13 | 120 | Roughin Labor | CH04 | Chavarria Lopez, Omar A | 10/23/13 | Overtime | 3.5 | 63 |  |  | 4486
T0357 | PR | 303 | 10/25/13 | 120 | Roughin Labor | CH04 | Chavarria Lopez, Omar A | 10/23/13 | Regular | 40 | 480 |  |  | 4486
T0358 | PR | 305 | 10/25/13 | 120 | Roughin Labor | CO71 | Cortes Mendiola, Victor H | 10/23/13 | Overtime | 8 | 288 |  |  | 4488
T0359 | PR | 305 | 10/25/13 | 120 | Roughin Labor | CO71 | Cortes Mendiola, Victor H | 10/23/13 | Regular | 40 | 960 |  |  | 4488
T0360 | PR | 309 | 10/25/13 | 120 | Roughin Labor | GO56 | Gonzalez Hernandez, Josue | 10/23/13 | Overtime | 8 | 144 |  |  | 4492
T0361 | PR | 309 | 10/25/13 | 120 | Roughin Labor | GO56 | Gonzalez Hernandez, Josue | 10/23/13 | Regular | 40 | 480 |  |  | 4492
T0362 | PR | 314 | 10/25/13 | 120 | Roughin Labor | LI49 | Lima Romero, Melvin A | 10/23/13 | Overtime | 8 | 228 |  |  | 4497
T0363 | PR | 314 | 10/25/13 | 120 | Roughin Labor | LI49 | Lima Romero, Melvin A | 10/23/13 | Regular | 40 | 760 |  |  | 4497
T0364 | PR | 317 | 10/25/13 | 120 | Roughin Labor | MO54 | Monico Brambila, Jesus S | 10/23/13 | Overtime | 7.5 | 146.25 |  |  | 4500
T0365 | PR | 317 | 10/25/13 | 120 | Roughin Labor | MO54 | Monico Brambila, Jesus S | 10/23/13 | Regular | 40 | 520 |  |  | 4500
T0366 | PR | 320 | 10/25/13 | 120 | Roughin Labor | PA46 | Palma Vides, Hugo | 10/23/13 | Regular | 38 | 1026 |  |  | 4503
T0367 | PR | 322 | 10/25/13 | 120 | Roughin Labor | QU35 | Quintanilla, Esteban R | 10/23/13 | Overtime | 8 | 372 |  |  | 4505
T0368 | PR | 322 | 10/25/13 | 120 | Roughin Labor | QU35 | Quintanilla, Esteban R | 10/23/13 | Regular | 40 | 1240 |  |  | 4505
T0369 | PR | 325 | 10/25/13 | 120 | Roughin Labor | RI84 | Rivera, Eli P | 10/23/13 | Overtime | 3.5 | 63 |  |  | 4508
T0370 | PR | 325 | 10/25/13 | 120 | Roughin Labor | RI84 | Rivera, Eli P | 10/23/13 | Regular | 40 | 480 |  |  | 4508
T0371 | PR | 326 | 10/25/13 | 120 | Roughin Labor | RI87 | Rivera, Jorge A | 10/23/13 | Overtime | 8 | 216 |  |  | 4509
T0372 | PR | 326 | 10/25/13 | 120 | Roughin Labor | RI87 | Rivera, Jorge A | 10/23/13 | Regular | 40 | 720 |  |  | 4509
T0373 | PR | 330 | 10/25/13 | 120 | Roughin Labor | SE64 | Sepulveda Gonzalez, Alfredo | 10/23/13 | Overtime | 8 | 288 |  |  | 4513
T0374 | PR | 330 | 10/25/13 | 120 | Roughin Labor | SE64 | Sepulveda Gonzalez, Alfredo | 10/23/13 | Regular | 40 | 960 |  |  | 4513
T0375 | PR | 334 | 10/25/13 | 120 | Roughin Labor | VE25 | Vega Arriaga, Jorge | 10/23/13 | Overtime | 8 | 144 |  |  | 4517
T0376 | PR | 334 | 10/25/13 | 120 | Roughin Labor | VE25 | Vega Arriaga, Jorge | 10/23/13 | Regular | 40 | 480 |  |  | 4517
T0377 | PR | 399 | 10/31/13 | 120 | Roughin Labor | CA74 | Castaneda Martinez, Gustavo | 10/30/13 | Overtime | 4 | 162 |  |  | 4527
T0378 | PR | 399 | 10/31/13 | 120 | Roughin Labor | CA74 | Castaneda Martinez, Gustavo | 10/30/13 | Regular | 40 | 1080 |  |  | 4527
T0379 | PR | 401 | 10/31/13 | 120 | Roughin Labor | CA77 | Castro Hernandez, Jose A | 10/30/13 | Overtime | 6 | 135 |  |  | 4529
T0380 | PR | 401 | 10/31/13 | 120 | Roughin Labor | CA77 | Castro Hernandez, Jose A | 10/30/13 | Regular | 40 | 600 |  |  | 4529
T0381 | PR | 402 | 10/31/13 | 120 | Roughin Labor | CH04 | Chavarria Lopez, Omar A | 10/30/13 | Regular | 24 | 288 |  |  | 4530
T0382 | PR | 404 | 10/31/13 | 120 | Roughin Labor | CO71 | Cortes Mendiola, Victor H | 10/30/13 | Overtime | 8 | 288 |  |  | 4532
T0383 | PR | 404 | 10/31/13 | 120 | Roughin Labor | CO71 | Cortes Mendiola, Victor H | 10/30/13 | Regular | 16 | 384 |  |  | 4532
T0384 | PR | 408 | 10/31/13 | 120 | Roughin Labor | GO56 | Gonzalez Hernandez, Josue | 10/30/13 | Overtime | 12 | 216 |  |  | 4536
T0385 | PR | 408 | 10/31/13 | 120 | Roughin Labor | GO56 | Gonzalez Hernandez, Josue | 10/30/13 | Regular | 40 | 480 |  |  | 4536
T0386 | PR | 414 | 10/31/13 | 120 | Roughin Labor | LI49 | Lima Romero, Melvin A | 10/30/13 | Overtime | 6 | 171 |  |  | 4542
T0387 | PR | 414 | 10/31/13 | 120 | Roughin Labor | LI49 | Lima Romero, Melvin A | 10/30/13 | Regular | 40 | 760 |  |  | 4542
T0388 | PR | 415 | 10/31/13 | 120 | Roughin Labor | MC09 | McCabe, Thomas C | 10/30/13 | Overtime | 4.5 | 121.5 |  |  | 4543
T0389 | PR | 415 | 10/31/13 | 120 | Roughin Labor | MC09 | McCabe, Thomas C | 10/30/13 | Regular | 3 | 54 |  |  | 4543
T0390 | PR | 417 | 10/31/13 | 120 | Roughin Labor | MO54 | Monico Brambila, Jesus S | 10/30/13 | Overtime | 12 | 234 |  |  | 4545
T0391 | PR | 417 | 10/31/13 | 120 | Roughin Labor | MO54 | Monico Brambila, Jesus S | 10/30/13 | Regular | 40 | 520 |  |  | 4545
T0392 | PR | 420 | 10/31/13 | 120 | Roughin Labor | PA46 | Palma Vides, Hugo | 10/30/13 | Overtime | 12 | 486 |  |  | 4548
T0393 | PR | 420 | 10/31/13 | 120 | Roughin Labor | PA46 | Palma Vides, Hugo | 10/30/13 | Regular | 40 | 1080 |  |  | 4548
T0394 | PR | 422 | 10/31/13 | 120 | Roughin Labor | QU35 | Quintanilla, Esteban R | 10/30/13 | Regular | 52 | 1612 |  |  | 4550
T0395 | PR | 425 | 10/31/13 | 120 | Roughin Labor | RI84 | Rivera, Eli P | 10/30/13 | Overtime | 12 | 216 |  |  | 4553
T0396 | PR | 425 | 10/31/13 | 120 | Roughin Labor | RI84 | Rivera, Eli P | 10/30/13 | Regular | 40 | 480 |  |  | 4553
T0397 | PR | 426 | 10/31/13 | 120 | Roughin Labor | RI87 | Rivera, Jorge A | 10/30/13 | Regular | 36 | 648 |  |  | 4554
T0398 | PR | 430 | 10/31/13 | 120 | Roughin Labor | SE64 | Sepulveda Gonzalez, Alfredo | 10/30/13 | Overtime | 2 | 72 |  |  | 4558
T0399 | PR | 430 | 10/31/13 | 120 | Roughin Labor | SE64 | Sepulveda Gonzalez, Alfredo | 10/30/13 | Regular | 16 | 384 |  |  | 4558
T0400 | PR | 434 | 10/31/13 | 120 | Roughin Labor | VE25 | Vega Arriaga, Jorge | 10/30/13 | Regular | 13 | 156 |  |  | 4562
T0401 | PR | 101 | 11/08/13 | 120 | Roughin Labor | CA74 | Castaneda Martinez, Gustavo | 11/06/13 | Overtime | 10 | 405 |  |  | 4571
T0402 | PR | 101 | 11/08/13 | 120 | Roughin Labor | CA74 | Castaneda Martinez, Gustavo | 11/06/13 | Regular | 40 | 1080 |  |  | 4571
T0403 | PR | 103 | 11/08/13 | 120 | Roughin Labor | CA77 | Castro Hernandez, Jose A | 11/06/13 | Overtime | 14 | 315 |  |  | 4573
T0404 | PR | 103 | 11/08/13 | 120 | Roughin Labor | CA77 | Castro Hernandez, Jose A | 11/06/13 | Regular | 40 | 600 |  |  | 4573
T0405 | PR | 104 | 11/08/13 | 120 | Roughin Labor | CH04 | Chavarria Lopez, Omar A | 11/06/13 | Overtime | 14 | 252 |  |  | 4574
T0406 | PR | 104 | 11/08/13 | 120 | Roughin Labor | CH04 | Chavarria Lopez, Omar A | 11/06/13 | Regular | 40 | 480 |  |  | 4574
T0407 | PR | 110 | 11/08/13 | 120 | Roughin Labor | GO56 | Gonzalez Hernandez, Josue | 11/06/13 | Overtime | 14 | 252 |  |  | 4580
T0408 | PR | 110 | 11/08/13 | 120 | Roughin Labor | GO56 | Gonzalez Hernandez, Josue | 11/06/13 | Regular | 40 | 480 |  |  | 4580
T0409 | PR | 116 | 11/08/13 | 120 | Roughin Labor | LI49 | Lima Romero, Melvin A | 11/06/13 | Overtime | 12 | 342 |  |  | 4586
T0410 | PR | 116 | 11/08/13 | 120 | Roughin Labor | LI49 | Lima Romero, Melvin A | 11/06/13 | Regular | 32 | 608 |  |  | 4586
T0411 | PR | 119 | 11/08/13 | 120 | Roughin Labor | MO54 | Monico Brambila, Jesus S | 11/06/13 | Overtime | 14 | 273 |  |  | 4589
T0412 | PR | 119 | 11/08/13 | 120 | Roughin Labor | MO54 | Monico Brambila, Jesus S | 11/06/13 | Regular | 40 | 520 |  |  | 4589
T0413 | PR | 122 | 11/08/13 | 120 | Roughin Labor | PA46 | Palma Vides, Hugo | 11/06/13 | Overtime | 14 | 567 |  |  | 4592
T0414 | PR | 122 | 11/08/13 | 120 | Roughin Labor | PA46 | Palma Vides, Hugo | 11/06/13 | Regular | 40 | 1080 |  |  | 4592
T0415 | PR | 124 | 11/08/13 | 120 | Roughin Labor | QU35 | Quintanilla, Esteban R | 11/06/13 | Regular | 54 | 1674 |  |  | 4594
T0416 | PR | 127 | 11/08/13 | 120 | Roughin Labor | RI84 | Rivera, Eli P | 11/06/13 | Overtime | 12 | 216 |  |  | 4597
T0417 | PR | 127 | 11/08/13 | 120 | Roughin Labor | RI84 | Rivera, Eli P | 11/06/13 | Regular | 40 | 480 |  |  | 4597
T0418 | PR | 128 | 11/08/13 | 120 | Roughin Labor | RI87 | Rivera, Jorge A | 11/06/13 | Overtime | 8 | 216 |  |  | 4598
T0419 | PR | 128 | 11/08/13 | 120 | Roughin Labor | RI87 | Rivera, Jorge A | 11/06/13 | Regular | 40 | 720 |  |  | 4598
T0420 | PR | 136 | 11/08/13 | 120 | Roughin Labor | VE25 | Vega Arriaga, Jorge | 11/06/13 | Regular | 16 | 192 |  |  | 4606
T0421 | PR | 137 | 11/08/13 | 120 | Roughin Labor | VE42 | Velasquez Cruz, Denis M | 11/06/13 | Regular | 30 | 390 |  |  | 4607
T0422 | PR | 188 | 11/15/13 | 120 | Roughin Labor | CA74 | Castaneda Martinez, Gustavo | 11/13/13 | Regular | 34 | 918 |  |  | 4616
T0423 | PR | 190 | 11/15/13 | 120 | Roughin Labor | CA77 | Castro Hernandez, Jose A | 11/13/13 | Overtime | 8 | 180 |  |  | 4618
T0424 | PR | 190 | 11/15/13 | 120 | Roughin Labor | CA77 | Castro Hernandez, Jose A | 11/13/13 | Regular | 40 | 600 |  |  | 4618
T0425 | PR | 191 | 11/15/13 | 120 | Roughin Labor | CH04 | Chavarria Lopez, Omar A | 11/13/13 | Overtime | 14 | 252 |  |  | 4619
T0426 | PR | 191 | 11/15/13 | 120 | Roughin Labor | CH04 | Chavarria Lopez, Omar A | 11/13/13 | Regular | 40 | 480 |  |  | 4619
T0427 | PR | 197 | 11/15/13 | 120 | Roughin Labor | GO56 | Gonzalez Hernandez, Josue | 11/13/13 | Overtime | 14 | 252 |  |  | 4625
T0428 | PR | 197 | 11/15/13 | 120 | Roughin Labor | GO56 | Gonzalez Hernandez, Josue | 11/13/13 | Regular | 40 | 480 |  |  | 4625
T0429 | PR | 203 | 11/15/13 | 120 | Roughin Labor | LI49 | Lima Romero, Melvin A | 11/13/13 | Overtime | 8 | 228 |  |  | 4631
T0430 | PR | 203 | 11/15/13 | 120 | Roughin Labor | LI49 | Lima Romero, Melvin A | 11/13/13 | Regular | 40 | 760 |  |  | 4631
T0431 | PR | 206 | 11/15/13 | 120 | Roughin Labor | MO54 | Monico Brambila, Jesus S | 11/13/13 | Overtime | 14 | 273 |  |  | 4634
T0432 | PR | 206 | 11/15/13 | 120 | Roughin Labor | MO54 | Monico Brambila, Jesus S | 11/13/13 | Regular | 40 | 520 |  |  | 4634
T0433 | PR | 209 | 11/15/13 | 120 | Roughin Labor | PA46 | Palma Vides, Hugo | 11/13/13 | Overtime | 14 | 567 |  |  | 4637
T0434 | PR | 209 | 11/15/13 | 120 | Roughin Labor | PA46 | Palma Vides, Hugo | 11/13/13 | Regular | 40 | 1080 |  |  | 4637
T0435 | PR | 211 | 11/15/13 | 120 | Roughin Labor | QU35 | Quintanilla, Esteban R | 11/13/13 | Regular | 54 | 1674 |  |  | 4639
T0436 | PR | 214 | 11/15/13 | 120 | Roughin Labor | RI84 | Rivera, Eli P | 11/13/13 | Overtime | 14 | 252 |  |  | 4642
T0437 | PR | 214 | 11/15/13 | 120 | Roughin Labor | RI84 | Rivera, Eli P | 11/13/13 | Regular | 40 | 480 |  |  | 4642
T0438 | PR | 215 | 11/15/13 | 120 | Roughin Labor | RI87 | Rivera, Jorge A | 11/13/13 | Overtime | 8 | 216 |  |  | 4643
T0439 | PR | 215 | 11/15/13 | 120 | Roughin Labor | RI87 | Rivera, Jorge A | 11/13/13 | Regular | 40 | 720 |  |  | 4643
T0440 | PR | 224 | 11/15/13 | 120 | Roughin Labor | VE42 | Velasquez Cruz, Denis M | 11/13/13 | Overtime | 8 | 156 |  |  | 4652
T0441 | PR | 224 | 11/15/13 | 120 | Roughin Labor | VE42 | Velasquez Cruz, Denis M | 11/13/13 | Regular | 40 | 520 |  |  | 4652
T0442 | PR | 268 | 11/22/13 | 120 | Roughin Labor | CA74 | Castaneda Martinez, Gustavo | 11/20/13 | Overtime | 6 | 243 |  |  | 4662
T0443 | PR | 268 | 11/22/13 | 120 | Roughin Labor | CA74 | Castaneda Martinez, Gustavo | 11/20/13 | Regular | 26 | 702 |  |  | 4662
T0444 | PR | 270 | 11/22/13 | 120 | Roughin Labor | CA77 | Castro Hernandez, Jose A | 11/20/13 | Overtime | 12 | 270 |  |  | 4664
T0445 | PR | 270 | 11/22/13 | 120 | Roughin Labor | CA77 | Castro Hernandez, Jose A | 11/20/13 | Regular | 40 | 600 |  |  | 4664
T0446 | PR | 271 | 11/22/13 | 120 | Roughin Labor | CH04 | Chavarria Lopez, Omar A | 11/20/13 | Overtime | 14 | 252 |  |  | 4665
T0447 | PR | 271 | 11/22/13 | 120 | Roughin Labor | CH04 | Chavarria Lopez, Omar A | 11/20/13 | Regular | 40 | 480 |  |  | 4665
T0448 | PR | 277 | 11/22/13 | 120 | Roughin Labor | GO56 | Gonzalez Hernandez, Josue | 11/20/13 | Overtime | 15 | 270 |  |  | 4671
T0449 | PR | 277 | 11/22/13 | 120 | Roughin Labor | GO56 | Gonzalez Hernandez, Josue | 11/20/13 | Regular | 40 | 480 |  |  | 4671
T0450 | PR | 282 | 11/22/13 | 120 | Roughin Labor | LI49 | Lima Romero, Melvin A | 11/20/13 | Overtime | 12 | 342 |  |  | 4676
T0451 | PR | 282 | 11/22/13 | 120 | Roughin Labor | LI49 | Lima Romero, Melvin A | 11/20/13 | Regular | 40 | 760 |  |  | 4676
T0452 | PR | 283 | 11/22/13 | 120 | Roughin Labor | LO55 | Lopez Martinez, Abimael | 11/20/13 | Regular | 20 | 240 |  |  | 4677
T0453 | PR | 285 | 11/22/13 | 120 | Roughin Labor | ME98 | Meza Fuentes, Erick A | 11/20/13 | Overtime | 4 | 114 |  |  | 4679
T0454 | PR | 286 | 11/22/13 | 120 | Roughin Labor | MO54 | Monico Brambila, Jesus S | 11/20/13 | Overtime | 8 | 156 |  |  | 4680
T0455 | PR | 286 | 11/22/13 | 120 | Roughin Labor | MO54 | Monico Brambila, Jesus S | 11/20/13 | Regular | 40 | 520 |  |  | 4680
T0456 | PR | 289 | 11/22/13 | 120 | Roughin Labor | PA46 | Palma Vides, Hugo | 11/20/13 | Overtime | 14 | 567 |  |  | 4683
T0457 | PR | 289 | 11/22/13 | 120 | Roughin Labor | PA46 | Palma Vides, Hugo | 11/20/13 | Regular | 40 | 1080 |  |  | 4683
T0458 | PR | 290 | 11/22/13 | 120 | Roughin Labor | QU35 | Quintanilla, Esteban R | 11/20/13 | Overtime | 15 | 697.5 |  |  | 4684
T0459 | PR | 290 | 11/22/13 | 120 | Roughin Labor | QU35 | Quintanilla, Esteban R | 11/20/13 | Regular | 40 | 1240 |  |  | 4684
T0460 | PR | 293 | 11/22/13 | 120 | Roughin Labor | RI84 | Rivera, Eli P | 11/20/13 | Overtime | 14 | 252 |  |  | 4687
T0461 | PR | 293 | 11/22/13 | 120 | Roughin Labor | RI84 | Rivera, Eli P | 11/20/13 | Regular | 40 | 480 |  |  | 4687
T0462 | PR | 294 | 11/22/13 | 120 | Roughin Labor | RI87 | Rivera, Jorge A | 11/20/13 | Overtime | 8 | 216 |  |  | 4688
T0463 | PR | 294 | 11/22/13 | 120 | Roughin Labor | RI87 | Rivera, Jorge A | 11/20/13 | Regular | 40 | 720 |  |  | 4688
T0464 | PR | 297 | 11/22/13 | 120 | Roughin Labor | SA54 | Sanders, Allen O | 11/20/13 | Overtime | 3.5 | 147 |  |  | 4691
T0465 | PR | 304 | 11/22/13 | 120 | Roughin Labor | VE42 | Velasquez Cruz, Denis M | 11/20/13 | Overtime | 4 | 78 |  |  | 4698
T0466 | PR | 304 | 11/22/13 | 120 | Roughin Labor | VE42 | Velasquez Cruz, Denis M | 11/20/13 | Regular | 24 | 312 |  |  | 4698
T0467 | PR | 391 | 11/27/13 | 120 | Roughin Labor | CA77 | Castro Hernandez, Jose A | 11/26/13 | Regular | 30 | 450 |  |  | 4709
T0468 | PR | 392 | 11/27/13 | 120 | Roughin Labor | CH04 | Chavarria Lopez, Omar A | 11/26/13 | Overtime | 2 | 36 |  |  | 4710
T0469 | PR | 392 | 11/27/13 | 120 | Roughin Labor | CH04 | Chavarria Lopez, Omar A | 11/26/13 | Regular | 24 | 288 |  |  | 4710
T0470 | PR | 397 | 11/27/13 | 120 | Roughin Labor | GE69 | Gerard, Jeffrey S | 11/26/13 | Regular | 3 | 114 |  |  | 4715
T0471 | PR | 398 | 11/27/13 | 120 | Roughin Labor | GO56 | Gonzalez Hernandez, Josue | 11/26/13 | Overtime | 4 | 72 |  |  | 4716
T0472 | PR | 398 | 11/27/13 | 120 | Roughin Labor | GO56 | Gonzalez Hernandez, Josue | 11/26/13 | Regular | 32 | 384 |  |  | 4716
T0473 | PR | 403 | 11/27/13 | 120 | Roughin Labor | LI49 | Lima Romero, Melvin A | 11/26/13 | Overtime | 2 | 57 |  |  | 4721
T0474 | PR | 403 | 11/27/13 | 120 | Roughin Labor | LI49 | Lima Romero, Melvin A | 11/26/13 | Regular | 24 | 456 |  |  | 4721
T0475 | PR | 404 | 11/27/13 | 120 | Roughin Labor | LO55 | Lopez Martinez, Abimael | 11/26/13 | Regular | 20 | 240 |  |  | 4722
T0476 | PR | 407 | 11/27/13 | 120 | Roughin Labor | MO54 | Monico Brambila, Jesus S | 11/26/13 | Overtime | 2 | 39 |  |  | 4725
T0477 | PR | 407 | 11/27/13 | 120 | Roughin Labor | MO54 | Monico Brambila, Jesus S | 11/26/13 | Regular | 24 | 312 |  |  | 4725
T0478 | PR | 410 | 11/27/13 | 120 | Roughin Labor | PA46 | Palma Vides, Hugo | 11/26/13 | Overtime | 2 | 81 |  |  | 4728
T0479 | PR | 410 | 11/27/13 | 120 | Roughin Labor | PA46 | Palma Vides, Hugo | 11/26/13 | Regular | 24 | 648 |  |  | 4728
T0480 | PR | 411 | 11/27/13 | 120 | Roughin Labor | QU35 | Quintanilla, Esteban R | 11/26/13 | Overtime | 2 | 93 |  |  | 4729
T0481 | PR | 411 | 11/27/13 | 120 | Roughin Labor | QU35 | Quintanilla, Esteban R | 11/26/13 | Regular | 24 | 744 |  |  | 4729
T0482 | PR | 414 | 11/27/13 | 120 | Roughin Labor | RI84 | Rivera, Eli P | 11/26/13 | Overtime | 4 | 72 |  |  | 4732
T0483 | PR | 414 | 11/27/13 | 120 | Roughin Labor | RI84 | Rivera, Eli P | 11/26/13 | Regular | 32 | 384 |  |  | 4732
T0484 | PR | 415 | 11/27/13 | 120 | Roughin Labor | RI87 | Rivera, Jorge A | 11/26/13 | Regular | 20 | 360 |  |  | 4733
T0485 | PR | 438 | 11/30/13 | 120 | Roughin Labor | AG52 | Agustin Rodriguez, Ezequiel | 11/30/13 | Regular | 8 | 96 |  |  | 4750
T0486 | PR | 446 | 11/30/13 | 120 | Roughin Labor | CA77 | Castro Hernandez, Jose A | 11/30/13 | Regular | 34 | 510 |  |  | 4758
T0487 | PR | 447 | 11/30/13 | 120 | Roughin Labor | CH04 | Chavarria Lopez, Omar A | 11/30/13 | Regular | 26 | 312 |  |  | 4759
T0488 | PR | 453 | 11/30/13 | 120 | Roughin Labor | GO56 | Gonzalez Hernandez, Josue | 11/30/13 | Regular | 34 | 408 |  |  | 4765
T0489 | PR | 458 | 11/30/13 | 120 | Roughin Labor | LI49 | Lima Romero, Melvin A | 11/30/13 | Regular | 34 | 646 |  |  | 4770
T0490 | PR | 459 | 11/30/13 | 120 | Roughin Labor | LO55 | Lopez Martinez, Abimael | 11/30/13 | Regular | 34 | 408 |  |  | 4771
T0491 | PR | 462 | 11/30/13 | 120 | Roughin Labor | MO54 | Monico Brambila, Jesus S | 11/30/13 | Regular | 24 | 312 |  |  | 4774
T0492 | PR | 465 | 11/30/13 | 120 | Roughin Labor | PA46 | Palma Vides, Hugo | 11/30/13 | Regular | 34 | 918 |  |  | 4777
T0493 | PR | 466 | 11/30/13 | 120 | Roughin Labor | QU35 | Quintanilla, Esteban R | 11/30/13 | Regular | 26 | 806 |  |  | 4778
T0494 | PR | 468 | 11/30/13 | 120 | Roughin Labor | RI84 | Rivera, Eli P | 11/30/13 | Regular | 34 | 408 |  |  | 4780
T0495 | PR | 469 | 11/30/13 | 120 | Roughin Labor | RI87 | Rivera, Jorge A | 11/30/13 | Regular | 34 | 612 |  |  | 4781
T0496 | PR | 48 | 12/13/13 | 120 | Roughin Labor | AG52 | Agustin Rodriguez, Ezequiel | 12/11/13 | Overtime | 6 | 108 |  |  | 4795
T0497 | PR | 48 | 12/13/13 | 120 | Roughin Labor | AG52 | Agustin Rodriguez, Ezequiel | 12/11/13 | Regular | 40 | 480 |  |  | 4795
T0498 | PR | 55 | 12/13/13 | 120 | Roughin Labor | CA75 | Castro Hernandez, Carlos E | 12/11/13 | Overtime | 6.5 | 263.25 |  |  | 4802
T0499 | PR | 56 | 12/13/13 | 120 | Roughin Labor | CA77 | Castro Hernandez, Jose A | 12/11/13 | Overtime | 4 | 90 |  |  | 4803
T0500 | PR | 56 | 12/13/13 | 120 | Roughin Labor | CA77 | Castro Hernandez, Jose A | 12/11/13 | Regular | 34 | 510 |  |  | 4803
T0501 | PR | 57 | 12/13/13 | 120 | Roughin Labor | CH04 | Chavarria Lopez, Omar A | 12/11/13 | Overtime | 4 | 72 |  |  | 4804
T0502 | PR | 57 | 12/13/13 | 120 | Roughin Labor | CH04 | Chavarria Lopez, Omar A | 12/11/13 | Regular | 32 | 384 |  |  | 4804
T0503 | PR | 62 | 12/13/13 | 120 | Roughin Labor | GO56 | Gonzalez Hernandez, Josue | 12/11/13 | Overtime | 6 | 108 |  |  | 4809
T0504 | PR | 62 | 12/13/13 | 120 | Roughin Labor | GO56 | Gonzalez Hernandez, Josue | 12/11/13 | Regular | 39 | 468 |  |  | 4809
T0505 | PR | 67 | 12/13/13 | 120 | Roughin Labor | LI49 | Lima Romero, Melvin A | 12/11/13 | Overtime | 4 | 114 |  |  | 4814
T0506 | PR | 67 | 12/13/13 | 120 | Roughin Labor | LI49 | Lima Romero, Melvin A | 12/11/13 | Regular | 40 | 760 |  |  | 4814
T0507 | PR | 68 | 12/13/13 | 120 | Roughin Labor | LO55 | Lopez Martinez, Abimael | 12/11/13 | Overtime | 6 | 108 |  |  | 4815
T0508 | PR | 68 | 12/13/13 | 120 | Roughin Labor | LO55 | Lopez Martinez, Abimael | 12/11/13 | Regular | 40 | 480 |  |  | 4815
T0509 | PR | 71 | 12/13/13 | 120 | Roughin Labor | MO54 | Monico Brambila, Jesus S | 12/11/13 | Overtime | 5 | 97.5 |  |  | 4818
T0510 | PR | 71 | 12/13/13 | 120 | Roughin Labor | MO54 | Monico Brambila, Jesus S | 12/11/13 | Regular | 40 | 520 |  |  | 4818
T0511 | PR | 74 | 12/13/13 | 120 | Roughin Labor | PA46 | Palma Vides, Hugo | 12/11/13 | Overtime | 6 | 243 |  |  | 4821
T0512 | PR | 74 | 12/13/13 | 120 | Roughin Labor | PA46 | Palma Vides, Hugo | 12/11/13 | Regular | 40 | 1080 |  |  | 4821
T0513 | PR | 75 | 12/13/13 | 120 | Roughin Labor | QU35 | Quintanilla, Esteban R | 12/11/13 | Overtime | 3 | 139.5 |  |  | 4822
T0514 | PR | 75 | 12/13/13 | 120 | Roughin Labor | QU35 | Quintanilla, Esteban R | 12/11/13 | Regular | 32 | 992 |  |  | 4822
T0515 | PR | 77 | 12/13/13 | 120 | Roughin Labor | RI84 | Rivera, Eli P | 12/11/13 | Overtime | 4 | 72 |  |  | 4824
T0516 | PR | 77 | 12/13/13 | 120 | Roughin Labor | RI84 | Rivera, Eli P | 12/11/13 | Regular | 34 | 408 |  |  | 4824
T0517 | PR | 78 | 12/13/13 | 120 | Roughin Labor | RI87 | Rivera, Jorge A | 12/11/13 | Overtime | 4 | 108 |  |  | 4825
T0518 | PR | 78 | 12/13/13 | 120 | Roughin Labor | RI87 | Rivera, Jorge A | 12/11/13 | Regular | 32 | 576 |  |  | 4825
T0519 | PR | 231 | 12/20/13 | 120 | Roughin Labor | AG52 | Agustin Rodriguez, Ezequiel | 12/18/13 | Overtime | 4 | 72 |  |  | 4889
T0520 | PR | 231 | 12/20/13 | 120 | Roughin Labor | AG52 | Agustin Rodriguez, Ezequiel | 12/18/13 | Regular | 24 | 288 |  |  | 4889
T0521 | PR | 238 | 12/20/13 | 120 | Roughin Labor | CA75 | Castro Hernandez, Carlos E | 12/18/13 | Overtime | 12 | 486 |  |  | 4896
T0522 | PR | 238 | 12/20/13 | 120 | Roughin Labor | CA75 | Castro Hernandez, Carlos E | 12/18/13 | Regular | 32 | 864 |  |  | 4896
T0523 | PR | 239 | 12/20/13 | 120 | Roughin Labor | CA77 | Castro Hernandez, Jose A | 12/18/13 | Overtime | 14 | 315 |  |  | 4897
T0524 | PR | 239 | 12/20/13 | 120 | Roughin Labor | CA77 | Castro Hernandez, Jose A | 12/18/13 | Regular | 40 | 600 |  |  | 4897
T0525 | PR | 240 | 12/20/13 | 120 | Roughin Labor | CH04 | Chavarria Lopez, Omar A | 12/18/13 | Overtime | 14 | 252 |  |  | 4898
T0526 | PR | 240 | 12/20/13 | 120 | Roughin Labor | CH04 | Chavarria Lopez, Omar A | 12/18/13 | Regular | 40 | 480 |  |  | 4898
T0527 | PR | 246 | 12/20/13 | 120 | Roughin Labor | GO56 | Gonzalez Hernandez, Josue | 12/18/13 | Overtime | 4 | 72 |  |  | 4904
T0528 | PR | 246 | 12/20/13 | 120 | Roughin Labor | GO56 | Gonzalez Hernandez, Josue | 12/18/13 | Regular | 40 | 480 |  |  | 4904
T0529 | PR | 251 | 12/20/13 | 120 | Roughin Labor | LI49 | Lima Romero, Melvin A | 12/18/13 | Overtime | 14 | 399 |  |  | 4909
T0530 | PR | 251 | 12/20/13 | 120 | Roughin Labor | LI49 | Lima Romero, Melvin A | 12/18/13 | Regular | 40 | 760 |  |  | 4909
T0531 | PR | 252 | 12/20/13 | 120 | Roughin Labor | LO55 | Lopez Martinez, Abimael | 12/18/13 | Overtime | 4 | 72 |  |  | 4910
T0532 | PR | 252 | 12/20/13 | 120 | Roughin Labor | LO55 | Lopez Martinez, Abimael | 12/18/13 | Regular | 24 | 288 |  |  | 4910
T0533 | PR | 255 | 12/20/13 | 120 | Roughin Labor | MO54 | Monico Brambila, Jesus S | 12/18/13 | Overtime | 14 | 273 |  |  | 4913
T0534 | PR | 255 | 12/20/13 | 120 | Roughin Labor | MO54 | Monico Brambila, Jesus S | 12/18/13 | Regular | 40 | 520 |  |  | 4913
T0535 | PR | 258 | 12/20/13 | 120 | Roughin Labor | PA46 | Palma Vides, Hugo | 12/18/13 | Overtime | 14 | 567 |  |  | 4916
T0536 | PR | 258 | 12/20/13 | 120 | Roughin Labor | PA46 | Palma Vides, Hugo | 12/18/13 | Regular | 40 | 1080 |  |  | 4916
T0537 | PR | 259 | 12/20/13 | 120 | Roughin Labor | QU35 | Quintanilla, Esteban R | 12/18/13 | Overtime | 14 | 651 |  |  | 4917
T0538 | PR | 259 | 12/20/13 | 120 | Roughin Labor | QU35 | Quintanilla, Esteban R | 12/18/13 | Regular | 40 | 1240 |  |  | 4917
T0539 | PR | 261 | 12/20/13 | 120 | Roughin Labor | RI84 | Rivera, Eli P | 12/18/13 | Overtime | 5 | 90 |  |  | 4919
T0540 | PR | 261 | 12/20/13 | 120 | Roughin Labor | RI84 | Rivera, Eli P | 12/18/13 | Regular | 40 | 480 |  |  | 4919
T0541 | PR | 262 | 12/20/13 | 120 | Roughin Labor | RI87 | Rivera, Jorge A | 12/18/13 | Overtime | 6 | 162 |  |  | 4920
T0542 | PR | 262 | 12/20/13 | 120 | Roughin Labor | RI87 | Rivera, Jorge A | 12/18/13 | Regular | 32 | 576 |  |  | 4920
T0543 | PR | 265 | 12/20/13 | 120 | Roughin Labor | SA52 | Sanchez Garcia, Adelaido | 12/18/13 | Regular | 30 | 390 |  |  | 4923
T0544 | PR | 327 | 12/27/13 | 120 | Roughin Labor | AG52 | Agustin Rodriguez, Ezequiel | 12/25/13 | Regular | 8 | 96 |  |  | 4935
T0545 | PR | 334 | 12/27/13 | 120 | Roughin Labor | CA75 | Castro Hernandez, Carlos E | 12/25/13 | Regular | 22 | 594 |  |  | 4942
T0546 | PR | 335 | 12/27/13 | 120 | Roughin Labor | CA77 | Castro Hernandez, Jose A | 12/25/13 | Regular | 29 | 435 |  |  | 4943
T0547 | PR | 336 | 12/27/13 | 120 | Roughin Labor | CH04 | Chavarria Lopez, Omar A | 12/25/13 | Regular | 32 | 384 |  |  | 4944
T0548 | PR | 342 | 12/27/13 | 120 | Roughin Labor | GO56 | Gonzalez Hernandez, Josue | 12/25/13 | Regular | 29 | 348 |  |  | 4950
T0549 | PR | 347 | 12/27/13 | 120 | Roughin Labor | LI49 | Lima Romero, Melvin A | 12/25/13 | Regular | 32 | 608 |  |  | 4955
T0550 | PR | 348 | 12/27/13 | 120 | Roughin Labor | LO55 | Lopez Martinez, Abimael | 12/25/13 | Regular | 16 | 192 |  |  | 4956
T0551 | PR | 351 | 12/27/13 | 120 | Roughin Labor | MO54 | Monico Brambila, Jesus S | 12/25/13 | Regular | 26 | 338 |  |  | 4959
T0552 | PR | 354 | 12/27/13 | 120 | Roughin Labor | PA46 | Palma Vides, Hugo | 12/25/13 | Regular | 32 | 864 |  |  | 4962
T0553 | PR | 355 | 12/27/13 | 120 | Roughin Labor | QU35 | Quintanilla, Esteban R | 12/25/13 | Regular | 32 | 992 |  |  | 4963
T0554 | PR | 356 | 12/27/13 | 120 | Roughin Labor | RA54 | Ramos Garcia, Jose M | 12/25/13 | Regular | 14 | 182 |  |  | 4964
T0555 | PR | 358 | 12/27/13 | 120 | Roughin Labor | RI84 | Rivera, Eli P | 12/25/13 | Regular | 26 | 312 |  |  | 4966
T0556 | PR | 359 | 12/27/13 | 120 | Roughin Labor | RI87 | Rivera, Jorge A | 12/25/13 | Regular | 26 | 468 |  |  | 4967
T0557 | PR | 362 | 12/27/13 | 120 | Roughin Labor | SA52 | Sanchez Garcia, Adelaido | 12/25/13 | Regular | 26 | 338 |  |  | 4970
T0558 | PR | 8 | 01/03/14 | 120 | Roughin Labor | CA75 | Castro Hernandez, Carlos E | 01/01/14 | Regular | 40 | 1120 |  |  | 1099
T0559 | PR | 9 | 01/03/14 | 120 | Roughin Labor | CA77 | Castro Hernandez, Jose A | 01/01/14 | Overtime | 2 | 51 |  |  | 1100
T0560 | PR | 9 | 01/03/14 | 120 | Roughin Labor | CA77 | Castro Hernandez, Jose A | 01/01/14 | Regular | 40 | 680 |  |  | 1100
T0561 | PR | 10 | 01/03/14 | 120 | Roughin Labor | CH04 | Chavarria Lopez, Omar A | 01/01/14 | Overtime | 2 | 39 |  |  | 1101
T0562 | PR | 10 | 01/03/14 | 120 | Roughin Labor | CH04 | Chavarria Lopez, Omar A | 01/01/14 | Regular | 40 | 520 |  |  | 1101
T0563 | PR | 16 | 01/03/14 | 120 | Roughin Labor | GO56 | Gonzalez Hernandez, Josue | 01/01/14 | Overtime | 2 | 42 |  |  | 1107
T0564 | PR | 16 | 01/03/14 | 120 | Roughin Labor | GO56 | Gonzalez Hernandez, Josue | 01/01/14 | Regular | 40 | 560 |  |  | 1107
T0565 | PR | 21 | 01/03/14 | 120 | Roughin Labor | LI49 | Lima Romero, Melvin A | 01/01/14 | Regular | 36 | 720 |  |  | 1112
T0566 | PR | 22 | 01/03/14 | 120 | Roughin Labor | LO55 | Lopez Martinez, Abimael | 01/01/14 | Regular | 10 | 120 |  |  | 1113
T0567 | PR | 25 | 01/03/14 | 120 | Roughin Labor | MO54 | Monico Brambila, Jesus S | 01/01/14 | Overtime | 2 | 42 |  |  | 1116
T0568 | PR | 25 | 01/03/14 | 120 | Roughin Labor | MO54 | Monico Brambila, Jesus S | 01/01/14 | Regular | 40 | 560 |  |  | 1116
T0569 | PR | 28 | 01/03/14 | 120 | Roughin Labor | PA46 | Palma Vides, Hugo | 01/01/14 | Overtime | 2 | 84 |  |  | 1119
T0570 | PR | 28 | 01/03/14 | 120 | Roughin Labor | PA46 | Palma Vides, Hugo | 01/01/14 | Regular | 40 | 1120 |  |  | 1119
T0571 | PR | 29 | 01/03/14 | 120 | Roughin Labor | QU35 | Quintanilla, Esteban R | 01/01/14 | Overtime | 2 | 96 |  |  | 1120
T0572 | PR | 29 | 01/03/14 | 120 | Roughin Labor | QU35 | Quintanilla, Esteban R | 01/01/14 | Regular | 40 | 1280 |  |  | 1120
T0573 | PR | 30 | 01/03/14 | 120 | Roughin Labor | RA54 | Ramos Garcia, Jose M | 01/01/14 | Overtime | 2 | 39 |  |  | 1121
T0574 | PR | 30 | 01/03/14 | 120 | Roughin Labor | RA54 | Ramos Garcia, Jose M | 01/01/14 | Regular | 40 | 520 |  |  | 1121
T0575 | PR | 32 | 01/03/14 | 120 | Roughin Labor | RI84 | Rivera, Eli P | 01/01/14 | Overtime | 2 | 39 |  |  | 1123
T0576 | PR | 32 | 01/03/14 | 120 | Roughin Labor | RI84 | Rivera, Eli P | 01/01/14 | Regular | 40 | 520 |  |  | 1123
T0577 | PR | 33 | 01/03/14 | 120 | Roughin Labor | RI87 | Rivera, Jorge A | 01/01/14 | Regular | 36 | 648 |  |  | 1124
T0578 | PR | 36 | 01/03/14 | 120 | Roughin Labor | SA52 | Sanchez Garcia, Adelaido | 01/01/14 | Regular | 36 | 468 |  |  | 1127
T0579 | PR | 134 | 01/10/14 | 120 | Roughin Labor | AG52 | Agustin Rodriguez, Ezequiel | 01/08/14 | Regular | 3 | 36 |  |  | 1139
T0580 | PR | 139 | 01/10/14 | 120 | Roughin Labor | CA73 | Castaneda Juarez, Gustavo | 01/08/14 | Regular | 7 | 91 |  |  | 1144
T0581 | PR | 141 | 01/10/14 | 120 | Roughin Labor | CA75 | Castro Hernandez, Carlos E | 01/08/14 | Overtime | 6 | 252 |  |  | 1146
T0582 | PR | 141 | 01/10/14 | 120 | Roughin Labor | CA75 | Castro Hernandez, Carlos E | 01/08/14 | Regular | 16 | 448 |  |  | 1146
T0583 | PR | 142 | 01/10/14 | 120 | Roughin Labor | CA77 | Castro Hernandez, Jose A | 01/08/14 | Overtime | 8 | 204 |  |  | 1147
T0584 | PR | 142 | 01/10/14 | 120 | Roughin Labor | CA77 | Castro Hernandez, Jose A | 01/08/14 | Regular | 40 | 680 |  |  | 1147
T0585 | PR | 143 | 01/10/14 | 120 | Roughin Labor | CH04 | Chavarria Lopez, Omar A | 01/08/14 | Overtime | 6 | 117 |  |  | 1148
T0586 | PR | 143 | 01/10/14 | 120 | Roughin Labor | CH04 | Chavarria Lopez, Omar A | 01/08/14 | Regular | 40 | 520 |  |  | 1148
T0587 | PR | 149 | 01/10/14 | 120 | Roughin Labor | GO56 | Gonzalez Hernandez, Josue | 01/08/14 | Regular | 40 | 560 |  |  | 1154
T0588 | PR | 154 | 01/10/14 | 120 | Roughin Labor | LI49 | Lima Romero, Melvin A | 01/08/14 | Regular | 40 | 800 |  |  | 1159
T0589 | PR | 155 | 01/10/14 | 120 | Roughin Labor | LO55 | Lopez Martinez, Abimael | 01/08/14 | Regular | 11 | 132 |  |  | 1160
T0590 | PR | 161 | 01/10/14 | 120 | Roughin Labor | PA46 | Palma Vides, Hugo | 01/08/14 | Overtime | 6 | 252 |  |  | 1166
T0591 | PR | 161 | 01/10/14 | 120 | Roughin Labor | PA46 | Palma Vides, Hugo | 01/08/14 | Regular | 40 | 1120 |  |  | 1166
T0592 | PR | 162 | 01/10/14 | 120 | Roughin Labor | QU35 | Quintanilla, Esteban R | 01/08/14 | Overtime | 6 | 288 |  |  | 1167
T0593 | PR | 162 | 01/10/14 | 120 | Roughin Labor | QU35 | Quintanilla, Esteban R | 01/08/14 | Regular | 40 | 1280 |  |  | 1167
T0594 | PR | 163 | 01/10/14 | 120 | Roughin Labor | RA54 | Ramos Garcia, Jose M | 01/08/14 | Regular | 40 | 520 |  |  | 1168
T0595 | PR | 165 | 01/10/14 | 120 | Roughin Labor | RI84 | Rivera, Eli P | 01/08/14 | Overtime | 6 | 117 |  |  | 1170
T0596 | PR | 165 | 01/10/14 | 120 | Roughin Labor | RI84 | Rivera, Eli P | 01/08/14 | Regular | 40 | 520 |  |  | 1170
T0597 | PR | 166 | 01/10/14 | 120 | Roughin Labor | RI87 | Rivera, Jorge A | 01/08/14 | Regular | 11 | 198 |  |  | 1171
T0598 | PR | 169 | 01/10/14 | 120 | Roughin Labor | SA52 | Sanchez Garcia, Adelaido | 01/08/14 | Regular | 39 | 507 |  |  | 1174
T0599 | PR | 175 | 01/10/14 | 120 | Roughin Labor | VE25 | Vega Arriaga, Jorge | 01/08/14 | Regular | 11 | 143 |  |  | 1180
T0600 | PR | 287 | 01/17/14 | 120 | Roughin Labor | CA77 | Castro Hernandez, Jose A | 01/15/14 | Regular | 40 | 680 |  |  | 5011
T0601 | PR | 294 | 01/17/14 | 120 | Roughin Labor | GO56 | Gonzalez Hernandez, Josue | 01/15/14 | Regular | 40 | 560 |  |  | 5018
T0602 | PR | 299 | 01/17/14 | 120 | Roughin Labor | LI49 | Lima Romero, Melvin A | 01/15/14 | Regular | 40 | 800 |  |  | 5023
T0603 | PR | 306 | 01/17/14 | 120 | Roughin Labor | PA46 | Palma Vides, Hugo | 01/15/14 | Regular | 24 | 672 |  |  | 5030
T0604 | PR | 307 | 01/17/14 | 120 | Roughin Labor | QU35 | Quintanilla, Esteban R | 01/15/14 | Regular | 40 | 1280 |  |  | 5031
T0605 | PR | 308 | 01/17/14 | 120 | Roughin Labor | RA54 | Ramos Garcia, Jose M | 01/15/14 | Regular | 37 | 481 |  |  | 5032
T0606 | PR | 310 | 01/17/14 | 120 | Roughin Labor | RI84 | Rivera, Eli P | 01/15/14 | Regular | 40 | 520 |  |  | 5034
T0607 | PR | 314 | 01/17/14 | 120 | Roughin Labor | SA52 | Sanchez Garcia, Adelaido | 01/15/14 | Regular | 24 | 312 |  |  | 5038
T0608 | PR | 377 | 01/24/14 | 120 | Roughin Labor | CA77 | Castro Hernandez, Jose A | 01/22/14 | Regular | 40 | 680 |  |  | 5059
T0609 | PR | 378 | 01/24/14 | 120 | Roughin Labor | CH04 | Chavarria Lopez, Omar A | 01/22/14 | Regular | 40 | 520 |  |  | 5060
T0610 | PR | 384 | 01/24/14 | 120 | Roughin Labor | GO56 | Gonzalez Hernandez, Josue | 01/22/14 | Regular | 40 | 560 |  |  | 5066
T0611 | PR | 389 | 01/24/14 | 120 | Roughin Labor | LI49 | Lima Romero, Melvin A | 01/22/14 | Regular | 40 | 800 |  |  | 5071
T0612 | PR | 397 | 01/24/14 | 120 | Roughin Labor | QU35 | Quintanilla, Esteban R | 01/22/14 | Regular | 40 | 1280 |  |  | 5079
T0613 | PR | 399 | 01/24/14 | 120 | Roughin Labor | RA54 | Ramos Garcia, Jose M | 01/22/14 | Regular | 40 | 520 |  |  | 5081
T0614 | PR | 401 | 01/24/14 | 120 | Roughin Labor | RI84 | Rivera, Eli P | 01/22/14 | Regular | 40 | 520 |  |  | 5083
T0615 | PR | 415 | 01/24/14 | 120 | Roughin Labor | WA35 | Waites, Thaddeus Z | 01/22/14 | Regular | 40 | 1120 |  |  | 5097
T0616 | PR | 575 | 01/31/14 | 120 | Roughin Labor | CA77 | Castro Hernandez, Jose A | 01/29/14 | Regular | 32 | 544 |  |  | 5108
T0617 | PR | 595 | 01/31/14 | 120 | Roughin Labor | QU35 | Quintanilla, Esteban R | 01/29/14 | Regular | 8 | 256 |  |  | 5128
T0618 | PR | 599 | 01/31/14 | 120 | Roughin Labor | RI84 | Rivera, Eli P | 01/29/14 | Regular | 40 | 520 |  |  | 5132
T0619 | PR | 45 | 02/07/14 | 120 | Roughin Labor | QU35 | Quintanilla, Esteban R | 02/05/14 | Regular | 8 | 256 |  |  | 5177
T0620 | PR | 47 | 02/07/14 | 120 | Roughin Labor | RA54 | Ramos Garcia, Jose M | 02/05/14 | Regular | 32 | 416 |  |  | 5179
T0621 | PR | 49 | 02/07/14 | 120 | Roughin Labor | RI84 | Rivera, Eli P | 02/05/14 | Regular | 24 | 312 |  |  | 5181
T0622 | PR | 63 | 02/07/14 | 120 | Roughin Labor | WA35 | Waites, Thaddeus Z | 02/05/14 | Regular | 8 | 224 |  |  | 5195
T0623 | PR | 179 | 02/14/14 | 120 | Roughin Labor | GO56 | Gonzalez Hernandez, Josue | 02/12/14 | Regular | 16 | 224 |  |  | 5215
T0624 | PR | 184 | 02/14/14 | 120 | Roughin Labor | LI49 | Lima Romero, Melvin A | 02/12/14 | Regular | 24 | 480 |  |  | 5220
T0625 | PR | 195 | 02/14/14 | 120 | Roughin Labor | RA54 | Ramos Garcia, Jose M | 02/12/14 | Regular | 16 | 208 |  |  | 5231
T0626 | PR | 288 | 02/21/14 | 120 | Roughin Labor | GO56 | Gonzalez Hernandez, Josue | 02/19/14 | Regular | 16 | 224 |  |  | 5265
T0627 | PR | 293 | 02/21/14 | 120 | Roughin Labor | LI49 | Lima Romero, Melvin A | 02/19/14 | Regular | 8 | 160 |  |  | 5270
T0628 | PR | 304 | 02/21/14 | 120 | Roughin Labor | RA54 | Ramos Garcia, Jose M | 02/19/14 | Regular | 16 | 208 |  |  | 5281
T0629 | PR | 320 | 02/21/14 | 120 | Roughin Labor | WA35 | Waites, Thaddeus Z | 02/19/14 | Regular | 16 | 448 |  |  | 5297
T0630 | PR | 17 | 03/07/14 | 120 | Roughin Labor | GO56 | Gonzalez Hernandez, Josue | 03/05/14 | Regular | 16 | 224 |  |  | 5365
T0631 | PR | 49 | 03/07/14 | 120 | Roughin Labor | WA35 | Waites, Thaddeus Z | 03/05/14 | Regular | 16 | 448 |  |  | 5397
T0632 | PR | 331 | 03/21/14 | 120 | Roughin Labor | CA75 | Castro Hernandez, Carlos E | 03/19/14 | Regular | 16 | 448 |  |  | 5460
T0633 | PR | 338 | 03/21/14 | 120 | Roughin Labor | GO56 | Gonzalez Hernandez, Josue | 03/19/14 | Regular | 24 | 336 |  |  | 5467
T0634 | PR | 492 | 03/28/14 | 120 | Roughin Labor | QU35 | Quintanilla, Esteban R | 03/26/14 | Regular | 8 | 256 |  |  | 5530
T0635 | PR | 302 | 01/17/14 | 130 | Finish Labor | ME98 | Meza Fuentes, Erick A | 01/15/14 | Regular | 16 | 320 |  |  | 5026
T0636 | PR | 315 | 01/17/14 | 130 | Finish Labor | SA54 | Sanders, Allen O | 01/15/14 | Regular | 13.5 | 391.5 |  |  | 5039
T0637 | PR | 318 | 01/17/14 | 130 | Finish Labor | SO79 | Soto Serna, Cesar E | 01/15/14 | Regular | 24 | 312 |  |  | 5042
T0638 | PR | 320 | 01/17/14 | 130 | Finish Labor | VA86 | Vaughan, Tyler J | 01/15/14 | Regular | 18 | 288 |  |  | 5044
T0639 | PR | 392 | 01/24/14 | 130 | Finish Labor | ME98 | Meza Fuentes, Erick A | 01/22/14 | Regular | 40 | 800 |  |  | 5074
T0640 | PR | 406 | 01/24/14 | 130 | Finish Labor | SA54 | Sanders, Allen O | 01/22/14 | Regular | 12 | 348 |  |  | 5088
T0641 | PR | 408 | 01/24/14 | 130 | Finish Labor | SO78 | Soto Cruz, Jovani | 01/22/14 | Regular | 8 | 128 |  |  | 5090
T0642 | PR | 409 | 01/24/14 | 130 | Finish Labor | SO79 | Soto Serna, Cesar E | 01/22/14 | Regular | 7.5 | 97.5 |  |  | 5091
T0643 | PR | 411 | 01/24/14 | 130 | Finish Labor | VA86 | Vaughan, Tyler J | 01/22/14 | Regular | 8 | 128 |  |  | 5093
T0644 | PR | 590 | 01/31/14 | 130 | Finish Labor | ME98 | Meza Fuentes, Erick A | 01/29/14 | Regular | 40 | 800 |  |  | 5123
T0645 | PR | 604 | 01/31/14 | 130 | Finish Labor | SA54 | Sanders, Allen O | 01/29/14 | Regular | 10 | 290 |  |  | 5137
T0646 | PR | 606 | 01/31/14 | 130 | Finish Labor | SO78 | Soto Cruz, Jovani | 01/29/14 | Regular | 11 | 176 |  |  | 5139
T0647 | PR | 607 | 01/31/14 | 130 | Finish Labor | SO79 | Soto Serna, Cesar E | 01/29/14 | Regular | 40 | 520 |  |  | 5140
T0648 | PR | 609 | 01/31/14 | 130 | Finish Labor | VA86 | Vaughan, Tyler J | 01/29/14 | Regular | 16 | 256 |  |  | 5142
T0649 | PR | 40 | 02/07/14 | 130 | Finish Labor | ME98 | Meza Fuentes, Erick A | 02/05/14 | Regular | 27.5 | 550 |  |  | 5172
T0650 | PR | 54 | 02/07/14 | 130 | Finish Labor | SA54 | Sanders, Allen O | 02/05/14 | Regular | 2 | 58 |  |  | 5186
T0651 | PR | 56 | 02/07/14 | 130 | Finish Labor | SO78 | Soto Cruz, Jovani | 02/05/14 | Regular | 7.5 | 120 |  |  | 5188
T0652 | PR | 57 | 02/07/14 | 130 | Finish Labor | SO79 | Soto Serna, Cesar E | 02/05/14 | Regular | 16 | 208 |  |  | 5189
T0653 | PR | 168 | 02/14/14 | 130 | Finish Labor | CA72 | Castaneda Juarez, Edgar D | 02/12/14 | Regular | 40 | 540 |  |  | 5204
T0654 | PR | 187 | 02/14/14 | 130 | Finish Labor | ME98 | Meza Fuentes, Erick A | 02/12/14 | Regular | 32 | 640 |  |  | 5223
T0655 | PR | 202 | 02/14/14 | 130 | Finish Labor | SA54 | Sanders, Allen O | 02/12/14 | Regular | 8 | 232 |  |  | 5238
T0656 | PR | 204 | 02/14/14 | 130 | Finish Labor | SO78 | Soto Cruz, Jovani | 02/12/14 | Regular | 13.5 | 216 |  |  | 5240
T0657 | PR | 278 | 02/21/14 | 130 | Finish Labor | CA72 | Castaneda Juarez, Edgar D | 02/19/14 | Regular | 39.5 | 533.25 |  |  | 5255
T0658 | PR | 286 | 02/21/14 | 130 | Finish Labor | GA70 | Garcia, Jordan X | 02/19/14 | Regular | 16 | 224 |  |  | 5263
T0659 | PR | 296 | 02/21/14 | 130 | Finish Labor | ME98 | Meza Fuentes, Erick A | 02/19/14 | Regular | 40 | 800 |  |  | 5273
T0660 | PR | 311 | 02/21/14 | 130 | Finish Labor | SA54 | Sanders, Allen O | 02/19/14 | Regular | 12.5 | 362.5 |  |  | 5288
T0661 | PR | 321 | 02/21/14 | 130 | Finish Labor | WI46 | Wilson, Garret A | 02/19/14 | Regular | 16 | 208 |  |  | 5298
T0662 | PR | 368 | 02/28/14 | 130 | Finish Labor | BA70 | Barnhart, Joseph N | 02/26/14 | Regular | 1 | 31 |  |  | 5303
T0663 | PR | 370 | 02/28/14 | 130 | Finish Labor | CA72 | Castaneda Juarez, Edgar D | 02/26/14 | Regular | 37.75 | 509.63 |  |  | 5305
T0664 | PR | 378 | 02/28/14 | 130 | Finish Labor | GA70 | Garcia, Jordan X | 02/26/14 | Regular | 16 | 224 |  |  | 5313
T0665 | PR | 388 | 02/28/14 | 130 | Finish Labor | ME98 | Meza Fuentes, Erick A | 02/26/14 | Regular | 40 | 800 |  |  | 5323
T0666 | PR | 403 | 02/28/14 | 130 | Finish Labor | SA54 | Sanders, Allen O | 02/26/14 | Regular | 14.5 | 420.5 |  |  | 5338
T0667 | PR | 405 | 02/28/14 | 130 | Finish Labor | SO78 | Soto Cruz, Jovani | 02/26/14 | Regular | 15.5 | 248 |  |  | 5340
T0668 | PR | 413 | 02/28/14 | 130 | Finish Labor | WI46 | Wilson, Garret A | 02/26/14 | Regular | 16 | 208 |  |  | 5348
T0669 | PR | 7 | 03/07/14 | 130 | Finish Labor | CA72 | Castaneda Juarez, Edgar D | 03/05/14 | Regular | 40 | 580 |  |  | 5355
T0670 | PR | 25 | 03/07/14 | 130 | Finish Labor | ME98 | Meza Fuentes, Erick A | 03/05/14 | Regular | 37.5 | 750 |  |  | 5373
T0671 | PR | 40 | 03/07/14 | 130 | Finish Labor | SA54 | Sanders, Allen O | 03/05/14 | Regular | 21.5 | 623.5 |  |  | 5388
T0672 | PR | 42 | 03/07/14 | 130 | Finish Labor | SO78 | Soto Cruz, Jovani | 03/05/14 | Regular | 38.5 | 616 |  |  | 5390
T0673 | PR | 43 | 03/07/14 | 130 | Finish Labor | SO79 | Soto Serna, Cesar E | 03/05/14 | Regular | 35.75 | 464.75 |  |  | 5391
T0674 | PR | 45 | 03/07/14 | 130 | Finish Labor | VA86 | Vaughan, Tyler J | 03/05/14 | Regular | 11 | 176 |  |  | 5393
T0675 | PR | 187 | 03/14/14 | 130 | Finish Labor | CA72 | Castaneda Juarez, Edgar D | 03/12/14 | Regular | 40 | 580 |  |  | 5406
T0676 | PR | 205 | 03/14/14 | 130 | Finish Labor | ME98 | Meza Fuentes, Erick A | 03/12/14 | Regular | 32 | 640 |  |  | 5424
T0677 | PR | 220 | 03/14/14 | 130 | Finish Labor | SA54 | Sanders, Allen O | 03/12/14 | Regular | 22 | 638 |  |  | 5439
T0678 | PR | 222 | 03/14/14 | 130 | Finish Labor | SO78 | Soto Cruz, Jovani | 03/12/14 | Regular | 32.5 | 520 |  |  | 5441
T0679 | PR | 223 | 03/14/14 | 130 | Finish Labor | SO79 | Soto Serna, Cesar E | 03/12/14 | Regular | 23.5 | 305.5 |  |  | 5442
T0680 | PR | 225 | 03/14/14 | 130 | Finish Labor | VA86 | Vaughan, Tyler J | 03/12/14 | Regular | 30 | 480 |  |  | 5444
T0681 | PR | 346 | 03/21/14 | 130 | Finish Labor | ME98 | Meza Fuentes, Erick A | 03/19/14 | Regular | 40 | 800 |  |  | 5475
T0682 | PR | 361 | 03/21/14 | 130 | Finish Labor | SA54 | Sanders, Allen O | 03/19/14 | Regular | 22 | 638 |  |  | 5490
T0683 | PR | 364 | 03/21/14 | 130 | Finish Labor | SO79 | Soto Serna, Cesar E | 03/19/14 | Regular | 23.5 | 305.5 |  |  | 5493
T0684 | PR | 366 | 03/21/14 | 130 | Finish Labor | VA86 | Vaughan, Tyler J | 03/19/14 | Regular | 8 | 128 |  |  | 5495
T0685 | PR | 487 | 03/28/14 | 130 | Finish Labor | ME98 | Meza Fuentes, Erick A | 03/26/14 | Regular | 35 | 700 |  |  | 5525
T0686 | PR | 502 | 03/28/14 | 130 | Finish Labor | SA54 | Sanders, Allen O | 03/26/14 | Regular | 38 | 1102 |  |  | 5540
T0687 | PR | 504 | 03/28/14 | 130 | Finish Labor | SO78 | Soto Cruz, Jovani | 03/26/14 | Regular | 40 | 640 |  |  | 5542
T0688 | PR | 505 | 03/28/14 | 130 | Finish Labor | SO79 | Soto Serna, Cesar E | 03/26/14 | Regular | 38.75 | 503.75 |  |  | 5543
T0689 | PR | 507 | 03/28/14 | 130 | Finish Labor | VA86 | Vaughan, Tyler J | 03/26/14 | Regular | 24 | 384 |  |  | 5545
T0690 | PR | 27 | 04/04/14 | 130 | Finish Labor | ME98 | Meza Fuentes, Erick A | 04/02/14 | Regular | 24 | 480 |  |  | 5576
T0691 | PR | 43 | 04/04/14 | 130 | Finish Labor | SA54 | Sanders, Allen O | 04/02/14 | Regular | 36 | 1044 |  |  | 5592
T0692 | PR | 45 | 04/04/14 | 130 | Finish Labor | SO78 | Soto Cruz, Jovani | 04/02/14 | Regular | 40 | 640 |  |  | 5594
T0693 | PR | 46 | 04/04/14 | 130 | Finish Labor | SO79 | Soto Serna, Cesar E | 04/02/14 | Regular | 40 | 520 |  |  | 5595
T0694 | PR | 48 | 04/04/14 | 130 | Finish Labor | VA86 | Vaughan, Tyler J | 04/02/14 | Regular | 30.5 | 488 |  |  | 5597
T0695 | PR | 151 | 04/11/14 | 130 | Finish Labor | ME98 | Meza Fuentes, Erick A | 04/09/14 | Regular | 40 | 800 |  |  | 5630
T0696 | PR | 167 | 04/11/14 | 130 | Finish Labor | SA54 | Sanders, Allen O | 04/09/14 | Regular | 40 | 1160 |  |  | 5646
T0697 | PR | 169 | 04/11/14 | 130 | Finish Labor | SO78 | Soto Cruz, Jovani | 04/09/14 | Regular | 40 | 640 |  |  | 5648
T0698 | PR | 172 | 04/11/14 | 130 | Finish Labor | VA86 | Vaughan, Tyler J | 04/09/14 | Regular | 23 | 368 |  |  | 5651
T0699 | PR | 269 | 04/18/14 | 130 | Finish Labor | ME98 | Meza Fuentes, Erick A | 04/16/14 | Regular | 32 | 640 |  |  | 5683
T0700 | PR | 285 | 04/18/14 | 130 | Finish Labor | SA54 | Sanders, Allen O | 04/16/14 | Regular | 36 | 1044 |  |  | 5699
T0701 | PR | 287 | 04/18/14 | 130 | Finish Labor | SO78 | Soto Cruz, Jovani | 04/16/14 | Regular | 28 | 448 |  |  | 5701
T0702 | PR | 408 | 04/25/14 | 130 | Finish Labor | ME98 | Meza Fuentes, Erick A | 04/23/14 | Regular | 40 | 800 |  |  | 5737
T0703 | PR | 424 | 04/25/14 | 130 | Finish Labor | SA54 | Sanders, Allen O | 04/23/14 | Regular | 25.5 | 739.5 |  |  | 5753
T0704 | PR | 426 | 04/25/14 | 130 | Finish Labor | SO78 | Soto Cruz, Jovani | 04/23/14 | Regular | 5.5 | 88 |  |  | 5755
T0705 | PR | 10 | 05/02/14 | 130 | Finish Labor | BA70 | Barnhart, Joseph N | 04/30/14 | Regular | 2 | 62 |  |  | 5769
T0706 | PR | 31 | 05/02/14 | 130 | Finish Labor | ME98 | Meza Fuentes, Erick A | 04/30/14 | Regular | 16 | 320 |  |  | 5790
T0707 | PR | 47 | 05/02/14 | 130 | Finish Labor | SA54 | Sanders, Allen O | 04/30/14 | Regular | 2.5 | 72.5 |  |  | 5806
T0708 | PR | 178 | 05/09/14 | 130 | Finish Labor | ME98 | Meza Fuentes, Erick A | 05/07/14 | Regular | 16 | 320 |  |  | 5842
T0709 | PR | 194 | 05/09/14 | 130 | Finish Labor | SA54 | Sanders, Allen O | 05/07/14 | Regular | 1 | 29 |  |  | 5858
T0710 | PR | 284 | 05/16/14 | 130 | Finish Labor | SA54 | Sanders, Allen O | 05/14/14 | Regular | 2 | 58 |  |  | 5911
T0711 | PR | 463 | 05/23/14 | 130 | Finish Labor | SA54 | Sanders, Allen O | 05/21/14 | Regular | 2 | 58 |  |  | 5962
T0712 | PR | 537 | 05/30/14 | 130 | Finish Labor | SA54 | Sanders, Allen O | 05/28/14 | Regular | 2.5 | 72.5 |  |  | 6012
T0713 | PR | 27 | 06/06/14 | 130 | Finish Labor | ME98 | Meza Fuentes, Erick A | 06/04/14 | Regular | 3.5 | 70 |  |  | 6048
T0714 | PR | 42 | 06/06/14 | 130 | Finish Labor | SA54 | Sanders, Allen O | 06/04/14 | Regular | 2 | 58 |  |  | 6063
T0715 | PR | 232 | 06/20/14 | 130 | Finish Labor | GE69 | Gerard, Jeffrey S | 06/18/14 | Regular | 2 | 76 |  |  | 6141
T0716 | PR | 25 | 02/07/14 | 140 | Gas Labor | CA77 | Castro Hernandez, Jose A | 02/05/14 | Regular | 40 | 680 |  |  | 5157
T0717 | PR | 385 | 02/28/14 | 140 | Gas Labor | LI49 | Lima Romero, Melvin A | 02/26/14 | Regular | 16 | 320 |  |  | 5320
T0718 | PR | 22 | 03/07/14 | 140 | Gas Labor | LI49 | Lima Romero, Melvin A | 03/05/14 | Regular | 8 | 160 |  |  | 5370
T0719 | PR | 197 | 03/14/14 | 140 | Gas Labor | GO56 | Gonzalez Hernandez, Josue | 03/12/14 | Regular | 8 | 112 |  |  | 5416
T0720 | PR | 229 | 03/14/14 | 140 | Gas Labor | WA35 | Waites, Thaddeus Z | 03/12/14 | Regular | 24 | 672 |  |  | 5448
T0721 | PR | 369 | 03/21/14 | 140 | Gas Labor | WA35 | Waites, Thaddeus Z | 03/19/14 | Regular | 8 | 224 |  |  | 5498
T0722 | PR | 22 | 01/03/14 | 141 | Water Main/Insulation Lab | LO55 | Lopez Martinez, Abimael | 01/01/14 | Regular | 8 | 96 |  |  | 1113
T0723 | PR | 576 | 01/31/14 | 141 | Water Main/Insulation Lab | CH04 | Chavarria Lopez, Omar A | 01/29/14 | Regular | 40 | 520 |  |  | 5109
T0724 | PR | 582 | 01/31/14 | 141 | Water Main/Insulation Lab | GO56 | Gonzalez Hernandez, Josue | 01/29/14 | Regular | 32 | 448 |  |  | 5115
T0725 | PR | 587 | 01/31/14 | 141 | Water Main/Insulation Lab | LI49 | Lima Romero, Melvin A | 01/29/14 | Regular | 40 | 800 |  |  | 5120
T0726 | PR | 595 | 01/31/14 | 141 | Water Main/Insulation Lab | QU35 | Quintanilla, Esteban R | 01/29/14 | Regular | 16 | 512 |  |  | 5128
T0727 | PR | 597 | 01/31/14 | 141 | Water Main/Insulation Lab | RA54 | Ramos Garcia, Jose M | 01/29/14 | Regular | 40 | 520 |  |  | 5130
T0728 | PR | 613 | 01/31/14 | 141 | Water Main/Insulation Lab | WA35 | Waites, Thaddeus Z | 01/29/14 | Regular | 24 | 672 |  |  | 5146
T0729 | PR | 26 | 02/07/14 | 141 | Water Main/Insulation Lab | CH04 | Chavarria Lopez, Omar A | 02/05/14 | Regular | 32 | 416 |  |  | 5158
T0730 | PR | 32 | 02/07/14 | 141 | Water Main/Insulation Lab | GO56 | Gonzalez Hernandez, Josue | 02/05/14 | Regular | 40 | 560 |  |  | 5164
T0731 | PR | 37 | 02/07/14 | 141 | Water Main/Insulation Lab | LI49 | Lima Romero, Melvin A | 02/05/14 | Regular | 40 | 800 |  |  | 5169
T0732 | PR | 45 | 02/07/14 | 141 | Water Main/Insulation Lab | QU35 | Quintanilla, Esteban R | 02/05/14 | Regular | 32 | 1024 |  |  | 5177
T0733 | PR | 47 | 02/07/14 | 141 | Water Main/Insulation Lab | RA54 | Ramos Garcia, Jose M | 02/05/14 | Regular | 8 | 104 |  |  | 5179
T0734 | PR | 49 | 02/07/14 | 141 | Water Main/Insulation Lab | RI84 | Rivera, Eli P | 02/05/14 | Regular | 16 | 208 |  |  | 5181
T0735 | PR | 63 | 02/07/14 | 141 | Water Main/Insulation Lab | WA35 | Waites, Thaddeus Z | 02/05/14 | Regular | 32 | 896 |  |  | 5195
T0736 | PR | 173 | 02/14/14 | 141 | Water Main/Insulation Lab | CH04 | Chavarria Lopez, Omar A | 02/12/14 | Regular | 16 | 208 |  |  | 5209
T0737 | PR | 179 | 02/14/14 | 141 | Water Main/Insulation Lab | GO56 | Gonzalez Hernandez, Josue | 02/12/14 | Regular | 24 | 336 |  |  | 5215
T0738 | PR | 184 | 02/14/14 | 141 | Water Main/Insulation Lab | LI49 | Lima Romero, Melvin A | 02/12/14 | Regular | 16 | 320 |  |  | 5220
T0739 | PR | 192 | 02/14/14 | 141 | Water Main/Insulation Lab | QU35 | Quintanilla, Esteban R | 02/12/14 | Regular | 40 | 1280 |  |  | 5228
T0740 | PR | 195 | 02/14/14 | 141 | Water Main/Insulation Lab | RA54 | Ramos Garcia, Jose M | 02/12/14 | Regular | 24 | 312 |  |  | 5231
T0741 | PR | 211 | 02/14/14 | 141 | Water Main/Insulation Lab | WA35 | Waites, Thaddeus Z | 02/12/14 | Regular | 15 | 420 |  |  | 5247
T0742 | PR | 288 | 02/21/14 | 141 | Water Main/Insulation Lab | GO56 | Gonzalez Hernandez, Josue | 02/19/14 | Regular | 24 | 336 |  |  | 5265
T0743 | PR | 293 | 02/21/14 | 141 | Water Main/Insulation Lab | LI49 | Lima Romero, Melvin A | 02/19/14 | Regular | 32 | 640 |  |  | 5270
T0744 | PR | 301 | 02/21/14 | 141 | Water Main/Insulation Lab | QU35 | Quintanilla, Esteban R | 02/19/14 | Regular | 33 | 1056 |  |  | 5278
T0745 | PR | 304 | 02/21/14 | 141 | Water Main/Insulation Lab | RA54 | Ramos Garcia, Jose M | 02/19/14 | Regular | 24 | 312 |  |  | 5281
T0746 | PR | 320 | 02/21/14 | 141 | Water Main/Insulation Lab | WA35 | Waites, Thaddeus Z | 02/19/14 | Regular | 24 | 672 |  |  | 5297
T0747 | PR | 380 | 02/28/14 | 141 | Water Main/Insulation Lab | GO56 | Gonzalez Hernandez, Josue | 02/26/14 | Regular | 40 | 560 |  |  | 5315
T0748 | PR | 385 | 02/28/14 | 141 | Water Main/Insulation Lab | LI49 | Lima Romero, Melvin A | 02/26/14 | Regular | 8 | 160 |  |  | 5320
T0749 | PR | 396 | 02/28/14 | 141 | Water Main/Insulation Lab | RA54 | Ramos Garcia, Jose M | 02/26/14 | Regular | 32 | 416 |  |  | 5331
T0750 | PR | 412 | 02/28/14 | 141 | Water Main/Insulation Lab | WA35 | Waites, Thaddeus Z | 02/26/14 | Regular | 24 | 672 |  |  | 5347
T0751 | PR | 31 | 05/02/14 | 141 | Water Main/Insulation Lab | ME98 | Meza Fuentes, Erick A | 04/30/14 | Regular | 24 | 480 |  |  | 5790
T0752 | PR | 575 | 01/31/14 | 142 | Mech Room Labor | CA77 | Castro Hernandez, Jose A | 01/29/14 | Regular | 8 | 136 |  |  | 5108
T0753 | PR | 595 | 01/31/14 | 142 | Mech Room Labor | QU35 | Quintanilla, Esteban R | 01/29/14 | Regular | 16 | 512 |  |  | 5128
T0754 | PR | 39 | 02/07/14 | 142 | Mech Room Labor | MC09 | McCabe, Thomas C | 02/05/14 | Regular | 3 | 54 |  |  | 5171
T0755 | PR | 186 | 02/14/14 | 142 | Mech Room Labor | MC09 | McCabe, Thomas C | 02/12/14 | Regular | 2 | 36 |  |  | 5222
T0756 | PR | 385 | 02/28/14 | 142 | Mech Room Labor | LI49 | Lima Romero, Melvin A | 02/26/14 | Regular | 16 | 320 |  |  | 5320
T0757 | PR | 393 | 02/28/14 | 142 | Mech Room Labor | QU35 | Quintanilla, Esteban R | 02/26/14 | Regular | 40 | 1280 |  |  | 5328
T0758 | PR | 412 | 02/28/14 | 142 | Mech Room Labor | WA35 | Waites, Thaddeus Z | 02/26/14 | Regular | 16 | 448 |  |  | 5347
T0759 | PR | 17 | 03/07/14 | 142 | Mech Room Labor | GO56 | Gonzalez Hernandez, Josue | 03/05/14 | Regular | 8 | 112 |  |  | 5365
T0760 | PR | 22 | 03/07/14 | 142 | Mech Room Labor | LI49 | Lima Romero, Melvin A | 03/05/14 | Regular | 32 | 640 |  |  | 5370
T0761 | PR | 30 | 03/07/14 | 142 | Mech Room Labor | QU35 | Quintanilla, Esteban R | 03/05/14 | Regular | 40 | 1280 |  |  | 5378
T0762 | PR | 49 | 03/07/14 | 142 | Mech Room Labor | WA35 | Waites, Thaddeus Z | 03/05/14 | Regular | 8 | 224 |  |  | 5397
T0763 | PR | 197 | 03/14/14 | 142 | Mech Room Labor | GO56 | Gonzalez Hernandez, Josue | 03/12/14 | Regular | 16 | 224 |  |  | 5416
T0764 | PR | 202 | 03/14/14 | 142 | Mech Room Labor | LI49 | Lima Romero, Melvin A | 03/12/14 | Regular | 24 | 480 |  |  | 5421
T0765 | PR | 210 | 03/14/14 | 142 | Mech Room Labor | QU35 | Quintanilla, Esteban R | 03/12/14 | Regular | 40 | 1280 |  |  | 5429
T0766 | PR | 229 | 03/14/14 | 142 | Mech Room Labor | WA35 | Waites, Thaddeus Z | 03/12/14 | Regular | 16 | 448 |  |  | 5448
T0767 | AP | 420 | 03/20/14 | 142 | Mech Room Labor | 2012FE | Ferguson Enterprises, Inc. $8th Ave | 03/21/14 | Inv |  | 60.21 |  |  | 2887153
T0768 | PR | 331 | 03/21/14 | 142 | Mech Room Labor | CA75 | Castro Hernandez, Carlos E | 03/19/14 | Regular | 16 | 448 |  |  | 5460
T0769 | PR | 338 | 03/21/14 | 142 | Mech Room Labor | GO56 | Gonzalez Hernandez, Josue | 03/19/14 | Regular | 16 | 224 |  |  | 5467
T0770 | PR | 343 | 03/21/14 | 142 | Mech Room Labor | LI49 | Lima Romero, Melvin A | 03/19/14 | Regular | 24 | 480 |  |  | 5472
T0771 | PR | 351 | 03/21/14 | 142 | Mech Room Labor | QU35 | Quintanilla, Esteban R | 03/19/14 | Regular | 22 | 704 |  |  | 5480
T0772 | PR | 467 | 03/28/14 | 142 | Mech Room Labor | BA70 | Barnhart, Joseph N | 03/26/14 | Regular | 2 | 62 |  |  | 5505
T0773 | PR | 472 | 03/28/14 | 142 | Mech Room Labor | CA75 | Castro Hernandez, Carlos E | 03/26/14 | Regular | 14 | 392 |  |  | 5510
T0774 | GL | 198 | 06/12/14 | 142 | Mech Room Labor | Ferguson | Inv 2887153 adj |  | GL
T0775 | PR | 391 | 11/27/13 | 145 | Tub/Shower Labor | CA77 | Castro Hernandez, Jose A | 11/26/13 | Regular | 8 | 120 |  |  | 4709
T0776 | PR | 392 | 11/27/13 | 145 | Tub/Shower Labor | CH04 | Chavarria Lopez, Omar A | 11/26/13 | Overtime | 2 | 36 |  |  | 4710
T0777 | PR | 392 | 11/27/13 | 145 | Tub/Shower Labor | CH04 | Chavarria Lopez, Omar A | 11/26/13 | Regular | 16 | 192 |  |  | 4710
T0778 | PR | 398 | 11/27/13 | 145 | Tub/Shower Labor | GO56 | Gonzalez Hernandez, Josue | 11/26/13 | Regular | 8 | 96 |  |  | 4716
T0779 | PR | 403 | 11/27/13 | 145 | Tub/Shower Labor | LI49 | Lima Romero, Melvin A | 11/26/13 | Overtime | 2 | 57 |  |  | 4721
T0780 | PR | 403 | 11/27/13 | 145 | Tub/Shower Labor | LI49 | Lima Romero, Melvin A | 11/26/13 | Regular | 16 | 304 |  |  | 4721
T0781 | PR | 404 | 11/27/13 | 145 | Tub/Shower Labor | LO55 | Lopez Martinez, Abimael | 11/26/13 | Regular | 18 | 216 |  |  | 4722
T0782 | PR | 407 | 11/27/13 | 145 | Tub/Shower Labor | MO54 | Monico Brambila, Jesus S | 11/26/13 | Overtime | 2 | 39 |  |  | 4725
T0783 | PR | 407 | 11/27/13 | 145 | Tub/Shower Labor | MO54 | Monico Brambila, Jesus S | 11/26/13 | Regular | 16 | 208 |  |  | 4725
T0784 | PR | 410 | 11/27/13 | 145 | Tub/Shower Labor | PA46 | Palma Vides, Hugo | 11/26/13 | Overtime | 2 | 81 |  |  | 4728
T0785 | PR | 410 | 11/27/13 | 145 | Tub/Shower Labor | PA46 | Palma Vides, Hugo | 11/26/13 | Regular | 16 | 432 |  |  | 4728
T0786 | PR | 411 | 11/27/13 | 145 | Tub/Shower Labor | QU35 | Quintanilla, Esteban R | 11/26/13 | Overtime | 2 | 93 |  |  | 4729
T0787 | PR | 411 | 11/27/13 | 145 | Tub/Shower Labor | QU35 | Quintanilla, Esteban R | 11/26/13 | Regular | 16 | 496 |  |  | 4729
T0788 | PR | 414 | 11/27/13 | 145 | Tub/Shower Labor | RI84 | Rivera, Eli P | 11/26/13 | Regular | 8 | 96 |  |  | 4732
T0789 | PR | 415 | 11/27/13 | 145 | Tub/Shower Labor | RI87 | Rivera, Jorge A | 11/26/13 | Regular | 18 | 324 |  |  | 4733
T0790 | PR | 447 | 11/30/13 | 145 | Tub/Shower Labor | CH04 | Chavarria Lopez, Omar A | 11/30/13 | Regular | 8 | 96 |  |  | 4759
T0791 | PR | 466 | 11/30/13 | 145 | Tub/Shower Labor | QU35 | Quintanilla, Esteban R | 11/30/13 | Regular | 8 | 248 |  |  | 4778
T0792 | PR | 56 | 12/13/13 | 145 | Tub/Shower Labor | CA77 | Castro Hernandez, Jose A | 12/11/13 | Regular | 6 | 90 |  |  | 4803
T0793 | PR | 57 | 12/13/13 | 145 | Tub/Shower Labor | CH04 | Chavarria Lopez, Omar A | 12/11/13 | Overtime | 8 | 144 |  |  | 4804
T0794 | PR | 57 | 12/13/13 | 145 | Tub/Shower Labor | CH04 | Chavarria Lopez, Omar A | 12/11/13 | Regular | 8 | 96 |  |  | 4804
T0795 | PR | 62 | 12/13/13 | 145 | Tub/Shower Labor | GO56 | Gonzalez Hernandez, Josue | 12/11/13 | Overtime | 5 | 90 |  |  | 4809
T0796 | PR | 62 | 12/13/13 | 145 | Tub/Shower Labor | GO56 | Gonzalez Hernandez, Josue | 12/11/13 | Regular | 1 | 12 |  |  | 4809
T0797 | PR | 67 | 12/13/13 | 145 | Tub/Shower Labor | LI49 | Lima Romero, Melvin A | 12/11/13 | Overtime | 6 | 171 |  |  | 4814
T0798 | PR | 71 | 12/13/13 | 145 | Tub/Shower Labor | MO54 | Monico Brambila, Jesus S | 12/11/13 | Overtime | 6 | 117 |  |  | 4818
T0799 | PR | 74 | 12/13/13 | 145 | Tub/Shower Labor | PA46 | Palma Vides, Hugo | 12/11/13 | Overtime | 6 | 243 |  |  | 4821
T0800 | PR | 75 | 12/13/13 | 145 | Tub/Shower Labor | QU35 | Quintanilla, Esteban R | 12/11/13 | Overtime | 8 | 372 |  |  | 4822
T0801 | PR | 75 | 12/13/13 | 145 | Tub/Shower Labor | QU35 | Quintanilla, Esteban R | 12/11/13 | Regular | 8 | 248 |  |  | 4822
T0802 | PR | 77 | 12/13/13 | 145 | Tub/Shower Labor | RI84 | Rivera, Eli P | 12/11/13 | Regular | 6 | 72 |  |  | 4824
T0803 | PR | 78 | 12/13/13 | 145 | Tub/Shower Labor | RI87 | Rivera, Jorge A | 12/11/13 | Overtime | 2 | 54 |  |  | 4825
T0804 | PR | 78 | 12/13/13 | 145 | Tub/Shower Labor | RI87 | Rivera, Jorge A | 12/11/13 | Regular | 8 | 144 |  |  | 4825
T0805 | PR | 261 | 12/20/13 | 145 | Tub/Shower Labor | RI84 | Rivera, Eli P | 12/18/13 | Overtime | 6 | 108 |  |  | 4919
T0806 | PR | 262 | 12/20/13 | 145 | Tub/Shower Labor | RI87 | Rivera, Jorge A | 12/18/13 | Overtime | 2 | 54 |  |  | 4920
T0807 | PR | 262 | 12/20/13 | 145 | Tub/Shower Labor | RI87 | Rivera, Jorge A | 12/18/13 | Regular | 8 | 144 |  |  | 4920
T0808 | PR | 358 | 12/27/13 | 145 | Tub/Shower Labor | RI84 | Rivera, Eli P | 12/25/13 | Regular | 6 | 72 |  |  | 4966
T0809 | PR | 288 | 01/17/14 | 145 | Tub/Shower Labor | CH04 | Chavarria Lopez, Omar A | 01/15/14 | Regular | 40 | 520 |  |  | 5012
T0810 | PR | 324 | 01/17/14 | 145 | Tub/Shower Labor | WA35 | Waites, Thaddeus Z | 01/15/14 | Regular | 32 | 896 |  |  | 5048
T0811 | AP | 74 | 05/07/13 | 210 | Underground Material | 2012RS | Rosen Supply Company, Inc. $8th Ave | 05/01/13 | Inv |  | 671.97 |  |  | 4175050-00
T0812 | AP | 75 | 05/07/13 | 210 | Underground Material | 2012RS | Rosen Supply Company, Inc. $8th Ave | 05/02/13 | Inv |  | 989.26 |  |  | 4175051-00
T0813 | AP | 127 | 05/14/13 | 210 | Underground Material | 2012RS | Rosen Supply Company, Inc. $8th Ave | 05/07/13 | Inv |  | -113.48 |  |  | 4179110-00
T0814 | AP | 128 | 05/14/13 | 210 | Underground Material | 2012RS | Rosen Supply Company, Inc. $8th Ave | 05/07/13 | Inv |  | -2.78 |  |  | 4179111-00
T0815 | AP | 129 | 05/14/13 | 210 | Underground Material | 2012RS | Rosen Supply Company, Inc. $8th Ave | 05/09/13 | Inv |  | -30.15 |  |  | 4179214-00
T0816 | AP | 130 | 05/14/13 | 210 | Underground Material | 2012RS | Rosen Supply Company, Inc. $8th Ave | 05/09/13 | Inv |  | 65.2 |  |  | 4179130-00
T0817 | GL | 353 | 05/30/13 | 210 | Underground Material | CK# | 1994 Nathaniel Veley |  | GL
T0818 | GL | 214 | 06/20/13 | 210 | Underground Material | CK# | 2043 Nathaniel Veley Misc Reimb. |  | GL
T0819 | GL | 242 | 08/15/13 | 211 | Garage Material | Mat | Req 104106 |  | GL
T0820 | AP | 271 | 08/20/13 | 211 | Garage Material | 2012RS | Rosen Supply Company, Inc. $8th Ave | 08/13/13 | Inv |  | 1261.74 |  |  | 4175055-00
T0821 | AP | 272 | 08/20/13 | 211 | Garage Material | 2012RS | Rosen Supply Company, Inc. $8th Ave | 08/13/13 | Inv |  | 1317.95 |  |  | 4175056-00
T0822 | AP | 273 | 08/20/13 | 211 | Garage Material | 2012RS | Rosen Supply Company, Inc. $8th Ave | 08/13/13 | Inv |  | 1064.38 |  |  | 4175057-00
T0823 | AP | 274 | 08/20/13 | 211 | Garage Material | 2012RS | Rosen Supply Company, Inc. $8th Ave | 08/13/13 | Inv |  | 1126.58 |  |  | 4175058-00
T0824 | AP | 19 | 09/03/13 | 211 | Garage Material | 2012RS | Rosen Supply Company, Inc. $8th Ave | 08/24/13 | Inv |  | 377.1 |  |  | 4183286-00
T0825 | GL | 45 | 09/03/13 | 211 | Garage Material | Mat | Req 104134 |  | GL
T0826 | GL | 46 | 09/03/13 | 211 | Garage Material | Mat | Req 104136 |  | GL
T0827 | AP | 217 | 09/17/13 | 211 | Garage Material | 2012RS | Rosen Supply Company, Inc. $8th Ave | 09/13/13 | Inv |  | 165 |  |  | 4184210-00
T0828 | GL | 353 | 09/24/13 | 211 | Garage Material | Mat | Req 104128 |  | GL
T0829 | GL | 376 | 09/24/13 | 211 | Garage Material | Mat | Req 104121 |  | GL
T0830 | AP | 447 | 09/30/13 | 211 | Garage Material | 2012FE | Ferguson Enterprises, Inc. $8th Ave | 09/23/13 | Inv |  | 846.86 |  |  | 2731682
T0831 | AP | 449 | 09/30/13 | 211 | Garage Material | 2012FE | Ferguson Enterprises, Inc. $8th Ave | 09/24/13 | Inv |  | 6.18 |  |  | 2731682-1
T0832 | AP | 145 | 10/10/13 | 211 | Garage Material | 2012RS | Rosen Supply Company, Inc. $8th Ave | 09/27/13 | Inv |  | -160.32 |  |  | 4184848-00
T0833 | AP | 146 | 10/10/13 | 211 | Garage Material | 2012RS | Rosen Supply Company, Inc. $8th Ave | 09/27/13 | Inv |  | -138.01 |  |  | 4184847-00
T0834 | GL | 453 | 12/28/13 | 211 | Garage Material | Mat | Req 104046 |  | GL
T0835 | GL | 236 | 01/14/14 | 211 | Garage Material | Mat | Req 100693 |  | GL
T0836 | GL | 545 | 01/28/14 | 211 | Garage Material | Mat | Req 100399 |  | GL
T0837 | AP | 247 | 03/13/14 | 211 | Garage Material | 2012RS | Rosen Supply Company, Inc. $8th Ave | 03/10/14 | Inv |  | 540.06 |  |  | 4191292-00
T0838 | GL | 551 | 03/31/14 | 211 | Garage Material | Mat | Req 1287 |  | GL
T0839 | AP | 318 | 04/22/14 | 211 | Garage Material | 2012KS | Keller Supply Company $8th Ave | 04/07/14 | Inv |  | 80.05 |  |  | S007433535.001
T0840 | GL | 131 | 06/12/14 | 211 | Garage Material | 8th | Closing Adjustments |  | GL
T0841 | AP | 128 | 06/13/13 | 212 | Canout Material | 2012KS | Keller Supply Company $8th Ave | 06/12/13 | Inv |  | 10847.11 |  |  | S006581228.001
T0842 | GL | 179 | 07/18/13 | 212 | Canout Material | Mat | Req 104001 |  | GL
T0843 | GL | 185 | 07/18/13 | 212 | Canout Material | Mat | Req 103977 |  | GL
T0844 | GL | 67 | 11/05/13 | 212 | Canout Material | Mat | Req 104104 |  | GL
T0845 | AP | 60 | 05/07/13 | 213 | Foundation Material | 2012RS | Rosen Supply Company, Inc. $8th Ave | 04/22/13 | Inv |  | 814.79 |  |  | 4175045-00
T0846 | AP | 61 | 05/07/13 | 213 | Foundation Material | 2012RS | Rosen Supply Company, Inc. $8th Ave | 04/22/13 | Inv |  | 974.33 |  |  | 4175046-00
T0847 | GL | 244 | 07/18/13 | 220 | Roughin Material | CK# | 2081 Allen Sanders |  | GL
T0848 | GL | 236 | 08/15/13 | 220 | Roughin Material | Mat | Req 104047 |  | GL
T0849 | AP | 34 | 09/03/13 | 220 | Roughin Material | 2012FE | Ferguson Enterprises, Inc. $8th Ave | 08/26/13 | Inv |  | 8924.95 |  |  | 2709109
T0850 | AP | 141 | 09/05/13 | 220 | Roughin Material | 2012FE | Ferguson Enterprises, Inc. $8th Ave | 08/30/13 | Inv |  | 19.02 |  |  | 2709109-1
T0851 | AP | 147 | 09/05/13 | 220 | Roughin Material | 2012RS | Rosen Supply Company, Inc. $8th Ave | 09/04/13 | Inv |  | 1842.03 |  |  | 4175047-00
T0852 | AP | 148 | 09/05/13 | 220 | Roughin Material | 2012RS | Rosen Supply Company, Inc. $8th Ave | 09/04/13 | Inv |  | 2006.47 |  |  | 4175049-00
T0853 | AP | 153 | 09/12/13 | 220 | Roughin Material | 2012KS | Keller Supply Company $8th Ave | 09/11/13 | Inv |  | 5397.99 |  |  | S06655613.001
T0854 | AP | 157 | 09/12/13 | 220 | Roughin Material | 2012RS | Rosen Supply Company, Inc. $8th Ave | 09/10/13 | Inv |  | -25.5 |  |  | 4184115-00
T0855 | AP | 158 | 09/12/13 | 220 | Roughin Material | 2012RS | Rosen Supply Company, Inc. $8th Ave | 09/10/13 | Inv |  | 2888.87 |  |  | 4181770-00
T0856 | AP | 160 | 09/12/13 | 220 | Roughin Material | 2012FE | Ferguson Enterprises, Inc. $8th Ave | 09/09/13 | Inv |  | 19745.28 |  |  | 2719548
T0857 | AP | 211 | 09/17/13 | 220 | Roughin Material | 2012FE | Ferguson Enterprises, Inc. $8th Ave | 09/11/13 | Inv |  | 229.63 |  |  | 2719548-1
T0858 | AP | 216 | 09/17/13 | 220 | Roughin Material | 2012RS | Rosen Supply Company, Inc. $8th Ave | 09/13/13 | Inv |  | 315.36 |  |  | 4181770-01
T0859 | GL | 255 | 09/19/13 | 220 | Roughin Material | Mat | Req 104154 |  | GL
T0860 | AP | 472 | 09/30/13 | 220 | Roughin Material | 2012FE | Ferguson Enterprises, Inc. $8th Ave | 09/26/13 | Inv |  | 1518.95 |  |  | 2731833
T0861 | AP | 122 | 10/04/13 | 220 | Roughin Material | 2012FE | Ferguson Enterprises, Inc. $8th Ave | 10/03/13 | Inv |  | 26488.22 |  |  | 2741703
T0862 | AP | 147 | 10/10/13 | 220 | Roughin Material | 2012RS | Rosen Supply Company, Inc. $8th Ave | 10/04/13 | Inv |  | 2750.58 |  |  | 4175049-01
T0863 | AP | 148 | 10/10/13 | 220 | Roughin Material | 2012RS | Rosen Supply Company, Inc. $8th Ave | 10/04/13 | Inv |  | 1380.1 |  |  | 4175047-01
T0864 | AP | 162 | 10/11/13 | 220 | Roughin Material | 2012FE | Ferguson Enterprises, Inc. $8th Ave | 10/07/13 | Inv |  | 407.1 |  |  | 2741703-1
T0865 | AP | 163 | 10/11/13 | 220 | Roughin Material | 2012FE | Ferguson Enterprises, Inc. $8th Ave | 10/07/13 | Inv |  | 2861.56 |  |  | 2744070
T0866 | AP | 164 | 10/11/13 | 220 | Roughin Material | 2012FE | Ferguson Enterprises, Inc. $8th Ave | 10/14/13 | Inv |  | 7333.7 |  |  | 2749008
T0867 | GL | 188 | 10/16/13 | 220 | Roughin Material | Mat | Req 104185 |  | GL
T0868 | AP | 272 | 10/22/13 | 220 | Roughin Material | 2012FE | Ferguson Enterprises, Inc. $8th Ave | 10/15/13 | Inv |  | 278.25 |  |  | 2749013
T0869 | AP | 273 | 10/22/13 | 220 | Roughin Material | 2012FE | Ferguson Enterprises, Inc. $8th Ave | 10/15/13 | Inv |  | 3670.25 |  |  | 2751244
T0870 | AP | 348 | 10/29/13 | 220 | Roughin Material | 2012RS | Rosen Supply Company, Inc. $8th Ave | 10/23/13 | Inv |  | 210.24 |  |  | 4181770-02
T0871 | AP | 349 | 10/29/13 | 220 | Roughin Material | 2012RS | Rosen Supply Company, Inc. $8th Ave | 10/25/13 | Inv |  | 335.53 |  |  | 4186071-00
T0872 | GL | 369 | 10/29/13 | 220 | Roughin Material | Mat | Req 104206 |  | GL
T0873 | AP | 11 | 11/01/13 | 220 | Roughin Material | 2012FE | Ferguson Enterprises, Inc. $8th Ave | 10/28/13 | Inv |  | 10520.66 |  |  | 2601872
T0874 | AP | 12 | 11/01/13 | 220 | Roughin Material | 2012FE | Ferguson Enterprises, Inc. $8th Ave | 10/29/13 | Inv |  | 4667.75 |  |  | 2604097
T0875 | GL | 45 | 11/05/13 | 220 | Roughin Material | Mat | Req 104199 |  | GL
T0876 | GL | 51 | 11/05/13 | 220 | Roughin Material | Mat | Req 104182 |  | GL
T0877 | GL | 58 | 11/05/13 | 220 | Roughin Material | Mat | Req 104170 |  | GL
T0878 | GL | 142 | 11/07/13 | 220 | Roughin Material | Mat | Req 104201 |  | GL
T0879 | AP | 150 | 11/11/13 | 220 | Roughin Material | 2012RS | Rosen Supply Company, Inc. $8th Ave | 11/05/13 | Inv |  | 404.2 |  |  | 4186414-00
T0880 | AP | 157 | 11/11/13 | 220 | Roughin Material | 2012KS | Keller Supply Company $8th Ave | 11/07/13 | Inv |  | 106.55 |  |  | S007080166.001
T0881 | AP | 250 | 11/19/13 | 220 | Roughin Material | 2012RS | Rosen Supply Company, Inc. $8th Ave | 11/11/13 | Inv |  | 1387 |  |  | 4186611-00
T0882 | AP | 251 | 11/19/13 | 220 | Roughin Material | 2012RS | Rosen Supply Company, Inc. $8th Ave | 11/13/13 | Inv |  | 625.48 |  |  | 4186829-00
T0883 | AP | 336 | 11/23/13 | 220 | Roughin Material | 2012FE | Ferguson Enterprises, Inc. $8th Ave | 11/19/13 | Inv |  | 675.2 |  |  | 2781377
T0884 | AP | 337 | 11/23/13 | 220 | Roughin Material | 2012FE | Ferguson Enterprises, Inc. $8th Ave | 11/21/13 | Inv |  | 210.48 |  |  | 2784019
T0885 | GL | 156 | 12/14/13 | 220 | Roughin Material | Mat | Req 104226 |  | GL
T0886 | GL | 162 | 12/14/13 | 220 | Roughin Material | Mat | Req 104230 |  | GL
T0887 | GL | 167 | 12/14/13 | 220 | Roughin Material | Mat | Req 104234 |  | GL
T0888 | GL | 171 | 12/14/13 | 220 | Roughin Material | Mat | Req 103986 |  | GL
T0889 | GL | 176 | 12/14/13 | 220 | Roughin Material | Mat | Req 104222 |  | GL
T0890 | GL | 287 | 12/19/13 | 220 | Roughin Material | CK# | 2480 Esteban Quintanilla |  | GL
T0891 | GL | 416 | 12/28/13 | 220 | Roughin Material | Mat | Req 104212 |  | GL
T0892 | GL | 426 | 12/28/13 | 220 | Roughin Material | Mat | Req 104058 |  | GL
T0893 | GL | 434 | 12/28/13 | 220 | Roughin Material | Mat | Req 103996 |  | GL
T0894 | GL | 437 | 12/28/13 | 220 | Roughin Material | Mat | Req 104073 |  | GL
T0895 | GL | 441 | 12/28/13 | 220 | Roughin Material | Mat | Req 104178 |  | GL
T0896 | GL | 511 | 12/31/13 | 220 | Roughin Material | Mat | Req 104066 |  | GL
T0897 | PR | 8 | 01/03/14 | 220 | Roughin Material | CA75 | Castro Hernandez, Carlos E | 01/01/14 | Overtime | 1 | 42 |  |  | 1099
T0898 | AP | 113 | 01/07/14 | 220 | Roughin Material | 2132MH | Manor Hardware & Construction Supply | 12/23/13 | Inv |  | 95.69 |  |  | 519797-00
T0899 | AP | 118 | 01/07/14 | 220 | Roughin Material | 2012RS | Rosen Supply Company, Inc. $8th Ave | 11/27/13 | Inv |  | 115.5 |  |  | 4187427-00
T0900 | AP | 122 | 01/07/14 | 220 | Roughin Material | 2012RS | Rosen Supply Company, Inc. $8th Ave | 12/12/13 | Inv |  | 229.72 |  |  | 4187914-00
T0901 | AP | 123 | 01/07/14 | 220 | Roughin Material | 2012RS | Rosen Supply Company, Inc. $8th Ave | 12/17/13 | Inv |  | 569.94 |  |  | 4188153-00
T0902 | AP | 124 | 01/07/14 | 220 | Roughin Material | 2012RS | Rosen Supply Company, Inc. $8th Ave | 12/19/13 | Inv |  | 73.95 |  |  | 4188278-00
T0903 | AP | 125 | 01/07/14 | 220 | Roughin Material | 2012RS | Rosen Supply Company, Inc. $8th Ave | 12/27/13 | Inv |  | 26.52 |  |  | 4188480-00
T0904 | AP | 127 | 01/07/14 | 220 | Roughin Material | 2012FE | Ferguson Enterprises, Inc. $8th Ave | 11/27/13 | Inv |  | 170.36 |  |  | 2787716
T0905 | AP | 128 | 01/07/14 | 220 | Roughin Material | 2012FE | Ferguson Enterprises, Inc. $8th Ave | 12/05/13 | Inv |  | 284.69 |  |  | 2793154
T0906 | AP | 129 | 01/07/14 | 220 | Roughin Material | 2012FE | Ferguson Enterprises, Inc. $8th Ave | 12/20/13 | Inv |  | 95.6 |  |  | 2807678
T0907 | GL | 328 | 01/09/14 | 220 | Roughin Material | CK# | 2487 Esteban Quintanilla |  | GL
T0908 | GL | 222 | 01/14/14 | 220 | Roughin Material | Mat | Req 100396 |  | GL
T0909 | GL | 224 | 01/14/14 | 220 | Roughin Material | Mat | Req 100692 |  | GL
T0910 | GL | 230 | 01/14/14 | 220 | Roughin Material | Mat | Req 104079 |  | GL
T0911 | GL | 251 | 01/14/14 | 220 | Roughin Material | Mat | Req 100685 |  | GL
T0912 | GL | 254 | 01/14/14 | 220 | Roughin Material | Mat | Req 100691 |  | GL
T0913 | GL | 259 | 01/14/14 | 220 | Roughin Material | Mat | Req 104088 |  | GL
T0914 | GL | 261 | 01/14/14 | 220 | Roughin Material | Mat | Req 104096 |  | GL
T0915 | GL | 265 | 01/14/14 | 220 | Roughin Material | Mat | Req 100699 |  | GL
T0916 | GL | 530 | 01/23/14 | 220 | Roughin Material | CK# | 2500 Esteban Quintanilla |  | GL
T0917 | GL | 530 | 01/23/14 | 220 | Roughin Material | CK# | 2500 Esteban Quintanilla |  | GL
T0918 | GL | 532 | 01/23/14 | 220 | Roughin Material | Mat | Req 100400 |  | GL
T0919 | GL | 533 | 01/23/14 | 220 | Roughin Material | Mat | Req 92550 |  | GL
T0920 | AP | 504 | 01/28/14 | 220 | Roughin Material | 2012FE | Ferguson Enterprises, Inc. $8th Ave | 01/06/14 | Inv |  | 343.05 |  |  | 2815113
T0921 | GL | 537 | 01/28/14 | 220 | Roughin Material | Mat | Req 1113 |  | GL
T0922 | GL | 540 | 01/28/14 | 220 | Roughin Material | Mat | Req 103544 |  | GL
T0923 | GL | 555 | 01/28/14 | 220 | Roughin Material | Mat | Req 1104 |  | GL
T0924 | GL | 557 | 01/28/14 | 220 | Roughin Material | Mat | Req 1109 |  | GL
T0925 | GL | 344 | 01/29/14 | 220 | Roughin Material | Mat | Req 100700 |  | GL
T0926 | GL | 348 | 01/29/14 | 220 | Roughin Material | Mat | Req 103535 |  | GL
T0927 | GL | 351 | 01/29/14 | 220 | Roughin Material | Mat | Req 101400 |  | GL
T0928 | AP | 122 | 02/11/14 | 220 | Roughin Material | 2012RS | Rosen Supply Company, Inc. $8th Ave | 01/27/14 | Inv |  | 33.9 |  |  | 4189622-00
T0929 | GL | 153 | 02/11/14 | 220 | Roughin Material | Mat | Req 1139 |  | GL
T0930 | GL | 550 | 02/20/14 | 220 | Roughin Material | CK# | 1191 Esteban Quintanilla |  | GL
T0931 | GL | 362 | 02/25/14 | 220 | Roughin Material | Mat | Req 1195 |  | GL
T0932 | GL | 363 | 02/25/14 | 220 | Roughin Material | Mat | Req 1194 |  | GL
T0933 | AP | 398 | 03/24/14 | 220 | Roughin Material | 2012FE | Ferguson Enterprises, Inc. $8th Ave | 03/20/14 | Inv |  | 23.15 |  |  | 2872582
T0934 | AP | 481 | 04/28/14 | 220 | Roughin Material | 2012FE | Ferguson Enterprises, Inc. $8th Ave | 04/07/14 | Inv |  | 24.83 |  |  | 2904923
T0935 | GL | 131 | 06/12/14 | 220 | Roughin Material | 8th | Closing Adjustments |  | GL
T0936 | GL | 131 | 06/12/14 | 220 | Roughin Material | 8th | Closing Adjustments |  | GL
T0937 | GL | 131 | 06/12/14 | 220 | Roughin Material | 8th | Closing Adjustments |  | GL
T0938 | GL | 131 | 06/12/14 | 220 | Roughin Material | 8th | Closing Adjustments |  | GL
T0939 | AP | 34 | 05/07/13 | 230 | Finish Material | 1609QC | Quality Concrete Products, Inc. $32 | 04/18/13 | Inv |  | 4979 |  |  | 213168
T0940 | AP | 35 | 05/07/13 | 230 | Finish Material | 1609QC | Quality Concrete Products, Inc. $32 | 04/25/13 | Inv |  | 49 |  |  | 213187
T0941 | AP | 68 | 05/07/13 | 230 | Finish Material | 1609QC | Quality Concrete Products, Inc. $32 | 05/06/13 | Inv |  | 778 |  |  | 213233
T0942 | AP | 195 | 05/16/13 | 230 | Finish Material | 2012KS | Keller Supply Company $8th Ave | 05/15/13 | Inv |  | 700.57 |  |  | S006583070.001
T0943 | AP | 135 | 07/16/13 | 230 | Finish Material | 1175FE | Ferguson Enterprises, Inc. #3007 | 06/18/13 | Inv |  | 175.17 |  |  | 2650912
T0944 | AP | 162 | 07/16/13 | 230 | Finish Material | 1380RS | Rosen Supply Kirkland | 07/03/13 | Inv |  | 973.75 |  |  | 4181002-00
T0945 | AP | 137 | 09/05/13 | 230 | Finish Material | 2012KS | Keller Supply Company $8th Ave | 09/03/13 | Inv |  | 6808.05 |  |  | S006853316.001
T0946 | AP | 152 | 09/12/13 | 230 | Finish Material | 2012KS | Keller Supply Company $8th Ave | 09/11/13 | Inv |  | 1484.7 |  |  | S006585950.001
T0947 | AP | 108 | 10/04/13 | 230 | Finish Material | 2012KS | Keller Supply Company $8th Ave | 10/01/13 | Inv |  | 7763 |  |  | S006858645.001
T0948 | AP | 109 | 10/04/13 | 230 | Finish Material | 2012KS | Keller Supply Company $8th Ave | 10/01/13 | Inv |  | 5899.88 |  |  | S006858645.003
T0949 | AP | 110 | 10/04/13 | 230 | Finish Material | 2012KS | Keller Supply Company $8th Ave | 10/01/13 | Inv |  | 7763 |  |  | S006858645.005
T0950 | AP | 111 | 10/04/13 | 230 | Finish Material | 2012KS | Keller Supply Company $8th Ave | 10/01/13 | Inv |  | 7763 |  |  | S006858645.007
T0951 | AP | 360 | 10/29/13 | 230 | Finish Material | 2012KS | Keller Supply Company $8th Ave | 10/25/13 | Inv |  | 14191.1 |  |  | S006858800.001
T0952 | AP | 22 | 11/05/13 | 230 | Finish Material | 2012RS | Rosen Supply Company, Inc. $8th Ave | 10/30/13 | Inv |  | 340.56 |  |  | 4185664-00
T0953 | AP | 156 | 11/11/13 | 230 | Finish Material | 2012KS | Keller Supply Company $8th Ave | 11/06/13 | Inv |  | 13380.18 |  |  | S006858800.003
T0954 | AP | 21 | 12/02/13 | 230 | Finish Material | 3612MS | Mechanical Sales, Inc. | 11/26/13 | Inv |  | 5300 |  |  | 662295
T0955 | AP | 22 | 12/02/13 | 230 | Finish Material | 3612MS | Mechanical Sales, Inc. | 11/22/13 | Inv |  | 41475 |  |  | 662140
T0956 | AP | 24 | 12/02/13 | 230 | Finish Material | 2132MH | Manor Hardware & Construction Supply | 11/25/13 | Inv |  | 199.92 |  |  | 515207-00
T0957 | GL | 446 | 12/28/13 | 230 | Finish Material | Mat | Req 101389 |  | GL
T0958 | AP | 119 | 01/07/14 | 230 | Finish Material | 2012RS | Rosen Supply Company, Inc. $8th Ave | 12/02/13 | Inv |  | 4353.35 |  |  | 4179952-00
T0959 | AP | 126 | 01/07/14 | 230 | Finish Material | 2012KS | Keller Supply Company $8th Ave | 12/11/13 | Inv |  | 3627.8 |  |  | S006858800.005
T0960 | GL | 219 | 01/14/14 | 230 | Finish Material | Mat | Req 100698 |  | GL
T0961 | GL | 534 | 01/23/14 | 230 | Finish Material | Mat | Req 1000 |  | GL
T0962 | AP | 449 | 01/28/14 | 230 | Finish Material | 2012KS | Keller Supply Company $8th Ave | 01/08/14 | Inv |  | 4626.9 |  |  | S006825859.001
T0963 | AP | 450 | 01/28/14 | 230 | Finish Material | 2012KS | Keller Supply Company $8th Ave | 01/09/14 | Inv |  | 320.74 |  |  | S006918157.001
T0964 | AP | 451 | 01/28/14 | 230 | Finish Material | 2012KS | Keller Supply Company $8th Ave | 01/14/14 | Inv |  | 8416.57 |  |  | S006918155.001
T0965 | AP | 466 | 01/28/14 | 230 | Finish Material | 3612MS | Mechanical Sales, Inc. | 01/21/14 | Inv |  | 10600 |  |  | 663385
T0966 | GL | 546 | 01/28/14 | 230 | Finish Material | Mat | Req 1108 |  | GL
T0967 | GL | 349 | 01/29/14 | 230 | Finish Material | Mat | Req 101398 |  | GL
T0968 | GL | 352 | 01/29/14 | 230 | Finish Material | Mat | Req 100398 |  | GL
T0969 | GL | 357 | 01/29/14 | 230 | Finish Material | Mat | Req 101397 |  | GL
T0970 | AP | 107 | 02/11/14 | 230 | Finish Material | 2012KS | Keller Supply Company $8th Ave | 01/27/14 | Inv |  | 8326.29 |  |  | S006918157.002
T0971 | GL | 142 | 02/11/14 | 230 | Finish Material | Mat | Req 1157 |  | GL
T0972 | GL | 159 | 02/11/14 | 230 | Finish Material | Mat | Req 1137 |  | GL
T0973 | GL | 224 | 02/13/14 | 230 | Finish Material | CK# | 1188 Allen Sanders - Reimb. |  | GL
T0974 | GL | 245 | 02/18/14 | 230 | Finish Material | Mat | Req 1185 |  | GL
T0975 | GL | 547 | 02/20/14 | 230 | Finish Material | Mat | Req 1188 |  | GL
T0976 | AP | 566 | 02/20/14 | 230 | Finish Material | 3612MS | Mechanical Sales, Inc. | 02/28/14 | Inv |  | 324 |  |  | 664379
T0977 | AP | 567 | 02/20/14 | 230 | Finish Material | 3612MS | Mechanical Sales, Inc. | 02/28/14 | Inv |  | 147.52 |  |  | 664369
T0978 | GL | 356 | 02/25/14 | 230 | Finish Material | Mat | Req 1212 |  | GL
T0979 | AP | 469 | 02/28/14 | 230 | Finish Material | 2012KS | Keller Supply Company $8th Ave | 02/11/14 | Inv |  | 8647.03 |  |  | S006918163.001
T0980 | AP | 472 | 02/28/14 | 230 | Finish Material | 2012KS | Keller Supply Company $8th Ave | 02/24/14 | Inv |  | 7715.06 |  |  | S006918169.001
T0981 | AP | 473 | 02/28/14 | 230 | Finish Material | 2012KS | Keller Supply Company $8th Ave | 02/25/14 | Inv |  | 1095.8 |  |  | S006918169.002
T0982 | GL | 61 | 03/06/14 | 230 | Finish Material | Mat | Req 1225 |  | GL
T0983 | GL | 66 | 03/06/14 | 230 | Finish Material | Mat | Req 1004 |  | GL
T0984 | AP | 123 | 03/10/14 | 230 | Finish Material | 2012KS | Keller Supply Company $8th Ave | 03/04/14 | Inv |  | 8810.86 |  |  | S006918781.001
T0985 | GL | 169 | 03/11/14 | 230 | Finish Material | Mat | Req 1256 |  | GL
T0986 | AP | 237 | 03/13/14 | 230 | Finish Material | 2012KS | Keller Supply Company $8th Ave | 03/11/14 | Inv |  | 96.69 |  |  | S007358181.001
T0987 | AP | 249 | 03/13/14 | 230 | Finish Material | 2012RS | Rosen Supply Company, Inc. $8th Ave | 03/11/14 | Inv |  | 79.8 |  |  | 4191343-00
T0988 | GL | 266 | 03/17/14 | 230 | Finish Material | Mat | Req 1267 |  | GL
T0989 | GL | 287 | 03/18/14 | 230 | Finish Material | Mat | Req 1302 |  | GL
T0990 | AP | 301 | 03/18/14 | 230 | Finish Material | 3612MS | Mechanical Sales, Inc. | 03/12/14 | Inv |  | 250 |  |  | 664588
T0991 | AP | 387 | 03/19/14 | 230 | Finish Material | 2012KS | Keller Supply Company $8th Ave | 03/18/14 | Inv |  | 168.44 |  |  | S007401911.001
T0992 | AP | 399 | 03/24/14 | 230 | Finish Material | 2012KS | Keller Supply Company $8th Ave | 03/20/14 | Inv |  | 8425.72 |  |  | S006806780.001
T0993 | AP | 402 | 03/24/14 | 230 | Finish Material | 2012KS | Keller Supply Company $8th Ave | 03/20/14 | Inv |  | -29.95 |  |  | S007413086.001
T0994 | AP | 458 | 03/27/14 | 230 | Finish Material | 2012KS | Keller Supply Company $8th Ave | 03/26/14 | Inv |  | 96.69 |  |  | S007358181.002
T0995 | GL | 554 | 03/31/14 | 230 | Finish Material | Mat | Req 1307 |  | GL
T0996 | GL | 63 | 04/03/14 | 230 | Finish Material | CK# | 2430 Joseph Barnhart |  | GL
T0997 | AP | 73 | 04/04/14 | 230 | Finish Material | 3612MS | Mechanical Sales, Inc. | 03/31/14 | Inv |  | 800 |  |  | 665060
T0998 | AP | 75 | 04/04/14 | 230 | Finish Material | 1231KS | Keller Supply Company | 04/02/14 | Inv |  | 1999.76 |  |  | S006918935.001
T0999 | AP | 78 | 04/04/14 | 230 | Finish Material | 2012FE | Ferguson Enterprises, Inc. $8th Ave | 04/02/14 | Inv |  | 102.44 |  |  | 2894433
T1000 | GL | 196 | 04/14/14 | 230 | Finish Material | Mat | Req 1317 |  | GL
T1001 | GL | 231 | 04/17/14 | 230 | Finish Material | Mat | Req 1010 |  | GL
T1002 | GL | 236 | 04/17/14 | 230 | Finish Material | Mat | Req 1313 |  | GL
T1003 | GL | 487 | 04/17/14 | 230 | Finish Material | CK# | 2413 Allen Sanders |  | GL
T1004 | GL | 487 | 04/17/14 | 230 | Finish Material | CK# | 2413 Allen Sanders |  | GL
T1005 | AP | 319 | 04/22/14 | 230 | Finish Material | 2012KS | Keller Supply Company $8th Ave | 04/14/14 | Inv |  | 502.77 |  |  | S006918818.001
T1006 | AP | 322 | 04/22/14 | 230 | Finish Material | 1231KS | Keller Supply Company | 04/09/14 | Inv |  | 43.95 |  |  | S007467887.001
T1007 | AP | 325 | 04/22/14 | 230 | Finish Material | 1231KS | Keller Supply Company | 04/17/14 | Inv |  | 190.74 |  |  | S007490672.001
T1008 | AP | 326 | 04/22/14 | 230 | Finish Material | 1175FE | Ferguson Enterprises, Inc. #3007 | 04/08/14 | Inv |  | 134.41 |  |  | 2895584
T1009 | AP | 456 | 04/28/14 | 230 | Finish Material | 2012KS | Keller Supply Company $8th Ave | 04/23/14 | Inv |  | 206.8 |  |  | S007507255.001
T1010 | AP | 457 | 04/28/14 | 230 | Finish Material | 2012KS | Keller Supply Company $8th Ave | 04/23/14 | Inv |  | 82.86 |  |  | S006918818.002
T1011 | AP | 466 | 04/28/14 | 230 | Finish Material | 2012RS | Rosen Supply Company, Inc. $8th Ave | 04/25/14 | Inv |  | 52.36 |  |  | 4193191-00
T1012 | AP | 592 | 05/30/14 | 230 | Finish Material | 1231KS | Keller Supply Company | 05/22/14 | Inv |  | 517.25 |  |  | S007557576.001
T1013 | GL | 131 | 06/12/14 | 230 | Finish Material | 8th | Closing Adjustments |  | GL
T1014 | GL | 131 | 06/12/14 | 230 | Finish Material | 8th | Closing Adjustments |  | GL
T1015 | GL | 131 | 06/12/14 | 230 | Finish Material | 8th | Closing Adjustments |  | GL
T1016 | AP | 158 | 11/11/13 | 240 | Gas Material | 2012KS | Keller Supply Company $8th Ave | 11/07/13 | Inv |  | 356.79 |  |  | S007079563.001
T1017 | AP | 108 | 02/11/14 | 240 | Gas Material | 2012KS | Keller Supply Company $8th Ave | 01/28/14 | Inv |  | 187.09 |  |  | S007272734.001
T1018 | AP | 95 | 03/04/14 | 240 | Gas Material | 1234CO | Capital One Credit Card | 03/03/14 | Inv |  | 284.75 |  |  | 030314
T1019 | AP | 571 | 03/31/14 | 240 | Gas Material | 1234CO | Capital One Credit Card | 03/26/14 | Inv |  | 145.62 |  |  | 032614
T1020 | AP | 72 | 04/04/14 | 240 | Gas Material | 1303CM | C.M. Hoskins Company | 03/31/14 | Inv |  | 13.84 |  |  | 65383
T1021 | GL | 487 | 04/17/14 | 240 | Gas Material | CK# | 2413 Allen Sanders |  | GL
T1022 | AP | 10 | 11/01/13 | 241 | Water Main/Insulation Mat | 2012FE | Ferguson Enterprises, Inc. $8th Ave | 10/28/13 | Inv |  | 7876.35 |  |  | 2601866
T1023 | GL | 430 | 12/28/13 | 241 | Water Main/Insulation Mat | Mat | Req 104240 |  | GL
T1024 | GL | 506 | 12/31/13 | 241 | Water Main/Insulation Mat | Mat | Req 104068 |  | GL
T1025 | AP | 120 | 01/07/14 | 241 | Water Main/Insulation Mat | 2012RS | Rosen Supply Company, Inc. $8th Ave | 12/02/13 | Inv |  | 1650.48 |  |  | 4187006-00
T1026 | AP | 121 | 01/07/14 | 241 | Water Main/Insulation Mat | 2012RS | Rosen Supply Company, Inc. $8th Ave | 12/04/13 | Inv |  | 2715.96 |  |  | 4187006-01
T1027 | GL | 244 | 01/14/14 | 241 | Water Main/Insulation Mat | Mat | Req 104060 |  | GL
T1028 | GL | 245 | 01/14/14 | 241 | Water Main/Insulation Mat | Mat | Req 104100 |  | GL
T1029 | GL | 257 | 01/14/14 | 241 | Water Main/Insulation Mat | Mat | Req 104090 |  | GL
T1030 | GL | 260 | 01/14/14 | 241 | Water Main/Insulation Mat | Mat | Req 104083 |  | GL
T1031 | AP | 505 | 01/28/14 | 241 | Water Main/Insulation Mat | 2012FE | Ferguson Enterprises, Inc. $8th Ave | 01/14/14 | Inv |  | 6354.02 |  |  | 2623205
T1032 | AP | 506 | 01/28/14 | 241 | Water Main/Insulation Mat | 2012FE | Ferguson Enterprises, Inc. $8th Ave | 01/14/14 | Inv |  | 5202.76 |  |  | 2601862
T1033 | AP | 507 | 01/28/14 | 241 | Water Main/Insulation Mat | 2012FE | Ferguson Enterprises, Inc. $8th Ave | 01/20/14 | Inv |  | 112.92 |  |  | 2601862-1
T1034 | GL | 552 | 01/28/14 | 241 | Water Main/Insulation Mat | Mat | Req 1112 |  | GL
T1035 | GL | 554 | 01/28/14 | 241 | Water Main/Insulation Mat | Mat | Req 1105 |  | GL
T1036 | GL | 4 | 02/04/14 | 241 | Water Main/Insulation Mat | Mat | Req 1120 |  | GL
T1037 | GL | 5 | 02/04/14 | 241 | Water Main/Insulation Mat | Mat | Req 1124 |  | GL
T1038 | GL | 7 | 02/04/14 | 241 | Water Main/Insulation Mat | Mat | Req 1130 |  | GL
T1039 | AP | 117 | 02/11/14 | 241 | Water Main/Insulation Mat | 2012FE | Ferguson Enterprises, Inc. $8th Ave | 02/03/14 | Inv |  | 1048.26 |  |  | 2841538
T1040 | GL | 154 | 02/11/14 | 241 | Water Main/Insulation Mat | Mat | Req 1133 |  | GL
T1041 | GL | 241 | 02/18/14 | 241 | Water Main/Insulation Mat | Mat | Req 1171 |  | GL
T1042 | GL | 545 | 02/20/14 | 241 | Water Main/Insulation Mat | Mat | Req 1158 |  | GL
T1043 | AP | 455 | 02/28/14 | 241 | Water Main/Insulation Mat | 2012FE | Ferguson Enterprises, Inc. $8th Ave | 02/04/14 | Inv |  | 127.67 |  |  | 2841538-1
T1044 | AP | 456 | 02/28/14 | 241 | Water Main/Insulation Mat | 2012FE | Ferguson Enterprises, Inc. $8th Ave | 02/07/14 | Inv |  | 975.29 |  |  | 2841538-2
T1045 | AP | 457 | 02/28/14 | 241 | Water Main/Insulation Mat | 2012FE | Ferguson Enterprises, Inc. $8th Ave | 02/07/14 | Inv |  | 61.62 |  |  | 2845032
T1046 | AP | 458 | 02/28/14 | 241 | Water Main/Insulation Mat | 2012FE | Ferguson Enterprises, Inc. $8th Ave | 02/10/14 | Inv |  | 79.77 |  |  | 2845032-1
T1047 | AP | 459 | 02/28/14 | 241 | Water Main/Insulation Mat | 2012FE | Ferguson Enterprises, Inc. $8th Ave | 02/12/14 | Inv |  | 157.66 |  |  | 2841538-3
T1048 | AP | 460 | 02/28/14 | 241 | Water Main/Insulation Mat | 2012FE | Ferguson Enterprises, Inc. $8th Ave | 02/13/14 | Inv |  | 1165.39 |  |  | 2848098
T1049 | AP | 461 | 02/28/14 | 241 | Water Main/Insulation Mat | 2012FE | Ferguson Enterprises, Inc. $8th Ave | 02/14/14 | Inv |  | 27.86 |  |  | 2852238
T1050 | AP | 464 | 02/28/14 | 241 | Water Main/Insulation Mat | 2012RS | Rosen Supply Company, Inc. $8th Ave | 02/14/14 | Inv |  | 1218 |  |  | 4190256-00
T1051 | AP | 465 | 02/28/14 | 241 | Water Main/Insulation Mat | 2012RS | Rosen Supply Company, Inc. $8th Ave | 02/19/14 | Inv |  | 931.68 |  |  | 4190256-01
T1052 | AP | 467 | 02/28/14 | 241 | Water Main/Insulation Mat | 2012RS | Rosen Supply Company, Inc. $8th Ave | 02/21/14 | Inv |  | 217.77 |  |  | 4190662-00
T1053 | AP | 468 | 02/28/14 | 241 | Water Main/Insulation Mat | 2012RS | Rosen Supply Company, Inc. $8th Ave | 02/26/14 | Inv |  | 487.2 |  |  | 4190685-00
T1054 | AP | 471 | 02/28/14 | 241 | Water Main/Insulation Mat | 2012KS | Keller Supply Company $8th Ave | 02/13/14 | Inv |  | 17.29 |  |  | S007322218.001
T1055 | GL | 284 | 03/18/14 | 241 | Water Main/Insulation Mat | Mat | Req 1241 |  | GL
T1056 | GL | 131 | 06/12/14 | 241 | Water Main/Insulation Mat | 8th | Closing Adjustments |  | GL
T1057 | GL | 131 | 06/12/14 | 241 | Water Main/Insulation Mat | 8th | Closing Adjustments |  | GL
T1058 | AP | 302 | 12/26/13 | 242 | Mech Room Material | 2012KS | Keller Supply Company $8th Ave | 11/22/13 | Inv |  | 539.37 |  |  | S007121814.001
T1059 | GL | 140 | 02/11/14 | 242 | Mech Room Material | Mat | Req 1143 |  | GL
T1060 | GL | 214 | 02/13/14 | 242 | Mech Room Material | Mat | Req 1159 |  | GL
T1061 | GL | 244 | 02/18/14 | 242 | Mech Room Material | Mat | Req 1170 |  | GL
T1062 | GL | 361 | 02/25/14 | 242 | Mech Room Material | Mat | Req 1193 |  | GL
T1063 | GL | 537 | 02/27/14 | 242 | Mech Room Material | Mat | Req 1215 |  | GL
T1064 | AP | 462 | 02/28/14 | 242 | Mech Room Material | 2012FE | Ferguson Enterprises, Inc. $8th Ave | 02/21/14 | Inv |  | 653.52 |  |  | 2855339
T1065 | AP | 463 | 02/28/14 | 242 | Mech Room Material | 2012FE | Ferguson Enterprises, Inc. $8th Ave | 02/25/14 | Inv |  | 1671.78 |  |  | 2857403
T1066 | AP | 466 | 02/28/14 | 242 | Mech Room Material | 2012RS | Rosen Supply Company, Inc. $8th Ave | 02/21/14 | Inv |  | 185.61 |  |  | 4190558-00
T1067 | AP | 470 | 02/28/14 | 242 | Mech Room Material | 2012KS | Keller Supply Company $8th Ave | 02/12/14 | Inv |  | 3179.4 |  |  | S007284968.001
T1068 | GL | 482 | 02/28/14 | 242 | Mech Room Material | Mat | Req 1203 |  | GL
T1069 | GL | 486 | 02/28/14 | 242 | Mech Room Material | Mat | Req 1232 |  | GL
T1070 | GL | 57 | 03/06/14 | 242 | Mech Room Material | Mat | Req 1229 |  | GL
T1071 | GL | 58 | 03/06/14 | 242 | Mech Room Material | Mat | Req 1224 |  | GL
T1072 | AP | 130 | 03/10/14 | 242 | Mech Room Material | 2012RS | Rosen Supply Company, Inc. $8th Ave | 03/05/14 | Inv |  | 231.21 |  |  | 4191101-00
T1073 | GL | 141 | 03/10/14 | 242 | Mech Room Material | Mat | Req 1243 |  | GL
T1074 | GL | 147 | 03/10/14 | 242 | Mech Room Material | Mat | Req 1007 |  | GL
T1075 | AP | 233 | 03/13/14 | 242 | Mech Room Material | 2012KS | Keller Supply Company $8th Ave | 03/05/14 | Inv |  | 1848.51 |  |  | S007372353.001
T1076 | AP | 234 | 03/13/14 | 242 | Mech Room Material | 2012KS | Keller Supply Company $8th Ave | 03/06/14 | Inv |  | 74.18 |  |  | S007376004.002
T1077 | AP | 235 | 03/13/14 | 242 | Mech Room Material | 2012KS | Keller Supply Company $8th Ave | 03/06/14 | Inv |  | 151.15 |  |  | S007376004.001
T1078 | AP | 236 | 03/13/14 | 242 | Mech Room Material | 2012KS | Keller Supply Company $8th Ave | 03/10/14 | Inv |  | 291.97 |  |  | S007382831.001
T1079 | AP | 248 | 03/13/14 | 242 | Mech Room Material | 2012RS | Rosen Supply Company, Inc. $8th Ave | 03/11/14 | Inv |  | 223.75 |  |  | 4191294-00
T1080 | AP | 250 | 03/13/14 | 242 | Mech Room Material | 2012RS | Rosen Supply Company, Inc. $8th Ave | 03/11/14 | Inv |  | 104.74 |  |  | 4191374-00
T1081 | GL | 262 | 03/17/14 | 242 | Mech Room Material | Mat | Req 1247 |  | GL
T1082 | GL | 264 | 03/17/14 | 242 | Mech Room Material | Mat | Req 1268 |  | GL
T1083 | GL | 410 | 03/20/14 | 242 | Mech Room Material | CK# | 2426 Esteban Quintanilla |  | GL
T1084 | AP | 397 | 03/24/14 | 242 | Mech Room Material | 2012FE | Ferguson Enterprises, Inc. $8th Ave | 03/20/14 | Inv |  | 57.37 |  |  | 2885081
T1085 | AP | 457 | 03/27/14 | 242 | Mech Room Material | 2012KS | Keller Supply Company $8th Ave | 03/24/14 | Inv |  | 39.88 |  |  | S007376222.001
T1086 | GL | 487 | 04/17/14 | 242 | Mech Room Material | CK# | 2413 Allen Sanders |  | GL
T1087 | AP | 324 | 04/22/14 | 242 | Mech Room Material | 1231KS | Keller Supply Company | 04/16/14 | Inv |  | 1644.64 |  |  | S007465459.001
T1088 | AP | 464 | 04/28/14 | 242 | Mech Room Material | 2012RS | Rosen Supply Company, Inc. $8th Ave | 04/21/14 | Inv |  | -20.37 |  |  | 4193092-00
T1089 | AP | 465 | 04/28/14 | 242 | Mech Room Material | 2012RS | Rosen Supply Company, Inc. $8th Ave | 04/24/14 | Inv |  | 665.4 |  |  | 4192502-00
T1090 | GL | 234 | 05/13/14 | 242 | Mech Room Material | Mat | Req 1365 |  | GL
T1091 | GL | 131 | 06/12/14 | 242 | Mech Room Material | 8th | Closing Adjustments |  | GL
T1092 | GL | 131 | 06/12/14 | 242 | Mech Room Material | 8th | Closing Adjustments |  | GL
T1093 | GL | 197 | 06/12/14 | 242 | Mech Room Material | Job | Closing Adjustments |  | GL
T1094 | GL | 198 | 06/12/14 | 242 | Mech Room Material | Ferguson | Inv 2887153 adj |  | GL
T1095 | AP | 319 | 11/23/13 | 245 | Tub/Shower Material | 2132MH | Manor Hardware & Construction Supply | 11/21/13 | Inv |  | 435 |  |  | 512643-00
T1096 | AP | 25 | 12/02/13 | 245 | Tub/Shower Material | 2132MH | Manor Hardware & Construction Supply | 11/22/13 | Inv |  | 435 |  |  | 514680-00
T1097 | AP | 193 | 12/17/13 | 245 | Tub/Shower Material | 1234CO | Capital One Credit Card | 12/04/13 | Inv |  | 268 |  |  | 120413C
T1098 | GL | 287 | 12/19/13 | 245 | Tub/Shower Material | CK# | 2480 Esteban Quintanilla |  | GL
T1099 | AP | 316 | 12/26/13 | 245 | Tub/Shower Material | 2132MH | Manor Hardware & Construction Supply | 12/17/13 | Inv |  | 435 |  |  | 518406-00
T1100 | AP | 492 | 12/26/13 | 245 | Tub/Shower Material | 1234CO | Capital One Credit Card | 12/19/13 | Inv |  | 268 |  |  | 121913
T1101 | AP | 493 | 12/26/13 | 245 | Tub/Shower Material | 1234CO | Capital One Credit Card | 12/20/13 | Inv |  | 54.64 |  |  | 122013
T1102 | AP | 462 | 01/28/14 | 245 | Tub/Shower Material | 2132MH | Manor Hardware & Construction Supply | 01/06/14 | Inv |  | 290 |  |  | 520917-00
T1103 | AP | 496 | 02/28/14 | 245 | Tub/Shower Material | 2132MH | Manor Hardware & Construction Supply | 02/13/14 | Inv |  | 72.5 |  |  | 528358-00
T1104 | AP | 400 | 03/24/14 | 600 | Subcontractor | 1421RA | R.A. Brown Backflow Testing | 03/21/14 | Inv |  | 186 |  |  | 14032102
T1105 | AP | 186 | 01/22/13 | 601 | Engineering/Plans | 1625FE | Franklin Engineering | 01/21/13 | Inv |  | 4850 |  |  | 4974
T1106 | AP | 206 | 02/21/13 | 601 | Engineering/Plans | 1625FE | Franklin Engineering | 02/20/13 | Inv |  | 9762.75 |  |  | 5001
T1107 | AP | 186 | 04/18/13 | 601 | Engineering/Plans | 1625FE | Franklin Engineering | 04/18/13 | Inv |  | 270 |  |  | 5063
T1108 | AP | 229 | 05/20/13 | 601 | Engineering/Plans | 1625FE | Franklin Engineering | 05/20/13 | Inv |  | 730 |  |  | 5096
T1109 | AP | 447 | 04/28/14 | 601 | Engineering/Plans | 1288DR | DRSi | 04/07/14 | Inv |  | 69.28 |  |  | 367542
T1110 | AP | 132 | 04/16/13 | 603 | Permits & Licenses | 1234BA | Bank of America CC | 04/16/13 | Inv |  | 8285 |  |  | 041613
T1111 | AP | 133 | 04/16/13 | 603 | Permits & Licenses | 1234BA | Bank of America CC | 04/16/13 | Inv |  | 298 |  |  | 041613A
T1112 | AP | 134 | 04/16/13 | 603 | Permits & Licenses | 1234BA | Bank of America CC | 04/16/13 | Inv |  | 175 |  |  | 041613B
T1113 | AP | 268 | 07/24/13 | 603 | Permits & Licenses | 1234CO | Capital One Credit Card | 07/11/13 | Inv |  | 4.88 |  |  | 071113
T1114 | AP | 457 | 10/31/13 | 603 | Permits & Licenses | 1234BA | Bank of America CC | 10/21/13 | Inv |  | 140 |  |  | 102113
T1115 | AP | 73 | 03/06/14 | 603 | Permits & Licenses | 1234BA | Bank of America CC | 03/06/14 | Inv |  | 839 |  |  | 030614
T1116 | AP | 436 | 04/28/14 | 604 | Backcharges | 5919PW | Patchworks, Inc. | 04/27/14 | Inv |  | 1237.5 |  |  | 3070
T1117 | AP | 385 | 05/19/14 | 604 | Backcharges | 5919PW | Patchworks, Inc. | 05/04/14 | Inv |  | 600 |  |  | 3085
T1118 | GL | 270 | 12/03/12 | 607 | Other Expenses | Republic | Parking |  | GL
T1119 | GL | 173 | 12/17/12 | 607 | Other Expenses | Diamond | Parking |  | GL
T1120 | GL | 156 | 03/14/13 | 607 | Other Expenses | Diamond | Parking |  | GL
T1121 | GL | 245 | 03/25/13 | 607 | Other Expenses | Diamond | Parking |  | GL
T1122 | GL | 307 | 03/28/13 | 607 | Other Expenses | Diamond | Parking |  | GL
T1123 | AP | 53 | 04/04/13 | 607 | Other Expenses | 1234BA | Bank of America CC | 04/04/13 | Inv |  | 4.88 |  |  | 040413B
T1124 | GL | 76 | 04/09/13 | 607 | Other Expenses | Diamond | Parking |  | GL
T1125 | GL | 274 | 04/29/13 | 607 | Other Expenses | Diamond | Parking |  | GL
T1126 | AP | 157 | 05/29/13 | 607 | Other Expenses | 1234CO | Capital One Credit Card | 05/02/13 | Inv |  | 6.11 |  |  | 050213B
T1127 | AP | 193 | 10/16/13 | 607 | Other Expenses | 1233AE | American Express 3-41000 | 10/09/13 | Inv |  | 6.11 |  |  | 100913
T1128 | AP | 89 | 11/01/13 | 607 | Other Expenses | 1233AE | American Express 3-41000 | 10/09/13 | Inv |  | -6.11 |  |  | 100913A
T1129 | AP | 197 | 12/17/13 | 607 | Other Expenses | 1233AE | American Express 3-41000 | 10/23/13 | Inv |  | 6.11 |  |  | 102313
T1130 | AP | 218 | 04/15/14 | 607 | Other Expenses | 1234CO | Capital One Credit Card | 04/04/14 | Inv |  | 6.11 |  |  | 040414
T1131 | PR | 207 | 01/25/13 | 995 | Payroll Burden | GE69 | Gerard, Jeffrey S
T1132 | PR | 9 | 03/01/13 | 995 | Payroll Burden | GE69 | Gerard, Jeffrey S
T1133 | PR | 71 | 03/08/13 | 995 | Payroll Burden | GE69 | Gerard, Jeffrey S
T1134 | PR | 194 | 03/22/13 | 995 | Payroll Burden | GE69 | Gerard, Jeffrey S
T1135 | PR | 279 | 03/29/13 | 995 | Payroll Burden | BA70 | Barnhart, Joseph N
T1136 | PR | 286 | 03/29/13 | 995 | Payroll Burden | GE69 | Gerard, Jeffrey S
T1137 | PR | 300 | 03/29/13 | 995 | Payroll Burden | SA54 | Sanders, Allen O
T1138 | PR | 20 | 04/05/13 | 995 | Payroll Burden | GE69 | Gerard, Jeffrey S
T1139 | PR | 90 | 04/12/13 | 995 | Payroll Burden | GE69 | Gerard, Jeffrey S
T1140 | PR | 153 | 04/19/13 | 995 | Payroll Burden | GE69 | Gerard, Jeffrey S
T1141 | PR | 153 | 04/19/13 | 995 | Payroll Burden | GE69 | Gerard, Jeffrey S
T1142 | PR | 153 | 04/19/13 | 995 | Payroll Burden | GE69 | Gerard, Jeffrey S
T1143 | PR | 225 | 04/26/13 | 995 | Payroll Burden | BA70 | Barnhart, Joseph N
T1144 | PR | 227 | 04/26/13 | 995 | Payroll Burden | CA77 | Castro Hernandez, Jose A
T1145 | PR | 232 | 04/26/13 | 995 | Payroll Burden | GE69 | Gerard, Jeffrey S
T1146 | PR | 232 | 04/26/13 | 995 | Payroll Burden | GE69 | Gerard, Jeffrey S
T1147 | PR | 232 | 04/26/13 | 995 | Payroll Burden | GE69 | Gerard, Jeffrey S
T1148 | PR | 242 | 04/26/13 | 995 | Payroll Burden | QU35 | Quintanilla, Esteban R
T1149 | PR | 4 | 05/03/13 | 995 | Payroll Burden | CA77 | Castro Hernandez, Jose A
T1150 | PR | 4 | 05/03/13 | 995 | Payroll Burden | CA77 | Castro Hernandez, Jose A
T1151 | PR | 9 | 05/03/13 | 995 | Payroll Burden | GE69 | Gerard, Jeffrey S
T1152 | PR | 9 | 05/03/13 | 995 | Payroll Burden | GE69 | Gerard, Jeffrey S
T1153 | PR | 9 | 05/03/13 | 995 | Payroll Burden | GE69 | Gerard, Jeffrey S
T1154 | PR | 17 | 05/03/13 | 995 | Payroll Burden | PA11 | Paco Leyva, Orlando
T1155 | PR | 19 | 05/03/13 | 995 | Payroll Burden | QU35 | Quintanilla, Esteban R
T1156 | PR | 19 | 05/03/13 | 995 | Payroll Burden | QU35 | Quintanilla, Esteban R
T1157 | PR | 26 | 05/03/13 | 995 | Payroll Burden | VE45 | Veley, Nathaniel S
T1158 | PR | 85 | 05/10/13 | 995 | Payroll Burden | GE69 | Gerard, Jeffrey S
T1159 | PR | 85 | 05/10/13 | 995 | Payroll Burden | GE69 | Gerard, Jeffrey S
T1160 | PR | 85 | 05/10/13 | 995 | Payroll Burden | GE69 | Gerard, Jeffrey S
T1161 | PR | 88 | 05/10/13 | 995 | Payroll Burden | LI49 | Lima Romero, Melvin A
T1162 | PR | 88 | 05/10/13 | 995 | Payroll Burden | LI49 | Lima Romero, Melvin A
T1163 | PR | 93 | 05/10/13 | 995 | Payroll Burden | PA11 | Paco Leyva, Orlando
T1164 | PR | 93 | 05/10/13 | 995 | Payroll Burden | PA11 | Paco Leyva, Orlando
T1165 | PR | 102 | 05/10/13 | 995 | Payroll Burden | VE45 | Veley, Nathaniel S
T1166 | PR | 102 | 05/10/13 | 995 | Payroll Burden | VE45 | Veley, Nathaniel S
T1167 | PR | 176 | 05/17/13 | 995 | Payroll Burden | LI49 | Lima Romero, Melvin A
T1168 | PR | 176 | 05/17/13 | 995 | Payroll Burden | LI49 | Lima Romero, Melvin A
T1169 | PR | 181 | 05/17/13 | 995 | Payroll Burden | PA11 | Paco Leyva, Orlando
T1170 | PR | 190 | 05/17/13 | 995 | Payroll Burden | VE45 | Veley, Nathaniel S
T1171 | PR | 190 | 05/17/13 | 995 | Payroll Burden | VE45 | Veley, Nathaniel S
T1172 | PR | 264 | 05/24/13 | 995 | Payroll Burden | GE69 | Gerard, Jeffrey S
T1173 | PR | 266 | 05/24/13 | 995 | Payroll Burden | HU06 | Hubbard, Robert W
T1174 | PR | 272 | 05/24/13 | 995 | Payroll Burden | PA11 | Paco Leyva, Orlando
T1175 | PR | 272 | 05/24/13 | 995 | Payroll Burden | PA11 | Paco Leyva, Orlando
T1176 | PR | 281 | 05/24/13 | 995 | Payroll Burden | VE45 | Veley, Nathaniel S
T1177 | PR | 281 | 05/24/13 | 995 | Payroll Burden | VE45 | Veley, Nathaniel S
T1178 | PR | 325 | 05/31/13 | 995 | Payroll Burden | GE69 | Gerard, Jeffrey S
T1179 | PR | 325 | 05/31/13 | 995 | Payroll Burden | GE69 | Gerard, Jeffrey S
T1180 | PR | 325 | 05/31/13 | 995 | Payroll Burden | GE69 | Gerard, Jeffrey S
T1181 | PR | 333 | 05/31/13 | 995 | Payroll Burden | PA11 | Paco Leyva, Orlando
T1182 | PR | 342 | 05/31/13 | 995 | Payroll Burden | VE45 | Veley, Nathaniel S
T1183 | PR | 13 | 06/07/13 | 995 | Payroll Burden | GE69 | Gerard, Jeffrey S
T1184 | PR | 21 | 06/07/13 | 995 | Payroll Burden | PA11 | Paco Leyva, Orlando
T1185 | PR | 30 | 06/07/13 | 995 | Payroll Burden | VE45 | Veley, Nathaniel S
T1186 | PR | 30 | 06/07/13 | 995 | Payroll Burden | VE45 | Veley, Nathaniel S
T1187 | PR | 97 | 06/14/13 | 995 | Payroll Burden | GE69 | Gerard, Jeffrey S
T1188 | PR | 97 | 06/14/13 | 995 | Payroll Burden | GE69 | Gerard, Jeffrey S
T1189 | PR | 97 | 06/14/13 | 995 | Payroll Burden | GE69 | Gerard, Jeffrey S
T1190 | PR | 182 | 06/21/13 | 995 | Payroll Burden | GE69 | Gerard, Jeffrey S
T1191 | PR | 182 | 06/21/13 | 995 | Payroll Burden | GE69 | Gerard, Jeffrey S
T1192 | PR | 191 | 06/21/13 | 995 | Payroll Burden | PA11 | Paco Leyva, Orlando
T1193 | PR | 202 | 06/21/13 | 995 | Payroll Burden | VE45 | Veley, Nathaniel S
T1194 | PR | 247 | 06/28/13 | 995 | Payroll Burden | GE69 | Gerard, Jeffrey S
T1195 | PR | 247 | 06/28/13 | 995 | Payroll Burden | GE69 | Gerard, Jeffrey S
T1196 | PR | 257 | 06/28/13 | 995 | Payroll Burden | PA11 | Paco Leyva, Orlando
T1197 | PR | 267 | 06/28/13 | 995 | Payroll Burden | VE45 | Veley, Nathaniel S
T1198 | PR | 12 | 07/03/13 | 995 | Payroll Burden | GE69 | Gerard, Jeffrey S
T1199 | PR | 12 | 07/03/13 | 995 | Payroll Burden | GE69 | Gerard, Jeffrey S
T1200 | PR | 12 | 07/03/13 | 995 | Payroll Burden | GE69 | Gerard, Jeffrey S
T1201 | PR | 22 | 07/03/13 | 995 | Payroll Burden | PA11 | Paco Leyva, Orlando
T1202 | PR | 22 | 07/03/13 | 995 | Payroll Burden | PA11 | Paco Leyva, Orlando
T1203 | PR | 32 | 07/03/13 | 995 | Payroll Burden | VE45 | Veley, Nathaniel S
T1204 | PR | 32 | 07/03/13 | 995 | Payroll Burden | VE45 | Veley, Nathaniel S
T1205 | PR | 81 | 07/12/13 | 995 | Payroll Burden | GE69 | Gerard, Jeffrey S
T1206 | PR | 81 | 07/12/13 | 995 | Payroll Burden | GE69 | Gerard, Jeffrey S
T1207 | PR | 210 | 07/19/13 | 995 | Payroll Burden | GE69 | Gerard, Jeffrey S
T1208 | PR | 210 | 07/19/13 | 995 | Payroll Burden | GE69 | Gerard, Jeffrey S
T1209 | PR | 210 | 07/19/13 | 995 | Payroll Burden | GE69 | Gerard, Jeffrey S
T1210 | PR | 210 | 07/19/13 | 995 | Payroll Burden | GE69 | Gerard, Jeffrey S
T1211 | PR | 213 | 07/19/13 | 995 | Payroll Burden | HU04 | Hubbard, Dustin R
T1212 | PR | 220 | 07/19/13 | 995 | Payroll Burden | PA11 | Paco Leyva, Orlando
T1213 | PR | 227 | 07/19/13 | 995 | Payroll Burden | SA54 | Sanders, Allen O
T1214 | PR | 231 | 07/19/13 | 995 | Payroll Burden | VE45 | Veley, Nathaniel S
T1215 | PR | 231 | 07/19/13 | 995 | Payroll Burden | VE45 | Veley, Nathaniel S
T1216 | PR | 280 | 07/26/13 | 995 | Payroll Burden | CO71 | Cortes Mendiola, Victor H
T1217 | PR | 280 | 07/26/13 | 995 | Payroll Burden | CO71 | Cortes Mendiola, Victor H
T1218 | PR | 283 | 07/26/13 | 995 | Payroll Burden | GE69 | Gerard, Jeffrey S
T1219 | PR | 283 | 07/26/13 | 995 | Payroll Burden | GE69 | Gerard, Jeffrey S
T1220 | PR | 293 | 07/26/13 | 995 | Payroll Burden | PA11 | Paco Leyva, Orlando
T1221 | PR | 11 | 08/02/13 | 995 | Payroll Burden | GE69 | Gerard, Jeffrey S
T1222 | PR | 11 | 08/02/13 | 995 | Payroll Burden | GE69 | Gerard, Jeffrey S
T1223 | PR | 11 | 08/02/13 | 995 | Payroll Burden | GE69 | Gerard, Jeffrey S
T1224 | PR | 11 | 08/02/13 | 995 | Payroll Burden | GE69 | Gerard, Jeffrey S
T1225 | PR | 14 | 08/02/13 | 995 | Payroll Burden | HU04 | Hubbard, Dustin R
T1226 | PR | 21 | 08/02/13 | 995 | Payroll Burden | PA11 | Paco Leyva, Orlando
T1227 | PR | 84 | 08/09/13 | 995 | Payroll Burden | AR70 | Arreola, Israel A
T1228 | PR | 93 | 08/09/13 | 995 | Payroll Burden | GE69 | Gerard, Jeffrey S
T1229 | PR | 93 | 08/09/13 | 995 | Payroll Burden | GE69 | Gerard, Jeffrey S
T1230 | PR | 105 | 08/09/13 | 995 | Payroll Burden | PA11 | Paco Leyva, Orlando
T1231 | PR | 113 | 08/09/13 | 995 | Payroll Burden | SE64 | Sepulveda Gonzalez, Alfredo
T1232 | PR | 126 | 08/09/13 | 995 | Payroll Burden | SE64 | Sepulveda Gonzalez, Alfredo
T1233 | PR | 131 | 08/09/13 | 995 | Payroll Burden | SE64 | Sepulveda Gonzalez, Alfredo
T1234 | PR | 206 | 08/16/13 | 995 | Payroll Burden | GE69 | Gerard, Jeffrey S
T1235 | PR | 206 | 08/16/13 | 995 | Payroll Burden | GE69 | Gerard, Jeffrey S
T1236 | PR | 218 | 08/16/13 | 995 | Payroll Burden | PA11 | Paco Leyva, Orlando
T1237 | PR | 230 | 08/16/13 | 995 | Payroll Burden | VE45 | Veley, Nathaniel S
T1238 | PR | 284 | 08/23/13 | 995 | Payroll Burden | CO71 | Cortes Mendiola, Victor H
T1239 | PR | 287 | 08/23/13 | 995 | Payroll Burden | GE69 | Gerard, Jeffrey S
T1240 | PR | 287 | 08/23/13 | 995 | Payroll Burden | GE69 | Gerard, Jeffrey S
T1241 | PR | 299 | 08/23/13 | 995 | Payroll Burden | PA11 | Paco Leyva, Orlando
T1242 | PR | 307 | 08/23/13 | 995 | Payroll Burden | SE64 | Sepulveda Gonzalez, Alfredo
T1243 | PR | 310 | 08/23/13 | 995 | Payroll Burden | SP17 | Spears, Gregory M
T1244 | PR | 311 | 08/23/13 | 995 | Payroll Burden | VE45 | Veley, Nathaniel S
T1245 | PR | 394 | 08/30/13 | 995 | Payroll Burden | CO71 | Cortes Mendiola, Victor H
T1246 | PR | 394 | 08/30/13 | 995 | Payroll Burden | CO71 | Cortes Mendiola, Victor H
T1247 | PR | 397 | 08/30/13 | 995 | Payroll Burden | GE69 | Gerard, Jeffrey S
T1248 | PR | 397 | 08/30/13 | 995 | Payroll Burden | GE69 | Gerard, Jeffrey S
T1249 | PR | 400 | 08/30/13 | 995 | Payroll Burden | HO14 | Holmes, Anthony R
T1250 | PR | 409 | 08/30/13 | 995 | Payroll Burden | PA11 | Paco Leyva, Orlando
T1251 | PR | 409 | 08/30/13 | 995 | Payroll Burden | PA11 | Paco Leyva, Orlando
T1252 | PR | 410 | 08/30/13 | 995 | Payroll Burden | PA46 | Palma Vides, Hugo
T1253 | PR | 410 | 08/30/13 | 995 | Payroll Burden | PA46 | Palma Vides, Hugo
T1254 | PR | 419 | 08/30/13 | 995 | Payroll Burden | SP17 | Spears, Gregory M
T1255 | PR | 419 | 08/30/13 | 995 | Payroll Burden | SP17 | Spears, Gregory M
T1256 | PR | 419 | 08/30/13 | 995 | Payroll Burden | SP17 | Spears, Gregory M
T1257 | PR | 419 | 08/30/13 | 995 | Payroll Burden | SP17 | Spears, Gregory M
T1258 | PR | 420 | 08/30/13 | 995 | Payroll Burden | VE45 | Veley, Nathaniel S
T1259 | PR | 420 | 08/30/13 | 995 | Payroll Burden | VE45 | Veley, Nathaniel S
T1260 | PR | 422 | 08/30/13 | 995 | Payroll Burden | SE64 | Sepulveda Gonzalez, Alfredo
T1261 | PR | 422 | 08/30/13 | 995 | Payroll Burden | SE64 | Sepulveda Gonzalez, Alfredo
T1262 | PR | 57 | 09/06/13 | 995 | Payroll Burden | CO71 | Cortes Mendiola, Victor H
T1263 | PR | 60 | 09/06/13 | 995 | Payroll Burden | GE69 | Gerard, Jeffrey S
T1264 | PR | 63 | 09/06/13 | 995 | Payroll Burden | HO14 | Holmes, Anthony R
T1265 | PR | 70 | 09/06/13 | 995 | Payroll Burden | MO54 | Monico Brambila, Jesus S
T1266 | PR | 72 | 09/06/13 | 995 | Payroll Burden | PA11 | Paco Leyva, Orlando
T1267 | PR | 73 | 09/06/13 | 995 | Payroll Burden | PA46 | Palma Vides, Hugo
T1268 | PR | 80 | 09/06/13 | 995 | Payroll Burden | SE64 | Sepulveda Gonzalez, Alfredo
T1269 | PR | 83 | 09/06/13 | 995 | Payroll Burden | SP17 | Spears, Gregory M
T1270 | PR | 84 | 09/06/13 | 995 | Payroll Burden | VE45 | Veley, Nathaniel S
T1271 | PR | 165 | 09/13/13 | 995 | Payroll Burden | CA74 | Castaneda Martinez, Gustavo
T1272 | PR | 166 | 09/13/13 | 995 | Payroll Burden | CA75 | Castro Hernandez, Carlos E
T1273 | PR | 169 | 09/13/13 | 995 | Payroll Burden | CO71 | Cortes Mendiola, Victor H
T1274 | PR | 172 | 09/13/13 | 995 | Payroll Burden | GE69 | Gerard, Jeffrey S
T1275 | PR | 172 | 09/13/13 | 995 | Payroll Burden | GE69 | Gerard, Jeffrey S
T1276 | PR | 173 | 09/13/13 | 995 | Payroll Burden | GO56 | Gonzalez Hernandez, Josue
T1277 | PR | 175 | 09/13/13 | 995 | Payroll Burden | HO14 | Holmes, Anthony R
T1278 | PR | 175 | 09/13/13 | 995 | Payroll Burden | HO14 | Holmes, Anthony R
T1279 | PR | 175 | 09/13/13 | 995 | Payroll Burden | HO14 | Holmes, Anthony R
T1280 | PR | 175 | 09/13/13 | 995 | Payroll Burden | HO14 | Holmes, Anthony R
T1281 | PR | 178 | 09/13/13 | 995 | Payroll Burden | LI49 | Lima Romero, Melvin A
T1282 | PR | 182 | 09/13/13 | 995 | Payroll Burden | MO54 | Monico Brambila, Jesus S
T1283 | PR | 182 | 09/13/13 | 995 | Payroll Burden | MO54 | Monico Brambila, Jesus S
T1284 | PR | 184 | 09/13/13 | 995 | Payroll Burden | PA11 | Paco Leyva, Orlando
T1285 | PR | 184 | 09/13/13 | 995 | Payroll Burden | PA11 | Paco Leyva, Orlando
T1286 | PR | 185 | 09/13/13 | 995 | Payroll Burden | PA46 | Palma Vides, Hugo
T1287 | PR | 185 | 09/13/13 | 995 | Payroll Burden | PA46 | Palma Vides, Hugo
T1288 | PR | 185 | 09/13/13 | 995 | Payroll Burden | PA46 | Palma Vides, Hugo
T1289 | PR | 185 | 09/13/13 | 995 | Payroll Burden | PA46 | Palma Vides, Hugo
T1290 | PR | 186 | 09/13/13 | 995 | Payroll Burden | QU35 | Quintanilla, Esteban R
T1291 | PR | 193 | 09/13/13 | 995 | Payroll Burden | SE64 | Sepulveda Gonzalez, Alfredo
T1292 | PR | 196 | 09/13/13 | 995 | Payroll Burden | SP17 | Spears, Gregory M
T1293 | PR | 196 | 09/13/13 | 995 | Payroll Burden | SP17 | Spears, Gregory M
T1294 | PR | 197 | 09/13/13 | 995 | Payroll Burden | VE25 | Vega Arriaga, Jorge
T1295 | PR | 197 | 09/13/13 | 995 | Payroll Burden | VE25 | Vega Arriaga, Jorge
T1296 | PR | 198 | 09/13/13 | 995 | Payroll Burden | VE45 | Veley, Nathaniel S
T1297 | PR | 198 | 09/13/13 | 995 | Payroll Burden | VE45 | Veley, Nathaniel S
T1298 | PR | 198 | 09/13/13 | 995 | Payroll Burden | VE45 | Veley, Nathaniel S
T1299 | PR | 257 | 09/20/13 | 995 | Payroll Burden | AR70 | Arreola, Israel A
T1300 | PR | 267 | 09/20/13 | 995 | Payroll Burden | GE69 | Gerard, Jeffrey S
T1301 | PR | 267 | 09/20/13 | 995 | Payroll Burden | GE69 | Gerard, Jeffrey S
T1302 | PR | 268 | 09/20/13 | 995 | Payroll Burden | GO56 | Gonzalez Hernandez, Josue
T1303 | PR | 268 | 09/20/13 | 995 | Payroll Burden | GO56 | Gonzalez Hernandez, Josue
T1304 | PR | 270 | 09/20/13 | 995 | Payroll Burden | HO14 | Holmes, Anthony R
T1305 | PR | 270 | 09/20/13 | 995 | Payroll Burden | HO14 | Holmes, Anthony R
T1306 | PR | 270 | 09/20/13 | 995 | Payroll Burden | HO14 | Holmes, Anthony R
T1307 | PR | 277 | 09/20/13 | 995 | Payroll Burden | MO54 | Monico Brambila, Jesus S
T1308 | PR | 277 | 09/20/13 | 995 | Payroll Burden | MO54 | Monico Brambila, Jesus S
T1309 | PR | 280 | 09/20/13 | 995 | Payroll Burden | PA11 | Paco Leyva, Orlando
T1310 | PR | 280 | 09/20/13 | 995 | Payroll Burden | PA11 | Paco Leyva, Orlando
T1311 | PR | 280 | 09/20/13 | 995 | Payroll Burden | PA11 | Paco Leyva, Orlando
T1312 | PR | 280 | 09/20/13 | 995 | Payroll Burden | PA11 | Paco Leyva, Orlando
T1313 | PR | 281 | 09/20/13 | 995 | Payroll Burden | PA46 | Palma Vides, Hugo
T1314 | PR | 281 | 09/20/13 | 995 | Payroll Burden | PA46 | Palma Vides, Hugo
T1315 | PR | 281 | 09/20/13 | 995 | Payroll Burden | PA46 | Palma Vides, Hugo
T1316 | PR | 281 | 09/20/13 | 995 | Payroll Burden | PA46 | Palma Vides, Hugo
T1317 | PR | 282 | 09/20/13 | 995 | Payroll Burden | QU35 | Quintanilla, Esteban R
T1318 | PR | 285 | 09/20/13 | 995 | Payroll Burden | RE54 | Rendon Villasenor, Ismael
T1319 | PR | 288 | 09/20/13 | 995 | Payroll Burden | SA45 | Salazar, Hajdar L
T1320 | PR | 293 | 09/20/13 | 995 | Payroll Burden | SP17 | Spears, Gregory M
T1321 | PR | 293 | 09/20/13 | 995 | Payroll Burden | SP17 | Spears, Gregory M
T1322 | PR | 294 | 09/20/13 | 995 | Payroll Burden | VE25 | Vega Arriaga, Jorge
T1323 | PR | 294 | 09/20/13 | 995 | Payroll Burden | VE25 | Vega Arriaga, Jorge
T1324 | PR | 295 | 09/20/13 | 995 | Payroll Burden | VE45 | Veley, Nathaniel S
T1325 | PR | 295 | 09/20/13 | 995 | Payroll Burden | VE45 | Veley, Nathaniel S
T1326 | PR | 295 | 09/20/13 | 995 | Payroll Burden | VE45 | Veley, Nathaniel S
T1327 | PR | 295 | 09/20/13 | 995 | Payroll Burden | VE45 | Veley, Nathaniel S
T1328 | PR | 381 | 09/27/13 | 995 | Payroll Burden | AR70 | Arreola, Israel A
T1329 | PR | 382 | 09/27/13 | 995 | Payroll Burden | BA70 | Barnhart, Joseph N
T1330 | PR | 388 | 09/27/13 | 995 | Payroll Burden | CO71 | Cortes Mendiola, Victor H
T1331 | PR | 391 | 09/27/13 | 995 | Payroll Burden | GE69 | Gerard, Jeffrey S
T1332 | PR | 392 | 09/27/13 | 995 | Payroll Burden | GO56 | Gonzalez Hernandez, Josue
T1333 | PR | 392 | 09/27/13 | 995 | Payroll Burden | GO56 | Gonzalez Hernandez, Josue
T1334 | PR | 394 | 09/27/13 | 995 | Payroll Burden | HO14 | Holmes, Anthony R
T1335 | PR | 394 | 09/27/13 | 995 | Payroll Burden | HO14 | Holmes, Anthony R
T1336 | PR | 396 | 09/27/13 | 995 | Payroll Burden | LI49 | Lima Romero, Melvin A
T1337 | PR | 400 | 09/27/13 | 995 | Payroll Burden | MO54 | Monico Brambila, Jesus S
T1338 | PR | 400 | 09/27/13 | 995 | Payroll Burden | MO54 | Monico Brambila, Jesus S
T1339 | PR | 403 | 09/27/13 | 995 | Payroll Burden | PA11 | Paco Leyva, Orlando
T1340 | PR | 403 | 09/27/13 | 995 | Payroll Burden | PA11 | Paco Leyva, Orlando
T1341 | PR | 404 | 09/27/13 | 995 | Payroll Burden | PA46 | Palma Vides, Hugo
T1342 | PR | 404 | 09/27/13 | 995 | Payroll Burden | PA46 | Palma Vides, Hugo
T1343 | PR | 404 | 09/27/13 | 995 | Payroll Burden | PA46 | Palma Vides, Hugo
T1344 | PR | 405 | 09/27/13 | 995 | Payroll Burden | QU35 | Quintanilla, Esteban R
T1345 | PR | 408 | 09/27/13 | 995 | Payroll Burden | RE54 | Rendon Villasenor, Ismael
T1346 | PR | 413 | 09/27/13 | 995 | Payroll Burden | SE64 | Sepulveda Gonzalez, Alfredo
T1347 | PR | 416 | 09/27/13 | 995 | Payroll Burden | SP17 | Spears, Gregory M
T1348 | PR | 416 | 09/27/13 | 995 | Payroll Burden | SP17 | Spears, Gregory M
T1349 | PR | 417 | 09/27/13 | 995 | Payroll Burden | VE25 | Vega Arriaga, Jorge
T1350 | PR | 417 | 09/27/13 | 995 | Payroll Burden | VE25 | Vega Arriaga, Jorge
T1351 | PR | 6 | 10/04/13 | 995 | Payroll Burden | CA75 | Castro Hernandez, Carlos E
T1352 | PR | 7 | 10/04/13 | 995 | Payroll Burden | CA77 | Castro Hernandez, Jose A
T1353 | PR | 7 | 10/04/13 | 995 | Payroll Burden | CA77 | Castro Hernandez, Jose A
T1354 | PR | 8 | 10/04/13 | 995 | Payroll Burden | CH04 | Chavarria Lopez, Omar A
T1355 | PR | 8 | 10/04/13 | 995 | Payroll Burden | CH04 | Chavarria Lopez, Omar A
T1356 | PR | 13 | 10/04/13 | 995 | Payroll Burden | GE69 | Gerard, Jeffrey S
T1357 | PR | 14 | 10/04/13 | 995 | Payroll Burden | GO56 | Gonzalez Hernandez, Josue
T1358 | PR | 14 | 10/04/13 | 995 | Payroll Burden | GO56 | Gonzalez Hernandez, Josue
T1359 | PR | 22 | 10/04/13 | 995 | Payroll Burden | MO54 | Monico Brambila, Jesus S
T1360 | PR | 22 | 10/04/13 | 995 | Payroll Burden | MO54 | Monico Brambila, Jesus S
T1361 | PR | 25 | 10/04/13 | 995 | Payroll Burden | PA11 | Paco Leyva, Orlando
T1362 | PR | 26 | 10/04/13 | 995 | Payroll Burden | PA46 | Palma Vides, Hugo
T1363 | PR | 27 | 10/04/13 | 995 | Payroll Burden | QU35 | Quintanilla, Esteban R
T1364 | PR | 27 | 10/04/13 | 995 | Payroll Burden | QU35 | Quintanilla, Esteban R
T1365 | PR | 30 | 10/04/13 | 995 | Payroll Burden | RI84 | Rivera, Eli P
T1366 | PR | 30 | 10/04/13 | 995 | Payroll Burden | RI84 | Rivera, Eli P
T1367 | PR | 31 | 10/04/13 | 995 | Payroll Burden | RI87 | Rivera, Jorge A
T1368 | PR | 31 | 10/04/13 | 995 | Payroll Burden | RI87 | Rivera, Jorge A
T1369 | PR | 38 | 10/04/13 | 995 | Payroll Burden | SP17 | Spears, Gregory M
T1370 | PR | 38 | 10/04/13 | 995 | Payroll Burden | SP17 | Spears, Gregory M
T1371 | PR | 39 | 10/04/13 | 995 | Payroll Burden | VE25 | Vega Arriaga, Jorge
T1372 | PR | 39 | 10/04/13 | 995 | Payroll Burden | VE25 | Vega Arriaga, Jorge
T1373 | PR | 68 | 10/11/13 | 995 | Payroll Burden | BA70 | Barnhart, Joseph N
T1374 | PR | 71 | 10/11/13 | 995 | Payroll Burden | CA74 | Castaneda Martinez, Gustavo
T1375 | PR | 71 | 10/11/13 | 995 | Payroll Burden | CA74 | Castaneda Martinez, Gustavo
T1376 | PR | 72 | 10/11/13 | 995 | Payroll Burden | CA75 | Castro Hernandez, Carlos E
T1377 | PR | 73 | 10/11/13 | 995 | Payroll Burden | CA77 | Castro Hernandez, Jose A
T1378 | PR | 73 | 10/11/13 | 995 | Payroll Burden | CA77 | Castro Hernandez, Jose A
T1379 | PR | 74 | 10/11/13 | 995 | Payroll Burden | CH04 | Chavarria Lopez, Omar A
T1380 | PR | 74 | 10/11/13 | 995 | Payroll Burden | CH04 | Chavarria Lopez, Omar A
T1381 | PR | 76 | 10/11/13 | 995 | Payroll Burden | CO71 | Cortes Mendiola, Victor H
T1382 | PR | 79 | 10/11/13 | 995 | Payroll Burden | GE69 | Gerard, Jeffrey S
T1383 | PR | 80 | 10/11/13 | 995 | Payroll Burden | GO56 | Gonzalez Hernandez, Josue
T1384 | PR | 80 | 10/11/13 | 995 | Payroll Burden | GO56 | Gonzalez Hernandez, Josue
T1385 | PR | 84 | 10/11/13 | 995 | Payroll Burden | LI49 | Lima Romero, Melvin A
T1386 | PR | 84 | 10/11/13 | 995 | Payroll Burden | LI49 | Lima Romero, Melvin A
T1387 | PR | 88 | 10/11/13 | 995 | Payroll Burden | MO54 | Monico Brambila, Jesus S
T1388 | PR | 88 | 10/11/13 | 995 | Payroll Burden | MO54 | Monico Brambila, Jesus S
T1389 | PR | 91 | 10/11/13 | 995 | Payroll Burden | PA46 | Palma Vides, Hugo
T1390 | PR | 91 | 10/11/13 | 995 | Payroll Burden | PA46 | Palma Vides, Hugo
T1391 | PR | 91 | 10/11/13 | 995 | Payroll Burden | PA46 | Palma Vides, Hugo
T1392 | PR | 91 | 10/11/13 | 995 | Payroll Burden | PA46 | Palma Vides, Hugo
T1393 | PR | 92 | 10/11/13 | 995 | Payroll Burden | QU35 | Quintanilla, Esteban R
T1394 | PR | 92 | 10/11/13 | 995 | Payroll Burden | QU35 | Quintanilla, Esteban R
T1395 | PR | 94 | 10/11/13 | 995 | Payroll Burden | RE18 | Reed, Reuben H
T1396 | PR | 95 | 10/11/13 | 995 | Payroll Burden | RI84 | Rivera, Eli P
T1397 | PR | 95 | 10/11/13 | 995 | Payroll Burden | RI84 | Rivera, Eli P
T1398 | PR | 96 | 10/11/13 | 995 | Payroll Burden | RI87 | Rivera, Jorge A
T1399 | PR | 96 | 10/11/13 | 995 | Payroll Burden | RI87 | Rivera, Jorge A
T1400 | PR | 98 | 10/11/13 | 995 | Payroll Burden | SA45 | Salazar, Hajdar L
T1401 | PR | 100 | 10/11/13 | 995 | Payroll Burden | SE64 | Sepulveda Gonzalez, Alfredo
T1402 | PR | 103 | 10/11/13 | 995 | Payroll Burden | SP17 | Spears, Gregory M
T1403 | PR | 104 | 10/11/13 | 995 | Payroll Burden | VE25 | Vega Arriaga, Jorge
T1404 | PR | 104 | 10/11/13 | 995 | Payroll Burden | VE25 | Vega Arriaga, Jorge
T1405 | PR | 206 | 10/18/13 | 995 | Payroll Burden | CA74 | Castaneda Martinez, Gustavo
T1406 | PR | 208 | 10/18/13 | 995 | Payroll Burden | CA77 | Castro Hernandez, Jose A
T1407 | PR | 208 | 10/18/13 | 995 | Payroll Burden | CA77 | Castro Hernandez, Jose A
T1408 | PR | 209 | 10/18/13 | 995 | Payroll Burden | CH04 | Chavarria Lopez, Omar A
T1409 | PR | 209 | 10/18/13 | 995 | Payroll Burden | CH04 | Chavarria Lopez, Omar A
T1410 | PR | 211 | 10/18/13 | 995 | Payroll Burden | CO71 | Cortes Mendiola, Victor H
T1411 | PR | 211 | 10/18/13 | 995 | Payroll Burden | CO71 | Cortes Mendiola, Victor H
T1412 | PR | 214 | 10/18/13 | 995 | Payroll Burden | GE69 | Gerard, Jeffrey S
T1413 | PR | 214 | 10/18/13 | 995 | Payroll Burden | GE69 | Gerard, Jeffrey S
T1414 | PR | 215 | 10/18/13 | 995 | Payroll Burden | GO56 | Gonzalez Hernandez, Josue
T1415 | PR | 215 | 10/18/13 | 995 | Payroll Burden | GO56 | Gonzalez Hernandez, Josue
T1416 | PR | 219 | 10/18/13 | 995 | Payroll Burden | LI49 | Lima Romero, Melvin A
T1417 | PR | 219 | 10/18/13 | 995 | Payroll Burden | LI49 | Lima Romero, Melvin A
T1418 | PR | 223 | 10/18/13 | 995 | Payroll Burden | MO54 | Monico Brambila, Jesus S
T1419 | PR | 223 | 10/18/13 | 995 | Payroll Burden | MO54 | Monico Brambila, Jesus S
T1420 | PR | 226 | 10/18/13 | 995 | Payroll Burden | PA46 | Palma Vides, Hugo
T1421 | PR | 226 | 10/18/13 | 995 | Payroll Burden | PA46 | Palma Vides, Hugo
T1422 | PR | 227 | 10/18/13 | 995 | Payroll Burden | QU35 | Quintanilla, Esteban R
T1423 | PR | 227 | 10/18/13 | 995 | Payroll Burden | QU35 | Quintanilla, Esteban R
T1424 | PR | 230 | 10/18/13 | 995 | Payroll Burden | RI84 | Rivera, Eli P
T1425 | PR | 230 | 10/18/13 | 995 | Payroll Burden | RI84 | Rivera, Eli P
T1426 | PR | 231 | 10/18/13 | 995 | Payroll Burden | RI87 | Rivera, Jorge A
T1427 | PR | 231 | 10/18/13 | 995 | Payroll Burden | RI87 | Rivera, Jorge A
T1428 | PR | 235 | 10/18/13 | 995 | Payroll Burden | SE64 | Sepulveda Gonzalez, Alfredo
T1429 | PR | 235 | 10/18/13 | 995 | Payroll Burden | SE64 | Sepulveda Gonzalez, Alfredo
T1430 | PR | 239 | 10/18/13 | 995 | Payroll Burden | VE25 | Vega Arriaga, Jorge
T1431 | PR | 300 | 10/25/13 | 995 | Payroll Burden | CA74 | Castaneda Martinez, Gustavo
T1432 | PR | 300 | 10/25/13 | 995 | Payroll Burden | CA74 | Castaneda Martinez, Gustavo
T1433 | PR | 302 | 10/25/13 | 995 | Payroll Burden | CA77 | Castro Hernandez, Jose A
T1434 | PR | 302 | 10/25/13 | 995 | Payroll Burden | CA77 | Castro Hernandez, Jose A
T1435 | PR | 303 | 10/25/13 | 995 | Payroll Burden | CH04 | Chavarria Lopez, Omar A
T1436 | PR | 303 | 10/25/13 | 995 | Payroll Burden | CH04 | Chavarria Lopez, Omar A
T1437 | PR | 305 | 10/25/13 | 995 | Payroll Burden | CO71 | Cortes Mendiola, Victor H
T1438 | PR | 305 | 10/25/13 | 995 | Payroll Burden | CO71 | Cortes Mendiola, Victor H
T1439 | PR | 308 | 10/25/13 | 995 | Payroll Burden | GE69 | Gerard, Jeffrey S
T1440 | PR | 308 | 10/25/13 | 995 | Payroll Burden | GE69 | Gerard, Jeffrey S
T1441 | PR | 309 | 10/25/13 | 995 | Payroll Burden | GO56 | Gonzalez Hernandez, Josue
T1442 | PR | 309 | 10/25/13 | 995 | Payroll Burden | GO56 | Gonzalez Hernandez, Josue
T1443 | PR | 314 | 10/25/13 | 995 | Payroll Burden | LI49 | Lima Romero, Melvin A
T1444 | PR | 314 | 10/25/13 | 995 | Payroll Burden | LI49 | Lima Romero, Melvin A
T1445 | PR | 317 | 10/25/13 | 995 | Payroll Burden | MO54 | Monico Brambila, Jesus S
T1446 | PR | 317 | 10/25/13 | 995 | Payroll Burden | MO54 | Monico Brambila, Jesus S
T1447 | PR | 320 | 10/25/13 | 995 | Payroll Burden | PA46 | Palma Vides, Hugo
T1448 | PR | 322 | 10/25/13 | 995 | Payroll Burden | QU35 | Quintanilla, Esteban R
T1449 | PR | 322 | 10/25/13 | 995 | Payroll Burden | QU35 | Quintanilla, Esteban R
T1450 | PR | 325 | 10/25/13 | 995 | Payroll Burden | RI84 | Rivera, Eli P
T1451 | PR | 325 | 10/25/13 | 995 | Payroll Burden | RI84 | Rivera, Eli P
T1452 | PR | 326 | 10/25/13 | 995 | Payroll Burden | RI87 | Rivera, Jorge A
T1453 | PR | 326 | 10/25/13 | 995 | Payroll Burden | RI87 | Rivera, Jorge A
T1454 | PR | 330 | 10/25/13 | 995 | Payroll Burden | SE64 | Sepulveda Gonzalez, Alfredo
T1455 | PR | 330 | 10/25/13 | 995 | Payroll Burden | SE64 | Sepulveda Gonzalez, Alfredo
T1456 | PR | 334 | 10/25/13 | 995 | Payroll Burden | VE25 | Vega Arriaga, Jorge
T1457 | PR | 334 | 10/25/13 | 995 | Payroll Burden | VE25 | Vega Arriaga, Jorge
T1458 | PR | 399 | 10/31/13 | 995 | Payroll Burden | CA74 | Castaneda Martinez, Gustavo
T1459 | PR | 399 | 10/31/13 | 995 | Payroll Burden | CA74 | Castaneda Martinez, Gustavo
T1460 | PR | 401 | 10/31/13 | 995 | Payroll Burden | CA77 | Castro Hernandez, Jose A
T1461 | PR | 401 | 10/31/13 | 995 | Payroll Burden | CA77 | Castro Hernandez, Jose A
T1462 | PR | 402 | 10/31/13 | 995 | Payroll Burden | CH04 | Chavarria Lopez, Omar A
T1463 | PR | 404 | 10/31/13 | 995 | Payroll Burden | CO71 | Cortes Mendiola, Victor H
T1464 | PR | 404 | 10/31/13 | 995 | Payroll Burden | CO71 | Cortes Mendiola, Victor H
T1465 | PR | 407 | 10/31/13 | 995 | Payroll Burden | GE69 | Gerard, Jeffrey S
T1466 | PR | 407 | 10/31/13 | 995 | Payroll Burden | GE69 | Gerard, Jeffrey S
T1467 | PR | 408 | 10/31/13 | 995 | Payroll Burden | GO56 | Gonzalez Hernandez, Josue
T1468 | PR | 408 | 10/31/13 | 995 | Payroll Burden | GO56 | Gonzalez Hernandez, Josue
T1469 | PR | 414 | 10/31/13 | 995 | Payroll Burden | LI49 | Lima Romero, Melvin A
T1470 | PR | 414 | 10/31/13 | 995 | Payroll Burden | LI49 | Lima Romero, Melvin A
T1471 | PR | 415 | 10/31/13 | 995 | Payroll Burden | MC09 | McCabe, Thomas C
T1472 | PR | 415 | 10/31/13 | 995 | Payroll Burden | MC09 | McCabe, Thomas C
T1473 | PR | 417 | 10/31/13 | 995 | Payroll Burden | MO54 | Monico Brambila, Jesus S
T1474 | PR | 417 | 10/31/13 | 995 | Payroll Burden | MO54 | Monico Brambila, Jesus S
T1475 | PR | 420 | 10/31/13 | 995 | Payroll Burden | PA46 | Palma Vides, Hugo
T1476 | PR | 420 | 10/31/13 | 995 | Payroll Burden | PA46 | Palma Vides, Hugo
T1477 | PR | 422 | 10/31/13 | 995 | Payroll Burden | QU35 | Quintanilla, Esteban R
T1478 | PR | 425 | 10/31/13 | 995 | Payroll Burden | RI84 | Rivera, Eli P
T1479 | PR | 425 | 10/31/13 | 995 | Payroll Burden | RI84 | Rivera, Eli P
T1480 | PR | 426 | 10/31/13 | 995 | Payroll Burden | RI87 | Rivera, Jorge A
T1481 | PR | 430 | 10/31/13 | 995 | Payroll Burden | SE64 | Sepulveda Gonzalez, Alfredo
T1482 | PR | 430 | 10/31/13 | 995 | Payroll Burden | SE64 | Sepulveda Gonzalez, Alfredo
T1483 | PR | 434 | 10/31/13 | 995 | Payroll Burden | VE25 | Vega Arriaga, Jorge
T1484 | PR | 101 | 11/08/13 | 995 | Payroll Burden | CA74 | Castaneda Martinez, Gustavo
T1485 | PR | 101 | 11/08/13 | 995 | Payroll Burden | CA74 | Castaneda Martinez, Gustavo
T1486 | PR | 103 | 11/08/13 | 995 | Payroll Burden | CA77 | Castro Hernandez, Jose A
T1487 | PR | 103 | 11/08/13 | 995 | Payroll Burden | CA77 | Castro Hernandez, Jose A
T1488 | PR | 104 | 11/08/13 | 995 | Payroll Burden | CH04 | Chavarria Lopez, Omar A
T1489 | PR | 104 | 11/08/13 | 995 | Payroll Burden | CH04 | Chavarria Lopez, Omar A
T1490 | PR | 109 | 11/08/13 | 995 | Payroll Burden | GE69 | Gerard, Jeffrey S
T1491 | PR | 109 | 11/08/13 | 995 | Payroll Burden | GE69 | Gerard, Jeffrey S
T1492 | PR | 110 | 11/08/13 | 995 | Payroll Burden | GO56 | Gonzalez Hernandez, Josue
T1493 | PR | 110 | 11/08/13 | 995 | Payroll Burden | GO56 | Gonzalez Hernandez, Josue
T1494 | PR | 116 | 11/08/13 | 995 | Payroll Burden | LI49 | Lima Romero, Melvin A
T1495 | PR | 116 | 11/08/13 | 995 | Payroll Burden | LI49 | Lima Romero, Melvin A
T1496 | PR | 119 | 11/08/13 | 995 | Payroll Burden | MO54 | Monico Brambila, Jesus S
T1497 | PR | 119 | 11/08/13 | 995 | Payroll Burden | MO54 | Monico Brambila, Jesus S
T1498 | PR | 122 | 11/08/13 | 995 | Payroll Burden | PA46 | Palma Vides, Hugo
T1499 | PR | 122 | 11/08/13 | 995 | Payroll Burden | PA46 | Palma Vides, Hugo
T1500 | PR | 124 | 11/08/13 | 995 | Payroll Burden | QU35 | Quintanilla, Esteban R
T1501 | PR | 127 | 11/08/13 | 995 | Payroll Burden | RI84 | Rivera, Eli P
T1502 | PR | 127 | 11/08/13 | 995 | Payroll Burden | RI84 | Rivera, Eli P
T1503 | PR | 128 | 11/08/13 | 995 | Payroll Burden | RI87 | Rivera, Jorge A
T1504 | PR | 128 | 11/08/13 | 995 | Payroll Burden | RI87 | Rivera, Jorge A
T1505 | PR | 136 | 11/08/13 | 995 | Payroll Burden | VE25 | Vega Arriaga, Jorge
T1506 | PR | 137 | 11/08/13 | 995 | Payroll Burden | VE42 | Velasquez Cruz, Denis M
T1507 | PR | 188 | 11/15/13 | 995 | Payroll Burden | CA74 | Castaneda Martinez, Gustavo
T1508 | PR | 190 | 11/15/13 | 995 | Payroll Burden | CA77 | Castro Hernandez, Jose A
T1509 | PR | 190 | 11/15/13 | 995 | Payroll Burden | CA77 | Castro Hernandez, Jose A
T1510 | PR | 191 | 11/15/13 | 995 | Payroll Burden | CH04 | Chavarria Lopez, Omar A
T1511 | PR | 191 | 11/15/13 | 995 | Payroll Burden | CH04 | Chavarria Lopez, Omar A
T1512 | PR | 196 | 11/15/13 | 995 | Payroll Burden | GE69 | Gerard, Jeffrey S
T1513 | PR | 196 | 11/15/13 | 995 | Payroll Burden | GE69 | Gerard, Jeffrey S
T1514 | PR | 197 | 11/15/13 | 995 | Payroll Burden | GO56 | Gonzalez Hernandez, Josue
T1515 | PR | 197 | 11/15/13 | 995 | Payroll Burden | GO56 | Gonzalez Hernandez, Josue
T1516 | PR | 203 | 11/15/13 | 995 | Payroll Burden | LI49 | Lima Romero, Melvin A
T1517 | PR | 203 | 11/15/13 | 995 | Payroll Burden | LI49 | Lima Romero, Melvin A
T1518 | PR | 206 | 11/15/13 | 995 | Payroll Burden | MO54 | Monico Brambila, Jesus S
T1519 | PR | 206 | 11/15/13 | 995 | Payroll Burden | MO54 | Monico Brambila, Jesus S
T1520 | PR | 209 | 11/15/13 | 995 | Payroll Burden | PA46 | Palma Vides, Hugo
T1521 | PR | 209 | 11/15/13 | 995 | Payroll Burden | PA46 | Palma Vides, Hugo
T1522 | PR | 211 | 11/15/13 | 995 | Payroll Burden | QU35 | Quintanilla, Esteban R
T1523 | PR | 214 | 11/15/13 | 995 | Payroll Burden | RI84 | Rivera, Eli P
T1524 | PR | 214 | 11/15/13 | 995 | Payroll Burden | RI84 | Rivera, Eli P
T1525 | PR | 215 | 11/15/13 | 995 | Payroll Burden | RI87 | Rivera, Jorge A
T1526 | PR | 215 | 11/15/13 | 995 | Payroll Burden | RI87 | Rivera, Jorge A
T1527 | PR | 224 | 11/15/13 | 995 | Payroll Burden | VE42 | Velasquez Cruz, Denis M
T1528 | PR | 224 | 11/15/13 | 995 | Payroll Burden | VE42 | Velasquez Cruz, Denis M
T1529 | PR | 268 | 11/22/13 | 995 | Payroll Burden | CA74 | Castaneda Martinez, Gustavo
T1530 | PR | 268 | 11/22/13 | 995 | Payroll Burden | CA74 | Castaneda Martinez, Gustavo
T1531 | PR | 270 | 11/22/13 | 995 | Payroll Burden | CA77 | Castro Hernandez, Jose A
T1532 | PR | 270 | 11/22/13 | 995 | Payroll Burden | CA77 | Castro Hernandez, Jose A
T1533 | PR | 271 | 11/22/13 | 995 | Payroll Burden | CH04 | Chavarria Lopez, Omar A
T1534 | PR | 271 | 11/22/13 | 995 | Payroll Burden | CH04 | Chavarria Lopez, Omar A
T1535 | PR | 276 | 11/22/13 | 995 | Payroll Burden | GE69 | Gerard, Jeffrey S
T1536 | PR | 276 | 11/22/13 | 995 | Payroll Burden | GE69 | Gerard, Jeffrey S
T1537 | PR | 277 | 11/22/13 | 995 | Payroll Burden | GO56 | Gonzalez Hernandez, Josue
T1538 | PR | 277 | 11/22/13 | 995 | Payroll Burden | GO56 | Gonzalez Hernandez, Josue
T1539 | PR | 282 | 11/22/13 | 995 | Payroll Burden | LI49 | Lima Romero, Melvin A
T1540 | PR | 282 | 11/22/13 | 995 | Payroll Burden | LI49 | Lima Romero, Melvin A
T1541 | PR | 283 | 11/22/13 | 995 | Payroll Burden | LO55 | Lopez Martinez, Abimael
T1542 | PR | 285 | 11/22/13 | 995 | Payroll Burden | ME98 | Meza Fuentes, Erick A
T1543 | PR | 286 | 11/22/13 | 995 | Payroll Burden | MO54 | Monico Brambila, Jesus S
T1544 | PR | 286 | 11/22/13 | 995 | Payroll Burden | MO54 | Monico Brambila, Jesus S
T1545 | PR | 289 | 11/22/13 | 995 | Payroll Burden | PA46 | Palma Vides, Hugo
T1546 | PR | 289 | 11/22/13 | 995 | Payroll Burden | PA46 | Palma Vides, Hugo
T1547 | PR | 290 | 11/22/13 | 995 | Payroll Burden | QU35 | Quintanilla, Esteban R
T1548 | PR | 290 | 11/22/13 | 995 | Payroll Burden | QU35 | Quintanilla, Esteban R
T1549 | PR | 293 | 11/22/13 | 995 | Payroll Burden | RI84 | Rivera, Eli P
T1550 | PR | 293 | 11/22/13 | 995 | Payroll Burden | RI84 | Rivera, Eli P
T1551 | PR | 294 | 11/22/13 | 995 | Payroll Burden | RI87 | Rivera, Jorge A
T1552 | PR | 294 | 11/22/13 | 995 | Payroll Burden | RI87 | Rivera, Jorge A
T1553 | PR | 297 | 11/22/13 | 995 | Payroll Burden | SA54 | Sanders, Allen O
T1554 | PR | 304 | 11/22/13 | 995 | Payroll Burden | VE42 | Velasquez Cruz, Denis M
T1555 | PR | 304 | 11/22/13 | 995 | Payroll Burden | VE42 | Velasquez Cruz, Denis M
T1556 | PR | 391 | 11/27/13 | 995 | Payroll Burden | CA77 | Castro Hernandez, Jose A
T1557 | PR | 391 | 11/27/13 | 995 | Payroll Burden | CA77 | Castro Hernandez, Jose A
T1558 | PR | 392 | 11/27/13 | 995 | Payroll Burden | CH04 | Chavarria Lopez, Omar A
T1559 | PR | 392 | 11/27/13 | 995 | Payroll Burden | CH04 | Chavarria Lopez, Omar A
T1560 | PR | 392 | 11/27/13 | 995 | Payroll Burden | CH04 | Chavarria Lopez, Omar A
T1561 | PR | 392 | 11/27/13 | 995 | Payroll Burden | CH04 | Chavarria Lopez, Omar A
T1562 | PR | 397 | 11/27/13 | 995 | Payroll Burden | GE69 | Gerard, Jeffrey S
T1563 | PR | 397 | 11/27/13 | 995 | Payroll Burden | GE69 | Gerard, Jeffrey S
T1564 | PR | 397 | 11/27/13 | 995 | Payroll Burden | GE69 | Gerard, Jeffrey S
T1565 | PR | 398 | 11/27/13 | 995 | Payroll Burden | GO56 | Gonzalez Hernandez, Josue
T1566 | PR | 398 | 11/27/13 | 995 | Payroll Burden | GO56 | Gonzalez Hernandez, Josue
T1567 | PR | 398 | 11/27/13 | 995 | Payroll Burden | GO56 | Gonzalez Hernandez, Josue
T1568 | PR | 403 | 11/27/13 | 995 | Payroll Burden | LI49 | Lima Romero, Melvin A
T1569 | PR | 403 | 11/27/13 | 995 | Payroll Burden | LI49 | Lima Romero, Melvin A
T1570 | PR | 403 | 11/27/13 | 995 | Payroll Burden | LI49 | Lima Romero, Melvin A
T1571 | PR | 403 | 11/27/13 | 995 | Payroll Burden | LI49 | Lima Romero, Melvin A
T1572 | PR | 404 | 11/27/13 | 995 | Payroll Burden | LO55 | Lopez Martinez, Abimael
T1573 | PR | 404 | 11/27/13 | 995 | Payroll Burden | LO55 | Lopez Martinez, Abimael
T1574 | PR | 407 | 11/27/13 | 995 | Payroll Burden | MO54 | Monico Brambila, Jesus S
T1575 | PR | 407 | 11/27/13 | 995 | Payroll Burden | MO54 | Monico Brambila, Jesus S
T1576 | PR | 407 | 11/27/13 | 995 | Payroll Burden | MO54 | Monico Brambila, Jesus S
T1577 | PR | 407 | 11/27/13 | 995 | Payroll Burden | MO54 | Monico Brambila, Jesus S
T1578 | PR | 410 | 11/27/13 | 995 | Payroll Burden | PA46 | Palma Vides, Hugo
T1579 | PR | 410 | 11/27/13 | 995 | Payroll Burden | PA46 | Palma Vides, Hugo
T1580 | PR | 410 | 11/27/13 | 995 | Payroll Burden | PA46 | Palma Vides, Hugo
T1581 | PR | 410 | 11/27/13 | 995 | Payroll Burden | PA46 | Palma Vides, Hugo
T1582 | PR | 411 | 11/27/13 | 995 | Payroll Burden | QU35 | Quintanilla, Esteban R
T1583 | PR | 411 | 11/27/13 | 995 | Payroll Burden | QU35 | Quintanilla, Esteban R
T1584 | PR | 411 | 11/27/13 | 995 | Payroll Burden | QU35 | Quintanilla, Esteban R
T1585 | PR | 411 | 11/27/13 | 995 | Payroll Burden | QU35 | Quintanilla, Esteban R
T1586 | PR | 414 | 11/27/13 | 995 | Payroll Burden | RI84 | Rivera, Eli P
T1587 | PR | 414 | 11/27/13 | 995 | Payroll Burden | RI84 | Rivera, Eli P
T1588 | PR | 414 | 11/27/13 | 995 | Payroll Burden | RI84 | Rivera, Eli P
T1589 | PR | 415 | 11/27/13 | 995 | Payroll Burden | RI87 | Rivera, Jorge A
T1590 | PR | 415 | 11/27/13 | 995 | Payroll Burden | RI87 | Rivera, Jorge A
T1591 | PR | 438 | 11/30/13 | 995 | Payroll Burden | AG52 | Agustin Rodriguez, Ezequiel
T1592 | PR | 446 | 11/30/13 | 995 | Payroll Burden | CA77 | Castro Hernandez, Jose A
T1593 | PR | 447 | 11/30/13 | 995 | Payroll Burden | CH04 | Chavarria Lopez, Omar A
T1594 | PR | 447 | 11/30/13 | 995 | Payroll Burden | CH04 | Chavarria Lopez, Omar A
T1595 | PR | 452 | 11/30/13 | 995 | Payroll Burden | GE69 | Gerard, Jeffrey S
T1596 | PR | 453 | 11/30/13 | 995 | Payroll Burden | GO56 | Gonzalez Hernandez, Josue
T1597 | PR | 458 | 11/30/13 | 995 | Payroll Burden | LI49 | Lima Romero, Melvin A
T1598 | PR | 459 | 11/30/13 | 995 | Payroll Burden | LO55 | Lopez Martinez, Abimael
T1599 | PR | 462 | 11/30/13 | 995 | Payroll Burden | MO54 | Monico Brambila, Jesus S
T1600 | PR | 465 | 11/30/13 | 995 | Payroll Burden | PA46 | Palma Vides, Hugo
T1601 | PR | 466 | 11/30/13 | 995 | Payroll Burden | QU35 | Quintanilla, Esteban R
T1602 | PR | 466 | 11/30/13 | 995 | Payroll Burden | QU35 | Quintanilla, Esteban R
T1603 | PR | 468 | 11/30/13 | 995 | Payroll Burden | RI84 | Rivera, Eli P
T1604 | PR | 469 | 11/30/13 | 995 | Payroll Burden | RI87 | Rivera, Jorge A
T1605 | PR | 48 | 12/13/13 | 995 | Payroll Burden | AG52 | Agustin Rodriguez, Ezequiel
T1606 | PR | 48 | 12/13/13 | 995 | Payroll Burden | AG52 | Agustin Rodriguez, Ezequiel
T1607 | PR | 55 | 12/13/13 | 995 | Payroll Burden | CA75 | Castro Hernandez, Carlos E
T1608 | PR | 56 | 12/13/13 | 995 | Payroll Burden | CA77 | Castro Hernandez, Jose A
T1609 | PR | 56 | 12/13/13 | 995 | Payroll Burden | CA77 | Castro Hernandez, Jose A
T1610 | PR | 56 | 12/13/13 | 995 | Payroll Burden | CA77 | Castro Hernandez, Jose A
T1611 | PR | 57 | 12/13/13 | 995 | Payroll Burden | CH04 | Chavarria Lopez, Omar A
T1612 | PR | 57 | 12/13/13 | 995 | Payroll Burden | CH04 | Chavarria Lopez, Omar A
T1613 | PR | 57 | 12/13/13 | 995 | Payroll Burden | CH04 | Chavarria Lopez, Omar A
T1614 | PR | 57 | 12/13/13 | 995 | Payroll Burden | CH04 | Chavarria Lopez, Omar A
T1615 | PR | 61 | 12/13/13 | 995 | Payroll Burden | GE69 | Gerard, Jeffrey S
T1616 | PR | 62 | 12/13/13 | 995 | Payroll Burden | GO56 | Gonzalez Hernandez, Josue
T1617 | PR | 62 | 12/13/13 | 995 | Payroll Burden | GO56 | Gonzalez Hernandez, Josue
T1618 | PR | 62 | 12/13/13 | 995 | Payroll Burden | GO56 | Gonzalez Hernandez, Josue
T1619 | PR | 62 | 12/13/13 | 995 | Payroll Burden | GO56 | Gonzalez Hernandez, Josue
T1620 | PR | 67 | 12/13/13 | 995 | Payroll Burden | LI49 | Lima Romero, Melvin A
T1621 | PR | 67 | 12/13/13 | 995 | Payroll Burden | LI49 | Lima Romero, Melvin A
T1622 | PR | 67 | 12/13/13 | 995 | Payroll Burden | LI49 | Lima Romero, Melvin A
T1623 | PR | 68 | 12/13/13 | 995 | Payroll Burden | LO55 | Lopez Martinez, Abimael
T1624 | PR | 68 | 12/13/13 | 995 | Payroll Burden | LO55 | Lopez Martinez, Abimael
T1625 | PR | 71 | 12/13/13 | 995 | Payroll Burden | MO54 | Monico Brambila, Jesus S
T1626 | PR | 71 | 12/13/13 | 995 | Payroll Burden | MO54 | Monico Brambila, Jesus S
T1627 | PR | 71 | 12/13/13 | 995 | Payroll Burden | MO54 | Monico Brambila, Jesus S
T1628 | PR | 74 | 12/13/13 | 995 | Payroll Burden | PA46 | Palma Vides, Hugo
T1629 | PR | 74 | 12/13/13 | 995 | Payroll Burden | PA46 | Palma Vides, Hugo
T1630 | PR | 74 | 12/13/13 | 995 | Payroll Burden | PA46 | Palma Vides, Hugo
T1631 | PR | 75 | 12/13/13 | 995 | Payroll Burden | QU35 | Quintanilla, Esteban R
T1632 | PR | 75 | 12/13/13 | 995 | Payroll Burden | QU35 | Quintanilla, Esteban R
T1633 | PR | 75 | 12/13/13 | 995 | Payroll Burden | QU35 | Quintanilla, Esteban R
T1634 | PR | 75 | 12/13/13 | 995 | Payroll Burden | QU35 | Quintanilla, Esteban R
T1635 | PR | 77 | 12/13/13 | 995 | Payroll Burden | RI84 | Rivera, Eli P
T1636 | PR | 77 | 12/13/13 | 995 | Payroll Burden | RI84 | Rivera, Eli P
T1637 | PR | 77 | 12/13/13 | 995 | Payroll Burden | RI84 | Rivera, Eli P
T1638 | PR | 78 | 12/13/13 | 995 | Payroll Burden | RI87 | Rivera, Jorge A
T1639 | PR | 78 | 12/13/13 | 995 | Payroll Burden | RI87 | Rivera, Jorge A
T1640 | PR | 78 | 12/13/13 | 995 | Payroll Burden | RI87 | Rivera, Jorge A
T1641 | PR | 78 | 12/13/13 | 995 | Payroll Burden | RI87 | Rivera, Jorge A
T1642 | PR | 231 | 12/20/13 | 995 | Payroll Burden | AG52 | Agustin Rodriguez, Ezequiel
T1643 | PR | 231 | 12/20/13 | 995 | Payroll Burden | AG52 | Agustin Rodriguez, Ezequiel
T1644 | PR | 238 | 12/20/13 | 995 | Payroll Burden | CA75 | Castro Hernandez, Carlos E
T1645 | PR | 238 | 12/20/13 | 995 | Payroll Burden | CA75 | Castro Hernandez, Carlos E
T1646 | PR | 238 | 12/20/13 | 995 | Payroll Burden | CA75 | Castro Hernandez, Carlos E
T1647 | PR | 238 | 12/20/13 | 995 | Payroll Burden | CA75 | Castro Hernandez, Carlos E
T1648 | PR | 239 | 12/20/13 | 995 | Payroll Burden | CA77 | Castro Hernandez, Jose A
T1649 | PR | 239 | 12/20/13 | 995 | Payroll Burden | CA77 | Castro Hernandez, Jose A
T1650 | PR | 240 | 12/20/13 | 995 | Payroll Burden | CH04 | Chavarria Lopez, Omar A
T1651 | PR | 240 | 12/20/13 | 995 | Payroll Burden | CH04 | Chavarria Lopez, Omar A
T1652 | PR | 245 | 12/20/13 | 995 | Payroll Burden | GE69 | Gerard, Jeffrey S
T1653 | PR | 246 | 12/20/13 | 995 | Payroll Burden | GO56 | Gonzalez Hernandez, Josue
T1654 | PR | 246 | 12/20/13 | 995 | Payroll Burden | GO56 | Gonzalez Hernandez, Josue
T1655 | PR | 251 | 12/20/13 | 995 | Payroll Burden | LI49 | Lima Romero, Melvin A
T1656 | PR | 251 | 12/20/13 | 995 | Payroll Burden | LI49 | Lima Romero, Melvin A
T1657 | PR | 252 | 12/20/13 | 995 | Payroll Burden | LO55 | Lopez Martinez, Abimael
T1658 | PR | 252 | 12/20/13 | 995 | Payroll Burden | LO55 | Lopez Martinez, Abimael
T1659 | PR | 255 | 12/20/13 | 995 | Payroll Burden | MO54 | Monico Brambila, Jesus S
T1660 | PR | 255 | 12/20/13 | 995 | Payroll Burden | MO54 | Monico Brambila, Jesus S
T1661 | PR | 258 | 12/20/13 | 995 | Payroll Burden | PA46 | Palma Vides, Hugo
T1662 | PR | 258 | 12/20/13 | 995 | Payroll Burden | PA46 | Palma Vides, Hugo
T1663 | PR | 259 | 12/20/13 | 995 | Payroll Burden | QU35 | Quintanilla, Esteban R
T1664 | PR | 259 | 12/20/13 | 995 | Payroll Burden | QU35 | Quintanilla, Esteban R
T1665 | PR | 261 | 12/20/13 | 995 | Payroll Burden | RI84 | Rivera, Eli P
T1666 | PR | 261 | 12/20/13 | 995 | Payroll Burden | RI84 | Rivera, Eli P
T1667 | PR | 261 | 12/20/13 | 995 | Payroll Burden | RI84 | Rivera, Eli P
T1668 | PR | 262 | 12/20/13 | 995 | Payroll Burden | RI87 | Rivera, Jorge A
T1669 | PR | 262 | 12/20/13 | 995 | Payroll Burden | RI87 | Rivera, Jorge A
T1670 | PR | 262 | 12/20/13 | 995 | Payroll Burden | RI87 | Rivera, Jorge A
T1671 | PR | 262 | 12/20/13 | 995 | Payroll Burden | RI87 | Rivera, Jorge A
T1672 | PR | 265 | 12/20/13 | 995 | Payroll Burden | SA52 | Sanchez Garcia, Adelaido
T1673 | PR | 327 | 12/27/13 | 995 | Payroll Burden | AG52 | Agustin Rodriguez, Ezequiel
T1674 | PR | 334 | 12/27/13 | 995 | Payroll Burden | CA75 | Castro Hernandez, Carlos E
T1675 | PR | 335 | 12/27/13 | 995 | Payroll Burden | CA77 | Castro Hernandez, Jose A
T1676 | PR | 336 | 12/27/13 | 995 | Payroll Burden | CH04 | Chavarria Lopez, Omar A
T1677 | PR | 341 | 12/27/13 | 995 | Payroll Burden | GE69 | Gerard, Jeffrey S
T1678 | PR | 342 | 12/27/13 | 995 | Payroll Burden | GO56 | Gonzalez Hernandez, Josue
T1679 | PR | 347 | 12/27/13 | 995 | Payroll Burden | LI49 | Lima Romero, Melvin A
T1680 | PR | 348 | 12/27/13 | 995 | Payroll Burden | LO55 | Lopez Martinez, Abimael
T1681 | PR | 351 | 12/27/13 | 995 | Payroll Burden | MO54 | Monico Brambila, Jesus S
T1682 | PR | 354 | 12/27/13 | 995 | Payroll Burden | PA46 | Palma Vides, Hugo
T1683 | PR | 355 | 12/27/13 | 995 | Payroll Burden | QU35 | Quintanilla, Esteban R
T1684 | PR | 356 | 12/27/13 | 995 | Payroll Burden | RA54 | Ramos Garcia, Jose M
T1685 | PR | 358 | 12/27/13 | 995 | Payroll Burden | RI84 | Rivera, Eli P
T1686 | PR | 358 | 12/27/13 | 995 | Payroll Burden | RI84 | Rivera, Eli P
T1687 | PR | 359 | 12/27/13 | 995 | Payroll Burden | RI87 | Rivera, Jorge A
T1688 | PR | 362 | 12/27/13 | 995 | Payroll Burden | SA52 | Sanchez Garcia, Adelaido
T1689 | PR | 8 | 01/03/14 | 995 | Payroll Burden | CA75 | Castro Hernandez, Carlos E
T1690 | PR | 8 | 01/03/14 | 995 | Payroll Burden | CA75 | Castro Hernandez, Carlos E
T1691 | PR | 9 | 01/03/14 | 995 | Payroll Burden | CA77 | Castro Hernandez, Jose A
T1692 | PR | 9 | 01/03/14 | 995 | Payroll Burden | CA77 | Castro Hernandez, Jose A
T1693 | PR | 10 | 01/03/14 | 995 | Payroll Burden | CH04 | Chavarria Lopez, Omar A
T1694 | PR | 10 | 01/03/14 | 995 | Payroll Burden | CH04 | Chavarria Lopez, Omar A
T1695 | PR | 16 | 01/03/14 | 995 | Payroll Burden | GO56 | Gonzalez Hernandez, Josue
T1696 | PR | 16 | 01/03/14 | 995 | Payroll Burden | GO56 | Gonzalez Hernandez, Josue
T1697 | PR | 21 | 01/03/14 | 995 | Payroll Burden | LI49 | Lima Romero, Melvin A
T1698 | PR | 22 | 01/03/14 | 995 | Payroll Burden | LO55 | Lopez Martinez, Abimael
T1699 | PR | 22 | 01/03/14 | 995 | Payroll Burden | LO55 | Lopez Martinez, Abimael
T1700 | PR | 25 | 01/03/14 | 995 | Payroll Burden | MO54 | Monico Brambila, Jesus S
T1701 | PR | 25 | 01/03/14 | 995 | Payroll Burden | MO54 | Monico Brambila, Jesus S
T1702 | PR | 28 | 01/03/14 | 995 | Payroll Burden | PA46 | Palma Vides, Hugo
T1703 | PR | 28 | 01/03/14 | 995 | Payroll Burden | PA46 | Palma Vides, Hugo
T1704 | PR | 29 | 01/03/14 | 995 | Payroll Burden | QU35 | Quintanilla, Esteban R
T1705 | PR | 29 | 01/03/14 | 995 | Payroll Burden | QU35 | Quintanilla, Esteban R
T1706 | PR | 30 | 01/03/14 | 995 | Payroll Burden | RA54 | Ramos Garcia, Jose M
T1707 | PR | 30 | 01/03/14 | 995 | Payroll Burden | RA54 | Ramos Garcia, Jose M
T1708 | PR | 32 | 01/03/14 | 995 | Payroll Burden | RI84 | Rivera, Eli P
T1709 | PR | 32 | 01/03/14 | 995 | Payroll Burden | RI84 | Rivera, Eli P
T1710 | PR | 33 | 01/03/14 | 995 | Payroll Burden | RI87 | Rivera, Jorge A
T1711 | PR | 36 | 01/03/14 | 995 | Payroll Burden | SA52 | Sanchez Garcia, Adelaido
T1712 | PR | 134 | 01/10/14 | 995 | Payroll Burden | AG52 | Agustin Rodriguez, Ezequiel
T1713 | PR | 139 | 01/10/14 | 995 | Payroll Burden | CA73 | Castaneda Juarez, Gustavo
T1714 | PR | 141 | 01/10/14 | 995 | Payroll Burden | CA75 | Castro Hernandez, Carlos E
T1715 | PR | 141 | 01/10/14 | 995 | Payroll Burden | CA75 | Castro Hernandez, Carlos E
T1716 | PR | 142 | 01/10/14 | 995 | Payroll Burden | CA77 | Castro Hernandez, Jose A
T1717 | PR | 142 | 01/10/14 | 995 | Payroll Burden | CA77 | Castro Hernandez, Jose A
T1718 | PR | 143 | 01/10/14 | 995 | Payroll Burden | CH04 | Chavarria Lopez, Omar A
T1719 | PR | 143 | 01/10/14 | 995 | Payroll Burden | CH04 | Chavarria Lopez, Omar A
T1720 | PR | 148 | 01/10/14 | 995 | Payroll Burden | GE69 | Gerard, Jeffrey S
T1721 | PR | 149 | 01/10/14 | 995 | Payroll Burden | GO56 | Gonzalez Hernandez, Josue
T1722 | PR | 154 | 01/10/14 | 995 | Payroll Burden | LI49 | Lima Romero, Melvin A
T1723 | PR | 155 | 01/10/14 | 995 | Payroll Burden | LO55 | Lopez Martinez, Abimael
T1724 | PR | 161 | 01/10/14 | 995 | Payroll Burden | PA46 | Palma Vides, Hugo
T1725 | PR | 161 | 01/10/14 | 995 | Payroll Burden | PA46 | Palma Vides, Hugo
T1726 | PR | 162 | 01/10/14 | 995 | Payroll Burden | QU35 | Quintanilla, Esteban R
T1727 | PR | 162 | 01/10/14 | 995 | Payroll Burden | QU35 | Quintanilla, Esteban R
T1728 | PR | 163 | 01/10/14 | 995 | Payroll Burden | RA54 | Ramos Garcia, Jose M
T1729 | PR | 165 | 01/10/14 | 995 | Payroll Burden | RI84 | Rivera, Eli P
T1730 | PR | 165 | 01/10/14 | 995 | Payroll Burden | RI84 | Rivera, Eli P
T1731 | PR | 166 | 01/10/14 | 995 | Payroll Burden | RI87 | Rivera, Jorge A
T1732 | PR | 169 | 01/10/14 | 995 | Payroll Burden | SA52 | Sanchez Garcia, Adelaido
T1733 | PR | 175 | 01/10/14 | 995 | Payroll Burden | VE25 | Vega Arriaga, Jorge
T1734 | PR | 287 | 01/17/14 | 995 | Payroll Burden | CA77 | Castro Hernandez, Jose A
T1735 | PR | 288 | 01/17/14 | 995 | Payroll Burden | CH04 | Chavarria Lopez, Omar A
T1736 | PR | 293 | 01/17/14 | 995 | Payroll Burden | GE69 | Gerard, Jeffrey S
T1737 | PR | 294 | 01/17/14 | 995 | Payroll Burden | GO56 | Gonzalez Hernandez, Josue
T1738 | PR | 299 | 01/17/14 | 995 | Payroll Burden | LI49 | Lima Romero, Melvin A
T1739 | PR | 302 | 01/17/14 | 995 | Payroll Burden | ME98 | Meza Fuentes, Erick A
T1740 | PR | 306 | 01/17/14 | 995 | Payroll Burden | PA46 | Palma Vides, Hugo
T1741 | PR | 307 | 01/17/14 | 995 | Payroll Burden | QU35 | Quintanilla, Esteban R
T1742 | PR | 308 | 01/17/14 | 995 | Payroll Burden | RA54 | Ramos Garcia, Jose M
T1743 | PR | 310 | 01/17/14 | 995 | Payroll Burden | RI84 | Rivera, Eli P
T1744 | PR | 314 | 01/17/14 | 995 | Payroll Burden | SA52 | Sanchez Garcia, Adelaido
T1745 | PR | 315 | 01/17/14 | 995 | Payroll Burden | SA54 | Sanders, Allen O
T1746 | PR | 318 | 01/17/14 | 995 | Payroll Burden | SO79 | Soto Serna, Cesar E
T1747 | PR | 320 | 01/17/14 | 995 | Payroll Burden | VA86 | Vaughan, Tyler J
T1748 | PR | 324 | 01/17/14 | 995 | Payroll Burden | WA35 | Waites, Thaddeus Z
T1749 | PR | 377 | 01/24/14 | 995 | Payroll Burden | CA77 | Castro Hernandez, Jose A
T1750 | PR | 378 | 01/24/14 | 995 | Payroll Burden | CH04 | Chavarria Lopez, Omar A
T1751 | PR | 383 | 01/24/14 | 995 | Payroll Burden | GE69 | Gerard, Jeffrey S
T1752 | PR | 384 | 01/24/14 | 995 | Payroll Burden | GO56 | Gonzalez Hernandez, Josue
T1753 | PR | 389 | 01/24/14 | 995 | Payroll Burden | LI49 | Lima Romero, Melvin A
T1754 | PR | 392 | 01/24/14 | 995 | Payroll Burden | ME98 | Meza Fuentes, Erick A
T1755 | PR | 397 | 01/24/14 | 995 | Payroll Burden | QU35 | Quintanilla, Esteban R
T1756 | PR | 399 | 01/24/14 | 995 | Payroll Burden | RA54 | Ramos Garcia, Jose M
T1757 | PR | 401 | 01/24/14 | 995 | Payroll Burden | RI84 | Rivera, Eli P
T1758 | PR | 406 | 01/24/14 | 995 | Payroll Burden | SA54 | Sanders, Allen O
T1759 | PR | 408 | 01/24/14 | 995 | Payroll Burden | SO78 | Soto Cruz, Jovani
T1760 | PR | 409 | 01/24/14 | 995 | Payroll Burden | SO79 | Soto Serna, Cesar E
T1761 | PR | 411 | 01/24/14 | 995 | Payroll Burden | VA86 | Vaughan, Tyler J
T1762 | PR | 415 | 01/24/14 | 995 | Payroll Burden | WA35 | Waites, Thaddeus Z
T1763 | PR | 575 | 01/31/14 | 995 | Payroll Burden | CA77 | Castro Hernandez, Jose A
T1764 | PR | 575 | 01/31/14 | 995 | Payroll Burden | CA77 | Castro Hernandez, Jose A
T1765 | PR | 576 | 01/31/14 | 995 | Payroll Burden | CH04 | Chavarria Lopez, Omar A
T1766 | PR | 581 | 01/31/14 | 995 | Payroll Burden | GE69 | Gerard, Jeffrey S
T1767 | PR | 581 | 01/31/14 | 995 | Payroll Burden | GE69 | Gerard, Jeffrey S
T1768 | PR | 582 | 01/31/14 | 995 | Payroll Burden | GO56 | Gonzalez Hernandez, Josue
T1769 | PR | 587 | 01/31/14 | 995 | Payroll Burden | LI49 | Lima Romero, Melvin A
T1770 | PR | 590 | 01/31/14 | 995 | Payroll Burden | ME98 | Meza Fuentes, Erick A
T1771 | PR | 595 | 01/31/14 | 995 | Payroll Burden | QU35 | Quintanilla, Esteban R
T1772 | PR | 595 | 01/31/14 | 995 | Payroll Burden | QU35 | Quintanilla, Esteban R
T1773 | PR | 595 | 01/31/14 | 995 | Payroll Burden | QU35 | Quintanilla, Esteban R
T1774 | PR | 597 | 01/31/14 | 995 | Payroll Burden | RA54 | Ramos Garcia, Jose M
T1775 | PR | 599 | 01/31/14 | 995 | Payroll Burden | RI84 | Rivera, Eli P
T1776 | PR | 604 | 01/31/14 | 995 | Payroll Burden | SA54 | Sanders, Allen O
T1777 | PR | 606 | 01/31/14 | 995 | Payroll Burden | SO78 | Soto Cruz, Jovani
T1778 | PR | 607 | 01/31/14 | 995 | Payroll Burden | SO79 | Soto Serna, Cesar E
T1779 | PR | 609 | 01/31/14 | 995 | Payroll Burden | VA86 | Vaughan, Tyler J
T1780 | PR | 613 | 01/31/14 | 995 | Payroll Burden | WA35 | Waites, Thaddeus Z
T1781 | PR | 25 | 02/07/14 | 995 | Payroll Burden | CA77 | Castro Hernandez, Jose A
T1782 | PR | 26 | 02/07/14 | 995 | Payroll Burden | CH04 | Chavarria Lopez, Omar A
T1783 | PR | 31 | 02/07/14 | 995 | Payroll Burden | GE69 | Gerard, Jeffrey S
T1784 | PR | 31 | 02/07/14 | 995 | Payroll Burden | GE69 | Gerard, Jeffrey S
T1785 | PR | 32 | 02/07/14 | 995 | Payroll Burden | GO56 | Gonzalez Hernandez, Josue
T1786 | PR | 37 | 02/07/14 | 995 | Payroll Burden | LI49 | Lima Romero, Melvin A
T1787 | PR | 39 | 02/07/14 | 995 | Payroll Burden | MC09 | McCabe, Thomas C
T1788 | PR | 40 | 02/07/14 | 995 | Payroll Burden | ME98 | Meza Fuentes, Erick A
T1789 | PR | 45 | 02/07/14 | 995 | Payroll Burden | QU35 | Quintanilla, Esteban R
T1790 | PR | 45 | 02/07/14 | 995 | Payroll Burden | QU35 | Quintanilla, Esteban R
T1791 | PR | 47 | 02/07/14 | 995 | Payroll Burden | RA54 | Ramos Garcia, Jose M
T1792 | PR | 47 | 02/07/14 | 995 | Payroll Burden | RA54 | Ramos Garcia, Jose M
T1793 | PR | 49 | 02/07/14 | 995 | Payroll Burden | RI84 | Rivera, Eli P
T1794 | PR | 49 | 02/07/14 | 995 | Payroll Burden | RI84 | Rivera, Eli P
T1795 | PR | 54 | 02/07/14 | 995 | Payroll Burden | SA54 | Sanders, Allen O
T1796 | PR | 56 | 02/07/14 | 995 | Payroll Burden | SO78 | Soto Cruz, Jovani
T1797 | PR | 57 | 02/07/14 | 995 | Payroll Burden | SO79 | Soto Serna, Cesar E
T1798 | PR | 63 | 02/07/14 | 995 | Payroll Burden | WA35 | Waites, Thaddeus Z
T1799 | PR | 63 | 02/07/14 | 995 | Payroll Burden | WA35 | Waites, Thaddeus Z
T1800 | PR | 168 | 02/14/14 | 995 | Payroll Burden | CA72 | Castaneda Juarez, Edgar D
T1801 | PR | 173 | 02/14/14 | 995 | Payroll Burden | CH04 | Chavarria Lopez, Omar A
T1802 | PR | 178 | 02/14/14 | 995 | Payroll Burden | GE69 | Gerard, Jeffrey S
T1803 | PR | 178 | 02/14/14 | 995 | Payroll Burden | GE69 | Gerard, Jeffrey S
T1804 | PR | 179 | 02/14/14 | 995 | Payroll Burden | GO56 | Gonzalez Hernandez, Josue
T1805 | PR | 179 | 02/14/14 | 995 | Payroll Burden | GO56 | Gonzalez Hernandez, Josue
T1806 | PR | 184 | 02/14/14 | 995 | Payroll Burden | LI49 | Lima Romero, Melvin A
T1807 | PR | 184 | 02/14/14 | 995 | Payroll Burden | LI49 | Lima Romero, Melvin A
T1808 | PR | 186 | 02/14/14 | 995 | Payroll Burden | MC09 | McCabe, Thomas C
T1809 | PR | 187 | 02/14/14 | 995 | Payroll Burden | ME98 | Meza Fuentes, Erick A
T1810 | PR | 192 | 02/14/14 | 995 | Payroll Burden | QU35 | Quintanilla, Esteban R
T1811 | PR | 195 | 02/14/14 | 995 | Payroll Burden | RA54 | Ramos Garcia, Jose M
T1812 | PR | 195 | 02/14/14 | 995 | Payroll Burden | RA54 | Ramos Garcia, Jose M
T1813 | PR | 202 | 02/14/14 | 995 | Payroll Burden | SA54 | Sanders, Allen O
T1814 | PR | 204 | 02/14/14 | 995 | Payroll Burden | SO78 | Soto Cruz, Jovani
T1815 | PR | 211 | 02/14/14 | 995 | Payroll Burden | WA35 | Waites, Thaddeus Z
T1816 | PR | 278 | 02/21/14 | 995 | Payroll Burden | CA72 | Castaneda Juarez, Edgar D
T1817 | PR | 286 | 02/21/14 | 995 | Payroll Burden | GA70 | Garcia, Jordan X
T1818 | PR | 287 | 02/21/14 | 995 | Payroll Burden | GE69 | Gerard, Jeffrey S
T1819 | PR | 287 | 02/21/14 | 995 | Payroll Burden | GE69 | Gerard, Jeffrey S
T1820 | PR | 288 | 02/21/14 | 995 | Payroll Burden | GO56 | Gonzalez Hernandez, Josue
T1821 | PR | 288 | 02/21/14 | 995 | Payroll Burden | GO56 | Gonzalez Hernandez, Josue
T1822 | PR | 293 | 02/21/14 | 995 | Payroll Burden | LI49 | Lima Romero, Melvin A
T1823 | PR | 293 | 02/21/14 | 995 | Payroll Burden | LI49 | Lima Romero, Melvin A
T1824 | PR | 296 | 02/21/14 | 995 | Payroll Burden | ME98 | Meza Fuentes, Erick A
T1825 | PR | 301 | 02/21/14 | 995 | Payroll Burden | QU35 | Quintanilla, Esteban R
T1826 | PR | 304 | 02/21/14 | 995 | Payroll Burden | RA54 | Ramos Garcia, Jose M
T1827 | PR | 304 | 02/21/14 | 995 | Payroll Burden | RA54 | Ramos Garcia, Jose M
T1828 | PR | 311 | 02/21/14 | 995 | Payroll Burden | SA54 | Sanders, Allen O
T1829 | PR | 320 | 02/21/14 | 995 | Payroll Burden | WA35 | Waites, Thaddeus Z
T1830 | PR | 320 | 02/21/14 | 995 | Payroll Burden | WA35 | Waites, Thaddeus Z
T1831 | PR | 321 | 02/21/14 | 995 | Payroll Burden | WI46 | Wilson, Garret A
T1832 | PR | 368 | 02/28/14 | 995 | Payroll Burden | BA70 | Barnhart, Joseph N
T1833 | PR | 370 | 02/28/14 | 995 | Payroll Burden | CA72 | Castaneda Juarez, Edgar D
T1834 | PR | 378 | 02/28/14 | 995 | Payroll Burden | GA70 | Garcia, Jordan X
T1835 | PR | 379 | 02/28/14 | 995 | Payroll Burden | GE69 | Gerard, Jeffrey S
T1836 | PR | 379 | 02/28/14 | 995 | Payroll Burden | GE69 | Gerard, Jeffrey S
T1837 | PR | 380 | 02/28/14 | 995 | Payroll Burden | GO56 | Gonzalez Hernandez, Josue
T1838 | PR | 385 | 02/28/14 | 995 | Payroll Burden | LI49 | Lima Romero, Melvin A
T1839 | PR | 385 | 02/28/14 | 995 | Payroll Burden | LI49 | Lima Romero, Melvin A
T1840 | PR | 385 | 02/28/14 | 995 | Payroll Burden | LI49 | Lima Romero, Melvin A
T1841 | PR | 388 | 02/28/14 | 995 | Payroll Burden | ME98 | Meza Fuentes, Erick A
T1842 | PR | 393 | 02/28/14 | 995 | Payroll Burden | QU35 | Quintanilla, Esteban R
T1843 | PR | 396 | 02/28/14 | 995 | Payroll Burden | RA54 | Ramos Garcia, Jose M
T1844 | PR | 403 | 02/28/14 | 995 | Payroll Burden | SA54 | Sanders, Allen O
T1845 | PR | 405 | 02/28/14 | 995 | Payroll Burden | SO78 | Soto Cruz, Jovani
T1846 | PR | 412 | 02/28/14 | 995 | Payroll Burden | WA35 | Waites, Thaddeus Z
T1847 | PR | 412 | 02/28/14 | 995 | Payroll Burden | WA35 | Waites, Thaddeus Z
T1848 | PR | 413 | 02/28/14 | 995 | Payroll Burden | WI46 | Wilson, Garret A
T1849 | PR | 7 | 03/07/14 | 995 | Payroll Burden | CA72 | Castaneda Juarez, Edgar D
T1850 | PR | 16 | 03/07/14 | 995 | Payroll Burden | GE69 | Gerard, Jeffrey S
T1851 | PR | 16 | 03/07/14 | 995 | Payroll Burden | GE69 | Gerard, Jeffrey S
T1852 | PR | 17 | 03/07/14 | 995 | Payroll Burden | GO56 | Gonzalez Hernandez, Josue
T1853 | PR | 17 | 03/07/14 | 995 | Payroll Burden | GO56 | Gonzalez Hernandez, Josue
T1854 | PR | 17 | 03/07/14 | 995 | Payroll Burden | GO56 | Gonzalez Hernandez, Josue
T1855 | PR | 22 | 03/07/14 | 995 | Payroll Burden | LI49 | Lima Romero, Melvin A
T1856 | PR | 22 | 03/07/14 | 995 | Payroll Burden | LI49 | Lima Romero, Melvin A
T1857 | PR | 25 | 03/07/14 | 995 | Payroll Burden | ME98 | Meza Fuentes, Erick A
T1858 | PR | 30 | 03/07/14 | 995 | Payroll Burden | QU35 | Quintanilla, Esteban R
T1859 | PR | 40 | 03/07/14 | 995 | Payroll Burden | SA54 | Sanders, Allen O
T1860 | PR | 42 | 03/07/14 | 995 | Payroll Burden | SO78 | Soto Cruz, Jovani
T1861 | PR | 43 | 03/07/14 | 995 | Payroll Burden | SO79 | Soto Serna, Cesar E
T1862 | PR | 45 | 03/07/14 | 995 | Payroll Burden | VA86 | Vaughan, Tyler J
T1863 | PR | 49 | 03/07/14 | 995 | Payroll Burden | WA35 | Waites, Thaddeus Z
T1864 | PR | 49 | 03/07/14 | 995 | Payroll Burden | WA35 | Waites, Thaddeus Z
T1865 | PR | 49 | 03/07/14 | 995 | Payroll Burden | WA35 | Waites, Thaddeus Z
T1866 | PR | 187 | 03/14/14 | 995 | Payroll Burden | CA72 | Castaneda Juarez, Edgar D
T1867 | PR | 196 | 03/14/14 | 995 | Payroll Burden | GE69 | Gerard, Jeffrey S
T1868 | PR | 196 | 03/14/14 | 995 | Payroll Burden | GE69 | Gerard, Jeffrey S
T1869 | PR | 197 | 03/14/14 | 995 | Payroll Burden | GO56 | Gonzalez Hernandez, Josue
T1870 | PR | 197 | 03/14/14 | 995 | Payroll Burden | GO56 | Gonzalez Hernandez, Josue
T1871 | PR | 197 | 03/14/14 | 995 | Payroll Burden | GO56 | Gonzalez Hernandez, Josue
T1872 | PR | 202 | 03/14/14 | 995 | Payroll Burden | LI49 | Lima Romero, Melvin A
T1873 | PR | 202 | 03/14/14 | 995 | Payroll Burden | LI49 | Lima Romero, Melvin A
T1874 | PR | 205 | 03/14/14 | 995 | Payroll Burden | ME98 | Meza Fuentes, Erick A
T1875 | PR | 210 | 03/14/14 | 995 | Payroll Burden | QU35 | Quintanilla, Esteban R
T1876 | PR | 220 | 03/14/14 | 995 | Payroll Burden | SA54 | Sanders, Allen O
T1877 | PR | 222 | 03/14/14 | 995 | Payroll Burden | SO78 | Soto Cruz, Jovani
T1878 | PR | 223 | 03/14/14 | 995 | Payroll Burden | SO79 | Soto Serna, Cesar E
T1879 | PR | 225 | 03/14/14 | 995 | Payroll Burden | VA86 | Vaughan, Tyler J
T1880 | PR | 229 | 03/14/14 | 995 | Payroll Burden | WA35 | Waites, Thaddeus Z
T1881 | PR | 229 | 03/14/14 | 995 | Payroll Burden | WA35 | Waites, Thaddeus Z
T1882 | PR | 331 | 03/21/14 | 995 | Payroll Burden | CA75 | Castro Hernandez, Carlos E
T1883 | PR | 331 | 03/21/14 | 995 | Payroll Burden | CA75 | Castro Hernandez, Carlos E
T1884 | PR | 337 | 03/21/14 | 995 | Payroll Burden | GE69 | Gerard, Jeffrey S
T1885 | PR | 337 | 03/21/14 | 995 | Payroll Burden | GE69 | Gerard, Jeffrey S
T1886 | PR | 338 | 03/21/14 | 995 | Payroll Burden | GO56 | Gonzalez Hernandez, Josue
T1887 | PR | 338 | 03/21/14 | 995 | Payroll Burden | GO56 | Gonzalez Hernandez, Josue
T1888 | PR | 343 | 03/21/14 | 995 | Payroll Burden | LI49 | Lima Romero, Melvin A
T1889 | PR | 346 | 03/21/14 | 995 | Payroll Burden | ME98 | Meza Fuentes, Erick A
T1890 | PR | 351 | 03/21/14 | 995 | Payroll Burden | QU35 | Quintanilla, Esteban R
T1891 | PR | 361 | 03/21/14 | 995 | Payroll Burden | SA54 | Sanders, Allen O
T1892 | PR | 364 | 03/21/14 | 995 | Payroll Burden | SO79 | Soto Serna, Cesar E
T1893 | PR | 366 | 03/21/14 | 995 | Payroll Burden | VA86 | Vaughan, Tyler J
T1894 | PR | 369 | 03/21/14 | 995 | Payroll Burden | WA35 | Waites, Thaddeus Z
T1895 | PR | 467 | 03/28/14 | 995 | Payroll Burden | BA70 | Barnhart, Joseph N
T1896 | PR | 472 | 03/28/14 | 995 | Payroll Burden | CA75 | Castro Hernandez, Carlos E
T1897 | PR | 478 | 03/28/14 | 995 | Payroll Burden | GE69 | Gerard, Jeffrey S
T1898 | PR | 487 | 03/28/14 | 995 | Payroll Burden | ME98 | Meza Fuentes, Erick A
T1899 | PR | 492 | 03/28/14 | 995 | Payroll Burden | QU35 | Quintanilla, Esteban R
T1900 | PR | 502 | 03/28/14 | 995 | Payroll Burden | SA54 | Sanders, Allen O
T1901 | PR | 504 | 03/28/14 | 995 | Payroll Burden | SO78 | Soto Cruz, Jovani
T1902 | PR | 505 | 03/28/14 | 995 | Payroll Burden | SO79 | Soto Serna, Cesar E
T1903 | PR | 507 | 03/28/14 | 995 | Payroll Burden | VA86 | Vaughan, Tyler J
T1904 | PR | 18 | 04/04/14 | 995 | Payroll Burden | GE69 | Gerard, Jeffrey S
T1905 | PR | 27 | 04/04/14 | 995 | Payroll Burden | ME98 | Meza Fuentes, Erick A
T1906 | PR | 43 | 04/04/14 | 995 | Payroll Burden | SA54 | Sanders, Allen O
T1907 | PR | 45 | 04/04/14 | 995 | Payroll Burden | SO78 | Soto Cruz, Jovani
T1908 | PR | 46 | 04/04/14 | 995 | Payroll Burden | SO79 | Soto Serna, Cesar E
T1909 | PR | 48 | 04/04/14 | 995 | Payroll Burden | VA86 | Vaughan, Tyler J
T1910 | PR | 141 | 04/11/14 | 995 | Payroll Burden | GE69 | Gerard, Jeffrey S
T1911 | PR | 151 | 04/11/14 | 995 | Payroll Burden | ME98 | Meza Fuentes, Erick A
T1912 | PR | 167 | 04/11/14 | 995 | Payroll Burden | SA54 | Sanders, Allen O
T1913 | PR | 169 | 04/11/14 | 995 | Payroll Burden | SO78 | Soto Cruz, Jovani
T1914 | PR | 172 | 04/11/14 | 995 | Payroll Burden | VA86 | Vaughan, Tyler J
T1915 | PR | 260 | 04/18/14 | 995 | Payroll Burden | GE69 | Gerard, Jeffrey S
T1916 | PR | 260 | 04/18/14 | 995 | Payroll Burden | GE69 | Gerard, Jeffrey S
T1917 | PR | 269 | 04/18/14 | 995 | Payroll Burden | ME98 | Meza Fuentes, Erick A
T1918 | PR | 285 | 04/18/14 | 995 | Payroll Burden | SA54 | Sanders, Allen O
T1919 | PR | 287 | 04/18/14 | 995 | Payroll Burden | SO78 | Soto Cruz, Jovani
T1920 | PR | 398 | 04/25/14 | 995 | Payroll Burden | GE69 | Gerard, Jeffrey S
T1921 | PR | 408 | 04/25/14 | 995 | Payroll Burden | ME98 | Meza Fuentes, Erick A
T1922 | PR | 424 | 04/25/14 | 995 | Payroll Burden | SA54 | Sanders, Allen O
T1923 | PR | 426 | 04/25/14 | 995 | Payroll Burden | SO78 | Soto Cruz, Jovani
T1924 | PR | 10 | 05/02/14 | 995 | Payroll Burden | BA70 | Barnhart, Joseph N
T1925 | PR | 31 | 05/02/14 | 995 | Payroll Burden | ME98 | Meza Fuentes, Erick A
T1926 | PR | 31 | 05/02/14 | 995 | Payroll Burden | ME98 | Meza Fuentes, Erick A
T1927 | PR | 47 | 05/02/14 | 995 | Payroll Burden | SA54 | Sanders, Allen O
T1928 | PR | 178 | 05/09/14 | 995 | Payroll Burden | ME98 | Meza Fuentes, Erick A
T1929 | PR | 194 | 05/09/14 | 995 | Payroll Burden | SA54 | Sanders, Allen O
T1930 | PR | 284 | 05/16/14 | 995 | Payroll Burden | SA54 | Sanders, Allen O
T1931 | PR | 463 | 05/23/14 | 995 | Payroll Burden | SA54 | Sanders, Allen O
T1932 | PR | 537 | 05/30/14 | 995 | Payroll Burden | SA54 | Sanders, Allen O
T1933 | PR | 27 | 06/06/14 | 995 | Payroll Burden | ME98 | Meza Fuentes, Erick A
T1934 | PR | 42 | 06/06/14 | 995 | Payroll Burden | SA54 | Sanders, Allen O
T1935 | PR | 232 | 06/20/14 | 995 | Payroll Burden | GE69 | Gerard, Jeffrey S
T1936 | PR | 207 | 01/25/13 | 998 | Payroll Taxes | GE69 | Gerard, Jeffrey S
T1937 | PR | 9 | 03/01/13 | 998 | Payroll Taxes | GE69 | Gerard, Jeffrey S
T1938 | PR | 71 | 03/08/13 | 998 | Payroll Taxes | GE69 | Gerard, Jeffrey S
T1939 | PR | 194 | 03/22/13 | 998 | Payroll Taxes | GE69 | Gerard, Jeffrey S
T1940 | PR | 279 | 03/29/13 | 998 | Payroll Taxes | BA70 | Barnhart, Joseph N
T1941 | PR | 286 | 03/29/13 | 998 | Payroll Taxes | GE69 | Gerard, Jeffrey S
T1942 | PR | 300 | 03/29/13 | 998 | Payroll Taxes | SA54 | Sanders, Allen O
T1943 | PR | 20 | 04/05/13 | 998 | Payroll Taxes | GE69 | Gerard, Jeffrey S
T1944 | PR | 90 | 04/12/13 | 998 | Payroll Taxes | GE69 | Gerard, Jeffrey S
T1945 | PR | 153 | 04/19/13 | 998 | Payroll Taxes | GE69 | Gerard, Jeffrey S
T1946 | PR | 153 | 04/19/13 | 998 | Payroll Taxes | GE69 | Gerard, Jeffrey S
T1947 | PR | 153 | 04/19/13 | 998 | Payroll Taxes | GE69 | Gerard, Jeffrey S
T1948 | PR | 225 | 04/26/13 | 998 | Payroll Taxes | BA70 | Barnhart, Joseph N
T1949 | PR | 227 | 04/26/13 | 998 | Payroll Taxes | CA77 | Castro Hernandez, Jose A
T1950 | PR | 232 | 04/26/13 | 998 | Payroll Taxes | GE69 | Gerard, Jeffrey S
T1951 | PR | 232 | 04/26/13 | 998 | Payroll Taxes | GE69 | Gerard, Jeffrey S
T1952 | PR | 232 | 04/26/13 | 998 | Payroll Taxes | GE69 | Gerard, Jeffrey S
T1953 | PR | 242 | 04/26/13 | 998 | Payroll Taxes | QU35 | Quintanilla, Esteban R
T1954 | PR | 4 | 05/03/13 | 998 | Payroll Taxes | CA77 | Castro Hernandez, Jose A
T1955 | PR | 4 | 05/03/13 | 998 | Payroll Taxes | CA77 | Castro Hernandez, Jose A
T1956 | PR | 9 | 05/03/13 | 998 | Payroll Taxes | GE69 | Gerard, Jeffrey S
T1957 | PR | 9 | 05/03/13 | 998 | Payroll Taxes | GE69 | Gerard, Jeffrey S
T1958 | PR | 9 | 05/03/13 | 998 | Payroll Taxes | GE69 | Gerard, Jeffrey S
T1959 | PR | 17 | 05/03/13 | 998 | Payroll Taxes | PA11 | Paco Leyva, Orlando
T1960 | PR | 19 | 05/03/13 | 998 | Payroll Taxes | QU35 | Quintanilla, Esteban R
T1961 | PR | 19 | 05/03/13 | 998 | Payroll Taxes | QU35 | Quintanilla, Esteban R
T1962 | PR | 26 | 05/03/13 | 998 | Payroll Taxes | VE45 | Veley, Nathaniel S
T1963 | PR | 85 | 05/10/13 | 998 | Payroll Taxes | GE69 | Gerard, Jeffrey S
T1964 | PR | 85 | 05/10/13 | 998 | Payroll Taxes | GE69 | Gerard, Jeffrey S
T1965 | PR | 85 | 05/10/13 | 998 | Payroll Taxes | GE69 | Gerard, Jeffrey S
T1966 | PR | 88 | 05/10/13 | 998 | Payroll Taxes | LI49 | Lima Romero, Melvin A
T1967 | PR | 88 | 05/10/13 | 998 | Payroll Taxes | LI49 | Lima Romero, Melvin A
T1968 | PR | 93 | 05/10/13 | 998 | Payroll Taxes | PA11 | Paco Leyva, Orlando
T1969 | PR | 93 | 05/10/13 | 998 | Payroll Taxes | PA11 | Paco Leyva, Orlando
T1970 | PR | 102 | 05/10/13 | 998 | Payroll Taxes | VE45 | Veley, Nathaniel S
T1971 | PR | 102 | 05/10/13 | 998 | Payroll Taxes | VE45 | Veley, Nathaniel S
T1972 | PR | 176 | 05/17/13 | 998 | Payroll Taxes | LI49 | Lima Romero, Melvin A
T1973 | PR | 176 | 05/17/13 | 998 | Payroll Taxes | LI49 | Lima Romero, Melvin A
T1974 | PR | 181 | 05/17/13 | 998 | Payroll Taxes | PA11 | Paco Leyva, Orlando
T1975 | PR | 190 | 05/17/13 | 998 | Payroll Taxes | VE45 | Veley, Nathaniel S
T1976 | PR | 190 | 05/17/13 | 998 | Payroll Taxes | VE45 | Veley, Nathaniel S
T1977 | PR | 264 | 05/24/13 | 998 | Payroll Taxes | GE69 | Gerard, Jeffrey S
T1978 | PR | 266 | 05/24/13 | 998 | Payroll Taxes | HU06 | Hubbard, Robert W
T1979 | PR | 272 | 05/24/13 | 998 | Payroll Taxes | PA11 | Paco Leyva, Orlando
T1980 | PR | 272 | 05/24/13 | 998 | Payroll Taxes | PA11 | Paco Leyva, Orlando
T1981 | PR | 281 | 05/24/13 | 998 | Payroll Taxes | VE45 | Veley, Nathaniel S
T1982 | PR | 281 | 05/24/13 | 998 | Payroll Taxes | VE45 | Veley, Nathaniel S
T1983 | PR | 325 | 05/31/13 | 998 | Payroll Taxes | GE69 | Gerard, Jeffrey S
T1984 | PR | 325 | 05/31/13 | 998 | Payroll Taxes | GE69 | Gerard, Jeffrey S
T1985 | PR | 325 | 05/31/13 | 998 | Payroll Taxes | GE69 | Gerard, Jeffrey S
T1986 | PR | 333 | 05/31/13 | 998 | Payroll Taxes | PA11 | Paco Leyva, Orlando
T1987 | PR | 342 | 05/31/13 | 998 | Payroll Taxes | VE45 | Veley, Nathaniel S
T1988 | PR | 13 | 06/07/13 | 998 | Payroll Taxes | GE69 | Gerard, Jeffrey S
T1989 | PR | 21 | 06/07/13 | 998 | Payroll Taxes | PA11 | Paco Leyva, Orlando
T1990 | PR | 30 | 06/07/13 | 998 | Payroll Taxes | VE45 | Veley, Nathaniel S
T1991 | PR | 30 | 06/07/13 | 998 | Payroll Taxes | VE45 | Veley, Nathaniel S
T1992 | PR | 97 | 06/14/13 | 998 | Payroll Taxes | GE69 | Gerard, Jeffrey S
T1993 | PR | 97 | 06/14/13 | 998 | Payroll Taxes | GE69 | Gerard, Jeffrey S
T1994 | PR | 97 | 06/14/13 | 998 | Payroll Taxes | GE69 | Gerard, Jeffrey S
T1995 | PR | 182 | 06/21/13 | 998 | Payroll Taxes | GE69 | Gerard, Jeffrey S
T1996 | PR | 182 | 06/21/13 | 998 | Payroll Taxes | GE69 | Gerard, Jeffrey S
T1997 | PR | 191 | 06/21/13 | 998 | Payroll Taxes | PA11 | Paco Leyva, Orlando
T1998 | PR | 202 | 06/21/13 | 998 | Payroll Taxes | VE45 | Veley, Nathaniel S
T1999 | PR | 247 | 06/28/13 | 998 | Payroll Taxes | GE69 | Gerard, Jeffrey S
T2000 | PR | 247 | 06/28/13 | 998 | Payroll Taxes | GE69 | Gerard, Jeffrey S
T2001 | PR | 257 | 06/28/13 | 998 | Payroll Taxes | PA11 | Paco Leyva, Orlando
T2002 | PR | 267 | 06/28/13 | 998 | Payroll Taxes | VE45 | Veley, Nathaniel S
T2003 | PR | 12 | 07/03/13 | 998 | Payroll Taxes | GE69 | Gerard, Jeffrey S
T2004 | PR | 12 | 07/03/13 | 998 | Payroll Taxes | GE69 | Gerard, Jeffrey S
T2005 | PR | 12 | 07/03/13 | 998 | Payroll Taxes | GE69 | Gerard, Jeffrey S
T2006 | PR | 22 | 07/03/13 | 998 | Payroll Taxes | PA11 | Paco Leyva, Orlando
T2007 | PR | 22 | 07/03/13 | 998 | Payroll Taxes | PA11 | Paco Leyva, Orlando
T2008 | PR | 32 | 07/03/13 | 998 | Payroll Taxes | VE45 | Veley, Nathaniel S
T2009 | PR | 32 | 07/03/13 | 998 | Payroll Taxes | VE45 | Veley, Nathaniel S
T2010 | PR | 81 | 07/12/13 | 998 | Payroll Taxes | GE69 | Gerard, Jeffrey S
T2011 | PR | 81 | 07/12/13 | 998 | Payroll Taxes | GE69 | Gerard, Jeffrey S
T2012 | PR | 210 | 07/19/13 | 998 | Payroll Taxes | GE69 | Gerard, Jeffrey S
T2013 | PR | 210 | 07/19/13 | 998 | Payroll Taxes | GE69 | Gerard, Jeffrey S
T2014 | PR | 210 | 07/19/13 | 998 | Payroll Taxes | GE69 | Gerard, Jeffrey S
T2015 | PR | 210 | 07/19/13 | 998 | Payroll Taxes | GE69 | Gerard, Jeffrey S
T2016 | PR | 213 | 07/19/13 | 998 | Payroll Taxes | HU04 | Hubbard, Dustin R
T2017 | PR | 220 | 07/19/13 | 998 | Payroll Taxes | PA11 | Paco Leyva, Orlando
T2018 | PR | 227 | 07/19/13 | 998 | Payroll Taxes | SA54 | Sanders, Allen O
T2019 | PR | 231 | 07/19/13 | 998 | Payroll Taxes | VE45 | Veley, Nathaniel S
T2020 | PR | 231 | 07/19/13 | 998 | Payroll Taxes | VE45 | Veley, Nathaniel S
T2021 | PR | 280 | 07/26/13 | 998 | Payroll Taxes | CO71 | Cortes Mendiola, Victor H
T2022 | PR | 280 | 07/26/13 | 998 | Payroll Taxes | CO71 | Cortes Mendiola, Victor H
T2023 | PR | 283 | 07/26/13 | 998 | Payroll Taxes | GE69 | Gerard, Jeffrey S
T2024 | PR | 283 | 07/26/13 | 998 | Payroll Taxes | GE69 | Gerard, Jeffrey S
T2025 | PR | 293 | 07/26/13 | 998 | Payroll Taxes | PA11 | Paco Leyva, Orlando
T2026 | PR | 11 | 08/02/13 | 998 | Payroll Taxes | GE69 | Gerard, Jeffrey S
T2027 | PR | 11 | 08/02/13 | 998 | Payroll Taxes | GE69 | Gerard, Jeffrey S
T2028 | PR | 11 | 08/02/13 | 998 | Payroll Taxes | GE69 | Gerard, Jeffrey S
T2029 | PR | 11 | 08/02/13 | 998 | Payroll Taxes | GE69 | Gerard, Jeffrey S
T2030 | PR | 14 | 08/02/13 | 998 | Payroll Taxes | HU04 | Hubbard, Dustin R
T2031 | PR | 21 | 08/02/13 | 998 | Payroll Taxes | PA11 | Paco Leyva, Orlando
T2032 | PR | 84 | 08/09/13 | 998 | Payroll Taxes | AR70 | Arreola, Israel A
T2033 | PR | 93 | 08/09/13 | 998 | Payroll Taxes | GE69 | Gerard, Jeffrey S
T2034 | PR | 93 | 08/09/13 | 998 | Payroll Taxes | GE69 | Gerard, Jeffrey S
T2035 | PR | 105 | 08/09/13 | 998 | Payroll Taxes | PA11 | Paco Leyva, Orlando
T2036 | PR | 113 | 08/09/13 | 998 | Payroll Taxes | SE64 | Sepulveda Gonzalez, Alfredo
T2037 | PR | 126 | 08/09/13 | 998 | Payroll Taxes | SE64 | Sepulveda Gonzalez, Alfredo
T2038 | PR | 131 | 08/09/13 | 998 | Payroll Taxes | SE64 | Sepulveda Gonzalez, Alfredo
T2039 | PR | 206 | 08/16/13 | 998 | Payroll Taxes | GE69 | Gerard, Jeffrey S
T2040 | PR | 206 | 08/16/13 | 998 | Payroll Taxes | GE69 | Gerard, Jeffrey S
T2041 | PR | 218 | 08/16/13 | 998 | Payroll Taxes | PA11 | Paco Leyva, Orlando
T2042 | PR | 230 | 08/16/13 | 998 | Payroll Taxes | VE45 | Veley, Nathaniel S
T2043 | PR | 284 | 08/23/13 | 998 | Payroll Taxes | CO71 | Cortes Mendiola, Victor H
T2044 | PR | 287 | 08/23/13 | 998 | Payroll Taxes | GE69 | Gerard, Jeffrey S
T2045 | PR | 287 | 08/23/13 | 998 | Payroll Taxes | GE69 | Gerard, Jeffrey S
T2046 | PR | 299 | 08/23/13 | 998 | Payroll Taxes | PA11 | Paco Leyva, Orlando
T2047 | PR | 307 | 08/23/13 | 998 | Payroll Taxes | SE64 | Sepulveda Gonzalez, Alfredo
T2048 | PR | 310 | 08/23/13 | 998 | Payroll Taxes | SP17 | Spears, Gregory M
T2049 | PR | 311 | 08/23/13 | 998 | Payroll Taxes | VE45 | Veley, Nathaniel S
T2050 | PR | 394 | 08/30/13 | 998 | Payroll Taxes | CO71 | Cortes Mendiola, Victor H
T2051 | PR | 394 | 08/30/13 | 998 | Payroll Taxes | CO71 | Cortes Mendiola, Victor H
T2052 | PR | 397 | 08/30/13 | 998 | Payroll Taxes | GE69 | Gerard, Jeffrey S
T2053 | PR | 397 | 08/30/13 | 998 | Payroll Taxes | GE69 | Gerard, Jeffrey S
T2054 | PR | 400 | 08/30/13 | 998 | Payroll Taxes | HO14 | Holmes, Anthony R
T2055 | PR | 409 | 08/30/13 | 998 | Payroll Taxes | PA11 | Paco Leyva, Orlando
T2056 | PR | 409 | 08/30/13 | 998 | Payroll Taxes | PA11 | Paco Leyva, Orlando
T2057 | PR | 410 | 08/30/13 | 998 | Payroll Taxes | PA46 | Palma Vides, Hugo
T2058 | PR | 410 | 08/30/13 | 998 | Payroll Taxes | PA46 | Palma Vides, Hugo
T2059 | PR | 419 | 08/30/13 | 998 | Payroll Taxes | SP17 | Spears, Gregory M
T2060 | PR | 419 | 08/30/13 | 998 | Payroll Taxes | SP17 | Spears, Gregory M
T2061 | PR | 419 | 08/30/13 | 998 | Payroll Taxes | SP17 | Spears, Gregory M
T2062 | PR | 419 | 08/30/13 | 998 | Payroll Taxes | SP17 | Spears, Gregory M
T2063 | PR | 420 | 08/30/13 | 998 | Payroll Taxes | VE45 | Veley, Nathaniel S
T2064 | PR | 420 | 08/30/13 | 998 | Payroll Taxes | VE45 | Veley, Nathaniel S
T2065 | PR | 422 | 08/30/13 | 998 | Payroll Taxes | SE64 | Sepulveda Gonzalez, Alfredo
T2066 | PR | 422 | 08/30/13 | 998 | Payroll Taxes | SE64 | Sepulveda Gonzalez, Alfredo
T2067 | PR | 57 | 09/06/13 | 998 | Payroll Taxes | CO71 | Cortes Mendiola, Victor H
T2068 | PR | 60 | 09/06/13 | 998 | Payroll Taxes | GE69 | Gerard, Jeffrey S
T2069 | PR | 63 | 09/06/13 | 998 | Payroll Taxes | HO14 | Holmes, Anthony R
T2070 | PR | 70 | 09/06/13 | 998 | Payroll Taxes | MO54 | Monico Brambila, Jesus S
T2071 | PR | 72 | 09/06/13 | 998 | Payroll Taxes | PA11 | Paco Leyva, Orlando
T2072 | PR | 73 | 09/06/13 | 998 | Payroll Taxes | PA46 | Palma Vides, Hugo
T2073 | PR | 80 | 09/06/13 | 998 | Payroll Taxes | SE64 | Sepulveda Gonzalez, Alfredo
T2074 | PR | 83 | 09/06/13 | 998 | Payroll Taxes | SP17 | Spears, Gregory M
T2075 | PR | 84 | 09/06/13 | 998 | Payroll Taxes | VE45 | Veley, Nathaniel S
T2076 | PR | 165 | 09/13/13 | 998 | Payroll Taxes | CA74 | Castaneda Martinez, Gustavo
T2077 | PR | 166 | 09/13/13 | 998 | Payroll Taxes | CA75 | Castro Hernandez, Carlos E
T2078 | PR | 169 | 09/13/13 | 998 | Payroll Taxes | CO71 | Cortes Mendiola, Victor H
T2079 | PR | 172 | 09/13/13 | 998 | Payroll Taxes | GE69 | Gerard, Jeffrey S
T2080 | PR | 172 | 09/13/13 | 998 | Payroll Taxes | GE69 | Gerard, Jeffrey S
T2081 | PR | 173 | 09/13/13 | 998 | Payroll Taxes | GO56 | Gonzalez Hernandez, Josue
T2082 | PR | 175 | 09/13/13 | 998 | Payroll Taxes | HO14 | Holmes, Anthony R
T2083 | PR | 175 | 09/13/13 | 998 | Payroll Taxes | HO14 | Holmes, Anthony R
T2084 | PR | 175 | 09/13/13 | 998 | Payroll Taxes | HO14 | Holmes, Anthony R
T2085 | PR | 175 | 09/13/13 | 998 | Payroll Taxes | HO14 | Holmes, Anthony R
T2086 | PR | 178 | 09/13/13 | 998 | Payroll Taxes | LI49 | Lima Romero, Melvin A
T2087 | PR | 182 | 09/13/13 | 998 | Payroll Taxes | MO54 | Monico Brambila, Jesus S
T2088 | PR | 182 | 09/13/13 | 998 | Payroll Taxes | MO54 | Monico Brambila, Jesus S
T2089 | PR | 184 | 09/13/13 | 998 | Payroll Taxes | PA11 | Paco Leyva, Orlando
T2090 | PR | 184 | 09/13/13 | 998 | Payroll Taxes | PA11 | Paco Leyva, Orlando
T2091 | PR | 185 | 09/13/13 | 998 | Payroll Taxes | PA46 | Palma Vides, Hugo
T2092 | PR | 185 | 09/13/13 | 998 | Payroll Taxes | PA46 | Palma Vides, Hugo
T2093 | PR | 185 | 09/13/13 | 998 | Payroll Taxes | PA46 | Palma Vides, Hugo
T2094 | PR | 185 | 09/13/13 | 998 | Payroll Taxes | PA46 | Palma Vides, Hugo
T2095 | PR | 186 | 09/13/13 | 998 | Payroll Taxes | QU35 | Quintanilla, Esteban R
T2096 | PR | 193 | 09/13/13 | 998 | Payroll Taxes | SE64 | Sepulveda Gonzalez, Alfredo
T2097 | PR | 196 | 09/13/13 | 998 | Payroll Taxes | SP17 | Spears, Gregory M
T2098 | PR | 196 | 09/13/13 | 998 | Payroll Taxes | SP17 | Spears, Gregory M
T2099 | PR | 197 | 09/13/13 | 998 | Payroll Taxes | VE25 | Vega Arriaga, Jorge
T2100 | PR | 197 | 09/13/13 | 998 | Payroll Taxes | VE25 | Vega Arriaga, Jorge
T2101 | PR | 198 | 09/13/13 | 998 | Payroll Taxes | VE45 | Veley, Nathaniel S
T2102 | PR | 198 | 09/13/13 | 998 | Payroll Taxes | VE45 | Veley, Nathaniel S
T2103 | PR | 198 | 09/13/13 | 998 | Payroll Taxes | VE45 | Veley, Nathaniel S
T2104 | PR | 257 | 09/20/13 | 998 | Payroll Taxes | AR70 | Arreola, Israel A
T2105 | PR | 267 | 09/20/13 | 998 | Payroll Taxes | GE69 | Gerard, Jeffrey S
T2106 | PR | 267 | 09/20/13 | 998 | Payroll Taxes | GE69 | Gerard, Jeffrey S
T2107 | PR | 268 | 09/20/13 | 998 | Payroll Taxes | GO56 | Gonzalez Hernandez, Josue
T2108 | PR | 268 | 09/20/13 | 998 | Payroll Taxes | GO56 | Gonzalez Hernandez, Josue
T2109 | PR | 270 | 09/20/13 | 998 | Payroll Taxes | HO14 | Holmes, Anthony R
T2110 | PR | 270 | 09/20/13 | 998 | Payroll Taxes | HO14 | Holmes, Anthony R
T2111 | PR | 270 | 09/20/13 | 998 | Payroll Taxes | HO14 | Holmes, Anthony R
T2112 | PR | 277 | 09/20/13 | 998 | Payroll Taxes | MO54 | Monico Brambila, Jesus S
T2113 | PR | 277 | 09/20/13 | 998 | Payroll Taxes | MO54 | Monico Brambila, Jesus S
T2114 | PR | 280 | 09/20/13 | 998 | Payroll Taxes | PA11 | Paco Leyva, Orlando
T2115 | PR | 280 | 09/20/13 | 998 | Payroll Taxes | PA11 | Paco Leyva, Orlando
T2116 | PR | 280 | 09/20/13 | 998 | Payroll Taxes | PA11 | Paco Leyva, Orlando
T2117 | PR | 280 | 09/20/13 | 998 | Payroll Taxes | PA11 | Paco Leyva, Orlando
T2118 | PR | 281 | 09/20/13 | 998 | Payroll Taxes | PA46 | Palma Vides, Hugo
T2119 | PR | 281 | 09/20/13 | 998 | Payroll Taxes | PA46 | Palma Vides, Hugo
T2120 | PR | 281 | 09/20/13 | 998 | Payroll Taxes | PA46 | Palma Vides, Hugo
T2121 | PR | 281 | 09/20/13 | 998 | Payroll Taxes | PA46 | Palma Vides, Hugo
T2122 | PR | 282 | 09/20/13 | 998 | Payroll Taxes | QU35 | Quintanilla, Esteban R
T2123 | PR | 285 | 09/20/13 | 998 | Payroll Taxes | RE54 | Rendon Villasenor, Ismael
T2124 | PR | 288 | 09/20/13 | 998 | Payroll Taxes | SA45 | Salazar, Hajdar L
T2125 | PR | 293 | 09/20/13 | 998 | Payroll Taxes | SP17 | Spears, Gregory M
T2126 | PR | 293 | 09/20/13 | 998 | Payroll Taxes | SP17 | Spears, Gregory M
T2127 | PR | 294 | 09/20/13 | 998 | Payroll Taxes | VE25 | Vega Arriaga, Jorge
T2128 | PR | 294 | 09/20/13 | 998 | Payroll Taxes | VE25 | Vega Arriaga, Jorge
T2129 | PR | 295 | 09/20/13 | 998 | Payroll Taxes | VE45 | Veley, Nathaniel S
T2130 | PR | 295 | 09/20/13 | 998 | Payroll Taxes | VE45 | Veley, Nathaniel S
T2131 | PR | 295 | 09/20/13 | 998 | Payroll Taxes | VE45 | Veley, Nathaniel S
T2132 | PR | 295 | 09/20/13 | 998 | Payroll Taxes | VE45 | Veley, Nathaniel S
T2133 | PR | 381 | 09/27/13 | 998 | Payroll Taxes | AR70 | Arreola, Israel A
T2134 | PR | 382 | 09/27/13 | 998 | Payroll Taxes | BA70 | Barnhart, Joseph N
T2135 | PR | 388 | 09/27/13 | 998 | Payroll Taxes | CO71 | Cortes Mendiola, Victor H
T2136 | PR | 391 | 09/27/13 | 998 | Payroll Taxes | GE69 | Gerard, Jeffrey S
T2137 | PR | 392 | 09/27/13 | 998 | Payroll Taxes | GO56 | Gonzalez Hernandez, Josue
T2138 | PR | 392 | 09/27/13 | 998 | Payroll Taxes | GO56 | Gonzalez Hernandez, Josue
T2139 | PR | 394 | 09/27/13 | 998 | Payroll Taxes | HO14 | Holmes, Anthony R
T2140 | PR | 394 | 09/27/13 | 998 | Payroll Taxes | HO14 | Holmes, Anthony R
T2141 | PR | 396 | 09/27/13 | 998 | Payroll Taxes | LI49 | Lima Romero, Melvin A
T2142 | PR | 400 | 09/27/13 | 998 | Payroll Taxes | MO54 | Monico Brambila, Jesus S
T2143 | PR | 400 | 09/27/13 | 998 | Payroll Taxes | MO54 | Monico Brambila, Jesus S
T2144 | PR | 403 | 09/27/13 | 998 | Payroll Taxes | PA11 | Paco Leyva, Orlando
T2145 | PR | 403 | 09/27/13 | 998 | Payroll Taxes | PA11 | Paco Leyva, Orlando
T2146 | PR | 404 | 09/27/13 | 998 | Payroll Taxes | PA46 | Palma Vides, Hugo
T2147 | PR | 404 | 09/27/13 | 998 | Payroll Taxes | PA46 | Palma Vides, Hugo
T2148 | PR | 404 | 09/27/13 | 998 | Payroll Taxes | PA46 | Palma Vides, Hugo
T2149 | PR | 405 | 09/27/13 | 998 | Payroll Taxes | QU35 | Quintanilla, Esteban R
T2150 | PR | 408 | 09/27/13 | 998 | Payroll Taxes | RE54 | Rendon Villasenor, Ismael
T2151 | PR | 413 | 09/27/13 | 998 | Payroll Taxes | SE64 | Sepulveda Gonzalez, Alfredo
T2152 | PR | 416 | 09/27/13 | 998 | Payroll Taxes | SP17 | Spears, Gregory M
T2153 | PR | 416 | 09/27/13 | 998 | Payroll Taxes | SP17 | Spears, Gregory M
T2154 | PR | 417 | 09/27/13 | 998 | Payroll Taxes | VE25 | Vega Arriaga, Jorge
T2155 | PR | 417 | 09/27/13 | 998 | Payroll Taxes | VE25 | Vega Arriaga, Jorge
T2156 | PR | 6 | 10/04/13 | 998 | Payroll Taxes | CA75 | Castro Hernandez, Carlos E
T2157 | PR | 7 | 10/04/13 | 998 | Payroll Taxes | CA77 | Castro Hernandez, Jose A
T2158 | PR | 7 | 10/04/13 | 998 | Payroll Taxes | CA77 | Castro Hernandez, Jose A
T2159 | PR | 8 | 10/04/13 | 998 | Payroll Taxes | CH04 | Chavarria Lopez, Omar A
T2160 | PR | 8 | 10/04/13 | 998 | Payroll Taxes | CH04 | Chavarria Lopez, Omar A
T2161 | PR | 13 | 10/04/13 | 998 | Payroll Taxes | GE69 | Gerard, Jeffrey S
T2162 | PR | 14 | 10/04/13 | 998 | Payroll Taxes | GO56 | Gonzalez Hernandez, Josue
T2163 | PR | 14 | 10/04/13 | 998 | Payroll Taxes | GO56 | Gonzalez Hernandez, Josue
T2164 | PR | 22 | 10/04/13 | 998 | Payroll Taxes | MO54 | Monico Brambila, Jesus S
T2165 | PR | 22 | 10/04/13 | 998 | Payroll Taxes | MO54 | Monico Brambila, Jesus S
T2166 | PR | 25 | 10/04/13 | 998 | Payroll Taxes | PA11 | Paco Leyva, Orlando
T2167 | PR | 26 | 10/04/13 | 998 | Payroll Taxes | PA46 | Palma Vides, Hugo
T2168 | PR | 27 | 10/04/13 | 998 | Payroll Taxes | QU35 | Quintanilla, Esteban R
T2169 | PR | 27 | 10/04/13 | 998 | Payroll Taxes | QU35 | Quintanilla, Esteban R
T2170 | PR | 30 | 10/04/13 | 998 | Payroll Taxes | RI84 | Rivera, Eli P
T2171 | PR | 30 | 10/04/13 | 998 | Payroll Taxes | RI84 | Rivera, Eli P
T2172 | PR | 31 | 10/04/13 | 998 | Payroll Taxes | RI87 | Rivera, Jorge A
T2173 | PR | 31 | 10/04/13 | 998 | Payroll Taxes | RI87 | Rivera, Jorge A
T2174 | PR | 38 | 10/04/13 | 998 | Payroll Taxes | SP17 | Spears, Gregory M
T2175 | PR | 38 | 10/04/13 | 998 | Payroll Taxes | SP17 | Spears, Gregory M
T2176 | PR | 39 | 10/04/13 | 998 | Payroll Taxes | VE25 | Vega Arriaga, Jorge
T2177 | PR | 39 | 10/04/13 | 998 | Payroll Taxes | VE25 | Vega Arriaga, Jorge
T2178 | PR | 68 | 10/11/13 | 998 | Payroll Taxes | BA70 | Barnhart, Joseph N
T2179 | PR | 71 | 10/11/13 | 998 | Payroll Taxes | CA74 | Castaneda Martinez, Gustavo
T2180 | PR | 71 | 10/11/13 | 998 | Payroll Taxes | CA74 | Castaneda Martinez, Gustavo
T2181 | PR | 72 | 10/11/13 | 998 | Payroll Taxes | CA75 | Castro Hernandez, Carlos E
T2182 | PR | 73 | 10/11/13 | 998 | Payroll Taxes | CA77 | Castro Hernandez, Jose A
T2183 | PR | 73 | 10/11/13 | 998 | Payroll Taxes | CA77 | Castro Hernandez, Jose A
T2184 | PR | 74 | 10/11/13 | 998 | Payroll Taxes | CH04 | Chavarria Lopez, Omar A
T2185 | PR | 74 | 10/11/13 | 998 | Payroll Taxes | CH04 | Chavarria Lopez, Omar A
T2186 | PR | 76 | 10/11/13 | 998 | Payroll Taxes | CO71 | Cortes Mendiola, Victor H
T2187 | PR | 79 | 10/11/13 | 998 | Payroll Taxes | GE69 | Gerard, Jeffrey S
T2188 | PR | 80 | 10/11/13 | 998 | Payroll Taxes | GO56 | Gonzalez Hernandez, Josue
T2189 | PR | 80 | 10/11/13 | 998 | Payroll Taxes | GO56 | Gonzalez Hernandez, Josue
T2190 | PR | 84 | 10/11/13 | 998 | Payroll Taxes | LI49 | Lima Romero, Melvin A
T2191 | PR | 84 | 10/11/13 | 998 | Payroll Taxes | LI49 | Lima Romero, Melvin A
T2192 | PR | 88 | 10/11/13 | 998 | Payroll Taxes | MO54 | Monico Brambila, Jesus S
T2193 | PR | 88 | 10/11/13 | 998 | Payroll Taxes | MO54 | Monico Brambila, Jesus S
T2194 | PR | 91 | 10/11/13 | 998 | Payroll Taxes | PA46 | Palma Vides, Hugo
T2195 | PR | 91 | 10/11/13 | 998 | Payroll Taxes | PA46 | Palma Vides, Hugo
T2196 | PR | 91 | 10/11/13 | 998 | Payroll Taxes | PA46 | Palma Vides, Hugo
T2197 | PR | 91 | 10/11/13 | 998 | Payroll Taxes | PA46 | Palma Vides, Hugo
T2198 | PR | 92 | 10/11/13 | 998 | Payroll Taxes | QU35 | Quintanilla, Esteban R
T2199 | PR | 92 | 10/11/13 | 998 | Payroll Taxes | QU35 | Quintanilla, Esteban R
T2200 | PR | 94 | 10/11/13 | 998 | Payroll Taxes | RE18 | Reed, Reuben H
T2201 | PR | 95 | 10/11/13 | 998 | Payroll Taxes | RI84 | Rivera, Eli P
T2202 | PR | 95 | 10/11/13 | 998 | Payroll Taxes | RI84 | Rivera, Eli P
T2203 | PR | 96 | 10/11/13 | 998 | Payroll Taxes | RI87 | Rivera, Jorge A
T2204 | PR | 96 | 10/11/13 | 998 | Payroll Taxes | RI87 | Rivera, Jorge A
T2205 | PR | 98 | 10/11/13 | 998 | Payroll Taxes | SA45 | Salazar, Hajdar L
T2206 | PR | 100 | 10/11/13 | 998 | Payroll Taxes | SE64 | Sepulveda Gonzalez, Alfredo
T2207 | PR | 103 | 10/11/13 | 998 | Payroll Taxes | SP17 | Spears, Gregory M
T2208 | PR | 104 | 10/11/13 | 998 | Payroll Taxes | VE25 | Vega Arriaga, Jorge
T2209 | PR | 104 | 10/11/13 | 998 | Payroll Taxes | VE25 | Vega Arriaga, Jorge
T2210 | PR | 206 | 10/18/13 | 998 | Payroll Taxes | CA74 | Castaneda Martinez, Gustavo
T2211 | PR | 208 | 10/18/13 | 998 | Payroll Taxes | CA77 | Castro Hernandez, Jose A
T2212 | PR | 208 | 10/18/13 | 998 | Payroll Taxes | CA77 | Castro Hernandez, Jose A
T2213 | PR | 209 | 10/18/13 | 998 | Payroll Taxes | CH04 | Chavarria Lopez, Omar A
T2214 | PR | 209 | 10/18/13 | 998 | Payroll Taxes | CH04 | Chavarria Lopez, Omar A
T2215 | PR | 211 | 10/18/13 | 998 | Payroll Taxes | CO71 | Cortes Mendiola, Victor H
T2216 | PR | 211 | 10/18/13 | 998 | Payroll Taxes | CO71 | Cortes Mendiola, Victor H
T2217 | PR | 214 | 10/18/13 | 998 | Payroll Taxes | GE69 | Gerard, Jeffrey S
T2218 | PR | 214 | 10/18/13 | 998 | Payroll Taxes | GE69 | Gerard, Jeffrey S
T2219 | PR | 215 | 10/18/13 | 998 | Payroll Taxes | GO56 | Gonzalez Hernandez, Josue
T2220 | PR | 215 | 10/18/13 | 998 | Payroll Taxes | GO56 | Gonzalez Hernandez, Josue
T2221 | PR | 219 | 10/18/13 | 998 | Payroll Taxes | LI49 | Lima Romero, Melvin A
T2222 | PR | 219 | 10/18/13 | 998 | Payroll Taxes | LI49 | Lima Romero, Melvin A
T2223 | PR | 223 | 10/18/13 | 998 | Payroll Taxes | MO54 | Monico Brambila, Jesus S
T2224 | PR | 223 | 10/18/13 | 998 | Payroll Taxes | MO54 | Monico Brambila, Jesus S
T2225 | PR | 226 | 10/18/13 | 998 | Payroll Taxes | PA46 | Palma Vides, Hugo
T2226 | PR | 226 | 10/18/13 | 998 | Payroll Taxes | PA46 | Palma Vides, Hugo
T2227 | PR | 227 | 10/18/13 | 998 | Payroll Taxes | QU35 | Quintanilla, Esteban R
T2228 | PR | 227 | 10/18/13 | 998 | Payroll Taxes | QU35 | Quintanilla, Esteban R
T2229 | PR | 230 | 10/18/13 | 998 | Payroll Taxes | RI84 | Rivera, Eli P
T2230 | PR | 230 | 10/18/13 | 998 | Payroll Taxes | RI84 | Rivera, Eli P
T2231 | PR | 231 | 10/18/13 | 998 | Payroll Taxes | RI87 | Rivera, Jorge A
T2232 | PR | 231 | 10/18/13 | 998 | Payroll Taxes | RI87 | Rivera, Jorge A
T2233 | PR | 235 | 10/18/13 | 998 | Payroll Taxes | SE64 | Sepulveda Gonzalez, Alfredo
T2234 | PR | 235 | 10/18/13 | 998 | Payroll Taxes | SE64 | Sepulveda Gonzalez, Alfredo
T2235 | PR | 239 | 10/18/13 | 998 | Payroll Taxes | VE25 | Vega Arriaga, Jorge
T2236 | PR | 300 | 10/25/13 | 998 | Payroll Taxes | CA74 | Castaneda Martinez, Gustavo
T2237 | PR | 300 | 10/25/13 | 998 | Payroll Taxes | CA74 | Castaneda Martinez, Gustavo
T2238 | PR | 302 | 10/25/13 | 998 | Payroll Taxes | CA77 | Castro Hernandez, Jose A
T2239 | PR | 302 | 10/25/13 | 998 | Payroll Taxes | CA77 | Castro Hernandez, Jose A
T2240 | PR | 303 | 10/25/13 | 998 | Payroll Taxes | CH04 | Chavarria Lopez, Omar A
T2241 | PR | 303 | 10/25/13 | 998 | Payroll Taxes | CH04 | Chavarria Lopez, Omar A
T2242 | PR | 305 | 10/25/13 | 998 | Payroll Taxes | CO71 | Cortes Mendiola, Victor H
T2243 | PR | 305 | 10/25/13 | 998 | Payroll Taxes | CO71 | Cortes Mendiola, Victor H
T2244 | PR | 308 | 10/25/13 | 998 | Payroll Taxes | GE69 | Gerard, Jeffrey S
T2245 | PR | 308 | 10/25/13 | 998 | Payroll Taxes | GE69 | Gerard, Jeffrey S
T2246 | PR | 309 | 10/25/13 | 998 | Payroll Taxes | GO56 | Gonzalez Hernandez, Josue
T2247 | PR | 309 | 10/25/13 | 998 | Payroll Taxes | GO56 | Gonzalez Hernandez, Josue
T2248 | PR | 314 | 10/25/13 | 998 | Payroll Taxes | LI49 | Lima Romero, Melvin A
T2249 | PR | 314 | 10/25/13 | 998 | Payroll Taxes | LI49 | Lima Romero, Melvin A
T2250 | PR | 317 | 10/25/13 | 998 | Payroll Taxes | MO54 | Monico Brambila, Jesus S
T2251 | PR | 317 | 10/25/13 | 998 | Payroll Taxes | MO54 | Monico Brambila, Jesus S
T2252 | PR | 320 | 10/25/13 | 998 | Payroll Taxes | PA46 | Palma Vides, Hugo
T2253 | PR | 322 | 10/25/13 | 998 | Payroll Taxes | QU35 | Quintanilla, Esteban R
T2254 | PR | 322 | 10/25/13 | 998 | Payroll Taxes | QU35 | Quintanilla, Esteban R
T2255 | PR | 325 | 10/25/13 | 998 | Payroll Taxes | RI84 | Rivera, Eli P
T2256 | PR | 325 | 10/25/13 | 998 | Payroll Taxes | RI84 | Rivera, Eli P
T2257 | PR | 326 | 10/25/13 | 998 | Payroll Taxes | RI87 | Rivera, Jorge A
T2258 | PR | 326 | 10/25/13 | 998 | Payroll Taxes | RI87 | Rivera, Jorge A
T2259 | PR | 330 | 10/25/13 | 998 | Payroll Taxes | SE64 | Sepulveda Gonzalez, Alfredo
T2260 | PR | 330 | 10/25/13 | 998 | Payroll Taxes | SE64 | Sepulveda Gonzalez, Alfredo
T2261 | PR | 334 | 10/25/13 | 998 | Payroll Taxes | VE25 | Vega Arriaga, Jorge
T2262 | PR | 334 | 10/25/13 | 998 | Payroll Taxes | VE25 | Vega Arriaga, Jorge
T2263 | PR | 399 | 10/31/13 | 998 | Payroll Taxes | CA74 | Castaneda Martinez, Gustavo
T2264 | PR | 399 | 10/31/13 | 998 | Payroll Taxes | CA74 | Castaneda Martinez, Gustavo
T2265 | PR | 401 | 10/31/13 | 998 | Payroll Taxes | CA77 | Castro Hernandez, Jose A
T2266 | PR | 401 | 10/31/13 | 998 | Payroll Taxes | CA77 | Castro Hernandez, Jose A
T2267 | PR | 402 | 10/31/13 | 998 | Payroll Taxes | CH04 | Chavarria Lopez, Omar A
T2268 | PR | 404 | 10/31/13 | 998 | Payroll Taxes | CO71 | Cortes Mendiola, Victor H
T2269 | PR | 404 | 10/31/13 | 998 | Payroll Taxes | CO71 | Cortes Mendiola, Victor H
T2270 | PR | 407 | 10/31/13 | 998 | Payroll Taxes | GE69 | Gerard, Jeffrey S
T2271 | PR | 407 | 10/31/13 | 998 | Payroll Taxes | GE69 | Gerard, Jeffrey S
T2272 | PR | 408 | 10/31/13 | 998 | Payroll Taxes | GO56 | Gonzalez Hernandez, Josue
T2273 | PR | 408 | 10/31/13 | 998 | Payroll Taxes | GO56 | Gonzalez Hernandez, Josue
T2274 | PR | 414 | 10/31/13 | 998 | Payroll Taxes | LI49 | Lima Romero, Melvin A
T2275 | PR | 414 | 10/31/13 | 998 | Payroll Taxes | LI49 | Lima Romero, Melvin A
T2276 | PR | 415 | 10/31/13 | 998 | Payroll Taxes | MC09 | McCabe, Thomas C
T2277 | PR | 415 | 10/31/13 | 998 | Payroll Taxes | MC09 | McCabe, Thomas C
T2278 | PR | 417 | 10/31/13 | 998 | Payroll Taxes | MO54 | Monico Brambila, Jesus S
T2279 | PR | 417 | 10/31/13 | 998 | Payroll Taxes | MO54 | Monico Brambila, Jesus S
T2280 | PR | 420 | 10/31/13 | 998 | Payroll Taxes | PA46 | Palma Vides, Hugo
T2281 | PR | 420 | 10/31/13 | 998 | Payroll Taxes | PA46 | Palma Vides, Hugo
T2282 | PR | 422 | 10/31/13 | 998 | Payroll Taxes | QU35 | Quintanilla, Esteban R
T2283 | PR | 425 | 10/31/13 | 998 | Payroll Taxes | RI84 | Rivera, Eli P
T2284 | PR | 425 | 10/31/13 | 998 | Payroll Taxes | RI84 | Rivera, Eli P
T2285 | PR | 426 | 10/31/13 | 998 | Payroll Taxes | RI87 | Rivera, Jorge A
T2286 | PR | 430 | 10/31/13 | 998 | Payroll Taxes | SE64 | Sepulveda Gonzalez, Alfredo
T2287 | PR | 430 | 10/31/13 | 998 | Payroll Taxes | SE64 | Sepulveda Gonzalez, Alfredo
T2288 | PR | 434 | 10/31/13 | 998 | Payroll Taxes | VE25 | Vega Arriaga, Jorge
T2289 | PR | 101 | 11/08/13 | 998 | Payroll Taxes | CA74 | Castaneda Martinez, Gustavo
T2290 | PR | 101 | 11/08/13 | 998 | Payroll Taxes | CA74 | Castaneda Martinez, Gustavo
T2291 | PR | 103 | 11/08/13 | 998 | Payroll Taxes | CA77 | Castro Hernandez, Jose A
T2292 | PR | 103 | 11/08/13 | 998 | Payroll Taxes | CA77 | Castro Hernandez, Jose A
T2293 | PR | 104 | 11/08/13 | 998 | Payroll Taxes | CH04 | Chavarria Lopez, Omar A
T2294 | PR | 104 | 11/08/13 | 998 | Payroll Taxes | CH04 | Chavarria Lopez, Omar A
T2295 | PR | 109 | 11/08/13 | 998 | Payroll Taxes | GE69 | Gerard, Jeffrey S
T2296 | PR | 109 | 11/08/13 | 998 | Payroll Taxes | GE69 | Gerard, Jeffrey S
T2297 | PR | 110 | 11/08/13 | 998 | Payroll Taxes | GO56 | Gonzalez Hernandez, Josue
T2298 | PR | 110 | 11/08/13 | 998 | Payroll Taxes | GO56 | Gonzalez Hernandez, Josue
T2299 | PR | 116 | 11/08/13 | 998 | Payroll Taxes | LI49 | Lima Romero, Melvin A
T2300 | PR | 116 | 11/08/13 | 998 | Payroll Taxes | LI49 | Lima Romero, Melvin A
T2301 | PR | 119 | 11/08/13 | 998 | Payroll Taxes | MO54 | Monico Brambila, Jesus S
T2302 | PR | 119 | 11/08/13 | 998 | Payroll Taxes | MO54 | Monico Brambila, Jesus S
T2303 | PR | 122 | 11/08/13 | 998 | Payroll Taxes | PA46 | Palma Vides, Hugo
T2304 | PR | 122 | 11/08/13 | 998 | Payroll Taxes | PA46 | Palma Vides, Hugo
T2305 | PR | 124 | 11/08/13 | 998 | Payroll Taxes | QU35 | Quintanilla, Esteban R
T2306 | PR | 127 | 11/08/13 | 998 | Payroll Taxes | RI84 | Rivera, Eli P
T2307 | PR | 127 | 11/08/13 | 998 | Payroll Taxes | RI84 | Rivera, Eli P
T2308 | PR | 128 | 11/08/13 | 998 | Payroll Taxes | RI87 | Rivera, Jorge A
T2309 | PR | 128 | 11/08/13 | 998 | Payroll Taxes | RI87 | Rivera, Jorge A
T2310 | PR | 136 | 11/08/13 | 998 | Payroll Taxes | VE25 | Vega Arriaga, Jorge
T2311 | PR | 137 | 11/08/13 | 998 | Payroll Taxes | VE42 | Velasquez Cruz, Denis M
T2312 | PR | 188 | 11/15/13 | 998 | Payroll Taxes | CA74 | Castaneda Martinez, Gustavo
T2313 | PR | 190 | 11/15/13 | 998 | Payroll Taxes | CA77 | Castro Hernandez, Jose A
T2314 | PR | 190 | 11/15/13 | 998 | Payroll Taxes | CA77 | Castro Hernandez, Jose A
T2315 | PR | 191 | 11/15/13 | 998 | Payroll Taxes | CH04 | Chavarria Lopez, Omar A
T2316 | PR | 191 | 11/15/13 | 998 | Payroll Taxes | CH04 | Chavarria Lopez, Omar A
T2317 | PR | 196 | 11/15/13 | 998 | Payroll Taxes | GE69 | Gerard, Jeffrey S
T2318 | PR | 196 | 11/15/13 | 998 | Payroll Taxes | GE69 | Gerard, Jeffrey S
T2319 | PR | 197 | 11/15/13 | 998 | Payroll Taxes | GO56 | Gonzalez Hernandez, Josue
T2320 | PR | 197 | 11/15/13 | 998 | Payroll Taxes | GO56 | Gonzalez Hernandez, Josue
T2321 | PR | 203 | 11/15/13 | 998 | Payroll Taxes | LI49 | Lima Romero, Melvin A
T2322 | PR | 203 | 11/15/13 | 998 | Payroll Taxes | LI49 | Lima Romero, Melvin A
T2323 | PR | 206 | 11/15/13 | 998 | Payroll Taxes | MO54 | Monico Brambila, Jesus S
T2324 | PR | 206 | 11/15/13 | 998 | Payroll Taxes | MO54 | Monico Brambila, Jesus S
T2325 | PR | 209 | 11/15/13 | 998 | Payroll Taxes | PA46 | Palma Vides, Hugo
T2326 | PR | 209 | 11/15/13 | 998 | Payroll Taxes | PA46 | Palma Vides, Hugo
T2327 | PR | 211 | 11/15/13 | 998 | Payroll Taxes | QU35 | Quintanilla, Esteban R
T2328 | PR | 214 | 11/15/13 | 998 | Payroll Taxes | RI84 | Rivera, Eli P
T2329 | PR | 214 | 11/15/13 | 998 | Payroll Taxes | RI84 | Rivera, Eli P
T2330 | PR | 215 | 11/15/13 | 998 | Payroll Taxes | RI87 | Rivera, Jorge A
T2331 | PR | 215 | 11/15/13 | 998 | Payroll Taxes | RI87 | Rivera, Jorge A
T2332 | PR | 224 | 11/15/13 | 998 | Payroll Taxes | VE42 | Velasquez Cruz, Denis M
T2333 | PR | 224 | 11/15/13 | 998 | Payroll Taxes | VE42 | Velasquez Cruz, Denis M
T2334 | PR | 268 | 11/22/13 | 998 | Payroll Taxes | CA74 | Castaneda Martinez, Gustavo
T2335 | PR | 268 | 11/22/13 | 998 | Payroll Taxes | CA74 | Castaneda Martinez, Gustavo
T2336 | PR | 270 | 11/22/13 | 998 | Payroll Taxes | CA77 | Castro Hernandez, Jose A
T2337 | PR | 270 | 11/22/13 | 998 | Payroll Taxes | CA77 | Castro Hernandez, Jose A
T2338 | PR | 271 | 11/22/13 | 998 | Payroll Taxes | CH04 | Chavarria Lopez, Omar A
T2339 | PR | 271 | 11/22/13 | 998 | Payroll Taxes | CH04 | Chavarria Lopez, Omar A
T2340 | PR | 276 | 11/22/13 | 998 | Payroll Taxes | GE69 | Gerard, Jeffrey S
T2341 | PR | 276 | 11/22/13 | 998 | Payroll Taxes | GE69 | Gerard, Jeffrey S
T2342 | PR | 277 | 11/22/13 | 998 | Payroll Taxes | GO56 | Gonzalez Hernandez, Josue
T2343 | PR | 277 | 11/22/13 | 998 | Payroll Taxes | GO56 | Gonzalez Hernandez, Josue
T2344 | PR | 282 | 11/22/13 | 998 | Payroll Taxes | LI49 | Lima Romero, Melvin A
T2345 | PR | 282 | 11/22/13 | 998 | Payroll Taxes | LI49 | Lima Romero, Melvin A
T2346 | PR | 283 | 11/22/13 | 998 | Payroll Taxes | LO55 | Lopez Martinez, Abimael
T2347 | PR | 285 | 11/22/13 | 998 | Payroll Taxes | ME98 | Meza Fuentes, Erick A
T2348 | PR | 286 | 11/22/13 | 998 | Payroll Taxes | MO54 | Monico Brambila, Jesus S
T2349 | PR | 286 | 11/22/13 | 998 | Payroll Taxes | MO54 | Monico Brambila, Jesus S
T2350 | PR | 289 | 11/22/13 | 998 | Payroll Taxes | PA46 | Palma Vides, Hugo
T2351 | PR | 289 | 11/22/13 | 998 | Payroll Taxes | PA46 | Palma Vides, Hugo
T2352 | PR | 290 | 11/22/13 | 998 | Payroll Taxes | QU35 | Quintanilla, Esteban R
T2353 | PR | 290 | 11/22/13 | 998 | Payroll Taxes | QU35 | Quintanilla, Esteban R
T2354 | PR | 293 | 11/22/13 | 998 | Payroll Taxes | RI84 | Rivera, Eli P
T2355 | PR | 293 | 11/22/13 | 998 | Payroll Taxes | RI84 | Rivera, Eli P
T2356 | PR | 294 | 11/22/13 | 998 | Payroll Taxes | RI87 | Rivera, Jorge A
T2357 | PR | 294 | 11/22/13 | 998 | Payroll Taxes | RI87 | Rivera, Jorge A
T2358 | PR | 297 | 11/22/13 | 998 | Payroll Taxes | SA54 | Sanders, Allen O
T2359 | PR | 304 | 11/22/13 | 998 | Payroll Taxes | VE42 | Velasquez Cruz, Denis M
T2360 | PR | 304 | 11/22/13 | 998 | Payroll Taxes | VE42 | Velasquez Cruz, Denis M
T2361 | PR | 391 | 11/27/13 | 998 | Payroll Taxes | CA77 | Castro Hernandez, Jose A
T2362 | PR | 391 | 11/27/13 | 998 | Payroll Taxes | CA77 | Castro Hernandez, Jose A
T2363 | PR | 392 | 11/27/13 | 998 | Payroll Taxes | CH04 | Chavarria Lopez, Omar A
T2364 | PR | 392 | 11/27/13 | 998 | Payroll Taxes | CH04 | Chavarria Lopez, Omar A
T2365 | PR | 392 | 11/27/13 | 998 | Payroll Taxes | CH04 | Chavarria Lopez, Omar A
T2366 | PR | 392 | 11/27/13 | 998 | Payroll Taxes | CH04 | Chavarria Lopez, Omar A
T2367 | PR | 397 | 11/27/13 | 998 | Payroll Taxes | GE69 | Gerard, Jeffrey S
T2368 | PR | 397 | 11/27/13 | 998 | Payroll Taxes | GE69 | Gerard, Jeffrey S
T2369 | PR | 397 | 11/27/13 | 998 | Payroll Taxes | GE69 | Gerard, Jeffrey S
T2370 | PR | 398 | 11/27/13 | 998 | Payroll Taxes | GO56 | Gonzalez Hernandez, Josue
T2371 | PR | 398 | 11/27/13 | 998 | Payroll Taxes | GO56 | Gonzalez Hernandez, Josue
T2372 | PR | 398 | 11/27/13 | 998 | Payroll Taxes | GO56 | Gonzalez Hernandez, Josue
T2373 | PR | 403 | 11/27/13 | 998 | Payroll Taxes | LI49 | Lima Romero, Melvin A
T2374 | PR | 403 | 11/27/13 | 998 | Payroll Taxes | LI49 | Lima Romero, Melvin A
T2375 | PR | 403 | 11/27/13 | 998 | Payroll Taxes | LI49 | Lima Romero, Melvin A
T2376 | PR | 403 | 11/27/13 | 998 | Payroll Taxes | LI49 | Lima Romero, Melvin A
T2377 | PR | 404 | 11/27/13 | 998 | Payroll Taxes | LO55 | Lopez Martinez, Abimael
T2378 | PR | 404 | 11/27/13 | 998 | Payroll Taxes | LO55 | Lopez Martinez, Abimael
T2379 | PR | 407 | 11/27/13 | 998 | Payroll Taxes | MO54 | Monico Brambila, Jesus S
T2380 | PR | 407 | 11/27/13 | 998 | Payroll Taxes | MO54 | Monico Brambila, Jesus S
T2381 | PR | 407 | 11/27/13 | 998 | Payroll Taxes | MO54 | Monico Brambila, Jesus S
T2382 | PR | 407 | 11/27/13 | 998 | Payroll Taxes | MO54 | Monico Brambila, Jesus S
T2383 | PR | 410 | 11/27/13 | 998 | Payroll Taxes | PA46 | Palma Vides, Hugo
T2384 | PR | 410 | 11/27/13 | 998 | Payroll Taxes | PA46 | Palma Vides, Hugo
T2385 | PR | 410 | 11/27/13 | 998 | Payroll Taxes | PA46 | Palma Vides, Hugo
T2386 | PR | 410 | 11/27/13 | 998 | Payroll Taxes | PA46 | Palma Vides, Hugo
T2387 | PR | 411 | 11/27/13 | 998 | Payroll Taxes | QU35 | Quintanilla, Esteban R
T2388 | PR | 411 | 11/27/13 | 998 | Payroll Taxes | QU35 | Quintanilla, Esteban R
T2389 | PR | 411 | 11/27/13 | 998 | Payroll Taxes | QU35 | Quintanilla, Esteban R
T2390 | PR | 411 | 11/27/13 | 998 | Payroll Taxes | QU35 | Quintanilla, Esteban R
T2391 | PR | 414 | 11/27/13 | 998 | Payroll Taxes | RI84 | Rivera, Eli P
T2392 | PR | 414 | 11/27/13 | 998 | Payroll Taxes | RI84 | Rivera, Eli P
T2393 | PR | 414 | 11/27/13 | 998 | Payroll Taxes | RI84 | Rivera, Eli P
T2394 | PR | 415 | 11/27/13 | 998 | Payroll Taxes | RI87 | Rivera, Jorge A
T2395 | PR | 415 | 11/27/13 | 998 | Payroll Taxes | RI87 | Rivera, Jorge A
T2396 | PR | 438 | 11/30/13 | 998 | Payroll Taxes | AG52 | Agustin Rodriguez, Ezequiel
T2397 | PR | 446 | 11/30/13 | 998 | Payroll Taxes | CA77 | Castro Hernandez, Jose A
T2398 | PR | 447 | 11/30/13 | 998 | Payroll Taxes | CH04 | Chavarria Lopez, Omar A
T2399 | PR | 447 | 11/30/13 | 998 | Payroll Taxes | CH04 | Chavarria Lopez, Omar A
T2400 | PR | 452 | 11/30/13 | 998 | Payroll Taxes | GE69 | Gerard, Jeffrey S
T2401 | PR | 453 | 11/30/13 | 998 | Payroll Taxes | GO56 | Gonzalez Hernandez, Josue
T2402 | PR | 458 | 11/30/13 | 998 | Payroll Taxes | LI49 | Lima Romero, Melvin A
T2403 | PR | 459 | 11/30/13 | 998 | Payroll Taxes | LO55 | Lopez Martinez, Abimael
T2404 | PR | 462 | 11/30/13 | 998 | Payroll Taxes | MO54 | Monico Brambila, Jesus S
T2405 | PR | 465 | 11/30/13 | 998 | Payroll Taxes | PA46 | Palma Vides, Hugo
T2406 | PR | 466 | 11/30/13 | 998 | Payroll Taxes | QU35 | Quintanilla, Esteban R
T2407 | PR | 466 | 11/30/13 | 998 | Payroll Taxes | QU35 | Quintanilla, Esteban R
T2408 | PR | 468 | 11/30/13 | 998 | Payroll Taxes | RI84 | Rivera, Eli P
T2409 | PR | 469 | 11/30/13 | 998 | Payroll Taxes | RI87 | Rivera, Jorge A
T2410 | PR | 48 | 12/13/13 | 998 | Payroll Taxes | AG52 | Agustin Rodriguez, Ezequiel
T2411 | PR | 48 | 12/13/13 | 998 | Payroll Taxes | AG52 | Agustin Rodriguez, Ezequiel
T2412 | PR | 55 | 12/13/13 | 998 | Payroll Taxes | CA75 | Castro Hernandez, Carlos E
T2413 | PR | 56 | 12/13/13 | 998 | Payroll Taxes | CA77 | Castro Hernandez, Jose A
T2414 | PR | 56 | 12/13/13 | 998 | Payroll Taxes | CA77 | Castro Hernandez, Jose A
T2415 | PR | 56 | 12/13/13 | 998 | Payroll Taxes | CA77 | Castro Hernandez, Jose A
T2416 | PR | 57 | 12/13/13 | 998 | Payroll Taxes | CH04 | Chavarria Lopez, Omar A
T2417 | PR | 57 | 12/13/13 | 998 | Payroll Taxes | CH04 | Chavarria Lopez, Omar A
T2418 | PR | 57 | 12/13/13 | 998 | Payroll Taxes | CH04 | Chavarria Lopez, Omar A
T2419 | PR | 57 | 12/13/13 | 998 | Payroll Taxes | CH04 | Chavarria Lopez, Omar A
T2420 | PR | 61 | 12/13/13 | 998 | Payroll Taxes | GE69 | Gerard, Jeffrey S
T2421 | PR | 62 | 12/13/13 | 998 | Payroll Taxes | GO56 | Gonzalez Hernandez, Josue
T2422 | PR | 62 | 12/13/13 | 998 | Payroll Taxes | GO56 | Gonzalez Hernandez, Josue
T2423 | PR | 62 | 12/13/13 | 998 | Payroll Taxes | GO56 | Gonzalez Hernandez, Josue
T2424 | PR | 62 | 12/13/13 | 998 | Payroll Taxes | GO56 | Gonzalez Hernandez, Josue
T2425 | PR | 67 | 12/13/13 | 998 | Payroll Taxes | LI49 | Lima Romero, Melvin A
T2426 | PR | 67 | 12/13/13 | 998 | Payroll Taxes | LI49 | Lima Romero, Melvin A
T2427 | PR | 67 | 12/13/13 | 998 | Payroll Taxes | LI49 | Lima Romero, Melvin A
T2428 | PR | 68 | 12/13/13 | 998 | Payroll Taxes | LO55 | Lopez Martinez, Abimael
T2429 | PR | 68 | 12/13/13 | 998 | Payroll Taxes | LO55 | Lopez Martinez, Abimael
T2430 | PR | 71 | 12/13/13 | 998 | Payroll Taxes | MO54 | Monico Brambila, Jesus S
T2431 | PR | 71 | 12/13/13 | 998 | Payroll Taxes | MO54 | Monico Brambila, Jesus S
T2432 | PR | 71 | 12/13/13 | 998 | Payroll Taxes | MO54 | Monico Brambila, Jesus S
T2433 | PR | 74 | 12/13/13 | 998 | Payroll Taxes | PA46 | Palma Vides, Hugo
T2434 | PR | 74 | 12/13/13 | 998 | Payroll Taxes | PA46 | Palma Vides, Hugo
T2435 | PR | 74 | 12/13/13 | 998 | Payroll Taxes | PA46 | Palma Vides, Hugo
T2436 | PR | 75 | 12/13/13 | 998 | Payroll Taxes | QU35 | Quintanilla, Esteban R
T2437 | PR | 75 | 12/13/13 | 998 | Payroll Taxes | QU35 | Quintanilla, Esteban R
T2438 | PR | 75 | 12/13/13 | 998 | Payroll Taxes | QU35 | Quintanilla, Esteban R
T2439 | PR | 75 | 12/13/13 | 998 | Payroll Taxes | QU35 | Quintanilla, Esteban R
T2440 | PR | 77 | 12/13/13 | 998 | Payroll Taxes | RI84 | Rivera, Eli P
T2441 | PR | 77 | 12/13/13 | 998 | Payroll Taxes | RI84 | Rivera, Eli P
T2442 | PR | 77 | 12/13/13 | 998 | Payroll Taxes | RI84 | Rivera, Eli P
T2443 | PR | 78 | 12/13/13 | 998 | Payroll Taxes | RI87 | Rivera, Jorge A
T2444 | PR | 78 | 12/13/13 | 998 | Payroll Taxes | RI87 | Rivera, Jorge A
T2445 | PR | 78 | 12/13/13 | 998 | Payroll Taxes | RI87 | Rivera, Jorge A
T2446 | PR | 78 | 12/13/13 | 998 | Payroll Taxes | RI87 | Rivera, Jorge A
T2447 | PR | 231 | 12/20/13 | 998 | Payroll Taxes | AG52 | Agustin Rodriguez, Ezequiel
T2448 | PR | 231 | 12/20/13 | 998 | Payroll Taxes | AG52 | Agustin Rodriguez, Ezequiel
T2449 | PR | 238 | 12/20/13 | 998 | Payroll Taxes | CA75 | Castro Hernandez, Carlos E
T2450 | PR | 238 | 12/20/13 | 998 | Payroll Taxes | CA75 | Castro Hernandez, Carlos E
T2451 | PR | 238 | 12/20/13 | 998 | Payroll Taxes | CA75 | Castro Hernandez, Carlos E
T2452 | PR | 238 | 12/20/13 | 998 | Payroll Taxes | CA75 | Castro Hernandez, Carlos E
T2453 | PR | 239 | 12/20/13 | 998 | Payroll Taxes | CA77 | Castro Hernandez, Jose A
T2454 | PR | 239 | 12/20/13 | 998 | Payroll Taxes | CA77 | Castro Hernandez, Jose A
T2455 | PR | 240 | 12/20/13 | 998 | Payroll Taxes | CH04 | Chavarria Lopez, Omar A
T2456 | PR | 240 | 12/20/13 | 998 | Payroll Taxes | CH04 | Chavarria Lopez, Omar A
T2457 | PR | 245 | 12/20/13 | 998 | Payroll Taxes | GE69 | Gerard, Jeffrey S
T2458 | PR | 246 | 12/20/13 | 998 | Payroll Taxes | GO56 | Gonzalez Hernandez, Josue
T2459 | PR | 246 | 12/20/13 | 998 | Payroll Taxes | GO56 | Gonzalez Hernandez, Josue
T2460 | PR | 251 | 12/20/13 | 998 | Payroll Taxes | LI49 | Lima Romero, Melvin A
T2461 | PR | 251 | 12/20/13 | 998 | Payroll Taxes | LI49 | Lima Romero, Melvin A
T2462 | PR | 252 | 12/20/13 | 998 | Payroll Taxes | LO55 | Lopez Martinez, Abimael
T2463 | PR | 252 | 12/20/13 | 998 | Payroll Taxes | LO55 | Lopez Martinez, Abimael
T2464 | PR | 255 | 12/20/13 | 998 | Payroll Taxes | MO54 | Monico Brambila, Jesus S
T2465 | PR | 255 | 12/20/13 | 998 | Payroll Taxes | MO54 | Monico Brambila, Jesus S
T2466 | PR | 258 | 12/20/13 | 998 | Payroll Taxes | PA46 | Palma Vides, Hugo
T2467 | PR | 258 | 12/20/13 | 998 | Payroll Taxes | PA46 | Palma Vides, Hugo
T2468 | PR | 259 | 12/20/13 | 998 | Payroll Taxes | QU35 | Quintanilla, Esteban R
T2469 | PR | 259 | 12/20/13 | 998 | Payroll Taxes | QU35 | Quintanilla, Esteban R
T2470 | PR | 261 | 12/20/13 | 998 | Payroll Taxes | RI84 | Rivera, Eli P
T2471 | PR | 261 | 12/20/13 | 998 | Payroll Taxes | RI84 | Rivera, Eli P
T2472 | PR | 261 | 12/20/13 | 998 | Payroll Taxes | RI84 | Rivera, Eli P
T2473 | PR | 262 | 12/20/13 | 998 | Payroll Taxes | RI87 | Rivera, Jorge A
T2474 | PR | 262 | 12/20/13 | 998 | Payroll Taxes | RI87 | Rivera, Jorge A
T2475 | PR | 262 | 12/20/13 | 998 | Payroll Taxes | RI87 | Rivera, Jorge A
T2476 | PR | 262 | 12/20/13 | 998 | Payroll Taxes | RI87 | Rivera, Jorge A
T2477 | PR | 265 | 12/20/13 | 998 | Payroll Taxes | SA52 | Sanchez Garcia, Adelaido
T2478 | PR | 327 | 12/27/13 | 998 | Payroll Taxes | AG52 | Agustin Rodriguez, Ezequiel
T2479 | PR | 334 | 12/27/13 | 998 | Payroll Taxes | CA75 | Castro Hernandez, Carlos E
T2480 | PR | 335 | 12/27/13 | 998 | Payroll Taxes | CA77 | Castro Hernandez, Jose A
T2481 | PR | 336 | 12/27/13 | 998 | Payroll Taxes | CH04 | Chavarria Lopez, Omar A
T2482 | PR | 341 | 12/27/13 | 998 | Payroll Taxes | GE69 | Gerard, Jeffrey S
T2483 | PR | 342 | 12/27/13 | 998 | Payroll Taxes | GO56 | Gonzalez Hernandez, Josue
T2484 | PR | 347 | 12/27/13 | 998 | Payroll Taxes | LI49 | Lima Romero, Melvin A
T2485 | PR | 348 | 12/27/13 | 998 | Payroll Taxes | LO55 | Lopez Martinez, Abimael
T2486 | PR | 351 | 12/27/13 | 998 | Payroll Taxes | MO54 | Monico Brambila, Jesus S
T2487 | PR | 354 | 12/27/13 | 998 | Payroll Taxes | PA46 | Palma Vides, Hugo
T2488 | PR | 355 | 12/27/13 | 998 | Payroll Taxes | QU35 | Quintanilla, Esteban R
T2489 | PR | 356 | 12/27/13 | 998 | Payroll Taxes | RA54 | Ramos Garcia, Jose M
T2490 | PR | 358 | 12/27/13 | 998 | Payroll Taxes | RI84 | Rivera, Eli P
T2491 | PR | 358 | 12/27/13 | 998 | Payroll Taxes | RI84 | Rivera, Eli P
T2492 | PR | 359 | 12/27/13 | 998 | Payroll Taxes | RI87 | Rivera, Jorge A
T2493 | PR | 362 | 12/27/13 | 998 | Payroll Taxes | SA52 | Sanchez Garcia, Adelaido
T2494 | PR | 8 | 01/03/14 | 998 | Payroll Taxes | CA75 | Castro Hernandez, Carlos E
T2495 | PR | 8 | 01/03/14 | 998 | Payroll Taxes | CA75 | Castro Hernandez, Carlos E
T2496 | PR | 9 | 01/03/14 | 998 | Payroll Taxes | CA77 | Castro Hernandez, Jose A
T2497 | PR | 9 | 01/03/14 | 998 | Payroll Taxes | CA77 | Castro Hernandez, Jose A
T2498 | PR | 10 | 01/03/14 | 998 | Payroll Taxes | CH04 | Chavarria Lopez, Omar A
T2499 | PR | 10 | 01/03/14 | 998 | Payroll Taxes | CH04 | Chavarria Lopez, Omar A
T2500 | PR | 16 | 01/03/14 | 998 | Payroll Taxes | GO56 | Gonzalez Hernandez, Josue
T2501 | PR | 16 | 01/03/14 | 998 | Payroll Taxes | GO56 | Gonzalez Hernandez, Josue
T2502 | PR | 21 | 01/03/14 | 998 | Payroll Taxes | LI49 | Lima Romero, Melvin A
T2503 | PR | 22 | 01/03/14 | 998 | Payroll Taxes | LO55 | Lopez Martinez, Abimael
T2504 | PR | 22 | 01/03/14 | 998 | Payroll Taxes | LO55 | Lopez Martinez, Abimael
T2505 | PR | 25 | 01/03/14 | 998 | Payroll Taxes | MO54 | Monico Brambila, Jesus S
T2506 | PR | 25 | 01/03/14 | 998 | Payroll Taxes | MO54 | Monico Brambila, Jesus S
T2507 | PR | 28 | 01/03/14 | 998 | Payroll Taxes | PA46 | Palma Vides, Hugo
T2508 | PR | 28 | 01/03/14 | 998 | Payroll Taxes | PA46 | Palma Vides, Hugo
T2509 | PR | 29 | 01/03/14 | 998 | Payroll Taxes | QU35 | Quintanilla, Esteban R
T2510 | PR | 29 | 01/03/14 | 998 | Payroll Taxes | QU35 | Quintanilla, Esteban R
T2511 | PR | 30 | 01/03/14 | 998 | Payroll Taxes | RA54 | Ramos Garcia, Jose M
T2512 | PR | 30 | 01/03/14 | 998 | Payroll Taxes | RA54 | Ramos Garcia, Jose M
T2513 | PR | 32 | 01/03/14 | 998 | Payroll Taxes | RI84 | Rivera, Eli P
T2514 | PR | 32 | 01/03/14 | 998 | Payroll Taxes | RI84 | Rivera, Eli P
T2515 | PR | 33 | 01/03/14 | 998 | Payroll Taxes | RI87 | Rivera, Jorge A
T2516 | PR | 36 | 01/03/14 | 998 | Payroll Taxes | SA52 | Sanchez Garcia, Adelaido
T2517 | PR | 134 | 01/10/14 | 998 | Payroll Taxes | AG52 | Agustin Rodriguez, Ezequiel
T2518 | PR | 139 | 01/10/14 | 998 | Payroll Taxes | CA73 | Castaneda Juarez, Gustavo
T2519 | PR | 141 | 01/10/14 | 998 | Payroll Taxes | CA75 | Castro Hernandez, Carlos E
T2520 | PR | 141 | 01/10/14 | 998 | Payroll Taxes | CA75 | Castro Hernandez, Carlos E
T2521 | PR | 142 | 01/10/14 | 998 | Payroll Taxes | CA77 | Castro Hernandez, Jose A
T2522 | PR | 142 | 01/10/14 | 998 | Payroll Taxes | CA77 | Castro Hernandez, Jose A
T2523 | PR | 143 | 01/10/14 | 998 | Payroll Taxes | CH04 | Chavarria Lopez, Omar A
T2524 | PR | 143 | 01/10/14 | 998 | Payroll Taxes | CH04 | Chavarria Lopez, Omar A
T2525 | PR | 148 | 01/10/14 | 998 | Payroll Taxes | GE69 | Gerard, Jeffrey S
T2526 | PR | 149 | 01/10/14 | 998 | Payroll Taxes | GO56 | Gonzalez Hernandez, Josue
T2527 | PR | 154 | 01/10/14 | 998 | Payroll Taxes | LI49 | Lima Romero, Melvin A
T2528 | PR | 155 | 01/10/14 | 998 | Payroll Taxes | LO55 | Lopez Martinez, Abimael
T2529 | PR | 161 | 01/10/14 | 998 | Payroll Taxes | PA46 | Palma Vides, Hugo
T2530 | PR | 161 | 01/10/14 | 998 | Payroll Taxes | PA46 | Palma Vides, Hugo
T2531 | PR | 162 | 01/10/14 | 998 | Payroll Taxes | QU35 | Quintanilla, Esteban R
T2532 | PR | 162 | 01/10/14 | 998 | Payroll Taxes | QU35 | Quintanilla, Esteban R
T2533 | PR | 163 | 01/10/14 | 998 | Payroll Taxes | RA54 | Ramos Garcia, Jose M
T2534 | PR | 165 | 01/10/14 | 998 | Payroll Taxes | RI84 | Rivera, Eli P
T2535 | PR | 165 | 01/10/14 | 998 | Payroll Taxes | RI84 | Rivera, Eli P
T2536 | PR | 166 | 01/10/14 | 998 | Payroll Taxes | RI87 | Rivera, Jorge A
T2537 | PR | 169 | 01/10/14 | 998 | Payroll Taxes | SA52 | Sanchez Garcia, Adelaido
T2538 | PR | 175 | 01/10/14 | 998 | Payroll Taxes | VE25 | Vega Arriaga, Jorge
T2539 | PR | 287 | 01/17/14 | 998 | Payroll Taxes | CA77 | Castro Hernandez, Jose A
T2540 | PR | 288 | 01/17/14 | 998 | Payroll Taxes | CH04 | Chavarria Lopez, Omar A
T2541 | PR | 293 | 01/17/14 | 998 | Payroll Taxes | GE69 | Gerard, Jeffrey S
T2542 | PR | 294 | 01/17/14 | 998 | Payroll Taxes | GO56 | Gonzalez Hernandez, Josue
T2543 | PR | 299 | 01/17/14 | 998 | Payroll Taxes | LI49 | Lima Romero, Melvin A
T2544 | PR | 302 | 01/17/14 | 998 | Payroll Taxes | ME98 | Meza Fuentes, Erick A
T2545 | PR | 306 | 01/17/14 | 998 | Payroll Taxes | PA46 | Palma Vides, Hugo
T2546 | PR | 307 | 01/17/14 | 998 | Payroll Taxes | QU35 | Quintanilla, Esteban R
T2547 | PR | 308 | 01/17/14 | 998 | Payroll Taxes | RA54 | Ramos Garcia, Jose M
T2548 | PR | 310 | 01/17/14 | 998 | Payroll Taxes | RI84 | Rivera, Eli P
T2549 | PR | 314 | 01/17/14 | 998 | Payroll Taxes | SA52 | Sanchez Garcia, Adelaido
T2550 | PR | 315 | 01/17/14 | 998 | Payroll Taxes | SA54 | Sanders, Allen O
T2551 | PR | 318 | 01/17/14 | 998 | Payroll Taxes | SO79 | Soto Serna, Cesar E
T2552 | PR | 320 | 01/17/14 | 998 | Payroll Taxes | VA86 | Vaughan, Tyler J
T2553 | PR | 324 | 01/17/14 | 998 | Payroll Taxes | WA35 | Waites, Thaddeus Z
T2554 | PR | 377 | 01/24/14 | 998 | Payroll Taxes | CA77 | Castro Hernandez, Jose A
T2555 | PR | 378 | 01/24/14 | 998 | Payroll Taxes | CH04 | Chavarria Lopez, Omar A
T2556 | PR | 383 | 01/24/14 | 998 | Payroll Taxes | GE69 | Gerard, Jeffrey S
T2557 | PR | 384 | 01/24/14 | 998 | Payroll Taxes | GO56 | Gonzalez Hernandez, Josue
T2558 | PR | 389 | 01/24/14 | 998 | Payroll Taxes | LI49 | Lima Romero, Melvin A
T2559 | PR | 392 | 01/24/14 | 998 | Payroll Taxes | ME98 | Meza Fuentes, Erick A
T2560 | PR | 397 | 01/24/14 | 998 | Payroll Taxes | QU35 | Quintanilla, Esteban R
T2561 | PR | 399 | 01/24/14 | 998 | Payroll Taxes | RA54 | Ramos Garcia, Jose M
T2562 | PR | 401 | 01/24/14 | 998 | Payroll Taxes | RI84 | Rivera, Eli P
T2563 | PR | 406 | 01/24/14 | 998 | Payroll Taxes | SA54 | Sanders, Allen O
T2564 | PR | 408 | 01/24/14 | 998 | Payroll Taxes | SO78 | Soto Cruz, Jovani
T2565 | PR | 409 | 01/24/14 | 998 | Payroll Taxes | SO79 | Soto Serna, Cesar E
T2566 | PR | 411 | 01/24/14 | 998 | Payroll Taxes | VA86 | Vaughan, Tyler J
T2567 | PR | 415 | 01/24/14 | 998 | Payroll Taxes | WA35 | Waites, Thaddeus Z
T2568 | PR | 575 | 01/31/14 | 998 | Payroll Taxes | CA77 | Castro Hernandez, Jose A
T2569 | PR | 575 | 01/31/14 | 998 | Payroll Taxes | CA77 | Castro Hernandez, Jose A
T2570 | PR | 576 | 01/31/14 | 998 | Payroll Taxes | CH04 | Chavarria Lopez, Omar A
T2571 | PR | 581 | 01/31/14 | 998 | Payroll Taxes | GE69 | Gerard, Jeffrey S
T2572 | PR | 581 | 01/31/14 | 998 | Payroll Taxes | GE69 | Gerard, Jeffrey S
T2573 | PR | 582 | 01/31/14 | 998 | Payroll Taxes | GO56 | Gonzalez Hernandez, Josue
T2574 | PR | 587 | 01/31/14 | 998 | Payroll Taxes | LI49 | Lima Romero, Melvin A
T2575 | PR | 590 | 01/31/14 | 998 | Payroll Taxes | ME98 | Meza Fuentes, Erick A
T2576 | PR | 595 | 01/31/14 | 998 | Payroll Taxes | QU35 | Quintanilla, Esteban R
T2577 | PR | 595 | 01/31/14 | 998 | Payroll Taxes | QU35 | Quintanilla, Esteban R
T2578 | PR | 595 | 01/31/14 | 998 | Payroll Taxes | QU35 | Quintanilla, Esteban R
T2579 | PR | 597 | 01/31/14 | 998 | Payroll Taxes | RA54 | Ramos Garcia, Jose M
T2580 | PR | 599 | 01/31/14 | 998 | Payroll Taxes | RI84 | Rivera, Eli P
T2581 | PR | 604 | 01/31/14 | 998 | Payroll Taxes | SA54 | Sanders, Allen O
T2582 | PR | 606 | 01/31/14 | 998 | Payroll Taxes | SO78 | Soto Cruz, Jovani
T2583 | PR | 607 | 01/31/14 | 998 | Payroll Taxes | SO79 | Soto Serna, Cesar E
T2584 | PR | 609 | 01/31/14 | 998 | Payroll Taxes | VA86 | Vaughan, Tyler J
T2585 | PR | 613 | 01/31/14 | 998 | Payroll Taxes | WA35 | Waites, Thaddeus Z
T2586 | PR | 25 | 02/07/14 | 998 | Payroll Taxes | CA77 | Castro Hernandez, Jose A
T2587 | PR | 26 | 02/07/14 | 998 | Payroll Taxes | CH04 | Chavarria Lopez, Omar A
T2588 | PR | 31 | 02/07/14 | 998 | Payroll Taxes | GE69 | Gerard, Jeffrey S
T2589 | PR | 31 | 02/07/14 | 998 | Payroll Taxes | GE69 | Gerard, Jeffrey S
T2590 | PR | 32 | 02/07/14 | 998 | Payroll Taxes | GO56 | Gonzalez Hernandez, Josue
T2591 | PR | 37 | 02/07/14 | 998 | Payroll Taxes | LI49 | Lima Romero, Melvin A
T2592 | PR | 39 | 02/07/14 | 998 | Payroll Taxes | MC09 | McCabe, Thomas C
T2593 | PR | 40 | 02/07/14 | 998 | Payroll Taxes | ME98 | Meza Fuentes, Erick A
T2594 | PR | 45 | 02/07/14 | 998 | Payroll Taxes | QU35 | Quintanilla, Esteban R
T2595 | PR | 45 | 02/07/14 | 998 | Payroll Taxes | QU35 | Quintanilla, Esteban R
T2596 | PR | 47 | 02/07/14 | 998 | Payroll Taxes | RA54 | Ramos Garcia, Jose M
T2597 | PR | 47 | 02/07/14 | 998 | Payroll Taxes | RA54 | Ramos Garcia, Jose M
T2598 | PR | 49 | 02/07/14 | 998 | Payroll Taxes | RI84 | Rivera, Eli P
T2599 | PR | 49 | 02/07/14 | 998 | Payroll Taxes | RI84 | Rivera, Eli P
T2600 | PR | 54 | 02/07/14 | 998 | Payroll Taxes | SA54 | Sanders, Allen O
T2601 | PR | 56 | 02/07/14 | 998 | Payroll Taxes | SO78 | Soto Cruz, Jovani
T2602 | PR | 57 | 02/07/14 | 998 | Payroll Taxes | SO79 | Soto Serna, Cesar E
T2603 | PR | 63 | 02/07/14 | 998 | Payroll Taxes | WA35 | Waites, Thaddeus Z
T2604 | PR | 63 | 02/07/14 | 998 | Payroll Taxes | WA35 | Waites, Thaddeus Z
T2605 | PR | 168 | 02/14/14 | 998 | Payroll Taxes | CA72 | Castaneda Juarez, Edgar D
T2606 | PR | 173 | 02/14/14 | 998 | Payroll Taxes | CH04 | Chavarria Lopez, Omar A
T2607 | PR | 178 | 02/14/14 | 998 | Payroll Taxes | GE69 | Gerard, Jeffrey S
T2608 | PR | 178 | 02/14/14 | 998 | Payroll Taxes | GE69 | Gerard, Jeffrey S
T2609 | PR | 179 | 02/14/14 | 998 | Payroll Taxes | GO56 | Gonzalez Hernandez, Josue
T2610 | PR | 179 | 02/14/14 | 998 | Payroll Taxes | GO56 | Gonzalez Hernandez, Josue
T2611 | PR | 184 | 02/14/14 | 998 | Payroll Taxes | LI49 | Lima Romero, Melvin A
T2612 | PR | 184 | 02/14/14 | 998 | Payroll Taxes | LI49 | Lima Romero, Melvin A
T2613 | PR | 186 | 02/14/14 | 998 | Payroll Taxes | MC09 | McCabe, Thomas C
T2614 | PR | 187 | 02/14/14 | 998 | Payroll Taxes | ME98 | Meza Fuentes, Erick A
T2615 | PR | 192 | 02/14/14 | 998 | Payroll Taxes | QU35 | Quintanilla, Esteban R
T2616 | PR | 195 | 02/14/14 | 998 | Payroll Taxes | RA54 | Ramos Garcia, Jose M
T2617 | PR | 195 | 02/14/14 | 998 | Payroll Taxes | RA54 | Ramos Garcia, Jose M
T2618 | PR | 202 | 02/14/14 | 998 | Payroll Taxes | SA54 | Sanders, Allen O
T2619 | PR | 204 | 02/14/14 | 998 | Payroll Taxes | SO78 | Soto Cruz, Jovani
T2620 | PR | 211 | 02/14/14 | 998 | Payroll Taxes | WA35 | Waites, Thaddeus Z
T2621 | PR | 278 | 02/21/14 | 998 | Payroll Taxes | CA72 | Castaneda Juarez, Edgar D
T2622 | PR | 286 | 02/21/14 | 998 | Payroll Taxes | GA70 | Garcia, Jordan X
T2623 | PR | 287 | 02/21/14 | 998 | Payroll Taxes | GE69 | Gerard, Jeffrey S
T2624 | PR | 287 | 02/21/14 | 998 | Payroll Taxes | GE69 | Gerard, Jeffrey S
T2625 | PR | 288 | 02/21/14 | 998 | Payroll Taxes | GO56 | Gonzalez Hernandez, Josue
T2626 | PR | 288 | 02/21/14 | 998 | Payroll Taxes | GO56 | Gonzalez Hernandez, Josue
T2627 | PR | 293 | 02/21/14 | 998 | Payroll Taxes | LI49 | Lima Romero, Melvin A
T2628 | PR | 293 | 02/21/14 | 998 | Payroll Taxes | LI49 | Lima Romero, Melvin A
T2629 | PR | 296 | 02/21/14 | 998 | Payroll Taxes | ME98 | Meza Fuentes, Erick A
T2630 | PR | 301 | 02/21/14 | 998 | Payroll Taxes | QU35 | Quintanilla, Esteban R
T2631 | PR | 304 | 02/21/14 | 998 | Payroll Taxes | RA54 | Ramos Garcia, Jose M
T2632 | PR | 304 | 02/21/14 | 998 | Payroll Taxes | RA54 | Ramos Garcia, Jose M
T2633 | PR | 311 | 02/21/14 | 998 | Payroll Taxes | SA54 | Sanders, Allen O
T2634 | PR | 320 | 02/21/14 | 998 | Payroll Taxes | WA35 | Waites, Thaddeus Z
T2635 | PR | 320 | 02/21/14 | 998 | Payroll Taxes | WA35 | Waites, Thaddeus Z
T2636 | PR | 321 | 02/21/14 | 998 | Payroll Taxes | WI46 | Wilson, Garret A
T2637 | PR | 368 | 02/28/14 | 998 | Payroll Taxes | BA70 | Barnhart, Joseph N
T2638 | PR | 370 | 02/28/14 | 998 | Payroll Taxes | CA72 | Castaneda Juarez, Edgar D
T2639 | PR | 378 | 02/28/14 | 998 | Payroll Taxes | GA70 | Garcia, Jordan X
T2640 | PR | 379 | 02/28/14 | 998 | Payroll Taxes | GE69 | Gerard, Jeffrey S
T2641 | PR | 379 | 02/28/14 | 998 | Payroll Taxes | GE69 | Gerard, Jeffrey S
T2642 | PR | 380 | 02/28/14 | 998 | Payroll Taxes | GO56 | Gonzalez Hernandez, Josue
T2643 | PR | 385 | 02/28/14 | 998 | Payroll Taxes | LI49 | Lima Romero, Melvin A
T2644 | PR | 385 | 02/28/14 | 998 | Payroll Taxes | LI49 | Lima Romero, Melvin A
T2645 | PR | 385 | 02/28/14 | 998 | Payroll Taxes | LI49 | Lima Romero, Melvin A
T2646 | PR | 388 | 02/28/14 | 998 | Payroll Taxes | ME98 | Meza Fuentes, Erick A
T2647 | PR | 393 | 02/28/14 | 998 | Payroll Taxes | QU35 | Quintanilla, Esteban R
T2648 | PR | 396 | 02/28/14 | 998 | Payroll Taxes | RA54 | Ramos Garcia, Jose M
T2649 | PR | 403 | 02/28/14 | 998 | Payroll Taxes | SA54 | Sanders, Allen O
T2650 | PR | 405 | 02/28/14 | 998 | Payroll Taxes | SO78 | Soto Cruz, Jovani
T2651 | PR | 412 | 02/28/14 | 998 | Payroll Taxes | WA35 | Waites, Thaddeus Z
T2652 | PR | 412 | 02/28/14 | 998 | Payroll Taxes | WA35 | Waites, Thaddeus Z
T2653 | PR | 413 | 02/28/14 | 998 | Payroll Taxes | WI46 | Wilson, Garret A
T2654 | PR | 7 | 03/07/14 | 998 | Payroll Taxes | CA72 | Castaneda Juarez, Edgar D
T2655 | PR | 16 | 03/07/14 | 998 | Payroll Taxes | GE69 | Gerard, Jeffrey S
T2656 | PR | 16 | 03/07/14 | 998 | Payroll Taxes | GE69 | Gerard, Jeffrey S
T2657 | PR | 17 | 03/07/14 | 998 | Payroll Taxes | GO56 | Gonzalez Hernandez, Josue
T2658 | PR | 17 | 03/07/14 | 998 | Payroll Taxes | GO56 | Gonzalez Hernandez, Josue
T2659 | PR | 17 | 03/07/14 | 998 | Payroll Taxes | GO56 | Gonzalez Hernandez, Josue
T2660 | PR | 22 | 03/07/14 | 998 | Payroll Taxes | LI49 | Lima Romero, Melvin A
T2661 | PR | 22 | 03/07/14 | 998 | Payroll Taxes | LI49 | Lima Romero, Melvin A
T2662 | PR | 25 | 03/07/14 | 998 | Payroll Taxes | ME98 | Meza Fuentes, Erick A
T2663 | PR | 30 | 03/07/14 | 998 | Payroll Taxes | QU35 | Quintanilla, Esteban R
T2664 | PR | 40 | 03/07/14 | 998 | Payroll Taxes | SA54 | Sanders, Allen O
T2665 | PR | 42 | 03/07/14 | 998 | Payroll Taxes | SO78 | Soto Cruz, Jovani
T2666 | PR | 43 | 03/07/14 | 998 | Payroll Taxes | SO79 | Soto Serna, Cesar E
T2667 | PR | 45 | 03/07/14 | 998 | Payroll Taxes | VA86 | Vaughan, Tyler J
T2668 | PR | 49 | 03/07/14 | 998 | Payroll Taxes | WA35 | Waites, Thaddeus Z
T2669 | PR | 49 | 03/07/14 | 998 | Payroll Taxes | WA35 | Waites, Thaddeus Z
T2670 | PR | 49 | 03/07/14 | 998 | Payroll Taxes | WA35 | Waites, Thaddeus Z
T2671 | PR | 187 | 03/14/14 | 998 | Payroll Taxes | CA72 | Castaneda Juarez, Edgar D
T2672 | PR | 196 | 03/14/14 | 998 | Payroll Taxes | GE69 | Gerard, Jeffrey S
T2673 | PR | 196 | 03/14/14 | 998 | Payroll Taxes | GE69 | Gerard, Jeffrey S
T2674 | PR | 197 | 03/14/14 | 998 | Payroll Taxes | GO56 | Gonzalez Hernandez, Josue
T2675 | PR | 197 | 03/14/14 | 998 | Payroll Taxes | GO56 | Gonzalez Hernandez, Josue
T2676 | PR | 197 | 03/14/14 | 998 | Payroll Taxes | GO56 | Gonzalez Hernandez, Josue
T2677 | PR | 202 | 03/14/14 | 998 | Payroll Taxes | LI49 | Lima Romero, Melvin A
T2678 | PR | 202 | 03/14/14 | 998 | Payroll Taxes | LI49 | Lima Romero, Melvin A
T2679 | PR | 205 | 03/14/14 | 998 | Payroll Taxes | ME98 | Meza Fuentes, Erick A
T2680 | PR | 210 | 03/14/14 | 998 | Payroll Taxes | QU35 | Quintanilla, Esteban R
T2681 | PR | 220 | 03/14/14 | 998 | Payroll Taxes | SA54 | Sanders, Allen O
T2682 | PR | 222 | 03/14/14 | 998 | Payroll Taxes | SO78 | Soto Cruz, Jovani
T2683 | PR | 223 | 03/14/14 | 998 | Payroll Taxes | SO79 | Soto Serna, Cesar E
T2684 | PR | 225 | 03/14/14 | 998 | Payroll Taxes | VA86 | Vaughan, Tyler J
T2685 | PR | 229 | 03/14/14 | 998 | Payroll Taxes | WA35 | Waites, Thaddeus Z
T2686 | PR | 229 | 03/14/14 | 998 | Payroll Taxes | WA35 | Waites, Thaddeus Z
T2687 | PR | 331 | 03/21/14 | 998 | Payroll Taxes | CA75 | Castro Hernandez, Carlos E
T2688 | PR | 331 | 03/21/14 | 998 | Payroll Taxes | CA75 | Castro Hernandez, Carlos E
T2689 | PR | 337 | 03/21/14 | 998 | Payroll Taxes | GE69 | Gerard, Jeffrey S
T2690 | PR | 337 | 03/21/14 | 998 | Payroll Taxes | GE69 | Gerard, Jeffrey S
T2691 | PR | 338 | 03/21/14 | 998 | Payroll Taxes | GO56 | Gonzalez Hernandez, Josue
T2692 | PR | 338 | 03/21/14 | 998 | Payroll Taxes | GO56 | Gonzalez Hernandez, Josue
T2693 | PR | 343 | 03/21/14 | 998 | Payroll Taxes | LI49 | Lima Romero, Melvin A
T2694 | PR | 346 | 03/21/14 | 998 | Payroll Taxes | ME98 | Meza Fuentes, Erick A
T2695 | PR | 351 | 03/21/14 | 998 | Payroll Taxes | QU35 | Quintanilla, Esteban R
T2696 | PR | 361 | 03/21/14 | 998 | Payroll Taxes | SA54 | Sanders, Allen O
T2697 | PR | 364 | 03/21/14 | 998 | Payroll Taxes | SO79 | Soto Serna, Cesar E
T2698 | PR | 366 | 03/21/14 | 998 | Payroll Taxes | VA86 | Vaughan, Tyler J
T2699 | PR | 369 | 03/21/14 | 998 | Payroll Taxes | WA35 | Waites, Thaddeus Z
T2700 | PR | 467 | 03/28/14 | 998 | Payroll Taxes | BA70 | Barnhart, Joseph N
T2701 | PR | 472 | 03/28/14 | 998 | Payroll Taxes | CA75 | Castro Hernandez, Carlos E
T2702 | PR | 478 | 03/28/14 | 998 | Payroll Taxes | GE69 | Gerard, Jeffrey S
T2703 | PR | 487 | 03/28/14 | 998 | Payroll Taxes | ME98 | Meza Fuentes, Erick A
T2704 | PR | 492 | 03/28/14 | 998 | Payroll Taxes | QU35 | Quintanilla, Esteban R
T2705 | PR | 502 | 03/28/14 | 998 | Payroll Taxes | SA54 | Sanders, Allen O
T2706 | PR | 504 | 03/28/14 | 998 | Payroll Taxes | SO78 | Soto Cruz, Jovani
T2707 | PR | 505 | 03/28/14 | 998 | Payroll Taxes | SO79 | Soto Serna, Cesar E
T2708 | PR | 507 | 03/28/14 | 998 | Payroll Taxes | VA86 | Vaughan, Tyler J
T2709 | PR | 18 | 04/04/14 | 998 | Payroll Taxes | GE69 | Gerard, Jeffrey S
T2710 | PR | 27 | 04/04/14 | 998 | Payroll Taxes | ME98 | Meza Fuentes, Erick A
T2711 | PR | 43 | 04/04/14 | 998 | Payroll Taxes | SA54 | Sanders, Allen O
T2712 | PR | 45 | 04/04/14 | 998 | Payroll Taxes | SO78 | Soto Cruz, Jovani
T2713 | PR | 46 | 04/04/14 | 998 | Payroll Taxes | SO79 | Soto Serna, Cesar E
T2714 | PR | 48 | 04/04/14 | 998 | Payroll Taxes | VA86 | Vaughan, Tyler J
T2715 | PR | 141 | 04/11/14 | 998 | Payroll Taxes | GE69 | Gerard, Jeffrey S
T2716 | PR | 151 | 04/11/14 | 998 | Payroll Taxes | ME98 | Meza Fuentes, Erick A
T2717 | PR | 167 | 04/11/14 | 998 | Payroll Taxes | SA54 | Sanders, Allen O
T2718 | PR | 169 | 04/11/14 | 998 | Payroll Taxes | SO78 | Soto Cruz, Jovani
T2719 | PR | 172 | 04/11/14 | 998 | Payroll Taxes | VA86 | Vaughan, Tyler J
T2720 | PR | 260 | 04/18/14 | 998 | Payroll Taxes | GE69 | Gerard, Jeffrey S
T2721 | PR | 260 | 04/18/14 | 998 | Payroll Taxes | GE69 | Gerard, Jeffrey S
T2722 | PR | 269 | 04/18/14 | 998 | Payroll Taxes | ME98 | Meza Fuentes, Erick A
T2723 | PR | 285 | 04/18/14 | 998 | Payroll Taxes | SA54 | Sanders, Allen O
T2724 | PR | 287 | 04/18/14 | 998 | Payroll Taxes | SO78 | Soto Cruz, Jovani
T2725 | PR | 398 | 04/25/14 | 998 | Payroll Taxes | GE69 | Gerard, Jeffrey S
T2726 | PR | 408 | 04/25/14 | 998 | Payroll Taxes | ME98 | Meza Fuentes, Erick A
T2727 | PR | 424 | 04/25/14 | 998 | Payroll Taxes | SA54 | Sanders, Allen O
T2728 | PR | 426 | 04/25/14 | 998 | Payroll Taxes | SO78 | Soto Cruz, Jovani
T2729 | PR | 10 | 05/02/14 | 998 | Payroll Taxes | BA70 | Barnhart, Joseph N
T2730 | PR | 31 | 05/02/14 | 998 | Payroll Taxes | ME98 | Meza Fuentes, Erick A
T2731 | PR | 31 | 05/02/14 | 998 | Payroll Taxes | ME98 | Meza Fuentes, Erick A
T2732 | PR | 47 | 05/02/14 | 998 | Payroll Taxes | SA54 | Sanders, Allen O
T2733 | PR | 178 | 05/09/14 | 998 | Payroll Taxes | ME98 | Meza Fuentes, Erick A
T2734 | PR | 194 | 05/09/14 | 998 | Payroll Taxes | SA54 | Sanders, Allen O
T2735 | PR | 284 | 05/16/14 | 998 | Payroll Taxes | SA54 | Sanders, Allen O
T2736 | PR | 463 | 05/23/14 | 998 | Payroll Taxes | SA54 | Sanders, Allen O
T2737 | PR | 537 | 05/30/14 | 998 | Payroll Taxes | SA54 | Sanders, Allen O
T2738 | PR | 27 | 06/06/14 | 998 | Payroll Taxes | ME98 | Meza Fuentes, Erick A
T2739 | PR | 42 | 06/06/14 | 998 | Payroll Taxes | SA54 | Sanders, Allen O
T2740 | PR | 232 | 06/20/14 | 998 | Payroll Taxes | GE69 | Gerard, Jeffrey S

## Crew & Labor
Crew & Labor — Per-Worker Breakdown (with OT split)
42 workers · 14,652.2 hrs · $291,364 gross pay · $19.89/hr blended (Crew-tab basis)
Worker | Total Hrs | Reg Hrs | OT Hrs | DT Hrs | Gross Pay | $/Hour | Tier
Quintanilla, Esteban R | 1199 | 1111 | 88 | 0 | 38981 | 32.5113 | Senior
Gonzalez Hernandez, Josue | 1135 | 1001 | 134 | 0 | 15342 | 13.5172 | Apprentice
Lima Romero, Melvin A | 1051 | 946 | 105 | 0 | 20866.5 | 19.8539 | Mid
Palma Vides, Hugo | 928 | 790 | 138 | 0 | 27035 | 29.1325 | Mid
Castro Hernandez, Jose A | 862 | 763 | 99 | 0 | 14160.5 | 16.4275 | Apprentice
Rivera, Eli P | 856 | 746 | 110 | 0 | 11184 | 13.0654 | Apprentice
Chavarria Lopez, Omar A | 851 | 738 | 113 | 0 | 11150 | 13.1022 | Apprentice
Monico Brambila, Jesus S | 810 | 660 | 150 | 0 | 11548 | 14.2568 | Apprentice
Meza Fuentes, Erick A | 579.5 | 575.5 | 4 | 0 | 11624 | 20.0587 | Mid
Rivera, Jorge A | 561 | 501 | 60 | 0 | 10638 | 18.9626 | Mid
Paco Leyva, Orlando | 488.5 | 450.5 | 38 | 0 | 7145.75 | 14.6279 | Apprentice
Gerard, Jeffrey S | 406 | 406 | 0 | 0 | 14595 | 35.9483 | Senior
Veley, Nathaniel S | 394 | 381 | 13 | 0 | 10976.5 | 27.8591 | Mid
Vega Arriaga, Jorge | 373 | 316 | 57 | 0 | 4829 | 12.9464 | Apprentice
Ramos Garcia, Jose M | 365 | 363 | 2 | 0 | 4758 | 13.0356 | Apprentice
Sanders, Allen O | 341 | 337.5 | 3.5 | 0 | 9898.5 | 29.0279 | Mid
Waites, Thaddeus Z | 319 | 319 | 0 | 0 | 8932 | 28 | Mid
Spears, Gregory M | 308 | 262 | 46 | 0 | 4303 | 13.9708 | Apprentice
Castaneda Martinez, Gustavo | 283 | 248 | 35 | 0 | 8113.5 | 28.6696 | Mid
Soto Cruz, Jovani | 280 | 280 | 0 | 0 | 4480 | 16 | Apprentice
Soto Serna, Cesar E | 249 | 249 | 0 | 0 | 3237 | 13 | Apprentice
Sepulveda Gonzalez, Alfredo | 242 | 176 | 66 | 0 | 6024 | 24.8926 | Mid
Cortes Mendiola, Victor H | 241 | 193 | 48 | 0 | 6345.5 | 26.3299 | Mid
Lopez Martinez, Abimael | 211 | 201 | 10 | 0 | 2592 | 12.2844 | Apprentice
Castro Hernandez, Carlos E | 208.5 | 171 | 37.5 | 0 | 6234.25 | 29.9005 | Mid
Castaneda Juarez, Edgar D | 197.25 | 197.25 | 0 | 0 | 2742.88 | 13.9056 | Apprentice
Holmes, Anthony R | 174 | 162 | 12 | 0 | 2340 | 13.4483 | Apprentice
Vaughan, Tyler J | 168.5 | 168.5 | 0 | 0 | 2696 | 16 | Apprentice
Sanchez Garcia, Adelaido | 155 | 155 | 0 | 0 | 2015 | 13 | Apprentice
Velasquez Cruz, Denis M | 106 | 94 | 12 | 0 | 1456 | 13.7358 | Apprentice
Agustin Rodriguez, Ezequiel | 93 | 83 | 10 | 0 | 1176 | 12.6452 | Apprentice
Arreola, Israel A | 42 | 42 | 0 | 0 | 609 | 14.5 | Apprentice
Rendon Villasenor, Ismael | 36 | 36 | 0 | 0 | 432 | 12 | Apprentice
Garcia, Jordan X | 32 | 32 | 0 | 0 | 448 | 14 | Apprentice
Wilson, Garret A | 32 | 32 | 0 | 0 | 416 | 13 | Apprentice
Barnhart, Joseph N | 25 | 11 | 14 | 0 | 932 | 37.28 | Senior
Salazar, Hajdar L | 14 | 0 | 14 | 0 | 252 | 18 | Mid
McCabe, Thomas C | 12.5 | 8 | 4.5 | 0 | 265.5 | 21.24 | Mid
Reed, Reuben H | 8 | 0 | 8 | 0 | 324 | 40.5 | Senior
Castaneda Juarez, Gustavo | 7 | 7 | 0 | 0 | 91 | 13 | Apprentice
Hubbard, Dustin R | 5 | 5 | 0 | 0 | 60 | 12 | Apprentice
Hubbard, Robert W | 3.5 | 3.5 | 0 | 0 | 115.5 | 33 | Senior
TOTAL (42 workers) | 14652.25 | 13220.75 | 1431.5 | 0 | 291363.88 | 19.8853

## Wage Basis Canonicals
Wage Basis Canonicals — Published Side-by-Side (Action #3)
Publishing THREE wage rates disambiguated by canonical name. Prevents the $10/hr divergence that confused Sam v3 vs Notion v2. All three are "correct" — they answer different questions.
Canonical Name | Basis | Numerator ($) | Denominator (hrs) | Rate ($/hr) | What it answers
pr_src_cost_per_hr | JDR by-Source PR (fully-loaded: labor + burden + taxes) | 439953.72 | 14652.25 | 30.0264 | "What does an hour of labor cost OWP all-in?" — Sam v3 canonical. Use for true labor COGS.
labor_code_cost_per_hr | Labor cost codes only (011–145) — no burden | 291321.88 | 14652.25 | 19.8824 | "What does an hour of direct labor cost?" — the Insights tab $19.94/hr rate.
per_worker_gross_wage | Sum of per-worker gross pay / sum of per-worker hours | 291363.88 | 14652.25 | 19.8853 | "What does a crew member earn per hour (pre-burden)?" — Crew-tab basis.
BURDEN RATIO
Burden multiplier (pr_src ÷ labor_code) |  |  |  | 1.5102

## Vendors
Vendors — AP Breakdown (16 vendors)
Total AP spend $408,537.07 · 186 invoices · Keller Supply largest (37.8% of AP)
Rank | Vendor | Invoices | Total Spend | % of AP | Avg Invoice
1 | Keller Supply Company | 45 | 154404.22 | 37.79% | 3431.2049
2 | Ferguson Enterprises, Inc. | 41 | 119072.08 | 29.15% | 2904.1971
3 | Mechanical Sales, Inc. | 7 | 58896.52 | 14.42% | 8413.7886
4 | Rosen Supply Company, Inc. | 54 | 38606.34 | 9.45% | 714.9322
5 | Franklin Engineering | 4 | 15612.75 | 3.822% | 3903.1875
6 | Bank of America CC | 6 | 9741.88 | 2.385% | 1623.6467
7 | Quality Concrete Products, Inc. $32 | 3 | 5806 | 1.421% | 1935.3333
8 | Manor Hardware & Construction Supply | 7 | 1963.11 | 0.4805% | 280.4443
9 | Patchworks, Inc. | 2 | 1837.5 | 0.4498% | 918.75
10 | Capital One Credit Card | 8 | 1038.11 | 0.2541% | 129.7637
11 | Rosen Supply Kirkland | 1 | 973.75 | 0.2384% | 973.75
12 | Ferguson Enterprises, Inc. #3007 | 2 | 309.58 | 0.07578% | 154.79
13 | R.A. Brown Backflow Testing | 1 | 186 | 0.04553% | 186
14 | DRSi | 1 | 69.28 | 0.01696% | 69.28
15 | C.M. Hoskins Company | 1 | 13.84 | 0.003388% | 13.84
16 | American Express 3-41000 | 3 | 6.11 | 0.001496% | 2.0367
| TOTAL | 186 | 408537.07 | 100% | 2196.4359

## Billing & SOV
Revenue & Billing Reconciliation
15 pay apps · Mar 2013–Jul 2014 · $1,391,455 final · $69,572.75 retainage (5%)
CONTRACT SUMMARY
Original Contract | 1394655
Change Orders (net) | -3200
Final Contract Value | 1391455
Retainage (5%) | 69572.75
Net Paid to OWP | 1321882.25

## Change Log
Change Log — Master Register (8 events)
Net change-order impact: +$7,598 (primarily ASI + T&M + 5 backcharges absorbed)
Event ID | Type | Date | Subject | Originator | Cost Impact | Sched Days | Status | Root Cause
ASI-025 | ASI | 2013-09-15 | Janitor sink and faucet — Kavela substitution | Architect (Kavela) | 0 | 0 | Closed — Incorporated | Design substitution
BC-001 | Backcharge | 2014-05-04 | Patchworks — drywall repair | GC (Exxel) | -850 | 0 | Paid | Coordination/damage
BC-002 | Backcharge | 2014-10-23 | Division 9 cleanup | GC (Exxel) | -420 | 0 | Paid | Cleanup/scope gap
BC-003 | Backcharge | 2014-10-23 | Painters Unlimited — wall repair | GC (Exxel) | -675 | 0 | Paid | Coordination/damage
BC-004 | Backcharge | 2015-02-26 | Unity Electric — conduit conflict | GC (Exxel) | -1200 | 0 | Paid | MEP coordination
BC-005 | Backcharge | 2014-04-27 | One Way — internal backcharge | OWP | -290 | 0 | Paid | Rework
TM-001 | T&M | 2013-11-01 | Cost code 038 T&M — directed work | Field (OWP) | 4350 | 0 | Billed | Owner directive
CO-001 | CO | 2013-12-15 | Net change orders to contract | GC (Exxel) | 6683 | 0 | Approved — Billed | Combined adjustments
TOTAL |  |  |  |  | 7598

## Insights
Key Insights — Structured Narrative (Action #10)
Each insight tagged by category + severity. Machine-readable alongside narrative.
# | Category | Title | Severity | Narrative
1 | Margin | MARGIN PROFILE | Baseline | Net profit of $533,274 on $1,391,455 revenue = 38.3% gross margin. Direct cost $858,181 absorbs 61.7% of revenue.
2 | Vendor | VENDOR CONCENTRATION | Watch | Keller Supply Company = $154,464 (38% of all AP) across 45 invoices. Total 16 AP vendors, $409,755 spend. Single-supplier exposure.
3 | Crew | CREW PROFILE | Baseline | 42 workers for 14,652 hours = 349 avg hrs/worker. Top 3 workers logged 3,044 hrs (21% of labor).
4 | Critical | ROUGHIN DOMINANCE | Critical | Code 120 Roughin Labor = 9,320 hrs (64% of all labor) and $177,292 actual — overrun of $37,492 vs $139,800 budget. Code 230 Finish Material = $210,145 (25% of direct cost).
5 | Savings | BUDGET DELIVERY | Positive | Revised budget $1,058,658 → actual $858,181 = $200,477 under revised budget (18.9% savings).
6 | Contract | CONTRACT GROWTH | Baseline | Contract grew from $1,394,655 to $1,391,455 — net $-3,200 (-0.2%). Retainage $69,573 (5%) withheld.
7 | Benchmark | BURDEN RATIO | Baseline | Burden codes 995+998 = $148,590 on $291,322 labor base = 51.0%. Within OWP target 48–52%.
8 | Scale | PROJECT SCALE | Baseline | 163 units · 1,004 fixtures · 17 months. Revenue/unit $8,537, hours/unit 89.9, profit/unit $3,272.
9 | Productivity | WAGE BASIS DISCLOSURE | Action | Three canonical wage rates published (see Wage Basis Canonicals tab): pr_src $30.03, labor_code $19.88, per_worker $19.89. Sam v3 uses pr_src.
10 | Action | SCHEMA RECONCILIATION | Action | Notion v3 rebuild: +Transactions tab (2,740 lines), +REG/OT/DT per code, +per-code net_due & retainage, structured Insights. Aligns with Sam v3.

## Metric Registry
Metric Registry — Notion ↔ Sam v3 Crosswalk
Canonical metric names aligned across Notion v3 and Sam v3. Use this as the schema contract.
Canonical Name | Notion Tab | Sam v3 Field | Sample Value | Category | Notes
job_id | Overview | job_id | 2012 | Profile
job_name | Overview | job_name | Exxel Pacific 8th Ave | Profile
gc_name | Overview | contractor | Exxel Pacific, Inc. | Profile
contract_original | Billing & SOV | contract_original | 1394655 | Contract
contract_final | Billing & SOV | contract_final | 1391455 | Contract
change_orders_net | Change Log | change_orders_net | -3200 | Contract
retainage_total | Billing & SOV | retainage_total | 69572.75 | Contract | At job-level (5% of final)
original_budget_total | Budget vs Actual | original_budget | 1065992.15 | Budget | Action #2 — published
revised_budget_total | Budget vs Actual | revised_budget | 1058658.15 | Budget | Action #2 — CANONICAL
budget_basis_delta | Reconciliation Proofs | budget_basis_delta | 7334 | Budget | Orig - Rev
direct_cost_total | Budget vs Actual | direct_cost_actual | 858180.7 | Cost
net_profit | Overview | net_profit | 533274.3 | Financial | contract_final - direct_cost_actual
gross_margin_pct | Overview | gross_margin | 38.32% | Financial
pr_src_cost_per_hr | Wage Basis Canonicals | pr_src_cost_per_hr | 30.0264 | Labor | Action #3 — CANONICAL (fully-loaded)
labor_code_cost_per_hr | Wage Basis Canonicals | labor_code_cost_per_hr | 19.8824 | Labor | Action #3 — direct labor only
per_worker_gross_wage | Wage Basis Canonicals | per_worker_gross_wage | 19.8853 | Labor | Action #3 — crew-tab basis
worker_count | Crew & Labor | worker_count | 42 | Labor
total_hours | Budget vs Actual | total_hours | 14652.25 | Labor | Sum of PR hours
ot_hours | Budget vs Actual | ot_hours | 1431.5 | Labor | Action #5
vendor_count | Vendors | vendor_count | 16 | AP
ap_total | Vendors | ap_total | 408537.07 | AP
top_vendor_pct | Vendors | top_vendor_pct | 37.81% | AP | Keller Supply share
transaction_count | Transactions | line_items_count | 2740 | Detail | Action #4 — matches Sam v3 grain
change_event_count | Change Log | change_events | 8 | Change
insights_count | Insights | insights_count | 10 | Narrative | Action #10 — structured

## Reconciliation Proofs
Reconciliation Proofs — Notion v3 ↔ Sam v3 (BOTH Actions #2 & #3)
Tie-out proofs for the two dual-ownership reconciliation actions. Publishes both bases side-by-side so Sam v4 can adopt canonical names verbatim.
A. BUDGET BASIS (Action #2) — Canonical: revised_budget
Check | Orig | Rev | Δ | Status | Notes
Total (non-Sales) Budget | 1065992.15 | 1058658.15 | 7334 | RECONCILED | Known $7,334 delta = Code 230 (+$8,266) + Code 607 (-$15,600)
Code 230 Finish Material | 261600 | 269866 | -8266 | EXPECTED | Revised UP by $8,266
Code 607 Other Expenses | 25600 | 10000 | 15600 | EXPECTED | Revised DOWN by $15,600
B. WAGE BASIS (Action #3) — Three rates published
Canonical | Numerator | Denominator | Rate | Owner | Usage
pr_src_cost_per_hr | 439953.72 | 14652.25 | 30.0264 | Sam v3 | Fully-loaded labor COGS
labor_code_cost_per_hr | 291321.88 | 14652.25 | 19.8824 | Notion Insights | Direct labor only
per_worker_gross_wage | 291363.88 | 14652.25 | 19.8853 | Notion Crew tab | Worker-level pay/hr
C. JDR JOB-LEVEL TIE-OUT
Metric | Notion v3 | JDR | Δ | Status | Notes
Contract Final Value | 1391455 | 1391455 | 0 | TIES | From JDR Sales code 999
Retainage (job-level) | 69572.75 | 69572.75 | 0 | TIES | From JDR Cost Code Totals row
Direct Cost (sum of code actuals) | 858180.7 | 858180.7 | 1.1642e-10 | TIES | JDR Job Totals expenses $858,181
AP by Source | 408537.07 | 408537.07 | 0 | TIES | From JDR by-Source footer
PR by Source | 439953.72 | 439953.72 | 0 | TIES | From JDR by-Source footer
GL by Source | 9689.91 | 9689.91 | 0 | TIES | From JDR by-Source footer
Sum of Sources = Expenses | 858180.7 | 858180.7 | 1.1642e-10 | TIES | GL + AP + PR = total expenses
Transaction Count | 2740 | 2740 | 0 | TIES | From JDR line-item parse