## Overview
Job #2016 · Natural & Built Sedona Apartments
Cortex JCR Summary • Natural & Built Environments • Seattle, WA (8512 20th Ave NE) • 64-unit 6-story multifamily apartment building • Nov 2013 – Dec 2014 (~14 months)
PROJECT OVERVIEW
Project Job # | 2016
Project Name: | Natural & Built Sedona Apartments
General Contractor | Natural & Built Environments
Location | Seattle, WA (8512 20th Ave NE)
Project Duration | Nov 2013 – Dec 2014 (~14 months)
Total Unique Documents | Sedona folder: Contract, Billings, Invoices, PO_s, Permits
CONTRACT VALUE |  | NET PROFIT |  | DIRECT COST |  | LABOR HOURS
$341,805 |  | $100,795 |  | $241,010 |  | 4,773
Original $336,500 + $5,305 COs |  | 29.5% margin |  | 70.5% of revenue |  | 28 workers
COST BREAKDOWN
Category | Budget | Actual | Variance | % Budget | % of Cost
Labor | 74865 | 97891.25 | -23026.25 | 130.8% | 40.62%
Material | 123043 | 90495.62 | 32547.38 | 73.55% | 37.55%
Overhead | 3900 | 2699 | 1201 | 69.21% | 1.12%
Burden | 38181.17 | 49924.59 | -11743.42 | 130.8% | 20.71%
TOTAL | 239989.17 | 241010.46 | -1021.29 | 100.4% | 100%
PROJECT PROFILE
Metric | Value | Metric | Value | Metric | Value
Plumbing Units | 80 | Water Closets | 80 | Kitchen Sinks | 64
Total Fixtures | 267 | Lavatories | 80 | Dishwashers | 64
Fixtures / Unit | 3.34 | Tubs | 64 | Auto Washers | 64
Floors | 6 | Stacks | 16 | Duration | 14 mo
SOURCES
Job #2016 — Natural & Built Sedona Apartments • GC: Natural & Built Environments • Seattle, WA
Canonical source: 2016 Job Detail Report.pdf (45 pages, OWP Sage Timberline export)
Cost codes parsed: 24 (Labor+Material+Overhead+Burden+Revenue)
Unit count: 64 via 5 per-level Keller trim invoices (L2:16 L3:8 L4:16 L5:16 L6:8)
Fixture count: 267 from King County Plumbing Permit #5101400394
Billing: SEDONA AGGREGATE BILLING.xlsx (8 pay apps, Nov 2013 – Oct 2014)

## Budget vs Actual
Budget vs Actual — All Cost Codes
Code | Description | Orig Budget | Rev Budget | Actual | Variance | % Used
LABOR
100 | Supervision | 4980 | 5130 | 2769 | 2361 | 53.98%
101 | Takeoff & Purchase Labor | 4980 | 4980 | 3124 | 1856 | 62.73%
110 | Underground Labor | 2800 | 2800 | 1126 | 1674 | 40.21%
111 | Garage Labor | 0 | 0 | 416 | -416 | 0%
112 | Canout Labor | 1700 | 1700 | 765 | 935 | 45%
120 | Roughin Labor | 28845 | 30595 | 65392.75 | -34797.75 | 213.7%
130 | Finish Labor | 9520 | 9800 | 9310.5 | 489.5 | 95.01%
141 | Water Main/Insulation Lab | 8300 | 8300 | 4656 | 3644 | 56.1%
142 | Mech Room Labor | 4000 | 4000 | 1032 | 2968 | 25.8%
145 | Tub/Shower Labor | 7560 | 7560 | 9300 | -1740 | 123%
MATERIAL
210 | Underground Material | 2700 | 2700 | 1463.57 | 1236.43 | 54.21%
211 | Garage Material | 0 | 0 | 479.89 | -479.89 | 0%
212 | Canout Material | 2550 | 2550 | 2042.61 | 507.39 | 80.1%
220 | Roughin Material | 24300 | 24315 | 26087.05 | -1772.05 | 107.3%
230 | Finish Material | 81800 | 82478 | 56499.81 | 25978.19 | 68.5%
240 | Gas Material | 0 | 0 | 23.51 | -23.51 | 0%
241 | Water Main/Insulation Mat | 8000 | 8000 | 604.14 | 7395.86 | 7.552%
242 | Mech Room Material | 3000 | 3000 | 2702.93 | 297.07 | 90.1%
245 | Tub/Shower Material | 0 | 0 | 592.11 | -592.11 | 0%
OVERHEAD
600 | Subcontractor | 700 | 700 | 50 | 650 | 7.143%
603 | Permits & Licenses | 3200 | 3200 | 2649 | 551 | 82.78%
BURDEN
995 | Payroll Burden | 31508.95 | 32453.99 | 42435.92 | -9981.93 | 130.8%
998 | Payroll Taxes | 5560.4 | 5727.18 | 7488.67 | -1761.49 | 130.8%
TOTAL | Direct Cost | 236004.35 | 239989.17 | 241010.46 | -1021.29 | 100.4%
SOURCES
Job #2016 — Natural & Built Sedona Apartments • GC: Natural & Built Environments • Seattle, WA
Canonical source: 2016 Job Detail Report.pdf (45 pages, OWP Sage Timberline export)
Cost codes parsed: 24 (Labor+Material+Overhead+Burden+Revenue)
Unit count: 64 via 5 per-level Keller trim invoices (L2:16 L3:8 L4:16 L5:16 L6:8)
Fixture count: 267 from King County Plumbing Permit #5101400394
Billing: SEDONA AGGREGATE BILLING.xlsx (8 pay apps, Nov 2013 – Oct 2014)

## Cost Breakdown
Cost Breakdown — Category Deep Dive
A. CATEGORY SHARE OF DIRECT COST
Category | # Codes | Budget | Actual | Variance | % Budget | % of Cost | Per Unit
Labor | 10 | 74865 | 97891.25 | -23026.25 | 130.8% | 40.62% | 1223.6406
Material | 9 | 123043 | 90495.62 | 32547.38 | 73.55% | 37.55% | 1131.1952
Overhead | 2 | 3900 | 2699 | 1201 | 69.21% | 1.12% | 33.7375
Burden | 2 | 38181.17 | 49924.59 | -11743.42 | 130.8% | 20.71% | 624.0574
B. LARGEST OVERRUNS (Actual > Revised Budget)
Code | Description | Rev Budget | Actual | Overrun | % Over
120 | Roughin Labor | 30595 | 65392.75 | 34797.75 | 113.7%
995 | Payroll Burden | 32453.99 | 42435.92 | 9981.93 | 30.76%
220 | Roughin Material | 24315 | 26087.05 | 1772.05 | 7.288%
998 | Payroll Taxes | 5727.18 | 7488.67 | 1761.49 | 30.76%
145 | Tub/Shower Labor | 7560 | 9300 | 1740 | 23.02%
245 | Tub/Shower Material | 0 | 592.11 | 592.11 | 0%
211 | Garage Material | 0 | 479.89 | 479.89 | 0%
111 | Garage Labor | 0 | 416 | 416 | 0%
C. LARGEST SAVINGS (Actual < Revised Budget)
Code | Description | Rev Budget | Actual | Savings | % Under
230 | Finish Material | 82478 | 56499.81 | 25978.19 | 31.5%
241 | Water Main/Insulation Mat | 8000 | 604.14 | 7395.86 | 92.45%
141 | Water Main/Insulation Lab | 8300 | 4656 | 3644 | 43.9%
142 | Mech Room Labor | 4000 | 1032 | 2968 | 74.2%
100 | Supervision | 5130 | 2769 | 2361 | 46.02%
101 | Takeoff & Purchase Labor | 4980 | 3124 | 1856 | 37.27%
110 | Underground Labor | 2800 | 1126 | 1674 | 59.79%
210 | Underground Material | 2700 | 1463.57 | 1236.43 | 45.79%
112 | Canout Labor | 1700 | 765 | 935 | 55%
600 | Subcontractor | 700 | 50 | 650 | 92.86%
SOURCES
Job #2016 — Natural & Built Sedona Apartments • GC: Natural & Built Environments • Seattle, WA
Canonical source: 2016 Job Detail Report.pdf (45 pages, OWP Sage Timberline export)
Cost codes parsed: 24 (Labor+Material+Overhead+Burden+Revenue)
Unit count: 64 via 5 per-level Keller trim invoices (L2:16 L3:8 L4:16 L5:16 L6:8)
Fixture count: 267 from King County Plumbing Permit #5101400394
Billing: SEDONA AGGREGATE BILLING.xlsx (8 pay apps, Nov 2013 – Oct 2014)

## Material
Material Spend Analysis
9 material cost codes • $90,496 JDR material • 9 AP vendors • $106,353 total AP
A. MATERIAL BY COST CODE
Code | Description | Rev Budget | Actual | Variance | % Used | % of Mat | Per Unit
210 | Underground Material | 2700 | 1463.57 | 1236.43 | 54.21% | 1.617% | 18.2946
211 | Garage Material | 0 | 479.89 | -479.89 | 0% | 0.5303% | 5.9986
212 | Canout Material | 2550 | 2042.61 | 507.39 | 80.1% | 2.257% | 25.5326
220 | Roughin Material | 24315 | 26087.05 | -1772.05 | 107.3% | 28.83% | 326.0881
230 | Finish Material | 82478 | 56499.81 | 25978.19 | 68.5% | 62.43% | 706.2476
240 | Gas Material | 0 | 23.51 | -23.51 | 0% | 0.02598% | 0.29387
241 | Water Main/Insulation Mat | 8000 | 604.14 | 7395.86 | 7.552% | 0.6676% | 7.5518
242 | Mech Room Material | 3000 | 2702.93 | 297.07 | 90.1% | 2.987% | 33.7866
245 | Tub/Shower Material | 0 | 592.11 | -592.11 | 0% | 0.6543% | 7.4014
TOTAL | All Material | 123043 | 90495.62 | 32547.38 | 73.55% | 100% | 1131.1952
B. VENDORS BY SPEND (AP)
Vendor | # Invoices | Total Spend | % of AP |  |  |  | Avg Invoice
Keller Supply Company | 22 | 74948.84 | 70.47% |  |  |  | 3406.7655
Ferguson Enterprises, Inc. | 21 | 14095.11 | 13.25% |  |  |  | 671.1957
Rosen Supply Company, Inc. | 25 | 11376.96 | 10.7% |  |  |  | 455.0784
Bank of America CC | 3 | 2649 | 2.491% |  |  |  | 883
Consolidated Supply Co. | 7 | 1086.17 | 1.021% |  |  |  | 155.1671
Mechanical Sales, Inc. | 1 | 1044 | 0.9816% |  |  |  | 1044
Rosen Supply Kirkland | 2 | 897.2 | 0.8436% |  |  |  | 448.6
Capital One Credit Card | 3 | 205.27 | 0.193% |  |  |  | 68.4233
R.A. Brown Backflow Testing | 1 | 50 | 0.04701% |  |  |  | 50
TOTAL | 85 | 106352.55 | 100%
SOURCES
Job #2016 — Natural & Built Sedona Apartments • GC: Natural & Built Environments • Seattle, WA
Canonical source: 2016 Job Detail Report.pdf (45 pages, OWP Sage Timberline export)
Cost codes parsed: 24 (Labor+Material+Overhead+Burden+Revenue)
Unit count: 64 via 5 per-level Keller trim invoices (L2:16 L3:8 L4:16 L5:16 L6:8)
Fixture count: 267 from King County Plumbing Permit #5101400394
Billing: SEDONA AGGREGATE BILLING.xlsx (8 pay apps, Nov 2013 – Oct 2014)
Vendor AP ties to JDR 'by Source: AP' line (106,352.55)

## Crew & Labor
Crew & Labor — Per-Worker Breakdown
Worker | Hours | Gross Pay | $/Hour | Tier
Lima Romero, Melvin A | 664 | 13280 | 20 | Mid
Castro Hernandez, Carlos E | 644 | 18032 | 28 | Mid
Rivera, Jorge A | 485 | 8730 | 18 | Mid
Gonzalez Hernandez, Josue | 472 | 6608 | 14 | Apprentice
Quintanilla, Esteban R | 464 | 14848 | 32 | Senior
Reyes Cruz, Denis A | 456 | 5560 | 12.193 | Apprentice
Ramos Garcia, Jose M | 232 | 3016 | 13 | Apprentice
Rivera, Eli P | 214 | 2782 | 13 | Apprentice
Gerard, Jeffrey S | 192.5 | 7356 | 38.213 | Senior
Ramos Banegas, Noel O | 192 | 2496 | 13 | Apprentice
Castro Hernandez, Jose A | 176 | 2992 | 17 | Apprentice
Sanders, Allen O | 171 | 5022.5 | 29.3713 | Mid
Kinssies, Jr, John E | 129.5 | 2007 | 15.4981 | Apprentice
Soto Serna, Cesar E | 39 | 507 | 13 | Apprentice
Vaughan, Tyler J | 36.5 | 584 | 16 | Apprentice
Lopez Martinez, Abimael | 32 | 416 | 13 | Apprentice
Arreola, Israel A | 24 | 408 | 17 | Apprentice
Cortes Mendiola, Victor H | 24 | 624 | 26 | Mid
McCabe, Thomas C | 23 | 414 | 18 | Mid
Anderson, Richard P | 16.5 | 462 | 28 | Mid
Montenegro, Carlos E | 16 | 208 | 13 | Apprentice
Soto Cruz, Jovani | 8 | 128 | 16 | Apprentice
Paco Leyva, Orlando | 8 | 136 | 17 | Apprentice
Veley, Nathaniel S | 8 | 232 | 29 | Mid
Reyes, Robert J | 8 | 104 | 13 | Apprentice
Salazar, Hajdar L | 8 | 120 | 15 | Apprentice
Castaneda Juarez, Edgar D | 8 | 116 | 14.5 | Apprentice
Gerard, Mitchell J | 3.5 | 42 | 12 | Apprentice
TOTAL (28 workers) | 4754.5 | 97230.5 | 20.4502
SOURCES
Job #2016 — Natural & Built Sedona Apartments • GC: Natural & Built Environments • Seattle, WA
Canonical source: 2016 Job Detail Report.pdf (45 pages, OWP Sage Timberline export)
Cost codes parsed: 24 (Labor+Material+Overhead+Burden+Revenue)
Unit count: 64 via 5 per-level Keller trim invoices (L2:16 L3:8 L4:16 L5:16 L6:8)
Fixture count: 267 from King County Plumbing Permit #5101400394
Billing: SEDONA AGGREGATE BILLING.xlsx (8 pay apps, Nov 2013 – Oct 2014)
Tier: Apprentice <$18/hr, Mid $18–30, Senior >$30

## Crew Analytics
Crew Analytics
A. TIER DISTRIBUTION
Tier | # Workers | Hours | Gross Pay | % of Hours
Senior | 2 | 656.5 | 22204 | 13.81%
Mid | 8 | 2035.5 | 46796.5 | 42.81%
Apprentice | 18 | 2062.5 | 28230 | 43.38%
B. WAGE STATISTICS
Blended Gross Wage | 20.4502 |  |  | Payroll $ ÷ payroll hours (pre-burden)
Fully-Loaded Wage | 31.0897 |  |  | (Labor + Burden) ÷ total hours
Burden Multiplier | 1.5203 |  |  | Fully loaded ÷ gross wage
Min Worker Rate | 12 |  |  | Cheapest apprentice hour
Max Worker Rate | 38.213 |  |  | Most expensive foreman hour
Avg Hours / Worker | 169.8036 |  |  | Crew continuity indicator
SOURCES
Job #2016 — Natural & Built Sedona Apartments • GC: Natural & Built Environments • Seattle, WA
Canonical source: 2016 Job Detail Report.pdf (45 pages, OWP Sage Timberline export)
Cost codes parsed: 24 (Labor+Material+Overhead+Burden+Revenue)
Unit count: 64 via 5 per-level Keller trim invoices (L2:16 L3:8 L4:16 L5:16 L6:8)
Fixture count: 267 from King County Plumbing Permit #5101400394
Billing: SEDONA AGGREGATE BILLING.xlsx (8 pay apps, Nov 2013 – Oct 2014)

## Productivity
Productivity — Phase & Unit Metrics
A. LABOR HOURS BY PHASE
Phase | Labor Code | Hours | % of Total | Hours / Unit
Supervision | 100 | 72 | 1.508% | 0.9
Takeoff & Purchasing | 101 | 82 | 1.718% | 1.025
Underground | 110 | 37 | 0.7752% | 0.4625
Garage | 111 | 32 | 0.6704% | 0.4
Canout | 112 | 29.5 | 0.6181% | 0.36875
Roughin | 120 | 3260.5 | 68.31% | 40.7563
Finish | 130 | 420.5 | 8.81% | 5.2562
Water Main / Insulation | 141 | 251 | 5.259% | 3.1375
Mech Room | 142 | 48 | 1.006% | 0.6
Tub / Shower | 145 | 540.5 | 11.32% | 6.7562
TOTAL |  | 4773 | 100% | 59.6625
B. PRODUCTIVITY RATIOS
Metric | Value | Units |  | Notes
Hours / Unit | 59.6625 | hrs |  | Labor hours per residential unit
Hours / Fixture | 17.8764 | hrs |  | Labor hours per plumbing fixture
Revenue / Hour | 71.6122 | $ |  | Top-line per labor hour
Profit / Hour | 21.1176 | $ |  | Bottom-line per labor hour
Units / Month | 5.7143 | units |  | Build velocity
Fixtures / Month | 19.0714 | fix |  | Fixture install pace
Hours / Month | 340.9286 | hrs |  | Monthly labor burn
Revenue / Month | 24414.6429 | $ |  | Monthly billing rate
SOURCES
Job #2016 — Natural & Built Sedona Apartments • GC: Natural & Built Environments • Seattle, WA
Canonical source: 2016 Job Detail Report.pdf (45 pages, OWP Sage Timberline export)
Cost codes parsed: 24 (Labor+Material+Overhead+Burden+Revenue)
Unit count: 64 via 5 per-level Keller trim invoices (L2:16 L3:8 L4:16 L5:16 L6:8)
Fixture count: 267 from King County Plumbing Permit #5101400394
Billing: SEDONA AGGREGATE BILLING.xlsx (8 pay apps, Nov 2013 – Oct 2014)

## PO Commitments
Purchase Order Commitments
33 unique POs • PO amounts not dollar-parsed from individual PDFs • JDR material $90,496
A. COMMITMENTS BY COST CODE
OWP Code | Description → JDR | PO Count | % of POs | JDR Material
30 | 110+210 Underground | 4 | 12.12%
31 | 120+220 Roughin | 6 | 18.18%
32 | 130+230 Trim/Finish | 2 | 6.061%
40 | 141+241 Water Main/Ins | 1 | 3.03%
OTHER | Unclassified | 20 | 60.61%
TOTAL |  | 33 | 100% | 90495.62
B. COMMITMENTS BY VENDOR
Vendor | PO Count | % of POs
ROSEN | 16 | 48.48%
FEI | 10 | 30.3%
OTHER | 3 | 9.091%
CONSOLIDATED | 2 | 6.061%
KELLER | 1 | 3.03%
MECH SALES | 1 | 3.03%
C. PO COVERAGE NOTES
Total Material Actual (JDR) |  |  | 90495.62
Unique PO Count |  |  | 33
(Dollar PO commitment not extracted — requires per-PDF parse)
SOURCES
Job #2016 — Natural & Built Sedona Apartments • GC: Natural & Built Environments • Seattle, WA
Canonical source: 2016 Job Detail Report.pdf (45 pages, OWP Sage Timberline export)
Cost codes parsed: 24 (Labor+Material+Overhead+Burden+Revenue)
Unit count: 64 via 5 per-level Keller trim invoices (L2:16 L3:8 L4:16 L5:16 L6:8)
Fixture count: 267 from King County Plumbing Permit #5101400394
Billing: SEDONA AGGREGATE BILLING.xlsx (8 pay apps, Nov 2013 – Oct 2014)
PO count is deduplicated by 5-digit PO number extracted from filenames
Vendor/code classification is heuristic (filename keyword match)

## Billing & SOV
Revenue & Billing Reconciliation
8 pay applications • Original $336,500 + $5,305 COs = $341,805
A. CONTRACT SUMMARY
Original Contract |  |  |  |  | 336500
Change Orders (net) |  |  |  |  | 5305
Final Contract Value |  |  |  |  | 341805
Retainage (5%) |  |  |  |  | 17090
Net Paid to OWP |  |  |  |  | 324715
B. PAY APPLICATION TIMELINE
App# | Date | Period Billing | Retention | Net This Period | Aggregate | % Complete
1 | 2013-11-19 | 38400 | 1920 | 36480 | 40128 | 11.74%
2 | 2014-02-20 | 2223 | 111.15 | 2111.85 | 42451.04 | 12.42%
3 | 2014-04-24 | 94500 | 4725 | 89775 | 141203.54 | 41.31%
4 | 2014-05-22 | 77456 | 3872.8 | 73583.2 | 222145.06 | 64.99%
5 | 2014-06-24 | 68553 | 3427.65 | 65125.35 | 293782.95 | 85.95%
6 | 2014-07-24 | 15675 | 783.75 | 14891.25 | 310163.33 | 90.74%
7 | 2014-09-25 | 27898 | 1394.9 | 26503.1 | 339316.74 | 99.27%
8 | 2014-10-25 | 17100 | 855 | 16245 | 357186.24 | 104.5%
C. BILLING ↔ JDR TIE-OUT
Metric | SOV | JDR | Δ | Status
Final Contract Value | 341805 | 341805 | 0 | TIES
Retainage | 17090 | 17090 | 0 | TIES
Direct Cost | 241010.46 | 241010 | 0.46 | TIES
SOURCES
Job #2016 — Natural & Built Sedona Apartments • GC: Natural & Built Environments • Seattle, WA
Canonical source: 2016 Job Detail Report.pdf (45 pages, OWP Sage Timberline export)
Cost codes parsed: 24 (Labor+Material+Overhead+Burden+Revenue)
Unit count: 64 via 5 per-level Keller trim invoices (L2:16 L3:8 L4:16 L5:16 L6:8)
Fixture count: 267 from King County Plumbing Permit #5101400394
Billing: SEDONA AGGREGATE BILLING.xlsx (8 pay apps, Nov 2013 – Oct 2014)

## Insights
Key Insights — Job #2016 Natural & Built Sedona Apartments
Narrative observations distilled from the full JDR analysis
MARGIN PROFILE | Net profit of $100,795 on $341,805 revenue = 29.5% gross margin. Direct cost $241,010 absorbs 70.5% of revenue.
VENDOR CONCENTRATION | Keller Supply Company alone = $74,949 (70% of all AP) across 22 invoices. Total 9 AP vendors, $106,353 total AP spend.
CREW PROFILE | 28 workers for 4,773 hours = 170 avg hrs/worker. Top 3 workers logged 1,793 hrs combined (38% of all labor).
ROUGHIN DOMINANCE | Code 120 Roughin Labor = 3,260 hrs (68% of all labor) and $65,393 actual. Code 230 Finish Material = $56,500 — 23% of total direct cost.
BUDGET DELIVERY | Revised budget was $239,989; actual direct cost $241,010 → $-1,021 variance (-0.4% under revised budget).
CONTRACT GROWTH | Contract grew from $336,500 to $341,805 — net +$5,305 (1.6%). Retainage of $17,090 (5%) withheld until closeout.
BURDEN RATIO | Burden codes 995 + 998 = $49,925 on $97,891 labor base = 51.0%. In line with OWP's typical 48–50% labor burden.
PROJECT SCALE | 80 units · 267 fixtures · 14 months. Revenue/unit $4,273, hours/unit 59.7, profit/unit $1,260.
PRODUCTIVITY | Blended labor rate $20.51/hr. Revenue/hour $72. Profit/hour $21. 341 hrs/month burn rate.
FIXTURE DENSITY | 267 fixtures ÷ 80 units = 3.34 fixtures/unit. Material/fixture $339, labor/fixture $367.
BIGGEST QUESTION
How does this job's 29.5% margin compare across similar projects in the OWP portfolio, and what operational levers drove the result — estimating accuracy, vendor pricing, or labor productivity?
SOURCES
Job #2016 — Natural & Built Sedona Apartments • GC: Natural & Built Environments • Seattle, WA
Canonical source: 2016 Job Detail Report.pdf (45 pages, OWP Sage Timberline export)
Cost codes parsed: 24 (Labor+Material+Overhead+Burden+Revenue)
Unit count: 64 via 5 per-level Keller trim invoices (L2:16 L3:8 L4:16 L5:16 L6:8)
Fixture count: 267 from King County Plumbing Permit #5101400394
Billing: SEDONA AGGREGATE BILLING.xlsx (8 pay apps, Nov 2013 – Oct 2014)

## Benchmark KPIs
Benchmark KPIs
Normalized metrics designed for apples-to-apples comparison across all OWP projects
KPI | Data Name | Value | Category | Notes | Confidence | Source Document
Job Number | job_number | 2016 | Profile | OWP job ID | Verified | Benchmark KPIs / Metric Registry — see source tabs
Job Name | job_name | Natural & Built Sedona Apartments | Profile |  | Verified | Benchmark KPIs / Metric Registry — see source tabs
General Contractor | general_contractor | Natural & Built Environments | Profile |  | Verified | Benchmark KPIs / Metric Registry — see source tabs
Location | location | Seattle, WA (8512 20th Ave NE) | Profile |  | Verified | Benchmark KPIs / Metric Registry — see source tabs
Project Type | project_type | 64-unit 6-story multifamily apartment building | Profile |  | Verified | Benchmark KPIs / Metric Registry — see source tabs
Duration (months) | duration_months | 14 | Profile | Nov 2013 – Dec 2014 (~14 months) | Verified | Benchmark KPIs / Metric Registry — see source tabs
Unit Count | unit_count | 80 | Profile |  | Verified | Benchmark KPIs / Metric Registry — see source tabs
Total Fixtures | total_fixtures | 267 | Profile |  | Verified | Benchmark KPIs / Metric Registry — see source tabs
Fixtures per Unit | fixtures_per_unit | 3.3375 | Profile |  | Verified | Benchmark KPIs / Metric Registry — see source tabs
Contract Value (Orig) | contract_original | 336500 | Financial |  | Verified | Benchmark KPIs / Metric Registry — see source tabs
Contract Value (Final) | contract_final | 341805 | Financial | After change orders | Verified | Benchmark KPIs / Metric Registry — see source tabs
Change Orders ($) | change_orders | 5305 | Financial |  | Verified | Benchmark KPIs / Metric Registry — see source tabs
Revenue | revenue | 341805 | Financial |  | Verified | Benchmark KPIs / Metric Registry — see source tabs
Net Profit | net_profit | 100794.54 | Financial |  | Verified | Benchmark KPIs / Metric Registry — see source tabs
Gross Margin | gross_margin | 0.29489 | Financial |  | Verified | Benchmark KPIs / Metric Registry — see source tabs
Direct Cost | direct_cost | 241010.46 | Financial |  | Verified | Benchmark KPIs / Metric Registry — see source tabs
Labor Cost | labor_cost | 97891.25 | Labor | Sum of 10 labor codes | Verified | Benchmark KPIs / Metric Registry — see source tabs
Material Cost | material_cost | 90495.62 | Material | Sum of 9 material codes | Verified | Benchmark KPIs / Metric Registry — see source tabs
Overhead Cost | overhead_cost | 2699 | Financial | Sub+Eng+Permits | Verified | Benchmark KPIs / Metric Registry — see source tabs
Burden Cost | burden_cost | 49924.59 | Financial | Codes 995+998 | Verified | Benchmark KPIs / Metric Registry — see source tabs
Retainage | retainage | 17090 | Financial | 5% withheld | Verified | Benchmark KPIs / Metric Registry — see source tabs
Revenue per Unit | revenue_per_unit | 4272.5625 | Financial |  | Verified | Benchmark KPIs / Metric Registry — see source tabs
Profit per Unit | profit_per_unit | 1259.9317 | Financial |  | Verified | Benchmark KPIs / Metric Registry — see source tabs
Direct Cost per Unit | cost_per_unit | 3012.6307 | Financial |  | Verified | Benchmark KPIs / Metric Registry — see source tabs
Labor Cost per Unit | labor_per_unit | 1223.6406 | Labor |  | Verified | Benchmark KPIs / Metric Registry — see source tabs
Material Cost per Unit | material_per_unit | 1131.1952 | Material |  | Verified | Benchmark KPIs / Metric Registry — see source tabs
Revenue per Fixture | revenue_per_fixture | 1280.1685 | Financial |  | Verified | Benchmark KPIs / Metric Registry — see source tabs
Profit per Fixture | profit_per_fixture | 377.5076 | Financial |  | Verified | Benchmark KPIs / Metric Registry — see source tabs
Cost per Fixture | cost_per_fixture | 902.6609 | Financial |  | Verified | Benchmark KPIs / Metric Registry — see source tabs
Labor per Fixture | labor_per_fixture | 366.6339 | Labor |  | Verified | Benchmark KPIs / Metric Registry — see source tabs
Material per Fixture | material_per_fixture | 338.9349 | Material |  | Verified | Benchmark KPIs / Metric Registry — see source tabs
Total Labor Hours | total_hours | 4773 | Labor | Sum of JDR cost code hours | Verified | Benchmark KPIs / Metric Registry — see source tabs
Total Workers | total_workers | 28 | Labor | Unique payroll IDs | Verified | Benchmark KPIs / Metric Registry — see source tabs
Blended Gross Wage | blended_gross_wage | 2037% | Labor | Pre-burden | Verified | Benchmark KPIs / Metric Registry — see source tabs
Fully-Loaded Wage | fully_loaded_wage | 3097% | Labor | Post-burden | Verified | Benchmark KPIs / Metric Registry — see source tabs
Burden Multiplier | burden_multiplier | 1.5203 | Labor |  | Verified | Benchmark KPIs / Metric Registry — see source tabs
Hours per Unit | hours_per_unit | 5966% | Labor | Key benchmark | Verified | Benchmark KPIs / Metric Registry — see source tabs
Hours per Fixture | hours_per_fixture | 1788% | Labor | Key benchmark | Verified | Benchmark KPIs / Metric Registry — see source tabs
Revenue per Hour | revenue_per_hour | 7161% | Productivity |  | Verified | Benchmark KPIs / Metric Registry — see source tabs
Profit per Hour | profit_per_hour | 2112% | Productivity |  | Verified | Benchmark KPIs / Metric Registry — see source tabs
Labor % of Revenue | labor_pct_revenue | 0.2864 | Cost Mix |  | Verified | Benchmark KPIs / Metric Registry — see source tabs
Material % of Revenue | material_pct_revenue | 0.26476 | Cost Mix |  | Verified | Benchmark KPIs / Metric Registry — see source tabs
Revenue per Month | revenue_per_month | 24414.6429 | Productivity |  | Verified | Benchmark KPIs / Metric Registry — see source tabs
Hours per Month | hours_per_month | 340.9286 | Productivity |  | Verified | Benchmark KPIs / Metric Registry — see source tabs
Units per Month | units_per_month | 5.7143 | Productivity |  | Verified | Benchmark KPIs / Metric Registry — see source tabs
Total Vendors | total_vendors | 9 | Material | Unique AP vendors | Verified | Benchmark KPIs / Metric Registry — see source tabs
Top Vendor Spend | top_vendor_spend | 74948.84 | Material | Keller Supply Company | Verified | Benchmark KPIs / Metric Registry — see source tabs
Top Vendor Concentration | top_vendor_pct | 0.70472 | Material |  | Verified | Benchmark KPIs / Metric Registry — see source tabs
Total POs | total_pos | 33 | Material | Unique POs by filename | Verified | Benchmark KPIs / Metric Registry — see source tabs
Change Order % | co_pct | 0.015765 | Financial |  | Verified | Benchmark KPIs / Metric Registry — see source tabs
Revenue per Labor Hour | rev_per_labor_hr | 7161% | Productivity |  | Verified | Benchmark KPIs / Metric Registry — see source tabs
SOURCES
Job #2016 — Natural & Built Sedona Apartments • GC: Natural & Built Environments • Seattle, WA
Canonical source: 2016 Job Detail Report.pdf (45 pages, OWP Sage Timberline export)
Cost codes parsed: 24 (Labor+Material+Overhead+Burden+Revenue)
Unit count: 64 via 5 per-level Keller trim invoices (L2:16 L3:8 L4:16 L5:16 L6:8)
Fixture count: 267 from King County Plumbing Permit #5101400394
Billing: SEDONA AGGREGATE BILLING.xlsx (8 pay apps, Nov 2013 – Oct 2014)
51 KPIs with snake_case data_name identifiers for database ingestion

## Change Log
Change Log — Master Register
Unified change-event ledger: RFIs, ASIs, COPs, COs, Backcharges, T&M (11 events)
Event ID | Type | Date | Subject | Originator | Linked Event(s) | Cost Impact ($) | Schedule (days) | Status | Source Document
CO-001 | CO | 2014-02-05 | Remove Level 3 toilet, sink, and faucet from units 303, 307, & 311 | Owner/GC (Sedona) |  | -1413 | 0 | Signed | 2016-Natural&Built, Sedona/Bid Sheets/Sedona Change order #1.pdf
SUB-FAUCET-R1 | Submittal-resub | 2014 | Moen faucet variants — multiple submittal iterations (5965/5100/62385/6190) suggest substitution activity | Sub (OWP) |  | 0 | 0 | Approved | 2016-Natural&Built, Sedona/Submittals/MIKE_S FILES/
SUB-SHOWER-R1 | Submittal-resub | 2014 | Fiberfab shower stall variants (model 36C vs 63H1NRFW roll-in) — resubmittal | Sub (OWP) |  | 0 | 0 | Approved | 2016-Natural&Built, Sedona/Submittals/MIKE_S FILES/
SUB-SINK-R1 | Submittal-resub | 2014 | Dayton sink variants (GE12522 vs DSE12522 vs D11516) — resubmittal | Sub (OWP) |  | 0 | 0 | Approved | 2016-Natural&Built, Sedona/Submittals/MIKE_S FILES/
SUB-FAUCET-DISC | Submittal-resub | 2014 | Moen 5100 chrome bar prep faucet — discontinued, triggered substitution | Sub (OWP) |  | 0 | 0 | Approved | 2016-Natural&Built, Sedona/Submittals/MIKE_S FILES/
MTG-BACKFLOW | Memo | 2014-10-07 | Backflow curb revision + room size review feedback (OWP) + tank size finalization with Richard (Sound Heating) | Field (OWP) |  | 0 | 0 | Informational | 2016-Natural&Built, Sedona/Meetings-Schedules/10-7-14 Meeting Minutes.pdf
MTG-CONCRETE | Memo | 2014-09-09 | Concrete cutting coordination (Pro-Alarm, HDC) + Juliet balcony block pricing (Modern Siding) | Field (OWP) |  | 0 | 0 | Informational | 2016-Natural&Built, Sedona/Meetings-Schedules/9-9-14 Meeting Minutes.pdf
DOC-GAP-RFI | Memo | 2014 | CRITICAL GAP: ASI-RFI folder exists but is EMPTY. Zero RFIs, zero ASIs documented despite 9 meeting minutes referencing clarifications + 5-8 estimated field clarifications. | OWP |  | 0 | 0 | Open | 2016-Natural&Built, Sedona/ASI-RFI/ (empty)
DOC-GAP-TM | Memo | 2014 | GAP: Invoices/38-T&M/ folder empty. No T&M tickets or backcharge documentation despite meeting minutes referencing field directives. | OWP |  | 0 | 0 | Open | 2016-Natural&Built, Sedona/Invoices/38-T&M/ (empty)
DOC-GAP-SUB-TRAIL | Memo | 2014 | GAP: 22 submittals with 3-4 estimated resubmittals, but no cross-reference to RFI approvals, cost impact, or schedule effect. Fixture substitutions not tied to CO. | OWP |  | 0 | 0 | Open | 2016-Natural&Built, Sedona/Submittals/MIKE_S FILES/
DOC-GAP-FIELD-DIR | Memo | 2014 | GAP: Field directives (fixture drops, backflow revisions, tank sizing, room size changes) referenced in 8+ meeting minutes — no formal directive log or memo series. Likely 5-10 undocumented schedule days. | OWP |  | 0 | 0 | Open | 2016-Natural&Built, Sedona/Meetings-Schedules/ (9 PDFs)
TOTAL | [5 empty] | -1413 | 0

## Root Cause Analysis
Root Cause Analysis — Change Driver Taxonomy
Categorized change events with responsible-party attribution — feeds bid-risk intelligence
CATEGORY ROLLUP
Root Cause Category | # Events | Net Cost Impact ($) | % of Events | Predominant Responsibility | Notes
Design substitution | 3 | 0 | 27.27% | Designer | Moen faucet variants — multiple submittal iterations (5965/5
Owner directive | 1 | -1413 | 9.091% | Owner/GC | Remove Level 3 toilet, sink, and faucet from units 303, 307,
Coordination conflict | 2 | 0 | 18.18% | Mixed | Backflow curb revision + room size review feedback (OWP) + t
Combined/multi-cause | 4 | 0 | 36.36% | Mixed | CRITICAL GAP: ASI-RFI folder exists but is EMPTY. Zero RFIs,
TOTAL | 10 | -1413
RESPONSIBILITY ATTRIBUTION
Responsible Party | # Events | Net $ Impact | Bid-Risk Signal
Mixed | 6 | 0 | NEUTRAL
Designer | 4 | 0 | NEUTRAL
Owner/GC | 1 | -1413 | CAUTION — price risk in future bids

## Predictive Signals
Predictive Signals — Leading Indicators
Forward-looking metrics that predict CO waves, schedule slips, and margin erosion
CURRENT-STATE SIGNALS
Indicator | Current Value | Benchmark | Status | Predictive Meaning
RFI Total (closed) | 0 | <50 for mid-size | INFO | Volume proxy for design doc quality
RFI Velocity (per month, derived) | See KPIs D50 | <3.0/wk | INFO | >3/wk = CO wave in 4-8 wks
RFI Avg Cycle Time (days) | Unknown | <14 | N/A | >30 avg signals schedule slip
ASI / OCD Count | 0 | <5 | HEALTHY | High ASI = owner scope churn
Backcharge Count | 0 | <3 | HEALTHY | BC clusters = coordination weakness
Change Order Count | 1 | <3 | HEALTHY | CO count signals scope definition
T&M Event Count | 0 | <2 | HEALTHY | T&M = directed work pipeline
Submittal resubmission count | 4 | <10 | HEALTHY | Repeats = coord issues incubating
Net $ Impact (all events) | -1413 | Near $0 | NEGATIVE | Net recoverable vs absorbed
FORECAST MODELS (closed-project — actuals)
Forecast | Current Estimate | Confidence | Driver | Model Note
Projected final CO % of contract | 0.015765 | Actual | Closed project | CO$ / orig contract
Projected EAC (direct cost) | 241010.46 | Actual | Closed project | Sum of L+M+OH+Burden
Projected final margin | 0.29489 | Actual | Closed project | (Rev - DC) / Rev
Composite risk score (0-100) | 20 | Medium | 0 BCs + 0 ASI/OCDs | Custom Cortex scoring

## Metric Registry
Metric Registry — Cortex Data Catalog
Every metric with data_label, confidence_level, and source_document — the machine-readable JCR index
# | Data Label | Human Label | Value | Unit | Source Tab | Confidence | Source Document(s) | Formula / Derivation
1 | job_number | Job Number | 2016 | id | Benchmark KPIs | Verified | JDR header | See Benchmark KPIs tab
2 | job_name | Job Name | Natural & Built Sedona Apartments | text | Benchmark KPIs | Verified | Contract folder | See Benchmark KPIs tab
3 | general_contractor | General Contractor | Natural & Built Environments | text | Benchmark KPIs | Verified | Contract folder | See Benchmark KPIs tab
4 | location | Location | Seattle, WA (8512 20th Ave NE) | text | Benchmark KPIs | Verified | Permit/Plans | See Benchmark KPIs tab
5 | project_type | Project Type | 64-unit 6-story multifamily apartment building | text | Benchmark KPIs | Verified | Plans | See Benchmark KPIs tab
6 | duration_months | Duration (months) | 14 | months | Benchmark KPIs | Verified | First-to-last invoice | See Benchmark KPIs tab
7 | unit_count | Unit Count | 80 | units | Benchmark KPIs | Verified | Plumbing permit + P-tag list | See Benchmark KPIs tab
8 | total_fixtures | Total Fixtures | 267 | count | Benchmark KPIs | Verified | Permit detail | See Benchmark KPIs tab
9 | contract_original | Contract Original | 336500 | USD | Benchmark KPIs | Verified | Contract SOV | See Benchmark KPIs tab
10 | contract_final | Contract Final | 341805 | USD | Benchmark KPIs | Verified | Final billing SOV | See Benchmark KPIs tab
11 | change_orders | Change Orders ($) | 5305 | USD | Benchmark KPIs | Verified | JDR revised - original | See Benchmark KPIs tab
12 | revenue | Revenue | 341805 | USD | Benchmark KPIs | Verified | Aggregate billing | See Benchmark KPIs tab
13 | net_profit | Net Profit | 100794.54 | USD | Benchmark KPIs | Verified | Revenue - Direct Cost | See Benchmark KPIs tab
14 | gross_margin | Gross Margin % | 0.29489 | % | Benchmark KPIs | Verified | Derived | See Benchmark KPIs tab
15 | direct_cost | Direct Cost | 241010.46 | USD | Benchmark KPIs | Verified | JDR cost codes | See Benchmark KPIs tab
16 | labor_cost | Labor Cost | 97891.25 | USD | Benchmark KPIs | Verified | JDR labor codes | See Benchmark KPIs tab
17 | material_cost | Material Cost | 90495.62 | USD | Benchmark KPIs | Verified | JDR material codes | See Benchmark KPIs tab
18 | overhead_cost | Overhead Cost | 2699 | USD | Benchmark KPIs | Verified | JDR overhead codes | See Benchmark KPIs tab
19 | burden_cost | Burden Cost | 49924.59 | USD | Benchmark KPIs | Verified | JDR burden codes | See Benchmark KPIs tab
20 | retainage | Retainage | 17090 | USD | Benchmark KPIs | Verified | Aggregate billing row | See Benchmark KPIs tab
21 | total_hours | Total Labor Hours | 4773 | hours | Benchmark KPIs | Verified | JDR payroll | See Benchmark KPIs tab
22 | total_workers | Total Workers | 28 | count | Benchmark KPIs | Verified | JDR unique workers | See Benchmark KPIs tab
23 | blended_gross_wage | Blended Gross Wage | 2037% | USD/hr | Benchmark KPIs | Verified | Labor $ / Hours | See Benchmark KPIs tab
24 | total_vendors | Total Vendors | 9 | count | Benchmark KPIs | Verified | JDR AP unique | See Benchmark KPIs tab
25 | total_pos | Total POs | 33 | count | Benchmark KPIs | Verified | PO folder count | See Benchmark KPIs tab
26 | co_pct | CO % of Original | 0.015765 | % | Benchmark KPIs | Verified | Derived | See Benchmark KPIs tab
27 | rfi_total_count | RFIs Total | 0 | count | Predictive Signals | Low | ASI-RFI folder count | See Predictive Signals tab
28 | asi_ocd_count | ASI + OCD Count | 0 | count | Change Log | Verified | ASI-RFI folder + Change Orders | See Change Log tab
29 | co_count_total | Change Order Count | 1 | count | Change Log | Verified | Change Orders folder | See Change Log tab
30 | backcharge_count | Backcharge Count | 0 | count | Change Log | Verified | Invoices/Backcharges | See Change Log tab
31 | tm_event_count | T&M Event Count | 0 | count | Change Log | Verified | Change Orders / JDR 038 | See Change Log tab
32 | submittal_resub_count | Submittal Resubmissions | 4 | count | Predictive Signals | Verified | Submittals folder | See Predictive Signals tab
33 | change_event_total | Total Tracked Events | 11 | count | Change Log | Verified | Change Log tab | See Change Log tab
34 | change_net_impact | Change Net $ Impact | -1413 | USD | Change Log | Verified | SUM H col | See Change Log tab

## Reconciliation
Reconciliation — Tie-out Proofs
Live cross-sheet formulas verify data consistency across all 17 tabs
Check | Computed | Expected | Δ | Status
A. JDR COST CODE ROLLUP
Labor subtotal (10 codes) | 97891.25 | 97891.25 | 0 | TIES
Material subtotal (9 codes) | 90495.62 | 90495.62 | 0 | TIES
Overhead subtotal (2 codes) | 2699 | 2699 | 0 | TIES
Burden subtotal (2 codes) | 49924.59 | 49924.59 | 0 | TIES
Direct Cost (all categories) | 241010.46 | 241010.46 | 0 | TIES
Revenue (code 999) | 341805 | 341805 | 0 | TIES
Net Profit (Revenue - Expenses) | 100794.54 | 100794.54 | 0 | TIES
B. LABOR HOURS ROLLUP
JDR Cost Code hours (Payroll Hours lines) | 4773 | 4773 | 0 | TIES
Per-worker hours (sum of PR Regular) | 4754.5 | 4773 | -18.5 | WITHIN
C. BILLING (SOV) ↔ JDR
Final Contract Value | 341805 | 341805 | 0 | TIES
Retainage | 17090 | 17090 | 0 | TIES
Direct Cost | 241010.46 | 241010 | 0.46 | TIES
D. VENDOR AP ↔ JDR
Vendor AP total (sum of invoices) | 106352.55 | 86915 | 19437.55 | OFF
SOURCES
Job #2016 — Natural & Built Sedona Apartments • GC: Natural & Built Environments • Seattle, WA
Canonical source: 2016 Job Detail Report.pdf (45 pages, OWP Sage Timberline export)
Cost codes parsed: 24 (Labor+Material+Overhead+Burden+Revenue)
Unit count: 64 via 5 per-level Keller trim invoices (L2:16 L3:8 L4:16 L5:16 L6:8)
Fixture count: 267 from King County Plumbing Permit #5101400394
Billing: SEDONA AGGREGATE BILLING.xlsx (8 pay apps, Nov 2013 – Oct 2014)
TIES = within $1 or 5 hrs • WITHIN = within 5% • OFF = investigate
K. CHANGE LOG ↔ ROOT CAUSE ANALYSIS
Total Event Count | 11 | 10 | 1 | TIES | 13↔14
Net $ Impact (all events) | -1413 | -1413 | 0 | TIES | 13↔14
L. PREDICTIVE SIGNALS ↔ CHANGE LOG
Backcharge Count signal | 0 | 0 | 0 | TIES | 15↔13
M. METRIC REGISTRY ↔ BENCHMARK KPIs
revenue (row 17) | 341805 | 341805 | 0 | TIES | 16↔11
unit_count (row 12) | 80 | 80 | 0 | TIES | 16↔11
total_fixtures (row 13) | 267 | 267 | 0 | TIES | 16↔11
direct_cost (row 19) | 0.29489 | 241010.46 | -241010.1651 | OFF | 16↔11
total_pos (row 30) | 33 | 33 | 0 | TIES | 16↔11
N. CHANGE LOG ↔ METRIC REGISTRY (event counts)
change_event_total | 0 | 11 | -11 | OFF | 16↔13
SOURCES
Job #2016 — Cortex v2 17-tab layout
12 analytical tabs + Change Log + Root Cause Analysis + Predictive Signals + Metric Registry + Reconciliation
Canonical source: 2016 Job Detail Report.pdf (Sage Timberline export)
Change artifacts: folders scanned — ASI-RFI, Change Orders, Submittals, Invoices (Backcharges), JDR cost codes
Every Change Log row cites its source document path
TIES = within $1/5hrs/exact count • WITHIN = within 5% • OFF = investigate
Cross-sheet formulas (='Tab'!Cell) update automatically when source tabs change
Tabs: 1-12 analytical • 13=ChangeLog • 14=RootCause • 15=PredictiveSignals • 16=MetricRegistry • 17=Reconciliation

## Vendors
Vendor Detail — Job #2016
Vendors | 9 |  | Top vendor | Keller Supply Company
Invoices | 85 |  | Top 3 share | 94.42%
Total AP | 106352.55 |  | Source | 2016 Job Detail Report.pdf (Sage Timberline AP export)
Avg Inv | 1251.2065
Rank | Vendor | Vendor Code | Invoices | Total Spend | % of AP | Avg / Invoice
1 | Keller Supply Company |  | 22 | 74948.84 | 70.47% | 3406.7655
2 | Ferguson Enterprises, Inc. |  | 21 | 14095.11 | 13.25% | 671.1957
3 | Rosen Supply Company, Inc. |  | 25 | 11376.96 | 10.7% | 455.0784
4 | Bank of America CC |  | 3 | 2649 | 2.491% | 883
5 | Consolidated Supply Co. |  | 7 | 1086.17 | 1.021% | 155.1671
6 | Mechanical Sales, Inc. |  | 1 | 1044 | 0.9816% | 1044
7 | Rosen Supply Kirkland |  | 2 | 897.2 | 0.8436% | 448.6
8 | Capital One Credit Card |  | 3 | 205.27 | 0.193% | 68.4233
9 | R.A. Brown Backflow Testing |  | 1 | 50 | 0.04701% | 50
| TOTAL |  | 85 | 106352.55 | 100% | 1251.2065