## Overview
Job #2018 · SRM Astro Apartments
Cortex JCR Summary • SRMQA, LLC (SRM Development) • Seattle, WA • 6-story multifamily apartments + 3 levels below-grade parking + retail/amenity • Dec 2013 – Feb 2015 (~15 months)
PROJECT OVERVIEW
Project Job # | 2018
Project Name: | SRM Astro Apartments
General Contractor | SRMQA, LLC (SRM Development)
Location | Seattle, WA
Project Duration | Dec 2013 – Feb 2015 (~15 months)
Total Unique Documents | Astro folder: Contract, Billings (15 SOVs + aggregate), PO_s, COs (5)
CONTRACT VALUE |  | NET PROFIT |  | DIRECT COST |  | LABOR HOURS
$2,305,058 |  | $1,072,788 |  | $1,232,270 |  | 23,300
Original $2,282,726 + $22,332 COs (5) |  | 46.5% margin |  | 53.5% of revenue |  | 48 workers
COST BREAKDOWN
Category | Budget | Actual | Variance | % Budget | % of Cost
Labor | 468235 | 440392.94 | 27842.06 | 94.05% | 35.74%
Material | 722677 | 556906.77 | 165770.23 | 77.06% | 45.19%
Overhead | 8150 | 4943.28 | 3206.72 | 60.65% | 0.4012%
Burden | 243900.6 | 230026.81 | 13873.79 | 94.31% | 18.67%
TOTAL | 1442962.6 | 1232269.8 | 210692.8 | 85.4% | 100%
PROJECT PROFILE
Metric | Value | Metric | Value | Metric | Value
Plumbing Units | 212 | Water Closets | 242 (239 res + 3 common) | Kitchen Sinks | 212
Total Fixtures | ~1,144 | Lavatories | 242 | Dishwashers | 212
Fixtures / Unit | 5.4 | Tubs/Showers | 233 (fiberglass) | Auto Washers | 212
Levels | L2–L6 residential (N+S wings) + L1 retail/amenity + P1/P2/P3 parking | Duration | 15 mo | Below-grade | 3 PT deck parking levels
SOURCES
Job #2018 — SRM Astro Apartments • GC: SRMQA, LLC (SRM Development) • Seattle, WA
Canonical source: 2018 Job Detail Report.pdf (183 pages, OWP Sage Timberline export)
Cost codes parsed: 29 (Labor+Material+Overhead+Burden+Revenue)
Unit count (212) from 11 Keller Supply per-level trim POs (L1N, L2N/S, L3N/S, L4N/S, L5N/S, L6N/S)
Per-level residential WCs: L2N=25, L2S=24, L3N=25, L3S=23, L4N=25, L4S=23, L5N=25, L5S=23, L6N=25, L6S=21 = 239 res + 3 common (L1N)
Billing: ASTRO AGGREGATE BILLING.xlsx (15 pay apps, Dec 2013 – Feb 2015) + 15 underlying SOV files
Change orders: 5 COs net +$22,332 (roof deck, ASK 40, sky lounge, trench drain, tub liners)

## Budget vs Actual
Budget vs Actual — All Cost Codes
Code | Description | Orig Budget | Rev Budget | Actual | Variance | % Used
LABOR
011 | DS & RD Labor | 17545 | 19105 | 4039 | 15066 | 21.14%
100 | Supervision | 10000 | 10000 | 7795 | 2205 | 77.95%
101 | Takeoff & Purchase Labor | 10000 | 10440 | 9680 | 760 | 92.72%
110 | Underground Labor | 9330 | 9330 | 8108.75 | 1221.25 | 86.91%
111 | Garage Labor | 71700 | 71700 | 33852.25 | 37847.75 | 47.21%
112 | Canout Labor | 10400 | 10400 | 5609.75 | 4790.25 | 53.94%
113 | Foundation Drain Labor | 6625 | 6625 | 952 | 5673 | 14.37%
120 | Roughin Labor | 207140 | 208010 | 256945.47 | -48935.47 | 123.5%
130 | Finish Labor | 43900 | 44800 | 58292.75 | -13492.75 | 130.1%
140 | Gas Labor | 7200 | 8390 | 8626.5 | -236.5 | 102.8%
141 | Water Main/Insulation Lab | 40550 | 40550 | 31534.47 | 9015.53 | 77.77%
142 | Mech Room Labor | 8400 | 8400 | 14152 | -5752 | 168.5%
145 | Tub/Shower Labor | 20485 | 20485 | 805 | 19680 | 3.93%
MATERIAL
210 | Underground Material | 5900 | 5900 | 3233.67 | 2666.33 | 54.81%
211 | Garage Material | 45820 | 45820 | 74066.35 | -28246.35 | 161.6%
212 | Canout Material | 18200 | 18200 | 5771.34 | 12428.66 | 31.71%
213 | Foundation Material | 10600 | 10600 | 5372.56 | 5227.44 | 50.68%
220 | Roughin Material | 201680 | 201680 | 141396.65 | 60283.35 | 70.11%
230 | Finish Material | 390477 | 336907 | 272549.22 | 64357.78 | 80.9%
240 | Gas Material | 10800 | 10800 | 3578.52 | 7221.48 | 33.13%
241 | Water Main/Insulation Mat | 87250 | 87250 | 48338.27 | 38911.73 | 55.4%
242 | Mech Room Material | 5520 | 5520 | 1947.18 | 3572.82 | 35.27%
245 | Tub/Shower Material | 0 | 0 | 653.01 | -653.01 | 0%
OVERHEAD
600 | Subcontractor | 3000 | 3000 | 691.7 | 2308.3 | 23.06%
601 | Engineering/Plans | 3000 | 3000 | 2252.62 | 747.38 | 75.09%
603 | Permits & Licenses | 2000 | 2150 | 1998.96 | 151.04 | 92.97%
BURDEN
995 | Payroll Burden | 205165 | 207315.16 | 195501.68 | 11813.48 | 94.3%
998 | Payroll Taxes | 36206 | 36585.44 | 34525.13 | 2060.31 | 94.37%
TOTAL | Direct Cost | 1488893 | 1442962.6 | 1232269.8 | 210692.8 | 85.4%
SOURCES
Job #2018 — SRM Astro Apartments • GC: SRMQA, LLC (SRM Development) • Seattle, WA
Canonical source: 2018 Job Detail Report.pdf (183 pages, OWP Sage Timberline export)
Cost codes parsed: 29 (Labor+Material+Overhead+Burden+Revenue)
Unit count (212) from 11 Keller Supply per-level trim POs (L1N, L2N/S, L3N/S, L4N/S, L5N/S, L6N/S)
Per-level residential WCs: L2N=25, L2S=24, L3N=25, L3S=23, L4N=25, L4S=23, L5N=25, L5S=23, L6N=25, L6S=21 = 239 res + 3 common (L1N)
Billing: ASTRO AGGREGATE BILLING.xlsx (15 pay apps, Dec 2013 – Feb 2015) + 15 underlying SOV files
Change orders: 5 COs net +$22,332 (roof deck, ASK 40, sky lounge, trench drain, tub liners)

## Cost Breakdown
Cost Breakdown — Category Deep Dive
A. CATEGORY SHARE OF DIRECT COST
Category | # Codes | Budget | Actual | Variance | % Budget | % of Cost | Per Unit
Labor | 13 | 468235 | 440392.94 | 27842.06 | 94.05% | 35.74% | 2077.3252
Material | 10 | 722677 | 556906.77 | 165770.23 | 77.06% | 45.19% | 2626.9187
Overhead | 3 | 8150 | 4943.28 | 3206.72 | 60.65% | 0.4012% | 23.3174
Burden | 2 | 243900.6 | 230026.81 | 13873.79 | 94.31% | 18.67% | 1085.0321
B. LARGEST OVERRUNS (Actual > Revised Budget)
Code | Description | Rev Budget | Actual | Overrun | % Over
120 | Roughin Labor | 208010 | 256945.47 | 48935.47 | 23.53%
211 | Garage Material | 45820 | 74066.35 | 28246.35 | 61.65%
130 | Finish Labor | 44800 | 58292.75 | 13492.75 | 30.12%
142 | Mech Room Labor | 8400 | 14152 | 5752 | 68.48%
245 | Tub/Shower Material | 0 | 653.01 | 653.01 | 0%
140 | Gas Labor | 8390 | 8626.5 | 236.5 | 2.819%
C. LARGEST SAVINGS (Actual < Revised Budget)
Code | Description | Rev Budget | Actual | Savings | % Under
230 | Finish Material | 336907 | 272549.22 | 64357.78 | 19.1%
220 | Roughin Material | 201680 | 141396.65 | 60283.35 | 29.89%
241 | Water Main/Insulation Mat | 87250 | 48338.27 | 38911.73 | 44.6%
111 | Garage Labor | 71700 | 33852.25 | 37847.75 | 52.79%
145 | Tub/Shower Labor | 20485 | 805 | 19680 | 96.07%
011 | DS & RD Labor | 19105 | 4039 | 15066 | 78.86%
212 | Canout Material | 18200 | 5771.34 | 12428.66 | 68.29%
995 | Payroll Burden | 207315.16 | 195501.68 | 11813.48 | 5.698%
141 | Water Main/Insulation Lab | 40550 | 31534.47 | 9015.53 | 22.23%
240 | Gas Material | 10800 | 3578.52 | 7221.48 | 66.87%
SOURCES
Job #2018 — SRM Astro Apartments • GC: SRMQA, LLC (SRM Development) • Seattle, WA
Canonical source: 2018 Job Detail Report.pdf (183 pages, OWP Sage Timberline export)
Cost codes parsed: 29 (Labor+Material+Overhead+Burden+Revenue)
Unit count (212) from 11 Keller Supply per-level trim POs (L1N, L2N/S, L3N/S, L4N/S, L5N/S, L6N/S)
Per-level residential WCs: L2N=25, L2S=24, L3N=25, L3S=23, L4N=25, L4S=23, L5N=25, L5S=23, L6N=25, L6S=21 = 239 res + 3 common (L1N)
Billing: ASTRO AGGREGATE BILLING.xlsx (15 pay apps, Dec 2013 – Feb 2015) + 15 underlying SOV files
Change orders: 5 COs net +$22,332 (roof deck, ASK 40, sky lounge, trench drain, tub liners)

## Material
Material Spend Analysis
10 material cost codes • $556,907 JDR material • 19 AP vendors • $535,198 total AP
A. MATERIAL BY COST CODE
Code | Description | Rev Budget | Actual | Variance | % Used | % of Mat | Per Unit
210 | Underground Material | 5900 | 3233.67 | 2666.33 | 54.81% | 0.5806% | 15.2532
211 | Garage Material | 45820 | 74066.35 | -28246.35 | 161.6% | 13.3% | 349.3696
212 | Canout Material | 18200 | 5771.34 | 12428.66 | 31.71% | 1.036% | 27.2233
213 | Foundation Material | 10600 | 5372.56 | 5227.44 | 50.68% | 0.9647% | 25.3423
220 | Roughin Material | 201680 | 141396.65 | 60283.35 | 70.11% | 25.39% | 666.9653
230 | Finish Material | 336907 | 272549.22 | 64357.78 | 80.9% | 48.94% | 1285.6095
240 | Gas Material | 10800 | 3578.52 | 7221.48 | 33.13% | 0.6426% | 16.8798
241 | Water Main/Insulation Mat | 87250 | 48338.27 | 38911.73 | 55.4% | 8.68% | 228.0107
242 | Mech Room Material | 5520 | 1947.18 | 3572.82 | 35.27% | 0.3496% | 9.1848
245 | Tub/Shower Material | 0 | 653.01 | -653.01 | 0% | 0.1173% | 3.0802
TOTAL | All Material | 722677 | 556906.77 | 165770.23 | 77.06% | 100% | 2626.9187
B. VENDORS BY SPEND (AP)
Vendor | # Invoices | Total Spend | % of AP |  |  |  | Avg Invoice
Rosen Supply Company, Inc. | 87 | 187929.87 | 35.11% |  |  |  | 2160.1134
Keller Supply Company | 64 | 141063.76 | 26.36% |  |  |  | 2204.1213
Ferguson Enterprises, Inc. | 45 | 65193.3 | 12.18% |  |  |  | 1448.74
Mechanical Sales, Inc. | 4 | 47527.77 | 8.88% |  |  |  | 11881.9425
Consolidated Supply Co. | 21 | 43369.79 | 8.103% |  |  |  | 2065.2281
Franklin Engineering | 6 | 23133.75 | 4.322% |  |  |  | 3855.625
Bank of America CC | 3 | 11633 | 2.174% |  |  |  | 3877.6667
Quality Concrete Products, Inc. | 4 | 8875 | 1.658% |  |  |  | 2218.75
United Rentals, Inc. | 4 | 2252.62 | 0.4209% |  |  |  | 563.155
Ferguson Enterprises, Inc. #3007 | 3 | 934.77 | 0.1747% |  |  |  | 311.59
C.M. Hoskins Company | 4 | 654.66 | 0.1223% |  |  |  | 163.665
Kele, Inc | 2 | 637.54 | 0.1191% |  |  |  | 318.77
MAD Concrete Cutting & Coring, Inc. | 1 | 500 | 0.09342% |  |  |  | 500
Capital One Credit Card | 44 | 431.75 | 0.08067% |  |  |  | 9.8125
Fastenal Company | 3 | 372.77 | 0.06965% |  |  |  | 124.2567
DRSi | 2 | 354.99 | 0.06633% |  |  |  | 177.495
R.A. Brown Backflow Testing | 1 | 191.7 | 0.03582% |  |  |  | 191.7
Rosen Supply Kirkland | 2 | 111.82 | 0.02089% |  |  |  | 55.91
Core & Main LP | 1 | 29.39 | 0.005491% |  |  |  | 29.39
TOTAL | 301 | 535198.25 | 100%
SOURCES
Job #2018 — SRM Astro Apartments • GC: SRMQA, LLC (SRM Development) • Seattle, WA
Canonical source: 2018 Job Detail Report.pdf (183 pages, OWP Sage Timberline export)
Cost codes parsed: 29 (Labor+Material+Overhead+Burden+Revenue)
Unit count (212) from 11 Keller Supply per-level trim POs (L1N, L2N/S, L3N/S, L4N/S, L5N/S, L6N/S)
Per-level residential WCs: L2N=25, L2S=24, L3N=25, L3S=23, L4N=25, L4S=23, L5N=25, L5S=23, L6N=25, L6S=21 = 239 res + 3 common (L1N)
Billing: ASTRO AGGREGATE BILLING.xlsx (15 pay apps, Dec 2013 – Feb 2015) + 15 underlying SOV files
Change orders: 5 COs net +$22,332 (roof deck, ASK 40, sky lounge, trench drain, tub liners)
Vendor AP ties to JDR 'by Source: AP' line (535,198.25)

## Crew & Labor
Crew & Labor — Per-Worker Breakdown
Worker | Hours | Gross Pay | $/Hour | Tier
Waites, Thaddeus Z | 1056 | 29568 | 28 | Mid
Reyes, Robert J | 1006.25 | 13441.25 | 13.3578 | Apprentice
Cortes Mendiola, Victor H | 978.5 | 24497.5 | 25.0358 | Mid
Sanders, Allen O | 941 | 28383.5 | 30.1631 | Senior
Vaughan, Tyler J | 857.5 | 13751 | 16.0362 | Apprentice
Castaneda Juarez, Edgar D | 855.5 | 12404.75 | 14.5 | Apprentice
Anzora, William | 835.75 | 10864.75 | 13 | Apprentice
Palma Vides, Hugo | 825.5 | 23138 | 28.0291 | Mid
Arreola, Israel A | 824 | 13248 | 16.0777 | Apprentice
Kinssies, Jr, John E | 762.5 | 12099.5 | 15.8682 | Apprentice
Castaneda Martinez, Gustavo | 740 | 20720 | 28 | Mid
Rivera, Eli P | 699.5 | 9417.5 | 13.4632 | Apprentice
Ramos Banegas, Noel O | 686.25 | 9218.25 | 13.4328 | Apprentice
Holmes, Anthony R | 639.5 | 9225 | 14.4253 | Apprentice
Hubbard, Robert W | 636 | 21627 | 34.0047 | Senior
Garcia, Jordan X | 636 | 9237 | 14.5236 | Apprentice
Balderas Ortiz, Ricardo I | 624 | 8568 | 13.7308 | Apprentice
Castro Hernandez, Jose A | 620.5 | 10548.5 | 17 | Apprentice
Castaneda Juarez, Gustavo | 611 | 8554 | 14 | Apprentice
Spears, Gregory M | 591.5 | 8281 | 14 | Apprentice
Paco Leyva, Orlando | 589.5 | 10021.5 | 17 | Apprentice
Monico Brambila, Jesus S | 581 | 8390 | 14.4406 | Apprentice
McCabe, Thomas C | 580.5 | 10980 | 18.9147 | Mid
Alba Martinez, Santiago | 571.5 | 8620.5 | 15.084 | Apprentice
Meza Fuentes, Erick A | 506.75 | 10135 | 20 | Mid
Reed, Reuben H | 495 | 13860 | 28 | Mid
Gerard, Jeffrey S | 493.5 | 19039 | 38.5795 | Senior
Lopez Martinez, Abimael | 479.25 | 5990.75 | 12.5003 | Apprentice
Agustin Rodriguez, Ezequiel | 472 | 5664 | 12 | Apprentice
Bateman, Rohan O | 367 | 4404 | 12 | Apprentice
Velasquez Cruz, Denis M | 363 | 5453 | 15.022 | Apprentice
Ross, Kelli M | 320 | 9280 | 29 | Mid
Ramirez, Lorenzo A | 314.25 | 5028 | 16 | Apprentice
Hubbard, Dustin R | 310 | 4030 | 13 | Apprentice
Veley, Nathaniel S | 281.5 | 8163.5 | 29 | Mid
Soto Cruz, Jovani | 226 | 3616 | 16 | Apprentice
Salazar, Hajdar L | 208 | 3112 | 14.9615 | Apprentice
Sepulveda Gonzalez, Alfredo | 202 | 5077 | 25.1337 | Mid
Gonzalez Hernandez, Josue | 158.5 | 2219 | 14 | Apprentice
Soto Serna, Cesar E | 134 | 1742 | 13 | Apprentice
Reyes Cruz, Denis A | 133.5 | 1602 | 12 | Apprentice
Ramos Garcia, Jose M | 88 | 1144 | 13 | Apprentice
Gerard, Mitchell J | 74 | 898 | 12.1351 | Apprentice
Nishiyama, Joshua K | 61 | 793 | 13 | Apprentice
Sanchez Garcia, Adelaido | 56 | 728 | 13 | Apprentice
Wilson, Garret A | 33 | 470 | 14.2424 | Apprentice
Barnhart, Joseph N | 20.5 | 635.5 | 31 | Senior
Donelson, Richard T | 20 | 900 | 45 | Senior
TOTAL (48 workers) | 23566 | 448788.25 | 19.0439
SOURCES
Job #2018 — SRM Astro Apartments • GC: SRMQA, LLC (SRM Development) • Seattle, WA
Canonical source: 2018 Job Detail Report.pdf (183 pages, OWP Sage Timberline export)
Cost codes parsed: 29 (Labor+Material+Overhead+Burden+Revenue)
Unit count (212) from 11 Keller Supply per-level trim POs (L1N, L2N/S, L3N/S, L4N/S, L5N/S, L6N/S)
Per-level residential WCs: L2N=25, L2S=24, L3N=25, L3S=23, L4N=25, L4S=23, L5N=25, L5S=23, L6N=25, L6S=21 = 239 res + 3 common (L1N)
Billing: ASTRO AGGREGATE BILLING.xlsx (15 pay apps, Dec 2013 – Feb 2015) + 15 underlying SOV files
Change orders: 5 COs net +$22,332 (roof deck, ASK 40, sky lounge, trench drain, tub liners)
Tier: Apprentice <$18/hr, Mid $18–30, Senior >$30

## Crew Analytics
Crew Analytics
A. TIER DISTRIBUTION
Tier | # Workers | Hours | Gross Pay | % of Hours
Senior | 5 | 2111 | 70585 | 8.958%
Mid | 10 | 5985.75 | 155419 | 25.4%
Apprentice | 33 | 15469.25 | 222784.25 | 65.64%
B. WAGE STATISTICS
Blended Gross Wage | 19.0439 |  |  | Payroll $ ÷ payroll hours (pre-burden)
Fully-Loaded Wage | 28.4486 |  |  | (Labor + Burden) ÷ total hours
Burden Multiplier | 1.4938 |  |  | Fully loaded ÷ gross wage
Min Worker Rate | 12 |  |  | Cheapest apprentice hour
Max Worker Rate | 45 |  |  | Most expensive foreman hour
Avg Hours / Worker | 490.9583 |  |  | Crew continuity indicator
SOURCES
Job #2018 — SRM Astro Apartments • GC: SRMQA, LLC (SRM Development) • Seattle, WA
Canonical source: 2018 Job Detail Report.pdf (183 pages, OWP Sage Timberline export)
Cost codes parsed: 29 (Labor+Material+Overhead+Burden+Revenue)
Unit count (212) from 11 Keller Supply per-level trim POs (L1N, L2N/S, L3N/S, L4N/S, L5N/S, L6N/S)
Per-level residential WCs: L2N=25, L2S=24, L3N=25, L3S=23, L4N=25, L4S=23, L5N=25, L5S=23, L6N=25, L6S=21 = 239 res + 3 common (L1N)
Billing: ASTRO AGGREGATE BILLING.xlsx (15 pay apps, Dec 2013 – Feb 2015) + 15 underlying SOV files
Change orders: 5 COs net +$22,332 (roof deck, ASK 40, sky lounge, trench drain, tub liners)

## Productivity
Productivity — Phase & Unit Metrics
A. LABOR HOURS BY PHASE
Phase | Labor Code | Hours | % of Total | Hours / Unit
DS & RD | 011 | 258 | 1.107% | 1.217
Supervision | 100 | 203 | 0.8712% | 0.95755
Takeoff & Purchasing | 101 | 250.5 | 1.075% | 1.1816
Underground | 110 | 340.5 | 1.461% | 1.6061
Garage | 111 | 1616 | 6.935% | 7.6226
Canout | 112 | 238 | 1.021% | 1.1226
Foundation Drain | 113 | 49 | 0.2103% | 0.23113
Roughin | 120 | 14241 | 61.12% | 67.1745
Finish | 130 | 2845 | 12.21% | 13.4198
Gas | 140 | 429.5 | 1.843% | 2.0259
Water Main / Insulation | 141 | 1935.5 | 8.307% | 9.1297
Mech Room | 142 | 856 | 3.674% | 4.0377
Tub / Shower | 145 | 38.5 | 0.1652% | 0.1816
TOTAL |  | 23300.5 | 100% | 109.908
B. PRODUCTIVITY RATIOS
Metric | Value | Units |  | Notes
Hours / Unit | 109.908 | hrs |  | Labor hours per residential unit
Hours / Fixture | 20.3676 | hrs |  | Labor hours per plumbing fixture
Revenue / Hour | 98.9274 | $ |  | Top-line per labor hour
Profit / Hour | 46.0414 | $ |  | Bottom-line per labor hour
Units / Month | 14.1333 | units |  | Build velocity
Fixtures / Month | 76.2667 | fix |  | Fixture install pace
Hours / Month | 1553.3667 | hrs |  | Monthly labor burn
Revenue / Month | 153670.5333 | $ |  | Monthly billing rate
SOURCES
Job #2018 — SRM Astro Apartments • GC: SRMQA, LLC (SRM Development) • Seattle, WA
Canonical source: 2018 Job Detail Report.pdf (183 pages, OWP Sage Timberline export)
Cost codes parsed: 29 (Labor+Material+Overhead+Burden+Revenue)
Unit count (212) from 11 Keller Supply per-level trim POs (L1N, L2N/S, L3N/S, L4N/S, L5N/S, L6N/S)
Per-level residential WCs: L2N=25, L2S=24, L3N=25, L3S=23, L4N=25, L4S=23, L5N=25, L5S=23, L6N=25, L6S=21 = 239 res + 3 common (L1N)
Billing: ASTRO AGGREGATE BILLING.xlsx (15 pay apps, Dec 2013 – Feb 2015) + 15 underlying SOV files
Change orders: 5 COs net +$22,332 (roof deck, ASK 40, sky lounge, trench drain, tub liners)

## PO Commitments
Purchase Order Commitments
147 unique POs • PO amounts not dollar-parsed from individual PDFs • JDR material $556,907
A. COMMITMENTS BY COST CODE
OWP Code | Description → JDR | PO Count | % of POs | JDR Material
30 | 110+210 Underground | 15 | 10.2%
31 | 120+220 Roughin | 30 | 20.41%
32 | 130+230 Trim/Finish | 21 | 14.29%
40 | 141+241 Water Main/Ins | 1 | 0.6803%
41 | 140+240 Gas | 11 | 7.483%
OTHER | Unclassified | 69 | 46.94%
TOTAL |  | 147 | 100% | 556906.77
B. COMMITMENTS BY VENDOR
Vendor | PO Count | % of POs
ROSEN | 49 | 33.33%
KELLER | 38 | 25.85%
OTHER | 23 | 15.65%
FEI | 19 | 12.93%
CONSOLIDATED | 13 | 8.844%
MECH SALES | 2 | 1.361%
FASTENAL | 2 | 1.361%
SIOUX CHIEF | 1 | 0.6803%
C. PO COVERAGE NOTES
Total Material Actual (JDR) |  |  | 556906.77
Unique PO Count |  |  | 147
(Dollar PO commitment not extracted — requires per-PDF parse)
SOURCES
Job #2018 — SRM Astro Apartments • GC: SRMQA, LLC (SRM Development) • Seattle, WA
Canonical source: 2018 Job Detail Report.pdf (183 pages, OWP Sage Timberline export)
Cost codes parsed: 29 (Labor+Material+Overhead+Burden+Revenue)
Unit count (212) from 11 Keller Supply per-level trim POs (L1N, L2N/S, L3N/S, L4N/S, L5N/S, L6N/S)
Per-level residential WCs: L2N=25, L2S=24, L3N=25, L3S=23, L4N=25, L4S=23, L5N=25, L5S=23, L6N=25, L6S=21 = 239 res + 3 common (L1N)
Billing: ASTRO AGGREGATE BILLING.xlsx (15 pay apps, Dec 2013 – Feb 2015) + 15 underlying SOV files
Change orders: 5 COs net +$22,332 (roof deck, ASK 40, sky lounge, trench drain, tub liners)
PO count is deduplicated by 5-digit PO number extracted from filenames
Vendor/code classification is heuristic (filename keyword match)

## Billing & SOV
Revenue & Billing Reconciliation
15 pay applications • Original $2,282,726 + $22,332 COs = $2,305,058
A. CONTRACT SUMMARY
Original Contract |  |  |  |  | 2282726
Change Orders (net) |  |  |  |  | 22332
Final Contract Value |  |  |  |  | 2305058
Retainage (5%) |  |  |  |  | 115253
Net Paid to OWP |  |  |  |  | 2189805
B. PAY APPLICATION TIMELINE
App# | Date | Period Billing | Retention | Net This Period | Aggregate | % Complete
1 | 2013-12-19 | 64000 | 3200 | 60800 | 66880 | 2.901%
2 | 2014-01-23 | 69200 | 3460 | 65740 | 139194 | 6.039%
3 | 2014-02-25 | 21900 | 1095 | 20805 | 162079.5 | 7.031%
4 | 2014-03-25 | 71500 | 3575 | 67925 | 236797 | 10.27%
5 | 2014-04-25 | 152200 | 7610 | 144590 | 395846 | 17.17%
6 | 2014-05-22 | 526600 | 26330 | 500270 | 946143 | 41.05%
7 | 2014-06-24 | 766800 | 38340 | 728460 | 1747449 | 75.81%
8 | 2014-07-24 | 245793 | 12289.65 | 233503.35 | 2004302.68 | 86.95%
9 | 2014-08-25 | 77356 | 3867.8 | 73488.2 | 2085139.7 | 90.46%
10 | 2014-09-25 | 69100 | 3455 | 65645 | 2157349.2 | 93.59%
11 | 2014-10-25 | 53690 | 2684.5 | 51005.5 | 2213455.24 | 96.03%
12 | 2014-11-18 | 78400 | 3920 | 74480 | 2295383.24 | 99.58%
13 | 2014-12-15 | 52000 | 2600 | 49400 | 2349723.24 | 101.9%
14 | 2015-01-22 | 32410 | 1620.5 | 30789.5 | 2383591.69 | 103.4%
15 | 2015-02-19 | 24109 | 1205.45 | 22903.55 | 2408785.59 | 104.5%
C. BILLING ↔ JDR TIE-OUT
Metric | SOV | JDR | Δ | Status
Final Contract Value | 2305058 | 2305058 | 0 | TIES
Retainage | 115253 | 115253 | 0 | TIES
Direct Cost | 1232269.8 | 1232269.8 | 0 | TIES
SOURCES
Job #2018 — SRM Astro Apartments • GC: SRMQA, LLC (SRM Development) • Seattle, WA
Canonical source: 2018 Job Detail Report.pdf (183 pages, OWP Sage Timberline export)
Cost codes parsed: 29 (Labor+Material+Overhead+Burden+Revenue)
Unit count (212) from 11 Keller Supply per-level trim POs (L1N, L2N/S, L3N/S, L4N/S, L5N/S, L6N/S)
Per-level residential WCs: L2N=25, L2S=24, L3N=25, L3S=23, L4N=25, L4S=23, L5N=25, L5S=23, L6N=25, L6S=21 = 239 res + 3 common (L1N)
Billing: ASTRO AGGREGATE BILLING.xlsx (15 pay apps, Dec 2013 – Feb 2015) + 15 underlying SOV files
Change orders: 5 COs net +$22,332 (roof deck, ASK 40, sky lounge, trench drain, tub liners)

## Insights
Key Insights — Job #2018 SRM Astro Apartments
Narrative observations distilled from the full JDR analysis
MARGIN PROFILE | Net profit of $1,072,788 on $2,305,058 revenue = 46.5% gross margin. Direct cost $1,232,270 absorbs 53.5% of revenue.
VENDOR CONCENTRATION | Rosen Supply Company, Inc. alone = $187,930 (35% of all AP) across 87 invoices. Total 19 AP vendors, $535,198 total AP spend.
CREW PROFILE | 48 workers for 23,300 hours = 485 avg hrs/worker. Top 3 workers logged 3,041 hrs combined (13% of all labor).
ROUGHIN DOMINANCE | Code 120 Roughin Labor = 14,241 hrs (61% of all labor) and $256,945 actual. Code 230 Finish Material = $272,549 — 22% of total direct cost.
BUDGET DELIVERY | Revised budget was $1,442,963; actual direct cost $1,232,270 → $210,693 variance (14.6% under revised budget).
CONTRACT GROWTH | Contract grew from $2,282,726 to $2,305,058 — net +$22,332 (1.0%). Retainage of $115,253 (5%) withheld until closeout.
BURDEN RATIO | Burden codes 995 + 998 = $230,027 on $440,393 labor base = 52.2%. In line with OWP's typical 48–50% labor burden.
PROJECT SCALE | 212 units · 1144 fixtures · 15 months. Revenue/unit $10,873, hours/unit 109.9, profit/unit $5,060.
PRODUCTIVITY | Blended labor rate $18.90/hr. Revenue/hour $99. Profit/hour $46. 1,553 hrs/month burn rate.
FIXTURE DENSITY | 1144 fixtures ÷ 212 units = 5.40 fixtures/unit. Material/fixture $487, labor/fixture $385.
BIGGEST QUESTION
How does this job's 46.5% margin compare across similar projects in the OWP portfolio, and what operational levers drove the result — estimating accuracy, vendor pricing, or labor productivity?
SOURCES
Job #2018 — SRM Astro Apartments • GC: SRMQA, LLC (SRM Development) • Seattle, WA
Canonical source: 2018 Job Detail Report.pdf (183 pages, OWP Sage Timberline export)
Cost codes parsed: 29 (Labor+Material+Overhead+Burden+Revenue)
Unit count (212) from 11 Keller Supply per-level trim POs (L1N, L2N/S, L3N/S, L4N/S, L5N/S, L6N/S)
Per-level residential WCs: L2N=25, L2S=24, L3N=25, L3S=23, L4N=25, L4S=23, L5N=25, L5S=23, L6N=25, L6S=21 = 239 res + 3 common (L1N)
Billing: ASTRO AGGREGATE BILLING.xlsx (15 pay apps, Dec 2013 – Feb 2015) + 15 underlying SOV files
Change orders: 5 COs net +$22,332 (roof deck, ASK 40, sky lounge, trench drain, tub liners)

## Benchmark KPIs
Benchmark KPIs
Normalized metrics designed for apples-to-apples comparison across all OWP projects
KPI | Data Name | Value | Category | Notes
Job Number | job_number | 2018 | Profile | OWP job ID
Job Name | job_name | SRM Astro Apartments | Profile
General Contractor | general_contractor | SRMQA, LLC (SRM Development) | Profile
Location | location | Seattle, WA | Profile
Project Type | project_type | 6-story multifamily apartments + 3 levels below-grade parking + retail/amenity | Profile
Duration (months) | duration_months | 15 | Profile | Dec 2013 – Feb 2015 (~15 months)
Unit Count | unit_count | 212 | Profile
Total Fixtures | total_fixtures | 1144 | Profile
Fixtures per Unit | fixtures_per_unit | 5.3962 | Profile
Contract Value (Orig) | contract_original | 2282726 | Financial
Contract Value (Final) | contract_final | 2305058 | Financial | After change orders
Change Orders ($) | change_orders | 22332 | Financial
Revenue | revenue | 2305058 | Financial
Net Profit | net_profit | 1072788.2 | Financial
Gross Margin | gross_margin | 0.46541 | Financial
Direct Cost | direct_cost | 1232269.8 | Financial
Labor Cost | labor_cost | 440392.94 | Labor | Sum of 13 labor codes
Material Cost | material_cost | 556906.77 | Material | Sum of 10 material codes
Overhead Cost | overhead_cost | 4943.28 | Financial | Sub+Eng+Permits
Burden Cost | burden_cost | 230026.81 | Financial | Codes 995+998
Retainage | retainage | 115253 | Financial | 5% withheld
Revenue per Unit | revenue_per_unit | 10872.9151 | Financial
Profit per Unit | profit_per_unit | 5060.3217 | Financial
Direct Cost per Unit | cost_per_unit | 5812.5934 | Financial
Labor Cost per Unit | labor_per_unit | 2077.3252 | Labor
Material Cost per Unit | material_per_unit | 2626.9187 | Material
Revenue per Fixture | revenue_per_fixture | 2014.9108 | Financial
Profit per Fixture | profit_per_fixture | 937.7519 | Financial
Cost per Fixture | cost_per_fixture | 1077.1589 | Financial
Labor per Fixture | labor_per_fixture | 384.9589 | Labor
Material per Fixture | material_per_fixture | 486.8066 | Material
Total Labor Hours | total_hours | 23300.5 | Labor | Sum of JDR cost code hours
Total Workers | total_workers | 48 | Labor | Unique payroll IDs
Blended Gross Wage | blended_gross_wage | 1926% | Labor | Pre-burden
Fully-Loaded Wage | fully_loaded_wage | 2877% | Labor | Post-burden
Burden Multiplier | burden_multiplier | 1.4938 | Labor
Hours per Unit | hours_per_unit | 109.908 | Labor | Key benchmark
Hours per Fixture | hours_per_fixture | 2037% | Labor | Key benchmark
Revenue per Hour | revenue_per_hour | 9893% | Productivity
Profit per Hour | profit_per_hour | 4604% | Productivity
Labor % of Revenue | labor_pct_revenue | 0.19106 | Cost Mix
Material % of Revenue | material_pct_revenue | 0.2416 | Cost Mix
Revenue per Month | revenue_per_month | 153670.5333 | Productivity
Hours per Month | hours_per_month | 1553.3667 | Productivity
Units per Month | units_per_month | 1413% | Productivity
Total Vendors | total_vendors | 19 | Material | Unique AP vendors
Top Vendor Spend | top_vendor_spend | 187929.87 | Material | Rosen Supply Company, Inc.
Top Vendor Concentration | top_vendor_pct | 0.35114 | Material
Total POs | total_pos | 147 | Material | Unique POs by filename
Change Order % | co_pct | 0.009783 | Financial
Revenue per Labor Hour | rev_per_labor_hr | 9893% | Productivity
SOURCES
Job #2018 — SRM Astro Apartments • GC: SRMQA, LLC (SRM Development) • Seattle, WA
Canonical source: 2018 Job Detail Report.pdf (183 pages, OWP Sage Timberline export)
Cost codes parsed: 29 (Labor+Material+Overhead+Burden+Revenue)
Unit count (212) from 11 Keller Supply per-level trim POs (L1N, L2N/S, L3N/S, L4N/S, L5N/S, L6N/S)
Per-level residential WCs: L2N=25, L2S=24, L3N=25, L3S=23, L4N=25, L4S=23, L5N=25, L5S=23, L6N=25, L6S=21 = 239 res + 3 common (L1N)
Billing: ASTRO AGGREGATE BILLING.xlsx (15 pay apps, Dec 2013 – Feb 2015) + 15 underlying SOV files
Change orders: 5 COs net +$22,332 (roof deck, ASK 40, sky lounge, trench drain, tub liners)
51 KPIs with snake_case data_name identifiers for database ingestion

## Reconciliation
Reconciliation — Tie-out Proofs
Check | Computed | Expected | Δ | Status
A. JDR COST CODE ROLLUP
Labor subtotal (13 codes) | 440392.94 | 440392.94 | 0 | TIES
Material subtotal (10 codes) | 556906.77 | 556906.77 | 0 | TIES
Overhead subtotal (3 codes) | 4943.28 | 4943.28 | 0 | TIES
Burden subtotal (2 codes) | 230026.81 | 230026.81 | 0 | TIES
Direct Cost (all categories) | 1232269.8 | 1232269.8 | 0 | TIES
Revenue (code 999) | 2305058 | 2305058 | 0 | TIES
Net Profit (Revenue - Expenses) | 1072788.2 | 1072788.2 | 0 | TIES
B. LABOR HOURS ROLLUP
JDR Cost Code hours (Payroll Hours lines) | 23300.5 | 23300.5 | 0 | TIES
Per-worker hours (sum of PR Regular) | 23566 | 23300.5 | 265.5 | WITHIN
C. BILLING (SOV) ↔ JDR
Final Contract Value | 2305058 | 2305058 | 0 | TIES
Retainage | 115253 | 115253 | 0 | TIES
Direct Cost | 1232269.8 | 1232269.8 | 0 | TIES
D. VENDOR AP ↔ JDR
Vendor AP total (sum of invoices) | 535198.25 | 529698 | 5500.25 | WITHIN
SOURCES
Job #2018 — SRM Astro Apartments • GC: SRMQA, LLC (SRM Development) • Seattle, WA
Canonical source: 2018 Job Detail Report.pdf (183 pages, OWP Sage Timberline export)
Cost codes parsed: 29 (Labor+Material+Overhead+Burden+Revenue)
Unit count (212) from 11 Keller Supply per-level trim POs (L1N, L2N/S, L3N/S, L4N/S, L5N/S, L6N/S)
Per-level residential WCs: L2N=25, L2S=24, L3N=25, L3S=23, L4N=25, L4S=23, L5N=25, L5S=23, L6N=25, L6S=21 = 239 res + 3 common (L1N)
Billing: ASTRO AGGREGATE BILLING.xlsx (15 pay apps, Dec 2013 – Feb 2015) + 15 underlying SOV files
Change orders: 5 COs net +$22,332 (roof deck, ASK 40, sky lounge, trench drain, tub liners)
TIES = within $1 or 5 hrs • WITHIN = within 5% • OFF = investigate

## Vendors
Vendor Detail — Job #2018
Vendors | 19 |  | Top vendor | Rosen Supply Company, Inc.
Invoices | 301 |  | Top 3 share | 73.65%
Total AP | 535198.25 |  | Source | 2018 Job Detail Report.pdf (Sage Timberline AP export)
Avg Inv | 1778.0673
Rank | Vendor | Vendor Code | Invoices | Total Spend | % of AP | Avg / Invoice
1 | Rosen Supply Company, Inc. |  | 87 | 187929.87 | 35.11% | 2160.1134
2 | Keller Supply Company |  | 64 | 141063.76 | 26.36% | 2204.1213
3 | Ferguson Enterprises, Inc. |  | 45 | 65193.3 | 12.18% | 1448.74
4 | Mechanical Sales, Inc. |  | 4 | 47527.77 | 8.88% | 11881.9425
5 | Consolidated Supply Co. |  | 21 | 43369.79 | 8.103% | 2065.2281
6 | Franklin Engineering |  | 6 | 23133.75 | 4.322% | 3855.625
7 | Bank of America CC |  | 3 | 11633 | 2.174% | 3877.6667
8 | Quality Concrete Products, Inc. |  | 4 | 8875 | 1.658% | 2218.75
9 | United Rentals, Inc. |  | 4 | 2252.62 | 0.4209% | 563.155
10 | Ferguson Enterprises, Inc. #3007 |  | 3 | 934.77 | 0.1747% | 311.59
11 | C.M. Hoskins Company |  | 4 | 654.66 | 0.1223% | 163.665
12 | Kele, Inc |  | 2 | 637.54 | 0.1191% | 318.77
13 | MAD Concrete Cutting & Coring, Inc. |  | 1 | 500 | 0.09342% | 500
14 | Capital One Credit Card |  | 44 | 431.75 | 0.08067% | 9.8125
15 | Fastenal Company |  | 3 | 372.77 | 0.06965% | 124.2567
16 | DRSi |  | 2 | 354.99 | 0.06633% | 177.495
17 | R.A. Brown Backflow Testing |  | 1 | 191.7 | 0.03582% | 191.7
18 | Rosen Supply Kirkland |  | 2 | 111.82 | 0.02089% | 55.91
19 | Core & Main LP |  | 1 | 29.39 | 0.005491% | 29.39
| TOTAL |  | 301 | 535198.25 | 100% | 1778.0673