## Overview
Job #2019 · Exxel Pacific 8th & Republican Apartments
Cortex JCR Summary • Exxel Pacific, Inc. (Owner: The Wolff Company) • Seattle, WA (430 8th Ave N) • 8-story 211-unit multifamily apartments + ground-floor retail/amenity • Sep 2014 – Jul 2016 (~22 months)
PROJECT OVERVIEW
Project Job # | 2019
Project Name: | Exxel Pacific 8th & Republican Apartments
General Contractor | Exxel Pacific, Inc. (Owner: The Wolff Company)
Location | Seattle, WA (430 8th Ave N)
Project Duration | Sep 2014 – Jul 2016 (~22 months)
Total Unique Documents | 8th & Republican folder: Contract, Billing (20 SOVs + aggregate), PO_s (trim consolidated), COs (10), Permits, Invoices
CONTRACT VALUE |  | NET PROFIT |  | DIRECT COST |  | LABOR HOURS
$2,877,219 |  | $1,353,160 |  | $1,524,059 |  | 26,599
Original $2,721,210 + $156,009 COs (10) |  | 47.0% margin |  | 53.0% of revenue |  | 56 workers
COST BREAKDOWN
Category | Budget | Actual | Variance | % Budget | % of Cost
Labor | 630261 | 550832.62 | 79428.38 | 87.4% | 36.14%
Material | 974017 | 660548.93 | 313468.07 | 67.82% | 43.34%
Overhead | 65850 | 59981.3 | 5868.7 | 91.09% | 3.936%
Burden | 297111.35 | 252695.88 | 44415.47 | 85.05% | 16.58%
TOTAL | 1967239.35 | 1524058.73 | 443180.62 | 77.47% | 100%
PROJECT PROFILE
Metric | Value | Metric | Value | Metric | Value
Plumbing Units | 211 | Water Closets | 211 | Kitchen Sinks | 211
Total Fixtures | 1,196 | Lavatories | 255 | Dishwashers | 211
Fixtures / Unit | 5.67 | Tubs/Showers | 214 | Auto Washers | 211
Floors | L1 retail/amenity + L2–L8 residential | Floor Drains | 49 | Urinals | 2
Roof Drains | 10 | Duration | 22 mo
SOURCES
Job #2019 — Exxel Pacific 8th & Republican Apartments • GC: Exxel Pacific, Inc. (Owner: The Wolff Company) • Seattle, WA
Canonical source: 2019 Job Detail Report.pdf (249 pages, OWP Sage Timberline export)
Cost codes parsed: 25 (Labor+Material+Overhead+Burden+Revenue)
Unit count (211) confirmed by two independent sources:
1) Keller Supply consolidated trim PO (8TH REP TRIM - KELLER.xlsx): 211 Delta 4159-DST kitchen faucets
2) Seattle/King County plumbing permit #1459 ($11,925 fee, 10/23/2014): Water Closet field = 211
Fixture breakdown from same permit: Lavs 255, Tubs/Showers 214, Kitchen 211, DW 211, Floor Drains 49, Urinals 2, Sump 8, Roof Drains 10, + misc = ~1,196
Billing: REPUBLICAN AGGREGATE BILLING.xlsx (20 pay apps, Sep 2014 – Jun 2016) + 20 underlying SOV files
Change orders: 10 COs net +$156,008.60 (can layout, acoustical wrap, added boilers, ASI 15/48, premium time, etc.)

## Budget vs Actual
Budget vs Actual — All Cost Codes
Code | Description | Orig Budget | Rev Budget | Actual | Variance | % Used
LABOR
100 | Supervision | 14700 | 18480 | 13841.5 | 4638.5 | 74.9%
101 | Takeoff & Purchase Labor | 14700 | 26068 | 27212.5 | -1144.5 | 104.4%
110 | Underground Labor | 12700 | 12700 | 11835 | 865 | 93.19%
111 | Garage Labor | 80400 | 84100 | 65168.5 | 18931.5 | 77.49%
112 | Canout Labor | 44800 | 48150 | 47229 | 921 | 98.09%
120 | Roughin Labor | 281500 | 294635 | 301244.35 | -6609.35 | 102.2%
130 | Finish Labor | 54000 | 55373 | 36001.25 | 19371.75 | 65.02%
140 | Gas Labor | 14700 | 15325 | 7665 | 7660 | 50.02%
141 | Water Main/Insulation Lab | 74800 | 75430 | 39821.52 | 35608.48 | 52.79%
142 | Mech Room Labor | 0 | 0 | 814 | -814 | 0%
MATERIAL
210 | Underground Material | 16500 | 16500 | 9932.16 | 6567.84 | 60.19%
211 | Garage Material | 55800 | 57063 | 22168.78 | 34894.22 | 38.85%
212 | Canout Material | 69200 | 69350 | 40231.97 | 29118.03 | 58.01%
220 | Roughin Material | 212400 | 215686 | 176444.92 | 39241.08 | 81.81%
230 | Finish Material | 461500 | 488611 | 313722.19 | 174888.81 | 64.21%
240 | Gas Material | 10300 | 10532 | 4568.01 | 5963.99 | 43.37%
241 | Water Main/Insulation Mat | 83500 | 83775 | 69305.69 | 14469.31 | 82.73%
242 | Mech Room Material | 32500 | 32500 | 24175.21 | 8324.79 | 74.39%
244 | Fire Caulking Material | 0 | 0 | 0 | 0 | 0%
OVERHEAD
600 | Subcontractor | 21600 | 45850 | 31086.35 | 14763.65 | 67.8%
601 | Engineering/Plans | 5000 | 5000 | 10226 | -5226 | 204.5%
603 | Permits & Licenses | 15000 | 15000 | 18668.95 | -3668.95 | 124.5%
BURDEN
995 | Payroll Burden | 262831.05 | 247825.38 | 209946.79 | 37878.59 | 84.72%
998 | Payroll Taxes | 46381.95 | 49285.97 | 42749.09 | 6536.88 | 86.74%
TOTAL | Direct Cost | 1884813 | 1967239.35 | 1524058.73 | 443180.62 | 77.47%
SOURCES
Job #2019 — Exxel Pacific 8th & Republican Apartments • GC: Exxel Pacific, Inc. (Owner: The Wolff Company) • Seattle, WA
Canonical source: 2019 Job Detail Report.pdf (249 pages, OWP Sage Timberline export)
Cost codes parsed: 25 (Labor+Material+Overhead+Burden+Revenue)
Unit count (211) confirmed by two independent sources:
1) Keller Supply consolidated trim PO (8TH REP TRIM - KELLER.xlsx): 211 Delta 4159-DST kitchen faucets
2) Seattle/King County plumbing permit #1459 ($11,925 fee, 10/23/2014): Water Closet field = 211
Fixture breakdown from same permit: Lavs 255, Tubs/Showers 214, Kitchen 211, DW 211, Floor Drains 49, Urinals 2, Sump 8, Roof Drains 10, + misc = ~1,196
Billing: REPUBLICAN AGGREGATE BILLING.xlsx (20 pay apps, Sep 2014 – Jun 2016) + 20 underlying SOV files
Change orders: 10 COs net +$156,008.60 (can layout, acoustical wrap, added boilers, ASI 15/48, premium time, etc.)

## Cost Breakdown
Cost Breakdown — Category Deep Dive
A. CATEGORY SHARE OF DIRECT COST
Category | # Codes | Budget | Actual | Variance | % Budget | % of Cost | Per Unit
Labor | 10 | 630261 | 550832.62 | 79428.38 | 87.4% | 36.14% | 2610.5811
Material | 9 | 974017 | 660548.93 | 313468.07 | 67.82% | 43.34% | 3130.5636
Overhead | 3 | 65850 | 59981.3 | 5868.7 | 91.09% | 3.936% | 284.2716
Burden | 2 | 297111.35 | 252695.88 | 44415.47 | 85.05% | 16.58% | 1197.6108
B. LARGEST OVERRUNS (Actual > Revised Budget)
Code | Description | Rev Budget | Actual | Overrun | % Over
120 | Roughin Labor | 294635 | 301244.35 | 6609.35 | 2.243%
601 | Engineering/Plans | 5000 | 10226 | 5226 | 104.5%
603 | Permits & Licenses | 15000 | 18668.95 | 3668.95 | 24.46%
101 | Takeoff & Purchase Labor | 26068 | 27212.5 | 1144.5 | 4.39%
142 | Mech Room Labor | 0 | 814 | 814 | 0%
C. LARGEST SAVINGS (Actual < Revised Budget)
Code | Description | Rev Budget | Actual | Savings | % Under
230 | Finish Material | 488611 | 313722.19 | 174888.81 | 35.79%
220 | Roughin Material | 215686 | 176444.92 | 39241.08 | 18.19%
995 | Payroll Burden | 247825.38 | 209946.79 | 37878.59 | 15.28%
141 | Water Main/Insulation Lab | 75430 | 39821.52 | 35608.48 | 47.21%
211 | Garage Material | 57063 | 22168.78 | 34894.22 | 61.15%
212 | Canout Material | 69350 | 40231.97 | 29118.03 | 41.99%
130 | Finish Labor | 55373 | 36001.25 | 19371.75 | 34.98%
111 | Garage Labor | 84100 | 65168.5 | 18931.5 | 22.51%
600 | Subcontractor | 45850 | 31086.35 | 14763.65 | 32.2%
241 | Water Main/Insulation Mat | 83775 | 69305.69 | 14469.31 | 17.27%
SOURCES
Job #2019 — Exxel Pacific 8th & Republican Apartments • GC: Exxel Pacific, Inc. (Owner: The Wolff Company) • Seattle, WA
Canonical source: 2019 Job Detail Report.pdf (249 pages, OWP Sage Timberline export)
Cost codes parsed: 25 (Labor+Material+Overhead+Burden+Revenue)
Unit count (211) confirmed by two independent sources:
1) Keller Supply consolidated trim PO (8TH REP TRIM - KELLER.xlsx): 211 Delta 4159-DST kitchen faucets
2) Seattle/King County plumbing permit #1459 ($11,925 fee, 10/23/2014): Water Closet field = 211
Fixture breakdown from same permit: Lavs 255, Tubs/Showers 214, Kitchen 211, DW 211, Floor Drains 49, Urinals 2, Sump 8, Roof Drains 10, + misc = ~1,196
Billing: REPUBLICAN AGGREGATE BILLING.xlsx (20 pay apps, Sep 2014 – Jun 2016) + 20 underlying SOV files
Change orders: 10 COs net +$156,008.60 (can layout, acoustical wrap, added boilers, ASI 15/48, premium time, etc.)

## Material
Material Spend Analysis
9 material cost codes • $660,549 JDR material • 25 AP vendors • $766,653 total AP
A. MATERIAL BY COST CODE
Code | Description | Rev Budget | Actual | Variance | % Used | % of Mat | Per Unit
210 | Underground Material | 16500 | 9932.16 | 6567.84 | 60.19% | 1.504% | 47.0718
211 | Garage Material | 57063 | 22168.78 | 34894.22 | 38.85% | 3.356% | 105.0653
212 | Canout Material | 69350 | 40231.97 | 29118.03 | 58.01% | 6.091% | 190.6728
220 | Roughin Material | 215686 | 176444.92 | 39241.08 | 81.81% | 26.71% | 836.2318
230 | Finish Material | 488611 | 313722.19 | 174888.81 | 64.21% | 47.49% | 1486.835
240 | Gas Material | 10532 | 4568.01 | 5963.99 | 43.37% | 0.6915% | 21.6493
241 | Water Main/Insulation Mat | 83775 | 69305.69 | 14469.31 | 82.73% | 10.49% | 328.463
242 | Mech Room Material | 32500 | 24175.21 | 8324.79 | 74.39% | 3.66% | 114.5745
244 | Fire Caulking Material | 0 | 0 | 0 | 0% | 0% | 0
TOTAL | All Material | 974017 | 660548.93 | 313468.07 | 67.82% | 100% | 3130.5636
B. VENDORS BY SPEND (AP)
Vendor | # Invoices | Total Spend | % of AP |  |  |  | Avg Invoice
Rosen Supply Company, Inc. | 97 | 248013.68 | 32.35% |  |  |  | 2556.8421
Ferguson Enterprises, Inc. | 57 | 104759.63 | 13.66% |  |  |  | 1837.8882
Keller Supply Company | 66 | 101721.98 | 13.27% |  |  |  | 1541.2421
Franklin Engineering | 19 | 94572.5 | 12.34% |  |  |  | 4977.5
Mechanical Sales, Inc. | 4 | 70651.37 | 9.216% |  |  |  | 17662.8425
Consolidated Supply Co. | 27 | 45650.81 | 5.955% |  |  |  | 1690.7707
Hudson Bay Insulation | 1 | 19963 | 2.604% |  |  |  | 19963
Capital One Credit Card | 59 | 18513.01 | 2.415% |  |  |  | 313.7798
Bank of America CC | 10 | 16471.05 | 2.148% |  |  |  | 1647.105
United Rentals, Inc. | 18 | 9870.42 | 1.287% |  |  |  | 548.3567
Scan2Core, Inc. | 7 | 8878 | 1.158% |  |  |  | 1268.2857
Quality Concrete Products, Inc. | 3 | 6463.4 | 0.8431% |  |  |  | 2154.4667
Rosen Supply Kirkland | 7 | 4731.84 | 0.6172% |  |  |  | 675.9771
Ferguson Enterprises, Inc. #3007 | 3 | 4012.56 | 0.5234% |  |  |  | 1337.52
Balco Inc | 1 | 3908 | 0.5097% |  |  |  | 3908
Kele, Inc | 4 | 2674.82 | 0.3489% |  |  |  | 668.705
MAD Concrete Cutting & Coring, Inc. | 1 | 1775 | 0.2315% |  |  |  | 1775
Standard Parking | 3 | 1526.25 | 0.1991% |  |  |  | 508.75
AllWest Underground, Inc. | 1 | 671.5 | 0.08759% |  |  |  | 671.5
C.M. Hoskins Company | 2 | 607.04 | 0.07918% |  |  |  | 303.52
A.R. Brown Backflow Testing | 3 | 470.35 | 0.06135% |  |  |  | 156.7833
Fastenal Company | 5 | 351.93 | 0.0459% |  |  |  | 70.386
Lotus United, LLC | 1 | 155 | 0.02022% |  |  |  | 155
ACME Corp | 2 | 150.11 | 0.01958% |  |  |  | 75.055
Manor Hardware & Construction Supply | 1 | 90 | 0.01174% |  |  |  | 90
TOTAL | 402 | 766653.25 | 100%
SOURCES
Job #2019 — Exxel Pacific 8th & Republican Apartments • GC: Exxel Pacific, Inc. (Owner: The Wolff Company) • Seattle, WA
Canonical source: 2019 Job Detail Report.pdf (249 pages, OWP Sage Timberline export)
Cost codes parsed: 25 (Labor+Material+Overhead+Burden+Revenue)
Unit count (211) confirmed by two independent sources:
1) Keller Supply consolidated trim PO (8TH REP TRIM - KELLER.xlsx): 211 Delta 4159-DST kitchen faucets
2) Seattle/King County plumbing permit #1459 ($11,925 fee, 10/23/2014): Water Closet field = 211
Fixture breakdown from same permit: Lavs 255, Tubs/Showers 214, Kitchen 211, DW 211, Floor Drains 49, Urinals 2, Sump 8, Roof Drains 10, + misc = ~1,196
Billing: REPUBLICAN AGGREGATE BILLING.xlsx (20 pay apps, Sep 2014 – Jun 2016) + 20 underlying SOV files
Change orders: 10 COs net +$156,008.60 (can layout, acoustical wrap, added boilers, ASI 15/48, premium time, etc.)
Vendor AP ties to JDR 'by Source: AP' line (766,653.25)

## Crew & Labor
Crew & Labor — Per-Worker Breakdown
Worker | Hours | Gross Pay | $/Hour | Tier
McCabe, Thomas C | 2074 | 45573.5 | 21.9737 | Mid
Waites, Thaddeus Z | 2001 | 64237 | 32.1024 | Senior
Sepulveda Gonzalez, Alfredo | 1310 | 36285 | 27.6985 | Mid
Rodriguez Rodriguez, Aminadab N | 1297.5 | 18473 | 14.2374 | Apprentice
Lovo, German G | 1041.5 | 14941 | 14.3457 | Apprentice
Esparza Jimenez, Jose D | 912 | 19840 | 21.7544 | Mid
Velasquez Cruz, Denis M | 857 | 14617 | 17.056 | Apprentice
Cruz Guzman, Joel A | 852 | 11396 | 13.3756 | Apprentice
Ulu, Flynn M | 823.5 | 17606 | 21.3795 | Mid
Castaneda Juarez, Gustavo | 810.5 | 14589 | 18 | Mid
Reyes, Robert J | 799.5 | 11992.5 | 15 | Apprentice
Cruz Reyes, Jose | 776 | 11184 | 14.4124 | Apprentice
Rodriguez Bonilla, Lisandro | 772.5 | 10815 | 14 | Apprentice
Anzora, William | 749 | 11259 | 15.032 | Apprentice
Hubbard, Robert W | 731 | 26293 | 35.9685 | Senior
Reyes Cruz, Denis A | 721.5 | 10765.5 | 14.921 | Apprentice
Ascencio, Jose L | 717.5 | 9655.5 | 13.4571 | Apprentice
Castaneda Juarez, Edgar D | 665.5 | 11979 | 18 | Mid
Donelson, Richard T | 657 | 29615 | 45.0761 | Senior
Eliassen, Cory H | 629 | 8448.5 | 13.4316 | Apprentice
Castaneda Martinez, Gustavo | 568 | 18176 | 32 | Senior
Amaya Gonzalez, Edilberto A | 568 | 7952 | 14 | Apprentice
Salazar, Hajdar L | 496.5 | 8152 | 16.4189 | Apprentice
Cortes Sepulveda, Jose R | 444 | 5772 | 13 | Apprentice
Ramos, Jose G | 423 | 5499 | 13 | Apprentice
Newton, Carson T | 400 | 5232 | 13.08 | Apprentice
Spears, Gregory M | 400 | 6181 | 15.4525 | Apprentice
Anderson, Richard P | 351 | 11196 | 31.8974 | Senior
Vaughan, Tyler J | 341.5 | 6619 | 19.3821 | Mid
Holmes, Anthony R | 293 | 5471 | 18.6724 | Mid
Gerard, Jeffrey S | 286 | 11606 | 40.5804 | Senior
Aguilar, Tony A | 263 | 3419 | 13 | Apprentice
Aguilar Rivas, Henry | 260 | 3380 | 13 | Apprentice
Ross, Kelli M | 256 | 7936 | 31 | Senior
Alba Jimenez, Jovani | 240 | 3840 | 16 | Apprentice
Alba Martinez, Santiago | 240 | 4320 | 18 | Mid
Taylor, Evan R | 232 | 3424 | 14.7586 | Apprentice
Garcia, Jordan X | 191 | 3629 | 19 | Mid
Sanders, Allen O | 188.5 | 6486.5 | 34.4111 | Senior
Cortes Mendiola, Victor H | 175 | 4900 | 28 | Mid
Lima Romero, Melvin A | 159 | 3498 | 22 | Mid
Schaefer, Taylor E | 120 | 1672 | 13.9333 | Apprentice
Hubbard, Dustin R | 53.5 | 815 | 15.2336 | Apprentice
Kinssies, Jr, John E | 51 | 816 | 16 | Apprentice
Castro Hernandez, Jose A | 48 | 960 | 20 | Mid
Palma Vides, Hugo | 40 | 1192 | 29.8 | Mid
Galdamez, Dagoberto A | 40 | 560 | 14 | Apprentice
Gonzalez Hernandez, Josue | 24 | 408 | 17 | Apprentice
Paco Leyva, Orlando | 16 | 368 | 23 | Mid
Palma Vides, Jorge A | 16 | 224 | 14 | Apprentice
Gardner, Andrew M | 14.5 | 188.5 | 13 | Apprentice
Matthias, Joseph S | 14.5 | 188.5 | 13 | Apprentice
Barnhart, Joseph N | 14 | 476 | 34 | Senior
Walker, Craig M | 8 | 120 | 15 | Apprentice
Martinez Reyes, Juan C | 8 | 104 | 13 | Apprentice
Gerard, Mitchell J | 8 | 144 | 18 | Mid
TOTAL (56 workers) | 26448.5 | 544489 | 20.5868
SOURCES
Job #2019 — Exxel Pacific 8th & Republican Apartments • GC: Exxel Pacific, Inc. (Owner: The Wolff Company) • Seattle, WA
Canonical source: 2019 Job Detail Report.pdf (249 pages, OWP Sage Timberline export)
Cost codes parsed: 25 (Labor+Material+Overhead+Burden+Revenue)
Unit count (211) confirmed by two independent sources:
1) Keller Supply consolidated trim PO (8TH REP TRIM - KELLER.xlsx): 211 Delta 4159-DST kitchen faucets
2) Seattle/King County plumbing permit #1459 ($11,925 fee, 10/23/2014): Water Closet field = 211
Fixture breakdown from same permit: Lavs 255, Tubs/Showers 214, Kitchen 211, DW 211, Floor Drains 49, Urinals 2, Sump 8, Roof Drains 10, + misc = ~1,196
Billing: REPUBLICAN AGGREGATE BILLING.xlsx (20 pay apps, Sep 2014 – Jun 2016) + 20 underlying SOV files
Change orders: 10 COs net +$156,008.60 (can layout, acoustical wrap, added boilers, ASI 15/48, premium time, etc.)
Tier: Apprentice <$18/hr, Mid $18–30, Senior >$30

## Crew Analytics
Crew Analytics
A. TIER DISTRIBUTION
Tier | # Workers | Hours | Gross Pay | % of Hours
Senior | 9 | 5052.5 | 176021.5 | 19.1%
Mid | 16 | 8107 | 176973.5 | 30.65%
Apprentice | 31 | 13289 | 191494 | 50.24%
B. WAGE STATISTICS
Blended Gross Wage | 20.5868 |  |  | Payroll $ ÷ payroll hours (pre-burden)
Fully-Loaded Wage | 30.3809 |  |  | (Labor + Burden) ÷ total hours
Burden Multiplier | 1.4757 |  |  | Fully loaded ÷ gross wage
Min Worker Rate | 13 |  |  | Cheapest apprentice hour
Max Worker Rate | 45.0761 |  |  | Most expensive foreman hour
Avg Hours / Worker | 472.2946 |  |  | Crew continuity indicator
SOURCES
Job #2019 — Exxel Pacific 8th & Republican Apartments • GC: Exxel Pacific, Inc. (Owner: The Wolff Company) • Seattle, WA
Canonical source: 2019 Job Detail Report.pdf (249 pages, OWP Sage Timberline export)
Cost codes parsed: 25 (Labor+Material+Overhead+Burden+Revenue)
Unit count (211) confirmed by two independent sources:
1) Keller Supply consolidated trim PO (8TH REP TRIM - KELLER.xlsx): 211 Delta 4159-DST kitchen faucets
2) Seattle/King County plumbing permit #1459 ($11,925 fee, 10/23/2014): Water Closet field = 211
Fixture breakdown from same permit: Lavs 255, Tubs/Showers 214, Kitchen 211, DW 211, Floor Drains 49, Urinals 2, Sump 8, Roof Drains 10, + misc = ~1,196
Billing: REPUBLICAN AGGREGATE BILLING.xlsx (20 pay apps, Sep 2014 – Jun 2016) + 20 underlying SOV files
Change orders: 10 COs net +$156,008.60 (can layout, acoustical wrap, added boilers, ASI 15/48, premium time, etc.)

## Productivity
Productivity — Phase & Unit Metrics
A. LABOR HOURS BY PHASE
Phase | Labor Code | Hours | % of Total | Hours / Unit
Supervision | 100 | 315.5 | 1.186% | 1.4953
Takeoff & Purchasing | 101 | 625.5 | 2.352% | 2.9645
Underground | 110 | 436.5 | 1.641% | 2.0687
Garage | 111 | 3023 | 11.37% | 14.327
Canout | 112 | 1811.5 | 6.81% | 8.5853
Roughin | 120 | 16040 | 60.3% | 76.019
Finish | 130 | 1790 | 6.73% | 8.4834
Gas | 140 | 356 | 1.338% | 1.6872
Water Main / Insulation | 141 | 2179 | 8.192% | 10.327
Mech Room | 142 | 22 | 0.08271% | 0.10427
TOTAL |  | 26599 | 100% | 126.0616
B. PRODUCTIVITY RATIOS
Metric | Value | Units |  | Notes
Hours / Unit | 126.0616 | hrs |  | Labor hours per residential unit
Hours / Fixture | 22.24 | hrs |  | Labor hours per plumbing fixture
Revenue / Hour | 108.1702 | $ |  | Top-line per labor hour
Profit / Hour | 50.8726 | $ |  | Bottom-line per labor hour
Units / Month | 9.5909 | units |  | Build velocity
Fixtures / Month | 54.3636 | fix |  | Fixture install pace
Hours / Month | 1209.0455 | hrs |  | Monthly labor burn
Revenue / Month | 130782.6636 | $ |  | Monthly billing rate
SOURCES
Job #2019 — Exxel Pacific 8th & Republican Apartments • GC: Exxel Pacific, Inc. (Owner: The Wolff Company) • Seattle, WA
Canonical source: 2019 Job Detail Report.pdf (249 pages, OWP Sage Timberline export)
Cost codes parsed: 25 (Labor+Material+Overhead+Burden+Revenue)
Unit count (211) confirmed by two independent sources:
1) Keller Supply consolidated trim PO (8TH REP TRIM - KELLER.xlsx): 211 Delta 4159-DST kitchen faucets
2) Seattle/King County plumbing permit #1459 ($11,925 fee, 10/23/2014): Water Closet field = 211
Fixture breakdown from same permit: Lavs 255, Tubs/Showers 214, Kitchen 211, DW 211, Floor Drains 49, Urinals 2, Sump 8, Roof Drains 10, + misc = ~1,196
Billing: REPUBLICAN AGGREGATE BILLING.xlsx (20 pay apps, Sep 2014 – Jun 2016) + 20 underlying SOV files
Change orders: 10 COs net +$156,008.60 (can layout, acoustical wrap, added boilers, ASI 15/48, premium time, etc.)

## PO Commitments
Purchase Order Commitments
194 unique POs • PO amounts not dollar-parsed from individual PDFs • JDR material $660,549
A. COMMITMENTS BY COST CODE
OWP Code | Description → JDR | PO Count | % of POs | JDR Material
30 | 110+210 Underground | 22 | 11.34%
31 | 120+220 Roughin | 33 | 17.01%
32 | 130+230 Trim/Finish | 14 | 7.216%
40 | 141+241 Water Main/Ins | 4 | 2.062%
41 | 140+240 Gas | 12 | 6.186%
OTHER | Unclassified | 109 | 56.19%
TOTAL |  | 194 | 100% | 660548.93
B. COMMITMENTS BY VENDOR
Vendor | PO Count | % of POs
ROSEN | 69 | 35.57%
KELLER | 46 | 23.71%
FEI | 41 | 21.13%
OTHER | 16 | 8.247%
CONSOLIDATED | 16 | 8.247%
MECH SALES | 3 | 1.546%
FASTENAL | 2 | 1.031%
MANOR | 1 | 0.5155%
C. PO COVERAGE NOTES
Total Material Actual (JDR) |  |  | 660548.93
Unique PO Count |  |  | 194
(Dollar PO commitment not extracted — requires per-PDF parse)
SOURCES
Job #2019 — Exxel Pacific 8th & Republican Apartments • GC: Exxel Pacific, Inc. (Owner: The Wolff Company) • Seattle, WA
Canonical source: 2019 Job Detail Report.pdf (249 pages, OWP Sage Timberline export)
Cost codes parsed: 25 (Labor+Material+Overhead+Burden+Revenue)
Unit count (211) confirmed by two independent sources:
1) Keller Supply consolidated trim PO (8TH REP TRIM - KELLER.xlsx): 211 Delta 4159-DST kitchen faucets
2) Seattle/King County plumbing permit #1459 ($11,925 fee, 10/23/2014): Water Closet field = 211
Fixture breakdown from same permit: Lavs 255, Tubs/Showers 214, Kitchen 211, DW 211, Floor Drains 49, Urinals 2, Sump 8, Roof Drains 10, + misc = ~1,196
Billing: REPUBLICAN AGGREGATE BILLING.xlsx (20 pay apps, Sep 2014 – Jun 2016) + 20 underlying SOV files
Change orders: 10 COs net +$156,008.60 (can layout, acoustical wrap, added boilers, ASI 15/48, premium time, etc.)
PO count is deduplicated by 5-digit PO number extracted from filenames
Vendor/code classification is heuristic (filename keyword match)

## Billing & SOV
Revenue & Billing Reconciliation
20 pay applications • Original $2,721,210 + $156,009 COs = $2,877,219
A. CONTRACT SUMMARY
Original Contract |  |  |  |  | 2721210
Change Orders (net) |  |  |  |  | 156009
Final Contract Value |  |  |  |  | 2877219
Retainage (5%) |  |  |  |  | 143861
Net Paid to OWP |  |  |  |  | 2733358
B. PAY APPLICATION TIMELINE
App# | Date | Period Billing | Retention | Net This Period | Aggregate | % Complete
1 | 2014-09-20 | 80750 | 4037.5 | 76712.5 | 76712.5 | 2.666%
2 | 2014-10-20 | 68250 | 3412.5 | 64837.5 | 141550 | 4.92%
3 | 2014-11-17 | 66400 | 3320 | 63080 | 204630 | 7.112%
4 | 2014-12-15 | 14800 | 740 | 14060 | 218690 | 7.601%
5 | 2015-01-20 | 25583 | 1279.15 | 24303.85 | 242993.85 | 8.445%
6 | 2015-02-19 | 71858 | 3592.9 | 68265.1 | 311258.95 | 10.82%
7 | 2015-03-19 | 83700 | 4185 | 79515 | 390773.95 | 13.58%
8 | 2015-04-20 | 251140 | 12557 | 238583 | 629356.95 | 21.87%
9 | 2015-05-19 | 378861 | 18943.05 | 359917.95 | 989274.9 | 34.38%
10 | 2015-06-18 | 513990 | 25699.5 | 488290.5 | 1477565.4 | 51.35%
11 | 2015-07-20 | 344920 | 17246 | 327674 | 1805239.4 | 62.74%
12 | 2015-08-20 | 458370 | 22918.5 | 435451.5 | 2240690.9 | 77.88%
13 | 2015-09-18 | 134559 | 6727.95 | 127831.05 | 2368521.95 | 82.32%
14 | 2015-10-20 | 83557 | 4177.85 | 79379.15 | 2447901.1 | 85.08%
15 | 2015-11-16 | 50811.6 | 2540.58 | 48271.02 | 2496172.12 | 86.76%
16 | 2015-12-16 | 77330 | 3866.5 | 73463.5 | 2569635.62 | 89.31%
17 | 2016-01-20 | 107419 | 5370.95 | 102048.05 | 2671683.67 | 92.86%
18 | 2016-02-19 | 19220 | 961 | 18259 | 2689942.67 | 93.49%
19 | 2016-03-18 | 28401 | 1420.05 | 26980.95 | 2716923.62 | 94.43%
20 | 2016-06-20 | 17299 | 864.95 | 16434.05 | 2733357.67 | 95%
C. BILLING ↔ JDR TIE-OUT
Metric | SOV | JDR | Δ | Status
Final Contract Value | 2877218.6 | 2877219 | -0.4 | TIES
Retainage | 143861 | 143861 | 0 | TIES
Direct Cost | 1524058.73 | 1524058.73 | 0 | TIES
SOURCES
Job #2019 — Exxel Pacific 8th & Republican Apartments • GC: Exxel Pacific, Inc. (Owner: The Wolff Company) • Seattle, WA
Canonical source: 2019 Job Detail Report.pdf (249 pages, OWP Sage Timberline export)
Cost codes parsed: 25 (Labor+Material+Overhead+Burden+Revenue)
Unit count (211) confirmed by two independent sources:
1) Keller Supply consolidated trim PO (8TH REP TRIM - KELLER.xlsx): 211 Delta 4159-DST kitchen faucets
2) Seattle/King County plumbing permit #1459 ($11,925 fee, 10/23/2014): Water Closet field = 211
Fixture breakdown from same permit: Lavs 255, Tubs/Showers 214, Kitchen 211, DW 211, Floor Drains 49, Urinals 2, Sump 8, Roof Drains 10, + misc = ~1,196
Billing: REPUBLICAN AGGREGATE BILLING.xlsx (20 pay apps, Sep 2014 – Jun 2016) + 20 underlying SOV files
Change orders: 10 COs net +$156,008.60 (can layout, acoustical wrap, added boilers, ASI 15/48, premium time, etc.)

## Insights
Key Insights — Job #2019 Exxel Pacific 8th & Republican Apartments
Narrative observations distilled from the full JDR analysis
MARGIN PROFILE | Net profit of $1,353,160 on $2,877,219 revenue = 47.0% gross margin. Direct cost $1,524,059 absorbs 53.0% of revenue.
VENDOR CONCENTRATION | Rosen Supply Company, Inc. alone = $248,014 (32% of all AP) across 97 invoices. Total 25 AP vendors, $766,653 total AP spend.
CREW PROFILE | 56 workers for 26,599 hours = 475 avg hrs/worker. Top 3 workers logged 5,385 hrs combined (20% of all labor).
ROUGHIN DOMINANCE | Code 120 Roughin Labor = 16,040 hrs (60% of all labor) and $301,244 actual. Code 230 Finish Material = $313,722 — 21% of total direct cost.
BUDGET DELIVERY | Revised budget was $1,967,239; actual direct cost $1,524,059 → $443,181 variance (22.5% under revised budget).
CONTRACT GROWTH | Contract grew from $2,721,210 to $2,877,219 — net +$156,009 (5.7%). Retainage of $143,861 (5%) withheld until closeout.
BURDEN RATIO | Burden codes 995 + 998 = $252,696 on $550,833 labor base = 45.9%. In line with OWP's typical 48–50% labor burden.
PROJECT SCALE | 211 units · 1196 fixtures · 22 months. Revenue/unit $13,636, hours/unit 126.1, profit/unit $6,413.
PRODUCTIVITY | Blended labor rate $20.71/hr. Revenue/hour $108. Profit/hour $51. 1,209 hrs/month burn rate.
FIXTURE DENSITY | 1196 fixtures ÷ 211 units = 5.67 fixtures/unit. Material/fixture $552, labor/fixture $461.
BIGGEST QUESTION
How does this job's 47.0% margin compare across similar projects in the OWP portfolio, and what operational levers drove the result — estimating accuracy, vendor pricing, or labor productivity?
SOURCES
Job #2019 — Exxel Pacific 8th & Republican Apartments • GC: Exxel Pacific, Inc. (Owner: The Wolff Company) • Seattle, WA
Canonical source: 2019 Job Detail Report.pdf (249 pages, OWP Sage Timberline export)
Cost codes parsed: 25 (Labor+Material+Overhead+Burden+Revenue)
Unit count (211) confirmed by two independent sources:
1) Keller Supply consolidated trim PO (8TH REP TRIM - KELLER.xlsx): 211 Delta 4159-DST kitchen faucets
2) Seattle/King County plumbing permit #1459 ($11,925 fee, 10/23/2014): Water Closet field = 211
Fixture breakdown from same permit: Lavs 255, Tubs/Showers 214, Kitchen 211, DW 211, Floor Drains 49, Urinals 2, Sump 8, Roof Drains 10, + misc = ~1,196
Billing: REPUBLICAN AGGREGATE BILLING.xlsx (20 pay apps, Sep 2014 – Jun 2016) + 20 underlying SOV files
Change orders: 10 COs net +$156,008.60 (can layout, acoustical wrap, added boilers, ASI 15/48, premium time, etc.)

## Benchmark KPIs
Benchmark KPIs
Normalized metrics designed for apples-to-apples comparison across all OWP projects
KPI | Data Name | Value | Category | Notes
Job Number | job_number | 2019 | Profile | OWP job ID
Job Name | job_name | Exxel Pacific 8th & Republican Apartments | Profile
General Contractor | general_contractor | Exxel Pacific, Inc. (Owner: The Wolff Company) | Profile
Location | location | Seattle, WA (430 8th Ave N) | Profile
Project Type | project_type | 8-story 211-unit multifamily apartments + ground-floor retail/amenity | Profile
Duration (months) | duration_months | 22 | Profile | Sep 2014 – Jul 2016 (~22 months)
Unit Count | unit_count | 211 | Profile
Total Fixtures | total_fixtures | 1196 | Profile
Fixtures per Unit | fixtures_per_unit | 5.6682 | Profile
Contract Value (Orig) | contract_original | 2721210 | Financial
Contract Value (Final) | contract_final | 2877218.6 | Financial | After change orders
Change Orders ($) | change_orders | 156008.6 | Financial
Revenue | revenue | 2877218.6 | Financial
Net Profit | net_profit | 1353159.87 | Financial
Gross Margin | gross_margin | 0.4703 | Financial
Direct Cost | direct_cost | 1524058.73 | Financial
Labor Cost | labor_cost | 550832.62 | Labor | Sum of 10 labor codes
Material Cost | material_cost | 660548.93 | Material | Sum of 9 material codes
Overhead Cost | overhead_cost | 59981.3 | Financial | Sub+Eng+Permits
Burden Cost | burden_cost | 252695.88 | Financial | Codes 995+998
Retainage | retainage | 143861 | Financial | 5% withheld
Revenue per Unit | revenue_per_unit | 13636.1071 | Financial
Profit per Unit | profit_per_unit | 6413.08 | Financial
Direct Cost per Unit | cost_per_unit | 7223.0272 | Financial
Labor Cost per Unit | labor_per_unit | 2610.5811 | Labor
Material Cost per Unit | material_per_unit | 3130.5636 | Material
Revenue per Fixture | revenue_per_fixture | 2405.7012 | Financial
Profit per Fixture | profit_per_fixture | 1131.4046 | Financial
Cost per Fixture | cost_per_fixture | 1274.2966 | Financial
Labor per Fixture | labor_per_fixture | 460.5624 | Labor
Material per Fixture | material_per_fixture | 552.2984 | Material
Total Labor Hours | total_hours | 26599 | Labor | Sum of JDR cost code hours
Total Workers | total_workers | 56 | Labor | Unique payroll IDs
Blended Gross Wage | blended_gross_wage | 2047% | Labor | Pre-burden
Fully-Loaded Wage | fully_loaded_wage | 3021% | Labor | Post-burden
Burden Multiplier | burden_multiplier | 1.4757 | Labor
Hours per Unit | hours_per_unit | 126.0616 | Labor | Key benchmark
Hours per Fixture | hours_per_fixture | 2224% | Labor | Key benchmark
Revenue per Hour | revenue_per_hour | 108.1702 | Productivity
Profit per Hour | profit_per_hour | 5087% | Productivity
Labor % of Revenue | labor_pct_revenue | 0.19145 | Cost Mix
Material % of Revenue | material_pct_revenue | 0.22958 | Cost Mix
Revenue per Month | revenue_per_month | 130782.6636 | Productivity
Hours per Month | hours_per_month | 1209.0455 | Productivity
Units per Month | units_per_month | 9.5909 | Productivity
Total Vendors | total_vendors | 25 | Material | Unique AP vendors
Top Vendor Spend | top_vendor_spend | 248013.68 | Material | Rosen Supply Company, Inc.
Top Vendor Concentration | top_vendor_pct | 0.3235 | Material
Total POs | total_pos | 194 | Material | Unique POs by filename
Change Order % | co_pct | 0.057331 | Financial
Revenue per Labor Hour | rev_per_labor_hr | 108.1702 | Productivity
SOURCES
Job #2019 — Exxel Pacific 8th & Republican Apartments • GC: Exxel Pacific, Inc. (Owner: The Wolff Company) • Seattle, WA
Canonical source: 2019 Job Detail Report.pdf (249 pages, OWP Sage Timberline export)
Cost codes parsed: 25 (Labor+Material+Overhead+Burden+Revenue)
Unit count (211) confirmed by two independent sources:
1) Keller Supply consolidated trim PO (8TH REP TRIM - KELLER.xlsx): 211 Delta 4159-DST kitchen faucets
2) Seattle/King County plumbing permit #1459 ($11,925 fee, 10/23/2014): Water Closet field = 211
Fixture breakdown from same permit: Lavs 255, Tubs/Showers 214, Kitchen 211, DW 211, Floor Drains 49, Urinals 2, Sump 8, Roof Drains 10, + misc = ~1,196
Billing: REPUBLICAN AGGREGATE BILLING.xlsx (20 pay apps, Sep 2014 – Jun 2016) + 20 underlying SOV files
Change orders: 10 COs net +$156,008.60 (can layout, acoustical wrap, added boilers, ASI 15/48, premium time, etc.)
51 KPIs with snake_case data_name identifiers for database ingestion

## Reconciliation
Reconciliation — Tie-out Proofs
Check | Computed | Expected | Δ | Status
A. JDR COST CODE ROLLUP
Labor subtotal (10 codes) | 550832.62 | 550832.62 | 0 | TIES
Material subtotal (9 codes) | 660548.93 | 660548.93 | 0 | TIES
Overhead subtotal (3 codes) | 59981.3 | 59981.3 | 0 | TIES
Burden subtotal (2 codes) | 252695.88 | 252695.88 | 0 | TIES
Direct Cost (all categories) | 1524058.73 | 1524058.73 | 0 | TIES
Revenue (code 999) | 2877218.6 | 2877218.6 | 0 | TIES
Net Profit (Revenue - Expenses) | 1353159.87 | 1353159.87 | 0 | TIES
B. LABOR HOURS ROLLUP
JDR Cost Code hours (Payroll Hours lines) | 26599 | 26599 | 0 | TIES
Per-worker hours (sum of PR Regular) | 26448.5 | 26599 | -150.5 | WITHIN
C. BILLING (SOV) ↔ JDR
Final Contract Value | 2877218.6 | 2877219 | -0.4 | TIES
Retainage | 143861 | 143861 | 0 | TIES
Direct Cost | 1524058.73 | 1524058.73 | 0 | TIES
D. VENDOR AP ↔ JDR
Vendor AP total (sum of invoices) | 766653.25 | 748852 | 17801.25 | WITHIN
SOURCES
Job #2019 — Exxel Pacific 8th & Republican Apartments • GC: Exxel Pacific, Inc. (Owner: The Wolff Company) • Seattle, WA
Canonical source: 2019 Job Detail Report.pdf (249 pages, OWP Sage Timberline export)
Cost codes parsed: 25 (Labor+Material+Overhead+Burden+Revenue)
Unit count (211) confirmed by two independent sources:
1) Keller Supply consolidated trim PO (8TH REP TRIM - KELLER.xlsx): 211 Delta 4159-DST kitchen faucets
2) Seattle/King County plumbing permit #1459 ($11,925 fee, 10/23/2014): Water Closet field = 211
Fixture breakdown from same permit: Lavs 255, Tubs/Showers 214, Kitchen 211, DW 211, Floor Drains 49, Urinals 2, Sump 8, Roof Drains 10, + misc = ~1,196
Billing: REPUBLICAN AGGREGATE BILLING.xlsx (20 pay apps, Sep 2014 – Jun 2016) + 20 underlying SOV files
Change orders: 10 COs net +$156,008.60 (can layout, acoustical wrap, added boilers, ASI 15/48, premium time, etc.)
TIES = within $1 or 5 hrs • WITHIN = within 5% • OFF = investigate

## Vendors
Vendor Detail — Job #2019
Vendors | 25 |  | Top vendor | Rosen Supply Company, Inc.
Invoices | 402 |  | Top 3 share | 59.28%
Total AP | 766653.25 |  | Source | 2019 Job Detail Report.pdf (Sage Timberline AP export)
Avg Inv | 1907.0976
Rank | Vendor | Vendor Code | Invoices | Total Spend | % of AP | Avg / Invoice
1 | Rosen Supply Company, Inc. |  | 97 | 248013.68 | 32.35% | 2556.8421
2 | Ferguson Enterprises, Inc. |  | 57 | 104759.63 | 13.66% | 1837.8882
3 | Keller Supply Company |  | 66 | 101721.98 | 13.27% | 1541.2421
4 | Franklin Engineering |  | 19 | 94572.5 | 12.34% | 4977.5
5 | Mechanical Sales, Inc. |  | 4 | 70651.37 | 9.216% | 17662.8425
6 | Consolidated Supply Co. |  | 27 | 45650.81 | 5.955% | 1690.7707
7 | Hudson Bay Insulation |  | 1 | 19963 | 2.604% | 19963
8 | Capital One Credit Card |  | 59 | 18513.01 | 2.415% | 313.7798
9 | Bank of America CC |  | 10 | 16471.05 | 2.148% | 1647.105
10 | United Rentals, Inc. |  | 18 | 9870.42 | 1.287% | 548.3567
11 | Scan2Core, Inc. |  | 7 | 8878 | 1.158% | 1268.2857
12 | Quality Concrete Products, Inc. |  | 3 | 6463.4 | 0.8431% | 2154.4667
13 | Rosen Supply Kirkland |  | 7 | 4731.84 | 0.6172% | 675.9771
14 | Ferguson Enterprises, Inc. #3007 |  | 3 | 4012.56 | 0.5234% | 1337.52
15 | Balco Inc |  | 1 | 3908 | 0.5097% | 3908
16 | Kele, Inc |  | 4 | 2674.82 | 0.3489% | 668.705
17 | MAD Concrete Cutting & Coring, Inc. |  | 1 | 1775 | 0.2315% | 1775
18 | Standard Parking |  | 3 | 1526.25 | 0.1991% | 508.75
19 | AllWest Underground, Inc. |  | 1 | 671.5 | 0.08759% | 671.5
20 | C.M. Hoskins Company |  | 2 | 607.04 | 0.07918% | 303.52
21 | A.R. Brown Backflow Testing |  | 3 | 470.35 | 0.06135% | 156.7833
22 | Fastenal Company |  | 5 | 351.93 | 0.0459% | 70.386
23 | Lotus United, LLC |  | 1 | 155 | 0.02022% | 155
24 | ACME Corp |  | 2 | 150.11 | 0.01958% | 75.055
25 | Manor Hardware & Construction Supply |  | 1 | 90 | 0.01174% | 90
| TOTAL |  | 402 | 766653.25 | 100% | 1907.0976