## Headline Reconciliation
OWP 2020 — JCR Test Labels (v4) vs OWP_2020_JCR_Cortex_v2.xlsx (rebuilt 2026-04-18)
Source of truth: JCR Test Labels — Job 2020.xlsx (v4 schema, 29 cost codes reconciled)
Metric | TL v4 | V2 (rebuilt) | Difference | Status
PROJECT TOTALS
Revenue (actual AR) | 2852262.93 | 2852262.93 | 0 | TIES
Direct Cost | 1992084.82 | 1992084.82 | 0 | TIES
Net Profit | 860178.11 | 860178.11 | 0 | TIES
Retainage | 142917.05 | 142917.05 | 0 | TIES
LABOR
Labor Hours (reg+ot, PR src) | 39280 | 39280 | 0 | TIES
Total Workers (DISTINCT PR) | 58 | 58 | 0 | TIES
WAGE METHODOLOGY
Straight-Time Rate ($/hr) | 19.5933 | 19.59 | -0.0033391 | TIES
PR-Src Cost/Hour ($/hr) | 30.0987 | 30.1 | 0.0013136 | TIES
Fully-Loaded Wage ($/hr) | 40.2467 | 40.25 | 0.0033404 | TIES
Burden Multiplier | 1.3372 | 1.337 | -0.00015668 | TIES

## Cost Codes — All 29
Cost Code Reconciliation — All 29 codes present in both files
Code | Description | TL Actual | V2 Actual | Diff | Status
100 | Supervision | 13026.5 | 13026.5 | 0 | TIES
101 | Takeoff & Purchase Labor | 18552.5 | 18552.5 | 0 | TIES
110 | Underground Labor | 16803.75 | 16803.75 | 0 | TIES
111 | Garage Labor | 142441 | 142441 | 0 | TIES
112 | Canout Labor | 16515.5 | 16515.5 | 0 | TIES
113 | Foundation Drain Labor | 2843 | 2843 | 0 | TIES
120 | Roughin Labor | 348602.98 | 348602.98 | 0 | TIES
130 | Finish Labor | 64250.9 | 64250.9 | 0 | TIES
140 | Gas Labor | 32025.5 | 32025.5 | 0 | TIES
141 | Water Main/Insulation Lab | 85831.88 | 85831.88 | 0 | TIES
142 | Mech Room Labor | 13690 | 13690 | 0 | TIES
143 | Condensation Drains Labor | 26035.5 | 26035.5 | 0 | TIES
210 | Underground Material | 24415.78 | 24415.78 | 0 | TIES
211 | Garage Material | 54034.99 | 54034.99 | 0 | TIES
212 | Canout Material | 24723.82 | 24723.82 | 0 | TIES
220 | Roughin Material | 87900.72 | 87900.72 | 0 | TIES
230 | Finish Material | 411991.97 | 411991.97 | 0 | TIES
240 | Gas Material | 8263.12 | 8263.12 | 0 | TIES
241 | Water Main/Insulation Mat | 122165.25 | 122165.25 | 0 | TIES
242 | Mech Room Material | 27133.61 | 27133.61 | 0 | TIES
243 | Condensation Drains Mat | 2198.97 | 2198.97 | 0 | TIES
600 | Subcontractor | 13494 | 13494 | 0 | TIES
602 | Rental Equipment | 21589.36 | 21589.36 | 0 | TIES
603 | Permits & Licenses | 480 | 480 | 0 | TIES
606 | Shop Labor | 2784 | 2784 | 0 | TIES
607 | Other Expenses | 11677.83 | 11677.83 | 0 | TIES
995 | Payroll Burden | 338661.76 | 338661.76 | 0 | TIES
998 | Payroll Taxes | 59950.63 | 59950.63 | 0 | TIES
999 | Sales | -2852262.93 | -2852262.93 | 0 | TIES
CATEGORY ROLLUPS
Labor (11 codes 100-143) |  | 780619.01 | 780619.01 | 0 | TIES
Material (9 codes 210-243) |  | 762828.23 | 762828.23 | 0 | TIES
Overhead (5 codes 600-607) |  | 50025.19 | 50025.19 | 0 | TIES
Burden (2 codes 995+998) |  | 398612.39 | 398612.39 | 0 | TIES
DIRECT COST (all non-revenue) |  | 1992084.82 | 1992084.82 | 2.3283e-10 | TIES

## Before vs After (V2 fix)
Cortex v2 — values before and after the 2026-04-18 rebuild
'Before' values are from the prior OWP_2020_JCR_Cortex_v2.xlsx (Apr 1, pre-fix).
Metric | TL v4 (truth) | V2 Before (buggy) | V2 After (fixed) | Bug
Revenue | $2,852,263 | $3,119,000 | $2,852,263 | Used original contract, not billed AR
Direct Cost | $1,992,085 | $1,934,503 | $1,992,085 | Missing $57,582 — dropped codes 142/243/600/606 and mislabeled rows
Net Profit | $860,178 | $1,184,497 | $860,178 | Followed from wrong revenue + wrong cost
Gross Margin % | 30.2% | 38.0% | 30.2% | Followed from wrong revenue + wrong cost
Labor Hours (banner) | 39,280 | 76,015 | 39,280 | ~2× aggregation bug in Overview banner
Total Workers (Overview) | 58 | 71 | 58 | Overview and Crew Analytics disagreed (71 vs 57)
Cost Codes in BvA | 29 | 23 | 29 | 143/243/602/606/607/999 missing; 142/242/600/603 mislabeled
Overhead Subtotal | $50,025 | $33,267 | $50,025 | Only 2 of 5 overhead codes included
Labor Subtotal | $780,619 | $766,929 | $780,619 | Code 142 dropped (row 142 held 143's data)
Material Subtotal | $762,828 | $735,695 | $762,828 | Code 242 dropped (row 242 held 243's data)
Straight-Time Rate | $19.59 | $19.62* | $19.59 | * was labeled 'Blended Gross Wage' (wrong label)
Fully-Loaded Wage | $40.25 | $30.67 | $40.25 | Wrong numerator/denominator in fully-loaded calc
Burden Multiplier | 1.337x | 1.563x | 1.337x | Followed from wrong FL wage
Retainage | $142,917 | $142,517 | $142,917 | $400 rounding drift