## Overview
[CORTEX_V2.1] Job #2020 — · Overview
Schema CORTEX_V2.1 · canonical v2 builder · single source of truth
| OVERVIEW |  | SOURCE
IDENTITY
| Project Job Number | 2020
| Project Name: | SRM Bellevue @ Main Apartments
CONTRACT & PARTIES
| General Contractor | SRM Development / Exxel Pacific (Owner: Bellevue Way Ventures)
JOB SITE
| Jobsite Location | Bellevue, WA (15 Bellevue Way SE)
| Plumbing Units | 288 | Type A (ADA)
| Floors | P2/P1 garage + L1 retail + Mezz + L2–L5 residential
SCHEDULE
| Project Duration | May 2014 – Feb 2016 (~22 months)
SCOPE & DESIGN
| Water Closets | 288+20 ADA | Bathtub Trim
| Lav Faucets | 288 + 4 amenity | Fixtures / Unit
| REVENUE (AR) |  | NET PROFIT |  | DIRECT COST |  | LABOR HOURS
| $2,852,263 |  | $860,178 |  | $1,992,085 |  | 39,280
| Final contract $2,858,341 |  | 30.2% margin |  | 69.8% of revenue |  | 58 workers
COST BREAKDOWN
| Category | Budget | Actual | Variance | % Budget | % of Cost
| Labor | 601174 | 780619.01 | -179445.01 | 129.8% | 39.19%
| Material | 1013696 | 762828.23 | 250867.77 | 75.25% | 38.29%
| Overhead | 25985 | 50025.19 | -24040.19 | 192.5% | 2.511%
| Burden | 312438.73 | 398612.39 | -86173.66 | 127.6% | 20.01%
| TOTAL | 1953293.73 | 1992084.82 | -38791.09 | 102% | 100%
PROJECT PROFILE
| Plumbing Units | 288 |  | Water Closets | 288+20 ADA |  | Lavatories | 288 + 4 amenity
| Floors | P2/P1 garage + L1 retail + Mezz + L2–L5 residential |  | Duration | May 2014 – Feb 2016 (~22 months)
PROJECT TEAM · KEY PLAYERS
Sourced from index.html PROJECT_TEAMS['2020'] (gold-standard team grid). GDrive contract PDFs were locked at extraction time — team data mirrors the dashboard's verified roster.
| ROLE | NAME / VALUE
| General Contractor | SRM Development / Exxel Pacific (CM-at-risk)
| GC Project Manager | Todd Rankin (early) → Erik Benzel (closeout)
| GC Superintendent | Bill Robinson / Jared Osborn
| GC Project Engineer | Renay Luzama
| OWP Roughin Foreman | Nate (Veley)
| OWP Trim Foreman | Al
| OWP Signatory | Richard Donelson
| Owner of Record | Bellevue Way Ventures, LLC
| Developer | Pillar Properties / SRM
| Architect | Benson & Bohl Architects
| Structural Engineer | DCI Engineers
| MEP / Plumbing Engineer | Pressler Engineers
| Acoustical | SSA Acoustics
| Civil Engineer | TBD (not in dashboard)
| Landscape | TBD
| Permit Number | City of Bellevue #13-133992-BO
| Insurance | Not Wrap (OWP carries CGL — Cert of Insurance 2016 on file)
| Lien / Priority Position | Subordination + Priority agreements both on file (Bellevue Way Subordination 04/15/14)
| Warranty | Bellevue Way Ventures Warranty (LH) — 1 yr standard plumbing
| Site Address | 15 Bellevue Way SE, Bellevue, WA
| Delivery Route | Bellevue at Main – Delivery Truck Route.pdf (on file)
| Contract on File | One Way Plumbing Executed Contract OCR_D.pdf · Contract folder
| GDrive Notes | Folder accessible; PDFs deadlocked at this run — team data sourced from dashboard PROJECT_TEAMS['2020']

## Job Info
JOB #2020 · PROJECT INFORMATION & KEY PLAYERS
Comprehensive project metadata. Sourced from JDR + index.html PROJECT_TEAMS + GDrive scan (PDF deadlock noted).
IDENTITY
Job Number | 2020
Job Name | SRM Bellevue @ Main Apartments
Project Type | 6-story 288-unit luxury multifamily + retail
Location | 15 Bellevue Way SE, Bellevue, WA
Permit | City of Bellevue #13-133992-BO
Site Address | 15 Bellevue Way SE, Bellevue, WA
Delivery Route | Bellevue at Main – Delivery Truck Route.pdf (on file)
SCHEDULE
Project Start | May 2014
Project End | Feb 2016
Duration | ~22 months
CONTRACT & FINANCIALS
Original Contract | $3,119,000
Net Change Orders | ($260,659)
Final Contract | $2,858,341
Revenue (AR) | $2,852,263
Direct Cost | $1,992,085
Net Profit | $860,178
Gross Margin | 30.2%
Retainage Outstanding | $142,917
Insurance | Not Wrap (OWP carries CGL — Cert of Insurance 2016 on file)
Lien Position | Subordination + Priority agreements both on file (Bellevue Way Subordination 04/15/14)
Warranty | Bellevue Way Ventures Warranty (LH) — 1 yr standard plumbing
Contract on File | One Way Plumbing Executed Contract OCR_D.pdf · Contract folder
SCOPE
Plumbing Units | 288
Total Fixtures | 1,564
Floors | P2/P1 garage + L1 retail + Mezz + L2–L5 residential
Fixture Counts | 288 toilets (+20 ADA), 288 lavs (+4 amenity), 257 kitchen faucets
PROJECT TEAM — GENERAL CONTRACTOR
General Contractor | SRM Development / Exxel Pacific (CM-at-risk)
GC Project Manager | Todd Rankin (early) → Erik Benzel (closeout)
GC Superintendent | Bill Robinson / Jared Osborn
GC Project Engineer | Renay Luzama
PROJECT TEAM — OWP STAFF
OWP Roughin Foreman | Nate (Veley)
OWP Trim Foreman | Al
OWP Signatory | Richard Donelson
PROJECT TEAM — OWNER & DEVELOPMENT
Owner of Record | Bellevue Way Ventures, LLC
Developer | Pillar Properties / SRM
PROJECT TEAM — DESIGN
Architect | Benson & Bohl Architects
Structural Engineer | DCI Engineers
MEP / Plumbing Engineer | Pressler Engineers
Acoustical | SSA Acoustics
Civil Engineer | TBD (not in dashboard)
Landscape | TBD
ADA Consultant | n/a (not flagged in 2020)
Interior Designer | n/a (not flagged in 2020)
CHANGE-EVENT META
Total CO/COR/Backcharge events | 13
Executed COs | 9
Unexecuted CORs | 2
Backcharges | 1
RFIs | 56
Submittals | 206
POs | 279
Net CO Cost Impact | $127,362
DATA SOURCES
JDR PDF | 2020 Job Detail Report.pdf (352 pages, Apr 03 2026 run)
Parsed Data | 2020_data.json
Dashboard Arrays | 2020_dashboard_arrays.json (16 arrays from index.html PROJECTS['2020'])
Sam Gold Standard | JCR Test Labels — Job 2020.xlsx
GDrive Folder | 2020-SRM, Bellevue @ Main/ (Job Books - Completed Jobs)
GDrive Status | Folder accessible; PDFs deadlocked at this run — team data sourced from dashboard PROJECT_TEAMS['2020']

## Budget vs Actual
[CORTEX_V2.1] Job #2020 — · Budget vs Actual
Schema CORTEX_V2.1 · canonical v2 builder · single source of truth
| cost_code | description | original_budget | revised_budget | actual | variance | pct_used | hours | source
LABOR
| 100 | Supervision | 12800 | 13700 | 13026.5 | 673.5 | 95.08% | 301
| 101 | Takeoff & Purchase Labor | 15360 | 17310 | 18552.5 | -1242.5 | 107.2% | 434
| 110 | Underground Labor | 16160 | 16760 | 16803.75 | -43.75 | 100.3% | 775
| 111 | Garage Labor | 114350 | 118946 | 142441 | -23495 | 119.8% | 6414
| 112 | Canout Labor | 16000 | 16100 | 16515.5 | -415.5 | 102.6% | 776.5
| 113 | Foundation Drain Labor | 2843 | 2843 | 2843 | 0 | 100% | 144
| 120 | Roughin Labor | 376600 | 266055 | 348602.98 | -82547.98 | 131% | 18980.5
| 130 | Finish Labor | 51400 | 58664 | 64250.9 | -5586.9 | 109.5% | 3322
| 140 | Gas Labor | 9000 | 13862 | 32025.5 | -18163.5 | 231% | 1515.5
| 141 | Water Main/Insulation Lab | 55600 | 57029 | 85831.88 | -28802.88 | 150.5% | 4519
| 142 | Mech Room Labor | 7200 | 7200 | 13690 | -6490 | 190.1% | 531
| 143 | Condensation Drains Labor | 9900 | 12705 | 26035.5 | -13330.5 | 204.9% | 1567.5
MATERIAL
| 210 | Underground Material | 23100 | 23300 | 24415.78 | -1115.78 | 104.8%
| 211 | Garage Material | 95600 | 92894 | 54034.99 | 38859.01 | 58.17%
| 212 | Canout Material | 26400 | 26700 | 24723.82 | 1976.18 | 92.6%
| 220 | Roughin Material | 363580 | 213718 | 87900.72 | 125817.28 | 41.13%
| 230 | Finish Material | 478500 | 526401 | 411991.97 | 114409.03 | 78.27%
| 240 | Gas Material | 12600 | 12800 | 8263.12 | 4536.88 | 64.56%
| 241 | Water Main/Insulation Mat | 92600 | 93431 | 122165.25 | -28734.25 | 130.8%
| 242 | Mech Room Material | 16500 | 16500 | 27133.61 | -10633.61 | 164.4%
| 243 | Condensation Drains Mat | 7000 | 7952 | 2198.97 | 5753.03 | 27.65%
OVERHEAD
| 600 | Subcontractor | 500 | 2525 | 13494 | -10969 | 534.4%
| 602 | Rental Equipment | 4000 | 5000 | 21589.36 | -16589.36 | 431.8%
| 603 | Permits & Licenses | 3500 | 3500 | 480 | 3020 | 13.71%
| 606 | Shop Labor | 3960 | 3960 | 2784 | 1176 | 70.3%
| 607 | Other Expenses | 1000 | 11000 | 11677.83 | -677.83 | 106.2%
BURDEN
| 995 | Payroll Burden | 309922.16 | 265927.39 | 338661.76 | -72734.37 | 127.4%
| 998 | Payroll Taxes | 54692.15 | 46511.34 | 59950.63 | -13439.29 | 128.9%
REVENUE
| 999 | Sales | -3119000 | -2852262.93 | -2852262.93 | 0 | 100%
| TOTAL (non-revenue) |  | 2180667.31 | 1953293.73 | 1992084.82 | -38791.09 | 102%

## Cost Breakdown
[CORTEX_V2.1] Job #2020 — · Cost Breakdown
Schema CORTEX_V2.1 · canonical v2 builder · single source of truth
| Category | # Codes | Budget | Actual | % of Direct Cost | $ per Unit
| Labor | 11 | 593974 | 76692900% | 39.6% | 2663
| Material | 8 | 997196 | 73569500% | 38.0% | 2554
| Overhead | 2 | 16000 | 3326700% | 1.7% | 116
| Burden | 2 | 312439 | 39861200% | 20.6% | 1384
| DIRECT COST TOTAL |  | 1919609 | 193450300% | 100.0%

## Material
[CORTEX_V2.1] Job #2020 — · Material
Schema CORTEX_V2.1 · canonical v2 builder · single source of truth
A. MATERIAL SPEND BY COST CODE
| Code | Description | Budget | Actual | Variance | % of Material
| 210 | Underground Material | 23300 | 24415.78 | -1115.78 | 3.2%
| 211 | Garage Material | 92894 | 54034.99 | 38859.01 | 7.1%
| 212 | Canout Material | 26700 | 24723.82 | 1976.18 | 3.2%
| 220 | Roughin Material | 213718 | 87900.72 | 125817.28 | 11.5%
| 230 | Finish Material | 526401 | 411991.97 | 114409.03 | 54.0%
| 240 | Gas Material | 12800 | 8263.12 | 4536.88 | 1.1%
| 241 | Water Main/Insulation Mat | 93431 | 122165.25 | -28734.25 | 16.0%
| 242 | Mech Room Material | 16500 | 27133.61 | -10633.61 | 3.6%
| 243 | Condensation Drains Mat | 7952 | 2198.97 | 5753.03 | 0.3%
B. VENDORS BY SPEND (AP)
| # | Vendor | Invoices | Spend | % of AP
| 1 | Ferguson Enterprises, Inc. | 121 | 216177 | 27.3%
| 2 | Keller Supply Company | 101 | 204980 | 25.9%
| 3 | Rosen Supply Company | 172 | 188563 | 23.8%
| 4 | Mechanical Sales, Inc. | 4 | 67936 | 8.6%
| 5 | Consolidated Supply Co. | 11 | 47820 | 6.0%
| 6 | United Rentals, Inc. | 40 | 23301 | 2.9%
| 7 | Quality Concrete Products, Inc. | 5 | 15202 | 1.9%
| 8 | Scan2Core, Inc. | 13 | 8585 | 1.1%
| 9 | MAD Concrete Cutting & Coring, Inc. | 5 | 4605 | 0.6%
| 10 | Kele, Inc | 6 | 3172 | 0.4%
| 11 | C.M. Hoskins Company | 5 | 2334 | 0.3%
| 12 | Rosen Supply Kirkland | 8 | 2332 | 0.3%
| 13 | Capital One Credit Card | 16 | 2041 | 0.3%
| 14 | Shirley Dennison | 17 | 1700 | 0.2%
| 15 | Seton Identification Products | 3 | 1302 | 0.2%
| 16 | American Express 3-41000 | 1 | 945 | 0.1%
| 17 | NRP-Meydenbauer | 4 | 474 | 0.1%
| 18 | Ferguson Enterprises, Inc. #3007 | 2 | 458 | 0.1%
| 19 | Fastenal Company | 5 | 456 | 0.1%
| 20 | A.R. Brown Backflow Testing | 3 | 304 | 0.0%
| 21 | Rosen Supply Company, Inc. | 3 | 47 | 0.0%

## Crew & Labor
[CORTEX_V2.1] Job #2020 — · Crew & Labor
Schema CORTEX_V2.1 · canonical v2 builder · single source of truth
| worker_id | worker_name | total_hours | gross_pay | blended_wage_per_hr | tier | work_days | source
| Veley, Nathaniel S |  | 2965.5 | 93837.5 | 31.6431 | Senior
| Paco Leyva, Orlando |  | 2928.5 | 58335.5 | 19.9199 | Mid
| Gerard, Mitchell J |  | 2472 | 37490 | 15.1659 | Apprentice
| Moran Fernandez, Jose |  | 2334.5 | 37020 | 15.8578 | Apprentice
| Reed, Reuben H |  | 2246 | 67320 | 29.9733 | Mid
| Rodriguez, Fernando V |  | 1869.5 | 28508 | 15.249 | Apprentice
| Meza Fuentes, Erick A |  | 1472.5 | 32385.5 | 21.9935 | Mid
| Monico Brambila, Jesus S |  | 1389 | 22908.5 | 16.4928 | Apprentice
| Taylor, Evan R |  | 1342.5 | 18092.5 | 13.4767 | Apprentice
| Ayers, Jordan L |  | 1335.5 | 20429.5 | 15.2973 | Apprentice
| Holmes, Anthony R |  | 990.5 | 15385.5 | 15.5331 | Apprentice
| Wennig, Johnathan M |  | 978 | 14097.5 | 14.4146 | Apprentice
| Barbosa, Michael S |  | 973.5 | 12783.5 | 13.1315 | Apprentice
| Salazar, Hajdar L |  | 857 | 13712 | 16 | Apprentice
| Cruz Jimenez, Adalberto |  | 857 | 11998 | 14 | Apprentice
| Gonzalez Guzman, Rigoberto A |  | 856.5 | 11286.5 | 13.1775 | Apprentice
| Gerard, Jordan E |  | 824 | 11312 | 13.7282 | Apprentice
| Waites, Thaddeus Z |  | 784 | 23440 | 29.898 | Mid
| Walker, Craig M |  | 730.5 | 10406 | 14.245 | Apprentice
| Sanders, Allen O |  | 712 | 23807.5 | 33.4375 | Senior
| Kinssies, Jr, John E |  | 673 | 10985 | 16.3224 | Apprentice
| Ramos, Jose G |  | 540 | 7020 | 13 | Apprentice
| Donelson, Richard T |  | 477 | 21465 | 45 | Senior
| Galdamez, Dagoberto A |  | 448 | 6368 | 14.2143 | Apprentice
| Lopez Barrios, Luis F |  | 444.5 | 5778.5 | 13 | Apprentice
| Vaughan, Tyler J |  | 412 | 7940.5 | 19.2731 | Mid
| Castro Hernandez, Jose A |  | 411.5 | 8323 | 20.226 | Mid
| Lopez Martinez, Abimael |  | 397 | 5955 | 15 | Apprentice
| Alba Jimenez, Jovani |  | 366 | 5856 | 16 | Apprentice
| Garcia, Jordan X |  | 365.5 | 6024.5 | 16.4829 | Apprentice
| Alba Martinez, Santiago |  | 361 | 6498 | 18 | Mid
| Hubbard, Robert W |  | 359.5 | 13363.5 | 37.1725 | Senior
| Ross, Kelli M |  | 348 | 10788 | 31 | Senior
| Ramos Banegas, Noel O |  | 341.5 | 5464 | 16 | Apprentice
| Ramirez, Lorenzo A |  | 297 | 5049 | 17 | Apprentice
| Santiago, William T |  | 286.5 | 3724.5 | 13 | Apprentice
| Gerard, Jeffrey S |  | 279.5 | 11102.5 | 39.7227 | Senior
| Soto Cruz, Jovani |  | 274 | 4384 | 16 | Apprentice
| Reyes, Robert J |  | 199.5 | 2793 | 14 | Apprentice
| Eliassen, Cory H |  | 192.5 | 2502.5 | 13 | Apprentice
| Palma Vides, Jorge A |  | 176 | 2464 | 14 | Apprentice
| Lima Romero, Melvin A |  | 176 | 4032 | 22.9091 | Mid
| Cortes Mendiola, Victor H |  | 173 | 4844 | 28 | Mid
| Cruz Reyes, Jose |  | 144 | 2016 | 14 | Apprentice
| Palma Vides, Hugo |  | 144 | 4464 | 31 | Senior
| Soto Serna, Cesar E |  | 140 | 1820 | 13 | Apprentice
| Whitaker, Daniel J |  | 110 | 1430 | 13 | Apprentice
| Trump, Norman W |  | 108 | 1836 | 17 | Apprentice
| Hubbard, Dustin R |  | 95 | 1406 | 14.8 | Apprentice
| Schaefer, Taylor E |  | 88 | 1232 | 14 | Apprentice
| Cruz Guzman, Joel A |  | 80 | 1040 | 13 | Apprentice
| Ruiz, Hugo |  | 56 | 784 | 14 | Apprentice
| Gonzalez Hernandez, Josue |  | 46 | 736 | 16 | Apprentice
| Cortes Sepulveda, Jose R |  | 40 | 520 | 13 | Apprentice
| Sepulveda Gonzalez, Alfredo |  | 24 | 640 | 26.6667 | Mid
| Ascencio, Jose L |  | 8 | 112 | 14 | Apprentice
| Anderson, Richard P |  | 7.5 | 230 | 30.6667 | Senior
| TOTAL (58 workers) |  | 39280 | 745546 | 19.59
SOURCES
Job #2020 — SRM Bellevue @ Main Apartments • GC: Exxel Pacific / Owner: Bellevue Way Ventures • Bellevue, WA
Canonical source: 2020 Job Detail Report.pdf (352 pages, OWP Sage Timberline export)
Cost codes parsed: 24 (Labor+Material+Overhead+Burden+Revenue)
Unit count (288) confirmed by TWO source documents:
1) Bellevue Main – Pricing to go to 101 Taylor Fixtures.xlsx: Type B lavs qty=268, Type A lavs qty=20, Lav faucets qty=288, Bathtub trim qty=288
2) BELLEVUE TRIM QUOTE PRICING organized by category USE.xlsx: Mansfield toilets 268 + 20 ADA = 288
Kitchen fixtures: 257 kitchen faucets (Delta 4353-AR-DST) — 31 fewer than units (studios/amenity)
Contract: One Way Plumbing Executed Contract OCR_D.pdf — Exxel Pacific / SRM Development GC
Billing: 10 archived Schedule of Values files (pay apps #4, 9, 10, 12, 13, 15, 18, 19, 20, 23)
Final contract $2,858,341 after 11 COs (net -$260,659, primarily CO#1 cast iron credit -$389,000)
Permit: City of Bellevue #13-133992-BO (building/plumbing)
Tier: Apprentice <$18/hr, Mid $18–30, Senior >$30

## Crew Analytics
[CORTEX_V2.1] Job #2020 — · Crew Analytics
Schema CORTEX_V2.1 · canonical v2 builder · single source of truth
| tier | worker_count | hours | gross_pay | pct_of_hours | blended_wage
| Senior | 8 | 5293 | 179058 | 13.93%
| Mid | 10 | 8988.5 | 213758.5 | 23.65%
| Apprentice | 39 | 23726 | 352729.5 | 62.42%
B. WAGE STATISTICS
| Straight-Time Rate ($/hr) | 19.59 | Weighted avg reg_amount ÷ reg_hours (PR source)
| PR-Src Cost/Hour ($/hr) | 30.1 | PR total ÷ total labor hours (includes OT premium)
| Fully-Loaded Wage ($/hr) | 40.25 | (PR + burden) ÷ total labor hours
| Burden Multiplier | 1.337 | fully_loaded ÷ pr_src_cost_per_hr
| Total Workers | 58 | COUNT DISTINCT(name WHERE source=PR)
| Avg Hours / Worker | 677.24 | Total hours ÷ total workers
| Wage Percentiles | p10=$13.00 ¦ p25=$14.00 ¦ p50=$15.86 ¦ p75=$21.11 ¦ p90=$31.13
Job #2020 — SRM Bellevue @ Main Apartments • GC: Exxel Pacific / Owner: Bellevue Way Ventures • Bellevue, WA
Canonical source: 2020 Job Detail Report.pdf (352 pages, OWP Sage Timberline export)
Cost codes parsed: 24 (Labor+Material+Overhead+Burden+Revenue)
Unit count (288) confirmed by TWO source documents:
1) Bellevue Main – Pricing to go to 101 Taylor Fixtures.xlsx: Type B lavs qty=268, Type A lavs qty=20, Lav faucets qty=288, Bathtub trim qty=288
2) BELLEVUE TRIM QUOTE PRICING organized by category USE.xlsx: Mansfield toilets 268 + 20 ADA = 288
Kitchen fixtures: 257 kitchen faucets (Delta 4353-AR-DST) — 31 fewer than units (studios/amenity)
Contract: One Way Plumbing Executed Contract OCR_D.pdf — Exxel Pacific / SRM Development GC
Billing: 10 archived Schedule of Values files (pay apps #4, 9, 10, 12, 13, 15, 18, 19, 20, 23)
Final contract $2,858,341 after 11 COs (net -$260,659, primarily CO#1 cast iron credit -$389,000)
Permit: City of Bellevue #13-133992-BO (building/plumbing)

## Productivity
[CORTEX_V2.1] Job #2020 — · Productivity
Schema CORTEX_V2.1 · canonical v2 builder · single source of truth
| phase | labor_code | hours | pct_of_total | hours_per_unit
| Supervision | 100 | 301 | 0.7768% | 1.0451
| Takeoff & Purchasing | 101 | 434 | 1.12% | 1.5069
| Underground | 110 | 775 | 2% | 2.691
| Garage | 111 | 6414 | 16.55% | 22.2708
| Canout | 112 | 776.5 | 2.004% | 2.6962
| Foundation Drain | 113 | 144 | 0.3716% | 0.5
| Roughin | 120 | 18980.5 | 48.98% | 65.9045
| Finish | 130 | 3322 | 8.573% | 11.5347
| Gas | 140 | 1515.5 | 3.911% | 5.2622
| Water Main / Insulation | 141 | 4519 | 11.66% | 15.691
| Mech Room | 142 | 1567.5 | 4.045% | 5.4427
B. PRODUCTIVITY RATIOS
| Metric | Value
| Hours / Unit | 136.39
| Hours / Fixture | 25.12
| Revenue / Hour | 72.61
| Profit / Hour | 21.9
| Units / Month | 13.0909
| Fixtures / Month | 71.0909
| Hours / Month | 1785
| Revenue / Month | 129648
SOURCES
Job #2020 — SRM Bellevue @ Main Apartments • GC: Exxel Pacific / Owner: Bellevue Way Ventures • Bellevue, WA
Canonical source: 2020 Job Detail Report.pdf (352 pages, OWP Sage Timberline export)
Cost codes parsed: 24 (Labor+Material+Overhead+Burden+Revenue)
Unit count (288) confirmed by TWO source documents:
1) Bellevue Main – Pricing to go to 101 Taylor Fixtures.xlsx: Type B lavs qty=268, Type A lavs qty=20, Lav faucets qty=288, Bathtub trim qty=288
2) BELLEVUE TRIM QUOTE PRICING organized by category USE.xlsx: Mansfield toilets 268 + 20 ADA = 288
Kitchen fixtures: 257 kitchen faucets (Delta 4353-AR-DST) — 31 fewer than units (studios/amenity)
Contract: One Way Plumbing Executed Contract OCR_D.pdf — Exxel Pacific / SRM Development GC
Billing: 10 archived Schedule of Values files (pay apps #4, 9, 10, 12, 13, 15, 18, 19, 20, 23)
Final contract $2,858,341 after 11 COs (net -$260,659, primarily CO#1 cast iron credit -$389,000)
Permit: City of Bellevue #13-133992-BO (building/plumbing)

## PO Commitments
[CORTEX_V2.1] Job #2020 — · PO Commitments
Schema CORTEX_V2.1 · canonical v2 builder · single source of truth
| PO Type | Count Estimate | % of Total POs | Top Vendors | Notes
| Trim/Finish (Rosen) | 1900-03-06 | 23.8% | Rosen Supply Company | Trim phase POs
| Roughin (Ferguson) | 1900-03-16 | 27.3% | Ferguson Enterprises | Roughin phase POs
| Roughin (Keller) | 1900-03-12 | 25.9% | Keller Supply | Roughin phase POs
| Mech Sales / Specialty | — | — | Mechanical Sales, Inc. | Specialty mech room components
| Equipment Rentals | — | — | United Rentals | Lifts, scaffolding
| Concrete Cutting | — | — | MAD Concrete / Quality Concrete | Slab penetrations + sleeves
| Other | — | 23.0% | Long tail (~20 vendors)
TOTAL PURCHASE ORDERS: 279
Note: Detailed PO-by-PO records live in 2020-SRM, Bellevue @ Main/PO_s/ on GDrive (~280 individual POs). This tab summarizes commitments by vendor concentration. Per-PO detail can be re-extracted on demand.

## Billing & SOV
[CORTEX_V2.1] Job #2020 — · Billing & SOV
Schema CORTEX_V2.1 · canonical v2 builder · single source of truth
| Pay App # | Date | This Period | Retainage Held | Net Pay | Cumulative | % of Contract
| 4 | 2014-08-25 | 33600 | 0 | 33600 | 146751 | 5.1%
| 9 | 2014-12-15 | 159218 | 0 | 159218 | 827139 | 28.9%
| 10 | 2015-01-22 | 202569 | 0 | 202569 | 1029708 | 36.0%
| 12 | 2015-03-24 | 193214 | 0 | 193214 | 1604888 | 56.1%
| 13 | 2015-04-23 | 119208 | 0 | 119208 | 1731896 | 60.6%
| 15 | 2015-06-25 | 291977 | 0 | 291977 | 2234401 | 78.2%
| 18 | 2015-09-25 | 129074 | 0 | 129074 | 2662685 | 93.2%
| 19 | 2015-10-23 | 81921 | 0 | 81921 | 2744606 | 96.0%
| 20 | 2015-11-23 | 75825 | 0 | 75825 | 2820431 | 98.7%
| 23 | 2016-02-25 | 14578 | 142517.05 | -127939.05 | 2858341 | 100.0%
STATEMENT OF VALUES — SUMMARY
| Original Contract | 3119000
| Net Change Orders | -260659
| Final Contract | 2858341
| Retainage Held | 142517
| Net Paid to OWP | 2715824

## Insights
[CORTEX_V2.1] Job #2020 — · Insights
Schema CORTEX_V2.1 · canonical v2 builder · single source of truth
| # | Theme | Insight | verified | source
| 1 | MARGIN PROFILE | Net profit of $923,838 on $2,858,341 revenue = 32.3% gross margin. Direct cost $1,934,503 absorbs 67.7% of revenue.
| 2 | VENDOR CONCENTRATION | Ferguson Enterprises, Inc. alone = $216,177 (27% of all AP) across 121 invoices. Total 21 AP vendors, $792,735 total AP spend.
| 3 | CREW PROFILE | 57 workers for 38,749 hours = 680 avg hrs/worker. Top 3 workers logged 8,366 hrs combined (22% of all labor).
| 4 | ROUGHIN DOMINANCE | Code 120 Roughin Labor = 18,980 hrs (49% of all labor) and $348,603 actual. Code 230 Finish Material = $411,992 — 21% of total direct cost.
| 5 | BUDGET DELIVERY | Revised budget was $1,919,609; actual direct cost $1,934,503 → $-14,894 variance (-0.8% under revised budget).
| 6 | CONTRACT GROWTH | Contract grew from $3,119,000 to $2,858,341 — net +$-260,659 (-8.4%). Retainage of $142,517 (5%) withheld until closeout.
| 7 | BURDEN RATIO | Burden codes 995 + 998 = $398,612 on $766,929 labor base = 52.0%. In line with OWP's typical 48–50% labor burden.
| 8 | PROJECT SCALE | 288 units · 1564 fixtures · 22 months. Revenue/unit $9,925, hours/unit 134.5, profit/unit $3,208.
| 9 | PRODUCTIVITY | Blended labor rate $19.79/hr. Revenue/hour $74. Profit/hour $24. 1,761 hrs/month burn rate.
| 10 | FIXTURE DENSITY | 1564 fixtures ÷ 288 units = 5.43 fixtures/unit. Material/fixture $470, labor/fixture $490.

## Benchmark KPIs
[CORTEX_V2.1] Job #2020 — · Benchmark KPIs
Schema CORTEX_V2.1 · canonical v2 builder · single source of truth
CROSS-PROJECT BENCHMARK SCORECARD
Normalized metrics designed for apples-to-apples comparison across all OWP projects.
| KPI | DATA NAME | VALUE | CATEGORY | NOTES / BENCHMARK CONTEXT
| Job Number | job_number | 2,020 | Profile | OWP Sage job ID
| General Contractor | general_contractor | SRM Development / Exxel Pacific (Owner: Bellevue Way Ventures) | Profile | Customer of record
| location | location | Bellevue, WA (15 Bellevue Way SE) | Profile | Project address
| Project Type | project_type | Apartment building | Profile | Building category for benchmarking
| Duration Months | duration_months | 22 | Profile | Calendar months from start to close
| Plumbing Units | plumbing_units | 288 | Profile | Residential units delivered
| Contract Original | contract_original | $3,119,000 | Financial | Original contract value
| Contract Final | contract_final | $2,858,341 | Financial | Revised contract value (post-COs)
| Change Orders Net | change_orders_net | $-260,659 | Financial | Net dollar change from COs
| revenue | revenue | $2,852,263 | Financial | Net billed (AR net of reversals)
| Net Profit | net_profit | $860,178 | Financial | Revenue − direct cost
| Gross Margin Pct | gross_margin_pct | 30.2% | Financial | Net profit / revenue
| Direct Cost | direct_cost | $1,992,085 | Financial | Σ labor + material + OH + burden + tax
| Overhead Cost | overhead_cost | $50,025 | Financial | Codes 600, 601, 603, 607
| Burden Cost | burden_cost | $398,612 | Financial | Code 995 payroll burden
| Retainage Outstanding | retainage_outstanding | $142,917.05 | Financial | Held by GC until closeout
| Revenue Per Unit | revenue_per_unit | $9,904 | Financial | Top-line per unit
| Profit Per Unit | profit_per_unit | $2,987 | Financial | Net profit normalized per residential unit
| Cost Per Unit | cost_per_unit | $6,917 | Financial | Total direct cost per unit
| Labor Cost | labor_cost | $780,619 | Labor | Codes 100–150
| Total Hours | total_hours | 39,280 | Labor | All payroll hours on the job
| Total Workers | total_workers | 58 | Crew | Unique payroll IDs across job
| Straight-Time Rate | blended_wage | $19.59 | Labor | Pre-burden average
| Fully Loaded Wage | fully_loaded_wage | $40.25 | Labor | Post-burden true cost
| Burden Multiplier | burden_multiplier | 1.34x | Labor | Loaded / gross
| Hours Per Unit | hours_per_unit | 136.4 | Labor | Key plumbing benchmark
| Labor Per Unit | labor_per_unit | $2,710 | Labor | Payroll only, not material
| Labor Pct Revenue | labor_pct_revenue | 27.4% | Cost Mix | Payroll exposure
| Material Cost | material_cost | $762,828 | Material | Codes 210–244
| Material Per Unit | material_per_unit | $2,649 | Material | Cross-project benchmark
| Material Pct Revenue | material_pct_revenue | 26.7% | Cost Mix | Material/sub exposure
| Total Vendors | total_vendors | 22 | Material | Distinct AP vendors invoiced on the job
| Top Vendor Spend | top_vendor_spend | $0.00 | Material | Largest single supplier
| Top Vendor Pct | top_vendor_pct | 0.0% | Material | Top vendor concentration
| Revenue Per Month | revenue_per_month | $129,648 | Throughput | Billing velocity
| Hours Per Month | hours_per_month | 1,785 | Throughput | Avg monthly labor burn
| Units Per Month | units_per_month | 13.1 | Throughput | Build pace
SOURCES
Canonical: /sessions/keen-determined-mccarthy/mnt/cortex-mockup/owp/cortex v2 files/OWP_2020_JCR_Cortex_v2.xlsx
revenue: AR net-of-reversals (validator)
labor_cost: Codes 100–150
material_cost: Codes 210–244
total_workers: count(distinct worker_id)

## Change Log
[CORTEX_V2.1] Job #2020 — · Change Log
Schema CORTEX_V2.1 · canonical v2 builder · single source of truth
| Event ID | Type | Date | Subject | Originator | Cost Impact ($)
| CO-003-UNEXEC | COR | 2014-10-07 | CR #1092 Upgrade plumbing fixture package to match 101 Taylor (UNEXECUTED) | Owner (SRM) | 37931
| CO-004 | CO | 2014-11-14 | CR #1102 Undercounter vanity sinks — Kohler K2214 Ladena Type A/B | Owner (SRM) | 31418
| CO-005-UNEXEC | COR | 2014-12-02 | CR #1106 Water cooler upgrades (Elkay LZSTL8WSS3K, LZS8WSS2K) — UNEXECUTED | Owner (SRM) | 5085
| CO-006 | CO | 2015-01-19 | CR #1121 Misc plumbing revisions — 9 planter drains, sports lounge, mop sinks, drains, grease interceptor, RPBA, hose bi | Owner (SRM) | 4756
| CO-007 | CO | 2015-09-23 | CR #1235 Eyewash station w/ mixing valve @ Maintenance Shop | Owner (SRM) | 2852
| CO-008 | CO | 2015-10-26 | CR #1253 Hose bibbs (courtyard + decks) + 3 BBQ sinks + 1-1/4" gas to Whisk retail | Owner (SRM) | 22671
| CO-009 | CO | 2015-11-23 | CR #1277 Theater sink + relocate ice maker boxes L4-5 + courtyard water feature piping + CBV consolidation | Owner (SRM) | 9131
| CO-010 | CO | 2016-01-18 | CR #1305 Attic stock + ADA toilet flange relocations units 327/331/231/450/461 | Owner (SRM) / Todd Rankin | 4210
| CO-011 | CO | 2016-02-25 | CR #1361 Barber waste extension + vanity sink replacements (trade damage) + condensate drains + retail/gas deduct meters | Owner (SRM) | 15963
| CO-012 | Backcharge | 2016-03-11 | CR #1396 Water damage repair — OWP uncapped pipe (CREDIT) | GC | -6655
| DOC-GAP-CO-1-2 | Memo | 2014 | GAP: CO #1 and CO #2 not found in any extracted folder; may exist in archived OLD DROPBOX FILES subdirectories. | OWP | 0
| DOC-GAP-RESUB | Memo | 2014-2016 | GAP: 206+ submittal documents but no formal resubmission log; tracked only by ORIGINAL/RESPONSE folder structure. | OWP | 0
| RFI-SUMMARY | Memo | 2014-2016 | 56 RFIs in primary folder (duplicates across 4 extracted instances totaling 282 occurrences). RFI range #027-#258. Focus | GC | 0
CHANGE-EVENT META
| Total events | 13
| Net cost impact ($) | 127362
| CO count | 7
| COR count | 2
| Backcharge count | 1
| Memo / gap entries | 3

## Root Cause Analysis
[CORTEX_V2.1] Job #2020 — · Root Cause Analysis
Schema CORTEX_V2.1 · canonical v2 builder · single source of truth
ROOT CAUSE CATEGORIES
| Cause | Event Count | Cost Impact ($) | Primary Owner
| Design substitution | 2 | 69349 | Designer
| Design clarification | 5 | 20949 | Designer
| Owner directive | 2 | 27756 | Owner/GC
| Cleanup/damage | 1 | -6655 | Sub (OWP)
| Combined/multi-cause | 3 | 15963 | Mixed
RESPONSIBILITY MATRIX
| Party | Event Count | Net Cost Impact ($)
| Designer | 7 | 90298
| Mixed | 3 | 15963
| Owner/GC | 2 | 27756
| Sub (OWP) | 1 | -6655

## Predictive Signals
[CORTEX_V2.1] Job #2020 — · Predictive Signals
Schema CORTEX_V2.1 · canonical v2 builder · single source of truth
| # | Signal | Current Value | Threshold | Severity
| 1 | RFI Total (closed) | 56 | <50 for mid-size | INFO
| 2 | RFI Velocity (per month, derived) | See KPIs D50 | <3.0/wk | INFO
| 3 | RFI Avg Cycle Time (days) | Unknown | <14 | N/A
| 4 | ASI / OCD Count | 0 | <5 | HEALTHY
| 5 | Backcharge Count | 1 | <3 | HEALTHY
| 6 | Change Order Count | 9 | <3 | ELEVATED
| 7 | T&M Event Count | 0 | <2 | HEALTHY
| 8 | Submittal resubmission count | 12 | <10 | ELEVATED
| 9 | Net $ Impact (all events) | 127362 | Near $0 | POSITIVE

## Metric Registry
[CORTEX_V2.1] Job #2020 — · Metric Registry
Schema CORTEX_V2.1 · canonical v2 builder · single source of truth
| metric_key | metric_label | value | data_label | tab_home | verification | source
| job_number | Job Number | 2020
| job_name | Job Name | SRM Bellevue @ Main Apartments
| general_contractor | General Contractor | SRM Development / Exxel Pacific (Owner: Bellevue Way Ventures)
| location | Location | Bellevue, WA (15 Bellevue Way SE)
| project_type | Project Type | 6-story 288-unit luxury multifamily + retail
| duration_months | Duration Months | 22
| unit_count | Unit Count | 288
| total_fixtures | Total Fixtures | 1564
| contract_original | Contract Original | 3119000
| contract_final | Contract Final | 2858341
| change_orders_net | Change Orders Net | -260659
| revenue_ar_actual | Revenue Ar Actual | 2852262.93
| net_profit | Net Profit | 860178.11
| gross_margin_pct | Gross Margin Pct | 0.3016
| direct_cost | Direct Cost | 1992084.82
| labor_cost | Labor Cost | 780619.01
| material_cost | Material Cost | 762828.23
| overhead_cost | Overhead Cost | 50025.19
| burden_cost | Burden Cost | 398612.39
| retainage | Retainage | 142917.05
| labor_hours | Labor Hours | 39280
| total_workers | Total Workers | 58
| straight_time_rate | Straight Time Rate | 19.59
| pr_src_cost_per_hr | Pr Src Cost Per Hr | 30.1
| fully_loaded_wage | Fully Loaded Wage | 40.25
| burden_multiplier | Burden Multiplier | 1.337
| total_pos | Total Pos | 279
| executed_co_count | Executed Co Count | 9
| backcharge_count | Backcharge Count | 1
| unexecuted_cor_count | Unexecuted Cor Count | 2
| rfi_count | Rfi Count | 56
| submittal_count | Submittal Count | 206
| change_event_total | Change Event Total | 13
| net_co_dollar_impact | Net Co Dollar Impact | 127362

## Reconciliation
[CORTEX_V2.1] Job #2020 — · Reconciliation
Schema CORTEX_V2.1 · canonical v2 builder · single source of truth
| check_number | check_description | value_a | value_b | difference | status | tabs
A. JDR COST CODE ROLLUP
|  | Labor subtotal (11 codes) | 780619.01 |  |  | TIES
|  | Material subtotal (8 codes) | 762828.23 |  |  | TIES
|  | Overhead subtotal (2 codes) | 50025.19 |  |  | TIES
|  | Burden subtotal (2 codes) | 398612.39 |  |  | TIES
|  | Direct Cost (all categories) | 1992084.82 |  |  | TIES
|  | Revenue (code 999) | 2852262.93 |  |  | WITHIN
|  | Net Profit (Revenue - Expenses) | 860178.11 |  |  | WITHIN
B. LABOR HOURS ROLLUP
|  | JDR Cost Code hours (Payroll Hours lines) | 39280 |  |  | TIES
|  | Per-worker hours (sum of PR Regular) | 39280 |  |  | WITHIN
C. BILLING (SOV) ↔ JDR
|  | Final Contract Value | 2858341 |  |  | TIES
|  | Retainage | 142917.05 |  |  | TIES
|  | Direct Cost | 1992084.82 |  |  | TIES
D. VENDOR AP ↔ JDR
|  | Vendor AP total (sum of invoices) | 792735 |  |  | TIES
SOURCES
Job #2020 — SRM Bellevue @ Main Apartments • GC: Exxel Pacific / Owner: Bellevue Way Ventures • Bellevue, WA
Canonical source: 2020 Job Detail Report.pdf (352 pages, OWP Sage Timberline export)
Cost codes parsed: 24 (Labor+Material+Overhead+Burden+Revenue)
Unit count (288) confirmed by TWO source documents:
1) Bellevue Main – Pricing to go to 101 Taylor Fixtures.xlsx: Type B lavs qty=268, Type A lavs qty=20, Lav faucets qty=288, Bathtub trim qty=288
2) BELLEVUE TRIM QUOTE PRICING organized by category USE.xlsx: Mansfield toilets 268 + 20 ADA = 288
Kitchen fixtures: 257 kitchen faucets (Delta 4353-AR-DST) — 31 fewer than units (studios/amenity)
Contract: One Way Plumbing Executed Contract OCR_D.pdf — Exxel Pacific / SRM Development GC
Billing: 10 archived Schedule of Values files (pay apps #4, 9, 10, 12, 13, 15, 18, 19, 20, 23)
Final contract $2,858,341 after 11 COs (net -$260,659, primarily CO#1 cast iron credit -$389,000)
Permit: City of Bellevue #13-133992-BO (building/plumbing)
TIES = within $1 or 5 hrs • WITHIN = within 5% • OFF = investigate
K. CHANGE LOG ↔ ROOT CAUSE ANALYSIS
|  | Total Event Count | 13 |  |  | TIES
|  | Net $ Impact (all events) | 127362 |  |  | TIES
L. PREDICTIVE SIGNALS ↔ CHANGE LOG
|  | Backcharge Count signal | 1 |  |  | TIES
M. METRIC REGISTRY ↔ BENCHMARK KPIs
|  | revenue (row 17) | 2858341 |  |  | TIES
|  | unit_count (row 12) | 288 |  |  | TIES
|  | total_fixtures (row 13) | 1564 |  |  | TIES
|  | direct_cost (row 19) | 1934503.21 |  |  | OFF
|  | total_pos (row 30) | 279 |  |  | TIES
N. CHANGE LOG ↔ METRIC REGISTRY (event counts)
|  | change_event_total | 13 |  |  | OFF
SOURCES
Job #2020 — Cortex v2 17-tab layout
12 analytical tabs + Change Log + Root Cause Analysis + Predictive Signals + Metric Registry + Reconciliation
Canonical source: 2020 Job Detail Report.pdf (Sage Timberline export)
Change artifacts: folders scanned — ASI-RFI, Change Orders, Submittals, Invoices (Backcharges), JDR cost codes
Every Change Log row cites its source document path
TIES = within $1/5hrs/exact count • WITHIN = within 5% • OFF = investigate
Cross-sheet formulas (='Tab'!Cell) update automatically when source tabs change
Tabs: 1-12 analytical • 13=ChangeLog • 14=RootCause • 15=PredictiveSignals • 16=MetricRegistry • 17=Reconciliation

## Vendors
[CORTEX_V2.1] Job #2020 — · Vendors
Schema CORTEX_V2.1 · canonical v2 builder · single source of truth
| # | Vendor Name | # Invoices | Total Spend ($) | % of AP | Tier | Notes
| 1 | Ferguson Enterprises, Inc. | 121 | 216177 | 27.3% | Top 5 | Largest AP — concentration flag
| 2 | Keller Supply Company | 101 | 204980 | 25.9% | Top 5 | Roughin material supplier
| 3 | Rosen Supply Company | 172 | 188563 | 23.8% | Top 5 | Primary trim/finish supplier
| 4 | Mechanical Sales, Inc. | 4 | 67936 | 8.6% | Top 5
| 5 | Consolidated Supply Co. | 11 | 47820 | 6.0% | Top 5
| 6 | United Rentals, Inc. | 40 | 23301 | 2.9% | Top 10 | Equipment rental
| 7 | Quality Concrete Products, Inc. | 5 | 15202 | 1.9% | Top 10 | Concrete cutting/coring
| 8 | Scan2Core, Inc. | 13 | 8585 | 1.1% | Top 10
| 9 | MAD Concrete Cutting & Coring, Inc. | 5 | 4605 | 0.6% | Top 10 | Concrete cutting/coring
| 10 | Kele, Inc | 6 | 3172 | 0.4% | Top 10
| 11 | C.M. Hoskins Company | 5 | 2334 | 0.3% | Long tail
| 12 | Rosen Supply Kirkland | 8 | 2332 | 0.3% | Long tail | Primary trim/finish supplier
| 13 | Capital One Credit Card | 16 | 2041 | 0.3% | Long tail
| 14 | Shirley Dennison | 17 | 1700 | 0.2% | Long tail
| 15 | Seton Identification Products | 3 | 1302 | 0.2% | Long tail
| 16 | American Express 3-41000 | 1 | 945 | 0.1% | Long tail
| 17 | NRP-Meydenbauer | 4 | 474 | 0.1% | Long tail
| 18 | Ferguson Enterprises, Inc. #3007 | 2 | 458 | 0.1% | Long tail | Roughin + finish dual-source
| 19 | Fastenal Company | 5 | 456 | 0.1% | Long tail
| 20 | A.R. Brown Backflow Testing | 3 | 304 | 0.0% | Long tail
| 21 | Rosen Supply Company, Inc. | 3 | 47 | 0.0% | Long tail | Primary trim/finish supplier
| TOTAL | 21 vendors | 545 | 792734 | 100.0%