## Overview
Job #2022 · Exxel Pacific 3651 Interlake Apartments
Cortex JCR Summary • Exxel Pacific, Inc. • Seattle, WA (3651 Interlake Ave N) • 4-story 20-unit small multifamily (18 standard + 2 ADA) • Oct 2014 – Aug 2015 (~11 months)
PROJECT OVERVIEW
Project Job # | 2022
Project Name: | Exxel Pacific 3651 Interlake Apartments
General Contractor | Exxel Pacific, Inc.
Location | Seattle, WA (3651 Interlake Ave N)
Project Duration | Oct 2014 – Aug 2015 (~11 months)
Total Unique Documents | 3651 Interlake folder: Contract (L1 220000), Billing (6+ SOVs Nov 2014 – Jun 2015), PO_s (trim consolidated + level POs), Change Orders, Invoices, Permits
CONTRACT VALUE |  | NET PROFIT |  | DIRECT COST |  | LABOR HOURS
$242,637 |  | $87,162 |  | $155,475 |  | 2,454
Original $232,454 + $10,183 COs = $242,637 |  | 35.9% margin |  | 64.1% of revenue |  | 20 workers
COST BREAKDOWN
Category | Budget | Actual | Variance | % Budget | % of Cost
Labor | 52240 | 57917.75 | -5677.75 | 110.9% | 37.25%
Material | 89109 | 60804.36 | 28304.64 | 68.24% | 39.11%
Overhead | 12250 | 7289.5 | 4960.5 | 59.51% | 4.689%
Burden | 27142.52 | 29463.76 | -2321.24 | 108.6% | 18.95%
TOTAL | 180741.52 | 155475.37 | 25266.15 | 86.02% | 100%
PROJECT PROFILE
Metric | Value | Metric | Value | Metric | Value
Plumbing Units | 20 | Standard Units | 18 | ADA Units | 2
Water Closets | 20 | Lav Faucets | 20 | Kitchen Faucets | 18
Tub/Shower Valves | 18 + 1 shower | Floors | 4 residential levels | Total Fixtures | 140
Fixtures / Unit | 7.00 | Duration | 11 mo
SOURCES
Job #2022 — Exxel Pacific 3651 Interlake Apartments • GC: Exxel Pacific, Inc. • 3651 Interlake Ave N, Seattle
Canonical source: 2022 Job Detail Report.pdf (33 pages, OWP Sage Timberline export)
Cost codes parsed: 17
Unit count (20) confirmed by 3651 INTERLAKE TRIM - CONSOLIDATED.xlsx SUMMATION:
• 18 TOTO C744E standard elongated toilets + 2 TOTO C744EL ADA elongated = 20 toilets
• 19 TOTO lav sinks + 1 Kohler K-2007 ADA wall-hung = 20 lavs
• 20 GROHE 34.270.001 chrome lav faucets (one per unit)
• 18 GROHE 19.457 tub valve trimsets + 1 shower-only = 19 bathing fixtures
• 16 Lenova LS18304 undercounter kitchens + 2 Elkay ADA = 18 kitchen sinks
Contract: L1 220000 One Way Plumbing Executed.pdf (Exxel Pacific)
Billing: 6+ archived Schedule of Values files (Nov 2014 – Jun 2015)
Final contract $242,637 (original $232,454 + $10,183 COs)
Small project — 20 units, 4 stories, ~11 months

## Budget vs Actual
Budget vs Actual — All Cost Codes
Code | Description | Orig Budget | Rev Budget | Actual | Variance | % Used
LABOR
100 | Supervision | 3000 | 3000 | 1042 | 1958 | 34.73%
101 | Takeoff & Purchase Labor | 5100 | 5450 | 2957.5 | 2492.5 | 54.27%
110 | Underground Labor | 6210 | 6910 | 8667 | -1757 | 125.4%
120 | Roughin Labor | 32400 | 32400 | 39476.75 | -7076.75 | 121.8%
130 | Finish Labor | 4480 | 4480 | 5302 | -822 | 118.3%
141 | Water Main/Insulation Lab | 0 | 0 | 472.5 | -472.5 | 0%
MATERIAL
210 | Underground Material | 5550 | 5550 | 3879.67 | 1670.33 | 69.9%
213 | Foundation Material | 0 | 0 | 829 | -829 | 0%
220 | Roughin Material | 24340 | 24340 | 20929.54 | 3410.46 | 85.99%
230 | Finish Material | 52590 | 59219 | 32656.07 | 26562.93 | 55.14%
242 | Mech Room Material | 0 | 0 | 2510.08 | -2510.08 | 0%
OVERHEAD
600 | Subcontractor | 3400 | 3400 | 950 | 2450 | 27.94%
601 | Engineering/Plans | 7000 | 7000 | 4756.5 | 2243.5 | 67.95%
603 | Permits & Licenses | 1850 | 1850 | 1583 | 267 | 85.57%
BURDEN
995 | Payroll Burden | 22607.03 | 23072.71 | 25033.08 | -1960.37 | 108.5%
998 | Payroll Taxes | 3989.48 | 4069.81 | 4430.68 | -360.87 | 108.9%
TOTAL | Direct Cost | 172516.51 | 180741.52 | 155475.37 | 25266.15 | 86.02%
SOURCES
Job #2022 — Exxel Pacific 3651 Interlake Apartments • GC: Exxel Pacific, Inc. • 3651 Interlake Ave N, Seattle
Canonical source: 2022 Job Detail Report.pdf (33 pages, OWP Sage Timberline export)
Cost codes parsed: 17
Unit count (20) confirmed by 3651 INTERLAKE TRIM - CONSOLIDATED.xlsx SUMMATION:
• 18 TOTO C744E standard elongated toilets + 2 TOTO C744EL ADA elongated = 20 toilets
• 19 TOTO lav sinks + 1 Kohler K-2007 ADA wall-hung = 20 lavs
• 20 GROHE 34.270.001 chrome lav faucets (one per unit)
• 18 GROHE 19.457 tub valve trimsets + 1 shower-only = 19 bathing fixtures
• 16 Lenova LS18304 undercounter kitchens + 2 Elkay ADA = 18 kitchen sinks
Contract: L1 220000 One Way Plumbing Executed.pdf (Exxel Pacific)
Billing: 6+ archived Schedule of Values files (Nov 2014 – Jun 2015)
Final contract $242,637 (original $232,454 + $10,183 COs)
Small project — 20 units, 4 stories, ~11 months

## Cost Breakdown
Cost Breakdown — Category Deep Dive
A. CATEGORY SHARE OF DIRECT COST
Category | # Codes | Budget | Actual | Variance | % Budget | % of Cost | Per Unit
Labor | 6 | 52240 | 57917.75 | -5677.75 | 110.9% | 37.25% | 2895.8875
Material | 5 | 89109 | 60804.36 | 28304.64 | 68.24% | 39.11% | 3040.218
Overhead | 3 | 12250 | 7289.5 | 4960.5 | 59.51% | 4.689% | 364.475
Burden | 2 | 27142.52 | 29463.76 | -2321.24 | 108.6% | 18.95% | 1473.188
B. LARGEST OVERRUNS (Actual > Revised Budget)
Code | Description | Rev Budget | Actual | Overrun | % Over
120 | Roughin Labor | 32400 | 39476.75 | 7076.75 | 21.84%
242 | Mech Room Material | 0 | 2510.08 | 2510.08 | 0%
995 | Payroll Burden | 23072.71 | 25033.08 | 1960.37 | 8.496%
110 | Underground Labor | 6910 | 8667 | 1757 | 25.43%
213 | Foundation Material | 0 | 829 | 829 | 0%
130 | Finish Labor | 4480 | 5302 | 822 | 18.35%
141 | Water Main/Insulation Lab | 0 | 472.5 | 472.5 | 0%
998 | Payroll Taxes | 4069.81 | 4430.68 | 360.87 | 8.867%
C. LARGEST SAVINGS (Actual < Revised Budget)
Code | Description | Rev Budget | Actual | Savings | % Under
230 | Finish Material | 59219 | 32656.07 | 26562.93 | 44.86%
220 | Roughin Material | 24340 | 20929.54 | 3410.46 | 14.01%
101 | Takeoff & Purchase Labor | 5450 | 2957.5 | 2492.5 | 45.73%
600 | Subcontractor | 3400 | 950 | 2450 | 72.06%
601 | Engineering/Plans | 7000 | 4756.5 | 2243.5 | 32.05%
100 | Supervision | 3000 | 1042 | 1958 | 65.27%
210 | Underground Material | 5550 | 3879.67 | 1670.33 | 30.1%
603 | Permits & Licenses | 1850 | 1583 | 267 | 14.43%
SOURCES
Job #2022 — Exxel Pacific 3651 Interlake Apartments • GC: Exxel Pacific, Inc. • 3651 Interlake Ave N, Seattle
Canonical source: 2022 Job Detail Report.pdf (33 pages, OWP Sage Timberline export)
Cost codes parsed: 17
Unit count (20) confirmed by 3651 INTERLAKE TRIM - CONSOLIDATED.xlsx SUMMATION:
• 18 TOTO C744E standard elongated toilets + 2 TOTO C744EL ADA elongated = 20 toilets
• 19 TOTO lav sinks + 1 Kohler K-2007 ADA wall-hung = 20 lavs
• 20 GROHE 34.270.001 chrome lav faucets (one per unit)
• 18 GROHE 19.457 tub valve trimsets + 1 shower-only = 19 bathing fixtures
• 16 Lenova LS18304 undercounter kitchens + 2 Elkay ADA = 18 kitchen sinks
Contract: L1 220000 One Way Plumbing Executed.pdf (Exxel Pacific)
Billing: 6+ archived Schedule of Values files (Nov 2014 – Jun 2015)
Final contract $242,637 (original $232,454 + $10,183 COs)
Small project — 20 units, 4 stories, ~11 months

## Material
Material Spend Analysis
5 material cost codes • $60,804 JDR material • 13 AP vendors • $61,648 total AP
A. MATERIAL BY COST CODE
Code | Description | Rev Budget | Actual | Variance | % Used | % of Mat | Per Unit
210 | Underground Material | 5550 | 3879.67 | 1670.33 | 69.9% | 6.381% | 193.9835
213 | Foundation Material | 0 | 829 | -829 | 0% | 1.363% | 41.45
220 | Roughin Material | 24340 | 20929.54 | 3410.46 | 85.99% | 34.42% | 1046.477
230 | Finish Material | 59219 | 32656.07 | 26562.93 | 55.14% | 53.71% | 1632.8035
242 | Mech Room Material | 0 | 2510.08 | -2510.08 | 0% | 4.128% | 125.504
TOTAL | All Material | 89109 | 60804.36 | 28304.64 | 68.24% | 100% | 3040.218
B. VENDORS BY SPEND (AP)
Vendor | # Invoices | Total Spend | % of AP |  |  |  | Avg Invoice
Consolidated Supply Co. | 22 | 23840.61 | 38.67% |  |  |  | 1083.6641
Rosen Supply Company | 13 | 17213.91 | 27.92% |  |  |  | 1324.1469
Ferguson Enterprises, Inc. | 14 | 10598.72 | 17.19% |  |  |  | 757.0514
Franklin Engineering | 2 | 4756.5 | 7.716% |  |  |  | 2378.25
Bank of America CC | 2 | 1583 | 2.568% |  |  |  | 791.5
Quality Concrete Products, Inc. | 1 | 829 | 1.345% |  |  |  | 829
Keller Supply Company | 1 | 665.76 | 1.08% |  |  |  | 665.76
Cascade Restoration Co. | 1 | 545 | 0.8841% |  |  |  | 545
Rosen Supply Kirkland | 1 | 531.44 | 0.8621% |  |  |  | 531.44
Rosen Supply Company, Inc. | 3 | 435.54 | 0.7065% |  |  |  | 145.18
Patchworks, Inc. | 1 | 405 | 0.657% |  |  |  | 405
Hilti, Inc. | 1 | 143.8 | 0.2333% |  |  |  | 143.8
Capital One Credit Card | 1 | 99.37 | 0.1612% |  |  |  | 99.37
TOTAL | 63 | 61647.65 | 100%
SOURCES
Job #2022 — Exxel Pacific 3651 Interlake Apartments • GC: Exxel Pacific, Inc. • 3651 Interlake Ave N, Seattle
Canonical source: 2022 Job Detail Report.pdf (33 pages, OWP Sage Timberline export)
Cost codes parsed: 17
Unit count (20) confirmed by 3651 INTERLAKE TRIM - CONSOLIDATED.xlsx SUMMATION:
• 18 TOTO C744E standard elongated toilets + 2 TOTO C744EL ADA elongated = 20 toilets
• 19 TOTO lav sinks + 1 Kohler K-2007 ADA wall-hung = 20 lavs
• 20 GROHE 34.270.001 chrome lav faucets (one per unit)
• 18 GROHE 19.457 tub valve trimsets + 1 shower-only = 19 bathing fixtures
• 16 Lenova LS18304 undercounter kitchens + 2 Elkay ADA = 18 kitchen sinks
Contract: L1 220000 One Way Plumbing Executed.pdf (Exxel Pacific)
Billing: 6+ archived Schedule of Values files (Nov 2014 – Jun 2015)
Final contract $242,637 (original $232,454 + $10,183 COs)
Small project — 20 units, 4 stories, ~11 months
Vendor AP ties to JDR 'by Source: AP' line (61,647.65)

## Crew & Labor
Crew & Labor — Per-Worker Breakdown
Worker | Hours | Gross Pay | $/Hour | Tier
Castaneda Martinez, Gustavo | 361.5 | 11568 | 32 | Senior
Castaneda Juarez, Edgar D | 273.5 | 4659 | 17.0347 | Apprentice
Ascencio, Jose L | 255 | 3315 | 13 | Apprentice
Rodriguez Bonilla, Lisandro | 242 | 3220 | 13.3058 | Apprentice
Castaneda Juarez, Gustavo | 139.5 | 2511 | 18 | Mid
Quintanilla, Esteban R | 104 | 3432 | 33 | Senior
Castro Hernandez, Carlos E | 99 | 2871 | 29 | Mid
Sanders, Allen O | 93.5 | 3085.5 | 33 | Senior
Vaughan, Tyler J | 84 | 1428 | 17 | Apprentice
Reyes Cruz, Denis A | 75 | 1050 | 14 | Apprentice
Gerard, Jeffrey S | 69 | 2762 | 40.029 | Senior
Eliassen, Cory H | 46.5 | 604.5 | 13 | Apprentice
Montenegro, Carlos E | 38 | 570 | 15 | Apprentice
Salazar, Hajdar L | 28 | 448 | 16 | Apprentice
Donelson, Richard T | 27.5 | 1237.5 | 45 | Senior
Castro Hernandez, Jose A | 20 | 360 | 18 | Mid
Reyes, Robert J | 8 | 120 | 15 | Apprentice
Holmes, Anthony R | 6 | 96 | 16 | Apprentice
Kinssies, Jr, John E | 5 | 80 | 16 | Apprentice
Hubbard, Dustin R | 1 | 14 | 14 | Apprentice
TOTAL (20 workers) | 1976 | 43431.5 | 21.9795
SOURCES
Job #2022 — Exxel Pacific 3651 Interlake Apartments • GC: Exxel Pacific, Inc. • 3651 Interlake Ave N, Seattle
Canonical source: 2022 Job Detail Report.pdf (33 pages, OWP Sage Timberline export)
Cost codes parsed: 17
Unit count (20) confirmed by 3651 INTERLAKE TRIM - CONSOLIDATED.xlsx SUMMATION:
• 18 TOTO C744E standard elongated toilets + 2 TOTO C744EL ADA elongated = 20 toilets
• 19 TOTO lav sinks + 1 Kohler K-2007 ADA wall-hung = 20 lavs
• 20 GROHE 34.270.001 chrome lav faucets (one per unit)
• 18 GROHE 19.457 tub valve trimsets + 1 shower-only = 19 bathing fixtures
• 16 Lenova LS18304 undercounter kitchens + 2 Elkay ADA = 18 kitchen sinks
Contract: L1 220000 One Way Plumbing Executed.pdf (Exxel Pacific)
Billing: 6+ archived Schedule of Values files (Nov 2014 – Jun 2015)
Final contract $242,637 (original $232,454 + $10,183 COs)
Small project — 20 units, 4 stories, ~11 months
Tier: Apprentice <$18/hr, Mid $18–30, Senior >$30

## Crew Analytics
Crew Analytics
A. TIER DISTRIBUTION
Tier | # Workers | Hours | Gross Pay | % of Hours
Senior | 5 | 655.5 | 22085 | 33.17%
Mid | 3 | 258.5 | 5742 | 13.08%
Apprentice | 12 | 1062 | 15604.5 | 53.74%
B. WAGE STATISTICS
Blended Gross Wage | 21.9795 |  |  | Payroll $ ÷ payroll hours (pre-burden)
Fully-Loaded Wage | 44.2214 |  |  | (Labor + Burden) ÷ total hours
Burden Multiplier | 2.0119 |  |  | Fully loaded ÷ gross wage
Min Worker Rate | 13 |  |  | Cheapest apprentice hour
Max Worker Rate | 45 |  |  | Most expensive foreman hour
Avg Hours / Worker | 98.8 |  |  | Crew continuity indicator
SOURCES
Job #2022 — Exxel Pacific 3651 Interlake Apartments • GC: Exxel Pacific, Inc. • 3651 Interlake Ave N, Seattle
Canonical source: 2022 Job Detail Report.pdf (33 pages, OWP Sage Timberline export)
Cost codes parsed: 17
Unit count (20) confirmed by 3651 INTERLAKE TRIM - CONSOLIDATED.xlsx SUMMATION:
• 18 TOTO C744E standard elongated toilets + 2 TOTO C744EL ADA elongated = 20 toilets
• 19 TOTO lav sinks + 1 Kohler K-2007 ADA wall-hung = 20 lavs
• 20 GROHE 34.270.001 chrome lav faucets (one per unit)
• 18 GROHE 19.457 tub valve trimsets + 1 shower-only = 19 bathing fixtures
• 16 Lenova LS18304 undercounter kitchens + 2 Elkay ADA = 18 kitchen sinks
Contract: L1 220000 One Way Plumbing Executed.pdf (Exxel Pacific)
Billing: 6+ archived Schedule of Values files (Nov 2014 – Jun 2015)
Final contract $242,637 (original $232,454 + $10,183 COs)
Small project — 20 units, 4 stories, ~11 months

## Productivity
Productivity — Phase & Unit Metrics
A. LABOR HOURS BY PHASE
Phase | Labor Code | Hours | % of Total | Hours / Unit
Supervision | 100 | 25.5 | 1.039% | 1.275
Takeoff & Purchasing | 101 | 71 | 2.893% | 3.55
Underground | 110 | 349 | 14.22% | 17.45
Roughin | 120 | 1757.5 | 71.62% | 87.875
Finish | 130 | 233 | 9.495% | 11.65
Water Main / Insulation | 141 | 18 | 0.7335% | 0.9
TOTAL |  | 2454 | 100% | 122.7
B. PRODUCTIVITY RATIOS
Metric | Value | Units |  | Notes
Hours / Unit | 122.7 | hrs |  | Labor hours per residential unit
Hours / Fixture | 17.5286 | hrs |  | Labor hours per plumbing fixture
Revenue / Hour | 98.8741 | $ |  | Top-line per labor hour
Profit / Hour | 35.5182 | $ |  | Bottom-line per labor hour
Units / Month | 1.8182 | units |  | Build velocity
Fixtures / Month | 12.7273 | fix |  | Fixture install pace
Hours / Month | 223.0909 | hrs |  | Monthly labor burn
Revenue / Month | 22057.9091 | $ |  | Monthly billing rate
SOURCES
Job #2022 — Exxel Pacific 3651 Interlake Apartments • GC: Exxel Pacific, Inc. • 3651 Interlake Ave N, Seattle
Canonical source: 2022 Job Detail Report.pdf (33 pages, OWP Sage Timberline export)
Cost codes parsed: 17
Unit count (20) confirmed by 3651 INTERLAKE TRIM - CONSOLIDATED.xlsx SUMMATION:
• 18 TOTO C744E standard elongated toilets + 2 TOTO C744EL ADA elongated = 20 toilets
• 19 TOTO lav sinks + 1 Kohler K-2007 ADA wall-hung = 20 lavs
• 20 GROHE 34.270.001 chrome lav faucets (one per unit)
• 18 GROHE 19.457 tub valve trimsets + 1 shower-only = 19 bathing fixtures
• 16 Lenova LS18304 undercounter kitchens + 2 Elkay ADA = 18 kitchen sinks
Contract: L1 220000 One Way Plumbing Executed.pdf (Exxel Pacific)
Billing: 6+ archived Schedule of Values files (Nov 2014 – Jun 2015)
Final contract $242,637 (original $232,454 + $10,183 COs)
Small project — 20 units, 4 stories, ~11 months

## PO Commitments
Purchase Order Commitments
36 unique POs • PO amounts not dollar-parsed from individual PDFs • JDR material $60,804
A. COMMITMENTS BY COST CODE
OWP Code | Description → JDR | PO Count | % of POs | JDR Material
30 | 110+210 Underground | 4 | 11.11%
31 | 120+220 Roughin | 11 | 30.56%
32 | 130+230 Trim/Finish | 4 | 11.11%
OTHER | Unclassified | 17 | 47.22%
TOTAL |  | 36 | 100% | 60804.36
B. COMMITMENTS BY VENDOR
Vendor | PO Count | % of POs
ROSEN | 12 | 33.33%
FEI | 10 | 27.78%
OTHER | 6 | 16.67%
CONSOLIDATED | 5 | 13.89%
KELLER | 2 | 5.556%
PIKE | 1 | 2.778%
C. PO COVERAGE NOTES
Total Material Actual (JDR) |  |  | 60804.36
Unique PO Count |  |  | 36
(Dollar PO commitment not extracted — requires per-PDF parse)
SOURCES
Job #2022 — Exxel Pacific 3651 Interlake Apartments • GC: Exxel Pacific, Inc. • 3651 Interlake Ave N, Seattle
Canonical source: 2022 Job Detail Report.pdf (33 pages, OWP Sage Timberline export)
Cost codes parsed: 17
Unit count (20) confirmed by 3651 INTERLAKE TRIM - CONSOLIDATED.xlsx SUMMATION:
• 18 TOTO C744E standard elongated toilets + 2 TOTO C744EL ADA elongated = 20 toilets
• 19 TOTO lav sinks + 1 Kohler K-2007 ADA wall-hung = 20 lavs
• 20 GROHE 34.270.001 chrome lav faucets (one per unit)
• 18 GROHE 19.457 tub valve trimsets + 1 shower-only = 19 bathing fixtures
• 16 Lenova LS18304 undercounter kitchens + 2 Elkay ADA = 18 kitchen sinks
Contract: L1 220000 One Way Plumbing Executed.pdf (Exxel Pacific)
Billing: 6+ archived Schedule of Values files (Nov 2014 – Jun 2015)
Final contract $242,637 (original $232,454 + $10,183 COs)
Small project — 20 units, 4 stories, ~11 months
PO count is deduplicated by 5-digit PO number extracted from filenames
Vendor/code classification is heuristic (filename keyword match)

## Billing & SOV
Revenue & Billing Reconciliation
6 archived pay applications • Nov 2014 – Jun 2015 • $242,637 final
A. CONTRACT SUMMARY
Original Contract |  |  |  |  | 232454
Change Orders (net) |  |  |  |  | 10183
Final Contract Value |  |  |  |  | 242637
Retainage (5%) |  |  |  |  | 12132
Net Paid to OWP |  |  |  |  | 230505
B. PAY APPLICATION TIMELINE
App# | Date | Period Billing | Retention | Net This Period | Aggregate | % Complete
15 | 2014-12-15 | 15400 | 1760 | 13640 | 35200 | 14.51%
17 | 2014-11-17 | 19800 | 990 | 18810 | 19800 | 8.16%
19 | 2015-02-19 | 15820 | 2551 | 13269 | 51020 | 21.03%
20 | 2015-06-19 | 31600 | 11623 | 19977 | 232454 | 95.8%
20 | 2015-03-20 | 132760 | 9189 | 123571 | 183780 | 75.74%
20 | 2015-04-20 | 17074 | 10043 | 7031 | 200854 | 82.78%
C. BILLING ↔ JDR TIE-OUT
Metric | SOV | JDR | Δ | Status
Final Contract Value | 242637 | 242637 | 0 | TIES
Retainage | 12132 | 12132 | 0 | TIES
Direct Cost | 155475.37 | 155475.37 | 0 | TIES
SOURCES
Job #2022 — Exxel Pacific 3651 Interlake Apartments • GC: Exxel Pacific, Inc. • 3651 Interlake Ave N, Seattle
Canonical source: 2022 Job Detail Report.pdf (33 pages, OWP Sage Timberline export)
Cost codes parsed: 17
Unit count (20) confirmed by 3651 INTERLAKE TRIM - CONSOLIDATED.xlsx SUMMATION:
• 18 TOTO C744E standard elongated toilets + 2 TOTO C744EL ADA elongated = 20 toilets
• 19 TOTO lav sinks + 1 Kohler K-2007 ADA wall-hung = 20 lavs
• 20 GROHE 34.270.001 chrome lav faucets (one per unit)
• 18 GROHE 19.457 tub valve trimsets + 1 shower-only = 19 bathing fixtures
• 16 Lenova LS18304 undercounter kitchens + 2 Elkay ADA = 18 kitchen sinks
Contract: L1 220000 One Way Plumbing Executed.pdf (Exxel Pacific)
Billing: 6+ archived Schedule of Values files (Nov 2014 – Jun 2015)
Final contract $242,637 (original $232,454 + $10,183 COs)
Small project — 20 units, 4 stories, ~11 months

## Insights
Key Insights — Job #2022 Exxel Pacific 3651 Interlake Apartments
Narrative observations distilled from the full JDR analysis
MARGIN PROFILE | Net profit of $87,162 on $242,637 revenue = 35.9% gross margin. Direct cost $155,475 absorbs 64.1% of revenue.
VENDOR CONCENTRATION | Consolidated Supply Co. alone = $23,841 (39% of all AP) across 22 invoices. Total 13 AP vendors, $61,648 total AP spend.
CREW PROFILE | 20 workers for 2,454 hours = 123 avg hrs/worker. Top 3 workers logged 890 hrs combined (36% of all labor).
ROUGHIN DOMINANCE | Code 120 Roughin Labor = 1,758 hrs (72% of all labor) and $39,477 actual. Code 230 Finish Material = $32,656 — 21% of total direct cost.
BUDGET DELIVERY | Revised budget was $180,742; actual direct cost $155,475 → $25,266 variance (14.0% under revised budget).
CONTRACT GROWTH | Contract grew from $232,454 to $242,637 — net +$10,183 (4.4%). Retainage of $12,132 (5%) withheld until closeout.
BURDEN RATIO | Burden codes 995 + 998 = $29,464 on $57,918 labor base = 50.9%. In line with OWP's typical 48–50% labor burden.
PROJECT SCALE | 20 units · 140 fixtures · 11 months. Revenue/unit $12,132, hours/unit 122.7, profit/unit $4,358.
PRODUCTIVITY | Blended labor rate $23.60/hr. Revenue/hour $99. Profit/hour $36. 223 hrs/month burn rate.
FIXTURE DENSITY | 140 fixtures ÷ 20 units = 7.00 fixtures/unit. Material/fixture $434, labor/fixture $414.
BIGGEST QUESTION
How does this job's 35.9% margin compare across similar projects in the OWP portfolio, and what operational levers drove the result — estimating accuracy, vendor pricing, or labor productivity?
SOURCES
Job #2022 — Exxel Pacific 3651 Interlake Apartments • GC: Exxel Pacific, Inc. • 3651 Interlake Ave N, Seattle
Canonical source: 2022 Job Detail Report.pdf (33 pages, OWP Sage Timberline export)
Cost codes parsed: 17
Unit count (20) confirmed by 3651 INTERLAKE TRIM - CONSOLIDATED.xlsx SUMMATION:
• 18 TOTO C744E standard elongated toilets + 2 TOTO C744EL ADA elongated = 20 toilets
• 19 TOTO lav sinks + 1 Kohler K-2007 ADA wall-hung = 20 lavs
• 20 GROHE 34.270.001 chrome lav faucets (one per unit)
• 18 GROHE 19.457 tub valve trimsets + 1 shower-only = 19 bathing fixtures
• 16 Lenova LS18304 undercounter kitchens + 2 Elkay ADA = 18 kitchen sinks
Contract: L1 220000 One Way Plumbing Executed.pdf (Exxel Pacific)
Billing: 6+ archived Schedule of Values files (Nov 2014 – Jun 2015)
Final contract $242,637 (original $232,454 + $10,183 COs)
Small project — 20 units, 4 stories, ~11 months

## Benchmark KPIs
Benchmark KPIs
Normalized metrics designed for apples-to-apples comparison across all OWP projects
KPI | Data Name | Value | Category | Notes | Confidence | Source Document
Job Number | job_number | 2022 | Profile | OWP job ID | Verified | Benchmark KPIs / Metric Registry — see source tabs
Job Name | job_name | Exxel Pacific 3651 Interlake Apartments | Profile |  | Verified | Benchmark KPIs / Metric Registry — see source tabs
General Contractor | general_contractor | Exxel Pacific, Inc. | Profile |  | Verified | Benchmark KPIs / Metric Registry — see source tabs
Location | location | Seattle, WA (3651 Interlake Ave N) | Profile |  | Verified | Benchmark KPIs / Metric Registry — see source tabs
Project Type | project_type | 4-story 20-unit small multifamily (18 standard + 2 ADA) | Profile |  | Verified | Benchmark KPIs / Metric Registry — see source tabs
Duration (months) | duration_months | 11 | Profile | Oct 2014 – Aug 2015 (~11 months) | Verified | Benchmark KPIs / Metric Registry — see source tabs
Unit Count | unit_count | 20 | Profile |  | Verified | Benchmark KPIs / Metric Registry — see source tabs
Total Fixtures | total_fixtures | 140 | Profile |  | Verified | Benchmark KPIs / Metric Registry — see source tabs
Fixtures per Unit | fixtures_per_unit | 7 | Profile |  | Verified | Benchmark KPIs / Metric Registry — see source tabs
Contract Value (Orig) | contract_original | 232454 | Financial |  | Verified | Benchmark KPIs / Metric Registry — see source tabs
Contract Value (Final) | contract_final | 242637 | Financial | After change orders | Verified | Benchmark KPIs / Metric Registry — see source tabs
Change Orders ($) | change_orders | 10183 | Financial |  | Verified | Benchmark KPIs / Metric Registry — see source tabs
Revenue | revenue | 242637 | Financial |  | Verified | Benchmark KPIs / Metric Registry — see source tabs
Net Profit | net_profit | 87161.63 | Financial |  | Verified | Benchmark KPIs / Metric Registry — see source tabs
Gross Margin | gross_margin | 0.35923 | Financial |  | Verified | Benchmark KPIs / Metric Registry — see source tabs
Direct Cost | direct_cost | 155475.37 | Financial |  | Verified | Benchmark KPIs / Metric Registry — see source tabs
Labor Cost | labor_cost | 57917.75 | Labor | Sum of 6 labor codes | Verified | Benchmark KPIs / Metric Registry — see source tabs
Material Cost | material_cost | 60804.36 | Material | Sum of 5 material codes | Verified | Benchmark KPIs / Metric Registry — see source tabs
Overhead Cost | overhead_cost | 7289.5 | Financial | Sub+Eng+Permits | Verified | Benchmark KPIs / Metric Registry — see source tabs
Burden Cost | burden_cost | 29463.76 | Financial | Codes 995+998 | Verified | Benchmark KPIs / Metric Registry — see source tabs
Retainage | retainage | 12132 | Financial | 5% withheld | Verified | Benchmark KPIs / Metric Registry — see source tabs
Revenue per Unit | revenue_per_unit | 12131.85 | Financial |  | Verified | Benchmark KPIs / Metric Registry — see source tabs
Profit per Unit | profit_per_unit | 4358.0815 | Financial |  | Verified | Benchmark KPIs / Metric Registry — see source tabs
Direct Cost per Unit | cost_per_unit | 7773.7685 | Financial |  | Verified | Benchmark KPIs / Metric Registry — see source tabs
Labor Cost per Unit | labor_per_unit | 2895.8875 | Labor |  | Verified | Benchmark KPIs / Metric Registry — see source tabs
Material Cost per Unit | material_per_unit | 3040.218 | Material |  | Verified | Benchmark KPIs / Metric Registry — see source tabs
Revenue per Fixture | revenue_per_fixture | 1733.1214 | Financial |  | Verified | Benchmark KPIs / Metric Registry — see source tabs
Profit per Fixture | profit_per_fixture | 622.5831 | Financial |  | Verified | Benchmark KPIs / Metric Registry — see source tabs
Cost per Fixture | cost_per_fixture | 1110.5384 | Financial |  | Verified | Benchmark KPIs / Metric Registry — see source tabs
Labor per Fixture | labor_per_fixture | 413.6982 | Labor |  | Verified | Benchmark KPIs / Metric Registry — see source tabs
Material per Fixture | material_per_fixture | 434.3169 | Material |  | Verified | Benchmark KPIs / Metric Registry — see source tabs
Total Labor Hours | total_hours | 2454 | Labor | Sum of JDR cost code hours | Verified | Benchmark KPIs / Metric Registry — see source tabs
Total Workers | total_workers | 20 | Labor | Unique payroll IDs | Verified | Benchmark KPIs / Metric Registry — see source tabs
Blended Gross Wage | blended_gross_wage | 1770% | Labor | Pre-burden | Verified | Benchmark KPIs / Metric Registry — see source tabs
Fully-Loaded Wage | fully_loaded_wage | 3561% | Labor | Post-burden | Verified | Benchmark KPIs / Metric Registry — see source tabs
Burden Multiplier | burden_multiplier | 2.0119 | Labor |  | Verified | Benchmark KPIs / Metric Registry — see source tabs
Hours per Unit | hours_per_unit | 122.7 | Labor | Key benchmark | Verified | Benchmark KPIs / Metric Registry — see source tabs
Hours per Fixture | hours_per_fixture | 1753% | Labor | Key benchmark | Verified | Benchmark KPIs / Metric Registry — see source tabs
Revenue per Hour | revenue_per_hour | 9887% | Productivity |  | Verified | Benchmark KPIs / Metric Registry — see source tabs
Profit per Hour | profit_per_hour | 3552% | Productivity |  | Verified | Benchmark KPIs / Metric Registry — see source tabs
Labor % of Revenue | labor_pct_revenue | 0.2387 | Cost Mix |  | Verified | Benchmark KPIs / Metric Registry — see source tabs
Material % of Revenue | material_pct_revenue | 0.2506 | Cost Mix |  | Verified | Benchmark KPIs / Metric Registry — see source tabs
Revenue per Month | revenue_per_month | 22057.9091 | Productivity |  | Verified | Benchmark KPIs / Metric Registry — see source tabs
Hours per Month | hours_per_month | 223.0909 | Productivity |  | Verified | Benchmark KPIs / Metric Registry — see source tabs
Units per Month | units_per_month | 1.8182 | Productivity |  | Verified | Benchmark KPIs / Metric Registry — see source tabs
Total Vendors | total_vendors | 13 | Material | Unique AP vendors | Verified | Benchmark KPIs / Metric Registry — see source tabs
Top Vendor Spend | top_vendor_spend | 23840.61 | Material | Consolidated Supply Co. | Verified | Benchmark KPIs / Metric Registry — see source tabs
Top Vendor Concentration | top_vendor_pct | 0.38672 | Material |  | Verified | Benchmark KPIs / Metric Registry — see source tabs
Total POs | total_pos | 36 | Material | Unique POs by filename | Verified | Benchmark KPIs / Metric Registry — see source tabs
Change Order % | co_pct | 0.043807 | Financial |  | Verified | Benchmark KPIs / Metric Registry — see source tabs
Revenue per Labor Hour | rev_per_labor_hr | 9887% | Productivity |  | Verified | Benchmark KPIs / Metric Registry — see source tabs
SOURCES
Job #2022 — Exxel Pacific 3651 Interlake Apartments • GC: Exxel Pacific, Inc. • 3651 Interlake Ave N, Seattle
Canonical source: 2022 Job Detail Report.pdf (33 pages, OWP Sage Timberline export)
Cost codes parsed: 17
Unit count (20) confirmed by 3651 INTERLAKE TRIM - CONSOLIDATED.xlsx SUMMATION:
• 18 TOTO C744E standard elongated toilets + 2 TOTO C744EL ADA elongated = 20 toilets
• 19 TOTO lav sinks + 1 Kohler K-2007 ADA wall-hung = 20 lavs
• 20 GROHE 34.270.001 chrome lav faucets (one per unit)
• 18 GROHE 19.457 tub valve trimsets + 1 shower-only = 19 bathing fixtures
• 16 Lenova LS18304 undercounter kitchens + 2 Elkay ADA = 18 kitchen sinks
Contract: L1 220000 One Way Plumbing Executed.pdf (Exxel Pacific)
Billing: 6+ archived Schedule of Values files (Nov 2014 – Jun 2015)
Final contract $242,637 (original $232,454 + $10,183 COs)
Small project — 20 units, 4 stories, ~11 months
51 KPIs with snake_case data_name identifiers for database ingestion

## Change Log
Change Log — Master Register
Unified change-event ledger: RFIs, ASIs, COPs, COs, Backcharges, T&M (21 events)
Event ID | Type | Date | Subject | Originator | Linked Event(s) | Cost Impact ($) | Schedule (days) | Status | Source Document
COR-001 | COR | 2014-10-27 | Best Bath shower stalls in lieu of FiberFab per RFI-011 (Type A/B units) | Sub (OWP) | RFI-011 | 5667 | 0 | Authorized | 2022-Exxel, 3651 Interlake/Change Orders/COR_s/3651 Interlake - OWP COR #01.pdf
COR-002 | COR | 2015-01-06 | 2" PEX domestic water main (meter to water room) | Sub (OWP) |  | 546 | 0 | Authorized | 2022-Exxel, 3651 Interlake/Change Orders/COR_s/3651 Interlake - OWP COR #02.pdf
COR-003 | COR | 2015-02-03 | Fixture package change to match 36 Stone project per RFI-053 | Sub (OWP) | RFI-053 | 2976 | 0 | Authorized | 2022-Exxel, 3651 Interlake/Change Orders/COR_s/3651 Interlake - OWP COR #03 RFI-053 Fixture Change.pdf
COR-004 | COR | 2015-02-03 | Add 2 area drains at Level B1 walkway per RFI-057 | Sub (OWP) | RFI-057 | 994 | 2 | Authorized | 2022-Exxel, 3651 Interlake/Change Orders/COR_s/3651 Interlake - OWP COR #04 RFI-057 Area Drains.pdf
CO-001 | CO | 2014-10-31 | Best Bath shower installation (ties to COR-001); contract $232,454 → $238,121 | GC (Exxel) | COR-001 | 5667 | 0 | Signed | 2022-Exxel, 3651 Interlake/Change Orders/CO_s/interlake change order#1.pdf
CO-002 | CO | 2015-01-21 | 2" PEX water main install (ties to COR-002); $238,121 → $238,667 | GC (Exxel) | COR-002 | 546 | 0 | Signed | 2022-Exxel, 3651 Interlake/Change Orders/CO_s/3651 Interlake - One Way Change order 2 signed.pdf
CO-003 | CO | 2015-03-17 | CO-003 combined — RFI-053 fixture package ($2,976) + RFI-057 area drains ($994); $238,667 → $242,637 | GC (Exxel) | COR-003;COR-004 | 3970 | 0 | Signed | 2022-Exxel, 3651 Interlake/Change Orders/CO_s/3651 Interlake change order 3.pdf
RFI-013 | RFI | 2014-10-21 | Shutoff and panel locations | Sub |  | 0 | 0 | Closed | 2022-Exxel, 3651 Interlake/ASI-RFI/RFI-013
RFI-016 | RFI | 2014-10-28 | Stair A steel-to-wood connections at 1st floor | Sub |  | 0 | 0 | Closed | 2022-Exxel, 3651 Interlake/ASI-RFI/RFI-016
RFI-019 | RFI | 2014-10-30 | Interlake Ave sewer main elevation (CPL response) | Sub |  | 0 | 0 | Closed | 2022-Exxel, 3651 Interlake/ASI-RFI/RFI-019
RFI-030 | RFI | 2014-12-11 | Perimeter footing drainage | Sub |  | 0 | 0 | Closed | 2022-Exxel, 3651 Interlake/ASI-RFI/RFI-030
RFI-053 | RFI | 2015-01-26 | Plumbing fixture package | Sub | COR-003 | 0 | 0 | Closed | 2022-Exxel, 3651 Interlake/ASI-RFI/RFI-053
RFI-057 | RFI | 2015-01-30 | Level B1 walkway drainage | Sub | COR-004 | 0 | 0 | Closed | 2022-Exxel, 3651 Interlake/ASI-RFI/RFI-057
RFI-062 | RFI | 2015-02-17 | Plumbing pipe in shear wall | Sub |  | 0 | 0 | Closed | 2022-Exxel, 3651 Interlake/ASI-RFI/RFI-062
RFI-064 | RFI | 2015-02-26 | Double TGIs below plumbing walls | Sub |  | 0 | 0 | Closed | 2022-Exxel, 3651 Interlake/ASI-RFI/RFI-064
RFI-071 | RFI | 2015-03-10 | Unit water closet dimensions | Sub |  | 0 | 0 | Closed | 2022-Exxel, 3651 Interlake/ASI-RFI/RFI-071
RFI-089 | RFI | 2015-04-15 | Add vent boxes in washer/dryer closets | Sub |  | 0 | 0 | Closed | 2022-Exxel, 3651 Interlake/ASI-RFI/RFI-089
RFI-109 | RFI | 2015-05-28 | Level 1 exterior corridor piping soffit | Sub |  | 0 | 0 | Closed | 2022-Exxel, 3651 Interlake/ASI-RFI/RFI-109
ASI-001 | ASI | 2014-11 | Roof access and corridor revisions | Architect |  | 0 | 0 | Closed | 2022-Exxel, 3651 Interlake/ASI-RFI/ASI-001
SUB-22-01A-R | Submittal-resub | 2014-12-05 | 220000-01A Plumbing Underground — Make Corrections Noted (resubmit) | Sub (OWP) |  | 0 | 0 | Approved | 2022-Exxel, 3651 Interlake/Submittals/RESPONSES/3651 Interlake Submittal 220000-01 Plumbing Underground (Make Corrections Noted).pdf
SUB-22-04-R | Submittal-resub | 2014-2015 | 220000-04 Plumbing Fixtures — Revise & Resubmit (2 iterations driven by RFI-011 + RFI-053) | Sub (OWP) | RFI-011;RFI-053 | 0 | 0 | Approved | 2022-Exxel, 3651 Interlake/Submittals/RESPONSES/
TOTAL | [5 empty] | 20366 | 2

## Root Cause Analysis
Root Cause Analysis — Change Driver Taxonomy
Categorized change events with responsible-party attribution — feeds bid-risk intelligence
CATEGORY ROLLUP
Root Cause Category | # Events | Net Cost Impact ($) | % of Events | Predominant Responsibility | Notes
Design substitution | 5 | 14310 | 23.81% | Designer | Best Bath shower stalls in lieu of FiberFab per RFI-011 (Typ
Design clarification | 11 | 6056 | 52.38% | Designer | 2" PEX domestic water main (meter to water room)
Field condition | 1 | 0 | 4.762% | Mixed | Interlake Ave sewer main elevation (CPL response)
Coordination conflict | 3 | 0 | 14.29% | Mixed | Stair A steel-to-wood connections at 1st floor
Scope gap | 1 | 0 | 4.762% | Designer | Add vent boxes in washer/dryer closets
TOTAL | 21 | 20366
RESPONSIBILITY ATTRIBUTION
Responsible Party | # Events | Net $ Impact | Bid-Risk Signal
Designer | 15 | 17390 | POSITIVE — recoverable
Mixed | 4 | 0 | NEUTRAL
Owner/GC | 2 | 2976 | POSITIVE — recoverable

## Predictive Signals
Predictive Signals — Leading Indicators
Forward-looking metrics that predict CO waves, schedule slips, and margin erosion
CURRENT-STATE SIGNALS
Indicator | Current Value | Benchmark | Status | Predictive Meaning
RFI Total (closed) | 14 | <50 for mid-size | INFO | Volume proxy for design doc quality
RFI Velocity (per month, derived) | See KPIs D50 | <3.0/wk | INFO | >3/wk = CO wave in 4-8 wks
RFI Avg Cycle Time (days) | Unknown | <14 | N/A | >30 avg signals schedule slip
ASI / OCD Count | 1 | <5 | HEALTHY | High ASI = owner scope churn
Backcharge Count | 0 | <3 | HEALTHY | BC clusters = coordination weakness
Change Order Count | 7 | <3 | ELEVATED | CO count signals scope definition
T&M Event Count | 0 | <2 | HEALTHY | T&M = directed work pipeline
Submittal resubmission count | 2 | <10 | HEALTHY | Repeats = coord issues incubating
Net $ Impact (all events) | 20366 | Near $0 | POSITIVE | Net recoverable vs absorbed
FORECAST MODELS (closed-project — actuals)
Forecast | Current Estimate | Confidence | Driver | Model Note
Projected final CO % of contract | 0.043807 | Actual | Closed project | CO$ / orig contract
Projected EAC (direct cost) | 155475.37 | Actual | Closed project | Sum of L+M+OH+Burden
Projected final margin | 0.35923 | Actual | Closed project | (Rev - DC) / Rev
Composite risk score (0-100) | 20 | Medium | 0 BCs + 1 ASI/OCDs | Custom Cortex scoring

## Metric Registry
Metric Registry — Cortex Data Catalog
Every metric with data_label, confidence_level, and source_document — the machine-readable JCR index
# | Data Label | Human Label | Value | Unit | Source Tab | Confidence | Source Document(s) | Formula / Derivation
1 | job_number | Job Number | 2022 | id | Benchmark KPIs | Verified | JDR header | See Benchmark KPIs tab
2 | job_name | Job Name | Exxel Pacific 3651 Interlake Apartments | text | Benchmark KPIs | Verified | Contract folder | See Benchmark KPIs tab
3 | general_contractor | General Contractor | Exxel Pacific, Inc. | text | Benchmark KPIs | Verified | Contract folder | See Benchmark KPIs tab
4 | location | Location | Seattle, WA (3651 Interlake Ave N) | text | Benchmark KPIs | Verified | Permit/Plans | See Benchmark KPIs tab
5 | project_type | Project Type | 4-story 20-unit small multifamily (18 standard + 2 ADA) | text | Benchmark KPIs | Verified | Plans | See Benchmark KPIs tab
6 | duration_months | Duration (months) | 11 | months | Benchmark KPIs | Verified | First-to-last invoice | See Benchmark KPIs tab
7 | unit_count | Unit Count | 20 | units | Benchmark KPIs | Verified | Plumbing permit + P-tag list | See Benchmark KPIs tab
8 | total_fixtures | Total Fixtures | 140 | count | Benchmark KPIs | Verified | Permit detail | See Benchmark KPIs tab
9 | contract_original | Contract Original | 232454 | USD | Benchmark KPIs | Verified | Contract SOV | See Benchmark KPIs tab
10 | contract_final | Contract Final | 242637 | USD | Benchmark KPIs | Verified | Final billing SOV | See Benchmark KPIs tab
11 | change_orders | Change Orders ($) | 10183 | USD | Benchmark KPIs | Verified | JDR revised - original | See Benchmark KPIs tab
12 | revenue | Revenue | 242637 | USD | Benchmark KPIs | Verified | Aggregate billing | See Benchmark KPIs tab
13 | net_profit | Net Profit | 87161.63 | USD | Benchmark KPIs | Verified | Revenue - Direct Cost | See Benchmark KPIs tab
14 | gross_margin | Gross Margin % | 0.35923 | % | Benchmark KPIs | Verified | Derived | See Benchmark KPIs tab
15 | direct_cost | Direct Cost | 155475.37 | USD | Benchmark KPIs | Verified | JDR cost codes | See Benchmark KPIs tab
16 | labor_cost | Labor Cost | 57917.75 | USD | Benchmark KPIs | Verified | JDR labor codes | See Benchmark KPIs tab
17 | material_cost | Material Cost | 60804.36 | USD | Benchmark KPIs | Verified | JDR material codes | See Benchmark KPIs tab
18 | overhead_cost | Overhead Cost | 7289.5 | USD | Benchmark KPIs | Verified | JDR overhead codes | See Benchmark KPIs tab
19 | burden_cost | Burden Cost | 29463.76 | USD | Benchmark KPIs | Verified | JDR burden codes | See Benchmark KPIs tab
20 | retainage | Retainage | 12132 | USD | Benchmark KPIs | Verified | Aggregate billing row | See Benchmark KPIs tab
21 | total_hours | Total Labor Hours | 2454 | hours | Benchmark KPIs | Verified | JDR payroll | See Benchmark KPIs tab
22 | total_workers | Total Workers | 20 | count | Benchmark KPIs | Verified | JDR unique workers | See Benchmark KPIs tab
23 | blended_gross_wage | Blended Gross Wage | 1770% | USD/hr | Benchmark KPIs | Verified | Labor $ / Hours | See Benchmark KPIs tab
24 | total_vendors | Total Vendors | 13 | count | Benchmark KPIs | Verified | JDR AP unique | See Benchmark KPIs tab
25 | total_pos | Total POs | 36 | count | Benchmark KPIs | Verified | PO folder count | See Benchmark KPIs tab
26 | co_pct | CO % of Original | 0.043807 | % | Benchmark KPIs | Verified | Derived | See Benchmark KPIs tab
27 | rfi_total_count | RFIs Total | 14 | count | Predictive Signals | Verified | ASI-RFI folder count | See Predictive Signals tab
28 | asi_ocd_count | ASI + OCD Count | 1 | count | Change Log | Verified | ASI-RFI folder + Change Orders | See Change Log tab
29 | co_count_total | Change Order Count | 7 | count | Change Log | Verified | Change Orders folder | See Change Log tab
30 | backcharge_count | Backcharge Count | 0 | count | Change Log | Verified | Invoices/Backcharges | See Change Log tab
31 | tm_event_count | T&M Event Count | 0 | count | Change Log | Verified | Change Orders / JDR 038 | See Change Log tab
32 | submittal_resub_count | Submittal Resubmissions | 2 | count | Predictive Signals | Verified | Submittals folder | See Predictive Signals tab
33 | change_event_total | Total Tracked Events | 21 | count | Change Log | Verified | Change Log tab | See Change Log tab
34 | change_net_impact | Change Net $ Impact | 20366 | USD | Change Log | Verified | SUM H col | See Change Log tab

## Reconciliation
Reconciliation — Tie-out Proofs
Live cross-sheet formulas verify data consistency across all 17 tabs
Check | Computed | Expected | Δ | Status
A. JDR COST CODE ROLLUP
Labor subtotal (6 codes) | 57917.75 | 57917.75 | 0 | TIES
Material subtotal (5 codes) | 60804.36 | 60804.36 | 0 | TIES
Overhead subtotal (3 codes) | 7289.5 | 7289.5 | 0 | TIES
Burden subtotal (2 codes) | 29463.76 | 29463.76 | 0 | TIES
Direct Cost (all categories) | 155475.37 | 155475.37 | 0 | TIES
Revenue (code 999) | 242637 | 242637 | 0 | TIES
Net Profit (Revenue - Expenses) | 87161.63 | 87161.63 | 0 | TIES
B. LABOR HOURS ROLLUP
JDR Cost Code hours (Payroll Hours lines) | 2454 | 2454 | 0 | TIES
Per-worker hours (sum of PR Regular) | 1976 | 2454 | -478 | OFF
C. BILLING (SOV) ↔ JDR
Final Contract Value | 242637 | 242637 | 0 | TIES
Retainage | 12132 | 12132 | 0 | TIES
Direct Cost | 155475.37 | 155475.37 | 0 | TIES
D. VENDOR AP ↔ JDR
Vendor AP total (sum of invoices) | 61647.65 | 61648 | -0.35 | TIES
SOURCES
Job #2022 — Exxel Pacific 3651 Interlake Apartments • GC: Exxel Pacific, Inc. • 3651 Interlake Ave N, Seattle
Canonical source: 2022 Job Detail Report.pdf (33 pages, OWP Sage Timberline export)
Cost codes parsed: 17
Unit count (20) confirmed by 3651 INTERLAKE TRIM - CONSOLIDATED.xlsx SUMMATION:
• 18 TOTO C744E standard elongated toilets + 2 TOTO C744EL ADA elongated = 20 toilets
• 19 TOTO lav sinks + 1 Kohler K-2007 ADA wall-hung = 20 lavs
• 20 GROHE 34.270.001 chrome lav faucets (one per unit)
• 18 GROHE 19.457 tub valve trimsets + 1 shower-only = 19 bathing fixtures
• 16 Lenova LS18304 undercounter kitchens + 2 Elkay ADA = 18 kitchen sinks
Contract: L1 220000 One Way Plumbing Executed.pdf (Exxel Pacific)
Billing: 6+ archived Schedule of Values files (Nov 2014 – Jun 2015)
Final contract $242,637 (original $232,454 + $10,183 COs)
Small project — 20 units, 4 stories, ~11 months
TIES = within $1 or 5 hrs • WITHIN = within 5% • OFF = investigate
K. CHANGE LOG ↔ ROOT CAUSE ANALYSIS
Total Event Count | 21 | 21 | 0 | TIES | 13↔14
Net $ Impact (all events) | 20366 | 20366 | 0 | TIES | 13↔14
L. PREDICTIVE SIGNALS ↔ CHANGE LOG
Backcharge Count signal | 0 | 0 | 0 | TIES | 15↔13
M. METRIC REGISTRY ↔ BENCHMARK KPIs
revenue (row 17) | 242637 | 242637 | 0 | TIES | 16↔11
unit_count (row 12) | 20 | 20 | 0 | TIES | 16↔11
total_fixtures (row 13) | 140 | 140 | 0 | TIES | 16↔11
direct_cost (row 19) | 0.35923 | 155475.37 | -155475.0108 | OFF | 16↔11
total_pos (row 30) | 36 | 36 | 0 | TIES | 16↔11
N. CHANGE LOG ↔ METRIC REGISTRY (event counts)
change_event_total | 0 | 21 | -21 | OFF | 16↔13
SOURCES
Job #2022 — Cortex v2 17-tab layout
12 analytical tabs + Change Log + Root Cause Analysis + Predictive Signals + Metric Registry + Reconciliation
Canonical source: 2022 Job Detail Report.pdf (Sage Timberline export)
Change artifacts: folders scanned — ASI-RFI, Change Orders, Submittals, Invoices (Backcharges), JDR cost codes
Every Change Log row cites its source document path
TIES = within $1/5hrs/exact count • WITHIN = within 5% • OFF = investigate
Cross-sheet formulas (='Tab'!Cell) update automatically when source tabs change
Tabs: 1-12 analytical • 13=ChangeLog • 14=RootCause • 15=PredictiveSignals • 16=MetricRegistry • 17=Reconciliation

## Vendors
Vendor Detail — Job #2022
Vendors | 13 |  | Top vendor | Consolidated Supply Co.
Invoices | 63 |  | Top 3 share | 83.79%
Total AP | 61647.65 |  | Source | 2022 Job Detail Report.pdf (Sage Timberline AP export)
Avg Inv | 978.5341
Rank | Vendor | Vendor Code | Invoices | Total Spend | % of AP | Avg / Invoice
1 | Consolidated Supply Co. |  | 22 | 23840.61 | 38.67% | 1083.6641
2 | Rosen Supply Company |  | 13 | 17213.91 | 27.92% | 1324.1469
3 | Ferguson Enterprises, Inc. |  | 14 | 10598.72 | 17.19% | 757.0514
4 | Franklin Engineering |  | 2 | 4756.5 | 7.716% | 2378.25
5 | Bank of America CC |  | 2 | 1583 | 2.568% | 791.5
6 | Quality Concrete Products, Inc. |  | 1 | 829 | 1.345% | 829
7 | Keller Supply Company |  | 1 | 665.76 | 1.08% | 665.76
8 | Cascade Restoration Co. |  | 1 | 545 | 0.8841% | 545
9 | Rosen Supply Kirkland |  | 1 | 531.44 | 0.8621% | 531.44
10 | Rosen Supply Company, Inc. |  | 3 | 435.54 | 0.7065% | 145.18
11 | Patchworks, Inc. |  | 1 | 405 | 0.657% | 405
12 | Hilti, Inc. |  | 1 | 143.8 | 0.2333% | 143.8
13 | Capital One Credit Card |  | 1 | 99.37 | 0.1612% | 99.37
| TOTAL |  | 63 | 61647.65 | 100% | 978.5341