## Overview
Job #2022 · Exxel Pacific 3651 Interlake Apartments
Cortex JCR Summary • Exxel Pacific, Inc. • Seattle, WA (3651 Interlake Ave N) • 4-story 20-unit small multifamily (18 standard + 2 ADA) • Oct 2014 – Aug 2015 (~11 months)
PROJECT OVERVIEW
Project Job # | 2022
Project Name: | Exxel Pacific 3651 Interlake Apartments
General Contractor | Exxel Pacific, Inc.
Location | Seattle, WA (3651 Interlake Ave N)
Project Duration | Oct 2014 – Aug 2015 (~11 months)
Total Unique Documents | 3651 Interlake folder: Contract (L1 220000), Billing (6+ SOVs Nov 2014 – Jun 2015), PO_s (trim consolidated + level POs), Change Orders, Invoices, Permits
CONTRACT VALUE |  | NET PROFIT |  | DIRECT COST |  | LABOR HOURS
$242,637 |  | $87,162 |  | $155,475 |  | 2,454
Original $232,454 + $10,183 COs = $242,637 |  | 35.9% margin |  | 64.1% of revenue |  | 20 workers
COST BREAKDOWN
Category | Budget | Actual | Variance | % Budget | % of Cost
Labor | 52240 | 57917.75 | -5677.75 | 110.9% | 37.25%
Material | 89109 | 60804.36 | 28304.64 | 68.24% | 39.11%
Overhead | 12250 | 7289.5 | 4960.5 | 59.51% | 4.689%
Burden | 27142.52 | 29463.76 | -2321.24 | 108.6% | 18.95%
TOTAL | 180741.52 | 155475.37 | 25266.15 | 86.02% | 100%
PROJECT PROFILE
Metric | Value | Metric | Value | Metric | Value
Plumbing Units | 20 | Standard Units | 18 | ADA Units | 2
Water Closets | 20 | Lav Faucets | 20 | Kitchen Faucets | 18
Tub/Shower Valves | 18 + 1 shower | Floors | 4 residential levels | Total Fixtures | 140
Fixtures / Unit | 7.00 | Duration | 11 mo
SOURCES
Job #2022 — Exxel Pacific 3651 Interlake Apartments • GC: Exxel Pacific, Inc. • 3651 Interlake Ave N, Seattle
Canonical source: 2022 Job Detail Report.pdf (33 pages, OWP Sage Timberline export)
Cost codes parsed: 17
Unit count (20) confirmed by 3651 INTERLAKE TRIM - CONSOLIDATED.xlsx SUMMATION:
• 18 TOTO C744E standard elongated toilets + 2 TOTO C744EL ADA elongated = 20 toilets
• 19 TOTO lav sinks + 1 Kohler K-2007 ADA wall-hung = 20 lavs
• 20 GROHE 34.270.001 chrome lav faucets (one per unit)
• 18 GROHE 19.457 tub valve trimsets + 1 shower-only = 19 bathing fixtures
• 16 Lenova LS18304 undercounter kitchens + 2 Elkay ADA = 18 kitchen sinks
Contract: L1 220000 One Way Plumbing Executed.pdf (Exxel Pacific)
Billing: 6+ archived Schedule of Values files (Nov 2014 – Jun 2015)
Final contract $242,637 (original $232,454 + $10,183 COs)
Small project — 20 units, 4 stories, ~11 months

## Budget vs Actual
Budget vs Actual — All Cost Codes
Code | Description | Orig Budget | Rev Budget | Actual | Variance | % Used
LABOR
100 | Supervision | 3000 | 3000 | 1042 | 1958 | 34.73%
101 | Takeoff & Purchase Labor | 5100 | 5450 | 2957.5 | 2492.5 | 54.27%
110 | Underground Labor | 6210 | 6910 | 8667 | -1757 | 125.4%
120 | Roughin Labor | 32400 | 32400 | 39476.75 | -7076.75 | 121.8%
130 | Finish Labor | 4480 | 4480 | 5302 | -822 | 118.3%
141 | Water Main/Insulation Lab | 0 | 0 | 472.5 | -472.5 | 0%
MATERIAL
210 | Underground Material | 5550 | 5550 | 3879.67 | 1670.33 | 69.9%
213 | Foundation Material | 0 | 0 | 829 | -829 | 0%
220 | Roughin Material | 24340 | 24340 | 20929.54 | 3410.46 | 85.99%
230 | Finish Material | 52590 | 59219 | 32656.07 | 26562.93 | 55.14%
242 | Mech Room Material | 0 | 0 | 2510.08 | -2510.08 | 0%
OVERHEAD
600 | Subcontractor | 3400 | 3400 | 950 | 2450 | 27.94%
601 | Engineering/Plans | 7000 | 7000 | 4756.5 | 2243.5 | 67.95%
603 | Permits & Licenses | 1850 | 1850 | 1583 | 267 | 85.57%
BURDEN
995 | Payroll Burden | 22607.03 | 23072.71 | 25033.08 | -1960.37 | 108.5%
998 | Payroll Taxes | 3989.48 | 4069.81 | 4430.68 | -360.87 | 108.9%
TOTAL | Direct Cost | 172516.51 | 180741.52 | 155475.37 | 25266.15 | 86.02%
SOURCES
Job #2022 — Exxel Pacific 3651 Interlake Apartments • GC: Exxel Pacific, Inc. • 3651 Interlake Ave N, Seattle
Canonical source: 2022 Job Detail Report.pdf (33 pages, OWP Sage Timberline export)
Cost codes parsed: 17
Unit count (20) confirmed by 3651 INTERLAKE TRIM - CONSOLIDATED.xlsx SUMMATION:
• 18 TOTO C744E standard elongated toilets + 2 TOTO C744EL ADA elongated = 20 toilets
• 19 TOTO lav sinks + 1 Kohler K-2007 ADA wall-hung = 20 lavs
• 20 GROHE 34.270.001 chrome lav faucets (one per unit)
• 18 GROHE 19.457 tub valve trimsets + 1 shower-only = 19 bathing fixtures
• 16 Lenova LS18304 undercounter kitchens + 2 Elkay ADA = 18 kitchen sinks
Contract: L1 220000 One Way Plumbing Executed.pdf (Exxel Pacific)
Billing: 6+ archived Schedule of Values files (Nov 2014 – Jun 2015)
Final contract $242,637 (original $232,454 + $10,183 COs)
Small project — 20 units, 4 stories, ~11 months

## Cost Breakdown
Cost Breakdown — Category Deep Dive
A. CATEGORY SHARE OF DIRECT COST
Category | # Codes | Budget | Actual | Variance | % Budget | % of Cost | Per Unit
Labor | 6 | 52240 | 57917.75 | -5677.75 | 110.9% | 37.25% | 2895.8875
Material | 5 | 89109 | 60804.36 | 28304.64 | 68.24% | 39.11% | 3040.218
Overhead | 3 | 12250 | 7289.5 | 4960.5 | 59.51% | 4.689% | 364.475
Burden | 2 | 27142.52 | 29463.76 | -2321.24 | 108.6% | 18.95% | 1473.188
B. LARGEST OVERRUNS (Actual > Revised Budget)
Code | Description | Rev Budget | Actual | Overrun | % Over
120 | Roughin Labor | 32400 | 39476.75 | 7076.75 | 21.84%
242 | Mech Room Material | 0 | 2510.08 | 2510.08 | 0%
995 | Payroll Burden | 23072.71 | 25033.08 | 1960.37 | 8.496%
110 | Underground Labor | 6910 | 8667 | 1757 | 25.43%
213 | Foundation Material | 0 | 829 | 829 | 0%
130 | Finish Labor | 4480 | 5302 | 822 | 18.35%
141 | Water Main/Insulation Lab | 0 | 472.5 | 472.5 | 0%
998 | Payroll Taxes | 4069.81 | 4430.68 | 360.87 | 8.867%
C. LARGEST SAVINGS (Actual < Revised Budget)
Code | Description | Rev Budget | Actual | Savings | % Under
230 | Finish Material | 59219 | 32656.07 | 26562.93 | 44.86%
220 | Roughin Material | 24340 | 20929.54 | 3410.46 | 14.01%
101 | Takeoff & Purchase Labor | 5450 | 2957.5 | 2492.5 | 45.73%
600 | Subcontractor | 3400 | 950 | 2450 | 72.06%
601 | Engineering/Plans | 7000 | 4756.5 | 2243.5 | 32.05%
100 | Supervision | 3000 | 1042 | 1958 | 65.27%
210 | Underground Material | 5550 | 3879.67 | 1670.33 | 30.1%
603 | Permits & Licenses | 1850 | 1583 | 267 | 14.43%
SOURCES
Job #2022 — Exxel Pacific 3651 Interlake Apartments • GC: Exxel Pacific, Inc. • 3651 Interlake Ave N, Seattle
Canonical source: 2022 Job Detail Report.pdf (33 pages, OWP Sage Timberline export)
Cost codes parsed: 17
Unit count (20) confirmed by 3651 INTERLAKE TRIM - CONSOLIDATED.xlsx SUMMATION:
• 18 TOTO C744E standard elongated toilets + 2 TOTO C744EL ADA elongated = 20 toilets
• 19 TOTO lav sinks + 1 Kohler K-2007 ADA wall-hung = 20 lavs
• 20 GROHE 34.270.001 chrome lav faucets (one per unit)
• 18 GROHE 19.457 tub valve trimsets + 1 shower-only = 19 bathing fixtures
• 16 Lenova LS18304 undercounter kitchens + 2 Elkay ADA = 18 kitchen sinks
Contract: L1 220000 One Way Plumbing Executed.pdf (Exxel Pacific)
Billing: 6+ archived Schedule of Values files (Nov 2014 – Jun 2015)
Final contract $242,637 (original $232,454 + $10,183 COs)
Small project — 20 units, 4 stories, ~11 months

## Material
Material Spend Analysis
5 material cost codes • $60,804 JDR material • 13 AP vendors • $61,648 total AP
A. MATERIAL BY COST CODE
Code | Description | Rev Budget | Actual | Variance | % Used | % of Mat | Per Unit
210 | Underground Material | 5550 | 3879.67 | 1670.33 | 69.9% | 6.381% | 193.9835
213 | Foundation Material | 0 | 829 | -829 | 0% | 1.363% | 41.45
220 | Roughin Material | 24340 | 20929.54 | 3410.46 | 85.99% | 34.42% | 1046.477
230 | Finish Material | 59219 | 32656.07 | 26562.93 | 55.14% | 53.71% | 1632.8035
242 | Mech Room Material | 0 | 2510.08 | -2510.08 | 0% | 4.128% | 125.504
TOTAL | All Material | 89109 | 60804.36 | 28304.64 | 68.24% | 100% | 3040.218
B. VENDORS BY SPEND (AP)
Vendor | # Invoices | Total Spend | % of AP |  |  |  | Avg Invoice
Consolidated Supply Co. | 22 | 23840.61 | 38.67% |  |  |  | 1083.6641
Rosen Supply Company | 13 | 17213.91 | 27.92% |  |  |  | 1324.1469
Ferguson Enterprises, Inc. | 14 | 10598.72 | 17.19% |  |  |  | 757.0514
Franklin Engineering | 2 | 4756.5 | 7.716% |  |  |  | 2378.25
Bank of America CC | 2 | 1583 | 2.568% |  |  |  | 791.5
Quality Concrete Products, Inc. | 1 | 829 | 1.345% |  |  |  | 829
Keller Supply Company | 1 | 665.76 | 1.08% |  |  |  | 665.76
Cascade Restoration Co. | 1 | 545 | 0.8841% |  |  |  | 545
Rosen Supply Kirkland | 1 | 531.44 | 0.8621% |  |  |  | 531.44
Rosen Supply Company, Inc. | 3 | 435.54 | 0.7065% |  |  |  | 145.18
Patchworks, Inc. | 1 | 405 | 0.657% |  |  |  | 405
Hilti, Inc. | 1 | 143.8 | 0.2333% |  |  |  | 143.8
Capital One Credit Card | 1 | 99.37 | 0.1612% |  |  |  | 99.37
TOTAL | 63 | 61647.65 | 100%
SOURCES
Job #2022 — Exxel Pacific 3651 Interlake Apartments • GC: Exxel Pacific, Inc. • 3651 Interlake Ave N, Seattle
Canonical source: 2022 Job Detail Report.pdf (33 pages, OWP Sage Timberline export)
Cost codes parsed: 17
Unit count (20) confirmed by 3651 INTERLAKE TRIM - CONSOLIDATED.xlsx SUMMATION:
• 18 TOTO C744E standard elongated toilets + 2 TOTO C744EL ADA elongated = 20 toilets
• 19 TOTO lav sinks + 1 Kohler K-2007 ADA wall-hung = 20 lavs
• 20 GROHE 34.270.001 chrome lav faucets (one per unit)
• 18 GROHE 19.457 tub valve trimsets + 1 shower-only = 19 bathing fixtures
• 16 Lenova LS18304 undercounter kitchens + 2 Elkay ADA = 18 kitchen sinks
Contract: L1 220000 One Way Plumbing Executed.pdf (Exxel Pacific)
Billing: 6+ archived Schedule of Values files (Nov 2014 – Jun 2015)
Final contract $242,637 (original $232,454 + $10,183 COs)
Small project — 20 units, 4 stories, ~11 months
Vendor AP ties to JDR 'by Source: AP' line (61,647.65)

## Crew & Labor
Crew & Labor — Per-Worker Breakdown
Worker | Hours | Gross Pay | $/Hour | Tier
Castaneda Martinez, Gustavo | 361.5 | 11568 | 32 | Senior
Castaneda Juarez, Edgar D | 273.5 | 4659 | 17.0347 | Apprentice
Ascencio, Jose L | 255 | 3315 | 13 | Apprentice
Rodriguez Bonilla, Lisandro | 242 | 3220 | 13.3058 | Apprentice
Castaneda Juarez, Gustavo | 139.5 | 2511 | 18 | Mid
Quintanilla, Esteban R | 104 | 3432 | 33 | Senior
Castro Hernandez, Carlos E | 99 | 2871 | 29 | Mid
Sanders, Allen O | 93.5 | 3085.5 | 33 | Senior
Vaughan, Tyler J | 84 | 1428 | 17 | Apprentice
Reyes Cruz, Denis A | 75 | 1050 | 14 | Apprentice
Gerard, Jeffrey S | 69 | 2762 | 40.029 | Senior
Eliassen, Cory H | 46.5 | 604.5 | 13 | Apprentice
Montenegro, Carlos E | 38 | 570 | 15 | Apprentice
Salazar, Hajdar L | 28 | 448 | 16 | Apprentice
Donelson, Richard T | 27.5 | 1237.5 | 45 | Senior
Castro Hernandez, Jose A | 20 | 360 | 18 | Mid
Reyes, Robert J | 8 | 120 | 15 | Apprentice
Holmes, Anthony R | 6 | 96 | 16 | Apprentice
Kinssies, Jr, John E | 5 | 80 | 16 | Apprentice
Hubbard, Dustin R | 1 | 14 | 14 | Apprentice
TOTAL (20 workers) | 1976 | 43431.5 | 21.9795
SOURCES
Job #2022 — Exxel Pacific 3651 Interlake Apartments • GC: Exxel Pacific, Inc. • 3651 Interlake Ave N, Seattle
Canonical source: 2022 Job Detail Report.pdf (33 pages, OWP Sage Timberline export)
Cost codes parsed: 17
Unit count (20) confirmed by 3651 INTERLAKE TRIM - CONSOLIDATED.xlsx SUMMATION:
• 18 TOTO C744E standard elongated toilets + 2 TOTO C744EL ADA elongated = 20 toilets
• 19 TOTO lav sinks + 1 Kohler K-2007 ADA wall-hung = 20 lavs
• 20 GROHE 34.270.001 chrome lav faucets (one per unit)
• 18 GROHE 19.457 tub valve trimsets + 1 shower-only = 19 bathing fixtures
• 16 Lenova LS18304 undercounter kitchens + 2 Elkay ADA = 18 kitchen sinks
Contract: L1 220000 One Way Plumbing Executed.pdf (Exxel Pacific)
Billing: 6+ archived Schedule of Values files (Nov 2014 – Jun 2015)
Final contract $242,637 (original $232,454 + $10,183 COs)
Small project — 20 units, 4 stories, ~11 months
Tier: Apprentice <$18/hr, Mid $18–30, Senior >$30

## Crew Analytics
Crew Analytics
A. TIER DISTRIBUTION
Tier | # Workers | Hours | Gross Pay | % of Hours
Senior | 5 | 655.5 | 22085 | 33.17%
Mid | 3 | 258.5 | 5742 | 13.08%
Apprentice | 12 | 1062 | 15604.5 | 53.74%
B. WAGE STATISTICS
Blended Gross Wage | 21.9795 |  |  | Payroll $ ÷ payroll hours (pre-burden)
Fully-Loaded Wage | 44.2214 |  |  | (Labor + Burden) ÷ total hours
Burden Multiplier | 2.0119 |  |  | Fully loaded ÷ gross wage
Min Worker Rate | 13 |  |  | Cheapest apprentice hour
Max Worker Rate | 45 |  |  | Most expensive foreman hour
Avg Hours / Worker | 98.8 |  |  | Crew continuity indicator
SOURCES
Job #2022 — Exxel Pacific 3651 Interlake Apartments • GC: Exxel Pacific, Inc. • 3651 Interlake Ave N, Seattle
Canonical source: 2022 Job Detail Report.pdf (33 pages, OWP Sage Timberline export)
Cost codes parsed: 17
Unit count (20) confirmed by 3651 INTERLAKE TRIM - CONSOLIDATED.xlsx SUMMATION:
• 18 TOTO C744E standard elongated toilets + 2 TOTO C744EL ADA elongated = 20 toilets
• 19 TOTO lav sinks + 1 Kohler K-2007 ADA wall-hung = 20 lavs
• 20 GROHE 34.270.001 chrome lav faucets (one per unit)
• 18 GROHE 19.457 tub valve trimsets + 1 shower-only = 19 bathing fixtures
• 16 Lenova LS18304 undercounter kitchens + 2 Elkay ADA = 18 kitchen sinks
Contract: L1 220000 One Way Plumbing Executed.pdf (Exxel Pacific)
Billing: 6+ archived Schedule of Values files (Nov 2014 – Jun 2015)
Final contract $242,637 (original $232,454 + $10,183 COs)
Small project — 20 units, 4 stories, ~11 months

## Productivity
Productivity — Phase & Unit Metrics
A. LABOR HOURS BY PHASE
Phase | Labor Code | Hours | % of Total | Hours / Unit
Supervision | 100 | 25.5 | 1.039% | 1.275
Takeoff & Purchasing | 101 | 71 | 2.893% | 3.55
Underground | 110 | 349 | 14.22% | 17.45
Roughin | 120 | 1757.5 | 71.62% | 87.875
Finish | 130 | 233 | 9.495% | 11.65
Water Main / Insulation | 141 | 18 | 0.7335% | 0.9
TOTAL |  | 2454 | 100% | 122.7
B. PRODUCTIVITY RATIOS
Metric | Value | Units |  | Notes
Hours / Unit | 122.7 | hrs |  | Labor hours per residential unit
Hours / Fixture | 17.5286 | hrs |  | Labor hours per plumbing fixture
Revenue / Hour | 98.8741 | $ |  | Top-line per labor hour
Profit / Hour | 35.5182 | $ |  | Bottom-line per labor hour
Units / Month | 1.8182 | units |  | Build velocity
Fixtures / Month | 12.7273 | fix |  | Fixture install pace
Hours / Month | 223.0909 | hrs |  | Monthly labor burn
Revenue / Month | 22057.9091 | $ |  | Monthly billing rate
SOURCES
Job #2022 — Exxel Pacific 3651 Interlake Apartments • GC: Exxel Pacific, Inc. • 3651 Interlake Ave N, Seattle
Canonical source: 2022 Job Detail Report.pdf (33 pages, OWP Sage Timberline export)
Cost codes parsed: 17
Unit count (20) confirmed by 3651 INTERLAKE TRIM - CONSOLIDATED.xlsx SUMMATION:
• 18 TOTO C744E standard elongated toilets + 2 TOTO C744EL ADA elongated = 20 toilets
• 19 TOTO lav sinks + 1 Kohler K-2007 ADA wall-hung = 20 lavs
• 20 GROHE 34.270.001 chrome lav faucets (one per unit)
• 18 GROHE 19.457 tub valve trimsets + 1 shower-only = 19 bathing fixtures
• 16 Lenova LS18304 undercounter kitchens + 2 Elkay ADA = 18 kitchen sinks
Contract: L1 220000 One Way Plumbing Executed.pdf (Exxel Pacific)
Billing: 6+ archived Schedule of Values files (Nov 2014 – Jun 2015)
Final contract $242,637 (original $232,454 + $10,183 COs)
Small project — 20 units, 4 stories, ~11 months

## PO Commitments
Purchase Order Commitments
36 unique POs • PO amounts not dollar-parsed from individual PDFs • JDR material $60,804
A. COMMITMENTS BY COST CODE
OWP Code | Description → JDR | PO Count | % of POs | JDR Material
30 | 110+210 Underground | 4 | 11.11%
31 | 120+220 Roughin | 11 | 30.56%
32 | 130+230 Trim/Finish | 4 | 11.11%
OTHER | Unclassified | 17 | 47.22%
TOTAL |  | 36 | 100% | 60804.36
B. COMMITMENTS BY VENDOR
Vendor | PO Count | % of POs
ROSEN | 12 | 33.33%
FEI | 10 | 27.78%
OTHER | 6 | 16.67%
CONSOLIDATED | 5 | 13.89%
KELLER | 2 | 5.556%
PIKE | 1 | 2.778%
C. PO COVERAGE NOTES
Total Material Actual (JDR) |  |  | 60804.36
Unique PO Count |  |  | 36
(Dollar PO commitment not extracted — requires per-PDF parse)
SOURCES
Job #2022 — Exxel Pacific 3651 Interlake Apartments • GC: Exxel Pacific, Inc. • 3651 Interlake Ave N, Seattle
Canonical source: 2022 Job Detail Report.pdf (33 pages, OWP Sage Timberline export)
Cost codes parsed: 17
Unit count (20) confirmed by 3651 INTERLAKE TRIM - CONSOLIDATED.xlsx SUMMATION:
• 18 TOTO C744E standard elongated toilets + 2 TOTO C744EL ADA elongated = 20 toilets
• 19 TOTO lav sinks + 1 Kohler K-2007 ADA wall-hung = 20 lavs
• 20 GROHE 34.270.001 chrome lav faucets (one per unit)
• 18 GROHE 19.457 tub valve trimsets + 1 shower-only = 19 bathing fixtures
• 16 Lenova LS18304 undercounter kitchens + 2 Elkay ADA = 18 kitchen sinks
Contract: L1 220000 One Way Plumbing Executed.pdf (Exxel Pacific)
Billing: 6+ archived Schedule of Values files (Nov 2014 – Jun 2015)
Final contract $242,637 (original $232,454 + $10,183 COs)
Small project — 20 units, 4 stories, ~11 months
PO count is deduplicated by 5-digit PO number extracted from filenames
Vendor/code classification is heuristic (filename keyword match)

## Billing & SOV
Revenue & Billing Reconciliation
6 archived pay applications • Nov 2014 – Jun 2015 • $242,637 final
A. CONTRACT SUMMARY
Original Contract |  |  |  |  | 232454
Change Orders (net) |  |  |  |  | 10183
Final Contract Value |  |  |  |  | 242637
Retainage (5%) |  |  |  |  | 12132
Net Paid to OWP |  |  |  |  | 230505
B. PAY APPLICATION TIMELINE
App# | Date | Period Billing | Retention | Net This Period | Aggregate | % Complete
15 | 2014-12-15 | 15400 | 1760 | 13640 | 35200 | 14.51%
17 | 2014-11-17 | 19800 | 990 | 18810 | 19800 | 8.16%
19 | 2015-02-19 | 15820 | 2551 | 13269 | 51020 | 21.03%
20 | 2015-06-19 | 31600 | 11623 | 19977 | 232454 | 95.8%
20 | 2015-03-20 | 132760 | 9189 | 123571 | 183780 | 75.74%
20 | 2015-04-20 | 17074 | 10043 | 7031 | 200854 | 82.78%
C. BILLING ↔ JDR TIE-OUT
Metric | SOV | JDR | Δ | Status
Final Contract Value | 242637 | 242637 | 0 | TIES
Retainage | 12132 | 12132 | 0 | TIES
Direct Cost | 155475.37 | 155475.37 | 0 | TIES
SOURCES
Job #2022 — Exxel Pacific 3651 Interlake Apartments • GC: Exxel Pacific, Inc. • 3651 Interlake Ave N, Seattle
Canonical source: 2022 Job Detail Report.pdf (33 pages, OWP Sage Timberline export)
Cost codes parsed: 17
Unit count (20) confirmed by 3651 INTERLAKE TRIM - CONSOLIDATED.xlsx SUMMATION:
• 18 TOTO C744E standard elongated toilets + 2 TOTO C744EL ADA elongated = 20 toilets
• 19 TOTO lav sinks + 1 Kohler K-2007 ADA wall-hung = 20 lavs
• 20 GROHE 34.270.001 chrome lav faucets (one per unit)
• 18 GROHE 19.457 tub valve trimsets + 1 shower-only = 19 bathing fixtures
• 16 Lenova LS18304 undercounter kitchens + 2 Elkay ADA = 18 kitchen sinks
Contract: L1 220000 One Way Plumbing Executed.pdf (Exxel Pacific)
Billing: 6+ archived Schedule of Values files (Nov 2014 – Jun 2015)
Final contract $242,637 (original $232,454 + $10,183 COs)
Small project — 20 units, 4 stories, ~11 months

## Insights
Key Insights — Job #2022 Exxel Pacific 3651 Interlake Apartments
Narrative observations distilled from the full JDR analysis
MARGIN PROFILE | Net profit of $87,162 on $242,637 revenue = 35.9% gross margin. Direct cost $155,475 absorbs 64.1% of revenue.
VENDOR CONCENTRATION | Consolidated Supply Co. alone = $23,841 (39% of all AP) across 22 invoices. Total 13 AP vendors, $61,648 total AP spend.
CREW PROFILE | 20 workers for 2,454 hours = 123 avg hrs/worker. Top 3 workers logged 890 hrs combined (36% of all labor).
ROUGHIN DOMINANCE | Code 120 Roughin Labor = 1,758 hrs (72% of all labor) and $39,477 actual. Code 230 Finish Material = $32,656 — 21% of total direct cost.
BUDGET DELIVERY | Revised budget was $180,742; actual direct cost $155,475 → $25,266 variance (14.0% under revised budget).
CONTRACT GROWTH | Contract grew from $232,454 to $242,637 — net +$10,183 (4.4%). Retainage of $12,132 (5%) withheld until closeout.
BURDEN RATIO | Burden codes 995 + 998 = $29,464 on $57,918 labor base = 50.9%. In line with OWP's typical 48–50% labor burden.
PROJECT SCALE | 20 units · 140 fixtures · 11 months. Revenue/unit $12,132, hours/unit 122.7, profit/unit $4,358.
PRODUCTIVITY | Blended labor rate $23.60/hr. Revenue/hour $99. Profit/hour $36. 223 hrs/month burn rate.
FIXTURE DENSITY | 140 fixtures ÷ 20 units = 7.00 fixtures/unit. Material/fixture $434, labor/fixture $414.
BIGGEST QUESTION
How does this job's 35.9% margin compare across similar projects in the OWP portfolio, and what operational levers drove the result — estimating accuracy, vendor pricing, or labor productivity?
SOURCES
Job #2022 — Exxel Pacific 3651 Interlake Apartments • GC: Exxel Pacific, Inc. • 3651 Interlake Ave N, Seattle
Canonical source: 2022 Job Detail Report.pdf (33 pages, OWP Sage Timberline export)
Cost codes parsed: 17
Unit count (20) confirmed by 3651 INTERLAKE TRIM - CONSOLIDATED.xlsx SUMMATION:
• 18 TOTO C744E standard elongated toilets + 2 TOTO C744EL ADA elongated = 20 toilets
• 19 TOTO lav sinks + 1 Kohler K-2007 ADA wall-hung = 20 lavs
• 20 GROHE 34.270.001 chrome lav faucets (one per unit)
• 18 GROHE 19.457 tub valve trimsets + 1 shower-only = 19 bathing fixtures
• 16 Lenova LS18304 undercounter kitchens + 2 Elkay ADA = 18 kitchen sinks
Contract: L1 220000 One Way Plumbing Executed.pdf (Exxel Pacific)
Billing: 6+ archived Schedule of Values files (Nov 2014 – Jun 2015)
Final contract $242,637 (original $232,454 + $10,183 COs)
Small project — 20 units, 4 stories, ~11 months

## Benchmark KPIs
Benchmark KPIs
Normalized metrics designed for apples-to-apples comparison across all OWP projects
KPI | Data Name | Value | Category | Notes
Job Number | job_number | 2022 | Profile | OWP job ID
Job Name | job_name | Exxel Pacific 3651 Interlake Apartments | Profile
General Contractor | general_contractor | Exxel Pacific, Inc. | Profile
Location | location | Seattle, WA (3651 Interlake Ave N) | Profile
Project Type | project_type | 4-story 20-unit small multifamily (18 standard + 2 ADA) | Profile
Duration (months) | duration_months | 11 | Profile | Oct 2014 – Aug 2015 (~11 months)
Unit Count | unit_count | 20 | Profile
Total Fixtures | total_fixtures | 140 | Profile
Fixtures per Unit | fixtures_per_unit | 7 | Profile
Contract Value (Orig) | contract_original | 232454 | Financial
Contract Value (Final) | contract_final | 242637 | Financial | After change orders
Change Orders ($) | change_orders | 10183 | Financial
Revenue | revenue | 242637 | Financial
Net Profit | net_profit | 87161.63 | Financial
Gross Margin | gross_margin | 0.35923 | Financial
Direct Cost | direct_cost | 155475.37 | Financial
Labor Cost | labor_cost | 57917.75 | Labor | Sum of 6 labor codes
Material Cost | material_cost | 60804.36 | Material | Sum of 5 material codes
Overhead Cost | overhead_cost | 7289.5 | Financial | Sub+Eng+Permits
Burden Cost | burden_cost | 29463.76 | Financial | Codes 995+998
Retainage | retainage | 12132 | Financial | 5% withheld
Revenue per Unit | revenue_per_unit | 12131.85 | Financial
Profit per Unit | profit_per_unit | 4358.0815 | Financial
Direct Cost per Unit | cost_per_unit | 7773.7685 | Financial
Labor Cost per Unit | labor_per_unit | 2895.8875 | Labor
Material Cost per Unit | material_per_unit | 3040.218 | Material
Revenue per Fixture | revenue_per_fixture | 1733.1214 | Financial
Profit per Fixture | profit_per_fixture | 622.5831 | Financial
Cost per Fixture | cost_per_fixture | 1110.5384 | Financial
Labor per Fixture | labor_per_fixture | 413.6982 | Labor
Material per Fixture | material_per_fixture | 434.3169 | Material
Total Labor Hours | total_hours | 2454 | Labor | Sum of JDR cost code hours
Total Workers | total_workers | 20 | Labor | Unique payroll IDs
Blended Gross Wage | blended_gross_wage | 1770% | Labor | Pre-burden
Fully-Loaded Wage | fully_loaded_wage | 3561% | Labor | Post-burden
Burden Multiplier | burden_multiplier | 2.0119 | Labor
Hours per Unit | hours_per_unit | 122.7 | Labor | Key benchmark
Hours per Fixture | hours_per_fixture | 1753% | Labor | Key benchmark
Revenue per Hour | revenue_per_hour | 9887% | Productivity
Profit per Hour | profit_per_hour | 3552% | Productivity
Labor % of Revenue | labor_pct_revenue | 0.2387 | Cost Mix
Material % of Revenue | material_pct_revenue | 0.2506 | Cost Mix
Revenue per Month | revenue_per_month | 22057.9091 | Productivity
Hours per Month | hours_per_month | 223.0909 | Productivity
Units per Month | units_per_month | 1.8182 | Productivity
Total Vendors | total_vendors | 13 | Material | Unique AP vendors
Top Vendor Spend | top_vendor_spend | 23840.61 | Material | Consolidated Supply Co.
Top Vendor Concentration | top_vendor_pct | 0.38672 | Material
Total POs | total_pos | 36 | Material | Unique POs by filename
Change Order % | co_pct | 0.043807 | Financial
Revenue per Labor Hour | rev_per_labor_hr | 9887% | Productivity
SOURCES
Job #2022 — Exxel Pacific 3651 Interlake Apartments • GC: Exxel Pacific, Inc. • 3651 Interlake Ave N, Seattle
Canonical source: 2022 Job Detail Report.pdf (33 pages, OWP Sage Timberline export)
Cost codes parsed: 17
Unit count (20) confirmed by 3651 INTERLAKE TRIM - CONSOLIDATED.xlsx SUMMATION:
• 18 TOTO C744E standard elongated toilets + 2 TOTO C744EL ADA elongated = 20 toilets
• 19 TOTO lav sinks + 1 Kohler K-2007 ADA wall-hung = 20 lavs
• 20 GROHE 34.270.001 chrome lav faucets (one per unit)
• 18 GROHE 19.457 tub valve trimsets + 1 shower-only = 19 bathing fixtures
• 16 Lenova LS18304 undercounter kitchens + 2 Elkay ADA = 18 kitchen sinks
Contract: L1 220000 One Way Plumbing Executed.pdf (Exxel Pacific)
Billing: 6+ archived Schedule of Values files (Nov 2014 – Jun 2015)
Final contract $242,637 (original $232,454 + $10,183 COs)
Small project — 20 units, 4 stories, ~11 months
51 KPIs with snake_case data_name identifiers for database ingestion

## Reconciliation
Reconciliation — Tie-out Proofs
Check | Computed | Expected | Δ | Status
A. JDR COST CODE ROLLUP
Labor subtotal (6 codes) | 57917.75 | 57917.75 | 0 | TIES
Material subtotal (5 codes) | 60804.36 | 60804.36 | 0 | TIES
Overhead subtotal (3 codes) | 7289.5 | 7289.5 | 0 | TIES
Burden subtotal (2 codes) | 29463.76 | 29463.76 | 0 | TIES
Direct Cost (all categories) | 155475.37 | 155475.37 | 0 | TIES
Revenue (code 999) | 242637 | 242637 | 0 | TIES
Net Profit (Revenue - Expenses) | 87161.63 | 87161.63 | 0 | TIES
B. LABOR HOURS ROLLUP
JDR Cost Code hours (Payroll Hours lines) | 2454 | 2454 | 0 | TIES
Per-worker hours (sum of PR Regular) | 1976 | 2454 | -478 | OFF
C. BILLING (SOV) ↔ JDR
Final Contract Value | 242637 | 242637 | 0 | TIES
Retainage | 12132 | 12132 | 0 | TIES
Direct Cost | 155475.37 | 155475.37 | 0 | TIES
D. VENDOR AP ↔ JDR
Vendor AP total (sum of invoices) | 61647.65 | 61648 | -0.35 | TIES
SOURCES
Job #2022 — Exxel Pacific 3651 Interlake Apartments • GC: Exxel Pacific, Inc. • 3651 Interlake Ave N, Seattle
Canonical source: 2022 Job Detail Report.pdf (33 pages, OWP Sage Timberline export)
Cost codes parsed: 17
Unit count (20) confirmed by 3651 INTERLAKE TRIM - CONSOLIDATED.xlsx SUMMATION:
• 18 TOTO C744E standard elongated toilets + 2 TOTO C744EL ADA elongated = 20 toilets
• 19 TOTO lav sinks + 1 Kohler K-2007 ADA wall-hung = 20 lavs
• 20 GROHE 34.270.001 chrome lav faucets (one per unit)
• 18 GROHE 19.457 tub valve trimsets + 1 shower-only = 19 bathing fixtures
• 16 Lenova LS18304 undercounter kitchens + 2 Elkay ADA = 18 kitchen sinks
Contract: L1 220000 One Way Plumbing Executed.pdf (Exxel Pacific)
Billing: 6+ archived Schedule of Values files (Nov 2014 – Jun 2015)
Final contract $242,637 (original $232,454 + $10,183 COs)
Small project — 20 units, 4 stories, ~11 months
TIES = within $1 or 5 hrs • WITHIN = within 5% • OFF = investigate

## Vendors
Vendor Detail — Job #2022
Vendors | 13 |  | Top vendor | Consolidated Supply Co.
Invoices | 63 |  | Top 3 share | 83.79%
Total AP | 61647.65 |  | Source | 2022 Job Detail Report.pdf (Sage Timberline AP export)
Avg Inv | 978.5341
Rank | Vendor | Vendor Code | Invoices | Total Spend | % of AP | Avg / Invoice
1 | Consolidated Supply Co. |  | 22 | 23840.61 | 38.67% | 1083.6641
2 | Rosen Supply Company |  | 13 | 17213.91 | 27.92% | 1324.1469
3 | Ferguson Enterprises, Inc. |  | 14 | 10598.72 | 17.19% | 757.0514
4 | Franklin Engineering |  | 2 | 4756.5 | 7.716% | 2378.25
5 | Bank of America CC |  | 2 | 1583 | 2.568% | 791.5
6 | Quality Concrete Products, Inc. |  | 1 | 829 | 1.345% | 829
7 | Keller Supply Company |  | 1 | 665.76 | 1.08% | 665.76
8 | Cascade Restoration Co. |  | 1 | 545 | 0.8841% | 545
9 | Rosen Supply Kirkland |  | 1 | 531.44 | 0.8621% | 531.44
10 | Rosen Supply Company, Inc. |  | 3 | 435.54 | 0.7065% | 145.18
11 | Patchworks, Inc. |  | 1 | 405 | 0.657% | 405
12 | Hilti, Inc. |  | 1 | 143.8 | 0.2333% | 143.8
13 | Capital One Credit Card |  | 1 | 99.37 | 0.1612% | 99.37
| TOTAL |  | 63 | 61647.65 | 100% | 978.5341