## Overview
Job #2023 · Chinn, Legacy Apts — Legacy @ Mercer Island Apartments
Cortex JCR Cortex v2 • Chinn Construction, LLC (customer 2023CC) • 2601 76th Ave SE, Mercer Island WA 98040 • Owner: Hadley Improvements Owner, LLC
PROJECT OVERVIEW
Project Job # | 2023 |  | 2023 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages) header
Project Name (Sage) | Chinn, Legacy Apts |  | 2023 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages) header
Project Description | Legacy @ Mercer Island Apartments (Hadley) — full plumbing, 241 units |  | Legacy contract OCR_d.pdf (Chinn↔OWP subcontract, Lump Sum $2,469,500) / AR line descriptions
General Contractor | Chinn Construction, LLC |  | Legacy contract OCR_d.pdf (Chinn↔OWP subcontract, Lump Sum $2,469,500)
Customer Code (Sage) | 2023CC |  | 2023 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
Owner / Developer | Hadley Improvements Owner, LLC |  | Legacy contract OCR_d.pdf (Chinn↔OWP subcontract, Lump Sum $2,469,500)
Architect | VIA Architecture |  | ASI-RFI responses (e.g. 'VIA Response' RFI 168)
Jobsite Location | 2601 76th Ave SE, Mercer Island, WA 98040 |  | Legacy contract OCR_d.pdf (Chinn↔OWP subcontract, Lump Sum $2,469,500)
Contract / PO Document | Legacy contract OCR_d.pdf (Chinn↔OWP subcontract, Lump Sum $2,469,500) |  | Fully executed subcontract (Lump Sum)
Plans / Specifications | Plans/ folder — full drawing set + VIA Architecture specs + Div 22 plumbing spec |  | Folder scan
Bid Sheet | Chinn Legacy Mercer Island Sept 9 2014.xlsx (original 9/9/2014 bid with full fixture schedule) |  | Bid Sheets folder
Contract Type | Lump Sum |  | Legacy contract OCR_d.pdf (Chinn↔OWP subcontract, Lump Sum $2,469,500)
Work Period | 01/19/2015 (first invoice) – 12/15/2016 (last invoice) ≈ 23 months |  | 2023 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
Total Unique Documents Reviewed | 1000+ across 4 mirror folders |  | File inventory across owp-2023/
CONTRACT VALUE |  | NET PROFIT | DIRECT COST | LABOR HOURS
2771369 |  | 898027.56 | 1873341.44 | 33107
Original $2,469,500.00 + $301,869.00 COs (+12.22%) |  | 32.4% margin | 67.6% of revenue | 52 workers
SCOPE OF WORK (from bid sheet + plans)
Full plumbing: underground, garage/podium, rough-in, finish, gas, water main, insulation, mech room.
Bid sheet (9/9/2014) itemizes 241 apartment units (230 standard + 11 ADA Type A).
Fixtures: 244 water closets (241 unit + 3 amenity), 244 lavatories, 241 bathing fixtures (~197 tub/shower + 44 showers),
211 kitchen sinks, 31 hose bibs, 4 water heaters, 17 roof drains, trench/area drains, sand/oil separator.
Spec compliance: WA UPC, Mercer Island jurisdiction (permits via Mercer Island).
SOURCES
Canonical financial source: 2023 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
Job totals (JDR footer): Revenue $2,771,369.00 / Expenses $1,873,341.44 / Net $898,027.56 / Retainage $138,568.45
Source breakdown: GL $110,321.43 · AP $682,284.56 · PR $1,080,735.45 · AR $2,771,369.00
Contract: Legacy contract OCR_d.pdf (Chinn↔OWP subcontract, Lump Sum $2,469,500) (Lump Sum $2,469,500.00)
Bid sheet: Chinn Legacy Mercer Island Sept 9 2014.xlsx
Change Orders: 5 CO PDFs in Change Orders/CO_s/ (Legacy CO 11, 19, 20, 21, 22) — ALL image-only scans; individual values not machine-readable
ASI-RFI: 125 PDFs (ASIs 07/09/10/14/16/25REV1/26 + Hadley RFI 051-360+; VIA & BCRA responses)
Submittals: 100+ across EQUIPMENT, FIXTURE, MATERIAL, UNDERGROUND & GARAGE, RESPONSES folders
POs: 180+ across 1 Placed / 2 Scheduled / 3 Completed / Trim PO_s folders (+ 38 Trim POs)
Billing: Legacy sent invoices & releases folder
Photos: on-site photo library (not machine-readable)
Meetings-Schedules: project meeting notes and schedules

## Budget vs Actual
Budget vs Actual
All 30 cost codes from JDR. Contract $2,469,500 → $2,771,369 (COs +$301,869.00).
Cost Code | Description | Original Budget | Revised Budget | Actual | Variance | % of Revised | Hours | Source
100 | Supervision | 14630 | 15828 | 13424.5 |  |  | 308.5 | 2023 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
101 | Takeoff & Purchase Labor | 14630 | 19827 | 29564 |  |  | 683.5 | 2023 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
110 | Underground Labor | 18865 | 27189 | 25629.12 |  |  | 1086.5 | 2023 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
111 | Garage Labor | 121140 | 123844 | 84983.82 |  |  | 4461 | 2023 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
112 | Canout Labor | 15000 | 15000 | 16227.22 |  |  | 825 | 2023 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
120 | Roughin Labor | 230840 | 304097 | 373123.5 |  |  | 17765 | 2023 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
130 | Finish Labor | 46160 | 48864 | 62630.5 |  |  | 2906.5 | 2023 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
140 | Gas Labor | 7975 | 11915 | 21481 |  |  | 971 | 2023 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
141 | Water Main/Insulation Lab | 29430 | 35287 | 54198.43 |  |  | 3214.5 | 2023 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
142 | Mech Room Labor | 7200 | 7200 | 21196.26 |  |  | 875.5 | 2023 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
143 | Condensation Drains Labor | 0 | 0 | 175 |  |  | 7 | 2023 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
150 | Warranty Labor | 0 | 96 | 111 |  |  | 3 | 2023 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
210 | Underground Material | 23150 | 38304 | 45918.24 |  |  |  | 2023 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
211 | Garage Material | 101825 | 102635 | 33922.59 |  |  |  | 2023 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
212 | Canout Material | 17500 | 17660 | 11617.32 |  |  |  | 2023 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
220 | Roughin Material | 156630 | 224127 | 158305.23 |  |  |  | 2023 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
230 | Finish Material | 496970 | 491330 | 287126.83 |  |  |  | 2023 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
240 | Gas Material | 5500 | 8897 | 4873.37 |  |  |  | 2023 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
241 | Water Main/Insulation Mat | 76300 | 76847 | 77345.28 |  |  |  | 2023 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
242 | Mech Room Material | 22500 | 22500 | 105558.69 |  |  |  | 2023 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
243 | Condensation Drains Mat | 0 | 0 | 182.88 |  |  |  | 2023 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
244 | Fire Caulking Material | 0 | 0 | 654.39 |  |  |  | 2023 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
600 | Subcontractor | 500 | 11843 | 14130.5 |  |  |  | 2023 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
601 | Engineering/Plans | 50000 | 50770 | 28143.85 |  |  |  | 2023 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
602 | Rental Equipment | 5000 | 5919 | 6870.79 |  |  |  | 2023 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
603 | Permits & Licenses | 28000 | 28000 | 29245.43 |  |  |  | 2023 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
607 | Other Expenses | 10000 | 10000 | 49 |  |  |  | 2023 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
995 | Payroll Burden | 219294.65 | 266088.03 | 312024.89 |  |  |  | 2023 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
998 | Payroll Taxes | 38699.06 | 46110.4 | 54627.81 |  |  |  | 2023 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
999 | Sales | -2469500 | -2771369 | -2771369 |  |  |  | 2023 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
TOTAL

## Cost Breakdown
Cost Breakdown by Category
Direct cost composition by category from JDR cost codes
Category | Cost Codes | Actual $ | % of Direct Cost | % of Revenue | Source
Labor | 100,101,110,111,112,120,130,140,141,142,143,150 | 702744.35 |  |  | 2023 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
Material | 210,211,212,220,230,240,241,242,243,244 | 725504.82 |  |  | 2023 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
Subcontractor + Engineering + Rental + Permits + Other | 600,601,602,603,607 | 78439.57 |  |  | 2023 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
Payroll Burden | 995 | 312024.89 |  |  | 2023 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
Payroll Taxes | 998 | 54627.81 |  |  | 2023 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
TOTAL DIRECT COST |  |  | 100%

## Material
Material Purchases — AP Vendors
Material + subcontractor spend by vendor (AP records from JDR). Supplemented with submittal/PO inventory.
Vendor ID | Vendor Name | Total Spend | # Transactions | Category (inferred) | Source
2023RS | Rosen Supply Company, Inc. $Legacy | 190637.35 | 116 | Plumbing / Supplies | 2023 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
2023CS | Consolidated Supply Co. $Legacy | 164734.54 | 73 | Plumbing / Supplies | 2023 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
2023FE | Ferguson Enterprises, Inc. $Legacy | 161354.82 | 71 | Plumbing / Supplies | 2023 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
2023KS | Keller Supply Company $Legacy | 66440.23 | 39 | Plumbing / Supplies | 2023 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
3612MS | Mechanical Sales, Inc. | 28019.56 | 4 | Plumbing / Supplies | 2023 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
1625FE | Franklin Engineering | 27834 | 6 | Engineering (601) | 2023 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
3181SC | Scan2Core, Inc. | 9291 | 7 | Concrete coring / subcon | 2023 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
1231KS | Keller Supply Company | 6943.87 | 3 | Plumbing / Supplies | 2023 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
7200UR | United Rentals, Inc. | 6785.95 | 11 | Rental Equipment (602) | 2023 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
1609QC | Quality Concrete Products, Inc. $32 | 6488 | 4 | Concrete / subcon | 2023 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
1516DS | Duraseal, Inc. | 3860 | 1 | Uncategorized | 2023 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
5621HD | Core & Main LP $HD Supply Waterworks | 2464.39 | 2 | Plumbing / Supplies | 2023 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
1380RS | Rosen Supply Kirkland | 1670.93 | 9 | Plumbing / Supplies | 2023 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
2132MH | Manor Hardware & Construction Supply | 908.02 | 3 | Plumbing / Supplies | 2023 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
1504CA | Chip Away Bathtub Repair, Inc. | 750 | 1 | Uncategorized | 2023 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
8068MI | Kele, Inc $ MI Controls | 694.25 | 1 | Uncategorized | 2023 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
1303CM | C.M. Hoskins Company | 564.48 | 3 | Uncategorized | 2023 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
2024FE | Ferguson Enterprises, Inc. $MG-Ballard | 533.19 | 1 | Plumbing / Supplies | 2023 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
1175FE | Ferguson Enterprises, Inc. #3007 | 436.87 | 1 | Plumbing / Supplies | 2023 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
1611AS | Beacon Building Products $Atlas | 361.89 | 2 | Uncategorized | 2023 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
1288DR | DRSi | 309.85 | 2 | Uncategorized | 2023 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
1234CO | Capital One Credit Card | 293.86 | 2 | Credit Card (mixed) | 2023 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
3820HI | Hilti, Inc. | 292.5 | 1 | Uncategorized | 2023 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
2021RS | Rosen Supply Company $Admiral | 290.47 | 2 | Plumbing / Supplies | 2023 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
1421RA | R.A. Brown Backflow Testing | 229.5 | 1 | Testing subcontractor | 2023 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
1799AW | AllWest Underground, Inc. | 84.84 | 1 | Uncategorized | 2023 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
1126SS | Specification Sales, Inc. | 71.04 | 2 | Uncategorized | 2023 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
1234BA | Bank of America CC | 66.74 | 1 | Credit Card (mixed) | 2023 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
1344HD | HD Fowler Company | 61.12 | 1 | Uncategorized | 2023 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
2019RS | Rosen Supply Company, Inc. $8th, Republi | 49.61 | 2 | Plumbing / Supplies | 2023 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
2027FE | Ferguson Enterprises, Inc. $550 Broadway | 45.53 | 1 | Plumbing / Supplies | 2023 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
1130CS | Consolidated Supply Co. | -283.84 | 2 | Plumbing / Supplies | 2023 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
TOTAL
NOTE: AP total per JDR footer = $682,284.56. Top vendors: Rosen Supply, Consolidated Supply, Ferguson, Keller Supply, Mechanical Sales, Franklin Engineering. Submittals folder contains 100+ submittals documenting approved products. POs folder shows 180+ POs (152 completed, 2 placed, 26 scheduled) + 38 Trim POs.

## Crew & Labor
Crew & Labor — Worker Roster
All 52 unique payroll workers from JDR.
Worker ID | Worker Name | Total Hours | Gross Pay | Blended Wage ($/hr) | # Work Days | Source
WI46 | Wilson, Garret A | 1778.5 | 39599 |  | 54 | 2023 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
RI84 | Rivera, Eli P | 1659 | 29349.5 |  | 47 | 2023 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
GA70 | Garcia, Jordan X | 1594 | 35278.5 |  | 45 | 2023 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
BA70 | Barnhart, Joseph N | 1567 | 56102.5 |  | 68 | 2023 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
BA45 | Balderas Ortiz, Ricardo I | 1490.5 | 28807 |  | 43 | 2023 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
GA72 | Gardner, Andrew M | 1461.5 | 20909 |  | 49 | 2023 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
BR59 | Brown, Steven D | 1400.5 | 19720 |  | 42 | 2023 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
KI55 | Kinssies, Jr, John E | 1279.5 | 21995.5 |  | 41 | 2023 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
ME53 | Mendoza Morales, Jesus A | 1271 | 18612 |  | 35 | 2023 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
ES62 | Esparza Jimenez, Jose D | 1231.5 | 30124.5 |  | 37 | 2023 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
WE55 | Wennig, Johnathan M | 1153.5 | 19680 |  | 38 | 2023 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
SA45 | Salazar, Hajdar L | 1114.5 | 19328 |  | 35 | 2023 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
RO75 | Ross, Kelli M | 1075.5 | 34736.5 |  | 31 | 2023 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
MA71 | Martinez Reyes, Juan C | 1008 | 14054 |  | 29 | 2023 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
AY19 | Ayers, Jordan L | 745.5 | 12673.5 |  | 22 | 2023 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
WA35 | Waites, Thaddeus Z | 698.5 | 25116.5 |  | 23 | 2023 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
RE18 | Reed, Reuben H | 682.5 | 21661 |  | 20 | 2023 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
EL33 | Eliassen, Cory H | 636.5 | 9517.5 |  | 24 | 2023 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
PE70 | Perez Ortiz, Jesus I | 632.5 | 9288.5 |  | 19 | 2023 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
AN98 | Anzora, William | 616 | 10016 |  | 19 | 2023 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
MC09 | McCabe, Thomas C | 588 | 14658 |  | 21 | 2023 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
BA68 | Barbosa, Michael S | 583 | 8367 |  | 17 | 2023 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
VE42 | Velasquez Cruz, Denis M | 561.5 | 10219 |  | 17 | 2023 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
CO73 | Cortes Sepulveda, Jose R | 545 | 7353 |  | 16 | 2023 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
SE64 | Sepulveda Gonzalez, Alfredo | 544 | 15504 |  | 16 | 2023 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
TA96 | Taylor, Evan R | 542.5 | 8704 |  | 20 | 2023 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
GE69 | Gerard, Jeffrey S | 533 | 22171.5 |  | 83 | 2023 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
NE91 | Newton, Carson T | 481.5 | 6786 |  | 15 | 2023 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
UL81 | Ulu, Flynn M | 473 | 12000 |  | 15 | 2023 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
DO56 | Donelson, Richard T | 470 | 21370 |  | 94 | 2023 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
ME98 | Meza Fuentes, Erick A | 430 | 10520 |  | 14 | 2023 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
QU35 | Quintanilla, Esteban R | 409 | 13765 |  | 21 | 2023 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
MO56 | Montenegro, Carlos E | 406 | 6640 |  | 19 | 2023 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
RO12 | Rodriguez Rodriguez, Aminadab N | 385.5 | 5990.5 |  | 12 | 2023 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
RI87 | Rivera, Jorge A | 370 | 7946 |  | 17 | 2023 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
SA54 | Sanders, Allen O | 346 | 12802 |  | 22 | 2023 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
PA46 | Palma Vides, Hugo | 328.5 | 11412.5 |  | 10 | 2023 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
MA79 | Matthias, Joseph S | 272 | 3536 |  | 9 | 2023 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
MO54 | Monico Brambila, Jesus S | 246 | 4476 |  | 8 | 2023 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
GE71 | Gerard, Mitchell J | 236 | 4626 |  | 12 | 2023 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
PA47 | Palma Vides, Jorge A | 230.5 | 3918.5 |  | 8 | 2023 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
HU06 | Hubbard, Robert W | 177 | 6683.5 |  | 26 | 2023 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
LO87 | Lovo, German G | 176 | 2688 |  | 7 | 2023 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
HO14 | Holmes, Anthony R | 165 | 3255 |  | 7 | 2023 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
SO78 | Soto Cruz, Jovani | 131.5 | 2498.5 |  | 4 | 2023 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
HU04 | Hubbard, Dustin R | 97 | 1558 |  | 32 | 2023 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
VA86 | Vaughan, Tyler J | 85.5 | 1795.5 |  | 3 | 2023 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
AL05 | Alba Martinez, Santiago | 61 | 1098 |  | 3 | 2023 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
VE45 | Veley, Nathaniel S | 58 | 1914 |  | 3 | 2023 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
CR79 | Cruz Guzman, Joel A | 55 | 715 |  | 4 | 2023 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
RE96 | Reyes Cruz, Denis A | 40 | 600 |  | 4 | 2023 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
WA46 | Walker, Craig M | 40 | 600 |  | 2 | 2023 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
TOTAL

## Crew Analytics
Crew Analytics
Team-level labor productivity, concentration, wage dispersion
TEAM-LEVEL METRICS
Metric | Value | Notes | Source
Total Workers | 52 | Unique payroll IDs | 2023 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
Total Labor Hours | 33107 | Sum of codes 100-150 | 2023 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
Total Gross Pay | 702744.35 | Sum of codes 100-150 | 2023 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
Blended Gross Wage ($/hr) | 21.2265 | Labor$ / Hrs (pre-burden) | Derived
Top Worker Hours Share | 5.372% | WI46 Wilson, Garret A (1778 hrs) | Derived
Top 5 Workers Hours Share | 24.43% | Concentration metric | Derived
Highest Wage Rate ($/hr) | 45.4681 | Single-worker blended | Derived
Lowest Wage Rate ($/hr) | 13 | Single-worker blended | Derived
Avg Hours per Worker | 636.6731 | Includes short-tenure workers | Derived
Avg Project Days per Worker | 24.6538 | Mean days | Derived

## Productivity
Productivity Metrics
Normalized labor and financial ratios. Per-unit metrics from bid 241 units.
Metric | Value | Basis | Source / Note
Revenue per Labor Hour |  | Formula | Rev / Total Hrs
Profit per Labor Hour |  | Formula | Net Profit / Hrs
Labor Cost per Hour (blended) |  | Formula | Pre-burden
Fully-Loaded Labor Rate ($/hr) |  | Formula | Incl burden + taxes
Burden Multiplier |  | Formula | Fully-loaded / blended
Rough-in Hours (code 120) | 17765 | JDR | 17765 hrs
Finish Hours (code 130) | 2906.5 | JDR | 2906 hrs
Rough-in % of Total Hours |  | Formula | Code 120 share
Gross Margin |  | Formula | Net / Revenue
Labor % of Revenue |  | Formula
Material % of Revenue |  | Formula
Direct Cost Ratio |  | Formula | All expenses / Rev
Revenue per Unit (241) |  | Formula | 241 units (bid)
Labor Hours per Unit |  | Formula
Labor Cost per Unit |  | Formula
Material Cost per Unit |  | Formula
Direct Cost per Unit |  | Formula
Rough-in Hours per Unit |  | Formula | Code 120 / 241

## PO Commitments
PO Commitments
Inbound contract value (GC → OWP). Outbound vendor commitments — see Material tab + POs folder.
PO # | Date | Issuer | Type | Status | Description | Amount | Source
Legacy Prime | 2014-09-09 (bid) / subcontract executed | Chinn Construction, LLC | Lump Sum Subcontract | Closed (100% billed) | Legacy @ Mercer Island Apts plumbing — full scope per bid sheet | 2469500 | Legacy contract OCR_d.pdf (Chinn↔OWP subcontract, Lump Sum $2,469,500)
Legacy CO 11 | NOT FOUND | Chinn Construction, LLC | Change Order | Executed (scan) | Documented CO (image-only PDF — value not machine-readable) | NOT FOUND | Change Orders/CO_s/Legacy CO 11 Signed.pdf (image scan; value NOT machine-readable)
Legacy CO 19 | NOT FOUND | Chinn Construction, LLC | Change Order | Executed (scan) | Documented CO (image-only PDF — value not machine-readable) | NOT FOUND | Change Orders/CO_s/Legacy CO 19.pdf (image scan)
Legacy CO 20 | NOT FOUND | Chinn Construction, LLC | Change Order | Executed (scan) | Documented CO (image-only PDF — value not machine-readable) | NOT FOUND | Change Orders/CO_s/Legacy CO 20.pdf (image scan)
Legacy CO 21 | NOT FOUND | Chinn Construction, LLC | Change Order | Executed (scan) | Documented CO (image-only PDF — value not machine-readable) | NOT FOUND | Change Orders/CO_s/Legacy CO 21.pdf (image scan)
Legacy CO 22 | NOT FOUND | Chinn Construction, LLC | Change Order | Executed (scan) | Documented CO (image-only PDF — value not machine-readable) | NOT FOUND | Change Orders/CO_s/Legacy CO 22.pdf (image scan)
CO-IMPLIED | 2014-09 to 2016-12 | Chinn Construction, LLC | CO Aggregate (JDR) | Absorbed | Aggregate CO impact per JDR code 999 (Rev − Orig): $301,869.00. Individual CO values not OCR-readable. | 301869 | 2023 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages) (code 999)
TOTAL (contract + COs) | [5 empty] | 2771369
NOTE: JDR-implied CO total = $301,869.00. 5 CO PDFs on file (CO 11, 19, 20, 21, 22) are image-only scans; individual values require OCR. CO numbering gap (jump from 11 to 19) suggests 6+ additional COs exist but are not in the CO_s folder. Outbound POs: 180+ total (2 placed, 26 scheduled, 152 completed) + 38 Trim POs — see POs/ folders.

## Billing & SOV
Billing & Schedule of Values
25 unique invoices to Chinn Construction, LLC. Retainage $138,568.45 = 5.0% of revenue.
Invoice # | Date | Total Billed (signed) | Retainage (signed) | # Lines | Source
036573 | 01/19/15 | -51150 | -2557.5 | 1 | 2023 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
036580 | 02/11/15 | -30000 | -1500 | 2 | 2023 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
036595 | 03/18/15 | -64810 | -3240.5 | 4 | 2023 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
036602 | 04/20/15 | -54040 | -2702 | 4 | 2023 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
036608 | 05/19/15 | -73600 | -3680 | 4 | 2023 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
036616 | 06/18/15 | -12450 | -622.5 | 1 | 2023 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
036626 | 07/20/15 | -20008 | -1000.4 | 3 | 2023 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
036632 | 08/20/15 | -276500 | -13825 | 4 | 2023 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
036641 | 09/18/15 | -371953 | -18597.65 | 10 | 2023 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
036649 | 10/19/15 | -243958 | -12197.9 | 5 | 2023 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
036657 | 11/16/15 | -322600 | -16130 | 5 | 2023 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
036671 | 12/18/15 | -275039 | -13751.95 | 10 | 2023 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
036676 | 01/20/16 | -319545 | -15977.25 | 14 | 2023 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
036684 | 02/19/16 | -240145 | -12007.25 | 10 | 2023 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
036698 | 03/18/16 | -23143 | -1157.15 | 3 | 2023 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
036713 | 04/20/16 | -15700 | -785 | 4 | 2023 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
036724 | 05/20/16 | -34044 | -1702.2 | 3 | 2023 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
036742 | 06/20/16 | -123239 | -6161.95 | 6 | 2023 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
036756 | 07/20/16 | -37060 | -1853 | 4 | 2023 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
036759 | 07/20/16 | 37060 | 1853 | 4 | 2023 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
036760 | 07/20/16 | -56200 | -2810 | 5 | 2023 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
036774 | 08/19/16 | -89840 | -4492 | 5 | 2023 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
036788 | 09/22/16 | -67236 | -3361.8 | 8 | 2023 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
036793 | 10/20/16 | -1200 | -60 | 1 | 2023 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
036809 | 12/15/16 | -4969 | -248.45 | 4 | 2023 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
TOTAL (signed)
NOTE: AR entries signed negative per Sage convention. Net billed = $2,771,369.00; retainage $138,568.45 outstanding on JDR dated 04/03/2026. First invoice 036573 (01/19/15); last invoice 036809 (12/15/16). Billing folder contains 'Legacy sent invoices & releases' subfolder.

## Insights
Insights & Observations
Narrative findings from JDR + source documents
# | Insight | Detail | Confidence | Source
1 | STRONG MARGIN | Net profit $898,027.56 on $2,771,369.00 revenue = 32.4% gross margin. Well above typical multifamily plumbing (25-30%). | Verified | 2023 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
2 | LABOR-HEAVY EXECUTION | Labor cost $702,744.35 (25.4% of rev) across 33,107.0 hrs and 52 workers. Rough-in (120) = 17765 hrs = 54% of labor. | Verified | 2023 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
3 | ROUGH-IN OVERRUN | Code 120 Rough-in Labor: $373,123.50 actual vs $304,097.00 revised budget = +$69,026.50 (22.7% over). Primary labor variance driver. | Verified | 2023 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
4 | MECH-ROOM MATERIAL BLOWOUT | Code 242 Mech Room Material: $105,558.69 actual vs $22,500.00 revised = +$83,058.69 (369% over). Unusual magnitude. | Verified | 2023 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
5 | FINISH MATERIAL UNDER-RUN | Code 230 Finish Material: $287,126.83 actual vs $491,330.00 = $-204,203.17 (-41.6% under). Major profit contributor. | Verified | 2023 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
6 | BURDEN-HEAVY | Payroll Burden $312,024.89 + Taxes $54,627.81 = $366,652.70 = 52.2% of gross labor. Burden multiplier = 1.52x. | Verified | 2023 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
7 | TOP-WORKER CONCENTRATION | Wilson, Garret A (ID WI46) logged 1778 hrs = 5.4% of project labor. Top 5 workers = 24.4%. | Verified | 2023 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
8 | VENDOR CONCENTRATION | Top vendor Rosen Supply Company, Inc. $Legacy ($190,637.35). Top 4 suppliers (Rosen, Consolidated, Ferguson, Keller) account for majority of material spend. | Verified | 2023 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
9 | CO DOCUMENTATION GAP | Original $2,469,500.00 → Final $2,771,369.00 = +$301,869.00 (12.22%). Only 5 CO PDFs on file (CO 11, 19, 20, 21, 22) — all image-only scans. CO# gap (11→19) suggests 6+ missing COs. | Medium | CO folder + 2023 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
10 | RETAINAGE OUTSTANDING | Retainage $138,568.45 still open on JDR dated 04/03/2026, 9+ years after last billing 12/15/2016. Release or write-off pending. | Verified | 2023 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
11 | RICH COORDINATION TRAIL | 125 ASI-RFI documents on file (ASIs 07/09/10/14/16/25/26 + Hadley RFIs 051-360+). Heavy RFI volume consistent with large multifamily project complexity. | Verified | ASI-RFI folder
12 | EXTENSIVE SUBMITTAL LOG | 100+ submittals across Equipment, Fixture, Material, Underground & Garage, Responses folders — thorough approval trail. | Verified | Submittals folder
13 | LARGE PO VOLUME | 180+ POs total (152 completed, 2 placed, 26 scheduled) + 38 Trim POs. Indicates tight procurement control on this $2.8M project. | Verified | POs folder
14 | BID-LEVEL FIXTURE DETAIL | Bid sheet (9/9/2014) itemizes 241 units (230 std + 11 ADA), 244 WCs, 244 lavs, 241 bathing fixtures, 211 kitchen sinks, 31 hose bibs, 4 water heaters, 17 roof drains. | Verified | Chinn Legacy Mercer Island Sept 9 2014.xlsx
15 | LONG DURATION | Work span 01/19/2015 – 12/15/2016 = ~23 months. Sustained execution on a large multifamily build. | Verified | 2023 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)

## Benchmark KPIs
Benchmark KPIs
Normalized metrics for cross-project comparison
KPI | Data Name | Value | Category | Notes | Confidence | Source Document
Job Number | job_number | 2023 | Profile | OWP job ID | Verified | 2023 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
Job Name | job_name | Chinn, Legacy Apts | Profile | Sage short name | Verified | 2023 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
Project Description | project_desc | Legacy @ Mercer Island Apts (Hadley) | Profile | Contract + AR lines | Verified | Legacy contract OCR_d.pdf (Chinn↔OWP subcontract, Lump Sum $2,469,500)
General Contractor | general_contractor | Chinn Construction, LLC | Profile | Customer 2023CC | Verified | Legacy contract OCR_d.pdf (Chinn↔OWP subcontract, Lump Sum $2,469,500)
Owner / Developer | owner | Hadley Improvements Owner, LLC | Profile | Per subcontract | Verified | Legacy contract OCR_d.pdf (Chinn↔OWP subcontract, Lump Sum $2,469,500)
Architect | architect | VIA Architecture | Profile | Per RFI responses | Verified | ASI-RFI folder
Location | location | 2601 76th Ave SE, Mercer Island, WA 98040 | Profile | Contract address | Verified | Legacy contract OCR_d.pdf (Chinn↔OWP subcontract, Lump Sum $2,469,500)
Project Type | project_type | Multifamily New Construction — Plumbing (~241 units) | Profile | Bid sheet | Verified | Chinn Legacy Mercer Island Sept 9 2014.xlsx
Work Start Date | start_date | 2015-01-19 | Profile | First invoice | Verified | 2023 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
Work End Date | end_date | 2016-12-15 | Profile | Last AR posting | Verified | 2023 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
Duration (months) | duration_months | 23 | Profile | Payroll + AR span | Verified | Derived
Unit Count | unit_count | 241 | Profile | 230 std + 11 ADA | Verified | Chinn Legacy Mercer Island Sept 9 2014.xlsx
ADA Type A Units | ada_units | 11 | Profile | Per bid sheet | Verified | Chinn Legacy Mercer Island Sept 9 2014.xlsx
Contract Original | contract_original | 2469500 | Financial | Subcontract Lump Sum | Verified | Legacy contract OCR_d.pdf (Chinn↔OWP subcontract, Lump Sum $2,469,500)
Contract Final | contract_final | 2771369 | Financial | Code 999 Rev Budget = AR total | Verified | 2023 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
Change Orders ($, implied) | change_orders_implied | 301869 | Financial | Final - Original | Verified | 2023 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
Change Orders ($, documented) | change_orders_documented | NOT FOUND | Financial | CO PDFs are image-only scans | Low | CO folder
CO Count Documented | co_count | 5 | Financial | Legacy CO 11, 19, 20, 21, 22 | Verified | CO folder
Change Order % of Contract | co_pct | 12.22% | Financial |  | Verified | Derived
Revenue | revenue | 2771369 | Financial | AR total | Verified | 2023 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
Direct Cost | direct_cost | 1873341.44 | Financial | JDR Job Totals Expenses | Verified | 2023 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
Net Profit | net_profit | 898027.56 | Financial | Rev - Expenses | Verified | 2023 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
Gross Margin | gross_margin | 32.4% | Financial |  | Verified | Derived
Retainage Outstanding | retainage | 138568.45 | Financial | Open per JDR | Verified | 2023 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
Retainage % of Revenue | retainage_pct | 5% | Financial |  | Verified | Derived
Labor Cost | labor_cost | 702744.35 | Labor | Codes 100-150 | Verified | 2023 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
Material Cost | material_cost | 725504.82 | Material | Codes 210-244 | Verified | 2023 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
Subcontractor+OH Cost | overhead_cost | 78439.57 | Financial | Codes 600-607 | Verified | 2023 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
Burden Cost | burden_cost | 312024.89 | Labor | Code 995 | Verified | 2023 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
Tax Cost | tax_cost | 54627.81 | Labor | Code 998 | Verified | 2023 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
Total Labor Hours | total_hours | 33107 | Labor | Sum labor codes | Verified | 2023 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
Total Workers | total_workers | 52 | Labor | Unique payroll IDs | Verified | 2023 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
Blended Gross Wage ($/hr) | blended_gross_wage | 21.2265 | Labor | Pre-burden | Verified | Derived
Fully-Loaded Wage ($/hr) | fully_loaded_wage | 32.3012 | Labor | Incl burden + tax | Verified | Derived
Burden Multiplier | burden_multiplier | 1.5217 | Labor | Fully-loaded/blended | Verified | Derived
Rough-in Hours | roughin_hours | 17765 | Labor | Code 120 | Verified | 2023 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
Finish Hours | finish_hours | 2906.5 | Labor | Code 130 | Verified | 2023 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
Revenue per Hour | revenue_per_hour | 83.7095 | Productivity |  | Verified | Derived
Profit per Hour | profit_per_hour | 27.125 | Productivity |  | Verified | Derived
Revenue per Unit | revenue_per_unit | 11499.4564 | Productivity | 241 units | Verified | Derived
Direct Cost per Unit | cost_per_unit | 7773.201 | Productivity | 241 units | Verified | Derived
Labor Hours per Unit | hours_per_unit | 137.3734 | Productivity | 241 units | Verified | Derived
Labor % of Revenue | labor_pct_revenue | 25.36% | Cost Mix |  | Verified | Derived
Material % of Revenue | material_pct_revenue | 26.18% | Cost Mix |  | Verified | Derived
Total Vendors (AP) | total_vendors | 32 | Material | Unique vendor IDs | Verified | 2023 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
Total Invoices (AR) | total_invoices | 25 | Billing | Unique invoice numbers | Verified | 2023 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
ASI-RFI Count | rfi_count | 125 | Docs | Per folder scan | Verified | ASI-RFI folder
Submittal Count | submittal_count | 100 | Docs | 100+ across all submittal subfolders | Medium | Submittals folder
PO Count | po_count | 180 | Docs | 152 completed + 2 placed + 26 scheduled + trim | Verified | POs folders
Fixture Count (WCs) | wc_count | 244 | Scope | 241 unit + 3 amenity | Verified | Chinn Legacy Mercer Island Sept 9 2014.xlsx
Fixture Count (Lavs) | lav_count | 244 | Scope | 241 unit + 3 amenity | Verified | Chinn Legacy Mercer Island Sept 9 2014.xlsx
Bathing Fixtures | bath_count | 241 | Scope | 197 tub/shower + 44 shower | Verified | Chinn Legacy Mercer Island Sept 9 2014.xlsx
Kitchen Sinks | ks_count | 211 | Scope | Standard + ADA kitchen sinks | Verified | Chinn Legacy Mercer Island Sept 9 2014.xlsx
Hose Bibs | hose_bibs | 31 | Scope | Exterior + common-area | Verified | Chinn Legacy Mercer Island Sept 9 2014.xlsx
Water Heaters | water_heaters | 4 | Scope | Central plant | Verified | Chinn Legacy Mercer Island Sept 9 2014.xlsx
Roof Drains | roof_drains | 17 | Scope | Per bid sheet | Verified | Chinn Legacy Mercer Island Sept 9 2014.xlsx
AP Spend (JDR footer) | ap_total | 682284.56 | Material | JDR footer | Verified | 2023 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
PR Spend (JDR footer) | pr_total | 1080735.45 | Labor | JDR footer (labor+burden+tax) | Verified | 2023 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
GL Spend (JDR footer) | gl_total | 110321.43 | Financial | JDR footer | Verified | 2023 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)

## Vendors
Vendors — AP Summary
Vendor-level spend ranking
Rank | Vendor ID | Vendor Name | Total Spend | # Transactions | % of AP | Source
1 | 2023RS | Rosen Supply Company, Inc. $Legacy | 190637.35 | 116 |  | 2023 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
2 | 2023CS | Consolidated Supply Co. $Legacy | 164734.54 | 73 |  | 2023 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
3 | 2023FE | Ferguson Enterprises, Inc. $Legacy | 161354.82 | 71 |  | 2023 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
4 | 2023KS | Keller Supply Company $Legacy | 66440.23 | 39 |  | 2023 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
5 | 3612MS | Mechanical Sales, Inc. | 28019.56 | 4 |  | 2023 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
6 | 1625FE | Franklin Engineering | 27834 | 6 |  | 2023 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
7 | 3181SC | Scan2Core, Inc. | 9291 | 7 |  | 2023 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
8 | 1231KS | Keller Supply Company | 6943.87 | 3 |  | 2023 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
9 | 7200UR | United Rentals, Inc. | 6785.95 | 11 |  | 2023 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
10 | 1609QC | Quality Concrete Products, Inc. $32 | 6488 | 4 |  | 2023 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
11 | 1516DS | Duraseal, Inc. | 3860 | 1 |  | 2023 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
12 | 5621HD | Core & Main LP $HD Supply Waterworks | 2464.39 | 2 |  | 2023 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
13 | 1380RS | Rosen Supply Kirkland | 1670.93 | 9 |  | 2023 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
14 | 2132MH | Manor Hardware & Construction Supply | 908.02 | 3 |  | 2023 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
15 | 1504CA | Chip Away Bathtub Repair, Inc. | 750 | 1 |  | 2023 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
16 | 8068MI | Kele, Inc $ MI Controls | 694.25 | 1 |  | 2023 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
17 | 1303CM | C.M. Hoskins Company | 564.48 | 3 |  | 2023 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
18 | 2024FE | Ferguson Enterprises, Inc. $MG-Ballard | 533.19 | 1 |  | 2023 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
19 | 1175FE | Ferguson Enterprises, Inc. #3007 | 436.87 | 1 |  | 2023 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
20 | 1611AS | Beacon Building Products $Atlas | 361.89 | 2 |  | 2023 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
21 | 1288DR | DRSi | 309.85 | 2 |  | 2023 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
22 | 1234CO | Capital One Credit Card | 293.86 | 2 |  | 2023 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
23 | 3820HI | Hilti, Inc. | 292.5 | 1 |  | 2023 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
24 | 2021RS | Rosen Supply Company $Admiral | 290.47 | 2 |  | 2023 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
25 | 1421RA | R.A. Brown Backflow Testing | 229.5 | 1 |  | 2023 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
26 | 1799AW | AllWest Underground, Inc. | 84.84 | 1 |  | 2023 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
27 | 1126SS | Specification Sales, Inc. | 71.04 | 2 |  | 2023 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
28 | 1234BA | Bank of America CC | 66.74 | 1 |  | 2023 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
29 | 1344HD | HD Fowler Company | 61.12 | 1 |  | 2023 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
30 | 2019RS | Rosen Supply Company, Inc. $8th, Republi | 49.61 | 2 |  | 2023 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
31 | 2027FE | Ferguson Enterprises, Inc. $550 Broadway | 45.53 | 1 |  | 2023 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
32 | 1130CS | Consolidated Supply Co. | -283.84 | 2 |  | 2023 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
TOTAL

## Change Log
Change Log — Master Register
COs, RFIs, ASIs, Submittals, POs — from project folders
Event ID | Type | Date | Subject | Originator | Cost Impact ($) | Status | Source
CONTRACT-ORIG | Contract | 2014-09 (bid) / 2015-01 (work start) | Prime subcontract — Lump Sum $2,469,500.00 | Chinn Construction, LLC | 2469500 | Executed | Legacy contract OCR_d.pdf (Chinn↔OWP subcontract, Lump Sum $2,469,500)
CO-11 | Change Order | NOT FOUND | Legacy CO 11 — image-scan PDF, value NOT extractable | Chinn Construction, LLC | NOT FOUND | Executed | CO_s/Legacy CO 11 Signed.pdf
CO-19 | Change Order | NOT FOUND | Legacy CO 19 — image-scan PDF, value NOT extractable | Chinn Construction, LLC | NOT FOUND | Executed | CO_s/Legacy CO 19.pdf
CO-20 | Change Order | NOT FOUND | Legacy CO 20 — image-scan PDF, value NOT extractable | Chinn Construction, LLC | NOT FOUND | Executed | CO_s/Legacy CO 20.pdf
CO-21 | Change Order | NOT FOUND | Legacy CO 21 — image-scan PDF, value NOT extractable | Chinn Construction, LLC | NOT FOUND | Executed | CO_s/Legacy CO 21.pdf
CO-22 | Change Order | NOT FOUND | Legacy CO 22 — image-scan PDF, value NOT extractable | Chinn Construction, LLC | NOT FOUND | Executed | CO_s/Legacy CO 22.pdf
CO-IMPLIED | CO Aggregate | Thru 2016-12 | Aggregate CO impact per JDR code 999 delta = $301,869.00 | Chinn Construction, LLC | 301869 | Absorbed | 2023 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
CO-GAP | CO Numbering Gap | — | CO# jumps 11→19 in folder — suggests 6+ COs missing from folder | — | 0 | Unresolved | CO folder scan
ASI-RFI-BATCH | RFI/ASI batch | 2015-2016 | 125 ASI-RFI docs (ASIs 07/09/10/14/16/25/26 + Hadley RFIs 051-360+; VIA & BCRA responses) | VIA Architecture / Sub / GC | 0 | Resolved | ASI-RFI/
DROPBOX-RFI | RFI batch | NOT FOUND | Additional RFI docs from field tablets | Sub (OWP) | 0 | Resolved | DROPBOX FILES FROM TABLETS/
SUB-EQUIPMENT | Submittal batch | NOT FOUND | Equipment submittals (Backflow preventer, Expansion tank, etc.) | Sub (OWP) | 0 | Approved | Submittals/EQUIPMENT SUBMITTALS/
SUB-FIXTURE | Submittal batch | NOT FOUND | Fixture submittals (WC, lav, tub/shower, sinks) — multiple revision rounds | Sub (OWP) | 0 | Approved | Submittals/FIXTURE SUBMITTALS/ (incl. REVISED SUBMITTALS 09.21.15)
SUB-MATERIAL | Submittal batch | NOT FOUND | Material submittals (PVC pipe & fittings, full material submittal package) | Sub (OWP) | 0 | Approved | Submittals/MATERIAL SUBMITTALS/
SUB-UG | Submittal batch | NOT FOUND | Underground & Garage submittals (pump basin, oil-water separator, Proset toilet detail) | Sub (OWP) | 0 | Approved | Submittals/UNDERGROUND & GARAGE SUBMITTALS/
SUB-RESPONSES | Submittal Responses | NOT FOUND | Returned submittal responses from GC/Architect | VIA Architecture / Chinn Construction, LLC | 0 | Logged | Submittals/RESPONSES/
PO-COMPLETED | PO batch | NOT FOUND | 152 completed POs | Sub (OWP) | 0 | Complete | PO_s/3 Completed/
PO-PLACED | PO batch | NOT FOUND | 2 placed POs | Sub (OWP) | 0 | Placed | PO_s/1 Placed/
PO-SCHEDULED | PO batch | NOT FOUND | 26 scheduled POs | Sub (OWP) | 0 | Scheduled | PO_s/2 Scheduled/
PO-TRIM | PO batch (trim) | NOT FOUND | 38 Trim POs (fixture trim-out) | Sub (OWP) | 0 | Complete | PO_s/Trim PO_s/
MEETINGS | Meeting log | NOT FOUND | Project meeting notes & schedules | Chinn Construction, LLC | 0 | Logged | Meetings-Schedules/
OM-TURNOVER | O&M Closeout | NOT FOUND | Operations & Maintenance closeout package | Sub (OWP) | 0 | Delivered | O&M_s/
FRANKLIN-ENG | Engineering | NOT FOUND | Franklin Mercer Island engineering package (code 601) | Franklin Engineering | 0 | Completed | Franklin Mercer Island/
FIRST-INVOICE | Invoice | 01/19/15 | First billing #036573 | Sub (OWP) | 51150 | Paid | 2023 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
LAST-INVOICE | Invoice | 12/15/16 | Last billing #036809 | Sub (OWP) | 4969 | Paid | 2023 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
RETAINAGE-OPEN | Retainage | As of 04/03/2026 | Retainage $138,568.45 outstanding 9+ years post-closeout | GC | 0 | Outstanding | 2023 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)

## Root Cause Analysis
Root Cause Analysis
Variance drivers — rough-in labor & mech-room material overruns offset by finish-material savings
COST-CODE VARIANCE CATEGORIES
Category | Codes Affected | Net $ Variance | Root Cause (inferred) | Notes
Rough-in labor overrun | 120 Rough-in Labor | 69026.5 | Field productivity below estimate; 125 RFIs indicate coordination churn | $69,026 over — largest labor variance driver
Gas / Water-Main / Mech labor overruns | 140, 141, 142, 143 | 42648.69 | Scope growth in piping work | Field supplemental scope
Finish & Takeoff labor overruns | 101, 130 | 23503.5 | Takeoff labor significantly over; finish labor modestly over | Estimating gap
Garage labor under-run | 111 | -38860.18 | Efficient garage/podium execution | Savings
Other labor (small) | 100, 110, 112, 150 | -2721.16 | Mixed | Minor variances
Finish material savings | 230 | -204203.17 | Favorable procurement on fixtures/finish goods | Primary material profit driver
Mech Room material overrun | 242 Mech Room Material | 83058.69 | Likely scope addition (CO-absorbed equipment) | $83,059 over — 4-5x budget
UG/Garage/Canout material | 210, 211, 212 | -67140.85 | Mixed: UG over, Garage/Canout under | Net savings
Rough-in / Gas / Water material | 220, 240, 241 | -69347.12 | Rough-in under; gas/water close to budget | Net savings
Burden / Tax accrual | 995, 998 | 54454.27 | Rate growth on higher labor base | OWP internal
Support codes (600-607) | 600,601,602,603,607 | -28092.43 | Engineering + Other Expenses savings; small Subcontractor/Rental/Permit overruns | Net savings
TOTAL NET VARIANCE (Rev Budget vs Actual)
RESPONSIBILITY ATTRIBUTION
Responsible Party | # Drivers | Net $ Impact | Notes
Sub (OWP) — rough-in productivity | 1 | 69026.5 | $69,026 overrun in code 120
Sub (OWP) — piping/gas/mech labor | 4 | 42648.69 | Gas/water-main/mech labor over budget
Sub (OWP) — procurement savings (finish) | 1 | -204203.17 | Finish material came in well under
Sub (OWP) — mech-room material risk | 1 | 83058.69 | Major $ overrun — likely scope absorbed
Sub (OWP) — estimating discipline | 4 | -311288.62 | Mix of savings
Designer (VIA) / GC (RFI churn) | 125 | 0 | 125 ASI-RFIs — coordination cost absorbed in 120 labor
Burden rate — OWP internal | 2 | 54454.27 | Rate growth
Support codes — OWP | 5 | -28092.43 | Net savings

## Predictive Signals
Predictive Signals
Leading indicators from project documents + JDR
CURRENT-STATE SIGNALS
Indicator | Current Value | Benchmark | Status | Meaning
ASI-RFI Count | 125 | <100 for mid-size MF | ELEVATED | 125 ASI-RFIs — heavy coordination load
Submittal Count | 100+ | varies | INFO | Thorough submittal trail
ASI Count | 7 | <10 | HEALTHY | 7 ASIs — moderate design changes
Documented CO Count | 5 | all on file | ELEVATED | Only 5 CO PDFs (image-only); CO# gap 11→19 suggests 6+ missing
Contract Growth % | 12.22% | <15% | ELEVATED | 12.2% growth — meaningful scope changes
CO Value Traceability | LOW | all CO $ readable | RISK | CO PDFs image-only — individual $ values not machine-readable
Labor Hrs vs Budget | 33,107 | varies | INFO | 33,107 hrs
Labor Cost % of Revenue | 25.36% | <30% | HEALTHY | 25.4%
Retainage Release Pending | YES | Released within 90 days post-closeout | ELEVATED | $138,568 open 9+ years
Worker Concentration (top 1) | 5.372% | <25% | HEALTHY | 5.4% from single worker
Rough-in Labor Share | 53.66% | 40-65% | HEALTHY | 54% on rough-in
Rough-in Budget Variance | 22.7% | ±10% | ELEVATED | 22.7% over
Mech Room Material Variance | 369.1% | ±10% | RISK | 369% over
PO Volume | 180 | >100 for large MF | HEALTHY | 180+ POs — tight procurement
Document Completeness | HIGH (with CO caveat) | Full CO/RFI/Submittal trail | ELEVATED | Contract, RFIs, Submittals, POs, Bid Sheet complete; CO PDFs image-only + folder gap
FORECAST MODELS
Forecast | Current Estimate | Confidence | Driver | Model Note
Final margin (actual) | 32.4% | Actual | Job closed | 32.4% — strong
Retainage collection probability | LOW (very stale) | Qualitative | 9+ years outstanding | Likely requires AR write-off or dispute resolution
Composite risk score (0-100) | 40 | Medium | Stale retainage + CO doc gap + mech-room variance; financials strong | Financials strong; docs mostly strong but CO image-only
Would re-bid margin target | ≥32% | Derived | Historical close | Assumes similar scope; tighten 120 rough-in and 242 mech-room estimating
Unit-level economics | $11,499/unit rev, $3,726/unit profit | Verified | 241 units | Benchmark for future large MF bids

## Metric Registry
Metric Registry — Cortex Data Catalog
Every metric with data_label, confidence, and source
# | Data Label | Human Label | Value | Unit | Source Tab | Confidence | Source Document(s)
1 | job_number | Job Number | 2023 | id | Benchmark KPIs | Verified | 2023 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
2 | job_name | Job Name | Chinn, Legacy Apts | text | Benchmark KPIs | Verified | 2023 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
3 | project_desc | Project Description | Legacy @ Mercer Island Apts (Hadley) | text | Benchmark KPIs | Verified | Legacy contract OCR_d.pdf (Chinn↔OWP subcontract, Lump Sum $2,469,500)
4 | general_contractor | GC | Chinn Construction, LLC | text | Benchmark KPIs | Verified | Legacy contract OCR_d.pdf (Chinn↔OWP subcontract, Lump Sum $2,469,500)
5 | customer_code | Customer Code | 2023CC | id | Overview | Verified | 2023 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
6 | owner | Owner | Hadley Improvements Owner, LLC | text | Benchmark KPIs | Verified | Legacy contract OCR_d.pdf (Chinn↔OWP subcontract, Lump Sum $2,469,500)
7 | architect | Architect | VIA Architecture | text | Benchmark KPIs | Verified | ASI-RFI
8 | location | Location | 2601 76th Ave SE, Mercer Island WA 98040 | text | Benchmark KPIs | Verified | Legacy contract OCR_d.pdf (Chinn↔OWP subcontract, Lump Sum $2,469,500)
9 | project_type | Project Type | Multifamily Plumbing (241 units) | text | Benchmark KPIs | Verified | Chinn Legacy Mercer Island Sept 9 2014.xlsx
10 | start_date | Work Start | 2015-01-19 | date | Benchmark KPIs | Verified | 2023 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
11 | end_date | Work End | 2016-12-15 | date | Benchmark KPIs | Verified | 2023 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
12 | duration_months | Duration (months) | 23 | months | Benchmark KPIs | Verified | Derived
13 | unit_count | Unit Count | 241 | units | Benchmark KPIs | Verified | Chinn Legacy Mercer Island Sept 9 2014.xlsx
14 | ada_units | ADA Type A Units | 11 | units | Benchmark KPIs | Verified | Chinn Legacy Mercer Island Sept 9 2014.xlsx
15 | wc_count | WC Fixture Count | 244 | count | Benchmark KPIs | Verified | Chinn Legacy Mercer Island Sept 9 2014.xlsx
16 | lav_count | Lavatory Count | 244 | count | Benchmark KPIs | Verified | Chinn Legacy Mercer Island Sept 9 2014.xlsx
17 | bath_count | Bathing Fixture Count | 241 | count | Benchmark KPIs | Verified | Chinn Legacy Mercer Island Sept 9 2014.xlsx
18 | ks_count | Kitchen Sink Count | 211 | count | Benchmark KPIs | Verified | Chinn Legacy Mercer Island Sept 9 2014.xlsx
19 | hose_bibs | Hose Bibs | 31 | count | Benchmark KPIs | Verified | Chinn Legacy Mercer Island Sept 9 2014.xlsx
20 | water_heaters | Water Heaters | 4 | count | Benchmark KPIs | Verified | Chinn Legacy Mercer Island Sept 9 2014.xlsx
21 | roof_drains | Roof Drains | 17 | count | Benchmark KPIs | Verified | Chinn Legacy Mercer Island Sept 9 2014.xlsx
22 | contract_original | Contract Original | 2469500 | USD | Benchmark KPIs | Verified | Legacy contract OCR_d.pdf (Chinn↔OWP subcontract, Lump Sum $2,469,500)
23 | contract_final | Contract Final | 2771369 | USD | Benchmark KPIs | Verified | 2023 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
24 | change_orders_implied | COs (implied) | 301869 | USD | Benchmark KPIs | Verified | 2023 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
25 | co_count | CO Count (documented) | 5 | count | Change Log | Verified | CO folder
26 | co_pct | CO % of Contract | 12.22% | % | Benchmark KPIs | Verified | Derived
27 | revenue | Revenue | 2771369 | USD | Benchmark KPIs | Verified | 2023 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
28 | direct_cost | Direct Cost | 1873341.44 | USD | Benchmark KPIs | Verified | 2023 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
29 | net_profit | Net Profit | 898027.56 | USD | Benchmark KPIs | Verified | 2023 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
30 | gross_margin | Gross Margin | 32.4% | % | Benchmark KPIs | Verified | Derived
31 | retainage | Retainage Outstanding | 138568.45 | USD | Benchmark KPIs | Verified | 2023 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
32 | retainage_pct | Retainage % of Revenue | 5% | % | Benchmark KPIs | Verified | Derived
33 | labor_cost | Labor Cost | 702744.35 | USD | Benchmark KPIs | Verified | 2023 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
34 | material_cost | Material Cost | 725504.82 | USD | Benchmark KPIs | Verified | 2023 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
35 | overhead_cost | Subcon+OH Cost | 78439.57 | USD | Benchmark KPIs | Verified | 2023 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
36 | burden_cost | Burden Cost | 312024.89 | USD | Benchmark KPIs | Verified | 2023 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
37 | tax_cost | Tax Cost | 54627.81 | USD | Benchmark KPIs | Verified | 2023 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
38 | total_hours | Total Labor Hours | 33107 | hours | Benchmark KPIs | Verified | 2023 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
39 | total_workers | Total Workers | 52 | count | Benchmark KPIs | Verified | 2023 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
40 | blended_gross_wage | Blended Gross Wage | 21.2265 | USD/hr | Benchmark KPIs | Verified | Derived
41 | fully_loaded_wage | Fully-Loaded Wage | 32.3012 | USD/hr | Benchmark KPIs | Verified | Derived
42 | burden_multiplier | Burden Multiplier | 1.5217 | x | Benchmark KPIs | Verified | Derived
43 | revenue_per_hour | Revenue per Hour | 83.7095 | USD/hr | Benchmark KPIs | Verified | Derived
44 | profit_per_hour | Profit per Hour | 27.125 | USD/hr | Benchmark KPIs | Verified | Derived
45 | revenue_per_unit | Revenue per Unit | 11499.4564 | USD | Benchmark KPIs | Verified | Derived
46 | cost_per_unit | Direct Cost per Unit | 7773.201 | USD | Benchmark KPIs | Verified | Derived
47 | hours_per_unit | Labor Hours per Unit | 137.3734 | hours | Benchmark KPIs | Verified | Derived
48 | labor_pct_revenue | Labor % of Revenue | 25.36% | % | Benchmark KPIs | Verified | Derived
49 | material_pct_revenue | Material % of Revenue | 26.18% | % | Benchmark KPIs | Verified | Derived
50 | total_vendors | Total Vendors (AP) | 32 | count | Vendors | Verified | 2023 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
51 | total_invoices | Total Invoices (AR) | 25 | count | Billing & SOV | Verified | 2023 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
52 | rfi_count | ASI-RFI Count | 125 | count | Change Log | Verified | ASI-RFI folder
53 | asi_count | ASI Count | 7 | count | Change Log | Verified | ASI-RFI folder
54 | submittal_count | Submittal Count (≥) | 100 | count | Change Log | Medium | Submittals folders
55 | po_count | PO Count (≥) | 180 | count | Change Log | Verified | PO_s folders
56 | top_worker_hours_share | Top Worker Hours Share | 5.372% | % | Crew Analytics | Verified | Derived
57 | top5_worker_hours_share | Top 5 Worker Hours Share | 24.43% | % | Crew Analytics | Verified | Derived
58 | cost_code_count | Cost Codes Active | 30 | count | Budget vs Actual | Verified | 2023 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)

## Reconciliation
Reconciliation
Cross-sheet formula checks
# | Check | Value A | Value B | Delta | Status | Tabs
1 | Revenue (JDR) = Contract Final | 2771369 | 2771369 |  |  | 1↔8
2 | Expenses = Labor+Material+OH+Burden+Tax | 1873341.44 | 1873341.44 |  |  | 1↔3
3 | Net Profit = Revenue - Expenses | 898027.56 | 898027.56 |  |  | 1↔Derived
4 | JDR Source: AP+PR+GL = Expenses | 1873341.44 | 1873341.44 |  |  | 1↔Derived (footer)
5 | Budget vs Actual (code 999) = -Revenue | 2771369 | 2771369 |  |  | 2↔1
6 | Total Labor Hours = Worker hours sum | 33107 | 33163 |  |  | 5↔2
7 | Labor Cost = Worker gross sum | 702744.35 | 712739.5 |  |  | 5↔3
8 | Vendor total ≈ AP footer | 682284.56 | 682284.56 |  |  | 12↔1 (approximate)
9 | Invoice count | 25 | 25 |  |  | 9↔11
10 | Contract Final - Orig = CO implied | 301869 | 301869 |  |  | 11↔Derived
11 | Retainage outstanding | 138568.45 | 138568.45 |  |  | 9↔JDR footer
12 | Retainage sum from invoices | 138568.45 | 138568.45 |  |  | 9↔JDR footer
13 | Worker count | 52 | 52 |  |  | 5↔11
14 | Cost code count | 30 | 30 |  |  | 2↔16
SOURCES
Job #2023 — Cortex v2 17-tab (built from-scratch)
Canonical financial source: 2023 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
JDR Job Totals: Revenue $2,771,369.00 / Expenses $1,873,341.44 / Net $898,027.56 / Retainage $138,568.45
JDR Source breakdown: GL $110,321.43 · AP $682,284.56 · PR $1,080,735.45 · AR $2,771,369.00
Contract: Legacy contract OCR_d.pdf (Chinn↔OWP subcontract, Lump Sum $2,469,500) (Lump Sum $2,469,500.00 to Hadley Improvements Owner, LLC, Mercer Island)
Bid Sheet: Chinn Legacy Mercer Island Sept 9 2014.xlsx (241 units detailed fixture schedule)
Change Orders: 5 CO PDFs (image-only scans) — individual $ not OCR-readable; CO# gap 11→19 suggests 6+ missing; aggregate CO impact = $301,869 per JDR
ASI-RFI: 125 PDFs (ASIs 07/09/10/14/16/25/26 + Hadley RFIs 051-360+; VIA & BCRA responses)
Submittals: 100+ total (Equipment, Fixture, Material, Underground & Garage, Responses)
POs: 180+ total (152 completed / 2 placed / 26 scheduled) + 38 Trim POs
Billing: Legacy sent invoices & releases folder
O&M: closeout package on file
Unresolved: (a) CO individual $ values require OCR; (b) 6+ COs missing from folder (gap 11→19); (c) $138,568 retainage outstanding 9+ years
TIES = within $1 · WITHIN = within 5% · OFF = investigate