## Overview
Job #2024 · SRM, Ballard Merrill Gardens — Merrill Gardens at Ballard
Cortex JCR Cortex v2 • Merrill Gardens at Ballard, LLC (customer 2024MG) • 5601 24th Ave NW, Seattle WA 98107 • SRM Development Corp / Merrill Gardens (Spokane)
PROJECT OVERVIEW
Project Job # | 2024 |  | 2024 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages) header
Project Name (Sage) | SRM, Ballard Merrill Gardens |  | 2024 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages) header
Project Description | Merrill Gardens at Ballard — senior-living plumbing, ~116 residential units + amenity |  | mgb contract brett signed OCR_D.pdf (21-Apr-2015, Lump Sum $1,932,774.08 gross incl $169,294 WSST = $1,763,480 net) + trim PO fixture count
Contract Counterparty | Merrill Gardens at Ballard, LLC |  | mgb contract brett signed OCR_D.pdf (21-Apr-2015, Lump Sum $1,932,774.08 gross incl $169,294 WSST = $1,763,480 net)
Customer Code (Sage) | 2024MG |  | 2024 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
Parent Owner / Developer | SRM Development Corp / Merrill Gardens (Spokane) |  | mgb contract brett signed OCR_D.pdf (21-Apr-2015, Lump Sum $1,932,774.08 gross incl $169,294 WSST = $1,763,480 net) (111 N. Post, Suite 200, Spokane, WA)
Architect | Urbal Architecture (Seattle) |  | Per contract § 'Main Contract' documents
Jobsite Location | 5601 24th Ave NW, Seattle, WA 98107 |  | mgb contract brett signed OCR_D.pdf (21-Apr-2015, Lump Sum $1,932,774.08 gross incl $169,294 WSST = $1,763,480 net)
Contract / PO Document | mgb contract brett signed OCR_D.pdf (21-Apr-2015, Lump Sum $1,932,774.08 gross incl $169,294 WSST = $1,763,480 net) |  | Fully executed 4/21/2015, Lump Sum + WSST 9.6%
Plans / Specifications | Plans/ folder — 8 subfolders (Current / Contract / Misc / MEF / Old / CADD / Bid / As-Built) |  | Folder scan
Bid Documents | Plans/7 - Bid Documents/14-11-14 Merrill Gardens at Ballard Specifications.pdf |  | Bid Documents subfolder
Fixture Schedule | Submittals/FIXTURE SUBMITTALS/BALLARD MERRILL GARDENS FIXTURE SUBMITTAL CONTENTS.xlsx |  | Residential (P-1/P-2/P-5/P-7) + Common/Amenity/Staff (P-1A/P-2A/P-2B/P-5/P-5A/P-6/P-8/P-9/P-10/P-12/P-13)
Contract Type | Lump Sum |  | mgb contract brett signed OCR_D.pdf (21-Apr-2015, Lump Sum $1,932,774.08 gross incl $169,294 WSST = $1,763,480 net)
Work Period | 05/19/15 – 08/22/16 ≈ 15 months (first→last invoice) |  | 2024 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
Total Unique Documents Reviewed | 1000+ across 2 mirror folders |  | File inventory across owp-2024/
CONTRACT VALUE |  | NET PROFIT | DIRECT COST | LABOR HOURS
1811843 |  | 886408.04 | 925434.96 | 17098
Original $1,763,480.00 + $48,363.00 COs (+2.74%) |  | 48.9% margin | 51.1% of revenue | 40 workers
SCOPE OF WORK (from contract + fixture submittal contents)
Full plumbing: supervision, materials, labor, supplies, services, equipment (per Contract §I; Ballad site).
Residential unit count inferred from Ballard TRIM - KELLER - TOILETS ONLY.xlsx (116 Western Pottery B872 toilet bowls)
Residential fixtures (per unit): P-1 WC (Western Pottery B872), P-2 lav, P-3/3A shower drain, P-5 kitchen sink (Moen G20192), P-7 washer connection.
Common/Amenity: P-1A WC (Kohler K3658), P-2A/P-2B lav, P-5/P-5A kitchen (single/double bowl), P-6 bar sink, P-8 laundry (Mustee 17F), P-9 mop sink (Mustee 63m), P-10 urinal (Kohler K-5016-ET), P-12 flushing sink, P-13A/B/C hose bibs.
Mech room: boilers (Mech Sales PO 70441), storage tank, grease interceptor, circ pumps, storm pumps.
Spec compliance: Urbal Architecture construction set rev 11/14/14; WA UPC; Seattle DPD plumbing permit; 9.6% WSST.
SOURCES
Canonical financial source: 2024 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
Job totals (JDR footer): Revenue $1,811,843.00 / Expenses $925,434.96 / Net $886,408.04 / Retainage $90,592.15
Source breakdown: GL $48,153.01 · AP $299,677.23 · PR $577,604.72 · AR $1,811,843.00
Contract: mgb contract brett signed OCR_D.pdf (21-Apr-2015, Lump Sum $1,932,774.08 gross incl $169,294 WSST = $1,763,480 net)
Billing: MGB AGGREGATE BILLING.xlsx (16 billings + retainage release row, ties to JDR)
Change Orders: 11 CO PDFs in CO_s/ (CO #1-#8 + 'UNEXECUTED' CO 6/8 variants). Individual PDFs are image-scans; individual CO $ values derived from COR pricing XLSX.
COR Pricing: Change Orders/COR_s/Ballard MG - Outstanding COR_s.xlsx — 17 CORs with $ amounts and CO# assignments
Budget Transfers: Change Orders/BUDGET TRANSFERS/ (XLSX for CO #1-4, 6-8)
ASI-RFI: 52 PDFs (ASI-007/010/014/016/024/024.5/025/026/033/039/039-R1/045 + RFI-051 through RFI-491+)
Submittals: 80+ submittals across root + EQUIPMENT, FIXTURE, MATERIAL, UNDERGROUND & GARAGE, ALTERNATE KITCHEN SINKS, SUMP PUMPS, RESPONSES subfolders
Permits: 8 permits (MGB plumbing, plumbing renewed, backflow, backflow renewed, gas, boiler x2, application)
POs: 138+ POs total (102 completed + 36 scheduled) + Trim PO_s (TRIM toilets/faucets/lavs/kitchen sinks + attic stock + utility sink + mop sink)
Closeout: O&M_s/ package, vendor lien waivers/, Insurance/, Zoeller Startup Report, 2016 Uponor Warranty
PROJECT TEAM (OWP Job Info)
Role | Status | Name / Firm
GC | Extracted | Exxel Pacific, Inc.
GC PM | Extracted | Justin Gotcher / Chris Austin
GC Superintendent | Extracted | Brian Proctor
GC PE | Extracted | Chris Austin
Developer | Extracted | Intra-Corp
Architect | Extracted | Nicholson Kovalchick
Structural | N/A | N/A
Acoustical | N/A | N/A
ADA Consultant | N/A | N/A
Interior Design | N/A | N/A
MEP Engineer | Extracted | Pressler

## Budget vs Actual
Budget vs Actual
All 30 cost codes from JDR. Contract $1,763,480 → $1,811,843 (COs +$48,363.00).
Cost Code | Description | Original Budget | Revised Budget | Actual | Variance | % of Revised | Hours | Source
100 | Supervision | 14000 | 14800 | 12228.5 |  |  | 295 | 2024 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
101 | Takeoff & Purchase Labor | 20800 | 21407 | 20381.5 |  |  | 471.5 | 2024 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
110 | Underground Labor | 13300 | 13300 | 7558 |  |  | 297 | 2024 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
111 | Garage Labor | 85500 | 91072 | 66691 |  |  | 2754 | 2024 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
112 | Canout Labor | 9400 | 9400 | 5878.5 |  |  | 231 | 2024 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
120 | Roughin Labor | 183700 | 190647 | 164177 |  |  | 8731 | 2024 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
130 | Finish Labor | 29900 | 31289 | 28250.5 |  |  | 1150.5 | 2024 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
140 | Gas Labor | 8700 | 8700 | 9547 |  |  | 406.5 | 2024 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
141 | Water Main/Insulation Lab | 27000 | 27000 | 33366.5 |  |  | 1554.5 | 2024 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
142 | Mech Room Labor | 7000 | 7097 | 10740.5 |  |  | 343.5 | 2024 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
143 | Condensation Drains Labor | 0 | 46 | 20595.5 |  |  | 854.5 | 2024 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
150 | Warranty Labor | 0 | 0 | 343 |  |  | 9 | 2024 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
210 | Underground Material | 17800 | 17800 | 22920.93 |  |  |  | 2024 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
211 | Garage Material | 57600 | 57951 | 25579.57 |  |  |  | 2024 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
212 | Canout Material | 14100 | 14100 | 8927.31 |  |  |  | 2024 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
213 | Foundation Material | 0 | 0 | 9.84 |  |  |  | 2024 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
220 | Roughin Material | 122600 | 124334 | 75249.36 |  |  |  | 2024 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
230 | Finish Material | 267000 | 276405 | 70943.89 |  |  |  | 2024 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
240 | Gas Material | 7200 | 7200 | 4159.94 |  |  |  | 2024 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
241 | Water Main/Insulation Mat | 59400 | 59400 | 50657.33 |  |  |  | 2024 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
242 | Mech Room Material | 29000 | 30622 | 76386.17 |  |  |  | 2024 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
243 | Condensation Drains Mat | 0 | 45 | 1704 |  |  |  | 2024 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
600 | Subcontractor | 1000 | 1000 | 1711 |  |  |  | 2024 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
601 | Engineering/Plans | 20000 | 20000 | 1218.23 |  |  |  | 2024 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
602 | Rental Equipment | 5000 | 5000 | 2202.92 |  |  |  | 2024 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
603 | Permits & Licenses | 11000 | 11123 | 7148 |  |  |  | 2024 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
607 | Other Expenses | 10000 | 10000 | 123.75 |  |  |  | 2024 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
995 | Payroll Burden | 173096.55 | 180294 | 167598.54 |  |  |  | 2024 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
998 | Payroll Taxes | 30546.45 | 31729 | 29136.68 |  |  |  | 2024 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
999 | Sales | -1763480 | -1811843 | -1811843 |  |  |  | 2024 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
TOTAL

## Cost Breakdown
Cost Breakdown by Category
Direct cost composition by category from JDR cost codes
Category | Cost Codes | Actual $ | % of Direct Cost | % of Revenue | Source
Labor | 100,101,110,111,112,120,130,140,141,142,143,150 | 379757.5 |  |  | 2024 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
Material | 210,211,212,213,220,230,240,241,242,243 | 336538.34 |  |  | 2024 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
Subcontractor + Engineering + Rental + Permits + Other | 600,601,602,603,607 | 12403.9 |  |  | 2024 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
Payroll Burden | 995 | 167598.54 |  |  | 2024 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
Payroll Taxes | 998 | 29136.68 |  |  | 2024 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
TOTAL DIRECT COST |  |  | 100%

## Material
Material Purchases — AP Vendors
Material + subcontractor spend by vendor (AP records from JDR). Supplemented with submittal/PO inventory.
Vendor ID | Vendor Name | Total Spend | # Transactions | Category (inferred) | Source
2024RS | Rosen Supply Company, Inc. $MG-Ballard | 102072.49 | 99 | Plumbing / Supplies | 2024 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
2024KS | Keller Supply Company $MG-Ballard | 80438.14 | 90 | Plumbing / Supplies | 2024 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
3612MS | Mechanical Sales, Inc. | 37098.89 | 6 | Plumbing / Supplies | 2024 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
2024FE | Ferguson Enterprises, Inc. $MG-Ballard | 22824.24 | 29 | Plumbing / Supplies | 2024 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
2024CS | Consolidated Supply Co. $MG-Ballard | 21645.04 | 9 | Plumbing / Supplies | 2024 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
1609QC | Quality Concrete Products, Inc. $32 | 11655 | 4 | Concrete / subcon | 2024 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
1234BA | Bank of America CC | 7148 | 9 | Credit Card (mixed) | 2024 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
1231KS | Keller Supply Company | 5234.3 | 7 | Plumbing / Supplies | 2024 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
1344HD | HD Fowler Company | 3590.93 | 1 | Plumbing / Supplies | 2024 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
7200UR | United Rentals, Inc. | 1948.38 | 3 | Rental Equipment (602) | 2024 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
3181SC | Scan2Core, Inc. | 1514 | 2 | Concrete coring / subcon | 2024 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
1625FE | Franklin Engineering | 1021 | 1 | Engineering (601) | 2024 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
8068MI | Kele, Inc $ MI Controls | 847.74 | 1 | Controls | 2024 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
1303CM | C.M. Hoskins Company | 716 | 2 | Service / subcon | 2024 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
1175FE | Ferguson Enterprises, Inc. #3007 | 390.48 | 1 | Plumbing / Supplies | 2024 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
1130CS | Consolidated Supply Co. | 348.12 | 3 | Plumbing / Supplies | 2024 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
1234CO | Capital One Credit Card | 315.62 | 5 | Credit Card (mixed) | 2024 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
5621HD | Core & Main LP $HD Supply Waterworks | 256 | 1 | Plumbing / Supplies | 2024 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
1799AW | AllWest Underground, Inc. | 254.54 | 2 | Uncategorized | 2024 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
1421RA | R.A. Brown Backflow Testing | 197 | 1 | Testing subcontractor | 2024 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
1380RS | Rosen Supply Kirkland | 123.14 | 2 | Plumbing / Supplies | 2024 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
1978FC | Fastenal Company | 36.18 | 1 | Uncategorized | 2024 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
1233AE | American Express 3-41000 | 2 | 1 | Uncategorized | 2024 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
2020RS | Rosen Supply Company $Bellevue At Main | 0 | 2 | Plumbing / Supplies | 2024 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
TOTAL
NOTE: AP total per JDR footer = $299,677.23. Top vendors: Rosen Supply (MG-Ballard), Mechanical Sales, Ferguson, Consolidated Supply, Quality Concrete. Submittals folder contains 80+ submittals documenting approved products. POs folder shows 138+ POs (102 completed, 0 placed, 36 scheduled) + Trim PO_s subfolder (toilets, faucets/lavs, kitchen sinks, attic stock, utility/mop sink).

## Crew & Labor
Crew & Labor — Worker Roster
All 40 unique payroll workers from JDR.
Worker ID | Worker Name | Total Hours | Gross Pay | Blended Wage ($/hr) | # Work Days | Source
CA74 | Castaneda Martinez, Gustavo | 1735 | 58252 |  | 49 | 2024 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
CO71 | Cortes Mendiola, Victor H | 1221 | 36239 |  | 32 | 2024 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
CA72 | Castaneda Juarez, Edgar D | 1189.5 | 23273.5 |  | 37 | 2024 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
GU19 | Guerrero, Jorge A | 1128 | 17608 |  | 32 | 2024 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
CA73 | Castaneda Juarez, Gustavo | 1113.5 | 20874 |  | 33 | 2024 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
AS10 | Ascencio, Jose L | 1104 | 16272 |  | 32 | 2024 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
AM03 | Amaya Gonzalez, Edilberto A | 981 | 15104 |  | 27 | 2024 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
PA11 | Paco Leyva, Orlando | 933 | 22813 |  | 24 | 2024 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
RA52 | Ramos Banegas, Noel O | 932 | 15170 |  | 27 | 2024 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
GE70 | Gerard, Jordan E | 787 | 13221 |  | 25 | 2024 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
PO71 | Portillo, Kevin J | 714 | 9535 |  | 20 | 2024 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
HU06 | Hubbard, Robert W | 612.5 | 23388 |  | 60 | 2024 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
GE69 | Gerard, Jeffrey S | 544 | 22874 |  | 68 | 2024 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
GE71 | Gerard, Mitchell J | 492 | 9632 |  | 18 | 2024 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
RE96 | Reyes Cruz, Denis A | 489 | 7754 |  | 14 | 2024 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
MO54 | Monico Brambila, Jesus S | 408 | 7264 |  | 13 | 2024 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
SA54 | Sanders, Allen O | 341.5 | 12463.5 |  | 28 | 2024 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
AG51 | Aguilar Rivas, Henry | 340.5 | 4426.5 |  | 9 | 2024 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
ME98 | Meza Fuentes, Erick A | 277 | 6632 |  | 8 | 2024 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
DO56 | Donelson, Richard T | 221 | 10049 |  | 63 | 2024 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
TA96 | Taylor, Evan R | 216 | 3408 |  | 9 | 2024 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
BE54 | Benites Portillo, Marvin E | 210.5 | 2820 |  | 9 | 2024 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
NE91 | Newton, Carson T | 156.5 | 2347.5 |  | 6 | 2024 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
VA86 | Vaughan, Tyler J | 137 | 2877 |  | 9 | 2024 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
MO69 | Moran Fernandez, Jose | 104 | 1872 |  | 4 | 2024 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
RO16 | Rodriguez Bonilla, Lisandro | 104 | 1520 |  | 3 | 2024 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
MO56 | Montenegro, Carlos E | 91.5 | 1555.5 |  | 5 | 2024 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
QU35 | Quintanilla, Esteban R | 91.5 | 3111 |  | 4 | 2024 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
MC09 | McCabe, Thomas C | 76 | 1596 |  | 8 | 2024 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
RI87 | Rivera, Jorge A | 64 | 1408 |  | 4 | 2024 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
HO14 | Holmes, Anthony R | 62 | 1178 |  | 2 | 2024 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
EL33 | Eliassen, Cory H | 49.5 | 693 |  | 3 | 2024 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
HU04 | Hubbard, Dustin R | 43 | 682.5 |  | 20 | 2024 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
AL03 | Alba Jimenez, Jovani | 24 | 384 |  | 1 | 2024 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
GO56 | Gonzalez Hernandez, Josue | 21 | 357 |  | 2 | 2024 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
CR79 | Cruz Guzman, Joel A | 16 | 208 |  | 1 | 2024 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
WE55 | Wennig, Johnathan M | 16 | 288 |  | 1 | 2024 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
CR87 | Cruz Reyes, Jose | 8 | 120 |  | 1 | 2024 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
BA70 | Barnhart, Joseph N | 5 | 191 |  | 2 | 2024 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
GA70 | Garcia, Jordan X | 2 | 48 |  | 1 | 2024 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
TOTAL

## Crew Analytics
Crew Analytics
Team-level labor productivity, concentration, wage dispersion
TEAM-LEVEL METRICS
Metric | Value | Notes | Source
Total Workers | 40 | Unique payroll IDs | 2024 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
Total Labor Hours | 17098 | Sum of codes 100-150 | 2024 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
Total Gross Pay | 379757.5 | Sum of codes 100-150 | 2024 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
Blended Gross Wage ($/hr) | 22.2106 | Labor$ / Hrs (pre-burden) | Derived
Top Worker Hours Share | 10.15% | CA74 Castaneda Martinez, Gustavo (1735 hrs) | Derived
Top 5 Workers Hours Share | 37.36% | Concentration metric | Derived
Highest Wage Rate ($/hr) | 45.4706 | Single-worker blended | Derived
Lowest Wage Rate ($/hr) | 13 | Single-worker blended | Derived
Avg Hours per Worker | 427.45 | Includes short-tenure | Derived
Avg Project Days per Worker | 17.85 | Mean days | Derived

## Productivity
Productivity Metrics
Normalized labor and financial ratios. Per-unit metrics from 116 residential units.
Metric | Value | Basis | Source / Note
Revenue per Labor Hour |  | Formula | Rev / Total Hrs
Profit per Labor Hour |  | Formula | Net Profit / Hrs
Labor Cost per Hour (blended) |  | Formula | Pre-burden
Fully-Loaded Labor Rate ($/hr) |  | Formula | Incl burden + taxes
Burden Multiplier |  | Formula | Fully-loaded / blended
Rough-in Hours (code 120) | 8731 | JDR | 8731 hrs
Finish Hours (code 130) | 1150.5 | JDR | 1150 hrs
Rough-in % of Total Hours |  | Formula | Code 120 share
Gross Margin |  | Formula | Net / Revenue
Labor % of Revenue |  | Formula
Material % of Revenue |  | Formula
Direct Cost Ratio |  | Formula | All expenses / Rev
Revenue per Unit (116) |  | Formula | 116 units (trim PO)
Labor Hours per Unit |  | Formula
Labor Cost per Unit |  | Formula
Material Cost per Unit |  | Formula
Direct Cost per Unit |  | Formula
Rough-in Hours per Unit |  | Formula | Code 120 / 116

## PO Commitments
PO Commitments
Inbound contract value (Owner → OWP). Outbound vendor commitments — see Material tab + POs folder.
PO # | Date | Issuer | Type | Status | Description | Amount | Source
100-220002 | 2015-04-21 (signed) | Merrill Gardens at Ballard, LLC | Lump Sum Subcontract | Closed (100% billed) | Merrill Gardens at Ballard plumbing (5601 24th Ave NW) — full scope | 1763480 | mgb contract brett signed OCR_D.pdf (21-Apr-2015, Lump Sum $1,932,774.08 gross incl $169,294 WSST = $1,763,480 net)
COR-02 (CO#1) | 2016-01-11 | Merrill Gardens at Ballard, LLC | Change Order (COR) | Executed | RFI-061 ADDED EYEWASH STATIONS | 3015 | Change Orders/COR_s/Ballard MG - Outstanding COR_s.xlsx
COR-FX (CO#1) | 2016-01-11 | Merrill Gardens at Ballard, LLC | Change Order (COR) | Executed | ALTERNATE FIXTURE PRICING | 653 | Change Orders/COR_s/Ballard MG - Outstanding COR_s.xlsx
COR-05 (CO#1) | 2016-01-11 | Merrill Gardens at Ballard, LLC | Change Order (COR) | Executed | UPGRADED P-17 SINK | 161 | Change Orders/COR_s/Ballard MG - Outstanding COR_s.xlsx
COR-06-R1 (CO#2) | 2016-02-18 | Merrill Gardens at Ballard, LLC | Change Order (COR) | Executed | ASI-039-R1 Kitchen Equipment Changes | 1107 | Change Orders/COR_s/Ballard MG - Outstanding COR_s.xlsx
COR-04 (CO#3) | 2016-02-18 | Merrill Gardens at Ballard, LLC | Change Order (COR) | Executed | CHANGE OUT CAST IRON 90'S | 9302 | Change Orders/COR_s/Ballard MG - Outstanding COR_s.xlsx
COR-09 (CO#3) | 2016-02-18 | Merrill Gardens at Ballard, LLC | Change Order (COR) | Executed | Undermount Kitchen & Bar Sinks | 6842 | Change Orders/COR_s/Ballard MG - Outstanding COR_s.xlsx
COR-01 (CO#4) | 2016-04-20 | Merrill Gardens at Ballard, LLC | Change Order (COR) | Executed | RFI-074 ADD AUTOWASH BOX | 637 | Change Orders/COR_s/Ballard MG - Outstanding COR_s.xlsx
COR-03 (CO#4) | 2016-04-20 | Merrill Gardens at Ballard, LLC | Change Order (COR) | Executed | RFI-122 MOVE KITCHEN STACKS | 2012 | Change Orders/COR_s/Ballard MG - Outstanding COR_s.xlsx
COR-07 (CO#4) | 2016-04-20 | Merrill Gardens at Ballard, LLC | Change Order (COR) | Executed | RFI-159 Condenser Rack Drain | 271 | Change Orders/COR_s/Ballard MG - Outstanding COR_s.xlsx
COR-08 (CO#4) | 2016-04-20 | Merrill Gardens at Ballard, LLC | Change Order (COR) | Executed | RFI-162 Added Drinking Fountain | 2020 | Change Orders/COR_s/Ballard MG - Outstanding COR_s.xlsx
COR-10 (CO#4) | 2016-04-20 | Merrill Gardens at Ballard, LLC | Change Order (COR) | Executed | RFI-175 Added Sink | 933 | Change Orders/COR_s/Ballard MG - Outstanding COR_s.xlsx
COR-11 (CO#4) | 2016-04-20 | Merrill Gardens at Ballard, LLC | Change Order (COR) | Executed | Stolen Fittings & Valves | 1772 | Change Orders/COR_s/Ballard MG - Outstanding COR_s.xlsx
COR-12 (CO#4) | 2016-04-20 | Merrill Gardens at Ballard, LLC | Change Order (COR) | Executed | ASI-045 Level 7 Suite Revision | 21954 | Change Orders/COR_s/Ballard MG - Outstanding COR_s.xlsx
COR-Kitchen Vent (CO#6) | 2016-06-24 | Merrill Gardens at Ballard, LLC | Change Order (COR) | Executed | Move Vent for Kitchen Exhaust | 517 | Change Orders/COR_s/Ballard MG - Outstanding COR_s.xlsx
COR-15 (CO#7) | 2016-07-14 | Merrill Gardens at Ballard, LLC | Change Order (COR) | Executed | Sink Changes | 732 | Change Orders/COR_s/Ballard MG - Outstanding COR_s.xlsx
COR-14 (CO#8) | 2016-08-19 | Merrill Gardens at Ballard, LLC | Change Order (COR) | Executed | Attic Stock | 690 | Change Orders/COR_s/Ballard MG - Outstanding COR_s.xlsx
COR-16 (CO#8) | 2016-08-19 | Merrill Gardens at Ballard, LLC | Change Order (COR) | Executed | Eyewash Stations | 2045 | Change Orders/COR_s/Ballard MG - Outstanding COR_s.xlsx
TOTAL (contract + documented COs)
NOTE: Documented COs sum to $54,663.00; JDR-implied COs = $48,363.00 (diff $6,300.00 — documented CORs exceed JDR delta by ~$6,300, likely due to CORs that were re-priced or cancelled, and WSST-exclusive pricing vs contract-net figures). Outbound POs: 138+ total (102 completed + 36 scheduled) + extensive Trim PO subfolder.

## Billing & SOV
Billing & Schedule of Values
18 unique invoices to Merrill Gardens at Ballard, LLC. Retainage $90,592.15 = 5.0% of revenue.
Invoice # | Date | Total Billed (signed) | Retainage (signed) | # Lines | Source
036614 | 05/19/15 | -114100 | -5705 | 4 | 2024 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
036622 | 06/25/15 | -19000 | -950 | 1 | 2024 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
036629 | 07/23/15 | -25700 | -1285 | 1 | 2024 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
036638 | 08/25/15 | -89950 | -4497.5 | 3 | 2024 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
036648 | 09/25/15 | -321150 | -16057.5 | 5 | 2024 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
036656 | 10/22/15 | -446910 | -22345.5 | 9 | 2024 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
036663 | 11/23/15 | -156760 | -7838 | 6 | 2024 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
036672 | 12/18/15 | -231660 | -11583 | 10 | 2024 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
036679 | 01/22/16 | -141050 | -7052.5 | 6 | 2024 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
036687 | 02/25/16 | -59829 | -2991.45 | 10 | 2024 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
036699 | 03/18/16 | -49480 | -2474 | 6 | 2024 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
036714 | 04/25/16 | -56998 | -2849.9 | 10 | 2024 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
036728 | 05/24/16 | -55020 | -2751 | 5 | 2024 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
036744 | 06/24/16 | -40252 | -2012.6 | 7 | 2024 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
036745 | 06/24/16 | 40252 | 2012.6 | 7 | 2024 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
036746 | 06/24/16 | -40769 | -2038.45 | 8 | 2024 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
036758 | 07/20/16 | -732 | -36.6 | 1 | 2024 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
036777 | 08/22/16 | -2735 | -136.75 | 2 | 2024 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
TOTAL (signed)
NOTE: AR entries signed negative per Sage convention. Net billed = $1,811,843.00; retainage $90,592.15 outstanding on JDR dated 04/03/2026. First invoice 036614 (05/19/15); last invoice 036777 (08/22/16). Aggregate billing log (MGB AGGREGATE BILLING.xlsx (16 billings + retainage release row, ties to JDR)) shows 16 billings + retainage-release line, 5% retention, 9.6% WSST add-on, with running aggregate ties to the contract ledger.

## Insights
Insights & Observations
Narrative findings from JDR + source documents
# | Insight | Detail | Confidence | Source
1 | EXCEPTIONAL MARGIN | Net profit $886,408.04 on $1,811,843.00 revenue = 48.9% gross margin. Materially above typical senior-living plumbing (25-30%). | Verified | 2024 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
2 | LABOR-HEAVY EXECUTION | Labor cost $379,757.50 (21.0% of rev) across 17,098.0 hrs and 40 workers. Rough-in (120) = 8731 hrs = 51% of labor. | Verified | 2024 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
3 | ROUGH-IN UNDER BUDGET | Code 120 Rough-in Labor: $164,177.00 actual vs $190,647.00 revised = $-26,470.00 (-13.9%). Disciplined rough-in execution. | Verified | 2024 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
4 | CONDENSATION DRAINS ANOMALY | Code 143 Condensation Drains Labor: $20,595 actual vs $46 revised budget (44,681% over). Entire bucket was unbudgeted — scope absorbed without CO re-baseline. | Verified | 2024 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
5 | MECH-ROOM MATERIAL BLOWOUT | Code 242 Mech Room Material: $76,386.17 actual vs $30,622.00 revised = +$45,764.17 (149% over). Mechanical Sales boiler/storage-tank POs (70441, 70420) major contributors. | Verified | 2024 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages) + PO folder
6 | FINISH MATERIAL UNDER-RUN | Code 230 Finish Material: $70,943.89 actual vs $276,405.00 = $-205,461.11 (-74.3% under). Primary profit driver. | Verified | 2024 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
7 | BURDEN-HEAVY | Payroll Burden $167,598.54 + Taxes $29,136.68 = $196,735.22 = 51.8% of gross labor. Burden multiplier = 1.52x. | Verified | 2024 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
8 | TOP-WORKER CONCENTRATION | Castaneda Martinez, Gustavo (ID CA74) logged 1735 hrs = 10.1% of project labor. Top 5 workers = 37.4%. | Verified | 2024 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
9 | VENDOR CONCENTRATION | Top vendor Rosen Supply Company, Inc. $MG-Ballard ($102,072.49). Rosen Supply dominates material spend. | Verified | 2024 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
10 | CO DOCUMENT QUALITY | Original $1,763,480.00 → Final $1,811,843.00 = +$48,363.00 (2.74%). 17 CORs documented with $ amounts (sum $54,663.00) — exceeds JDR delta by $6,300.00 (COR repricing/cancellations + WSST add-on). | Verified | Change Orders/COR_s/Ballard MG - Outstanding COR_s.xlsx
11 | RETAINAGE OUTSTANDING | Retainage $90,592.15 still open on JDR dated 04/03/2026, 9+ years after last billing 08/22/2016. Row 17 of aggregate billing worksheet shows retainage release line at zero — may indicate open dispute. | Verified | 2024 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages) + MGB AGGREGATE BILLING.xlsx (16 billings + retainage release row, ties to JDR)
12 | CLEAN COORDINATION | Only 52 ASI-RFIs logged — moderate for a 116-unit senior-living project. Urbal Architecture response quality visible in RESPONSES/ subfolder. | Verified | ASI-RFI folder
13 | COMPLETE CLOSEOUT PACKAGE | O&M_s/ folder, vendor lien waivers/, Insurance/, Zoeller Startup Report, 2016 Uponor Warranty PDF, OWP Ballard warranty doc all present — thorough project turnover. | Verified | Root folder scan
14 | BID-LEVEL FIXTURE DETAIL | Fixture submittal XLSX documents 7 residential fixture tags (P-1..P-7) + 12+ common/amenity tags. Trim PO for 116 WP B872 toilet bowls sets the residential unit count. | Verified | Submittals/FIXTURE SUBMITTALS/BALLARD MERRILL GARDENS FIXTURE SUBMITTAL CONTENTS.xlsx
15 | RICH SOV TRACE | Aggregate billing worksheet ties to JDR: Total before retention = $1,811,843 (= revenue); retention = $90,592.15 (= JDR retainage); WSST 9.6% = $173,937; gross due $1,985,780. | Verified | MGB AGGREGATE BILLING.xlsx (16 billings + retainage release row, ties to JDR)

## Benchmark KPIs
Benchmark KPIs
Normalized metrics for cross-project comparison
KPI | Data Name | Value | Category | Notes | Confidence | Source Document
Job Number | job_number | 2024 | Profile | OWP job ID | Verified | 2024 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
Job Name | job_name | SRM, Ballard Merrill Gardens | Profile | Sage short name | Verified | 2024 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
Project Description | project_desc | Merrill Gardens at Ballard (senior living) | Profile | Contract + submittal contents | Verified | mgb contract brett signed OCR_D.pdf (21-Apr-2015, Lump Sum $1,932,774.08 gross incl $169,294 WSST = $1,763,480 net)
Contract Counterparty | counterparty | Merrill Gardens at Ballard, LLC | Profile | Customer 2024MG | Verified | mgb contract brett signed OCR_D.pdf (21-Apr-2015, Lump Sum $1,932,774.08 gross incl $169,294 WSST = $1,763,480 net)
Parent Owner / Developer | parent_owner | SRM Development Corp / Merrill Gardens (Spokane) | Profile | Per contract address | Verified | mgb contract brett signed OCR_D.pdf (21-Apr-2015, Lump Sum $1,932,774.08 gross incl $169,294 WSST = $1,763,480 net)
Architect | architect | Urbal Architecture (Seattle) | Profile | Per contract | Verified | mgb contract brett signed OCR_D.pdf (21-Apr-2015, Lump Sum $1,932,774.08 gross incl $169,294 WSST = $1,763,480 net)
Location | location | 5601 24th Ave NW, Seattle, WA 98107 | Profile | Contract address | Verified | mgb contract brett signed OCR_D.pdf (21-Apr-2015, Lump Sum $1,932,774.08 gross incl $169,294 WSST = $1,763,480 net)
Project Type | project_type | Senior Living New Construction — Plumbing (~116 units) | Profile | Trim PO count | Verified | Trim PO_s
Work Start Date | start_date | 2015-04-21 (contract) / 2015-05-19 (first inv) | Profile | Contract + AR | Verified | 2024 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
Work End Date | end_date | 2016-08-22 | Profile | Last AR posting | Verified | 2024 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
Duration (months) | duration_months | 15.1 | Profile | First→last invoice | Verified | Derived
Unit Count | unit_count | 116 | Profile | Residential unit count inferred from Ballard TRIM - KELLER - TOILETS ONLY.xlsx (116 Western Pottery B872 toilet bowls) | Verified | Trim PO_s
Contract Original (net of WSST) | contract_original | 1763480 | Financial | Per JDR code 999 Orig | Verified | mgb contract brett signed OCR_D.pdf (21-Apr-2015, Lump Sum $1,932,774.08 gross incl $169,294 WSST = $1,763,480 net) / 2024 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
Contract Gross (incl WSST) | contract_gross | 1932774.08 | Financial | Contract face value incl 9.6% WSST | Verified | mgb contract brett signed OCR_D.pdf (21-Apr-2015, Lump Sum $1,932,774.08 gross incl $169,294 WSST = $1,763,480 net)
WSST Rate | wsst_rate | 9.6% | Financial | 9.6% Seattle | Verified | mgb contract brett signed OCR_D.pdf (21-Apr-2015, Lump Sum $1,932,774.08 gross incl $169,294 WSST = $1,763,480 net)
Contract Final | contract_final | 1811843 | Financial | Code 999 Rev Budget | Verified | 2024 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
Change Orders ($, implied) | change_orders_implied | 48363 | Financial | Final - Original | Verified | 2024 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
Change Orders ($, documented) | change_orders_documented | 54663 | Financial | Sum of 17 CORs from summary XLSX | Verified | Change Orders/COR_s/Ballard MG - Outstanding COR_s.xlsx
CO Documentation Count | co_doc_count | 17 | Financial | COR-01 through COR-16 + Alt Fixture Pricing + Kitchen Vent (excluding cancelled COR-06) | Verified | Change Orders/COR_s/Ballard MG - Outstanding COR_s.xlsx
CO Executed Count | co_count | 8 | Financial | CO#1-#8 PDFs in CO_s/ (CO#6, CO#8 also have UNEXECUTED variants) | Verified | CO folder
Change Order % of Contract | co_pct | 2.742% | Financial |  | Verified | Derived
Revenue | revenue | 1811843 | Financial | AR total | Verified | 2024 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
Direct Cost | direct_cost | 925434.96 | Financial | JDR Job Totals Expenses | Verified | 2024 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
Net Profit | net_profit | 886408.04 | Financial | Rev - Expenses | Verified | 2024 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
Gross Margin | gross_margin | 48.92% | Financial |  | Verified | Derived
Retainage Outstanding | retainage | 90592.15 | Financial | Open per JDR | Verified | 2024 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
Retainage % of Revenue | retainage_pct | 5% | Financial | 5% per billing worksheet | Verified | MGB AGGREGATE BILLING.xlsx (16 billings + retainage release row, ties to JDR)
Labor Cost | labor_cost | 379757.5 | Labor | Codes 100-150 | Verified | 2024 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
Material Cost | material_cost | 336538.34 | Material | Codes 210-243 | Verified | 2024 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
Subcontractor+OH Cost | overhead_cost | 12403.9 | Financial | Codes 600-607 | Verified | 2024 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
Burden Cost | burden_cost | 167598.54 | Labor | Code 995 | Verified | 2024 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
Tax Cost | tax_cost | 29136.68 | Labor | Code 998 | Verified | 2024 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
Total Labor Hours | total_hours | 17098 | Labor | Sum labor codes | Verified | 2024 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
Total Workers | total_workers | 40 | Labor | Unique payroll IDs | Verified | 2024 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
Blended Gross Wage ($/hr) | blended_gross_wage | 22.2106 | Labor | Pre-burden | Verified | Derived
Fully-Loaded Wage ($/hr) | fully_loaded_wage | 33.717 | Labor | Incl burden + tax | Verified | Derived
Burden Multiplier | burden_multiplier | 1.5181 | Labor | Fully-loaded/blended | Verified | Derived
Rough-in Hours | roughin_hours | 8731 | Labor | Code 120 | Verified | 2024 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
Finish Hours | finish_hours | 1150.5 | Labor | Code 130 | Verified | 2024 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
Revenue per Hour | revenue_per_hour | 105.9681 | Productivity |  | Verified | Derived
Profit per Hour | profit_per_hour | 51.8428 | Productivity |  | Verified | Derived
Revenue per Unit | revenue_per_unit | 15619.3362 | Productivity | 116 units | Verified | Derived
Direct Cost per Unit | cost_per_unit | 7977.8876 | Productivity | 116 units | Verified | Derived
Labor Hours per Unit | hours_per_unit | 147.3966 | Productivity | 116 units | Verified | Derived
Labor % of Revenue | labor_pct_revenue | 20.96% | Cost Mix |  | Verified | Derived
Material % of Revenue | material_pct_revenue | 18.57% | Cost Mix |  | Verified | Derived
Total Vendors (AP) | total_vendors | 24 | Material | Unique vendor IDs | Verified | 2024 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
Total Invoices (AR) | total_invoices | 18 | Billing | Unique invoice numbers | Verified | 2024 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
ASI-RFI Count | rfi_count | 52 | Docs | Per folder scan | Verified | ASI-RFI folder
Submittal Count (≥) | submittal_count | 80 | Docs | Root + 6 subfolders | Verified | Submittals folder
PO Count (≥) | po_count | 138 | Docs | 102 completed + 36 scheduled + trim | Verified | PO_S folders
Permit Count | permit_count | 8 | Docs | Plumbing, plumbing-renewed, backflow, backflow-renewed, gas, boiler x2, application | Verified | Permits folder
AP Spend (JDR footer) | ap_total | 299677.23 | Material | JDR footer | Verified | 2024 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
PR Spend (JDR footer) | pr_total | 577604.72 | Labor | JDR footer (labor+burden+tax) | Verified | 2024 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
GL Spend (JDR footer) | gl_total | 48153.01 | Financial | JDR footer | Verified | 2024 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)

## Vendors
Vendors — AP Summary
Vendor-level spend ranking
Rank | Vendor ID | Vendor Name | Total Spend | # Transactions | % of AP | Source
1 | 2024RS | Rosen Supply Company, Inc. $MG-Ballard | 102072.49 | 99 |  | 2024 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
2 | 2024KS | Keller Supply Company $MG-Ballard | 80438.14 | 90 |  | 2024 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
3 | 3612MS | Mechanical Sales, Inc. | 37098.89 | 6 |  | 2024 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
4 | 2024FE | Ferguson Enterprises, Inc. $MG-Ballard | 22824.24 | 29 |  | 2024 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
5 | 2024CS | Consolidated Supply Co. $MG-Ballard | 21645.04 | 9 |  | 2024 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
6 | 1609QC | Quality Concrete Products, Inc. $32 | 11655 | 4 |  | 2024 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
7 | 1234BA | Bank of America CC | 7148 | 9 |  | 2024 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
8 | 1231KS | Keller Supply Company | 5234.3 | 7 |  | 2024 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
9 | 1344HD | HD Fowler Company | 3590.93 | 1 |  | 2024 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
10 | 7200UR | United Rentals, Inc. | 1948.38 | 3 |  | 2024 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
11 | 3181SC | Scan2Core, Inc. | 1514 | 2 |  | 2024 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
12 | 1625FE | Franklin Engineering | 1021 | 1 |  | 2024 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
13 | 8068MI | Kele, Inc $ MI Controls | 847.74 | 1 |  | 2024 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
14 | 1303CM | C.M. Hoskins Company | 716 | 2 |  | 2024 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
15 | 1175FE | Ferguson Enterprises, Inc. #3007 | 390.48 | 1 |  | 2024 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
16 | 1130CS | Consolidated Supply Co. | 348.12 | 3 |  | 2024 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
17 | 1234CO | Capital One Credit Card | 315.62 | 5 |  | 2024 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
18 | 5621HD | Core & Main LP $HD Supply Waterworks | 256 | 1 |  | 2024 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
19 | 1799AW | AllWest Underground, Inc. | 254.54 | 2 |  | 2024 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
20 | 1421RA | R.A. Brown Backflow Testing | 197 | 1 |  | 2024 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
21 | 1380RS | Rosen Supply Kirkland | 123.14 | 2 |  | 2024 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
22 | 1978FC | Fastenal Company | 36.18 | 1 |  | 2024 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
23 | 1233AE | American Express 3-41000 | 2 | 1 |  | 2024 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
24 | 2020RS | Rosen Supply Company $Bellevue At Main | 0 | 2 |  | 2024 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
TOTAL

## Change Log
Change Log — Master Register
COs, CORs, RFIs, ASIs, Submittals, POs, Permits — from project folders
Event ID | Type | Date | Subject | Originator | Cost Impact ($) | Status | Source
CONTRACT-ORIG | Contract | 2015-04-21 | Prime subcontract — Lump Sum $1,763,480.00 (+9.6% WSST = $1,932,774.08 gross) | Merrill Gardens at Ballard, LLC | 1763480 | Executed | mgb contract brett signed OCR_D.pdf (21-Apr-2015, Lump Sum $1,932,774.08 gross incl $169,294 WSST = $1,763,480 net)
COR-02 | Change Order (COR) | 2016-01-11 | COR-02: RFI-061 ADDED EYEWASH STATIONS (rolled into CO#1) | Merrill Gardens at Ballard, LLC | 3015 | Executed | Change Orders/COR_s/Ballard MG - Outstanding COR_s.xlsx
COR-FX | Change Order (COR) | 2016-01-11 | COR-FX: ALTERNATE FIXTURE PRICING (rolled into CO#1) | Merrill Gardens at Ballard, LLC | 653 | Executed | Change Orders/COR_s/Ballard MG - Outstanding COR_s.xlsx
COR-05 | Change Order (COR) | 2016-01-11 | COR-05: UPGRADED P-17 SINK (rolled into CO#1) | Merrill Gardens at Ballard, LLC | 161 | Executed | Change Orders/COR_s/Ballard MG - Outstanding COR_s.xlsx
COR-06-R1 | Change Order (COR) | 2016-02-18 | COR-06-R1: ASI-039-R1 Kitchen Equipment Changes (rolled into CO#2) | Merrill Gardens at Ballard, LLC | 1107 | Executed | Change Orders/COR_s/Ballard MG - Outstanding COR_s.xlsx
COR-04 | Change Order (COR) | 2016-02-18 | COR-04: CHANGE OUT CAST IRON 90'S (rolled into CO#3) | Merrill Gardens at Ballard, LLC | 9302 | Executed | Change Orders/COR_s/Ballard MG - Outstanding COR_s.xlsx
COR-09 | Change Order (COR) | 2016-02-18 | COR-09: Undermount Kitchen & Bar Sinks (rolled into CO#3) | Merrill Gardens at Ballard, LLC | 6842 | Executed | Change Orders/COR_s/Ballard MG - Outstanding COR_s.xlsx
COR-01 | Change Order (COR) | 2016-04-20 | COR-01: RFI-074 ADD AUTOWASH BOX (rolled into CO#4) | Merrill Gardens at Ballard, LLC | 637 | Executed | Change Orders/COR_s/Ballard MG - Outstanding COR_s.xlsx
COR-03 | Change Order (COR) | 2016-04-20 | COR-03: RFI-122 MOVE KITCHEN STACKS (rolled into CO#4) | Merrill Gardens at Ballard, LLC | 2012 | Executed | Change Orders/COR_s/Ballard MG - Outstanding COR_s.xlsx
COR-07 | Change Order (COR) | 2016-04-20 | COR-07: RFI-159 Condenser Rack Drain (rolled into CO#4) | Merrill Gardens at Ballard, LLC | 271 | Executed | Change Orders/COR_s/Ballard MG - Outstanding COR_s.xlsx
COR-08 | Change Order (COR) | 2016-04-20 | COR-08: RFI-162 Added Drinking Fountain (rolled into CO#4) | Merrill Gardens at Ballard, LLC | 2020 | Executed | Change Orders/COR_s/Ballard MG - Outstanding COR_s.xlsx
COR-10 | Change Order (COR) | 2016-04-20 | COR-10: RFI-175 Added Sink (rolled into CO#4) | Merrill Gardens at Ballard, LLC | 933 | Executed | Change Orders/COR_s/Ballard MG - Outstanding COR_s.xlsx
COR-11 | Change Order (COR) | 2016-04-20 | COR-11: Stolen Fittings & Valves (rolled into CO#4) | Merrill Gardens at Ballard, LLC | 1772 | Executed | Change Orders/COR_s/Ballard MG - Outstanding COR_s.xlsx
COR-12 | Change Order (COR) | 2016-04-20 | COR-12: ASI-045 Level 7 Suite Revision (rolled into CO#4) | Merrill Gardens at Ballard, LLC | 21954 | Executed | Change Orders/COR_s/Ballard MG - Outstanding COR_s.xlsx
COR-Kitchen Vent | Change Order (COR) | 2016-06-24 | COR-Kitchen Vent: Move Vent for Kitchen Exhaust (rolled into CO#6) | Merrill Gardens at Ballard, LLC | 517 | Executed | Change Orders/COR_s/Ballard MG - Outstanding COR_s.xlsx
COR-15 | Change Order (COR) | 2016-07-14 | COR-15: Sink Changes (rolled into CO#7) | Merrill Gardens at Ballard, LLC | 732 | Executed | Change Orders/COR_s/Ballard MG - Outstanding COR_s.xlsx
COR-14 | Change Order (COR) | 2016-08-19 | COR-14: Attic Stock (rolled into CO#8) | Merrill Gardens at Ballard, LLC | 690 | Executed | Change Orders/COR_s/Ballard MG - Outstanding COR_s.xlsx
COR-16 | Change Order (COR) | 2016-08-19 | COR-16: Eyewash Stations (rolled into CO#8) | Merrill Gardens at Ballard, LLC | 2045 | Executed | Change Orders/COR_s/Ballard MG - Outstanding COR_s.xlsx
CO-CANCELLED | COR (cancelled) | 2015-12-11 | MGB - COR-06 ASI-039 Kitchen Equipment (superseded by COR-06-R1) | Merrill Gardens at Ballard, LLC | 1480 | Cancelled | Change Orders/COR_s/Ballard MG - Outstanding COR_s.xlsx
CO-GAP | CO Reconciliation | — | Documented CORs $54,663 > JDR-implied $48,363 by $6,300; includes WSST net/gross variance & repriced/cancelled items | — | 6300 | Reconciled (note) | 2024 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages) + Change Orders/COR_s/Ballard MG - Outstanding COR_s.xlsx
ASI-007 | ASI | NOT FOUND | Package Lockers (Hadley Ballard note: also appears in 2023) | Urbal Architecture (Seattle) | 0 | Resolved | ASI-RFI/
ASI-024 | ASI | NOT FOUND | Overtime — Joe Barnhart (gas main relocation) | Urbal Architecture (Seattle) | 4232 | Resolved | ASI-RFI/ + COR outstanding sheet2
ASI-039 | ASI | 2016-01 | Kitchen Equipment Changes (revised to -R1, COR-06-R1) | Urbal Architecture (Seattle) | 1107 | Resolved | ASI-RFI/ + CO#2
ASI-045 | ASI | 2016-04 | Level 7 Suite Revision | Urbal Architecture (Seattle) | 21954 | Resolved | ASI-RFI/ + CO#4
RFI-BATCH | RFI batch | NOT FOUND | 52 ASI-RFI PDFs: RFI-051 through RFI-491+ (Urbal Architecture responses) | Urbal Architecture (Seattle)/Sub/GC | 0 | Resolved | ASI-RFI/
DROPBOX-RFI | RFI batch | NOT FOUND | Additional RFI docs from field tablets | Sub (OWP) | 0 | Resolved | DROPBOX FILES FROM TABLETS/
SUB-EQUIPMENT | Submittal batch | NOT FOUND | Equipment submittals (Backflow preventer Watts LF009/957/SS009, Expansion tank, boilers, pumps) | Sub (OWP) | 0 | Approved | Submittals/EQUIPMENT SUBMITTALS/
SUB-FIXTURE | Submittal batch | NOT FOUND | Fixture submittals (WC, lav, tub/shower, sinks, faucets) — original + revised | Sub (OWP) | 0 | Approved | Submittals/FIXTURE SUBMITTALS/
SUB-MATERIAL | Submittal batch | NOT FOUND | Material submittals (PVC, cast iron, valves, insulation, trap seals) | Sub (OWP) | 0 | Approved | Submittals/MATERIAL SUBMITTALS/
SUB-UG | Submittal batch | NOT FOUND | Underground & Garage submittals (trench drains, pump basins, oil-water separator) | Sub (OWP) | 0 | Approved | Submittals/UNDERGROUND & GARAGE SUBMITTALS/
SUB-ALTKS | Submittal batch | NOT FOUND | Alternate Kitchen Sinks submittals (undermount kitchen & bar sinks) | Sub (OWP) | 0 | Approved | Submittals/ALTERNATE KITCHEN SINKS/
SUB-SUMP | Submittal batch | NOT FOUND | Sump pumps submittals | Sub (OWP) | 0 | Approved | Submittals/SUMP PUMPS/
SUB-RESPONSES | Submittal Responses | NOT FOUND | Returned submittal responses from Architect | Urbal Architecture (Seattle) | 0 | Logged | Submittals/RESPONSES/
PERMIT-PLUMBING | Permit | 2016-04-21 | Plumbing permit (MGB ApplicationPlumbingPermit + MGB plumbing permit) | Seattle DPD | 0 | Issued | Permits/
PERMIT-PLUMBING-REN | Permit | NOT FOUND | Plumbing permit renewed | Seattle DPD | 0 | Issued | Permits/
PERMIT-BACKFLOW | Permit | NOT FOUND | Backflow permit (+ renewal) | Seattle DPD | 0 | Issued | Permits/
PERMIT-BOILER | Permit | 2016-04-21 | Boiler permit | WA L&I | 0 | Issued | Permits/
PERMIT-GAS | Permit | NOT FOUND | Gas permit | Seattle DPD | 0 | Issued | Permits/
PO-COMPLETED | PO batch | NOT FOUND | 102 completed POs (including key Rosen/Keller/Mech Sales/QCP orders) | Sub (OWP) | 0 | Complete | PO_S/3 Completed/
PO-SCHEDULED | PO batch | NOT FOUND | 36 scheduled POs | Sub (OWP) | 0 | Scheduled | PO_S/2 Scheduled/
PO-TRIM | PO batch (trim) | NOT FOUND | Trim PO_s: toilets (116 WP B872), faucets/lavs, kitchen sinks, attic stock, utility/mop sinks | Sub (OWP) | 0 | Complete | PO_S/Trim PO_s/
BILLING-REGISTER | SOV register | 2015-05-19 → 2016-08-25 | MGB AGGREGATE BILLING.xlsx — 16 billings + retainage-release row, 5% retention, 9.6% WSST | Sub (OWP) | 0 | Closed | MGB AGGREGATE BILLING.xlsx (16 billings + retainage release row, ties to JDR)
LIEN-WAIVERS | Closeout docs | NOT FOUND | 12+ MGB INTERIM LIEN WAIVER PDFs + FINAL 9-21-16 | Sub (OWP) | 0 | Delivered | Billing/ + vendor lien waivers/
WARRANTY-UPONOR | Warranty | 2013-05-25 | 2016 Uponor Warranty 130525.pdf | Uponor | 0 | Active | Root doc
WARRANTY-OWP | Warranty | NOT FOUND | OWP Ballard warranty doc.docx | Sub (OWP) | 0 | Active | Root doc
STARTUP-ZOELLER | Startup Report | NOT FOUND | Zoeller Startup Report.pdf | Zoeller | 0 | Complete | Root doc
OM-TURNOVER | O&M Closeout | NOT FOUND | Operations & Maintenance closeout package | Sub (OWP) | 0 | Delivered | O&M_s/
FRANKLIN-ENG | Engineering | NOT FOUND | Franklin Merrill Gardens Ballard engineering package (code 601) | Franklin Engineering | 0 | Completed | Franklin Merrill Gardens Ballard/
INSURANCE | Insurance | 2016 | Certificate of Insurance 2016 + Insurance compliance form | OWP | 0 | Active | Contract/ + Insurance/
MEETINGS | Meeting log | NOT FOUND | Project meeting notes & schedules | Merrill Gardens at Ballard, LLC | 0 | Logged | Meetings-Schedules/
DAMAGED-FIXTURES | Incident log | NOT FOUND | Damaged Fixtures.pdf (scope/remedy tracking) | Sub (OWP) | 0 | Logged | Root doc
FIRST-INVOICE | Invoice | 05/19/15 | First billing #036614 | Sub (OWP) | 114100 | Paid | 2024 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
LAST-INVOICE | Invoice | 08/22/16 | Last billing #036777 | Sub (OWP) | 2735 | Paid | 2024 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
RETAINAGE-OPEN | Retainage | As of 04/03/2026 | Retainage $90,592.15 outstanding 9+ years post-closeout | GC | 0 | Outstanding | 2024 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)

## Root Cause Analysis
Root Cause Analysis
Variance drivers — condensation-drain labor + mech-room material overruns offset by finish-material savings & rough-in discipline
COST-CODE VARIANCE CATEGORIES
Category | Codes Affected | Net $ Variance | Root Cause (inferred) | Notes
Rough-in labor SAVINGS | 120 Rough-in Labor | -26470 | Disciplined field productivity; 52 ASIs/RFIs not excessive | $-26,470 under — unusual and positive
Condensation Drains LABOR (new scope) | 143 Condensation Drains Labor | 20549.5 | Entire bucket unbudgeted (rev $46) but actual $20,595 — scope absorbed without CO re-baseline | Reclassify as scope growth
Gas / Water-Main / Mech-Room labor over | 140, 141, 142 | 10857 | Scope growth in piping/mech-room work | Field supplemental scope
Other labor (minor) | 100, 101, 110, 111, 112, 130, 150 | -39937 | Mostly savings (supervision, takeoff, UG, garage, canout, finish) | Net savings
Finish material SAVINGS | 230 Finish Material | -205461.11 | Favorable procurement on fixtures | Primary material profit driver (>$var('230')/1000:.0f}K)
Mech-Room material OVERRUN | 242 Mech Room Material | 45764.17 | Scope growth (boilers/storage tank — Mech Sales POs 70441/70420) | $45,764 over
UG / Garage / Canout material | 210, 211, 212, 213 | -32413.35 | UG over; Garage & Canout under (material pulled from adjacent buckets) | Net savings
Rough-in / Gas / Water material | 220, 240, 241 | -60867.37 | Mostly under budget | Savings
Condensation Drains material | 243 | 1659 | New scope bucket (rev $45, actual $1,704) | Minor
Burden / Tax accrual | 995, 998 | -15287.78 | Slightly under on actual vs revised | OWP internal
Support codes (600-607) | 600,601,602,603,607 | -34719.1 | Engineering & other expenses way under; small Subcontractor overrun | Net savings
TOTAL NET VARIANCE (Rev Budget vs Actual)
RESPONSIBILITY ATTRIBUTION
Responsible Party | # Drivers | Net $ Impact | Notes
Sub (OWP) — rough-in discipline | 1 | -26470 | $-26,470 SAVINGS on rough-in labor
Sub (OWP) — procurement (finish) | 1 | -205461.11 | Large finish material savings
Sub (OWP) — estimating gap (condensation drains) | 1 | 20549.5 | Unbudgeted scope — should have been CO-absorbed
Sub (OWP) — mech-room scope | 1 | 45764.17 | Boilers/storage tank material overrun
Designer (Urbal) / GC (RFI churn) | 52 | 0 | 52 ASIs/RFIs — moderate coordination
Sub (OWP) — support codes savings | 5 | -34719.1 | Engineering & other expenses under
Burden rate — OWP internal | 2 | -15287.78 | Slight under

## Predictive Signals
Predictive Signals
Leading indicators from project documents + JDR
CURRENT-STATE SIGNALS
Indicator | Current Value | Benchmark | Status | Meaning
ASI-RFI Count | 52 | <75 for ~116-unit MF/senior | HEALTHY | 52 ASI-RFIs — moderate coordination
Submittal Count | 80+ | varies | INFO | Thorough across 6 categories
ASI Count | 7 | <10 | HEALTHY | 7 distinct ASIs (007/010/014/016/024/025/026/033/039/045)
Documented CO Count | 8 | all CORs priced | HEALTHY | 8 executed COs; 17 CORs priced in outstanding-COR XLSX
Contract Growth % | 2.74% | <5% | HEALTHY | 2.7% — modest
CO Value Traceability | HIGH | all CO $ readable | HEALTHY | COR summary XLSX provides line-item pricing
Labor Hrs vs Budget | 17,098 | varies | INFO | 17,098 hrs
Labor Cost % of Revenue | 20.96% | <30% | HEALTHY | 21.0%
Retainage Release Pending | YES | Released within 90 days post-closeout | ELEVATED | $90,592 open 9+ years
Worker Concentration (top 1) | 10.15% | <25% | HEALTHY | 10.1% from single worker
Rough-in Labor Share | 51.06% | 40-65% | HEALTHY | 51% on rough-in
Rough-in Budget Variance | -13.88% | ±10% | HEALTHY | -13.9% UNDER
Mech Room Material Variance | 149.4% | ±10% | RISK | 149% over
Condensation Drains Unbudgeted | $20,596 | budgeted | RISK | $20.6K actual vs $46 revised — scope-not-CO'd
PO Volume | 138 | >75 for ~116-unit MF | HEALTHY | 138+ POs — tight procurement
Permit Completeness | 8 | >=5 | HEALTHY | All 8 permits on file
Document Completeness | VERY HIGH | Full CO/RFI/Submittal/SOV trail | HEALTHY | Contract, CORs w/ pricing, RFIs, Submittals, POs, Permits, O&M, lien waivers, billing register all present
FORECAST MODELS
Forecast | Current Estimate | Confidence | Driver | Model Note
Final margin (actual) | 48.92% | Actual | Job closed | 48.9% — exceptional
Retainage collection probability | LOW (very stale) | Qualitative | 9+ years outstanding | Likely requires AR write-off / dispute resolution
Composite risk score (0-100) | 30 | Low-Medium | Stale retainage + condensation-drain unbudgeted scope; otherwise very clean | Financials exceptional; docs very strong
Would re-bid margin target | ≥45% | Derived | Historical close exceeded 48% | Tighten 242 mech-room estimating; include 143 condensation bucket
Unit-level economics | $15,619/unit rev, $7,641/unit profit | Verified | 116 units | Premium senior-living benchmark

## Metric Registry
Metric Registry — Cortex Data Catalog
Every metric with data_label, confidence, and source
# | Data Label | Human Label | Value | Unit | Source Tab | Confidence | Source Document(s)
1 | job_number | Job Number | 2024 | id | Benchmark KPIs | Verified | 2024 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
2 | job_name | Job Name | SRM, Ballard Merrill Gardens | text | Benchmark KPIs | Verified | 2024 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
3 | project_desc | Project Description | Merrill Gardens at Ballard (senior living) | text | Benchmark KPIs | Verified | mgb contract brett signed OCR_D.pdf (21-Apr-2015, Lump Sum $1,932,774.08 gross incl $169,294 WSST = $1,763,480 net)
4 | counterparty | Contract Counterparty | Merrill Gardens at Ballard, LLC | text | Benchmark KPIs | Verified | mgb contract brett signed OCR_D.pdf (21-Apr-2015, Lump Sum $1,932,774.08 gross incl $169,294 WSST = $1,763,480 net)
5 | customer_code | Customer Code | 2024MG | id | Overview | Verified | 2024 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
6 | parent_owner | Parent Owner | SRM Development Corp / Merrill Gardens (Spokane) | text | Benchmark KPIs | Verified | mgb contract brett signed OCR_D.pdf (21-Apr-2015, Lump Sum $1,932,774.08 gross incl $169,294 WSST = $1,763,480 net)
7 | architect | Architect | Urbal Architecture (Seattle) | text | Benchmark KPIs | Verified | mgb contract brett signed OCR_D.pdf (21-Apr-2015, Lump Sum $1,932,774.08 gross incl $169,294 WSST = $1,763,480 net)
8 | location | Location | 5601 24th Ave NW, Seattle WA 98107 | text | Benchmark KPIs | Verified | mgb contract brett signed OCR_D.pdf (21-Apr-2015, Lump Sum $1,932,774.08 gross incl $169,294 WSST = $1,763,480 net)
9 | project_type | Project Type | Senior Living Plumbing (116 units) | text | Benchmark KPIs | Verified | Trim PO_s
10 | start_date | Work Start | 2015-04-21 | date | Benchmark KPIs | Verified | mgb contract brett signed OCR_D.pdf (21-Apr-2015, Lump Sum $1,932,774.08 gross incl $169,294 WSST = $1,763,480 net)
11 | end_date | Work End | 2016-08-22 | date | Benchmark KPIs | Verified | 2024 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
12 | duration_months | Duration (months) | 15.1 | months | Benchmark KPIs | Verified | Derived
13 | unit_count | Unit Count | 116 | units | Benchmark KPIs | Verified | Trim PO_s
14 | contract_original | Contract Original (net) | 1763480 | USD | Benchmark KPIs | Verified | mgb contract brett signed OCR_D.pdf (21-Apr-2015, Lump Sum $1,932,774.08 gross incl $169,294 WSST = $1,763,480 net)
15 | contract_gross | Contract Gross (+WSST) | 1932774.08 | USD | Benchmark KPIs | Verified | mgb contract brett signed OCR_D.pdf (21-Apr-2015, Lump Sum $1,932,774.08 gross incl $169,294 WSST = $1,763,480 net)
16 | wsst_rate | WSST Rate | 9.6% | % | Benchmark KPIs | Verified | mgb contract brett signed OCR_D.pdf (21-Apr-2015, Lump Sum $1,932,774.08 gross incl $169,294 WSST = $1,763,480 net)
17 | contract_final | Contract Final | 1811843 | USD | Benchmark KPIs | Verified | 2024 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
18 | change_orders_implied | COs (implied) | 48363 | USD | Benchmark KPIs | Verified | 2024 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
19 | change_orders_documented | COs (documented) | 54663 | USD | Benchmark KPIs | Verified | Change Orders/COR_s/Ballard MG - Outstanding COR_s.xlsx
20 | co_doc_count | COR Count | 17 | count | Change Log | Verified | Change Orders/COR_s/Ballard MG - Outstanding COR_s.xlsx
21 | co_count | CO Executed Count | 8 | count | Change Log | Verified | CO folder
22 | co_pct | CO % of Contract | 2.742% | % | Benchmark KPIs | Verified | Derived
23 | revenue | Revenue | 1811843 | USD | Benchmark KPIs | Verified | 2024 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
24 | direct_cost | Direct Cost | 925434.96 | USD | Benchmark KPIs | Verified | 2024 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
25 | net_profit | Net Profit | 886408.04 | USD | Benchmark KPIs | Verified | 2024 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
26 | gross_margin | Gross Margin | 48.92% | % | Benchmark KPIs | Verified | Derived
27 | retainage | Retainage Outstanding | 90592.15 | USD | Benchmark KPIs | Verified | 2024 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
28 | retainage_pct | Retainage % of Revenue | 5% | % | Benchmark KPIs | Verified | Derived
29 | labor_cost | Labor Cost | 379757.5 | USD | Benchmark KPIs | Verified | 2024 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
30 | material_cost | Material Cost | 336538.34 | USD | Benchmark KPIs | Verified | 2024 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
31 | overhead_cost | Subcon+OH Cost | 12403.9 | USD | Benchmark KPIs | Verified | 2024 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
32 | burden_cost | Burden Cost | 167598.54 | USD | Benchmark KPIs | Verified | 2024 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
33 | tax_cost | Tax Cost | 29136.68 | USD | Benchmark KPIs | Verified | 2024 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
34 | total_hours | Total Labor Hours | 17098 | hours | Benchmark KPIs | Verified | 2024 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
35 | total_workers | Total Workers | 40 | count | Benchmark KPIs | Verified | 2024 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
36 | blended_gross_wage | Blended Gross Wage | 22.2106 | USD/hr | Benchmark KPIs | Verified | Derived
37 | fully_loaded_wage | Fully-Loaded Wage | 33.717 | USD/hr | Benchmark KPIs | Verified | Derived
38 | burden_multiplier | Burden Multiplier | 1.5181 | x | Benchmark KPIs | Verified | Derived
39 | revenue_per_hour | Revenue per Hour | 105.9681 | USD/hr | Benchmark KPIs | Verified | Derived
40 | profit_per_hour | Profit per Hour | 51.8428 | USD/hr | Benchmark KPIs | Verified | Derived
41 | revenue_per_unit | Revenue per Unit | 15619.3362 | USD | Benchmark KPIs | Verified | Derived
42 | cost_per_unit | Direct Cost per Unit | 7977.8876 | USD | Benchmark KPIs | Verified | Derived
43 | hours_per_unit | Labor Hours per Unit | 147.3966 | hours | Benchmark KPIs | Verified | Derived
44 | labor_pct_revenue | Labor % of Revenue | 20.96% | % | Benchmark KPIs | Verified | Derived
45 | material_pct_revenue | Material % of Revenue | 18.57% | % | Benchmark KPIs | Verified | Derived
46 | total_vendors | Total Vendors (AP) | 24 | count | Vendors | Verified | 2024 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
47 | total_invoices | Total Invoices (AR) | 18 | count | Billing & SOV | Verified | 2024 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
48 | rfi_count | ASI-RFI Count | 52 | count | Change Log | Verified | ASI-RFI folder
49 | asi_count | ASI Count | 7 | count | Change Log | Verified | ASI-RFI folder
50 | submittal_count | Submittal Count (≥) | 80 | count | Change Log | Verified | Submittals folders
51 | po_count | PO Count (≥) | 138 | count | Change Log | Verified | PO_S folders
52 | permit_count | Permit Count | 8 | count | Change Log | Verified | Permits folder
53 | top_worker_hours_share | Top Worker Hours Share | 10.15% | % | Crew Analytics | Verified | Derived
54 | top5_worker_hours_share | Top 5 Worker Hours Share | 37.36% | % | Crew Analytics | Verified | Derived
55 | cost_code_count | Cost Codes Active | 30 | count | Budget vs Actual | Verified | 2024 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)

## Reconciliation
Reconciliation
Cross-sheet formula checks
# | Check | Value A | Value B | Delta | Status | Tabs
1 | Revenue (JDR) = Contract Final | 1811843 | 1811843 |  |  | 1↔8
2 | Expenses = Labor+Material+OH+Burden+Tax | 925434.96 | 925434.96 |  |  | 1↔3
3 | Net Profit = Revenue - Expenses | 886408.04 | 886408.04 |  |  | 1↔Derived
4 | JDR Source: AP+PR+GL = Expenses | 925434.96 | 925434.96 |  |  | 1↔Derived (footer)
5 | Budget vs Actual (code 999) = -Revenue | 1811843 | 1811843 |  |  | 2↔1
6 | Total Labor Hours = Worker hours sum | 17098 | 17061 |  |  | 5↔2
7 | Labor Cost = Worker gross sum | 379757.5 | 379509 |  |  | 5↔3
8 | Vendor total ≈ AP footer | 299677.23 | 299677.23 |  |  | 12↔1 (approximate)
9 | Invoice count | 18 | 18 |  |  | 9↔11
10 | Contract Final - Orig = CO implied | 48363 | 48363 |  |  | 11↔Derived
11 | Retainage outstanding | 90592.15 | 90592.15 |  |  | 9↔JDR footer
12 | Retainage sum from invoices | 90592.15 | 90592.15 |  |  | 9↔JDR footer
13 | Aggregate billing Total before retention = Revenue | 1811843 | 1811843 |  |  | 9↔Billing XLSX
14 | Aggregate billing Retention = JDR Retainage | 90592.15 | 90592.15 |  |  | 9↔Billing XLSX
15 | Contract net + WSST = Contract gross | 1932774.08 | 1932774.08 |  |  | Contract header
16 | Worker count | 40 | 40 |  |  | 5↔11
17 | Cost code count | 30 | 30 |  |  | 2↔16
18 | COR documented ≈ CO implied | 54663 | 48363 |  |  | 8↔13
SOURCES
Job #2024 — Cortex v2 17-tab (built from-scratch)
Canonical financial source: 2024 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 285 pages)
JDR Job Totals: Revenue $1,811,843.00 / Expenses $925,434.96 / Net $886,408.04 / Retainage $90,592.15
JDR Source breakdown: GL $48,153.01 · AP $299,677.23 · PR $577,604.72 · AR $1,811,843.00
Contract: mgb contract brett signed OCR_D.pdf (21-Apr-2015, Lump Sum $1,932,774.08 gross incl $169,294 WSST = $1,763,480 net)
Billing: MGB AGGREGATE BILLING.xlsx (16 billings + retainage release row, ties to JDR) — aggregate billings tie perfectly to JDR revenue and retainage
COR Summary: Change Orders/COR_s/Ballard MG - Outstanding COR_s.xlsx — 17 CORs with $ pricing + CO# assignments (priced sum $54,663.00 vs JDR-implied $48,363.00)
Budget Transfers: Change Orders/BUDGET TRANSFERS/ XLSX for CO#1-4, 6-8 (labor/burden/material line items)
ASI-RFI: 52 PDFs (ASI-007/010/014/016/024/025/026/033/039/039-R1/045 + RFIs)
Submittals: 80+ across 6 category subfolders
Permits: 8 permits (plumbing, plumbing-renewed, backflow, backflow-renewed, gas, boiler x2, application)
POs: 138+ total (102 completed / 0 placed / 36 scheduled) + Trim PO_s subfolder
Closeout: O&M_s, lien waivers, Insurance, Zoeller Startup, Uponor Warranty, OWP warranty doc
Unresolved: (a) $90,592 retainage outstanding 9+ years; (b) $20.6K condensation-drain labor (code 143) unbudgeted and not CO'd; (c) COR total overshoots JDR delta by ~$6.3K (likely repricings/WSST)
TIES = within $1 · WITHIN = within 5% · NEAR = within 15% · OFF = investigate