## Overview
Job #2026 · Synergy 525 Boren — Fox and Finch Apartments
Cortex JCR Cortex v2 • Synergy Construction, Inc. (customer code 2026SC) • 525 Boren Ave, Seattle (per invoice descriptions) • 106-pg JDR is sole financial source
PROJECT OVERVIEW
Project Job # | 2026 |  | 2026 Job Detail Report.pdf (Sage Timberline export, printed 04/03/2026 1:51PM, 106 pages) header
Project Name (Sage) | Synergy 525 Boren |  | 2026 Job Detail Report.pdf (Sage Timberline export, printed 04/03/2026 1:51PM, 106 pages) header
Project Description | Fox and Finch Apartments — 525 Boren Midrise Apartment / Mixed Use, 525 Boren Avenue North, Seattle WA 98109 |  | Contract/525 Boren Contract.pdf header
General Contractor | Synergy Construction, Inc. (14040 NE 181st St, Woodinville WA 98072) |  | Contract/525 Boren Contract.pdf
Customer Code (Sage) | 2026SC |  | 2026 Job Detail Report.pdf (Sage Timberline export, printed 04/03/2026 1:51PM, 106 pages)
Jobsite Location | 525 Boren Ave N, Seattle, WA 98109 · Parcel 1983200345 |  | Permits/Boren Gas permit.pdf
Synergy Project Reference | Synergy project #750 · Subcontract #007 · cost code 15400 |  | Contract/525 Boren Contract.pdf
Unit Count | 60 residential units (inferred from 60 TOTO C744E bowls + 60 ST743E tanks) |  | Vendor Quotes/BOREN - Vender Quote Spreadsheet.xlsx
Fixture Inventory | 669 fixture-line units across 20 SKUs — 60 toilets (56 TOTO C744E + 4 C744EL ADA) · 60 china lavs (TOTO LT231) · 60 Grohe lav faucets · 51 kitchen faucets · 59 shower valve trims · 17 tub spouts · 59 Aquatic tub/shower units (32×1483EN + 17×2603SMTE + 10×1423C) · 3 Moen ADA hand-shower kits · 1 Mustee dog wash + 1 Kohler grid drain. Submittals on file: 12 fixture PDFs + 8 tub/shower PDFs. |  | Vendor Quotes/BOREN - Vender Quote Spreadsheet.xlsx · Submittals/FIXTURE SUBMITTALS/ · Submittals/TUB & SHOWER SUBMITTALS/
Building Profile | 7-story midrise apartment (L1-L7 + rooftop mech room + basement) per SOV — mixed-use with L1 retail + dog wash + leasing office |  | Billing/525 Boren SOV template with contract value.xlsx
Contract / PO Document | Subcontract #007 — Lump Sum $825,370.00 (AGC of Washington 2006 Ed.) + 8% retainage clause |  | Contract/525 Boren Contract.pdf
Contract Type | Lump Sum subcontract per AGC Washington 2006 GC template |  | Contract/525 Boren Contract.pdf
Plans / Specifications | Full plumbing construction set (525-Plumbing Construction Set PR.pdf) + 11 MEP DWGs (basement, L1-L7, Roof) in Brett 525 Boren/; MEP Superplots 2016-02/02/03 |  | Folder scan — Brett 525 Boren/
Change Orders (on file) | 2 CORs (COR#01 Temp Gas $357 executed as CO, COR#02 Unclog Toilet $293 warranty-era); 1 Budget Transfer (CO#02); SOV shows +$4,940 adjustment between draws #1-#2 |  | Change Orders/COR_s · Change Orders/CO_s · Billing/*.xlsx
ASI / RFI | 2 change-events: ASI-12 MEP Peer Review Response + PR-02 Media Room Redesign |  | ASI-RFI/
Submittals | 44 submittals across 7 categories (Equipment-7, Fixtures-12, Material-5, Responses-1, Sleeving Plans-1, Tub/Shower-8, Underground/Garage-10) |  | Submittals/ subfolder scan
Permits | 5 permits (Plumbing, Gas, Gas Temp Heat, Backflow, Renewed Plumbing+Gas+Backflow). Gas permit SR1397520 to 525 Boren LLC. |  | Permits/
Insurance / Closeout | Certificate of Insurance 2016-17 on file; O&M manual + Warranty package; 5 vendor lien waivers (Consolidated/Ferguson/Keller/Rosen + template); Full & Final Lien Claim Waiver |  | Insurance/ · O&M_s/ · Vendor Lien Waivers/ · Billing/
Billing | 15 pay applications (App #1 2016-03-20 → App #15 2017-07-20), Contract Total $830,667.00 @ App #15. 16.5-mo billing window. |  | Billing/525 Boren SOV draw #*.xlsx
Invoices (subfolder) | 36 AP invoice PDFs filed by cost code (212-Canout:5, 230-Trim:9, 241-Water Main:13, 243-Cond-Drain:2, 601-Eng:3, 607-Other:4) |  | Invoices/
Vendor Quotes (bid file) | Bidding spreadsheet w/ 5 suppliers (CONS/KELLER/FEI/ROSEN + alternate); 7 quote docs on file |  | Vendor Quotes/
Work Period | 03/09/2016 – 07/24/2017 (~16.5 months, per payroll/AR dates) |  | 2026 Job Detail Report.pdf (Sage Timberline export, printed 04/03/2026 1:51PM, 106 pages)
Warranty Incident | Retail Sewer Problem — 30 photos+videos dated 12/06/2018 (~17 months post-closeout). COR#02 Unclog Toilet $293 issued 10/27/2017. |  | Retail Sewer Problem/ · Change Orders/COR_s/
Total Unique Documents Reviewed | 130+ |  | Full folder scan of owp-2026/2026-Synergy, 525 Boren -Fox and Finch Apts 4/ including Contract, COs/CORs, Billing, Submittals, Invoices, Permits, ASI-RFI, Plans, Vendor Lien Waivers, Vendor Quotes
CONTRACT VALUE |  | NET PROFIT | DIRECT COST | LABOR HOURS
830667 |  | 282699.94 | 547967.06 | 8541.5
Original $825,370.00 + $4,940.00 SOV adj + $357.00 CO#1 |  | 34.0% margin | 66.0% of revenue | 25 workers
SCOPE OF WORK (inferred from cost codes)
Complete plumbing rough-in + finish for Fox and Finch Apartments at 525 Boren Ave N, Seattle (60 residential units · 7 floors + basement + rooftop mech room · mixed-use L1 retail/leasing/dog-wash).
SOV-billed phases: pre-con/design ($62k), permits, basement UG + duplex sewage pump, basement water room (PRVs/backflow), domestic/irrigation/retail water mains, gas piping, ProSet canout per level, roughin per level (L1-L7), fiberglass tub stock+install per level, rooftop mech room (water heaters + expansion/circ/mixing), trim package.
Cost codes: 100-150 labor (Supervision, Takeoff, UG, Garage, Canout, Rough-in, Finish, Gas, Water Main/Insul, Mech Room); 210-244 material (incl 243 Condensation Drains); 600 Sub / 601 Eng / 603 Permits / 607 Other.
Contract signed per AGC Washington 2006 Ed. — Lump Sum $825,370 (Subcontract #007, Synergy project #750, cost code 15400), with 8% retainage withholding per AGC template.
Full plumbing construction set on file (525-Plumbing Construction Set PR.pdf + 11 MEP DWGs, L1-L7 + Roof + UG/Below Roof + Vault Shift), plus MEP Superplots series 2016-02-09 / 02-22 / 03-07.
SOURCES
Canonical source: 2026 Job Detail Report.pdf (Sage Timberline export, printed 04/03/2026 1:51PM, 106 pages)
Job totals (JDR footer): Revenue $830,667.00 / Expenses $547,967.06 / Net $282,699.94 / Retainage $41,533.35
Source breakdown (JDR footer): GL $30,577.13 · AP $197,171.05 · PR $320,218.88 · AR $830,667.00
Secondary folder items: Plans/525 Boren MEP/ELEC (electrical only); Franklin 525 Boren/In to FE/1 Revit Model Sharing/ (backup)
NO contract/PO, submittal, RFI, CO, ASI, billing, insurance, or closeout document folders exist in project.

## Budget vs Actual
Budget vs Actual
All 28 cost codes from JDR. Contract adjusted $825,370 → $830,667 (implied COs +$5,297.00).
Cost Code | Description | Original Budget | Revised Budget | Actual | Variance | % of Revised | Hours | Source
100 | Supervision | 7840 | 7840 | 2078.5 |  |  | 45.5 | 2026 Job Detail Report.pdf (Sage Timberline export, printed 04/03/2026 1:51PM, 106 pages)
101 | Takeoff & Purchase Labor | 7840 | 7840 | 5998 |  |  | 130 | 2026 Job Detail Report.pdf (Sage Timberline export, printed 04/03/2026 1:51PM, 106 pages)
110 | Underground Labor | 5450 | 5450 | 2899.5 |  |  | 104 | 2026 Job Detail Report.pdf (Sage Timberline export, printed 04/03/2026 1:51PM, 106 pages)
111 | Garage Labor | 13550 | 13550 | 22565 |  |  | 870 | 2026 Job Detail Report.pdf (Sage Timberline export, printed 04/03/2026 1:51PM, 106 pages)
112 | Canout Labor | 4375 | 4375 | 9448.5 |  |  | 327 | 2026 Job Detail Report.pdf (Sage Timberline export, printed 04/03/2026 1:51PM, 106 pages)
120 | Roughin Labor | 101805 | 101946 | 116564.5 |  |  | 4901 | 2026 Job Detail Report.pdf (Sage Timberline export, printed 04/03/2026 1:51PM, 106 pages)
130 | Finish Labor | 16920 | 16920 | 12520 |  |  | 625.5 | 2026 Job Detail Report.pdf (Sage Timberline export, printed 04/03/2026 1:51PM, 106 pages)
140 | Gas Labor | 6000 | 6000 | 3916 |  |  | 133.5 | 2026 Job Detail Report.pdf (Sage Timberline export, printed 04/03/2026 1:51PM, 106 pages)
141 | Water Main/Insulation Lab | 18820 | 18820 | 20543 |  |  | 967 | 2026 Job Detail Report.pdf (Sage Timberline export, printed 04/03/2026 1:51PM, 106 pages)
142 | Mech Room Labor | 9180 | 9180 | 14056.5 |  |  | 435 | 2026 Job Detail Report.pdf (Sage Timberline export, printed 04/03/2026 1:51PM, 106 pages)
150 | Warranty Labor | 0 | 0 | 126 |  |  | 3 | 2026 Job Detail Report.pdf (Sage Timberline export, printed 04/03/2026 1:51PM, 106 pages)
210 | Underground Material | 11900 | 11900 | 6574.76 |  |  |  | 2026 Job Detail Report.pdf (Sage Timberline export, printed 04/03/2026 1:51PM, 106 pages)
211 | Garage Material | 16750 | 16750 | 16318.46 |  |  |  | 2026 Job Detail Report.pdf (Sage Timberline export, printed 04/03/2026 1:51PM, 106 pages)
212 | Canout Material | 4375 | 4375 | 5237.21 |  |  |  | 2026 Job Detail Report.pdf (Sage Timberline export, printed 04/03/2026 1:51PM, 106 pages)
220 | Roughin Material | 60210 | 60210 | 42655.4 |  |  |  | 2026 Job Detail Report.pdf (Sage Timberline export, printed 04/03/2026 1:51PM, 106 pages)
230 | Finish Material | 78595 | 82765 | 68397.28 |  |  |  | 2026 Job Detail Report.pdf (Sage Timberline export, printed 04/03/2026 1:51PM, 106 pages)
240 | Gas Material | 3600 | 3600 | 625.77 |  |  |  | 2026 Job Detail Report.pdf (Sage Timberline export, printed 04/03/2026 1:51PM, 106 pages)
241 | Water Main/Insulation Mat | 32420 | 32420 | 21103.03 |  |  |  | 2026 Job Detail Report.pdf (Sage Timberline export, printed 04/03/2026 1:51PM, 106 pages)
242 | Mech Room Material | 53250 | 53250 | 33752.74 |  |  |  | 2026 Job Detail Report.pdf (Sage Timberline export, printed 04/03/2026 1:51PM, 106 pages)
243 | Condensation Drains Mat | 0 | 0 | 27.08 |  |  |  | 2026 Job Detail Report.pdf (Sage Timberline export, printed 04/03/2026 1:51PM, 106 pages)
244 | Fire Caulking Material | 0 | 0 | 178.63 |  |  |  | 2026 Job Detail Report.pdf (Sage Timberline export, printed 04/03/2026 1:51PM, 106 pages)
600 | Subcontractor | 500 | 500 | 186 |  |  |  | 2026 Job Detail Report.pdf (Sage Timberline export, printed 04/03/2026 1:51PM, 106 pages)
601 | Engineering/Plans | 35000 | 35000 | 17344 |  |  |  | 2026 Job Detail Report.pdf (Sage Timberline export, printed 04/03/2026 1:51PM, 106 pages)
603 | Permits & Licenses | 5420 | 5560 | 3352 |  |  |  | 2026 Job Detail Report.pdf (Sage Timberline export, printed 04/03/2026 1:51PM, 106 pages)
607 | Other Expenses | 15000 | 15000 | 11995.82 |  |  |  | 2026 Job Detail Report.pdf (Sage Timberline export, printed 04/03/2026 1:51PM, 106 pages)
995 | Payroll Burden | 83136.63 | 83200.08 | 93383.48 |  |  |  | 2026 Job Detail Report.pdf (Sage Timberline export, printed 04/03/2026 1:51PM, 106 pages)
998 | Payroll Taxes | 14671.17 | 14681.96 | 16119.9 |  |  |  | 2026 Job Detail Report.pdf (Sage Timberline export, printed 04/03/2026 1:51PM, 106 pages)
999 | Sales | -825370 | -830667 | -830667 |  |  |  | 2026 Job Detail Report.pdf (Sage Timberline export, printed 04/03/2026 1:51PM, 106 pages)
TOTAL

## Cost Breakdown
Cost Breakdown by Category
Direct cost composition by category from JDR cost codes
Category | Cost Codes | Actual $ | % of Direct Cost | % of Revenue | Source
Labor | 100,101,110,111,112,120,130,140,141,142,150 | 210715.5 |  |  | 2026 Job Detail Report.pdf (Sage Timberline export, printed 04/03/2026 1:51PM, 106 pages)
Material | 210,211,212,220,230,240,241,242,243,244 | 194870.36 |  |  | 2026 Job Detail Report.pdf (Sage Timberline export, printed 04/03/2026 1:51PM, 106 pages)
Subcontractor + Engineering + Permits + Other | 600,601,603,607 | 32877.82 |  |  | 2026 Job Detail Report.pdf (Sage Timberline export, printed 04/03/2026 1:51PM, 106 pages)
Payroll Burden | 995 | 93383.48 |  |  | 2026 Job Detail Report.pdf (Sage Timberline export, printed 04/03/2026 1:51PM, 106 pages)
Payroll Taxes | 998 | 16119.9 |  |  | 2026 Job Detail Report.pdf (Sage Timberline export, printed 04/03/2026 1:51PM, 106 pages)
TOTAL DIRECT COST |  |  | 100%

## Material
Material Purchases — AP Vendors
Material + subcontractor spend by vendor (AP records from JDR)
Vendor ID | Vendor Name | Total Spend | # Transactions | Category (inferred) | Source
2026RS | Rosen Supply Company, Inc. $Boren | 49659.22 | 41 | Plumbing / Supplies | 2026 Job Detail Report.pdf (Sage Timberline export, printed 04/03/2026 1:51PM, 106 pages)
2026CS | Consolidated Supply Co $Boren | 49441.46 | 48 | Plumbing / Supplies | 2026 Job Detail Report.pdf (Sage Timberline export, printed 04/03/2026 1:51PM, 106 pages)
2026FE | Ferguson Enterprises, Inc. $525 Boren | 28251.03 | 12 | Plumbing / Supplies | 2026 Job Detail Report.pdf (Sage Timberline export, printed 04/03/2026 1:51PM, 106 pages)
2026KS | Keller Supply Company $Boren | 23867.69 | 20 | Plumbing / Supplies | 2026 Job Detail Report.pdf (Sage Timberline export, printed 04/03/2026 1:51PM, 106 pages)
1625FE | Franklin Engineering | 17344 | 9 | Engineering (601) | 2026 Job Detail Report.pdf (Sage Timberline export, printed 04/03/2026 1:51PM, 106 pages)
1234BA | Bank of America CC | 11361.41 | 18 | Credit Card (mixed) | 2026 Job Detail Report.pdf (Sage Timberline export, printed 04/03/2026 1:51PM, 106 pages)
1401LU | Lotus United, LLC | 8215 | 1 | Other (inferred 607) | 2026 Job Detail Report.pdf (Sage Timberline export, printed 04/03/2026 1:51PM, 106 pages)
1234CO | Capital One Credit Card | 5734.1 | 32 | Credit Card (mixed) | 2026 Job Detail Report.pdf (Sage Timberline export, printed 04/03/2026 1:51PM, 106 pages)
3612MS | Mechanical Sales, Inc. | 2098.04 | 2 | Plumbing / Supplies | 2026 Job Detail Report.pdf (Sage Timberline export, printed 04/03/2026 1:51PM, 106 pages)
1611AS | Beacon Building Products $Atlas | 733.88 | 4 | Plumbing / Supplies | 2026 Job Detail Report.pdf (Sage Timberline export, printed 04/03/2026 1:51PM, 106 pages)
2132MH | Manor Hardware & Construction Supply | 305.76 | 1 | Plumbing / Supplies | 2026 Job Detail Report.pdf (Sage Timberline export, printed 04/03/2026 1:51PM, 106 pages)
1175FE | Ferguson Enterprises, Inc. #3007 | 296.86 | 2 | Plumbing / Supplies | 2026 Job Detail Report.pdf (Sage Timberline export, printed 04/03/2026 1:51PM, 106 pages)
1421RA | R.A. Brown Backflow Testing | 186 | 1 | Testing subcontractor | 2026 Job Detail Report.pdf (Sage Timberline export, printed 04/03/2026 1:51PM, 106 pages)
1130CS | Consolidated Supply Co. | -323.4 | 1 | Plumbing / Supplies | 2026 Job Detail Report.pdf (Sage Timberline export, printed 04/03/2026 1:51PM, 106 pages)
TOTAL
NOTE: AP total per JDR footer = $197,171.05. Sum of vendor totals here should approximate this (credit card rows aggregate misc. small expenses).

## Crew & Labor
Crew & Labor — Worker Roster
All 25 unique payroll workers from JDR. Individual-line detail omitted (thousands of entries); roll-up by worker.
Worker ID | Worker Name | Total Hours | Gross Pay | Blended Wage ($/hr) | # Work Days | Source
CA74 | Castaneda Martinez, Gustavo | 1798 | 65368 |  | 61 | 2026 Job Detail Report.pdf (Sage Timberline export, printed 04/03/2026 1:51PM, 106 pages)
CA73 | Castaneda Juarez, Gustavo | 1290 | 26856 |  | 38 | 2026 Job Detail Report.pdf (Sage Timberline export, printed 04/03/2026 1:51PM, 106 pages)
CA72 | Castaneda Juarez, Edgar D | 1235 | 26475 |  | 37 | 2026 Job Detail Report.pdf (Sage Timberline export, printed 04/03/2026 1:51PM, 106 pages)
CA71 | Castaneda Juarez, Cesar O | 960 | 12566 |  | 32 | 2026 Job Detail Report.pdf (Sage Timberline export, printed 04/03/2026 1:51PM, 106 pages)
AM03 | Amaya Gonzalez, Edilberto A | 919 | 18191 |  | 25 | 2026 Job Detail Report.pdf (Sage Timberline export, printed 04/03/2026 1:51PM, 106 pages)
RO12 | Rodriguez Rodriguez, Aminadab N | 289 | 5491 |  | 8 | 2026 Job Detail Report.pdf (Sage Timberline export, printed 04/03/2026 1:51PM, 106 pages)
AS10 | Ascencio, Jose L | 277 | 5263 |  | 9 | 2026 Job Detail Report.pdf (Sage Timberline export, printed 04/03/2026 1:51PM, 106 pages)
RE18 | Reed, Reuben H | 247 | 8661 |  | 8 | 2026 Job Detail Report.pdf (Sage Timberline export, printed 04/03/2026 1:51PM, 106 pages)
EL33 | Eliassen, Cory H | 232 | 4104 |  | 10 | 2026 Job Detail Report.pdf (Sage Timberline export, printed 04/03/2026 1:51PM, 106 pages)
HU06 | Hubbard, Robert W | 215 | 8912.5 |  | 44 | 2026 Job Detail Report.pdf (Sage Timberline export, printed 04/03/2026 1:51PM, 106 pages)
MA71 | Martinez Reyes, Juan C | 152 | 2584 |  | 6 | 2026 Job Detail Report.pdf (Sage Timberline export, printed 04/03/2026 1:51PM, 106 pages)
SA51 | Sanchez, Derli | 144 | 2160 |  | 6 | 2026 Job Detail Report.pdf (Sage Timberline export, printed 04/03/2026 1:51PM, 106 pages)
SA54 | Sanders, Allen O | 143 | 5605.5 |  | 21 | 2026 Job Detail Report.pdf (Sage Timberline export, printed 04/03/2026 1:51PM, 106 pages)
AY19 | Ayers, Jordan L | 133 | 2394 |  | 5 | 2026 Job Detail Report.pdf (Sage Timberline export, printed 04/03/2026 1:51PM, 106 pages)
GO51 | Gomez Reyes, Edith N | 123 | 1845 |  | 4 | 2026 Job Detail Report.pdf (Sage Timberline export, printed 04/03/2026 1:51PM, 106 pages)
GE69 | Gerard, Jeffrey S | 105.5 | 4755.5 |  | 34 | 2026 Job Detail Report.pdf (Sage Timberline export, printed 04/03/2026 1:51PM, 106 pages)
LO87 | Lovo, German G | 75 | 1350 |  | 3 | 2026 Job Detail Report.pdf (Sage Timberline export, printed 04/03/2026 1:51PM, 106 pages)
GA70 | Garcia, Jordan X | 75 | 2025 |  | 3 | 2026 Job Detail Report.pdf (Sage Timberline export, printed 04/03/2026 1:51PM, 106 pages)
DO56 | Donelson, Richard T | 70 | 3321 |  | 39 | 2026 Job Detail Report.pdf (Sage Timberline export, printed 04/03/2026 1:51PM, 106 pages)
PA47 | Palma Vides, Jorge A | 67 | 1206 |  | 2 | 2026 Job Detail Report.pdf (Sage Timberline export, printed 04/03/2026 1:51PM, 106 pages)
HU04 | Hubbard, Dustin R | 24 | 441 |  | 6 | 2026 Job Detail Report.pdf (Sage Timberline export, printed 04/03/2026 1:51PM, 106 pages)
MC09 | McCabe, Thomas C | 23 | 598 |  | 2 | 2026 Job Detail Report.pdf (Sage Timberline export, printed 04/03/2026 1:51PM, 106 pages)
JO31 | Johnson, Samuel A | 16 | 256 |  | 1 | 2026 Job Detail Report.pdf (Sage Timberline export, printed 04/03/2026 1:51PM, 106 pages)
WA35 | Waites, Thaddeus Z | 7 | 259 |  | 1 | 2026 Job Detail Report.pdf (Sage Timberline export, printed 04/03/2026 1:51PM, 106 pages)
HE70 | Hernandez Gonzalez, Osbaldo | 2 | 28 |  | 1 | 2026 Job Detail Report.pdf (Sage Timberline export, printed 04/03/2026 1:51PM, 106 pages)
TOTAL

## Crew Analytics
Crew Analytics
Team-level labor productivity, concentration, and wage dispersion
TEAM-LEVEL METRICS
Metric | Value | Notes | Source
Total Workers | 25 | Unique payroll IDs | 2026 Job Detail Report.pdf (Sage Timberline export, printed 04/03/2026 1:51PM, 106 pages)
Total Labor Hours | 8541.5 | Sum of codes 100-150 | 2026 Job Detail Report.pdf (Sage Timberline export, printed 04/03/2026 1:51PM, 106 pages)
Total Gross Pay | 210715.5 | Sum of codes 100-150 | 2026 Job Detail Report.pdf (Sage Timberline export, printed 04/03/2026 1:51PM, 106 pages)
Blended Gross Wage ($/hr) | 24.6696 | Labor$ / Hrs (pre-burden) | Derived
Top Worker Hours Share | 21.05% | CA74 Castaneda Martinez, Gustavo (1798 hrs) | Derived
Top 5 Workers Hours Share | 72.61% | Concentration metric | Derived
Highest Wage Rate ($/hr) | 47.4429 | Single-worker blended | Derived
Lowest Wage Rate ($/hr) | 13.0896 | Single-worker blended | Derived
Avg Hours per Worker | 341.66 | Includes many short-tenure workers | Derived
Avg Project Days per Worker | 16.24 | Mean days | Derived

## Productivity
Productivity Metrics
Normalized labor and financial ratios
Metric | Value | Basis | Source / Note
Revenue per Labor Hour |  | Formula | Rev / Total Hrs
Profit per Labor Hour |  | Formula | Net Profit / Hrs
Labor Cost per Hour (blended) |  | Formula | Pre-burden
Fully-Loaded Labor Rate ($/hr) |  | Formula | Incl burden + taxes
Burden Multiplier |  | Formula | Fully-loaded / blended
Rough-in Hours (code 120) | 4901 | JDR | Code 120 Roughin Labor: 4901 hrs
Garage Hours (code 111) | 870 | JDR | Code 111 Garage Labor: 870 hrs
Rough-in % of Total Hours |  | Formula | Code 120 share
Gross Margin |  | Formula | Net / Revenue
Labor % of Revenue |  | Formula
Material % of Revenue |  | Formula
Direct Cost Ratio |  | Formula | All expenses / Rev

## PO Commitments
PO Commitments
Inbound contract value (GC → OWP). Outbound AP vendor commitments on Material tab.
PO # | Date | Issuer | Type | Status | Description | Amount | Source
NOT FOUND | 2016-03 (implied, first PR 03/09/16) | Synergy Construction, Inc. | NOT FOUND | Closed (100% billed) | Fox and Finch Apts plumbing (underground, rough-in, finish, gas, water main, mech room) | 830667 | 2026 Job Detail Report.pdf (Sage Timberline export, printed 04/03/2026 1:51PM, 106 pages) (cost-code budget + AR invoices). No PO document in folder.
TOTAL
NOTE: Contract $825,370.00 (code 999 Org) + $4,940 SOV adj (App#1→#2) + $357 CO#1 Temp Gas (App#15) = $830,667.00 final. Ties exactly to JDR revenue and to SOV draw #15 Contract Total.

## Billing & SOV
Billing & Schedule of Values
21 unique JDR invoices + 15 Pay-App SOV XLSX drafts on file (Mar-2016 → Jul-2017). Retainage $41,533.35 = 5.0% of revenue.
PAY APPLICATION SOV PROGRESSION (Billing/525 Boren SOV draw #*.xlsx)
App # | Date | Contract Total | This Period | Stored | Cumulative | % Complete | Source
1 | 2016-03-20 | 825370 | 49600 | 0 | 49600 | 5.97% | 525 Boren SOV draw #1.xlsx
2 | 2016-05-20 | 830310 | 48300 | 0 | 97900 | 11.79% | 525 Boren SOV draw #2 5-20-16.xlsx
3 | 2016-07-20 | 830310 | 4200 | 0 | 102100 | 12.3% | 525 Boren SOV draw #3 7-20-16.xlsx
4 | 2016-08-19 | 830310 | 17300 | 0 | 119400 | 14.38% | 525 Boren SOV draw #4 8-19-16.xlsx
5 | 2016-09-19 | 830310 | 103300 | 0 | 222700 | 26.82% | 525 Boren SOV draw #5 9-19-16.xlsx
6 | 2016-10-20 | 830310 | 167600 | 0 | 390300 | 47.01% | 525 Boren SOV draw #6 10-20-16.xlsx
7 | 2016-11-15 | 830310 | 137100 | 0 | 527400 | 63.52% | 525 Boren SOV draw #7 11-15-16.xlsx
8 | 2016-12-15 | 830310 | 144725 | 0 | 672125 | 80.95% | 525 Boren SOV draw #8 12-15-16.xlsx
9 | 2017-01-20 | 830310 | 56205 | 0 | 728330 | 87.72% | 525 Boren SOV draw #9 1-20-17.xlsx
10 | 2017-02-20 | 830310 | 4540 | 0 | 732870 | 88.27% | 525 Boren SOV draw #10 2-20-17.xlsx
11 | 2017-03-20 | 830310 | 16900 | 0 | 749770 | 90.3% | 525 Boren SOV draw #11 3-20-17.xlsx
12 | 2017-04-20 | 830310 | 23440 | 0 | 773210 | 93.12% | 525 Boren SOV draw #12 4-20-17.xlsx
13 | 2017-05-19 | 830310 | 13125 | 0 | 786335 | 94.7% | 525 Boren SOV draw #13 5-19-17.xlsx
14 | 2017-06-20 | 830310 | 43975 | 0 | 830310 | 100% | 525 Boren SOV draw #14 6-20-17.xlsx
15 | 2017-07-20 | 830667 | 357 | 0 | 830667 | 100% | 525 Boren SOV draw #15 7-20-17.xlsx (CO#1 Temp Gas +$357)
TOTAL BILLED (PAY APPS)
PAY APPS RECONCILIATION: Sum of 'This Period' = $830,667 (ties exactly to Contract Total @ App#15 and JDR revenue). Billing cadence 16.5 mo: slow start Mar-May 2016 (~$100K/2 mo underground+design) → roughin ramp Aug-Nov 2016 (52% of value in 4 months) → trim/punchlist Dec 2016-Jun 2017.
JDR AR INVOICES (Sage AR ledger)
Invoice # | Date | Total Billed (signed) | Retainage (signed) | # Lines | Source
036700 | 03/21/16 | -62000 | -3100 | 1 | 2026 Job Detail Report.pdf (Sage Timberline export, printed 04/03/2026 1:51PM, 106 pages)
036701 | 03/21/16 | 62000 | 3100 | 1 | 2026 Job Detail Report.pdf (Sage Timberline export, printed 04/03/2026 1:51PM, 106 pages)
036702 | 03/21/16 | -49600 | -2480 | 1 | 2026 Job Detail Report.pdf (Sage Timberline export, printed 04/03/2026 1:51PM, 106 pages)
036725 | 05/20/16 | -48300 | -2415 | 3 | 2026 Job Detail Report.pdf (Sage Timberline export, printed 04/03/2026 1:51PM, 106 pages)
036757 | 07/20/16 | -4200 | -210 | 1 | 2026 Job Detail Report.pdf (Sage Timberline export, printed 04/03/2026 1:51PM, 106 pages)
036770 | 08/19/16 | -17300 | -865 | 2 | 2026 Job Detail Report.pdf (Sage Timberline export, printed 04/03/2026 1:51PM, 106 pages)
036783 | 09/19/16 | -103300 | -5165 | 4 | 2026 Job Detail Report.pdf (Sage Timberline export, printed 04/03/2026 1:51PM, 106 pages)
036794 | 10/20/16 | -167600 | -8380 | 7 | 2026 Job Detail Report.pdf (Sage Timberline export, printed 04/03/2026 1:51PM, 106 pages)
036800 | 11/15/16 | -137100 | -6855 | 9 | 2026 Job Detail Report.pdf (Sage Timberline export, printed 04/03/2026 1:51PM, 106 pages)
036807 | 12/15/16 | -144725 | -7236.25 | 7 | 2026 Job Detail Report.pdf (Sage Timberline export, printed 04/03/2026 1:51PM, 106 pages)
036822 | 01/20/17 | -56205 | -2810.25 | 7 | 2026 Job Detail Report.pdf (Sage Timberline export, printed 04/03/2026 1:51PM, 106 pages)
036836 | 02/20/17 | -4540 | -227 | 2 | 2026 Job Detail Report.pdf (Sage Timberline export, printed 04/03/2026 1:51PM, 106 pages)
036850 | 03/17/17 | -16900 | -845 | 3 | 2026 Job Detail Report.pdf (Sage Timberline export, printed 04/03/2026 1:51PM, 106 pages)
036861 | 04/20/17 | -18500 | -925 | 2 | 2026 Job Detail Report.pdf (Sage Timberline export, printed 04/03/2026 1:51PM, 106 pages)
036863 | 04/20/17 | 18500 | 925 | 2 | 2026 Job Detail Report.pdf (Sage Timberline export, printed 04/03/2026 1:51PM, 106 pages)
036864 | 04/20/17 | -23440 | -1172 | 3 | 2026 Job Detail Report.pdf (Sage Timberline export, printed 04/03/2026 1:51PM, 106 pages)
036881 | 05/19/17 | -18065 | -903.25 | 3 | 2026 Job Detail Report.pdf (Sage Timberline export, printed 04/03/2026 1:51PM, 106 pages)
036886 | 05/19/17 | 18065 | 903.25 | 3 | 2026 Job Detail Report.pdf (Sage Timberline export, printed 04/03/2026 1:51PM, 106 pages)
036887 | 05/19/17 | -13125 | -656.25 | 2 | 2026 Job Detail Report.pdf (Sage Timberline export, printed 04/03/2026 1:51PM, 106 pages)
036902 | 06/19/17 | -43975 | -2198.75 | 6 | 2026 Job Detail Report.pdf (Sage Timberline export, printed 04/03/2026 1:51PM, 106 pages)
036923 | 07/24/17 | -357 | -17.85 | 1 | 2026 Job Detail Report.pdf (Sage Timberline export, printed 04/03/2026 1:51PM, 106 pages)
TOTAL (net of reversals)
NOTE: JDR AR includes reversal+reissue pairs (Sage practice). Net cumulative billed = $830,667.00 revenue + $41,533.35 retainage, matches Pay App #15 Contract Total. Retainage NOT released as of JDR 04/03/2026. Full & Final Lien Claim Waiver on file (Billing folder).

## Insights
Insights & Observations
Narrative findings from JDR analysis
# | Insight | Detail | Confidence | Source
1 | HEALTHY MARGIN | Net profit $282,699.94 on $830,667.00 revenue = 34.0% gross margin. Within healthy range for multifamily plumbing. | Verified | 2026 Job Detail Report.pdf (Sage Timberline export, printed 04/03/2026 1:51PM, 106 pages)
2 | LABOR-HEAVY EXECUTION | Total labor cost $210,715.50 (25.4% of rev) across 8,541.5 hrs and 25 workers. Rough-in (code 120) alone = 4901 hrs = 57% of labor. | Verified | 2026 Job Detail Report.pdf (Sage Timberline export, printed 04/03/2026 1:51PM, 106 pages)
3 | BURDEN-HEAVY | Payroll Burden $93,383.48 + Taxes $16,119.90 = $109,503.38 = 52.0% of gross labor. Burden multiplier = 1.52x. | Verified | 2026 Job Detail Report.pdf (Sage Timberline export, printed 04/03/2026 1:51PM, 106 pages)
4 | TOP-WORKER CONCENTRATION | Castaneda Martinez, Gustavo (ID CA74) alone logged 1798 hours = 21.1% of project labor. Top 5 workers = 72.6%. | Verified | 2026 Job Detail Report.pdf (Sage Timberline export, printed 04/03/2026 1:51PM, 106 pages)
5 | VENDOR CONCENTRATION | Top vendor Rosen Supply Company, Inc. $Boren ($49,659.22). Top 4 vendors (Rosen, Consolidated Supply, Ferguson, Keller) account for majority of material spend. | Verified | 2026 Job Detail Report.pdf (Sage Timberline export, printed 04/03/2026 1:51PM, 106 pages)
6 | CONTRACT GROWTH MODEST | Original contract $825,370.00 → Final $830,667.00 = +$5,297.00 (0.64%). Break-down: +$4,940 SOV adj (App#1→#2 May-2016) + $357 CO#1 Temp Gas (App#15 Jul-2017). Tight CO discipline. | Verified | 2026 Job Detail Report.pdf (Sage Timberline export, printed 04/03/2026 1:51PM, 106 pages) + Billing SOVs
7 | CERTAIN COST CODES OVER BUDGET | Garage Labor (111) ran 67% over budget ($22,565 vs $13,550). Canout Labor (112) ran 116% over. Mech Room Labor (142) ran 53% over. Offset by Rough-in Material (220), Gas Labor (140), Supervision (100) under budget. | Verified | 2026 Job Detail Report.pdf (Sage Timberline export, printed 04/03/2026 1:51PM, 106 pages)
8 | RETAINAGE OUTSTANDING | Retainage $41,533.35 still shown outstanding on JDR dated 04/03/2026, despite last work posting 07/24/2017. Likely closeout release pending or reconciliation needed. | Verified | 2026 Job Detail Report.pdf (Sage Timberline export, printed 04/03/2026 1:51PM, 106 pages)
9 | DOCUMENT COMPLETENESS | Project folder (Apts 4/) is substantially complete: Contract (AGC LS Subcontract #007), 2 CORs + 1 executed CO, 15 Pay App SOV XLSX, 44 submittals across 7 categories, 2 ASI/PR docs, 5 permits, 5 vendor lien waivers, full plumbing plan set + 11 DWGs + MEP Superplots, O&M + Warranty package, Certificate of Insurance, Full & Final Lien Claim Waiver. 130+ documents total. | High | Folder scan of owp-2026/2026-Synergy, 525 Boren -Fox and Finch Apts 4/
10 | WARRANTY EVENT | Retail Sewer Problem documented with 30 photos+videos on 12/06/2018 (~17 months post-closeout). Paired with 'Sewer Problem pricing' COR XLSX (PM + Foreman + Apprentice + camera). No CO resulted — likely absorbed as backcharge or warranty obligation. COR#02 Unclog Toilet $293 (Oct-2017) may be related. | Verified | Retail Sewer Problem/ (30 JPG/MP4 files) + Change Orders/COR_s/Sewer Problem pricing.xlsx
11 | CONTRACT STRUCTURE | Subcontract #007 (Synergy project #750, cost code 15400) under AGC of Washington 2006 Ed. template. Lump Sum $825,370.00 with 8% retainage withholding clause. Standard Synergy flow-down provisions. | Verified | Contract/525 Boren Contract.pdf
12 | AR REVERSAL PATTERN | 21 unique invoice numbers contain multiple reversal+reissue pairs (e.g. 036863/036864, 036886/036887). Standard Sage AR correction practice; net billings tie to revenue $830,667 exactly. | Verified | 2026 Job Detail Report.pdf (Sage Timberline export, printed 04/03/2026 1:51PM, 106 pages)
13 | LONG-DURATION JOB | Work span 03/09/2016 – 07/24/2017 = ~16.5 months. Late AR entries (through July 2017) suggest punchlist / closeout billing pattern. | Verified | 2026 Job Detail Report.pdf (Sage Timberline export, printed 04/03/2026 1:51PM, 106 pages)

## Benchmark KPIs
Benchmark KPIs
Normalized metrics for cross-project comparison
KPI | Data Name | Value | Category | Notes | Confidence | Source Document
Job Number | job_number | 2026 | Profile | OWP job ID | Verified | 2026 Job Detail Report.pdf (Sage Timberline export, printed 04/03/2026 1:51PM, 106 pages)
Job Name | job_name | Synergy 525 Boren | Profile | Sage short name | Verified | 2026 Job Detail Report.pdf (Sage Timberline export, printed 04/03/2026 1:51PM, 106 pages)
Project Description | project_desc | Fox and Finch Apts @ 525 Boren | Profile | From AR lines | Verified | 2026 Job Detail Report.pdf (Sage Timberline export, printed 04/03/2026 1:51PM, 106 pages)
General Contractor | general_contractor | Synergy Construction, Inc. | Profile | Customer 2026SC | Verified | 2026 Job Detail Report.pdf (Sage Timberline export, printed 04/03/2026 1:51PM, 106 pages)
Location | location | 525 Boren Ave, Seattle, WA | Profile | From AR description (no plans) | Medium | 2026 Job Detail Report.pdf (Sage Timberline export, printed 04/03/2026 1:51PM, 106 pages)
Project Type | project_type | Multifamily New Construction — Plumbing | Profile | Inferred from cost codes | Medium | Inferred
Work Start Date | start_date | 2016-03-09 | Profile | First payroll date | Verified | 2026 Job Detail Report.pdf (Sage Timberline export, printed 04/03/2026 1:51PM, 106 pages)
Work End Date | end_date | 2017-07-24 | Profile | Last AR posting | Verified | 2026 Job Detail Report.pdf (Sage Timberline export, printed 04/03/2026 1:51PM, 106 pages)
Duration (months) | duration_months | 16.5 | Profile | Payroll + AR span | Verified | Derived
Unit Count | unit_count | NOT FOUND | Profile | No plans/permit available | Low | Folder scan
Fixture Count | fixture_count | NOT FOUND | Profile | No fixture schedule available | Low | Folder scan
Contract Original | contract_original | 825370 | Financial | Code 999 Org Budget | Verified | 2026 Job Detail Report.pdf (Sage Timberline export, printed 04/03/2026 1:51PM, 106 pages)
Contract Final | contract_final | 830667 | Financial | Code 999 Rev Budget = AR total | Verified | 2026 Job Detail Report.pdf (Sage Timberline export, printed 04/03/2026 1:51PM, 106 pages)
Change Orders ($) | change_orders | 5297 | Financial | Implied from budget revision | Medium | Derived
Change Order % of Contract | co_pct | 0.6418% | Financial |  | Medium | Derived
Revenue | revenue | 830667 | Financial | AR total (net of reversals) | Verified | 2026 Job Detail Report.pdf (Sage Timberline export, printed 04/03/2026 1:51PM, 106 pages)
Direct Cost | direct_cost | 547967.06 | Financial | JDR Job Totals Expenses | Verified | 2026 Job Detail Report.pdf (Sage Timberline export, printed 04/03/2026 1:51PM, 106 pages)
Net Profit | net_profit | 282699.94 | Financial | Rev - Expenses | Verified | 2026 Job Detail Report.pdf (Sage Timberline export, printed 04/03/2026 1:51PM, 106 pages)
Gross Margin | gross_margin | 34.03% | Financial |  | Verified | Derived
Retainage Outstanding | retainage | 41533.35 | Financial | Still open per JDR | Verified | 2026 Job Detail Report.pdf (Sage Timberline export, printed 04/03/2026 1:51PM, 106 pages)
Retainage % of Revenue | retainage_pct | 5% | Financial |  | Verified | Derived
Labor Cost | labor_cost | 210715.5 | Labor | Codes 100-150 | Verified | 2026 Job Detail Report.pdf (Sage Timberline export, printed 04/03/2026 1:51PM, 106 pages)
Material Cost | material_cost | 194870.36 | Material | Codes 210-244 | Verified | 2026 Job Detail Report.pdf (Sage Timberline export, printed 04/03/2026 1:51PM, 106 pages)
Subcontractor+OH Cost | overhead_cost | 32877.82 | Financial | Codes 600,601,603,607 | Verified | 2026 Job Detail Report.pdf (Sage Timberline export, printed 04/03/2026 1:51PM, 106 pages)
Burden Cost | burden_cost | 93383.48 | Labor | Code 995 | Verified | 2026 Job Detail Report.pdf (Sage Timberline export, printed 04/03/2026 1:51PM, 106 pages)
Tax Cost | tax_cost | 16119.9 | Labor | Code 998 | Verified | 2026 Job Detail Report.pdf (Sage Timberline export, printed 04/03/2026 1:51PM, 106 pages)
Total Labor Hours | total_hours | 8541.5 | Labor | Sum labor cost codes | Verified | 2026 Job Detail Report.pdf (Sage Timberline export, printed 04/03/2026 1:51PM, 106 pages)
Total Workers | total_workers | 25 | Labor | Unique payroll IDs | Verified | 2026 Job Detail Report.pdf (Sage Timberline export, printed 04/03/2026 1:51PM, 106 pages)
Blended Gross Wage ($/hr) | blended_gross_wage | 24.6696 | Labor | Pre-burden | Verified | Derived
Fully-Loaded Wage ($/hr) | fully_loaded_wage | 37.4898 | Labor | Incl burden + tax | Verified | Derived
Burden Multiplier | burden_multiplier | 1.5197 | Labor | Fully-loaded/blended | Verified | Derived
Rough-in Hours | roughin_hours | 4901 | Labor | Code 120 | Verified | 2026 Job Detail Report.pdf (Sage Timberline export, printed 04/03/2026 1:51PM, 106 pages)
Finish Hours | finish_hours | 625.5 | Labor | Code 130 | Verified | 2026 Job Detail Report.pdf (Sage Timberline export, printed 04/03/2026 1:51PM, 106 pages)
Revenue per Hour | revenue_per_hour | 97.2507 | Productivity |  | Verified | Derived
Profit per Hour | profit_per_hour | 33.0972 | Productivity |  | Verified | Derived
Labor % of Revenue | labor_pct_revenue | 25.37% | Cost Mix |  | Verified | Derived
Material % of Revenue | material_pct_revenue | 23.46% | Cost Mix |  | Verified | Derived
Total Vendors (AP) | total_vendors | 14 | Material | Unique vendor IDs | Verified | 2026 Job Detail Report.pdf (Sage Timberline export, printed 04/03/2026 1:51PM, 106 pages)
Total Invoices (AR) | total_invoices | 21 | Billing | Unique invoice numbers | Verified | 2026 Job Detail Report.pdf (Sage Timberline export, printed 04/03/2026 1:51PM, 106 pages)
AP Spend (JDR footer) | ap_total | 197171.05 | Material | JDR footer | Verified | 2026 Job Detail Report.pdf (Sage Timberline export, printed 04/03/2026 1:51PM, 106 pages)
PR Spend (JDR footer) | pr_total | 320218.88 | Labor | JDR footer (labor + burden + tax) | Verified | 2026 Job Detail Report.pdf (Sage Timberline export, printed 04/03/2026 1:51PM, 106 pages)
GL Spend (JDR footer) | gl_total | 30577.13 | Financial | JDR footer | Verified | 2026 Job Detail Report.pdf (Sage Timberline export, printed 04/03/2026 1:51PM, 106 pages)

## Vendors
Vendors — AP Summary
Vendor-level spend ranking
Rank | Vendor ID | Vendor Name | Total Spend | # Transactions | % of AP | Source
1 | 2026RS | Rosen Supply Company, Inc. $Boren | 49659.22 | 41 |  | 2026 Job Detail Report.pdf (Sage Timberline export, printed 04/03/2026 1:51PM, 106 pages)
2 | 2026CS | Consolidated Supply Co $Boren | 49441.46 | 48 |  | 2026 Job Detail Report.pdf (Sage Timberline export, printed 04/03/2026 1:51PM, 106 pages)
3 | 2026FE | Ferguson Enterprises, Inc. $525 Boren | 28251.03 | 12 |  | 2026 Job Detail Report.pdf (Sage Timberline export, printed 04/03/2026 1:51PM, 106 pages)
4 | 2026KS | Keller Supply Company $Boren | 23867.69 | 20 |  | 2026 Job Detail Report.pdf (Sage Timberline export, printed 04/03/2026 1:51PM, 106 pages)
5 | 1625FE | Franklin Engineering | 17344 | 9 |  | 2026 Job Detail Report.pdf (Sage Timberline export, printed 04/03/2026 1:51PM, 106 pages)
6 | 1234BA | Bank of America CC | 11361.41 | 18 |  | 2026 Job Detail Report.pdf (Sage Timberline export, printed 04/03/2026 1:51PM, 106 pages)
7 | 1401LU | Lotus United, LLC | 8215 | 1 |  | 2026 Job Detail Report.pdf (Sage Timberline export, printed 04/03/2026 1:51PM, 106 pages)
8 | 1234CO | Capital One Credit Card | 5734.1 | 32 |  | 2026 Job Detail Report.pdf (Sage Timberline export, printed 04/03/2026 1:51PM, 106 pages)
9 | 3612MS | Mechanical Sales, Inc. | 2098.04 | 2 |  | 2026 Job Detail Report.pdf (Sage Timberline export, printed 04/03/2026 1:51PM, 106 pages)
10 | 1611AS | Beacon Building Products $Atlas | 733.88 | 4 |  | 2026 Job Detail Report.pdf (Sage Timberline export, printed 04/03/2026 1:51PM, 106 pages)
11 | 2132MH | Manor Hardware & Construction Supply | 305.76 | 1 |  | 2026 Job Detail Report.pdf (Sage Timberline export, printed 04/03/2026 1:51PM, 106 pages)
12 | 1175FE | Ferguson Enterprises, Inc. #3007 | 296.86 | 2 |  | 2026 Job Detail Report.pdf (Sage Timberline export, printed 04/03/2026 1:51PM, 106 pages)
13 | 1421RA | R.A. Brown Backflow Testing | 186 | 1 |  | 2026 Job Detail Report.pdf (Sage Timberline export, printed 04/03/2026 1:51PM, 106 pages)
14 | 1130CS | Consolidated Supply Co. | -323.4 | 1 |  | 2026 Job Detail Report.pdf (Sage Timberline export, printed 04/03/2026 1:51PM, 106 pages)
TOTAL

## Change Log
Change Log — Master Register
Change events reconstructed from Contract, CO/COR folder, Billing SOVs, ASI-RFI, and JDR. 2 CORs + 1 SOV adjustment + 2 ASI/PR events.
Event ID | Type | Date | Subject | Originator | Linked | Cost Impact ($) | Status | Source
CONTRACT-ORIG | Contract (AGC LS) | ~2016-03 (effective 03/09/2016 per first PR) | Original prime subcontract #007 for Fox and Finch plumbing — $825,370.00 Lump Sum (AGC of Washington 2006 Ed., Synergy proj #750) | GC (Synergy Construction, Inc.) |  | 825370 | Executed | Contract/525 Boren Contract.pdf
SOV-ADJ | SOV adjustment | Between 2016-03-20 (App#1) and 2016-05-20 (App#2) | Contract total rolled from $825,370.00 → $830,310.00 (+$4,940.00) — no formal CO doc in folder, surfaces first in Billing draw #2 SOV | Synergy / OWP | CONTRACT-ORIG | 4940 | Billed | Billing/525 Boren SOV draw #2 5-20-16.xlsx
ASI-12-MEP | ASI | 2016 (pre-rough-in) | ASI-12 MEP Peer Review Response — design-reviewer response to MEP drawings | Designer / MEP |  | 0 | Informational | ASI-RFI/ASI 12 MEP Peer Review Response.pdf
PR-02-MEDIA | Proposal Request | 2016 | PR-02 Media Room Redesign — designer-issued proposal request (no CO resulted; absorbed into base) | Designer (Synergy) |  | 0 | Informational (no CO) | ASI-RFI/PR 02 Media Room Redesign.pdf
COR-01 | COR → CO | 2016-12-06 (COR) · 2017-04-24 (Permit SR1397520) | COR #01 Temp Gas Permit — total $357 to pull temp gas permit + inspection (1 permit $140 + 2 hrs labor $170 + tax). Executed as CO#2 Temporary Gas Meter (signed). Tied to Budget Transfer CO #02 XLSX ($357 sale price at code 603 Permits). | GC (Synergy Construction, Inc.) | CO-2-TEMP-GAS | 357 | Executed | Change Orders/COR_s/525 Boren - COR #01 Temp Gas Permit.pdf · Change Orders/COR_s/Temp Gas Permit.xlsx · Change Orders/BUDGET TRANSFERS/525 Boren - Budget Transfer - CO #02.xlsx
CO-2-TEMP-GAS | CO (executed) | 2017-04-24 | CO#2 Temporary Gas Meter — $357 signed PDF + scanned copy on file. Appears in Billing draw #15 SOV as +$357 to contract total = $830,667. | GC (Synergy Construction, Inc.) | COR-01 | 357 | Signed / Billed | Change Orders/CO_s/CO 2 Temporary Gas Meter Signed.pdf · Billing/525 Boren SOV draw #15 7-20-17.xlsx
COR-02 | COR | 2017-10-27 | COR #02 Unclog Construction Debris from Toilet — $293 to unclog 2x2 wood debris lodged in toilet. Post-closeout / warranty-era; no corresponding CO signed (likely absorbed as backcharge or OH). | Sub (OWP, Richard Donelson) |  | 293 | Submitted (no CO on file) | Change Orders/COR_s/525 Boren - COR #02 Unclog Construction Debris from Toilet.pdf
COR-SHOWER-OPT | COR (priced, not issued) | 2016-06-03 | Shower option pricing — 32 tub swap (1483EN → 1363BFSD w/ removable threshold). Priced $1,936 labor + $5,666 material. No CO issued; absorbed or cancelled. | Sub (OWP) |  | 0 | Priced only | Change Orders/COR_s/Shower option.xlsx
COR-SEWER-PX | COR pricing (warranty) | 2017-04-24 (per XLSX date) · 2018-12-06 (photo event) | Sewer Problem pricing — PM + Foreman + Apprentice + camera equipment to investigate sewer blockage. Likely related to 2018-12-06 Retail Sewer Problem warranty incident (30 photos/videos). No CO resulted (likely backcharge-offset / warranty absorb). | Sub (OWP) | RETAIL-SEWER-INCIDENT | 0 | Pricing only | Change Orders/COR_s/Sewer Problem pricing.xlsx
BUDGET-REV-230 | Budget revision | NOT FOUND | Finish Material (code 230) revised $78,595 → $82,765 (+$4,170) | Internal OWP |  | 4170 | Applied | 2026 Job Detail Report.pdf (Sage Timberline export, printed 04/03/2026 1:51PM, 106 pages)
BUDGET-REV-603 | Budget revision | NOT FOUND | Permits & Licenses (code 603) revised $5,420 → $5,560 (+$140) — includes Temp Gas CO#1 $140 | Internal / CO#1 | COR-01 | 140 | Applied | 2026 Job Detail Report.pdf (Sage Timberline export, printed 04/03/2026 1:51PM, 106 pages) + Budget Transfer CO#02 XLSX
BUDGET-REV-995 | Burden rate adjustment | NOT FOUND | Payroll Burden (code 995) revised $83,136.63 → $83,200.08 | OWP internal |  | 63.45 | Applied | 2026 Job Detail Report.pdf (Sage Timberline export, printed 04/03/2026 1:51PM, 106 pages)
BUDGET-REV-998 | Tax rate adjustment | NOT FOUND | Payroll Taxes (code 998) revised $14,671.17 → $14,681.96 | OWP internal |  | 10.79 | Applied | 2026 Job Detail Report.pdf (Sage Timberline export, printed 04/03/2026 1:51PM, 106 pages)
CONTRACT-FINAL | Contract revision (cumulative) | 2017-07-20 (App #15) | Final contract value $830,667.00 = $825,370 orig + $4,940 SOV adj + $357 CO#1 = +$5,297.00 (+0.64%). Reconciles to JDR revenue. | GC (Synergy Construction, Inc.) | CONTRACT-ORIG | 5297 | Executed | Billing/525 Boren SOV draw #15 7-20-17.xlsx + 2026 Job Detail Report.pdf (Sage Timberline export, printed 04/03/2026 1:51PM, 106 pages)
AR-PATTERN-REVERSALS | AR reversal+reissue | 2017-04-20 (036863/036864), 2017-05-19 (036886/036887) | Standard Sage AR corrections — not change events per se, but worth flagging | Sub (OWP) |  | 0 | Corrected | 2026 Job Detail Report.pdf (Sage Timberline export, printed 04/03/2026 1:51PM, 106 pages)
FIRST-INVOICE | Invoice | 036700 date: 03/21/16 | First billing invoice #036700 (Pay App #1, 2016-03-20 in SOV) | Sub (OWP) |  | 0 | Paid (per zero net due) | 2026 Job Detail Report.pdf (Sage Timberline export, printed 04/03/2026 1:51PM, 106 pages) + Billing/draw#1
LAST-INVOICE | Invoice | 036923 date: 07/24/17 | Last billing invoice #036923 $-357.00 (closeout, SOV Pay App #15 2017-07-20) | Sub (OWP) |  | -357 | Paid | 2026 Job Detail Report.pdf (Sage Timberline export, printed 04/03/2026 1:51PM, 106 pages) + Billing/draw#15
RETAIL-SEWER-INCIDENT | Warranty incident | 2018-12-06 | Retail Sewer Problem — 30 photos+videos documenting retail-level sewer blockage. ~17 months post-closeout. Subject of Sewer Problem pricing XLSX. | Sub (OWP, forensic) | COR-SEWER-PX | 0 | Documented (no claim on file) | Retail Sewer Problem/ (30 JPG/MP4 files dated 20181206)
RETAINAGE-OPEN | Retainage | As of 04/03/2026 | Retainage $41,533.35 outstanding 8+ years after last billing (2017-07-20). Full & Final Lien Claim Waiver on file (undated). Release documentation NOT FOUND in folder. | GC (Synergy Construction, Inc.) |  | 0 | Outstanding | 2026 Job Detail Report.pdf (Sage Timberline export, printed 04/03/2026 1:51PM, 106 pages) · Billing/525 Boren Full & Final Lien Claim waiver.pdf
TOTAL COST IMPACT (net)

## Root Cause Analysis
Root Cause Analysis
Cost-code variance drivers. Primary signal: labor over-runs on Garage, Canout, Mech Room offset by Material under-runs.
COST-CODE VARIANCE CATEGORIES
Category | Codes Affected | Net $ Variance | Root Cause (inferred) | Notes
Labor over-runs (productivity) | 111 Garage, 112 Canout, 142 Mech Room | 18965 | Field productivity below estimate | Sum of labor over-runs = $18,965
Labor under-runs | 100 Sup, 101 Takeoff, 110 UG, 130 Finish, 140 Gas | -16638 | Savings / scope reduction / efficiency | Offsetting savings
Rough-in overrun (scope) | 120 Roughin Labor | 14618.5 | Possibly scope increase with budget revision | $14,618 over
Material under-runs | 220 Rough Mat, 230 Finish Mat, 241 Water Main Mat, 242 Mech Room Mat | -62736.55 | Favorable procurement / takeoff savings | Material came in well under
Burden / Tax accrual | 995, 998 | 11621.34 | Higher-than-estimated burden rates | OWP internal rate volatility
Support-code savings | 601 Eng, 603 Permit, 607 Other | -22868.18 | Under-utilization of support budget | Savings
TOTAL NET VARIANCE (Rev Budget vs Actual)
RESPONSIBILITY ATTRIBUTION
Responsible Party | # Drivers | Net $ Impact | Notes
Sub (OWP) — labor productivity | 3 | 18965 | Over-runs on Garage/Canout/Mech Room
Sub (OWP) — procurement savings | 4 | -62736.55 | Favorable material cost
Designer / GC (scope) | 1 | 14618.5 | Rough-in scope growth (budget also revised)
Burden rate — OWP internal | 2 | 11621.34 | Accrual volatility
Support codes — OWP | 3 | -22868.18 | Savings

## Predictive Signals
Predictive Signals
Leading indicators reconstructed from JDR only (no RFI/CO logs to draw from)
CURRENT-STATE SIGNALS
Indicator | Current Value | Benchmark | Status | Meaning
RFI Count | NOT FOUND | <50 | UNKNOWN | No RFI folder exists
Submittal Count | NOT FOUND | varies | UNKNOWN | No Submittal folder exists
ASI / OCD Count | NOT FOUND | <5 | UNKNOWN | No ASI folder exists
Change Order Document Count | 0 | <3 | NEUTRAL | 0 docs — but budget revision implies changes happened
Contract Growth % | 0.64% | <3% | HEALTHY | Very low contract growth
Labor Hrs vs Budget |  | varies | INFO | 8,542 hrs
Labor Cost % of Revenue | 25.37% | <35% | HEALTHY | 25.4% — labor-heavy
Retainage Release Pending | YES | Released within 90 days post-closeout | ELEVATED | $41,533 open 9+ years after work end
Worker Concentration (top 1) | 21.05% | <25% | ELEVATED | 21.1% from single worker
Rough-in Labor Share | 57.38% | 40-60% | HEALTHY | 57% of labor on rough-in
Document Completeness | LOW | Full CO/RFI/Submittal trail | RISK | Only JDR + electrical plans + Revit backup
FORECAST MODELS
Forecast | Current Estimate | Confidence | Driver | Model Note
Final margin (actual) | 34.03% | Actual | Job closed financially | Net / Revenue
Retainage collection probability | MEDIUM (stale) | Qualitative | 9+ years outstanding | May require AR write-off or dispute
Composite risk score (0-100) | 45 | Low-Medium | Doc-gap + stale retainage + labor concentration | Financials healthy; file hygiene poor
Would re-bid margin target | ≥34% | Derived from actuals | Historical close | Assumes similar scope; tighten labor estimating for garage/canout/mech room

## Metric Registry
Metric Registry — Cortex Data Catalog
Every metric with data_label, confidence, and source
# | Data Label | Human Label | Value | Unit | Source Tab | Confidence | Source Document(s)
1 | job_number | Job Number | 2026 | id | Benchmark KPIs | Verified | 2026 Job Detail Report.pdf (Sage Timberline export, printed 04/03/2026 1:51PM, 106 pages)
2 | job_name | Job Name | Synergy 525 Boren | text | Benchmark KPIs | Verified | 2026 Job Detail Report.pdf (Sage Timberline export, printed 04/03/2026 1:51PM, 106 pages)
3 | project_desc | Project Description | Fox and Finch Apts @ 525 Boren | text | Benchmark KPIs | Verified | 2026 Job Detail Report.pdf (Sage Timberline export, printed 04/03/2026 1:51PM, 106 pages)
4 | general_contractor | GC | Synergy Construction, Inc. | text | Benchmark KPIs | Verified | 2026 Job Detail Report.pdf (Sage Timberline export, printed 04/03/2026 1:51PM, 106 pages)
5 | customer_code | Customer Code | 2026SC | id | Overview | Verified | 2026 Job Detail Report.pdf (Sage Timberline export, printed 04/03/2026 1:51PM, 106 pages)
6 | location | Location | 525 Boren Ave, Seattle | text | Benchmark KPIs | Medium | 2026 Job Detail Report.pdf (Sage Timberline export, printed 04/03/2026 1:51PM, 106 pages)
7 | project_type | Project Type | Multifamily Plumbing (New Construction) | text | Benchmark KPIs | Medium | Inferred
8 | start_date | Work Start | 2016-03-09 | date | Benchmark KPIs | Verified | 2026 Job Detail Report.pdf (Sage Timberline export, printed 04/03/2026 1:51PM, 106 pages)
9 | end_date | Work End | 2017-07-24 | date | Benchmark KPIs | Verified | 2026 Job Detail Report.pdf (Sage Timberline export, printed 04/03/2026 1:51PM, 106 pages)
10 | duration_months | Duration (months) | 16.5 | months | Benchmark KPIs | Verified | Derived
11 | unit_count | Unit Count | NOT FOUND | units | Benchmark KPIs | Low | No plans
12 | fixture_count | Fixture Count | NOT FOUND | count | Benchmark KPIs | Low | No plans
13 | contract_original | Contract Original | 825370 | USD | Benchmark KPIs | Verified | 2026 Job Detail Report.pdf (Sage Timberline export, printed 04/03/2026 1:51PM, 106 pages)
14 | contract_final | Contract Final | 830667 | USD | Benchmark KPIs | Verified | 2026 Job Detail Report.pdf (Sage Timberline export, printed 04/03/2026 1:51PM, 106 pages)
15 | change_orders | Change Orders $ | 5297 | USD | Benchmark KPIs | Medium | Derived
16 | co_pct | CO % of Contract | 0.6418% | % | Benchmark KPIs | Medium | Derived
17 | revenue | Revenue | 830667 | USD | Benchmark KPIs | Verified | 2026 Job Detail Report.pdf (Sage Timberline export, printed 04/03/2026 1:51PM, 106 pages)
18 | direct_cost | Direct Cost | 547967.06 | USD | Benchmark KPIs | Verified | 2026 Job Detail Report.pdf (Sage Timberline export, printed 04/03/2026 1:51PM, 106 pages)
19 | net_profit | Net Profit | 282699.94 | USD | Benchmark KPIs | Verified | 2026 Job Detail Report.pdf (Sage Timberline export, printed 04/03/2026 1:51PM, 106 pages)
20 | gross_margin | Gross Margin | 34.03% | % | Benchmark KPIs | Verified | Derived
21 | retainage | Retainage Outstanding | 41533.35 | USD | Benchmark KPIs | Verified | 2026 Job Detail Report.pdf (Sage Timberline export, printed 04/03/2026 1:51PM, 106 pages)
22 | retainage_pct | Retainage % of Revenue | 5% | % | Benchmark KPIs | Verified | Derived
23 | labor_cost | Labor Cost | 210715.5 | USD | Benchmark KPIs | Verified | 2026 Job Detail Report.pdf (Sage Timberline export, printed 04/03/2026 1:51PM, 106 pages)
24 | material_cost | Material Cost | 194870.36 | USD | Benchmark KPIs | Verified | 2026 Job Detail Report.pdf (Sage Timberline export, printed 04/03/2026 1:51PM, 106 pages)
25 | overhead_cost | Subcon+OH Cost | 32877.82 | USD | Benchmark KPIs | Verified | 2026 Job Detail Report.pdf (Sage Timberline export, printed 04/03/2026 1:51PM, 106 pages)
26 | burden_cost | Burden Cost | 93383.48 | USD | Benchmark KPIs | Verified | 2026 Job Detail Report.pdf (Sage Timberline export, printed 04/03/2026 1:51PM, 106 pages)
27 | tax_cost | Tax Cost | 16119.9 | USD | Benchmark KPIs | Verified | 2026 Job Detail Report.pdf (Sage Timberline export, printed 04/03/2026 1:51PM, 106 pages)
28 | total_hours | Total Labor Hours | 8541.5 | hours | Benchmark KPIs | Verified | 2026 Job Detail Report.pdf (Sage Timberline export, printed 04/03/2026 1:51PM, 106 pages)
29 | total_workers | Total Workers | 25 | count | Benchmark KPIs | Verified | 2026 Job Detail Report.pdf (Sage Timberline export, printed 04/03/2026 1:51PM, 106 pages)
30 | blended_gross_wage | Blended Gross Wage | 24.6696 | USD/hr | Benchmark KPIs | Verified | Derived
31 | fully_loaded_wage | Fully-Loaded Wage | 37.4898 | USD/hr | Benchmark KPIs | Verified | Derived
32 | burden_multiplier | Burden Multiplier | 1.5197 | x | Benchmark KPIs | Verified | Derived
33 | revenue_per_hour | Revenue per Hour | 97.2507 | USD/hr | Benchmark KPIs | Verified | Derived
34 | profit_per_hour | Profit per Hour | 33.0972 | USD/hr | Benchmark KPIs | Verified | Derived
35 | labor_pct_revenue | Labor % of Revenue | 25.37% | % | Benchmark KPIs | Verified | Derived
36 | material_pct_revenue | Material % of Revenue | 23.46% | % | Benchmark KPIs | Verified | Derived
37 | total_vendors | Total Vendors (AP) | 14 | count | Vendors | Verified | 2026 Job Detail Report.pdf (Sage Timberline export, printed 04/03/2026 1:51PM, 106 pages)
38 | total_invoices | Total Invoices (AR) | 21 | count | Billing & SOV | Verified | 2026 Job Detail Report.pdf (Sage Timberline export, printed 04/03/2026 1:51PM, 106 pages)
39 | rfi_count | RFI Count | NOT FOUND | count | Predictive Signals | Low | No RFI folder
40 | submittal_count | Submittal Count | NOT FOUND | count | Predictive Signals | Low | No submittal folder
41 | co_doc_count | CO Document Count | 0 | count | Change Log | Verified | No CO folder
42 | top_worker_hours_share | Top Worker Hours Share | 21.05% | % | Crew Analytics | Verified | Derived
43 | top5_worker_hours_share | Top 5 Worker Hours Share | 72.61% | % | Crew Analytics | Verified | Derived
44 | cost_code_count | Cost Codes Active | 28 | count | Budget vs Actual | Verified | 2026 Job Detail Report.pdf (Sage Timberline export, printed 04/03/2026 1:51PM, 106 pages)

## Reconciliation
Reconciliation
Cross-sheet formula checks
# | Check | Value A | Value B | Delta | Status | Tabs
1 | Revenue (JDR) = Contract Final | 830667 | 830667 |  |  | 1↔8
2 | Expenses = Labor+Material+OH+Burden+Tax | 547967.06 | 547967.06 |  |  | 1↔3
3 | Net Profit = Revenue - Expenses | 282699.94 | 282699.94 |  |  | 1↔Derived
4 | JDR Source: AP+PR+GL = Expenses | 547967.06 | 547967.06 |  |  | 1↔Derived (footer)
5 | Budget vs Actual (code 999) = Revenue | 830667 | 830667 |  |  | 2↔1
6 | Total Labor Hours = Worker hours sum | 8541.5 | 8621.5 |  |  | 5↔2
7 | Labor Cost = Worker gross sum | 210715.5 | 210715.5 |  |  | 5↔3
8 | Vendor total ≈ AP footer | 197171.05 | 197171.05 |  |  | 12↔1 (approximate)
9 | Invoice count = 21 | 21 | 21 |  |  | 9↔11
10 | Contract Final - Orig = CO implied | 5297 | 5297 |  |  | 11↔Derived
11 | CO breakdown: SOV-adj + CO#1 Temp Gas = CO total | 5297 | 5297 |  |  | 13↔11
12 | Pay Apps (sum of 'This Period') = Revenue | 830667 | 830667 |  |  | 9↔1 (Billing SOV)
13 | Pay App #15 Contract Total = JDR Revenue | 830667 | 830667 |  |  | 9↔1 (SOV draw #15)
14 | Retainage outstanding | 41533.35 | 41533.35 |  |  | 9↔JDR footer
15 | Worker count = 25 | 25 | 25 |  |  | 5↔11
16 | Cost code count = 28 | 28 | 28 |  |  | 2↔16
17 | Unit count (TOTO bowls) = 60 | 60 | 60 |  |  | 1↔Vendor Quote XLSX
18 | Pay App count (SOV files) = 15 | 15 | 15 |  |  | 9↔Billing folder
19 | Fixture inventory (Vendor Quote XLSX) = 669 | 669 | 669 |  |  | 1↔Vendor Quote XLSX
SOURCES
Job #2026 — Cortex v2 17-tab (REBUILD 2026-04-14 after expanded folder ingestion — 130+ documents now on file in Apts 4/)
Canonical source: 2026 Job Detail Report.pdf (Sage Timberline export, printed 04/03/2026 1:51PM, 106 pages)
JDR Job Totals footer: Revenue $830,667.00 / Expenses $547,967.06 / Net $282,699.94 / Retainage $41,533.35
JDR Source breakdown: GL $30,577.13 · AP $197,171.05 · PR $320,218.88 · AR $830,667.00
Contract: Contract/525 Boren Contract.pdf — AGC Washington 2006 Ed. Lump Sum $825,370.00 (Subcontract #007, Synergy project #750, cost code 15400)
Billing: 15 Pay App SOV XLSX drafts (2016-03-20 → 2017-07-20) + Full & Final Lien Claim Waiver. Pay App #15 Contract Total $830,667 ties to JDR revenue.
Change Orders: 2 CORs priced (COR#01 Temp Gas $357 executed as CO#2, COR#02 Unclog Toilet $293 warranty); 1 Budget Transfer XLSX (CO#02); 2 additional priced COR XLSX (Shower option, Sewer Problem pricing — neither issued)
ASI-RFI: ASI-12 MEP Peer Review Response + PR-02 Media Room Redesign (informational, no cost impact)
Submittals: 44 submittals across 7 categories (Equipment-7, Fixtures-12, Material-5, Responses-1, Sleeving Plans-1, Tub/Shower-8, Underground/Garage-10)
Permits: 5 PDFs (Plumbing, Gas, Gas Temp Heat, Backflow, Renewed). Gas permit SR1397520 in 525 Boren LLC name
Plans: 525-Plumbing Construction Set PR.pdf + 11 DWGs (L1-L7 + Roof + UG/Vault Shift) + MEP Superplots (2016-02-09/02-22/03-07)
Vendor: 7 quote PDFs + master Vender Quote Spreadsheet (5 suppliers) + 5 vendor lien waivers (Consolidated/Ferguson/Keller/Rosen + template) + 1 Keller Notice-to-Owner (2016-08-11)
Warranty: Retail Sewer Problem 30 photos/videos 12/06/2018 (~17 mo post-closeout) — paired with 'Sewer Problem pricing' COR XLSX (no CO issued)
Closeout: O&M manual + Warranty package + Certificate of Insurance 2016-17
Unresolved: (a) $41,533 retainage outstanding 8+ yrs; (b) COR#02 Unclog Toilet $293 submitted but no signed CO; (c) Sewer Problem warranty — pricing done, resolution undocumented; (d) +$4,940 SOV adj (App#1→#2) lacks formal CO paper — inferred reline
TIES = within $1 · WITHIN = within 5% · OFF = investigate