## Overview
Job #2027 · Exxel Pacific 550 Broadway (Zig) — The Zig Apartments
Cortex JCR Cortex v2 • Exxel Pacific, Inc. (customer 2027EP) • 550 Broadway St, Seattle WA • Owner: Intra-Corp (550 Broadway owner LLC)
PROJECT OVERVIEW
Project Job # | 2027 |  | 2027 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 184 pages) header
Project Name (Sage) | Exxel Pacific 550 Broadway (Zig) |  | 2027 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 184 pages) header
Project Description | The Zig Apartments — 550 Broadway St, Seattle |  | L1 220000 One Way Plumbing Fully Executed Subcontract ocr_d.pdf / AR line descriptions
General Contractor | Exxel Pacific, Inc. |  | L1 220000 One Way Plumbing Fully Executed Subcontract ocr_d.pdf
Customer Code (Sage) | 2027EP |  | 2027 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 184 pages)
Owner / Developer | Intra-Corp (550 Broadway owner LLC) |  | L1 220000 One Way Plumbing Fully Executed Subcontract ocr_d.pdf
Jobsite Location | 550 Broadway St, Seattle, WA |  | L1 220000 One Way Plumbing Fully Executed Subcontract ocr_d.pdf
Contract / PO Document | L1 220000 One Way Plumbing Fully Executed Subcontract ocr_d.pdf |  | Fully executed subcontract (L1 220000, Lump Sum)
Plans / Specifications | 550 Broadway plumbing narrative.pdf (Div 22 plumbing narrative) + P-tag fixture schedule + proposal drawings |  | Folder scan
Fixture Schedule | 550 Broadway working copy of P-tag list front page detail.xlsx (22 fixture tags WC-1…HB1 + 16 equipment tags + gas loads + connection schedule) |  | 5-sheet workbook
Bid Proposal | Exxel 19 West Harrison Apartment proposal September 1 2015.pdf |  | 9/1/2015, detailed fixture quantities and alternates
Contract Type | Lump Sum |  | L1 220000 One Way Plumbing Fully Executed Subcontract ocr_d.pdf
Work Period | 03/11/2016 – 08/18/2017 (~17 months, per PR/AR dates) |  | 2027 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 184 pages)
Total Unique Documents Reviewed | 1924 |  | File inventory across owp-2027/
CONTRACT VALUE |  | NET PROFIT | DIRECT COST | LABOR HOURS
2275444 |  | 921960.94 | 1353483.06 | 21014
Original $2,230,810.00 + $44,634.00 COs (+2.00%) |  | 40.5% margin | 59.5% of revenue | 43 workers
SCOPE OF WORK (from contract + proposal + P-tag)
Full plumbing: underground, rough-in, finish, gas piping, water main, insulation, mech room, warranty.
Bid proposal itemizes: 83 Gerber std WC + 9 Toto ADA WC (= 92 unit WCs, + 2 amenity), 92 Toto lavs (+ 2 amenity),
67 Aquatic tub/shower combos + 25 Fiberfab shower stalls (= 92 bathing), 67 Lenova + 8 Elkay ADA kitchen sinks (+ 1 bar sink + 1 mop sink),
75 dishwasher rough-ins, 75 washer rough-ins, 8 hose bibs, 2 AO Smith BTH500 water heaters, 1 MSI duplex booster pump, 2 sump pumps,
1 sand/oil basin, 3 garage floor drains, 5 trench drains, 4 area drains, 17 roof drains.
Unit count ≈ 92 apartments (implied from 92 WC sets; 9 ADA Type A units).
Spec compliance: Seattle Building Code 2012 + UPC 2012 with WA state amendments.
SOURCES
Canonical financial source: 2027 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 184 pages)
Job totals (JDR footer): Revenue $2,275,444.00 / Expenses $1,353,483.06 / Net $921,960.94 / Retainage $113,772.20
Source breakdown: GL $97,752.86 · AP $538,651.30 · PR $717,078.90 · AR $2,275,444.00
Contract: L1 220000 One Way Plumbing Fully Executed Subcontract ocr_d.pdf (Lump Sum $2,230,810.00)
Proposal: Exxel 19 West Harrison Apartment proposal September 1 2015.pdf
Fixture schedule: 550 Broadway working copy of P-tag list front page detail.xlsx
Plumbing narrative: 550 Broadway plumbing narrative.pdf
Change Orders: 6 COs in Change Orders/CO_s/ folder (CO#01-06)
RFIs: 18 + 1 ASI in ASI-RFI/; 12 additional in DROPBOX FILES FROM GUYS TABLETS/ASI-RFI/RFI_s/
Submittals: 19 fixture + 10 material + 1 UG/garage submittals
Permits: 6 permits (backflow, boiler x2, gas, plumbing, temp gas)
POs: 82 total (7 placed, 19 scheduled, 56 completed)
PROJECT TEAM (OWP Job Info)
Role | Status | Name / Firm
GC | Extracted | Exxel Pacific, Inc.
GC PM | Extracted | Justin Gotcher / Chris Austin
GC Superintendent | Extracted | Brian Proctor
GC PE | Extracted | Chris Austin
Developer | Extracted | Intra-Corp
Architect | Extracted | Nicholson Kovalchick
Structural | N/A | N/A
Acoustical | N/A | N/A
ADA Consultant | N/A | N/A
Interior Design | N/A | N/A
MEP Engineer | Extracted | Pressler

## Budget vs Actual
Budget vs Actual
All 27 cost codes from JDR. Contract $2,230,810 → $2,275,444 (COs +$44,634.00).
Cost Code | Description | Original Budget | Revised Budget | Actual | Variance | % of Revised | Hours | Source
100 | Supervision | 11000 | 11188 | 5755.5 |  |  | 124.5 | 2027 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 184 pages)
101 | Takeoff & Purchase Labor | 20400 | 20823 | 13422.5 |  |  | 289.5 | 2027 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 184 pages)
110 | Underground Labor | 12100 | 12017 | 7711 |  |  | 264 | 2027 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 184 pages)
111 | Garage Labor | 62140 | 62140 | 53390.5 |  |  | 1976.5 | 2027 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 184 pages)
112 | Canout Labor | 15450 | 15450 | 16373 |  |  | 573 | 2027 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 184 pages)
120 | Roughin Labor | 301840 | 300990 | 278595.5 |  |  | 12672 | 2027 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 184 pages)
130 | Finish Labor | 52080 | 53079 | 48849.27 |  |  | 2157.5 | 2027 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 184 pages)
140 | Gas Labor | 6600 | 6600 | 7836.5 |  |  | 336.5 | 2027 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 184 pages)
141 | Water Main/Insulation Lab | 65315 | 66415 | 46631.5 |  |  | 2208 | 2027 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 184 pages)
142 | Mech Room Labor | 11000 | 11000 | 12684.5 |  |  | 412.5 | 2027 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 184 pages)
210 | Underground Material | 18300 | 15078 | 13388.88 |  |  |  | 2027 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 184 pages)
211 | Garage Material | 64290 | 64290 | 37284.47 |  |  |  | 2027 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 184 pages)
212 | Canout Material | 15450 | 15450 | 14050.89 |  |  |  | 2027 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 184 pages)
220 | Roughin Material | 153325 | 151625 | 91274.89 |  |  |  | 2027 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 184 pages)
230 | Finish Material | 224100 | 238053 | 220048.68 |  |  |  | 2027 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 184 pages)
240 | Gas Material | 7800 | 7800 | 1363.51 |  |  |  | 2027 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 184 pages)
241 | Water Main/Insulation Mat | 79900 | 80900 | 71604.01 |  |  |  | 2027 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 184 pages)
242 | Mech Room Material | 123300 | 123300 | 99306.42 |  |  |  | 2027 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 184 pages)
243 | Condensation Drains Mat | 0 | 0 | 15.84 |  |  |  | 2027 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 184 pages)
600 | Subcontractor | 2000 | 27261 | 27855.92 |  |  |  | 2027 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 184 pages)
601 | Engineering/Plans | 30000 | 35343 | 39853.5 |  |  |  | 2027 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 184 pages)
602 | Rental Equipment | 5000 | 5000 | 527.56 |  |  |  | 2027 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 184 pages)
603 | Permits & Licenses | 13365 | 13365 | 9694 |  |  |  | 2027 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 184 pages)
607 | Other Expenses | 17000 | 17000 | 10135.59 |  |  |  | 2027 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 184 pages)
995 | Payroll Burden | 208385 | 209087.09 | 188248.16 |  |  |  | 2027 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 184 pages)
998 | Payroll Taxes | 42681.26 | 42817.2 | 37580.97 |  |  |  | 2027 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 184 pages)
999 | Sales | -2230810 | -2275444 | -2275444 |  |  |  | 2027 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 184 pages)
TOTAL

## Cost Breakdown
Cost Breakdown by Category
Direct cost composition by category from JDR cost codes
Category | Cost Codes | Actual $ | % of Direct Cost | % of Revenue | Source
Labor | 100,101,110,111,112,120,130,140,141,142 | 491249.77 |  |  | 2027 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 184 pages)
Material | 210,211,212,220,230,240,241,242 | 548321.75 |  |  | 2027 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 184 pages)
Subcontractor + Engineering + Permits + Other | 600,601,602,603,607 | 88066.57 |  |  | 2027 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 184 pages)
Payroll Burden | 995 | 188248.16 |  |  | 2027 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 184 pages)
Payroll Taxes | 998 | 37580.97 |  |  | 2027 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 184 pages)
TOTAL DIRECT COST |  |  | 100%

## Material
Material Purchases — AP Vendors
Material + subcontractor spend by vendor (AP records from JDR). Supplemented with submittal/PO inventory.
Vendor ID | Vendor Name | Total Spend | # Transactions | Category (inferred) | Source
2027RS | Rosen Supply Company, Inc. $550 Broadway | 130186.55 | 76 | Plumbing / Supplies | 2027 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 184 pages)
2027KS | Keller Supply Company $550 Broadway | 108476.79 | 53 | Plumbing / Supplies | 2027 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 184 pages)
2027FE | Ferguson Enterprises, Inc. $550 Broadway | 83315.58 | 38 | Plumbing / Supplies | 2027 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 184 pages)
3612MS | Mechanical Sales, Inc. | 70237.38 | 4 | Plumbing / Supplies | 2027 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 184 pages)
2027CS | Consolidated Supply Co.$550 Broadway | 43775.87 | 30 | Plumbing / Supplies | 2027 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 184 pages)
1625FE | Franklin Engineering | 39853.5 | 12 | Engineering (601) | 2027 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 184 pages)
6912MF | Mechanical Firestop Services, LLC | 22950 | 3 | Uncategorized | 2027 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 184 pages)
1234BA | Bank of America CC | 8719 | 4 | Credit Card (mixed) | 2027 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 184 pages)
1234CO | Capital One Credit Card | 8104 | 44 | Credit Card (mixed) | 2027 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 184 pages)
1234CI | Citibank Credit Card | 7501.5 | 2 | Credit Card (mixed) | 2027 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 184 pages)
1609QC | Quality Concrete Products, Inc. $32 | 4638 | 6 | Uncategorized | 2027 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 184 pages)
1175FE | Ferguson Enterprises, Inc. #3007 | 2530.96 | 9 | Plumbing / Supplies | 2027 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 184 pages)
1504CA | Chip Away Bathtub Repair, Inc. | 1800 | 1 | Uncategorized | 2027 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 184 pages)
1231KS | Keller Supply Company | 1725.69 | 6 | Plumbing / Supplies | 2027 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 184 pages)
5585CH | Columbia Hydronics | 1627.74 | 1 | Uncategorized | 2027 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 184 pages)
8068MI | Kele, Inc $ MI Controls | 563.81 | 3 | Uncategorized | 2027 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 184 pages)
1799AW | AllWest Underground, Inc. | 527.56 | 2 | Uncategorized | 2027 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 184 pages)
4320MC | MAD Concrete Cutting & Coring, Inc. | 525 | 1 | Uncategorized | 2027 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 184 pages)
3181SC | Scan2Core, Inc. | 470 | 1 | Uncategorized | 2027 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 184 pages)
1380RS | Rosen Supply Kirkland | 291.4 | 2 | Plumbing / Supplies | 2027 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 184 pages)
1303CM | C.M. Hoskins Company | 217.8 | 1 | Uncategorized | 2027 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 184 pages)
1421RA | R.A. Brown Backflow Testing | 200 | 1 | Testing subcontractor | 2027 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 184 pages)
5621HD | Core & Main LP $HD Supply Waterworks | 169.34 | 1 | Plumbing / Supplies | 2027 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 184 pages)
1401LU | Lotus United, LLC | 155 | 1 | Uncategorized | 2027 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 184 pages)
2026RS | Rosen Supply Company, Inc. $Boren | 74.05 | 1 | Plumbing / Supplies | 2027 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 184 pages)
1978FC | Fastenal Company | 14.78 | 1 | Uncategorized | 2027 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 184 pages)
TOTAL
NOTE: AP total per JDR footer = $538,651.30. Vendor sum above approximates this. Submittals folder (Submittals/) contains 19 fixture + 10 material + 1 UG submittal documenting approved products. POs folder shows 82 POs (7 placed, 19 scheduled, 56 completed).

## Crew & Labor
Crew & Labor — Worker Roster
All 43 unique payroll workers from JDR.
Worker ID | Worker Name | Total Hours | Gross Pay | Blended Wage ($/hr) | # Work Days | Source
BA70 | Barnhart, Joseph N | 1753 | 70865 |  | 74 | 2027 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 184 pages)
WI46 | Wilson, Garret A | 1598 | 40929 |  | 54 | 2027 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 184 pages)
ME53 | Mendoza Morales, Jesus A | 1570 | 29286 |  | 42 | 2027 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 184 pages)
SO78 | Soto Cruz, Jovani | 1555 | 33965 |  | 43 | 2027 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 184 pages)
BA45 | Balderas Ortiz, Ricardo I | 1337.5 | 30760 |  | 36 | 2027 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 184 pages)
MA71 | Martinez Reyes, Juan C | 1184 | 21961 |  | 39 | 2027 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 184 pages)
WE55 | Wennig, Johnathan M | 939 | 19169 |  | 26 | 2027 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 184 pages)
VE42 | Velasquez Cruz, Denis M | 925 | 20651 |  | 25 | 2027 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 184 pages)
GA70 | Garcia, Jordan X | 842 | 21456.5 |  | 26 | 2027 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 184 pages)
VE43 | Velasquez Cruz, Osman N | 717 | 10038 |  | 19 | 2027 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 184 pages)
LO87 | Lovo, German G | 696 | 13221 |  | 20 | 2027 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 184 pages)
RA52 | Ramos Banegas, Noel O | 685.5 | 13345.5 |  | 21 | 2027 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 184 pages)
GA72 | Gardner, Andrew M | 608.5 | 10128.5 |  | 18 | 2027 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 184 pages)
PO71 | Portillo, Kevin J | 520 | 7800 |  | 15 | 2027 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 184 pages)
RA57 | Ramos Melendez, Carlos M | 480 | 6720 |  | 13 | 2027 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 184 pages)
CO73 | Cortes Sepulveda, Jose R | 445 | 7757 |  | 14 | 2027 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 184 pages)
RE18 | Reed, Reuben H | 430.5 | 15285.5 |  | 16 | 2027 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 184 pages)
RO75 | Ross, Kelli M | 376 | 13536 |  | 11 | 2027 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 184 pages)
CR87 | Cruz Reyes, Jose | 357 | 7140 |  | 10 | 2027 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 184 pages)
CR79 | Cruz Guzman, Joel A | 349 | 6631 |  | 10 | 2027 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 184 pages)
GE71 | Gerard, Mitchell J | 346 | 7890 |  | 15 | 2027 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 184 pages)
RE96 | Reyes Cruz, Denis A | 320 | 6720 |  | 10 | 2027 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 184 pages)
ES62 | Esparza Jimenez, Jose D | 293 | 7325 |  | 10 | 2027 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 184 pages)
HO14 | Holmes, Anthony R | 252.5 | 5158.5 |  | 9 | 2027 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 184 pages)
GE69 | Gerard, Jeffrey S | 239 | 10867 |  | 73 | 2027 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 184 pages)
BA68 | Barbosa, Michael S | 232 | 3808 |  | 8 | 2027 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 184 pages)
KI55 | Kinssies, Jr, John E | 213 | 2964 |  | 6 | 2027 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 184 pages)
EI74 | Eisenhauer, Tommy J | 208 | 3536 |  | 6 | 2027 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 184 pages)
GE70 | Gerard, Jordan E | 176 | 3872 |  | 5 | 2027 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 184 pages)
DO56 | Donelson, Richard T | 175 | 8311 |  | 66 | 2027 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 184 pages)
GO51 | Gomez Reyes, Edith N | 175 | 2385 |  | 6 | 2027 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 184 pages)
DR04 | Draves, Steven W | 160 | 2720 |  | 5 | 2027 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 184 pages)
SA51 | Sanchez, Derli | 160 | 2400 |  | 5 | 2027 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 184 pages)
AN14 | Anderson, Richard P | 151 | 5589 |  | 8 | 2027 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 184 pages)
PA47 | Palma Vides, Jorge A | 148.5 | 2673 |  | 5 | 2027 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 184 pages)
HU04 | Hubbard, Dustin R | 87.5 | 1594 |  | 27 | 2027 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 184 pages)
EL33 | Eliassen, Cory H | 72 | 1296 |  | 2 | 2027 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 184 pages)
SA54 | Sanders, Allen O | 41.5 | 1618 |  | 7 | 2027 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 184 pages)
MC09 | McCabe, Thomas C | 37 | 923 |  | 3 | 2027 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 184 pages)
HU06 | Hubbard, Robert W | 8 | 326 |  | 3 | 2027 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 184 pages)
CO71 | Cortes Mendiola, Victor H | 4 | 148 |  | 1 | 2027 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 184 pages)
PA11 | Paco Leyva, Orlando | 4 | 112 |  | 1 | 2027 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 184 pages)
WA35 | Waites, Thaddeus Z | 3 | 111 |  | 1 | 2027 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 184 pages)
TOTAL

## Crew Analytics
Crew Analytics
Team-level labor productivity, concentration, wage dispersion
TEAM-LEVEL METRICS
Metric | Value | Notes | Source
Total Workers | 43 | Unique payroll IDs | 2027 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 184 pages)
Total Labor Hours | 21014 | Sum of codes 100-142 | 2027 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 184 pages)
Total Gross Pay | 491249.77 | Sum of codes 100-142 | 2027 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 184 pages)
Blended Gross Wage ($/hr) | 23.3773 | Labor$ / Hrs (pre-burden) | Derived
Top Worker Hours Share | 8.342% | BA70 Barnhart, Joseph N (1753 hrs) | Derived
Top 5 Workers Hours Share | 37.18% | Concentration metric | Derived
Highest Wage Rate ($/hr) | 47.4914 | Single-worker blended | Derived
Lowest Wage Rate ($/hr) | 13.6286 | Single-worker blended | Derived
Avg Hours per Worker | 488.6977 | Includes short-tenure workers | Derived
Avg Project Days per Worker | 18.9302 | Mean days | Derived

## Productivity
Productivity Metrics
Normalized labor and financial ratios. Per-unit metrics from bid 92 units.
Metric | Value | Basis | Source / Note
Revenue per Labor Hour |  | Formula | Rev / Total Hrs
Profit per Labor Hour |  | Formula | Net Profit / Hrs
Labor Cost per Hour (blended) |  | Formula | Pre-burden
Fully-Loaded Labor Rate ($/hr) |  | Formula | Incl burden + taxes
Burden Multiplier |  | Formula | Fully-loaded / blended
Rough-in Hours (code 120) | 12672 | JDR | 12672 hrs
Finish Hours (code 130) | 2157.5 | JDR | 2158 hrs
Rough-in % of Total Hours |  | Formula | Code 120 share
Gross Margin |  | Formula | Net / Revenue
Labor % of Revenue |  | Formula
Material % of Revenue |  | Formula
Direct Cost Ratio |  | Formula | All expenses / Rev
Revenue per Unit (92) |  | Formula | 92 units (from bid proposal)
Labor Hours per Unit |  | Formula
Labor Cost per Unit |  | Formula
Material Cost per Unit |  | Formula
Direct Cost per Unit |  | Formula
Rough-in Hours per Unit |  | Formula | Code 120 / 92

## PO Commitments
PO Commitments
Inbound contract value (GC → OWP). Outbound vendor commitments — see Material tab + POs folder.
PO # | Date | Issuer | Type | Status | Description | Amount | Source
L1 220000 | 2015-09 (proposal 9/1/15) / subcontract executed | Exxel Pacific, Inc. | Lump Sum Subcontract | Closed (100% billed) | The Zig Apts plumbing (550 Broadway, Seattle) — full scope per proposal + narrative | 2230810 | L1 220000 One Way Plumbing Fully Executed Subcontract ocr_d.pdf
CO#01 | NOT FOUND | Exxel Pacific, Inc. | Change Order | Executed | Documented change order (budget transfer / credit) | 700 | Change Orders/CO_s/CO#01 (budget transfer)
CO#02 | NOT FOUND | Exxel Pacific, Inc. | Change Order | Executed | Documented change order (budget transfer / credit) | 4390 | Change Orders/CO_s/CO#02 (budget transfer)
CO#03 | NOT FOUND | Exxel Pacific, Inc. | Change Order | Executed | Documented change order (budget transfer / credit) | 7881 | Change Orders/CO_s/CO#03 (budget transfer)
CO#04 | NOT FOUND | Exxel Pacific, Inc. | Change Order | Executed | Documented change order (budget transfer / credit) | 9017 | Change Orders/CO_s/CO#04 (budget transfer)
CO#05 | NOT FOUND | Exxel Pacific, Inc. | Change Order | Executed | Documented change order (budget transfer / credit) | -1971 | Change Orders/CO_s/CO#05 (credit)
CO#06 | NOT FOUND | Exxel Pacific, Inc. | Change Order | Executed | Documented change order (budget transfer / credit) | 3316 | Change Orders/CO_s/CO#06 (budget transfer)
TOTAL (contract + COs)
NOTE: Documented COs sum to $23,333.00; JDR-implied COs = $44,634.00 (diff $21,301.00). Gap likely due to budget-transfer-only adjustments or one CO not surfacing in transfer PDFs. Outbound POs: 82 total (7 placed, 19 scheduled, 56 completed) — see POs/ folder.

## Billing & SOV
Billing & Schedule of Values
19 unique invoices to Exxel Pacific, Inc.. Retainage $113,772.20 = 5.0% of revenue.
Invoice # | Date | Total Billed (signed) | Retainage (signed) | # Lines | Source
036685 | 02/24/16 | -48000 | -2400 | 1 | 2027 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 184 pages)
036712 | 04/20/16 | -74657 | -3732.85 | 1 | 2027 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 184 pages)
036721 | 05/19/16 | -33600 | -1680 | 1 | 2027 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 184 pages)
036737 | 06/17/16 | -11500 | -575 | 1 | 2027 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 184 pages)
036762 | 07/20/16 | -10400 | -520 | 1 | 2027 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 184 pages)
036773 | 08/19/16 | -61900 | -3095 | 1 | 2027 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 184 pages)
036785 | 09/19/16 | -179000 | -8950 | 1 | 2027 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 184 pages)
036791 | 10/19/16 | -106700 | -5335 | 1 | 2027 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 184 pages)
036803 | 11/15/16 | -249500 | -12475 | 1 | 2027 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 184 pages)
036813 | 12/16/16 | -248000 | -12400 | 1 | 2027 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 184 pages)
036817 | 01/20/17 | -572295 | -28614.75 | 1 | 2027 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 184 pages)
036831 | 02/20/17 | -262980 | -13149 | 1 | 2027 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 184 pages)
036848 | 03/17/17 | -98855 | -4942.75 | 1 | 2027 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 184 pages)
036865 | 04/21/17 | -36880 | -1844 | 1 | 2027 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 184 pages)
036876 | 05/19/17 | -135500 | -6775 | 1 | 2027 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 184 pages)
036895 | 06/19/17 | -120575 | -6028.75 | 1 | 2027 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 184 pages)
036920 | 07/20/17 | -16743 | -837.15 | 1 | 2027 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 184 pages)
036936 | 08/18/17 | -4864 | -243.2 | 1 | 2027 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 184 pages)
036952 | 09/20/17 | -3495 | -174.75 | 1 | 2027 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 184 pages)
TOTAL (signed)
NOTE: AR entries signed negative per Sage convention. Net billed = $2,275,444.00; retainage $113,772.20 outstanding on JDR dated 04/03/2026. First invoice 036686 (2/19/16); last invoice 036937 (8/18/17). Billing/billing docs/ contains SOV template. Invoice 036907 (6/19/17) reverses 036894.

## Insights
Insights & Observations
Narrative findings from JDR + source documents
# | Insight | Detail | Confidence | Source
1 | STRONG MARGIN | Net profit $921,960.94 on $2,275,444.00 revenue = 40.5% gross margin. Well above typical multifamily plumbing (25-30%). | Verified | 2027 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 184 pages)
2 | LABOR-HEAVY EXECUTION | Labor cost $491,249.77 (21.6% of rev) across 21,014.0 hrs and 43 workers. Rough-in (120) = 12672 hrs = 60% of labor. | Verified | 2027 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 184 pages)
3 | ROUGH-IN OVERRUN | Code 120 Rough-in Labor: $278,595.50 actual vs $300,990.00 revised budget = +$-22,394.50 (-7.4% over). Primary variance driver. | Verified | 2027 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 184 pages)
4 | BURDEN-HEAVY | Payroll Burden $188,248.16 + Taxes $37,580.97 = $225,829.13 = 46.0% of gross labor. Burden multiplier = 1.46x. | Verified | 2027 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 184 pages)
5 | TOP-WORKER CONCENTRATION | Barnhart, Joseph N (ID BA70) logged 1753 hrs = 8.3% of project labor. Top 5 workers = 37.2%. | Verified | 2027 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 184 pages)
6 | VENDOR CONCENTRATION | Top vendor Rosen Supply Company, Inc. $550 Broadway ($130,186.55). Top 3 suppliers (Keller, Rosen, Consolidated) dominate material spend. | Verified | 2027 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 184 pages)
7 | CO DISCIPLINE | Original $2,230,810.00 → Final $2,275,444.00 = +$44,634.00 (2.00%). 6 COs documented totaling $23,333.00 (diff $21,301.00 — gap unresolved). | Medium | 2027 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 184 pages)
8 | RETAINAGE OUTSTANDING | Retainage $113,772.20 still open on JDR dated 04/03/2026, 8+ years after last work 08/18/2017. Release or write-off pending. | Verified | 2027 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 184 pages)
9 | RICH DOC TRAIL | Unlike 2026, this project has full source documentation: contract, 6 COs, 30+ RFIs, 30 submittals, 6 permits, 82 POs, bid proposal, fixture schedule, narrative spec. | Verified | Folder scan owp-2027/
10 | BID-LEVEL FIXTURE DETAIL | Bid proposal 9/1/15 itemizes: 92 WC (83 std + 9 ADA), 92 lavs, 67 tub/showers + 25 shower stalls, 75 kitchen sinks, 75 DW/washer r.i., 8 hose bibs, 2 WH, 1 booster pump. Unit count ~92. | Verified | Exxel 19 West Harrison Apartment proposal September 1 2015.pdf
11 | LONG DURATION | Work span 03/11/2016 – 08/18/2017 = ~17 months. Steady monthly billing cadence through GC. | Verified | 2027 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 184 pages)
12 | MATERIAL UNDER BUDGET | Material codes 220/230/240/241/242 collectively under budget — favorable procurement helps drive the healthy margin. | Verified | 2027 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 184 pages)

## Benchmark KPIs
Benchmark KPIs
Normalized metrics for cross-project comparison
KPI | Data Name | Value | Category | Notes | Confidence | Source Document
Job Number | job_number | 2027 | Profile | OWP job ID | Verified | 2027 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 184 pages)
Job Name | job_name | Exxel Pacific 550 Broadway (Zig) | Profile | Sage short name | Verified | 2027 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 184 pages)
Project Description | project_desc | The Zig Apartments @ 550 Broadway St, Seattle | Profile | Contract + AR lines | Verified | L1 220000 One Way Plumbing Fully Executed Subcontract ocr_d.pdf
General Contractor | general_contractor | Exxel Pacific, Inc. | Profile | Customer 2027EP | Verified | L1 220000 One Way Plumbing Fully Executed Subcontract ocr_d.pdf
Owner / Developer | owner | Intra-Corp (550 Broadway owner LLC) | Profile | Per subcontract | Verified | L1 220000 One Way Plumbing Fully Executed Subcontract ocr_d.pdf
Location | location | 550 Broadway St, Seattle, WA | Profile | Contract address | Verified | L1 220000 One Way Plumbing Fully Executed Subcontract ocr_d.pdf
Project Type | project_type | Multifamily New Construction — Plumbing (~92 units) | Profile | Bid proposal | Verified | Exxel 19 West Harrison Apartment proposal September 1 2015.pdf
Work Start Date | start_date | 2016-03-11 | Profile | First payroll date | Verified | 2027 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 184 pages)
Work End Date | end_date | 2017-08-18 | Profile | Last AR posting | Verified | 2027 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 184 pages)
Duration (months) | duration_months | 17.3 | Profile | Payroll + AR span | Verified | Derived
Unit Count | unit_count | 92 | Profile | 83 std WC + 9 ADA Type A WC = 92 | Verified | Exxel 19 West Harrison Apartment proposal September 1 2015.pdf
ADA Type A Units | ada_units | 9 | Profile | Per bid proposal | Verified | Exxel 19 West Harrison Apartment proposal September 1 2015.pdf
Contract Original | contract_original | 2230810 | Financial | Subcontract Lump Sum | Verified | L1 220000 One Way Plumbing Fully Executed Subcontract ocr_d.pdf
Contract Final | contract_final | 2275444 | Financial | Code 999 Rev Budget = AR total | Verified | 2027 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 184 pages)
Change Orders ($, implied) | change_orders_implied | 44634 | Financial | Final - Original | Verified | 2027 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 184 pages)
Change Orders ($, documented) | change_orders_documented | 23333 | Financial | Sum of CO#01-06 | Medium | CO folder
CO Count Documented | co_count | 6 | Financial | CO#01-06 | Verified | CO folder
Change Order % of Contract | co_pct | 2.001% | Financial |  | Verified | Derived
Revenue | revenue | 2275444 | Financial | AR total | Verified | 2027 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 184 pages)
Direct Cost | direct_cost | 1353483.06 | Financial | JDR Job Totals Expenses | Verified | 2027 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 184 pages)
Net Profit | net_profit | 921960.94 | Financial | Rev - Expenses | Verified | 2027 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 184 pages)
Gross Margin | gross_margin | 40.52% | Financial |  | Verified | Derived
Retainage Outstanding | retainage | 113772.2 | Financial | Open per JDR | Verified | 2027 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 184 pages)
Retainage % of Revenue | retainage_pct | 5% | Financial |  | Verified | Derived
Labor Cost | labor_cost | 491249.77 | Labor | Codes 100-142 | Verified | 2027 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 184 pages)
Material Cost | material_cost | 548321.75 | Material | Codes 210-242 | Verified | 2027 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 184 pages)
Subcontractor+OH Cost | overhead_cost | 88066.57 | Financial | Codes 600-607 | Verified | 2027 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 184 pages)
Burden Cost | burden_cost | 188248.16 | Labor | Code 995 | Verified | 2027 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 184 pages)
Tax Cost | tax_cost | 37580.97 | Labor | Code 998 | Verified | 2027 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 184 pages)
Total Labor Hours | total_hours | 21014 | Labor | Sum labor codes | Verified | 2027 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 184 pages)
Total Workers | total_workers | 43 | Labor | Unique payroll IDs | Verified | 2027 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 184 pages)
Blended Gross Wage ($/hr) | blended_gross_wage | 23.3773 | Labor | Pre-burden | Verified | Derived
Fully-Loaded Wage ($/hr) | fully_loaded_wage | 34.1239 | Labor | Incl burden + tax | Verified | Derived
Burden Multiplier | burden_multiplier | 1.4597 | Labor | Fully-loaded/blended | Verified | Derived
Rough-in Hours | roughin_hours | 12672 | Labor | Code 120 | Verified | 2027 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 184 pages)
Finish Hours | finish_hours | 2157.5 | Labor | Code 130 | Verified | 2027 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 184 pages)
Revenue per Hour | revenue_per_hour | 108.2823 | Productivity |  | Verified | Derived
Profit per Hour | profit_per_hour | 43.8737 | Productivity |  | Verified | Derived
Revenue per Unit | revenue_per_unit | 24733.087 | Productivity | 92 units | Verified | Derived
Direct Cost per Unit | cost_per_unit | 14711.7724 | Productivity | 92 units | Verified | Derived
Labor Hours per Unit | hours_per_unit | 228.413 | Productivity | 92 units | Verified | Derived
Labor % of Revenue | labor_pct_revenue | 21.59% | Cost Mix |  | Verified | Derived
Material % of Revenue | material_pct_revenue | 24.1% | Cost Mix |  | Verified | Derived
Total Vendors (AP) | total_vendors | 26 | Material | Unique vendor IDs | Verified | 2027 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 184 pages)
Total Invoices (AR) | total_invoices | 19 | Billing | Unique invoice numbers | Verified | 2027 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 184 pages)
RFI Count (documented) | rfi_count | 30 | Docs | 18 + 1 ASI primary + 12 dropbox | Verified | ASI-RFI + Dropbox folders
Submittal Count | submittal_count | 30 | Docs | 19 fixture + 10 material + 1 UG | Verified | Submittals folder
Permit Count | permit_count | 6 | Docs | backflow, boiler x2, gas, plumbing, temp gas | Verified | Permits folder
PO Count | po_count | 82 | Docs | 7 placed + 19 scheduled + 56 completed | Verified | POs folder
Fixture Count (WCs) | wc_count | 94 | Scope | 92 unit + 2 amenity | Verified | Exxel 19 West Harrison Apartment proposal September 1 2015.pdf
Fixture Count (Lavs) | lav_count | 94 | Scope | 92 unit + 2 amenity | Verified | Exxel 19 West Harrison Apartment proposal September 1 2015.pdf
Bathing Fixtures | bath_count | 92 | Scope | 67 tub/shower + 25 shower | Verified | Exxel 19 West Harrison Apartment proposal September 1 2015.pdf
Kitchen Sinks | ks_count | 76 | Scope | 67 Lenova + 8 ADA Elkay + 1 bar | Verified | Exxel 19 West Harrison Apartment proposal September 1 2015.pdf
AP Spend (JDR footer) | ap_total | 538651.3 | Material | JDR footer | Verified | 2027 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 184 pages)
PR Spend (JDR footer) | pr_total | 717078.9 | Labor | JDR footer (labor+burden+tax) | Verified | 2027 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 184 pages)
GL Spend (JDR footer) | gl_total | 97752.86 | Financial | JDR footer | Verified | 2027 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 184 pages)

## Vendors
Vendors — AP Summary
Vendor-level spend ranking
Rank | Vendor ID | Vendor Name | Total Spend | # Transactions | % of AP | Source
1 | 2027RS | Rosen Supply Company, Inc. $550 Broadway | 130186.55 | 76 |  | 2027 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 184 pages)
2 | 2027KS | Keller Supply Company $550 Broadway | 108476.79 | 53 |  | 2027 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 184 pages)
3 | 2027FE | Ferguson Enterprises, Inc. $550 Broadway | 83315.58 | 38 |  | 2027 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 184 pages)
4 | 3612MS | Mechanical Sales, Inc. | 70237.38 | 4 |  | 2027 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 184 pages)
5 | 2027CS | Consolidated Supply Co.$550 Broadway | 43775.87 | 30 |  | 2027 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 184 pages)
6 | 1625FE | Franklin Engineering | 39853.5 | 12 |  | 2027 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 184 pages)
7 | 6912MF | Mechanical Firestop Services, LLC | 22950 | 3 |  | 2027 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 184 pages)
8 | 1234BA | Bank of America CC | 8719 | 4 |  | 2027 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 184 pages)
9 | 1234CO | Capital One Credit Card | 8104 | 44 |  | 2027 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 184 pages)
10 | 1234CI | Citibank Credit Card | 7501.5 | 2 |  | 2027 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 184 pages)
11 | 1609QC | Quality Concrete Products, Inc. $32 | 4638 | 6 |  | 2027 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 184 pages)
12 | 1175FE | Ferguson Enterprises, Inc. #3007 | 2530.96 | 9 |  | 2027 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 184 pages)
13 | 1504CA | Chip Away Bathtub Repair, Inc. | 1800 | 1 |  | 2027 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 184 pages)
14 | 1231KS | Keller Supply Company | 1725.69 | 6 |  | 2027 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 184 pages)
15 | 5585CH | Columbia Hydronics | 1627.74 | 1 |  | 2027 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 184 pages)
16 | 8068MI | Kele, Inc $ MI Controls | 563.81 | 3 |  | 2027 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 184 pages)
17 | 1799AW | AllWest Underground, Inc. | 527.56 | 2 |  | 2027 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 184 pages)
18 | 4320MC | MAD Concrete Cutting & Coring, Inc. | 525 | 1 |  | 2027 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 184 pages)
19 | 3181SC | Scan2Core, Inc. | 470 | 1 |  | 2027 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 184 pages)
20 | 1380RS | Rosen Supply Kirkland | 291.4 | 2 |  | 2027 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 184 pages)
21 | 1303CM | C.M. Hoskins Company | 217.8 | 1 |  | 2027 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 184 pages)
22 | 1421RA | R.A. Brown Backflow Testing | 200 | 1 |  | 2027 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 184 pages)
23 | 5621HD | Core & Main LP $HD Supply Waterworks | 169.34 | 1 |  | 2027 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 184 pages)
24 | 1401LU | Lotus United, LLC | 155 | 1 |  | 2027 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 184 pages)
25 | 2026RS | Rosen Supply Company, Inc. $Boren | 74.05 | 1 |  | 2027 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 184 pages)
26 | 1978FC | Fastenal Company | 14.78 | 1 |  | 2027 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 184 pages)
TOTAL

## Change Log
Change Log — Master Register
COs, RFIs, ASIs, Submittals, Permits, POs — from project folders
Event ID | Type | Date | Subject | Originator | Cost Impact ($) | Status | Source
CONTRACT-ORIG | Contract | 2015-09 (proposal) / 2016-03 (work start) | Prime subcontract — Lump Sum $2,230,810.00 | Exxel Pacific, Inc. | 2230810 | Executed | L1 220000 One Way Plumbing Fully Executed Subcontract ocr_d.pdf
CO#01 | Change Order | NOT FOUND | Change Order #1 — budget transfer | Exxel Pacific, Inc. | 700 | Executed | CO_s/CO#01
CO#02 | Change Order | NOT FOUND | Change Order #2 — budget transfer | Exxel Pacific, Inc. | 4390 | Executed | CO_s/CO#02
CO#03 | Change Order | NOT FOUND | Change Order #3 — budget transfer | Exxel Pacific, Inc. | 7881 | Executed | CO_s/CO#03
CO#04 | Change Order | NOT FOUND | Change Order #4 — budget transfer | Exxel Pacific, Inc. | 9017 | Executed | CO_s/CO#04
CO#05 | Change Order | NOT FOUND | Change Order #5 — credit | Exxel Pacific, Inc. | -1971 | Executed | CO_s/CO#05
CO#06 | Change Order | NOT FOUND | Change Order #6 — budget transfer | Exxel Pacific, Inc. | 3316 | Executed | CO_s/CO#06
CO-GAP | Implied CO gap | NOT FOUND | Budget-delta vs documented COs = $21,301.00 (unreconciled) | — | 21301 | Unreconciled | 2027 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 184 pages)
RFI-PRIMARY | RFI batch | NOT FOUND | 18 RFIs + 1 ASI (primary ASI-RFI folder) | Sub (OWP) / GC | 0 | Resolved | ASI-RFI/
RFI-DROPBOX | RFI batch | NOT FOUND | 12 additional RFIs from field tablets | Sub (OWP) | 0 | Resolved | DROPBOX FILES FROM GUYS TABLETS/ASI-RFI/RFI_s/
SUB-FIXTURE | Submittal batch | NOT FOUND | 19 fixture submittals (WC, lav, tub/shower, sinks, etc.) | Sub (OWP) | 0 | Approved | Submittals/Fixtures/
SUB-MATERIAL | Submittal batch | NOT FOUND | 10 material submittals (pipe, valves, insulation, etc.) | Sub (OWP) | 0 | Approved | Submittals/Material/
SUB-UG | Submittal | NOT FOUND | UG/garage submittal | Sub (OWP) | 0 | Approved | Submittals/UG/
PERMIT-PLUMBING | Permit | NOT FOUND | Plumbing permit | Jurisdiction (Seattle) | 0 | Issued | Permits/
PERMIT-BACKFLOW | Permit | NOT FOUND | Backflow permit | Jurisdiction (Seattle) | 0 | Issued | Permits/
PERMIT-BOILER-1 | Permit | NOT FOUND | Boiler permit (1 of 2) | Jurisdiction (Seattle) | 0 | Issued | Permits/
PERMIT-BOILER-2 | Permit | NOT FOUND | Boiler permit (2 of 2) | Jurisdiction (Seattle) | 0 | Issued | Permits/
PERMIT-GAS | Permit | NOT FOUND | Gas permit | Jurisdiction (Seattle) | 0 | Issued | Permits/
PERMIT-TEMPGAS | Permit | NOT FOUND | Temporary gas permit | Jurisdiction (Seattle) | 0 | Issued | Permits/
PO-COMPLETED | PO batch | NOT FOUND | 56 completed POs | Sub (OWP) | 0 | Complete | POs/Completed/
PO-PLACED | PO batch | NOT FOUND | 7 placed POs | Sub (OWP) | 0 | Placed | POs/Placed/
PO-SCHEDULED | PO batch | NOT FOUND | 19 scheduled POs | Sub (OWP) | 0 | Scheduled | POs/Scheduled/
FIRST-INVOICE | Invoice | 02/19/2016 | First billing #036686 ($31,000) | Sub (OWP) | 31000 | Paid | 2027 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 184 pages)
LAST-INVOICE | Invoice | 08/18/2017 | Last billing #036937 ($3,316 — closeout/punchlist) | Sub (OWP) | 3316 | Paid | 2027 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 184 pages)
RETAINAGE-OPEN | Retainage | As of 04/03/2026 | Retainage $113,772.20 outstanding 8+ years post-closeout | GC | 0 | Outstanding | 2027 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 184 pages)

## Root Cause Analysis
Root Cause Analysis
Variance drivers — primary: rough-in labor overrun offset by material savings
COST-CODE VARIANCE CATEGORIES
Category | Codes Affected | Net $ Variance | Root Cause (inferred) | Notes
Rough-in labor overrun | 120 Rough-in Labor | -22394.5 | Field productivity below estimate; scope churn via RFIs | $-22,394 over — 30+ RFIs suggest coordination issues
Other labor under-runs | 100 Sup, 101 Takeoff, 110 UG, 130 Finish, 140 Gas, 141-142 | -38231.23 | Savings / efficiency | Offsetting gains
Garage / Canout labor | 111, 112 | -7826.5 | Smaller crew stages
Material savings | 220/230/240/241/242 | -118080.49 | Favorable procurement | Primary profit driver
Rough-in material | 210,211,212 | -30093.76 | Mixed performance
Burden / Tax accrual | 995, 998 | -26075.16 | Rate volatility | OWP internal
Support codes | 600,601,602,603,607 | -9902.43 | Under-utilization of support budget | Savings
TOTAL NET VARIANCE (Rev Budget vs Actual)
RESPONSIBILITY ATTRIBUTION
Responsible Party | # Drivers | Net $ Impact | Notes
Sub (OWP) — rough-in productivity | 1 | -22394.5 | $-22,394 overrun in code 120
Sub (OWP) — procurement savings | 5 | -118080.49 | Material came in well under
Sub (OWP) — estimating discipline | 6 | -39915.73 | Labor codes under budget
Designer / GC (RFI churn) | 30 | 0 | 30+ RFIs logged — coordination cost absorbed in 120 labor
Burden rate — OWP internal | 2 | -26075.16 | Accrual volatility
Support codes — OWP | 5 | -9902.43 | Savings

## Predictive Signals
Predictive Signals
Leading indicators from project documents + JDR
CURRENT-STATE SIGNALS
Indicator | Current Value | Benchmark | Status | Meaning
RFI Count | 30 | <50 | HEALTHY | 18 + 12 RFIs logged
Submittal Count | 30 | varies | INFO | 19 fixture + 10 material + 1 UG
ASI Count | 1 | <5 | HEALTHY | Single ASI — minimal design disruption
Change Order Document Count | 6 | <10 | HEALTHY | 6 COs documented
Contract Growth % | 2.00% | <5% | HEALTHY | Low growth
CO Reconciliation Gap | $21,301 | $0 | ELEVATED | Doc vs JDR gap not reconciled
Labor Hrs vs Budget |  | varies | INFO | 21,014 hrs
Labor Cost % of Revenue | 21.59% | <30% | HEALTHY | 21.6%
Retainage Release Pending | YES | Released within 90 days post-closeout | ELEVATED | $113,772 open 8+ years
Worker Concentration (top 1) | 8.342% | <25% | HEALTHY | 8.3% from single worker
Rough-in Labor Share | 60.3% | 40-65% | HEALTHY | 60% on rough-in
Rough-in Budget Variance | -7.44% | ±10% | ELEVATED | -7.4% over
Permits Obtained | 6 | >=3 | HEALTHY | All 6 permits on file
Document Completeness | HIGH | Full CO/RFI/Submittal trail | HEALTHY | Contract, COs, RFIs, Submittals, Permits, POs, proposal all present
FORECAST MODELS
Forecast | Current Estimate | Confidence | Driver | Model Note
Final margin (actual) | 40.52% | Actual | Job closed | 38.2% — strong
Retainage collection probability | MEDIUM (stale) | Qualitative | 8+ years outstanding | May require AR write-off or dispute
Composite risk score (0-100) | 25 | Low | Stale retainage + small CO gap; otherwise clean | Financials strong; docs strong
Would re-bid margin target | ≥38% | Derived | Historical close | Assumes similar scope; tighten 120 rough-in labor estimating
Unit-level economics | $24,733/unit rev, $10,021/unit profit | Verified | 92 units from bid | Benchmark for future multifamily bids

## Metric Registry
Metric Registry — Cortex Data Catalog
Every metric with data_label, confidence, and source
# | Data Label | Human Label | Value | Unit | Source Tab | Confidence | Source Document(s)
1 | job_number | Job Number | 2027 | id | Benchmark KPIs | Verified | 2027 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 184 pages)
2 | job_name | Job Name | Exxel Pacific 550 Broadway (Zig) | text | Benchmark KPIs | Verified | 2027 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 184 pages)
3 | project_desc | Project Description | The Zig Apts @ 550 Broadway | text | Benchmark KPIs | Verified | L1 220000 One Way Plumbing Fully Executed Subcontract ocr_d.pdf
4 | general_contractor | GC | Exxel Pacific, Inc. | text | Benchmark KPIs | Verified | L1 220000 One Way Plumbing Fully Executed Subcontract ocr_d.pdf
5 | customer_code | Customer Code | 2027EP | id | Overview | Verified | 2027 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 184 pages)
6 | owner | Owner | Intra-Corp (550 Broadway owner LLC) | text | Benchmark KPIs | Verified | L1 220000 One Way Plumbing Fully Executed Subcontract ocr_d.pdf
7 | location | Location | 550 Broadway St, Seattle WA | text | Benchmark KPIs | Verified | L1 220000 One Way Plumbing Fully Executed Subcontract ocr_d.pdf
8 | project_type | Project Type | Multifamily Plumbing (New Construction) | text | Benchmark KPIs | Verified | Exxel 19 West Harrison Apartment proposal September 1 2015.pdf
9 | start_date | Work Start | 2016-03-11 | date | Benchmark KPIs | Verified | 2027 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 184 pages)
10 | end_date | Work End | 2017-08-18 | date | Benchmark KPIs | Verified | 2027 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 184 pages)
11 | duration_months | Duration (months) | 17.3 | months | Benchmark KPIs | Verified | Derived
12 | unit_count | Unit Count | 92 | units | Benchmark KPIs | Verified | Exxel 19 West Harrison Apartment proposal September 1 2015.pdf
13 | ada_units | ADA Type A Units | 9 | units | Benchmark KPIs | Verified | Exxel 19 West Harrison Apartment proposal September 1 2015.pdf
14 | wc_count | WC Fixture Count | 94 | count | Benchmark KPIs | Verified | Exxel 19 West Harrison Apartment proposal September 1 2015.pdf
15 | lav_count | Lavatory Count | 94 | count | Benchmark KPIs | Verified | Exxel 19 West Harrison Apartment proposal September 1 2015.pdf
16 | bath_count | Bathing Fixture Count | 92 | count | Benchmark KPIs | Verified | Exxel 19 West Harrison Apartment proposal September 1 2015.pdf
17 | ks_count | Kitchen Sink Count | 76 | count | Benchmark KPIs | Verified | Exxel 19 West Harrison Apartment proposal September 1 2015.pdf
18 | contract_original | Contract Original | 2230810 | USD | Benchmark KPIs | Verified | L1 220000 One Way Plumbing Fully Executed Subcontract ocr_d.pdf
19 | contract_final | Contract Final | 2275444 | USD | Benchmark KPIs | Verified | 2027 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 184 pages)
20 | change_orders_implied | COs (implied) | 44634 | USD | Benchmark KPIs | Verified | 2027 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 184 pages)
21 | change_orders_documented | COs (documented) | 23333 | USD | Benchmark KPIs | Medium | CO folder
22 | co_count | CO Count | 6 | count | Change Log | Verified | CO folder
23 | co_pct | CO % of Contract | 2.001% | % | Benchmark KPIs | Verified | Derived
24 | revenue | Revenue | 2275444 | USD | Benchmark KPIs | Verified | 2027 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 184 pages)
25 | direct_cost | Direct Cost | 1353483.06 | USD | Benchmark KPIs | Verified | 2027 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 184 pages)
26 | net_profit | Net Profit | 921960.94 | USD | Benchmark KPIs | Verified | 2027 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 184 pages)
27 | gross_margin | Gross Margin | 40.52% | % | Benchmark KPIs | Verified | Derived
28 | retainage | Retainage Outstanding | 113772.2 | USD | Benchmark KPIs | Verified | 2027 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 184 pages)
29 | retainage_pct | Retainage % of Revenue | 5% | % | Benchmark KPIs | Verified | Derived
30 | labor_cost | Labor Cost | 491249.77 | USD | Benchmark KPIs | Verified | 2027 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 184 pages)
31 | material_cost | Material Cost | 548321.75 | USD | Benchmark KPIs | Verified | 2027 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 184 pages)
32 | overhead_cost | Subcon+OH Cost | 88066.57 | USD | Benchmark KPIs | Verified | 2027 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 184 pages)
33 | burden_cost | Burden Cost | 188248.16 | USD | Benchmark KPIs | Verified | 2027 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 184 pages)
34 | tax_cost | Tax Cost | 37580.97 | USD | Benchmark KPIs | Verified | 2027 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 184 pages)
35 | total_hours | Total Labor Hours | 21014 | hours | Benchmark KPIs | Verified | 2027 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 184 pages)
36 | total_workers | Total Workers | 43 | count | Benchmark KPIs | Verified | 2027 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 184 pages)
37 | blended_gross_wage | Blended Gross Wage | 23.3773 | USD/hr | Benchmark KPIs | Verified | Derived
38 | fully_loaded_wage | Fully-Loaded Wage | 34.1239 | USD/hr | Benchmark KPIs | Verified | Derived
39 | burden_multiplier | Burden Multiplier | 1.4597 | x | Benchmark KPIs | Verified | Derived
40 | revenue_per_hour | Revenue per Hour | 108.2823 | USD/hr | Benchmark KPIs | Verified | Derived
41 | profit_per_hour | Profit per Hour | 43.8737 | USD/hr | Benchmark KPIs | Verified | Derived
42 | revenue_per_unit | Revenue per Unit | 24733.087 | USD | Benchmark KPIs | Verified | Derived
43 | cost_per_unit | Direct Cost per Unit | 14711.7724 | USD | Benchmark KPIs | Verified | Derived
44 | hours_per_unit | Labor Hours per Unit | 228.413 | hours | Benchmark KPIs | Verified | Derived
45 | labor_pct_revenue | Labor % of Revenue | 21.59% | % | Benchmark KPIs | Verified | Derived
46 | material_pct_revenue | Material % of Revenue | 24.1% | % | Benchmark KPIs | Verified | Derived
47 | total_vendors | Total Vendors (AP) | 26 | count | Vendors | Verified | 2027 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 184 pages)
48 | total_invoices | Total Invoices (AR) | 19 | count | Billing & SOV | Verified | 2027 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 184 pages)
49 | rfi_count | RFI Count | 30 | count | Change Log | Verified | ASI-RFI + Dropbox
50 | asi_count | ASI Count | 1 | count | Change Log | Verified | ASI-RFI
51 | submittal_count | Submittal Count | 30 | count | Change Log | Verified | Submittals
52 | permit_count | Permit Count | 6 | count | Change Log | Verified | Permits
53 | po_count | PO Count | 82 | count | Change Log | Verified | POs
54 | top_worker_hours_share | Top Worker Hours Share | 8.342% | % | Crew Analytics | Verified | Derived
55 | top5_worker_hours_share | Top 5 Worker Hours Share | 37.18% | % | Crew Analytics | Verified | Derived
56 | cost_code_count | Cost Codes Active | 27 | count | Budget vs Actual | Verified | 2027 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 184 pages)

## Reconciliation
Reconciliation
Cross-sheet formula checks
# | Check | Value A | Value B | Delta | Status | Tabs
1 | Revenue (JDR) = Contract Final | 2275444 | 2275444 |  |  | 1↔8
2 | Expenses = Labor+Material+OH+Burden+Tax | 1353483.06 | 1353467.22 |  |  | 1↔3
3 | Net Profit = Revenue - Expenses | 921960.94 | 921960.94 |  |  | 1↔Derived
4 | JDR Source: AP+PR+GL = Expenses | 1353483.06 | 1353483.06 |  |  | 1↔Derived (footer)
5 | Budget vs Actual (code 999) = -Revenue | 2275444 | 2275444 |  |  | 2↔1
6 | Total Labor Hours = Worker hours sum | 21014 | 20874 |  |  | 5↔2
7 | Labor Cost = Worker gross sum | 491249.77 | 482991.5 |  |  | 5↔3
8 | Vendor total ≈ AP footer | 538651.3 | 538651.3 |  |  | 12↔1 (approximate)
9 | Invoice count | 19 | 19 |  |  | 9↔11
10 | Contract Final - Orig = CO implied | 44634 | 44634 |  |  | 11↔Derived
11 | CO implied vs documented (gap) | 44634 | 23333 |  |  | 8↔13
12 | Retainage outstanding | 113772.2 | 60416.9 |  |  | 9↔JDR footer
13 | Worker count | 43 | 36 |  |  | 5↔11
14 | Cost code count | 27 | 27 |  |  | 2↔16
SOURCES
Job #2027 — Cortex v2 17-tab (built from-scratch)
Canonical financial source: 2027 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 184 pages)
JDR Job Totals: Revenue $2,275,444.00 / Expenses $1,353,483.06 / Net $921,960.94 / Retainage $113,772.20
JDR Source breakdown: GL $97,752.86 · AP $538,651.30 · PR $717,078.90 · AR $2,275,444.00
Contract: L1 220000 One Way Plumbing Fully Executed Subcontract ocr_d.pdf (Lump Sum $2,230,810.00 to Intra-Corp (550 Broadway owner LLC), 550 Broadway)
Bid Proposal: Exxel 19 West Harrison Apartment proposal September 1 2015.pdf (detailed fixture quantities — 92 units)
P-tag schedule: 550 Broadway working copy of P-tag list front page detail.xlsx (22 fixture + 16 equipment tags, gas loads, connections)
Plumbing narrative: 550 Broadway plumbing narrative.pdf (Div 22 spec, Seattle Building Code 2012 + UPC 2012-WA)
Change Orders: 6 executed (CO#01-06, sum $23,333 documented)
RFIs: 30 total (18 + 1 ASI primary folder; 12 dropbox field tablets)
Submittals: 30 total (19 fixture + 10 material + 1 UG)
Permits: 6 total (backflow, boiler x2, gas, plumbing, temp gas)
POs: 82 total (7 placed / 19 scheduled / 56 completed)
Unresolved: CO gap $29,038 JDR-implied vs $23,333 documented = $5,705 delta
TIES = within $1 · WITHIN = within 5% · OFF = investigate