## Overview
Job #2028 · Exxel Pacific Reserve @ Lynnwood
Cortex JCR Cortex v2 • Exxel Pacific, Inc. (customer 2028EP) • Lynnwood, WA • Owner: AVS Communities
PROJECT OVERVIEW
Project Job # | 2028 |  | 2028 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages) header
Project Name (Sage) | Exxel Pacific Reserve @ Lynnwood |  | 2028 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages) header
Project Description | Reserve @ Lynnwood — 296-unit new construction plumbing |  | Exxel Pacific Reserve @ Lynnwood Subcontract / AR line descriptions
General Contractor | Exxel Pacific, Inc. |  | Exxel Pacific Reserve @ Lynnwood Subcontract
Customer Code (Sage) | 2028EP |  | 2028 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
Owner / Developer | AVS Communities |  | Exxel Pacific Reserve @ Lynnwood Subcontract
Jobsite Location | Lynnwood, WA |  | Exxel Pacific Reserve @ Lynnwood Subcontract
Contract / PO Document | Exxel Pacific Reserve @ Lynnwood Subcontract |  | Lump Sum subcontract
Plans / Specifications | Reserve @ Lynnwood plumbing narrative (Div 22 plumbing narrative) + fixture schedule + proposal |  | Folder scan
Fixture Schedule | Reserve @ Lynnwood fixture schedule (fixture schedule for 296-unit multifamily) |  | Referenced
Bid Proposal | Exxel Pacific Reserve @ Lynnwood Proposal |  | Detailed scope and fixture quantities
Contract Type | Lump Sum |  | Exxel Pacific Reserve @ Lynnwood Subcontract
Work Period | Per PR/AR posting dates in JDR |  | 2028 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
Total Unique Documents Reviewed | 1924 |  | File inventory across owp-2028/
CONTRACT VALUE |  | NET PROFIT | DIRECT COST | LABOR HOURS
2684887 |  | 1313608.9 | 1371278.1 | 24053.5
Original $2,979,880.00 + $-294,993.00 COs (-9.90%) |  | 48.9% margin | 51.1% of revenue | 45 workers
SCOPE OF WORK (from contract + proposal)
Full plumbing installation: underground, rough-in, finish, gas piping, water mains, insulation, mechanical room, and warranty.
296-unit multifamily new construction at Lynnwood, WA.
5 levels above ground, 1 level below grade (per Job Info).
Comprehensive fixture schedule with standard and ADA-compliant units.
Spec compliance: Current Building Code + UPC with Washington state amendments.
SOURCES
Canonical financial source: 2028 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
Job totals (JDR footer): Revenue $2,684,887.00 / Expenses $1,371,278.10 / Net $1,313,608.90 / Retainage $134,244.35
Source breakdown: GL $83,985.62 · AP $420,949.02 · PR $866,343.46 · AR $2,684,887.00
Contract: Exxel Pacific Reserve @ Lynnwood Subcontract (Lump Sum $2,979,880.00, descoped to $2,684,887.00)
Proposal: Exxel Pacific Reserve @ Lynnwood Proposal
Fixture schedule: Reserve @ Lynnwood fixture schedule
Plumbing narrative: Reserve @ Lynnwood plumbing narrative
Change Orders: Deductive scope changes; net contract reduction ${CO_TOTAL_IMPLIED:,.2f}
PROJECT TEAM (OWP Job Info)
Role | Status | Name / Firm
GC | Extracted | Exxel Pacific, Inc.
GC PM | Extracted | TJ Mellema / Coby Jones
GC Superintendent | Extracted | Brad Holz
GC PE | N/A | N/A
Developer | Extracted | AVS Communities
Architect | Extracted | Charles Morgan & Associates, LLC
Structural | N/A | N/A
Acoustical | N/A | N/A
ADA Consultant | N/A | N/A
Interior Design | N/A | N/A
MEP Engineer | N/A | N/A

## Budget vs Actual
Budget vs Actual
All 29 cost codes from JDR. Contract $2,979,880 → $2,684,887 (COs +$-294,993.00).
Cost Code | Description | Original Budget | Revised Budget | Actual | Variance | % of Revised | Hours | Source
100 | Supervision | 20000 | 10499 | 9454.5 |  |  | 209.5 | 2028 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
101 | Takeoff & Purchase Labor | 35400 | 18154 | 17076 |  |  | 380 | 2028 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
110 | Underground Labor | 54560 | 53331 | 24769 |  |  | 962 | 2028 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
111 | Garage Labor | 108000 | 109292 | 46509 |  |  | 1862 | 2028 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
112 | Canout Labor | 11700 | 11775 | 12283 |  |  | 469 | 2028 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
120 | Roughin Labor | 348060 | 350306 | 366998.59 |  |  | 16225 | 2028 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
130 | Finish Labor | 83600 | 719.5 | 719 |  |  | 19 | 2028 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
140 | Gas Labor | 14400 | 14400 | 10210.5 |  |  | 425.5 | 2028 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
141 | Water Main/Insulation Lab | 124740 | 124740 | 60276 |  |  | 2837 | 2028 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
142 | Mech Room Labor | 12500 | 14310 | 18210 |  |  | 664.5 | 2028 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
143 | Condensation Drains Labor | 0 | 0 | 905 |  |  | 37 | 2028 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
150 | Warranty Labor | 0 | 0 | 240.5 |  |  | 6.5 | 2028 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
210 | Underground Material | 62400 | 58475 | 19678.27 |  |  |  | 2028 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
211 | Garage Material | 79425 | 80707 | 41996.33 |  |  |  | 2028 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
212 | Canout Material | 17700 | 17954 | 9133.37 |  |  |  | 2028 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
220 | Roughin Material | 149440 | 151272 | 77241.99 |  |  |  | 2028 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
230 | Finish Material | 283585 | 143340 | 140999.27 |  |  |  | 2028 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
240 | Gas Material | 9600 | 9600 | 4382.08 |  |  |  | 2028 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
241 | Water Main/Insulation Mat | 148955 | 148955 | 97106.59 |  |  |  | 2028 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
242 | Mech Room Material | 75350 | 84131 | 68176.58 |  |  |  | 2028 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
243 | Condensation Drains Mat | 0 | 0 | 38.65 |  |  |  | 2028 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
600 | Subcontractor | 2500 | 2500 | 4405 |  |  |  | 2028 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
601 | Engineering/Plans | 25000 | 25000 | 20232.56 |  |  |  | 2028 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
602 | Rental Equipment | 6000 | 6000 | 1758.76 |  |  |  | 2028 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
603 | Permits & Licenses | 24000 | 24000 | 22287.6 |  |  |  | 2028 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
607 | Other Expenses | 10000 | 300 | 226 |  |  |  | 2028 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
995 | Payroll Burden | 352418.16 | 306897.99 | 252329.63 |  |  |  | 2028 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
998 | Payroll Taxes | 62191.44 | 54147.36 | 43634.33 |  |  |  | 2028 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
999 | Sales | -2979880 | -2684887 | -2684887 |  |  |  | 2028 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
TOTAL

## Cost Breakdown
Cost Breakdown by Category
Direct cost composition by category from JDR cost codes
Category | Cost Codes | Actual $ | % of Direct Cost | % of Revenue | Source
Labor | 100,101,110,111,112,120,130,140,141,142 | 566505.59 |  |  | 2028 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
Material | 210,211,212,220,230,240,241,242 | 458714.48 |  |  | 2028 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
Subcontractor + Engineering + Permits + Other | 600,601,602,603,607 | 48909.92 |  |  | 2028 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
Payroll Burden | 995 | 252329.63 |  |  | 2028 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
Payroll Taxes | 998 | 43634.33 |  |  | 2028 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
TOTAL DIRECT COST |  |  | 100%

## Material
Material Purchases — AP Vendors
Material + subcontractor spend by vendor (AP records from JDR). Supplemented with submittal/PO inventory.
Vendor ID | Vendor Name | Total Spend | # Transactions | Category (inferred) | Source
2028FE | Ferguson Enterprises, Inc. $Reserve@Lynn | 133734.62 | 42 | Plumbing / Supplies | 2028 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
2028RS | Rosen Supply Company $Reserve@Lynnwood | 117180.14 | 107 | Plumbing / Supplies | 2028 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
2028CS | Consolidated Supply Co.$Reserve@Lynnwood | 83009.23 | 52 | Plumbing / Supplies | 2028 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
2028KS | Keller Supply Company $Reserve@Lynnwood | 31988.36 | 47 | Plumbing / Supplies | 2028 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
1625FE | Franklin Engineering | 18771 | 3 | Engineering (601) | 2028 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
1126SS | Specification Sales, Inc. | 12844 | 1 | Uncategorized | 2028 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
1609QC | Quality Concrete Products, Inc. $32 | 6295 | 3 | Uncategorized | 2028 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
3612MS | Mechanical Sales, Inc. | 3819 | 2 | Plumbing / Supplies | 2028 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
4320MC | MAD Concrete Cutting & Coring, Inc. | 2530 | 3 | Uncategorized | 2028 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
5919PW | Patchworks, Inc. | 1875 | 1 | Uncategorized | 2028 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
7200UR | United Rentals, Inc. | 1758.76 | 7 | Uncategorized | 2028 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
8068MI | Kele, Inc $ MI Controls | 1635.61 | 2 | Uncategorized | 2028 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
1288DR | DRSi | 1409.16 | 3 | Uncategorized | 2028 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
2132MH | Manor Hardware & Construction Supply | 1199.52 | 4 | Plumbing / Supplies | 2028 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
5621HD | Core & Main LP $HD Supply Waterworks | 935.35 | 5 | Plumbing / Supplies | 2028 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
1303CM | C.M. Hoskins Company | 677.45 | 2 | Uncategorized | 2028 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
1380RS | Rosen Supply Kirkland | 580.07 | 4 | Plumbing / Supplies | 2028 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
1234CO | Capital One Credit Card | 362.9 | 4 | Credit Card (mixed) | 2028 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
1231KS | Keller Supply Company | 186.51 | 2 | Plumbing / Supplies | 2028 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
1978FC | Fastenal Company | 113.75 | 3 | Uncategorized | 2028 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
1175FE | Ferguson Enterprises, Inc. #3007 | 111.88 | 2 | Plumbing / Supplies | 2028 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
2027RS | Rosen Supply Company, Inc. $550 Broadway | 0 | 2 | Plumbing / Supplies | 2028 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
2027KS | Keller Supply Company $550 Broadway | 0 | 2 | Plumbing / Supplies | 2028 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
1130CS | Consolidated Supply Co. | -68.29 | 1 | Plumbing / Supplies | 2028 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
TOTAL
NOTE: AP total per JDR footer = $420,949.02. Vendor sum above approximates this. Submittals folder (Submittals/) contains 19 fixture + 10 material + 1 UG submittal documenting approved products. POs folder shows 82 POs (7 placed, 19 scheduled, 56 completed).

## Crew & Labor
Crew & Labor — Worker Roster
All 45 unique payroll workers from JDR.
Worker ID | Worker Name | Total Hours | Gross Pay | Blended Wage ($/hr) | # Work Days | Source
QU35 | Quintanilla, Esteban R | 1409.5 | 45272.5 |  | 37 | 2028 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
MO56 | Montenegro, Carlos E | 1288 | 27522.5 |  | 39 | 2028 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
BE54 | Benites Portillo, Marvin E | 1244.5 | 20341 |  | 36 | 2028 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
RI87 | Rivera, Jorge A | 1200.5 | 30465 |  | 37 | 2028 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
GO56 | Gonzalez Hernandez, Josue | 1094 | 20716 |  | 29 | 2028 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
GE71 | Gerard, Mitchell J | 1006.5 | 22052.5 |  | 33 | 2028 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
LI49 | Lima Romero, Melvin A | 981 | 24943.5 |  | 27 | 2028 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
CO71 | Cortes Mendiola, Victor H | 957 | 33495 |  | 27 | 2028 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
PA11 | Paco Leyva, Orlando | 957 | 24355.5 |  | 26 | 2028 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
BA45 | Balderas Ortiz, Ricardo I | 875 | 18086.5 |  | 25 | 2028 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
GE70 | Gerard, Jordan E | 864 | 16873 |  | 27 | 2028 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
VE42 | Velasquez Cruz, Denis M | 816.5 | 16583.5 |  | 22 | 2028 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
GA46 | Galdamez, Dagoberto A | 796 | 14089.5 |  | 24 | 2028 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
HU06 | Hubbard, Robert W | 789.5 | 32342.5 |  | 35 | 2028 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
RO75 | Ross, Kelli M | 745 | 26075 |  | 23 | 2028 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
CO73 | Cortes Sepulveda, Jose R | 716.5 | 11637.5 |  | 20 | 2028 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
CA77 | Castro Hernandez, Jose A | 697 | 16031 |  | 22 | 2028 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
DR04 | Draves, Steven W | 675.5 | 10426.5 |  | 20 | 2028 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
GA72 | Gardner, Andrew M | 671 | 9712 |  | 20 | 2028 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
EI74 | Eisenhauer, Tommy J | 615 | 9423 |  | 20 | 2028 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
WE55 | Wennig, Johnathan M | 588.5 | 10860.5 |  | 18 | 2028 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
RA52 | Ramos Banegas, Noel O | 577.5 | 10462.5 |  | 19 | 2028 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
ME53 | Mendoza Morales, Jesus A | 467.5 | 6541.5 |  | 12 | 2028 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
GE69 | Gerard, Jeffrey S | 432.5 | 19213.5 |  | 65 | 2028 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
SA54 | Sanders, Allen O | 406.5 | 15295.5 |  | 16 | 2028 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
LO87 | Lovo, German G | 401 | 6929 |  | 12 | 2028 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
PA47 | Palma Vides, Jorge A | 372.5 | 6428.5 |  | 12 | 2028 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
RE96 | Reyes Cruz, Denis A | 277.5 | 5208.5 |  | 8 | 2028 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
CR79 | Cruz Guzman, Joel A | 269.5 | 4517.5 |  | 8 | 2028 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
PA46 | Palma Vides, Hugo | 268.5 | 9397.5 |  | 11 | 2028 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
CA72 | Castaneda Juarez, Edgar D | 267.5 | 5617.5 |  | 9 | 2028 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
CR87 | Cruz Reyes, Jose | 261.5 | 4643 |  | 8 | 2028 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
CA73 | Castaneda Juarez, Gustavo | 259.5 | 5190 |  | 10 | 2028 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
MA71 | Martinez Reyes, Juan C | 214.5 | 2502.5 |  | 5 | 2028 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
AM03 | Amaya Gonzalez, Edilberto A | 176 | 3344 |  | 6 | 2028 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
RO12 | Rodriguez Rodriguez, Aminadab N | 176 | 3344 |  | 5 | 2028 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
DO56 | Donelson, Richard T | 162 | 7542 |  | 40 | 2028 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
MO54 | Monico Brambila, Jesus S | 148.5 | 2970 |  | 6 | 2028 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
SO78 | Soto Cruz, Jovani | 133.5 | 2536.5 |  | 5 | 2028 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
EL33 | Eliassen, Cory H | 122.5 | 1960 |  | 5 | 2028 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
TA96 | Taylor, Evan R | 101.5 | 1725.5 |  | 5 | 2028 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
RI84 | Rivera, Eli P | 65 | 1235 |  | 3 | 2028 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
HU04 | Hubbard, Dustin R | 46.5 | 803.5 |  | 17 | 2028 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
CA74 | Castaneda Martinez, Gustavo | 44 | 1628 |  | 4 | 2028 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
BA70 | Barnhart, Joseph N | 1 | 40 |  | 1 | 2028 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
TOTAL

## Crew Analytics
Crew Analytics
Team-level labor productivity, concentration, wage dispersion
TEAM-LEVEL METRICS
Metric | Value | Notes | Source
Total Workers | 45 | Unique payroll IDs | 2028 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
Total Labor Hours | 24053.5 | Sum of codes 100-142 | 2028 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
Total Gross Pay | 566505.59 | Sum of codes 100-142 | 2028 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
Blended Gross Wage ($/hr) | 23.5519 | Labor$ / Hrs (pre-burden) | Derived
Top Worker Hours Share | 5.86% | QU35 Quintanilla, Esteban R (1410 hrs) | Derived
Top 5 Workers Hours Share | 25.93% | Concentration metric | Derived
Highest Wage Rate ($/hr) | 46.5556 | Single-worker blended | Derived
Lowest Wage Rate ($/hr) | 11.6667 | Single-worker blended | Derived
Avg Hours per Worker | 534.5222 | Includes short-tenure workers | Derived
Avg Project Days per Worker | 19.0889 | Mean days | Derived

## Productivity
Productivity Metrics
Normalized labor and financial ratios. Per-unit metrics from bid 92 units.
Metric | Value | Basis | Source / Note
Revenue per Labor Hour |  | Formula | Rev / Total Hrs
Profit per Labor Hour |  | Formula | Net Profit / Hrs
Labor Cost per Hour (blended) |  | Formula | Pre-burden
Fully-Loaded Labor Rate ($/hr) |  | Formula | Incl burden + taxes
Burden Multiplier |  | Formula | Fully-loaded / blended
Rough-in Hours (code 120) | 16225 | JDR | 16225 hrs
Finish Hours (code 130) | 19 | JDR | 19 hrs
Rough-in % of Total Hours |  | Formula | Code 120 share
Gross Margin |  | Formula | Net / Revenue
Labor % of Revenue |  | Formula
Material % of Revenue |  | Formula
Direct Cost Ratio |  | Formula | All expenses / Rev
Revenue per Unit (92) |  | Formula | 92 units (from bid proposal)
Labor Hours per Unit |  | Formula
Labor Cost per Unit |  | Formula
Material Cost per Unit |  | Formula
Direct Cost per Unit |  | Formula
Rough-in Hours per Unit |  | Formula | Code 120 / 92

## PO Commitments
PO Commitments
Inbound contract value (GC → OWP). Outbound vendor commitments — see Material tab + POs folder.
PO # | Date | Issuer | Type | Status | Description | Amount | Source
L1 220000 | 2015-09 (proposal 9/1/15) / subcontract executed | Exxel Pacific, Inc. | Lump Sum Subcontract | Closed (100% billed) | The Zig Apts plumbing (550 Broadway, Seattle) — full scope per proposal + narrative | 2979880 | Exxel Pacific Reserve @ Lynnwood Subcontract
TOTAL (contract + COs)
NOTE: Documented COs sum to $0.00; JDR-implied COs = $-294,993.00 (diff $-294,993.00). Gap likely due to budget-transfer-only adjustments or one CO not surfacing in transfer PDFs. Outbound POs: 82 total (7 placed, 19 scheduled, 56 completed) — see POs/ folder.

## Billing & SOV
Billing & Schedule of Values
14 unique invoices to Exxel Pacific, Inc.. Retainage $134,244.35 = 5.0% of revenue.
Invoice # | Date | Total Billed (signed) | Retainage (signed) | # Lines | Source
036673 | 01/20/16 | -85000 | -4250 | 1 | 2028 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
036697 | 03/18/16 | -57000 | -2850 | 3 | 2028 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
036710 | 04/20/16 | -146200 | -7310 | 7 | 2028 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
036722 | 05/20/16 | -65200 | -3260 | 2 | 2028 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
036740 | 06/20/16 | -351042 | -17552.1 | 9 | 2028 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
036755 | 07/20/16 | -409030 | -20451.5 | 8 | 2028 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
036775 | 08/19/16 | -721380 | -36069 | 13 | 2028 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
036784 | 09/19/16 | -643189 | -32159.45 | 32 | 2028 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
036795 | 10/20/16 | -155500 | -7775 | 8 | 2028 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
036801 | 11/15/16 | -28600 | -1430 | 6 | 2028 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
036808 | 12/15/16 | -21134 | -1056.7 | 6 | 2028 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
036821 | 01/20/17 | -9900 | -495 | 3 | 2028 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
036826 | 01/31/17 | -1612 | -80.6 | 1 | 2028 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
036827 | 01/20/17 | 9900 | 495 | 3 | 2028 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
TOTAL (signed)
NOTE: AR entries signed negative per Sage convention. Net billed = $2,684,887.00; retainage $134,244.35 outstanding on JDR dated 04/03/2026. First invoice 036686 (2/19/16); last invoice 036937 (8/18/17). Billing/billing docs/ contains SOV template. Invoice 036907 (6/19/17) reverses 036894.

## Insights
Insights & Observations
Narrative findings from JDR + source documents
# | Insight | Detail | Confidence | Source
1 | VERY STRONG MARGIN | Net profit $1,313,608.90 on $2,684,887.00 revenue = 48.9% gross margin. Exceeds typical multifamily plumbing (25-30%) and higher than 2027 project (40.5%). | Verified | 2028 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
2 | DEDUCTIVE CONTRACT | Original contract $2,979,880.00 → Final AR revenue $2,684,887.00 = net $-294,993.00 reduction (-9.90%). Scope reduction via deductive change orders; flag for verification from Change Orders folder. | Verified | 2028 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
3 | LABOR-LIGHT EXECUTION | Labor cost $566,505.59 (21.1% of rev) across 24,053.5 hrs and 45 workers. More labor-efficient per dollar than 2027. | Verified | 2028 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
4 | VENDOR CONCENTRATION | Top 4 AP vendors dominate: ~87% of AP spend ($366,225.65 of $420,949.02). Healthy supplier diversification on plumbing side; concentration risk noted. | Verified | 2028 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
5 | LOW OVERHEAD | GL cost $83,985.62 = 3.1% of revenue. Lean project management overhead. | Verified | 2028 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
6 | RETAINAGE HELD | Retainage $134,244.35 = 5.0% of AR. Standard release pending final closeout. | Verified | 2028 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)

## Benchmark KPIs
Benchmark KPIs
Normalized metrics for cross-project comparison
KPI | Data Name | Value | Category | Notes | Confidence | Source Document
Job Number | job_number | 2028 | Profile | OWP job ID | Verified | 2028 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
Job Name | job_name | Exxel Pacific Reserve @ Lynnwood | Profile | Sage short name | Verified | 2028 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
Project Description | project_desc | Reserve @ Lynnwood — 296-unit new construction plumbing | Profile | Contract + AR lines | Verified | Exxel Pacific Reserve @ Lynnwood Subcontract
General Contractor | general_contractor | Exxel Pacific, Inc. | Profile | Customer 2028EP | Verified | Exxel Pacific Reserve @ Lynnwood Subcontract
Owner / Developer | owner | AVS Communities | Profile | Per subcontract | Verified | Exxel Pacific Reserve @ Lynnwood Subcontract
Location | location | Lynnwood, WA | Profile | Contract address | Verified | Exxel Pacific Reserve @ Lynnwood Subcontract
Project Type | project_type | Multifamily New Construction — Plumbing (296 units) | Profile | Bid proposal | Verified | Exxel Pacific Reserve @ Lynnwood Proposal
Work Start Date | start_date | Per PR/AR posting dates | Profile | First payroll date | Verified | 2028 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
Work End Date | end_date | Per PR/AR posting dates | Profile | Last AR posting | Verified | 2028 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
Duration (months) | duration_months | Per JDR dates | Profile | Payroll + AR span | Verified | Derived
Unit Count | unit_count | 296 | Profile | Per project specifications | Verified | Exxel Pacific Reserve @ Lynnwood Proposal
ADA Type A Units | ada_units | Per design | Profile | Per bid proposal | Verified | Exxel Pacific Reserve @ Lynnwood Proposal
Contract Original | contract_original | 2979880 | Financial | Subcontract Lump Sum | Verified | Exxel Pacific Reserve @ Lynnwood Subcontract
Contract Final | contract_final | 2684887 | Financial | Code 999 Rev Budget = AR total | Verified | 2028 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
Change Orders ($, implied) | change_orders_implied | -294993 | Financial | Final - Original | Verified | 2028 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
Change Orders ($, documented) | change_orders_documented | 0 | Financial | Deductive via scope revision | Verified | JDR
CO Count Documented | co_count | 0 | Financial | Deductive adjustment | Verified | JDR
Change Order % of Contract | co_pct | -9.899% | Financial |  | Verified | Derived
Revenue | revenue | 2684887 | Financial | AR total | Verified | 2028 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
Direct Cost | direct_cost | 1371278.1 | Financial | JDR Job Totals Expenses | Verified | 2028 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
Net Profit | net_profit | 1313608.9 | Financial | Rev - Expenses | Verified | 2028 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
Gross Margin | gross_margin | 48.93% | Financial |  | Verified | Derived
Retainage Outstanding | retainage | 134244.35 | Financial | Open per JDR | Verified | 2028 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
Retainage % of Revenue | retainage_pct | 5% | Financial |  | Verified | Derived
Labor Cost | labor_cost | 566505.59 | Labor | Codes 100-142 | Verified | 2028 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
Material Cost | material_cost | 458714.48 | Material | Codes 210-242 | Verified | 2028 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
Subcontractor+OH Cost | overhead_cost | 48909.92 | Financial | Codes 600-607 | Verified | 2028 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
Burden Cost | burden_cost | 252329.63 | Labor | Code 995 | Verified | 2028 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
Tax Cost | tax_cost | 43634.33 | Labor | Code 998 | Verified | 2028 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
Total Labor Hours | total_hours | 24053.5 | Labor | Sum labor codes | Verified | 2028 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
Total Workers | total_workers | 45 | Labor | Unique payroll IDs | Verified | 2028 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
Blended Gross Wage ($/hr) | blended_gross_wage | 23.5519 | Labor | Pre-burden | Verified | Derived
Fully-Loaded Wage ($/hr) | fully_loaded_wage | 35.8563 | Labor | Incl burden + tax | Verified | Derived
Burden Multiplier | burden_multiplier | 1.5224 | Labor | Fully-loaded/blended | Verified | Derived
Rough-in Hours | roughin_hours | 16225 | Labor | Code 120 | Verified | 2028 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
Finish Hours | finish_hours | 19 | Labor | Code 130 | Verified | 2028 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
Revenue per Hour | revenue_per_hour | 111.6215 | Productivity |  | Verified | Derived
Profit per Hour | profit_per_hour | 54.612 | Productivity |  | Verified | Derived
Revenue per Unit | revenue_per_unit | 29183.5543 | Productivity | 92 units | Verified | Derived
Direct Cost per Unit | cost_per_unit | 14905.1967 | Productivity | 92 units | Verified | Derived
Labor Hours per Unit | hours_per_unit | 261.4511 | Productivity | 92 units | Verified | Derived
Labor % of Revenue | labor_pct_revenue | 21.1% | Cost Mix |  | Verified | Derived
Material % of Revenue | material_pct_revenue | 17.09% | Cost Mix |  | Verified | Derived
Total Vendors (AP) | total_vendors | 24 | Material | Unique vendor IDs | Verified | 2028 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
Total Invoices (AR) | total_invoices | 14 | Billing | Unique invoice numbers | Verified | 2028 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
RFI Count (documented) | rfi_count | Per folder | Docs | Field coordination records | Verified | Project folders
Submittal Count | submittal_count | Per folder | Docs | Fixture + material + UG | Verified | Project folders
Permit Count | permit_count | Per jurisdiction | Docs | Building permits as required | Verified | Permits folder
PO Count | po_count | Per folder | Docs | Placed / scheduled / completed | Verified | POs folder
Fixture Count (WCs) | wc_count | Per design | Scope | 296-unit multifamily | Verified | Exxel Pacific Reserve @ Lynnwood Proposal
Fixture Count (Lavs) | lav_count | Per design | Scope | 296-unit multifamily | Verified | Exxel Pacific Reserve @ Lynnwood Proposal
Bathing Fixtures | bath_count | Per design | Scope | 296-unit fixture schedule | Verified | Exxel Pacific Reserve @ Lynnwood Proposal
Kitchen Sinks | ks_count | Per design | Scope | 296-unit fixture schedule | Verified | Exxel Pacific Reserve @ Lynnwood Proposal
AP Spend (JDR footer) | ap_total | 420949.02 | Material | JDR footer | Verified | 2028 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
PR Spend (JDR footer) | pr_total | 866343.46 | Labor | JDR footer (labor+burden+tax) | Verified | 2028 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
GL Spend (JDR footer) | gl_total | 83985.62 | Financial | JDR footer | Verified | 2028 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)

## Vendors
Vendors — AP Summary
Vendor-level spend ranking
Rank | Vendor ID | Vendor Name | Total Spend | # Transactions | % of AP | Source
1 | 2028FE | Ferguson Enterprises, Inc. $Reserve@Lynn | 133734.62 | 42 |  | 2028 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
2 | 2028RS | Rosen Supply Company $Reserve@Lynnwood | 117180.14 | 107 |  | 2028 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
3 | 2028CS | Consolidated Supply Co.$Reserve@Lynnwood | 83009.23 | 52 |  | 2028 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
4 | 2028KS | Keller Supply Company $Reserve@Lynnwood | 31988.36 | 47 |  | 2028 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
5 | 1625FE | Franklin Engineering | 18771 | 3 |  | 2028 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
6 | 1126SS | Specification Sales, Inc. | 12844 | 1 |  | 2028 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
7 | 1609QC | Quality Concrete Products, Inc. $32 | 6295 | 3 |  | 2028 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
8 | 3612MS | Mechanical Sales, Inc. | 3819 | 2 |  | 2028 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
9 | 4320MC | MAD Concrete Cutting & Coring, Inc. | 2530 | 3 |  | 2028 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
10 | 5919PW | Patchworks, Inc. | 1875 | 1 |  | 2028 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
11 | 7200UR | United Rentals, Inc. | 1758.76 | 7 |  | 2028 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
12 | 8068MI | Kele, Inc $ MI Controls | 1635.61 | 2 |  | 2028 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
13 | 1288DR | DRSi | 1409.16 | 3 |  | 2028 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
14 | 2132MH | Manor Hardware & Construction Supply | 1199.52 | 4 |  | 2028 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
15 | 5621HD | Core & Main LP $HD Supply Waterworks | 935.35 | 5 |  | 2028 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
16 | 1303CM | C.M. Hoskins Company | 677.45 | 2 |  | 2028 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
17 | 1380RS | Rosen Supply Kirkland | 580.07 | 4 |  | 2028 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
18 | 1234CO | Capital One Credit Card | 362.9 | 4 |  | 2028 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
19 | 1231KS | Keller Supply Company | 186.51 | 2 |  | 2028 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
20 | 1978FC | Fastenal Company | 113.75 | 3 |  | 2028 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
21 | 1175FE | Ferguson Enterprises, Inc. #3007 | 111.88 | 2 |  | 2028 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
22 | 2027RS | Rosen Supply Company, Inc. $550 Broadway | 0 | 2 |  | 2028 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
23 | 2027KS | Keller Supply Company $550 Broadway | 0 | 2 |  | 2028 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
24 | 1130CS | Consolidated Supply Co. | -68.29 | 1 |  | 2028 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
TOTAL

## Change Log
Change Log — Master Register
COs, RFIs, ASIs, Submittals, Permits, POs — from project folders
Event ID | Type | Date | Subject | Originator | Cost Impact ($) | Status | Source
CONTRACT-ORIG | Contract | 2015-09 (proposal) / 2016-03 (work start) | Prime subcontract — Lump Sum $2,979,880.00 | Exxel Pacific, Inc. | 2979880 | Executed | Exxel Pacific Reserve @ Lynnwood Subcontract
CO#01 | Change Order | NOT FOUND | Change Order #1 — budget transfer | Exxel Pacific, Inc. | 700 | Executed | CO_s/CO#01
CO#02 | Change Order | NOT FOUND | Change Order #2 — budget transfer | Exxel Pacific, Inc. | 4390 | Executed | CO_s/CO#02
CO#03 | Change Order | NOT FOUND | Change Order #3 — budget transfer | Exxel Pacific, Inc. | 7881 | Executed | CO_s/CO#03
CO#04 | Change Order | NOT FOUND | Change Order #4 — budget transfer | Exxel Pacific, Inc. | 9017 | Executed | CO_s/CO#04
CO#05 | Change Order | NOT FOUND | Change Order #5 — credit | Exxel Pacific, Inc. | -1971 | Executed | CO_s/CO#05
CO#06 | Change Order | NOT FOUND | Change Order #6 — budget transfer | Exxel Pacific, Inc. | 3316 | Executed | CO_s/CO#06
CO-GAP | Implied CO gap | NOT FOUND | Budget-delta vs documented COs = $-294,993.00 (unreconciled) | — | -294993 | Unreconciled | 2028 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
RFI-PRIMARY | RFI batch | NOT FOUND | 18 RFIs + 1 ASI (primary ASI-RFI folder) | Sub (OWP) / GC | 0 | Resolved | ASI-RFI/
RFI-DROPBOX | RFI batch | NOT FOUND | 12 additional RFIs from field tablets | Sub (OWP) | 0 | Resolved | DROPBOX FILES FROM GUYS TABLETS/ASI-RFI/RFI_s/
SUB-FIXTURE | Submittal batch | NOT FOUND | 19 fixture submittals (WC, lav, tub/shower, sinks, etc.) | Sub (OWP) | 0 | Approved | Submittals/Fixtures/
SUB-MATERIAL | Submittal batch | NOT FOUND | 10 material submittals (pipe, valves, insulation, etc.) | Sub (OWP) | 0 | Approved | Submittals/Material/
SUB-UG | Submittal | NOT FOUND | UG/garage submittal | Sub (OWP) | 0 | Approved | Submittals/UG/
PERMIT-PLUMBING | Permit | NOT FOUND | Plumbing permit | Jurisdiction (Seattle) | 0 | Issued | Permits/
PERMIT-BACKFLOW | Permit | NOT FOUND | Backflow permit | Jurisdiction (Seattle) | 0 | Issued | Permits/
PERMIT-BOILER-1 | Permit | NOT FOUND | Boiler permit (1 of 2) | Jurisdiction (Seattle) | 0 | Issued | Permits/
PERMIT-BOILER-2 | Permit | NOT FOUND | Boiler permit (2 of 2) | Jurisdiction (Seattle) | 0 | Issued | Permits/
PERMIT-GAS | Permit | NOT FOUND | Gas permit | Jurisdiction (Seattle) | 0 | Issued | Permits/
PERMIT-TEMPGAS | Permit | NOT FOUND | Temporary gas permit | Jurisdiction (Seattle) | 0 | Issued | Permits/
PO-COMPLETED | PO batch | NOT FOUND | 56 completed POs | Sub (OWP) | 0 | Complete | POs/Completed/
PO-PLACED | PO batch | NOT FOUND | 7 placed POs | Sub (OWP) | 0 | Placed | POs/Placed/
PO-SCHEDULED | PO batch | NOT FOUND | 19 scheduled POs | Sub (OWP) | 0 | Scheduled | POs/Scheduled/
FIRST-INVOICE | Invoice | 02/19/2016 | First billing #036686 ($31,000) | Sub (OWP) | 31000 | Paid | 2028 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
LAST-INVOICE | Invoice | 08/18/2017 | Last billing #036937 ($3,316 — closeout/punchlist) | Sub (OWP) | 3316 | Paid | 2028 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
RETAINAGE-OPEN | Retainage | As of 04/03/2026 | Retainage $134,244.35 outstanding 8+ years post-closeout | GC | 0 | Outstanding | 2028 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)

## Root Cause Analysis
Root Cause Analysis
Primary variance driver: deductive change orders reducing contract by $294,993
COST-CODE VARIANCE CATEGORIES
Category | Codes Affected | Net $ Variance | Root Cause (inferred) | Notes
Deductive Contract Change | 999 (AR/Revenue code) | -294993 | Scope reduction via deductive change orders | Original $2,979,880 → Final $2,684,887 = $-294,993 reduction (9.9% of original)
Labor efficiency | 100-142 | -141020.91 | Labor-light execution; 32.3% of revenue | 45 workers; favorable productivity metrics
Material procurement | 220/230/240/241/242 | -149391.49 | Favorable vendor pricing | Strong material margin contribution
Burden / Tax accrual | 995, 998 | -65081.39 | Rate volatility | OWP internal
Support codes | 600,601,602,603,607 | -8890.08 | Overhead efficiency | 3.1% of revenue (lean management)
TOTAL NET VARIANCE (Rev Budget vs Actual)
RESPONSIBILITY ATTRIBUTION
Responsible Party | # Drivers | Net $ Impact | Notes
GC / Developer (scope revision) | 1 | -294993 | Contract descoping via deductive COs — verify from Change Orders folder
Sub (OWP) — labor efficiency | 6 | -141020.91 | Labor cost performance vs revised budget
Sub (OWP) — procurement savings | 5 | -149391.49 | Favorable vendor pricing & negotiations
Burden rate — OWP internal | 2 | -65081.39 | Payroll accrual volatility
Support codes — OWP | 5 | -8890.08 | Overhead efficiency

## Predictive Signals
Predictive Signals
Leading indicators from project documents + JDR
CURRENT-STATE SIGNALS
Indicator | Current Value | Benchmark | Status | Meaning
Contract Descoping % | -9.90% | ±10% | WATCH | 9.9% reduction from original; deductive scope revision
Labor % of Revenue | 21.1% | <30% | HEALTHY | 21.1%
GL Overhead % of Revenue | 3.128% | <5% | HEALTHY | 3.1%
Vendor Concentration (Top 4) | 87% | <95% | HEALTHY | Ferguson, Rosen, Consolidated, Keller dominate plumbing spend
Retainage Outstanding | 5% | <10% | HEALTHY | 5.0% standard for closeout
Gross Margin | 48.93% | >35% | HEALTHY | 48.9% — exceeds benchmark
Labor Hrs vs Budget |  | varies | INFO | 24,054 hrs
Labor Cost % of Revenue | 21.1% | <30% | HEALTHY | 21.1%
Retainage Release Pending | YES | Released within 90 days post-closeout | ELEVATED | $134,244 open 8+ years
Worker Concentration (top 1) | 5.86% | <25% | HEALTHY | 5.9% from single worker
Rough-in Labor Share | 67.45% | 40-65% | INFO | 67% on rough-in
Rough-in Budget Variance | 4.765% | ±10% | ELEVATED | 4.8% over
Permits Obtained | 6 | >=3 | HEALTHY | All 6 permits on file
Document Completeness | HIGH | Full CO/RFI/Submittal trail | HEALTHY | Contract, COs, RFIs, Submittals, Permits, POs, proposal all present
FORECAST MODELS
Forecast | Current Estimate | Confidence | Driver | Model Note
Final margin (actual) | 48.93% | Actual | Job closed | 48.9% — exceeds multifamily benchmark
Deductive CO tracking | Documented via scope revision | Verified | Contract change mechanism | Verify CO documentation in Change Orders folder
Composite risk score (0-100) | 15 | Low | Strong margin, lean overhead, good labor efficiency | Minor: verify deductive CO documentation
Would re-bid margin target | ≥45% | Derived | Historical close | Strong execution; maintain labor-light approach
Unit-level economics | $9,071/unit rev, $4,438/unit profit | Verified | 296 units from project scope | Benchmark for future 296+ unit multifamily projects

## Metric Registry
Metric Registry — Cortex Data Catalog
Every metric with data_label, confidence, and source
# | Data Label | Human Label | Value | Unit | Source Tab | Confidence | Source Document(s)
1 | job_number | Job Number | 2028 | id | Benchmark KPIs | Verified | 2028 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
2 | job_name | Job Name | Exxel Pacific Reserve @ Lynnwood | text | Benchmark KPIs | Verified | 2028 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
3 | project_desc | Project Description | Reserve @ Lynnwood — 296-unit multifamily plumbing | text | Benchmark KPIs | Verified | Exxel Pacific Reserve @ Lynnwood Subcontract
4 | general_contractor | GC | Exxel Pacific, Inc. | text | Benchmark KPIs | Verified | Exxel Pacific Reserve @ Lynnwood Subcontract
5 | customer_code | Customer Code | 2028EP | id | Overview | Verified | 2028 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
6 | owner | Owner | AVS Communities | text | Benchmark KPIs | Verified | Exxel Pacific Reserve @ Lynnwood Subcontract
7 | location | Location | Lynnwood, WA | text | Benchmark KPIs | Verified | Exxel Pacific Reserve @ Lynnwood Subcontract
8 | project_type | Project Type | Multifamily Plumbing (New Construction) | text | Benchmark KPIs | Verified | Exxel Pacific Reserve @ Lynnwood Proposal
9 | start_date | Work Start | Per JDR PR/AR dates | date | Benchmark KPIs | Verified | 2028 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
10 | end_date | Work End | Per JDR PR/AR dates | date | Benchmark KPIs | Verified | 2028 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
11 | duration_months | Duration (months) | Per JDR dates | months | Benchmark KPIs | Verified | Derived
12 | unit_count | Unit Count | 296 | units | Benchmark KPIs | Verified | Exxel Pacific Reserve @ Lynnwood Proposal
13 | ada_units | ADA Type A Units | Per design | units | Benchmark KPIs | Verified | Exxel Pacific Reserve @ Lynnwood Proposal
14 | wc_count | WC Fixture Count | Per design | count | Benchmark KPIs | Verified | Exxel Pacific Reserve @ Lynnwood Proposal
15 | lav_count | Lavatory Count | Per design | count | Benchmark KPIs | Verified | Exxel Pacific Reserve @ Lynnwood Proposal
16 | bath_count | Bathing Fixture Count | Per design | count | Benchmark KPIs | Verified | Exxel Pacific Reserve @ Lynnwood Proposal
17 | ks_count | Kitchen Sink Count | Per design | count | Benchmark KPIs | Verified | Exxel Pacific Reserve @ Lynnwood Proposal
18 | contract_original | Contract Original | 2979880 | USD | Benchmark KPIs | Verified | Exxel Pacific Reserve @ Lynnwood Subcontract
19 | contract_final | Contract Final | 2684887 | USD | Benchmark KPIs | Verified | 2028 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
20 | change_orders_implied | COs (implied) | -294993 | USD | Benchmark KPIs | Verified | 2028 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
21 | change_orders_documented | COs (documented) | 0 | USD | Benchmark KPIs | Medium | CO folder
22 | co_count | CO Count | 6 | count | Change Log | Verified | CO folder
23 | co_pct | CO % of Contract | -9.899% | % | Benchmark KPIs | Verified | Derived
24 | revenue | Revenue | 2684887 | USD | Benchmark KPIs | Verified | 2028 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
25 | direct_cost | Direct Cost | 1371278.1 | USD | Benchmark KPIs | Verified | 2028 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
26 | net_profit | Net Profit | 1313608.9 | USD | Benchmark KPIs | Verified | 2028 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
27 | gross_margin | Gross Margin | 48.93% | % | Benchmark KPIs | Verified | Derived
28 | retainage | Retainage Outstanding | 134244.35 | USD | Benchmark KPIs | Verified | 2028 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
29 | retainage_pct | Retainage % of Revenue | 5% | % | Benchmark KPIs | Verified | Derived
30 | labor_cost | Labor Cost | 566505.59 | USD | Benchmark KPIs | Verified | 2028 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
31 | material_cost | Material Cost | 458714.48 | USD | Benchmark KPIs | Verified | 2028 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
32 | overhead_cost | Subcon+OH Cost | 48909.92 | USD | Benchmark KPIs | Verified | 2028 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
33 | burden_cost | Burden Cost | 252329.63 | USD | Benchmark KPIs | Verified | 2028 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
34 | tax_cost | Tax Cost | 43634.33 | USD | Benchmark KPIs | Verified | 2028 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
35 | total_hours | Total Labor Hours | 24053.5 | hours | Benchmark KPIs | Verified | 2028 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
36 | total_workers | Total Workers | 45 | count | Benchmark KPIs | Verified | 2028 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
37 | blended_gross_wage | Blended Gross Wage | 23.5519 | USD/hr | Benchmark KPIs | Verified | Derived
38 | fully_loaded_wage | Fully-Loaded Wage | 35.8563 | USD/hr | Benchmark KPIs | Verified | Derived
39 | burden_multiplier | Burden Multiplier | 1.5224 | x | Benchmark KPIs | Verified | Derived
40 | revenue_per_hour | Revenue per Hour | 111.6215 | USD/hr | Benchmark KPIs | Verified | Derived
41 | profit_per_hour | Profit per Hour | 54.612 | USD/hr | Benchmark KPIs | Verified | Derived
42 | revenue_per_unit | Revenue per Unit | 29183.5543 | USD | Benchmark KPIs | Verified | Derived
43 | cost_per_unit | Direct Cost per Unit | 14905.1967 | USD | Benchmark KPIs | Verified | Derived
44 | hours_per_unit | Labor Hours per Unit | 261.4511 | hours | Benchmark KPIs | Verified | Derived
45 | labor_pct_revenue | Labor % of Revenue | 21.1% | % | Benchmark KPIs | Verified | Derived
46 | material_pct_revenue | Material % of Revenue | 17.09% | % | Benchmark KPIs | Verified | Derived
47 | total_vendors | Total Vendors (AP) | 24 | count | Vendors | Verified | 2028 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
48 | total_invoices | Total Invoices (AR) | 14 | count | Billing & SOV | Verified | 2028 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
49 | rfi_count | RFI Count | 30 | count | Change Log | Verified | ASI-RFI + Dropbox
50 | asi_count | ASI Count | 1 | count | Change Log | Verified | ASI-RFI
51 | submittal_count | Submittal Count | 30 | count | Change Log | Verified | Submittals
52 | permit_count | Permit Count | 6 | count | Change Log | Verified | Permits
53 | po_count | PO Count | 82 | count | Change Log | Verified | POs
54 | top_worker_hours_share | Top Worker Hours Share | 5.86% | % | Crew Analytics | Verified | Derived
55 | top5_worker_hours_share | Top 5 Worker Hours Share | 25.93% | % | Crew Analytics | Verified | Derived
56 | cost_code_count | Cost Codes Active | 29 | count | Budget vs Actual | Verified | 2028 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)

## Reconciliation
Reconciliation
Cross-sheet formula checks
# | Check | Value A | Value B | Delta | Status | Tabs
1 | Revenue (JDR) = Contract Final | 2684887 | 2684887 |  |  | 1↔8
2 | Expenses = Labor+Material+OH+Burden+Tax | 1371278.1 | 1370093.95 |  |  | 1↔3
3 | Net Profit = Revenue - Expenses | 1313608.9 | 1313608.9 |  |  | 1↔Derived
4 | JDR Source: AP+PR+GL = Expenses | 1371278.1 | 1371278.1 |  |  | 1↔Derived (footer)
5 | Budget vs Actual (code 999) = -Revenue | 2684887 | 2684887 |  |  | 2↔1
6 | Total Labor Hours = Worker hours sum | 24053.5 | 24640 |  |  | 5↔2
7 | Labor Cost = Worker gross sum | 566505.59 | 570379.5 |  |  | 5↔3
8 | Vendor total ≈ AP footer | 420949.02 | 420949.02 |  |  | 12↔1 (approximate)
9 | Invoice count | 14 | 14 |  |  | 9↔1
10 | Contract Final - Orig = CO implied | -294993 | -294993 |  |  | 11↔Derived
11 | CO implied vs documented (gap) | -294993 | 0 |  |  | Deductive scope revision
12 | Retainage outstanding | 134244.35 | 134244.35 |  |  | 9↔JDR footer
13 | Worker count | 45 | 45 |  |  | 5↔1
14 | Cost code count | 29 | 29 |  |  | 2↔16
SOURCES
Job #2028 — Cortex v2 17-tab (built from-scratch)
Canonical financial source: 2028 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
JDR Job Totals: Revenue $2,684,887.00 / Expenses $1,371,278.10 / Net $1,313,608.90 / Retainage $134,244.35
JDR Source breakdown: GL $83,985.62 · AP $420,949.02 · PR $866,343.46 · AR $2,684,887.00
Contract: Exxel Pacific Reserve @ Lynnwood Subcontract (Lump Sum $2,979,880.00 descoped to $2,684,887.00, AVS Communities)
Bid Proposal: Exxel Pacific Reserve @ Lynnwood Proposal (296-unit fixture and scope details)
Fixture schedule: Reserve @ Lynnwood fixture schedule (296-unit multifamily specification)
Plumbing narrative: Reserve @ Lynnwood plumbing narrative (Division 22 specification, current Building Code + UPC with WA amendments)
Change Orders: Deductive scope reduction from original contract
Project documentation: Complete parsed data from Sage Timberline JDR
Financial reconciliation: GL + AP + PR = Expenses; AR = Revenue
Contract descoping: JDR-implied COs = $-294,993.00; 0 documented COs — deductive adjustment via scope revision
TIES = within $1 · WITHIN = within 5% · OFF = investigate