## Overview
Job #2029 · Exxel Pacific Parsonage
Cortex JCR Cortex v2 • Exxel Pacific, Inc. (customer 2029EP) • Parsonage, WA • Owner: Exxel Pacific (self-performed developer)
PROJECT OVERVIEW
Project Job # | 2029 |  | 2029 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages) header
Project Name (Sage) | Exxel Pacific Parsonage |  | 2029 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages) header
Project Description | Parsonage — 296-unit new construction plumbing |  | Exxel Pacific Parsonage Subcontract / AR line descriptions
General Contractor | Exxel Pacific, Inc. |  | Exxel Pacific Parsonage Subcontract
Customer Code (Sage) | 2029EP |  | 2029 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
Owner / Developer | Exxel Pacific (self-performed developer) |  | Exxel Pacific Parsonage Subcontract
Jobsite Location | Parsonage, WA |  | Exxel Pacific Parsonage Subcontract
Contract / PO Document | Exxel Pacific Parsonage Subcontract |  | Lump Sum subcontract
Plans / Specifications | Parsonage plumbing narrative (Div 22 plumbing narrative) + fixture schedule + proposal |  | Folder scan
Fixture Schedule | Parsonage fixture schedule (fixture schedule for 296-unit multifamily) |  | Referenced
Bid Proposal | Exxel Pacific Parsonage Proposal |  | Detailed scope and fixture quantities
Contract Type | Lump Sum |  | Exxel Pacific Parsonage Subcontract
Work Period | Per PR/AR posting dates in JDR |  | 2029 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
Total Unique Documents Reviewed | 1924 |  | File inventory across owp-2029/
CONTRACT VALUE |  | NET PROFIT | DIRECT COST | LABOR HOURS
1123747 |  | 560158.01 | 563588.99 | 7596
Original $1,113,220.00 + $10,527.00 COs (0.95%) |  | 49.8% margin | 50.2% of revenue | 21 workers
SCOPE OF WORK (from contract + proposal)
Full plumbing installation: underground, rough-in, finish, gas piping, water mains, insulation, mechanical room, and warranty.
296-unit multifamily new construction at Parsonage, WA.
5 levels above ground, 1 level below grade (per Job Info).
Comprehensive fixture schedule with standard and ADA-compliant units.
Spec compliance: Current Building Code + UPC with Washington state amendments.
SOURCES
Canonical financial source: 2029 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
Job totals (JDR footer): Revenue $1,123,747.00 / Expenses $563,588.99 / Net $560,158.01 / Retainage $56,289.55
Source breakdown: GL $34,886.41 · AP $243,624.11 · PR $188,045.50 · AR $1,123,747.00
Contract: Exxel Pacific Parsonage Subcontract (Lump Sum $1,113,220.00, descoped to $1,123,747.00)
Proposal: Exxel Pacific Parsonage Proposal
Fixture schedule: Parsonage fixture schedule
Plumbing narrative: Parsonage plumbing narrative
Change Orders: Deductive scope changes; net contract reduction ${CO_TOTAL_IMPLIED:,.2f}
PROJECT TEAM (OWP Job Info)
Role | Status | Name / Firm
GC | Extracted | Exxel Pacific, Inc.
GC PM | Extracted | Brett / Franklin (per project subfolders)
GC Superintendent | N/A | N/A
GC PE | N/A | N/A
Developer | Extracted | Exxel Pacific (self-performed)
Architect | N/A | N/A
Structural | N/A | N/A
Acoustical | N/A | N/A
ADA Consultant | N/A | N/A
Interior Design | N/A | N/A
MEP Engineer | Extracted | Franklin Engineering

## Budget vs Actual
Budget vs Actual
All 27 cost codes from JDR. Contract $1,113,220 → $1,123,747 (COs +$10,527.00).
Cost Code | Description | Original Budget | Revised Budget | Actual | Variance | % of Revised | Hours | Source
100 | Supervision | 8700 | 8747 | 3269.5 |  |  | 71.5 | 2029 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
101 | Takeoff & Purchase Labor | 13700 | 13896 | 9512.5 |  |  | 203.5 | 2029 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
110 | Underground Labor | 11700 | 12114.5 | 12604 |  |  | 450 | 2029 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
111 | Garage Labor | 0 | 0 | 848 |  |  | 34 | 2029 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
112 | Canout Labor | 6800 | 6800 | 5435 |  |  | 188 | 2029 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
120 | Roughin Labor | 148500 | 149251 | 103433 |  |  | 4553.5 | 2029 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
130 | Finish Labor | 26200 | 26808 | 25915.5 |  |  | 979 | 2029 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
140 | Gas Labor | 2400 | 2856 | 2133 |  |  | 90.5 | 2029 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
141 | Water Main/Insulation Lab | 28200 | 28756 | 12249 |  |  | 553 | 2029 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
142 | Mech Room Labor | 11400 | 11400 | 12326 |  |  | 465 | 2029 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
150 | Warranty Labor | 0 | 0 | 320 |  |  | 8 | 2029 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
210 | Underground Material | 13900 | 14089 | 10418.9 |  |  |  | 2029 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
211 | Garage Material | 0 | 0 | 467.8 |  |  |  | 2029 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
212 | Canout Material | 7500 | 7500 | 6161.22 |  |  |  | 2029 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
220 | Roughin Material | 79600 | 80398 | 63196.04 |  |  |  | 2029 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
230 | Finish Material | 94600 | 95549.5 | 82322 |  |  |  | 2029 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
240 | Gas Material | 2400 | 2987 | 1057.3 |  |  |  | 2029 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
241 | Water Main/Insulation Mat | 40200 | 40200 | 26177.22 |  |  |  | 2029 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
242 | Mech Room Material | 68600 | 69326 | 53061.22 |  |  |  | 2029 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
243 | Condensation Drains Mat | 0 | 0 | 13.2 |  |  |  | 2029 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
600 | Subcontractor | 2500 | 2744.5 | 1566 |  |  |  | 2029 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
601 | Engineering/Plans | 22000 | 22000 | 20121 |  |  |  | 2029 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
603 | Permits & Licenses | 5600 | 5740 | 4247 |  |  |  | 2029 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
607 | Other Expenses | 14500 | 14500 | 8952.41 |  |  |  | 2029 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
995 | Payroll Burden | 117128.35 | 118491.17 | 83396.48 |  |  |  | 2029 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
998 | Payroll Taxes | 20203.65 | 20435.34 | 14385.7 |  |  |  | 2029 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
999 | Sales | -1113220 | -1123747 | -1123747 |  |  |  | 2029 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
TOTAL

## Cost Breakdown
Cost Breakdown by Category
Direct cost composition by category from JDR cost codes
Category | Cost Codes | Actual $ | % of Direct Cost | % of Revenue | Source
Labor | 100,101,110,111,112,120,130,140,141,142,150 | 188045.5 |  |  | 2029 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
Material | 210,211,212,220,230,240,241,242,243 | 242874.9 |  |  | 2029 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
Subcontractor + Engineering + Permits + Other | 600,601,603,607 | 34886.41 |  |  | 2029 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
Payroll Burden | 995 | 83396.48 |  |  | 2029 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
Payroll Taxes | 998 | 14385.7 |  |  | 2029 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
TOTAL DIRECT COST |  |  | 100%

## Material
Material Purchases — AP Vendors
Material + subcontractor spend by vendor (AP records from JDR). Supplemented with submittal/PO inventory.
Vendor ID | Vendor Name | Total Spend | # Transactions | Category (inferred) | Source
2029KS | Keller Supply Company $Parsonage | 96387.89 | 77 | Plumbing / Supplies | 2029 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
2029RS | Rosen Supply Company, Inc. $Parsonage | 70473.25 | 51 | Plumbing / Supplies | 2029 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
2029CS | Consolidated Supply Co. $Parsonage | 24212.57 | 20 | Plumbing / Supplies | 2029 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
1625FE | Franklin Engineering | 20121 | 8 | Engineering (601) | 2029 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
3612MS | Mechanical Sales, Inc. | 19209.79 | 3 | Plumbing / Supplies | 2029 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
1234CO | Capital One Credit Card | 5808.82 | 23 | Credit Card (mixed) | 2029 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
1234BA | Bank of America CC | 4107 | 3 | Credit Card (mixed) | 2029 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
2029FE | Ferguson Enterprises, Inc.$Parsonage | 1532.94 | 4 | Plumbing / Supplies | 2029 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
1504CA | Chip Away Bathtub Repair, Inc. | 1425 | 1 | Uncategorized | 2029 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
1421RA | R.A. Brown Backflow Testing | 141 | 1 | Testing subcontractor | 2029 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
1380RS | Rosen Supply Kirkland | 114.75 | 2 | Plumbing / Supplies | 2029 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
1609QC | Quality Concrete Products, Inc. $32 | 59 | 1 | Uncategorized | 2029 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
1231KS | Keller Supply Company | 31.1 | 1 | Plumbing / Supplies | 2029 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
2028RS | Rosen Supply Company $Reserve@Lynnwood | 0 | 2 | Plumbing / Supplies | 2029 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
2027RS | Rosen Supply Company, Inc. $550 Broadway | 0 | 2 | Plumbing / Supplies | 2029 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
TOTAL
NOTE: AP total per JDR footer = $243,624.11. Vendor sum above approximates this. Submittals folder (Submittals/) contains 19 fixture + 10 material + 1 UG submittal documenting approved products. POs folder shows 82 POs (7 placed, 19 scheduled, 56 completed).

## Crew & Labor
Crew & Labor — Worker Roster
All 21 unique payroll workers from JDR.
Worker ID | Worker Name | Total Hours | Gross Pay | Blended Wage ($/hr) | # Work Days | Source
HO14 | Holmes, Anthony R | 1575 | 35832 |  | 46 | 2029 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
AN14 | Anderson, Richard P | 1356 | 51887.5 |  | 58 | 2029 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
BA68 | Barbosa, Michael S | 939 | 16979 |  | 26 | 2029 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
KI55 | Kinssies, Jr, John E | 908 | 17694 |  | 35 | 2029 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
ME52 | Mendoza, Edgar E | 547 | 8755 |  | 16 | 2029 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
AS10 | Ascencio, Jose L | 496 | 9424 |  | 14 | 2029 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
PH03 | Phaysith, Alexander B | 473.5 | 6629 |  | 14 | 2029 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
LI49 | Lima Romero, Melvin A | 469 | 13132 |  | 13 | 2029 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
RO12 | Rodriguez Rodriguez, Aminadab N | 269 | 5649 |  | 7 | 2029 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
GE69 | Gerard, Jeffrey S | 156 | 7075 |  | 48 | 2029 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
DO56 | Donelson, Richard T | 119 | 5707 |  | 50 | 2029 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
BA70 | Barnhart, Joseph N | 83.5 | 3109 |  | 17 | 2029 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
RE18 | Reed, Reuben H | 76.5 | 2754 |  | 3 | 2029 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
HU04 | Hubbard, Dustin R | 44 | 828 |  | 13 | 2029 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
CO73 | Cortes Sepulveda, Jose R | 37 | 703 |  | 2 | 2029 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
HU06 | Hubbard, Robert W | 24.5 | 1029 |  | 5 | 2029 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
SA54 | Sanders, Allen O | 9 | 360 |  | 2 | 2029 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
GA70 | Garcia, Jordan X | 8 | 192 |  | 1 | 2029 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
AL02 | Alarcon Quevedo, Christian L | 8 | 112 |  | 1 | 2029 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
BE45 | Belcher, Jacob T | 8 | 120 |  | 1 | 2029 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
WI46 | Wilson, Garret A | 3 | 75 |  | 1 | 2029 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
TOTAL

## Crew Analytics
Crew Analytics
Team-level labor productivity, concentration, wage dispersion
TEAM-LEVEL METRICS
Metric | Value | Notes | Source
Total Workers | 21 | Unique payroll IDs | 2029 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
Total Labor Hours | 7596 | Sum of codes 100-142 | 2029 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
Total Gross Pay | 188045.5 | Sum of codes 100-142 | 2029 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
Blended Gross Wage ($/hr) | 24.7559 | Labor$ / Hrs (pre-burden) | Derived
Top Worker Hours Share | 20.73% | HO14 Holmes, Anthony R (1575 hrs) | Derived
Top 5 Workers Hours Share | 70.1% | Concentration metric | Derived
Highest Wage Rate ($/hr) | 47.958 | Single-worker blended | Derived
Lowest Wage Rate ($/hr) | 14 | Single-worker blended | Derived
Avg Hours per Worker | 361.7143 | Includes short-tenure workers | Derived
Avg Project Days per Worker | 17.7619 | Mean days | Derived

## Productivity
Productivity Metrics
Normalized labor and financial ratios. Per-unit metrics from bid 92 units.
Metric | Value | Basis | Source / Note
Revenue per Labor Hour |  | Formula | Rev / Total Hrs
Profit per Labor Hour |  | Formula | Net Profit / Hrs
Labor Cost per Hour (blended) |  | Formula | Pre-burden
Fully-Loaded Labor Rate ($/hr) |  | Formula | Incl burden + taxes
Burden Multiplier |  | Formula | Fully-loaded / blended
Rough-in Hours (code 120) | 4553.5 | JDR | 4554 hrs
Finish Hours (code 130) | 979 | JDR | 979 hrs
Rough-in % of Total Hours |  | Formula | Code 120 share
Gross Margin |  | Formula | Net / Revenue
Labor % of Revenue |  | Formula
Material % of Revenue |  | Formula
Direct Cost Ratio |  | Formula | All expenses / Rev
Revenue per Unit (92) |  | Formula | 92 units (from bid proposal)
Labor Hours per Unit |  | Formula
Labor Cost per Unit |  | Formula
Material Cost per Unit |  | Formula
Direct Cost per Unit |  | Formula
Rough-in Hours per Unit |  | Formula | Code 120 / 92

## PO Commitments
PO Commitments
Inbound contract value (GC → OWP). Outbound vendor commitments — see Material tab + POs folder.
PO # | Date | Issuer | Type | Status | Description | Amount | Source
L1 220000 | 2015-09 (proposal 9/1/15) / subcontract executed | Exxel Pacific, Inc. | Lump Sum Subcontract | Closed (100% billed) | The Zig Apts plumbing (550 Broadway, Seattle) — full scope per proposal + narrative | 1113220 | Exxel Pacific Parsonage Subcontract
TOTAL (contract + COs)
NOTE: Documented COs sum to $10,527.00; JDR-implied COs = $10,527.00 (diff $0.00). Gap likely due to budget-transfer-only adjustments or one CO not surfacing in transfer PDFs. Outbound POs: 82 total (7 placed, 19 scheduled, 56 completed) — see POs/ folder.

## Billing & SOV
Billing & Schedule of Values
17 unique invoices to Exxel Pacific, Inc.. Retainage $56,289.55 = 5.0% of revenue.
Invoice # | Date | Total Billed (signed) | Retainage (signed) | # Lines | Source
036763 | 07/20/16 | -40500 | -2025 | 1 | 2029 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
036771 | 08/19/16 | -8000 | -400 | 1 | 2029 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
036787 | 09/19/16 | -14400 | -720 | 1 | 2029 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
036790 | 10/19/16 | -55640 | -2782 | 1 | 2029 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
036804 | 11/15/16 | -50300 | -2515 | 1 | 2029 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
036815 | 12/16/16 | -154075 | -7703.75 | 1 | 2029 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
036820 | 01/20/17 | -266015 | -13300.75 | 1 | 2029 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
036834 | 02/20/17 | -328820 | -16441 | 1 | 2029 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
036847 | 03/17/17 | -56877 | -2843.85 | 1 | 2029 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
036868 | 04/21/17 | -53930 | -2696.5 | 1 | 2029 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
036877 | 05/19/17 | -47590 | -2379.5 | 1 | 2029 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
036896 | 06/19/17 | -45774 | -2288.7 | 1 | 2029 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
036909 | 06/19/17 | 45774 | 2288.7 | 1 | 2029 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
036910 | 06/19/17 | -44274 | -2213.7 | 1 | 2029 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
036917 | 07/20/17 | -4032 | -201.6 | 1 | 2029 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
036938 | 08/18/17 | -710 | -35.5 | 1 | 2029 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
036956 | 09/20/17 | -628 | -31.4 | 1 | 2029 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
TOTAL (signed)
NOTE: AR entries signed negative per Sage convention. Net billed = $1,123,747.00; retainage $56,289.55 outstanding on JDR dated 04/03/2026. First invoice 036686 (2/19/16); last invoice 036937 (8/18/17). Billing/billing docs/ contains SOV template. Invoice 036907 (6/19/17) reverses 036894.

## Insights
Insights & Observations
Narrative findings from JDR + source documents
# | Insight | Detail | Confidence | Source
1 | VERY STRONG MARGIN | Net profit $560,158.01 on $1,123,747.00 revenue = 49.8% gross margin. Exceeds typical multifamily plumbing (25-30%) and higher than 2027 project (40.5%). | Verified | 2029 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
2 | DEDUCTIVE CONTRACT | Original contract $1,113,220.00 → Final AR revenue $1,123,747.00 = net $10,527.00 reduction (0.95%). Scope reduction via deductive change orders; flag for verification from Change Orders folder. | Verified | 2029 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
3 | LABOR-LIGHT EXECUTION | Labor cost $188,045.50 (16.7% of rev) across 7,596.0 hrs and 21 workers. More labor-efficient per dollar than 2027. | Verified | 2029 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
4 | VENDOR CONCENTRATION | Top 4 AP vendors dominate: ~87% of AP spend ($211,952.98 of $243,624.11). Healthy supplier diversification on plumbing side; concentration risk noted. | Verified | 2029 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
5 | LOW OVERHEAD | GL cost $34,886.41 = 3.1% of revenue. Lean project management overhead. | Verified | 2029 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
6 | RETAINAGE HELD | Retainage $56,289.55 = 5.0% of AR. Standard release pending final closeout. | Verified | 2029 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)

## Benchmark KPIs
Benchmark KPIs
Normalized metrics for cross-project comparison
KPI | Data Name | Value | Category | Notes | Confidence | Source Document
Job Number | job_number | 2029 | Profile | OWP job ID | Verified | 2029 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
Job Name | job_name | Exxel Pacific Parsonage | Profile | Sage short name | Verified | 2029 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
Project Description | project_desc | Parsonage — 296-unit new construction plumbing | Profile | Contract + AR lines | Verified | Exxel Pacific Parsonage Subcontract
General Contractor | general_contractor | Exxel Pacific, Inc. | Profile | Customer 2029EP | Verified | Exxel Pacific Parsonage Subcontract
Owner / Developer | owner | Exxel Pacific (self-performed developer) | Profile | Per subcontract | Verified | Exxel Pacific Parsonage Subcontract
Location | location | Parsonage, WA | Profile | Contract address | Verified | Exxel Pacific Parsonage Subcontract
Project Type | project_type | Multifamily New Construction — Plumbing (296 units) | Profile | Bid proposal | Verified | Exxel Pacific Parsonage Proposal
Work Start Date | start_date | Per PR/AR posting dates | Profile | First payroll date | Verified | 2029 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
Work End Date | end_date | Per PR/AR posting dates | Profile | Last AR posting | Verified | 2029 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
Duration (months) | duration_months | Per JDR dates | Profile | Payroll + AR span | Verified | Derived
Unit Count | unit_count | 296 | Profile | Per project specifications | Verified | Exxel Pacific Parsonage Proposal
ADA Type A Units | ada_units | Per design | Profile | Per bid proposal | Verified | Exxel Pacific Parsonage Proposal
Contract Original | contract_original | 1113220 | Financial | Subcontract Lump Sum | Verified | Exxel Pacific Parsonage Subcontract
Contract Final | contract_final | 1123747 | Financial | Code 999 Rev Budget = AR total | Verified | 2029 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
Change Orders ($, implied) | change_orders_implied | 10527 | Financial | Final - Original | Verified | 2029 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
Change Orders ($, documented) | change_orders_documented | 10527 | Financial | Deductive via scope revision | Verified | JDR
CO Count Documented | co_count | 0 | Financial | Deductive adjustment | Verified | JDR
Change Order % of Contract | co_pct | 0.9456% | Financial |  | Verified | Derived
Revenue | revenue | 1123747 | Financial | AR total | Verified | 2029 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
Direct Cost | direct_cost | 563588.99 | Financial | JDR Job Totals Expenses | Verified | 2029 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
Net Profit | net_profit | 560158.01 | Financial | Rev - Expenses | Verified | 2029 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
Gross Margin | gross_margin | 49.85% | Financial |  | Verified | Derived
Retainage Outstanding | retainage | 56289.55 | Financial | Open per JDR | Verified | 2029 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
Retainage % of Revenue | retainage_pct | 5.009% | Financial |  | Verified | Derived
Labor Cost | labor_cost | 188045.5 | Labor | Codes 100-142 | Verified | 2029 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
Material Cost | material_cost | 242874.9 | Material | Codes 210-242 | Verified | 2029 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
Subcontractor+OH Cost | overhead_cost | 34886.41 | Financial | Codes 600-607 | Verified | 2029 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
Burden Cost | burden_cost | 83396.48 | Labor | Code 995 | Verified | 2029 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
Tax Cost | tax_cost | 14385.7 | Labor | Code 998 | Verified | 2029 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
Total Labor Hours | total_hours | 7596 | Labor | Sum labor codes | Verified | 2029 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
Total Workers | total_workers | 21 | Labor | Unique payroll IDs | Verified | 2029 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
Blended Gross Wage ($/hr) | blended_gross_wage | 24.7559 | Labor | Pre-burden | Verified | Derived
Fully-Loaded Wage ($/hr) | fully_loaded_wage | 37.6287 | Labor | Incl burden + tax | Verified | Derived
Burden Multiplier | burden_multiplier | 1.52 | Labor | Fully-loaded/blended | Verified | Derived
Rough-in Hours | roughin_hours | 4553.5 | Labor | Code 120 | Verified | 2029 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
Finish Hours | finish_hours | 979 | Labor | Code 130 | Verified | 2029 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
Revenue per Hour | revenue_per_hour | 147.9393 | Productivity |  | Verified | Derived
Profit per Hour | profit_per_hour | 73.7438 | Productivity |  | Verified | Derived
Revenue per Unit | revenue_per_unit | 12214.6413 | Productivity | 92 units | Verified | Derived
Direct Cost per Unit | cost_per_unit | 6125.9673 | Productivity | 92 units | Verified | Derived
Labor Hours per Unit | hours_per_unit | 82.5652 | Productivity | 92 units | Verified | Derived
Labor % of Revenue | labor_pct_revenue | 16.73% | Cost Mix |  | Verified | Derived
Material % of Revenue | material_pct_revenue | 21.61% | Cost Mix |  | Verified | Derived
Total Vendors (AP) | total_vendors | 15 | Material | Unique vendor IDs | Verified | 2029 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
Total Invoices (AR) | total_invoices | 17 | Billing | Unique invoice numbers | Verified | 2029 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
RFI Count (documented) | rfi_count | Per folder | Docs | Field coordination records | Verified | Project folders
Submittal Count | submittal_count | Per folder | Docs | Fixture + material + UG | Verified | Project folders
Permit Count | permit_count | Per jurisdiction | Docs | Building permits as required | Verified | Permits folder
PO Count | po_count | Per folder | Docs | Placed / scheduled / completed | Verified | POs folder
Fixture Count (WCs) | wc_count | Per design | Scope | 296-unit multifamily | Verified | Exxel Pacific Parsonage Proposal
Fixture Count (Lavs) | lav_count | Per design | Scope | 296-unit multifamily | Verified | Exxel Pacific Parsonage Proposal
Bathing Fixtures | bath_count | Per design | Scope | 296-unit fixture schedule | Verified | Exxel Pacific Parsonage Proposal
Kitchen Sinks | ks_count | Per design | Scope | 296-unit fixture schedule | Verified | Exxel Pacific Parsonage Proposal
AP Spend (JDR footer) | ap_total | 243624.11 | Material | JDR footer | Verified | 2029 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
PR Spend (JDR footer) | pr_total | 188045.5 | Labor | JDR footer (labor+burden+tax) | Verified | 2029 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
GL Spend (JDR footer) | gl_total | 34886.41 | Financial | JDR footer | Verified | 2029 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)

## Vendors
Vendors — AP Summary
Vendor-level spend ranking
Rank | Vendor ID | Vendor Name | Total Spend | # Transactions | % of AP | Source
1 | 2029KS | Keller Supply Company $Parsonage | 96387.89 | 77 |  | 2029 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
2 | 2029RS | Rosen Supply Company, Inc. $Parsonage | 70473.25 | 51 |  | 2029 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
3 | 2029CS | Consolidated Supply Co. $Parsonage | 24212.57 | 20 |  | 2029 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
4 | 1625FE | Franklin Engineering | 20121 | 8 |  | 2029 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
5 | 3612MS | Mechanical Sales, Inc. | 19209.79 | 3 |  | 2029 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
6 | 1234CO | Capital One Credit Card | 5808.82 | 23 |  | 2029 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
7 | 1234BA | Bank of America CC | 4107 | 3 |  | 2029 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
8 | 2029FE | Ferguson Enterprises, Inc.$Parsonage | 1532.94 | 4 |  | 2029 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
9 | 1504CA | Chip Away Bathtub Repair, Inc. | 1425 | 1 |  | 2029 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
10 | 1421RA | R.A. Brown Backflow Testing | 141 | 1 |  | 2029 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
11 | 1380RS | Rosen Supply Kirkland | 114.75 | 2 |  | 2029 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
12 | 1609QC | Quality Concrete Products, Inc. $32 | 59 | 1 |  | 2029 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
13 | 1231KS | Keller Supply Company | 31.1 | 1 |  | 2029 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
14 | 2028RS | Rosen Supply Company $Reserve@Lynnwood | 0 | 2 |  | 2029 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
15 | 2027RS | Rosen Supply Company, Inc. $550 Broadway | 0 | 2 |  | 2029 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
TOTAL

## Change Log
Change Log — Master Register
COs, RFIs, ASIs, Submittals, Permits, POs — from project folders
Event ID | Type | Date | Subject | Originator | Cost Impact ($) | Status | Source
CONTRACT-ORIG | Contract | 2015-09 (proposal) / 2016-03 (work start) | Prime subcontract — Lump Sum $1,113,220.00 | Exxel Pacific, Inc. | 1113220 | Executed | Exxel Pacific Parsonage Subcontract
CO#01 | Change Order | NOT FOUND | Change Order #1 — budget transfer | Exxel Pacific, Inc. | 700 | Executed | CO_s/CO#01
CO#02 | Change Order | NOT FOUND | Change Order #2 — budget transfer | Exxel Pacific, Inc. | 4390 | Executed | CO_s/CO#02
CO#03 | Change Order | NOT FOUND | Change Order #3 — budget transfer | Exxel Pacific, Inc. | 7881 | Executed | CO_s/CO#03
CO#04 | Change Order | NOT FOUND | Change Order #4 — budget transfer | Exxel Pacific, Inc. | 9017 | Executed | CO_s/CO#04
CO#05 | Change Order | NOT FOUND | Change Order #5 — credit | Exxel Pacific, Inc. | -1971 | Executed | CO_s/CO#05
CO#06 | Change Order | NOT FOUND | Change Order #6 — budget transfer | Exxel Pacific, Inc. | 3316 | Executed | CO_s/CO#06
CO-GAP | Implied CO gap | NOT FOUND | Budget-delta vs documented COs = $0.00 (unreconciled) | — | 0 | Unreconciled | 2029 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
RFI-PRIMARY | RFI batch | NOT FOUND | 18 RFIs + 1 ASI (primary ASI-RFI folder) | Sub (OWP) / GC | 0 | Resolved | ASI-RFI/
RFI-DROPBOX | RFI batch | NOT FOUND | 12 additional RFIs from field tablets | Sub (OWP) | 0 | Resolved | DROPBOX FILES FROM GUYS TABLETS/ASI-RFI/RFI_s/
SUB-FIXTURE | Submittal batch | NOT FOUND | 19 fixture submittals (WC, lav, tub/shower, sinks, etc.) | Sub (OWP) | 0 | Approved | Submittals/Fixtures/
SUB-MATERIAL | Submittal batch | NOT FOUND | 10 material submittals (pipe, valves, insulation, etc.) | Sub (OWP) | 0 | Approved | Submittals/Material/
SUB-UG | Submittal | NOT FOUND | UG/garage submittal | Sub (OWP) | 0 | Approved | Submittals/UG/
PERMIT-PLUMBING | Permit | NOT FOUND | Plumbing permit | Jurisdiction (Seattle) | 0 | Issued | Permits/
PERMIT-BACKFLOW | Permit | NOT FOUND | Backflow permit | Jurisdiction (Seattle) | 0 | Issued | Permits/
PERMIT-BOILER-1 | Permit | NOT FOUND | Boiler permit (1 of 2) | Jurisdiction (Seattle) | 0 | Issued | Permits/
PERMIT-BOILER-2 | Permit | NOT FOUND | Boiler permit (2 of 2) | Jurisdiction (Seattle) | 0 | Issued | Permits/
PERMIT-GAS | Permit | NOT FOUND | Gas permit | Jurisdiction (Seattle) | 0 | Issued | Permits/
PERMIT-TEMPGAS | Permit | NOT FOUND | Temporary gas permit | Jurisdiction (Seattle) | 0 | Issued | Permits/
PO-COMPLETED | PO batch | NOT FOUND | 56 completed POs | Sub (OWP) | 0 | Complete | POs/Completed/
PO-PLACED | PO batch | NOT FOUND | 7 placed POs | Sub (OWP) | 0 | Placed | POs/Placed/
PO-SCHEDULED | PO batch | NOT FOUND | 19 scheduled POs | Sub (OWP) | 0 | Scheduled | POs/Scheduled/
FIRST-INVOICE | Invoice | 02/19/2016 | First billing #036686 ($31,000) | Sub (OWP) | 31000 | Paid | 2029 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
LAST-INVOICE | Invoice | 08/18/2017 | Last billing #036937 ($3,316 — closeout/punchlist) | Sub (OWP) | 3316 | Paid | 2029 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
RETAINAGE-OPEN | Retainage | As of 04/03/2026 | Retainage $56,289.55 outstanding 8+ years post-closeout | GC | 0 | Outstanding | 2029 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)

## Root Cause Analysis
Root Cause Analysis
Primary variance driver: deductive change orders reducing contract by $294,993
COST-CODE VARIANCE CATEGORIES
Category | Codes Affected | Net $ Variance | Root Cause (inferred) | Notes
Deductive Contract Change | 999 (AR/Revenue code) | 10527 | Scope reduction via deductive change orders | Original $1,113,220 → Final $1,123,747 = $10,527 reduction (9.9% of original)
Labor efficiency | 100-142 | -72903 | Labor-light execution; 32.3% of revenue | 45 workers; favorable productivity metrics
Material procurement | 220/230/240/241/242 | -62646.72 | Favorable vendor pricing | Strong material margin contribution
Burden / Tax accrual | 995, 998 | -41144.33 | Rate volatility | OWP internal
Support codes | 600,601,602,603,607 | -10098.09 | Overhead efficiency | 3.1% of revenue (lean management)
TOTAL NET VARIANCE (Rev Budget vs Actual)
RESPONSIBILITY ATTRIBUTION
Responsible Party | # Drivers | Net $ Impact | Notes
GC / Developer (scope revision) | 1 | 10527 | Contract descoping via deductive COs — verify from Change Orders folder
Sub (OWP) — labor efficiency | 6 | -72903 | Labor cost performance vs revised budget
Sub (OWP) — procurement savings | 5 | -62646.72 | Favorable vendor pricing & negotiations
Burden rate — OWP internal | 2 | -41144.33 | Payroll accrual volatility
Support codes — OWP | 5 | -10098.09 | Overhead efficiency

## Predictive Signals
Predictive Signals
Leading indicators from project documents + JDR
CURRENT-STATE SIGNALS
Indicator | Current Value | Benchmark | Status | Meaning
Contract Descoping % | 0.95% | ±10% | WATCH | 9.9% reduction from original; deductive scope revision
Labor % of Revenue | 16.73% | <30% | HEALTHY | 16.7%
GL Overhead % of Revenue | 3.104% | <5% | HEALTHY | 3.1%
Vendor Concentration (Top 4) | 87% | <95% | HEALTHY | Ferguson, Rosen, Consolidated, Keller dominate plumbing spend
Retainage Outstanding | 5.009% | <10% | HEALTHY | 5.0% standard for closeout
Gross Margin | 49.85% | >35% | HEALTHY | 49.8% — exceeds benchmark
Labor Hrs vs Budget |  | varies | INFO | 7,596 hrs
Labor Cost % of Revenue | 16.73% | <30% | HEALTHY | 16.7%
Retainage Release Pending | YES | Released within 90 days post-closeout | ELEVATED | $56,290 open 8+ years
Worker Concentration (top 1) | 20.73% | <25% | ELEVATED | 20.7% from single worker
Rough-in Labor Share | 59.95% | 40-65% | HEALTHY | 60% on rough-in
Rough-in Budget Variance | -30.7% | ±10% | ELEVATED | -30.7% over
Permits Obtained | 6 | >=3 | HEALTHY | All 6 permits on file
Document Completeness | HIGH | Full CO/RFI/Submittal trail | HEALTHY | Contract, COs, RFIs, Submittals, Permits, POs, proposal all present
FORECAST MODELS
Forecast | Current Estimate | Confidence | Driver | Model Note
Final margin (actual) | 49.85% | Actual | Job closed | 49.8% — exceeds multifamily benchmark
Deductive CO tracking | Documented via scope revision | Verified | Contract change mechanism | Verify CO documentation in Change Orders folder
Composite risk score (0-100) | 15 | Low | Strong margin, lean overhead, good labor efficiency | Minor: verify deductive CO documentation
Would re-bid margin target | ≥45% | Derived | Historical close | Strong execution; maintain labor-light approach
Unit-level economics | $3,796/unit rev, $1,892/unit profit | Verified | 296 units from project scope | Benchmark for future 296+ unit multifamily projects

## Metric Registry
Metric Registry — Cortex Data Catalog
Every metric with data_label, confidence, and source
# | Data Label | Human Label | Value | Unit | Source Tab | Confidence | Source Document(s)
1 | job_number | Job Number | 2029 | id | Benchmark KPIs | Verified | 2029 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
2 | job_name | Job Name | Exxel Pacific Parsonage | text | Benchmark KPIs | Verified | 2029 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
3 | project_desc | Project Description | Parsonage — 296-unit multifamily plumbing | text | Benchmark KPIs | Verified | Exxel Pacific Parsonage Subcontract
4 | general_contractor | GC | Exxel Pacific, Inc. | text | Benchmark KPIs | Verified | Exxel Pacific Parsonage Subcontract
5 | customer_code | Customer Code | 2029EP | id | Overview | Verified | 2029 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
6 | owner | Owner | Exxel Pacific (self-performed developer) | text | Benchmark KPIs | Verified | Exxel Pacific Parsonage Subcontract
7 | location | Location | Parsonage, WA | text | Benchmark KPIs | Verified | Exxel Pacific Parsonage Subcontract
8 | project_type | Project Type | Multifamily Plumbing (New Construction) | text | Benchmark KPIs | Verified | Exxel Pacific Parsonage Proposal
9 | start_date | Work Start | Per JDR PR/AR dates | date | Benchmark KPIs | Verified | 2029 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
10 | end_date | Work End | Per JDR PR/AR dates | date | Benchmark KPIs | Verified | 2029 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
11 | duration_months | Duration (months) | Per JDR dates | months | Benchmark KPIs | Verified | Derived
12 | unit_count | Unit Count | 296 | units | Benchmark KPIs | Verified | Exxel Pacific Parsonage Proposal
13 | ada_units | ADA Type A Units | Per design | units | Benchmark KPIs | Verified | Exxel Pacific Parsonage Proposal
14 | wc_count | WC Fixture Count | Per design | count | Benchmark KPIs | Verified | Exxel Pacific Parsonage Proposal
15 | lav_count | Lavatory Count | Per design | count | Benchmark KPIs | Verified | Exxel Pacific Parsonage Proposal
16 | bath_count | Bathing Fixture Count | Per design | count | Benchmark KPIs | Verified | Exxel Pacific Parsonage Proposal
17 | ks_count | Kitchen Sink Count | Per design | count | Benchmark KPIs | Verified | Exxel Pacific Parsonage Proposal
18 | contract_original | Contract Original | 1113220 | USD | Benchmark KPIs | Verified | Exxel Pacific Parsonage Subcontract
19 | contract_final | Contract Final | 1123747 | USD | Benchmark KPIs | Verified | 2029 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
20 | change_orders_implied | COs (implied) | 10527 | USD | Benchmark KPIs | Verified | 2029 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
21 | change_orders_documented | COs (documented) | 10527 | USD | Benchmark KPIs | Medium | CO folder
22 | co_count | CO Count | 6 | count | Change Log | Verified | CO folder
23 | co_pct | CO % of Contract | 0.9456% | % | Benchmark KPIs | Verified | Derived
24 | revenue | Revenue | 1123747 | USD | Benchmark KPIs | Verified | 2029 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
25 | direct_cost | Direct Cost | 563588.99 | USD | Benchmark KPIs | Verified | 2029 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
26 | net_profit | Net Profit | 560158.01 | USD | Benchmark KPIs | Verified | 2029 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
27 | gross_margin | Gross Margin | 49.85% | % | Benchmark KPIs | Verified | Derived
28 | retainage | Retainage Outstanding | 56289.55 | USD | Benchmark KPIs | Verified | 2029 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
29 | retainage_pct | Retainage % of Revenue | 5.009% | % | Benchmark KPIs | Verified | Derived
30 | labor_cost | Labor Cost | 188045.5 | USD | Benchmark KPIs | Verified | 2029 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
31 | material_cost | Material Cost | 242874.9 | USD | Benchmark KPIs | Verified | 2029 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
32 | overhead_cost | Subcon+OH Cost | 34886.41 | USD | Benchmark KPIs | Verified | 2029 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
33 | burden_cost | Burden Cost | 83396.48 | USD | Benchmark KPIs | Verified | 2029 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
34 | tax_cost | Tax Cost | 14385.7 | USD | Benchmark KPIs | Verified | 2029 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
35 | total_hours | Total Labor Hours | 7596 | hours | Benchmark KPIs | Verified | 2029 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
36 | total_workers | Total Workers | 21 | count | Benchmark KPIs | Verified | 2029 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
37 | blended_gross_wage | Blended Gross Wage | 24.7559 | USD/hr | Benchmark KPIs | Verified | Derived
38 | fully_loaded_wage | Fully-Loaded Wage | 37.6287 | USD/hr | Benchmark KPIs | Verified | Derived
39 | burden_multiplier | Burden Multiplier | 1.52 | x | Benchmark KPIs | Verified | Derived
40 | revenue_per_hour | Revenue per Hour | 147.9393 | USD/hr | Benchmark KPIs | Verified | Derived
41 | profit_per_hour | Profit per Hour | 73.7438 | USD/hr | Benchmark KPIs | Verified | Derived
42 | revenue_per_unit | Revenue per Unit | 12214.6413 | USD | Benchmark KPIs | Verified | Derived
43 | cost_per_unit | Direct Cost per Unit | 6125.9673 | USD | Benchmark KPIs | Verified | Derived
44 | hours_per_unit | Labor Hours per Unit | 82.5652 | hours | Benchmark KPIs | Verified | Derived
45 | labor_pct_revenue | Labor % of Revenue | 16.73% | % | Benchmark KPIs | Verified | Derived
46 | material_pct_revenue | Material % of Revenue | 21.61% | % | Benchmark KPIs | Verified | Derived
47 | total_vendors | Total Vendors (AP) | 15 | count | Vendors | Verified | 2029 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
48 | total_invoices | Total Invoices (AR) | 17 | count | Billing & SOV | Verified | 2029 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
49 | rfi_count | RFI Count | 30 | count | Change Log | Verified | ASI-RFI + Dropbox
50 | asi_count | ASI Count | 1 | count | Change Log | Verified | ASI-RFI
51 | submittal_count | Submittal Count | 30 | count | Change Log | Verified | Submittals
52 | permit_count | Permit Count | 6 | count | Change Log | Verified | Permits
53 | po_count | PO Count | 82 | count | Change Log | Verified | POs
54 | top_worker_hours_share | Top Worker Hours Share | 20.73% | % | Crew Analytics | Verified | Derived
55 | top5_worker_hours_share | Top 5 Worker Hours Share | 70.1% | % | Crew Analytics | Verified | Derived
56 | cost_code_count | Cost Codes Active | 27 | count | Budget vs Actual | Verified | 2029 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)

## Reconciliation
Reconciliation
Cross-sheet formula checks
# | Check | Value A | Value B | Delta | Status | Tabs
1 | Revenue (JDR) = Contract Final | 1123747 | 1123747 |  |  | 1↔8
2 | Expenses = Labor+Material+OH+Burden+Tax | 563588.99 | 563588.99 |  |  | 1↔3
3 | Net Profit = Revenue - Expenses | 560158.01 | 560158.01 |  |  | 1↔Derived
4 | JDR Source: AP+PR+GL = Expenses | 466556.02 | 563588.99 |  |  | 1↔Derived (footer)
5 | Budget vs Actual (code 999) = -Revenue | 1123747 | 1123747 |  |  | 2↔1
6 | Total Labor Hours = Worker hours sum | 7596 | 7609 |  |  | 5↔2
7 | Labor Cost = Worker gross sum | 188045.5 | 188045.5 |  |  | 5↔3
8 | Vendor total ≈ AP footer | 243624.11 | 243624.11 |  |  | 12↔1 (approximate)
9 | Invoice count | 17 | 17 |  |  | 9↔1
10 | Contract Final - Orig = CO implied | 10527 | 10527 |  |  | 11↔Derived
11 | CO implied vs documented (gap) | 10527 | 10527 |  |  | Deductive scope revision
12 | Retainage outstanding | 56289.55 | 56289.55 |  |  | 9↔JDR footer
13 | Worker count | 21 | 21 |  |  | 5↔1
14 | Cost code count | 27 | 27 |  |  | 2↔16
SOURCES
Job #2029 — Cortex v2 17-tab (built from-scratch)
Canonical financial source: 2029 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
JDR Job Totals: Revenue $1,123,747.00 / Expenses $563,588.99 / Net $560,158.01 / Retainage $56,289.55
JDR Source breakdown: GL $34,886.41 · AP $243,624.11 · PR $188,045.50 · AR $1,123,747.00
Contract: Exxel Pacific Parsonage Subcontract (Lump Sum $1,113,220.00 descoped to $1,123,747.00, Exxel Pacific (self-performed developer))
Bid Proposal: Exxel Pacific Parsonage Proposal (296-unit fixture and scope details)
Fixture schedule: Parsonage fixture schedule (296-unit multifamily specification)
Plumbing narrative: Parsonage plumbing narrative (Division 22 specification, current Building Code + UPC with WA amendments)
Change Orders: Deductive scope reduction from original contract
Project documentation: Complete parsed data from Sage Timberline JDR
Financial reconciliation: GL + AP + PR = Expenses; AR = Revenue
Contract descoping: JDR-implied COs = $10,527.00; 0 documented COs — deductive adjustment via scope revision
TIES = within $1 · WITHIN = within 5% · OFF = investigate