## Overview
Job #2030 · Exxel Pacific East Union
Cortex JCR Cortex v2 • Exxel Pacific, Inc. (customer 2030EP) • East Union, WA • Owner: Lake Union Partners (developer)
PROJECT OVERVIEW
Project Job # | 2030 |  | 2030 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages) header
Project Name (Sage) | Exxel Pacific East Union |  | 2030 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages) header
Project Description | East Union — 296-unit new construction plumbing |  | Exxel Pacific East Union Subcontract / AR line descriptions
General Contractor | Exxel Pacific, Inc. |  | Exxel Pacific East Union Subcontract
Customer Code (Sage) | 2030EP |  | 2030 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
Owner / Developer | Lake Union Partners (developer) |  | Exxel Pacific East Union Subcontract
Jobsite Location | East Union, WA |  | Exxel Pacific East Union Subcontract
Contract / PO Document | Exxel Pacific East Union Subcontract |  | Lump Sum subcontract
Plans / Specifications | East Union plumbing narrative (Div 22 plumbing narrative) + fixture schedule + proposal |  | Folder scan
Fixture Schedule | East Union fixture schedule (fixture schedule for 296-unit multifamily) |  | Referenced
Bid Proposal | Exxel Pacific East Union Proposal |  | Detailed scope and fixture quantities
Contract Type | Lump Sum |  | Exxel Pacific East Union Subcontract
Work Period | Per PR/AR posting dates in JDR |  | 2030 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
Total Unique Documents Reviewed | 1924 |  | File inventory across owp-2030/
CONTRACT VALUE |  | NET PROFIT | DIRECT COST | LABOR HOURS
2322781 |  | 885352.03 | 1437428.97 | 18665
Original $2,135,080.00 + $187,701.00 COs (8.79%) |  | 38.1% margin | 61.9% of revenue | 45 workers
SCOPE OF WORK (from contract + proposal)
Full plumbing installation: underground, rough-in, finish, gas piping, water mains, insulation, mechanical room, and warranty.
296-unit multifamily new construction at East Union, WA.
5 levels above ground, 1 level below grade (per Job Info).
Comprehensive fixture schedule with standard and ADA-compliant units.
Spec compliance: Current Building Code + UPC with Washington state amendments.
SOURCES
Canonical financial source: 2030 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
Job totals (JDR footer): Revenue $2,322,781.00 / Expenses $1,437,428.97 / Net $885,352.03 / Retainage $116,139.05
Source breakdown: GL $101,304.62 · AP $555,579.87 · PR $481,197.50 · AR $2,322,781.00
Contract: Exxel Pacific East Union Subcontract (Lump Sum $2,135,080.00, descoped to $2,322,781.00)
Proposal: Exxel Pacific East Union Proposal
Fixture schedule: East Union fixture schedule
Plumbing narrative: East Union plumbing narrative
Change Orders: Deductive scope changes; net contract reduction ${CO_TOTAL_IMPLIED:,.2f}

## Budget vs Actual
Budget vs Actual
All 29 cost codes from JDR. Contract $2,135,080 → $2,322,781 (COs +$187,701.00).
Cost Code | Description | Original Budget | Revised Budget | Actual | Variance | % of Revised | Hours | Source
100 | Supervision | 14400 | 16050 | 4994.5 |  |  | 102.5 | 2030 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
101 | Takeoff & Purchase Labor | 23040 | 25090 | 19747 |  |  | 392 | 2030 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
110 | Underground Labor | 9400 | 10618 | 4496.5 |  |  | 143.5 | 2030 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
111 | Garage Labor | 110300 | 123843 | 83224.5 |  |  | 3139.5 | 2030 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
112 | Canout Labor | 13900 | 20455 | 10888 |  |  | 373.75 | 2030 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
120 | Roughin Labor | 246760 | 245447 | 255360.5 |  |  | 9692.25 | 2030 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
130 | Finish Labor | 48300 | 48437 | 47557.25 |  |  | 1737.5 | 2030 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
140 | Gas Labor | 9600 | 11720 | 16593 |  |  | 578 | 2030 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
141 | Water Main/Insulation Lab | 44785 | 49085 | 42757 |  |  | 1889 | 2030 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
142 | Mech Room Labor | 21000 | 24886 | 18473 |  |  | 617 | 2030 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
210 | Underground Material | 19300 | 23202 | 14590.94 |  |  |  | 2030 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
211 | Garage Material | 108050 | 126594 | 72845.97 |  |  |  | 2030 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
212 | Canout Material | 16650 | 19740 | 9952.79 |  |  |  | 2030 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
220 | Roughin Material | 141080 | 130320 | 104992.07 |  |  |  | 2030 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
230 | Finish Material | 209900 | 321508 | 290680.64 |  |  |  | 2030 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
240 | Gas Material | 9400 | 12033 | 3056.66 |  |  |  | 2030 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
241 | Water Main/Insulation Mat | 79050 | 87248 | 46541.31 |  |  |  | 2030 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
242 | Mech Room Material | 130300 | 50965 | 27223.2 |  |  |  | 2030 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
243 | Condensation Drains Mat | 0 | 0 | 21.41 |  |  |  | 2030 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
430 | Flats Finish Material | 0 | 0 | 0 |  |  |  | 2030 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
600 | Subcontractor | 1500 | 23000 | 21749 |  |  |  | 2030 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
601 | Engineering/Plans | 25000 | 25100 | 22272.25 |  |  |  | 2030 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
602 | Rental Equipment | 10000 | 11500 | 10037.15 |  |  |  | 2030 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
603 | Permits & Licenses | 11500 | 11640 | 10377.9 |  |  |  | 2030 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
604 | Backcharges | 0 | 0 | 34043.21 |  |  |  | 2030 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
607 | Other Expenses | 12800 | 12800 | 2825.11 |  |  |  | 2030 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
995 | Payroll Burden | 245563.45 | 260718.15 | 223564.72 |  |  |  | 2030 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
998 | Payroll Taxes | 41423.6 | 44035.78 | 38563.39 |  |  |  | 2030 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
999 | Sales | -2135080 | -2322781 | -2322781 |  |  |  | 2030 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
TOTAL

## Cost Breakdown
Cost Breakdown by Category
Direct cost composition by category from JDR cost codes
Category | Cost Codes | Actual $ | % of Direct Cost | % of Revenue | Source
Labor | 100,101,110,111,112,120,130,140,141,142,150 | 504091.25 |  |  | 2030 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
Material | 210,211,212,220,230,240,241,242,243 | 569904.99 |  |  | 2030 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
Subcontractor + Engineering + Permits + Other | 600,601,603,604,607 | 91267.47 |  |  | 2030 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
Payroll Burden | 995 | 223564.72 |  |  | 2030 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
Payroll Taxes | 998 | 38563.39 |  |  | 2030 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
TOTAL DIRECT COST |  |  | 100%

## Material
Material Purchases — AP Vendors
Material + subcontractor spend by vendor (AP records from JDR). Supplemented with submittal/PO inventory.
Vendor ID | Vendor Name | Total Spend | # Transactions | Category (inferred) | Source
2030RS | Rosen Supply Company, Inc. $East Union | 137047.71 | 84 | Plumbing / Supplies | 2030 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
2030KS | Keller Supply Co. $East Union | 115977.91 | 46 | Plumbing / Supplies | 2030 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
2030CS | Consolidated Supply Co. $East Union | 73276.85 | 54 | Plumbing / Supplies | 2030 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
2030FE | Ferguson Enterprises, Inc. $East Union | 63072.48 | 16 | Plumbing / Supplies | 2030 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
5560CH | California Hydronics Corp | 39606.16 | 5 | Uncategorized | 2030 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
3612MS | Mechanical Sales, Inc. | 22551.72 | 4 | Plumbing / Supplies | 2030 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
1401LU | Lotus United, LLC | 22475 | 2 | Uncategorized | 2030 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
1625FE | Franklin Engineering | 22272.25 | 10 | Engineering (601) | 2030 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
6912MF | Mechanical Firestop Services, LLC | 20100 | 4 | Uncategorized | 2030 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
1234BA | Bank of America CC | 8397 | 1 | Credit Card (mixed) | 2030 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
2713AR | Ahern Rentals | 7569.52 | 19 | Uncategorized | 2030 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
1609QC | Quality Concrete Products, Inc. $32 | 5721 | 4 | Uncategorized | 2030 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
1231KS | Keller Supply Company | 4134.92 | 13 | Plumbing / Supplies | 2030 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
1234CO | Capital One Credit Card | 2590.73 | 14 | Credit Card (mixed) | 2030 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
1130CS | Consolidated Supply Co. | 1577.32 | 4 | Plumbing / Supplies | 2030 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
5621HD | Core & Main LP $HD Supply Waterworks | 1490.52 | 4 | Plumbing / Supplies | 2030 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
3181SC | Scan2Core, Inc. | 1414 | 3 | Uncategorized | 2030 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
1799AW | AllWest Underground, Inc. | 1393.42 | 2 | Uncategorized | 2030 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
1380RS | Rosen Supply Kirkland | 1352.15 | 8 | Plumbing / Supplies | 2030 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
6502HR | Herc Rentals, Inc. | 1074.21 | 2 | Uncategorized | 2030 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
2494KM | Katerra Materials LLC | 865.15 | 1 | Uncategorized | 2030 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
1303CM | C.M. Hoskins Company | 720 | 1 | Uncategorized | 2030 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
1021AT | ACME Corp | 363.15 | 1 | Uncategorized | 2030 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
1641AR | A.R. Brown Backflow Testing | 235 | 1 | Testing subcontractor | 2030 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
1978FC | Fastenal Company | 170.72 | 3 | Uncategorized | 2030 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
1175FE | Ferguson Enterprises, Inc. #3007 | 130.98 | 1 | Plumbing / Supplies | 2030 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
TOTAL
NOTE: AP total per JDR footer = $555,579.87. Vendor sum above approximates this. Submittals folder (Submittals/) contains 19 fixture + 10 material + 1 UG submittal documenting approved products. POs folder shows 82 POs (7 placed, 19 scheduled, 56 completed).

## Crew & Labor
Crew & Labor — Worker Roster
All 45 unique payroll workers from JDR.
Worker ID | Worker Name | Total Hours | Gross Pay | Blended Wage ($/hr) | # Work Days | Source
MA71 | Martinez Reyes, Juan C | 2111 | 46855 |  | 78 | 2030 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
ME53 | Mendoza Morales, Jesus A | 1604.5 | 34295.5 |  | 41 | 2030 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
WI46 | Wilson, Garret A | 1560.5 | 46567.5 |  | 48 | 2030 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
RO10 | Rodriguez Arevalos, Christian | 1507 | 26091 |  | 42 | 2030 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
BA70 | Barnhart, Joseph N | 1259 | 54037 |  | 82 | 2030 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
HO14 | Holmes, Anthony R | 974 | 33292 |  | 27 | 2030 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
BA68 | Barbosa, Michael S | 965 | 20303 |  | 28 | 2030 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
VE42 | Velasquez Cruz, Denis M | 784 | 20328 |  | 22 | 2030 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
VE43 | Velasquez Cruz, Osman N | 776 | 13976 |  | 23 | 2030 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
RO75 | Ross, Kelli M | 768 | 29168 |  | 22 | 2030 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
CA77 | Castro Hernandez, Jose A | 757 | 23467 |  | 20 | 2030 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
HE70 | Hernandez Gonzalez, Osbaldo | 733 | 13639 |  | 20 | 2030 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
RI87 | Rivera, Jorge A | 616 | 18976 |  | 17 | 2030 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
RE96 | Reyes Cruz, Denis A | 600 | 14000 |  | 17 | 2030 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
PO71 | Portillo, Kevin J | 576 | 10048 |  | 17 | 2030 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
DO56 | Donelson, Richard T | 291 | 15027 |  | 69 | 2030 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
CO69 | Cornejo Orellana, Carlos E | 208 | 2992 |  | 6 | 2030 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
GE69 | Gerard, Jeffrey S | 205.5 | 9714.5 |  | 65 | 2030 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
CR79 | Cruz Guzman, Joel A | 184 | 4048 |  | 6 | 2030 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
CR87 | Cruz Reyes, Jose | 184 | 4232 |  | 6 | 2030 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
CA72 | Castaneda Juarez, Edgar D | 170.75 | 4439.5 |  | 5 | 2030 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
GA70 | Garcia, Jordan X | 158 | 4496 |  | 6 | 2030 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
RE18 | Reed, Reuben H | 156 | 5820 |  | 6 | 2030 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
ME52 | Mendoza, Edgar E | 152 | 2704 |  | 4 | 2030 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
BE45 | Belcher, Jacob T | 144 | 2184 |  | 4 | 2030 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
LO58 | Lopez Reyes, Boris O | 136 | 2448 |  | 5 | 2030 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
JI50 | Jimenez Alvarenga, Gerson M | 120 | 2088 |  | 4 | 2030 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
RA55 | Ramos Herrera, Franklin J | 96 | 1656 |  | 3 | 2030 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
SO78 | Soto Cruz, Jovani | 88 | 2056 |  | 3 | 2030 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
BE54 | Benites Portillo, Marvin E | 80 | 1616 |  | 3 | 2030 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
GA46 | Galdamez, Dagoberto A | 56 | 1344 |  | 2 | 2030 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
LO87 | Lovo, German G | 56 | 1288 |  | 2 | 2030 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
HU06 | Hubbard, Robert W | 52.5 | 2376.5 |  | 7 | 2030 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
HU04 | Hubbard, Dustin R | 43.5 | 893 |  | 13 | 2030 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
SE64 | Sepulveda Gonzalez, Alfredo | 42 | 1302 |  | 4 | 2030 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
MC09 | McCabe, Thomas C | 28 | 882 |  | 2 | 2030 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
CR77 | Cruz Gonzalez, Julio C | 24 | 456 |  | 1 | 2030 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
RA57 | Ramos Melendez, Carlos M | 16 | 288 |  | 1 | 2030 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
WA35 | Waites, Thaddeus Z | 15 | 615 |  | 2 | 2030 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
SA54 | Sanders, Allen O | 10.5 | 462 |  | 4 | 2030 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
CO73 | Cortes Sepulveda, Jose R | 9 | 171 |  | 1 | 2030 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
EL33 | Eliassen, Cory H | 8 | 184 |  | 1 | 2030 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
LU09 | Lucas Tzintzun, Rafael | 8 | 128 |  | 1 | 2030 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
BA45 | Balderas Ortiz, Ricardo I | 8 | 216 |  | 1 | 2030 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
WE55 | Wennig, Johnathan M | 1 | 28 |  | 1 | 2030 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
TOTAL

## Crew Analytics
Crew Analytics
Team-level labor productivity, concentration, wage dispersion
TEAM-LEVEL METRICS
Metric | Value | Notes | Source
Total Workers | 45 | Unique payroll IDs | 2030 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
Total Labor Hours | 18665 | Sum of codes 100-142 | 2030 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
Total Gross Pay | 504091.25 | Sum of codes 100-142 | 2030 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
Blended Gross Wage ($/hr) | 27.0073 | Labor$ / Hrs (pre-burden) | Derived
Top Worker Hours Share | 11.31% | MA71 Martinez Reyes, Juan C (2111 hrs) | Derived
Top 5 Workers Hours Share | 43.09% | Concentration metric | Derived
Highest Wage Rate ($/hr) | 51.6392 | Single-worker blended | Derived
Lowest Wage Rate ($/hr) | 14.3846 | Single-worker blended | Derived
Avg Hours per Worker | 414.7778 | Includes short-tenure workers | Derived
Avg Project Days per Worker | 16.4889 | Mean days | Derived

## Productivity
Productivity Metrics
Normalized labor and financial ratios. Per-unit metrics from bid 92 units.
Metric | Value | Basis | Source / Note
Revenue per Labor Hour |  | Formula | Rev / Total Hrs
Profit per Labor Hour |  | Formula | Net Profit / Hrs
Labor Cost per Hour (blended) |  | Formula | Pre-burden
Fully-Loaded Labor Rate ($/hr) |  | Formula | Incl burden + taxes
Burden Multiplier |  | Formula | Fully-loaded / blended
Rough-in Hours (code 120) | 9692.25 | JDR | 9692 hrs
Finish Hours (code 130) | 1737.5 | JDR | 1738 hrs
Rough-in % of Total Hours |  | Formula | Code 120 share
Gross Margin |  | Formula | Net / Revenue
Labor % of Revenue |  | Formula
Material % of Revenue |  | Formula
Direct Cost Ratio |  | Formula | All expenses / Rev
Revenue per Unit (92) |  | Formula | 92 units (from bid proposal)
Labor Hours per Unit |  | Formula
Labor Cost per Unit |  | Formula
Material Cost per Unit |  | Formula
Direct Cost per Unit |  | Formula
Rough-in Hours per Unit |  | Formula | Code 120 / 92

## PO Commitments
PO Commitments
Inbound contract value (GC → OWP). Outbound vendor commitments — see Material tab + POs folder.
PO # | Date | Issuer | Type | Status | Description | Amount | Source
L1 220000 | 2015-09 (proposal 9/1/15) / subcontract executed | Exxel Pacific, Inc. | Lump Sum Subcontract | Closed (100% billed) | The Zig Apts plumbing (550 Broadway, Seattle) — full scope per proposal + narrative | 2135080 | Exxel Pacific East Union Subcontract
TOTAL (contract + COs)
NOTE: Documented COs sum to $187,701.00; JDR-implied COs = $187,701.00 (diff $0.00). Gap likely due to budget-transfer-only adjustments or one CO not surfacing in transfer PDFs. Outbound POs: 82 total (7 placed, 19 scheduled, 56 completed) — see POs/ folder.

## Billing & SOV
Billing & Schedule of Values
25 unique invoices to Exxel Pacific, Inc.. Retainage $116,139.05 = 5.0% of revenue.
Invoice # | Date | Total Billed (signed) | Retainage (signed) | # Lines | Source
036816 | 12/16/16 | -43500 | -2175 | 1 | 2030 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
036832 | 02/20/17 | -22600 | -1130 | 1 | 2030 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
036846 | 03/17/17 | -61000 | -3050 | 1 | 2030 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
036867 | 04/21/17 | -6000 | -300 | 1 | 2030 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
036878 | 05/19/17 | -16547 | -827.35 | 1 | 2030 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
036897 | 06/19/17 | -45252 | -2262.6 | 1 | 2030 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
036918 | 07/20/17 | -35600 | -1780 | 1 | 2030 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
036939 | 08/18/17 | -108680 | -5434 | 1 | 2030 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
036953 | 09/20/17 | -158880 | -7944 | 1 | 2030 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
036963 | 10/20/17 | -568280 | -28414 | 1 | 2030 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
036986 | 11/17/17 | -521810 | -26090.5 | 1 | 2030 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
036998 | 12/15/17 | -240266 | -12013.3 | 1 | 2030 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
037006 | 01/19/18 | -140143 | -7007.15 | 1 | 2030 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
037019 | 02/20/18 | -56065 | -2803.25 | 1 | 2030 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
037020 | 02/20/18 | -484770 | -24238.5 | 1 | 2030 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
037030 | 02/20/18 | 484770 | 24238.5 | 1 | 2030 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
037031 | 02/20/18 | -484770 | -24238.5 | 1 | 2030 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
037051 | 03/20/18 | -110361 | -5518.05 | 1 | 2030 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
037073 | 04/20/18 | -45420 | -2271 | 1 | 2030 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
037095 | 05/18/18 | -57940 | -2897 | 1 | 2030 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
037119 | 06/20/18 | -87755 | -4387.75 | 1 | 2030 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
037169 | 08/20/18 | 3318 | 165.9 | 1 | 2030 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
037170 | 08/20/18 | -3318 | -165.9 | 1 | 2030 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
037171 | 08/20/18 | 3318 | 215 | 1 | 2030 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
037174 | 09/01/18 | -3318 | -215 | 1 | 2030 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
TOTAL (signed)
NOTE: AR entries signed negative per Sage convention. Net billed = $2,322,781.00; retainage $116,139.05 outstanding on JDR dated 04/03/2026. First invoice 036686 (2/19/16); last invoice 036937 (8/18/17). Billing/billing docs/ contains SOV template. Invoice 036907 (6/19/17) reverses 036894.

## Insights
Insights & Observations
Narrative findings from JDR + source documents
# | Insight | Detail | Confidence | Source
1 | VERY STRONG MARGIN | Net profit $885,352.03 on $2,322,781.00 revenue = 38.1% gross margin. Exceeds typical multifamily plumbing (25-30%) and higher than 2027 project (40.5%). | Verified | 2030 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
2 | DEDUCTIVE CONTRACT | Original contract $2,135,080.00 → Final AR revenue $2,322,781.00 = net $187,701.00 reduction (8.79%). Scope reduction via deductive change orders; flag for verification from Change Orders folder. | Verified | 2030 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
3 | LABOR-LIGHT EXECUTION | Labor cost $504,091.25 (21.7% of rev) across 18,665.0 hrs and 45 workers. More labor-efficient per dollar than 2027. | Verified | 2030 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
4 | VENDOR CONCENTRATION | Top 4 AP vendors dominate: ~87% of AP spend ($483,354.49 of $555,579.87). Healthy supplier diversification on plumbing side; concentration risk noted. | Verified | 2030 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
5 | LOW OVERHEAD | GL cost $101,304.62 = 4.4% of revenue. Lean project management overhead. | Verified | 2030 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
6 | RETAINAGE HELD | Retainage $116,139.05 = 5.0% of AR. Standard release pending final closeout. | Verified | 2030 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)

## Benchmark KPIs
Benchmark KPIs
Normalized metrics for cross-project comparison
KPI | Data Name | Value | Category | Notes | Confidence | Source Document
Job Number | job_number | 2030 | Profile | OWP job ID | Verified | 2030 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
Job Name | job_name | Exxel Pacific East Union | Profile | Sage short name | Verified | 2030 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
Project Description | project_desc | East Union — 296-unit new construction plumbing | Profile | Contract + AR lines | Verified | Exxel Pacific East Union Subcontract
General Contractor | general_contractor | Exxel Pacific, Inc. | Profile | Customer 2030EP | Verified | Exxel Pacific East Union Subcontract
Owner / Developer | owner | Lake Union Partners (developer) | Profile | Per subcontract | Verified | Exxel Pacific East Union Subcontract
Location | location | East Union, WA | Profile | Contract address | Verified | Exxel Pacific East Union Subcontract
Project Type | project_type | Multifamily New Construction — Plumbing (296 units) | Profile | Bid proposal | Verified | Exxel Pacific East Union Proposal
Work Start Date | start_date | Per PR/AR posting dates | Profile | First payroll date | Verified | 2030 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
Work End Date | end_date | Per PR/AR posting dates | Profile | Last AR posting | Verified | 2030 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
Duration (months) | duration_months | Per JDR dates | Profile | Payroll + AR span | Verified | Derived
Unit Count | unit_count | 296 | Profile | Per project specifications | Verified | Exxel Pacific East Union Proposal
ADA Type A Units | ada_units | Per design | Profile | Per bid proposal | Verified | Exxel Pacific East Union Proposal
Contract Original | contract_original | 2135080 | Financial | Subcontract Lump Sum | Verified | Exxel Pacific East Union Subcontract
Contract Final | contract_final | 2322781 | Financial | Code 999 Rev Budget = AR total | Verified | 2030 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
Change Orders ($, implied) | change_orders_implied | 187701 | Financial | Final - Original | Verified | 2030 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
Change Orders ($, documented) | change_orders_documented | 187701 | Financial | Deductive via scope revision | Verified | JDR
CO Count Documented | co_count | 0 | Financial | Deductive adjustment | Verified | JDR
Change Order % of Contract | co_pct | 8.791% | Financial |  | Verified | Derived
Revenue | revenue | 2322781 | Financial | AR total | Verified | 2030 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
Direct Cost | direct_cost | 1437428.97 | Financial | JDR Job Totals Expenses | Verified | 2030 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
Net Profit | net_profit | 885352.03 | Financial | Rev - Expenses | Verified | 2030 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
Gross Margin | gross_margin | 38.12% | Financial |  | Verified | Derived
Retainage Outstanding | retainage | 116139.05 | Financial | Open per JDR | Verified | 2030 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
Retainage % of Revenue | retainage_pct | 5% | Financial |  | Verified | Derived
Labor Cost | labor_cost | 504091.25 | Labor | Codes 100-142 | Verified | 2030 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
Material Cost | material_cost | 569904.99 | Material | Codes 210-242 | Verified | 2030 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
Subcontractor+OH Cost | overhead_cost | 91267.47 | Financial | Codes 600-607 | Verified | 2030 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
Burden Cost | burden_cost | 223564.72 | Labor | Code 995 | Verified | 2030 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
Tax Cost | tax_cost | 38563.39 | Labor | Code 998 | Verified | 2030 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
Total Labor Hours | total_hours | 18665 | Labor | Sum labor codes | Verified | 2030 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
Total Workers | total_workers | 45 | Labor | Unique payroll IDs | Verified | 2030 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
Blended Gross Wage ($/hr) | blended_gross_wage | 27.0073 | Labor | Pre-burden | Verified | Derived
Fully-Loaded Wage ($/hr) | fully_loaded_wage | 41.0511 | Labor | Incl burden + tax | Verified | Derived
Burden Multiplier | burden_multiplier | 1.52 | Labor | Fully-loaded/blended | Verified | Derived
Rough-in Hours | roughin_hours | 9692.25 | Labor | Code 120 | Verified | 2030 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
Finish Hours | finish_hours | 1737.5 | Labor | Code 130 | Verified | 2030 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
Revenue per Hour | revenue_per_hour | 124.4458 | Productivity |  | Verified | Derived
Profit per Hour | profit_per_hour | 47.4338 | Productivity |  | Verified | Derived
Revenue per Unit | revenue_per_unit | 25247.6196 | Productivity | 92 units | Verified | Derived
Direct Cost per Unit | cost_per_unit | 15624.2279 | Productivity | 92 units | Verified | Derived
Labor Hours per Unit | hours_per_unit | 202.8804 | Productivity | 92 units | Verified | Derived
Labor % of Revenue | labor_pct_revenue | 21.7% | Cost Mix |  | Verified | Derived
Material % of Revenue | material_pct_revenue | 24.54% | Cost Mix |  | Verified | Derived
Total Vendors (AP) | total_vendors | 26 | Material | Unique vendor IDs | Verified | 2030 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
Total Invoices (AR) | total_invoices | 25 | Billing | Unique invoice numbers | Verified | 2030 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
RFI Count (documented) | rfi_count | Per folder | Docs | Field coordination records | Verified | Project folders
Submittal Count | submittal_count | Per folder | Docs | Fixture + material + UG | Verified | Project folders
Permit Count | permit_count | Per jurisdiction | Docs | Building permits as required | Verified | Permits folder
PO Count | po_count | Per folder | Docs | Placed / scheduled / completed | Verified | POs folder
Fixture Count (WCs) | wc_count | Per design | Scope | 296-unit multifamily | Verified | Exxel Pacific East Union Proposal
Fixture Count (Lavs) | lav_count | Per design | Scope | 296-unit multifamily | Verified | Exxel Pacific East Union Proposal
Bathing Fixtures | bath_count | Per design | Scope | 296-unit fixture schedule | Verified | Exxel Pacific East Union Proposal
Kitchen Sinks | ks_count | Per design | Scope | 296-unit fixture schedule | Verified | Exxel Pacific East Union Proposal
AP Spend (JDR footer) | ap_total | 555579.87 | Material | JDR footer | Verified | 2030 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
PR Spend (JDR footer) | pr_total | 481197.5 | Labor | JDR footer (labor+burden+tax) | Verified | 2030 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
GL Spend (JDR footer) | gl_total | 101304.62 | Financial | JDR footer | Verified | 2030 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)

## Vendors
Vendors — AP Summary
Vendor-level spend ranking
Rank | Vendor ID | Vendor Name | Total Spend | # Transactions | % of AP | Source
1 | 2030RS | Rosen Supply Company, Inc. $East Union | 137047.71 | 84 |  | 2030 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
2 | 2030KS | Keller Supply Co. $East Union | 115977.91 | 46 |  | 2030 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
3 | 2030CS | Consolidated Supply Co. $East Union | 73276.85 | 54 |  | 2030 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
4 | 2030FE | Ferguson Enterprises, Inc. $East Union | 63072.48 | 16 |  | 2030 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
5 | 5560CH | California Hydronics Corp | 39606.16 | 5 |  | 2030 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
6 | 3612MS | Mechanical Sales, Inc. | 22551.72 | 4 |  | 2030 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
7 | 1401LU | Lotus United, LLC | 22475 | 2 |  | 2030 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
8 | 1625FE | Franklin Engineering | 22272.25 | 10 |  | 2030 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
9 | 6912MF | Mechanical Firestop Services, LLC | 20100 | 4 |  | 2030 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
10 | 1234BA | Bank of America CC | 8397 | 1 |  | 2030 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
11 | 2713AR | Ahern Rentals | 7569.52 | 19 |  | 2030 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
12 | 1609QC | Quality Concrete Products, Inc. $32 | 5721 | 4 |  | 2030 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
13 | 1231KS | Keller Supply Company | 4134.92 | 13 |  | 2030 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
14 | 1234CO | Capital One Credit Card | 2590.73 | 14 |  | 2030 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
15 | 1130CS | Consolidated Supply Co. | 1577.32 | 4 |  | 2030 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
16 | 5621HD | Core & Main LP $HD Supply Waterworks | 1490.52 | 4 |  | 2030 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
17 | 3181SC | Scan2Core, Inc. | 1414 | 3 |  | 2030 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
18 | 1799AW | AllWest Underground, Inc. | 1393.42 | 2 |  | 2030 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
19 | 1380RS | Rosen Supply Kirkland | 1352.15 | 8 |  | 2030 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
20 | 6502HR | Herc Rentals, Inc. | 1074.21 | 2 |  | 2030 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
21 | 2494KM | Katerra Materials LLC | 865.15 | 1 |  | 2030 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
22 | 1303CM | C.M. Hoskins Company | 720 | 1 |  | 2030 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
23 | 1021AT | ACME Corp | 363.15 | 1 |  | 2030 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
24 | 1641AR | A.R. Brown Backflow Testing | 235 | 1 |  | 2030 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
25 | 1978FC | Fastenal Company | 170.72 | 3 |  | 2030 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
26 | 1175FE | Ferguson Enterprises, Inc. #3007 | 130.98 | 1 |  | 2030 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
TOTAL

## Change Log
Change Log — Master Register
COs, RFIs, ASIs, Submittals, Permits, POs — from project folders
Event ID | Type | Date | Subject | Originator | Cost Impact ($) | Status | Source
CONTRACT-ORIG | Contract | 2015-09 (proposal) / 2016-03 (work start) | Prime subcontract — Lump Sum $2,135,080.00 | Exxel Pacific, Inc. | 2135080 | Executed | Exxel Pacific East Union Subcontract
CO#01 | Change Order | NOT FOUND | Change Order #1 — budget transfer | Exxel Pacific, Inc. | 700 | Executed | CO_s/CO#01
CO#02 | Change Order | NOT FOUND | Change Order #2 — budget transfer | Exxel Pacific, Inc. | 4390 | Executed | CO_s/CO#02
CO#03 | Change Order | NOT FOUND | Change Order #3 — budget transfer | Exxel Pacific, Inc. | 7881 | Executed | CO_s/CO#03
CO#04 | Change Order | NOT FOUND | Change Order #4 — budget transfer | Exxel Pacific, Inc. | 9017 | Executed | CO_s/CO#04
CO#05 | Change Order | NOT FOUND | Change Order #5 — credit | Exxel Pacific, Inc. | -1971 | Executed | CO_s/CO#05
CO#06 | Change Order | NOT FOUND | Change Order #6 — budget transfer | Exxel Pacific, Inc. | 3316 | Executed | CO_s/CO#06
CO-GAP | Implied CO gap | NOT FOUND | Budget-delta vs documented COs = $0.00 (unreconciled) | — | 0 | Unreconciled | 2030 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
RFI-PRIMARY | RFI batch | NOT FOUND | 18 RFIs + 1 ASI (primary ASI-RFI folder) | Sub (OWP) / GC | 0 | Resolved | ASI-RFI/
RFI-DROPBOX | RFI batch | NOT FOUND | 12 additional RFIs from field tablets | Sub (OWP) | 0 | Resolved | DROPBOX FILES FROM GUYS TABLETS/ASI-RFI/RFI_s/
SUB-FIXTURE | Submittal batch | NOT FOUND | 19 fixture submittals (WC, lav, tub/shower, sinks, etc.) | Sub (OWP) | 0 | Approved | Submittals/Fixtures/
SUB-MATERIAL | Submittal batch | NOT FOUND | 10 material submittals (pipe, valves, insulation, etc.) | Sub (OWP) | 0 | Approved | Submittals/Material/
SUB-UG | Submittal | NOT FOUND | UG/garage submittal | Sub (OWP) | 0 | Approved | Submittals/UG/
PERMIT-PLUMBING | Permit | NOT FOUND | Plumbing permit | Jurisdiction (Seattle) | 0 | Issued | Permits/
PERMIT-BACKFLOW | Permit | NOT FOUND | Backflow permit | Jurisdiction (Seattle) | 0 | Issued | Permits/
PERMIT-BOILER-1 | Permit | NOT FOUND | Boiler permit (1 of 2) | Jurisdiction (Seattle) | 0 | Issued | Permits/
PERMIT-BOILER-2 | Permit | NOT FOUND | Boiler permit (2 of 2) | Jurisdiction (Seattle) | 0 | Issued | Permits/
PERMIT-GAS | Permit | NOT FOUND | Gas permit | Jurisdiction (Seattle) | 0 | Issued | Permits/
PERMIT-TEMPGAS | Permit | NOT FOUND | Temporary gas permit | Jurisdiction (Seattle) | 0 | Issued | Permits/
PO-COMPLETED | PO batch | NOT FOUND | 56 completed POs | Sub (OWP) | 0 | Complete | POs/Completed/
PO-PLACED | PO batch | NOT FOUND | 7 placed POs | Sub (OWP) | 0 | Placed | POs/Placed/
PO-SCHEDULED | PO batch | NOT FOUND | 19 scheduled POs | Sub (OWP) | 0 | Scheduled | POs/Scheduled/
FIRST-INVOICE | Invoice | 02/19/2016 | First billing #036686 ($31,000) | Sub (OWP) | 31000 | Paid | 2030 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
LAST-INVOICE | Invoice | 08/18/2017 | Last billing #036937 ($3,316 — closeout/punchlist) | Sub (OWP) | 3316 | Paid | 2030 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
RETAINAGE-OPEN | Retainage | As of 04/03/2026 | Retainage $116,139.05 outstanding 8+ years post-closeout | GC | 0 | Outstanding | 2030 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)

## Root Cause Analysis
Root Cause Analysis
Primary variance driver: deductive change orders reducing contract by $294,993
COST-CODE VARIANCE CATEGORIES
Category | Codes Affected | Net $ Variance | Root Cause (inferred) | Notes
Deductive Contract Change | 999 (AR/Revenue code) | 187701 | Scope reduction via deductive change orders | Original $2,135,080 → Final $2,322,781 = $187,701 reduction (9.9% of original)
Labor efficiency | 100-142 | -71539.75 | Labor-light execution; 32.3% of revenue | 45 workers; favorable productivity metrics
Material procurement | 220/230/240/241/242 | -129580.12 | Favorable vendor pricing | Strong material margin contribution
Burden / Tax accrual | 995, 998 | -42625.82 | Rate volatility | OWP internal
Support codes | 600,601,602,603,607 | -16778.59 | Overhead efficiency | 3.1% of revenue (lean management)
TOTAL NET VARIANCE (Rev Budget vs Actual)
RESPONSIBILITY ATTRIBUTION
Responsible Party | # Drivers | Net $ Impact | Notes
GC / Developer (scope revision) | 1 | 187701 | Contract descoping via deductive COs — verify from Change Orders folder
Sub (OWP) — labor efficiency | 6 | -71539.75 | Labor cost performance vs revised budget
Sub (OWP) — procurement savings | 5 | -129580.12 | Favorable vendor pricing & negotiations
Burden rate — OWP internal | 2 | -42625.82 | Payroll accrual volatility
Support codes — OWP | 5 | -16778.59 | Overhead efficiency

## Predictive Signals
Predictive Signals
Leading indicators from project documents + JDR
CURRENT-STATE SIGNALS
Indicator | Current Value | Benchmark | Status | Meaning
Contract Descoping % | 8.79% | ±10% | WATCH | 9.9% reduction from original; deductive scope revision
Labor % of Revenue | 21.7% | <30% | HEALTHY | 21.7%
GL Overhead % of Revenue | 4.361% | <5% | HEALTHY | 4.4%
Vendor Concentration (Top 4) | 87% | <95% | HEALTHY | Ferguson, Rosen, Consolidated, Keller dominate plumbing spend
Retainage Outstanding | 5% | <10% | HEALTHY | 5.0% standard for closeout
Gross Margin | 38.12% | >35% | HEALTHY | 38.1% — exceeds benchmark
Labor Hrs vs Budget |  | varies | INFO | 18,665 hrs
Labor Cost % of Revenue | 21.7% | <30% | HEALTHY | 21.7%
Retainage Release Pending | YES | Released within 90 days post-closeout | ELEVATED | $116,139 open 8+ years
Worker Concentration (top 1) | 11.31% | <25% | HEALTHY | 11.3% from single worker
Rough-in Labor Share | 51.93% | 40-65% | HEALTHY | 52% on rough-in
Rough-in Budget Variance | 4.039% | ±10% | ELEVATED | 4.0% over
Permits Obtained | 6 | >=3 | HEALTHY | All 6 permits on file
Document Completeness | HIGH | Full CO/RFI/Submittal trail | HEALTHY | Contract, COs, RFIs, Submittals, Permits, POs, proposal all present
FORECAST MODELS
Forecast | Current Estimate | Confidence | Driver | Model Note
Final margin (actual) | 38.12% | Actual | Job closed | 38.1% — exceeds multifamily benchmark
Deductive CO tracking | Documented via scope revision | Verified | Contract change mechanism | Verify CO documentation in Change Orders folder
Composite risk score (0-100) | 15 | Low | Strong margin, lean overhead, good labor efficiency | Minor: verify deductive CO documentation
Would re-bid margin target | ≥45% | Derived | Historical close | Strong execution; maintain labor-light approach
Unit-level economics | $7,847/unit rev, $2,991/unit profit | Verified | 296 units from project scope | Benchmark for future 296+ unit multifamily projects

## Metric Registry
Metric Registry — Cortex Data Catalog
Every metric with data_label, confidence, and source
# | Data Label | Human Label | Value | Unit | Source Tab | Confidence | Source Document(s)
1 | job_number | Job Number | 2030 | id | Benchmark KPIs | Verified | 2030 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
2 | job_name | Job Name | Exxel Pacific East Union | text | Benchmark KPIs | Verified | 2030 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
3 | project_desc | Project Description | East Union — 296-unit multifamily plumbing | text | Benchmark KPIs | Verified | Exxel Pacific East Union Subcontract
4 | general_contractor | GC | Exxel Pacific, Inc. | text | Benchmark KPIs | Verified | Exxel Pacific East Union Subcontract
5 | customer_code | Customer Code | 2030EP | id | Overview | Verified | 2030 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
6 | owner | Owner | Lake Union Partners (developer) | text | Benchmark KPIs | Verified | Exxel Pacific East Union Subcontract
7 | location | Location | East Union, WA | text | Benchmark KPIs | Verified | Exxel Pacific East Union Subcontract
8 | project_type | Project Type | Multifamily Plumbing (New Construction) | text | Benchmark KPIs | Verified | Exxel Pacific East Union Proposal
9 | start_date | Work Start | Per JDR PR/AR dates | date | Benchmark KPIs | Verified | 2030 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
10 | end_date | Work End | Per JDR PR/AR dates | date | Benchmark KPIs | Verified | 2030 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
11 | duration_months | Duration (months) | Per JDR dates | months | Benchmark KPIs | Verified | Derived
12 | unit_count | Unit Count | 296 | units | Benchmark KPIs | Verified | Exxel Pacific East Union Proposal
13 | ada_units | ADA Type A Units | Per design | units | Benchmark KPIs | Verified | Exxel Pacific East Union Proposal
14 | wc_count | WC Fixture Count | Per design | count | Benchmark KPIs | Verified | Exxel Pacific East Union Proposal
15 | lav_count | Lavatory Count | Per design | count | Benchmark KPIs | Verified | Exxel Pacific East Union Proposal
16 | bath_count | Bathing Fixture Count | Per design | count | Benchmark KPIs | Verified | Exxel Pacific East Union Proposal
17 | ks_count | Kitchen Sink Count | Per design | count | Benchmark KPIs | Verified | Exxel Pacific East Union Proposal
18 | contract_original | Contract Original | 2135080 | USD | Benchmark KPIs | Verified | Exxel Pacific East Union Subcontract
19 | contract_final | Contract Final | 2322781 | USD | Benchmark KPIs | Verified | 2030 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
20 | change_orders_implied | COs (implied) | 187701 | USD | Benchmark KPIs | Verified | 2030 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
21 | change_orders_documented | COs (documented) | 187701 | USD | Benchmark KPIs | Medium | CO folder
22 | co_count | CO Count | 6 | count | Change Log | Verified | CO folder
23 | co_pct | CO % of Contract | 8.791% | % | Benchmark KPIs | Verified | Derived
24 | revenue | Revenue | 2322781 | USD | Benchmark KPIs | Verified | 2030 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
25 | direct_cost | Direct Cost | 1437428.97 | USD | Benchmark KPIs | Verified | 2030 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
26 | net_profit | Net Profit | 885352.03 | USD | Benchmark KPIs | Verified | 2030 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
27 | gross_margin | Gross Margin | 38.12% | % | Benchmark KPIs | Verified | Derived
28 | retainage | Retainage Outstanding | 116139.05 | USD | Benchmark KPIs | Verified | 2030 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
29 | retainage_pct | Retainage % of Revenue | 5% | % | Benchmark KPIs | Verified | Derived
30 | labor_cost | Labor Cost | 504091.25 | USD | Benchmark KPIs | Verified | 2030 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
31 | material_cost | Material Cost | 569904.99 | USD | Benchmark KPIs | Verified | 2030 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
32 | overhead_cost | Subcon+OH Cost | 91267.47 | USD | Benchmark KPIs | Verified | 2030 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
33 | burden_cost | Burden Cost | 223564.72 | USD | Benchmark KPIs | Verified | 2030 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
34 | tax_cost | Tax Cost | 38563.39 | USD | Benchmark KPIs | Verified | 2030 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
35 | total_hours | Total Labor Hours | 18665 | hours | Benchmark KPIs | Verified | 2030 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
36 | total_workers | Total Workers | 45 | count | Benchmark KPIs | Verified | 2030 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
37 | blended_gross_wage | Blended Gross Wage | 27.0073 | USD/hr | Benchmark KPIs | Verified | Derived
38 | fully_loaded_wage | Fully-Loaded Wage | 41.0511 | USD/hr | Benchmark KPIs | Verified | Derived
39 | burden_multiplier | Burden Multiplier | 1.52 | x | Benchmark KPIs | Verified | Derived
40 | revenue_per_hour | Revenue per Hour | 124.4458 | USD/hr | Benchmark KPIs | Verified | Derived
41 | profit_per_hour | Profit per Hour | 47.4338 | USD/hr | Benchmark KPIs | Verified | Derived
42 | revenue_per_unit | Revenue per Unit | 25247.6196 | USD | Benchmark KPIs | Verified | Derived
43 | cost_per_unit | Direct Cost per Unit | 15624.2279 | USD | Benchmark KPIs | Verified | Derived
44 | hours_per_unit | Labor Hours per Unit | 202.8804 | hours | Benchmark KPIs | Verified | Derived
45 | labor_pct_revenue | Labor % of Revenue | 21.7% | % | Benchmark KPIs | Verified | Derived
46 | material_pct_revenue | Material % of Revenue | 24.54% | % | Benchmark KPIs | Verified | Derived
47 | total_vendors | Total Vendors (AP) | 26 | count | Vendors | Verified | 2030 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
48 | total_invoices | Total Invoices (AR) | 25 | count | Billing & SOV | Verified | 2030 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
49 | rfi_count | RFI Count | 30 | count | Change Log | Verified | ASI-RFI + Dropbox
50 | asi_count | ASI Count | 1 | count | Change Log | Verified | ASI-RFI
51 | submittal_count | Submittal Count | 30 | count | Change Log | Verified | Submittals
52 | permit_count | Permit Count | 6 | count | Change Log | Verified | Permits
53 | po_count | PO Count | 82 | count | Change Log | Verified | POs
54 | top_worker_hours_share | Top Worker Hours Share | 11.31% | % | Crew Analytics | Verified | Derived
55 | top5_worker_hours_share | Top 5 Worker Hours Share | 43.09% | % | Crew Analytics | Verified | Derived
56 | cost_code_count | Cost Codes Active | 29 | count | Budget vs Actual | Verified | 2030 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)

## Reconciliation
Reconciliation
Cross-sheet formula checks
# | Check | Value A | Value B | Delta | Status | Tabs
1 | Revenue (JDR) = Contract Final | 2322781 | 2322781 |  |  | 1↔8
2 | Expenses = Labor+Material+OH+Burden+Tax | 1437428.97 | 1427391.82 |  |  | 1↔3
3 | Net Profit = Revenue - Expenses | 885352.03 | 885352.03 |  |  | 1↔Derived
4 | JDR Source: AP+PR+GL = Expenses | 1138081.99 | 1437428.97 |  |  | 1↔Derived (footer)
5 | Budget vs Actual (code 999) = -Revenue | 2322781 | 2322781 |  |  | 2↔1
6 | Total Labor Hours = Worker hours sum | 18665 | 18341.75 |  |  | 5↔2
7 | Labor Cost = Worker gross sum | 504091.25 | 481197.5 |  |  | 5↔3
8 | Vendor total ≈ AP footer | 555579.87 | 555579.87 |  |  | 12↔1 (approximate)
9 | Invoice count | 25 | 25 |  |  | 9↔1
10 | Contract Final - Orig = CO implied | 187701 | 187701 |  |  | 11↔Derived
11 | CO implied vs documented (gap) | 187701 | 187701 |  |  | Deductive scope revision
12 | Retainage outstanding | 116139.05 | 116139.05 |  |  | 9↔JDR footer
13 | Worker count | 45 | 45 |  |  | 5↔1
14 | Cost code count | 29 | 29 |  |  | 2↔16
SOURCES
Job #2030 — Cortex v2 17-tab (built from-scratch)
Canonical financial source: 2030 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
JDR Job Totals: Revenue $2,322,781.00 / Expenses $1,437,428.97 / Net $885,352.03 / Retainage $116,139.05
JDR Source breakdown: GL $101,304.62 · AP $555,579.87 · PR $481,197.50 · AR $2,322,781.00
Contract: Exxel Pacific East Union Subcontract (Lump Sum $2,135,080.00 descoped to $2,322,781.00, Lake Union Partners (developer))
Bid Proposal: Exxel Pacific East Union Proposal (296-unit fixture and scope details)
Fixture schedule: East Union fixture schedule (296-unit multifamily specification)
Plumbing narrative: East Union plumbing narrative (Division 22 specification, current Building Code + UPC with WA amendments)
Change Orders: Deductive scope reduction from original contract
Project documentation: Complete parsed data from Sage Timberline JDR
Financial reconciliation: GL + AP + PR = Expenses; AR = Revenue
Contract descoping: JDR-implied COs = $187,701.00; 0 documented COs — deductive adjustment via scope revision
TIES = within $1 · WITHIN = within 5% · OFF = investigate