## Overview
Job #2031 · Exxel Pacific Issaquah Gateway
Cortex JCR Cortex v2 • Exxel Pacific, Inc. (customer 2031EP) • Issaquah Gateway, WA • Owner: Katerra / Exxel Pacific
PROJECT OVERVIEW
Project Job # | 2031 |  | 2030 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages) header
Project Name (Sage) | Exxel Pacific Issaquah Gateway |  | 2030 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages) header
Project Description | Issaquah Gateway — 296-unit new construction plumbing |  | Exxel Pacific Issaquah Gateway Subcontract / AR line descriptions
General Contractor | Exxel Pacific, Inc. |  | Exxel Pacific Issaquah Gateway Subcontract
Customer Code (Sage) | 2031EP |  | 2030 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
Owner / Developer | Katerra / Exxel Pacific |  | Exxel Pacific Issaquah Gateway Subcontract
Jobsite Location | Issaquah Gateway, WA |  | Exxel Pacific Issaquah Gateway Subcontract
Contract / PO Document | Exxel Pacific Issaquah Gateway Subcontract |  | Lump Sum subcontract
Plans / Specifications | Issaquah Gateway plumbing narrative (Div 22 plumbing narrative) + fixture schedule + proposal |  | Folder scan
Fixture Schedule | Issaquah Gateway fixture schedule (fixture schedule for 296-unit multifamily) |  | Referenced
Bid Proposal | Exxel Pacific Issaquah Gateway Proposal |  | Detailed scope and fixture quantities
Contract Type | Lump Sum |  | Exxel Pacific Issaquah Gateway Subcontract
Work Period | Per PR/AR posting dates in JDR |  | 2030 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
Total Unique Documents Reviewed | 1924 |  | File inventory across owp-2031/
CONTRACT VALUE |  | NET PROFIT | DIRECT COST | LABOR HOURS
5187754 |  | 2760345.77 | 2427408.23 | 52168.25
Original $5,051,600.00 + $136,154.00 COs (2.70%) |  | 53.2% margin | 46.8% of revenue | 72 workers
SCOPE OF WORK (from contract + proposal)
Full plumbing installation: underground, rough-in, finish, gas piping, water mains, insulation, mechanical room, and warranty.
296-unit multifamily new construction at Issaquah Gateway, WA.
5 levels above ground, 1 level below grade (per Job Info).
Comprehensive fixture schedule with standard and ADA-compliant units.
Spec compliance: Current Building Code + UPC with Washington state amendments.
SOURCES
Canonical financial source: 2030 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
Job totals (JDR footer): Revenue $5,187,754.00 / Expenses $2,427,408.23 / Net $2,760,345.77 / Retainage $259,387.70
Source breakdown: GL $79,204.72 · AP $1,072,286.18 · PR $1,237,777.26 · AR $5,187,754.00
Contract: Exxel Pacific Issaquah Gateway Subcontract (Lump Sum $5,051,600.00, descoped to $5,187,754.00)
Proposal: Exxel Pacific Issaquah Gateway Proposal
Fixture schedule: Issaquah Gateway fixture schedule
Plumbing narrative: Issaquah Gateway plumbing narrative
Change Orders: Deductive scope changes; net contract reduction ${CO_TOTAL_IMPLIED:,.2f}
PROJECT TEAM (OWP Job Info)
Role | Status | Name / Firm
GC | Extracted | Exxel Pacific, Inc.
GC PM | Extracted | Brett / Franklin (per project subfolders)
GC Superintendent | N/A | N/A
GC PE | N/A | N/A
Developer | Extracted | Katerra / Exxel Pacific
Architect | N/A | N/A
Structural | N/A | N/A
Acoustical | N/A | N/A
ADA Consultant | N/A | N/A
Interior Design | N/A | N/A
MEP Engineer | Extracted | Franklin Engineering

## Budget vs Actual
Budget vs Actual
All 34 cost codes from JDR. Contract $5,051,600 → $5,187,754 (COs +$136,154.00).
Cost Code | Description | Original Budget | Revised Budget | Actual | Variance | % of Revised | Hours | Source
100 | Supervision | 57900 | 59438 | 21845.5 |  |  | 459 | 2030 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
101 | Takeoff & Purchase Labor | 79800 | 85062 | 32080.5 |  |  | 661.5 | 2030 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
110 | Underground Labor | 34660 | 35728 | 5913 |  |  | 238.5 | 2030 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
111 | Garage Labor | 38740 | 38740 | 62078.5 |  |  | 2482 | 2030 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
112 | Canout Labor | 9310 | 9310 | 11258.5 |  |  | 380 | 2030 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
120 | Roughin Labor | 239070 | 261460 | 289348.75 |  |  | 12464.75 | 2030 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
130 | Finish Labor | 62435 | 64440 | 69830.75 |  |  | 2669.5 | 2030 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
140 | Gas Labor | 8800 | 9370 | 6952.5 |  |  | 260.5 | 2030 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
141 | Water Main/Insulation Lab | 52870 | 57700 | 31378.38 |  |  | 1450.25 | 2030 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
142 | Mech Room Labor | 23440 | 27517 | 32815 |  |  | 920 | 2030 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
143 | Condensation Drains Labor | 0 | 0 | 1419 |  |  | 37 | 2030 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
210 | Underground Material | 38085 | 40845 | 10306.12 |  |  |  | 2030 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
211 | Garage Material | 30580 | 30580 | 14259.91 |  |  |  | 2030 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
212 | Canout Material | 9310 | 9310 | 7891.24 |  |  |  | 2030 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
220 | Roughin Material | 142470 | 145264 | 90966.27 |  |  |  | 2030 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
230 | Finish Material | 264020 | 230010 | 268692.84 |  |  |  | 2030 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
240 | Gas Material | 10400 | 10930 | 5822.71 |  |  |  | 2030 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
241 | Water Main/Insulation Mat | 59980 | 62068 | 48502.22 |  |  |  | 2030 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
242 | Mech Room Material | 102264 | 113823 | 38991.48 |  |  |  | 2030 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
243 | Condensation Drains Mat | 0 | 0 | 6.64 |  |  |  | 2030 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
310 | Flats Underground Labor | 143266 | 138337 | 101967.5 |  |  | 4229.5 | 2030 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
320 | Flats Roughin Labor | 423275 | 449230 | 452849.38 |  |  | 21198.75 | 2030 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
330 | Flats Finish Labor | 117750 | 118330 | 118040 |  |  | 4717 | 2030 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
410 | Flats Underground Mat | 58800 | 37808 | 50431.67 |  |  |  | 2030 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
420 | Flats Roughin Material | 259245 | 274177 | 200867.48 |  |  |  | 2030 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
430 | Flats Finish Material | 460418 | 470355 | 373687.67 |  |  |  | 2030 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
600 | Subcontractor | 0 | 58006 | 65165 |  |  |  | 2030 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
601 | Engineering/Plans | 56720 | 56720 | 3927.4 |  |  |  | 2030 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
602 | Rental Equipment | 8060 | 6541 | 5415.52 |  |  |  | 2030 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
603 | Permits & Licenses | 0 | 2327 | 1959.3 |  |  |  | 2030 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
607 | Other Expenses | 9900 | 9900 | 2737.5 |  |  |  | 2030 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
995 | Payroll Burden | 0 | 0 | 0 |  |  |  | 2030 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
998 | Payroll Taxes | 0 | 0 | 0 |  |  |  | 2030 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
999 | Sales | -5051600 | -5187754 | -5187754 |  |  |  | 2030 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
TOTAL

## Cost Breakdown
Cost Breakdown by Category
Direct cost composition by category from JDR cost codes
Category | Cost Codes | Actual $ | % of Direct Cost | % of Revenue | Source
Labor | 100,101,110,111,112,120,130,140,141,142,143,310,320,330 | 1237777.26 |  |  | 2030 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
Material | 210,211,212,220,230,240,241,242,243,410,420,430 | 1110426.25 |  |  | 2030 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
Subcontractor + Engineering + Permits + Other | 600,601,602,603,607 | 79204.72 |  |  | 2030 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
Payroll Burden | 995 | 0 |  |  | 2030 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
Payroll Taxes | 998 | 0 |  |  | 2030 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
TOTAL DIRECT COST |  |  | 100%

## Material
Material Purchases — AP Vendors
Material + subcontractor spend by vendor (AP records from JDR). Supplemented with submittal/PO inventory.
Vendor ID | Vendor Name | Total Spend | # Transactions | Category (inferred) | Source
2031RS | Rosen Supply Company, Inc. $Gateway | 447211.94 | 294 | Plumbing / Supplies | 2030 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
2031CS | Consolidated Supply Co. $Iss Gateway | 166661.73 | 104 | Plumbing / Supplies | 2030 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
1380RS | Rosen Supply Kirkland | 148601.82 | 153 | Plumbing / Supplies | 2030 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
2031FE | Ferguson Enterprises, Inc. $Gateway | 59000.2 | 40 | Plumbing / Supplies | 2030 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
6912MF | Mechanical Firestop Services, LLC | 53330 | 10 | Uncategorized | 2030 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
1175FE | Ferguson Enterprises, Inc. #3007 | 45236.43 | 40 | Plumbing / Supplies | 2030 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
1231KS | Keller Supply Company | 43202.49 | 49 | Plumbing / Supplies | 2030 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
2494KM | Katerra Materials LLC | 31946.2 | 24 | Uncategorized | 2030 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
2031KS | Keller Supply Co. $Issaquah Gateway | 25025.54 | 20 | Plumbing / Supplies | 2030 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
1130CS | Consolidated Supply Co. | 13285.17 | 13 | Plumbing / Supplies | 2030 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
3181SC | Scan2Core, Inc. | 7916 | 16 | Uncategorized | 2030 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
1234CO | Capital One Credit Card | 7431.17 | 58 | Credit Card (mixed) | 2030 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
1401LU | Lotus United, LLC | 4030 | 4 | Uncategorized | 2030 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
1625FE | Franklin Engineering | 3757 | 4 | Engineering (601) | 2030 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
3612MS | Mechanical Sales, Inc. | 3272.43 | 4 | Plumbing / Supplies | 2030 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
1421RA | R.A. Brown Backflow Testing | 2124 | 10 | Testing subcontractor | 2030 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
5560CH | California Hydronics Corp | 1950 | 2 | Uncategorized | 2030 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
8056MS | Mechanical Service & Integration LLC | 1600 | 2 | Uncategorized | 2030 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
1799AW | AllWest Underground, Inc. | 1581.62 | 2 | Uncategorized | 2030 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
5621HD | Core & Main LP $HD Supply Waterworks | 1394.49 | 2 | Plumbing / Supplies | 2030 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
2713AR | Ahern Rentals | 1006.5 | 2 | Uncategorized | 2030 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
5919PW | Patchworks, Inc. | 905 | 1 | Uncategorized | 2030 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
4320MC | MAD Concrete Cutting & Coring, Inc. | 825 | 1 | Uncategorized | 2030 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
1978FC | Fastenal Company | 326.84 | 5 | Uncategorized | 2030 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
1021AT | ACME Corp | 320.31 | 2 | Uncategorized | 2030 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
2850PL | Platt $Rexel USA, Inc. | 168.31 | 2 | Uncategorized | 2030 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
1234BA | Bank of America CC | 110.99 | 1 | Credit Card (mixed) | 2030 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
1641AR | A.R. Brown Backflow Testing | 65 | 1 | Testing subcontractor | 2030 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
2030KS | Keller Supply Co. $East Union | 0 | 2 | Plumbing / Supplies | 2030 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
TOTAL
NOTE: AP total per JDR footer = $1,072,286.18. Vendor sum above approximates this. Submittals folder (Submittals/) contains 19 fixture + 10 material + 1 UG submittal documenting approved products. POs folder shows 82 POs (7 placed, 19 scheduled, 56 completed).

## Crew & Labor
Crew & Labor — Worker Roster
All 72 unique payroll workers from JDR.
Worker ID | Worker Name | Total Hours | Gross Pay | Blended Wage ($/hr) | # Work Days | Source
GA46 | Galdamez, Dagoberto A | 3140 | 70964 |  | 92 | 2030 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
EI74 | Eisenhauer, Tommy J | 3106.5 | 61781.5 |  | 88 | 2030 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
GE71 | Gerard, Mitchell J | 3046 | 85084 |  | 85 | 2030 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
QU35 | Quintanilla, Esteban R | 2985 | 112163.5 |  | 91 | 2030 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
GE70 | Gerard, Jordan E | 2890 | 74736 |  | 88 | 2030 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
BE54 | Benites Portillo, Marvin E | 2280.5 | 45266.5 |  | 68 | 2030 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
CR77 | Cruz Gonzalez, Julio C | 2238.5 | 36690.5 |  | 59 | 2030 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
CH20 | Chevez, Herson G | 1940.5 | 30105 |  | 49 | 2030 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
CO69 | Cornejo Orellana, Carlos E | 1696.5 | 27362.5 |  | 50 | 2030 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
SA54 | Sanders, Allen O | 1670 | 72120 |  | 97 | 2030 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
LO87 | Lovo, German G | 1629.5 | 34738 |  | 47 | 2030 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
PO73 | Portillo Soriano, Walter A | 1544 | 26336 |  | 41 | 2030 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
AM03 | Amaya Gonzalez, Edilberto A | 1460 | 38504 |  | 40 | 2030 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
RA55 | Ramos Herrera, Franklin J | 1432 | 26712 |  | 40 | 2030 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
JI50 | Jimenez Alvarenga, Gerson M | 1359.5 | 23934.5 |  | 37 | 2030 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
GO51 | Gomez Reyes, Edith N | 1339 | 23999 |  | 53 | 2030 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
ST02 | Stahlschmidt, John P | 1095 | 18306 |  | 33 | 2030 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
HO90 | Howey, Shawn M | 1080 | 17208 |  | 29 | 2030 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
CA77 | Castro Hernandez, Jose A | 921.5 | 23328.5 |  | 28 | 2030 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
ES09 | Escalante Escobar, Boanerge | 913 | 15010 |  | 25 | 2030 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
RA57 | Ramos Melendez, Carlos M | 818.5 | 12744 |  | 24 | 2030 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
CR87 | Cruz Reyes, Jose | 816 | 16320 |  | 22 | 2030 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
CR79 | Cruz Guzman, Joel A | 776 | 14744 |  | 22 | 2030 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
GO56 | Gonzalez Hernandez, Josue | 766 | 21071 |  | 21 | 2030 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
GE69 | Gerard, Jeffrey S | 763.5 | 35839 |  | 124 | 2030 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
RI84 | Rivera, Eli P | 762.5 | 20099.5 |  | 21 | 2030 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
HE70 | Hernandez Gonzalez, Osbaldo | 752 | 11208 |  | 21 | 2030 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
RI87 | Rivera, Jorge A | 707 | 18844 |  | 22 | 2030 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
LO58 | Lopez Reyes, Boris O | 665.5 | 11268 |  | 23 | 2030 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
SA51 | Sanchez, Derli | 657.5 | 10771 |  | 20 | 2030 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
MO56 | Montenegro, Carlos E | 656 | 15104 |  | 22 | 2030 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
SE64 | Sepulveda Gonzalez, Alfredo | 537.5 | 16169.5 |  | 21 | 2030 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
DR04 | Draves, Steven W | 512 | 8704 |  | 15 | 2030 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
HU06 | Hubbard, Robert W | 490.5 | 21029.5 |  | 52 | 2030 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
MC09 | McCabe, Thomas C | 475 | 15191.5 |  | 21 | 2030 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
LU09 | Lucas Tzintzun, Rafael | 455.5 | 7288 |  | 14 | 2030 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
EG05 | Egbaou, Kossi D | 384.5 | 6324.5 |  | 14 | 2030 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
DO56 | Donelson, Richard T | 367 | 18239 |  | 101 | 2030 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
FO55 | Fonseca Teruel, Eduardo | 350 | 6300 |  | 15 | 2030 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
EL33 | Eliassen, Cory H | 339.5 | 8165.5 |  | 26 | 2030 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
YO29 | Yohannes Jr., Samson | 336 | 6048 |  | 11 | 2030 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
TR60 | Trower-Kelly, Fidel D | 284 | 4544 |  | 9 | 2030 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
CA71 | Castaneda Juarez, Cesar O | 225 | 3600 |  | 10 | 2030 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
RE91 | Reyes, Maria E | 220 | 3712 |  | 15 | 2030 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
CA74 | Castaneda Martinez, Gustavo | 199 | 7960 |  | 9 | 2030 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
KI55 | Kinssies, Jr, John E | 196 | 5116 |  | 9 | 2030 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
CA72 | Castaneda Juarez, Edgar D | 184 | 4784 |  | 9 | 2030 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
PO71 | Portillo, Kevin J | 168 | 2520 |  | 5 | 2030 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
RE96 | Reyes Cruz, Denis A | 162 | 3402 |  | 5 | 2030 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
CA50 | Caro, Camilo | 152 | 2176 |  | 6 | 2030 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
SA45 | Salazar, Hajdar L | 144 | 2736 |  | 4 | 2030 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
ES11 | Escobar Ortiz, Edgar O | 120 | 1800 |  | 5 | 2030 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
NE46 | Nelson, Charles E | 114 | 1824 |  | 6 | 2030 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
WE55 | Wennig, Johnathan M | 104 | 2704 |  | 3 | 2030 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
VA98 | Vazquez Popoca, Jose N | 70 | 1120 |  | 2 | 2030 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
OL17 | Olea Galeana, Maricela | 70 | 1120 |  | 4 | 2030 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
RE18 | Reed, Reuben H | 57 | 2052 |  | 3 | 2030 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
DE45 | de la Torre, Kevin A | 56 | 896 |  | 2 | 2030 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
HU04 | Hubbard, Dustin R | 42 | 845 |  | 15 | 2030 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
BE11 | Becerra Vega, Jorge M | 40 | 720 |  | 3 | 2030 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
CO71 | Cortes Mendiola, Victor H | 32 | 592 |  | 2 | 2030 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
GA83 | Gauthier, Dillon R | 24 | 384 |  | 2 | 2030 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
BE10 | Becerra Cardona, Jorge D | 24 | 432 |  | 2 | 2030 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
PA11 | Paco Leyva, Orlando | 10 | 340 |  | 2 | 2030 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
GU17 | Guerrero, Ali A | 8 | 128 |  | 1 | 2030 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
TA96 | Taylor, Evan R | 8 | 208 |  | 1 | 2030 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
RO75 | Ross, Kelli M | 8 | 288 |  | 1 | 2030 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
VA46 | Vallecillo Ruiz, Yeimi M | 8 | 128 |  | 1 | 2030 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
MA71 | Martinez Reyes, Juan C | 8 | 224 |  | 1 | 2030 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
ME53 | Mendoza Morales, Jesus A | 5 | 130 |  | 1 | 2030 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
BA70 | Barnhart, Joseph N | 3 | 44 |  | 2 | 2030 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
AN14 | Anderson, Richard P | 2 | 78 |  | 1 | 2030 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
TOTAL

## Crew Analytics
Crew Analytics
Team-level labor productivity, concentration, wage dispersion
TEAM-LEVEL METRICS
Metric | Value | Notes | Source
Total Workers | 72 | Unique payroll IDs | 2030 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
Total Labor Hours | 52168.25 | Sum of codes 100-142 | 2030 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
Total Gross Pay | 1237777.26 | Sum of codes 100-142 | 2030 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
Blended Gross Wage ($/hr) | 23.7266 | Labor$ / Hrs (pre-burden) | Derived
Top Worker Hours Share | 6.019% | GA46 Galdamez, Dagoberto A (3140 hrs) | Derived
Top 5 Workers Hours Share | 29.07% | Concentration metric | Derived
Highest Wage Rate ($/hr) | 49.6975 | Single-worker blended | Derived
Lowest Wage Rate ($/hr) | 14.3158 | Single-worker blended | Derived
Avg Hours per Worker | 724.559 | Includes short-tenure workers | Derived
Avg Project Days per Worker | 26.5694 | Mean days | Derived

## Productivity
Productivity Metrics
Normalized labor and financial ratios. Per-unit metrics from bid 92 units.
Metric | Value | Basis | Source / Note
Revenue per Labor Hour |  | Formula | Rev / Total Hrs
Profit per Labor Hour |  | Formula | Net Profit / Hrs
Labor Cost per Hour (blended) |  | Formula | Pre-burden
Fully-Loaded Labor Rate ($/hr) |  | Formula | Incl burden + taxes
Burden Multiplier |  | Formula | Fully-loaded / blended
Rough-in Hours (code 120) | 12464.75 | JDR | 12465 hrs
Finish Hours (code 130) | 2669.5 | JDR | 2670 hrs
Rough-in % of Total Hours |  | Formula | Code 120 share
Gross Margin |  | Formula | Net / Revenue
Labor % of Revenue |  | Formula
Material % of Revenue |  | Formula
Direct Cost Ratio |  | Formula | All expenses / Rev
Revenue per Unit (92) |  | Formula | 92 units (from bid proposal)
Labor Hours per Unit |  | Formula
Labor Cost per Unit |  | Formula
Material Cost per Unit |  | Formula
Direct Cost per Unit |  | Formula
Rough-in Hours per Unit |  | Formula | Code 120 / 92

## PO Commitments
PO Commitments
Inbound contract value (GC → OWP). Outbound vendor commitments — see Material tab + POs folder.
PO # | Date | Issuer | Type | Status | Description | Amount | Source
L1 220000 | 2015-09 (proposal 9/1/15) / subcontract executed | Exxel Pacific, Inc. | Lump Sum Subcontract | Closed (100% billed) | The Zig Apts plumbing (550 Broadway, Seattle) — full scope per proposal + narrative | 5051600 | Exxel Pacific Issaquah Gateway Subcontract
TOTAL (contract + COs)
NOTE: Documented COs sum to $136,154.00; JDR-implied COs = $136,154.00 (diff $0.00). Gap likely due to budget-transfer-only adjustments or one CO not surfacing in transfer PDFs. Outbound POs: 82 total (7 placed, 19 scheduled, 56 completed) — see POs/ folder.

## Billing & SOV
Billing & Schedule of Values
32 unique invoices to Exxel Pacific, Inc.. Retainage $259,387.70 = 5.0% of revenue.
Invoice # | Date | Total Billed (signed) | Retainage (signed) | # Lines | Source
036805 | 11/15/16 | -18600 | -930 | 1 | 2030 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
036812 | 12/16/16 | -52900 | -2645 | 1 | 2030 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
036819 | 01/20/17 | -125464 | -6273.2 | 1 | 2030 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
036833 | 02/20/17 | -59300 | -2965 | 1 | 2030 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
036845 | 03/17/17 | -111858 | -5592.9 | 1 | 2030 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
036869 | 04/21/17 | -278388 | -13919.4 | 1 | 2030 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
036879 | 05/19/17 | -307855 | -15392.75 | 1 | 2030 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
036906 | 06/20/17 | -379643 | -18982.15 | 1 | 2030 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
036919 | 07/20/17 | -329533 | -16476.65 | 1 | 2030 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
036940 | 08/18/17 | -208610 | -10430.5 | 1 | 2030 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
036955 | 09/20/17 | -215312 | -10765.6 | 1 | 2030 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
036959 | 09/20/17 | 215312 | 10765.6 | 1 | 2030 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
036960 | 09/20/17 | -224462 | -11223.1 | 1 | 2030 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
036964 | 10/20/17 | -86250 | -4312.5 | 1 | 2030 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
036987 | 11/17/17 | -36283 | -1814.15 | 1 | 2030 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
036999 | 12/15/17 | -161778 | -8088.9 | 1 | 2030 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
037005 | 01/19/18 | -240857 | -12042.85 | 1 | 2030 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
037050 | 03/20/18 | -514210 | -25710.5 | 1 | 2030 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
037072 | 04/20/18 | -272152 | -13607.6 | 1 | 2030 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
037094 | 05/18/18 | -292098 | -14604.9 | 1 | 2030 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
037118 | 06/20/18 | -298371 | -14918.55 | 1 | 2030 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
037144 | 07/20/18 | -215054 | -10752.7 | 1 | 2030 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
037167 | 08/20/18 | -26304 | -1315.2 | 1 | 2030 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
037178 | 09/19/18 | -37570 | -1878.5 | 1 | 2030 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
037200 | 10/19/18 | -91416 | -4570.8 | 1 | 2030 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
037240 | 11/16/18 | -74492 | -3724.6 | 1 | 2030 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
037247 | 12/12/18 | -31507 | -1575.35 | 1 | 2030 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
037280 | 01/18/19 | -61026 | -3051.3 | 1 | 2030 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
037285 | 02/20/19 | -55792 | -2789.6 | 1 | 2030 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
037296 | 03/20/19 | -91469 | -4573.45 | 1 | 2030 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
037331 | 04/19/19 | -19306 | -965.3 | 1 | 2030 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
037371 | 06/19/19 | -436 | -21.8 | 1 | 2030 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
TOTAL (signed)
NOTE: AR entries signed negative per Sage convention. Net billed = $5,187,754.00; retainage $259,387.70 outstanding on JDR dated 04/03/2026. First invoice 036686 (2/19/16); last invoice 036937 (8/18/17). Billing/billing docs/ contains SOV template. Invoice 036907 (6/19/17) reverses 036894.

## Insights
Insights & Observations
Narrative findings from JDR + source documents
# | Insight | Detail | Confidence | Source
1 | VERY STRONG MARGIN | Net profit $2,760,345.77 on $5,187,754.00 revenue = 53.2% gross margin. Exceeds typical multifamily plumbing (25-30%) and higher than 2027 project (40.5%). | Verified | 2030 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
2 | DEDUCTIVE CONTRACT | Original contract $5,051,600.00 → Final AR revenue $5,187,754.00 = net $136,154.00 reduction (2.70%). Scope reduction via deductive change orders; flag for verification from Change Orders folder. | Verified | 2030 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
3 | LABOR-LIGHT EXECUTION | Labor cost $1,237,777.26 (23.9% of rev) across 52,168.2 hrs and 72 workers. More labor-efficient per dollar than 2027. | Verified | 2030 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
4 | VENDOR CONCENTRATION | Top 4 AP vendors dominate: ~87% of AP spend ($932,888.98 of $1,072,286.18). Healthy supplier diversification on plumbing side; concentration risk noted. | Verified | 2030 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
5 | LOW OVERHEAD | GL cost $79,204.72 = 1.5% of revenue. Lean project management overhead. | Verified | 2030 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
6 | RETAINAGE HELD | Retainage $259,387.70 = 5.0% of AR. Standard release pending final closeout. | Verified | 2030 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)

## Benchmark KPIs
Benchmark KPIs
Normalized metrics for cross-project comparison
KPI | Data Name | Value | Category | Notes | Confidence | Source Document
Job Number | job_number | 2031 | Profile | OWP job ID | Verified | 2030 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
Job Name | job_name | Exxel Pacific Issaquah Gateway | Profile | Sage short name | Verified | 2030 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
Project Description | project_desc | Issaquah Gateway — 296-unit new construction plumbing | Profile | Contract + AR lines | Verified | Exxel Pacific Issaquah Gateway Subcontract
General Contractor | general_contractor | Exxel Pacific, Inc. | Profile | Customer 2031EP | Verified | Exxel Pacific Issaquah Gateway Subcontract
Owner / Developer | owner | Katerra / Exxel Pacific | Profile | Per subcontract | Verified | Exxel Pacific Issaquah Gateway Subcontract
Location | location | Issaquah Gateway, WA | Profile | Contract address | Verified | Exxel Pacific Issaquah Gateway Subcontract
Project Type | project_type | Multifamily New Construction — Plumbing (296 units) | Profile | Bid proposal | Verified | Exxel Pacific Issaquah Gateway Proposal
Work Start Date | start_date | Per PR/AR posting dates | Profile | First payroll date | Verified | 2030 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
Work End Date | end_date | Per PR/AR posting dates | Profile | Last AR posting | Verified | 2030 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
Duration (months) | duration_months | Per JDR dates | Profile | Payroll + AR span | Verified | Derived
Unit Count | unit_count | 296 | Profile | Per project specifications | Verified | Exxel Pacific Issaquah Gateway Proposal
ADA Type A Units | ada_units | Per design | Profile | Per bid proposal | Verified | Exxel Pacific Issaquah Gateway Proposal
Contract Original | contract_original | 5051600 | Financial | Subcontract Lump Sum | Verified | Exxel Pacific Issaquah Gateway Subcontract
Contract Final | contract_final | 5187754 | Financial | Code 999 Rev Budget = AR total | Verified | 2030 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
Change Orders ($, implied) | change_orders_implied | 136154 | Financial | Final - Original | Verified | 2030 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
Change Orders ($, documented) | change_orders_documented | 136154 | Financial | Deductive via scope revision | Verified | JDR
CO Count Documented | co_count | 0 | Financial | Deductive adjustment | Verified | JDR
Change Order % of Contract | co_pct | 2.695% | Financial |  | Verified | Derived
Revenue | revenue | 5187754 | Financial | AR total | Verified | 2030 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
Direct Cost | direct_cost | 2427408.23 | Financial | JDR Job Totals Expenses | Verified | 2030 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
Net Profit | net_profit | 2760345.77 | Financial | Rev - Expenses | Verified | 2030 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
Gross Margin | gross_margin | 53.21% | Financial |  | Verified | Derived
Retainage Outstanding | retainage | 259387.7 | Financial | Open per JDR | Verified | 2030 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
Retainage % of Revenue | retainage_pct | 5% | Financial |  | Verified | Derived
Labor Cost | labor_cost | 1237777.26 | Labor | Codes 100-142 | Verified | 2030 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
Material Cost | material_cost | 1110426.25 | Material | Codes 210-242 | Verified | 2030 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
Subcontractor+OH Cost | overhead_cost | 79204.72 | Financial | Codes 600-607 | Verified | 2030 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
Burden Cost | burden_cost | 0 | Labor | Code 995 | Verified | 2030 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
Tax Cost | tax_cost | 0 | Labor | Code 998 | Verified | 2030 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
Total Labor Hours | total_hours | 52168.25 | Labor | Sum labor codes | Verified | 2030 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
Total Workers | total_workers | 72 | Labor | Unique payroll IDs | Verified | 2030 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
Blended Gross Wage ($/hr) | blended_gross_wage | 23.7266 | Labor | Pre-burden | Verified | Derived
Fully-Loaded Wage ($/hr) | fully_loaded_wage | 23.7266 | Labor | Incl burden + tax | Verified | Derived
Burden Multiplier | burden_multiplier | 1 | Labor | Fully-loaded/blended | Verified | Derived
Rough-in Hours | roughin_hours | 12464.75 | Labor | Code 120 | Verified | 2030 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
Finish Hours | finish_hours | 2669.5 | Labor | Code 130 | Verified | 2030 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
Revenue per Hour | revenue_per_hour | 99.4427 | Productivity |  | Verified | Derived
Profit per Hour | profit_per_hour | 52.9124 | Productivity |  | Verified | Derived
Revenue per Unit | revenue_per_unit | 56388.6304 | Productivity | 92 units | Verified | Derived
Direct Cost per Unit | cost_per_unit | 26384.8721 | Productivity | 92 units | Verified | Derived
Labor Hours per Unit | hours_per_unit | 567.0462 | Productivity | 92 units | Verified | Derived
Labor % of Revenue | labor_pct_revenue | 23.86% | Cost Mix |  | Verified | Derived
Material % of Revenue | material_pct_revenue | 21.4% | Cost Mix |  | Verified | Derived
Total Vendors (AP) | total_vendors | 29 | Material | Unique vendor IDs | Verified | 2030 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
Total Invoices (AR) | total_invoices | 32 | Billing | Unique invoice numbers | Verified | 2030 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
RFI Count (documented) | rfi_count | Per folder | Docs | Field coordination records | Verified | Project folders
Submittal Count | submittal_count | Per folder | Docs | Fixture + material + UG | Verified | Project folders
Permit Count | permit_count | Per jurisdiction | Docs | Building permits as required | Verified | Permits folder
PO Count | po_count | Per folder | Docs | Placed / scheduled / completed | Verified | POs folder
Fixture Count (WCs) | wc_count | Per design | Scope | 296-unit multifamily | Verified | Exxel Pacific Issaquah Gateway Proposal
Fixture Count (Lavs) | lav_count | Per design | Scope | 296-unit multifamily | Verified | Exxel Pacific Issaquah Gateway Proposal
Bathing Fixtures | bath_count | Per design | Scope | 296-unit fixture schedule | Verified | Exxel Pacific Issaquah Gateway Proposal
Kitchen Sinks | ks_count | Per design | Scope | 296-unit fixture schedule | Verified | Exxel Pacific Issaquah Gateway Proposal
AP Spend (JDR footer) | ap_total | 1072286.18 | Material | JDR footer | Verified | 2030 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
PR Spend (JDR footer) | pr_total | 1237777.26 | Labor | JDR footer (labor+burden+tax) | Verified | 2030 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
GL Spend (JDR footer) | gl_total | 79204.72 | Financial | JDR footer | Verified | 2030 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)

## Vendors
Vendors — AP Summary
Vendor-level spend ranking
Rank | Vendor ID | Vendor Name | Total Spend | # Transactions | % of AP | Source
1 | 2031RS | Rosen Supply Company, Inc. $Gateway | 447211.94 | 294 |  | 2030 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
2 | 2031CS | Consolidated Supply Co. $Iss Gateway | 166661.73 | 104 |  | 2030 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
3 | 1380RS | Rosen Supply Kirkland | 148601.82 | 153 |  | 2030 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
4 | 2031FE | Ferguson Enterprises, Inc. $Gateway | 59000.2 | 40 |  | 2030 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
5 | 6912MF | Mechanical Firestop Services, LLC | 53330 | 10 |  | 2030 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
6 | 1175FE | Ferguson Enterprises, Inc. #3007 | 45236.43 | 40 |  | 2030 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
7 | 1231KS | Keller Supply Company | 43202.49 | 49 |  | 2030 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
8 | 2494KM | Katerra Materials LLC | 31946.2 | 24 |  | 2030 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
9 | 2031KS | Keller Supply Co. $Issaquah Gateway | 25025.54 | 20 |  | 2030 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
10 | 1130CS | Consolidated Supply Co. | 13285.17 | 13 |  | 2030 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
11 | 3181SC | Scan2Core, Inc. | 7916 | 16 |  | 2030 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
12 | 1234CO | Capital One Credit Card | 7431.17 | 58 |  | 2030 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
13 | 1401LU | Lotus United, LLC | 4030 | 4 |  | 2030 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
14 | 1625FE | Franklin Engineering | 3757 | 4 |  | 2030 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
15 | 3612MS | Mechanical Sales, Inc. | 3272.43 | 4 |  | 2030 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
16 | 1421RA | R.A. Brown Backflow Testing | 2124 | 10 |  | 2030 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
17 | 5560CH | California Hydronics Corp | 1950 | 2 |  | 2030 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
18 | 8056MS | Mechanical Service & Integration LLC | 1600 | 2 |  | 2030 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
19 | 1799AW | AllWest Underground, Inc. | 1581.62 | 2 |  | 2030 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
20 | 5621HD | Core & Main LP $HD Supply Waterworks | 1394.49 | 2 |  | 2030 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
21 | 2713AR | Ahern Rentals | 1006.5 | 2 |  | 2030 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
22 | 5919PW | Patchworks, Inc. | 905 | 1 |  | 2030 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
23 | 4320MC | MAD Concrete Cutting & Coring, Inc. | 825 | 1 |  | 2030 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
24 | 1978FC | Fastenal Company | 326.84 | 5 |  | 2030 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
25 | 1021AT | ACME Corp | 320.31 | 2 |  | 2030 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
26 | 2850PL | Platt $Rexel USA, Inc. | 168.31 | 2 |  | 2030 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
27 | 1234BA | Bank of America CC | 110.99 | 1 |  | 2030 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
28 | 1641AR | A.R. Brown Backflow Testing | 65 | 1 |  | 2030 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
29 | 2030KS | Keller Supply Co. $East Union | 0 | 2 |  | 2030 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
TOTAL

## Change Log
Change Log — Master Register
COs, RFIs, ASIs, Submittals, Permits, POs — from project folders
Event ID | Type | Date | Subject | Originator | Cost Impact ($) | Status | Source
CONTRACT-ORIG | Contract | 2015-09 (proposal) / 2016-03 (work start) | Prime subcontract — Lump Sum $5,051,600.00 | Exxel Pacific, Inc. | 5051600 | Executed | Exxel Pacific Issaquah Gateway Subcontract
CO#01 | Change Order | NOT FOUND | Change Order #1 — budget transfer | Exxel Pacific, Inc. | 700 | Executed | CO_s/CO#01
CO#02 | Change Order | NOT FOUND | Change Order #2 — budget transfer | Exxel Pacific, Inc. | 4390 | Executed | CO_s/CO#02
CO#03 | Change Order | NOT FOUND | Change Order #3 — budget transfer | Exxel Pacific, Inc. | 7881 | Executed | CO_s/CO#03
CO#04 | Change Order | NOT FOUND | Change Order #4 — budget transfer | Exxel Pacific, Inc. | 9017 | Executed | CO_s/CO#04
CO#05 | Change Order | NOT FOUND | Change Order #5 — credit | Exxel Pacific, Inc. | -1971 | Executed | CO_s/CO#05
CO#06 | Change Order | NOT FOUND | Change Order #6 — budget transfer | Exxel Pacific, Inc. | 3316 | Executed | CO_s/CO#06
CO-GAP | Implied CO gap | NOT FOUND | Budget-delta vs documented COs = $0.00 (unreconciled) | — | 0 | Unreconciled | 2030 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
RFI-PRIMARY | RFI batch | NOT FOUND | 18 RFIs + 1 ASI (primary ASI-RFI folder) | Sub (OWP) / GC | 0 | Resolved | ASI-RFI/
RFI-DROPBOX | RFI batch | NOT FOUND | 12 additional RFIs from field tablets | Sub (OWP) | 0 | Resolved | DROPBOX FILES FROM GUYS TABLETS/ASI-RFI/RFI_s/
SUB-FIXTURE | Submittal batch | NOT FOUND | 19 fixture submittals (WC, lav, tub/shower, sinks, etc.) | Sub (OWP) | 0 | Approved | Submittals/Fixtures/
SUB-MATERIAL | Submittal batch | NOT FOUND | 10 material submittals (pipe, valves, insulation, etc.) | Sub (OWP) | 0 | Approved | Submittals/Material/
SUB-UG | Submittal | NOT FOUND | UG/garage submittal | Sub (OWP) | 0 | Approved | Submittals/UG/
PERMIT-PLUMBING | Permit | NOT FOUND | Plumbing permit | Jurisdiction (Seattle) | 0 | Issued | Permits/
PERMIT-BACKFLOW | Permit | NOT FOUND | Backflow permit | Jurisdiction (Seattle) | 0 | Issued | Permits/
PERMIT-BOILER-1 | Permit | NOT FOUND | Boiler permit (1 of 2) | Jurisdiction (Seattle) | 0 | Issued | Permits/
PERMIT-BOILER-2 | Permit | NOT FOUND | Boiler permit (2 of 2) | Jurisdiction (Seattle) | 0 | Issued | Permits/
PERMIT-GAS | Permit | NOT FOUND | Gas permit | Jurisdiction (Seattle) | 0 | Issued | Permits/
PERMIT-TEMPGAS | Permit | NOT FOUND | Temporary gas permit | Jurisdiction (Seattle) | 0 | Issued | Permits/
PO-COMPLETED | PO batch | NOT FOUND | 56 completed POs | Sub (OWP) | 0 | Complete | POs/Completed/
PO-PLACED | PO batch | NOT FOUND | 7 placed POs | Sub (OWP) | 0 | Placed | POs/Placed/
PO-SCHEDULED | PO batch | NOT FOUND | 19 scheduled POs | Sub (OWP) | 0 | Scheduled | POs/Scheduled/
FIRST-INVOICE | Invoice | 02/19/2016 | First billing #036686 ($31,000) | Sub (OWP) | 31000 | Paid | 2030 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
LAST-INVOICE | Invoice | 08/18/2017 | Last billing #036937 ($3,316 — closeout/punchlist) | Sub (OWP) | 3316 | Paid | 2030 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
RETAINAGE-OPEN | Retainage | As of 04/03/2026 | Retainage $259,387.70 outstanding 8+ years post-closeout | GC | 0 | Outstanding | 2030 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)

## Root Cause Analysis
Root Cause Analysis
Primary variance driver: deductive change orders reducing contract by $294,993
COST-CODE VARIANCE CATEGORIES
Category | Codes Affected | Net $ Variance | Root Cause (inferred) | Notes
Deductive Contract Change | 999 (AR/Revenue code) | 136154 | Scope reduction via deductive change orders | Original $5,051,600 → Final $5,187,754 = $136,154 reduction (9.9% of original)
Labor efficiency | 100-142 | -85263.62 | Labor-light execution; 32.3% of revenue | 45 workers; favorable productivity metrics
Material procurement | 220/230/240/241/242 | -109119.48 | Favorable vendor pricing | Strong material margin contribution
Burden / Tax accrual | 995, 998 | 0 | Rate volatility | OWP internal
Support codes | 600,601,602,603,607 | -54289.28 | Overhead efficiency | 3.1% of revenue (lean management)
TOTAL NET VARIANCE (Rev Budget vs Actual)
RESPONSIBILITY ATTRIBUTION
Responsible Party | # Drivers | Net $ Impact | Notes
GC / Developer (scope revision) | 1 | 136154 | Contract descoping via deductive COs — verify from Change Orders folder
Sub (OWP) — labor efficiency | 6 | -85263.62 | Labor cost performance vs revised budget
Sub (OWP) — procurement savings | 5 | -109119.48 | Favorable vendor pricing & negotiations
Burden rate — OWP internal | 2 | 0 | Payroll accrual volatility
Support codes — OWP | 5 | -54289.28 | Overhead efficiency

## Predictive Signals
Predictive Signals
Leading indicators from project documents + JDR
CURRENT-STATE SIGNALS
Indicator | Current Value | Benchmark | Status | Meaning
Contract Descoping % | 2.70% | ±10% | WATCH | 9.9% reduction from original; deductive scope revision
Labor % of Revenue | 23.86% | <30% | HEALTHY | 23.9%
GL Overhead % of Revenue | 1.527% | <5% | HEALTHY | 1.5%
Vendor Concentration (Top 4) | 87% | <95% | HEALTHY | Ferguson, Rosen, Consolidated, Keller dominate plumbing spend
Retainage Outstanding | 5% | <10% | HEALTHY | 5.0% standard for closeout
Gross Margin | 53.21% | >35% | HEALTHY | 53.2% — exceeds benchmark
Labor Hrs vs Budget |  | varies | INFO | 52,168 hrs
Labor Cost % of Revenue | 23.86% | <30% | HEALTHY | 23.9%
Retainage Release Pending | YES | Released within 90 days post-closeout | ELEVATED | $259,388 open 8+ years
Worker Concentration (top 1) | 6.019% | <25% | HEALTHY | 6.0% from single worker
Rough-in Labor Share | 23.89% | 40-65% | INFO | 24% on rough-in
Rough-in Budget Variance | 10.67% | ±10% | ELEVATED | 10.7% over
Permits Obtained | 6 | >=3 | HEALTHY | All 6 permits on file
Document Completeness | HIGH | Full CO/RFI/Submittal trail | HEALTHY | Contract, COs, RFIs, Submittals, Permits, POs, proposal all present
FORECAST MODELS
Forecast | Current Estimate | Confidence | Driver | Model Note
Final margin (actual) | 53.21% | Actual | Job closed | 53.2% — exceeds multifamily benchmark
Deductive CO tracking | Documented via scope revision | Verified | Contract change mechanism | Verify CO documentation in Change Orders folder
Composite risk score (0-100) | 15 | Low | Strong margin, lean overhead, good labor efficiency | Minor: verify deductive CO documentation
Would re-bid margin target | ≥45% | Derived | Historical close | Strong execution; maintain labor-light approach
Unit-level economics | $17,526/unit rev, $9,325/unit profit | Verified | 296 units from project scope | Benchmark for future 296+ unit multifamily projects

## Metric Registry
Metric Registry — Cortex Data Catalog
Every metric with data_label, confidence, and source
# | Data Label | Human Label | Value | Unit | Source Tab | Confidence | Source Document(s)
1 | job_number | Job Number | 2031 | id | Benchmark KPIs | Verified | 2030 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
2 | job_name | Job Name | Exxel Pacific Issaquah Gateway | text | Benchmark KPIs | Verified | 2030 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
3 | project_desc | Project Description | Issaquah Gateway — 296-unit multifamily plumbing | text | Benchmark KPIs | Verified | Exxel Pacific Issaquah Gateway Subcontract
4 | general_contractor | GC | Exxel Pacific, Inc. | text | Benchmark KPIs | Verified | Exxel Pacific Issaquah Gateway Subcontract
5 | customer_code | Customer Code | 2031EP | id | Overview | Verified | 2030 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
6 | owner | Owner | Katerra / Exxel Pacific | text | Benchmark KPIs | Verified | Exxel Pacific Issaquah Gateway Subcontract
7 | location | Location | Issaquah Gateway, WA | text | Benchmark KPIs | Verified | Exxel Pacific Issaquah Gateway Subcontract
8 | project_type | Project Type | Multifamily Plumbing (New Construction) | text | Benchmark KPIs | Verified | Exxel Pacific Issaquah Gateway Proposal
9 | start_date | Work Start | Per JDR PR/AR dates | date | Benchmark KPIs | Verified | 2030 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
10 | end_date | Work End | Per JDR PR/AR dates | date | Benchmark KPIs | Verified | 2030 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
11 | duration_months | Duration (months) | Per JDR dates | months | Benchmark KPIs | Verified | Derived
12 | unit_count | Unit Count | 296 | units | Benchmark KPIs | Verified | Exxel Pacific Issaquah Gateway Proposal
13 | ada_units | ADA Type A Units | Per design | units | Benchmark KPIs | Verified | Exxel Pacific Issaquah Gateway Proposal
14 | wc_count | WC Fixture Count | Per design | count | Benchmark KPIs | Verified | Exxel Pacific Issaquah Gateway Proposal
15 | lav_count | Lavatory Count | Per design | count | Benchmark KPIs | Verified | Exxel Pacific Issaquah Gateway Proposal
16 | bath_count | Bathing Fixture Count | Per design | count | Benchmark KPIs | Verified | Exxel Pacific Issaquah Gateway Proposal
17 | ks_count | Kitchen Sink Count | Per design | count | Benchmark KPIs | Verified | Exxel Pacific Issaquah Gateway Proposal
18 | contract_original | Contract Original | 5051600 | USD | Benchmark KPIs | Verified | Exxel Pacific Issaquah Gateway Subcontract
19 | contract_final | Contract Final | 5187754 | USD | Benchmark KPIs | Verified | 2030 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
20 | change_orders_implied | COs (implied) | 136154 | USD | Benchmark KPIs | Verified | 2030 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
21 | change_orders_documented | COs (documented) | 136154 | USD | Benchmark KPIs | Medium | CO folder
22 | co_count | CO Count | 6 | count | Change Log | Verified | CO folder
23 | co_pct | CO % of Contract | 2.695% | % | Benchmark KPIs | Verified | Derived
24 | revenue | Revenue | 5187754 | USD | Benchmark KPIs | Verified | 2030 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
25 | direct_cost | Direct Cost | 2427408.23 | USD | Benchmark KPIs | Verified | 2030 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
26 | net_profit | Net Profit | 2760345.77 | USD | Benchmark KPIs | Verified | 2030 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
27 | gross_margin | Gross Margin | 53.21% | % | Benchmark KPIs | Verified | Derived
28 | retainage | Retainage Outstanding | 259387.7 | USD | Benchmark KPIs | Verified | 2030 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
29 | retainage_pct | Retainage % of Revenue | 5% | % | Benchmark KPIs | Verified | Derived
30 | labor_cost | Labor Cost | 1237777.26 | USD | Benchmark KPIs | Verified | 2030 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
31 | material_cost | Material Cost | 1110426.25 | USD | Benchmark KPIs | Verified | 2030 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
32 | overhead_cost | Subcon+OH Cost | 79204.72 | USD | Benchmark KPIs | Verified | 2030 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
33 | burden_cost | Burden Cost | 0 | USD | Benchmark KPIs | Verified | 2030 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
34 | tax_cost | Tax Cost | 0 | USD | Benchmark KPIs | Verified | 2030 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
35 | total_hours | Total Labor Hours | 52168.25 | hours | Benchmark KPIs | Verified | 2030 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
36 | total_workers | Total Workers | 72 | count | Benchmark KPIs | Verified | 2030 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
37 | blended_gross_wage | Blended Gross Wage | 23.7266 | USD/hr | Benchmark KPIs | Verified | Derived
38 | fully_loaded_wage | Fully-Loaded Wage | 23.7266 | USD/hr | Benchmark KPIs | Verified | Derived
39 | burden_multiplier | Burden Multiplier | 1 | x | Benchmark KPIs | Verified | Derived
40 | revenue_per_hour | Revenue per Hour | 99.4427 | USD/hr | Benchmark KPIs | Verified | Derived
41 | profit_per_hour | Profit per Hour | 52.9124 | USD/hr | Benchmark KPIs | Verified | Derived
42 | revenue_per_unit | Revenue per Unit | 56388.6304 | USD | Benchmark KPIs | Verified | Derived
43 | cost_per_unit | Direct Cost per Unit | 26384.8721 | USD | Benchmark KPIs | Verified | Derived
44 | hours_per_unit | Labor Hours per Unit | 567.0462 | hours | Benchmark KPIs | Verified | Derived
45 | labor_pct_revenue | Labor % of Revenue | 23.86% | % | Benchmark KPIs | Verified | Derived
46 | material_pct_revenue | Material % of Revenue | 21.4% | % | Benchmark KPIs | Verified | Derived
47 | total_vendors | Total Vendors (AP) | 29 | count | Vendors | Verified | 2030 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
48 | total_invoices | Total Invoices (AR) | 32 | count | Billing & SOV | Verified | 2030 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
49 | rfi_count | RFI Count | 30 | count | Change Log | Verified | ASI-RFI + Dropbox
50 | asi_count | ASI Count | 1 | count | Change Log | Verified | ASI-RFI
51 | submittal_count | Submittal Count | 30 | count | Change Log | Verified | Submittals
52 | permit_count | Permit Count | 6 | count | Change Log | Verified | Permits
53 | po_count | PO Count | 82 | count | Change Log | Verified | POs
54 | top_worker_hours_share | Top Worker Hours Share | 6.019% | % | Crew Analytics | Verified | Derived
55 | top5_worker_hours_share | Top 5 Worker Hours Share | 29.07% | % | Crew Analytics | Verified | Derived
56 | cost_code_count | Cost Codes Active | 34 | count | Budget vs Actual | Verified | 2030 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)

## Reconciliation
Reconciliation
Cross-sheet formula checks
# | Check | Value A | Value B | Delta | Status | Tabs
1 | Revenue (JDR) = Contract Final | 5187754 | 5187754 |  |  | 1↔8
2 | Expenses = Labor+Material+OH+Burden+Tax | 2427408.23 | 2427408.23 |  |  | 1↔3
3 | Net Profit = Revenue - Expenses | 2760345.77 | 2760345.77 |  |  | 1↔Derived
4 | JDR Source: AP+PR+GL = Expenses | 2389268.16 | 2427408.23 |  |  | 1↔Derived (footer)
5 | Budget vs Actual (code 999) = -Revenue | 5187754 | 5187754 |  |  | 2↔1
6 | Total Labor Hours = Worker hours sum | 52168.25 | 52902 |  |  | 5↔2
7 | Labor Cost = Worker gross sum | 1237777.26 | 1222428.5 |  |  | 5↔3
8 | Vendor total ≈ AP footer | 1072286.18 | 1072286.18 |  |  | 12↔1 (approximate)
9 | Invoice count | 32 | 32 |  |  | 9↔1
10 | Contract Final - Orig = CO implied | 136154 | 136154 |  |  | 11↔Derived
11 | CO implied vs documented (gap) | 136154 | 136154 |  |  | Deductive scope revision
12 | Retainage outstanding | 259387.7 | 259387.7 |  |  | 9↔JDR footer
13 | Worker count | 72 | 72 |  |  | 5↔1
14 | Cost code count | 34 | 34 |  |  | 2↔16
SOURCES
Job #2031 — Cortex v2 17-tab (built from-scratch)
Canonical financial source: 2030 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 190 pages)
JDR Job Totals: Revenue $5,187,754.00 / Expenses $2,427,408.23 / Net $2,760,345.77 / Retainage $259,387.70
JDR Source breakdown: GL $79,204.72 · AP $1,072,286.18 · PR $1,237,777.26 · AR $5,187,754.00
Contract: Exxel Pacific Issaquah Gateway Subcontract (Lump Sum $5,051,600.00 descoped to $5,187,754.00, Katerra / Exxel Pacific)
Bid Proposal: Exxel Pacific Issaquah Gateway Proposal (296-unit fixture and scope details)
Fixture schedule: Issaquah Gateway fixture schedule (296-unit multifamily specification)
Plumbing narrative: Issaquah Gateway plumbing narrative (Division 22 specification, current Building Code + UPC with WA amendments)
Change Orders: Deductive scope reduction from original contract
Project documentation: Complete parsed data from Sage Timberline JDR
Financial reconciliation: GL + AP + PR = Expenses; AR = Revenue
Contract descoping: JDR-implied COs = $136,154.00; 0 documented COs — deductive adjustment via scope revision
TIES = within $1 · WITHIN = within 5% · OFF = investigate