## Overview
Job #2032 · Blueprint Luna Apts-Roosevelt
Cortex JCR v2 • Blueprint Capital Services, LLC (customer 2032BC) • 6921 Roosevelt Way NE, Seattle WA • Owner: Blueprint Capital Services
PROJECT OVERVIEW
Project Job # | 2032 |  | 2032 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 72 pages) header
Project Name (Sage) | Blueprint Luna Apts-Roosevelt |  | 2032 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 72 pages) header
Project Description | Luna Apartments — 71-unit multifamily new construction plumbing |  | Blueprint Capital Services Luna Apts-Roosevelt Subcontract / AR line descriptions
General Contractor | Blueprint Capital Services, LLC |  | Blueprint Capital Services Luna Apts-Roosevelt Subcontract
Customer Code (Sage) | 2032BC |  | 2032 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 72 pages)
Owner / Developer | Blueprint Capital Services |  | Blueprint Capital Services Luna Apts-Roosevelt Subcontract
Jobsite Location | 6921 Roosevelt Way NE, Seattle WA |  | Blueprint Capital Services Luna Apts-Roosevelt Subcontract
Contract / PO Document | Blueprint Capital Services Luna Apts-Roosevelt Subcontract |  | Lump Sum subcontract
Plans / Specifications | Luna Apts-Roosevelt plumbing narrative (Div 22 plumbing narrative) + fixture schedule + proposal |  | Folder scan
Fixture Schedule | Luna Apts-Roosevelt fixture schedule (fixture schedule for 71-unit multifamily) |  | Referenced
Bid Proposal | Blueprint Capital Services Luna Apts-Roosevelt Proposal |  | Detailed scope and fixture quantities
Contract Type | Lump Sum |  | Blueprint Capital Services Luna Apts-Roosevelt Subcontract
Work Period | Per PR/AR posting dates in JDR |  | 2032 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 72 pages)
Total Unique Documents Reviewed | 1008 |  | File inventory across owp-2032/
CONTRACT VALUE |  | NET PROFIT | DIRECT COST | LABOR HOURS
726403 |  | 328108.48 | 398294.52 | 5157
Original $685,300.00 + $41,103.00 COs (6.00%) |  | 45.2% margin | 54.8% of revenue | 26 workers
SCOPE OF WORK (from contract + proposal)
Full plumbing installation: underground, rough-in, finish, gas piping, water mains, insulation, mechanical room, and warranty.
71-unit multifamily new construction at 6921 Roosevelt Way NE, Seattle WA.
Per project specifications and bid proposal.
Comprehensive fixture schedule with standard and ADA-compliant units.
Spec compliance: Current Building Code + UPC with Washington state amendments.
SOURCES
Canonical financial source: 2032 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 72 pages)
Job totals (JDR footer): Revenue $726,403.00 / Expenses $398,294.52 / Net $328,108.48 / Retainage $36,320.15
Source breakdown: GL $26,110.86 · AP $175,969.52 · PR $134,465.25 · AR $726,403.00
Contract: Blueprint Capital Services Luna Apts-Roosevelt Subcontract (Lump Sum $685,300.00, revised to $726,403.00 via 7 COs)
Proposal: Blueprint Capital Services Luna Apts-Roosevelt Proposal
Fixture schedule: Luna Apts-Roosevelt fixture schedule
Plumbing narrative: Luna Apts-Roosevelt plumbing narrative
Change Orders: 7 executed COs netting +$41,103.00 (6.0% of original)
PROJECT TEAM (OWP Job Info)
Role | Status | Name / Firm
GC | Extracted | Blueprint Capital Services, LLC
GC PM | Extracted | Rick (per OWP Project List)
GC Superintendent | Extracted | Andrew Withnell / Scott McSpadden
GC PE | N/A | N/A
Developer | Extracted | Blueprint Capital Services
Architect | N/A | N/A
Structural | N/A | N/A
Acoustical | N/A | N/A
ADA Consultant | N/A | N/A
Interior Design | N/A | N/A
MEP Engineer | Extracted | Franklin Engineering

## Budget vs Actual
Budget vs Actual
All 27 cost codes from JDR. Contract $685,300 → $726,403 (COs +$41,103.00).
Cost Code | Description | Original Budget | Revised Budget | Actual | Variance | % of Revised | Hours | Source
100 | Supervision | 6390 | 6531 | 2980.5 |  |  | 62.5 | 2032 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 72 pages)
101 | Takeoff & Purchase Labor | 10295 | 10765 | 8067.5 |  |  | 166 | 2032 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 72 pages)
110 | Underground Labor | 6720 | 8170 | 6693 |  |  | 231 | 2032 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 72 pages)
120 | Roughin Labor | 86310 | 87991 | 77199.5 |  |  | 3132 | 2032 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 72 pages)
130 | Finish Labor | 23215 | 24174 | 15430.25 |  |  | 682.5 | 2032 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 72 pages)
140 | Gas Labor | 5250 | 5250 | 1836 |  |  | 50.5 | 2032 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 72 pages)
141 | Water Main/Insulation Lab | 25980 | 25980 | 12390 |  |  | 558.5 | 2032 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 72 pages)
142 | Mech Room Labor | 12060 | 12762 | 9868.5 |  |  | 274 | 2032 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 72 pages)
210 | Underground Material | 7845 | 12333 | 7410.05 |  |  |  | 2032 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 72 pages)
211 | Garage Material | 0 | 0 | 203.65 |  |  |  | 2032 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 72 pages)
212 | Canout Material | 0 | 0 | 80.8 |  |  |  | 2032 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 72 pages)
220 | Roughin Material | 48085 | 49835 | 27891.8 |  |  |  | 2032 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 72 pages)
230 | Finish Material | 79470 | 92626 | 98389.06 |  |  |  | 2032 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 72 pages)
240 | Gas Material | 3500 | 3500 | 1008.16 |  |  |  | 2032 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 72 pages)
241 | Water Main/Insulation Mat | 33025 | 33025 | 21425.26 |  |  |  | 2032 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 72 pages)
242 | Mech Room Material | 32450 | 39250 | 11291.75 |  |  |  | 2032 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 72 pages)
243 | Condensation Drains Mat | 0 | 0 | 0 |  |  |  | 2032 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 72 pages)
310 | Flats Underground Labor | 0 | 0 | 0 |  |  | 8 | 2032 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 72 pages)
320 | Flats Roughin Labor | 0 | 0 | 0 |  |  |  | 2032 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 72 pages)
420 | Flats Roughin Material | 0 | 0 | 0 |  |  |  | 2032 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 72 pages)
600 | Subcontractor | 1000 | 1000 | 135 |  |  |  | 2032 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 72 pages)
601 | Engineering/Plans | 21000 | 21000 | 17538.5 |  |  |  | 2032 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 72 pages)
603 | Permits & Licenses | 5155 | 5165 | 4198 |  |  |  | 2032 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 72 pages)
607 | Other Expenses | 7000 | 7000 | 4239.36 |  |  |  | 2032 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 72 pages)
995 | Payroll Burden | 78153.57 | 80584.7 | 59716.99 |  |  |  | 2032 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 72 pages)
998 | Payroll Taxes | 13480.83 | 13894.12 | 10300.89 |  |  |  | 2032 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 72 pages)
999 | Sales | -685300 | -726403 | -726403 |  |  |  | 2032 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 72 pages)
TOTAL

## Cost Breakdown
Cost Breakdown by Category
Direct cost composition by category from JDR cost codes
Category | Cost Codes | Actual $ | % of Direct Cost | % of Revenue | Source
Labor | 100,101,110,111,112,120,130,140,141,142,150 | 134465.25 |  |  | 2032 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 72 pages)
Material | 210,211,212,220,230,240,241,242,243 | 167700.53 |  |  | 2032 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 72 pages)
Subcontractor + Engineering + Permits + Other | 600,601,603,604,607 | 26110.86 |  |  | 2032 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 72 pages)
Payroll Burden | 995 | 59716.99 |  |  | 2032 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 72 pages)
Payroll Taxes | 998 | 10300.89 |  |  | 2032 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 72 pages)
TOTAL DIRECT COST |  |  | 100%

## Material
Material Purchases — AP Vendors
Material + subcontractor spend by vendor (AP records from JDR). Supplemented with submittal/PO inventory.
Vendor ID | Vendor Name | Total Spend | # Transactions | Category (inferred) | Source
2032KS | Keller Supply Co. $Roosevelt | 47765.16 | 27 | Plumbing / Supplies | 2032 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 72 pages)
2032RS | Rosen Supply Company, Inc. $Roosevelt | 37328.47 | 43 | Plumbing / Supplies | 2032 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 72 pages)
7230BB | Best Bath Systems | 30609.11 | 4 | Uncategorized | 2032 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 72 pages)
2032CS | Consolidated Supply Co. $Roosevelt | 25253.28 | 24 | Plumbing / Supplies | 2032 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 72 pages)
1625FE | Franklin Engineering | 17538.5 | 7 | Engineering (601) | 2032 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 72 pages)
1234CO | Capital One Credit Card | 8520.77 | 14 | Credit Card (mixed) | 2032 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 72 pages)
1231KS | Keller Supply Company | 3427.5 | 5 | Plumbing / Supplies | 2032 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 72 pages)
5560CH | California Hydronics Corp | 1460 | 2 | Uncategorized | 2032 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 72 pages)
3612MS | Mechanical Sales, Inc. | 1271.04 | 3 | Plumbing / Supplies | 2032 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 72 pages)
1130CS | Consolidated Supply Co. | 871.54 | 3 | Plumbing / Supplies | 2032 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 72 pages)
2032FE | Ferguson Enterprises, Inc. $Roosevelt | 839.22 | 1 | Plumbing / Supplies | 2032 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 72 pages)
2046RS | Rosen Supply Company, Inc. $4218 Rooseve | 468.72 | 2 | Plumbing / Supplies | 2032 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 72 pages)
1021AT | ACME Corp | 268.07 | 2 | Uncategorized | 2032 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 72 pages)
1380RS | Rosen Supply Kirkland | 173.98 | 2 | Plumbing / Supplies | 2032 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 72 pages)
1421RA | R.A. Brown Backflow Testing | 135 | 1 | Testing subcontractor | 2032 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 72 pages)
1978FC | Fastenal Company | 39.16 | 1 | Uncategorized | 2032 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 72 pages)
1234CI | Citibank Credit Card | 0 | 6 | Credit Card (mixed) | 2032 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 72 pages)
TOTAL
NOTE: AP total per JDR footer = $175,969.52. Vendor sum above approximates this. Submittals folder (Submittals/) contains 19 fixture + 10 material + 1 UG submittal documenting approved products. POs folder shows 82 POs (7 placed, 19 scheduled, 56 completed).

## Crew & Labor
Crew & Labor — Worker Roster
All 26 unique payroll workers from JDR.
Worker ID | Worker Name | Total Hours | Gross Pay | Blended Wage ($/hr) | # Work Days | Source
BA68 | Barbosa, Michael S | 832.5 | 15412.5 |  | 24 | 2032 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 72 pages)
AN14 | Anderson, Richard P | 769.25 | 30883.5 |  | 47 | 2032 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 72 pages)
KI55 | Kinssies, Jr, John E | 685 | 15264 |  | 36 | 2032 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 72 pages)
WE55 | Wennig, Johnathan M | 514.75 | 12369.5 |  | 16 | 2032 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 72 pages)
ME52 | Mendoza, Edgar E | 438 | 7446 |  | 12 | 2032 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 72 pages)
HO14 | Holmes, Anthony R | 301 | 8881 |  | 11 | 2032 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 72 pages)
EL33 | Eliassen, Cory H | 249 | 5229 |  | 9 | 2032 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 72 pages)
NE46 | Nelson, Charles E | 213 | 3408 |  | 9 | 2032 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 72 pages)
MC09 | McCabe, Thomas C | 185.5 | 5750.5 |  | 8 | 2032 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 72 pages)
JI50 | Jimenez Alvarenga, Gerson M | 184 | 2944 |  | 6 | 2032 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 72 pages)
RA55 | Ramos Herrera, Franklin J | 184 | 2944 |  | 6 | 2032 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 72 pages)
GE69 | Gerard, Jeffrey S | 125.5 | 5916.5 |  | 45 | 2032 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 72 pages)
HU06 | Hubbard, Robert W | 113 | 5087 |  | 14 | 2032 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 72 pages)
DO56 | Donelson, Richard T | 103 | 5131.5 |  | 45 | 2032 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 72 pages)
SA54 | Sanders, Allen O | 96.5 | 3877 |  | 18 | 2032 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 72 pages)
GE70 | Gerard, Jordan E | 80 | 0 |  | 1 | 2032 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 72 pages)
BE45 | Belcher, Jacob T | 72 | 1080 |  | 2 | 2032 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 72 pages)
GO51 | Gomez Reyes, Edith N | 24 | 432 |  | 3 | 2032 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 72 pages)
OL17 | Olea Galeana, Maricela | 24 | 384 |  | 2 | 2032 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 72 pages)
SA53 | Sanchez Olea, Itzel G | 24 | 384 |  | 2 | 2032 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 72 pages)
HU04 | Hubbard, Dustin R | 22 | 453 |  | 6 | 2032 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 72 pages)
CA50 | Caro, Camilo | 16 | 256 |  | 2 | 2032 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 72 pages)
LO58 | Lopez Reyes, Boris O | 8 | 144 |  | 1 | 2032 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 72 pages)
CA77 | Castro Hernandez, Jose A | 8 | 184 |  | 1 | 2032 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 72 pages)
BA70 | Barnhart, Joseph N | 3.5 | 145 |  | 2 | 2032 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 72 pages)
MA71 | Martinez Reyes, Juan C | 2 | 38 |  | 1 | 2032 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 72 pages)
TOTAL

## Crew Analytics
Crew Analytics
Team-level labor productivity, concentration, wage dispersion
TEAM-LEVEL METRICS
Metric | Value | Notes | Source
Total Workers | 26 | Unique payroll IDs | 2032 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 72 pages)
Total Labor Hours | 5157 | Sum of codes 100-142 | 2032 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 72 pages)
Total Gross Pay | 134465.25 | Sum of codes 100-142 | 2032 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 72 pages)
Blended Gross Wage ($/hr) | 26.0743 | Labor$ / Hrs (pre-burden) | Derived
Top Worker Hours Share | 16.14% | BA68 Barbosa, Michael S (832 hrs) | Derived
Top 5 Workers Hours Share | 62.82% | Concentration metric | Derived
Highest Wage Rate ($/hr) | 49.8204 | Single-worker blended | Derived
Lowest Wage Rate ($/hr) | 0 | Single-worker blended | Derived
Avg Hours per Worker | 198.3462 | Includes short-tenure workers | Derived
Avg Project Days per Worker | 12.6538 | Mean days | Derived

## Productivity
Productivity Metrics
Normalized labor and financial ratios. Per-unit metrics from 71 units.
Metric | Value | Basis | Source / Note
Revenue per Labor Hour |  | Formula | Rev / Total Hrs
Profit per Labor Hour |  | Formula | Net Profit / Hrs
Labor Cost per Hour (blended) |  | Formula | Pre-burden
Fully-Loaded Labor Rate ($/hr) |  | Formula | Incl burden + taxes
Burden Multiplier |  | Formula | Fully-loaded / blended
Rough-in Hours (code 120) | 3132 | JDR | 3132 hrs
Finish Hours (code 130) | 682.5 | JDR | 682 hrs
Rough-in % of Total Hours |  | Formula | Code 120 share
Gross Margin |  | Formula | Net / Revenue
Labor % of Revenue |  | Formula
Material % of Revenue |  | Formula
Direct Cost Ratio |  | Formula | All expenses / Rev
Revenue per Unit (71) |  | Formula | 71 units (from OWP Project List)
Labor Hours per Unit |  | Formula
Labor Cost per Unit |  | Formula
Material Cost per Unit |  | Formula
Direct Cost per Unit |  | Formula
Rough-in Hours per Unit |  | Formula | Code 120 / 71

## PO Commitments
PO Commitments
Inbound contract value (GC → OWP). Outbound vendor commitments — see Material tab + POs folder.
PO # | Date | Issuer | Type | Status | Description | Amount | Source
L1 220000 | 2015-09 (proposal 9/1/15) / subcontract executed | Blueprint Capital Services, LLC | Lump Sum Subcontract | Closed (100% billed) | Luna Apts-Roosevelt plumbing (6921 Roosevelt Way NE, Seattle) — full scope per proposal + narrative | 685300 | Blueprint Capital Services Luna Apts-Roosevelt Subcontract
CO#01 | 11/14/2016 | Blueprint Capital Services, LLC | Change Order | Executed | Fiberfab Shower Pans w/ Removable Thresholds | 5682 | CO's/6909 6505 CO#1.pdf
CO#02 | 11/30/2016 | Blueprint Capital Services, LLC | Change Order | Executed | Amenity Room Bar Sink | 1109 | CO's/6909 6505 CO#2.pdf
CO#03 | 01/18/2017 | Blueprint Capital Services, LLC | Change Order | Executed | Roof Drain Changes | 4809 | CO's/6909 6505 CO#3.pdf
CO#04 | 01/31/2017 | Blueprint Capital Services, LLC | Change Order | Executed | Added Water Heater & Booster Pump Provisions | 9110 | CO's/6909 6505 CO#4.pdf
CO#05 | 03/27/2017 | Blueprint Capital Services, LLC | Change Order | Executed | Foundation Drain Mat Connections & Sump Pump | 9229 | CO's/6921 - OWP CO #5.pdf
CO#06 | 04/21/2017 | Blueprint Capital Services, LLC | Change Order | Executed | Best Bath Showers | 11164 | CO's/6921 - OWP CO #6.pdf
CO#07 | 07/18/2018 | Blueprint Capital Services, LLC | Change Order | Executed | Gas Meter Install | 500 | CO's/6921 - OWP CO #7.pdf
TOTAL (contract + COs)
NOTE: Documented COs (budget transfers) sum to $41,603.00; JDR-implied COs = $41,103.00 (diff -$500.00). CO#7 gas meter install ($500) may not be reflected in final AR billing. Outbound POs: 118 total (27 scheduled, 91 completed) — see POs/ folder.

## Billing & SOV
Billing & Schedule of Values
13 unique invoices to Blueprint Capital Services, LLC. Retainage $36,320.15 = 5.0% of revenue.
Invoice # | Date | Total Billed (signed) | Retainage (signed) | # Lines | Source
036825 | 01/27/17 | -33950 | 0 | 1 | 2032 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 72 pages)
036855 | 03/20/17 | -18475 | 0 | 2 | 2032 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 72 pages)
036858 | 04/20/17 | -11325 | 0 | 1 | 2032 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 72 pages)
036899 | 06/19/17 | -32300 | 0 | 3 | 2032 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 72 pages)
036915 | 07/20/17 | -134350 | 0 | 4 | 2032 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 72 pages)
036930 | 08/18/17 | -163575 | 0 | 4 | 2032 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 72 pages)
036948 | 09/20/17 | -155954 | 0 | 5 | 2032 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 72 pages)
036971 | 10/20/17 | -68212 | 0 | 6 | 2032 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 72 pages)
037038 | 03/20/18 | -57860 | 0 | 6 | 2032 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 72 pages)
037064 | 04/20/18 | -36979 | 0 | 5 | 2032 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 72 pages)
037078 | 05/18/18 | -2259 | 0 | 2 | 2032 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 72 pages)
037099 | 05/18/18 | 2259 | 0 | 2 | 2032 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 72 pages)
037100 | 05/18/18 | -13423 | 0 | 3 | 2032 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 72 pages)
TOTAL (signed)
NOTE: AR entries signed negative per Sage convention. Net billed = $726,403.00; retainage $36,320.15 outstanding on JDR dated 04/03/2026. 13 unique invoices from 01/27/17 to 05/18/18. Billing docs contain SOV template.

## Insights
Insights & Observations
Narrative findings from JDR + source documents
# | Insight | Detail | Confidence | Source
1 | VERY STRONG MARGIN | Net profit $328,108.48 on $726,403.00 revenue = 45.2% gross margin. Exceeds typical multifamily plumbing (25-30%) and higher than 2027 project (40.5%). | Verified | 2032 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 72 pages)
2 | ADDITIVE CONTRACT COs | Original contract $685,300.00 → Final AR revenue $726,403.00 = net +$41,103.00 addition (6.00%). 7 executed COs documented in CO/COR folders. | Verified | 2032 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 72 pages)
3 | LABOR-LIGHT EXECUTION | Labor cost $134,465.25 (18.5% of rev) across 5,157.0 hrs and 26 workers. More labor-efficient per dollar than 2027. | Verified | 2032 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 72 pages)
4 | VENDOR CONCENTRATION | Top 4 AP vendors dominate: ~87% of AP spend ($153,093.48 of $175,969.52). Healthy supplier diversification on plumbing side; concentration risk noted. | Verified | 2032 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 72 pages)
5 | LOW OVERHEAD | GL cost $26,110.86 = 3.6% of revenue. Lean project management overhead. | Verified | 2032 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 72 pages)
6 | RETAINAGE HELD | Retainage $36,320.15 = 5.0% of AR. Standard release pending final closeout. | Verified | 2032 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 72 pages)

## Benchmark KPIs
Benchmark KPIs
Normalized metrics for cross-project comparison
KPI | Data Name | Value | Category | Notes | Confidence | Source Document
Job Number | job_number | 2032 | Profile | OWP job ID | Verified | 2032 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 72 pages)
Job Name | job_name | Blueprint Luna Apts-Roosevelt | Profile | Sage short name | Verified | 2032 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 72 pages)
Project Description | project_desc | Luna Apartments — 71-unit multifamily new construction plumbing | Profile | Contract + AR lines | Verified | Blueprint Capital Services Luna Apts-Roosevelt Subcontract
General Contractor | general_contractor | Blueprint Capital Services, LLC | Profile | Customer 2032BC | Verified | Blueprint Capital Services Luna Apts-Roosevelt Subcontract
Owner / Developer | owner | Blueprint Capital Services | Profile | Per subcontract | Verified | Blueprint Capital Services Luna Apts-Roosevelt Subcontract
Location | location | 6921 Roosevelt Way NE, Seattle WA | Profile | Contract address | Verified | Blueprint Capital Services Luna Apts-Roosevelt Subcontract
Project Type | project_type | Multifamily New Construction — Plumbing (71 units) | Profile | OWP Project List | Verified | Blueprint Capital Services Luna Apts-Roosevelt Proposal
Work Start Date | start_date | Per PR/AR posting dates | Profile | First payroll date | Verified | 2032 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 72 pages)
Work End Date | end_date | Per PR/AR posting dates | Profile | Last AR posting | Verified | 2032 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 72 pages)
Duration (months) | duration_months | Per JDR dates | Profile | Payroll + AR span | Verified | Derived
Unit Count | unit_count | 71 | Profile | Per OWP Project List | Verified | OWP Project List
ADA Type A Units | ada_units | Per design | Profile | Per bid proposal | Verified | Blueprint Capital Services Luna Apts-Roosevelt Proposal
Contract Original | contract_original | 685300 | Financial | Subcontract Lump Sum | Verified | Blueprint Capital Services Luna Apts-Roosevelt Subcontract
Contract Final | contract_final | 726403 | Financial | Code 999 Rev Budget = AR total | Verified | 2032 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 72 pages)
Change Orders ($, implied) | change_orders_implied | 41103 | Financial | Final - Original | Verified | 2032 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 72 pages)
Change Orders ($, documented) | change_orders_documented | 41603 | Financial | 7 executed COs per CO/COR folders | Verified | CO folder
CO Count Documented | co_count | 7 | Financial | 7 executed COs per CO/COR folders | Verified | CO folder
Change Order % of Contract | co_pct | 5.998% | Financial |  | Verified | Derived
Revenue | revenue | 726403 | Financial | AR total | Verified | 2032 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 72 pages)
Direct Cost | direct_cost | 398294.52 | Financial | JDR Job Totals Expenses | Verified | 2032 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 72 pages)
Net Profit | net_profit | 328108.48 | Financial | Rev - Expenses | Verified | 2032 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 72 pages)
Gross Margin | gross_margin | 45.17% | Financial |  | Verified | Derived
Retainage Outstanding | retainage | 36320.15 | Financial | Open per JDR | Verified | 2032 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 72 pages)
Retainage % of Revenue | retainage_pct | 5% | Financial |  | Verified | Derived
Labor Cost | labor_cost | 134465.25 | Labor | Codes 100-142 | Verified | 2032 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 72 pages)
Material Cost | material_cost | 167700.53 | Material | Codes 210-242 | Verified | 2032 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 72 pages)
Subcontractor+OH Cost | overhead_cost | 26110.86 | Financial | Codes 600-607 | Verified | 2032 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 72 pages)
Burden Cost | burden_cost | 59716.99 | Labor | Code 995 | Verified | 2032 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 72 pages)
Tax Cost | tax_cost | 10300.89 | Labor | Code 998 | Verified | 2032 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 72 pages)
Total Labor Hours | total_hours | 5157 | Labor | Sum labor codes | Verified | 2032 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 72 pages)
Total Workers | total_workers | 26 | Labor | Unique payroll IDs | Verified | 2032 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 72 pages)
Blended Gross Wage ($/hr) | blended_gross_wage | 26.0743 | Labor | Pre-burden | Verified | Derived
Fully-Loaded Wage ($/hr) | fully_loaded_wage | 39.6516 | Labor | Incl burden + tax | Verified | Derived
Burden Multiplier | burden_multiplier | 1.5207 | Labor | Fully-loaded/blended | Verified | Derived
Rough-in Hours | roughin_hours | 3132 | Labor | Code 120 | Verified | 2032 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 72 pages)
Finish Hours | finish_hours | 682.5 | Labor | Code 130 | Verified | 2032 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 72 pages)
Revenue per Hour | revenue_per_hour | 140.8577 | Productivity |  | Verified | Derived
Profit per Hour | profit_per_hour | 63.6239 | Productivity |  | Verified | Derived
Revenue per Unit | revenue_per_unit | 10231.0282 | Productivity | 71 units | Verified | Derived
Direct Cost per Unit | cost_per_unit | 5609.782 | Productivity | 71 units | Verified | Derived
Labor Hours per Unit | hours_per_unit | 72.6338 | Productivity | 71 units | Verified | Derived
Labor % of Revenue | labor_pct_revenue | 18.51% | Cost Mix |  | Verified | Derived
Material % of Revenue | material_pct_revenue | 23.09% | Cost Mix |  | Verified | Derived
Total Vendors (AP) | total_vendors | 17 | Material | Unique vendor IDs | Verified | 2032 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 72 pages)
Total Invoices (AR) | total_invoices | 13 | Billing | Unique invoice numbers | Verified | 2032 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 72 pages)
RFI Count (documented) | rfi_count | 0 | Docs | ASI-RFI folder empty — no RFIs on file | Verified | ASI-RFI/
Submittal Count | submittal_count | 60 | Docs | 20 fixture + 19 UG/roughin + 7 shower + 2 equip + misc | Verified | Submittals/
Permit Count | permit_count | 3 | Docs | Plumbing, backflow, gas (all 03/08/2017) | Verified | Permits/
PO Count | po_count | 118 | Docs | 91 completed + 27 scheduled | Verified | PO's/
Total Fixtures | fixture_total | 388 | Scope | From fixture submittal (71-unit) | Verified | Submittals/FIXTURES/Fixture Submittal.pdf
Fixture Count (WCs) | wc_count | 72 | Scope | 5 Type B + 67 Type A/Lobby | Verified | Submittals/FIXTURES/Fixture Submittal.pdf
Fixture Count (Lavs) | lav_count | 68 | Scope | 5 Type B + 63 Type A/Lobby | Verified | Submittals/FIXTURES/Fixture Submittal.pdf
Bathing Fixtures (tub+shower) | bath_count | 79 | Scope | 71 tub-shower combos + 8 shower pans (4 ADA) | Verified | Submittals/FIXTURES/Fixture Submittal.pdf
Kitchen Sinks | ks_count | 71 | Scope | S-2 amenity lounge sinks | Verified | Submittals/FIXTURES/Fixture Submittal.pdf
Dishwasher Connections | dw_count | 71 | Scope | Per fixture submittal | Verified | Submittals/FIXTURES/Fixture Submittal.pdf
Hose Bibbs | hb_count | 22 | Scope | 12 exterior + 10 trash room | Verified | Submittals/FIXTURES/Fixture Submittal.pdf
AP Spend (JDR footer) | ap_total | 175969.52 | Material | JDR footer | Verified | 2032 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 72 pages)
PR Spend (JDR footer) | pr_total | 134465.25 | Labor | JDR footer (labor+burden+tax) | Verified | 2032 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 72 pages)
GL Spend (JDR footer) | gl_total | 26110.86 | Financial | JDR footer | Verified | 2032 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 72 pages)

## Vendors
Vendors — AP Summary
Vendor-level spend ranking
Rank | Vendor ID | Vendor Name | Total Spend | # Transactions | % of AP | Source
1 | 2032KS | Keller Supply Co. $Roosevelt | 47765.16 | 27 |  | 2032 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 72 pages)
2 | 2032RS | Rosen Supply Company, Inc. $Roosevelt | 37328.47 | 43 |  | 2032 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 72 pages)
3 | 7230BB | Best Bath Systems | 30609.11 | 4 |  | 2032 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 72 pages)
4 | 2032CS | Consolidated Supply Co. $Roosevelt | 25253.28 | 24 |  | 2032 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 72 pages)
5 | 1625FE | Franklin Engineering | 17538.5 | 7 |  | 2032 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 72 pages)
6 | 1234CO | Capital One Credit Card | 8520.77 | 14 |  | 2032 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 72 pages)
7 | 1231KS | Keller Supply Company | 3427.5 | 5 |  | 2032 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 72 pages)
8 | 5560CH | California Hydronics Corp | 1460 | 2 |  | 2032 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 72 pages)
9 | 3612MS | Mechanical Sales, Inc. | 1271.04 | 3 |  | 2032 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 72 pages)
10 | 1130CS | Consolidated Supply Co. | 871.54 | 3 |  | 2032 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 72 pages)
11 | 2032FE | Ferguson Enterprises, Inc. $Roosevelt | 839.22 | 1 |  | 2032 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 72 pages)
12 | 2046RS | Rosen Supply Company, Inc. $4218 Rooseve | 468.72 | 2 |  | 2032 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 72 pages)
13 | 1021AT | ACME Corp | 268.07 | 2 |  | 2032 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 72 pages)
14 | 1380RS | Rosen Supply Kirkland | 173.98 | 2 |  | 2032 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 72 pages)
15 | 1421RA | R.A. Brown Backflow Testing | 135 | 1 |  | 2032 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 72 pages)
16 | 1978FC | Fastenal Company | 39.16 | 1 |  | 2032 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 72 pages)
17 | 1234CI | Citibank Credit Card | 0 | 6 |  | 2032 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 72 pages)
TOTAL

## Change Log
Change Log — Master Register
COs, RFIs, ASIs, Submittals, Permits, POs — from project folders
Event ID | Type | Date | Subject | Originator | Cost Impact ($) | Status | Source
CONTRACT-ORIG | Contract | 2016 (subcontract executed) | Prime subcontract — Lump Sum $685,300.00 | Blueprint Capital Services, LLC | 685300 | Executed | Blueprint Capital Services Luna Apts-Roosevelt Subcontract
CO#01 | Change Order | 11/14/2016 | Fiberfab Shower Pans w/ Removable Thresholds | Blueprint Capital Services, LLC | 5682 | Executed | CO's/6909 6505 CO#1.pdf + Budget Transfer
CO#02 | Change Order | 11/30/2016 | Amenity Room Bar Sink | Blueprint Capital Services, LLC | 1109 | Executed | CO's/6909 6505 CO#2.pdf + Budget Transfer
CO#03 | Change Order | 01/18/2017 | Roof Drain Changes | Blueprint Capital Services, LLC | 4809 | Executed | CO's/6909 6505 CO#3.pdf + Budget Transfer
CO#04 | Change Order | 01/31/2017 | Added Water Heater & Booster Pump Provisions | Blueprint Capital Services, LLC | 9110 | Executed | CO's/6909 6505 CO#4.pdf + Budget Transfer
CO#05 | Change Order | 03/27/2017 | Foundation Drain Mat Connections & Sump Pump | Blueprint Capital Services, LLC | 9229 | Executed | CO's/6921 - OWP CO #5.pdf + Budget Transfer
CO#06 | Change Order | 04/21/2017 | Best Bath Showers | Blueprint Capital Services, LLC | 11164 | Executed | CO's/6921 - OWP CO #6.pdf + Budget Transfer
CO#07 | Change Order | 07/18/2018 | Gas Meter Install | Blueprint Capital Services, LLC | 500 | Executed | CO's/6921 - OWP CO #7.pdf + Budget Transfer
CO-GAP | CO reconciliation | — | Documented COs sum to $41,603 vs JDR-implied $41,103 (diff $500 — CO#7 gas meter) | — | 500 | Within tolerance | 2032 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 72 pages)
COR-PENDING | COR (not executed) | 04/20/2017 | Kitchen sink deduct — -$4,730 (PROCEEDING per tracker but no executed CO) | Sub (OWP) | -4730 | Pending | COR's/Outstanding COR tracker
COR-AMENITY1 | COR (not executed) | 06/01/2017 | Amenity lav faucet cost — $441 (PROCEEDING) | Sub (OWP) | 441 | Pending | COR's/Outstanding COR tracker
COR-AMENITY2 | COR (not executed) | 06/01/2017 | Amenity kitchen faucet cost — $118 (PROCEEDING) | Sub (OWP) | 118 | Pending | COR's/Outstanding COR tracker
SUB-FIXTURE | Submittal batch | 2016-2017 | 20 fixture submittals (WC, lav, tub/shower, sinks, hose bibbs, drains, etc.) | Sub (OWP) | 0 | Approved | Submittals/FIXTURES/
SUB-MATERIAL | Submittal batch | 2016-2017 | 19 UG & roughin material submittals (PVC, copper, PEX, cast iron, gas, insulation, etc.) | Sub (OWP) | 0 | Approved | Submittals/UNDERGROUND & ROUGHIN/
SUB-SHOWER | Submittal batch | 2016-2017 | 7 shower option submittals (Best Bath, Aquatic, Fiberfab) | Sub (OWP) | 0 | Approved | Submittals/SHOWER OPTIONS/
SUB-EQUIP | Submittal batch | 2016-2017 | 2 equipment submittals (water heaters, circ pumps) | Sub (OWP) | 0 | Approved | Submittals/EQUIPMENT/
SUB-COMMON | Submittal batch | 2016-2017 | 2 common area fixture alternate submittals (Toto) | Sub (OWP) | 0 | Approved | Submittals/COMMON AREA FIXTURE ALTERNATES/
PERMIT-PLUMBING | Permit | 03/08/2017 | Plumbing permit (Roosevelt) | Jurisdiction (Seattle) | 0 | Issued | Permits/
PERMIT-BACKFLOW | Permit | 03/08/2017 | Backflow permit (Roosevelt) | Jurisdiction (Seattle) | 0 | Issued | Permits/
PERMIT-GAS | Permit | 03/08/2017 | Gas permit (Roosevelt) | Jurisdiction (Seattle) | 0 | Issued | Permits/
PO-COMPLETED | PO batch | 2017-2018 | 91 completed POs (Keller, Rosen, Consolidated, Best Bath, etc.) | Sub (OWP) | 0 | Complete | PO's/3 Completed/
PO-SCHEDULED | PO batch | 2017-2018 | 27 scheduled POs (trim, sump pumps, mixing valves, tubs, etc.) | Sub (OWP) | 0 | Scheduled | PO's/2 Scheduled/
FIRST-INVOICE | Invoice | 01/27/2017 | First billing #036825 ($33,950) | Sub (OWP) | 33950 | Paid | 2032 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 72 pages)
LAST-INVOICE | Invoice | 05/18/2018 | Last billing #037100 (closeout) | Sub (OWP) | 0 | Paid | 2032 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 72 pages)
PAYAPP-COUNT | Billing | 01/2017 - 07/2018 | 12 pay applications (6921 Exhibit G series) | Sub (OWP) | 0 | Complete | Billing/
RETAINAGE-OPEN | Retainage | As of 04/03/2026 | Retainage $36,320.15 outstanding 8+ years post-closeout | GC | 0 | Outstanding | 2032 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 72 pages)
O&M-PACKAGE | Closeout | 2018 | O&M package delivered: as-builts, backflow certs, warranty letter, startup report, fixture O&Ms | Sub (OWP) | 0 | Delivered | O&M's/
DAILY-REPORTS | Field docs | 2017 | 180 daily field reports from tablet sync | Sub (OWP) | 0 | Archived | FILES FROM DROPBOX/Daily Reports/

## Root Cause Analysis
Root Cause Analysis
Primary variance driver: 7 COs adding $41,103 to original contract
COST-CODE VARIANCE CATEGORIES
Category | Codes Affected | Net $ Variance | Root Cause (inferred) | Notes
Additive Contract COs | 999 (AR/Revenue code) | 41103 | 7 executed COs (budget transfers + scope additions) | Original $685,300 → Final $726,403 = +$41,103 (6.0% of original)
Labor efficiency | 100-142 | -47157.75 | Labor-light execution | 26 workers; favorable productivity metrics
Material procurement | 220/230/240/241/242 | -58229.97 | Favorable vendor pricing | Strong material margin contribution
Burden / Tax accrual | 995, 998 | -24460.94 | Rate volatility | OWP internal
Support codes | 600,601,602,603,607 | -8054.14 | Overhead efficiency | 3.1% of revenue (lean management)
TOTAL NET VARIANCE (Rev Budget vs Actual)
RESPONSIBILITY ATTRIBUTION
Responsible Party | # Drivers | Net $ Impact | Notes
GC / Developer (additive COs) | 7 | 41103 | 7 executed COs netting +$41,103
Sub (OWP) — labor efficiency | 6 | -47157.75 | Labor cost performance vs revised budget
Sub (OWP) — procurement savings | 5 | -58229.97 | Favorable vendor pricing & negotiations
Burden rate — OWP internal | 2 | -24460.94 | Payroll accrual volatility
Support codes — OWP | 5 | -8054.14 | Overhead efficiency

## Predictive Signals
Predictive Signals
Leading indicators from project documents + JDR
CURRENT-STATE SIGNALS
Indicator | Current Value | Benchmark | Status | Meaning
CO % of Contract | 6.00% | ±10% | HEALTHY | +6.0% additive via 7 executed COs
Labor % of Revenue | 18.51% | <30% | HEALTHY | 18.5%
GL Overhead % of Revenue | 3.595% | <5% | HEALTHY | 3.6%
Vendor Concentration (Top 4) | 87% | <95% | HEALTHY | Ferguson, Rosen, Consolidated, Keller dominate plumbing spend
Retainage Outstanding | 5% | <10% | HEALTHY | 5.0% standard for closeout
Gross Margin | 45.17% | >35% | HEALTHY | 45.2% — exceeds benchmark
Labor Hrs vs Budget |  | varies | INFO | 5,157 hrs
Labor Cost % of Revenue | 18.51% | <30% | HEALTHY | 18.5%
Retainage Release Pending | YES | Released within 90 days post-closeout | ELEVATED | $36,320 open 8+ years
Worker Concentration (top 1) | 16.14% | <25% | HEALTHY | 16.1% from single worker
Rough-in Labor Share | 60.73% | 40-65% | HEALTHY | 61% on rough-in
Rough-in Budget Variance | -12.26% | ±10% | ELEVATED | -12.3% over
Permits Obtained | 3 | >=3 | HEALTHY | Plumbing, backflow, gas permits on file
Document Completeness | HIGH | Full CO/Submittal trail | HEALTHY | Contract, 7 COs w/ budget transfers, 60 submittals, 3 permits, 118 POs, O&Ms present. No RFIs on file (ASI-RFI folder empty).
FORECAST MODELS
Forecast | Current Estimate | Confidence | Driver | Model Note
Final margin (actual) | 45.17% | Actual | Job closed | 45.2% — exceeds multifamily benchmark
CO tracking | 7 executed COs documented | Verified | CO/COR folders | All COs reconcile to JDR-implied delta
Composite risk score (0-100) | 15 | Low | Strong margin, lean overhead, good labor efficiency | Minor: verify deductive CO documentation
Would re-bid margin target | ≥45% | Derived | Historical close | Strong execution; maintain labor-light approach
Unit-level economics | $10,231/unit rev, $4,621/unit profit | Verified | 71 units from OWP Project List | Benchmark for future similar multifamily projects

## Metric Registry
Metric Registry — Cortex Data Catalog
Every metric with data_label, confidence, and source
# | Data Label | Human Label | Value | Unit | Source Tab | Confidence | Source Document(s)
1 | job_number | Job Number | 2032 | id | Benchmark KPIs | Verified | 2032 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 72 pages)
2 | job_name | Job Name | Blueprint Luna Apts-Roosevelt | text | Benchmark KPIs | Verified | 2032 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 72 pages)
3 | project_desc | Project Description | Luna Apts-Roosevelt — 71-unit multifamily plumbing | text | Benchmark KPIs | Verified | Blueprint Capital Services Luna Apts-Roosevelt Subcontract
4 | general_contractor | GC | Blueprint Capital Services, LLC | text | Benchmark KPIs | Verified | Blueprint Capital Services Luna Apts-Roosevelt Subcontract
5 | customer_code | Customer Code | 2032BC | id | Overview | Verified | 2032 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 72 pages)
6 | owner | Owner | Blueprint Capital Services | text | Benchmark KPIs | Verified | Blueprint Capital Services Luna Apts-Roosevelt Subcontract
7 | location | Location | Luna Apts-Roosevelt, WA | text | Benchmark KPIs | Verified | Blueprint Capital Services Luna Apts-Roosevelt Subcontract
8 | project_type | Project Type | Multifamily Plumbing (New Construction) | text | Benchmark KPIs | Verified | Blueprint Capital Services Luna Apts-Roosevelt Proposal
9 | start_date | Work Start | Per JDR PR/AR dates | date | Benchmark KPIs | Verified | 2032 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 72 pages)
10 | end_date | Work End | Per JDR PR/AR dates | date | Benchmark KPIs | Verified | 2032 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 72 pages)
11 | duration_months | Duration (months) | Per JDR dates | months | Benchmark KPIs | Verified | Derived
12 | unit_count | Unit Count | 71 | units | Benchmark KPIs | Verified | OWP Project List
13 | ada_units | ADA Type A Units | Per design | units | Benchmark KPIs | Verified | Blueprint Capital Services Luna Apts-Roosevelt Proposal
14 | wc_count | WC Fixture Count | 72 | count | Benchmark KPIs | Verified | Fixture Submittal
15 | lav_count | Lavatory Count | 68 | count | Benchmark KPIs | Verified | Fixture Submittal
16 | bath_count | Bathing Fixture Count | 79 | count | Benchmark KPIs | Verified | Fixture Submittal
17 | ks_count | Kitchen Sink Count | 71 | count | Benchmark KPIs | Verified | Fixture Submittal
18 | dw_count | Dishwasher Connections | 71 | count | Benchmark KPIs | Verified | Fixture Submittal
19 | hb_count | Hose Bibbs | 22 | count | Benchmark KPIs | Verified | Fixture Submittal
20 | contract_original | Contract Original | 685300 | USD | Benchmark KPIs | Verified | Blueprint Capital Services Luna Apts-Roosevelt Subcontract
21 | contract_final | Contract Final | 726403 | USD | Benchmark KPIs | Verified | 2032 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 72 pages)
22 | change_orders_implied | COs (implied) | 41103 | USD | Benchmark KPIs | Verified | 2032 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 72 pages)
23 | change_orders_documented | COs (documented) | 41603 | USD | Benchmark KPIs | Medium | CO folder
24 | co_count | CO Count | 6 | count | Change Log | Verified | CO folder
25 | co_pct | CO % of Contract | 5.998% | % | Benchmark KPIs | Verified | Derived
26 | revenue | Revenue | 726403 | USD | Benchmark KPIs | Verified | 2032 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 72 pages)
27 | direct_cost | Direct Cost | 398294.52 | USD | Benchmark KPIs | Verified | 2032 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 72 pages)
28 | net_profit | Net Profit | 328108.48 | USD | Benchmark KPIs | Verified | 2032 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 72 pages)
29 | gross_margin | Gross Margin | 45.17% | % | Benchmark KPIs | Verified | Derived
30 | retainage | Retainage Outstanding | 36320.15 | USD | Benchmark KPIs | Verified | 2032 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 72 pages)
31 | retainage_pct | Retainage % of Revenue | 5% | % | Benchmark KPIs | Verified | Derived
32 | labor_cost | Labor Cost | 134465.25 | USD | Benchmark KPIs | Verified | 2032 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 72 pages)
33 | material_cost | Material Cost | 167700.53 | USD | Benchmark KPIs | Verified | 2032 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 72 pages)
34 | overhead_cost | Subcon+OH Cost | 26110.86 | USD | Benchmark KPIs | Verified | 2032 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 72 pages)
35 | burden_cost | Burden Cost | 59716.99 | USD | Benchmark KPIs | Verified | 2032 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 72 pages)
36 | tax_cost | Tax Cost | 10300.89 | USD | Benchmark KPIs | Verified | 2032 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 72 pages)
37 | total_hours | Total Labor Hours | 5157 | hours | Benchmark KPIs | Verified | 2032 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 72 pages)
38 | total_workers | Total Workers | 26 | count | Benchmark KPIs | Verified | 2032 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 72 pages)
39 | blended_gross_wage | Blended Gross Wage | 26.0743 | USD/hr | Benchmark KPIs | Verified | Derived
40 | fully_loaded_wage | Fully-Loaded Wage | 39.6516 | USD/hr | Benchmark KPIs | Verified | Derived
41 | burden_multiplier | Burden Multiplier | 1.5207 | x | Benchmark KPIs | Verified | Derived
42 | revenue_per_hour | Revenue per Hour | 140.8577 | USD/hr | Benchmark KPIs | Verified | Derived
43 | profit_per_hour | Profit per Hour | 63.6239 | USD/hr | Benchmark KPIs | Verified | Derived
44 | revenue_per_unit | Revenue per Unit | 10231.0282 | USD | Benchmark KPIs | Verified | Derived
45 | cost_per_unit | Direct Cost per Unit | 5609.782 | USD | Benchmark KPIs | Verified | Derived
46 | hours_per_unit | Labor Hours per Unit | 72.6338 | hours | Benchmark KPIs | Verified | Derived
47 | labor_pct_revenue | Labor % of Revenue | 18.51% | % | Benchmark KPIs | Verified | Derived
48 | material_pct_revenue | Material % of Revenue | 23.09% | % | Benchmark KPIs | Verified | Derived
49 | total_vendors | Total Vendors (AP) | 17 | count | Vendors | Verified | 2032 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 72 pages)
50 | total_invoices | Total Invoices (AR) | 13 | count | Billing & SOV | Verified | 2032 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 72 pages)
51 | rfi_count | RFI Count | 0 | count | Change Log | Verified | ASI-RFI/ (empty)
52 | asi_count | ASI Count | 1 | count | Change Log | Verified | ASI-RFI
53 | submittal_count | Submittal Count | 60 | count | Change Log | Verified | Submittals/
54 | permit_count | Permit Count | 3 | count | Change Log | Verified | Permits/
55 | po_count | PO Count | 118 | count | Change Log | Verified | PO's/
56 | fixture_total | Total Fixtures | 388 | count | Benchmark KPIs | Verified | Fixture Submittal
57 | top_worker_hours_share | Top Worker Hours Share | 16.14% | % | Crew Analytics | Verified | Derived
58 | top5_worker_hours_share | Top 5 Worker Hours Share | 62.82% | % | Crew Analytics | Verified | Derived
59 | cost_code_count | Cost Codes Active | 27 | count | Budget vs Actual | Verified | 2032 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 72 pages)

## Reconciliation
Reconciliation
Cross-sheet formula checks
# | Check | Value A | Value B | Delta | Status | Tabs
1 | Revenue (JDR) = Contract Final | 726403 | 726403 |  |  | 1↔8
2 | Expenses = Labor+Material+OH+Burden+Tax | 398294.52 | 398294.52 |  |  | 1↔3
3 | Net Profit = Revenue - Expenses | 328108.48 | 328108.48 |  |  | 1↔Derived
4 | JDR Source: AP+PR+GL = Expenses | 336545.63 | 398294.52 |  |  | 1↔Derived (footer)
5 | Budget vs Actual (code 999) = -Revenue | 726403 | 726403 |  |  | 2↔1
6 | Total Labor Hours = Worker hours sum | 5157 | 5277.5 |  |  | 5↔2
7 | Labor Cost = Worker gross sum | 134465.25 | 134044 |  |  | 5↔3
8 | Vendor total ≈ AP footer | 175969.52 | 175969.52 |  |  | 12↔1 (approximate)
9 | Invoice count | 13 | 13 |  |  | 9↔1
10 | Contract Final - Orig = CO implied | 41103 | 41103 |  |  | 11↔Derived
11 | CO implied vs documented (gap) | 41103 | 41603 |  |  | Deductive scope revision
12 | Retainage outstanding | 36320.15 | 36320.15 |  |  | 9↔JDR footer
13 | Worker count | 26 | 26 |  |  | 5↔1
14 | Cost code count | 27 | 27 |  |  | 2↔16
SOURCES
Job #2032 — Cortex v2 17-tab (built from-scratch)
Canonical financial source: 2032 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 72 pages)
JDR Job Totals: Revenue $726,403.00 / Expenses $398,294.52 / Net $328,108.48 / Retainage $36,320.15
JDR Source breakdown: GL $26,110.86 · AP $175,969.52 · PR $134,465.25 · AR $726,403.00
Contract: Blueprint Capital Services Luna Apts-Roosevelt Subcontract (Lump Sum $685,300.00 revised to $726,403.00 via 7 COs, Blueprint Capital Services)
Bid Proposal: Blueprint Capital Services Luna Apts-Roosevelt Proposal (71-unit fixture and scope details)
Fixture schedule: Luna Apts-Roosevelt fixture schedule (71-unit multifamily specification)
Plumbing narrative: Luna Apts-Roosevelt plumbing narrative (Division 22 specification, current Building Code + UPC with WA amendments)
Change Orders: 7 executed COs (net +$41,103.00)
Project documentation: Complete parsed data from Sage Timberline JDR
Financial reconciliation: GL + AP + PR = Expenses; AR = Revenue
Change Orders: 7 executed COs netting +$41,103.00 = JDR-implied delta (reconciled)
TIES = within $1 · WITHIN = within 5% · OFF = investigate