## Overview
Job #2033 · Compass Vuecrest
Cortex JCR v2 • Compass Harbor Construction, LLC (customer 2033BV) • 1000 100th Ave NE, Bellevue, WA 98004 • Owner: Bellevue Vuecrest, LP (Developer: Continental)
PROJECT OVERVIEW
Project Job # | 2033 |  | 2033 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 191 pages) header
Project Name (Sage) | Compass Vuecrest |  | 2033 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 191 pages) header
Project Description | Vuecrest (LUX) — 137-unit luxury multifamily plumbing, Bellevue WA |  | Vuecrest-One Way Plumbing Fully Executed 9.26.16.pdf + Job Info sheet
General Contractor | Compass Harbor Construction, LLC |  | Vuecrest-One Way Plumbing Fully Executed 9.26.16.pdf
Customer Code (Sage) | 2033BV |  | 2033 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 191 pages)
Owner / Developer | Bellevue Vuecrest, LP (Developer: Continental) |  | Vuecrest-One Way Plumbing Fully Executed 9.26.16.pdf + Job Info
GC PM | Ryan Ames / Vince Dennison |  | Job Info sheet
GC Superintendent | Todd Mortenson |  | Job Info sheet
GC PE | Dan Peck |  | Job Info sheet
OWP Rough-in Foreman | Victor |  | Schedule tab
Jobsite Location | 1000 100th Ave NE, Bellevue, WA 98004 |  | Vuecrest-One Way Plumbing Fully Executed 9.26.16.pdf
Contract / PO Document | Vuecrest-One Way Plumbing Fully Executed 9.26.16.pdf |  | Lump Sum subcontract (Fully Executed 9/26/2016)
Insurance | Wrap (OCIP) |  | OCIP Enrollment Form + Insurance folder
Plans / Specifications | Vuecrest plumbing narrative / Div 22 spec (Div 22 plumbing) + P-tag fixture schedule + OWP drawings |  | Plans/ folder
Fixture Schedule | Vuecrest P-tag and equipment list working copy.xlsx (137-unit luxury multifamily) |  | Plans folder
Contract Type | Lump Sum |  | Vuecrest-One Way Plumbing Fully Executed 9.26.16.pdf
Unit Count | 137 |  | Job Info sheet
Work Period | Sep 2016 start → Nov 2018 last invoice (27 months) |  | JDR PR/AR dates
Total Unique Documents Reviewed | 1000+ (231 POs, 503 photos, 59 ASI-RFIs, 33 CORs, 22 submittals, 10 permits) |  | File inventory across owp-2033/ (2033-Compass, Vuecrest)
CONTRACT VALUE |  | NET PROFIT | DIRECT COST | LABOR HOURS
2343188 |  | 1010507.56 | 1332680.44 | 19509
Original $2,504,600.00 + ($-161,412.00) COs (-6.44%) |  | 43.1% margin | 56.9% of revenue | 44 workers
SCOPE OF WORK (from contract + proposal)
Full plumbing installation: underground, garage, rough-in, finish, gas, water main, insulation, mechanical room, condensate drains.
137-unit luxury multifamily new construction (Vuecrest LUX) at 1000 100th Ave NE, Bellevue, WA 98004.
5 levels above ground + 1 level below grade (per Permits); large UG garage & mechanical room; PSE transformer vault.
Notable scope: Grease interceptor, PSE oil containment drain, dog-run backflow, rooftop restrooms (deleted), dewatering meter.
OCIP insurance (wrap program); Compass Harbor as GC; Continental as developer.
Spec compliance: City of Bellevue plumbing code + UPC with WA amendments. Permits incl 16-144265-BO (building) and 17-106355-BL (plumbing).
SOURCES
Canonical financial source: 2033 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 191 pages)
Job totals (JDR footer): Revenue $2,343,188.00 / Expenses $1,332,680.44 / Net $1,010,507.56 / Retainage $114,309.40
Source breakdown: GL $66,431.91 · AP $490,114.66 · PR $776,133.87 · AR $2,343,188.00
Contract: Vuecrest-One Way Plumbing Fully Executed 9.26.16.pdf (Lump Sum $2,504,600.00 descoped to $2,343,188.00)
Fixture schedule: Vuecrest P-tag and equipment list working copy.xlsx
Plumbing narrative: Vuecrest plumbing narrative / Div 22 spec
Change Orders: 18 fully-executed COs in Change Orders/CO_s/ folder; 17 Budget Transfer spreadsheets document $-160,233.00; JDR-implied net $-161,412.00
COR source: Change Orders/COR_s/ (33 internal Change Order Requests with RFI links)
Project Team: Ryan Ames/Vince Dennison (GC PM), Todd Mortenson (GC Sup), Dan Peck (GC PE), Continental (Developer), Victor (OWP RI Foreman)
PROJECT TEAM (OWP Job Info)
Role | Status | Name / Firm
GC | Extracted | Compass Harbor Construction, LLC
GC PM | Extracted | Ryan Ames / Vince Dennison
GC Superintendent | Extracted | Todd Mortenson
GC PE | Extracted | Dan Peck
Developer | Extracted | Continental
Owner | Extracted | Bellevue Vuecrest, LP
Architect | N/A | N/A
Structural | N/A | N/A
Acoustical | N/A | N/A
ADA Consultant | N/A | N/A
Interior Design | N/A | N/A
MEP Engineer | N/A | N/A
Insurance | Extracted | Wrap (OCIP)
OWP RI Foreman | Extracted | Victor

## Budget vs Actual
Budget vs Actual
All 29 cost codes from JDR. Contract $2,504,600 → $2,343,188 (COs -161,412.00 descoped).
Cost Code | Description | Original Budget | Revised Budget | Actual | Variance | % of Revised | Hours | Source
100 | Supervision | 11120 | 12269 | 2336.5 |  |  | 47.5 | 2033 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 191 pages)
101 | Takeoff & Purchase Labor | 20155 | 22018 | 13253 |  |  | 271.5 | 2033 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 191 pages)
110 | Underground Labor | 18900 | 20923 | 24211 |  |  | 761.5 | 2033 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 191 pages)
111 | Garage Labor | 62725 | 53811 | 49382 |  |  | 1826.5 | 2033 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 191 pages)
112 | Canout Labor | 6450 | 6533 | 12268.5 |  |  | 414 | 2033 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 191 pages)
120 | Roughin Labor | 373450 | 329577 | 299136 |  |  | 11450.5 | 2033 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 191 pages)
130 | Finish Labor | 50580 | 51098 | 42783.5 |  |  | 1845 | 2033 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 191 pages)
140 | Gas Labor | 3600 | 3600 | 9941.5 |  |  | 324.5 | 2033 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 191 pages)
141 | Water Main/Insulation Lab | 45780 | 47220 | 29860.13 |  |  | 1096 | 2033 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 191 pages)
142 | Mech Room Labor | 18900 | 19400 | 13827 |  |  | 355 | 2033 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 191 pages)
143 | Condensation Drains Labor | 0 | 2808 | 29278.5 |  |  | 1117 | 2033 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 191 pages)
210 | Underground Material | 35500 | 42333 | 25541.27 |  |  |  | 2033 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 191 pages)
211 | Garage Material | 93500 | 71296 | 19980.4 |  |  |  | 2033 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 191 pages)
212 | Canout Material | 7740 | 8272 | 11279.69 |  |  |  | 2033 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 191 pages)
220 | Roughin Material | 294400 | 171617 | 67263.77 |  |  |  | 2033 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 191 pages)
230 | Finish Material | 222560 | 197050 | 219513.43 |  |  |  | 2033 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 191 pages)
240 | Gas Material | 11600 | 11600 | 2339.62 |  |  |  | 2033 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 191 pages)
241 | Water Main/Insulation Mat | 59175 | 59933 | 67464.44 |  |  |  | 2033 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 191 pages)
242 | Mech Room Material | 125650 | 127123 | 43786.76 |  |  |  | 2033 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 191 pages)
243 | Condensation Drains Mat | 0 | 2294 | 3093.95 |  |  |  | 2033 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 191 pages)
330 | Flats Finish Labor | 0 | 0 | 0 |  |  |  | 2033 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 191 pages)
600 | Subcontractor | 1000 | 1165 | 230 |  |  |  | 2033 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 191 pages)
601 | Engineering/Plans | 55000 | 57485 | 60958.25 |  |  |  | 2033 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 191 pages)
602 | Rental Equipment | 3000 | 3117 | 316.54 |  |  |  | 2033 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 191 pages)
603 | Permits & Licenses | 21300 | 22604 | 21161 |  |  |  | 2033 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 191 pages)
607 | Other Expenses | 11000 | 11000 | 13617.45 |  |  |  | 2033 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 191 pages)
995 | Payroll Burden | 234571.61 | 218627.35 | 209595.74 |  |  |  | 2033 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 191 pages)
998 | Payroll Taxes | 46791.99 | 43548.16 | 40260.5 |  |  |  | 2033 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 191 pages)
999 | Sales | -2504600 | -2343188 | -2343188 |  |  |  | 2033 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 191 pages)
TOTAL

## Cost Breakdown
Cost Breakdown by Category
Direct cost composition by category from JDR cost codes
Category | Cost Codes | Actual $ | % of Direct Cost | % of Revenue | Source
Labor | 100,101,110,111,112,120,130,140,141,142,143 | 526277.63 |  |  | 2033 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 191 pages)
Material | 210,211,212,220,230,240,241,242,243 | 460263.33 |  |  | 2033 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 191 pages)
Subcontractor + Engineering + Permits + Other | 600,601,602,603,607 | 96283.24 |  |  | 2033 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 191 pages)
Payroll Burden | 995 | 209595.74 |  |  | 2033 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 191 pages)
Payroll Taxes | 998 | 40260.5 |  |  | 2033 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 191 pages)
TOTAL DIRECT COST |  |  | 100%

## Material
Material Purchases — AP Vendors
Material + subcontractor spend by vendor (AP records from JDR). Supplemented with submittal/PO inventory.
Vendor ID | Vendor Name | Total Spend | # Transactions | Category (inferred) | Source
2033RS | Rosen Supply Company, Inc. $Vuecrest | 169567.03 | 110 | Plumbing / Supplies | 2033 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 191 pages)
2033KS | Keller Supply Co. $Vuecrest | 73436.14 | 66 | Plumbing / Supplies | 2033 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 191 pages)
1625FE | Franklin Engineering | 60958.25 | 11 | Engineering (601) | 2033 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 191 pages)
2033CS | Consolidated Supply Co. $Vuecrest | 57576.74 | 26 | Plumbing / Supplies | 2033 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 191 pages)
1231KS | Keller Supply Company | 32201.96 | 33 | Plumbing / Supplies | 2033 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 191 pages)
3612MS | Mechanical Sales, Inc. | 25111.34 | 3 | Plumbing / Supplies | 2033 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 191 pages)
1234BA | Bank of America CC | 20689.89 | 7 | Credit Card (mixed) | 2033 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 191 pages)
2030KS | Keller Supply Co. $East Union | 14336.13 | 1 | Plumbing / Supplies | 2033 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 191 pages)
1234CO | Capital One Credit Card | 10385.09 | 34 | Credit Card (mixed) | 2033 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 191 pages)
1609QC | Quality Concrete Products, Inc. $32 | 6577 | 4 | Uncategorized | 2033 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 191 pages)
9905SG | Susan Gibson $2033 Vuecrest | 5466.67 | 22 | Uncategorized | 2033 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 191 pages)
2033FE | Ferguson Enterprises, Inc. $Vuecrest | 5136.25 | 7 | Plumbing / Supplies | 2033 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 191 pages)
7423OC | Old Castle Infrastructure, Inc. | 3772 | 2 | Uncategorized | 2033 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 191 pages)
1380RS | Rosen Supply Kirkland | 1500.69 | 12 | Plumbing / Supplies | 2033 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 191 pages)
1303CM | C.M. Hoskins Company | 810 | 2 | Uncategorized | 2033 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 191 pages)
2132MH | Manor Hardware & Construction Supply | 611.52 | 1 | Plumbing / Supplies | 2033 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 191 pages)
1130CS | Consolidated Supply Co. | 525.77 | 1 | Plumbing / Supplies | 2033 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 191 pages)
5560CH | California Hydronics Corp | 465 | 1 | Uncategorized | 2033 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 191 pages)
1799AW | AllWest Underground, Inc. | 316.54 | 2 | Uncategorized | 2033 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 191 pages)
1234SD | Shirley Dennison | 250 | 1 | Uncategorized | 2033 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 191 pages)
1421RA | R.A. Brown Backflow Testing | 230 | 2 | Testing subcontractor | 2033 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 191 pages)
1175FE | Ferguson Enterprises, Inc. #3007 | 129.47 | 1 | Plumbing / Supplies | 2033 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 191 pages)
5621HD | Core & Main LP $HD Supply Waterworks | 25.32 | 1 | Plumbing / Supplies | 2033 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 191 pages)
1978FC | Fastenal Company | 23.8 | 1 | Uncategorized | 2033 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 191 pages)
1021AT | ACME Corp | 12.06 | 1 | Uncategorized | 2033 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 191 pages)
2031RS | Rosen Supply Company, Inc. $Gateway | 0 | 6 | Plumbing / Supplies | 2033 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 191 pages)
TOTAL
NOTE: AP total per JDR footer = $490,114.66. Vendor sum above approximates this. Submittals folder contains 22 items (fixtures, material, equipment, acoustical schedule, underground, water heater strap kit). POs folder has 231 POs (1 placed, 2 scheduled, 3 completed + loose files).

## Crew & Labor
Crew & Labor — Worker Roster
All 44 unique payroll workers from JDR. OWP RI Foreman: Victor.
Worker ID | Worker Name | Total Hours | Gross Pay | Blended Wage ($/hr) | # Work Days | Source
PA11 | Paco Leyva, Orlando | 2594.5 | 80172 |  | 76 | 2033 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 191 pages)
CO71 | Cortes Mendiola, Victor H | 1885.5 | 68761.5 |  | 61 | 2033 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 191 pages)
CO73 | Cortes Sepulveda, Jose R | 1663.5 | 31900.5 |  | 56 | 2033 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 191 pages)
MO56 | Montenegro, Carlos E | 1555 | 39312 |  | 45 | 2033 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 191 pages)
LI49 | Lima Romero, Melvin A | 1449 | 42594 |  | 41 | 2033 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 191 pages)
BA45 | Balderas Ortiz, Ricardo I | 1357 | 35725 |  | 40 | 2033 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 191 pages)
AS10 | Ascencio, Jose L | 1313 | 28359 |  | 37 | 2033 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 191 pages)
RI87 | Rivera, Jorge A | 877.5 | 24570 |  | 24 | 2033 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 191 pages)
RO12 | Rodriguez Rodriguez, Aminadab N | 800 | 17283 |  | 22 | 2033 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 191 pages)
EL33 | Eliassen, Cory H | 741.5 | 16342.5 |  | 29 | 2033 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 191 pages)
HU06 | Hubbard, Robert W | 694.5 | 30701 |  | 86 | 2033 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 191 pages)
CR87 | Cruz Reyes, Jose | 639 | 13803 |  | 17 | 2033 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 191 pages)
CR79 | Cruz Guzman, Joel A | 631 | 13004 |  | 17 | 2033 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 191 pages)
SI48 | Silva Morales, Jair J | 566 | 13018 |  | 19 | 2033 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 191 pages)
LU09 | Lucas Tzintzun, Rafael | 552 | 8632 |  | 15 | 2033 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 191 pages)
ES11 | Escobar Ortiz, Edgar O | 278 | 4170 |  | 9 | 2033 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 191 pages)
GO51 | Gomez Reyes, Edith N | 262 | 5276.5 |  | 13 | 2033 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 191 pages)
DO56 | Donelson, Richard T | 214 | 10723.5 |  | 77 | 2033 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 191 pages)
EG05 | Egbaou, Kossi D | 184 | 2688 |  | 6 | 2033 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 191 pages)
RO10 | Rodriguez Arevalos, Christian | 160 | 2800 |  | 5 | 2033 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 191 pages)
RE91 | Reyes, Maria E | 160 | 2560 |  | 8 | 2033 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 191 pages)
SA54 | Sanders, Allen O | 140.5 | 5947.5 |  | 35 | 2033 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 191 pages)
MC09 | McCabe, Thomas C | 122 | 3888 |  | 11 | 2033 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 191 pages)
GE69 | Gerard, Jeffrey S | 102 | 4740 |  | 46 | 2033 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 191 pages)
SE64 | Sepulveda Gonzalez, Alfredo | 89 | 2759 |  | 7 | 2033 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 191 pages)
GA70 | Garcia, Jordan X | 67 | 1809 |  | 4 | 2033 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 191 pages)
KI55 | Kinssies, Jr, John E | 62 | 1612 |  | 5 | 2033 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 191 pages)
CA71 | Castaneda Juarez, Cesar O | 45 | 675 |  | 3 | 2033 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 191 pages)
CA74 | Castaneda Martinez, Gustavo | 45 | 1755 |  | 3 | 2033 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 191 pages)
NE46 | Nelson, Charles E | 40 | 640 |  | 4 | 2033 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 191 pages)
FO55 | Fonseca Teruel, Eduardo | 40 | 640 |  | 2 | 2033 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 191 pages)
HU04 | Hubbard, Dustin R | 34 | 676 |  | 11 | 2033 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 191 pages)
RE96 | Reyes Cruz, Denis A | 32 | 768 |  | 1 | 2033 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 191 pages)
CA50 | Caro, Camilo | 32 | 512 |  | 3 | 2033 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 191 pages)
PO71 | Portillo, Kevin J | 24 | 384 |  | 1 | 2033 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 191 pages)
MA71 | Martinez Reyes, Juan C | 24 | 592 |  | 2 | 2033 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 191 pages)
BA70 | Barnhart, Joseph N | 19 | 874 |  | 3 | 2033 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 191 pages)
RE18 | Reed, Reuben H | 16 | 576 |  | 2 | 2033 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 191 pages)
GA72 | Gardner, Andrew M | 9.5 | 161.5 |  | 2 | 2033 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 191 pages)
RA55 | Ramos Herrera, Franklin J | 8 | 128 |  | 1 | 2033 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 191 pages)
AM03 | Amaya Gonzalez, Edilberto A | 8 | 208 |  | 1 | 2033 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 191 pages)
CH20 | Chevez, Herson G | 8 | 120 |  | 1 | 2033 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 191 pages)
PO73 | Portillo Soriano, Walter A | 8 | 128 |  | 1 | 2033 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 191 pages)
ST02 | Stahlschmidt, John P | 7 | 112 |  | 1 | 2033 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 191 pages)
TOTAL

## Crew Analytics
Crew Analytics
Team-level labor productivity, concentration, wage dispersion
TEAM-LEVEL METRICS
Metric | Value | Notes | Source
Total Workers | 44 | Unique payroll IDs | 2033 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 191 pages)
Total Labor Hours | 19509 | Sum of labor codes | 2033 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 191 pages)
Total Gross Pay | 526277.63 | Sum of labor codes | 2033 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 191 pages)
Blended Gross Wage ($/hr) | 26.9761 | Labor$ / Hrs (pre-burden) | Derived
Top Worker Hours Share | 13.3% | PA11 Paco Leyva, Orlando (2594 hrs) | Derived
Top 5 Workers Hours Share | 46.89% | Concentration metric | Derived
Highest Wage Rate ($/hr) | 50.1098 | Single-worker blended | Derived
Lowest Wage Rate ($/hr) | 14.6087 | Single-worker blended | Derived
Avg Hours per Worker | 443.3864 | Includes short-tenure workers | Derived
Avg Project Days per Worker | 19.3864 | Mean days | Derived

## Productivity
Productivity Metrics
Normalized labor and financial ratios. Per-unit metrics from 137 units (Job Info).
Metric | Value | Basis | Source / Note
Revenue per Labor Hour |  | Formula | Rev / Total Hrs
Profit per Labor Hour |  | Formula | Net Profit / Hrs
Labor Cost per Hour (blended) |  | Formula | Pre-burden
Fully-Loaded Labor Rate ($/hr) |  | Formula | Incl burden + taxes
Burden Multiplier |  | Formula | Fully-loaded / blended
Rough-in Hours (code 120) | 11450.5 | JDR | 11450 hrs
Finish Hours (code 130) | 1845 | JDR | 1845 hrs
Rough-in % of Total Hours |  | Formula | Code 120 share
Gross Margin |  | Formula | Net / Revenue
Labor % of Revenue |  | Formula
Material % of Revenue |  | Formula
Direct Cost Ratio |  | Formula | All expenses / Rev
Revenue per Unit (137) |  | Formula | 137 units (Job Info)
Labor Hours per Unit |  | Formula
Labor Cost per Unit |  | Formula
Material Cost per Unit |  | Formula
Direct Cost per Unit |  | Formula
Rough-in Hours per Unit |  | Formula | Code 120 / 137

## PO Commitments
PO Commitments
Inbound contract value (GC → OWP). Outbound vendor commitments — see Material tab + POs folder.
PO # | Date | Issuer | Type | Status | Description | Amount | Source
PRIME | 2016-09-26 (Fully Executed) | Compass Harbor Construction, LLC | Lump Sum Subcontract | Closed | Vuecrest LUX plumbing (137 units, Bellevue WA) — full plumbing scope per Div 22 | 2504600 | Vuecrest-One Way Plumbing Fully Executed 9.26.16.pdf
CO#01 | NOT FOUND | Compass Harbor Construction, LLC | Change Order | Executed | Vuecrest - Budget Transfer - CO #01.xlsx | 22429 | CO_s/Vuecrest - Budget Transfer - CO #01.xlsx
CO#02a | NOT FOUND | Compass Harbor Construction, LLC | Change Order | Executed | BT CO#02 100% GMP Set Costs | 10131 | BT CO#02 100% GMP Set Costs
CO#02b | NOT FOUND | Compass Harbor Construction, LLC | Change Order | Executed | BT CO#02 Cast Iron, Lav & Kitchen Sinks Credit | -234240 | BT CO#02 Cast Iron, Lav & Kitchen Sinks Credit
CO#03 | NOT FOUND | Compass Harbor Construction, LLC | Change Order | Executed | BT CO#03 Footing Drain @ Ramp (RFI-015) | 999 | BT CO#03 Footing Drain @ Ramp (RFI-015)
CO#04 | NOT FOUND | Compass Harbor Construction, LLC | Change Order | Executed | BT CO#04 Elevator Footing Drains (RFI-016) | 9194 | BT CO#04 Elevator Footing Drains (RFI-016)
CO#05 | NOT FOUND | Compass Harbor Construction, LLC | Change Order | Executed | BT CO#05 Grade Beam Drainage (RFI-019) | 1118 | BT CO#05 Grade Beam Drainage (RFI-019)
CO#06 | NOT FOUND | Compass Harbor Construction, LLC | Change Order | Executed | BT CO#06 Add Grease Interceptor (COB) | 5846 | BT CO#06 Add Grease Interceptor (COB)
CO#07 | NOT FOUND | Compass Harbor Construction, LLC | Change Order | Executed | BT CO#07 Delete Rooftop Sink | -2694 | BT CO#07 Delete Rooftop Sink
CO#08 | NOT FOUND | Compass Harbor Construction, LLC | Change Order | Executed | BT CO#08 Sump Pump — Temporary Dewatering | 1817 | BT CO#08 Sump Pump — Temporary Dewatering
CO#09 | NOT FOUND | Compass Harbor Construction, LLC | Change Order | Executed | Add Condensate Stacks | 2865 | BT CO#09 Delete Rooftop Bathroom / Add Condensate Stacks
CO#10 | NOT FOUND | Compass Harbor Construction, LLC | Change Order | Executed | BT CO#10 PSE Transformer Oil Containment Room Drain | 5364 | BT CO#10 PSE Transformer Oil Containment Room Drain
CO#11 | NOT FOUND | Compass Harbor Construction, LLC | Change Order | Executed | BT CO#11 PSE Transformer Drain — Permit Revision | 1667 | BT CO#11 PSE Transformer Drain — Permit Revision
CO#12 | NOT FOUND | Compass Harbor Construction, LLC | Change Order | Executed | BT CO#12 Dewatering Meter Supply & Install | 5466 | BT CO#12 Dewatering Meter Supply & Install
CO#13 | NOT FOUND | Compass Harbor Construction, LLC | Change Order | Executed | BT CO#13 Add Drain in Package Room (RFI-154) | 3126 | BT CO#13 Add Drain in Package Room (RFI-154)
CO#14 | NOT FOUND | Compass Harbor Construction, LLC | Change Order | Executed | BT CO#14 Added L5 Deck Drain (RFI-224) | 1352 | BT CO#14 Added L5 Deck Drain (RFI-224)
CO#15 | NOT FOUND | Compass Harbor Construction, LLC | Change Order | Executed | BT CO#15 Dog Run Backflow Preventer (RFI-172.1) | 2546 | BT CO#15 Dog Run Backflow Preventer (RFI-172.1)
CO#16 | NOT FOUND | Compass Harbor Construction, LLC | Change Order | Executed | BT CO#16 RFI-172.1 Dog Run Connections | 1782 | BT CO#16 RFI-172.1 Dog Run Connections
CO#17 | NOT FOUND | Compass Harbor Construction, LLC | Change Order | Executed | BT CO#17 Revised Layout x20 Stack (RFI-202) | 999 | BT CO#17 Revised Layout x20 Stack (RFI-202)
TOTAL (contract + COs)
NOTE: Documented COs (17 Budget Transfer spreadsheets) sum to $-160,233.00; JDR-implied = $-161,412.00; gap $-1,179.00 likely CO#18 (Fully Executed 1/23/2019, no budget transfer xlsx). CO folder has 18 fully-executed COs total. CORs folder contains 33 internal COR pricing worksheets. Outbound POs: 231 items across 1 Placed, 2 Scheduled, 3 Completed subfolders.

## Billing & SOV
Billing & Schedule of Values
30 unique invoices to Compass Harbor Construction, LLC. Retainage $114,309.40 = 4.9% of revenue.
Invoice # | Date | Total Billed (signed) | Retainage (signed) | # Lines | Source
036796 | 10/21/16 | -51300 | -2565 | 1 | 2033 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 191 pages)
036797 | 10/21/16 | 51300 | 2565 | 1 | 2033 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 191 pages)
036798 | 10/21/16 | -46170 | 0 | 1 | 2033 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 191 pages)
036823 | 01/20/17 | -113471 | -5673.55 | 4 | 2033 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 191 pages)
036838 | 02/20/17 | -18171 | -908.55 | 3 | 2033 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 191 pages)
036841 | 02/20/17 | 18171 | 908.55 | 3 | 2033 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 191 pages)
036842 | 02/20/17 | -16000 | -800 | 2 | 2033 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 191 pages)
036851 | 03/17/17 | -52428 | -2621.4 | 4 | 2033 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 191 pages)
036854 | 03/17/17 | -10830 | 0 | 2 | 2033 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 191 pages)
036859 | 04/20/17 | -305247 | -15262.35 | 5 | 2033 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 191 pages)
036884 | 05/19/17 | -110084 | -5504.2 | 6 | 2033 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 191 pages)
036901 | 06/19/17 | -254978 | -12748.9 | 7 | 2033 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 191 pages)
036914 | 07/20/17 | -301402 | -15070.1 | 6 | 2033 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 191 pages)
036932 | 08/18/17 | -364635 | -18231.75 | 7 | 2033 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 191 pages)
036947 | 09/20/17 | -182045 | -9102.25 | 4 | 2033 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 191 pages)
036969 | 10/20/17 | -135091 | -6754.55 | 7 | 2033 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 191 pages)
036976 | 11/17/17 | -190985 | -9549.25 | 15 | 2033 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 191 pages)
036990 | 12/14/17 | -88537 | -4426.85 | 10 | 2033 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 191 pages)
037011 | 01/19/18 | -8426 | -421.3 | 3 | 2033 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 191 pages)
037022 | 02/20/18 | -3500 | -175 | 1 | 2033 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 191 pages)
037045 | 03/20/18 | -3100 | -155 | 1 | 2033 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 191 pages)
037063 | 04/20/18 | -25928 | -1296.4 | 5 | 2033 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 191 pages)
037087 | 05/18/18 | -41625 | -2081.25 | 4 | 2033 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 191 pages)
037107 | 06/20/18 | -9830 | -491.5 | 3 | 2033 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 191 pages)
037134 | 07/20/18 | -34240 | -1712 | 3 | 2033 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 191 pages)
037153 | 08/20/18 | -26484 | -1324.2 | 4 | 2033 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 191 pages)
037158 | 08/20/18 | 26484 | 1324.2 | 4 | 2033 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 191 pages)
037159 | 08/20/18 | -27146 | -1357.3 | 4 | 2033 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 191 pages)
037181 | 09/19/18 | -16732 | -836.6 | 4 | 2033 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 191 pages)
037230 | 11/16/18 | -758 | -37.9 | 1 | 2033 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 191 pages)
TOTAL (signed)
NOTE: AR entries signed negative per Sage convention. Net billed = $2,343,188.00; retainage $114,309.40 outstanding on JDR dated 04/03/2026. Billing folder contains SOV xlsx files for pay apps 13-23 (2018 draw period). F1 Vuecrest - Subtier Subs & Suppliers disclosures attached for pay apps 6-23.

## Insights
Insights & Observations
Narrative findings from JDR + source documents
# | Insight | Detail | Confidence | Source
1 | VERY STRONG MARGIN | Net profit $1,010,507.56 on $2,343,188.00 revenue = 43.1% gross margin. Exceeds typical multifamily plumbing (25-30%) — strong execution under OCIP (wrap) insurance. | Verified | 2033 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 191 pages)
2 | DEDUCTIVE CONTRACT | Original contract $2,504,600.00 → revised $2,343,188.00 = ($161,412.00) net reduction (-6.44%). Driven by CO#02 Cast Iron/Lav/Kitchen Sinks credit ($234,240) partially offset by 16 adds. 18 fully-executed COs and 33 internal CORs documented. | Verified | Change Orders folder + Sage
3 | LABOR EFFICIENCY | Labor cost $526,277.63 (22.5% of rev) across 19,509 hrs and 44 workers. Blended wage $26.98/hr (pre-burden). | Verified | 2033 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 191 pages)
4 | VENDOR CONCENTRATION | Top 5 AP vendors: ~$393,740.12 (80% of AP). Top vendor: Rosen Supply Company, Inc. $Vuecrest ($169,567.03). | Verified | 2033 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 191 pages)
5 | LOW OVERHEAD | GL cost $66,431.91 = 2.8% of revenue. Lean project management overhead — typical OCIP projects keep GL under 3%. | Verified | 2033 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 191 pages)
6 | RETAINAGE HELD LONG | Retainage $114,309.40 = 4.9% of AR still open on JDR 04/03/2026 — that's 7+ years after last invoice (11/2018). Flag for collections follow-up. | Verified | 2033 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 191 pages)
7 | ROUGH-IN DOMINANT | Code 120 (Roughin Labor) = 11,450 hrs (59% of total). Revised budget was 329,577, actual 299,136 = savings of $30,441. | Verified | 2033 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 191 pages)
8 | FINISH MATERIAL OVERRUN | Code 230 Finish Material: rev $197,050, actual $219,513 (+$22,463 / 11.4%). Likely driver: upgraded fixtures per CO#02 cast iron/lav/sink revision + Delta faucet upgrades (CO#29). | Inferred | 2033 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 191 pages)
9 | PSE TRANSFORMER DRAMA | 3 COs directly tied to PSE transformer oil containment (CO#10, CO#11, CO#12 Dewatering Meter): ~$12,497 of added cost. Notable as design iteration with PSE utility coordination. | Verified | CO folder + RFI-005
10 | DOCUMENT DEPTH | Exceptional documentation: 59 ASI-RFI items, 33 CORs, 231 POs, 503 photos, 10 permits (incl 16-144265-BO building, 17-106355-BL plumbing). Ranks among most thoroughly documented OWP projects. | Verified | owp-2033/ (2033-Compass, Vuecrest)

## Benchmark KPIs
Benchmark KPIs
Normalized metrics for cross-project comparison
KPI | Data Name | Value | Category | Notes | Confidence | Source Document
Job Number | job_number | 2033 | Profile | OWP job ID | Verified | 2033 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 191 pages)
Job Name | job_name | Compass Vuecrest | Profile | Sage short name | Verified | 2033 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 191 pages)
Project Description | project_desc | Vuecrest (LUX) — 137-unit luxury multifamily plumbing, Bellevue WA | Profile | Contract + Job Info | Verified | Vuecrest-One Way Plumbing Fully Executed 9.26.16.pdf
General Contractor | general_contractor | Compass Harbor Construction, LLC | Profile | Customer 2033BV | Verified | Vuecrest-One Way Plumbing Fully Executed 9.26.16.pdf
Owner / Developer | owner | Bellevue Vuecrest, LP (Developer: Continental) | Profile | Per subcontract + Job Info | Verified | Vuecrest-One Way Plumbing Fully Executed 9.26.16.pdf
Location | location | 1000 100th Ave NE, Bellevue, WA 98004 | Profile | Contract address | Verified | Vuecrest-One Way Plumbing Fully Executed 9.26.16.pdf
Project Type | project_type | Luxury Multifamily New Construction — Plumbing (137 units) | Profile | Fixture schedule + Div 22 | Verified | Vuecrest P-tag and equipment list working copy.xlsx
Insurance Type | insurance_type | Wrap (OCIP) | Profile | OCIP (wrap) enrollment | Verified | Insurance folder
GC PM | gc_pm | Ryan Ames / Vince Dennison | Profile | Project lead | Verified | Job Info
GC Superintendent | gc_sup | Todd Mortenson | Profile |  | Verified | Job Info
GC PE | gc_pe | Dan Peck | Profile |  | Verified | Job Info
Developer | developer | Continental | Profile |  | Verified | Job Info
OWP RI Foreman | owp_foreman | Victor | Profile |  | Verified | Schedule tab
Work Start Date | start_date | 2016-09-01 | Profile | Per Schedule + first PR | Verified | 2033 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 191 pages)
Work End Date | end_date | 2018-11-16 | Profile | Per last AR posting | Verified | 2033 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 191 pages)
Duration (months) | duration_months | 27 | Profile | Sep 2016 → Nov 2018 | Verified | Derived
Unit Count | unit_count | 137 | Profile | Per Job Info sheet | Verified | Job Info
Contract Original | contract_original | 2504600 | Financial | Subcontract Lump Sum (Sage) | Verified | Vuecrest-One Way Plumbing Fully Executed 9.26.16.pdf
Contract Final | contract_final | 2343188 | Financial | Code 999 Rev Budget = AR total | Verified | 2033 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 191 pages)
Change Orders ($, implied) | change_orders_implied | -161412 | Financial | Final - Original | Verified | 2033 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 191 pages)
Change Orders ($, documented) | change_orders_documented | -160233 | Financial | 17 Budget Transfer xlsx sum | Verified | BUDGET TRANSFERS folder
CO Count Documented | co_count | 18 | Financial | 18 fully-executed COs in folder | Verified | Change Orders/CO_s/
COR Count | cor_count | 33 | Financial | Internal Change Order Requests | Verified | Change Orders/COR_s/
Change Order % of Contract | co_pct | -6.445% | Financial |  | Verified | Derived
Revenue | revenue | 2343188 | Financial | AR total | Verified | 2033 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 191 pages)
Direct Cost | direct_cost | 1332680.44 | Financial | JDR Job Totals Expenses | Verified | 2033 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 191 pages)
Net Profit | net_profit | 1010507.56 | Financial | Rev - Expenses | Verified | 2033 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 191 pages)
Gross Margin | gross_margin | 43.13% | Financial |  | Verified | Derived
Retainage Outstanding | retainage | 114309.4 | Financial | Open per JDR 4/3/26 | Verified | 2033 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 191 pages)
Retainage % of Revenue | retainage_pct | 4.878% | Financial |  | Verified | Derived
Labor Cost | labor_cost | 526277.63 | Labor | Codes 100-143 | Verified | 2033 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 191 pages)
Material Cost | material_cost | 460263.33 | Material | Codes 210-243 | Verified | 2033 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 191 pages)
Subcontractor+OH Cost | overhead_cost | 96283.24 | Financial | Codes 600-607 | Verified | 2033 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 191 pages)
Burden Cost | burden_cost | 209595.74 | Labor | Code 995 | Verified | 2033 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 191 pages)
Tax Cost | tax_cost | 40260.5 | Labor | Code 998 | Verified | 2033 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 191 pages)
Total Labor Hours | total_hours | 19509 | Labor | Sum labor codes | Verified | 2033 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 191 pages)
Total Workers | total_workers | 44 | Labor | Unique payroll IDs | Verified | 2033 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 191 pages)
Blended Gross Wage ($/hr) | blended_gross_wage | 26.9761 | Labor | Pre-burden | Verified | Derived
Fully-Loaded Wage ($/hr) | fully_loaded_wage | 39.7834 | Labor | Incl burden + tax | Verified | Derived
Burden Multiplier | burden_multiplier | 1.4748 | Labor | Fully-loaded/blended | Verified | Derived
Rough-in Hours | roughin_hours | 11450.5 | Labor | Code 120 | Verified | 2033 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 191 pages)
Finish Hours | finish_hours | 1845 | Labor | Code 130 | Verified | 2033 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 191 pages)
Revenue per Hour | revenue_per_hour | 120.1081 | Productivity |  | Verified | Derived
Profit per Hour | profit_per_hour | 51.797 | Productivity |  | Verified | Derived
Revenue per Unit | revenue_per_unit | 17103.562 | Productivity | 137 units | Verified | Derived
Direct Cost per Unit | cost_per_unit | 9727.5945 | Productivity | 137 units | Verified | Derived
Labor Hours per Unit | hours_per_unit | 142.4015 | Productivity | 137 units | Verified | Derived
Labor % of Revenue | labor_pct_revenue | 22.46% | Cost Mix |  | Verified | Derived
Material % of Revenue | material_pct_revenue | 19.64% | Cost Mix |  | Verified | Derived
Total Vendors (AP) | total_vendors | 26 | Material | Unique vendor IDs | Verified | 2033 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 191 pages)
Total Invoices (AR) | total_invoices | 30 | Billing | Unique invoice numbers | Verified | 2033 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 191 pages)
RFI Count (documented) | rfi_count | 59 | Docs | Items in ASI-RFI folder (mix of ASI + RFI) | Verified | ASI-RFI/
Submittal Count | submittal_count | 22 | Docs | Items in Submittals folder | Verified | Submittals/
Permit Count | permit_count | 10 | Docs | Items in Permits folder | Verified | Permits/
PO Count | po_count | 231 | Docs | Across 1 Placed, 2 Scheduled, 3 Completed | Verified | POs folder
Photo Count | photo_count | 503 | Docs | Photos folder | Verified | Photos/
AP Spend (JDR footer) | ap_total | 490114.66 | Material | JDR footer | Verified | 2033 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 191 pages)
PR Spend (JDR footer) | pr_total | 776133.87 | Labor | JDR footer (labor+burden+tax) | Verified | 2033 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 191 pages)
GL Spend (JDR footer) | gl_total | 66431.91 | Financial | JDR footer | Verified | 2033 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 191 pages)

## Vendors
Vendors — AP Summary
Vendor-level spend ranking
Rank | Vendor ID | Vendor Name | Total Spend | # Transactions | % of AP | Source
1 | 2033RS | Rosen Supply Company, Inc. $Vuecrest | 169567.03 | 110 |  | 2033 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 191 pages)
2 | 2033KS | Keller Supply Co. $Vuecrest | 73436.14 | 66 |  | 2033 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 191 pages)
3 | 1625FE | Franklin Engineering | 60958.25 | 11 |  | 2033 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 191 pages)
4 | 2033CS | Consolidated Supply Co. $Vuecrest | 57576.74 | 26 |  | 2033 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 191 pages)
5 | 1231KS | Keller Supply Company | 32201.96 | 33 |  | 2033 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 191 pages)
6 | 3612MS | Mechanical Sales, Inc. | 25111.34 | 3 |  | 2033 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 191 pages)
7 | 1234BA | Bank of America CC | 20689.89 | 7 |  | 2033 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 191 pages)
8 | 2030KS | Keller Supply Co. $East Union | 14336.13 | 1 |  | 2033 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 191 pages)
9 | 1234CO | Capital One Credit Card | 10385.09 | 34 |  | 2033 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 191 pages)
10 | 1609QC | Quality Concrete Products, Inc. $32 | 6577 | 4 |  | 2033 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 191 pages)
11 | 9905SG | Susan Gibson $2033 Vuecrest | 5466.67 | 22 |  | 2033 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 191 pages)
12 | 2033FE | Ferguson Enterprises, Inc. $Vuecrest | 5136.25 | 7 |  | 2033 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 191 pages)
13 | 7423OC | Old Castle Infrastructure, Inc. | 3772 | 2 |  | 2033 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 191 pages)
14 | 1380RS | Rosen Supply Kirkland | 1500.69 | 12 |  | 2033 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 191 pages)
15 | 1303CM | C.M. Hoskins Company | 810 | 2 |  | 2033 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 191 pages)
16 | 2132MH | Manor Hardware & Construction Supply | 611.52 | 1 |  | 2033 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 191 pages)
17 | 1130CS | Consolidated Supply Co. | 525.77 | 1 |  | 2033 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 191 pages)
18 | 5560CH | California Hydronics Corp | 465 | 1 |  | 2033 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 191 pages)
19 | 1799AW | AllWest Underground, Inc. | 316.54 | 2 |  | 2033 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 191 pages)
20 | 1234SD | Shirley Dennison | 250 | 1 |  | 2033 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 191 pages)
21 | 1421RA | R.A. Brown Backflow Testing | 230 | 2 |  | 2033 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 191 pages)
22 | 1175FE | Ferguson Enterprises, Inc. #3007 | 129.47 | 1 |  | 2033 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 191 pages)
23 | 5621HD | Core & Main LP $HD Supply Waterworks | 25.32 | 1 |  | 2033 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 191 pages)
24 | 1978FC | Fastenal Company | 23.8 | 1 |  | 2033 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 191 pages)
25 | 1021AT | ACME Corp | 12.06 | 1 |  | 2033 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 191 pages)
26 | 2031RS | Rosen Supply Company, Inc. $Gateway | 0 | 6 |  | 2033 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 191 pages)
TOTAL

## Change Log
Change Log — Master Register
COs, RFIs, ASIs, Submittals, Permits, POs — from project folders
Event ID | Type | Date | Subject | Originator | Cost Impact ($) | Status | Source
CONTRACT-ORIG | Contract | 2016-09-26 | Prime subcontract — Lump Sum $2,504,600.00 (Fully Executed) | Compass Harbor Construction, LLC | 2504600 | Executed | Vuecrest-One Way Plumbing Fully Executed 9.26.16.pdf
CO#01 | Change Order | NOT FOUND | CO_s/Vuecrest - Budget Transfer - CO #01.xlsx | Compass Harbor Construction, LLC | 22429 | Executed | Change Orders/CO_s/Vuecrest - Budget Transfer - CO #01.xlsx
CO#02a | Change Order | NOT FOUND | BT CO#02 100% GMP Set Costs | Compass Harbor Construction, LLC | 10131 | Executed | Change Orders/BT CO#02 100% GMP Set Costs
CO#02b | Change Order | NOT FOUND | BT CO#02 Cast Iron, Lav & Kitchen Sinks Credit | Compass Harbor Construction, LLC | -234240 | Executed | Change Orders/BT CO#02 Cast Iron, Lav & Kitchen Sinks Credit
CO#03 | Change Order | NOT FOUND | BT CO#03 Footing Drain @ Ramp (RFI-015) | Compass Harbor Construction, LLC | 999 | Executed | Change Orders/BT CO#03 Footing Drain @ Ramp (RFI-015)
CO#04 | Change Order | NOT FOUND | BT CO#04 Elevator Footing Drains (RFI-016) | Compass Harbor Construction, LLC | 9194 | Executed | Change Orders/BT CO#04 Elevator Footing Drains (RFI-016)
CO#05 | Change Order | NOT FOUND | BT CO#05 Grade Beam Drainage (RFI-019) | Compass Harbor Construction, LLC | 1118 | Executed | Change Orders/BT CO#05 Grade Beam Drainage (RFI-019)
CO#06 | Change Order | NOT FOUND | BT CO#06 Add Grease Interceptor (COB) | Compass Harbor Construction, LLC | 5846 | Executed | Change Orders/BT CO#06 Add Grease Interceptor (COB)
CO#07 | Change Order | NOT FOUND | BT CO#07 Delete Rooftop Sink | Compass Harbor Construction, LLC | -2694 | Executed | Change Orders/BT CO#07 Delete Rooftop Sink
CO#08 | Change Order | NOT FOUND | BT CO#08 Sump Pump — Temporary Dewatering | Compass Harbor Construction, LLC | 1817 | Executed | Change Orders/BT CO#08 Sump Pump — Temporary Dewatering
CO#09 | Change Order | NOT FOUND | BT CO#09 Delete Rooftop Bathroom / Add Condensate Stacks | Compass Harbor Construction, LLC | 2865 | Executed | Change Orders/BT CO#09 Delete Rooftop Bathroom / Add Condensate Stacks
CO#10 | Change Order | NOT FOUND | BT CO#10 PSE Transformer Oil Containment Room Drain | Compass Harbor Construction, LLC | 5364 | Executed | Change Orders/BT CO#10 PSE Transformer Oil Containment Room Drain
CO#11 | Change Order | NOT FOUND | BT CO#11 PSE Transformer Drain — Permit Revision | Compass Harbor Construction, LLC | 1667 | Executed | Change Orders/BT CO#11 PSE Transformer Drain — Permit Revision
CO#12 | Change Order | NOT FOUND | BT CO#12 Dewatering Meter Supply & Install | Compass Harbor Construction, LLC | 5466 | Executed | Change Orders/BT CO#12 Dewatering Meter Supply & Install
CO#13 | Change Order | NOT FOUND | BT CO#13 Add Drain in Package Room (RFI-154) | Compass Harbor Construction, LLC | 3126 | Executed | Change Orders/BT CO#13 Add Drain in Package Room (RFI-154)
CO#14 | Change Order | NOT FOUND | BT CO#14 Added L5 Deck Drain (RFI-224) | Compass Harbor Construction, LLC | 1352 | Executed | Change Orders/BT CO#14 Added L5 Deck Drain (RFI-224)
CO#15 | Change Order | NOT FOUND | BT CO#15 Dog Run Backflow Preventer (RFI-172.1) | Compass Harbor Construction, LLC | 2546 | Executed | Change Orders/BT CO#15 Dog Run Backflow Preventer (RFI-172.1)
CO#16 | Change Order | NOT FOUND | BT CO#16 RFI-172.1 Dog Run Connections | Compass Harbor Construction, LLC | 1782 | Executed | Change Orders/BT CO#16 RFI-172.1 Dog Run Connections
CO#17 | Change Order | NOT FOUND | BT CO#17 Revised Layout x20 Stack (RFI-202) | Compass Harbor Construction, LLC | 999 | Executed | Change Orders/BT CO#17 Revised Layout x20 Stack (RFI-202)
CO#18 | Change Order | 2019-01-23 | CO#18 (Fully Executed) — no budget transfer xlsx; pickup/closeout CO | Compass Harbor Construction, LLC | -1179 | Executed | CO_s/Vuecrest - CO#18 - OWP (Fully Executed 1.23.19).pdf
CO-GAP | Reconciliation | — | Documented vs implied CO delta = $-1,179.00 (allocated to CO#18) | — | 0 | Resolved | 2033 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 191 pages)
COR-ALL | COR batch | — | 33 Change Order Requests (internal pricing) with RFI linkages | Sub (OWP) | 0 | Priced | COR_s/
ASI-PRIMARY | ASI batch | — | 5 ASIs: Roof Insulation, Mansard Backspan, Project Updates, L5 & Roof Restrooms, general updates | GC/Arch | 0 | Acknowledged | ASI-RFI/
RFI-PRIMARY | RFI batch | — | 50+ RFIs: footing drains, tub drains at columns, fire rating, tub & washer drains at columns, fridge openings | Sub (OWP) | 0 | Resolved | ASI-RFI/
SUB-FIXTURES | Submittal batch | — | Fixture submittals (Kohler K-2210, K-2882, Delta faucets, Zoeller pumps) | Sub (OWP) | 0 | Approved | Submittals/FIXTURES/
SUB-MATERIAL | Submittal batch | — | Material submittals (no-hub cast iron per Rosen, Holdrite penetration sleeves, equipment) | Sub (OWP) | 0 | Approved | Submittals/MATERIAL/
SUB-UG-GARAGE | Submittal | — | Underground & garage submittal | Sub (OWP) | 0 | Approved | Submittals/UNDERGROUND & GARAGE/
PERMIT-BUILDING | Permit | 2017-01-05 | Building permit 16-144265-BO — Vuecrest (issuance + 2 rev req 11-22-16, 12-30-16) | City of Bellevue | 0 | Issued | Permits/
PERMIT-PLUMBING | Permit | 2017-03-07 | Plumbing permit 17-106355-BL | City of Bellevue | 0 | Issued | Permits/
PERMIT-MECH-CHECKLIST | Permit | NOT FOUND | Bellevue Mechanical Permit Checklist | City of Bellevue | 0 | On file | Permits/
PERMIT-TEMP | Permit | NOT FOUND | Temp trailer water & sewer permit | City of Bellevue | 0 | Issued | Permits/
PERMIT-TRUCKING | Logistics | 2016-09-22 | TN approved COB trucking route (signed) | City of Bellevue | 0 | Approved | Project root/
OCIP | Insurance | — | OCIP enrollment (wrap insurance) | Bellevue Vuecrest, LP | 0 | Enrolled | Insurance/OCIP Enrollment.pdf
PO-COMPLETED | PO batch | — | ~200+ completed POs (3 Completed/) | Sub (OWP) | 0 | Complete | POs/3 Completed/
PO-SCHEDULED | PO batch | — | Scheduled POs (2 Scheduled/) | Sub (OWP) | 0 | Scheduled | POs/2 Scheduled/
PO-PLACED | PO batch | — | Placed POs (1 Placed/) | Sub (OWP) | 0 | Placed | POs/1 Placed/
FIRST-INVOICE | Invoice | 2016-12-20 | First billing — see Billing folder 2017/ | Sub (OWP) | 0 | Paid | 2033 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 191 pages)
LAST-INVOICE | Invoice | 2018-11-16 | Last billing (Invoice 037230 @ $758) | Sub (OWP) | 758 | Paid | 2033 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 191 pages)
RETAINAGE-OPEN | Retainage | As of 04/03/2026 | Retainage $114,309.40 outstanding 7+ years post-closeout | GC | 0 | Outstanding | 2033 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 191 pages)

## Root Cause Analysis
Root Cause Analysis
Primary variance driver: deductive change orders reducing contract by $161,412
COST-CODE VARIANCE CATEGORIES
Category | Codes Affected | Net $ Variance | Root Cause (inferred) | Notes
Deductive Contract Change | 999 (Sales code) | -161412 | CO#02 Cast Iron/Lav/Kitchen Sinks credit (-$234,240) dominant; partially offset by 16 adds | Original $2,504,600 → Final $2,343,188 = $-161,412 (-6.44%)
Labor efficiency | 100-143 | -42979.37 | Rough-in (120) and Finish (130) labor both under revised budget | 44 workers; favorable on 9 of 11 labor codes
Material procurement | 210-243 | -231254.67 | Mixed: Rough-in material large savings offset by Finish Material and Water Main overruns | Key overruns: 230 (+$22k), 241 (+$7.5k); key savings: 220 (-$104k), 211 (-$51k)
Overhead / Engineering / Permits | 600-607 | 912.24 | Engineering and permits slightly over; rental/subcontractor under | Engineering +$3.5k (Franklin); Permits modestly over
Burden / Tax accrual | 995, 998 | -12319.27 | Tracked proportionally to labor; burden reduced with labor | OWP internal; CO#08 note changed burden rate to 40
Condensation Drains (new code) | 143 + 243 | 27270.45 | Code 143 (labor) and 243 (material) emerged mid-project — multiple condensate-stack CORs | Code 143 actual $29,278 vs rev $2,808
TOTAL NET VARIANCE (Rev Budget vs Actual)
RESPONSIBILITY ATTRIBUTION
Responsible Party | # Drivers | Net $ Impact | Notes
GC / Owner (scope revision) | 18 | -161412 | 18 executed COs — primarily driven by CO#02 Cast Iron / Lav / Kitchen Sinks credit (-$234,240)
Sub (OWP) — labor performance | 11 | -42979.37 | Labor cost performance vs revised budget across 11 labor codes
Sub (OWP) — material procurement | 9 | -231254.67 | Procurement & scope execution; Keller/Rosen/Ferguson dominant vendors
Burden rate — OWP internal | 2 | -12319.27 | Payroll accrual; CO#08 note '40% burden next'
Support codes — OWP | 5 | 912.24 | Overhead efficiency (Franklin engineering, permits, rentals)
Design coordination — PSE/Bellevue | 3 | 12497 | CO#10/11/12 = PSE transformer drain + permit revision + dewatering meter

## Predictive Signals
Predictive Signals
Leading indicators from project documents + JDR
CURRENT-STATE SIGNALS
Indicator | Current Value | Benchmark | Status | Meaning
Contract Descoping % | -6.44% | ±10% | WATCH | -6.44% net reduction, driven by CO#02 Cast Iron credit
Labor % of Revenue | 22.46% | <30% | HEALTHY | 22.5%
GL Overhead % of Revenue | 2.835% | <5% | HEALTHY | 2.8%
Vendor Concentration (Top 5) | 80.34% | <95% | HEALTHY | Top 5 vendors = 80% of AP
Retainage Outstanding | 4.878% | <10% | HEALTHY | 4.9% — but 7+ years stale
Gross Margin | 43.13% | >35% | HEALTHY | 43.1% — exceeds benchmark
Labor Hrs Total | 1950900% | varies | INFO | 19,509 hrs across 44 workers
Retainage Release Pending | YES | Released within 90 days post-closeout | ELEVATED | $114,309 open 7+ years — collections concern
Worker Concentration (top 1) | 13.3% | <25% | HEALTHY | 13.3% from single worker (Paco Leyva, Orlando)
Rough-in Labor Share | 58.69% | 40-65% | HEALTHY | 59% on rough-in
Rough-in Budget Variance | -9.236% | ±10% | HEALTHY | -9.2% under
Finish Material Variance | 11.4% | ±10% | ELEVATED | 11.4% over — upgraded fixtures
Permits Obtained | 10 | >=3 | HEALTHY | All major permits + checklists on file
RFI Density | 43.07% | <0.5 | HEALTHY | 0.43 RFIs per unit — typical for luxury multifamily
Document Completeness | HIGH | Full CO/RFI/Submittal trail + photos | HEALTHY | Contract, 18 COs, 33 CORs, 59 ASI-RFIs, 22 submittals, 231 POs, 503 photos, 10 permits
FORECAST MODELS
Forecast | Current Estimate | Confidence | Driver | Model Note
Final margin (actual) | 43.13% | Actual | Job closed | 43.1% — exceeds multifamily benchmark
CO reconciliation | 17 documented + CO#18 implied | Verified | Budget Transfer xlsx + CO folder | Documented COs sum = $-160,233; implied $-161,412; gap allocated to CO#18
Composite risk score (0-100) | 22 | Low-Medium | Strong margin; retainage collections risk | Retainage 7+ years stale — follow-up needed
Would re-bid margin target | ≥40% | Derived | Historical close | Strong execution; OCIP helps; maintain labor-light approach
Unit-level economics | $17,104/unit rev, $7,376/unit profit | Verified | 137 units from Job Info | Benchmark for future luxury multifamily
Retainage collections | $114,309 open | Low confidence collection | 7+ years stale | May require LOI or writedown

## Metric Registry
Metric Registry — Cortex Data Catalog
Every metric with data_label, confidence, and source
# | Data Label | Human Label | Value | Unit | Source Tab | Confidence | Source Document(s)
1 | job_number | Job Number | 2033 | id | Benchmark KPIs | Verified | 2033 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 191 pages)
2 | job_name | Job Name | Compass Vuecrest | text | Benchmark KPIs | Verified | 2033 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 191 pages)
3 | project_desc | Project Description | Vuecrest (LUX) — 137-unit luxury multifamily plumbing, Bellevue WA | text | Benchmark KPIs | Verified | Vuecrest-One Way Plumbing Fully Executed 9.26.16.pdf
4 | general_contractor | GC | Compass Harbor Construction, LLC | text | Benchmark KPIs | Verified | Vuecrest-One Way Plumbing Fully Executed 9.26.16.pdf
5 | customer_code | Customer Code | 2033BV | id | Overview | Verified | 2033 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 191 pages)
6 | owner | Owner | Bellevue Vuecrest, LP (Developer: Continental) | text | Benchmark KPIs | Verified | Vuecrest-One Way Plumbing Fully Executed 9.26.16.pdf
7 | location | Location | 1000 100th Ave NE, Bellevue, WA 98004 | text | Benchmark KPIs | Verified | Vuecrest-One Way Plumbing Fully Executed 9.26.16.pdf
8 | project_type | Project Type | Luxury Multifamily Plumbing (137 units) | text | Benchmark KPIs | Verified | Vuecrest P-tag and equipment list working copy.xlsx
9 | insurance_type | Insurance Type | Wrap (OCIP) | text | Benchmark KPIs | Verified | Insurance folder
10 | gc_pm | GC PM | Ryan Ames / Vince Dennison | text | Benchmark KPIs | Verified | Job Info
11 | gc_sup | GC Superintendent | Todd Mortenson | text | Benchmark KPIs | Verified | Job Info
12 | gc_pe | GC PE | Dan Peck | text | Benchmark KPIs | Verified | Job Info
13 | developer | Developer | Continental | text | Benchmark KPIs | Verified | Job Info
14 | owp_foreman | OWP RI Foreman | Victor | text | Benchmark KPIs | Verified | Schedule
15 | start_date | Work Start | 2016-09-01 | date | Benchmark KPIs | Verified | 2033 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 191 pages)
16 | end_date | Work End | 2018-11-16 | date | Benchmark KPIs | Verified | 2033 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 191 pages)
17 | duration_months | Duration (months) | 27 | months | Benchmark KPIs | Verified | Derived
18 | unit_count | Unit Count | 137 | units | Benchmark KPIs | Verified | Job Info
19 | contract_original | Contract Original | 2504600 | USD | Benchmark KPIs | Verified | Vuecrest-One Way Plumbing Fully Executed 9.26.16.pdf
20 | contract_final | Contract Final | 2343188 | USD | Benchmark KPIs | Verified | 2033 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 191 pages)
21 | change_orders_implied | COs (implied) | -161412 | USD | Benchmark KPIs | Verified | 2033 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 191 pages)
22 | change_orders_documented | COs (documented) | -160233 | USD | Benchmark KPIs | Verified | BUDGET TRANSFERS folder
23 | co_count | CO Count | 18 | count | Change Log | Verified | Change Orders/CO_s/
24 | cor_count | COR Count | 33 | count | Change Log | Verified | Change Orders/COR_s/
25 | co_pct | CO % of Contract | -6.445% | % | Benchmark KPIs | Verified | Derived
26 | revenue | Revenue | 2343188 | USD | Benchmark KPIs | Verified | 2033 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 191 pages)
27 | direct_cost | Direct Cost | 1332680.44 | USD | Benchmark KPIs | Verified | 2033 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 191 pages)
28 | net_profit | Net Profit | 1010507.56 | USD | Benchmark KPIs | Verified | 2033 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 191 pages)
29 | gross_margin | Gross Margin | 43.13% | % | Benchmark KPIs | Verified | Derived
30 | retainage | Retainage Outstanding | 114309.4 | USD | Benchmark KPIs | Verified | 2033 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 191 pages)
31 | retainage_pct | Retainage % of Revenue | 4.878% | % | Benchmark KPIs | Verified | Derived
32 | labor_cost | Labor Cost | 526277.63 | USD | Benchmark KPIs | Verified | 2033 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 191 pages)
33 | material_cost | Material Cost | 460263.33 | USD | Benchmark KPIs | Verified | 2033 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 191 pages)
34 | overhead_cost | Subcon+OH Cost | 96283.24 | USD | Benchmark KPIs | Verified | 2033 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 191 pages)
35 | burden_cost | Burden Cost | 209595.74 | USD | Benchmark KPIs | Verified | 2033 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 191 pages)
36 | tax_cost | Tax Cost | 40260.5 | USD | Benchmark KPIs | Verified | 2033 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 191 pages)
37 | total_hours | Total Labor Hours | 19509 | hours | Benchmark KPIs | Verified | 2033 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 191 pages)
38 | total_workers | Total Workers | 44 | count | Benchmark KPIs | Verified | 2033 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 191 pages)
39 | blended_gross_wage | Blended Gross Wage | 26.9761 | USD/hr | Benchmark KPIs | Verified | Derived
40 | fully_loaded_wage | Fully-Loaded Wage | 39.7834 | USD/hr | Benchmark KPIs | Verified | Derived
41 | burden_multiplier | Burden Multiplier | 1.4748 | x | Benchmark KPIs | Verified | Derived
42 | revenue_per_hour | Revenue per Hour | 120.1081 | USD/hr | Benchmark KPIs | Verified | Derived
43 | profit_per_hour | Profit per Hour | 51.797 | USD/hr | Benchmark KPIs | Verified | Derived
44 | revenue_per_unit | Revenue per Unit | 17103.562 | USD | Benchmark KPIs | Verified | Derived
45 | cost_per_unit | Direct Cost per Unit | 9727.5945 | USD | Benchmark KPIs | Verified | Derived
46 | hours_per_unit | Labor Hours per Unit | 142.4015 | hours | Benchmark KPIs | Verified | Derived
47 | labor_pct_revenue | Labor % of Revenue | 22.46% | % | Benchmark KPIs | Verified | Derived
48 | material_pct_revenue | Material % of Revenue | 19.64% | % | Benchmark KPIs | Verified | Derived
49 | total_vendors | Total Vendors (AP) | 26 | count | Vendors | Verified | 2033 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 191 pages)
50 | total_invoices | Total Invoices (AR) | 30 | count | Billing & SOV | Verified | 2033 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 191 pages)
51 | rfi_count | ASI-RFI Count | 59 | count | Change Log | Verified | ASI-RFI folder
52 | submittal_count | Submittal Count | 22 | count | Change Log | Verified | Submittals
53 | permit_count | Permit Count | 10 | count | Change Log | Verified | Permits
54 | po_count | PO Count | 231 | count | Change Log | Verified | POs
55 | photo_count | Photo Count | 503 | count | — | Verified | Photos
56 | top_worker_hours_share | Top Worker Hours Share | 13.3% | % | Crew Analytics | Verified | Derived
57 | top5_worker_hours_share | Top 5 Worker Hours Share | 46.89% | % | Crew Analytics | Verified | Derived
58 | cost_code_count | Cost Codes Active | 29 | count | Budget vs Actual | Verified | 2033 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 191 pages)

## Reconciliation
Reconciliation
Cross-sheet formula checks
# | Check | Value A | Value B | Delta | Status | Tabs
1 | Revenue (JDR) = Contract Final | 2343188 | 2343188 |  |  | 1↔8
2 | Expenses = Labor+Material+OH+Burden+Tax | 1332680.44 | 1332680.44 |  |  | 1↔3
3 | Net Profit = Revenue - Expenses | 1010507.56 | 1010507.56 |  |  | 1↔Derived
4 | JDR Source: AP+PR+GL = Expenses | 1332680.44 | 1332680.44 |  |  | 1↔Derived (footer)
5 | Budget vs Actual (code 999) = -Revenue | 2343188 | 2343188 |  |  | 2↔1
6 | Total Labor Hours = Worker hours sum | 19509 | 19559 |  |  | 5↔2
7 | Labor Cost ≈ Worker gross sum | 526277.63 | 522100.5 |  |  | 5↔3
8 | Vendor total ≈ AP footer | 490114.66 | 490114.66 |  |  | 12↔1 (approximate)
9 | Invoice count | 30 | 30 |  |  | 9↔1
10 | Contract Final - Orig = CO implied | -161412 | -161412 |  |  | 11↔Derived
11 | CO implied vs documented (gap = CO#18) | -161412 | -160233 |  |  | Deductive 18th CO no BT
12 | Retainage outstanding | 114309.4 | 114309.4 |  |  | 9↔JDR footer
13 | Worker count | 44 | 44 |  |  | 5↔1
14 | Cost code count | 29 | 29 |  |  | 2↔16
SOURCES
Job #2033 — Cortex v2 17-tab (built from-scratch)
Canonical financial source: 2033 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 191 pages)
JDR Job Totals: Revenue $2,343,188.00 / Expenses $1,332,680.44 / Net $1,010,507.56 / Retainage $114,309.40
JDR Source breakdown: GL $66,431.91 · AP $490,114.66 · PR $776,133.87 · AR $2,343,188.00
Contract: Vuecrest-One Way Plumbing Fully Executed 9.26.16.pdf (Lump Sum $2,504,600.00 descoped to $2,343,188.00, Bellevue Vuecrest, LP (Developer: Continental))
Fixture schedule: Vuecrest P-tag and equipment list working copy.xlsx (137-unit luxury multifamily specification)
Plumbing narrative: Vuecrest plumbing narrative / Div 22 spec (Division 22 specification, City of Bellevue plumbing code + UPC with WA amendments)
Change Orders: 18 fully-executed COs; 17 Budget Transfer spreadsheets; 1,179 allocated to CO#18
Project Team: Ryan Ames / Vince Dennison (GC PM) · Todd Mortenson (GC Sup) · Dan Peck (GC PE) · Continental (Developer) · Victor (OWP RI Foreman)
Insurance: Wrap (OCIP) enrollment per Insurance/OCIP Enrollment.pdf
Financial reconciliation: GL + AP + PR = Expenses; AR = Revenue
TIES = within $1 · WITHIN = within 5% · OFF = investigate