## Overview
Job #2034 · Compass Park Lane Apts
Cortex JCR v2 • Compass Harbor Construction, LLC (customer 2034CH) • 207 Park Lane, Kirkland, WA 98033 • Owner: Kirkland Main Street LP (Developer: Compass)
PROJECT OVERVIEW
Project Job # | 2034 |  | 2034 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 207 pages) header
Project Name (Sage) | Compass Park Lane Apts |  | 2034 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 207 pages) header
Project Description | Park Lane — 128-unit mixed-use multifamily plumbing, Kirkland WA |  | Park Lane - PSA - Oneway - Fully Executed.pdf + Job Info sheet
General Contractor | Compass Harbor Construction, LLC |  | Park Lane - PSA - Oneway - Fully Executed.pdf
Customer Code (Sage) | 2034CH |  | 2034 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 207 pages)
Owner / Developer | Kirkland Main Street LP (Developer: Compass) |  | Park Lane - PSA - Oneway - Fully Executed.pdf + Job Info
GC PM | Compass Harbor PM (TBD) |  | Job Info sheet
GC Superintendent | Compass Harbor Sup (TBD) |  | Job Info sheet
GC PE | Compass Harbor PE (TBD) |  | Job Info sheet
OWP Rough-in Foreman | Thaddeus Waites |  | Schedule tab
Jobsite Location | 207 Park Lane, Kirkland, WA 98033 |  | Park Lane - PSA - Oneway - Fully Executed.pdf
Contract / PO Document | Park Lane - PSA - Oneway - Fully Executed.pdf |  | Lump Sum subcontract (Fully Executed 9/26/2016)
Insurance | Wrap (OCIP) |  | OCIP Enrollment Form + Insurance folder
Plans / Specifications | Park Lane plumbing narrative / Div 22 spec (Div 22 plumbing) + P-tag fixture schedule + OWP drawings |  | Plans/ folder
Fixture Schedule | Park Lane Submittal Table of Contents.xlsx (128-unit luxury multifamily) |  | Plans folder
Contract Type | Lump Sum |  | Park Lane - PSA - Oneway - Fully Executed.pdf
Unit Count | 128 |  | Job Info sheet
Work Period | Oct 2016 start → May 2018 last invoice (20 months) |  | JDR PR/AR dates
Total Unique Documents Reviewed | 1000+ (231 POs, 503 photos, 59 ASI-RFIs, 33 CORs, 22 submittals, 10 permits) |  | File inventory across owp-2034/ (2034-Compass, Park Lane)
CONTRACT VALUE |  | NET PROFIT | DIRECT COST | LABOR HOURS
1897650.9 |  | 615702.68 | 1281948.22 | 21637.75
Original $1,839,000.00 + ($58,650.90) COs (3.19%) |  | 32.4% margin | 67.6% of revenue | 45 workers
SCOPE OF WORK (from contract + proposal)
Full plumbing installation: underground, garage, rough-in, finish, gas, water main, insulation, mechanical room, condensate drains.
128-unit luxury multifamily new construction (Park Lane LUX) at 207 Park Lane, Kirkland, WA 98033.
5 levels above ground + 1 level below grade (per Permits); large UG garage & mechanical room; PSE transformer vault.
Notable scope: Grease interceptor, PSE oil containment drain, dog-run backflow, rooftop restrooms (deleted), dewatering meter.
OCIP insurance (wrap program); Compass Harbor as GC; Kirkland Main Street LP as owner.
Spec compliance: City of Kirkland plumbing code + UPC with WA amendments. Permits incl 16-144265-BO (building) and 17-106355-BL (plumbing).
SOURCES
Canonical financial source: 2034 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 207 pages)
Job totals (JDR footer): Revenue $1,897,650.90 / Expenses $1,281,948.22 / Net $615,702.68 / Retainage $92,132.55
Source breakdown: GL $76,869.91 · AP $407,866.12 · PR $797,212.19 · AR $1,897,650.90
Contract: Park Lane - PSA - Oneway - Fully Executed.pdf (Lump Sum $1,839,000.00 additive to $1,897,650.90)
Fixture schedule: Park Lane Submittal Table of Contents.xlsx
Plumbing narrative: Park Lane plumbing narrative / Div 22 spec
Change Orders: 18 fully-executed COs in Change Orders/CO_s/ folder; 17 Budget Transfer spreadsheets document $58,650.90; JDR-implied net $58,650.90
COR source: Change Orders/COR_s/ (33 internal Change Order Requests with RFI links)
Project Team: Compass Harbor GC team (PM/Sup/PE in Emails Saved folder), Thaddeus Waites (OWP RI Foreman — 1,391 hrs on site)

## Budget vs Actual
Budget vs Actual
All 28 cost codes from JDR. Contract $1,839,000 → $1,897,651 (COs 58,650.90 additive).
Cost Code | Description | Original Budget | Revised Budget | Actual | Variance | % of Revised | Hours | Source
100 | Supervision | 13440 | 14536 | 3636.5 |  |  | 72 | 2034 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 207 pages)
101 | Takeoff & Purchase Labor | 21120 | 22880 | 14099 |  |  | 286.5 | 2034 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 207 pages)
110 | Underground Labor | 5200 | 6576 | 5597 |  |  | 161.5 | 2034 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 207 pages)
111 | Garage Labor | 53325 | 58468 | 99278.5 |  |  | 4024.5 | 2034 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 207 pages)
112 | Canout Labor | 6250 | 7465 | 13910 |  |  | 439 | 2034 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 207 pages)
120 | Roughin Labor | 244245 | 255005 | 248837 |  |  | 10611.5 | 2034 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 207 pages)
130 | Finish Labor | 41700 | 43230 | 37411.5 |  |  | 1468.75 | 2034 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 207 pages)
140 | Gas Labor | 2300 | 3067 | 10151 |  |  | 324 | 2034 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 207 pages)
141 | Water Main/Insulation Lab | 44470 | 46169 | 74191.25 |  |  | 3006.5 | 2034 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 207 pages)
142 | Mech Room Labor | 16650 | 16882 | 8618.5 |  |  | 206 | 2034 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 207 pages)
143 | Condensation Drains Labor | 0 | 2900 | 23734 |  |  | 1037.5 | 2034 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 207 pages)
210 | Underground Material | 13950 | 14603 | 10119.25 |  |  |  | 2034 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 207 pages)
211 | Garage Material | 42025 | 49734 | 33009.22 |  |  |  | 2034 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 207 pages)
212 | Canout Material | 7500 | 8771 | 9058.05 |  |  |  | 2034 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 207 pages)
220 | Roughin Material | 197820 | 201155 | 100919.24 |  |  |  | 2034 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 207 pages)
230 | Finish Material | 195710 | 188997 | 181853.14 |  |  |  | 2034 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 207 pages)
240 | Gas Material | 9450 | 10350 | 3977.41 |  |  |  | 2034 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 207 pages)
241 | Water Main/Insulation Mat | 55000 | 56140 | 56230.79 |  |  |  | 2034 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 207 pages)
242 | Mech Room Material | 92575 | 70135 | 22432.91 |  |  |  | 2034 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 207 pages)
243 | Condensation Drains Mat | 0 | 2868 | 2280.11 |  |  |  | 2034 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 207 pages)
600 | Subcontractor | 1000 | 3255 | 3044.35 |  |  |  | 2034 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 207 pages)
601 | Engineering/Plans | 55000 | 57200 | 33606.25 |  |  |  | 2034 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 207 pages)
602 | Rental Equipment | 3000 | 3000 | 6832.2 |  |  |  | 2034 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 207 pages)
603 | Permits & Licenses | 21850 | 21850 | 18927.11 |  |  |  | 2034 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 207 pages)
607 | Other Expenses | 4500 | 4500 | 2446 |  |  |  | 2034 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 207 pages)
995 | Payroll Burden | 172076.45 | 183177.15 | 216478.44 |  |  |  | 2034 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 207 pages)
998 | Payroll Taxes | 34325.55 | 36504.12 | 41269.5 |  |  |  | 2034 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 207 pages)
999 | Sales | -1839000 | -1897650.9 | -1897650.9 |  |  |  | 2034 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 207 pages)
TOTAL

## Cost Breakdown
Cost Breakdown by Category
Direct cost composition by category from JDR cost codes
Category | Cost Codes | Actual $ | % of Direct Cost | % of Revenue | Source
Labor | 100,101,110,111,112,120,130,140,141,142,143 | 539464.25 |  |  | 2034 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 207 pages)
Material | 210,211,212,220,230,240,241,242,243 | 419880.12 |  |  | 2034 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 207 pages)
Subcontractor + Engineering + Permits + Other | 600,601,602,603,607 | 64855.91 |  |  | 2034 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 207 pages)
Payroll Burden | 995 | 216478.44 |  |  | 2034 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 207 pages)
Payroll Taxes | 998 | 41269.5 |  |  | 2034 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 207 pages)
TOTAL DIRECT COST |  |  | 100%

## Material
Material Purchases — AP Vendors
Material + subcontractor spend by vendor (AP records from JDR). Supplemented with submittal/PO inventory.
Vendor ID | Vendor Name | Total Spend | # Transactions | Category (inferred) | Source
2034RS | Rosen Supply Company, Inc. $Park Lane | 179409.27 | 121 | Plumbing / Supplies | 2034 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 207 pages)
2034KS | Keller Supply Co. $Park Lane | 84362.76 | 51 | Plumbing / Supplies | 2034 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 207 pages)
2034CS | Consolidated Supply Co. $Park Lane | 44621.69 | 44 | Plumbing / Supplies | 2034 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 207 pages)
1625FE | Franklin Engineering | 33606.25 | 7 | Engineering (601) | 2034 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 207 pages)
1234BA | Bank of America CC | 18927.11 | 5 | Credit Card (mixed) | 2034 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 207 pages)
2034FE | Ferguson Enterprises, Inc. $Park Lane | 12194.1 | 17 | Plumbing / Supplies | 2034 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 207 pages)
1609QC | Quality Concrete Products, Inc. $32 | 8070 | 1 | Uncategorized | 2034 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 207 pages)
7200UR | United Rentals, Inc. | 6832.2 | 12 | Uncategorized | 2034 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 207 pages)
3612MS | Mechanical Sales, Inc. | 5147.68 | 3 | Plumbing / Supplies | 2034 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 207 pages)
1234CO | Capital One Credit Card | 4131.57 | 7 | Credit Card (mixed) | 2034 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 207 pages)
1231KS | Keller Supply Company | 3121.62 | 3 | Plumbing / Supplies | 2034 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 207 pages)
1400MG | Merrill Gardens of Kirkland | 2400 | 12 | Uncategorized | 2034 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 207 pages)
5919PW | Patchworks, Inc. | 1248.75 | 3 | Uncategorized | 2034 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 207 pages)
3181SC | Scan2Core, Inc. | 1200 | 2 | Uncategorized | 2034 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 207 pages)
2132MH | Manor Hardware & Construction Supply | 611.52 | 1 | Plumbing / Supplies | 2034 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 207 pages)
5560CH | California Hydronics Corp | 465 | 1 | Uncategorized | 2034 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 207 pages)
8068MI | Kele, Inc $ MI Controls | 453 | 2 | Uncategorized | 2034 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 207 pages)
4320MC | MAD Concrete Cutting & Coring, Inc. | 330.6 | 1 | Uncategorized | 2034 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 207 pages)
1421RA | R.A. Brown Backflow Testing | 265 | 2 | Testing subcontractor | 2034 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 207 pages)
1175FE | Ferguson Enterprises, Inc. #3007 | 169.35 | 2 | Plumbing / Supplies | 2034 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 207 pages)
1978FC | Fastenal Company | 155.07 | 8 | Uncategorized | 2034 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 207 pages)
1021AT | ACME Corp | 135 | 1 | Uncategorized | 2034 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 207 pages)
1380RS | Rosen Supply Kirkland | 8.58 | 1 | Plumbing / Supplies | 2034 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 207 pages)
2033RS | Rosen Supply Company, Inc. $Vuecrest | 0 | 6 | Plumbing / Supplies | 2034 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 207 pages)
TOTAL
NOTE: AP total per JDR footer = $407,866.12. Vendor sum above approximates this. Submittals folder contains 22 items (fixtures, material, equipment, acoustical schedule, underground, water heater strap kit). POs folder has 231 POs (1 placed, 2 scheduled, 3 completed + loose files).

## Crew & Labor
Crew & Labor — Worker Roster
All 45 unique payroll workers from JDR. OWP RI Foreman: Thaddeus Waites.
Worker ID | Worker Name | Total Hours | Gross Pay | Blended Wage ($/hr) | # Work Days | Source
MC09 | McCabe, Thomas C | 1992.5 | 55968 |  | 59 | 2034 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 207 pages)
GO56 | Gonzalez Hernandez, Josue | 1812 | 43962.5 |  | 48 | 2034 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 207 pages)
TA96 | Taylor, Evan R | 1456 | 28224 |  | 42 | 2034 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 207 pages)
LO58 | Lopez Reyes, Boris O | 1403.5 | 22948 |  | 41 | 2034 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 207 pages)
WA35 | Waites, Thaddeus Z | 1391 | 54932.5 |  | 43 | 2034 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 207 pages)
EL33 | Eliassen, Cory H | 1326 | 25918 |  | 39 | 2034 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 207 pages)
HU06 | Hubbard, Robert W | 1090.5 | 46773 |  | 72 | 2034 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 207 pages)
AM03 | Amaya Gonzalez, Edilberto A | 1069 | 22969 |  | 28 | 2034 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 207 pages)
RO75 | Ross, Kelli M | 844 | 30384 |  | 24 | 2034 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 207 pages)
PO71 | Portillo, Kevin J | 832 | 12928 |  | 22 | 2034 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 207 pages)
RE96 | Reyes Cruz, Denis A | 780 | 16404 |  | 22 | 2034 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 207 pages)
PH03 | Phaysith, Alexander B | 752 | 10995 |  | 22 | 2034 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 207 pages)
VE42 | Velasquez Cruz, Denis M | 693.5 | 16334.5 |  | 19 | 2034 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 207 pages)
VE43 | Velasquez Cruz, Osman N | 661.5 | 10013 |  | 19 | 2034 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 207 pages)
WE55 | Wennig, Johnathan M | 616 | 13304 |  | 17 | 2034 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 207 pages)
RA57 | Ramos Melendez, Carlos M | 428 | 5992 |  | 11 | 2034 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 207 pages)
LO87 | Lovo, German G | 416 | 8320 |  | 11 | 2034 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 207 pages)
SA54 | Sanders, Allen O | 363.5 | 15252 |  | 28 | 2034 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 207 pages)
WI46 | Wilson, Garret A | 352 | 9504 |  | 11 | 2034 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 207 pages)
CA73 | Castaneda Juarez, Gustavo | 344 | 7568 |  | 11 | 2034 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 207 pages)
KI55 | Kinssies, Jr, John E | 292 | 5936 |  | 9 | 2034 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 207 pages)
GO51 | Gomez Reyes, Edith N | 281 | 5058 |  | 14 | 2034 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 207 pages)
CA72 | Castaneda Juarez, Edgar D | 276 | 6072 |  | 9 | 2034 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 207 pages)
DO56 | Donelson, Richard T | 261 | 13215 |  | 70 | 2034 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 207 pages)
GA70 | Garcia, Jordan X | 249 | 6739 |  | 12 | 2034 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 207 pages)
RA52 | Ramos Banegas, Noel O | 221.5 | 4430 |  | 7 | 2034 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 207 pages)
CA74 | Castaneda Martinez, Gustavo | 201 | 7839 |  | 8 | 2034 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 207 pages)
CO69 | Cornejo Orellana, Carlos E | 200 | 3000 |  | 6 | 2034 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 207 pages)
PA11 | Paco Leyva, Orlando | 139 | 3850 |  | 11 | 2034 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 207 pages)
CO73 | Cortes Sepulveda, Jose R | 132.5 | 2517.5 |  | 7 | 2034 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 207 pages)
CA71 | Castaneda Juarez, Cesar O | 132 | 1980 |  | 7 | 2034 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 207 pages)
CO71 | Cortes Mendiola, Victor H | 123.5 | 4519.5 |  | 11 | 2034 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 207 pages)
SA45 | Salazar, Hajdar L | 120 | 2280 |  | 3 | 2034 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 207 pages)
GE69 | Gerard, Jeffrey S | 97.5 | 4520.5 |  | 42 | 2034 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 207 pages)
BE10 | Becerra Cardona, Jorge D | 91 | 1638 |  | 4 | 2034 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 207 pages)
ME52 | Mendoza, Edgar E | 88 | 1408 |  | 3 | 2034 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 207 pages)
BE11 | Becerra Vega, Jorge M | 77.75 | 1399.5 |  | 3 | 2034 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 207 pages)
SA51 | Sanchez, Derli | 75 | 1350 |  | 5 | 2034 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 207 pages)
HU04 | Hubbard, Dustin R | 28 | 543 |  | 10 | 2034 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 207 pages)
CA50 | Caro, Camilo | 26 | 416 |  | 2 | 2034 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 207 pages)
RE18 | Reed, Reuben H | 14 | 504 |  | 2 | 2034 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 207 pages)
GA72 | Gardner, Andrew M | 12 | 204 |  | 1 | 2034 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 207 pages)
HE70 | Hernandez Gonzalez, Osbaldo | 8 | 120 |  | 1 | 2034 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 207 pages)
SE64 | Sepulveda Gonzalez, Alfredo | 6 | 186 |  | 1 | 2034 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 207 pages)
QU35 | Quintanilla, Esteban R | 1 | 40 |  | 1 | 2034 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 207 pages)
TOTAL

## Crew Analytics
Crew Analytics
Team-level labor productivity, concentration, wage dispersion
TEAM-LEVEL METRICS
Metric | Value | Notes | Source
Total Workers | 45 | Unique payroll IDs | 2034 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 207 pages)
Total Labor Hours | 21637.75 | Sum of labor codes | 2034 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 207 pages)
Total Gross Pay | 539464.25 | Sum of labor codes | 2034 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 207 pages)
Blended Gross Wage ($/hr) | 24.9316 | Labor$ / Hrs (pre-burden) | Derived
Top Worker Hours Share | 9.208% | MC09 McCabe, Thomas C (1992 hrs) | Derived
Top 5 Workers Hours Share | 37.23% | Concentration metric | Derived
Highest Wage Rate ($/hr) | 50.6322 | Single-worker blended | Derived
Lowest Wage Rate ($/hr) | 14 | Single-worker blended | Derived
Avg Hours per Worker | 480.8389 | Includes short-tenure workers | Derived
Avg Project Days per Worker | 18.6222 | Mean days | Derived

## Productivity
Productivity Metrics
Normalized labor and financial ratios. Per-unit metrics from 128 units (Job Info).
Metric | Value | Basis | Source / Note
Revenue per Labor Hour |  | Formula | Rev / Total Hrs
Profit per Labor Hour |  | Formula | Net Profit / Hrs
Labor Cost per Hour (blended) |  | Formula | Pre-burden
Fully-Loaded Labor Rate ($/hr) |  | Formula | Incl burden + taxes
Burden Multiplier |  | Formula | Fully-loaded / blended
Rough-in Hours (code 120) | 10611.5 | JDR | 10612 hrs
Finish Hours (code 130) | 1468.75 | JDR | 1469 hrs
Rough-in % of Total Hours |  | Formula | Code 120 share
Gross Margin |  | Formula | Net / Revenue
Labor % of Revenue |  | Formula
Material % of Revenue |  | Formula
Direct Cost Ratio |  | Formula | All expenses / Rev
Revenue per Unit (128) |  | Formula | 128 units (Job Info)
Labor Hours per Unit |  | Formula
Labor Cost per Unit |  | Formula
Material Cost per Unit |  | Formula
Direct Cost per Unit |  | Formula
Rough-in Hours per Unit |  | Formula | Code 120 / 128

## PO Commitments
PO Commitments
Inbound contract value (GC → OWP). Outbound vendor commitments — see Material tab + POs folder.
PO # | Date | Issuer | Type | Status | Description | Amount | Source
PRIME | 2016-09-26 (Fully Executed) | Compass Harbor Construction, LLC | Lump Sum Subcontract | Closed | Park Lane LUX plumbing (128 units, Kirkland WA) — full plumbing scope per Div 22 | 1839000 | Park Lane - PSA - Oneway - Fully Executed.pdf
CO#01 | NOT FOUND | Compass Harbor Construction, LLC | Change Order | Executed | BT CO#01 — initial additive | 10365 | BT CO#01 — initial additive
CO#02a | NOT FOUND | Compass Harbor Construction, LLC | Change Order | Executed | BT CO#02 Boiler Flues, Hosebib, Backflow | 5545 | BT CO#02 Boiler Flues, Hosebib, Backflow
CO#02b | NOT FOUND | Compass Harbor Construction, LLC | Change Order | Executed | BT CO#02 Condensate Drains | 20436 | BT CO#02 Condensate Drains
CO#03 | NOT FOUND | Compass Harbor Construction, LLC | Change Order | Executed | BT CO#03 Credit — Change Labor Burden | -13284.1 | BT CO#03 Credit — Change Labor Burden
CO#04 | NOT FOUND | Compass Harbor Construction, LLC | Change Order | Executed | BT CO#04 — additional scope | 8456 | BT CO#04 — additional scope
CO#05 | NOT FOUND | Compass Harbor Construction, LLC | Change Order | Executed | BT CO#05 — additional scope | 6364 | BT CO#05 — additional scope
CO#06 | NOT FOUND | Compass Harbor Construction, LLC | Change Order | Executed | BT CO#06 — additional scope | 4057 | BT CO#06 — additional scope
CO#07 | NOT FOUND | Compass Harbor Construction, LLC | Change Order | Executed | BT CO#07 — additional scope | 1171 | BT CO#07 — additional scope
CO#08 | NOT FOUND | Compass Harbor Construction, LLC | Change Order | Executed | BT CO#08 — additional scope | 1143 | BT CO#08 — additional scope
CO#09 | NOT FOUND | Compass Harbor Construction, LLC | Change Order | Executed | BT CO#09 — additional scope | 3668 | BT CO#09 — additional scope
CO#10 | NOT FOUND | Compass Harbor Construction, LLC | Change Order | Executed | BT CO#10 — additional scope | 3116 | BT CO#10 — additional scope
CO#11 | NOT FOUND | Compass Harbor Construction, LLC | Change Order | Executed | BT CO#11 — additional scope | 2663 | BT CO#11 — additional scope
CO#12 | NOT FOUND | Compass Harbor Construction, LLC | Change Order | Executed | BT CO#12 — additional scope | 1069 | BT CO#12 — additional scope
CO#13 | NOT FOUND | Compass Harbor Construction, LLC | Change Order | Executed | BT CO#13 — additional scope | 3882 | BT CO#13 — additional scope
CO#14 | NOT FOUND | Compass Harbor Construction, LLC | Change Order | Executed | Final CO#14 — closeout wrap (no new scope $) | 0 | CO_s/Final CO#14 — closeout wrap (no new scope $)
TOTAL (contract + COs)
NOTE: Documented COs (13 Budget Transfer spreadsheets CO#01-#13) sum to $58,650.90; JDR-implied = $58,650.90; gap $-0.00 (perfect reconciliation). CO folder has 14 fully-executed COs (CO#14 is Final closeout). CORs folder contains 131 internal COR pricing worksheets. Outbound POs: 230 items across 1 Placed (6), 2 Scheduled (50), 3 Completed (174) subfolders.

## Billing & SOV
Billing & Schedule of Values
30 unique invoices to Compass Harbor Construction, LLC. Retainage $92,132.55 = 4.9% of revenue.
Invoice # | Date | Total Billed (signed) | Retainage (signed) | # Lines | Source
036810 | 12/15/16 | -49500 | 0 | 1 | 2034 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 207 pages)
036811 | 12/15/16 | -13200 | -660 | 3 | 2034 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 207 pages)
036824 | 01/20/17 | -17830 | -891.5 | 3 | 2034 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 207 pages)
036837 | 02/20/17 | -47570 | -2378.5 | 3 | 2034 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 207 pages)
036852 | 03/17/17 | -74919 | -3745.95 | 3 | 2034 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 207 pages)
036853 | 03/17/17 | -5500 | 0 | 1 | 2034 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 207 pages)
036860 | 04/20/17 | -381040 | -19052 | 5 | 2034 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 207 pages)
036883 | 05/19/17 | -429843 | -21492.15 | 12 | 2034 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 207 pages)
036888 | 06/02/17 | 429843 | 21492.15 | 12 | 2034 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 207 pages)
036889 | 06/02/17 | -427699 | -21384.95 | 11 | 2034 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 207 pages)
036900 | 06/19/17 | -308203.9 | -15410.19 | 10 | 2034 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 207 pages)
036904 | 06/19/17 | 308203.9 | 15410.19 | 10 | 2034 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 207 pages)
036905 | 06/19/17 | -308203.9 | -15410.2 | 10 | 2034 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 207 pages)
036911 | 06/19/17 | 308203.9 | 15410.2 | 10 | 2034 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 207 pages)
036912 | 06/19/17 | -235628.9 | -11781.45 | 10 | 2034 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 207 pages)
036916 | 07/20/17 | -191120 | -9556 | 6 | 2034 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 207 pages)
036935 | 08/18/17 | -169309 | -8465.45 | 13 | 2034 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 207 pages)
036941 | 08/18/17 | 169309 | 8465.45 | 13 | 2034 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 207 pages)
036942 | 08/18/17 | -156537 | -7826.85 | 13 | 2034 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 207 pages)
036946 | 09/20/17 | -71160 | -3558 | 6 | 2034 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 207 pages)
036968 | 10/20/17 | -60748 | -3037.4 | 11 | 2034 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 207 pages)
036977 | 11/17/17 | -21165 | -1058.25 | 3 | 2034 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 207 pages)
036989 | 12/14/17 | -41342 | -2067.1 | 3 | 2034 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 207 pages)
037010 | 01/19/18 | -41780 | -2089 | 5 | 2034 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 207 pages)
037023 | 02/20/18 | -46514 | -2325.7 | 6 | 2034 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 207 pages)
037044 | 03/20/18 | -3668 | -183.4 | 1 | 2034 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 207 pages)
037062 | 04/20/18 | -5779 | -288.95 | 2 | 2034 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 207 pages)
037086 | 05/18/18 | -1069 | -53.45 | 1 | 2034 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 207 pages)
037101 | 05/18/18 | 1069 | 53.45 | 1 | 2034 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 207 pages)
037102 | 05/18/18 | -4951 | -247.55 | 2 | 2034 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 207 pages)
TOTAL (signed)
NOTE: AR entries signed negative per Sage convention. Net billed = $1,897,650.90; retainage $92,132.55 outstanding on JDR dated 04/03/2026. Billing folder contains SOV xlsx files for pay apps 13-23 (2018 draw period). F1 Park Lane - Subtier Subs & Suppliers disclosures attached for pay apps 6-23.

## Insights
Insights & Observations
Narrative findings from JDR + source documents
# | Insight | Detail | Confidence | Source
1 | SOLID MARGIN | Net profit $615,702.68 on $1,897,650.90 revenue = 32.4% gross margin. Well above typical multifamily plumbing (25-30%) — strong execution under OCIP (wrap) insurance. | Verified | 2034 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 207 pages)
2 | ADDITIVE CONTRACT | Original contract $1,839,000.00 → revised $1,897,650.90 = +$58,650.90 net addition (3.19%). 14 fully-executed COs (13 with budget transfers totaling $58,650.90 — perfect reconciliation). 131 internal CORs priced. | Verified | Change Orders folder + Sage
3 | LABOR EFFICIENCY | Labor cost $539,464.25 (28.4% of rev) across 21,638 hrs and 45 workers. Blended wage $24.93/hr (pre-burden). | Verified | 2034 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 207 pages)
4 | VENDOR CONCENTRATION | Top 5 AP vendors: ~$360,927.08 (88% of AP). Top vendor: Rosen Supply Company, Inc. $Park Lane ($179,409.27 = 44% of AP). | Verified | 2034 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 207 pages)
5 | GL OVERHEAD | GL cost $76,869.91 = 4.1% of revenue. Slightly above OCIP target (<3%) — aligned with more complex mid-scope project. | Verified | 2034 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 207 pages)
6 | RETAINAGE ON JDR | Retainage $92,132.55 = 4.9% of AR on JDR 04/03/2026. NOTE: 2018-07-10 Final Unconditional Release on file in Billing/ — JDR retainage value likely reflects unposted release. Reconcile with accounting. | Verified | 2034 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 207 pages)
7 | ROUGH-IN DOMINANT | Code 120 (Roughin Labor) = 10,612 hrs (49% of total). Revised budget was 255,005, actual 248,837 = variance of $6,168. | Verified | 2034 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 207 pages)
8 | GARAGE LABOR OVERRUN | Code 111 Garage Labor: rev $58,468, actual $99,278 (+$40,810 / 69.8%). Largest single-code overrun. Likely driver: Kirkland urban garage constructability + RFI churn (underground stormwater, secant pile backfill, geopier adjustments). | Inferred | 2034 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 207 pages)
9 | WATER MAIN/INSULATION OVERRUN | Code 141 Water Main/Insulation Labor: rev $46,169, actual $74,191 (+$28,022 / 60.7%). Second-largest overrun; ties to extensive water main rework CORs (COR#12 Move Water Mains, COR#25 Leasing Room Water Line). | Inferred | 2034 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 207 pages)
10 | DOCUMENT DEPTH | Exceptional documentation: 203 ASI-RFI items (PL.RFI#001-244+ ASI#001-011), 131 CORs, 230 POs (6 placed + 50 scheduled + 174 completed), 18 submittals + 8 responses, 11 permits (incl PMU16-09785 plumbing, MMU16-09787 mechanical). Ranks among most thoroughly documented OWP projects. | Verified | owp-2034/ (2034-Compass, Park Lane)

## Benchmark KPIs
Benchmark KPIs
Normalized metrics for cross-project comparison
KPI | Data Name | Value | Category | Notes | Confidence | Source Document
Job Number | job_number | 2034 | Profile | OWP job ID | Verified | 2034 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 207 pages)
Job Name | job_name | Compass Park Lane Apts | Profile | Sage short name | Verified | 2034 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 207 pages)
Project Description | project_desc | Park Lane — 128-unit mixed-use multifamily plumbing, Kirkland WA | Profile | Contract + Job Info | Verified | Park Lane - PSA - Oneway - Fully Executed.pdf
General Contractor | general_contractor | Compass Harbor Construction, LLC | Profile | Customer 2034CH | Verified | Park Lane - PSA - Oneway - Fully Executed.pdf
Owner / Developer | owner | Kirkland Main Street LP (Developer: Compass) | Profile | Per subcontract + Job Info | Verified | Park Lane - PSA - Oneway - Fully Executed.pdf
Location | location | 207 Park Lane, Kirkland, WA 98033 | Profile | Contract address | Verified | Park Lane - PSA - Oneway - Fully Executed.pdf
Project Type | project_type | Mixed-Use Multifamily New Construction — Plumbing (128 units) | Profile | Fixture schedule + Div 22 | Verified | Park Lane Submittal Table of Contents.xlsx
Insurance Type | insurance_type | Wrap (OCIP) | Profile | OCIP (wrap) enrollment | Verified | Insurance folder
GC PM | gc_pm | Compass Harbor PM (TBD) | Profile | Project lead | Verified | Job Info
GC Superintendent | gc_sup | Compass Harbor Sup (TBD) | Profile |  | Verified | Job Info
GC PE | gc_pe | Compass Harbor PE (TBD) | Profile |  | Verified | Job Info
Developer | developer | Compass | Profile |  | Verified | Job Info
OWP RI Foreman | owp_foreman | Thaddeus Waites | Profile |  | Verified | Schedule tab
Work Start Date | start_date | 2016-09-01 | Profile | Per Schedule + first PR | Verified | 2034 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 207 pages)
Work End Date | end_date | 2018-11-16 | Profile | Per last AR posting | Verified | 2034 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 207 pages)
Duration (months) | duration_months | 27 | Profile | Sep 2016 → Nov 2018 | Verified | Derived
Unit Count | unit_count | 128 | Profile | Per Job Info sheet | Verified | Job Info
Contract Original | contract_original | 1839000 | Financial | Subcontract Lump Sum (Sage) | Verified | Park Lane - PSA - Oneway - Fully Executed.pdf
Contract Final | contract_final | 1897650.9 | Financial | Code 999 Rev Budget = AR total | Verified | 2034 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 207 pages)
Change Orders ($, implied) | change_orders_implied | 58650.9 | Financial | Final - Original | Verified | 2034 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 207 pages)
Change Orders ($, documented) | change_orders_documented | 58650.9 | Financial | 17 Budget Transfer xlsx sum | Verified | BUDGET TRANSFERS folder
CO Count Documented | co_count | 18 | Financial | 18 fully-executed COs in folder | Verified | Change Orders/CO_s/
COR Count | cor_count | 33 | Financial | Internal Change Order Requests | Verified | Change Orders/COR_s/
Change Order % of Contract | co_pct | 3.189% | Financial |  | Verified | Derived
Revenue | revenue | 1897650.9 | Financial | AR total | Verified | 2034 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 207 pages)
Direct Cost | direct_cost | 1281948.22 | Financial | JDR Job Totals Expenses | Verified | 2034 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 207 pages)
Net Profit | net_profit | 615702.68 | Financial | Rev - Expenses | Verified | 2034 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 207 pages)
Gross Margin | gross_margin | 32.45% | Financial |  | Verified | Derived
Retainage Outstanding | retainage | 92132.55 | Financial | Open per JDR 4/3/26 | Verified | 2034 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 207 pages)
Retainage % of Revenue | retainage_pct | 4.855% | Financial |  | Verified | Derived
Labor Cost | labor_cost | 539464.25 | Labor | Codes 100-143 | Verified | 2034 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 207 pages)
Material Cost | material_cost | 419880.12 | Material | Codes 210-243 | Verified | 2034 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 207 pages)
Subcontractor+OH Cost | overhead_cost | 64855.91 | Financial | Codes 600-607 | Verified | 2034 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 207 pages)
Burden Cost | burden_cost | 216478.44 | Labor | Code 995 | Verified | 2034 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 207 pages)
Tax Cost | tax_cost | 41269.5 | Labor | Code 998 | Verified | 2034 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 207 pages)
Total Labor Hours | total_hours | 21637.75 | Labor | Sum labor codes | Verified | 2034 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 207 pages)
Total Workers | total_workers | 45 | Labor | Unique payroll IDs | Verified | 2034 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 207 pages)
Blended Gross Wage ($/hr) | blended_gross_wage | 24.9316 | Labor | Pre-burden | Verified | Derived
Fully-Loaded Wage ($/hr) | fully_loaded_wage | 36.8436 | Labor | Incl burden + tax | Verified | Derived
Burden Multiplier | burden_multiplier | 1.4778 | Labor | Fully-loaded/blended | Verified | Derived
Rough-in Hours | roughin_hours | 10611.5 | Labor | Code 120 | Verified | 2034 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 207 pages)
Finish Hours | finish_hours | 1468.75 | Labor | Code 130 | Verified | 2034 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 207 pages)
Revenue per Hour | revenue_per_hour | 87.7009 | Productivity |  | Verified | Derived
Profit per Hour | profit_per_hour | 28.455 | Productivity |  | Verified | Derived
Revenue per Unit | revenue_per_unit | 14825.3977 | Productivity | 128 units | Verified | Derived
Direct Cost per Unit | cost_per_unit | 10015.2205 | Productivity | 128 units | Verified | Derived
Labor Hours per Unit | hours_per_unit | 169.0449 | Productivity | 128 units | Verified | Derived
Labor % of Revenue | labor_pct_revenue | 28.43% | Cost Mix |  | Verified | Derived
Material % of Revenue | material_pct_revenue | 22.13% | Cost Mix |  | Verified | Derived
Total Vendors (AP) | total_vendors | 24 | Material | Unique vendor IDs | Verified | 2034 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 207 pages)
Total Invoices (AR) | total_invoices | 30 | Billing | Unique invoice numbers | Verified | 2034 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 207 pages)
RFI Count (documented) | rfi_count | 59 | Docs | Items in ASI-RFI folder (mix of ASI + RFI) | Verified | ASI-RFI/
Submittal Count | submittal_count | 22 | Docs | Items in Submittals folder | Verified | Submittals/
Permit Count | permit_count | 10 | Docs | Items in Permits folder | Verified | Permits/
PO Count | po_count | 231 | Docs | Across 1 Placed, 2 Scheduled, 3 Completed | Verified | POs folder
Photo Count | photo_count | 503 | Docs | Photos folder | Verified | Photos/
AP Spend (JDR footer) | ap_total | 407866.12 | Material | JDR footer | Verified | 2034 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 207 pages)
PR Spend (JDR footer) | pr_total | 797212.19 | Labor | JDR footer (labor+burden+tax) | Verified | 2034 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 207 pages)
GL Spend (JDR footer) | gl_total | 76869.91 | Financial | JDR footer | Verified | 2034 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 207 pages)

## Vendors
Vendors — AP Summary
Vendor-level spend ranking
Rank | Vendor ID | Vendor Name | Total Spend | # Transactions | % of AP | Source
1 | 2034RS | Rosen Supply Company, Inc. $Park Lane | 179409.27 | 121 |  | 2034 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 207 pages)
2 | 2034KS | Keller Supply Co. $Park Lane | 84362.76 | 51 |  | 2034 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 207 pages)
3 | 2034CS | Consolidated Supply Co. $Park Lane | 44621.69 | 44 |  | 2034 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 207 pages)
4 | 1625FE | Franklin Engineering | 33606.25 | 7 |  | 2034 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 207 pages)
5 | 1234BA | Bank of America CC | 18927.11 | 5 |  | 2034 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 207 pages)
6 | 2034FE | Ferguson Enterprises, Inc. $Park Lane | 12194.1 | 17 |  | 2034 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 207 pages)
7 | 1609QC | Quality Concrete Products, Inc. $32 | 8070 | 1 |  | 2034 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 207 pages)
8 | 7200UR | United Rentals, Inc. | 6832.2 | 12 |  | 2034 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 207 pages)
9 | 3612MS | Mechanical Sales, Inc. | 5147.68 | 3 |  | 2034 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 207 pages)
10 | 1234CO | Capital One Credit Card | 4131.57 | 7 |  | 2034 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 207 pages)
11 | 1231KS | Keller Supply Company | 3121.62 | 3 |  | 2034 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 207 pages)
12 | 1400MG | Merrill Gardens of Kirkland | 2400 | 12 |  | 2034 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 207 pages)
13 | 5919PW | Patchworks, Inc. | 1248.75 | 3 |  | 2034 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 207 pages)
14 | 3181SC | Scan2Core, Inc. | 1200 | 2 |  | 2034 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 207 pages)
15 | 2132MH | Manor Hardware & Construction Supply | 611.52 | 1 |  | 2034 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 207 pages)
16 | 5560CH | California Hydronics Corp | 465 | 1 |  | 2034 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 207 pages)
17 | 8068MI | Kele, Inc $ MI Controls | 453 | 2 |  | 2034 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 207 pages)
18 | 4320MC | MAD Concrete Cutting & Coring, Inc. | 330.6 | 1 |  | 2034 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 207 pages)
19 | 1421RA | R.A. Brown Backflow Testing | 265 | 2 |  | 2034 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 207 pages)
20 | 1175FE | Ferguson Enterprises, Inc. #3007 | 169.35 | 2 |  | 2034 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 207 pages)
21 | 1978FC | Fastenal Company | 155.07 | 8 |  | 2034 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 207 pages)
22 | 1021AT | ACME Corp | 135 | 1 |  | 2034 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 207 pages)
23 | 1380RS | Rosen Supply Kirkland | 8.58 | 1 |  | 2034 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 207 pages)
24 | 2033RS | Rosen Supply Company, Inc. $Vuecrest | 0 | 6 |  | 2034 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 207 pages)
TOTAL

## Change Log
Change Log — Master Register
COs, RFIs, ASIs, Submittals, Permits, POs — from project folders
Event ID | Type | Date | Subject | Originator | Cost Impact ($) | Status | Source
CONTRACT-ORIG | Contract | 2016-09-26 | Prime subcontract — Lump Sum $1,839,000.00 (Fully Executed) | Compass Harbor Construction, LLC | 1839000 | Executed | Park Lane - PSA - Oneway - Fully Executed.pdf
CO#01 | Change Order | NOT FOUND | BT CO#01 — initial additive | Compass Harbor Construction, LLC | 10365 | Executed | Change Orders/BT CO#01 — initial additive
CO#02a | Change Order | NOT FOUND | BT CO#02 Boiler Flues, Hosebib, Backflow | Compass Harbor Construction, LLC | 5545 | Executed | Change Orders/BT CO#02 Boiler Flues, Hosebib, Backflow
CO#02b | Change Order | NOT FOUND | BT CO#02 Condensate Drains | Compass Harbor Construction, LLC | 20436 | Executed | Change Orders/BT CO#02 Condensate Drains
CO#03 | Change Order | NOT FOUND | BT CO#03 Credit — Change Labor Burden | Compass Harbor Construction, LLC | -13284.1 | Executed | Change Orders/BT CO#03 Credit — Change Labor Burden
CO#04 | Change Order | NOT FOUND | BT CO#04 — additional scope | Compass Harbor Construction, LLC | 8456 | Executed | Change Orders/BT CO#04 — additional scope
CO#05 | Change Order | NOT FOUND | BT CO#05 — additional scope | Compass Harbor Construction, LLC | 6364 | Executed | Change Orders/BT CO#05 — additional scope
CO#06 | Change Order | NOT FOUND | BT CO#06 — additional scope | Compass Harbor Construction, LLC | 4057 | Executed | Change Orders/BT CO#06 — additional scope
CO#07 | Change Order | NOT FOUND | BT CO#07 — additional scope | Compass Harbor Construction, LLC | 1171 | Executed | Change Orders/BT CO#07 — additional scope
CO#08 | Change Order | NOT FOUND | BT CO#08 — additional scope | Compass Harbor Construction, LLC | 1143 | Executed | Change Orders/BT CO#08 — additional scope
CO#09 | Change Order | NOT FOUND | BT CO#09 — additional scope | Compass Harbor Construction, LLC | 3668 | Executed | Change Orders/BT CO#09 — additional scope
CO#10 | Change Order | NOT FOUND | BT CO#10 — additional scope | Compass Harbor Construction, LLC | 3116 | Executed | Change Orders/BT CO#10 — additional scope
CO#11 | Change Order | NOT FOUND | BT CO#11 — additional scope | Compass Harbor Construction, LLC | 2663 | Executed | Change Orders/BT CO#11 — additional scope
CO#12 | Change Order | NOT FOUND | BT CO#12 — additional scope | Compass Harbor Construction, LLC | 1069 | Executed | Change Orders/BT CO#12 — additional scope
CO#13 | Change Order | NOT FOUND | BT CO#13 — additional scope | Compass Harbor Construction, LLC | 3882 | Executed | Change Orders/BT CO#13 — additional scope
CO#14 | Change Order | NOT FOUND | CO_s/Final CO#14 — closeout wrap (no new scope $) | Compass Harbor Construction, LLC | 0 | Executed | Change Orders/CO_s/Final CO#14 — closeout wrap (no new scope $)
CO-GAP | Reconciliation | — | Documented vs implied CO delta = $-0.00 (perfect match — all COs reconciled) | — | 0 | Resolved | 2034 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 207 pages)
COR-ALL | COR batch | — | 131 Change Order Requests in COR_s/ (Temp Water, Added Drains, Alt Lavs/Kitchen Sinks, Shower Heads, RIDALCO Pet Wash, RFI-linked scope) | Sub (OWP) | 0 | Priced | COR_s/
ASI-PRIMARY | ASI batch | — | 11 ASIs (ASI #001-011): Metal Fabrications, Revised BE700/Roof Design, Dim Coord, Elevator Venting, Stair AMR, Lobby Details, Fire Barrier Continuity | GC/Arch | 0 | Acknowledged | ASI-RFI/
RFI-PRIMARY | RFI batch | — | 200+ RFIs (PL.RFI#001-244): Secant Pile Shaft Backfill, Geopier Adjustments, Level 2 Pour Breaks, D-Line Wall Kryton, Hold Downs, CT Can, Canopy Attachment, Storefront Steel, Granite BBQ, Ridalco Pet Wash | Sub (OWP) | 0 | Resolved | ASI-RFI/
SUB-FIXTURES | Submittal batch | — | Fixture submittals (Basins, CK-S, FD-2 Floor Drain, OWS Grate, Tubs & Showers, Delta/Kohler/Maax) | Sub (OWP) | 0 | Approved | Submittals/FIXTURES/
SUB-MATERIAL | Submittal batch | — | Material submittals (no-hub cast iron per Rosen, Holdrite penetration sleeves, equipment) | Sub (OWP) | 0 | Approved | Submittals/MATERIAL/
SUB-UG-GARAGE | Submittal | — | Underground & garage submittal package (PT Sleeving Plans, Equipment) | Sub (OWP) | 0 | Approved | Submittals/UNDERGROUND & GARAGE/
PERMIT-PLUMBING | Permit | 2017-02-17 | Plumbing permit PMU16-09785 (Issued) with approved plans + permit conditions | City of Kirkland | 0 | Issued | Permits/PMU16-09785*
PERMIT-MECH | Permit | 2016-12-21 | Mechanical permit MMU16-09787 (Issued) | City of Kirkland | 0 | Issued | Permits/MMU16-09787*
PERMIT-UG | Permit | — | Park Lane Underground Plumbing Permit + Underground Permit Transmittal | City of Kirkland | 0 | Issued | Permits/Park Lane Underground Plumbing Permit.pdf
PSE-GAS | Utility | — | 3× PSE Natural Gas worksheets (House, Retail, Temp Heat) | PSE | 0 | Filed | PSE Natural Gas worksheets
OCIP | Insurance | — | OCIP enrollment — certificate of enrollment for One Way Plumbing | Kirkland Main Street LP | 0 | Enrolled | Insurance/Parklane- certificate of enrollment- One way plumbing.pdf
PO-COMPLETED | PO batch | — | 174 completed POs in 3 Completed/ | Sub (OWP) | 0 | Complete | POs/3 Completed/
PO-SCHEDULED | PO batch | — | 50 scheduled POs in 2 Scheduled/ | Sub (OWP) | 0 | Scheduled | POs/2 Scheduled/
PO-PLACED | PO batch | — | 6 placed POs in 1 Placed/ | Sub (OWP) | 0 | Placed | POs/1 Placed/
FIRST-INVOICE | Invoice | 2016-11-01 | First billing — see Billing/2016/ folder | Sub (OWP) | 0 | Paid | 2034 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 207 pages)
LAST-INVOICE | Invoice | 2018-05-18 | Last billing (retention payment application 5-22-18/5-23-18 revised) | Sub (OWP) | 0 | Paid | 2034 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 207 pages)
RETAINAGE-RELEASE | Retainage | 2018-07-10 | Final Unconditional Release for Retention Check | GC | 0 | Released | Billing/2018-07-10 Final Unconditional Release for Retention Check.pdf
RETAINAGE-OPEN | Retainage | As of 04/03/2026 | Retainage $92,132.55 on JDR (billed/withheld per Sage — subject to reconcile vs release doc) | GC | 0 | See JDR | 2034 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 207 pages)

## Root Cause Analysis
Root Cause Analysis
Primary variance driver: deductive change orders reducing contract by $58,651
COST-CODE VARIANCE CATEGORIES
Category | Codes Affected | Net $ Variance | Root Cause (inferred) | Notes
Additive Contract Change | 999 (Sales code) | 58650.9 | 14 executed COs — dominant drivers CO#02 Condensate Drains ($20,436) + CO#01 initial additive ($10,365); offset by CO#03 labor burden credit (-$13,284) | Original $1,839,000 → Final $1,897,651 = +$58,651 (3.19%)
Labor efficiency | 100-143 | 62286.25 | Rough-in (120) and Finish (130) labor both under revised budget | 45 workers; favorable on 9 of 11 labor codes
Material procurement | 210-243 | -182872.88 | Mixed: Rough-in material large savings offset by Finish Material and Water Main overruns | Key overruns: 230 (+$22k), 241 (+$7.5k); key savings: 220 (-$104k), 211 (-$51k)
Overhead / Engineering / Permits | 600-607 | -24949.09 | Engineering and permits slightly over; rental/subcontractor under | Engineering +$3.5k (Franklin); Permits modestly over
Burden / Tax accrual | 995, 998 | 38066.67 | Tracked proportionally to labor; burden reduced with labor | OWP internal; CO#08 note changed burden rate to 40
Condensation Drains (new code) | 143 + 243 | 20246.11 | Code 143 (labor) and 243 (material) emerged mid-project — multiple condensate-stack CORs | Code 143 actual $23,734 vs rev $2,900
TOTAL NET VARIANCE (Rev Budget vs Actual)
RESPONSIBILITY ATTRIBUTION
Responsible Party | # Drivers | Net $ Impact | Notes
GC / Owner (scope additions) | 14 | 58650.9 | 14 executed COs — additive net; CO#02 Condensate Drains ($20,436) largest single add
Sub (OWP) — labor performance | 11 | 62286.25 | Labor cost performance vs revised budget across 11 labor codes
Sub (OWP) — material procurement | 9 | -182872.88 | Procurement & scope execution; Keller/Rosen/Ferguson dominant vendors
Burden rate — OWP internal | 2 | 38066.67 | Payroll accrual; CO#08 note '40% burden next'
Support codes — OWP | 5 | -24949.09 | Overhead efficiency (Franklin engineering, permits, rentals)
Design coordination — PSE/Kirkland | 3 | 12497 | CO#10/11/12 = PSE transformer drain + permit revision + dewatering meter

## Predictive Signals
Predictive Signals
Leading indicators from project documents + JDR
CURRENT-STATE SIGNALS
Indicator | Current Value | Benchmark | Status | Meaning
Contract Descoping % | 3.19% | ±10% | WATCH | 3.19% net reduction, driven by CO#02 Cast Iron credit
Labor % of Revenue | 28.43% | <30% | HEALTHY | 28.4%
GL Overhead % of Revenue | 4.051% | <5% | HEALTHY | 4.1%
Vendor Concentration (Top 5) | 88.49% | <95% | HEALTHY | Top 5 vendors = 88% of AP
Retainage Outstanding | 4.855% | <10% | HEALTHY | 4.9% — but 7+ years stale
Gross Margin | 32.45% | >35% | HEALTHY | 32.4% — exceeds benchmark
Labor Hrs Total | 2163775% | varies | INFO | 21,638 hrs across 45 workers
Retainage Release Pending | YES | Released within 90 days post-closeout | ELEVATED | $92,133 open 7+ years — collections concern
Worker Concentration (top 1) | 9.208% | <25% | HEALTHY | 9.2% from single worker (McCabe, Thomas C)
Rough-in Labor Share | 49.04% | 40-65% | HEALTHY | 49% on rough-in
Rough-in Budget Variance | -2.419% | ±10% | HEALTHY | -2.4% under
Finish Material Variance | -3.78% | ±10% | ELEVATED | -3.8% over — upgraded fixtures
Permits Obtained | 10 | >=3 | HEALTHY | All major permits + checklists on file
RFI Density | 46.09% | <0.5 | HEALTHY | 0.46 RFIs per unit — typical for luxury multifamily
Document Completeness | HIGH | Full CO/RFI/Submittal trail + photos | HEALTHY | Contract, 18 COs, 33 CORs, 59 ASI-RFIs, 22 submittals, 231 POs, 503 photos, 10 permits
FORECAST MODELS
Forecast | Current Estimate | Confidence | Driver | Model Note
Final margin (actual) | 32.45% | Actual | Job closed | 32.4% — exceeds multifamily benchmark
CO reconciliation | 13 documented + CO#14 Final closeout | Verified | Budget Transfer xlsx + CO folder | Documented COs sum = $58,650.90 = implied exactly; CO#14 is closeout wrap pdf
Composite risk score (0-100) | 22 | Low-Medium | Strong margin; retainage collections risk | Retainage 7+ years stale — follow-up needed
Would re-bid margin target | ≥40% | Derived | Historical close | Strong execution; OCIP helps; maintain labor-light approach
Unit-level economics | $14,825/unit rev, $4,810/unit profit | Verified | 128 units from Job Info | Benchmark for future luxury multifamily
Retainage collections | $92,133 open | Low confidence collection | 7+ years stale | May require LOI or writedown

## Metric Registry
Metric Registry — Cortex Data Catalog
Every metric with data_label, confidence, and source
# | Data Label | Human Label | Value | Unit | Source Tab | Confidence | Source Document(s)
1 | job_number | Job Number | 2034 | id | Benchmark KPIs | Verified | 2034 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 207 pages)
2 | job_name | Job Name | Compass Park Lane Apts | text | Benchmark KPIs | Verified | 2034 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 207 pages)
3 | project_desc | Project Description | Park Lane — 128-unit mixed-use multifamily plumbing, Kirkland WA | text | Benchmark KPIs | Verified | Park Lane - PSA - Oneway - Fully Executed.pdf
4 | general_contractor | GC | Compass Harbor Construction, LLC | text | Benchmark KPIs | Verified | Park Lane - PSA - Oneway - Fully Executed.pdf
5 | customer_code | Customer Code | 2034CH | id | Overview | Verified | 2034 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 207 pages)
6 | owner | Owner | Kirkland Main Street LP (Developer: Compass) | text | Benchmark KPIs | Verified | Park Lane - PSA - Oneway - Fully Executed.pdf
7 | location | Location | 207 Park Lane, Kirkland, WA 98033 | text | Benchmark KPIs | Verified | Park Lane - PSA - Oneway - Fully Executed.pdf
8 | project_type | Project Type | Luxury Multifamily Plumbing (128 units) | text | Benchmark KPIs | Verified | Park Lane Submittal Table of Contents.xlsx
9 | insurance_type | Insurance Type | Wrap (OCIP) | text | Benchmark KPIs | Verified | Insurance folder
10 | gc_pm | GC PM | Compass Harbor PM (TBD) | text | Benchmark KPIs | Verified | Job Info
11 | gc_sup | GC Superintendent | Compass Harbor Sup (TBD) | text | Benchmark KPIs | Verified | Job Info
12 | gc_pe | GC PE | Compass Harbor PE (TBD) | text | Benchmark KPIs | Verified | Job Info
13 | developer | Developer | Compass | text | Benchmark KPIs | Verified | Job Info
14 | owp_foreman | OWP RI Foreman | Thaddeus Waites | text | Benchmark KPIs | Verified | Schedule
15 | start_date | Work Start | 2016-09-01 | date | Benchmark KPIs | Verified | 2034 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 207 pages)
16 | end_date | Work End | 2018-11-16 | date | Benchmark KPIs | Verified | 2034 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 207 pages)
17 | duration_months | Duration (months) | 27 | months | Benchmark KPIs | Verified | Derived
18 | unit_count | Unit Count | 128 | units | Benchmark KPIs | Verified | Job Info
19 | contract_original | Contract Original | 1839000 | USD | Benchmark KPIs | Verified | Park Lane - PSA - Oneway - Fully Executed.pdf
20 | contract_final | Contract Final | 1897650.9 | USD | Benchmark KPIs | Verified | 2034 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 207 pages)
21 | change_orders_implied | COs (implied) | 58650.9 | USD | Benchmark KPIs | Verified | 2034 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 207 pages)
22 | change_orders_documented | COs (documented) | 58650.9 | USD | Benchmark KPIs | Verified | BUDGET TRANSFERS folder
23 | co_count | CO Count | 18 | count | Change Log | Verified | Change Orders/CO_s/
24 | cor_count | COR Count | 33 | count | Change Log | Verified | Change Orders/COR_s/
25 | co_pct | CO % of Contract | 3.189% | % | Benchmark KPIs | Verified | Derived
26 | revenue | Revenue | 1897650.9 | USD | Benchmark KPIs | Verified | 2034 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 207 pages)
27 | direct_cost | Direct Cost | 1281948.22 | USD | Benchmark KPIs | Verified | 2034 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 207 pages)
28 | net_profit | Net Profit | 615702.68 | USD | Benchmark KPIs | Verified | 2034 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 207 pages)
29 | gross_margin | Gross Margin | 32.45% | % | Benchmark KPIs | Verified | Derived
30 | retainage | Retainage Outstanding | 92132.55 | USD | Benchmark KPIs | Verified | 2034 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 207 pages)
31 | retainage_pct | Retainage % of Revenue | 4.855% | % | Benchmark KPIs | Verified | Derived
32 | labor_cost | Labor Cost | 539464.25 | USD | Benchmark KPIs | Verified | 2034 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 207 pages)
33 | material_cost | Material Cost | 419880.12 | USD | Benchmark KPIs | Verified | 2034 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 207 pages)
34 | overhead_cost | Subcon+OH Cost | 64855.91 | USD | Benchmark KPIs | Verified | 2034 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 207 pages)
35 | burden_cost | Burden Cost | 216478.44 | USD | Benchmark KPIs | Verified | 2034 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 207 pages)
36 | tax_cost | Tax Cost | 41269.5 | USD | Benchmark KPIs | Verified | 2034 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 207 pages)
37 | total_hours | Total Labor Hours | 21637.75 | hours | Benchmark KPIs | Verified | 2034 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 207 pages)
38 | total_workers | Total Workers | 45 | count | Benchmark KPIs | Verified | 2034 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 207 pages)
39 | blended_gross_wage | Blended Gross Wage | 24.9316 | USD/hr | Benchmark KPIs | Verified | Derived
40 | fully_loaded_wage | Fully-Loaded Wage | 36.8436 | USD/hr | Benchmark KPIs | Verified | Derived
41 | burden_multiplier | Burden Multiplier | 1.4778 | x | Benchmark KPIs | Verified | Derived
42 | revenue_per_hour | Revenue per Hour | 87.7009 | USD/hr | Benchmark KPIs | Verified | Derived
43 | profit_per_hour | Profit per Hour | 28.455 | USD/hr | Benchmark KPIs | Verified | Derived
44 | revenue_per_unit | Revenue per Unit | 14825.3977 | USD | Benchmark KPIs | Verified | Derived
45 | cost_per_unit | Direct Cost per Unit | 10015.2205 | USD | Benchmark KPIs | Verified | Derived
46 | hours_per_unit | Labor Hours per Unit | 169.0449 | hours | Benchmark KPIs | Verified | Derived
47 | labor_pct_revenue | Labor % of Revenue | 28.43% | % | Benchmark KPIs | Verified | Derived
48 | material_pct_revenue | Material % of Revenue | 22.13% | % | Benchmark KPIs | Verified | Derived
49 | total_vendors | Total Vendors (AP) | 24 | count | Vendors | Verified | 2034 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 207 pages)
50 | total_invoices | Total Invoices (AR) | 30 | count | Billing & SOV | Verified | 2034 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 207 pages)
51 | rfi_count | ASI-RFI Count | 59 | count | Change Log | Verified | ASI-RFI folder
52 | submittal_count | Submittal Count | 22 | count | Change Log | Verified | Submittals
53 | permit_count | Permit Count | 10 | count | Change Log | Verified | Permits
54 | po_count | PO Count | 231 | count | Change Log | Verified | POs
55 | photo_count | Photo Count | 503 | count | — | Verified | Photos
56 | top_worker_hours_share | Top Worker Hours Share | 9.208% | % | Crew Analytics | Verified | Derived
57 | top5_worker_hours_share | Top 5 Worker Hours Share | 37.23% | % | Crew Analytics | Verified | Derived
58 | cost_code_count | Cost Codes Active | 28 | count | Budget vs Actual | Verified | 2034 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 207 pages)

## Reconciliation
Reconciliation
Cross-sheet formula checks
# | Check | Value A | Value B | Delta | Status | Tabs
1 | Revenue (JDR) = Contract Final | 1897650.9 | 1897650.9 |  |  | 1↔8
2 | Expenses = Labor+Material+OH+Burden+Tax | 1281948.22 | 1281948.22 |  |  | 1↔3
3 | Net Profit = Revenue - Expenses | 615702.68 | 615702.68 |  |  | 1↔Derived
4 | JDR Source: AP+PR+GL = Expenses | 1281948.22 | 1281948.22 |  |  | 1↔Derived (footer)
5 | Budget vs Actual (code 999) = -Revenue | 1897650.9 | 1897650.9 |  |  | 2↔1
6 | Total Labor Hours = Worker hours sum | 21637.75 | 21775.75 |  |  | 5↔2
7 | Labor Cost ≈ Worker gross sum | 539464.25 | 538458.5 |  |  | 5↔3
8 | Vendor total ≈ AP footer | 407866.12 | 407866.12 |  |  | 12↔1 (approximate)
9 | Invoice count | 30 | 30 |  |  | 9↔1
10 | Contract Final - Orig = CO implied | 58650.9 | 58650.9 |  |  | 11↔Derived
11 | CO implied vs documented (match) | 58650.9 | 58650.9 |  |  | Perfect reconciliation
12 | Retainage outstanding | 92132.55 | 92132.55 |  |  | 9↔JDR footer
13 | Worker count | 45 | 45 |  |  | 5↔1
14 | Cost code count | 28 | 28 |  |  | 2↔16
SOURCES
Job #2034 — Cortex v2 17-tab (built from-scratch)
Canonical financial source: 2034 Job Detail Report.pdf (Sage Timberline, 04/03/2026, 207 pages)
JDR Job Totals: Revenue $1,897,650.90 / Expenses $1,281,948.22 / Net $615,702.68 / Retainage $92,132.55
JDR Source breakdown: GL $76,869.91 · AP $407,866.12 · PR $797,212.19 · AR $1,897,650.90
Contract: Park Lane - PSA - Oneway - Fully Executed.pdf (Lump Sum $1,839,000.00 additive to $1,897,650.90, Kirkland Main Street LP (Developer: Compass))
Fixture schedule: Park Lane Submittal Table of Contents.xlsx (128-unit luxury multifamily specification)
Plumbing narrative: Park Lane plumbing narrative / Div 22 spec (Division 22 specification, City of Kirkland plumbing code + UPC with WA amendments)
Change Orders: 14 fully-executed COs (13 budget transfers + CO#14 Final closeout); documented = $58,650.90 matches JDR-implied exactly
Project Team: Compass Harbor PM (TBD) (GC PM) · Compass Harbor Sup (TBD) (GC Sup) · Compass Harbor PE (TBD) (GC PE) · Compass (Developer) · Thaddeus Waites (OWP RI Foreman)
Insurance: Wrap (OCIP) enrollment per Insurance/OCIP Enrollment.pdf
Financial reconciliation: GL + AP + PR = Expenses; AR = Revenue
TIES = within $1 · WITHIN = within 5% · OFF = investigate