## Overview
Job #2035 · 162 Ten Apartments
Cortex JCR v2 • Natural & Built LLC (customer 2035NB) • 16210 NE 80th St, Redmond, WA 98052 • Owner: 162 Ten Apartments LLC (Natural & Built)
PROJECT OVERVIEW
Project Job # | 2035 |  | 2035 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
Project Name (Sage) | 162 Ten Apartments |  | 2035 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
Project Description | 162 Ten — 92-unit multifamily plumbing, Redmond WA |  | OWP Project List with Schedule - UPDATED 04-01-26.xlsx + contract
General Contractor | Natural & Built LLC |  | OWP Project List with Schedule - UPDATED 04-01-26.xlsx
Customer Code (Sage) | 2035NB |  | 2035 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
Owner / Developer | 162 Ten Apartments LLC (Natural & Built) |  | OWP Project List with Schedule - UPDATED 04-01-26.xlsx
GC PM | Tyson Cornett |  | OWP Project List with Schedule - UPDATED 04-01-26.xlsx
GC Superintendent | Tyson Cornett |  | OWP Project List with Schedule - UPDATED 04-01-26.xlsx
GC PE | TBD |  | OWP Project List with Schedule - UPDATED 04-01-26.xlsx
OWP Rough-in Foreman | Reuben |  | Schedule tab
Jobsite Location | 16210 NE 80th St, Redmond, WA 98052 |  | OWP Project List with Schedule - UPDATED 04-01-26.xlsx
Insurance | Not Wrap |  | OWP Project List with Schedule - UPDATED 04-01-26.xlsx
Fixture Schedule | 92-unit multifamily new construction |  | Project scope
Contract Type | Lump Sum |  | 2035-Natural & Built LLC subcontract + Job Info sheet
Unit Count | 92 |  | OWP Project List with Schedule - UPDATED 04-01-26.xlsx
Work Period | 2016-08-16 start → 2018 (24 months) |  | JDR PR/AR dates
CONTRACT VALUE |  | NET PROFIT | DIRECT COST | LABOR HOURS
722290 |  | 358523.29 | 363766.71 | 5204.75
Original $717,400.00 + ($4,890.00) COs (0.68%) |  | 49.6% margin | 50.4% of revenue | 24 workers
SCOPE OF WORK
Full plumbing installation per Division 22: underground, garage, rough-in, finish, gas, water main, insulation.
92-unit multifamily new construction at 16210 NE 80th St, Redmond, WA 98052.
GC: Natural & Built LLC (2035NB); Owner/Developer: 162 Ten Apartments LLC (Natural & Built).
Insurance: Not Wrap.
Project team: Tyson Cornett (GC PM) · Tyson Cornett (GC Sup) · TBD (GC PE) · Reuben (OWP RI).
SOURCES
Canonical financial source: 2035 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
Job totals (JDR footer): Revenue $722,290.00 / Expenses $363,766.71 / Net $358,523.29 / Retainage $36,114.51
Source breakdown (derived): PR $132,990.50 · AP $135,428.20 · GL+other $95,348.01
Contract: Lump Sum $717,400.00 → $722,290.00
Change Orders (JDR-implied): $4,890.00 net
Project Team: Tyson Cornett · Tyson Cornett · TBD · Natural & Built · Reuben
PROJECT TEAM (OWP Job Info)
Role | Status | Name / Firm
GC | Extracted | Natural & Built LLC
GC PM | Extracted | Tyson Cornett
GC Superintendent | Extracted | Tyson Cornett
GC PE | N/A | N/A
Developer | Extracted | Natural & Built
Owner | Extracted | 162 Ten Apartments LLC
Architect | N/A | N/A
Structural | N/A | N/A
Acoustical | N/A | N/A
ADA Consultant | N/A | N/A
Interior Design | N/A | N/A
MEP Engineer | N/A | N/A
Insurance | Extracted | Not Wrap
OWP RI Foreman | Extracted | Reuben

## Budget vs Actual
Budget vs Actual
All 22 cost codes from JDR. Contract $717,400 → $722,290.
Cost Code | Description | Original Budget | Revised Budget | Actual | Variance | % of Revised | Hours | Source
100 | Supervision | 9200 | 9200 | 4434 |  |  | 95 | 2035 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
101 | Takeoff & Purchase Labor | 9200 | 9450 | 9333 |  |  | 197.5 | 2035 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
110 | Underground Labor | 12690 | 12690 | 5630.5 |  |  | 174.5 | 2035 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
111 | Garage Labor | 16050 | 16050 | 15337 |  |  | 521.75 | 2035 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
112 | Canout Labor | 5120 | 5120 | 4060 |  |  | 125 | 2035 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
120 | Roughin Labor | 83320 | 83320 | 65658 |  |  | 2891 | 2035 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
130 | Finish Labor | 19110 | 19284 | 15449 |  |  | 590 | 2035 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
141 | Water Main/Insulation Lab | 25000 | 25960 | 12963 |  |  | 596 | 2035 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
142 | Mech Room Labor | 4200 | 4200 | 588 |  |  | 14 | 2035 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
210 | Underground Material | 12700 | 12700 | 8289.11 |  |  |  | 2035 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
211 | Garage Material | 20700 | 20700 | 7036.09 |  |  |  | 2035 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
212 | Canout Material | 4800 | 4800 | 5117.23 |  |  |  | 2035 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
220 | Roughin Material | 35575 | 35575 | 17359.05 |  |  |  | 2035 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
230 | Finish Material | 96100 | 94265 | 96906.5 |  |  |  | 2035 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
241 | Water Main/Insulation Mat | 36000 | 36300 | 17346.53 |  |  |  | 2035 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
242 | Mech Room Material | 6000 | 6000 | 7233.3 |  |  |  | 2035 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
243 | Condensation Drains Mat | 0 | 0 | 121.8 |  |  |  | 2035 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
600 | Subcontractor | 1000 | 2200 | 1400 |  |  |  | 2035 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
603 | Permits & Licenses | 0 | 0 | 109 |  |  |  | 2035 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
995 | Payroll Burden | 81302.42 | 81925.22 | 59186.15 |  |  |  | 2035 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
998 | Payroll Taxes | 14023.98 | 14129.86 | 10209.45 |  |  |  | 2035 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
999 | Sales | -717400 | -722290 | -722290 |  |  |  | 2035 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
TOTAL

## Cost Breakdown
Cost Breakdown by Category
Direct cost composition by category from JDR cost codes
Category | Cost Codes | Actual $ | % of Direct Cost | % of Revenue | Source
Labor | 100,101,110,111,112,120,130,141,142 | 133452.5 |  |  | 2035 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
Material | 210,211,212,220,230,241,242,243 | 159409.61 |  |  | 2035 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
Subcon+Engineering+Permits+Other | 600,603 | 1509 |  |  | 2035 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
Payroll Burden | 995 | 59186.15 |  |  | 2035 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
Payroll Taxes | 998 | 10209.45 |  |  | 2035 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
TOTAL DIRECT COST |  |  | 100%

## Material
Material Purchases — AP Vendors
Material + subcontractor spend by vendor from JDR AP records
Vendor ID | Vendor Name | Total Spend | # Transactions | Category (inferred) | Source
2035CS | Consolidated Supply Co. $162Ten | 63855.41 | 22 | Plumbing / Supplies | 2035 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
2035RS | Rosen Supply Company, Inc. $162Ten | 54966.5 | 52 | Plumbing / Supplies | 2035 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
2035KS | Keller Supply Co. $162 Ten | 5440.66 | 8 | Plumbing / Supplies | 2035 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
7423OC | Old Castle Infrastructure, Inc. | 3511 | 1 | Uncategorized | 2035 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
2031CS | Consolidated Supply Co. $Iss Gateway | 1855.54 | 1 | Plumbing / Supplies | 2035 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
5919PW | Patchworks, Inc. | 1200 | 1 | Uncategorized | 2035 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
1130CS | Consolidated Supply Co. | 1139.94 | 4 | Plumbing / Supplies | 2035 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
5585CH | Columbia Hydronics | 765 | 1 | Uncategorized | 2035 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
1609QC | Quality Concrete Products, Inc. $32 | 660 | 2 | Uncategorized | 2035 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
5621HD | Core & Main LP $HD Supply Waterworks | 570 | 1 | Plumbing / Supplies | 2035 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
1380RS | Rosen Supply Kirkland | 478.37 | 5 | Plumbing / Supplies | 2035 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
1175FE | Ferguson Enterprises, Inc. #3007 | 371.02 | 3 | Plumbing / Supplies | 2035 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
2132MH | Manor Hardware & Construction Supply | 305.76 | 1 | Plumbing / Supplies | 2035 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
1421RA | R.A. Brown Backflow Testing | 200 | 2 | Testing subcontractor | 2035 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
1234BA | Bank of America CC | 109 | 1 | Uncategorized | 2035 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
2034RS | Rosen Supply Company, Inc. $Park Lane | 0 | 2 | Plumbing / Supplies | 2035 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
TOTAL

## Crew & Labor
Crew & Labor — Worker Roster
All 24 unique payroll workers. OWP RI: Reuben.
Worker ID | Worker Name | Total Hours | Gross Pay | Blended Wage ($/hr) | # Work Days | Source
RE18 | Reed, Reuben H | 1092 | 39409.5 |  | 44 | 2035 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
GA70 | Garcia, Jordan X | 1070.5 | 26737.5 |  | 32 | 2035 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
RA55 | Ramos Herrera, Franklin J | 572 | 8884 |  | 18 | 2035 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
JI50 | Jimenez Alvarenga, Gerson M | 556 | 8636 |  | 17 | 2035 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
BE45 | Belcher, Jacob T | 384 | 5760 |  | 10 | 2035 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
ME52 | Mendoza, Edgar E | 257.5 | 4213 |  | 8 | 2035 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
CO69 | Cornejo Orellana, Carlos E | 253.5 | 3890.5 |  | 8 | 2035 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
GE69 | Gerard, Jeffrey S | 231.5 | 10760.5 |  | 59 | 2035 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
GE70 | Gerard, Jordan E | 149 | 4023 |  | 5 | 2035 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
SA54 | Sanders, Allen O | 131.5 | 5523 |  | 17 | 2035 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
GO51 | Gomez Reyes, Edith N | 112 | 2016 |  | 11 | 2035 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
HU06 | Hubbard, Robert W | 101.5 | 4185 |  | 29 | 2035 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
SA51 | Sanchez, Derli | 89.5 | 1611 |  | 7 | 2035 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
DO56 | Donelson, Richard T | 61 | 3006.5 |  | 30 | 2035 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
EL33 | Eliassen, Cory H | 40 | 840 |  | 2 | 2035 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
TA96 | Taylor, Evan R | 40 | 880 |  | 1 | 2035 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
CR79 | Cruz Guzman, Joel A | 32 | 608 |  | 2 | 2035 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
LU09 | Lucas Tzintzun, Rafael | 24 | 384 |  | 2 | 2035 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
CR87 | Cruz Reyes, Jose | 24 | 480 |  | 2 | 2035 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
HO18 | Hoeg, Xavier A | 19 | 285 |  | 2 | 2035 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
HU04 | Hubbard, Dustin R | 14 | 274 |  | 8 | 2035 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
EI74 | Eisenhauer, Tommy J | 12 | 252 |  | 2 | 2035 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
GE71 | Gerard, Mitchell J | 8 | 256 |  | 1 | 2035 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
HO90 | Howey, Shawn M | 4 | 76 |  | 1 | 2035 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
TOTAL

## Crew Analytics
Crew Analytics
Team-level labor productivity, concentration, wage dispersion
TEAM-LEVEL METRICS
Metric | Value | Notes | Source
Total Workers | 24 | Unique payroll IDs | 2035 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
Total Labor Hours | 5204.75 | Sum of labor codes | 2035 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
Total Gross Pay | 133452.5 | Sum of labor codes | 2035 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
Blended Gross Wage ($/hr) | 25.6405 | Labor$/Hrs (pre-burden) | Derived
Top Worker Hours Share | 20.98% | RE18 Reed, Reuben H (1092 hrs) | Derived
Top 5 Workers Hours Share | 70.6% | Concentration metric | Derived
Highest Wage Rate ($/hr) | 49.2869 | Single-worker blended | Derived
Lowest Wage Rate ($/hr) | 15 | Single-worker blended | Derived
Avg Hours per Worker | 216.8646 | Includes short-tenure workers | Derived
Avg Project Days per Worker | 13.25 | Mean days | Derived

## Productivity
Productivity Metrics
Normalized ratios. Per-unit from 92 units.
Metric | Value | Basis | Source / Note
Revenue per Labor Hour | 138.7752 | USD/hr
Profit per Labor Hour | 68.8839 | USD/hr
Labor Cost per Hour (blended) | 25.6405 | USD/hr | Pre-burden
Fully-Loaded Labor Rate ($/hr) | 38.9736 | USD/hr | Incl burden+taxes
Burden Multiplier | 1.52 | x | Fully-loaded/blended
Rough-in Hours (code 120) | 2891 | hrs
Finish Hours (code 130) | 590 | hrs
Rough-in % of Total Hours | 55.55% | %
Gross Margin | 49.64% | %
Labor % of Revenue | 18.48% | %
Material % of Revenue | 22.07% | %
Direct Cost Ratio | 50.36% | % | All exp/Rev
Revenue per Unit (92) | 7850.9783 | USD | 92 units
Labor Hours per Unit | 56.5734 | hrs
Labor Cost per Unit | 1450.5707 | USD
Material Cost per Unit | 1732.7132 | USD
Direct Cost per Unit | 3953.986 | USD
Rough-in Hours per Unit | 31.4239 | hrs

## PO Commitments
PO Commitments
Inbound contract (GC → OWP). Outbound vendor commitments — see Material tab.
PO # | Date | Issuer | Type | Status | Description | Amount | Source
PRIME | 2016-08-16 | Natural & Built LLC | Lump Sum Subcontract | Closed | 162 Ten Apartments plumbing (92 units) — per Div 22 | 717400 | 2035-Natural & Built LLC subcontract + Job Info sheet
CO-NET | — | Natural & Built LLC | Change Orders (net, JDR-implied) | Executed | Net CO impact (Sage 999 rev - orig) | 4890 | 2035 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
TOTAL (contract + COs)

## Billing & SOV
Billing & Schedule of Values
18 invoices to Natural & Built LLC. Retainage $36,114.51.
Invoice # | Date | Total Billed (signed) | Retainage (signed) | # Lines | Source
036806 | 12/02/16 | -36800 | -1840 | 1 | 2035 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
036835 | 02/20/17 | -18400 | -920 | 1 | 2035 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
036849 | 03/17/17 | -7290 | -364.5 | 1 | 2035 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
036862 | 04/20/17 | -39410 | -1970.5 | 2 | 2035 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
036872 | 04/20/17 | 39410 | 1970.5 | 2 | 2035 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
036873 | 04/20/17 | -39126 | -1956.3 | 2 | 2035 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
036882 | 05/19/17 | -177657 | -8882.85 | 9 | 2035 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
036890 | 06/01/17 | 177657 | 8882.85 | 9 | 2035 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
036891 | 06/01/17 | -177657.5 | -8882.88 | 9 | 2035 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
036898 | 06/19/17 | -231966.5 | -11598.33 | 13 | 2035 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
036922 | 07/20/17 | -91750 | -4587.5 | 1 | 2035 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
036926 | 08/18/17 | -31210 | -1560.5 | 1 | 2035 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
036984 | 11/17/17 | -22450 | -1122.5 | 1 | 2035 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
036996 | 12/15/17 | -23145 | -1157.25 | 1 | 2035 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
037007 | 01/19/18 | -38539 | -1926.95 | 5 | 2035 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
037014 | 01/19/18 | 38539 | 1926.95 | 5 | 2035 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
037015 | 01/19/18 | -41115 | -2055.75 | 7 | 2035 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
037059 | 04/20/18 | -1380 | -69 | 1 | 2035 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
TOTAL (signed)

## Insights
Insights & Observations
Narrative findings from JDR
# | Insight | Detail | Confidence | Source
1 | MARGIN PROFILE | Net profit $358,523.29 on $722,290.00 revenue = 49.6% gross margin. | Verified | 2035 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
2 | CONTRACT CHANGE | Original $717,400.00 → final $722,290.00 = $+4,890.00 net (+0.68%). | Verified | 2035 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
3 | LABOR PROFILE | Labor cost $133,452.50 (18.5% of rev) across 5,205 hrs and 24 workers. Blended wage $25.64/hr. | Verified | 2035 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
4 | VENDOR CONCENTRATION | Top 5 AP vendors: ~$129,629.11 (96% of AP). Top vendor: Consolidated Supply Co. $162Ten ($63,855.41). | Verified | 2035 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
5 | RETAINAGE | Retainage $36,114.51 = 5.0% of AR per JDR 04/03/2026 — legacy project, likely 7+ years stale. | Verified | 2035 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
6 | ROUGH-IN SHARE | Code 120 Roughin Labor = 2,891 hrs (56% of labor hours). | Verified | 2035 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
7 | TOP COST CODE | Largest actual cost: 230 Finish Material = $96,906.50 | Verified | 2035 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
8 | WORKER CONCENTRATION | Top worker Reed, Reuben H = 1092 hrs (21% of total). | Verified | 2035 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
9 | INSURANCE | Not Wrap — OCIP wrap. | Verified | OWP Project List with Schedule - UPDATED 04-01-26.xlsx
10 | SCOPE CONTEXT | 162 Ten — 92-unit multifamily plumbing, Redmond WA. | Verified | OWP Project List with Schedule - UPDATED 04-01-26.xlsx + JDR

## Benchmark KPIs
Benchmark KPIs
Normalized metrics for cross-project comparison
KPI | Data Name | Value | Category | Notes | Confidence | Source Document
Job Number | job_number | 2035 | Profile | OWP job ID | Verified | 2035 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
Job Name | job_name | 162 Ten Apartments | Profile |  | Verified | 2035 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
General Contractor | gc | Natural & Built LLC | Profile |  | Verified | OWP Project List with Schedule - UPDATED 04-01-26.xlsx
Owner | owner | 162 Ten Apartments LLC (Natural & Built) | Profile |  | Verified | OWP Project List with Schedule - UPDATED 04-01-26.xlsx
Location | location | 16210 NE 80th St, Redmond, WA 98052 | Profile |  | Verified | OWP Project List with Schedule - UPDATED 04-01-26.xlsx
Project Type | project_type | Multifamily New Construction (92 units) | Profile |  | Verified | OWP Project List with Schedule - UPDATED 04-01-26.xlsx
Insurance Type | insurance | Not Wrap | Profile |  | Verified | OWP Project List with Schedule - UPDATED 04-01-26.xlsx
GC PM | gc_pm | Tyson Cornett | Profile |  | Verified | OWP Project List with Schedule - UPDATED 04-01-26.xlsx
GC Sup | gc_sup | Tyson Cornett | Profile |  | Verified | OWP Project List with Schedule - UPDATED 04-01-26.xlsx
GC PE | gc_pe | TBD | Profile |  | Verified | OWP Project List with Schedule - UPDATED 04-01-26.xlsx
Developer | developer | Natural & Built | Profile |  | Verified | OWP Project List with Schedule - UPDATED 04-01-26.xlsx
OWP RI Foreman | owp_foreman | Reuben | Profile |  | Verified | Schedule
Work Start | start_date | 2016-08-16 | Profile |  | Verified | 2035 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
Work End | end_date | 2018 | Profile |  | Verified | 2035 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
Duration (months) | duration_months | 24 | Profile |  | Verified | Derived
Unit Count | unit_count | 92 | Profile |  | Verified | OWP Project List with Schedule - UPDATED 04-01-26.xlsx
Contract Original | contract_original | 717400 | Financial |  | Verified | OWP Project List with Schedule - UPDATED 04-01-26.xlsx
Contract Final | contract_final | 722290 | Financial |  | Verified | OWP Project List with Schedule - UPDATED 04-01-26.xlsx
Change Orders ($, implied) | co_implied | 4890 | Financial | Final - Original | Verified | 2035 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
CO % of Contract | co_pct | 0.6816% | Financial |  | Verified | Derived
Revenue | revenue | 722290 | Financial | AR total | Verified | 2035 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
Direct Cost | direct_cost | 363766.71 | Financial | JDR Expenses | Verified | 2035 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
Net Profit | net_profit | 358523.29 | Financial | Rev - Exp | Verified | 2035 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
Gross Margin | gross_margin | 49.64% | Financial |  | Verified | Derived
Retainage | retainage | 36114.51 | Financial | JDR AR retainage | Verified | 2035 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
Retainage % of Revenue | retainage_pct | 5% | Financial |  | Verified | Derived
Labor Cost | labor_cost | 133452.5 | Labor | Codes 100-151 | Verified | 2035 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
Material Cost | material_cost | 159409.61 | Material | Codes 210-245 | Verified | 2035 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
Overhead Cost | overhead_cost | 1509 | Financial | Codes 600-607 | Verified | 2035 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
Burden Cost | burden_cost | 59186.15 | Labor | Code 995 | Verified | 2035 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
Tax Cost | tax_cost | 10209.45 | Labor | Code 998 | Verified | 2035 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
Total Labor Hours | total_hours | 5204.75 | Labor | Sum labor codes | Verified | 2035 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
Total Workers | total_workers | 24 | Labor | Unique PR IDs | Verified | 2035 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
Blended Gross Wage | blended_wage | 25.6405 | Labor |  | Verified | Derived
Fully-Loaded Wage | loaded_wage | 38.9736 | Labor |  | Verified | Derived
Burden Multiplier | burden_mult | 1.52 | Labor |  | Verified | Derived
Rough-in Hours | roughin_hours | 2891 | Labor | Code 120 | Verified | 2035 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
Finish Hours | finish_hours | 590 | Labor | Code 130 | Verified | 2035 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
Revenue per Hour | rev_per_hour | 138.7752 | Productivity |  | Verified | Derived
Profit per Hour | profit_per_hour | 68.8839 | Productivity |  | Verified | Derived
Revenue per Unit | rev_per_unit | 7850.9783 | Productivity |  | Verified | Derived
Direct Cost per Unit | cost_per_unit | 3953.986 | Productivity |  | Verified | Derived
Hours per Unit | hours_per_unit | 56.5734 | Productivity |  | Verified | Derived
Labor % of Revenue | labor_pct | 18.48% | Cost Mix |  | Verified | Derived
Material % of Revenue | material_pct | 22.07% | Cost Mix |  | Verified | Derived
Total Vendors | total_vendors | 16 | Material |  | Verified | 2035 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
Total Invoices | total_invoices | 18 | Billing |  | Verified | 2035 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
Cost Codes Active | cost_codes | 22 | Structure |  | Verified | 2035 Job Detail Report.pdf (Sage Timberline, 04/03/2026)

## Vendors
Vendors — AP Summary
Vendor-level spend ranking
Rank | Vendor ID | Vendor Name | Total Spend | # Transactions | % of AP | Source
1 | 2035CS | Consolidated Supply Co. $162Ten | 63855.41 | 22 |  | 2035 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
2 | 2035RS | Rosen Supply Company, Inc. $162Ten | 54966.5 | 52 |  | 2035 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
3 | 2035KS | Keller Supply Co. $162 Ten | 5440.66 | 8 |  | 2035 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
4 | 7423OC | Old Castle Infrastructure, Inc. | 3511 | 1 |  | 2035 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
5 | 2031CS | Consolidated Supply Co. $Iss Gateway | 1855.54 | 1 |  | 2035 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
6 | 5919PW | Patchworks, Inc. | 1200 | 1 |  | 2035 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
7 | 1130CS | Consolidated Supply Co. | 1139.94 | 4 |  | 2035 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
8 | 5585CH | Columbia Hydronics | 765 | 1 |  | 2035 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
9 | 1609QC | Quality Concrete Products, Inc. $32 | 660 | 2 |  | 2035 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
10 | 5621HD | Core & Main LP $HD Supply Waterworks | 570 | 1 |  | 2035 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
11 | 1380RS | Rosen Supply Kirkland | 478.37 | 5 |  | 2035 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
12 | 1175FE | Ferguson Enterprises, Inc. #3007 | 371.02 | 3 |  | 2035 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
13 | 2132MH | Manor Hardware & Construction Supply | 305.76 | 1 |  | 2035 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
14 | 1421RA | R.A. Brown Backflow Testing | 200 | 2 |  | 2035 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
15 | 1234BA | Bank of America CC | 109 | 1 |  | 2035 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
16 | 2034RS | Rosen Supply Company, Inc. $Park Lane | 0 | 2 |  | 2035 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
TOTAL

## Change Log
Change Log — Master Register
Contract, CO net, retainage events — JDR only
Event ID | Type | Date | Subject | Originator | Cost Impact ($) | Status | Source
CONTRACT-ORIG | Contract | 2016-08-16 | Prime subcontract — Lump Sum $717,400.00 | Natural & Built LLC | 717400 | Executed | 2035-Natural & Built LLC subcontract + Job Info sheet
CO-NET | Change Order (net) | — | Net JDR-implied COs $+4,890.00 | Natural & Built LLC | 4890 | Executed | 2035 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
FIRST-INVOICE | Invoice | 01/19/18 | First billing (per JDR) | Sub (OWP) | 0 | Paid | 2035 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
LAST-INVOICE | Invoice | 12/15/17 | Last billing (per JDR) | Sub (OWP) | 0 | Paid | 2035 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
RETAINAGE-OPEN | Retainage | As of 04/03/2026 | Retainage $36,114.51 open | GC | 0 | Outstanding | 2035 Job Detail Report.pdf (Sage Timberline, 04/03/2026)

## Root Cause Analysis
Root Cause Analysis
Primary variance drivers by category
Category | Codes | Net $ Variance | Root Cause (inferred) | Notes
Contract Change | 999 (Sales) | 4890 | JDR-implied net CO impact | $717,400 → $722,290
Labor | 100,101,110,111,112,120,130,141,142 | -51821.5 | Labor variance vs revised budget | 24 workers
Material | 210,211,212,220,230,241,242,243 | -50930.39 | Material procurement variance | 16 vendors
Overhead | 600,603 | -691 | Engineering/permits/subcon variance
Burden+Tax | 995+998 | -26659.48 | Payroll accrual tracking labor
TOTAL NET VARIANCE
RESPONSIBILITY ATTRIBUTION
Responsible Party | # Drivers | Net $ Impact | Notes
GC / Owner (scope changes) | 1 | 4890 | Aggregate JDR-implied COs
Sub (OWP) labor performance | 9 | -51821.5 | Hours + rate vs budget
Sub (OWP) material procurement | 8 | -50930.39 | 16 vendors
OWP burden accrual | 2 | -26659.48 | Payroll burden + tax
OWP overhead | 2 | -691 | Engineering/permits/subcon

## Predictive Signals
Predictive Signals
Leading indicators from JDR
CURRENT-STATE SIGNALS
Indicator | Current Value | Benchmark | Status | Meaning
Contract Change % | 0.68% | ±10% | HEALTHY | +0.68% net
Labor % of Revenue | 18.48% | <30% | HEALTHY | 18.5%
GL Overhead % of Revenue | 13.2% | <5% | HEALTHY | 13.2%
Vendor Concentration (Top 5) | 95.72% | <95% | HEALTHY | Top 5 = 96% of AP
Retainage % | 5% | <10% | HEALTHY | 5.0%
Gross Margin | 49.64% | >30% | HEALTHY | 49.6%
Labor Hrs Total | 520475% | varies | INFO | 5,205 hrs, 24 workers
Worker Concentration (top 1) | 20.98% | <25% | HEALTHY | 21.0% (Reed, Reuben H)
Rough-in Labor Share | 55.55% | 40-65% | HEALTHY | 56%
Retainage Legacy | STALE | <90 days post-closeout | ELEVATED | $36,115 outstanding
FORECAST MODELS
Forecast | Current Estimate | Confidence | Driver | Model Note
Final margin (actual) | 49.64% | Actual | Job closed | 49.6%
Retainage collection | $36,115 open | Low | Legacy project | May require LOI/writedown
Unit-level economics | $7,851/unit rev, $3,897/unit profit | Verified | 92 units | Multifamily New Construction benchmark

## Metric Registry
Metric Registry — Cortex Data Catalog
Every metric with data_label, confidence, and source
# | Data Label | Human Label | Value | Unit | Source Tab | Confidence | Source Document(s)
1 | job_number | Job Number | 2035 | id | Benchmark KPIs | Verified | 2035 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
2 | job_name | Job Name | 162 Ten Apartments | text | Benchmark KPIs | Verified | 2035 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
3 | general_contractor | GC | Natural & Built LLC | text | Benchmark KPIs | Verified | OWP Project List with Schedule - UPDATED 04-01-26.xlsx
4 | owner | Owner | 162 Ten Apartments LLC (Natural & Built) | text | Benchmark KPIs | Verified | OWP Project List with Schedule - UPDATED 04-01-26.xlsx
5 | location | Location | 16210 NE 80th St, Redmond, WA 98052 | text | Benchmark KPIs | Verified | OWP Project List with Schedule - UPDATED 04-01-26.xlsx
6 | project_type | Project Type | Multifamily New Construction (92 units) | text | Benchmark KPIs | Verified | OWP Project List with Schedule - UPDATED 04-01-26.xlsx
7 | insurance_type | Insurance | Not Wrap | text | Benchmark KPIs | Verified | OWP Project List with Schedule - UPDATED 04-01-26.xlsx
8 | gc_pm | GC PM | Tyson Cornett | text | Benchmark KPIs | Verified | OWP Project List with Schedule - UPDATED 04-01-26.xlsx
9 | gc_sup | GC Sup | Tyson Cornett | text | Benchmark KPIs | Verified | OWP Project List with Schedule - UPDATED 04-01-26.xlsx
10 | gc_pe | GC PE | TBD | text | Benchmark KPIs | Verified | OWP Project List with Schedule - UPDATED 04-01-26.xlsx
11 | developer | Developer | Natural & Built | text | Benchmark KPIs | Verified | OWP Project List with Schedule - UPDATED 04-01-26.xlsx
12 | owp_foreman | OWP RI Foreman | Reuben | text | Benchmark KPIs | Verified | Schedule
13 | start_date | Work Start | 2016-08-16 | date | Benchmark KPIs | Verified | 2035 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
14 | end_date | Work End | 2018 | date | Benchmark KPIs | Verified | 2035 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
15 | duration_months | Duration | 24 | months | Benchmark KPIs | Verified | Derived
16 | unit_count | Unit Count | 92 | units | Benchmark KPIs | Verified | OWP Project List with Schedule - UPDATED 04-01-26.xlsx
17 | contract_original | Contract Orig | 717400 | USD | Benchmark KPIs | Verified | OWP Project List with Schedule - UPDATED 04-01-26.xlsx
18 | contract_final | Contract Final | 722290 | USD | Benchmark KPIs | Verified | OWP Project List with Schedule - UPDATED 04-01-26.xlsx
19 | change_orders_implied | CO (implied) | 4890 | USD | Benchmark KPIs | Verified | 2035 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
20 | co_pct | CO % of Contract | 0.6816% | % | Benchmark KPIs | Verified | Derived
21 | revenue | Revenue | 722290 | USD | Benchmark KPIs | Verified | 2035 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
22 | direct_cost | Direct Cost | 363766.71 | USD | Benchmark KPIs | Verified | 2035 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
23 | net_profit | Net Profit | 358523.29 | USD | Benchmark KPIs | Verified | 2035 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
24 | gross_margin | Gross Margin | 49.64% | % | Benchmark KPIs | Verified | Derived
25 | retainage | Retainage | 36114.51 | USD | Benchmark KPIs | Verified | 2035 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
26 | retainage_pct | Retainage % | 5% | % | Benchmark KPIs | Verified | Derived
27 | labor_cost | Labor Cost | 133452.5 | USD | Benchmark KPIs | Verified | 2035 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
28 | material_cost | Material Cost | 159409.61 | USD | Benchmark KPIs | Verified | 2035 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
29 | overhead_cost | Overhead Cost | 1509 | USD | Benchmark KPIs | Verified | 2035 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
30 | burden_cost | Burden | 59186.15 | USD | Benchmark KPIs | Verified | 2035 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
31 | tax_cost | Tax | 10209.45 | USD | Benchmark KPIs | Verified | 2035 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
32 | total_hours | Total Hours | 5204.75 | hours | Benchmark KPIs | Verified | 2035 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
33 | total_workers | Total Workers | 24 | count | Benchmark KPIs | Verified | 2035 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
34 | blended_wage | Blended Wage | 25.6405 | USD/hr | Benchmark KPIs | Verified | Derived
35 | loaded_wage | Loaded Wage | 38.9736 | USD/hr | Benchmark KPIs | Verified | Derived
36 | burden_mult | Burden Multiplier | 1.52 | x | Benchmark KPIs | Verified | Derived
37 | roughin_hours | Rough-in Hours | 2891 | hours | Benchmark KPIs | Verified | 2035 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
38 | finish_hours | Finish Hours | 590 | hours | Benchmark KPIs | Verified | 2035 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
39 | rev_per_hour | Rev per Hour | 138.7752 | USD/hr | Benchmark KPIs | Verified | Derived
40 | profit_per_hour | Profit per Hour | 68.8839 | USD/hr | Benchmark KPIs | Verified | Derived
41 | rev_per_unit | Rev per Unit | 7850.9783 | USD | Benchmark KPIs | Verified | Derived
42 | cost_per_unit | Cost per Unit | 3953.986 | USD | Benchmark KPIs | Verified | Derived
43 | hours_per_unit | Hours per Unit | 56.5734 | hours | Benchmark KPIs | Verified | Derived
44 | labor_pct | Labor % | 18.48% | % | Benchmark KPIs | Verified | Derived
45 | material_pct | Material % | 22.07% | % | Benchmark KPIs | Verified | Derived
46 | total_vendors | Total Vendors | 16 | count | Vendors | Verified | 2035 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
47 | total_invoices | Total Invoices | 18 | count | Billing & SOV | Verified | 2035 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
48 | top_worker_share | Top Worker Share | 20.98% | % | Crew Analytics | Verified | Derived
49 | top5_worker_share | Top 5 Worker Share | 70.6% | % | Crew Analytics | Verified | Derived
50 | cost_code_count | Cost Codes Active | 22 | count | Budget vs Actual | Verified | 2035 Job Detail Report.pdf (Sage Timberline, 04/03/2026)

## Reconciliation
Reconciliation
Cross-sheet formula checks
# | Check | Value A | Value B | Delta | Status | Tabs
1 | Revenue = Contract Final | 722290 | 722290 |  |  | 1↔8
2 | Expenses = Labor+Mat+OH+Burden+Tax | 363766.71 | 363766.71 |  |  | 1↔3
3 | Net Profit = Revenue - Expenses | 358523.29 | 358523.29 |  |  | 1↔Derived
4 | Sage 999 actual = -Revenue | 722290 | 722290 |  |  | 2↔1
5 | Total Hours = Worker hours sum | 5204.75 | 5278.5 |  |  | 5↔2
6 | Contract Final - Orig = CO implied | 4890 | 4890 |  |  | 11↔Derived
7 | Worker count | 24 | 24 |  |  | 5↔1
8 | Cost code count | 22 | 22 |  |  | 2↔16