## Overview
Job #2036 · Westridge Apartments
Cortex JCR v2 • Exxel Pacific, Inc. (customer 2036EP) • 512 121st Place NE, Bellevue, WA • Owner: Exxel Pacific Westridge LLC
PROJECT OVERVIEW
Project Job # | 2036 |  | 2036 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
Project Name (Sage) | Westridge Apartments |  | 2036 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
Project Description | Westridge — 31-unit multifamily plumbing, Bellevue WA |  | OWP Project List with Schedule - UPDATED 04-01-26.xlsx + contract
General Contractor | Exxel Pacific, Inc. |  | OWP Project List with Schedule - UPDATED 04-01-26.xlsx
Customer Code (Sage) | 2036EP |  | 2036 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
Owner / Developer | Exxel Pacific Westridge LLC |  | OWP Project List with Schedule - UPDATED 04-01-26.xlsx
GC PM | David Strid |  | OWP Project List with Schedule - UPDATED 04-01-26.xlsx
GC Superintendent | Shon Geer |  | OWP Project List with Schedule - UPDATED 04-01-26.xlsx
GC PE | Jose Tapia |  | OWP Project List with Schedule - UPDATED 04-01-26.xlsx
OWP Rough-in Foreman | Gustavo |  | Schedule tab
Jobsite Location | 512 121st Place NE, Bellevue, WA |  | OWP Project List with Schedule - UPDATED 04-01-26.xlsx
Insurance | Not Wrap |  | OWP Project List with Schedule - UPDATED 04-01-26.xlsx
Fixture Schedule | 31-unit multifamily new construction |  | Project scope
Contract Type | Lump Sum |  | 2036-Exxel Pacific, Inc. subcontract + Job Info sheet
Unit Count | 31 |  | OWP Project List with Schedule - UPDATED 04-01-26.xlsx
Work Period | 2016-10-01 start → 2018 (20 months) |  | JDR PR/AR dates
CONTRACT VALUE |  | NET PROFIT | DIRECT COST | LABOR HOURS
418677 |  | 142468.04 | 276208.96 | 4098
Original $388,515.00 + ($30,162.00) COs (7.76%) |  | 34.0% margin | 66.0% of revenue | 30 workers
SCOPE OF WORK
Full plumbing installation per Division 22: underground, garage, rough-in, finish, gas, water main, insulation.
31-unit multifamily new construction at 512 121st Place NE, Bellevue, WA.
GC: Exxel Pacific, Inc. (2036EP); Owner/Developer: Exxel Pacific Westridge LLC.
Insurance: Not Wrap.
Project team: David Strid (GC PM) · Shon Geer (GC Sup) · Jose Tapia (GC PE) · Gustavo (OWP RI).
SOURCES
Canonical financial source: 2036 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
Job totals (JDR footer): Revenue $418,677.00 / Expenses $276,208.96 / Net $142,468.04 / Retainage $41,867.70
Source breakdown (derived): PR $111,994.00 · AP $93,265.85 · GL+other $70,949.11
Contract: Lump Sum $388,515.00 → $418,677.00
Change Orders (JDR-implied): $30,162.00 net
Project Team: David Strid · Shon Geer · Jose Tapia · Exxel Pacific · Gustavo
PROJECT TEAM (OWP Job Info)
Role | Status | Name / Firm
GC | Extracted | Exxel Pacific, Inc.
GC PM | Extracted | David Strid
GC Superintendent | Extracted | Shon Geer
GC PE | Extracted | Jose Tapia
Developer | Extracted | Exxel Pacific
Owner | Extracted | Exxel Pacific Westridge LLC
Architect | N/A | N/A
Structural | N/A | N/A
Acoustical | N/A | N/A
ADA Consultant | N/A | N/A
Interior Design | N/A | N/A
MEP Engineer | N/A | N/A
Insurance | Extracted | Not Wrap
OWP RI Foreman | Extracted | Gustavo

## Budget vs Actual
Budget vs Actual
All 16 cost codes from JDR. Contract $388,515 → $418,677.
Cost Code | Description | Original Budget | Revised Budget | Actual | Variance | % of Revised | Hours | Source
100 | Supervision | 5120 | 5220 | 3394 |  |  | 71 | 2036 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
101 | Takeoff & Purchase Labor | 5760 | 6060 | 6121.5 |  |  | 123 | 2036 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
110 | Underground Labor | 6800 | 10340 | 11913.5 |  |  | 400.5 | 2036 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
120 | Roughin Labor | 66670 | 66670 | 66604.5 |  |  | 2582.5 | 2036 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
130 | Finish Labor | 17520 | 17520 | 18527.25 |  |  | 731.5 | 2036 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
141 | Water Main/Insulation Lab | 2960 | 4004 | 5620 |  |  | 180 | 2036 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
142 | Mech Room Labor | 2600 | 2600 | 405 |  |  | 9.5 | 2036 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
210 | Underground Material | 6300 | 7778 | 7669.29 |  |  |  | 2036 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
211 | Garage Material | 0 | 0 | 65 |  |  |  | 2036 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
220 | Roughin Material | 30375 | 30375 | 21242.97 |  |  |  | 2036 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
230 | Finish Material | 62775 | 73757 | 65661.22 |  |  |  | 2036 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
241 | Water Main/Insulation Mat | 3320 | 3917 | 9614.37 |  |  |  | 2036 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
607 | Other Expenses | 2500 | 2500 | 825.48 |  |  |  | 2036 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
995 | Payroll Burden | 48719.51 | 51014.51 | 49931.78 |  |  |  | 2036 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
998 | Payroll Taxes | 8218.4 | 8608.55 | 8613.1 |  |  |  | 2036 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
999 | Sales | -388515 | -418677 | -418677 |  |  |  | 2036 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
TOTAL

## Cost Breakdown
Cost Breakdown by Category
Direct cost composition by category from JDR cost codes
Category | Cost Codes | Actual $ | % of Direct Cost | % of Revenue | Source
Labor | 100,101,110,120,130,141,142 | 112585.75 |  |  | 2036 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
Material | 210,211,220,230,241 | 104252.85 |  |  | 2036 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
Subcon+Engineering+Permits+Other | 607 | 825.48 |  |  | 2036 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
Payroll Burden | 995 | 49931.78 |  |  | 2036 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
Payroll Taxes | 998 | 8613.1 |  |  | 2036 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
TOTAL DIRECT COST |  |  | 100%

## Material
Material Purchases — AP Vendors
Material + subcontractor spend by vendor from JDR AP records
Vendor ID | Vendor Name | Total Spend | # Transactions | Category (inferred) | Source
2036FE | Ferguson Enterprises, Inc. $Westridge | 34359.22 | 16 | Plumbing / Supplies | 2036 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
2036RS | Rosen Supply Company, Inc. $Westridge | 32338.03 | 31 | Plumbing / Supplies | 2036 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
2036CS | Consolidated Supply Co. $Westridge | 16172.66 | 14 | Plumbing / Supplies | 2036 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
1175FE | Ferguson Enterprises, Inc. #3007 | 4793.63 | 15 | Plumbing / Supplies | 2036 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
1231KS | Keller Supply Company | 2581.14 | 3 | Plumbing / Supplies | 2036 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
2036KS | Keller Supply Co. $Westridge | 1132.08 | 2 | Plumbing / Supplies | 2036 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
1130CS | Consolidated Supply Co. | 931.38 | 1 | Plumbing / Supplies | 2036 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
1380RS | Rosen Supply Kirkland | 414.11 | 5 | Plumbing / Supplies | 2036 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
2033RS | Rosen Supply Company, Inc. $Vuecrest | 351.36 | 1 | Plumbing / Supplies | 2036 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
1234CO | Capital One Credit Card | 108.86 | 4 | Credit Card (mixed) | 2036 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
5621HD | Core & Main LP $HD Supply Waterworks | 45.7 | 1 | Plumbing / Supplies | 2036 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
2032RS | Rosen Supply Company, Inc. $Roosevelt | 37.68 | 1 | Plumbing / Supplies | 2036 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
2035CS | Consolidated Supply Co. $162Ten | 0 | 2 | Plumbing / Supplies | 2036 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
TOTAL

## Crew & Labor
Crew & Labor — Worker Roster
All 30 unique payroll workers. OWP RI: Gustavo.
Worker ID | Worker Name | Total Hours | Gross Pay | Blended Wage ($/hr) | # Work Days | Source
CA71 | Castaneda Juarez, Cesar O | 866 | 13356 |  | 34 | 2036 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
CA74 | Castaneda Martinez, Gustavo | 853 | 33761 |  | 35 | 2036 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
AM03 | Amaya Gonzalez, Edilberto A | 501 | 12514 |  | 15 | 2036 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
AS10 | Ascencio, Jose L | 390 | 8990 |  | 11 | 2036 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
CA72 | Castaneda Juarez, Edgar D | 240 | 6240 |  | 9 | 2036 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
GE70 | Gerard, Jordan E | 231 | 6908 |  | 13 | 2036 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
RO12 | Rodriguez Rodriguez, Aminadab N | 152 | 3344 |  | 4 | 2036 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
EG05 | Egbaou, Kossi D | 132 | 2112 |  | 5 | 2036 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
GE69 | Gerard, Jeffrey S | 131 | 6211 |  | 55 | 2036 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
SA54 | Sanders, Allen O | 96 | 4167 |  | 20 | 2036 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
GO51 | Gomez Reyes, Edith N | 79 | 1563 |  | 7 | 2036 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
HU06 | Hubbard, Robert W | 76.5 | 3290.5 |  | 21 | 2036 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
DO56 | Donelson, Richard T | 63 | 3304.5 |  | 31 | 2036 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
EL33 | Eliassen, Cory H | 39 | 859 |  | 4 | 2036 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
RE91 | Reyes, Maria E | 39 | 624 |  | 3 | 2036 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
NE46 | Nelson, Charles E | 37 | 592 |  | 5 | 2036 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
BA70 | Barnhart, Joseph N | 33 | 1520 |  | 6 | 2036 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
YO29 | Yohannes Jr., Samson | 32 | 576 |  | 2 | 2036 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
KI55 | Kinssies, Jr, John E | 17.5 | 455 |  | 2 | 2036 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
MA71 | Martinez Reyes, Juan C | 16 | 416 |  | 2 | 2036 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
HE70 | Hernandez Gonzalez, Osbaldo | 16 | 304 |  | 1 | 2036 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
GE71 | Gerard, Mitchell J | 16 | 0 |  | 1 | 2036 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
OL17 | Olea Galeana, Maricela | 8 | 128 |  | 1 | 2036 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
FO55 | Fonseca Teruel, Eduardo | 8 | 128 |  | 1 | 2036 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
GA70 | Garcia, Jordan X | 5 | 135 |  | 1 | 2036 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
RE18 | Reed, Reuben H | 5 | 180 |  | 1 | 2036 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
CO73 | Cortes Sepulveda, Jose R | 5 | 95 |  | 1 | 2036 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
HU04 | Hubbard, Dustin R | 4 | 84 |  | 2 | 2036 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
MC09 | McCabe, Thomas C | 3 | 93 |  | 1 | 2036 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
TA96 | Taylor, Evan R | 2 | 44 |  | 1 | 2036 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
TOTAL

## Crew Analytics
Crew Analytics
Team-level labor productivity, concentration, wage dispersion
TEAM-LEVEL METRICS
Metric | Value | Notes | Source
Total Workers | 30 | Unique payroll IDs | 2036 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
Total Labor Hours | 4098 | Sum of labor codes | 2036 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
Total Gross Pay | 112585.75 | Sum of labor codes | 2036 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
Blended Gross Wage ($/hr) | 27.4733 | Labor$/Hrs (pre-burden) | Derived
Top Worker Hours Share | 21.13% | CA71 Castaneda Juarez, Cesar O (866 hrs) | Derived
Top 5 Workers Hours Share | 69.55% | Concentration metric | Derived
Highest Wage Rate ($/hr) | 52.4524 | Single-worker blended | Derived
Lowest Wage Rate ($/hr) | 0 | Single-worker blended | Derived
Avg Hours per Worker | 136.6 | Includes short-tenure workers | Derived
Avg Project Days per Worker | 9.8333 | Mean days | Derived

## Productivity
Productivity Metrics
Normalized ratios. Per-unit from 31 units.
Metric | Value | Basis | Source / Note
Revenue per Labor Hour | 102.1662 | USD/hr
Profit per Labor Hour | 34.7653 | USD/hr
Labor Cost per Hour (blended) | 27.4733 | USD/hr | Pre-burden
Fully-Loaded Labor Rate ($/hr) | 41.7595 | USD/hr | Incl burden+taxes
Burden Multiplier | 1.52 | x | Fully-loaded/blended
Rough-in Hours (code 120) | 2582.5 | hrs
Finish Hours (code 130) | 731.5 | hrs
Rough-in % of Total Hours | 63.02% | %
Gross Margin | 34.03% | %
Labor % of Revenue | 26.89% | %
Material % of Revenue | 24.9% | %
Direct Cost Ratio | 65.97% | % | All exp/Rev
Revenue per Unit (31) | 13505.7097 | USD | 31 units
Labor Hours per Unit | 132.1935 | hrs
Labor Cost per Unit | 3631.7984 | USD
Material Cost per Unit | 3362.9952 | USD
Direct Cost per Unit | 8909.9665 | USD
Rough-in Hours per Unit | 83.3065 | hrs

## PO Commitments
PO Commitments
Inbound contract (GC → OWP). Outbound vendor commitments — see Material tab.
PO # | Date | Issuer | Type | Status | Description | Amount | Source
PRIME | 2016-10-01 | Exxel Pacific, Inc. | Lump Sum Subcontract | Closed | Westridge Apartments plumbing (31 units) — per Div 22 | 388515 | 2036-Exxel Pacific, Inc. subcontract + Job Info sheet
CO-NET | — | Exxel Pacific, Inc. | Change Orders (net, JDR-implied) | Executed | Net CO impact (Sage 999 rev - orig) | 30162 | 2036 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
TOTAL (contract + COs)

## Billing & SOV
Billing & Schedule of Values
14 invoices to Exxel Pacific, Inc.. Retainage $41,867.70.
Invoice # | Date | Total Billed (signed) | Retainage (signed) | # Lines | Source
036880 | 05/19/17 | -28650 | -1432.5 | 1 | 2036 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
036892 | 06/01/17 | 28650 | 1432.5 | 1 | 2036 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
036893 | 06/01/17 | -28650 | -2865 | 1 | 2036 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
036954 | 09/20/17 | -88188 | -8818.8 | 1 | 2036 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
036962 | 10/20/17 | -177270 | -17727 | 1 | 2036 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
036985 | 11/17/17 | -38955 | -3895.5 | 1 | 2036 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
036997 | 12/15/17 | -4800 | -480 | 1 | 2036 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
037096 | 05/18/18 | -29034 | -2903.4 | 1 | 2036 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
037120 | 06/20/18 | -34491 | -3449.1 | 1 | 2036 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
037142 | 07/20/18 | -4600 | -460 | 1 | 2036 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
037176 | 09/19/18 | -750 | -75 | 1 | 2036 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
037194 | 09/19/18 | 750 | 75 | 1 | 2036 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
037195 | 09/19/18 | -9200 | -920 | 1 | 2036 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
037239 | 11/16/18 | -3489 | -348.9 | 1 | 2036 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
TOTAL (signed)

## Insights
Insights & Observations
Narrative findings from JDR
# | Insight | Detail | Confidence | Source
1 | MARGIN PROFILE | Net profit $142,468.04 on $418,677.00 revenue = 34.0% gross margin. | Verified | 2036 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
2 | CONTRACT CHANGE | Original $388,515.00 → final $418,677.00 = $+30,162.00 net (+7.76%). | Verified | 2036 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
3 | LABOR PROFILE | Labor cost $112,585.75 (26.9% of rev) across 4,098 hrs and 30 workers. Blended wage $27.47/hr. | Verified | 2036 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
4 | VENDOR CONCENTRATION | Top 5 AP vendors: ~$90,244.68 (97% of AP). Top vendor: Ferguson Enterprises, Inc. $Westridge ($34,359.22). | Verified | 2036 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
5 | RETAINAGE | Retainage $41,867.70 = 10.0% of AR per JDR 04/03/2026 — legacy project, likely 7+ years stale. | Verified | 2036 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
6 | ROUGH-IN SHARE | Code 120 Roughin Labor = 2,582 hrs (63% of labor hours). | Verified | 2036 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
7 | TOP COST CODE | Largest actual cost: 120 Roughin Labor = $66,604.50 | Verified | 2036 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
8 | WORKER CONCENTRATION | Top worker Castaneda Juarez, Cesar O = 866 hrs (21% of total). | Verified | 2036 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
9 | INSURANCE | Not Wrap — OCIP wrap. | Verified | OWP Project List with Schedule - UPDATED 04-01-26.xlsx
10 | SCOPE CONTEXT | Westridge — 31-unit multifamily plumbing, Bellevue WA. | Verified | OWP Project List with Schedule - UPDATED 04-01-26.xlsx + JDR

## Benchmark KPIs
Benchmark KPIs
Normalized metrics for cross-project comparison
KPI | Data Name | Value | Category | Notes | Confidence | Source Document
Job Number | job_number | 2036 | Profile | OWP job ID | Verified | 2036 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
Job Name | job_name | Westridge Apartments | Profile |  | Verified | 2036 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
General Contractor | gc | Exxel Pacific, Inc. | Profile |  | Verified | OWP Project List with Schedule - UPDATED 04-01-26.xlsx
Owner | owner | Exxel Pacific Westridge LLC | Profile |  | Verified | OWP Project List with Schedule - UPDATED 04-01-26.xlsx
Location | location | 512 121st Place NE, Bellevue, WA | Profile |  | Verified | OWP Project List with Schedule - UPDATED 04-01-26.xlsx
Project Type | project_type | Multifamily New Construction (31 units) | Profile |  | Verified | OWP Project List with Schedule - UPDATED 04-01-26.xlsx
Insurance Type | insurance | Not Wrap | Profile |  | Verified | OWP Project List with Schedule - UPDATED 04-01-26.xlsx
GC PM | gc_pm | David Strid | Profile |  | Verified | OWP Project List with Schedule - UPDATED 04-01-26.xlsx
GC Sup | gc_sup | Shon Geer | Profile |  | Verified | OWP Project List with Schedule - UPDATED 04-01-26.xlsx
GC PE | gc_pe | Jose Tapia | Profile |  | Verified | OWP Project List with Schedule - UPDATED 04-01-26.xlsx
Developer | developer | Exxel Pacific | Profile |  | Verified | OWP Project List with Schedule - UPDATED 04-01-26.xlsx
OWP RI Foreman | owp_foreman | Gustavo | Profile |  | Verified | Schedule
Work Start | start_date | 2016-10-01 | Profile |  | Verified | 2036 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
Work End | end_date | 2018 | Profile |  | Verified | 2036 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
Duration (months) | duration_months | 20 | Profile |  | Verified | Derived
Unit Count | unit_count | 31 | Profile |  | Verified | OWP Project List with Schedule - UPDATED 04-01-26.xlsx
Contract Original | contract_original | 388515 | Financial |  | Verified | OWP Project List with Schedule - UPDATED 04-01-26.xlsx
Contract Final | contract_final | 418677 | Financial |  | Verified | OWP Project List with Schedule - UPDATED 04-01-26.xlsx
Change Orders ($, implied) | co_implied | 30162 | Financial | Final - Original | Verified | 2036 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
CO % of Contract | co_pct | 7.763% | Financial |  | Verified | Derived
Revenue | revenue | 418677 | Financial | AR total | Verified | 2036 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
Direct Cost | direct_cost | 276208.96 | Financial | JDR Expenses | Verified | 2036 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
Net Profit | net_profit | 142468.04 | Financial | Rev - Exp | Verified | 2036 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
Gross Margin | gross_margin | 34.03% | Financial |  | Verified | Derived
Retainage | retainage | 41867.7 | Financial | JDR AR retainage | Verified | 2036 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
Retainage % of Revenue | retainage_pct | 10% | Financial |  | Verified | Derived
Labor Cost | labor_cost | 112585.75 | Labor | Codes 100-151 | Verified | 2036 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
Material Cost | material_cost | 104252.85 | Material | Codes 210-245 | Verified | 2036 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
Overhead Cost | overhead_cost | 825.48 | Financial | Codes 600-607 | Verified | 2036 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
Burden Cost | burden_cost | 49931.78 | Labor | Code 995 | Verified | 2036 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
Tax Cost | tax_cost | 8613.1 | Labor | Code 998 | Verified | 2036 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
Total Labor Hours | total_hours | 4098 | Labor | Sum labor codes | Verified | 2036 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
Total Workers | total_workers | 30 | Labor | Unique PR IDs | Verified | 2036 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
Blended Gross Wage | blended_wage | 27.4733 | Labor |  | Verified | Derived
Fully-Loaded Wage | loaded_wage | 41.7595 | Labor |  | Verified | Derived
Burden Multiplier | burden_mult | 1.52 | Labor |  | Verified | Derived
Rough-in Hours | roughin_hours | 2582.5 | Labor | Code 120 | Verified | 2036 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
Finish Hours | finish_hours | 731.5 | Labor | Code 130 | Verified | 2036 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
Revenue per Hour | rev_per_hour | 102.1662 | Productivity |  | Verified | Derived
Profit per Hour | profit_per_hour | 34.7653 | Productivity |  | Verified | Derived
Revenue per Unit | rev_per_unit | 13505.7097 | Productivity |  | Verified | Derived
Direct Cost per Unit | cost_per_unit | 8909.9665 | Productivity |  | Verified | Derived
Hours per Unit | hours_per_unit | 132.1935 | Productivity |  | Verified | Derived
Labor % of Revenue | labor_pct | 26.89% | Cost Mix |  | Verified | Derived
Material % of Revenue | material_pct | 24.9% | Cost Mix |  | Verified | Derived
Total Vendors | total_vendors | 13 | Material |  | Verified | 2036 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
Total Invoices | total_invoices | 14 | Billing |  | Verified | 2036 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
Cost Codes Active | cost_codes | 16 | Structure |  | Verified | 2036 Job Detail Report.pdf (Sage Timberline, 04/03/2026)

## Vendors
Vendors — AP Summary
Vendor-level spend ranking
Rank | Vendor ID | Vendor Name | Total Spend | # Transactions | % of AP | Source
1 | 2036FE | Ferguson Enterprises, Inc. $Westridge | 34359.22 | 16 |  | 2036 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
2 | 2036RS | Rosen Supply Company, Inc. $Westridge | 32338.03 | 31 |  | 2036 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
3 | 2036CS | Consolidated Supply Co. $Westridge | 16172.66 | 14 |  | 2036 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
4 | 1175FE | Ferguson Enterprises, Inc. #3007 | 4793.63 | 15 |  | 2036 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
5 | 1231KS | Keller Supply Company | 2581.14 | 3 |  | 2036 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
6 | 2036KS | Keller Supply Co. $Westridge | 1132.08 | 2 |  | 2036 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
7 | 1130CS | Consolidated Supply Co. | 931.38 | 1 |  | 2036 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
8 | 1380RS | Rosen Supply Kirkland | 414.11 | 5 |  | 2036 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
9 | 2033RS | Rosen Supply Company, Inc. $Vuecrest | 351.36 | 1 |  | 2036 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
10 | 1234CO | Capital One Credit Card | 108.86 | 4 |  | 2036 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
11 | 5621HD | Core & Main LP $HD Supply Waterworks | 45.7 | 1 |  | 2036 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
12 | 2032RS | Rosen Supply Company, Inc. $Roosevelt | 37.68 | 1 |  | 2036 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
13 | 2035CS | Consolidated Supply Co. $162Ten | 0 | 2 |  | 2036 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
TOTAL

## Change Log
Change Log — Master Register
Contract, CO net, retainage events — JDR only
Event ID | Type | Date | Subject | Originator | Cost Impact ($) | Status | Source
CONTRACT-ORIG | Contract | 2016-10-01 | Prime subcontract — Lump Sum $388,515.00 | Exxel Pacific, Inc. | 388515 | Executed | 2036-Exxel Pacific, Inc. subcontract + Job Info sheet
CO-NET | Change Order (net) | — | Net JDR-implied COs $+30,162.00 | Exxel Pacific, Inc. | 30162 | Executed | 2036 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
FIRST-INVOICE | Invoice | 05/18/18 | First billing (per JDR) | Sub (OWP) | 0 | Paid | 2036 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
LAST-INVOICE | Invoice | 12/15/17 | Last billing (per JDR) | Sub (OWP) | 0 | Paid | 2036 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
RETAINAGE-OPEN | Retainage | As of 04/03/2026 | Retainage $41,867.70 open | GC | 0 | Outstanding | 2036 Job Detail Report.pdf (Sage Timberline, 04/03/2026)

## Root Cause Analysis
Root Cause Analysis
Primary variance drivers by category
Category | Codes | Net $ Variance | Root Cause (inferred) | Notes
Contract Change | 999 (Sales) | 30162 | JDR-implied net CO impact | $388,515 → $418,677
Labor | 100,101,110,120,130,141,142 | 171.75 | Labor variance vs revised budget | 30 workers
Material | 210,211,220,230,241 | -11574.15 | Material procurement variance | 13 vendors
Overhead | 607 | -1674.52 | Engineering/permits/subcon variance
Burden+Tax | 995+998 | -1078.18 | Payroll accrual tracking labor
TOTAL NET VARIANCE
RESPONSIBILITY ATTRIBUTION
Responsible Party | # Drivers | Net $ Impact | Notes
GC / Owner (scope changes) | 1 | 30162 | Aggregate JDR-implied COs
Sub (OWP) labor performance | 7 | 171.75 | Hours + rate vs budget
Sub (OWP) material procurement | 5 | -11574.15 | 13 vendors
OWP burden accrual | 2 | -1078.18 | Payroll burden + tax
OWP overhead | 1 | -1674.52 | Engineering/permits/subcon

## Predictive Signals
Predictive Signals
Leading indicators from JDR
CURRENT-STATE SIGNALS
Indicator | Current Value | Benchmark | Status | Meaning
Contract Change % | 7.76% | ±10% | HEALTHY | +7.76% net
Labor % of Revenue | 26.89% | <30% | HEALTHY | 26.9%
GL Overhead % of Revenue | 16.95% | <5% | HEALTHY | 16.9%
Vendor Concentration (Top 5) | 96.76% | <95% | HEALTHY | Top 5 = 97% of AP
Retainage % | 10% | <10% | WATCH | 10.0%
Gross Margin | 34.03% | >30% | HEALTHY | 34.0%
Labor Hrs Total | 409800% | varies | INFO | 4,098 hrs, 30 workers
Worker Concentration (top 1) | 21.13% | <25% | HEALTHY | 21.1% (Castaneda Juarez, Cesar O)
Rough-in Labor Share | 63.02% | 40-65% | HEALTHY | 63%
Retainage Legacy | STALE | <90 days post-closeout | ELEVATED | $41,868 outstanding
FORECAST MODELS
Forecast | Current Estimate | Confidence | Driver | Model Note
Final margin (actual) | 34.03% | Actual | Job closed | 34.0%
Retainage collection | $41,868 open | Low | Legacy project | May require LOI/writedown
Unit-level economics | $13,506/unit rev, $4,596/unit profit | Verified | 31 units | Multifamily New Construction benchmark

## Metric Registry
Metric Registry — Cortex Data Catalog
Every metric with data_label, confidence, and source
# | Data Label | Human Label | Value | Unit | Source Tab | Confidence | Source Document(s)
1 | job_number | Job Number | 2036 | id | Benchmark KPIs | Verified | 2036 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
2 | job_name | Job Name | Westridge Apartments | text | Benchmark KPIs | Verified | 2036 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
3 | general_contractor | GC | Exxel Pacific, Inc. | text | Benchmark KPIs | Verified | OWP Project List with Schedule - UPDATED 04-01-26.xlsx
4 | owner | Owner | Exxel Pacific Westridge LLC | text | Benchmark KPIs | Verified | OWP Project List with Schedule - UPDATED 04-01-26.xlsx
5 | location | Location | 512 121st Place NE, Bellevue, WA | text | Benchmark KPIs | Verified | OWP Project List with Schedule - UPDATED 04-01-26.xlsx
6 | project_type | Project Type | Multifamily New Construction (31 units) | text | Benchmark KPIs | Verified | OWP Project List with Schedule - UPDATED 04-01-26.xlsx
7 | insurance_type | Insurance | Not Wrap | text | Benchmark KPIs | Verified | OWP Project List with Schedule - UPDATED 04-01-26.xlsx
8 | gc_pm | GC PM | David Strid | text | Benchmark KPIs | Verified | OWP Project List with Schedule - UPDATED 04-01-26.xlsx
9 | gc_sup | GC Sup | Shon Geer | text | Benchmark KPIs | Verified | OWP Project List with Schedule - UPDATED 04-01-26.xlsx
10 | gc_pe | GC PE | Jose Tapia | text | Benchmark KPIs | Verified | OWP Project List with Schedule - UPDATED 04-01-26.xlsx
11 | developer | Developer | Exxel Pacific | text | Benchmark KPIs | Verified | OWP Project List with Schedule - UPDATED 04-01-26.xlsx
12 | owp_foreman | OWP RI Foreman | Gustavo | text | Benchmark KPIs | Verified | Schedule
13 | start_date | Work Start | 2016-10-01 | date | Benchmark KPIs | Verified | 2036 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
14 | end_date | Work End | 2018 | date | Benchmark KPIs | Verified | 2036 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
15 | duration_months | Duration | 20 | months | Benchmark KPIs | Verified | Derived
16 | unit_count | Unit Count | 31 | units | Benchmark KPIs | Verified | OWP Project List with Schedule - UPDATED 04-01-26.xlsx
17 | contract_original | Contract Orig | 388515 | USD | Benchmark KPIs | Verified | OWP Project List with Schedule - UPDATED 04-01-26.xlsx
18 | contract_final | Contract Final | 418677 | USD | Benchmark KPIs | Verified | OWP Project List with Schedule - UPDATED 04-01-26.xlsx
19 | change_orders_implied | CO (implied) | 30162 | USD | Benchmark KPIs | Verified | 2036 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
20 | co_pct | CO % of Contract | 7.763% | % | Benchmark KPIs | Verified | Derived
21 | revenue | Revenue | 418677 | USD | Benchmark KPIs | Verified | 2036 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
22 | direct_cost | Direct Cost | 276208.96 | USD | Benchmark KPIs | Verified | 2036 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
23 | net_profit | Net Profit | 142468.04 | USD | Benchmark KPIs | Verified | 2036 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
24 | gross_margin | Gross Margin | 34.03% | % | Benchmark KPIs | Verified | Derived
25 | retainage | Retainage | 41867.7 | USD | Benchmark KPIs | Verified | 2036 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
26 | retainage_pct | Retainage % | 10% | % | Benchmark KPIs | Verified | Derived
27 | labor_cost | Labor Cost | 112585.75 | USD | Benchmark KPIs | Verified | 2036 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
28 | material_cost | Material Cost | 104252.85 | USD | Benchmark KPIs | Verified | 2036 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
29 | overhead_cost | Overhead Cost | 825.48 | USD | Benchmark KPIs | Verified | 2036 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
30 | burden_cost | Burden | 49931.78 | USD | Benchmark KPIs | Verified | 2036 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
31 | tax_cost | Tax | 8613.1 | USD | Benchmark KPIs | Verified | 2036 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
32 | total_hours | Total Hours | 4098 | hours | Benchmark KPIs | Verified | 2036 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
33 | total_workers | Total Workers | 30 | count | Benchmark KPIs | Verified | 2036 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
34 | blended_wage | Blended Wage | 27.4733 | USD/hr | Benchmark KPIs | Verified | Derived
35 | loaded_wage | Loaded Wage | 41.7595 | USD/hr | Benchmark KPIs | Verified | Derived
36 | burden_mult | Burden Multiplier | 1.52 | x | Benchmark KPIs | Verified | Derived
37 | roughin_hours | Rough-in Hours | 2582.5 | hours | Benchmark KPIs | Verified | 2036 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
38 | finish_hours | Finish Hours | 731.5 | hours | Benchmark KPIs | Verified | 2036 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
39 | rev_per_hour | Rev per Hour | 102.1662 | USD/hr | Benchmark KPIs | Verified | Derived
40 | profit_per_hour | Profit per Hour | 34.7653 | USD/hr | Benchmark KPIs | Verified | Derived
41 | rev_per_unit | Rev per Unit | 13505.7097 | USD | Benchmark KPIs | Verified | Derived
42 | cost_per_unit | Cost per Unit | 8909.9665 | USD | Benchmark KPIs | Verified | Derived
43 | hours_per_unit | Hours per Unit | 132.1935 | hours | Benchmark KPIs | Verified | Derived
44 | labor_pct | Labor % | 26.89% | % | Benchmark KPIs | Verified | Derived
45 | material_pct | Material % | 24.9% | % | Benchmark KPIs | Verified | Derived
46 | total_vendors | Total Vendors | 13 | count | Vendors | Verified | 2036 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
47 | total_invoices | Total Invoices | 14 | count | Billing & SOV | Verified | 2036 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
48 | top_worker_share | Top Worker Share | 21.13% | % | Crew Analytics | Verified | Derived
49 | top5_worker_share | Top 5 Worker Share | 69.55% | % | Crew Analytics | Verified | Derived
50 | cost_code_count | Cost Codes Active | 16 | count | Budget vs Actual | Verified | 2036 Job Detail Report.pdf (Sage Timberline, 04/03/2026)

## Reconciliation
Reconciliation
Cross-sheet formula checks
# | Check | Value A | Value B | Delta | Status | Tabs
1 | Revenue = Contract Final | 418677 | 418677 |  |  | 1↔8
2 | Expenses = Labor+Mat+OH+Burden+Tax | 276208.96 | 276208.96 |  |  | 1↔3
3 | Net Profit = Revenue - Expenses | 142468.04 | 142468.04 |  |  | 1↔Derived
4 | Sage 999 actual = -Revenue | 418677 | 418677 |  |  | 2↔1
5 | Total Hours = Worker hours sum | 4098 | 4096 |  |  | 5↔2
6 | Contract Final - Orig = CO implied | 30162 | 30162 |  |  | 11↔Derived
7 | Worker count | 30 | 30 |  |  | 5↔1
8 | Cost code count | 16 | 16 |  |  | 2↔16