## Overview
Job #2037 · University Apartments (MYSA)
Cortex JCR v2 • Marpac Construction (customer 2037MP) • 3025 NE 130th Street, Seattle WA • Owner: MYSA University Apartments LP
PROJECT OVERVIEW
Project Job # | 2037 |  | 2037 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
Project Name (Sage) | University Apartments (MYSA) |  | 2037 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
Project Description | University Apartments (MYSA) — 122-unit multifamily + 5 townhomes, Seattle WA |  | OWP Project List with Schedule - UPDATED 04-01-26.xlsx + contract
General Contractor | Marpac Construction |  | OWP Project List with Schedule - UPDATED 04-01-26.xlsx
Customer Code (Sage) | 2037MP |  | 2037 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
Owner / Developer | MYSA University Apartments LP |  | OWP Project List with Schedule - UPDATED 04-01-26.xlsx
GC PM | Evan Chan |  | OWP Project List with Schedule - UPDATED 04-01-26.xlsx
GC Superintendent | Doyle Gustafson |  | OWP Project List with Schedule - UPDATED 04-01-26.xlsx
GC PE | TBD |  | OWP Project List with Schedule - UPDATED 04-01-26.xlsx
OWP Rough-in Foreman | Rick / Joe |  | Schedule tab
Jobsite Location | 3025 NE 130th Street, Seattle WA |  | OWP Project List with Schedule - UPDATED 04-01-26.xlsx
Insurance | Not Wrap |  | OWP Project List with Schedule - UPDATED 04-01-26.xlsx
Fixture Schedule | 122-unit multifamily new construction |  | Project scope
Contract Type | Lump Sum |  | 2037-Marpac Construction subcontract + Job Info sheet
Unit Count | 122 |  | OWP Project List with Schedule - UPDATED 04-01-26.xlsx
Work Period | 2017-01-09 start → 2018 (24 months) |  | JDR PR/AR dates
CONTRACT VALUE |  | NET PROFIT | DIRECT COST | LABOR HOURS
2076783 |  | 859548.37 | 1217234.63 | 14799
Original $1,920,850.00 + ($155,933.00) COs (8.12%) |  | 41.4% margin | 58.6% of revenue | 50 workers
SCOPE OF WORK
Full plumbing installation per Division 22: underground, garage, rough-in, finish, gas, water main, insulation.
122-unit multifamily new construction at 3025 NE 130th Street, Seattle WA.
GC: Marpac Construction (2037MP); Owner/Developer: MYSA University Apartments LP.
Insurance: Not Wrap.
Project team: Evan Chan (GC PM) · Doyle Gustafson (GC Sup) · TBD (GC PE) · Rick / Joe (OWP RI).
SOURCES
Canonical financial source: 2037 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
Job totals (JDR footer): Revenue $2,076,783.00 / Expenses $1,217,234.63 / Net $859,548.37 / Retainage $103,839.15
Source breakdown (derived): PR $417,369.25 · AP $478,332.73 · GL+other $321,532.65
Contract: Lump Sum $1,920,850.00 → $2,076,783.00
Change Orders (JDR-implied): $155,933.00 net
Project Team: Evan Chan · Doyle Gustafson · TBD · MYSA · Rick / Joe

## Budget vs Actual
Budget vs Actual
All 29 cost codes from JDR. Contract $1,920,850 → $2,076,783.
Cost Code | Description | Original Budget | Revised Budget | Actual | Variance | % of Revised | Hours | Source
100 | Supervision | 10110 | 11810 | 7079 |  |  | 142.5 | 2037 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
101 | Takeoff & Purchase Labor | 18425 | 20125 | 15008.5 |  |  | 279.5 | 2037 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
110 | Underground Labor | 15920 | 20680 | 12034.5 |  |  | 390 | 2037 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
111 | Garage Labor | 55665 | 57225 | 57346.75 |  |  | 2025 | 2037 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
112 | Canout Labor | 15875 | 17510 | 16173.5 |  |  | 508.5 | 2037 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
120 | Roughin Labor | 263000 | 265970 | 240637.46 |  |  | 8156.5 | 2037 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
130 | Finish Labor | 43380 | 44150 | 41886.75 |  |  | 1644 | 2037 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
140 | Gas Labor | 7750 | 7750 | 6410 |  |  | 194 | 2037 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
141 | Water Main/Insulation Lab | 51720 | 51720 | 25492.04 |  |  | 983.5 | 2037 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
142 | Mech Room Labor | 13000 | 24060 | 17394.75 |  |  | 446.5 | 2037 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
143 | Condensation Drains Labor | 0 | 0 | 432 |  |  | 24 | 2037 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
150 | Warranty Labor | 0 | 0 | 250 |  |  | 5 | 2037 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
210 | Underground Material | 37500 | 27000 | 15243.5 |  |  |  | 2037 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
211 | Garage Material | 58095 | 56631 | 17635.16 |  |  |  | 2037 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
212 | Canout Material | 17575 | 17575 | 11652.7 |  |  |  | 2037 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
220 | Roughin Material | 101645 | 105468 | 106312.24 |  |  |  | 2037 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
230 | Finish Material | 187500 | 331860 | 273944.52 |  |  |  | 2037 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
240 | Gas Material | 5625 | 5625 | 4633.76 |  |  |  | 2037 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
241 | Water Main/Insulation Mat | 66355 | 66355 | 33059.1 |  |  |  | 2037 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
242 | Mech Room Material | 102185 | 32687 | 24688.69 |  |  |  | 2037 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
243 | Condensation Drains Mat | 0 | 0 | 106.54 |  |  |  | 2037 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
600 | Subcontractor | 500 | 4225 | 4420.5 |  |  |  | 2037 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
601 | Engineering/Plans | 36000 | 39220 | 44369.11 |  |  |  | 2037 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
602 | Rental Equipment | 4000 | 4000 | 1208.69 |  |  |  | 2037 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
603 | Permits & Licenses | 11735 | 12335 | 9138 |  |  |  | 2037 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
607 | Other Expenses | 10000 | 10000 | 71.1 |  |  |  | 2037 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
995 | Payroll Burden | 228804.89 | 240448.43 | 196679.65 |  |  |  | 2037 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
998 | Payroll Taxes | 38601.52 | 40602.38 | 33926.12 |  |  |  | 2037 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
999 | Sales | -1920850 | -2076783 | -2076783 |  |  |  | 2037 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
TOTAL

## Cost Breakdown
Cost Breakdown by Category
Direct cost composition by category from JDR cost codes
Category | Cost Codes | Actual $ | % of Direct Cost | % of Revenue | Source
Labor | 100,101,110,111,112,120,130,140,141,142,143,150 | 440145.25 |  |  | 2037 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
Material | 210,211,212,220,230,240,241,242,243 | 487276.21 |  |  | 2037 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
Subcon+Engineering+Permits+Other | 600,601,602,603,607 | 59207.4 |  |  | 2037 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
Payroll Burden | 995 | 196679.65 |  |  | 2037 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
Payroll Taxes | 998 | 33926.12 |  |  | 2037 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
TOTAL DIRECT COST |  |  | 100%

## Material
Material Purchases — AP Vendors
Material + subcontractor spend by vendor from JDR AP records
Vendor ID | Vendor Name | Total Spend | # Transactions | Category (inferred) | Source
2037RS | Rosen Supply Company, Inc. $University | 93793.49 | 40 | Plumbing / Supplies | 2037 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
1231KS | Keller Supply Company | 93338.89 | 41 | Plumbing / Supplies | 2037 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
1380RS | Rosen Supply Kirkland | 58453.46 | 70 | Plumbing / Supplies | 2037 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
1625FE | Franklin Engineering | 44211.75 | 14 | Engineering (601) | 2037 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
7230BB | Best Bath Systems | 39139.25 | 3 | Uncategorized | 2037 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
2037FE | Ferguson Enterprises, Inc. $University | 35851.78 | 6 | Plumbing / Supplies | 2037 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
2037CS | Consolidated Supply Co. $University | 26940.43 | 13 | Plumbing / Supplies | 2037 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
3612MS | Mechanical Sales, Inc. | 21350.99 | 4 | Plumbing / Supplies | 2037 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
1175FE | Ferguson Enterprises, Inc. #3007 | 14532.28 | 22 | Plumbing / Supplies | 2037 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
1609QC | Quality Concrete Products, Inc. $32 | 12766 | 5 | Uncategorized | 2037 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
2037KS | Keller Supply Co. $University | 11104.17 | 9 | Plumbing / Supplies | 2037 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
1234CO | Capital One Credit Card | 9409.73 | 22 | Credit Card (mixed) | 2037 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
1130CS | Consolidated Supply Co. | 4756.55 | 12 | Plumbing / Supplies | 2037 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
5560CH | California Hydronics Corp | 4422.57 | 4 | Uncategorized | 2037 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
3129MR | Mechanical Resource Services, Inc. | 1712.5 | 1 | Uncategorized | 2037 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
1234CI | Citibank Credit Card | 1570.69 | 1 | Credit Card (mixed) | 2037 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
3181SC | Scan2Core, Inc. | 1278 | 2 | Uncategorized | 2037 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
1799AW | AllWest Underground, Inc. | 1208.69 | 3 | Uncategorized | 2037 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
1504CA | Chip Away Bathtub Repair, Inc. | 725 | 1 | Uncategorized | 2037 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
4320MC | MAD Concrete Cutting & Coring, Inc. | 450 | 1 | Uncategorized | 2037 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
2046RS | Rosen Supply Company, Inc. $4218 Rooseve | 351.16 | 1 | Plumbing / Supplies | 2037 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
5621HD | Core & Main LP $HD Supply Waterworks | 332.1 | 3 | Plumbing / Supplies | 2037 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
1421RA | R.A. Brown Backflow Testing | 255 | 2 | Testing subcontractor | 2037 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
1288DR | DRSi | 157.36 | 2 | Uncategorized | 2037 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
2132MH | Manor Hardware & Construction Supply | 155 | 1 | Plumbing / Supplies | 2037 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
1021AT | ACME Corp | 65.89 | 1 | Uncategorized | 2037 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
2036CS | Consolidated Supply Co. $Westridge | 0 | 2 | Plumbing / Supplies | 2037 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
TOTAL

## Crew & Labor
Crew & Labor — Worker Roster
All 50 unique payroll workers. OWP RI: Rick / Joe.
Worker ID | Worker Name | Total Hours | Gross Pay | Blended Wage ($/hr) | # Work Days | Source
AN14 | Anderson, Richard P | 1517 | 64215.5 |  | 68 | 2037 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
KI55 | Kinssies, Jr, John E | 1422.25 | 37288.5 |  | 64 | 2037 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
RI87 | Rivera, Jorge A | 1415 | 42138 |  | 39 | 2037 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
RO75 | Ross, Kelli M | 1013 | 39000 |  | 27 | 2037 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
OB46 | O'Bleness, Caleb N | 728 | 19501 |  | 20 | 2037 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
GO56 | Gonzalez Hernandez, Josue | 600 | 17400 |  | 19 | 2037 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
ME53 | Mendoza Morales, Jesus A | 590.5 | 14152 |  | 17 | 2037 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
HU06 | Hubbard, Robert W | 503.5 | 22079.5 |  | 37 | 2037 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
EL33 | Eliassen, Cory H | 425.5 | 10506.5 |  | 24 | 2037 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
MC09 | McCabe, Thomas C | 399 | 13152 |  | 16 | 2037 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
VE42 | Velasquez Cruz, Denis M | 397 | 11056 |  | 11 | 2037 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
GA70 | Garcia, Jordan X | 384.5 | 12264 |  | 11 | 2037 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
RO06 | Roberts, Lake A | 370 | 6722.5 |  | 12 | 2037 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
BA42 | Baker, Scott W | 360 | 6120 |  | 11 | 2037 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
VE43 | Velasquez Cruz, Osman N | 359 | 7120 |  | 11 | 2037 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
HO18 | Hoeg, Xavier A | 359 | 5720 |  | 11 | 2037 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
PI54 | Pineda Lemus, Gerson S | 343 | 5488 |  | 10 | 2037 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
WE55 | Wennig, Johnathan M | 330.25 | 8602.5 |  | 18 | 2037 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
RE96 | Reyes Cruz, Denis A | 329 | 8205 |  | 10 | 2037 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
HE70 | Hernandez Gonzalez, Osbaldo | 321.75 | 6056.75 |  | 16 | 2037 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
LO58 | Lopez Reyes, Boris O | 313 | 5634 |  | 11 | 2037 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
GE69 | Gerard, Jeffrey S | 276 | 13450 |  | 94 | 2037 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
GO51 | Gomez Reyes, Edith N | 219.5 | 4769.5 |  | 13 | 2037 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
BA68 | Barbosa, Michael S | 215.5 | 4859.5 |  | 8 | 2037 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
RE91 | Reyes, Maria E | 196 | 3272 |  | 12 | 2037 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
TR60 | Trower-Kelly, Fidel D | 196 | 3184 |  | 13 | 2037 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
DO56 | Donelson, Richard T | 148 | 8637.5 |  | 71 | 2037 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
SA54 | Sanders, Allen O | 139 | 6393 |  | 23 | 2037 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
NE46 | Nelson, Charles E | 94 | 1504 |  | 3 | 2037 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
FO55 | Fonseca Teruel, Eduardo | 68 | 1224 |  | 6 | 2037 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
ST02 | Stahlschmidt, John P | 40 | 664 |  | 5 | 2037 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
SE64 | Sepulveda Gonzalez, Alfredo | 39 | 1248 |  | 3 | 2037 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
BA70 | Barnhart, Joseph N | 38 | 1660.5 |  | 14 | 2037 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
GA83 | Gauthier, Dillon R | 24 | 384 |  | 1 | 2037 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
VA98 | Vazquez Popoca, Jose N | 24 | 384 |  | 2 | 2037 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
WI46 | Wilson, Garret A | 22.5 | 802.5 |  | 4 | 2037 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
YO29 | Yohannes Jr., Samson | 22.5 | 411.5 |  | 2 | 2037 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
LE17 | Lee, Ha Nul | 18.25 | 292 |  | 3 | 2037 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
RO10 | Rodriguez Arevalos, Christian | 16 | 368 |  | 1 | 2037 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
EI74 | Eisenhauer, Tommy J | 8 | 144 |  | 1 | 2037 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
GE71 | Gerard, Mitchell J | 8 | 208 |  | 1 | 2037 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
LO87 | Lovo, German G | 8 | 184 |  | 1 | 2037 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
TA96 | Taylor, Evan R | 8 | 208 |  | 1 | 2037 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
BE54 | Benites Portillo, Marvin E | 6 | 144 |  | 1 | 2037 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
PO71 | Portillo, Kevin J | 5 | 90 |  | 1 | 2037 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
RE18 | Reed, Reuben H | 5 | 215 |  | 1 | 2037 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
ME52 | Mendoza, Edgar E | 3.5 | 59.5 |  | 1 | 2037 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
MA71 | Martinez Reyes, Juan C | 3 | 57 |  | 1 | 2037 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
HU04 | Hubbard, Dustin R | 2 | 44 |  | 1 | 2037 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
WA35 | Waites, Thaddeus Z | 2 | 86 |  | 1 | 2037 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
TOTAL

## Crew Analytics
Crew Analytics
Team-level labor productivity, concentration, wage dispersion
TEAM-LEVEL METRICS
Metric | Value | Notes | Source
Total Workers | 50 | Unique payroll IDs | 2037 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
Total Labor Hours | 14799 | Sum of labor codes | 2037 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
Total Gross Pay | 440145.25 | Sum of labor codes | 2037 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
Blended Gross Wage ($/hr) | 29.7416 | Labor$/Hrs (pre-burden) | Derived
Top Worker Hours Share | 10.25% | AN14 Anderson, Richard P (1517 hrs) | Derived
Top 5 Workers Hours Share | 41.19% | Concentration metric | Derived
Highest Wage Rate ($/hr) | 58.3615 | Single-worker blended | Derived
Lowest Wage Rate ($/hr) | 15.9331 | Single-worker blended | Derived
Avg Hours per Worker | 295.98 | Includes short-tenure workers | Derived
Avg Project Days per Worker | 15.04 | Mean days | Derived

## Productivity
Productivity Metrics
Normalized ratios. Per-unit from 122 units.
Metric | Value | Basis | Source / Note
Revenue per Labor Hour | 140.3327 | USD/hr
Profit per Labor Hour | 58.0815 | USD/hr
Labor Cost per Hour (blended) | 29.7416 | USD/hr | Pre-burden
Fully-Loaded Labor Rate ($/hr) | 45.3241 | USD/hr | Incl burden+taxes
Burden Multiplier | 1.5239 | x | Fully-loaded/blended
Rough-in Hours (code 120) | 8156.5 | hrs
Finish Hours (code 130) | 1644 | hrs
Rough-in % of Total Hours | 55.12% | %
Gross Margin | 41.39% | %
Labor % of Revenue | 21.19% | %
Material % of Revenue | 23.46% | %
Direct Cost Ratio | 58.61% | % | All exp/Rev
Revenue per Unit (122) | 17022.8115 | USD | 122 units
Labor Hours per Unit | 121.3033 | hrs
Labor Cost per Unit | 3607.748 | USD
Material Cost per Unit | 3994.0673 | USD
Direct Cost per Unit | 9977.333 | USD
Rough-in Hours per Unit | 66.8566 | hrs

## PO Commitments
PO Commitments
Inbound contract (GC → OWP). Outbound vendor commitments — see Material tab.
PO # | Date | Issuer | Type | Status | Description | Amount | Source
PRIME | 2017-01-09 | Marpac Construction | Lump Sum Subcontract | Closed | University Apartments (MYSA) plumbing (122 units) — per Div 22 | 1920850 | 2037-Marpac Construction subcontract + Job Info sheet
CO-NET | — | Marpac Construction | Change Orders (net, JDR-implied) | Executed | Net CO impact (Sage 999 rev - orig) | 155933 | 2037 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
TOTAL (contract + COs)

## Billing & SOV
Billing & Schedule of Values
25 invoices to Marpac Construction. Retainage $103,839.15.
Invoice # | Date | Total Billed (signed) | Retainage (signed) | # Lines | Source
036885 | 05/19/17 | -62750 | -3137.5 | 2 | 2037 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
036903 | 06/19/17 | -23550 | -1177.5 | 2 | 2037 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
036929 | 08/18/17 | -46550 | -2327.5 | 2 | 2037 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
036950 | 09/20/17 | -6700 | -335 | 1 | 2037 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
036975 | 11/17/17 | -12100 | -605 | 1 | 2037 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
036995 | 12/15/17 | -27980 | -1399 | 3 | 2037 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
037004 | 01/19/18 | -9300 | -465 | 1 | 2037 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
037024 | 02/20/18 | -137040 | -6852 | 3 | 2037 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
037040 | 03/20/18 | -132480 | -6624 | 4 | 2037 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
037058 | 04/20/18 | -218050 | -10902.5 | 8 | 2037 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
037090 | 05/18/18 | -222546 | -11127.3 | 10 | 2037 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
037106 | 06/20/18 | -448210 | -22410.5 | 7 | 2037 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
037127 | 07/20/18 | -157585 | -7879.25 | 11 | 2037 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
037145 | 07/20/18 | 157585 | 7879.25 | 11 | 2037 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
037146 | 07/20/18 | -157585 | -7879.25 | 11 | 2037 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
037156 | 08/20/18 | -183130 | -9156.5 | 12 | 2037 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
037183 | 09/19/18 | -75300 | -3765 | 7 | 2037 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
037201 | 10/19/18 | -75040 | -3752 | 4 | 2037 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
037235 | 11/16/18 | -82890 | -4144.5 | 6 | 2037 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
037253 | 12/14/18 | -38598 | -1929.9 | 4 | 2037 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
037275 | 01/18/19 | -4981 | -249.05 | 1 | 2037 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
037298 | 03/20/19 | -65397 | -3269.85 | 11 | 2037 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
037318 | 04/19/19 | -10958 | -547.9 | 5 | 2037 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
037363 | 06/19/19 | -15260 | -763 | 4 | 2037 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
037373 | 07/19/19 | -20388 | -1019.4 | 6 | 2037 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
TOTAL (signed)

## Insights
Insights & Observations
Narrative findings from JDR
# | Insight | Detail | Confidence | Source
1 | MARGIN PROFILE | Net profit $859,548.37 on $2,076,783.00 revenue = 41.4% gross margin. | Verified | 2037 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
2 | CONTRACT CHANGE | Original $1,920,850.00 → final $2,076,783.00 = $+155,933.00 net (+8.12%). | Verified | 2037 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
3 | LABOR PROFILE | Labor cost $440,145.25 (21.2% of rev) across 14,799 hrs and 50 workers. Blended wage $29.74/hr. | Verified | 2037 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
4 | VENDOR CONCENTRATION | Top 5 AP vendors: ~$328,936.84 (69% of AP). Top vendor: Rosen Supply Company, Inc. $University ($93,793.49). | Verified | 2037 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
5 | RETAINAGE | Retainage $103,839.15 = 5.0% of AR per JDR 04/03/2026 — legacy project, likely 7+ years stale. | Verified | 2037 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
6 | ROUGH-IN SHARE | Code 120 Roughin Labor = 8,156 hrs (55% of labor hours). | Verified | 2037 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
7 | TOP COST CODE | Largest actual cost: 230 Finish Material = $273,944.52 | Verified | 2037 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
8 | WORKER CONCENTRATION | Top worker Anderson, Richard P = 1517 hrs (10% of total). | Verified | 2037 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
9 | INSURANCE | Not Wrap — OCIP wrap. | Verified | OWP Project List with Schedule - UPDATED 04-01-26.xlsx
10 | SCOPE CONTEXT | University Apartments (MYSA) — 122-unit multifamily + 5 townhomes, Seattle WA. | Verified | OWP Project List with Schedule - UPDATED 04-01-26.xlsx + JDR

## Benchmark KPIs
Benchmark KPIs
Normalized metrics for cross-project comparison
KPI | Data Name | Value | Category | Notes | Confidence | Source Document
Job Number | job_number | 2037 | Profile | OWP job ID | Verified | 2037 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
Job Name | job_name | University Apartments (MYSA) | Profile |  | Verified | 2037 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
General Contractor | gc | Marpac Construction | Profile |  | Verified | OWP Project List with Schedule - UPDATED 04-01-26.xlsx
Owner | owner | MYSA University Apartments LP | Profile |  | Verified | OWP Project List with Schedule - UPDATED 04-01-26.xlsx
Location | location | 3025 NE 130th Street, Seattle WA | Profile |  | Verified | OWP Project List with Schedule - UPDATED 04-01-26.xlsx
Project Type | project_type | Multifamily New Construction (122 units) | Profile |  | Verified | OWP Project List with Schedule - UPDATED 04-01-26.xlsx
Insurance Type | insurance | Not Wrap | Profile |  | Verified | OWP Project List with Schedule - UPDATED 04-01-26.xlsx
GC PM | gc_pm | Evan Chan | Profile |  | Verified | OWP Project List with Schedule - UPDATED 04-01-26.xlsx
GC Sup | gc_sup | Doyle Gustafson | Profile |  | Verified | OWP Project List with Schedule - UPDATED 04-01-26.xlsx
GC PE | gc_pe | TBD | Profile |  | Verified | OWP Project List with Schedule - UPDATED 04-01-26.xlsx
Developer | developer | MYSA | Profile |  | Verified | OWP Project List with Schedule - UPDATED 04-01-26.xlsx
OWP RI Foreman | owp_foreman | Rick / Joe | Profile |  | Verified | Schedule
Work Start | start_date | 2017-01-09 | Profile |  | Verified | 2037 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
Work End | end_date | 2018 | Profile |  | Verified | 2037 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
Duration (months) | duration_months | 24 | Profile |  | Verified | Derived
Unit Count | unit_count | 122 | Profile |  | Verified | OWP Project List with Schedule - UPDATED 04-01-26.xlsx
Contract Original | contract_original | 1920850 | Financial |  | Verified | OWP Project List with Schedule - UPDATED 04-01-26.xlsx
Contract Final | contract_final | 2076783 | Financial |  | Verified | OWP Project List with Schedule - UPDATED 04-01-26.xlsx
Change Orders ($, implied) | co_implied | 155933 | Financial | Final - Original | Verified | 2037 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
CO % of Contract | co_pct | 8.118% | Financial |  | Verified | Derived
Revenue | revenue | 2076783 | Financial | AR total | Verified | 2037 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
Direct Cost | direct_cost | 1217234.63 | Financial | JDR Expenses | Verified | 2037 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
Net Profit | net_profit | 859548.37 | Financial | Rev - Exp | Verified | 2037 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
Gross Margin | gross_margin | 41.39% | Financial |  | Verified | Derived
Retainage | retainage | 103839.15 | Financial | JDR AR retainage | Verified | 2037 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
Retainage % of Revenue | retainage_pct | 5% | Financial |  | Verified | Derived
Labor Cost | labor_cost | 440145.25 | Labor | Codes 100-151 | Verified | 2037 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
Material Cost | material_cost | 487276.21 | Material | Codes 210-245 | Verified | 2037 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
Overhead Cost | overhead_cost | 59207.4 | Financial | Codes 600-607 | Verified | 2037 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
Burden Cost | burden_cost | 196679.65 | Labor | Code 995 | Verified | 2037 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
Tax Cost | tax_cost | 33926.12 | Labor | Code 998 | Verified | 2037 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
Total Labor Hours | total_hours | 14799 | Labor | Sum labor codes | Verified | 2037 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
Total Workers | total_workers | 50 | Labor | Unique PR IDs | Verified | 2037 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
Blended Gross Wage | blended_wage | 29.7416 | Labor |  | Verified | Derived
Fully-Loaded Wage | loaded_wage | 45.3241 | Labor |  | Verified | Derived
Burden Multiplier | burden_mult | 1.5239 | Labor |  | Verified | Derived
Rough-in Hours | roughin_hours | 8156.5 | Labor | Code 120 | Verified | 2037 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
Finish Hours | finish_hours | 1644 | Labor | Code 130 | Verified | 2037 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
Revenue per Hour | rev_per_hour | 140.3327 | Productivity |  | Verified | Derived
Profit per Hour | profit_per_hour | 58.0815 | Productivity |  | Verified | Derived
Revenue per Unit | rev_per_unit | 17022.8115 | Productivity |  | Verified | Derived
Direct Cost per Unit | cost_per_unit | 9977.333 | Productivity |  | Verified | Derived
Hours per Unit | hours_per_unit | 121.3033 | Productivity |  | Verified | Derived
Labor % of Revenue | labor_pct | 21.19% | Cost Mix |  | Verified | Derived
Material % of Revenue | material_pct | 23.46% | Cost Mix |  | Verified | Derived
Total Vendors | total_vendors | 27 | Material |  | Verified | 2037 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
Total Invoices | total_invoices | 25 | Billing |  | Verified | 2037 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
Cost Codes Active | cost_codes | 29 | Structure |  | Verified | 2037 Job Detail Report.pdf (Sage Timberline, 04/03/2026)

## Vendors
Vendors — AP Summary
Vendor-level spend ranking
Rank | Vendor ID | Vendor Name | Total Spend | # Transactions | % of AP | Source
1 | 2037RS | Rosen Supply Company, Inc. $University | 93793.49 | 40 |  | 2037 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
2 | 1231KS | Keller Supply Company | 93338.89 | 41 |  | 2037 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
3 | 1380RS | Rosen Supply Kirkland | 58453.46 | 70 |  | 2037 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
4 | 1625FE | Franklin Engineering | 44211.75 | 14 |  | 2037 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
5 | 7230BB | Best Bath Systems | 39139.25 | 3 |  | 2037 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
6 | 2037FE | Ferguson Enterprises, Inc. $University | 35851.78 | 6 |  | 2037 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
7 | 2037CS | Consolidated Supply Co. $University | 26940.43 | 13 |  | 2037 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
8 | 3612MS | Mechanical Sales, Inc. | 21350.99 | 4 |  | 2037 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
9 | 1175FE | Ferguson Enterprises, Inc. #3007 | 14532.28 | 22 |  | 2037 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
10 | 1609QC | Quality Concrete Products, Inc. $32 | 12766 | 5 |  | 2037 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
11 | 2037KS | Keller Supply Co. $University | 11104.17 | 9 |  | 2037 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
12 | 1234CO | Capital One Credit Card | 9409.73 | 22 |  | 2037 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
13 | 1130CS | Consolidated Supply Co. | 4756.55 | 12 |  | 2037 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
14 | 5560CH | California Hydronics Corp | 4422.57 | 4 |  | 2037 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
15 | 3129MR | Mechanical Resource Services, Inc. | 1712.5 | 1 |  | 2037 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
16 | 1234CI | Citibank Credit Card | 1570.69 | 1 |  | 2037 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
17 | 3181SC | Scan2Core, Inc. | 1278 | 2 |  | 2037 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
18 | 1799AW | AllWest Underground, Inc. | 1208.69 | 3 |  | 2037 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
19 | 1504CA | Chip Away Bathtub Repair, Inc. | 725 | 1 |  | 2037 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
20 | 4320MC | MAD Concrete Cutting & Coring, Inc. | 450 | 1 |  | 2037 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
21 | 2046RS | Rosen Supply Company, Inc. $4218 Rooseve | 351.16 | 1 |  | 2037 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
22 | 5621HD | Core & Main LP $HD Supply Waterworks | 332.1 | 3 |  | 2037 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
23 | 1421RA | R.A. Brown Backflow Testing | 255 | 2 |  | 2037 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
24 | 1288DR | DRSi | 157.36 | 2 |  | 2037 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
25 | 2132MH | Manor Hardware & Construction Supply | 155 | 1 |  | 2037 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
26 | 1021AT | ACME Corp | 65.89 | 1 |  | 2037 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
27 | 2036CS | Consolidated Supply Co. $Westridge | 0 | 2 |  | 2037 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
TOTAL

## Change Log
Change Log — Master Register
Contract, CO net, retainage events — JDR only
Event ID | Type | Date | Subject | Originator | Cost Impact ($) | Status | Source
CONTRACT-ORIG | Contract | 2017-01-09 | Prime subcontract — Lump Sum $1,920,850.00 | Marpac Construction | 1920850 | Executed | 2037-Marpac Construction subcontract + Job Info sheet
CO-NET | Change Order (net) | — | Net JDR-implied COs $+155,933.00 | Marpac Construction | 155933 | Executed | 2037 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
FIRST-INVOICE | Invoice | 01/18/19 | First billing (per JDR) | Sub (OWP) | 0 | Paid | 2037 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
LAST-INVOICE | Invoice | 12/15/17 | Last billing (per JDR) | Sub (OWP) | 0 | Paid | 2037 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
RETAINAGE-OPEN | Retainage | As of 04/03/2026 | Retainage $103,839.15 open | GC | 0 | Outstanding | 2037 Job Detail Report.pdf (Sage Timberline, 04/03/2026)

## Root Cause Analysis
Root Cause Analysis
Primary variance drivers by category
Category | Codes | Net $ Variance | Root Cause (inferred) | Notes
Contract Change | 999 (Sales) | 155933 | JDR-implied net CO impact | $1,920,850 → $2,076,783
Labor | 100,101,110,111,112,120,130,140,141,142,143,150 | -80854.75 | Labor variance vs revised budget | 50 workers
Material | 210,211,212,220,230,240,241,242,243 | -155924.79 | Material procurement variance | 27 vendors
Overhead | 600,601,602,603,607 | -10572.6 | Engineering/permits/subcon variance
Burden+Tax | 995+998 | -50445.04 | Payroll accrual tracking labor
TOTAL NET VARIANCE
RESPONSIBILITY ATTRIBUTION
Responsible Party | # Drivers | Net $ Impact | Notes
GC / Owner (scope changes) | 1 | 155933 | Aggregate JDR-implied COs
Sub (OWP) labor performance | 12 | -80854.75 | Hours + rate vs budget
Sub (OWP) material procurement | 9 | -155924.79 | 27 vendors
OWP burden accrual | 2 | -50445.04 | Payroll burden + tax
OWP overhead | 5 | -10572.6 | Engineering/permits/subcon

## Predictive Signals
Predictive Signals
Leading indicators from JDR
CURRENT-STATE SIGNALS
Indicator | Current Value | Benchmark | Status | Meaning
Contract Change % | 8.12% | ±10% | HEALTHY | +8.12% net
Labor % of Revenue | 21.19% | <30% | HEALTHY | 21.2%
GL Overhead % of Revenue | 15.48% | <5% | HEALTHY | 15.5%
Vendor Concentration (Top 5) | 68.77% | <95% | HEALTHY | Top 5 = 69% of AP
Retainage % | 5% | <10% | HEALTHY | 5.0%
Gross Margin | 41.39% | >30% | HEALTHY | 41.4%
Labor Hrs Total | 1479900% | varies | INFO | 14,799 hrs, 50 workers
Worker Concentration (top 1) | 10.25% | <25% | HEALTHY | 10.3% (Anderson, Richard P)
Rough-in Labor Share | 55.12% | 40-65% | HEALTHY | 55%
Retainage Legacy | STALE | <90 days post-closeout | ELEVATED | $103,839 outstanding
FORECAST MODELS
Forecast | Current Estimate | Confidence | Driver | Model Note
Final margin (actual) | 41.39% | Actual | Job closed | 41.4%
Retainage collection | $103,839 open | Low | Legacy project | May require LOI/writedown
Unit-level economics | $17,023/unit rev, $7,045/unit profit | Verified | 122 units | Multifamily New Construction benchmark

## Metric Registry
Metric Registry — Cortex Data Catalog
Every metric with data_label, confidence, and source
# | Data Label | Human Label | Value | Unit | Source Tab | Confidence | Source Document(s)
1 | job_number | Job Number | 2037 | id | Benchmark KPIs | Verified | 2037 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
2 | job_name | Job Name | University Apartments (MYSA) | text | Benchmark KPIs | Verified | 2037 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
3 | general_contractor | GC | Marpac Construction | text | Benchmark KPIs | Verified | OWP Project List with Schedule - UPDATED 04-01-26.xlsx
4 | owner | Owner | MYSA University Apartments LP | text | Benchmark KPIs | Verified | OWP Project List with Schedule - UPDATED 04-01-26.xlsx
5 | location | Location | 3025 NE 130th Street, Seattle WA | text | Benchmark KPIs | Verified | OWP Project List with Schedule - UPDATED 04-01-26.xlsx
6 | project_type | Project Type | Multifamily New Construction (122 units) | text | Benchmark KPIs | Verified | OWP Project List with Schedule - UPDATED 04-01-26.xlsx
7 | insurance_type | Insurance | Not Wrap | text | Benchmark KPIs | Verified | OWP Project List with Schedule - UPDATED 04-01-26.xlsx
8 | gc_pm | GC PM | Evan Chan | text | Benchmark KPIs | Verified | OWP Project List with Schedule - UPDATED 04-01-26.xlsx
9 | gc_sup | GC Sup | Doyle Gustafson | text | Benchmark KPIs | Verified | OWP Project List with Schedule - UPDATED 04-01-26.xlsx
10 | gc_pe | GC PE | TBD | text | Benchmark KPIs | Verified | OWP Project List with Schedule - UPDATED 04-01-26.xlsx
11 | developer | Developer | MYSA | text | Benchmark KPIs | Verified | OWP Project List with Schedule - UPDATED 04-01-26.xlsx
12 | owp_foreman | OWP RI Foreman | Rick / Joe | text | Benchmark KPIs | Verified | Schedule
13 | start_date | Work Start | 2017-01-09 | date | Benchmark KPIs | Verified | 2037 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
14 | end_date | Work End | 2018 | date | Benchmark KPIs | Verified | 2037 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
15 | duration_months | Duration | 24 | months | Benchmark KPIs | Verified | Derived
16 | unit_count | Unit Count | 122 | units | Benchmark KPIs | Verified | OWP Project List with Schedule - UPDATED 04-01-26.xlsx
17 | contract_original | Contract Orig | 1920850 | USD | Benchmark KPIs | Verified | OWP Project List with Schedule - UPDATED 04-01-26.xlsx
18 | contract_final | Contract Final | 2076783 | USD | Benchmark KPIs | Verified | OWP Project List with Schedule - UPDATED 04-01-26.xlsx
19 | change_orders_implied | CO (implied) | 155933 | USD | Benchmark KPIs | Verified | 2037 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
20 | co_pct | CO % of Contract | 8.118% | % | Benchmark KPIs | Verified | Derived
21 | revenue | Revenue | 2076783 | USD | Benchmark KPIs | Verified | 2037 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
22 | direct_cost | Direct Cost | 1217234.63 | USD | Benchmark KPIs | Verified | 2037 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
23 | net_profit | Net Profit | 859548.37 | USD | Benchmark KPIs | Verified | 2037 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
24 | gross_margin | Gross Margin | 41.39% | % | Benchmark KPIs | Verified | Derived
25 | retainage | Retainage | 103839.15 | USD | Benchmark KPIs | Verified | 2037 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
26 | retainage_pct | Retainage % | 5% | % | Benchmark KPIs | Verified | Derived
27 | labor_cost | Labor Cost | 440145.25 | USD | Benchmark KPIs | Verified | 2037 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
28 | material_cost | Material Cost | 487276.21 | USD | Benchmark KPIs | Verified | 2037 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
29 | overhead_cost | Overhead Cost | 59207.4 | USD | Benchmark KPIs | Verified | 2037 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
30 | burden_cost | Burden | 196679.65 | USD | Benchmark KPIs | Verified | 2037 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
31 | tax_cost | Tax | 33926.12 | USD | Benchmark KPIs | Verified | 2037 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
32 | total_hours | Total Hours | 14799 | hours | Benchmark KPIs | Verified | 2037 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
33 | total_workers | Total Workers | 50 | count | Benchmark KPIs | Verified | 2037 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
34 | blended_wage | Blended Wage | 29.7416 | USD/hr | Benchmark KPIs | Verified | Derived
35 | loaded_wage | Loaded Wage | 45.3241 | USD/hr | Benchmark KPIs | Verified | Derived
36 | burden_mult | Burden Multiplier | 1.5239 | x | Benchmark KPIs | Verified | Derived
37 | roughin_hours | Rough-in Hours | 8156.5 | hours | Benchmark KPIs | Verified | 2037 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
38 | finish_hours | Finish Hours | 1644 | hours | Benchmark KPIs | Verified | 2037 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
39 | rev_per_hour | Rev per Hour | 140.3327 | USD/hr | Benchmark KPIs | Verified | Derived
40 | profit_per_hour | Profit per Hour | 58.0815 | USD/hr | Benchmark KPIs | Verified | Derived
41 | rev_per_unit | Rev per Unit | 17022.8115 | USD | Benchmark KPIs | Verified | Derived
42 | cost_per_unit | Cost per Unit | 9977.333 | USD | Benchmark KPIs | Verified | Derived
43 | hours_per_unit | Hours per Unit | 121.3033 | hours | Benchmark KPIs | Verified | Derived
44 | labor_pct | Labor % | 21.19% | % | Benchmark KPIs | Verified | Derived
45 | material_pct | Material % | 23.46% | % | Benchmark KPIs | Verified | Derived
46 | total_vendors | Total Vendors | 27 | count | Vendors | Verified | 2037 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
47 | total_invoices | Total Invoices | 25 | count | Billing & SOV | Verified | 2037 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
48 | top_worker_share | Top Worker Share | 10.25% | % | Crew Analytics | Verified | Derived
49 | top5_worker_share | Top 5 Worker Share | 41.19% | % | Crew Analytics | Verified | Derived
50 | cost_code_count | Cost Codes Active | 29 | count | Budget vs Actual | Verified | 2037 Job Detail Report.pdf (Sage Timberline, 04/03/2026)

## Reconciliation
Reconciliation
Cross-sheet formula checks
# | Check | Value A | Value B | Delta | Status | Tabs
1 | Revenue = Contract Final | 2076783 | 2076783 |  |  | 1↔8
2 | Expenses = Labor+Mat+OH+Burden+Tax | 1217234.63 | 1217234.63 |  |  | 1↔3
3 | Net Profit = Revenue - Expenses | 859548.37 | 859548.37 |  |  | 1↔Derived
4 | Sage 999 actual = -Revenue | 2076783 | 2076783 |  |  | 2↔1
5 | Total Hours = Worker hours sum | 14799 | 14335 |  |  | 5↔2
6 | Contract Final - Orig = CO implied | 155933 | 155933 |  |  | 11↔Derived
7 | Worker count | 50 | 50 |  |  | 5↔1
8 | Cost code count | 29 | 29 |  |  | 2↔16