## Overview
Job #2038 · 2nd & John
Cortex JCR v2 • Compass Harbor Construction, LLC (customer 2038CH) • 200 2nd Ave West, Seattle, WA • Owner: 2nd & John Apartments (Continental)
PROJECT OVERVIEW
Project Job # | 2038 |  | 2038 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
Project Name (Sage) | 2nd & John |  | 2038 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
Project Description | 2nd & John — 80-unit multifamily plumbing, Lower Queen Anne Seattle |  | OWP Project List with Schedule - UPDATED 04-01-26.xlsx + contract
General Contractor | Compass Harbor Construction, LLC |  | OWP Project List with Schedule - UPDATED 04-01-26.xlsx
Customer Code (Sage) | 2038CH |  | 2038 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
Owner / Developer | 2nd & John Apartments (Continental) |  | OWP Project List with Schedule - UPDATED 04-01-26.xlsx
GC PM | Justin Anderson |  | OWP Project List with Schedule - UPDATED 04-01-26.xlsx
GC Superintendent | Kurt Weagant |  | OWP Project List with Schedule - UPDATED 04-01-26.xlsx
GC PE | Karl Clocksin |  | OWP Project List with Schedule - UPDATED 04-01-26.xlsx
OWP Rough-in Foreman | Thaddeus / Joe |  | Schedule tab
Jobsite Location | 200 2nd Ave West, Seattle, WA |  | OWP Project List with Schedule - UPDATED 04-01-26.xlsx
Insurance | Wrap (OCIP) |  | OWP Project List with Schedule - UPDATED 04-01-26.xlsx
Fixture Schedule | 80-unit multifamily new construction |  | Project scope
Contract Type | Lump Sum |  | 2038-Compass Harbor Construction, LLC subcontract + Job Info sheet
Unit Count | 80 |  | OWP Project List with Schedule - UPDATED 04-01-26.xlsx
Work Period | 2017-02-17 start → 2019 (24 months) |  | JDR PR/AR dates
CONTRACT VALUE |  | NET PROFIT | DIRECT COST | LABOR HOURS
1229419 |  | 422105.87 | 807313.13 | 11814.25
Original $1,210,378.00 + ($19,041.00) COs (1.57%) |  | 34.3% margin | 65.7% of revenue | 36 workers
SCOPE OF WORK
Full plumbing installation per Division 22: underground, garage, rough-in, finish, gas, water main, insulation.
80-unit multifamily new construction at 200 2nd Ave West, Seattle, WA.
GC: Compass Harbor Construction, LLC (2038CH); Owner/Developer: 2nd & John Apartments (Continental).
Insurance: Wrap (OCIP).
Project team: Justin Anderson (GC PM) · Kurt Weagant (GC Sup) · Karl Clocksin (GC PE) · Thaddeus / Joe (OWP RI).
SOURCES
Canonical financial source: 2038 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
Job totals (JDR footer): Revenue $1,229,419.00 / Expenses $807,313.13 / Net $422,105.87 / Retainage $59,720.95
Source breakdown (derived): PR $318,362.00 · AP $282,413.73 · GL+other $206,537.40
Contract: Lump Sum $1,210,378.00 → $1,229,419.00
Change Orders (JDR-implied): $19,041.00 net
Project Team: Justin Anderson · Kurt Weagant · Karl Clocksin · Continental · Thaddeus / Joe

## Budget vs Actual
Budget vs Actual
All 29 cost codes from JDR. Contract $1,210,378 → $1,229,419.
Cost Code | Description | Original Budget | Revised Budget | Actual | Variance | % of Revised | Hours | Source
100 | Supervision | 7460 | 7660 | 1667 |  |  | 32 | 2038 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
101 | Takeoff & Purchase Labor | 11600 | 12550 | 11937.5 |  |  | 228 | 2038 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
110 | Underground Labor | 10620 | 11115 | 5314.5 |  |  | 169.25 | 2038 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
111 | Garage Labor | 34205 | 39485 | 44370.5 |  |  | 1695 | 2038 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
112 | Canout Labor | 4250 | 4895 | 9423.5 |  |  | 277 | 2038 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
120 | Roughin Labor | 136655 | 143435 | 181998 |  |  | 7100 | 2038 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
130 | Finish Labor | 25860 | 26050 | 20959 |  |  | 872.5 | 2038 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
140 | Gas Labor | 3000 | 3360 | 2740 |  |  | 91 | 2038 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
141 | Water Main/Insulation Lab | 31600 | 31700 | 38061 |  |  | 1339 | 2038 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
142 | Mech Room Labor | 20000 | 20300 | 7634.5 |  |  |  | 2038 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
150 | Warranty Labor | 0 | 0 | 719.25 |  |  | 10.5 | 2038 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
210 | Underground Material | 26470 | 26903 | 11448.44 |  |  |  | 2038 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
211 | Garage Material | 34080 | 37555 | 26750.81 |  |  |  | 2038 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
212 | Canout Material | 5100 | 6316 | 4514.39 |  |  |  | 2038 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
220 | Roughin Material | 83800 | 88698 | 61984.15 |  |  |  | 2038 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
230 | Finish Material | 137370 | 109090 | 116427.88 |  |  |  | 2038 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
240 | Gas Material | 7000 | 7250 | 1301.17 |  |  |  | 2038 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
241 | Water Main/Insulation Mat | 38115 | 36610 | 32240.09 |  |  |  | 2038 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
242 | Mech Room Material | 59460 | 59760 | 13768.11 |  |  |  | 2038 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
243 | Condensation Drains Mat | 0 | 0 | 258.5 |  |  |  | 2038 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
330 | Flats Finish Labor | 0 | 0 | 0 |  |  |  | 2038 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
600 | Subcontractor | 1000 | 1000 | 2967 |  |  |  | 2038 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
601 | Engineering/Plans | 40000 | 40000 | 36872.75 |  |  |  | 2038 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
602 | Rental Equipment | 4000 | 4000 | 4897.67 |  |  |  | 2038 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
603 | Permits & Licenses | 6710 | 6850 | 5797 |  |  |  | 2038 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
607 | Other Expenses | 10000 | 10000 | 7498.01 |  |  |  | 2038 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
995 | Payroll Burden | 112245.88 | 118365.88 | 130913.02 |  |  |  | 2038 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
998 | Payroll Taxes | 21821.63 | 22992.11 | 24849.39 |  |  |  | 2038 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
999 | Sales | -1210378 | -1229419 | -1229419 |  |  |  | 2038 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
TOTAL

## Cost Breakdown
Cost Breakdown by Category
Direct cost composition by category from JDR cost codes
Category | Cost Codes | Actual $ | % of Direct Cost | % of Revenue | Source
Labor | 100,101,110,111,112,120,130,140,141,142,150 | 324824.75 |  |  | 2038 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
Material | 210,211,212,220,230,240,241,242,243 | 268693.54 |  |  | 2038 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
Subcon+Engineering+Permits+Other | 600,601,602,603,607 | 58032.43 |  |  | 2038 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
Payroll Burden | 995 | 130913.02 |  |  | 2038 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
Payroll Taxes | 998 | 24849.39 |  |  | 2038 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
TOTAL DIRECT COST |  |  | 100%

## Material
Material Purchases — AP Vendors
Material + subcontractor spend by vendor from JDR AP records
Vendor ID | Vendor Name | Total Spend | # Transactions | Category (inferred) | Source
2038RS | Rosen Supply Company, Inc. $2nd & John | 119372.62 | 58 | Plumbing / Supplies | 2038 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
1231KS | Keller Supply Company | 49490.05 | 26 | Plumbing / Supplies | 2038 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
1625FE | Franklin Engineering | 36872.75 | 9 | Engineering (601) | 2038 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
2038CS | Consolidated Supply Co. $2nd & John | 27539.6 | 15 | Plumbing / Supplies | 2038 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
1234CO | Capital One Credit Card | 10523.28 | 54 | Credit Card (mixed) | 2038 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
2038KS | Keller Supply Co. $2nd & John | 9390.68 | 11 | Plumbing / Supplies | 2038 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
1380RS | Rosen Supply Kirkland | 6021.82 | 23 | Plumbing / Supplies | 2038 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
1175FE | Ferguson Enterprises, Inc. #3007 | 5186.33 | 10 | Plumbing / Supplies | 2038 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
2713AR | Ahern Rentals | 4698.61 | 12 | Uncategorized | 2038 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
1609QC | Quality Concrete Products, Inc. $32 | 4653 | 1 | Uncategorized | 2038 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
1234CI | Citibank Credit Card | 2534 | 7 | Credit Card (mixed) | 2038 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
3181SC | Scan2Core, Inc. | 1897 | 2 | Uncategorized | 2038 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
3612MS | Mechanical Sales, Inc. | 1698 | 2 | Plumbing / Supplies | 2038 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
5560CH | California Hydronics Corp | 975 | 2 | Uncategorized | 2038 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
2132MH | Manor Hardware & Construction Supply | 611.52 | 2 | Plumbing / Supplies | 2038 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
1978FC | Fastenal Company | 302.9 | 1 | Uncategorized | 2038 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
1421RA | R.A. Brown Backflow Testing | 270 | 2 | Testing subcontractor | 2038 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
1799AW | AllWest Underground, Inc. | 199.06 | 1 | Uncategorized | 2038 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
5621HD | Core & Main LP $HD Supply Waterworks | 167.4 | 1 | Plumbing / Supplies | 2038 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
1234BA | Bank of America CC | 10.11 | 1 | Uncategorized | 2038 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
2037CS | Consolidated Supply Co. $University | 0 | 2 | Plumbing / Supplies | 2038 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
TOTAL

## Crew & Labor
Crew & Labor — Worker Roster
All 36 unique payroll workers. OWP RI: Thaddeus / Joe.
Worker ID | Worker Name | Total Hours | Gross Pay | Blended Wage ($/hr) | # Work Days | Source
WA35 | Waites, Thaddeus Z | 1272.5 | 51721 |  | 64 | 2038 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
CA77 | Castro Hernandez, Jose A | 1186 | 37394 |  | 33 | 2038 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
TA96 | Taylor, Evan R | 998 | 22232 |  | 33 | 2038 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
RE96 | Reyes Cruz, Denis A | 806 | 19344 |  | 22 | 2038 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
CR87 | Cruz Reyes, Jose | 728 | 16744 |  | 19 | 2038 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
CR79 | Cruz Guzman, Joel A | 704 | 15488 |  | 19 | 2038 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
MO56 | Montenegro, Carlos E | 686 | 16386 |  | 17 | 2038 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
BE45 | Belcher, Jacob T | 672 | 10752 |  | 18 | 2038 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
HO18 | Hoeg, Xavier A | 576 | 8640 |  | 18 | 2038 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
PO71 | Portillo, Kevin J | 528 | 9504 |  | 15 | 2038 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
VE42 | Velasquez Cruz, Denis M | 496 | 13392 |  | 13 | 2038 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
VE43 | Velasquez Cruz, Osman N | 488 | 9272 |  | 13 | 2038 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
HO14 | Holmes, Anthony R | 408 | 13872 |  | 12 | 2038 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
LI49 | Lima Romero, Melvin A | 357 | 11067 |  | 11 | 2038 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
RE91 | Reyes, Maria E | 260 | 4200 |  | 13 | 2038 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
GO51 | Gomez Reyes, Edith N | 252 | 5332 |  | 12 | 2038 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
BA70 | Barnhart, Joseph N | 234.5 | 10072 |  | 47 | 2038 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
RO10 | Rodriguez Arevalos, Christian | 224 | 4480 |  | 7 | 2038 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
HU06 | Hubbard, Robert W | 169 | 6367 |  | 17 | 2038 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
HE70 | Hernandez Gonzalez, Osbaldo | 168 | 3360 |  | 6 | 2038 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
DO56 | Donelson, Richard T | 161 | 8897.5 |  | 64 | 2038 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
SA54 | Sanders, Allen O | 149.5 | 6709 |  | 28 | 2038 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
EL33 | Eliassen, Cory H | 102 | 2362 |  | 9 | 2038 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
GE69 | Gerard, Jeffrey S | 99 | 4707 |  | 46 | 2038 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
FO55 | Fonseca Teruel, Eduardo | 72 | 1296 |  | 5 | 2038 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
MC09 | McCabe, Thomas C | 71 | 1252 |  | 4 | 2038 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
MA71 | Martinez Reyes, Juan C | 66 | 1320 |  | 5 | 2038 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
EG05 | Egbaou, Kossi D | 48 | 256 |  | 2 | 2038 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
KI55 | Kinssies, Jr, John E | 28 | 756 |  | 2 | 2038 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
LO58 | Lopez Reyes, Boris O | 16 | 288 |  | 2 | 2038 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
GE71 | Gerard, Mitchell J | 8 | 208 |  | 1 | 2038 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
SE64 | Sepulveda Gonzalez, Alfredo | 8 | 256 |  | 1 | 2038 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
CR77 | Cruz Gonzalez, Julio C | 8 | 152 |  | 1 | 2038 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
WI46 | Wilson, Garret A | 6 | 162 |  | 2 | 2038 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
HU04 | Hubbard, Dustin R | 3.5 | 73.5 |  | 1 | 2038 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
TR60 | Trower-Kelly, Fidel D | 3 | 48 |  | 1 | 2038 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
TOTAL

## Crew Analytics
Crew Analytics
Team-level labor productivity, concentration, wage dispersion
TEAM-LEVEL METRICS
Metric | Value | Notes | Source
Total Workers | 36 | Unique payroll IDs | 2038 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
Total Labor Hours | 11814.25 | Sum of labor codes | 2038 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
Total Gross Pay | 324824.75 | Sum of labor codes | 2038 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
Blended Gross Wage ($/hr) | 27.4943 | Labor$/Hrs (pre-burden) | Derived
Top Worker Hours Share | 10.77% | WA35 Waites, Thaddeus Z (1272 hrs) | Derived
Top 5 Workers Hours Share | 42.24% | Concentration metric | Derived
Highest Wage Rate ($/hr) | 55.264 | Single-worker blended | Derived
Lowest Wage Rate ($/hr) | 5.3333 | Single-worker blended | Derived
Avg Hours per Worker | 328.1736 | Includes short-tenure workers | Derived
Avg Project Days per Worker | 16.1944 | Mean days | Derived

## Productivity
Productivity Metrics
Normalized ratios. Per-unit from 80 units.
Metric | Value | Basis | Source / Note
Revenue per Labor Hour | 104.0624 | USD/hr
Profit per Labor Hour | 35.7285 | USD/hr
Labor Cost per Hour (blended) | 27.4943 | USD/hr | Pre-burden
Fully-Loaded Labor Rate ($/hr) | 40.6786 | USD/hr | Incl burden+taxes
Burden Multiplier | 1.4795 | x | Fully-loaded/blended
Rough-in Hours (code 120) | 7100 | hrs
Finish Hours (code 130) | 872.5 | hrs
Rough-in % of Total Hours | 60.1% | %
Gross Margin | 34.33% | %
Labor % of Revenue | 26.42% | %
Material % of Revenue | 21.86% | %
Direct Cost Ratio | 65.67% | % | All exp/Rev
Revenue per Unit (80) | 15367.7375 | USD | 80 units
Labor Hours per Unit | 147.6781 | hrs
Labor Cost per Unit | 4060.3094 | USD
Material Cost per Unit | 3358.6692 | USD
Direct Cost per Unit | 10091.4141 | USD
Rough-in Hours per Unit | 88.75 | hrs

## PO Commitments
PO Commitments
Inbound contract (GC → OWP). Outbound vendor commitments — see Material tab.
PO # | Date | Issuer | Type | Status | Description | Amount | Source
PRIME | 2017-02-17 | Compass Harbor Construction, LLC | Lump Sum Subcontract | Closed | 2nd & John plumbing (80 units) — per Div 22 | 1210378 | 2038-Compass Harbor Construction, LLC subcontract + Job Info sheet
CO-NET | — | Compass Harbor Construction, LLC | Change Orders (net, JDR-implied) | Executed | Net CO impact (Sage 999 rev - orig) | 19041 | 2038 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
TOTAL (contract + COs)

## Billing & SOV
Billing & Schedule of Values
29 invoices to Compass Harbor Construction, LLC. Retainage $59,720.95.
Invoice # | Date | Total Billed (signed) | Retainage (signed) | # Lines | Source
036870 | 04/27/17 | -25600 | 0 | 1 | 2038 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
036871 | 04/27/17 | 25600 | 0 | 1 | 2038 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
036874 | 05/19/17 | -25600 | 0 | 1 | 2038 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
036928 | 08/18/17 | -9400 | 0 | 2 | 2038 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
036931 | 08/18/17 | -39875 | 0 | 2 | 2038 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
036933 | 08/18/17 | 39875 | 0 | 2 | 2038 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
036934 | 08/18/17 | -39875 | -1993.75 | 2 | 2038 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
036945 | 09/20/17 | -26825 | -1341.25 | 2 | 2038 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
036967 | 10/20/17 | -15056 | -752.8 | 2 | 2038 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
036979 | 11/17/17 | -12900 | -645 | 1 | 2038 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
036988 | 12/14/17 | -13019 | -650.95 | 3 | 2038 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
037009 | 01/19/18 | -77100 | -3855 | 1 | 2038 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
037012 | 01/19/18 | 77100 | 3855 | 1 | 2038 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
037013 | 01/19/18 | -88900 | -4445 | 4 | 2038 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
037021 | 02/20/18 | -161225 | -8061.25 | 6 | 2038 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
037043 | 03/20/18 | -484695 | -24234.75 | 14 | 2038 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
037046 | 03/20/18 | 484695 | 24234.75 | 14 | 2038 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
037047 | 03/20/18 | -489503 | -24475.15 | 17 | 2038 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
037061 | 04/20/18 | -75000 | -3750 | 7 | 2038 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
037085 | 05/18/18 | -49650 | -2482.5 | 10 | 2038 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
037108 | 06/20/18 | -79670 | -3983.5 | 4 | 2038 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
037133 | 07/20/18 | -33707 | -1685.35 | 5 | 2038 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
037152 | 08/20/18 | -12567 | -628.35 | 4 | 2038 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
037180 | 09/19/18 | -39528 | -1976.4 | 7 | 2038 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
037203 | 10/19/18 | -31228 | -1561.4 | 5 | 2038 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
037229 | 11/16/18 | -24582 | -1229.1 | 6 | 2038 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
037301 | 03/20/19 | -1184 | 0 | 1 | 2038 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
037310 | 03/20/19 | 1184 | 0 | 1 | 2038 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
037311 | 03/20/19 | -1184 | -59.2 | 1 | 2038 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
TOTAL (signed)

## Insights
Insights & Observations
Narrative findings from JDR
# | Insight | Detail | Confidence | Source
1 | MARGIN PROFILE | Net profit $422,105.87 on $1,229,419.00 revenue = 34.3% gross margin. | Verified | 2038 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
2 | CONTRACT CHANGE | Original $1,210,378.00 → final $1,229,419.00 = $+19,041.00 net (+1.57%). | Verified | 2038 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
3 | LABOR PROFILE | Labor cost $324,824.75 (26.4% of rev) across 11,814 hrs and 36 workers. Blended wage $27.49/hr. | Verified | 2038 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
4 | VENDOR CONCENTRATION | Top 5 AP vendors: ~$243,798.30 (86% of AP). Top vendor: Rosen Supply Company, Inc. $2nd & John ($119,372.62). | Verified | 2038 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
5 | RETAINAGE | Retainage $59,720.95 = 4.9% of AR per JDR 04/03/2026 — legacy project, likely 7+ years stale. | Verified | 2038 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
6 | ROUGH-IN SHARE | Code 120 Roughin Labor = 7,100 hrs (60% of labor hours). | Verified | 2038 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
7 | TOP COST CODE | Largest actual cost: 120 Roughin Labor = $181,998.00 | Verified | 2038 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
8 | WORKER CONCENTRATION | Top worker Waites, Thaddeus Z = 1272 hrs (11% of total). | Verified | 2038 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
9 | INSURANCE | Wrap (OCIP) — OCIP wrap. | Verified | OWP Project List with Schedule - UPDATED 04-01-26.xlsx
10 | SCOPE CONTEXT | 2nd & John — 80-unit multifamily plumbing, Lower Queen Anne Seattle. | Verified | OWP Project List with Schedule - UPDATED 04-01-26.xlsx + JDR

## Benchmark KPIs
Benchmark KPIs
Normalized metrics for cross-project comparison
KPI | Data Name | Value | Category | Notes | Confidence | Source Document
Job Number | job_number | 2038 | Profile | OWP job ID | Verified | 2038 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
Job Name | job_name | 2nd & John | Profile |  | Verified | 2038 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
General Contractor | gc | Compass Harbor Construction, LLC | Profile |  | Verified | OWP Project List with Schedule - UPDATED 04-01-26.xlsx
Owner | owner | 2nd & John Apartments (Continental) | Profile |  | Verified | OWP Project List with Schedule - UPDATED 04-01-26.xlsx
Location | location | 200 2nd Ave West, Seattle, WA | Profile |  | Verified | OWP Project List with Schedule - UPDATED 04-01-26.xlsx
Project Type | project_type | Multifamily New Construction (80 units) | Profile |  | Verified | OWP Project List with Schedule - UPDATED 04-01-26.xlsx
Insurance Type | insurance | Wrap (OCIP) | Profile |  | Verified | OWP Project List with Schedule - UPDATED 04-01-26.xlsx
GC PM | gc_pm | Justin Anderson | Profile |  | Verified | OWP Project List with Schedule - UPDATED 04-01-26.xlsx
GC Sup | gc_sup | Kurt Weagant | Profile |  | Verified | OWP Project List with Schedule - UPDATED 04-01-26.xlsx
GC PE | gc_pe | Karl Clocksin | Profile |  | Verified | OWP Project List with Schedule - UPDATED 04-01-26.xlsx
Developer | developer | Continental | Profile |  | Verified | OWP Project List with Schedule - UPDATED 04-01-26.xlsx
OWP RI Foreman | owp_foreman | Thaddeus / Joe | Profile |  | Verified | Schedule
Work Start | start_date | 2017-02-17 | Profile |  | Verified | 2038 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
Work End | end_date | 2019 | Profile |  | Verified | 2038 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
Duration (months) | duration_months | 24 | Profile |  | Verified | Derived
Unit Count | unit_count | 80 | Profile |  | Verified | OWP Project List with Schedule - UPDATED 04-01-26.xlsx
Contract Original | contract_original | 1210378 | Financial |  | Verified | OWP Project List with Schedule - UPDATED 04-01-26.xlsx
Contract Final | contract_final | 1229419 | Financial |  | Verified | OWP Project List with Schedule - UPDATED 04-01-26.xlsx
Change Orders ($, implied) | co_implied | 19041 | Financial | Final - Original | Verified | 2038 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
CO % of Contract | co_pct | 1.573% | Financial |  | Verified | Derived
Revenue | revenue | 1229419 | Financial | AR total | Verified | 2038 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
Direct Cost | direct_cost | 807313.13 | Financial | JDR Expenses | Verified | 2038 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
Net Profit | net_profit | 422105.87 | Financial | Rev - Exp | Verified | 2038 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
Gross Margin | gross_margin | 34.33% | Financial |  | Verified | Derived
Retainage | retainage | 59720.95 | Financial | JDR AR retainage | Verified | 2038 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
Retainage % of Revenue | retainage_pct | 4.858% | Financial |  | Verified | Derived
Labor Cost | labor_cost | 324824.75 | Labor | Codes 100-151 | Verified | 2038 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
Material Cost | material_cost | 268693.54 | Material | Codes 210-245 | Verified | 2038 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
Overhead Cost | overhead_cost | 58032.43 | Financial | Codes 600-607 | Verified | 2038 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
Burden Cost | burden_cost | 130913.02 | Labor | Code 995 | Verified | 2038 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
Tax Cost | tax_cost | 24849.39 | Labor | Code 998 | Verified | 2038 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
Total Labor Hours | total_hours | 11814.25 | Labor | Sum labor codes | Verified | 2038 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
Total Workers | total_workers | 36 | Labor | Unique PR IDs | Verified | 2038 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
Blended Gross Wage | blended_wage | 27.4943 | Labor |  | Verified | Derived
Fully-Loaded Wage | loaded_wage | 40.6786 | Labor |  | Verified | Derived
Burden Multiplier | burden_mult | 1.4795 | Labor |  | Verified | Derived
Rough-in Hours | roughin_hours | 7100 | Labor | Code 120 | Verified | 2038 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
Finish Hours | finish_hours | 872.5 | Labor | Code 130 | Verified | 2038 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
Revenue per Hour | rev_per_hour | 104.0624 | Productivity |  | Verified | Derived
Profit per Hour | profit_per_hour | 35.7285 | Productivity |  | Verified | Derived
Revenue per Unit | rev_per_unit | 15367.7375 | Productivity |  | Verified | Derived
Direct Cost per Unit | cost_per_unit | 10091.4141 | Productivity |  | Verified | Derived
Hours per Unit | hours_per_unit | 147.6781 | Productivity |  | Verified | Derived
Labor % of Revenue | labor_pct | 26.42% | Cost Mix |  | Verified | Derived
Material % of Revenue | material_pct | 21.86% | Cost Mix |  | Verified | Derived
Total Vendors | total_vendors | 21 | Material |  | Verified | 2038 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
Total Invoices | total_invoices | 29 | Billing |  | Verified | 2038 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
Cost Codes Active | cost_codes | 29 | Structure |  | Verified | 2038 Job Detail Report.pdf (Sage Timberline, 04/03/2026)

## Vendors
Vendors — AP Summary
Vendor-level spend ranking
Rank | Vendor ID | Vendor Name | Total Spend | # Transactions | % of AP | Source
1 | 2038RS | Rosen Supply Company, Inc. $2nd & John | 119372.62 | 58 |  | 2038 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
2 | 1231KS | Keller Supply Company | 49490.05 | 26 |  | 2038 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
3 | 1625FE | Franklin Engineering | 36872.75 | 9 |  | 2038 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
4 | 2038CS | Consolidated Supply Co. $2nd & John | 27539.6 | 15 |  | 2038 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
5 | 1234CO | Capital One Credit Card | 10523.28 | 54 |  | 2038 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
6 | 2038KS | Keller Supply Co. $2nd & John | 9390.68 | 11 |  | 2038 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
7 | 1380RS | Rosen Supply Kirkland | 6021.82 | 23 |  | 2038 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
8 | 1175FE | Ferguson Enterprises, Inc. #3007 | 5186.33 | 10 |  | 2038 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
9 | 2713AR | Ahern Rentals | 4698.61 | 12 |  | 2038 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
10 | 1609QC | Quality Concrete Products, Inc. $32 | 4653 | 1 |  | 2038 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
11 | 1234CI | Citibank Credit Card | 2534 | 7 |  | 2038 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
12 | 3181SC | Scan2Core, Inc. | 1897 | 2 |  | 2038 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
13 | 3612MS | Mechanical Sales, Inc. | 1698 | 2 |  | 2038 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
14 | 5560CH | California Hydronics Corp | 975 | 2 |  | 2038 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
15 | 2132MH | Manor Hardware & Construction Supply | 611.52 | 2 |  | 2038 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
16 | 1978FC | Fastenal Company | 302.9 | 1 |  | 2038 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
17 | 1421RA | R.A. Brown Backflow Testing | 270 | 2 |  | 2038 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
18 | 1799AW | AllWest Underground, Inc. | 199.06 | 1 |  | 2038 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
19 | 5621HD | Core & Main LP $HD Supply Waterworks | 167.4 | 1 |  | 2038 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
20 | 1234BA | Bank of America CC | 10.11 | 1 |  | 2038 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
21 | 2037CS | Consolidated Supply Co. $University | 0 | 2 |  | 2038 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
TOTAL

## Change Log
Change Log — Master Register
Contract, CO net, retainage events — JDR only
Event ID | Type | Date | Subject | Originator | Cost Impact ($) | Status | Source
CONTRACT-ORIG | Contract | 2017-02-17 | Prime subcontract — Lump Sum $1,210,378.00 | Compass Harbor Construction, LLC | 1210378 | Executed | 2038-Compass Harbor Construction, LLC subcontract + Job Info sheet
CO-NET | Change Order (net) | — | Net JDR-implied COs $+19,041.00 | Compass Harbor Construction, LLC | 19041 | Executed | 2038 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
FIRST-INVOICE | Invoice | 01/19/18 | First billing (per JDR) | Sub (OWP) | 0 | Paid | 2038 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
LAST-INVOICE | Invoice | 12/14/17 | Last billing (per JDR) | Sub (OWP) | 0 | Paid | 2038 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
RETAINAGE-OPEN | Retainage | As of 04/03/2026 | Retainage $59,720.95 open | GC | 0 | Outstanding | 2038 Job Detail Report.pdf (Sage Timberline, 04/03/2026)

## Root Cause Analysis
Root Cause Analysis
Primary variance drivers by category
Category | Codes | Net $ Variance | Root Cause (inferred) | Notes
Contract Change | 999 (Sales) | 19041 | JDR-implied net CO impact | $1,210,378 → $1,229,419
Labor | 100,101,110,111,112,120,130,140,141,142,150 | 24274.75 | Labor variance vs revised budget | 36 workers
Material | 210,211,212,220,230,240,241,242,243 | -103488.46 | Material procurement variance | 21 vendors
Overhead | 600,601,602,603,607 | -3817.57 | Engineering/permits/subcon variance
Burden+Tax | 995+998 | 14404.42 | Payroll accrual tracking labor
TOTAL NET VARIANCE
RESPONSIBILITY ATTRIBUTION
Responsible Party | # Drivers | Net $ Impact | Notes
GC / Owner (scope changes) | 1 | 19041 | Aggregate JDR-implied COs
Sub (OWP) labor performance | 11 | 24274.75 | Hours + rate vs budget
Sub (OWP) material procurement | 9 | -103488.46 | 21 vendors
OWP burden accrual | 2 | 14404.42 | Payroll burden + tax
OWP overhead | 5 | -3817.57 | Engineering/permits/subcon

## Predictive Signals
Predictive Signals
Leading indicators from JDR
CURRENT-STATE SIGNALS
Indicator | Current Value | Benchmark | Status | Meaning
Contract Change % | 1.57% | ±10% | HEALTHY | +1.57% net
Labor % of Revenue | 26.42% | <30% | HEALTHY | 26.4%
GL Overhead % of Revenue | 16.8% | <5% | HEALTHY | 16.8%
Vendor Concentration (Top 5) | 86.33% | <95% | HEALTHY | Top 5 = 86% of AP
Retainage % | 4.858% | <10% | HEALTHY | 4.9%
Gross Margin | 34.33% | >30% | HEALTHY | 34.3%
Labor Hrs Total | 1181425% | varies | INFO | 11,814 hrs, 36 workers
Worker Concentration (top 1) | 10.77% | <25% | HEALTHY | 10.8% (Waites, Thaddeus Z)
Rough-in Labor Share | 60.1% | 40-65% | HEALTHY | 60%
Retainage Legacy | STALE | <90 days post-closeout | ELEVATED | $59,721 outstanding
FORECAST MODELS
Forecast | Current Estimate | Confidence | Driver | Model Note
Final margin (actual) | 34.33% | Actual | Job closed | 34.3%
Retainage collection | $59,721 open | Low | Legacy project | May require LOI/writedown
Unit-level economics | $15,368/unit rev, $5,276/unit profit | Verified | 80 units | Multifamily New Construction benchmark

## Metric Registry
Metric Registry — Cortex Data Catalog
Every metric with data_label, confidence, and source
# | Data Label | Human Label | Value | Unit | Source Tab | Confidence | Source Document(s)
1 | job_number | Job Number | 2038 | id | Benchmark KPIs | Verified | 2038 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
2 | job_name | Job Name | 2nd & John | text | Benchmark KPIs | Verified | 2038 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
3 | general_contractor | GC | Compass Harbor Construction, LLC | text | Benchmark KPIs | Verified | OWP Project List with Schedule - UPDATED 04-01-26.xlsx
4 | owner | Owner | 2nd & John Apartments (Continental) | text | Benchmark KPIs | Verified | OWP Project List with Schedule - UPDATED 04-01-26.xlsx
5 | location | Location | 200 2nd Ave West, Seattle, WA | text | Benchmark KPIs | Verified | OWP Project List with Schedule - UPDATED 04-01-26.xlsx
6 | project_type | Project Type | Multifamily New Construction (80 units) | text | Benchmark KPIs | Verified | OWP Project List with Schedule - UPDATED 04-01-26.xlsx
7 | insurance_type | Insurance | Wrap (OCIP) | text | Benchmark KPIs | Verified | OWP Project List with Schedule - UPDATED 04-01-26.xlsx
8 | gc_pm | GC PM | Justin Anderson | text | Benchmark KPIs | Verified | OWP Project List with Schedule - UPDATED 04-01-26.xlsx
9 | gc_sup | GC Sup | Kurt Weagant | text | Benchmark KPIs | Verified | OWP Project List with Schedule - UPDATED 04-01-26.xlsx
10 | gc_pe | GC PE | Karl Clocksin | text | Benchmark KPIs | Verified | OWP Project List with Schedule - UPDATED 04-01-26.xlsx
11 | developer | Developer | Continental | text | Benchmark KPIs | Verified | OWP Project List with Schedule - UPDATED 04-01-26.xlsx
12 | owp_foreman | OWP RI Foreman | Thaddeus / Joe | text | Benchmark KPIs | Verified | Schedule
13 | start_date | Work Start | 2017-02-17 | date | Benchmark KPIs | Verified | 2038 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
14 | end_date | Work End | 2019 | date | Benchmark KPIs | Verified | 2038 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
15 | duration_months | Duration | 24 | months | Benchmark KPIs | Verified | Derived
16 | unit_count | Unit Count | 80 | units | Benchmark KPIs | Verified | OWP Project List with Schedule - UPDATED 04-01-26.xlsx
17 | contract_original | Contract Orig | 1210378 | USD | Benchmark KPIs | Verified | OWP Project List with Schedule - UPDATED 04-01-26.xlsx
18 | contract_final | Contract Final | 1229419 | USD | Benchmark KPIs | Verified | OWP Project List with Schedule - UPDATED 04-01-26.xlsx
19 | change_orders_implied | CO (implied) | 19041 | USD | Benchmark KPIs | Verified | 2038 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
20 | co_pct | CO % of Contract | 1.573% | % | Benchmark KPIs | Verified | Derived
21 | revenue | Revenue | 1229419 | USD | Benchmark KPIs | Verified | 2038 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
22 | direct_cost | Direct Cost | 807313.13 | USD | Benchmark KPIs | Verified | 2038 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
23 | net_profit | Net Profit | 422105.87 | USD | Benchmark KPIs | Verified | 2038 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
24 | gross_margin | Gross Margin | 34.33% | % | Benchmark KPIs | Verified | Derived
25 | retainage | Retainage | 59720.95 | USD | Benchmark KPIs | Verified | 2038 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
26 | retainage_pct | Retainage % | 4.858% | % | Benchmark KPIs | Verified | Derived
27 | labor_cost | Labor Cost | 324824.75 | USD | Benchmark KPIs | Verified | 2038 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
28 | material_cost | Material Cost | 268693.54 | USD | Benchmark KPIs | Verified | 2038 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
29 | overhead_cost | Overhead Cost | 58032.43 | USD | Benchmark KPIs | Verified | 2038 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
30 | burden_cost | Burden | 130913.02 | USD | Benchmark KPIs | Verified | 2038 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
31 | tax_cost | Tax | 24849.39 | USD | Benchmark KPIs | Verified | 2038 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
32 | total_hours | Total Hours | 11814.25 | hours | Benchmark KPIs | Verified | 2038 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
33 | total_workers | Total Workers | 36 | count | Benchmark KPIs | Verified | 2038 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
34 | blended_wage | Blended Wage | 27.4943 | USD/hr | Benchmark KPIs | Verified | Derived
35 | loaded_wage | Loaded Wage | 40.6786 | USD/hr | Benchmark KPIs | Verified | Derived
36 | burden_mult | Burden Multiplier | 1.4795 | x | Benchmark KPIs | Verified | Derived
37 | roughin_hours | Rough-in Hours | 7100 | hours | Benchmark KPIs | Verified | 2038 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
38 | finish_hours | Finish Hours | 872.5 | hours | Benchmark KPIs | Verified | 2038 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
39 | rev_per_hour | Rev per Hour | 104.0624 | USD/hr | Benchmark KPIs | Verified | Derived
40 | profit_per_hour | Profit per Hour | 35.7285 | USD/hr | Benchmark KPIs | Verified | Derived
41 | rev_per_unit | Rev per Unit | 15367.7375 | USD | Benchmark KPIs | Verified | Derived
42 | cost_per_unit | Cost per Unit | 10091.4141 | USD | Benchmark KPIs | Verified | Derived
43 | hours_per_unit | Hours per Unit | 147.6781 | hours | Benchmark KPIs | Verified | Derived
44 | labor_pct | Labor % | 26.42% | % | Benchmark KPIs | Verified | Derived
45 | material_pct | Material % | 21.86% | % | Benchmark KPIs | Verified | Derived
46 | total_vendors | Total Vendors | 21 | count | Vendors | Verified | 2038 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
47 | total_invoices | Total Invoices | 29 | count | Billing & SOV | Verified | 2038 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
48 | top_worker_share | Top Worker Share | 10.77% | % | Crew Analytics | Verified | Derived
49 | top5_worker_share | Top 5 Worker Share | 42.24% | % | Crew Analytics | Verified | Derived
50 | cost_code_count | Cost Codes Active | 29 | count | Budget vs Actual | Verified | 2038 Job Detail Report.pdf (Sage Timberline, 04/03/2026)

## Reconciliation
Reconciliation
Cross-sheet formula checks
# | Check | Value A | Value B | Delta | Status | Tabs
1 | Revenue = Contract Final | 1229419 | 1229419 |  |  | 1↔8
2 | Expenses = Labor+Mat+OH+Burden+Tax | 807313.13 | 807313.13 |  |  | 1↔3
3 | Net Profit = Revenue - Expenses | 422105.87 | 422105.87 |  |  | 1↔Derived
4 | Sage 999 actual = -Revenue | 1229419 | 1229419 |  |  | 2↔1
5 | Total Hours = Worker hours sum | 11814.25 | 12062 |  |  | 5↔2
6 | Contract Final - Orig = CO implied | 19041 | 19041 |  |  | 11↔Derived
7 | Worker count | 36 | 36 |  |  | 5↔1
8 | Cost code count | 29 | 29 |  |  | 2↔16