## Overview
Job #2039 · Ravello Gas Piping
Cortex JCR v2 • Shelter Holdings (customer 2039SH) • Ravello (site TBD), WA • Owner: Ravello HOA / Shelter Holdings
PROJECT OVERVIEW
Project Job # | 2039 |  | 2039 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
Project Name (Sage) | Ravello Gas Piping |  | 2039 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
Project Description | Ravello Gas Piping — small-scope gas piping retrofit |  | OWP Project List with Schedule - UPDATED 04-01-26.xlsx + contract
General Contractor | Shelter Holdings |  | OWP Project List with Schedule - UPDATED 04-01-26.xlsx
Customer Code (Sage) | 2039SH |  | 2039 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
Owner / Developer | Ravello HOA / Shelter Holdings |  | OWP Project List with Schedule - UPDATED 04-01-26.xlsx
GC PM | Renay Luzama |  | OWP Project List with Schedule - UPDATED 04-01-26.xlsx
GC Superintendent | Bill Robinson |  | OWP Project List with Schedule - UPDATED 04-01-26.xlsx
GC PE | TBD |  | OWP Project List with Schedule - UPDATED 04-01-26.xlsx
OWP Rough-in Foreman | OWP RI |  | Schedule tab
Jobsite Location | Ravello (site TBD), WA |  | OWP Project List with Schedule - UPDATED 04-01-26.xlsx
Insurance | Not Wrap |  | OWP Project List with Schedule - UPDATED 04-01-26.xlsx
Fixture Schedule | 1-unit gas piping retrofit |  | Project scope
Contract Type | Lump Sum |  | 2039-Shelter Holdings subcontract + Job Info sheet
Unit Count | 1 |  | OWP Project List with Schedule - UPDATED 04-01-26.xlsx
Work Period | 2017-05-03 start → 2018 (13 months) |  | JDR PR/AR dates
CONTRACT VALUE |  | NET PROFIT | DIRECT COST | LABOR HOURS
54900 |  | 35329.29 | 19570.71 | 238
Original $54,900.00 + ($0.00) COs (0.00%) |  | 64.4% margin | 35.6% of revenue | 12 workers
SCOPE OF WORK
Full plumbing installation per Division 22: underground, garage, rough-in, finish, gas, water main, insulation.
1-unit gas piping retrofit at Ravello (site TBD), WA.
GC: Shelter Holdings (2039SH); Owner/Developer: Ravello HOA / Shelter Holdings.
Insurance: Not Wrap.
Project team: Renay Luzama (GC PM) · Bill Robinson (GC Sup) · TBD (GC PE) · OWP RI (OWP RI).
SOURCES
Canonical financial source: 2039 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
Job totals (JDR footer): Revenue $54,900.00 / Expenses $19,570.71 / Net $35,329.29 / Retainage $2,745.00
Source breakdown (derived): PR $7,228.50 · AP $5,566.61 · GL+other $6,775.60
Contract: Lump Sum $54,900.00 → $54,900.00
Change Orders (JDR-implied): $0.00 net
Project Team: Renay Luzama · Bill Robinson · TBD · Shelter Holdings · OWP RI
PROJECT TEAM (OWP Job Info)
Role | Status | Name / Firm
GC | Extracted | Shelter Holdings
GC PM | Extracted | Renay Luzama
GC Superintendent | Extracted | Bill Robinson
GC PE | N/A | N/A
Developer | Extracted | Shelter Holdings
Owner | Extracted | Ravello HOA
Architect | N/A | N/A
Structural | N/A | N/A
Acoustical | N/A | N/A
ADA Consultant | N/A | N/A
Interior Design | N/A | N/A
MEP Engineer | N/A | N/A
Insurance | Extracted | Not Wrap
OWP RI Foreman | Extracted | OWP RI

## Budget vs Actual
Budget vs Actual
All 14 cost codes from JDR. Contract $54,900 → $54,900.
Cost Code | Description | Original Budget | Revised Budget | Actual | Variance | % of Revised | Hours | Source
100 | Supervision | 1128 | 1128 | 159.5 |  |  | 3 | 2039 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
101 | Takeoff & Purchase Labor | 1128 | 1128 | 341 |  |  | 7 | 2039 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
112 | Canout Labor | 360 | 360 | 72 |  |  | 2 | 2039 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
140 | Gas Labor | 7360 | 7360 | 7599.75 |  |  | 226 | 2039 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
141 | Water Main/Insulation Lab | 0 | 0 | 0 |  |  |  | 2039 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
151 | T&M Labor | 0 | 0 | 178.25 |  |  |  | 2039 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
220 | Roughin Material | 0 | 0 | 30.2 |  |  |  | 2039 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
240 | Gas Material | 10650 | 10650 | 2667.14 |  |  |  | 2039 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
601 | Engineering/Plans | 5000 | 5000 | 3337.5 |  |  |  | 2039 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
603 | Permits & Licenses | 944 | 944 | 838.05 |  |  |  | 2039 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
607 | Other Expenses | 0 | 0 | 5 |  |  |  | 2039 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
995 | Payroll Burden | 4524.12 | 4524.12 | 3703.52 |  |  |  | 2039 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
998 | Payroll Taxes | 763.16 | 763.16 | 638.8 |  |  |  | 2039 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
999 | Sales | -54900 | -54900 | -54900 |  |  |  | 2039 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
TOTAL

## Cost Breakdown
Cost Breakdown by Category
Direct cost composition by category from JDR cost codes
Category | Cost Codes | Actual $ | % of Direct Cost | % of Revenue | Source
Labor | 100,101,112,140,141,151 | 8350.5 |  |  | 2039 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
Material | 220,240 | 2697.34 |  |  | 2039 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
Subcon+Engineering+Permits+Other | 601,603,607 | 4180.55 |  |  | 2039 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
Payroll Burden | 995 | 3703.52 |  |  | 2039 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
Payroll Taxes | 998 | 638.8 |  |  | 2039 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
TOTAL DIRECT COST |  |  | 100%

## Material
Material Purchases — AP Vendors
Material + subcontractor spend by vendor from JDR AP records
Vendor ID | Vendor Name | Total Spend | # Transactions | Category (inferred) | Source
1625FE | Franklin Engineering | 3337.5 | 2 | Engineering (601) | 2039 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
2039RS | Rosen Supply Company, Inc. $Ravello | 1370.62 | 9 | Plumbing / Supplies | 2039 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
1234CO | Capital One Credit Card | 843.05 | 3 | Credit Card (mixed) | 2039 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
2039KS | Keller Supply Co. $Ravello | 15.44 | 1 | Plumbing / Supplies | 2039 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
TOTAL

## Crew & Labor
Crew & Labor — Worker Roster
All 12 unique payroll workers. OWP RI: OWP RI.
Worker ID | Worker Name | Total Hours | Gross Pay | Blended Wage ($/hr) | # Work Days | Source
RE18 | Reed, Reuben H | 92 | 2900 |  | 14 | 2039 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
GA70 | Garcia, Jordan X | 75 | 1675 |  | 6 | 2039 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
ME52 | Mendoza, Edgar E | 31.5 | 630 |  | 2 | 2039 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
HO18 | Hoeg, Xavier A | 13 | 195 |  | 2 | 2039 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
HU06 | Hubbard, Robert W | 11 | 508 |  | 5 | 2039 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
EI74 | Eisenhauer, Tommy J | 8 | 168 |  | 1 | 2039 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
GE70 | Gerard, Jordan E | 8 | 216 |  | 1 | 2039 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
GE71 | Gerard, Mitchell J | 8 | 256 |  | 1 | 2039 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
GE69 | Gerard, Jeffrey S | 6 | 288 |  | 3 | 2039 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
DO56 | Donelson, Richard T | 4 | 212.5 |  | 4 | 2039 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
EL33 | Eliassen, Cory H | 4 | 92 |  | 1 | 2039 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
BA70 | Barnhart, Joseph N | 2 | 88 |  | 1 | 2039 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
TOTAL

## Crew Analytics
Crew Analytics
Team-level labor productivity, concentration, wage dispersion
TEAM-LEVEL METRICS
Metric | Value | Notes | Source
Total Workers | 12 | Unique payroll IDs | 2039 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
Total Labor Hours | 238 | Sum of labor codes | 2039 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
Total Gross Pay | 8350.5 | Sum of labor codes | 2039 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
Blended Gross Wage ($/hr) | 35.0861 | Labor$/Hrs (pre-burden) | Derived
Top Worker Hours Share | 38.66% | RE18 Reed, Reuben H (92 hrs) | Derived
Top 5 Workers Hours Share | 93.49% | Concentration metric | Derived
Highest Wage Rate ($/hr) | 53.125 | Single-worker blended | Derived
Lowest Wage Rate ($/hr) | 15 | Single-worker blended | Derived
Avg Hours per Worker | 19.8333 | Includes short-tenure workers | Derived
Avg Project Days per Worker | 3.4167 | Mean days | Derived

## Productivity
Productivity Metrics
Normalized ratios. Per-unit from 1 units.
Metric | Value | Basis | Source / Note
Revenue per Labor Hour | 230.6723 | USD/hr
Profit per Labor Hour | 148.4424 | USD/hr
Labor Cost per Hour (blended) | 35.0861 | USD/hr | Pre-burden
Fully-Loaded Labor Rate ($/hr) | 53.3312 | USD/hr | Incl burden+taxes
Burden Multiplier | 1.52 | x | Fully-loaded/blended
Rough-in Hours (code 120) | 0 | hrs
Finish Hours (code 130) | 0 | hrs
Rough-in % of Total Hours | 0% | %
Gross Margin | 64.35% | %
Labor % of Revenue | 15.21% | %
Material % of Revenue | 4.913% | %
Direct Cost Ratio | 35.65% | % | All exp/Rev
Revenue per Unit (1) | 54900 | USD | 1 units
Labor Hours per Unit | 238 | hrs
Labor Cost per Unit | 8350.5 | USD
Material Cost per Unit | 2697.34 | USD
Direct Cost per Unit | 19570.71 | USD
Rough-in Hours per Unit | 0 | hrs

## PO Commitments
PO Commitments
Inbound contract (GC → OWP). Outbound vendor commitments — see Material tab.
PO # | Date | Issuer | Type | Status | Description | Amount | Source
PRIME | 2017-05-03 | Shelter Holdings | Lump Sum Subcontract | Closed | Ravello Gas Piping plumbing (1 units) — per Div 22 | 54900 | 2039-Shelter Holdings subcontract + Job Info sheet
CO-NET | — | Shelter Holdings | Change Orders (net, JDR-implied) | Executed | Net CO impact (Sage 999 rev - orig) | 0 | 2039 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
TOTAL (contract + COs)

## Billing & SOV
Billing & Schedule of Values
5 invoices to Shelter Holdings. Retainage $2,745.00.
Invoice # | Date | Total Billed (signed) | Retainage (signed) | # Lines | Source
036924 | 07/24/17 | -9000 | -450 | 3 | 2039 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
036951 | 09/20/17 | -11000 | -550 | 1 | 2039 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
036980 | 11/17/17 | -24120 | -1206 | 1 | 2039 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
037026 | 02/20/18 | -8780 | -439 | 1 | 2039 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
037082 | 05/18/18 | -2000 | -100 | 1 | 2039 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
TOTAL (signed)

## Insights
Insights & Observations
Narrative findings from JDR
# | Insight | Detail | Confidence | Source
1 | MARGIN PROFILE | Net profit $35,329.29 on $54,900.00 revenue = 64.4% gross margin. | Verified | 2039 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
2 | CONTRACT CHANGE | Original $54,900.00 → final $54,900.00 = $+0.00 net (+0.00%). | Verified | 2039 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
3 | LABOR PROFILE | Labor cost $8,350.50 (15.2% of rev) across 238 hrs and 12 workers. Blended wage $35.09/hr. | Verified | 2039 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
4 | VENDOR CONCENTRATION | Top 5 AP vendors: ~$5,566.61 (100% of AP). Top vendor: Franklin Engineering ($3,337.50). | Verified | 2039 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
5 | RETAINAGE | Retainage $2,745.00 = 5.0% of AR per JDR 04/03/2026 — legacy project, likely 7+ years stale. | Verified | 2039 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
6 | ROUGH-IN SHARE | Code 120 Roughin Labor = 0 hrs (0% of labor hours). | Verified | 2039 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
7 | TOP COST CODE | Largest actual cost: 140 Gas Labor = $7,599.75 | Verified | 2039 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
8 | WORKER CONCENTRATION | Top worker Reed, Reuben H = 92 hrs (39% of total). | Verified | 2039 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
9 | INSURANCE | Not Wrap — OCIP wrap. | Verified | OWP Project List with Schedule - UPDATED 04-01-26.xlsx
10 | SCOPE CONTEXT | Ravello Gas Piping — small-scope gas piping retrofit. | Verified | OWP Project List with Schedule - UPDATED 04-01-26.xlsx + JDR

## Benchmark KPIs
Benchmark KPIs
Normalized metrics for cross-project comparison
KPI | Data Name | Value | Category | Notes | Confidence | Source Document
Job Number | job_number | 2039 | Profile | OWP job ID | Verified | 2039 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
Job Name | job_name | Ravello Gas Piping | Profile |  | Verified | 2039 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
General Contractor | gc | Shelter Holdings | Profile |  | Verified | OWP Project List with Schedule - UPDATED 04-01-26.xlsx
Owner | owner | Ravello HOA / Shelter Holdings | Profile |  | Verified | OWP Project List with Schedule - UPDATED 04-01-26.xlsx
Location | location | Ravello (site TBD), WA | Profile |  | Verified | OWP Project List with Schedule - UPDATED 04-01-26.xlsx
Project Type | project_type | Gas Piping Retrofit (1 units) | Profile |  | Verified | OWP Project List with Schedule - UPDATED 04-01-26.xlsx
Insurance Type | insurance | Not Wrap | Profile |  | Verified | OWP Project List with Schedule - UPDATED 04-01-26.xlsx
GC PM | gc_pm | Renay Luzama | Profile |  | Verified | OWP Project List with Schedule - UPDATED 04-01-26.xlsx
GC Sup | gc_sup | Bill Robinson | Profile |  | Verified | OWP Project List with Schedule - UPDATED 04-01-26.xlsx
GC PE | gc_pe | TBD | Profile |  | Verified | OWP Project List with Schedule - UPDATED 04-01-26.xlsx
Developer | developer | Shelter Holdings | Profile |  | Verified | OWP Project List with Schedule - UPDATED 04-01-26.xlsx
OWP RI Foreman | owp_foreman | OWP RI | Profile |  | Verified | Schedule
Work Start | start_date | 2017-05-03 | Profile |  | Verified | 2039 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
Work End | end_date | 2018 | Profile |  | Verified | 2039 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
Duration (months) | duration_months | 13 | Profile |  | Verified | Derived
Unit Count | unit_count | 1 | Profile |  | Verified | OWP Project List with Schedule - UPDATED 04-01-26.xlsx
Contract Original | contract_original | 54900 | Financial |  | Verified | OWP Project List with Schedule - UPDATED 04-01-26.xlsx
Contract Final | contract_final | 54900 | Financial |  | Verified | OWP Project List with Schedule - UPDATED 04-01-26.xlsx
Change Orders ($, implied) | co_implied | 0 | Financial | Final - Original | Verified | 2039 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
CO % of Contract | co_pct | 0% | Financial |  | Verified | Derived
Revenue | revenue | 54900 | Financial | AR total | Verified | 2039 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
Direct Cost | direct_cost | 19570.71 | Financial | JDR Expenses | Verified | 2039 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
Net Profit | net_profit | 35329.29 | Financial | Rev - Exp | Verified | 2039 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
Gross Margin | gross_margin | 64.35% | Financial |  | Verified | Derived
Retainage | retainage | 2745 | Financial | JDR AR retainage | Verified | 2039 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
Retainage % of Revenue | retainage_pct | 5% | Financial |  | Verified | Derived
Labor Cost | labor_cost | 8350.5 | Labor | Codes 100-151 | Verified | 2039 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
Material Cost | material_cost | 2697.34 | Material | Codes 210-245 | Verified | 2039 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
Overhead Cost | overhead_cost | 4180.55 | Financial | Codes 600-607 | Verified | 2039 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
Burden Cost | burden_cost | 3703.52 | Labor | Code 995 | Verified | 2039 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
Tax Cost | tax_cost | 638.8 | Labor | Code 998 | Verified | 2039 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
Total Labor Hours | total_hours | 238 | Labor | Sum labor codes | Verified | 2039 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
Total Workers | total_workers | 12 | Labor | Unique PR IDs | Verified | 2039 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
Blended Gross Wage | blended_wage | 35.0861 | Labor |  | Verified | Derived
Fully-Loaded Wage | loaded_wage | 53.3312 | Labor |  | Verified | Derived
Burden Multiplier | burden_mult | 1.52 | Labor |  | Verified | Derived
Rough-in Hours | roughin_hours | 0 | Labor | Code 120 | Verified | 2039 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
Finish Hours | finish_hours | 0 | Labor | Code 130 | Verified | 2039 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
Revenue per Hour | rev_per_hour | 230.6723 | Productivity |  | Verified | Derived
Profit per Hour | profit_per_hour | 148.4424 | Productivity |  | Verified | Derived
Revenue per Unit | rev_per_unit | 54900 | Productivity |  | Verified | Derived
Direct Cost per Unit | cost_per_unit | 19570.71 | Productivity |  | Verified | Derived
Hours per Unit | hours_per_unit | 238 | Productivity |  | Verified | Derived
Labor % of Revenue | labor_pct | 15.21% | Cost Mix |  | Verified | Derived
Material % of Revenue | material_pct | 4.913% | Cost Mix |  | Verified | Derived
Total Vendors | total_vendors | 4 | Material |  | Verified | 2039 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
Total Invoices | total_invoices | 5 | Billing |  | Verified | 2039 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
Cost Codes Active | cost_codes | 14 | Structure |  | Verified | 2039 Job Detail Report.pdf (Sage Timberline, 04/03/2026)

## Vendors
Vendors — AP Summary
Vendor-level spend ranking
Rank | Vendor ID | Vendor Name | Total Spend | # Transactions | % of AP | Source
1 | 1625FE | Franklin Engineering | 3337.5 | 2 |  | 2039 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
2 | 2039RS | Rosen Supply Company, Inc. $Ravello | 1370.62 | 9 |  | 2039 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
3 | 1234CO | Capital One Credit Card | 843.05 | 3 |  | 2039 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
4 | 2039KS | Keller Supply Co. $Ravello | 15.44 | 1 |  | 2039 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
TOTAL

## Change Log
Change Log — Master Register
Contract, CO net, retainage events — JDR only
Event ID | Type | Date | Subject | Originator | Cost Impact ($) | Status | Source
CONTRACT-ORIG | Contract | 2017-05-03 | Prime subcontract — Lump Sum $54,900.00 | Shelter Holdings | 54900 | Executed | 2039-Shelter Holdings subcontract + Job Info sheet
CO-NET | Change Order (net) | — | Net JDR-implied COs $+0.00 | Shelter Holdings | 0 | Executed | 2039 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
FIRST-INVOICE | Invoice | 02/20/18 | First billing (per JDR) | Sub (OWP) | 0 | Paid | 2039 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
LAST-INVOICE | Invoice | 11/17/17 | Last billing (per JDR) | Sub (OWP) | 0 | Paid | 2039 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
RETAINAGE-OPEN | Retainage | As of 04/03/2026 | Retainage $2,745.00 open | GC | 0 | Outstanding | 2039 Job Detail Report.pdf (Sage Timberline, 04/03/2026)

## Root Cause Analysis
Root Cause Analysis
Primary variance drivers by category
Category | Codes | Net $ Variance | Root Cause (inferred) | Notes
Contract Change | 999 (Sales) | 0 | JDR-implied net CO impact | $54,900 → $54,900
Labor | 100,101,112,140,141,151 | -1625.5 | Labor variance vs revised budget | 12 workers
Material | 220,240 | -7952.66 | Material procurement variance | 4 vendors
Overhead | 601,603,607 | -1763.45 | Engineering/permits/subcon variance
Burden+Tax | 995+998 | -944.96 | Payroll accrual tracking labor
TOTAL NET VARIANCE
RESPONSIBILITY ATTRIBUTION
Responsible Party | # Drivers | Net $ Impact | Notes
GC / Owner (scope changes) | 1 | 0 | Aggregate JDR-implied COs
Sub (OWP) labor performance | 6 | -1625.5 | Hours + rate vs budget
Sub (OWP) material procurement | 2 | -7952.66 | 4 vendors
OWP burden accrual | 2 | -944.96 | Payroll burden + tax
OWP overhead | 3 | -1763.45 | Engineering/permits/subcon

## Predictive Signals
Predictive Signals
Leading indicators from JDR
CURRENT-STATE SIGNALS
Indicator | Current Value | Benchmark | Status | Meaning
Contract Change % | 0.00% | ±10% | HEALTHY | +0.00% net
Labor % of Revenue | 15.21% | <30% | HEALTHY | 15.2%
GL Overhead % of Revenue | 12.34% | <5% | HEALTHY | 12.3%
Vendor Concentration (Top 5) | 100% | <95% | HEALTHY | Top 5 = 100% of AP
Retainage % | 5% | <10% | HEALTHY | 5.0%
Gross Margin | 64.35% | >30% | HEALTHY | 64.4%
Labor Hrs Total | 23800% | varies | INFO | 238 hrs, 12 workers
Worker Concentration (top 1) | 38.66% | <25% | ELEVATED | 38.7% (Reed, Reuben H)
Rough-in Labor Share | 0% | 40-65% | INFO | 0%
Retainage Legacy | STALE | <90 days post-closeout | ELEVATED | $2,745 outstanding
FORECAST MODELS
Forecast | Current Estimate | Confidence | Driver | Model Note
Final margin (actual) | 64.35% | Actual | Job closed | 64.4%
Retainage collection | $2,745 open | Low | Legacy project | May require LOI/writedown
Unit-level economics | $54,900/unit rev, $35,329/unit profit | Verified | 1 units | Gas Piping Retrofit benchmark

## Metric Registry
Metric Registry — Cortex Data Catalog
Every metric with data_label, confidence, and source
# | Data Label | Human Label | Value | Unit | Source Tab | Confidence | Source Document(s)
1 | job_number | Job Number | 2039 | id | Benchmark KPIs | Verified | 2039 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
2 | job_name | Job Name | Ravello Gas Piping | text | Benchmark KPIs | Verified | 2039 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
3 | general_contractor | GC | Shelter Holdings | text | Benchmark KPIs | Verified | OWP Project List with Schedule - UPDATED 04-01-26.xlsx
4 | owner | Owner | Ravello HOA / Shelter Holdings | text | Benchmark KPIs | Verified | OWP Project List with Schedule - UPDATED 04-01-26.xlsx
5 | location | Location | Ravello (site TBD), WA | text | Benchmark KPIs | Verified | OWP Project List with Schedule - UPDATED 04-01-26.xlsx
6 | project_type | Project Type | Gas Piping Retrofit (1 units) | text | Benchmark KPIs | Verified | OWP Project List with Schedule - UPDATED 04-01-26.xlsx
7 | insurance_type | Insurance | Not Wrap | text | Benchmark KPIs | Verified | OWP Project List with Schedule - UPDATED 04-01-26.xlsx
8 | gc_pm | GC PM | Renay Luzama | text | Benchmark KPIs | Verified | OWP Project List with Schedule - UPDATED 04-01-26.xlsx
9 | gc_sup | GC Sup | Bill Robinson | text | Benchmark KPIs | Verified | OWP Project List with Schedule - UPDATED 04-01-26.xlsx
10 | gc_pe | GC PE | TBD | text | Benchmark KPIs | Verified | OWP Project List with Schedule - UPDATED 04-01-26.xlsx
11 | developer | Developer | Shelter Holdings | text | Benchmark KPIs | Verified | OWP Project List with Schedule - UPDATED 04-01-26.xlsx
12 | owp_foreman | OWP RI Foreman | OWP RI | text | Benchmark KPIs | Verified | Schedule
13 | start_date | Work Start | 2017-05-03 | date | Benchmark KPIs | Verified | 2039 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
14 | end_date | Work End | 2018 | date | Benchmark KPIs | Verified | 2039 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
15 | duration_months | Duration | 13 | months | Benchmark KPIs | Verified | Derived
16 | unit_count | Unit Count | 1 | units | Benchmark KPIs | Verified | OWP Project List with Schedule - UPDATED 04-01-26.xlsx
17 | contract_original | Contract Orig | 54900 | USD | Benchmark KPIs | Verified | OWP Project List with Schedule - UPDATED 04-01-26.xlsx
18 | contract_final | Contract Final | 54900 | USD | Benchmark KPIs | Verified | OWP Project List with Schedule - UPDATED 04-01-26.xlsx
19 | change_orders_implied | CO (implied) | 0 | USD | Benchmark KPIs | Verified | 2039 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
20 | co_pct | CO % of Contract | 0% | % | Benchmark KPIs | Verified | Derived
21 | revenue | Revenue | 54900 | USD | Benchmark KPIs | Verified | 2039 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
22 | direct_cost | Direct Cost | 19570.71 | USD | Benchmark KPIs | Verified | 2039 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
23 | net_profit | Net Profit | 35329.29 | USD | Benchmark KPIs | Verified | 2039 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
24 | gross_margin | Gross Margin | 64.35% | % | Benchmark KPIs | Verified | Derived
25 | retainage | Retainage | 2745 | USD | Benchmark KPIs | Verified | 2039 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
26 | retainage_pct | Retainage % | 5% | % | Benchmark KPIs | Verified | Derived
27 | labor_cost | Labor Cost | 8350.5 | USD | Benchmark KPIs | Verified | 2039 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
28 | material_cost | Material Cost | 2697.34 | USD | Benchmark KPIs | Verified | 2039 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
29 | overhead_cost | Overhead Cost | 4180.55 | USD | Benchmark KPIs | Verified | 2039 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
30 | burden_cost | Burden | 3703.52 | USD | Benchmark KPIs | Verified | 2039 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
31 | tax_cost | Tax | 638.8 | USD | Benchmark KPIs | Verified | 2039 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
32 | total_hours | Total Hours | 238 | hours | Benchmark KPIs | Verified | 2039 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
33 | total_workers | Total Workers | 12 | count | Benchmark KPIs | Verified | 2039 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
34 | blended_wage | Blended Wage | 35.0861 | USD/hr | Benchmark KPIs | Verified | Derived
35 | loaded_wage | Loaded Wage | 53.3312 | USD/hr | Benchmark KPIs | Verified | Derived
36 | burden_mult | Burden Multiplier | 1.52 | x | Benchmark KPIs | Verified | Derived
37 | roughin_hours | Rough-in Hours | 0 | hours | Benchmark KPIs | Verified | 2039 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
38 | finish_hours | Finish Hours | 0 | hours | Benchmark KPIs | Verified | 2039 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
39 | rev_per_hour | Rev per Hour | 230.6723 | USD/hr | Benchmark KPIs | Verified | Derived
40 | profit_per_hour | Profit per Hour | 148.4424 | USD/hr | Benchmark KPIs | Verified | Derived
41 | rev_per_unit | Rev per Unit | 54900 | USD | Benchmark KPIs | Verified | Derived
42 | cost_per_unit | Cost per Unit | 19570.71 | USD | Benchmark KPIs | Verified | Derived
43 | hours_per_unit | Hours per Unit | 238 | hours | Benchmark KPIs | Verified | Derived
44 | labor_pct | Labor % | 15.21% | % | Benchmark KPIs | Verified | Derived
45 | material_pct | Material % | 4.913% | % | Benchmark KPIs | Verified | Derived
46 | total_vendors | Total Vendors | 4 | count | Vendors | Verified | 2039 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
47 | total_invoices | Total Invoices | 5 | count | Billing & SOV | Verified | 2039 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
48 | top_worker_share | Top Worker Share | 38.66% | % | Crew Analytics | Verified | Derived
49 | top5_worker_share | Top 5 Worker Share | 93.49% | % | Crew Analytics | Verified | Derived
50 | cost_code_count | Cost Codes Active | 14 | count | Budget vs Actual | Verified | 2039 Job Detail Report.pdf (Sage Timberline, 04/03/2026)

## Reconciliation
Reconciliation
Cross-sheet formula checks
# | Check | Value A | Value B | Delta | Status | Tabs
1 | Revenue = Contract Final | 54900 | 54900 |  |  | 1↔8
2 | Expenses = Labor+Mat+OH+Burden+Tax | 19570.71 | 19570.71 |  |  | 1↔3
3 | Net Profit = Revenue - Expenses | 35329.29 | 35329.29 |  |  | 1↔Derived
4 | Sage 999 actual = -Revenue | 54900 | 54900 |  |  | 2↔1
5 | Total Hours = Worker hours sum | 238 | 262.5 |  |  | 5↔2
6 | Contract Final - Orig = CO implied | 0 | 0 |  |  | 11↔Derived
7 | Worker count | 12 | 12 |  |  | 5↔1
8 | Cost code count | 14 | 14 |  |  | 2↔16