## Overview
Job #2040 · Roosevelt 65th (Brooklyn 65)
Cortex JCR v2 • Blueprint Capital (customer 2040BP) • 1222 NE 65th Street, Seattle, WA 98115 • Owner: Brooklyn 65 LLC (Blueprint)
PROJECT OVERVIEW
Project Job # | 2040 |  | 2040 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
Project Name (Sage) | Roosevelt 65th (Brooklyn 65) |  | 2040 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
Project Description | Brooklyn 65 (Roosevelt 65th) — 55-unit multifamily plumbing, NE Seattle |  | OWP Project List with Schedule - UPDATED 04-01-26.xlsx + contract
General Contractor | Blueprint Capital |  | OWP Project List with Schedule - UPDATED 04-01-26.xlsx
Customer Code (Sage) | 2040BP |  | 2040 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
Owner / Developer | Brooklyn 65 LLC (Blueprint) |  | OWP Project List with Schedule - UPDATED 04-01-26.xlsx
GC PM | Andrew Withnell |  | OWP Project List with Schedule - UPDATED 04-01-26.xlsx
GC Superintendent | Mike Sanderson |  | OWP Project List with Schedule - UPDATED 04-01-26.xlsx
GC PE | Kyle Stenson |  | OWP Project List with Schedule - UPDATED 04-01-26.xlsx
OWP Rough-in Foreman | Garrett / Joe |  | Schedule tab
Jobsite Location | 1222 NE 65th Street, Seattle, WA 98115 |  | OWP Project List with Schedule - UPDATED 04-01-26.xlsx
Insurance | Not Wrap |  | OWP Project List with Schedule - UPDATED 04-01-26.xlsx
Fixture Schedule | 55-unit multifamily new construction |  | Project scope
Contract Type | Lump Sum |  | 2040-Blueprint Capital subcontract + Job Info sheet
Unit Count | 55 |  | OWP Project List with Schedule - UPDATED 04-01-26.xlsx
Work Period | 2017-03-01 start → 2019 (22 months) |  | JDR PR/AR dates
CONTRACT VALUE |  | NET PROFIT | DIRECT COST | LABOR HOURS
624171 |  | 219653.24 | 404517.76 | 5454
Original $604,000.00 + ($20,171.00) COs (3.34%) |  | 35.2% margin | 64.8% of revenue | 32 workers
SCOPE OF WORK
Full plumbing installation per Division 22: underground, garage, rough-in, finish, gas, water main, insulation.
55-unit multifamily new construction at 1222 NE 65th Street, Seattle, WA 98115.
GC: Blueprint Capital (2040BP); Owner/Developer: Brooklyn 65 LLC (Blueprint).
Insurance: Not Wrap.
Project team: Andrew Withnell (GC PM) · Mike Sanderson (GC Sup) · Kyle Stenson (GC PE) · Garrett / Joe (OWP RI).
SOURCES
Canonical financial source: 2040 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
Job totals (JDR footer): Revenue $624,171.00 / Expenses $404,517.76 / Net $219,653.24 / Retainage $0.00
Source breakdown (derived): PR $139,635.75 · AP $154,865.96 · GL+other $110,016.05
Contract: Lump Sum $604,000.00 → $624,171.00
Change Orders (JDR-implied): $20,171.00 net
Project Team: Andrew Withnell · Mike Sanderson · Kyle Stenson · Blueprint · Garrett / Joe
PROJECT TEAM (OWP Job Info)
Role | Status | Name / Firm
GC | Extracted | Blueprint Capital
GC PM | Extracted | Andrew Withnell
GC Superintendent | Extracted | Mike Sanderson
GC PE | Extracted | Kyle Stenson
Developer | Extracted | Blueprint
Owner | Extracted | Brooklyn 65 LLC
Architect | N/A | N/A
Structural | N/A | N/A
Acoustical | N/A | N/A
ADA Consultant | N/A | N/A
Interior Design | N/A | N/A
MEP Engineer | N/A | N/A
Insurance | Extracted | Not Wrap
OWP RI Foreman | Extracted | Garrett / Joe

## Budget vs Actual
Budget vs Actual
All 27 cost codes from JDR. Contract $604,000 → $624,171.
Cost Code | Description | Original Budget | Revised Budget | Actual | Variance | % of Revised | Hours | Source
100 | Supervision | 5225 | 5225 | 2160 |  |  | 44 | 2040 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
101 | Takeoff & Purchase Labor | 8250 | 8250 | 5076.5 |  |  | 96 | 2040 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
110 | Underground Labor | 5515 | 5515 | 2443 |  |  | 80 | 2040 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
111 | Garage Labor | 0 | 850 | 8649.5 |  |  | 274 | 2040 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
112 | Canout Labor | 3150 | 3300 | 3009.5 |  |  | 87 | 2040 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
120 | Roughin Labor | 74440 | 75910 | 86788 |  |  | 3429.75 | 2040 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
130 | Finish Labor | 16860 | 16920 | 13510.25 |  |  | 531.75 | 2040 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
140 | Gas Labor | 7500 | 7500 | 2784 |  |  | 83 | 2040 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
141 | Water Main/Insulation Lab | 21435 | 21435 | 15056.5 |  |  | 635.5 | 2040 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
142 | Mech Room Labor | 12060 | 12060 | 7174 |  |  | 192 | 2040 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
150 | Warranty Labor | 0 | 0 | 48 |  |  | 1 | 2040 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
210 | Underground Material | 11800 | 11800 | 2062.26 |  |  |  | 2040 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
211 | Garage Material | 0 | 0 | 1763.95 |  |  |  | 2040 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
212 | Canout Material | 3150 | 3605 | 2644.13 |  |  |  | 2040 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
220 | Roughin Material | 32500 | 32895 | 24915.98 |  |  |  | 2040 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
230 | Finish Material | 68220 | 79636 | 88855.74 |  |  |  | 2040 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
240 | Gas Material | 6750 | 6750 | 1504.45 |  |  |  | 2040 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
241 | Water Main/Insulation Mat | 22530 | 22530 | 17052.68 |  |  |  | 2040 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
242 | Mech Room Material | 28770 | 28770 | 15297.78 |  |  |  | 2040 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
243 | Condensation Drains Mat | 0 | 0 | 7.2 |  |  |  | 2040 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
600 | Subcontractor | 500 | 650 | 2304 |  |  |  | 2040 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
601 | Engineering/Plans | 16000 | 16000 | 15976 |  |  |  | 2040 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
603 | Permits & Licenses | 4385 | 4385 | 3518 |  |  |  | 2040 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
607 | Other Expenses | 7000 | 7000 | 5632.2 |  |  |  | 2040 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
995 | Payroll Burden | 70036.27 | 71174.77 | 65061.2 |  |  |  | 2040 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
998 | Payroll Taxes | 11814.28 | 12007.83 | 11222.94 |  |  |  | 2040 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
999 | Sales | -604000 | -624171 | -624171 |  |  |  | 2040 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
TOTAL

## Cost Breakdown
Cost Breakdown by Category
Direct cost composition by category from JDR cost codes
Category | Cost Codes | Actual $ | % of Direct Cost | % of Revenue | Source
Labor | 100,101,110,111,112,120,130,140,141,142,150 | 146699.25 |  |  | 2040 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
Material | 210,211,212,220,230,240,241,242,243 | 154104.17 |  |  | 2040 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
Subcon+Engineering+Permits+Other | 600,601,603,607 | 27430.2 |  |  | 2040 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
Payroll Burden | 995 | 65061.2 |  |  | 2040 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
Payroll Taxes | 998 | 11222.94 |  |  | 2040 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
TOTAL DIRECT COST |  |  | 100%

## Material
Material Purchases — AP Vendors
Material + subcontractor spend by vendor from JDR AP records
Vendor ID | Vendor Name | Total Spend | # Transactions | Category (inferred) | Source
1231KS | Keller Supply Company | 37520.04 | 31 | Plumbing / Supplies | 2040 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
7230BB | Best Bath Systems | 26250.23 | 3 | Uncategorized | 2040 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
1625FE | Franklin Engineering | 15976 | 8 | Engineering (601) | 2040 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
2040CS | Consolidated Supply Co. $65th Apts | 15318.38 | 14 | Plumbing / Supplies | 2040 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
1380RS | Rosen Supply Kirkland | 13591.59 | 20 | Plumbing / Supplies | 2040 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
2040RS | Rosen Supply Company, Inc. $65th Apts | 9330.63 | 16 | Plumbing / Supplies | 2040 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
1175FE | Ferguson Enterprises, Inc. #3007 | 8842.43 | 8 | Plumbing / Supplies | 2040 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
1234CO | Capital One Credit Card | 8619.07 | 24 | Credit Card (mixed) | 2040 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
2032RS | Rosen Supply Company, Inc. $Roosevelt | 6670.44 | 4 | Plumbing / Supplies | 2040 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
2040KS | Keller Supply Co. $65th Apts | 3484.94 | 6 | Plumbing / Supplies | 2040 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
1130CS | Consolidated Supply Co. | 2489.21 | 7 | Plumbing / Supplies | 2040 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
3181SC | Scan2Core, Inc. | 1699 | 2 | Uncategorized | 2040 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
3612MS | Mechanical Sales, Inc. | 999.5 | 2 | Plumbing / Supplies | 2040 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
5560CH | California Hydronics Corp | 975 | 2 | Uncategorized | 2040 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
8056MS | Mechanical Service & Integration LLC | 800 | 1 | Uncategorized | 2040 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
2032KS | Keller Supply Co. $Roosevelt | 785.36 | 1 | Plumbing / Supplies | 2040 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
1234BA | Bank of America CC | 667.53 | 2 | Uncategorized | 2040 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
4320MC | MAD Concrete Cutting & Coring, Inc. | 450 | 1 | Uncategorized | 2040 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
1021AT | ACME Corp | 241.61 | 3 | Uncategorized | 2040 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
1421RA | R.A. Brown Backflow Testing | 155 | 1 | Testing subcontractor | 2040 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
TOTAL

## Crew & Labor
Crew & Labor — Worker Roster
All 32 unique payroll workers. OWP RI: Garrett / Joe.
Worker ID | Worker Name | Total Hours | Gross Pay | Blended Wage ($/hr) | # Work Days | Source
WE55 | Wennig, Johnathan M | 888.25 | 23822.5 |  | 28 | 2040 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
HE70 | Hernandez Gonzalez, Osbaldo | 881.75 | 17220.25 |  | 25 | 2040 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
WI46 | Wilson, Garret A | 647.5 | 22446.5 |  | 33 | 2040 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
LE17 | Lee, Ha Nul | 613.75 | 10014 |  | 17 | 2040 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
BA68 | Barbosa, Michael S | 345 | 7935 |  | 12 | 2040 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
PO71 | Portillo, Kevin J | 255 | 3150 |  | 6 | 2040 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
CA74 | Castaneda Martinez, Gustavo | 198 | 7920 |  | 7 | 2040 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
CA71 | Castaneda Juarez, Cesar O | 183 | 2928 |  | 7 | 2040 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
AN14 | Anderson, Richard P | 169 | 7005 |  | 19 | 2040 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
MC09 | McCabe, Thomas C | 155 | 3452 |  | 7 | 2040 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
KI55 | Kinssies, Jr, John E | 133 | 3123 |  | 13 | 2040 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
BA70 | Barnhart, Joseph N | 118 | 5292 |  | 29 | 2040 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
EL33 | Eliassen, Cory H | 107.5 | 2654.5 |  | 8 | 2040 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
GE69 | Gerard, Jeffrey S | 96 | 4624 |  | 43 | 2040 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
HU06 | Hubbard, Robert W | 92.5 | 3780.5 |  | 14 | 2040 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
GO51 | Gomez Reyes, Edith N | 74.5 | 1696.5 |  | 5 | 2040 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
SA54 | Sanders, Allen O | 70.5 | 3270 |  | 12 | 2040 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
FO55 | Fonseca Teruel, Eduardo | 70.5 | 1269 |  | 6 | 2040 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
RE91 | Reyes, Maria E | 65.5 | 1163 |  | 4 | 2040 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
TR60 | Trower-Kelly, Fidel D | 58 | 928 |  | 4 | 2040 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
DO56 | Donelson, Richard T | 44 | 2612.5 |  | 30 | 2040 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
RO10 | Rodriguez Arevalos, Christian | 26.5 | 554 |  | 7 | 2040 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
YO29 | Yohannes Jr., Samson | 24 | 448 |  | 2 | 2040 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
LO58 | Lopez Reyes, Boris O | 24 | 432 |  | 1 | 2040 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
RE18 | Reed, Reuben H | 21 | 861 |  | 1 | 2040 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
GE70 | Gerard, Jordan E | 13 | 442 |  | 2 | 2040 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
ST02 | Stahlschmidt, John P | 8 | 136 |  | 1 | 2040 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
RO06 | Roberts, Lake A | 8 | 136 |  | 1 | 2040 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
MA71 | Martinez Reyes, Juan C | 4 | 104 |  | 2 | 2040 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
SE64 | Sepulveda Gonzalez, Alfredo | 4 | 128 |  | 1 | 2040 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
HU04 | Hubbard, Dustin R | 2.5 | 51.5 |  | 2 | 2040 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
HO14 | Holmes, Anthony R | 1 | 37 |  | 1 | 2040 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
TOTAL

## Crew Analytics
Crew Analytics
Team-level labor productivity, concentration, wage dispersion
TEAM-LEVEL METRICS
Metric | Value | Notes | Source
Total Workers | 32 | Unique payroll IDs | 2040 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
Total Labor Hours | 5454 | Sum of labor codes | 2040 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
Total Gross Pay | 146699.25 | Sum of labor codes | 2040 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
Blended Gross Wage ($/hr) | 26.8976 | Labor$/Hrs (pre-burden) | Derived
Top Worker Hours Share | 16.29% | WE55 Wennig, Johnathan M (888 hrs) | Derived
Top 5 Workers Hours Share | 61.9% | Concentration metric | Derived
Highest Wage Rate ($/hr) | 59.375 | Single-worker blended | Derived
Lowest Wage Rate ($/hr) | 12.3529 | Single-worker blended | Derived
Avg Hours per Worker | 170.4375 | Includes short-tenure workers | Derived
Avg Project Days per Worker | 10.9375 | Mean days | Derived

## Productivity
Productivity Metrics
Normalized ratios. Per-unit from 55 units.
Metric | Value | Basis | Source / Note
Revenue per Labor Hour | 114.4428 | USD/hr
Profit per Labor Hour | 40.2738 | USD/hr
Labor Cost per Hour (blended) | 26.8976 | USD/hr | Pre-burden
Fully-Loaded Labor Rate ($/hr) | 40.8844 | USD/hr | Incl burden+taxes
Burden Multiplier | 1.52 | x | Fully-loaded/blended
Rough-in Hours (code 120) | 3429.75 | hrs
Finish Hours (code 130) | 531.75 | hrs
Rough-in % of Total Hours | 62.89% | %
Gross Margin | 35.19% | %
Labor % of Revenue | 23.5% | %
Material % of Revenue | 24.69% | %
Direct Cost Ratio | 64.81% | % | All exp/Rev
Revenue per Unit (55) | 11348.5636 | USD | 55 units
Labor Hours per Unit | 99.1636 | hrs
Labor Cost per Unit | 2667.2591 | USD
Material Cost per Unit | 2801.894 | USD
Direct Cost per Unit | 7354.8684 | USD
Rough-in Hours per Unit | 62.3591 | hrs

## PO Commitments
PO Commitments
Inbound contract (GC → OWP). Outbound vendor commitments — see Material tab.
PO # | Date | Issuer | Type | Status | Description | Amount | Source
PRIME | 2017-03-01 | Blueprint Capital | Lump Sum Subcontract | Closed | Roosevelt 65th (Brooklyn 65) plumbing (55 units) — per Div 22 | 604000 | 2040-Blueprint Capital subcontract + Job Info sheet
CO-NET | — | Blueprint Capital | Change Orders (net, JDR-implied) | Executed | Net CO impact (Sage 999 rev - orig) | 20171 | 2040 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
TOTAL (contract + COs)

## Billing & SOV
Billing & Schedule of Values
18 invoices to Blueprint Capital. Retainage $0.00.
Invoice # | Date | Total Billed (signed) | Retainage (signed) | # Lines | Source
036927 | 08/18/17 | -36300 | 0 | 2 | 2040 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
036949 | 09/20/17 | -22100 | 0 | 1 | 2040 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
036957 | 09/20/17 | 22100 | 0 | 1 | 2040 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
036958 | 09/20/17 | -17680 | 0 | 1 | 2040 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
036970 | 10/20/17 | -10420 | 0 | 2 | 2040 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
036983 | 11/17/17 | -5000 | 0 | 1 | 2040 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
037003 | 01/19/18 | -79910 | 0 | 2 | 2040 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
037053 | 03/20/18 | -63410 | 0 | 3 | 2040 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
037065 | 04/20/18 | -43520 | 0 | 3 | 2040 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
037079 | 05/18/18 | -108008 | 0 | 7 | 2040 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
037116 | 06/20/18 | -45825 | 0 | 8 | 2040 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
037136 | 07/20/18 | -90140 | 0 | 7 | 2040 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
037160 | 08/20/18 | -21910 | 0 | 4 | 2040 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
037190 | 09/19/18 | -24184 | 0 | 2 | 2040 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
037215 | 10/19/18 | -7124 | 0 | 3 | 2040 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
037232 | 11/16/18 | -25500 | 0 | 2 | 2040 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
037257 | 12/14/18 | -38250 | 0 | 3 | 2040 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
037278 | 01/18/19 | -6990 | 0 | 2 | 2040 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
TOTAL (signed)

## Insights
Insights & Observations
Narrative findings from JDR
# | Insight | Detail | Confidence | Source
1 | MARGIN PROFILE | Net profit $219,653.24 on $624,171.00 revenue = 35.2% gross margin. | Verified | 2040 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
2 | CONTRACT CHANGE | Original $604,000.00 → final $624,171.00 = $+20,171.00 net (+3.34%). | Verified | 2040 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
3 | LABOR PROFILE | Labor cost $146,699.25 (23.5% of rev) across 5,454 hrs and 32 workers. Blended wage $26.90/hr. | Verified | 2040 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
4 | VENDOR CONCENTRATION | Top 5 AP vendors: ~$108,656.24 (70% of AP). Top vendor: Keller Supply Company ($37,520.04). | Verified | 2040 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
5 | RETAINAGE | Retainage $0 — closed out cleanly. | Verified | 2040 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
6 | ROUGH-IN SHARE | Code 120 Roughin Labor = 3,430 hrs (63% of labor hours). | Verified | 2040 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
7 | TOP COST CODE | Largest actual cost: 230 Finish Material = $88,855.74 | Verified | 2040 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
8 | WORKER CONCENTRATION | Top worker Wennig, Johnathan M = 888 hrs (16% of total). | Verified | 2040 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
9 | INSURANCE | Not Wrap — OCIP wrap. | Verified | OWP Project List with Schedule - UPDATED 04-01-26.xlsx
10 | SCOPE CONTEXT | Brooklyn 65 (Roosevelt 65th) — 55-unit multifamily plumbing, NE Seattle. | Verified | OWP Project List with Schedule - UPDATED 04-01-26.xlsx + JDR

## Benchmark KPIs
Benchmark KPIs
Normalized metrics for cross-project comparison
KPI | Data Name | Value | Category | Notes | Confidence | Source Document
Job Number | job_number | 2040 | Profile | OWP job ID | Verified | 2040 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
Job Name | job_name | Roosevelt 65th (Brooklyn 65) | Profile |  | Verified | 2040 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
General Contractor | gc | Blueprint Capital | Profile |  | Verified | OWP Project List with Schedule - UPDATED 04-01-26.xlsx
Owner | owner | Brooklyn 65 LLC (Blueprint) | Profile |  | Verified | OWP Project List with Schedule - UPDATED 04-01-26.xlsx
Location | location | 1222 NE 65th Street, Seattle, WA 98115 | Profile |  | Verified | OWP Project List with Schedule - UPDATED 04-01-26.xlsx
Project Type | project_type | Multifamily New Construction (55 units) | Profile |  | Verified | OWP Project List with Schedule - UPDATED 04-01-26.xlsx
Insurance Type | insurance | Not Wrap | Profile |  | Verified | OWP Project List with Schedule - UPDATED 04-01-26.xlsx
GC PM | gc_pm | Andrew Withnell | Profile |  | Verified | OWP Project List with Schedule - UPDATED 04-01-26.xlsx
GC Sup | gc_sup | Mike Sanderson | Profile |  | Verified | OWP Project List with Schedule - UPDATED 04-01-26.xlsx
GC PE | gc_pe | Kyle Stenson | Profile |  | Verified | OWP Project List with Schedule - UPDATED 04-01-26.xlsx
Developer | developer | Blueprint | Profile |  | Verified | OWP Project List with Schedule - UPDATED 04-01-26.xlsx
OWP RI Foreman | owp_foreman | Garrett / Joe | Profile |  | Verified | Schedule
Work Start | start_date | 2017-03-01 | Profile |  | Verified | 2040 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
Work End | end_date | 2019 | Profile |  | Verified | 2040 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
Duration (months) | duration_months | 22 | Profile |  | Verified | Derived
Unit Count | unit_count | 55 | Profile |  | Verified | OWP Project List with Schedule - UPDATED 04-01-26.xlsx
Contract Original | contract_original | 604000 | Financial |  | Verified | OWP Project List with Schedule - UPDATED 04-01-26.xlsx
Contract Final | contract_final | 624171 | Financial |  | Verified | OWP Project List with Schedule - UPDATED 04-01-26.xlsx
Change Orders ($, implied) | co_implied | 20171 | Financial | Final - Original | Verified | 2040 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
CO % of Contract | co_pct | 3.34% | Financial |  | Verified | Derived
Revenue | revenue | 624171 | Financial | AR total | Verified | 2040 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
Direct Cost | direct_cost | 404517.76 | Financial | JDR Expenses | Verified | 2040 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
Net Profit | net_profit | 219653.24 | Financial | Rev - Exp | Verified | 2040 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
Gross Margin | gross_margin | 35.19% | Financial |  | Verified | Derived
Retainage | retainage | 0 | Financial | JDR AR retainage | Verified | 2040 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
Retainage % of Revenue | retainage_pct | 0% | Financial |  | Verified | Derived
Labor Cost | labor_cost | 146699.25 | Labor | Codes 100-151 | Verified | 2040 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
Material Cost | material_cost | 154104.17 | Material | Codes 210-245 | Verified | 2040 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
Overhead Cost | overhead_cost | 27430.2 | Financial | Codes 600-607 | Verified | 2040 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
Burden Cost | burden_cost | 65061.2 | Labor | Code 995 | Verified | 2040 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
Tax Cost | tax_cost | 11222.94 | Labor | Code 998 | Verified | 2040 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
Total Labor Hours | total_hours | 5454 | Labor | Sum labor codes | Verified | 2040 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
Total Workers | total_workers | 32 | Labor | Unique PR IDs | Verified | 2040 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
Blended Gross Wage | blended_wage | 26.8976 | Labor |  | Verified | Derived
Fully-Loaded Wage | loaded_wage | 40.8844 | Labor |  | Verified | Derived
Burden Multiplier | burden_mult | 1.52 | Labor |  | Verified | Derived
Rough-in Hours | roughin_hours | 3429.75 | Labor | Code 120 | Verified | 2040 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
Finish Hours | finish_hours | 531.75 | Labor | Code 130 | Verified | 2040 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
Revenue per Hour | rev_per_hour | 114.4428 | Productivity |  | Verified | Derived
Profit per Hour | profit_per_hour | 40.2738 | Productivity |  | Verified | Derived
Revenue per Unit | rev_per_unit | 11348.5636 | Productivity |  | Verified | Derived
Direct Cost per Unit | cost_per_unit | 7354.8684 | Productivity |  | Verified | Derived
Hours per Unit | hours_per_unit | 99.1636 | Productivity |  | Verified | Derived
Labor % of Revenue | labor_pct | 23.5% | Cost Mix |  | Verified | Derived
Material % of Revenue | material_pct | 24.69% | Cost Mix |  | Verified | Derived
Total Vendors | total_vendors | 20 | Material |  | Verified | 2040 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
Total Invoices | total_invoices | 18 | Billing |  | Verified | 2040 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
Cost Codes Active | cost_codes | 27 | Structure |  | Verified | 2040 Job Detail Report.pdf (Sage Timberline, 04/03/2026)

## Vendors
Vendors — AP Summary
Vendor-level spend ranking
Rank | Vendor ID | Vendor Name | Total Spend | # Transactions | % of AP | Source
1 | 1231KS | Keller Supply Company | 37520.04 | 31 |  | 2040 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
2 | 7230BB | Best Bath Systems | 26250.23 | 3 |  | 2040 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
3 | 1625FE | Franklin Engineering | 15976 | 8 |  | 2040 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
4 | 2040CS | Consolidated Supply Co. $65th Apts | 15318.38 | 14 |  | 2040 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
5 | 1380RS | Rosen Supply Kirkland | 13591.59 | 20 |  | 2040 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
6 | 2040RS | Rosen Supply Company, Inc. $65th Apts | 9330.63 | 16 |  | 2040 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
7 | 1175FE | Ferguson Enterprises, Inc. #3007 | 8842.43 | 8 |  | 2040 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
8 | 1234CO | Capital One Credit Card | 8619.07 | 24 |  | 2040 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
9 | 2032RS | Rosen Supply Company, Inc. $Roosevelt | 6670.44 | 4 |  | 2040 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
10 | 2040KS | Keller Supply Co. $65th Apts | 3484.94 | 6 |  | 2040 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
11 | 1130CS | Consolidated Supply Co. | 2489.21 | 7 |  | 2040 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
12 | 3181SC | Scan2Core, Inc. | 1699 | 2 |  | 2040 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
13 | 3612MS | Mechanical Sales, Inc. | 999.5 | 2 |  | 2040 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
14 | 5560CH | California Hydronics Corp | 975 | 2 |  | 2040 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
15 | 8056MS | Mechanical Service & Integration LLC | 800 | 1 |  | 2040 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
16 | 2032KS | Keller Supply Co. $Roosevelt | 785.36 | 1 |  | 2040 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
17 | 1234BA | Bank of America CC | 667.53 | 2 |  | 2040 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
18 | 4320MC | MAD Concrete Cutting & Coring, Inc. | 450 | 1 |  | 2040 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
19 | 1021AT | ACME Corp | 241.61 | 3 |  | 2040 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
20 | 1421RA | R.A. Brown Backflow Testing | 155 | 1 |  | 2040 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
TOTAL

## Change Log
Change Log — Master Register
Contract, CO net, retainage events — JDR only
Event ID | Type | Date | Subject | Originator | Cost Impact ($) | Status | Source
CONTRACT-ORIG | Contract | 2017-03-01 | Prime subcontract — Lump Sum $604,000.00 | Blueprint Capital | 604000 | Executed | 2040-Blueprint Capital subcontract + Job Info sheet
CO-NET | Change Order (net) | — | Net JDR-implied COs $+20,171.00 | Blueprint Capital | 20171 | Executed | 2040 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
FIRST-INVOICE | Invoice | 01/18/19 | First billing (per JDR) | Sub (OWP) | 0 | Paid | 2040 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
LAST-INVOICE | Invoice | 12/14/18 | Last billing (per JDR) | Sub (OWP) | 0 | Paid | 2040 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
RETAINAGE-OPEN | Retainage | As of 04/03/2026 | Retainage $0 (cleared) | GC | 0 | Cleared | 2040 Job Detail Report.pdf (Sage Timberline, 04/03/2026)

## Root Cause Analysis
Root Cause Analysis
Primary variance drivers by category
Category | Codes | Net $ Variance | Root Cause (inferred) | Notes
Contract Change | 999 (Sales) | 20171 | JDR-implied net CO impact | $604,000 → $624,171
Labor | 100,101,110,111,112,120,130,140,141,142,150 | -10265.75 | Labor variance vs revised budget | 32 workers
Material | 210,211,212,220,230,240,241,242,243 | -31881.83 | Material procurement variance | 20 vendors
Overhead | 600,601,603,607 | -604.8 | Engineering/permits/subcon variance
Burden+Tax | 995+998 | -6898.46 | Payroll accrual tracking labor
TOTAL NET VARIANCE
RESPONSIBILITY ATTRIBUTION
Responsible Party | # Drivers | Net $ Impact | Notes
GC / Owner (scope changes) | 1 | 20171 | Aggregate JDR-implied COs
Sub (OWP) labor performance | 11 | -10265.75 | Hours + rate vs budget
Sub (OWP) material procurement | 9 | -31881.83 | 20 vendors
OWP burden accrual | 2 | -6898.46 | Payroll burden + tax
OWP overhead | 4 | -604.8 | Engineering/permits/subcon

## Predictive Signals
Predictive Signals
Leading indicators from JDR
CURRENT-STATE SIGNALS
Indicator | Current Value | Benchmark | Status | Meaning
Contract Change % | 3.34% | ±10% | HEALTHY | +3.34% net
Labor % of Revenue | 23.5% | <30% | HEALTHY | 23.5%
GL Overhead % of Revenue | 17.63% | <5% | HEALTHY | 17.6%
Vendor Concentration (Top 5) | 70.16% | <95% | HEALTHY | Top 5 = 70% of AP
Retainage % | 0% | <10% | HEALTHY | 0.0%
Gross Margin | 35.19% | >30% | HEALTHY | 35.2%
Labor Hrs Total | 545400% | varies | INFO | 5,454 hrs, 32 workers
Worker Concentration (top 1) | 16.29% | <25% | HEALTHY | 16.3% (Wennig, Johnathan M)
Rough-in Labor Share | 62.89% | 40-65% | HEALTHY | 63%
Retainage Legacy | CLEARED | <90 days post-closeout | HEALTHY | Cleared
FORECAST MODELS
Forecast | Current Estimate | Confidence | Driver | Model Note
Final margin (actual) | 35.19% | Actual | Job closed | 35.2%
Retainage collection | N/A | N/A | Legacy project | Closed
Unit-level economics | $11,349/unit rev, $3,994/unit profit | Verified | 55 units | Multifamily New Construction benchmark

## Metric Registry
Metric Registry — Cortex Data Catalog
Every metric with data_label, confidence, and source
# | Data Label | Human Label | Value | Unit | Source Tab | Confidence | Source Document(s)
1 | job_number | Job Number | 2040 | id | Benchmark KPIs | Verified | 2040 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
2 | job_name | Job Name | Roosevelt 65th (Brooklyn 65) | text | Benchmark KPIs | Verified | 2040 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
3 | general_contractor | GC | Blueprint Capital | text | Benchmark KPIs | Verified | OWP Project List with Schedule - UPDATED 04-01-26.xlsx
4 | owner | Owner | Brooklyn 65 LLC (Blueprint) | text | Benchmark KPIs | Verified | OWP Project List with Schedule - UPDATED 04-01-26.xlsx
5 | location | Location | 1222 NE 65th Street, Seattle, WA 98115 | text | Benchmark KPIs | Verified | OWP Project List with Schedule - UPDATED 04-01-26.xlsx
6 | project_type | Project Type | Multifamily New Construction (55 units) | text | Benchmark KPIs | Verified | OWP Project List with Schedule - UPDATED 04-01-26.xlsx
7 | insurance_type | Insurance | Not Wrap | text | Benchmark KPIs | Verified | OWP Project List with Schedule - UPDATED 04-01-26.xlsx
8 | gc_pm | GC PM | Andrew Withnell | text | Benchmark KPIs | Verified | OWP Project List with Schedule - UPDATED 04-01-26.xlsx
9 | gc_sup | GC Sup | Mike Sanderson | text | Benchmark KPIs | Verified | OWP Project List with Schedule - UPDATED 04-01-26.xlsx
10 | gc_pe | GC PE | Kyle Stenson | text | Benchmark KPIs | Verified | OWP Project List with Schedule - UPDATED 04-01-26.xlsx
11 | developer | Developer | Blueprint | text | Benchmark KPIs | Verified | OWP Project List with Schedule - UPDATED 04-01-26.xlsx
12 | owp_foreman | OWP RI Foreman | Garrett / Joe | text | Benchmark KPIs | Verified | Schedule
13 | start_date | Work Start | 2017-03-01 | date | Benchmark KPIs | Verified | 2040 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
14 | end_date | Work End | 2019 | date | Benchmark KPIs | Verified | 2040 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
15 | duration_months | Duration | 22 | months | Benchmark KPIs | Verified | Derived
16 | unit_count | Unit Count | 55 | units | Benchmark KPIs | Verified | OWP Project List with Schedule - UPDATED 04-01-26.xlsx
17 | contract_original | Contract Orig | 604000 | USD | Benchmark KPIs | Verified | OWP Project List with Schedule - UPDATED 04-01-26.xlsx
18 | contract_final | Contract Final | 624171 | USD | Benchmark KPIs | Verified | OWP Project List with Schedule - UPDATED 04-01-26.xlsx
19 | change_orders_implied | CO (implied) | 20171 | USD | Benchmark KPIs | Verified | 2040 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
20 | co_pct | CO % of Contract | 3.34% | % | Benchmark KPIs | Verified | Derived
21 | revenue | Revenue | 624171 | USD | Benchmark KPIs | Verified | 2040 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
22 | direct_cost | Direct Cost | 404517.76 | USD | Benchmark KPIs | Verified | 2040 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
23 | net_profit | Net Profit | 219653.24 | USD | Benchmark KPIs | Verified | 2040 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
24 | gross_margin | Gross Margin | 35.19% | % | Benchmark KPIs | Verified | Derived
25 | retainage | Retainage | 0 | USD | Benchmark KPIs | Verified | 2040 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
26 | retainage_pct | Retainage % | 0% | % | Benchmark KPIs | Verified | Derived
27 | labor_cost | Labor Cost | 146699.25 | USD | Benchmark KPIs | Verified | 2040 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
28 | material_cost | Material Cost | 154104.17 | USD | Benchmark KPIs | Verified | 2040 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
29 | overhead_cost | Overhead Cost | 27430.2 | USD | Benchmark KPIs | Verified | 2040 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
30 | burden_cost | Burden | 65061.2 | USD | Benchmark KPIs | Verified | 2040 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
31 | tax_cost | Tax | 11222.94 | USD | Benchmark KPIs | Verified | 2040 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
32 | total_hours | Total Hours | 5454 | hours | Benchmark KPIs | Verified | 2040 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
33 | total_workers | Total Workers | 32 | count | Benchmark KPIs | Verified | 2040 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
34 | blended_wage | Blended Wage | 26.8976 | USD/hr | Benchmark KPIs | Verified | Derived
35 | loaded_wage | Loaded Wage | 40.8844 | USD/hr | Benchmark KPIs | Verified | Derived
36 | burden_mult | Burden Multiplier | 1.52 | x | Benchmark KPIs | Verified | Derived
37 | roughin_hours | Rough-in Hours | 3429.75 | hours | Benchmark KPIs | Verified | 2040 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
38 | finish_hours | Finish Hours | 531.75 | hours | Benchmark KPIs | Verified | 2040 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
39 | rev_per_hour | Rev per Hour | 114.4428 | USD/hr | Benchmark KPIs | Verified | Derived
40 | profit_per_hour | Profit per Hour | 40.2738 | USD/hr | Benchmark KPIs | Verified | Derived
41 | rev_per_unit | Rev per Unit | 11348.5636 | USD | Benchmark KPIs | Verified | Derived
42 | cost_per_unit | Cost per Unit | 7354.8684 | USD | Benchmark KPIs | Verified | Derived
43 | hours_per_unit | Hours per Unit | 99.1636 | hours | Benchmark KPIs | Verified | Derived
44 | labor_pct | Labor % | 23.5% | % | Benchmark KPIs | Verified | Derived
45 | material_pct | Material % | 24.69% | % | Benchmark KPIs | Verified | Derived
46 | total_vendors | Total Vendors | 20 | count | Vendors | Verified | 2040 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
47 | total_invoices | Total Invoices | 18 | count | Billing & SOV | Verified | 2040 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
48 | top_worker_share | Top Worker Share | 16.29% | % | Crew Analytics | Verified | Derived
49 | top5_worker_share | Top 5 Worker Share | 61.9% | % | Crew Analytics | Verified | Derived
50 | cost_code_count | Cost Codes Active | 27 | count | Budget vs Actual | Verified | 2040 Job Detail Report.pdf (Sage Timberline, 04/03/2026)

## Reconciliation
Reconciliation
Cross-sheet formula checks
# | Check | Value A | Value B | Delta | Status | Tabs
1 | Revenue = Contract Final | 624171 | 624171 |  |  | 1↔8
2 | Expenses = Labor+Mat+OH+Burden+Tax | 404517.76 | 404517.76 |  |  | 1↔3
3 | Net Profit = Revenue - Expenses | 219653.24 | 219653.24 |  |  | 1↔Derived
4 | Sage 999 actual = -Revenue | 624171 | 624171 |  |  | 2↔1
5 | Total Hours = Worker hours sum | 5454 | 5402.25 |  |  | 5↔2
6 | Contract Final - Orig = CO implied | 20171 | 20171 |  |  | 11↔Derived
7 | Worker count | 32 | 32 |  |  | 5↔1
8 | Cost code count | 27 | 27 |  |  | 2↔16