## Overview
Job #2041 · Luna @ 2749 California Ave
Cortex JCR v2 • Chinn Construction, LLC (customer 2041CC) • 2749 California Avenue SW, Seattle, WA 98116 • Owner: 2741 California LLC
PROJECT OVERVIEW
Project Job # | 2041 |  | 2041 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
Project Name (Sage) | Chinn California Ave Luna |  | 2041 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
Project Description | Luna Apartments — 108-unit mixed-use residential + PCC retail, West Seattle |  | OWP Project List with Schedule - UPDATED 04-01-26.xlsx + contract
General Contractor | Chinn Construction, LLC |  | OWP Project List with Schedule - UPDATED 04-01-26.xlsx
Customer Code (Sage) | 2041CC |  | 2041 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
Owner / Developer | 2741 California LLC |  | OWP Project List with Schedule - UPDATED 04-01-26.xlsx
GC PM | Joe Hanley / Amir Molavi |  | 2041-Chinn Construction subcontract + Job Info sheet
GC Superintendent | James Casal |  | 2041-Chinn Construction subcontract + Job Info sheet
GC PE | N/A |  | 2041-Chinn Construction subcontract + Job Info sheet
OWP Signatory | Mike Donelson |  | 2041-Chinn Construction subcontract + Job Info sheet
Jobsite Location | 2749 California Avenue SW, Seattle, WA 98116 |  | OWP Project List with Schedule - UPDATED 04-01-26.xlsx
Insurance | Not Wrap |  | OWP Project List with Schedule - UPDATED 04-01-26.xlsx
Fixture Schedule | 754 fixtures total (656 unit + 98 retail/common) |  | Submittal Table of Contents + Plumbing Scope
Architect | Hewitt Architects |  | Chinn Luna project info.pdf
Contract Type | Lump Sum |  | 2041-Chinn Construction subcontract + Job Info sheet
Unit Count | 108 |  | Submittal TOC (102 Type B + 6 Type A/ADA)
Work Period | 2018-01 start → 2019-12 (24 months) |  | JDR PR/AR dates
CONTRACT VALUE |  | NET PROFIT | DIRECT COST | LABOR HOURS
1883761 |  | 553900.64 | 1329860.36 | 14650.5
Original $1,766,205.00 + ($117,556.00) COs (6.66%) |  | 29.4% margin | 70.6% of revenue | 44 workers
SCOPE OF WORK
Full plumbing installation per Division 22: underground, garage, rough-in, finish, gas, water main, insulation, roof drains.
108-unit mixed-use (102 Type B + 6 Type A/ADA) at 2749 California Avenue SW, Seattle, WA 98116, 4-story residential + PCC retail ground floor + P1/P2 parking.
GC: Chinn Construction, LLC (2041CC); Owner: 2741 California LLC.
Insurance: Not Wrap (retail-adjacent residential).
Project team: Joe Hanley / Amir Molavi (GC PM) · James Casal (GC Sup) · Hewitt Architects (Architect) · Mike Donelson (OWP signatory).
SOURCES
Canonical financial source: 2041 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
Job totals (JDR footer): Revenue $1,883,761.00 / Expenses $1,329,860.36 / Net $553,900.64 / Retainage $93,941.20
Source breakdown (derived): PR $725,409.66 · AP $546,513.36 · GL $57,937.34
Contract: Lump Sum $1,766,205.00 → $1,883,761.00
Change Orders (executed): $117,556.00 net across 18 COs (CO log in enriched meta)
Project Team: Joe Hanley / Amir Molavi (PM) · James Casal (Sup) · Hewitt Architects · 2741 California LLC
PROJECT TEAM (OWP Job Info)
Role | Status | Name / Firm
GC | Extracted | Chinn Construction, LLC
GC PM | Extracted | Joe Hanley / Amir Molavi
GC Superintendent | Extracted | James Casal
GC PE | N/A | N/A
Owner | Extracted | 2741 California LLC
Architect | Extracted | Hewitt Architects
Structural | N/A | N/A
Acoustical | N/A | N/A
ADA Consultant | N/A | N/A
Interior Design | N/A | N/A
MEP Engineer | N/A | N/A
Insurance | Extracted | Not Wrap
OWP Signatory | Extracted | Mike Donelson

## Budget vs Actual
Budget vs Actual
All 29 cost codes from JDR. Contract $1,766,205 → $1,883,761.
Cost Code | Description | Original Budget | Revised Budget | Actual | Variance | % of Revised | Hours | Source
100 | Supervision | 8640 | 9440 | 5242 | -4198 | 55.53% | 100 | 2041 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
101 | Takeoff & Purchase Labor | 15120 | 16020 | 16934 | 914 | 105.7% | 297 | 2041 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
110 | Underground Labor | 14780 | 17300 | 11895 | -5405 | 68.76% | 312.5 | 2041 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
111 | Garage Labor | 92270 | 107770 | 120082.91 | 12312.91 | 111.4% | 3647.5 | 2041 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
112 | Canout Labor | 22500 | 22590 | 13665 | -8925 | 60.49% | 379 | 2041 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
120 | Roughin Labor | 155820 | 150920 | 187351.59 | 36431.59 | 124.1% | 6131 | 2041 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
130 | Finish Labor | 42870 | 43420 | 33336 | -10084 | 76.78% | 1290 | 2041 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
140 | Gas Labor | 9750 | 10950 | 7098 | -3852 | 64.82% | 217 | 2041 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
141 | Water Main/Insulation Lab | 52850 | 53000 | 53432 | 432 | 100.8% | 1697.5 | 2041 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
142 | Mech Room Labor | 17500 | 17500 | 15740.5 | -1759.5 | 89.95% | 424.5 | 2041 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
143 | Condensation Drains Labor | 0 | 0 | 2447 | 2447 |  | 69 | 2041 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
150 | Warranty Labor | 0 | 0 | 73.5 | 73.5 |  | 1.5 | 2041 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
210 | Underground Material | 9540 | 14690 | 6296.57 | -8393.43 | 42.86% |  | 2041 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
211 | Garage Material | 86250 | 95533 | 71058.87 | -24474.13 | 74.38% |  | 2041 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
212 | Canout Material | 22500 | 22695 | 8465.53 | -14229.47 | 37.3% |  | 2041 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
220 | Roughin Material | 90850 | 90170 | 79004.39 | -11165.61 | 87.62% |  | 2041 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
230 | Finish Material | 311040 | 337431 | 251663.7 | -85767.3 | 74.58% |  | 2041 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
240 | Gas Material | 5250 | 5580 | 4155.07 | -1424.93 | 74.46% |  | 2041 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
241 | Water Main/Insulation Mat | 50200 | 51126 | 62146.49 | 11020.49 | 121.6% |  | 2041 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
242 | Mech Room Material | 22500 | 22500 | 19825.43 | -2674.57 | 88.11% |  | 2041 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
243 | Condensation Drains Mat | 0 | 0 | 0 | 0 |  |  | 2041 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
600 | Subcontractor | 500 | 23850 | 33916.25 | 10066.25 | 142.2% |  | 2041 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
601 | Engineering/Plans | 50000 | 50000 | 57943.23 | 7943.23 | 115.9% |  | 2041 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
602 | Rental Equipment | 6000 | 13696 | 11181.2 | -2514.8 | 81.64% |  | 2041 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
603 | Permits & Licenses | 10000 | 10000 | 8662 | -1338 | 86.62% |  | 2041 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
607 | Other Expenses | 8000 | 8000 | 76.97 | -7923.03 | 0.9621% |  | 2041 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
995 | Payroll Burden | 195957.35 | 203353.75 | 211657.53 | 8303.78 | 104.1% |  | 2041 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
998 | Payroll Taxes | 33055.65 | 34341.65 | 36509.63 | 2167.98 | 106.3% |  | 2041 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
999 | Sales | -1766205 | -1883761 | -1883761 | 0 | 100% |  | 2041 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
TOTAL |  | -432462 | -451884.6 | -553900.64 | -102016.04 |  | 14566.5

## Cost Breakdown
Cost Breakdown by Category
Direct cost composition by category from JDR cost codes
Category | Cost Codes | Actual $ | % of Direct Cost | % of Revenue | Source
Labor | 100,101,110,111,112,120,130,140,141,142,143,150 | 467297.5 | 35.14% | 24.81% | 2041 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
Material | 210,211,212,220,230,240,241,242,243 | 502616.05 | 37.79% | 26.68% | 2041 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
Overhead | 600,601,602,603,607 | 111779.65 | 8.405% | 5.934% | 2041 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
Payroll Burden | 995 | 211657.53 | 15.92% | 11.24% | 2041 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
Payroll Taxes | 998 | 36509.63 | 2.745% | 1.938% | 2041 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
TOTAL DIRECT COST |  | 1329860.36 | 100% | 70.6%

## Material
Material Purchases — AP Vendors
Material + subcontractor spend by vendor from JDR AP records
Vendor ID | Vendor Name | Total Spend | # Transactions | Category (inferred) | Source
1380RS | Rosen Supply Kirkland | 171816.03 | 97 | Plumbing / Supplies | 2041 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
1130CS | Consolidated Supply Co. | 124509.19 | 50 | Plumbing / Supplies | 2041 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
1625FE | Franklin Engineering | 57662.63 | 17 | Engineering (601) | 2041 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
1231KS | Keller Supply Company | 51636.71 | 20 | Plumbing / Supplies | 2041 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
5560CH | California Hydronics Corp | 35401 | 3 | Plumbing / Supplies | 2041 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
3129MR | Mechanical Resource Services, Inc. | 27506.25 | 2 | Uncategorized | 2041 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
1175FE | Ferguson Enterprises, Inc. #3007 | 19078.32 | 31 | Plumbing / Supplies | 2041 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
7423OC | Old Castle Infrastructure, Inc. | 12187 | 3 | Uncategorized | 2041 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
1234CO | Capital One Credit Card | 10916.31 | 35 | Credit Card (mixed) | 2041 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
2713AR | Ahern Rentals | 9940.79 | 25 | Uncategorized | 2041 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
1609QC | Quality Concrete Products, Inc. $32 | 7385 | 1 | Uncategorized | 2041 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
5621HD | Core & Main LP $HD Supply Waterworks | 5930.19 | 4 | Plumbing / Supplies | 2041 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
2041RS | Rosen Supply Company, Inc. $Cal Luna | 4157.49 | 6 | Plumbing / Supplies | 2041 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
3181SC | Scan2Core, Inc. | 3465 | 5 | Uncategorized | 2041 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
5919PW | Patchworks, Inc. | 2720 | 1 | Uncategorized | 2041 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
1799AW | AllWest Underground, Inc. | 597.74 | 1 | Uncategorized | 2041 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
8068MI | Kele, Inc $ MI Controls | 570.89 | 2 | Uncategorized | 2041 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
3612MS | Mechanical Sales, Inc. | 290.58 | 1 | Plumbing / Supplies | 2041 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
1288DR | DRSi | 280.6 | 2 | Uncategorized | 2041 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
1641AR | A.R. Brown Backflow Testing | 225 | 1 | Testing subcontractor | 2041 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
2132MH | Manor Hardware & Construction Supply | 155 | 1 | Plumbing / Supplies | 2041 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
2041KS | Keller Supply Co. $Cali Luna | 81.64 | 1 | Plumbing / Supplies | 2041 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
TOTAL |  | 546513.36 | 309

## Crew & Labor
Crew & Labor — Worker Roster
All 44 unique payroll workers. OWP signatory: Mike Donelson.
Worker ID | Worker Name | Total Hours | Gross Pay | Blended Wage ($/hr) | # Work Days | Source
RI87 | Rivera, Jorge A | 1608.5 | 55278.25 | 34.3663 | 44 | 2041 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
HE70 | Hernandez Gonzalez, Osbaldo | 1585.5 | 38863.5 | 24.5118 | 41 | 2041 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
GO56 | Gonzalez Hernandez, Josue | 1579 | 49246 | 31.1881 | 48 | 2041 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
AN14 | Anderson, Richard P | 1413.5 | 65444.75 | 46.2998 | 58 | 2041 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
LE17 | Lee, Ha Nul | 1169 | 24208.75 | 20.7089 | 29 | 2041 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
ME53 | Mendoza Morales, Jesus A | 1083.5 | 30229 | 27.8994 | 30 | 2041 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
RE96 | Reyes Cruz, Denis A | 1082.5 | 31596 | 29.188 | 28 | 2041 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
RO75 | Ross, Kelli M | 845 | 35631 | 42.1669 | 22 | 2041 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
BA68 | Barbosa, Michael S | 583 | 16388.5 | 28.1106 | 17 | 2041 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
BA70 | Barnhart, Joseph N | 499 | 24658 | 49.4148 | 59 | 2041 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
LI49 | Lima Romero, Melvin A | 443 | 15610 | 35.237 | 12 | 2041 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
TR60 | Trower-Kelly, Fidel D | 397 | 7194 | 18.1209 | 14 | 2041 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
VA98 | Vazquez Popoca, Jose N | 339 | 5787 | 17.0708 | 13 | 2041 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
SE64 | Sepulveda Gonzalez, Alfredo | 329.5 | 11532.5 | 35 | 12 | 2041 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
SA54 | Sanders, Allen O | 241 | 12171.5 | 50.5041 | 30 | 2041 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
GE69 | Gerard, Jeffrey S | 230 | 11788.5 | 51.2543 | 82 | 2041 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
DO56 | Donelson, Richard T | 167 | 10387.5 | 62.2006 | 70 | 2041 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
MA71 | Martinez Reyes, Juan C | 145 | 3838 | 26.469 | 13 | 2041 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
CR79 | Cruz Guzman, Joel A | 130 | 3528 | 27.1385 | 6 | 2041 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
HU06 | Hubbard, Robert W | 121.5 | 6062.5 | 49.8971 | 17 | 2041 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
MO56 | Montenegro, Carlos E | 98 | 2871 | 29.2959 | 3 | 2041 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
ST02 | Stahlschmidt, John P | 64 | 1216 | 19 | 5 | 2041 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
EL33 | Eliassen, Cory H | 61 | 1671 | 27.3934 | 6 | 2041 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
GA83 | Gauthier, Dillon R | 56 | 960 | 17.1429 | 4 | 2041 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
MC09 | McCabe, Thomas C | 53.5 | 1862.5 | 34.8131 | 4 | 2041 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
KI55 | Kinssies, Jr, John E | 50.5 | 1523.5 | 30.1683 | 4 | 2041 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
CR87 | Cruz Reyes, Jose | 50 | 1610 | 32.2 | 5 | 2041 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
CR77 | Cruz Gonzalez, Julio C | 40 | 1000 | 25 | 3 | 2041 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
GE70 | Gerard, Jordan E | 32 | 1200 | 37.5 | 3 | 2041 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
RE91 | Reyes, Maria E | 28 | 0 | 0 | 1 | 2041 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
RO10 | Rodriguez Arevalos, Christian | 16 | 402.5 | 25.1562 | 2 | 2041 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
HU04 | Hubbard, Dustin R | 15 | 356 | 23.7333 | 3 | 2041 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
LU09 | Lucas Tzintzun, Rafael | 14 | 306 | 21.8571 | 2 | 2041 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
WI46 | Wilson, Garret A | 11 | 401 | 36.4545 | 2 | 2041 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
CO69 | Cornejo Orellana, Carlos E | 8 | 225.75 | 28.2188 | 1 | 2041 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
VE43 | Velasquez Cruz, Osman N | 8 | 209 | 26.125 | 1 | 2041 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
WE55 | Wennig, Johnathan M | 8 | 240 | 30 | 1 | 2041 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
FR04 | Frausto Mendoza, Pedro | 8 | 252 | 31.5 | 1 | 2041 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
VE42 | Velasquez Cruz, Denis M | 8 | 348 | 43.5 | 1 | 2041 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
AS10 | Ascencio, Jose L | 8 | 336 | 42 | 1 | 2041 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
FO75 | Foster, Antonio T | 8 | 240 | 30 | 1 | 2041 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
SI48 | Silva Morales, Jair J | 8 | 324 | 40.5 | 1 | 2041 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
RE18 | Reed, Reuben H | 5 | 205 | 41 | 1 | 2041 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
HO14 | Holmes, Anthony R | 1 | 40 | 40 | 1 | 2041 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
TOTAL |  | 14650.5 | 477242.5

## Crew Analytics
Crew Analytics
Team-level labor productivity, concentration, wage dispersion
TEAM-LEVEL METRICS
Metric | Value | Notes | Source
Total Workers | 44 | Unique payroll IDs | 2041 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
Total Labor Hours | 14650.5 | Sum of labor codes | 2041 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
Total Gross Pay | 477242.5 | Sum of labor codes | 2041 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
Blended Gross Wage ($/hr) | 32.5752 | Labor$/Hrs (pre-burden) | Derived
Top Worker Hours Share | 10.98% | RI87 Rivera, Jorge A (1608 hrs) | Derived
Top 5 Workers Hours Share | 50.21% | Concentration metric | Derived
Highest Wage Rate ($/hr) | 62.2006 | Single-worker blended | Derived
Lowest Wage Rate ($/hr) | 0 | Single-worker blended | Derived
Avg Hours per Worker | 332.9659 | Includes short-tenure workers | Derived
Avg Project Days per Worker | 15.9545 | Mean days | Derived

## Productivity
Productivity Metrics
Normalized ratios. Per-unit from 108 units (754 fixtures).
Metric | Value | Basis | Source / Note
Revenue per Labor Hour | 128.58 | USD/hr
Profit per Labor Hour | 37.8076 | USD/hr
Labor Cost per Hour (blended) | 31.8964 | USD/hr | Pre-burden
Fully-Loaded Labor Rate ($/hr) | 66.4535 | USD/hr | Incl burden+taxes
Burden Multiplier | 1.3421 | x | Fully-loaded/blended
Rough-in Hours (code 120) | 6131 | hrs
Finish Hours (code 130) | 1290 | hrs
Rough-in % of Total Hours | 42.09% | %
Gross Margin | 29.4% | %
Labor % of Revenue | 24.81% | %
Material % of Revenue | 26.68% | %
Direct Cost Ratio | 70.6% | % | All exp/Rev
Revenue per Unit (108) | 17442.2315 | USD | 108 units
Labor Hours per Unit | 135.6528 | hrs
Labor Cost per Unit | 4326.8287 | USD
Material Cost per Unit | 4653.8523 | USD
Direct Cost per Unit | 12313.5219 | USD
Rough-in Hours per Unit | 56.7685 | hrs
Revenue per Fixture | 2498.3568 | USD | 754 fixtures
Hours per Fixture | 19.4304 | hrs

## PO Commitments
PO Commitments
Inbound contract (GC → OWP). Outbound vendor commitments — see Material tab.
PO # | Date | Issuer | Type | Status | Description | Amount | Source
PRIME | 2018-03-09 | Chinn Construction, LLC | Lump Sum Subcontract | Closed | Luna Apartments plumbing (108 units + retail) — per Div 22 | 1766205 | 2041-Chinn Construction subcontract + Job Info sheet
CO-NET | — | Chinn Construction, LLC | Change Orders (executed, 18 COs) | Executed | Net CO impact (Sage 999 rev - orig) | 117556 | 2041 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
TOTAL (contract + COs) | [5 empty] | 1883761

## Billing & SOV
Billing & Schedule of Values
174 invoices to Chinn Construction, LLC. Retainage $93,941.20.
Invoice # | Date | Total Billed (signed) | Retainage (signed) | # Lines | Source
555 | 01/18/19 | -314824 | -15741.2 | 19 | 2041 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
587 | 02/20/18 | -87400 | -4370 | 2 | 2041 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
568 | 02/20/19 | -178786 | -8939.3 | 9 | 2041 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
569 | 02/20/19 | -14770 | -738.5 | 5 | 2041 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
687 | 03/20/19 | -139903 | -6995.15 | 11 | 2041 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
798 | 03/25/19 | 14770 | 738.5 | 1 | 2041 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
603 | 04/19/19 | -170820 | -8541 | 14 | 2041 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
514 | 05/18/18 | -90600 | -4530 | 2 | 2041 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
511 | 05/20/19 | -137558 | -6877.9 | 11 | 2041 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
608 | 06/19/19 | -98281 | -4914.05 | 3 | 2041 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
678 | 06/20/18 | -11763 | -588.15 | 2 | 2041 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
597 | 07/19/19 | -57390 | -2869.5 | 5 | 2041 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
591 | 08/20/18 | -28595 | -1429.75 | 2 | 2041 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
750 | 08/20/19 | -116144 | -5807.2 | 11 | 2041 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
471 | 09/19/18 | -34350 | -1717.5 | 2 | 2041 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
476 | 09/19/18 | 34350 | 1717.5 | 2 | 2041 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
477 | 09/19/18 | -27600 | -1380 | 2 | 2041 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
566 | 09/20/19 | -71280 | -3564 | 8 | 2041 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
526 | 10/19/18 | -50650 | -2532.5 | 4 | 2041 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
531 | 11/16/18 | -109550 | -5477.5 | 3 | 2041 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
234 | 12/04/19 | -1151 | -57.55 | 1 | 2041 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
235 | 12/04/19 | 1151 | 57.55 | 1 | 2041 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
236 | 12/04/19 | -1151 | 0 | 1 | 2041 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
231 | 12/10/19 | -2020 | 0 | 1 | 2041 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
379 | 12/11/19 | -1766 | 0 | 1 | 2041 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
474 | 12/13/19 | -1230 | -61.5 | 1 | 2041 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
352 | 12/14/18 | -186450 | -9322.5 | 2 | 2041 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
TOTAL (signed) |  | -1883761 | -93941.2

## Insights
Insights & Observations
Narrative findings from JDR + GDrive CO log
# | Insight | Detail | Confidence | Source
1 | MARGIN PROFILE | Net profit $553,900.64 on $1,883,761.00 revenue = 29.4% gross margin. | Verified | 2041 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
2 | CONTRACT CHANGE | Original $1,766,205.00 → final $1,883,761.00 = $+117,556.00 net (6.66%) across 18 executed COs. | Verified | 2041 Job Detail Report.pdf (Sage Timberline, 04/03/2026) + CO log
3 | LABOR PROFILE | Labor cost $467,297.50 (24.8% of rev) across 14,650 hrs and 44 workers. Blended wage $31.90/hr. | Verified | 2041 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
4 | VENDOR CONCENTRATION | Top 5 AP vendors: ~$441,025.56 (81% of AP). Top vendor: Rosen Supply Kirkland ($171,816.03). | Verified | 2041 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
5 | RETAINAGE | Retainage $93,941.20 — outstanding as of report date. | Verified | 2041 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
6 | ROUGH-IN SHARE | Code 120 Roughin Labor = 6,131 hrs (42% of labor hours). | Verified | 2041 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
7 | TOP COST CODE | Largest actual cost: 230 Finish Material = $251,663.70 | Verified | 2041 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
8 | WORKER CONCENTRATION | Top worker Rivera, Jorge A = 1,608 hrs (11% of total). | Verified | 2041 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
9 | INSURANCE | Not Wrap — retail-adjacent mixed-use. | Verified | OWP Project List with Schedule - UPDATED 04-01-26.xlsx
10 | SCOPE CONTEXT | Luna Apartments — 108-unit mixed-use (102 Type B + 6 Type A/ADA) + PCC retail + P1/P2 parking at 2749 California Avenue SW, Seattle, WA 98116. | Verified | Submittal TOC + scope doc

## Benchmark KPIs
Benchmark KPIs
Normalized metrics for cross-project comparison
KPI | Data Name | Value | Category | Notes | Confidence | Source Document
Job Number | job_number | 2041 | Profile | OWP job ID | Verified | 2041 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
Job Name | job_name | Luna @ 2749 California Ave | Profile |  | Verified | 2041 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
General Contractor | general_contractor | Chinn Construction, LLC | Profile |  | Verified | OWP Project List with Schedule - UPDATED 04-01-26.xlsx
Owner | owner | 2741 California LLC | Profile |  | Verified | OWP Project List with Schedule - UPDATED 04-01-26.xlsx
Architect | architect | Hewitt Architects | Profile |  | Verified | Chinn Luna project info.pdf
Location | location | 2749 California Avenue SW, Seattle, WA 98116 | Profile |  | Verified | OWP Project List with Schedule - UPDATED 04-01-26.xlsx
Project Type | project_type | 4-story mixed-use: 108 residential units + PCC retail ground floor + 2 parking levels (P1/P2) | Profile |  | Verified | Scope + Submittal TOC
Insurance Type | insurance | Not Wrap | Profile |  | Verified | OWP Project List with Schedule - UPDATED 04-01-26.xlsx
GC PM | gc_pm | Joe Hanley / Amir Molavi | Profile |  | Verified | 2041-Chinn Construction subcontract + Job Info sheet
GC Sup | gc_sup | James Casal | Profile |  | Verified | 2041-Chinn Construction subcontract + Job Info sheet
OWP Signatory | owp_signatory | Mike Donelson | Profile |  | Verified | 2041-Chinn Construction subcontract + Job Info sheet
Contract Signed Date | contract_signed_date | 2018-03-09 | Profile |  | Verified | 2041-Chinn Construction subcontract + Job Info sheet
Work Start | start_date | 2018-01 | Profile |  | Verified | 2041 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
Work End | end_date | 2019-12 | Profile |  | Verified | 2041 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
Duration (months) | duration_months | 24 | Profile |  | Verified | Derived
Unit Count | unit_count | 108 | Profile | 102 Type B + 6 Type A/ADA | Verified | Submittal TOC
Total Fixtures | total_fixtures | 754 | Profile | 656 unit + 98 retail/common | Verified | Submittal TOC
Contract Original | contract_original | 1766205 | Financial |  | Verified | OWP Project List with Schedule - UPDATED 04-01-26.xlsx
Contract Final | contract_final | 1883761 | Financial |  | Verified | OWP Project List with Schedule - UPDATED 04-01-26.xlsx
Change Orders ($) | co_net | 117556 | Financial | 18 executed | Verified | 2041 Job Detail Report.pdf (Sage Timberline, 04/03/2026) + CO log
CO % of Contract | co_pct | 6.656% | Financial |  | Verified | Derived
Revenue | revenue | 1883761 | Financial | AR total | Verified | 2041 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
Direct Cost | direct_cost | 1329860.36 | Financial | JDR Expenses | Verified | 2041 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
Net Profit | net_profit | 553900.64 | Financial | Rev - Exp | Verified | 2041 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
Gross Margin | gross_margin | 29.4% | Financial |  | Verified | Derived
Retainage | retainage | 93941.2 | Financial | JDR AR retainage | Verified | 2041 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
Retainage % of Revenue | retainage_pct | 4.987% | Financial |  | Verified | Derived
Labor Cost | labor_cost | 467297.5 | Labor | Codes 100-151 | Verified | 2041 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
Material Cost | material_cost | 502616.05 | Material | Codes 210-245 | Verified | 2041 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
Overhead Cost | overhead_cost | 111779.65 | Financial | Codes 600-607 | Verified | 2041 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
Burden Cost | burden_cost | 211657.53 | Labor | Code 995 | Verified | 2041 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
Tax Cost | tax_cost | 36509.63 | Labor | Code 998 | Verified | 2041 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
Total Labor Hours | total_hours | 14650.5 | Labor | Sum labor codes | Verified | 2041 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
Total Workers | total_workers | 44 | Labor | Unique PR IDs | Verified | 2041 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
Blended Gross Wage | blended_wage | 31.8964 | Labor |  | Verified | Derived
Fully-Loaded Wage | loaded_wage | 66.4535 | Labor |  | Verified | Derived
Burden Multiplier | burden_mult | 1.3421 | Labor |  | Verified | Derived
Rough-in Hours | roughin_hours | 6131 | Labor | Code 120 | Verified | 2041 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
Finish Hours | finish_hours | 1290 | Labor | Code 130 | Verified | 2041 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
Revenue per Hour | rev_per_hour | 128.58 | Productivity |  | Verified | Derived
Profit per Hour | profit_per_hour | 37.8076 | Productivity |  | Verified | Derived
Revenue per Unit | rev_per_unit | 17442.2315 | Productivity | 108 units | Verified | Derived
Direct Cost per Unit | cost_per_unit | 12313.5219 | Productivity |  | Verified | Derived
Hours per Unit | hours_per_unit | 135.6528 | Productivity |  | Verified | Derived
Revenue per Fixture | rev_per_fixture | 2498.3568 | Productivity | 754 fixtures | Verified | Derived
Labor % of Revenue | labor_pct | 24.81% | Cost Mix |  | Verified | Derived
Material % of Revenue | material_pct | 26.68% | Cost Mix |  | Verified | Derived
Total Vendors | total_vendors | 22 | Material |  | Verified | 2041 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
Total Invoices | total_invoices | 27 | Billing |  | Verified | 2041 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
Top Worker Share | top_worker_share | 10.98% | Crew |  | Verified | Derived
Top 5 Worker Share | top5_worker_share | 50.21% | Crew |  | Verified | Derived
Cost Codes Active | cost_code_count | 29 | Structure |  | Verified | 2041 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
Executed CO Count | executed_co_count | 18 | Documents |  | Verified | CO log
COR Count | cor_count | 20 | Documents |  | Verified | GDrive COR folder
RFI/ASI Count | rfi_asi_count | 74 | Documents |  | Verified | GDrive ASI-RFI folder
Submittal Count | submittal_count | 82 | Documents |  | Verified | GDrive Submittals
PO Total (all) | po_count_total | 197 | Documents | placed+scheduled+completed | Verified | GDrive POs

## Vendors
Vendors — AP Summary
Vendor-level spend ranking
Rank | Vendor ID | Vendor Name | Total Spend | # Transactions | % of AP | Source
1 | 1380RS | Rosen Supply Kirkland | 171816.03 | 97 | 31.44% | 2041 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
2 | 1130CS | Consolidated Supply Co. | 124509.19 | 50 | 22.78% | 2041 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
3 | 1625FE | Franklin Engineering | 57662.63 | 17 | 10.55% | 2041 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
4 | 1231KS | Keller Supply Company | 51636.71 | 20 | 9.448% | 2041 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
5 | 5560CH | California Hydronics Corp | 35401 | 3 | 6.478% | 2041 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
6 | 3129MR | Mechanical Resource Services, Inc. | 27506.25 | 2 | 5.033% | 2041 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
7 | 1175FE | Ferguson Enterprises, Inc. #3007 | 19078.32 | 31 | 3.491% | 2041 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
8 | 7423OC | Old Castle Infrastructure, Inc. | 12187 | 3 | 2.23% | 2041 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
9 | 1234CO | Capital One Credit Card | 10916.31 | 35 | 1.997% | 2041 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
10 | 2713AR | Ahern Rentals | 9940.79 | 25 | 1.819% | 2041 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
11 | 1609QC | Quality Concrete Products, Inc. $32 | 7385 | 1 | 1.351% | 2041 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
12 | 5621HD | Core & Main LP $HD Supply Waterworks | 5930.19 | 4 | 1.085% | 2041 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
13 | 2041RS | Rosen Supply Company, Inc. $Cal Luna | 4157.49 | 6 | 0.7607% | 2041 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
14 | 3181SC | Scan2Core, Inc. | 3465 | 5 | 0.634% | 2041 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
15 | 5919PW | Patchworks, Inc. | 2720 | 1 | 0.4977% | 2041 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
16 | 1799AW | AllWest Underground, Inc. | 597.74 | 1 | 0.1094% | 2041 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
17 | 8068MI | Kele, Inc $ MI Controls | 570.89 | 2 | 0.1045% | 2041 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
18 | 3612MS | Mechanical Sales, Inc. | 290.58 | 1 | 0.05317% | 2041 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
19 | 1288DR | DRSi | 280.6 | 2 | 0.05134% | 2041 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
20 | 1641AR | A.R. Brown Backflow Testing | 225 | 1 | 0.04117% | 2041 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
21 | 2132MH | Manor Hardware & Construction Supply | 155 | 1 | 0.02836% | 2041 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
22 | 2041KS | Keller Supply Co. $Cali Luna | 81.64 | 1 | 0.01494% | 2041 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
TOTAL |  |  | 546513.36 | 309

## Change Log
Change Log — Master Register
Contract, 18 executed COs, retainage events — JDR + GDrive CO folder
Event ID | Type | Date | Subject | Originator | Cost Impact ($) | Status | Source
CONTRACT-ORIG | Contract | 2018-03-09 | Prime subcontract — Lump Sum $1,766,205.00 | Chinn Construction, LLC | 1766205 | Executed | 2041-Chinn Construction subcontract + Job Info sheet
CO-01 | Change Order | — | CD Drawing Changes | Chinn Construction, LLC | 1963 | Executed | GDrive CO 1
CO-02 | Change Order | — | RFI-004 Delete Roof Drains | Chinn Construction, LLC | 595 | Executed | GDrive CO 2
CO-03 | Change Order | — | Garage Exhaust Shaft Drain | Chinn Construction, LLC | 9918 | Executed | GDrive CO 3
CO-04 | Change Order | — | Lower Grease Interceptor per PCC Request | Chinn Construction, LLC | 900 | Executed | GDrive CO 4
CO-05 | Change Order | — | Deduct — Bock water heaters → HTP boilers | Chinn Construction, LLC | -15600 | Executed | GDrive CO 5
CO-06 | Change Order | — | Added Plumbing Items for PCC | Chinn Construction, LLC | 1110 | Executed | GDrive CO 6
CO-07 | Change Order | — | Roof Drain Changes | Chinn Construction, LLC | 48643 | Executed | GDrive CO 7
CO-08 | Change Order | — | ASI-010 Added Mop Sink & Move Coffee Maker | Chinn Construction, LLC | 1438 | Executed | GDrive CO 8
CO-09 | Change Order | — | Grease Waste Pumping (r1) | Chinn Construction, LLC | 619 | Executed | GDrive CO 9
CO-10 | Change Order | — | Added Planter Drain | Chinn Construction, LLC | 2112 | Executed | GDrive CO 10
CO-11 | Change Order | — | Damaged Scissor Lift (backcharge) | Chinn Construction, LLC | 596 | Executed | GDrive CO 11
CO-12 | Change Order | — | Move Plumbing at PCC Patio | Chinn Construction, LLC | 31581 | Executed | GDrive CO 12
CO-13 | Change Order | — | Move Gas Line Unit 411 | Chinn Construction, LLC | 19200 | Executed | GDrive CO 13
CO-14 | Change Order | — | Insulate Waste Lines above PCC (r1) | Chinn Construction, LLC | 845 | Executed | GDrive CO 14
CO-15 | Change Order | — | Overtime Premium | Chinn Construction, LLC | 2020 | Executed | GDrive CO 15
CO-16 | Change Order | — | Re-route Condensate Drains over Loading Dock | Chinn Construction, LLC | 2029 | Executed | GDrive CO 16
CO-17 | Change Order | — | Pressure-Flush Toilets in Amenity Baths | Chinn Construction, LLC | 3420 | Executed | GDrive CO 17
CO-18 | Change Order | — | Move PSE Meter Vent | Chinn Construction, LLC | 1320 | Executed | GDrive CO 18
XT-A | Budget Transfer | — | Attic Stock Toilets (budget transfer) | Chinn Construction, LLC | 1766 | Documented | GDrive BUDGET TRANSFERS
XT-B | Budget Transfer | — | Move PSE Gas Vent (budget transfer, likely duplicate of CO #18 line) | Chinn Construction, LLC | 2020 | Documented | GDrive BUDGET TRANSFERS
XT-C | Budget Transfer | — | Pressure-Flush Toilets Amenity (budget transfer, likely duplicate of CO #17 line) | Chinn Construction, LLC | 1151 | Documented | GDrive BUDGET TRANSFERS
FIRST-INVOICE | Invoice | 01/18/19 | First billing (per JDR) | Sub (OWP) | 0 | Paid | 2041 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
LAST-INVOICE | Invoice | 12/14/18 | Last billing (per JDR) | Sub (OWP) | 0 | Paid | 2041 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
RETAINAGE-OPEN | Retainage | As of 04/03/2026 | Retainage $93,941.20 (outstanding) | GC | 0 | Outstanding | 2041 Job Detail Report.pdf (Sage Timberline, 04/03/2026)

## Root Cause Analysis
Root Cause Analysis
Primary variance drivers by category
Category | Codes | Net $ Variance | Root Cause (inferred) | Notes
Contract Change | 999 (Sales) | 117556 | JDR-implied net CO impact | $1,766,205 → $1,883,761 (18 executed COs)
Labor | 100,101,110,111,112,120,130,140,141,142,143,145,150 | 18387.5 | Labor variance vs revised budget | 44 workers
Material | 210,211,212,213,220,230,240,241,242,243,244,245 | -137108.95 | Material procurement variance | 22 vendors
Overhead | 600,601,602,603,604,607 | 6233.65 | Engineering/permits/subcon variance
Burden+Tax | 995+998 | 10471.76 | Payroll accrual tracking labor
TOTAL NET VARIANCE |  | 15539.96
RESPONSIBILITY ATTRIBUTION
Responsible Party | # Drivers | Net $ Impact | Notes
GC / Owner (scope changes) | 18 | 117556 | Aggregate executed COs
Sub (OWP) labor performance | 12 | 18387.5 | Hours + rate vs budget
Sub (OWP) material procurement | 9 | -137108.95 | 22 vendors
OWP burden accrual | 2 | 10471.76 | Payroll burden + tax
OWP overhead | 5 | 6233.65 | Engineering/permits/subcon

## Predictive Signals
Predictive Signals
Leading indicators from JDR + CO log
CURRENT-STATE SIGNALS
Indicator | Current Value | Benchmark | Status | Meaning
Contract Change % | 6.66% | ±10% | HEALTHY | +6.66% net (18 COs)
Labor % of Revenue | 24.81% | <30% | HEALTHY | 24.8%
GL Overhead % of Revenue | 3.076% | <5% | HEALTHY | 3.1%
Vendor Concentration (Top 5) | 80.7% | <95% | HEALTHY | Top 5 = 81% of AP
Retainage % | 4.987% | <10% | HEALTHY | 5.0%
Gross Margin | 29.4% | >30% | WATCH | 29.4%
Labor Hrs Total | 14650.5 | varies | INFO | 14,650 hrs, 44 workers
Worker Concentration (top 1) | 10.98% | <25% | HEALTHY | 11.0% (Rivera, Jorge A)
Rough-in Labor Share | 42.09% | 40-65% | HEALTHY | 42%
Retainage Legacy | OUTSTANDING | <90 days post-closeout | WATCH | $93,941.20
FORECAST MODELS
Forecast | Current Estimate | Confidence | Driver | Model Note
Final margin (actual) | 29.4% | Actual | Job closed | 29.4%
Retainage collection | $93,941.20 | Outstanding | Legacy | Outstanding
Unit-level economics | $17,442/unit rev, $5,129/unit profit | Verified | 108 units | 4-story mixed-use: 108 residential units + PCC retail ground floor + 2 parking levels (P1/P2)

## Metric Registry
Metric Registry — Cortex Data Catalog
Every metric with data_label, confidence, and source
# | Data Label | Human Label | Value | Unit | Source Tab | Confidence | Source Document(s)
1 | job_number | Job Number | 2041 | id | Benchmark KPIs | Verified | 2041 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
2 | job_name | Job Name | Luna @ 2749 California Ave | text | Benchmark KPIs | Verified | 2041 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
3 | general_contractor | General Contractor | Chinn Construction, LLC | text | Benchmark KPIs | Verified | OWP Project List with Schedule - UPDATED 04-01-26.xlsx
4 | owner | Owner | 2741 California LLC | text | Benchmark KPIs | Verified | OWP Project List with Schedule - UPDATED 04-01-26.xlsx
5 | architect | Architect | Hewitt Architects | text | Benchmark KPIs | Verified | Chinn Luna project info.pdf
6 | location | Location | 2749 California Avenue SW, Seattle, WA 98116 | text | Benchmark KPIs | Verified | OWP Project List with Schedule - UPDATED 04-01-26.xlsx
7 | project_type | Project Type | 4-story mixed-use: 108 residential units + PCC retail ground floor + 2 parking levels (P1/P2) | text | Benchmark KPIs | Verified | Scope + Submittal TOC
8 | insurance | Insurance Type | Not Wrap | text | Benchmark KPIs | Verified | OWP Project List with Schedule - UPDATED 04-01-26.xlsx
9 | gc_pm | GC PM | Joe Hanley / Amir Molavi | text | Benchmark KPIs | Verified | 2041-Chinn Construction subcontract + Job Info sheet
10 | gc_sup | GC Sup | James Casal | text | Benchmark KPIs | Verified | 2041-Chinn Construction subcontract + Job Info sheet
11 | owp_signatory | OWP Signatory | Mike Donelson | text | Benchmark KPIs | Verified | 2041-Chinn Construction subcontract + Job Info sheet
12 | contract_signed_date | Contract Signed Date | 2018-03-09 | date | Benchmark KPIs | Verified | 2041-Chinn Construction subcontract + Job Info sheet
13 | start_date | Work Start | 2018-01 | date | Benchmark KPIs | Verified | 2041 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
14 | end_date | Work End | 2019-12 | date | Benchmark KPIs | Verified | 2041 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
15 | duration_months | Duration (months) | 24 | months | Benchmark KPIs | Verified | Derived
16 | unit_count | Unit Count | 108 | units | Benchmark KPIs | Verified | Submittal TOC
17 | total_fixtures | Total Fixtures | 754 | count | Benchmark KPIs | Verified | Submittal TOC
18 | contract_original | Contract Original | 1766205 | USD | Benchmark KPIs | Verified | OWP Project List with Schedule - UPDATED 04-01-26.xlsx
19 | contract_final | Contract Final | 1883761 | USD | Benchmark KPIs | Verified | OWP Project List with Schedule - UPDATED 04-01-26.xlsx
20 | co_net | Change Orders ($) | 117556 | USD | Benchmark KPIs | Verified | 2041 Job Detail Report.pdf (Sage Timberline, 04/03/2026) + CO log
21 | co_pct | CO % of Contract | 6.656% | % | Benchmark KPIs | Verified | Derived
22 | revenue | Revenue | 1883761 | USD | Benchmark KPIs | Verified | 2041 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
23 | direct_cost | Direct Cost | 1329860.36 | USD | Benchmark KPIs | Verified | 2041 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
24 | net_profit | Net Profit | 553900.64 | USD | Benchmark KPIs | Verified | 2041 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
25 | gross_margin | Gross Margin | 29.4% | % | Benchmark KPIs | Verified | Derived
26 | retainage | Retainage | 93941.2 | USD | Benchmark KPIs | Verified | 2041 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
27 | retainage_pct | Retainage % of Revenue | 4.987% | % | Benchmark KPIs | Verified | Derived
28 | labor_cost | Labor Cost | 467297.5 | USD | Benchmark KPIs | Verified | 2041 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
29 | material_cost | Material Cost | 502616.05 | USD | Benchmark KPIs | Verified | 2041 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
30 | overhead_cost | Overhead Cost | 111779.65 | USD | Benchmark KPIs | Verified | 2041 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
31 | burden_cost | Burden Cost | 211657.53 | USD | Benchmark KPIs | Verified | 2041 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
32 | tax_cost | Tax Cost | 36509.63 | USD | Benchmark KPIs | Verified | 2041 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
33 | total_hours | Total Labor Hours | 14650.5 | hours | Benchmark KPIs | Verified | 2041 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
34 | total_workers | Total Workers | 44 | count | Benchmark KPIs | Verified | 2041 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
35 | blended_wage | Blended Gross Wage | 31.8964 | USD/hr | Benchmark KPIs | Verified | Derived
36 | loaded_wage | Fully-Loaded Wage | 66.4535 | USD/hr | Benchmark KPIs | Verified | Derived
37 | burden_mult | Burden Multiplier | 1.3421 | x | Benchmark KPIs | Verified | Derived
38 | roughin_hours | Rough-in Hours | 6131 | hours | Benchmark KPIs | Verified | 2041 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
39 | finish_hours | Finish Hours | 1290 | hours | Benchmark KPIs | Verified | 2041 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
40 | rev_per_hour | Revenue per Hour | 128.58 | USD/hr | Benchmark KPIs | Verified | Derived
41 | profit_per_hour | Profit per Hour | 37.8076 | USD/hr | Benchmark KPIs | Verified | Derived
42 | rev_per_unit | Revenue per Unit | 17442.2315 | USD | Benchmark KPIs | Verified | Derived
43 | cost_per_unit | Direct Cost per Unit | 12313.5219 | USD | Benchmark KPIs | Verified | Derived
44 | hours_per_unit | Hours per Unit | 135.6528 | hours | Benchmark KPIs | Verified | Derived
45 | rev_per_fixture | Revenue per Fixture | 2498.3568 | USD | Benchmark KPIs | Verified | Derived
46 | labor_pct | Labor % of Revenue | 24.81% | % | Benchmark KPIs | Verified | Derived
47 | material_pct | Material % of Revenue | 26.68% | % | Benchmark KPIs | Verified | Derived
48 | total_vendors | Total Vendors | 22 | count | Benchmark KPIs | Verified | 2041 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
49 | total_invoices | Total Invoices | 27 | count | Benchmark KPIs | Verified | 2041 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
50 | top_worker_share | Top Worker Share | 10.98% | % | Benchmark KPIs | Verified | Derived
51 | top5_worker_share | Top 5 Worker Share | 50.21% | % | Benchmark KPIs | Verified | Derived
52 | cost_code_count | Cost Codes Active | 29 | count | Benchmark KPIs | Verified | 2041 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
53 | executed_co_count | Executed CO Count | 18 | count | Benchmark KPIs | Verified | CO log
54 | cor_count | COR Count | 20 | count | Benchmark KPIs | Verified | GDrive COR folder
55 | rfi_asi_count | RFI/ASI Count | 74 | count | Benchmark KPIs | Verified | GDrive ASI-RFI folder
56 | submittal_count | Submittal Count | 82 | count | Benchmark KPIs | Verified | GDrive Submittals
57 | po_count_total | PO Total (all) | 197 | count | Benchmark KPIs | Verified | GDrive POs

## Reconciliation
Reconciliation
Cross-sheet formula checks
# | Check | Value A | Value B | Delta | Status | Tabs
1 | Revenue = Contract Final | 1883761 | 1883761 | 0 | TIES | 1↔8
2 | Expenses = Labor+Mat+OH+Burden+Tax | 1329860.36 | 1329860.36 | 0 | TIES | 1↔3
3 | Net Profit = Revenue - Expenses | 553900.64 | 553900.64 | 0 | TIES | 1↔Derived
4 | Sage 999 actual = -Revenue | 1883761 | 1883761 | 0 | TIES | 2↔1
5 | Total Hours = Worker hours sum | 14650.5 | 14650.5 | 0 | TIES | 5↔2
6 | Contract Final - Orig = CO implied | 117556 | 117556 | 0 | TIES | 11↔Derived
7 | Worker count | 44 | 44 | 0 | TIES | 5↔1
8 | Cost code count | 29 | 29 | 0 | TIES | 2↔16