## Overview
Job #2042 · Metro Line Flats (Boren & Spruce)
Cortex JCR v2 • Shelter Holdings (customer 2042SH) • 915 East Spruce Street, Seattle, WA 98122 • Owner: Boren and Spruce, LLC
PROJECT OVERVIEW
Project Job # | 2042 |  | 2042 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
Project Name (Sage) | ShelterHoldings MetroLine |  | 2042 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
Project Description | Metro Line Flats — 72-unit 7-story midrise multi-family (4 Type A ADA), Seattle |  | OWP Project List with Schedule - UPDATED 04-01-26.xlsx + contract
General Contractor | Shelter Holdings |  | OWP Project List with Schedule - UPDATED 04-01-26.xlsx
Customer Code (Sage) | 2042SH |  | 2042 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
Owner / Developer | Boren and Spruce, LLC |  | OWP Project List with Schedule - UPDATED 04-01-26.xlsx
GC PM | TBD |  | 2042-Shelter Holdings subcontract SC-53799-027 + Boren & Spruce CO docs
GC Superintendent | Brett (Metro Line plan review Brett folder) |  | 2042-Shelter Holdings subcontract SC-53799-027 + Boren & Spruce CO docs
GC PE | N/A |  | 2042-Shelter Holdings subcontract SC-53799-027 + Boren & Spruce CO docs
OWP Signatory | Mike Donelson |  | 2042-Shelter Holdings subcontract SC-53799-027 + Boren & Spruce CO docs
Jobsite Location | 915 East Spruce Street, Seattle, WA 98122 |  | OWP Project List with Schedule - UPDATED 04-01-26.xlsx
Insurance | Not Wrap |  | OWP Project List with Schedule - UPDATED 04-01-26.xlsx
Fixture Schedule | 502 fixtures total (656 unit + 98 retail/common) |  | Submittal Table of Contents + Plumbing Scope
Architect | TBD |  | Metro Line Flats project info.pdf
Contract Type | Lump Sum |  | 2042-Shelter Holdings subcontract SC-53799-027 + Boren & Spruce CO docs
Unit Count | 72 |  | Submittal TOC (102 Type B + 6 Type A/ADA)
Work Period | 2017-09 start → 2019-04 (19 months) |  | JDR PR/AR dates
CONTRACT VALUE |  | NET PROFIT | DIRECT COST | LABOR HOURS
922104 |  | 328519.48 | 593584.52 | 7215
Original $998,152.29 + ($13,882.05) COs (1.39%) |  | 35.6% margin | 64.4% of revenue | 35 workers
SCOPE OF WORK
Full plumbing installation per Division 22: underground, garage, rough-in, finish, gas, water main, insulation, roof drains.
72-unit mixed-use (102 Type B + 6 Type A/ADA) at 915 East Spruce Street, Seattle, WA 98122, 7-story midrise multi-family (Type 1A podium + Type VA above).
GC: Shelter Holdings (2042SH); Owner: Boren and Spruce, LLC.
Insurance: Not Wrap (retail-adjacent residential).
Project team: TBD (GC PM) · Brett (Metro Line plan review Brett folder) (GC Sup) · TBD (Architect) · Mike Donelson (OWP signatory).
SOURCES
Canonical financial source: 2042 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
Job totals (JDR footer): Revenue $922,104.00 / Expenses $593,584.52 / Net $328,519.48 / Retainage $46,105.20
Source breakdown (derived): PR $295,397.92 · AP $268,713.50 · GL $29,473.10
Contract: Lump Sum $998,152.29 → $1,012,034.34
Change Orders (executed): $13,882.05 net across 5 COs (CO log in enriched meta)
Project Team: TBD (PM) · Brett (Metro Line plan review Brett folder) (Sup) · TBD · Boren and Spruce, LLC
PROJECT TEAM (OWP Job Info)
Role | Status | Name / Firm
GC | Extracted | Shelter Holdings
GC PM | Extracted | TBD
GC Superintendent | Extracted | Brett (Metro Line plan review Brett folder)
GC PE | N/A | N/A
Owner | Extracted | Boren and Spruce, LLC
Architect | Extracted | TBD
Structural | N/A | N/A
Acoustical | N/A | N/A
ADA Consultant | N/A | N/A
Interior Design | N/A | N/A
MEP Engineer | N/A | N/A
Insurance | Extracted | Not Wrap
OWP Signatory | Extracted | Mike Donelson

## Budget vs Actual
Budget vs Actual
All 25 cost codes from JDR. Contract $998,152 → $1,012,034.
Cost Code | Description | Original Budget | Revised Budget | Actual | Variance | % of Revised | Hours | Source
100 | Supervision | 5760 | 5760 | 1676 | -4084 | 29.1% | 33 | 2042 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
101 | Takeoff & Purchase Labor | 10440 | 10440 | 7902.5 | -2537.5 | 75.69% | 147 | 2042 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
110 | Underground Labor | 20608 | 20608 | 8776.5 | -11831.5 | 42.59% | 249 | 2042 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
112 | Canout Labor | 3110 | 3550 | 3698.5 | 148.5 | 104.2% | 112 | 2042 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
120 | Roughin Labor | 105400 | 106060 | 128045 | 21985 | 120.7% | 4990 | 2042 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
130 | Finish Labor | 21840 | 22595 | 16956.5 | -5638.5 | 75.05% | 651 | 2042 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
140 | Gas Labor | 2400 | 2400 | 1625.5 | -774.5 | 67.73% | 41 | 2042 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
141 | Water Main/Insulation Lab | 26080 | 26080 | 13633.5 | -12446.5 | 52.28% | 585.5 | 2042 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
142 | Mech Room Labor | 17500 | 17750 | 12026.5 | -5723.5 | 67.75% | 284.5 | 2042 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
210 | Underground Material | 15383 | 15383 | 5226.84 | -10156.16 | 33.98% |  | 2042 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
211 | Garage Material | 0 | 0 | 1607.11 | 1607.11 |  |  | 2042 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
212 | Canout Material | 3480 | 3480 | 2967.63 | -512.37 | 85.28% |  | 2042 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
220 | Roughin Material | 74450 | 74650 | 62128.4 | -12521.6 | 83.23% |  | 2042 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
230 | Finish Material | 162699 | 168539 | 148333.68 | -20205.32 | 88.01% |  | 2042 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
240 | Gas Material | 7150 | 7150 | 665.67 | -6484.33 | 9.31% |  | 2042 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
241 | Water Main/Insulation Mat | 8935 | 8935 | 13163.4 | 4228.4 | 147.3% |  | 2042 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
242 | Mech Room Material | 38400 | 38653 | 16059.71 | -22593.29 | 41.55% |  | 2042 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
243 | Condensation Drains Mat | 0 | 0 | 91.07 | 91.07 |  |  | 2042 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
600 | Subcontractor | 1000 | 1000 | 215 | -785 | 21.5% |  | 2042 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
601 | Engineering/Plans | 27000 | 27000 | 32640.89 | 5640.89 | 120.9% |  | 2042 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
603 | Permits & Licenses | 5930 | 5930 | 4774.5 | -1155.5 | 80.51% |  | 2042 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
607 | Other Expenses | 8500 | 8500 | 10312.7 | 1812.7 | 121.3% |  | 2042 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
995 | Payroll Burden | 94526.7 | 95452.9 | 86190.15 | -9262.75 | 90.3% |  | 2042 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
998 | Payroll Taxes | 16305.06 | 16466.1 | 14867.27 | -1598.83 | 90.29% |  | 2042 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
999 | Sales | -906587 | -922104 | -922104 | 0 | 100% |  | 2042 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
TOTAL |  | -229690.24 | -235722 | -328519.48 | -92797.48 |  | 7093

## Cost Breakdown
Cost Breakdown by Category
Direct cost composition by category from JDR cost codes
Category | Cost Codes | Actual $ | % of Direct Cost | % of Revenue | Source
Labor | 100,101,110,112,120,130,140,141,142 | 194340.5 | 32.74% | 21.08% | 2042 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
Material | 210,211,212,220,230,240,241,242,243 | 250243.51 | 42.16% | 27.14% | 2042 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
Overhead | 600,601,603,607 | 47943.09 | 8.077% | 5.199% | 2042 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
Payroll Burden | 995 | 86190.15 | 14.52% | 9.347% | 2042 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
Payroll Taxes | 998 | 14867.27 | 2.505% | 1.612% | 2042 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
TOTAL DIRECT COST |  | 593584.52 | 100% | 64.37%

## Material
Material Purchases — AP Vendors
Material + subcontractor spend by vendor from JDR AP records
Vendor ID | Vendor Name | Total Spend | # Transactions | Category (inferred) | Source
2042RS | Rosen Supply Company, Inc. $Metro Flats | 49362.67 | 26 | Plumbing / Supplies | 2042 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
5560CH | California Hydronics Corp | 49222 | 3 | Plumbing / Supplies | 2042 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
2042CS | Consolidated Supply Co. $Metro Flats | 44219.62 | 16 | Plumbing / Supplies | 2042 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
1130CS | Consolidated Supply Co. | 33109.64 | 15 | Plumbing / Supplies | 2042 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
1625FE | Franklin Engineering | 32392.25 | 8 | Engineering (601) | 2042 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
1175FE | Ferguson Enterprises, Inc. #3007 | 17571.09 | 16 | Plumbing / Supplies | 2042 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
1231KS | Keller Supply Company | 14550.79 | 18 | Plumbing / Supplies | 2042 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
1234CO | Capital One Credit Card | 13819.24 | 47 | Credit Card (mixed) | 2042 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
1380RS | Rosen Supply Kirkland | 6263.82 | 10 | Plumbing / Supplies | 2042 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
2042FE | Ferguson Enterprises, Inc. $Metro Flats | 3356.24 | 3 | Plumbing / Supplies | 2042 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
2042KS | Keller Supply Co. $Metro Flats | 2982.64 | 2 | Plumbing / Supplies | 2042 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
1234BA | Bank of America CC | 977.21 | 3 | Credit Card (mixed) | 2042 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
1609QC | Quality Concrete Products, Inc. $32 | 251 | 2 | Uncategorized | 2042 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
1288DR | DRSi | 248.64 | 1 | Uncategorized | 2042 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
1641AR | A.R. Brown Backflow Testing | 215 | 1 | Testing subcontractor | 2042 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
3612MS | Mechanical Sales, Inc. | 145.29 | 1 | Plumbing / Supplies | 2042 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
1021AT | ACME Corp | 26.36 | 1 | Uncategorized | 2042 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
2040CS | Consolidated Supply Co. $65th Apts | 0 | 2 | Plumbing / Supplies | 2042 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
TOTAL |  | 268713.5 | 175

## Crew & Labor
Crew & Labor — Worker Roster
All 35 unique payroll workers. OWP signatory: Mike Donelson.
Worker ID | Worker Name | Total Hours | Gross Pay | Blended Wage ($/hr) | # Work Days | Source
RE18 | Reed, Reuben H | 1271 | 52053 | 40.9544 | 44 | 2042 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
ME52 | Mendoza, Edgar E | 899 | 18781 | 20.891 | 27 | 2042 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
LU09 | Lucas Tzintzun, Rafael | 771.5 | 12789 | 16.5768 | 21 | 2042 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
CR87 | Cruz Reyes, Jose | 682 | 16350 | 23.9736 | 19 | 2042 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
CR79 | Cruz Guzman, Joel A | 665 | 15320 | 23.0376 | 19 | 2042 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
BE45 | Belcher, Jacob T | 532 | 9047 | 17.0056 | 14 | 2042 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
RE91 | Reyes, Maria E | 282.5 | 4027.5 | 14.2566 | 10 | 2042 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
GA70 | Garcia, Jordan X | 267 | 8277 | 31 | 9 | 2042 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
VE43 | Velasquez Cruz, Osman N | 227 | 4028 | 17.7445 | 7 | 2042 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
VE42 | Velasquez Cruz, Denis M | 202 | 5481 | 27.1337 | 5 | 2042 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
GO51 | Gomez Reyes, Edith N | 192.5 | 4525.25 | 23.5078 | 10 | 2042 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
BA70 | Barnhart, Joseph N | 163 | 7329 | 44.9632 | 26 | 2042 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
HU06 | Hubbard, Robert W | 161 | 6735.5 | 41.8354 | 28 | 2042 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
SA54 | Sanders, Allen O | 111.5 | 5491.25 | 49.2489 | 25 | 2042 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
DO56 | Donelson, Richard T | 97 | 5525 | 56.9588 | 44 | 2042 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
HO18 | Hoeg, Xavier A | 86 | 1312.5 | 15.2616 | 3 | 2042 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
GE69 | Gerard, Jeffrey S | 86 | 4116 | 47.8605 | 30 | 2042 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
KI55 | Kinssies, Jr, John E | 79.5 | 1908 | 24 | 5 | 2042 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
MC09 | McCabe, Thomas C | 58 | 1914 | 33 | 4 | 2042 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
AN14 | Anderson, Richard P | 57.25 | 2404.5 | 42 | 4 | 2042 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
SI48 | Silva Morales, Jair J | 53 | 1272 | 24 | 2 | 2042 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
TR60 | Trower-Kelly, Fidel D | 45 | 760 | 16.8889 | 6 | 2042 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
EL33 | Eliassen, Cory H | 31.5 | 812.5 | 25.7937 | 5 | 2042 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
BA68 | Barbosa, Michael S | 30 | 630 | 21 | 3 | 2042 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
MA71 | Martinez Reyes, Juan C | 30 | 720 | 24 | 3 | 2042 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
FO55 | Fonseca Teruel, Eduardo | 24.5 | 445.5 | 18.1837 | 3 | 2042 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
WE55 | Wennig, Johnathan M | 20.75 | 539.5 | 26 | 2 | 2042 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
SE64 | Sepulveda Gonzalez, Alfredo | 19 | 608 | 32 | 3 | 2042 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
LO58 | Lopez Reyes, Boris O | 16 | 288 | 18 | 2 | 2042 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
CO71 | Cortes Mendiola, Victor H | 16 | 0 | 0 | 2 | 2042 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
GE70 | Gerard, Jordan E | 13 | 442 | 34 | 2 | 2042 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
ST02 | Stahlschmidt, John P | 8 | 136 | 17 | 1 | 2042 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
HU04 | Hubbard, Dustin R | 6 | 42 | 7 | 2 | 2042 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
RO06 | Roberts, Lake A | 6 | 126 | 21 | 1 | 2042 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
HE70 | Hernandez Gonzalez, Osbaldo | 5.5 | 104.5 | 19 | 1 | 2042 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
TOTAL |  | 7215 | 194340.5

## Crew Analytics
Crew Analytics
Team-level labor productivity, concentration, wage dispersion
TEAM-LEVEL METRICS
Metric | Value | Notes | Source
Total Workers | 35 | Unique payroll IDs | 2042 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
Total Labor Hours | 7215 | Sum of labor codes | 2042 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
Total Gross Pay | 194340.5 | Sum of labor codes | 2042 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
Blended Gross Wage ($/hr) | 26.9356 | Labor$/Hrs (pre-burden) | Derived
Top Worker Hours Share | 17.62% | RE18 Reed, Reuben H (1271 hrs) | Derived
Top 5 Workers Hours Share | 59.44% | Concentration metric | Derived
Highest Wage Rate ($/hr) | 56.9588 | Single-worker blended | Derived
Lowest Wage Rate ($/hr) | 0 | Single-worker blended | Derived
Avg Hours per Worker | 206.1429 | Includes short-tenure workers | Derived
Avg Project Days per Worker | 11.2 | Mean days | Derived

## Productivity
Productivity Metrics
Normalized ratios. Per-unit from 72 units (502 fixtures).
Metric | Value | Basis | Source / Note
Revenue per Labor Hour | 127.8037 | USD/hr
Profit per Labor Hour | 45.5328 | USD/hr
Labor Cost per Hour (blended) | 26.9356 | USD/hr | Pre-burden
Fully-Loaded Labor Rate ($/hr) | 54.9488 | USD/hr | Incl burden+taxes
Burden Multiplier | 1.3421 | x | Fully-loaded/blended
Rough-in Hours (code 120) | 4990 | hrs
Finish Hours (code 130) | 651 | hrs
Rough-in % of Total Hours | 70.35% | %
Gross Margin | 35.63% | %
Labor % of Revenue | 21.08% | %
Material % of Revenue | 27.14% | %
Direct Cost Ratio | 64.37% | % | All exp/Rev
Revenue per Unit (72) | 12807 | USD | 72 units
Labor Hours per Unit | 100.2083 | hrs
Labor Cost per Unit | 2699.1736 | USD
Material Cost per Unit | 3475.6043 | USD
Direct Cost per Unit | 8244.2294 | USD
Rough-in Hours per Unit | 69.3056 | hrs
Revenue per Fixture | 1836.8606 | USD | 502 fixtures
Hours per Fixture | 14.3725 | hrs

## PO Commitments
PO Commitments
Inbound contract (GC → OWP). Outbound vendor commitments — see Material tab.
PO # | Date | Issuer | Type | Status | Description | Amount | Source
PRIME | 2017-07-21 | Shelter Holdings | Lump Sum Subcontract | Closed | Metro Line Flats plumbing (72 units, 7 stories) — per Div 22 | 998152.29 | 2042-Shelter Holdings subcontract SC-53799-027 + Boren & Spruce CO docs
CO-NET | — | Shelter Holdings | Change Orders (executed, 5 COs) | Executed | Net CO impact (Sage 999 rev - orig) | 13882.05 | 2042 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
TOTAL (contract + COs) | [5 empty] | 1012034.34

## Billing & SOV
Billing & Schedule of Values
123 invoices to Shelter Holdings. Retainage $46,105.20.
Invoice # | Date | Total Billed (signed) | Retainage (signed) | # Lines | Source
554 | 01/18/19 | -37403 | -1870.15 | 5 | 2042 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
467 | 01/19/18 | -12100 | -605 | 1 | 2042 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
585 | 02/20/18 | -14000 | -700 | 1 | 2042 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
436 | 03/20/18 | -69160 | -3458 | 3 | 2042 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
686 | 03/20/19 | -644 | -32.2 | 1 | 2042 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
797 | 03/25/19 | -14770 | -738.5 | 1 | 2042 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
545 | 04/20/18 | -108089 | -5404.45 | 5 | 2042 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
503 | 05/18/18 | -189469 | -9473.45 | 12 | 2042 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
510 | 05/20/19 | -2178 | -108.9 | 2 | 2042 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
676 | 06/20/18 | -124132 | -6206.6 | 9 | 2042 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
513 | 07/19/18 | -128329 | -6416.45 | 14 | 2042 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
594 | 08/20/18 | -44550 | -2227.5 | 8 | 2042 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
470 | 09/19/18 | -62100 | -3105 | 2 | 2042 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
525 | 10/19/18 | -6155 | -307.75 | 4 | 2042 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
373 | 10/20/17 | -34400 | -1720 | 2 | 2042 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
356 | 12/14/18 | -17825 | -891.25 | 4 | 2042 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
536 | 12/15/17 | -56800 | -2840 | 1 | 2042 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
TOTAL (signed) |  | -922104 | -46105.2

## Insights
Insights & Observations
Narrative findings from JDR + GDrive CO log
# | Insight | Detail | Confidence | Source
1 | MARGIN PROFILE | Net profit $328,519.48 on $922,104.00 revenue = 35.6% gross margin. | Verified | 2042 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
2 | CONTRACT CHANGE | Original $998,152.29 → final $1,012,034.34 = $+13,882.05 net (1.39%) across 5 executed COs. | Verified | 2042 Job Detail Report.pdf (Sage Timberline, 04/03/2026) + CO log
3 | LABOR PROFILE | Labor cost $194,340.50 (21.1% of rev) across 7,215 hrs and 35 workers. Blended wage $26.94/hr. | Verified | 2042 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
4 | VENDOR CONCENTRATION | Top 5 AP vendors: ~$208,306.18 (78% of AP). Top vendor: Rosen Supply Company, Inc. $Metro Flats ($49,362.67). | Verified | 2042 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
5 | RETAINAGE | Retainage $46,105.20 — outstanding as of report date. | Verified | 2042 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
6 | ROUGH-IN SHARE | Code 120 Roughin Labor = 4,990 hrs (70% of labor hours). | Verified | 2042 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
7 | TOP COST CODE | Largest actual cost: 230 Finish Material = $148,333.68 | Verified | 2042 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
8 | WORKER CONCENTRATION | Top worker Reed, Reuben H = 1,271 hrs (18% of total). | Verified | 2042 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
9 | INSURANCE | Not Wrap — retail-adjacent mixed-use. | Verified | OWP Project List with Schedule - UPDATED 04-01-26.xlsx
10 | SCOPE CONTEXT | Metro Line Flats — 72-unit 7-story midrise (68 standard + 4 Type A ADA) + P1/P2 parking at 915 East Spruce Street, Seattle, WA 98122. | Verified | Submittal TOC + scope doc

## Benchmark KPIs
Benchmark KPIs
Normalized metrics for cross-project comparison
KPI | Data Name | Value | Category | Notes | Confidence | Source Document
Job Number | job_number | 2042 | Profile | OWP job ID | Verified | 2042 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
Job Name | job_name | Metro Line Flats (Boren & Spruce) | Profile |  | Verified | 2042 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
General Contractor | general_contractor | Shelter Holdings | Profile |  | Verified | OWP Project List with Schedule - UPDATED 04-01-26.xlsx
Owner | owner | Boren and Spruce, LLC | Profile |  | Verified | OWP Project List with Schedule - UPDATED 04-01-26.xlsx
Architect | architect | TBD | Profile |  | Verified | Metro Line Flats project info.pdf
Location | location | 915 East Spruce Street, Seattle, WA 98122 | Profile |  | Verified | OWP Project List with Schedule - UPDATED 04-01-26.xlsx
Project Type | project_type | 7-story, 72-unit multi-family residential (midrise / urban infill), including studios, open 1-BR, 1-BR, 2-BR, and 4 Type A ADA units | Profile |  | Verified | Scope + Submittal TOC
Insurance Type | insurance | Not Wrap | Profile |  | Verified | OWP Project List with Schedule - UPDATED 04-01-26.xlsx
GC PM | gc_pm | TBD | Profile |  | Verified | 2042-Shelter Holdings subcontract SC-53799-027 + Boren & Spruce CO docs
GC Sup | gc_sup | Brett (Metro Line plan review Brett folder) | Profile |  | Verified | 2042-Shelter Holdings subcontract SC-53799-027 + Boren & Spruce CO docs
OWP Signatory | owp_signatory | Mike Donelson | Profile |  | Verified | 2042-Shelter Holdings subcontract SC-53799-027 + Boren & Spruce CO docs
Contract Signed Date | contract_signed_date | 2017-07-21 | Profile |  | Verified | 2042-Shelter Holdings subcontract SC-53799-027 + Boren & Spruce CO docs
Work Start | start_date | 2017-09 | Profile |  | Verified | 2042 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
Work End | end_date | 2019-04 | Profile |  | Verified | 2042 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
Duration (months) | duration_months | 19 | Profile |  | Verified | Derived
Unit Count | unit_count | 72 | Profile | 102 Type B + 6 Type A/ADA | Verified | Submittal TOC
Total Fixtures | total_fixtures | 502 | Profile | 656 unit + 98 retail/common | Verified | Submittal TOC
Contract Original | contract_original | 998152.29 | Financial |  | Verified | OWP Project List with Schedule - UPDATED 04-01-26.xlsx
Contract Final | contract_final | 1012034.34 | Financial |  | Verified | OWP Project List with Schedule - UPDATED 04-01-26.xlsx
Change Orders ($) | co_net | 13882.05 | Financial | 5 executed | Verified | 2042 Job Detail Report.pdf (Sage Timberline, 04/03/2026) + CO log
CO % of Contract | co_pct | 1.391% | Financial |  | Verified | Derived
Revenue | revenue | 922104 | Financial | AR total | Verified | 2042 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
Direct Cost | direct_cost | 593584.52 | Financial | JDR Expenses | Verified | 2042 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
Net Profit | net_profit | 328519.48 | Financial | Rev - Exp | Verified | 2042 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
Gross Margin | gross_margin | 35.63% | Financial |  | Verified | Derived
Retainage | retainage | 46105.2 | Financial | JDR AR retainage | Verified | 2042 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
Retainage % of Revenue | retainage_pct | 5% | Financial |  | Verified | Derived
Labor Cost | labor_cost | 194340.5 | Labor | Codes 100-151 | Verified | 2042 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
Material Cost | material_cost | 250243.51 | Material | Codes 210-245 | Verified | 2042 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
Overhead Cost | overhead_cost | 47943.09 | Financial | Codes 600-607 | Verified | 2042 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
Burden Cost | burden_cost | 86190.15 | Labor | Code 995 | Verified | 2042 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
Tax Cost | tax_cost | 14867.27 | Labor | Code 998 | Verified | 2042 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
Total Labor Hours | total_hours | 7215 | Labor | Sum labor codes | Verified | 2042 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
Total Workers | total_workers | 35 | Labor | Unique PR IDs | Verified | 2042 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
Blended Gross Wage | blended_wage | 26.9356 | Labor |  | Verified | Derived
Fully-Loaded Wage | loaded_wage | 54.9488 | Labor |  | Verified | Derived
Burden Multiplier | burden_mult | 1.3421 | Labor |  | Verified | Derived
Rough-in Hours | roughin_hours | 4990 | Labor | Code 120 | Verified | 2042 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
Finish Hours | finish_hours | 651 | Labor | Code 130 | Verified | 2042 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
Revenue per Hour | rev_per_hour | 127.8037 | Productivity |  | Verified | Derived
Profit per Hour | profit_per_hour | 45.5328 | Productivity |  | Verified | Derived
Revenue per Unit | rev_per_unit | 12807 | Productivity | 72 units | Verified | Derived
Direct Cost per Unit | cost_per_unit | 8244.2294 | Productivity |  | Verified | Derived
Hours per Unit | hours_per_unit | 100.2083 | Productivity |  | Verified | Derived
Revenue per Fixture | rev_per_fixture | 1836.8606 | Productivity | 502 fixtures | Verified | Derived
Labor % of Revenue | labor_pct | 21.08% | Cost Mix |  | Verified | Derived
Material % of Revenue | material_pct | 27.14% | Cost Mix |  | Verified | Derived
Total Vendors | total_vendors | 18 | Material |  | Verified | 2042 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
Total Invoices | total_invoices | 17 | Billing |  | Verified | 2042 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
Top Worker Share | top_worker_share | 17.62% | Crew |  | Verified | Derived
Top 5 Worker Share | top5_worker_share | 59.44% | Crew |  | Verified | Derived
Cost Codes Active | cost_code_count | 25 | Structure |  | Verified | 2042 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
Executed CO Count | executed_co_count | 5 | Documents |  | Verified | CO log
COR Count | cor_count | 11 | Documents |  | Verified | GDrive COR folder
RFI/ASI Count | rfi_asi_count | 0 | Documents |  | Verified | GDrive ASI-RFI folder
Submittal Count | submittal_count | 0 | Documents |  | Verified | GDrive Submittals
PO Total (all) | po_count_total | 0 | Documents | placed+scheduled+completed | Verified | GDrive POs

## Vendors
Vendors — AP Summary
Vendor-level spend ranking
Rank | Vendor ID | Vendor Name | Total Spend | # Transactions | % of AP | Source
1 | 2042RS | Rosen Supply Company, Inc. $Metro Flats | 49362.67 | 26 | 18.37% | 2042 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
2 | 5560CH | California Hydronics Corp | 49222 | 3 | 18.32% | 2042 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
3 | 2042CS | Consolidated Supply Co. $Metro Flats | 44219.62 | 16 | 16.46% | 2042 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
4 | 1130CS | Consolidated Supply Co. | 33109.64 | 15 | 12.32% | 2042 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
5 | 1625FE | Franklin Engineering | 32392.25 | 8 | 12.05% | 2042 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
6 | 1175FE | Ferguson Enterprises, Inc. #3007 | 17571.09 | 16 | 6.539% | 2042 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
7 | 1231KS | Keller Supply Company | 14550.79 | 18 | 5.415% | 2042 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
8 | 1234CO | Capital One Credit Card | 13819.24 | 47 | 5.143% | 2042 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
9 | 1380RS | Rosen Supply Kirkland | 6263.82 | 10 | 2.331% | 2042 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
10 | 2042FE | Ferguson Enterprises, Inc. $Metro Flats | 3356.24 | 3 | 1.249% | 2042 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
11 | 2042KS | Keller Supply Co. $Metro Flats | 2982.64 | 2 | 1.11% | 2042 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
12 | 1234BA | Bank of America CC | 977.21 | 3 | 0.3637% | 2042 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
13 | 1609QC | Quality Concrete Products, Inc. $32 | 251 | 2 | 0.09341% | 2042 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
14 | 1288DR | DRSi | 248.64 | 1 | 0.09253% | 2042 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
15 | 1641AR | A.R. Brown Backflow Testing | 215 | 1 | 0.08001% | 2042 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
16 | 3612MS | Mechanical Sales, Inc. | 145.29 | 1 | 0.05407% | 2042 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
17 | 1021AT | ACME Corp | 26.36 | 1 | 0.00981% | 2042 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
18 | 2040CS | Consolidated Supply Co. $65th Apts | 0 | 2 | 0% | 2042 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
TOTAL |  |  | 268713.5 | 175

## Change Log
Change Log — Master Register
Contract, 5 executed COs, retainage events — JDR + GDrive CO folder
Event ID | Type | Date | Subject | Originator | Cost Impact ($) | Status | Source
CONTRACT-ORIG | Contract | 2017-07-21 | Prime subcontract — Lump Sum $998,152.29 | Shelter Holdings | 998152.29 | Executed | 2042-Shelter Holdings subcontract SC-53799-027 + Boren & Spruce CO docs
CO-01 | Change Order | — | Saturday Work 1/20/18 (T&M authorization per signed ticket) | Shelter Holdings | 942 | Executed | GDrive CO 1
CO-02 | Change Order | — | Common Area Lav Sink (COR#03) — revised scope misc addition | Shelter Holdings | 530.68 | Executed | GDrive CO 2
CO-03 | Change Order | — | Added Level 1 scope (commercial/retail finish) | Shelter Holdings | 4170.59 | Executed | GDrive CO 3
CO-04 | Change Order | — | Replaced CE#097 version ($5,829.80 cancelled). Consolidates change items including garbage disposals (COR#06) and unit water meters (COR#07) | Shelter Holdings | 5266.08 | Executed | GDrive CO 4
CO-05 | Change Order | — | Elevator Room Condensate Line (COR#04) + balance of bundled items | Shelter Holdings | 2972.7 | Executed | GDrive CO 5
FIRST-INVOICE | Invoice | 01/18/19 | First billing (per JDR) | Sub (OWP) | 0 | Paid | 2042 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
LAST-INVOICE | Invoice | 12/15/17 | Last billing (per JDR) | Sub (OWP) | 0 | Paid | 2042 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
RETAINAGE-OPEN | Retainage | As of 04/03/2026 | Retainage $46,105.20 (outstanding) | GC | 0 | Outstanding | 2042 Job Detail Report.pdf (Sage Timberline, 04/03/2026)

## Root Cause Analysis
Root Cause Analysis
Primary variance drivers by category
Category | Codes | Net $ Variance | Root Cause (inferred) | Notes
Contract Change | 999 (Sales) | 13882.05 | JDR-implied net CO impact | $998,152 → $1,012,034 (5 executed COs)
Labor | 100,101,110,111,112,120,130,140,141,142,143,145,150 | -20902.5 | Labor variance vs revised budget | 35 workers
Material | 210,211,212,213,220,230,240,241,242,243,244,245 | -66546.49 | Material procurement variance | 18 vendors
Overhead | 600,601,602,603,604,607 | 5513.09 | Engineering/permits/subcon variance
Burden+Tax | 995+998 | -10861.58 | Payroll accrual tracking labor
TOTAL NET VARIANCE |  | -78915.43
RESPONSIBILITY ATTRIBUTION
Responsible Party | # Drivers | Net $ Impact | Notes
GC / Owner (scope changes) | 5 | 13882.05 | Aggregate executed COs
Sub (OWP) labor performance | 9 | -20902.5 | Hours + rate vs budget
Sub (OWP) material procurement | 9 | -66546.49 | 18 vendors
OWP burden accrual | 2 | -10861.58 | Payroll burden + tax
OWP overhead | 4 | 5513.09 | Engineering/permits/subcon

## Predictive Signals
Predictive Signals
Leading indicators from JDR + CO log
CURRENT-STATE SIGNALS
Indicator | Current Value | Benchmark | Status | Meaning
Contract Change % | 1.39% | ±10% | HEALTHY | +1.39% net (5 COs)
Labor % of Revenue | 21.08% | <30% | HEALTHY | 21.1%
GL Overhead % of Revenue | 3.196% | <5% | HEALTHY | 3.2%
Vendor Concentration (Top 5) | 77.52% | <95% | HEALTHY | Top 5 = 78% of AP
Retainage % | 5% | <10% | HEALTHY | 5.0%
Gross Margin | 35.63% | >30% | HEALTHY | 35.6%
Labor Hrs Total | 7215 | varies | INFO | 7,215 hrs, 35 workers
Worker Concentration (top 1) | 17.62% | <25% | HEALTHY | 17.6% (Reed, Reuben H)
Rough-in Labor Share | 70.35% | 40-65% | WATCH | 70%
Retainage Legacy | OUTSTANDING | <90 days post-closeout | WATCH | $46,105.20
FORECAST MODELS
Forecast | Current Estimate | Confidence | Driver | Model Note
Final margin (actual) | 35.63% | Actual | Job closed | 35.6%
Retainage collection | $46,105.20 | Outstanding | Legacy | Outstanding
Unit-level economics | $12,807/unit rev, $4,563/unit profit | Verified | 72 units | 7-story, 72-unit multi-family residential (midrise / urban infill), including studios, open 1-BR, 1-BR, 2-BR, and 4 Type A ADA units

## Metric Registry
Metric Registry — Cortex Data Catalog
Every metric with data_label, confidence, and source
# | Data Label | Human Label | Value | Unit | Source Tab | Confidence | Source Document(s)
1 | job_number | Job Number | 2042 | id | Benchmark KPIs | Verified | 2042 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
2 | job_name | Job Name | Metro Line Flats (Boren & Spruce) | text | Benchmark KPIs | Verified | 2042 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
3 | general_contractor | General Contractor | Shelter Holdings | text | Benchmark KPIs | Verified | OWP Project List with Schedule - UPDATED 04-01-26.xlsx
4 | owner | Owner | Boren and Spruce, LLC | text | Benchmark KPIs | Verified | OWP Project List with Schedule - UPDATED 04-01-26.xlsx
5 | architect | Architect | TBD | text | Benchmark KPIs | Verified | Metro Line Flats project info.pdf
6 | location | Location | 915 East Spruce Street, Seattle, WA 98122 | text | Benchmark KPIs | Verified | OWP Project List with Schedule - UPDATED 04-01-26.xlsx
7 | project_type | Project Type | 7-story, 72-unit multi-family residential (midrise / urban infill), including studios, open 1-BR, 1-BR, 2-BR, and 4 Type A ADA units | text | Benchmark KPIs | Verified | Scope + Submittal TOC
8 | insurance | Insurance Type | Not Wrap | text | Benchmark KPIs | Verified | OWP Project List with Schedule - UPDATED 04-01-26.xlsx
9 | gc_pm | GC PM | TBD | text | Benchmark KPIs | Verified | 2042-Shelter Holdings subcontract SC-53799-027 + Boren & Spruce CO docs
10 | gc_sup | GC Sup | Brett (Metro Line plan review Brett folder) | text | Benchmark KPIs | Verified | 2042-Shelter Holdings subcontract SC-53799-027 + Boren & Spruce CO docs
11 | owp_signatory | OWP Signatory | Mike Donelson | text | Benchmark KPIs | Verified | 2042-Shelter Holdings subcontract SC-53799-027 + Boren & Spruce CO docs
12 | contract_signed_date | Contract Signed Date | 2017-07-21 | date | Benchmark KPIs | Verified | 2042-Shelter Holdings subcontract SC-53799-027 + Boren & Spruce CO docs
13 | start_date | Work Start | 2017-09 | date | Benchmark KPIs | Verified | 2042 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
14 | end_date | Work End | 2019-04 | date | Benchmark KPIs | Verified | 2042 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
15 | duration_months | Duration (months) | 19 | months | Benchmark KPIs | Verified | Derived
16 | unit_count | Unit Count | 72 | units | Benchmark KPIs | Verified | Submittal TOC
17 | total_fixtures | Total Fixtures | 502 | count | Benchmark KPIs | Verified | Submittal TOC
18 | contract_original | Contract Original | 998152.29 | USD | Benchmark KPIs | Verified | OWP Project List with Schedule - UPDATED 04-01-26.xlsx
19 | contract_final | Contract Final | 1012034.34 | USD | Benchmark KPIs | Verified | OWP Project List with Schedule - UPDATED 04-01-26.xlsx
20 | co_net | Change Orders ($) | 13882.05 | USD | Benchmark KPIs | Verified | 2042 Job Detail Report.pdf (Sage Timberline, 04/03/2026) + CO log
21 | co_pct | CO % of Contract | 1.391% | % | Benchmark KPIs | Verified | Derived
22 | revenue | Revenue | 922104 | USD | Benchmark KPIs | Verified | 2042 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
23 | direct_cost | Direct Cost | 593584.52 | USD | Benchmark KPIs | Verified | 2042 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
24 | net_profit | Net Profit | 328519.48 | USD | Benchmark KPIs | Verified | 2042 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
25 | gross_margin | Gross Margin | 35.63% | % | Benchmark KPIs | Verified | Derived
26 | retainage | Retainage | 46105.2 | USD | Benchmark KPIs | Verified | 2042 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
27 | retainage_pct | Retainage % of Revenue | 5% | % | Benchmark KPIs | Verified | Derived
28 | labor_cost | Labor Cost | 194340.5 | USD | Benchmark KPIs | Verified | 2042 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
29 | material_cost | Material Cost | 250243.51 | USD | Benchmark KPIs | Verified | 2042 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
30 | overhead_cost | Overhead Cost | 47943.09 | USD | Benchmark KPIs | Verified | 2042 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
31 | burden_cost | Burden Cost | 86190.15 | USD | Benchmark KPIs | Verified | 2042 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
32 | tax_cost | Tax Cost | 14867.27 | USD | Benchmark KPIs | Verified | 2042 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
33 | total_hours | Total Labor Hours | 7215 | hours | Benchmark KPIs | Verified | 2042 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
34 | total_workers | Total Workers | 35 | count | Benchmark KPIs | Verified | 2042 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
35 | blended_wage | Blended Gross Wage | 26.9356 | USD/hr | Benchmark KPIs | Verified | Derived
36 | loaded_wage | Fully-Loaded Wage | 54.9488 | USD/hr | Benchmark KPIs | Verified | Derived
37 | burden_mult | Burden Multiplier | 1.3421 | x | Benchmark KPIs | Verified | Derived
38 | roughin_hours | Rough-in Hours | 4990 | hours | Benchmark KPIs | Verified | 2042 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
39 | finish_hours | Finish Hours | 651 | hours | Benchmark KPIs | Verified | 2042 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
40 | rev_per_hour | Revenue per Hour | 127.8037 | USD/hr | Benchmark KPIs | Verified | Derived
41 | profit_per_hour | Profit per Hour | 45.5328 | USD/hr | Benchmark KPIs | Verified | Derived
42 | rev_per_unit | Revenue per Unit | 12807 | USD | Benchmark KPIs | Verified | Derived
43 | cost_per_unit | Direct Cost per Unit | 8244.2294 | USD | Benchmark KPIs | Verified | Derived
44 | hours_per_unit | Hours per Unit | 100.2083 | hours | Benchmark KPIs | Verified | Derived
45 | rev_per_fixture | Revenue per Fixture | 1836.8606 | USD | Benchmark KPIs | Verified | Derived
46 | labor_pct | Labor % of Revenue | 21.08% | % | Benchmark KPIs | Verified | Derived
47 | material_pct | Material % of Revenue | 27.14% | % | Benchmark KPIs | Verified | Derived
48 | total_vendors | Total Vendors | 18 | count | Benchmark KPIs | Verified | 2042 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
49 | total_invoices | Total Invoices | 17 | count | Benchmark KPIs | Verified | 2042 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
50 | top_worker_share | Top Worker Share | 17.62% | % | Benchmark KPIs | Verified | Derived
51 | top5_worker_share | Top 5 Worker Share | 59.44% | % | Benchmark KPIs | Verified | Derived
52 | cost_code_count | Cost Codes Active | 25 | count | Benchmark KPIs | Verified | 2042 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
53 | executed_co_count | Executed CO Count | 5 | count | Benchmark KPIs | Verified | CO log
54 | cor_count | COR Count | 11 | count | Benchmark KPIs | Verified | GDrive COR folder
55 | rfi_asi_count | RFI/ASI Count | 0 | count | Benchmark KPIs | Verified | GDrive ASI-RFI folder
56 | submittal_count | Submittal Count | 0 | count | Benchmark KPIs | Verified | GDrive Submittals
57 | po_count_total | PO Total (all) | 0 | count | Benchmark KPIs | Verified | GDrive POs

## Reconciliation
Reconciliation
Cross-sheet formula checks
# | Check | Value A | Value B | Delta | Status | Tabs
1 | Revenue = Contract Final | 922104 | 1012034.34 | -89930.34 | OFF | 1↔8
2 | Expenses = Labor+Mat+OH+Burden+Tax | 593584.52 | 593584.52 | 0 | TIES | 1↔3
3 | Net Profit = Revenue - Expenses | 328519.48 | 328519.48 | 0 | TIES | 1↔Derived
4 | Sage 999 actual = -Revenue | 922104 | 922104 | 0 | TIES | 2↔1
5 | Total Hours = Worker hours sum | 7215 | 7215 | 0 | TIES | 5↔2
6 | Contract Final - Orig = CO implied | 13882.05 | 13882.05 | -1.0004e-10 | TIES | 11↔Derived
7 | Worker count | 35 | 35 | 0 | TIES | 5↔1
8 | Cost code count | 25 | 25 | 0 | TIES | 2↔16