## Report Record
JCR TEST LABELS — JOB 2042
Report-level fields from the v4 schema. Parsed from 1,939-line Job Detail Report (Apr 03, 2026 run). Mirrors the Job 2020 test-labels structure.
Field | Value
job_number | 2042
job_name | ShelterHoldings MetroLine
report_date | 2026-04-03
general_contractor | Shelter Holdings
owner | Boren and Spruce, LLC
architect | TBD
location | 915 East Spruce Street, Seattle, WA 98122
project_type | 7-story, 72-unit multi-family residential (midrise / urban infill), including studios, open 1-BR, 1-BR, 2-BR, and 4 Type A ADA units
project_start_date | 2017-09
project_end_date | 2019-04
duration_months | 19
contract_signed_date | 2017-07-21
contract_original | 998152.29
contract_final | 1012034.34
change_orders_net | 13882.05
scope_metrics | 72 residential units (68 standard + 4 Type A ADA) · ~502 fixtures (scope estimate) · 7 residential stories · 19-month duration · 5 executed COs · 11 CORs · 12 permits · 123 invoices
line_items | Array of 1,939 objects (see Line Items tab)
cost_code_summaries | Array of 25 objects (see Cost Code Summaries tab)
job_totals_revenue | -922104
job_totals_expenses | 593584.52
job_totals_net | -328519.48
job_totals_net_due | 0
job_totals_retainage | -46105.2
job_totals_by_source | PR: $295,397.92, AP: $268,713.50, GL: $29,473.10, AR: $-922,104.00

## Line Items
LINE ITEMS — 1,939 TRANSACTIONS
Every transaction line parsed from the 175-page JDR. AR amounts are negative per Sage convention (credits). Retainage is stored in the retainage column (AR only).
cost_code | description | source | ref_number | document_date | posted_date | number | name | regular_hours | overtime_hours | regular_amount | overtime_amount | actual_amount | check_number | net_due | retainage
100 | Supervision | PR | 67 | 10/04/17 | 10/06/17 | DO56 | Donelson, Richard T | 1 | 0 | 50 | 0 | 50 | 19638 | 0 | 0
100 | Supervision | PR | 548 | 10/25/17 | 10/27/17 | GE69 | Gerard, Jeffrey S | 2 | 0 | 94 | 0 | 94 | 17827 | 0 | 0
100 | Supervision | PR | 68 | 11/01/17 | 11/03/17 | GE69 | Gerard, Jeffrey S | 1 | 0 | 47 | 0 | 47 | 17892 | 0 | 0
100 | Supervision | PR | 466 | 12/13/17 | 12/15/17 | GE69 | Gerard, Jeffrey S | 2 | 0 | 94 | 0 | 94 | 18280 | 0 | 0
100 | Supervision | PR | 655 | 12/20/17 | 12/22/17 | DO56 | Donelson, Richard T | 2 | 0 | 100 | 0 | 100 | 18409 | 0 | 0
100 | Supervision | PR | 656 | 12/20/17 | 12/22/17 | GE69 | Gerard, Jeffrey S | 1 | 0 | 47 | 0 | 47 | 18410 | 0 | 0
100 | Supervision | PR | 847 | 12/27/17 | 12/29/17 | GE69 | Gerard, Jeffrey S | 2 | 0 | 94 | 0 | 94 | 98476 | 0 | 0
100 | Supervision | PR | 66 | 01/03/18 | 01/05/18 | GE69 | Gerard, Jeffrey S | 2 | 0 | 94 | 0 | 94 | 98540 | 0 | 0
100 | Supervision | PR | 290 | 01/10/18 | 01/12/18 | GE69 | Gerard, Jeffrey S | 2 | 0 | 94 | 0 | 94 | 918605 | 0 | 0
100 | Supervision | PR | 651 | 01/24/18 | 01/26/18 | GE69 | Gerard, Jeffrey S | 1 | 0 | 47 | 0 | 47 | 18734 | 0 | 0
100 | Supervision | PR | 227 | 02/07/18 | 02/09/18 | GE69 | Gerard, Jeffrey S | 1 | 0 | 47 | 0 | 47 | 18868 | 0 | 0
100 | Supervision | PR | 484 | 02/14/18 | 02/16/18 | GE69 | Gerard, Jeffrey S | 2 | 0 | 94 | 0 | 94 | 18884 | 0 | 0
100 | Supervision | PR | 68 | 02/28/18 | 03/02/18 | GE69 | Gerard, Jeffrey S | 1 | 0 | 47 | 0 | 47 | 100000 | 0 | 0
100 | Supervision | PR | 385 | 03/14/18 | 03/16/18 | GE69 | Gerard, Jeffrey S | 1 | 0 | 50 | 0 | 50 | 19206 | 0 | 0
100 | Supervision | PR | 811 | 03/28/18 | 03/30/18 | DO56 | Donelson, Richard T | 1 | 0 | 62.5 | 0 | 62.5 | 99350 | 0 | 0
100 | Supervision | PR | 85 | 04/04/18 | 04/06/18 | GE69 | Gerard, Jeffrey S | 1 | 0 | 50 | 0 | 50 | 99427 | 0 | 0
100 | Supervision | PR | 807 | 05/23/18 | 05/25/18 | GE69 | Gerard, Jeffrey S | 2 | 0 | 100 | 0 | 100 | 99936 | 0 | 0
100 | Supervision | PR | 76 | 05/30/18 | 06/01/18 | GE69 | Gerard, Jeffrey S | 1 | 0 | 50 | 0 | 50 | 920008 | 0 | 0
100 | Supervision | PR | 1019 | 06/27/18 | 06/29/18 | DO56 | Donelson, Richard T | 1 | 0 | 62.5 | 0 | 62.5 | 20300 | 0 | 0
100 | Supervision | PR | 1070 | 08/29/18 | 08/31/18 | GE69 | Gerard, Jeffrey S | 1 | 0 | 50 | 0 | 50 | 90962 | 0 | 0
100 | Supervision | PR | 577 | 12/19/18 | 12/21/18 | DO56 | Donelson, Richard T | 4 | 0 | 250 | 0 | 250 | 922268 | 0 | 0
100 | Supervision | PR | 777 | 03/20/19 | 03/22/19 | GE69 | Gerard, Jeffrey S | 1 | 0 | 52 | 0 | 52 | 923198 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 184 | 09/06/17 | 09/08/17 | DO56 | Donelson, Richard T | 1 | 0 | 50 | 0 | 50 | 97386 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 761 | 09/27/17 | 09/29/17 | DO56 | Donelson, Richard T | 1 | 0 | 50 | 0 | 50 | 19576 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 762 | 09/27/17 | 09/29/17 | GE69 | Gerard, Jeffrey S | 3 | 0 | 141 | 0 | 141 | 19577 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 67 | 10/04/17 | 10/06/17 | DO56 | Donelson, Richard T | 4 | 0 | 200 | 0 | 200 | 19638 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 68 | 10/04/17 | 10/06/17 | GE69 | Gerard, Jeffrey S | 1 | 0 | 47 | 0 | 47 | 19639 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 225 | 10/11/17 | 10/13/17 | DO56 | Donelson, Richard T | 9 | 0 | 450 | 0 | 450 | 17701 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 350 | 10/18/17 | 10/20/17 | DO56 | Donelson, Richard T | 1 | 0 | 50 | 0 | 50 | 97762 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 547 | 10/25/17 | 10/27/17 | DO56 | Donelson, Richard T | 2 | 0 | 100 | 0 | 100 | 17826 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 548 | 10/25/17 | 10/27/17 | GE69 | Gerard, Jeffrey S | 2 | 0 | 94 | 0 | 94 | 17827 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 67 | 11/01/17 | 11/03/17 | DO56 | Donelson, Richard T | 7 | 0 | 350 | 0 | 350 | 17891 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 68 | 11/01/17 | 11/03/17 | GE69 | Gerard, Jeffrey S | 1 | 0 | 47 | 0 | 47 | 17892 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 343 | 11/15/17 | 11/17/17 | DO56 | Donelson, Richard T | 2 | 0 | 100 | 0 | 100 | 18019 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 344 | 11/15/17 | 11/17/17 | GE69 | Gerard, Jeffrey S | 1 | 0 | 47 | 0 | 47 | 18020 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 66 | 11/29/17 | 12/01/17 | DO56 | Donelson, Richard T | 2 | 0 | 100 | 0 | 100 | 98147 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 465 | 12/13/17 | 12/15/17 | DO56 | Donelson, Richard T | 1 | 0 | 50 | 0 | 50 | 18279 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 466 | 12/13/17 | 12/15/17 | GE69 | Gerard, Jeffrey S | 3 | 0 | 141 | 0 | 141 | 18280 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 656 | 12/20/17 | 12/22/17 | GE69 | Gerard, Jeffrey S | 6 | 0 | 282 | 0 | 282 | 18410 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 847 | 12/27/17 | 12/29/17 | GE69 | Gerard, Jeffrey S | 2 | 0 | 94 | 0 | 94 | 98476 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 66 | 01/03/18 | 01/05/18 | GE69 | Gerard, Jeffrey S | 4 | 0 | 188 | 0 | 188 | 98540 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 290 | 01/10/18 | 01/12/18 | GE69 | Gerard, Jeffrey S | 3 | 0 | 141 | 0 | 141 | 918605 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 454 | 01/17/18 | 01/19/18 | DO56 | Donelson, Richard T | 1 | 0 | 62.5 | 0 | 62.5 | 18669 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 455 | 01/17/18 | 01/19/18 | GE69 | Gerard, Jeffrey S | 2 | 0 | 94 | 0 | 94 | 18670 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 457 | 01/17/18 | 01/19/18 | DO56 | Donelson, Richard T | 1 | 0 | -62.5 | 0 | -62.5 | 18669 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 458 | 01/17/18 | 01/19/18 | DO56 | Donelson, Richard T | 1 | 0 | 62.5 | 0 | 62.5 | 18672 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 650 | 01/24/18 | 01/26/18 | DO56 | Donelson, Richard T | 1 | 0 | 62.5 | 0 | 62.5 | 18733 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 651 | 01/24/18 | 01/26/18 | GE69 | Gerard, Jeffrey S | 2 | 0 | 94 | 0 | 94 | 18734 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 71 | 01/31/18 | 02/02/18 | GE69 | Gerard, Jeffrey S | 2 | 0 | 94 | 0 | 94 | 98802 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 227 | 02/07/18 | 02/09/18 | GE69 | Gerard, Jeffrey S | 4 | 0 | 188 | 0 | 188 | 18868 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 483 | 02/14/18 | 02/16/18 | DO56 | Donelson, Richard T | 1 | 0 | 62.5 | 0 | 62.5 | 18883 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 669 | 02/21/18 | 02/23/18 | DO56 | Donelson, Richard T | 2 | 0 | 125 | 0 | 125 | 18953 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 670 | 02/21/18 | 02/23/18 | GE69 | Gerard, Jeffrey S | 1 | 0 | 47 | 0 | 47 | 18954 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 67 | 02/28/18 | 03/02/18 | DO56 | Donelson, Richard T | 2 | 0 | 125 | 0 | 125 | 99999 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 68 | 02/28/18 | 03/02/18 | GE69 | Gerard, Jeffrey S | 6 | 0 | 282 | 0 | 282 | 100000 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 184 | 03/07/18 | 03/09/18 | GE69 | Gerard, Jeffrey S | 2 | 0 | 94 | 0 | 94 | 99998 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 385 | 03/14/18 | 03/16/18 | GE69 | Gerard, Jeffrey S | 2 | 0 | 100 | 0 | 100 | 19206 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 584 | 03/21/18 | 03/23/18 | GE69 | Gerard, Jeffrey S | 3 | 0 | 150 | 0 | 150 | 99998 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 811 | 03/28/18 | 03/30/18 | DO56 | Donelson, Richard T | 1 | 0 | 62.5 | 0 | 62.5 | 99350 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 85 | 04/04/18 | 04/06/18 | GE69 | Gerard, Jeffrey S | 2 | 0 | 100 | 0 | 100 | 99427 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 333 | 04/11/18 | 04/13/18 | DO56 | Donelson, Richard T | 2 | 0 | 125 | 0 | 125 | 99500 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 517 | 04/18/18 | 04/20/18 | DO56 | Donelson, Richard T | 1 | 0 | 62.5 | 0 | 62.5 | 99575 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 518 | 04/18/18 | 04/20/18 | GE69 | Gerard, Jeffrey S | 3 | 0 | 150 | 0 | 150 | 99576 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 684 | 04/25/18 | 04/27/18 | GE69 | Gerard, Jeffrey S | 1 | 0 | 50 | 0 | 50 | 99649 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 286 | 05/09/18 | 05/11/18 | DO56 | Donelson, Richard T | 4 | 0 | 250 | 0 | 250 | 99793 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 492 | 05/16/18 | 05/18/18 | GE69 | Gerard, Jeffrey S | 1 | 0 | 50 | 0 | 50 | 19865 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 806 | 05/23/18 | 05/25/18 | DO56 | Donelson, Richard T | 1 | 0 | 62.5 | 0 | 62.5 | 99935 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 807 | 05/23/18 | 05/25/18 | GE69 | Gerard, Jeffrey S | 2 | 0 | 100 | 0 | 100 | 99936 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 76 | 05/30/18 | 06/01/18 | GE69 | Gerard, Jeffrey S | 1 | 0 | 50 | 0 | 50 | 920008 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 340 | 06/06/18 | 06/08/18 | GE69 | Gerard, Jeffrey S | 1 | 0 | 50 | 0 | 50 | 20080 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 754 | 06/20/18 | 06/22/18 | GE69 | Gerard, Jeffrey S | 1 | 0 | 50 | 0 | 50 | 290233 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 550 | 08/15/18 | 08/17/18 | DO56 | Donelson, Richard T | 7 | 0 | 437.5 | 0 | 437.5 | 20808 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 811 | 08/22/18 | 08/24/18 | DO56 | Donelson, Richard T | 1 | 0 | 62.5 | 0 | 62.5 | 20879 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 105 | 09/05/18 | 09/07/18 | DO56 | Donelson, Richard T | 1 | 0 | 62.5 | 0 | 62.5 | 91031 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 739 | 09/26/18 | 09/28/18 | DO56 | Donelson, Richard T | 1 | 0 | 62.5 | 0 | 62.5 | 90883 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 102 | 10/03/18 | 10/05/18 | DO56 | Donelson, Richard T | 1 | 0 | 62.5 | 0 | 62.5 | 91391 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 507 | 10/17/18 | 10/19/18 | DO56 | Donelson, Richard T | 3 | 0 | 187.5 | 0 | 187.5 | 91541 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 257 | 11/07/18 | 11/09/18 | DO56 | Donelson, Richard T | 1 | 0 | 62.5 | 0 | 62.5 | 20891 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 113 | 12/05/18 | 12/07/18 | DO56 | Donelson, Richard T | 2 | 0 | 125 | 0 | 125 | 22056 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 337 | 12/12/18 | 12/14/18 | DO56 | Donelson, Richard T | 2 | 0 | 125 | 0 | 125 | 22197 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 70 | 01/30/19 | 02/01/19 | DO56 | Donelson, Richard T | 2 | 0 | 125 | 0 | 125 | 22699 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 226 | 02/06/19 | 02/08/19 | DO56 | Donelson, Richard T | 1 | 0 | 62.5 | 0 | 62.5 | 22768 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 388 | 02/13/19 | 02/15/19 | DO56 | Donelson, Richard T | 1 | 0 | 62.5 | 0 | 62.5 | 922839 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 647 | 02/20/19 | 02/22/19 | DO56 | Donelson, Richard T | 2 | 0 | 125 | 0 | 125 | 922909 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 314 | 03/06/19 | 03/08/19 | DO56 | Donelson, Richard T | 1 | 0 | 62.5 | 0 | 62.5 | 923053 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 562 | 03/13/19 | 03/15/19 | DO56 | Donelson, Richard T | 1 | 0 | 62.5 | 0 | 62.5 | 23124 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 776 | 03/20/19 | 03/22/19 | DO56 | Donelson, Richard T | 3 | 0 | 187.5 | 0 | 187.5 | 923197 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 989 | 03/27/19 | 03/29/19 | DO56 | Donelson, Richard T | 3 | 0 | 187.5 | 0 | 187.5 | 23272 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 151 | 04/03/19 | 04/05/19 | DO56 | Donelson, Richard T | 3 | 0 | 187.5 | 0 | 187.5 | 923345 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 81 | 05/01/19 | 05/03/19 | DO56 | Donelson, Richard T | 1 | 0 | 62.5 | 0 | 62.5 | 923643 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 952 | 05/29/19 | 05/31/19 | DO56 | Donelson, Richard T | 2 | 0 | 125 | 0 | 125 | 923952 | 0 | 0
110 | Underground Labor | PR | 488 | 10/25/17 | 10/27/17 | BA70 | Barnhart, Joseph N | 1 | 0 | 44 | 0 | 44 | 17767 | 0 | 0
110 | Underground Labor | PR | 7 | 11/01/17 | 11/03/17 | BA70 | Barnhart, Joseph N | 1 | 0 | 44 | 0 | 44 | 17831 | 0 | 0
110 | Underground Labor | PR | 154 | 11/08/17 | 11/10/17 | BA70 | Barnhart, Joseph N | 1 | 0 | 44 | 0 | 44 | 17897 | 0 | 0
110 | Underground Labor | PR | 430 | 11/22/17 | 11/22/17 | BA70 | Barnhart, Joseph N | 0.5 | 0 | 22 | 0 | 22 | 18024 | 0 | 0
110 | Underground Labor | PR | 208 | 12/06/17 | 12/08/17 | BA70 | Barnhart, Joseph N | 1 | 0 | 44 | 0 | 44 | 18153 | 0 | 0
110 | Underground Labor | PR | 405 | 12/13/17 | 12/15/17 | BA70 | Barnhart, Joseph N | 2 | 0 | 88 | 0 | 88 | 18219 | 0 | 0
110 | Underground Labor | PR | 591 | 12/20/17 | 12/22/17 | AN14 | Anderson, Richard P | 24 | 0 | 1008 | 0 | 1008 | 18345 | 0 | 0
110 | Underground Labor | PR | 595 | 12/20/17 | 12/22/17 | BA70 | Barnhart, Joseph N | 25.5 | 0 | 1122 | 0 | 1122 | 18349 | 0 | 0
110 | Underground Labor | PR | 625 | 12/20/17 | 12/22/17 | KI55 | Kinssies, Jr, John E | 12.5 | 0 | 300 | 0 | 300 | 18379 | 0 | 0
110 | Underground Labor | PR | 782 | 12/27/17 | 12/29/17 | AN14 | Anderson, Richard P | 13.5 | 0 | 567 | 0 | 567 | 18410 | 0 | 0
110 | Underground Labor | PR | 785 | 12/27/17 | 12/29/17 | BA68 | Barbosa, Michael S | 8 | 0 | 168 | 0 | 168 | 18414 | 0 | 0
110 | Underground Labor | PR | 786 | 12/27/17 | 12/29/17 | BA70 | Barnhart, Joseph N | 14 | 0 | 616 | 0 | 616 | 18415 | 0 | 0
110 | Underground Labor | PR | 816 | 12/27/17 | 12/29/17 | KI55 | Kinssies, Jr, John E | 21.5 | 0 | 516 | 0 | 516 | 18445 | 0 | 0
110 | Underground Labor | PR | 2 | 01/03/18 | 01/05/18 | AN14 | Anderson, Richard P | 11 | 0 | 462 | 0 | 462 | 18475 | 0 | 0
110 | Underground Labor | PR | 6 | 01/03/18 | 01/05/18 | BA70 | Barnhart, Joseph N | 14 | 0 | 616 | 0 | 616 | 18479 | 0 | 0
110 | Underground Labor | PR | 36 | 01/03/18 | 01/05/18 | KI55 | Kinssies, Jr, John E | 16 | 0 | 384 | 0 | 384 | 18510 | 0 | 0
110 | Underground Labor | PR | 63 | 01/03/18 | 01/05/18 | WE55 | Wennig, Johnathan M | 12 | 0 | 312 | 0 | 312 | 18537 | 0 | 0
110 | Underground Labor | PR | 65 | 01/03/18 | 01/05/18 | DO56 | Donelson, Richard T | 1 | 0 | 62.5 | 0 | 62.5 | 98539 | 0 | 0
110 | Underground Labor | PR | 225 | 01/10/18 | 01/12/18 | AN14 | Anderson, Richard P | 8.75 | 0 | 367.5 | 0 | 367.5 | 18540 | 0 | 0
110 | Underground Labor | PR | 229 | 01/10/18 | 01/12/18 | BA70 | Barnhart, Joseph N | 26 | 0 | 1144 | 0 | 1144 | 18544 | 0 | 0
110 | Underground Labor | PR | 256 | 01/10/18 | 01/12/18 | HU04 | Hubbard, Dustin R | 2 | 0 | 42 | 0 | 42 | 18571 | 0 | 0
110 | Underground Labor | PR | 259 | 01/10/18 | 01/12/18 | KI55 | Kinssies, Jr, John E | 22 | 0 | 528 | 0 | 528 | 18574 | 0 | 0
110 | Underground Labor | PR | 286 | 01/10/18 | 01/12/18 | WE55 | Wennig, Johnathan M | 8.75 | 0 | 227.5 | 0 | 227.5 | 18601 | 0 | 0
110 | Underground Labor | PR | 425 | 01/17/18 | 01/19/18 | KI55 | Kinssies, Jr, John E | 2 | 0 | 48 | 0 | 48 | 18640 | 0 | 0
112 | Canout Labor | PR | 425 | 01/17/18 | 01/19/18 | KI55 | Kinssies, Jr, John E | 5.5 | 0 | 132 | 0 | 132 | 18640 | 0 | 0
112 | Canout Labor | PR | 589 | 01/24/18 | 01/26/18 | BA68 | Barbosa, Michael S | 14 | 0 | 294 | 0 | 294 | 18673 | 0 | 0
112 | Canout Labor | PR | 590 | 01/24/18 | 01/26/18 | BA70 | Barnhart, Joseph N | 0 | 5.5 | 0 | 363 | 363 | 18674 | 0 | 0
112 | Canout Labor | PR | 590 | 01/24/18 | 01/26/18 | BA70 | Barnhart, Joseph N | 17 | 0 | 748 | 0 | 748 | 18674 | 0 | 0
112 | Canout Labor | PR | 614 | 01/24/18 | 01/26/18 | HE70 | Hernandez Gonzalez, Osbaldo | 5.5 | 0 | 104.5 | 0 | 104.5 | 18698 | 0 | 0
112 | Canout Labor | PR | 7 | 01/31/18 | 02/02/18 | BA68 | Barbosa, Michael S | 8 | 0 | 168 | 0 | 168 | 18737 | 0 | 0
112 | Canout Labor | PR | 8 | 01/31/18 | 02/02/18 | BA70 | Barnhart, Joseph N | 2 | 0 | 88 | 0 | 88 | 18738 | 0 | 0
112 | Canout Labor | PR | 165 | 02/07/18 | 02/09/18 | BA70 | Barnhart, Joseph N | 2 | 0 | 88 | 0 | 88 | 18806 | 0 | 0
112 | Canout Labor | PR | 419 | 02/14/18 | 02/16/18 | BA70 | Barnhart, Joseph N | 18 | 0 | 792 | 0 | 792 | 18872 | 0 | 0
112 | Canout Labor | PR | 456 | 02/14/18 | 02/16/18 | MA71 | Martinez Reyes, Juan C | 16 | 0 | 384 | 0 | 384 | 18910 | 0 | 0
112 | Canout Labor | PR | 607 | 02/21/18 | 02/23/18 | BA70 | Barnhart, Joseph N | 1 | 0 | 44 | 0 | 44 | 18940 | 0 | 0
112 | Canout Labor | PR | 643 | 02/21/18 | 02/23/18 | MA71 | Martinez Reyes, Juan C | 8 | 0 | 192 | 0 | 192 | 18977 | 0 | 0
112 | Canout Labor | PR | 6 | 02/28/18 | 03/02/18 | BA70 | Barnhart, Joseph N | 0.5 | 0 | 22 | 0 | 22 | 19007 | 0 | 0
112 | Canout Labor | PR | 35 | 02/28/18 | 03/02/18 | HU06 | Hubbard, Robert W | 3 | 0 | 135 | 0 | 135 | 19037 | 0 | 0
112 | Canout Labor | PR | 42 | 02/28/18 | 03/02/18 | MA71 | Martinez Reyes, Juan C | 6 | 0 | 144 | 0 | 144 | 19044 | 0 | 0
120 | Roughin Labor | PR | 622 | 12/20/17 | 12/22/17 | HU04 | Hubbard, Dustin R | 2 | 0 | 42 | 0 | 42 | 18376 | 0 | 0
120 | Roughin Labor | PR | 256 | 01/10/18 | 01/12/18 | HU04 | Hubbard, Dustin R | 2 | 0 | -42 | 0 | -42 | 18571 | 0 | 0
120 | Roughin Labor | PR | 8 | 01/31/18 | 02/02/18 | BA70 | Barnhart, Joseph N | 1 | 0 | 44 | 0 | 44 | 18738 | 0 | 0
120 | Roughin Labor | PR | 449 | 02/14/18 | 02/16/18 | HU06 | Hubbard, Robert W | 4 | 0 | 180 | 0 | 180 | 18903 | 0 | 0
120 | Roughin Labor | PR | 6 | 02/28/18 | 03/02/18 | BA70 | Barnhart, Joseph N | 4 | 0 | 176 | 0 | 176 | 19007 | 0 | 0
120 | Roughin Labor | PR | 26 | 02/28/18 | 03/02/18 | GA70 | Garcia, Jordan X | 15 | 0 | 465 | 0 | 465 | 19028 | 0 | 0
120 | Roughin Labor | PR | 44 | 02/28/18 | 03/02/18 | ME52 | Mendoza, Edgar E | 7 | 0 | 140 | 0 | 140 | 19046 | 0 | 0
120 | Roughin Labor | PR | 53 | 02/28/18 | 03/02/18 | RE18 | Reed, Reuben H | 10 | 0 | 400 | 0 | 400 | 19055 | 0 | 0
120 | Roughin Labor | PR | 122 | 03/07/18 | 03/09/18 | BA70 | Barnhart, Joseph N | 4 | 0 | 176 | 0 | 176 | 19078 | 0 | 0
120 | Roughin Labor | PR | 140 | 03/07/18 | 03/09/18 | GA70 | Garcia, Jordan X | 40 | 0 | 1240 | 0 | 1240 | 19096 | 0 | 0
120 | Roughin Labor | PR | 158 | 03/07/18 | 03/09/18 | ME52 | Mendoza, Edgar E | 38.5 | 0 | 770 | 0 | 770 | 19115 | 0 | 0
120 | Roughin Labor | PR | 167 | 03/07/18 | 03/09/18 | RE18 | Reed, Reuben H | 40 | 0 | 1600 | 0 | 1600 | 19124 | 0 | 0
120 | Roughin Labor | PR | 341 | 03/14/18 | 03/16/18 | GA70 | Garcia, Jordan X | 40 | 0 | 1240 | 0 | 1240 | 19162 | 0 | 0
120 | Roughin Labor | PR | 359 | 03/14/18 | 03/16/18 | ME52 | Mendoza, Edgar E | 40 | 0 | 800 | 0 | 800 | 19180 | 0 | 0
120 | Roughin Labor | PR | 369 | 03/14/18 | 03/16/18 | RE18 | Reed, Reuben H | 21 | 0 | 840 | 0 | 840 | 19190 | 0 | 0
120 | Roughin Labor | PR | 539 | 03/21/18 | 03/23/18 | GA70 | Garcia, Jordan X | 32 | 0 | 992 | 0 | 992 | 19230 | 0 | 0
120 | Roughin Labor | PR | 555 | 03/21/18 | 03/23/18 | LU09 | Lucas Tzintzun, Rafael | 24 | 0 | 384 | 0 | 384 | 19246 | 0 | 0
120 | Roughin Labor | PR | 558 | 03/21/18 | 03/23/18 | ME52 | Mendoza, Edgar E | 32 | 0 | 640 | 0 | 640 | 19249 | 0 | 0
120 | Roughin Labor | PR | 568 | 03/21/18 | 03/23/18 | RE18 | Reed, Reuben H | 32 | 0 | 1280 | 0 | 1280 | 19259 | 0 | 0
120 | Roughin Labor | PR | 758 | 03/28/18 | 03/30/18 | GA70 | Garcia, Jordan X | 40 | 0 | 1240 | 0 | 1240 | 19298 | 0 | 0
120 | Roughin Labor | PR | 777 | 03/28/18 | 03/30/18 | LU09 | Lucas Tzintzun, Rafael | 39 | 0 | 624 | 0 | 624 | 19317 | 0 | 0
120 | Roughin Labor | PR | 780 | 03/28/18 | 03/30/18 | ME52 | Mendoza, Edgar E | 38.5 | 0 | 770 | 0 | 770 | 19320 | 0 | 0
120 | Roughin Labor | PR | 791 | 03/28/18 | 03/30/18 | RE18 | Reed, Reuben H | 40 | 0 | 1600 | 0 | 1600 | 19331 | 0 | 0
120 | Roughin Labor | PR | 34 | 04/04/18 | 04/06/18 | GA70 | Garcia, Jordan X | 40 | 0 | 1240 | 0 | 1240 | 19377 | 0 | 0
120 | Roughin Labor | PR | 52 | 04/04/18 | 04/06/18 | LU09 | Lucas Tzintzun, Rafael | 39.5 | 0 | 632 | 0 | 632 | 19395 | 0 | 0
120 | Roughin Labor | PR | 55 | 04/04/18 | 04/06/18 | ME52 | Mendoza, Edgar E | 36.5 | 0 | 730 | 0 | 730 | 19398 | 0 | 0
120 | Roughin Labor | PR | 65 | 04/04/18 | 04/06/18 | RE18 | Reed, Reuben H | 36 | 0 | 1440 | 0 | 1440 | 19408 | 0 | 0
120 | Roughin Labor | PR | 263 | 04/11/18 | 04/13/18 | BA70 | Barnhart, Joseph N | 3 | 0 | 132 | 0 | 132 | 19431 | 0 | 0
120 | Roughin Labor | PR | 282 | 04/11/18 | 04/13/18 | GA70 | Garcia, Jordan X | 20 | 0 | 620 | 0 | 620 | 19450 | 0 | 0
120 | Roughin Labor | PR | 301 | 04/11/18 | 04/13/18 | LU09 | Lucas Tzintzun, Rafael | 30 | 0 | 480 | 0 | 480 | 19469 | 0 | 0
120 | Roughin Labor | PR | 304 | 04/11/18 | 04/13/18 | ME52 | Mendoza, Edgar E | 24 | 0 | 480 | 0 | 480 | 19472 | 0 | 0
120 | Roughin Labor | PR | 315 | 04/11/18 | 04/13/18 | RE18 | Reed, Reuben H | 24 | 0 | 960 | 0 | 960 | 19483 | 0 | 0
120 | Roughin Labor | PR | 467 | 04/18/18 | 04/20/18 | GA70 | Garcia, Jordan X | 36 | 0 | 1116 | 0 | 1116 | 19525 | 0 | 0
120 | Roughin Labor | PR | 486 | 04/18/18 | 04/20/18 | LU09 | Lucas Tzintzun, Rafael | 31.5 | 0 | 504 | 0 | 504 | 19544 | 0 | 0
120 | Roughin Labor | PR | 489 | 04/18/18 | 04/20/18 | ME52 | Mendoza, Edgar E | 32 | 0 | 640 | 0 | 640 | 19547 | 0 | 0
120 | Roughin Labor | PR | 500 | 04/18/18 | 04/20/18 | RE18 | Reed, Reuben H | 40 | 0 | 1600 | 0 | 1600 | 19558 | 0 | 0
120 | Roughin Labor | PR | 617 | 04/25/18 | 04/27/18 | BA70 | Barnhart, Joseph N | 1 | 0 | 44 | 0 | 44 | 19582 | 0 | 0
120 | Roughin Labor | PR | 653 | 04/25/18 | 04/27/18 | LU09 | Lucas Tzintzun, Rafael | 39 | 0 | 624 | 0 | 624 | 19618 | 0 | 0
120 | Roughin Labor | PR | 656 | 04/25/18 | 04/27/18 | ME52 | Mendoza, Edgar E | 40 | 0 | 800 | 0 | 800 | 19621 | 0 | 0
120 | Roughin Labor | PR | 666 | 04/25/18 | 04/27/18 | RE18 | Reed, Reuben H | 32 | 0 | 1280 | 0 | 1280 | 19631 | 0 | 0
120 | Roughin Labor | PR | 677 | 04/25/18 | 04/27/18 | VE42 | Velasquez Cruz, Denis M | 40 | 0 | 1080 | 0 | 1080 | 19642 | 0 | 0
120 | Roughin Labor | PR | 678 | 04/25/18 | 04/27/18 | VE43 | Velasquez Cruz, Osman N | 40 | 0 | 760 | 0 | 760 | 19643 | 0 | 0
120 | Roughin Labor | PR | 31 | 05/02/18 | 05/04/18 | BA70 | Barnhart, Joseph N | 1 | 0 | 44 | 0 | 44 | 19654 | 0 | 0
120 | Roughin Labor | PR | 67 | 05/02/18 | 05/04/18 | LU09 | Lucas Tzintzun, Rafael | 38.5 | 0 | 616 | 0 | 616 | 19690 | 0 | 0
120 | Roughin Labor | PR | 70 | 05/02/18 | 05/04/18 | ME52 | Mendoza, Edgar E | 40 | 0 | 800 | 0 | 800 | 19693 | 0 | 0
120 | Roughin Labor | PR | 81 | 05/02/18 | 05/04/18 | RE18 | Reed, Reuben H | 40 | 0 | 1600 | 0 | 1600 | 19704 | 0 | 0
120 | Roughin Labor | PR | 92 | 05/02/18 | 05/04/18 | VE42 | Velasquez Cruz, Denis M | 40 | 0 | 1080 | 0 | 1080 | 19715 | 0 | 0
120 | Roughin Labor | PR | 93 | 05/02/18 | 05/04/18 | VE43 | Velasquez Cruz, Osman N | 40 | 0 | 760 | 0 | 760 | 19716 | 0 | 0
120 | Roughin Labor | PR | 260 | 05/09/18 | 05/11/18 | LU09 | Lucas Tzintzun, Rafael | 40 | 0 | 640 | 0 | 640 | 19767 | 0 | 0
120 | Roughin Labor | PR | 263 | 05/09/18 | 05/11/18 | ME52 | Mendoza, Edgar E | 40 | 0 | 800 | 0 | 800 | 19770 | 0 | 0
120 | Roughin Labor | PR | 273 | 05/09/18 | 05/11/18 | RE18 | Reed, Reuben H | 40 | 0 | 1600 | 0 | 1600 | 19780 | 0 | 0
120 | Roughin Labor | PR | 281 | 05/09/18 | 05/11/18 | VE42 | Velasquez Cruz, Denis M | 40 | 0 | 1080 | 0 | 1080 | 19788 | 0 | 0
120 | Roughin Labor | PR | 282 | 05/09/18 | 05/11/18 | VE43 | Velasquez Cruz, Osman N | 40 | 0 | 760 | 0 | 760 | 19789 | 0 | 0
120 | Roughin Labor | PR | 435 | 05/16/18 | 05/18/18 | CR79 | Cruz Guzman, Joel A | 24 | 0 | 528 | 0 | 528 | 19808 | 0 | 0
120 | Roughin Labor | PR | 436 | 05/16/18 | 05/18/18 | CR87 | Cruz Reyes, Jose | 24 | 0 | 552 | 0 | 552 | 19809 | 0 | 0
120 | Roughin Labor | PR | 452 | 05/16/18 | 05/18/18 | HU06 | Hubbard, Robert W | 11.5 | 0 | 517.5 | 0 | 517.5 | 19825 | 0 | 0
120 | Roughin Labor | PR | 461 | 05/16/18 | 05/18/18 | LU09 | Lucas Tzintzun, Rafael | 40 | 0 | 640 | 0 | 640 | 19834 | 0 | 0
120 | Roughin Labor | PR | 464 | 05/16/18 | 05/18/18 | ME52 | Mendoza, Edgar E | 40 | 0 | 800 | 0 | 800 | 19837 | 0 | 0
120 | Roughin Labor | PR | 475 | 05/16/18 | 05/18/18 | RE18 | Reed, Reuben H | 24 | 0 | 960 | 0 | 960 | 19848 | 0 | 0
120 | Roughin Labor | PR | 485 | 05/16/18 | 05/18/18 | VE42 | Velasquez Cruz, Denis M | 40 | 0 | 1080 | 0 | 1080 | 19858 | 0 | 0
120 | Roughin Labor | PR | 486 | 05/16/18 | 05/18/18 | VE43 | Velasquez Cruz, Osman N | 32 | 0 | 608 | 0 | 608 | 19859 | 0 | 0
120 | Roughin Labor | PR | 742 | 05/23/18 | 05/25/18 | BE45 | Belcher, Jacob T | 0 | 2 | 0 | 48 | 48 | 19871 | 0 | 0
120 | Roughin Labor | PR | 742 | 05/23/18 | 05/25/18 | BE45 | Belcher, Jacob T | 32 | 0 | 512 | 0 | 512 | 19871 | 0 | 0
120 | Roughin Labor | PR | 750 | 05/23/18 | 05/25/18 | CR79 | Cruz Guzman, Joel A | 0 | 2 | 0 | 66 | 66 | 19879 | 0 | 0
120 | Roughin Labor | PR | 750 | 05/23/18 | 05/25/18 | CR79 | Cruz Guzman, Joel A | 28 | 0 | 616 | 0 | 616 | 19879 | 0 | 0
120 | Roughin Labor | PR | 751 | 05/23/18 | 05/25/18 | CR87 | Cruz Reyes, Jose | 0 | 2 | 0 | 69 | 69 | 19880 | 0 | 0
120 | Roughin Labor | PR | 751 | 05/23/18 | 05/25/18 | CR87 | Cruz Reyes, Jose | 28 | 0 | 644 | 0 | 644 | 19880 | 0 | 0
120 | Roughin Labor | PR | 757 | 05/23/18 | 05/25/18 | GA70 | Garcia, Jordan X | 4 | 0 | 124 | 0 | 124 | 19886 | 0 | 0
120 | Roughin Labor | PR | 764 | 05/23/18 | 05/25/18 | HO18 | Hoeg, Xavier A | 0 | 2 | 0 | 45 | 45 | 19893 | 0 | 0
120 | Roughin Labor | PR | 764 | 05/23/18 | 05/25/18 | HO18 | Hoeg, Xavier A | 32 | 0 | 480 | 0 | 480 | 19893 | 0 | 0
120 | Roughin Labor | PR | 776 | 05/23/18 | 05/25/18 | LU09 | Lucas Tzintzun, Rafael | 0 | 2 | 0 | 48 | 48 | 19905 | 0 | 0
120 | Roughin Labor | PR | 776 | 05/23/18 | 05/25/18 | LU09 | Lucas Tzintzun, Rafael | 40 | 0 | 640 | 0 | 640 | 19905 | 0 | 0
120 | Roughin Labor | PR | 779 | 05/23/18 | 05/25/18 | ME52 | Mendoza, Edgar E | 0 | 2 | 0 | 60 | 60 | 19908 | 0 | 0
120 | Roughin Labor | PR | 779 | 05/23/18 | 05/25/18 | ME52 | Mendoza, Edgar E | 40 | 0 | 800 | 0 | 800 | 19908 | 0 | 0
120 | Roughin Labor | PR | 790 | 05/23/18 | 05/25/18 | RE18 | Reed, Reuben H | 0 | 2 | 0 | 120 | 120 | 19919 | 0 | 0
120 | Roughin Labor | PR | 790 | 05/23/18 | 05/25/18 | RE18 | Reed, Reuben H | 36 | 0 | 1440 | 0 | 1440 | 19919 | 0 | 0
120 | Roughin Labor | PR | 800 | 05/23/18 | 05/25/18 | VE42 | Velasquez Cruz, Denis M | 0 | 2 | 0 | 81 | 81 | 19929 | 0 | 0
120 | Roughin Labor | PR | 800 | 05/23/18 | 05/25/18 | VE42 | Velasquez Cruz, Denis M | 40 | 0 | 1080 | 0 | 1080 | 19929 | 0 | 0
120 | Roughin Labor | PR | 801 | 05/23/18 | 05/25/18 | VE43 | Velasquez Cruz, Osman N | 0 | 2 | 0 | 57 | 57 | 19930 | 0 | 0
120 | Roughin Labor | PR | 801 | 05/23/18 | 05/25/18 | VE43 | Velasquez Cruz, Osman N | 40 | 0 | 760 | 0 | 760 | 19930 | 0 | 0
120 | Roughin Labor | PR | 9 | 05/30/18 | 06/01/18 | BE45 | Belcher, Jacob T | 35 | 0 | 560 | 0 | 560 | 19942 | 0 | 0
120 | Roughin Labor | PR | 17 | 05/30/18 | 06/01/18 | CR79 | Cruz Guzman, Joel A | 35 | 0 | 770 | 0 | 770 | 19951 | 0 | 0
120 | Roughin Labor | PR | 18 | 05/30/18 | 06/01/18 | CR87 | Cruz Reyes, Jose | 35 | 0 | 805 | 0 | 805 | 19952 | 0 | 0
120 | Roughin Labor | PR | 31 | 05/30/18 | 06/01/18 | HO18 | Hoeg, Xavier A | 35 | 0 | 525 | 0 | 525 | 19965 | 0 | 0
120 | Roughin Labor | PR | 43 | 05/30/18 | 06/01/18 | LU09 | Lucas Tzintzun, Rafael | 35 | 0 | 560 | 0 | 560 | 19977 | 0 | 0
120 | Roughin Labor | PR | 46 | 05/30/18 | 06/01/18 | ME52 | Mendoza, Edgar E | 35 | 0 | 700 | 0 | 700 | 19980 | 0 | 0
120 | Roughin Labor | PR | 56 | 05/30/18 | 06/01/18 | RE18 | Reed, Reuben H | 32 | 0 | 1280 | 0 | 1280 | 19990 | 0 | 0
120 | Roughin Labor | PR | 68 | 05/30/18 | 06/01/18 | VE43 | Velasquez Cruz, Osman N | 17 | 0 | 323 | 0 | 323 | 20002 | 0 | 0
120 | Roughin Labor | PR | 274 | 06/06/18 | 06/08/18 | BE45 | Belcher, Jacob T | 0 | 4 | 0 | 96 | 96 | 20014 | 0 | 0
120 | Roughin Labor | PR | 274 | 06/06/18 | 06/08/18 | BE45 | Belcher, Jacob T | 40 | 0 | 640 | 0 | 640 | 20014 | 0 | 0
120 | Roughin Labor | PR | 282 | 06/06/18 | 06/08/18 | CR79 | Cruz Guzman, Joel A | 0 | 4 | 0 | 132 | 132 | 20022 | 0 | 0
120 | Roughin Labor | PR | 282 | 06/06/18 | 06/08/18 | CR79 | Cruz Guzman, Joel A | 40 | 0 | 880 | 0 | 880 | 20022 | 0 | 0
120 | Roughin Labor | PR | 283 | 06/06/18 | 06/08/18 | CR87 | Cruz Reyes, Jose | 9 | 0 | 207 | 0 | 207 | 20023 | 0 | 0
120 | Roughin Labor | PR | 296 | 06/06/18 | 06/08/18 | HO18 | Hoeg, Xavier A | 0 | 1 | 0 | 22.5 | 22.5 | 20036 | 0 | 0
120 | Roughin Labor | PR | 296 | 06/06/18 | 06/08/18 | HO18 | Hoeg, Xavier A | 16 | 0 | 240 | 0 | 240 | 20036 | 0 | 0
120 | Roughin Labor | PR | 308 | 06/06/18 | 06/08/18 | LU09 | Lucas Tzintzun, Rafael | 0 | 4 | 0 | 96 | 96 | 20048 | 0 | 0
120 | Roughin Labor | PR | 308 | 06/06/18 | 06/08/18 | LU09 | Lucas Tzintzun, Rafael | 40 | 0 | 640 | 0 | 640 | 20048 | 0 | 0
120 | Roughin Labor | PR | 311 | 06/06/18 | 06/08/18 | ME52 | Mendoza, Edgar E | 0 | 3 | 0 | 90 | 90 | 20051 | 0 | 0
120 | Roughin Labor | PR | 311 | 06/06/18 | 06/08/18 | ME52 | Mendoza, Edgar E | 40 | 0 | 800 | 0 | 800 | 20051 | 0 | 0
120 | Roughin Labor | PR | 321 | 06/06/18 | 06/08/18 | RE18 | Reed, Reuben H | 0 | 2 | 0 | 120 | 120 | 20061 | 0 | 0
120 | Roughin Labor | PR | 321 | 06/06/18 | 06/08/18 | RE18 | Reed, Reuben H | 24 | 0 | 960 | 0 | 960 | 20061 | 0 | 0
120 | Roughin Labor | PR | 334 | 06/06/18 | 06/08/18 | VE43 | Velasquez Cruz, Osman N | 8 | 0 | 152 | 0 | 152 | 20074 | 0 | 0
120 | Roughin Labor | PR | 350 | 06/06/18 | 06/08/18 | VE43 | Velasquez Cruz, Osman N | 8 | 0 | -152 | 0 | -152 | 20082 | 0 | 0
120 | Roughin Labor | PR | 464 | 06/13/18 | 06/15/18 | BE45 | Belcher, Jacob T | 0 | 1 | 0 | 25.5 | 25.5 | 20099 | 0 | 0
120 | Roughin Labor | PR | 464 | 06/13/18 | 06/15/18 | BE45 | Belcher, Jacob T | 16 | 0 | 272 | 0 | 272 | 20099 | 0 | 0
120 | Roughin Labor | PR | 472 | 06/13/18 | 06/15/18 | CR79 | Cruz Guzman, Joel A | 17 | 0 | 391 | 0 | 391 | 20107 | 0 | 0
120 | Roughin Labor | PR | 498 | 06/13/18 | 06/15/18 | LU09 | Lucas Tzintzun, Rafael | 0 | 1 | 0 | 25.5 | 25.5 | 20133 | 0 | 0
120 | Roughin Labor | PR | 498 | 06/13/18 | 06/15/18 | LU09 | Lucas Tzintzun, Rafael | 16 | 0 | 272 | 0 | 272 | 20133 | 0 | 0
120 | Roughin Labor | PR | 501 | 06/13/18 | 06/15/18 | ME52 | Mendoza, Edgar E | 0 | 4 | 0 | 126 | 126 | 20136 | 0 | 0
120 | Roughin Labor | PR | 501 | 06/13/18 | 06/15/18 | ME52 | Mendoza, Edgar E | 40 | 0 | 840 | 0 | 840 | 20136 | 0 | 0
120 | Roughin Labor | PR | 510 | 06/13/18 | 06/15/18 | RE18 | Reed, Reuben H | 0 | 2 | 0 | 123 | 123 | 20145 | 0 | 0
120 | Roughin Labor | PR | 510 | 06/13/18 | 06/15/18 | RE18 | Reed, Reuben H | 19 | 0 | 779 | 0 | 779 | 20145 | 0 | 0
120 | Roughin Labor | PR | 690 | 06/20/18 | 06/22/18 | BE45 | Belcher, Jacob T | 17 | 0 | 289 | 0 | 289 | 20169 | 0 | 0
120 | Roughin Labor | PR | 698 | 06/20/18 | 06/22/18 | CR79 | Cruz Guzman, Joel A | 0 | 4 | 0 | 138 | 138 | 20177 | 0 | 0
120 | Roughin Labor | PR | 698 | 06/20/18 | 06/22/18 | CR79 | Cruz Guzman, Joel A | 40 | 0 | 920 | 0 | 920 | 20177 | 0 | 0
120 | Roughin Labor | PR | 699 | 06/20/18 | 06/22/18 | CR87 | Cruz Reyes, Jose | 0 | 3 | 0 | 108 | 108 | 20178 | 0 | 0
120 | Roughin Labor | PR | 699 | 06/20/18 | 06/22/18 | CR87 | Cruz Reyes, Jose | 24 | 0 | 576 | 0 | 576 | 20178 | 0 | 0
120 | Roughin Labor | PR | 724 | 06/20/18 | 06/22/18 | LU09 | Lucas Tzintzun, Rafael | 26 | 0 | 442 | 0 | 442 | 20203 | 0 | 0
120 | Roughin Labor | PR | 727 | 06/20/18 | 06/22/18 | ME52 | Mendoza, Edgar E | 0 | 2 | 0 | 63 | 63 | 20206 | 0 | 0
120 | Roughin Labor | PR | 727 | 06/20/18 | 06/22/18 | ME52 | Mendoza, Edgar E | 40 | 0 | 840 | 0 | 840 | 20206 | 0 | 0
120 | Roughin Labor | PR | 736 | 06/20/18 | 06/22/18 | RE18 | Reed, Reuben H | 0 | 3 | 0 | 184.5 | 184.5 | 20215 | 0 | 0
120 | Roughin Labor | PR | 736 | 06/20/18 | 06/22/18 | RE18 | Reed, Reuben H | 40 | 0 | 1640 | 0 | 1640 | 20215 | 0 | 0
120 | Roughin Labor | PR | 958 | 06/27/18 | 06/29/18 | BE45 | Belcher, Jacob T | 0 | 2 | 0 | 51 | 51 | 20239 | 0 | 0
120 | Roughin Labor | PR | 958 | 06/27/18 | 06/29/18 | BE45 | Belcher, Jacob T | 10 | 0 | 170 | 0 | 170 | 20239 | 0 | 0
120 | Roughin Labor | PR | 965 | 06/27/18 | 06/29/18 | CR79 | Cruz Guzman, Joel A | 0 | 1 | 0 | 34.5 | 34.5 | 20246 | 0 | 0
120 | Roughin Labor | PR | 965 | 06/27/18 | 06/29/18 | CR79 | Cruz Guzman, Joel A | 8 | 0 | 184 | 0 | 184 | 20246 | 0 | 0
120 | Roughin Labor | PR | 966 | 06/27/18 | 06/29/18 | CR87 | Cruz Reyes, Jose | 9 | 0 | 216 | 0 | 216 | 20247 | 0 | 0
120 | Roughin Labor | PR | 992 | 06/27/18 | 06/29/18 | LU09 | Lucas Tzintzun, Rafael | 0 | 4 | 0 | 102 | 102 | 20272 | 0 | 0
120 | Roughin Labor | PR | 992 | 06/27/18 | 06/29/18 | LU09 | Lucas Tzintzun, Rafael | 40 | 0 | 680 | 0 | 680 | 20272 | 0 | 0
120 | Roughin Labor | PR | 995 | 06/27/18 | 06/29/18 | ME52 | Mendoza, Edgar E | 0 | 3 | 0 | 99 | 99 | 20275 | 0 | 0
120 | Roughin Labor | PR | 995 | 06/27/18 | 06/29/18 | ME52 | Mendoza, Edgar E | 40 | 0 | 880 | 0 | 880 | 20275 | 0 | 0
120 | Roughin Labor | PR | 1003 | 06/27/18 | 06/29/18 | RE18 | Reed, Reuben H | 0 | 2 | 0 | 123 | 123 | 20283 | 0 | 0
120 | Roughin Labor | PR | 1003 | 06/27/18 | 06/29/18 | RE18 | Reed, Reuben H | 16 | 0 | 656 | 0 | 656 | 20283 | 0 | 0
120 | Roughin Labor | PR | 11 | 07/04/18 | 07/06/18 | BE45 | Belcher, Jacob T | 32 | 0 | 544 | 0 | 544 | 20308 | 0 | 0
120 | Roughin Labor | PR | 19 | 07/04/18 | 07/06/18 | CR79 | Cruz Guzman, Joel A | 17 | 0 | 391 | 0 | 391 | 20316 | 0 | 0
120 | Roughin Labor | PR | 20 | 07/04/18 | 07/06/18 | CR87 | Cruz Reyes, Jose | 32 | 0 | 768 | 0 | 768 | 20317 | 0 | 0
120 | Roughin Labor | PR | 47 | 07/04/18 | 07/06/18 | LU09 | Lucas Tzintzun, Rafael | 32 | 0 | 544 | 0 | 544 | 20343 | 0 | 0
120 | Roughin Labor | PR | 50 | 07/04/18 | 07/06/18 | ME52 | Mendoza, Edgar E | 23 | 0 | 506 | 0 | 506 | 20346 | 0 | 0
120 | Roughin Labor | PR | 58 | 07/04/18 | 07/06/18 | RE18 | Reed, Reuben H | 32 | 0 | 1312 | 0 | 1312 | 20354 | 0 | 0
120 | Roughin Labor | PR | 241 | 07/11/18 | 07/13/18 | BA70 | Barnhart, Joseph N | 2 | 0 | 92 | 0 | 92 | 20376 | 0 | 0
120 | Roughin Labor | PR | 302 | 07/11/18 | 07/13/18 | BE45 | Belcher, Jacob T | 40 | 0 | 680 | 0 | 680 | 20382 | 0 | 0
120 | Roughin Labor | PR | 310 | 07/11/18 | 07/13/18 | CR79 | Cruz Guzman, Joel A | 24 | 0 | 552 | 0 | 552 | 20390 | 0 | 0
120 | Roughin Labor | PR | 311 | 07/11/18 | 07/13/18 | CR87 | Cruz Reyes, Jose | 40 | 0 | 960 | 0 | 960 | 20391 | 0 | 0
120 | Roughin Labor | PR | 338 | 07/11/18 | 07/13/18 | LU09 | Lucas Tzintzun, Rafael | 40 | 0 | 680 | 0 | 680 | 20418 | 0 | 0
120 | Roughin Labor | PR | 341 | 07/11/18 | 07/13/18 | ME52 | Mendoza, Edgar E | 40 | 0 | 880 | 0 | 880 | 20421 | 0 | 0
120 | Roughin Labor | PR | 350 | 07/11/18 | 07/13/18 | RE18 | Reed, Reuben H | 32 | 0 | 1312 | 0 | 1312 | 20430 | 0 | 0
120 | Roughin Labor | PR | 442 | 07/18/18 | 07/20/18 | BE45 | Belcher, Jacob T | 40 | 0 | 680 | 0 | 680 | 20453 | 0 | 0
120 | Roughin Labor | PR | 450 | 07/18/18 | 07/20/18 | CR79 | Cruz Guzman, Joel A | 40 | 0 | 920 | 0 | 920 | 20461 | 0 | 0
120 | Roughin Labor | PR | 451 | 07/18/18 | 07/20/18 | CR87 | Cruz Reyes, Jose | 40 | 0 | 960 | 0 | 960 | 20462 | 0 | 0
120 | Roughin Labor | PR | 470 | 07/18/18 | 07/20/18 | HU06 | Hubbard, Robert W | 1.5 | 0 | 70.5 | 0 | 70.5 | 20480 | 0 | 0
120 | Roughin Labor | PR | 479 | 07/18/18 | 07/20/18 | LU09 | Lucas Tzintzun, Rafael | 40 | 0 | 680 | 0 | 680 | 20489 | 0 | 0
120 | Roughin Labor | PR | 482 | 07/18/18 | 07/20/18 | ME52 | Mendoza, Edgar E | 40 | 0 | 880 | 0 | 880 | 20492 | 0 | 0
120 | Roughin Labor | PR | 490 | 07/18/18 | 07/20/18 | RE18 | Reed, Reuben H | 40 | 0 | 1640 | 0 | 1640 | 20500 | 0 | 0
120 | Roughin Labor | PR | 768 | 07/25/18 | 07/27/18 | BE45 | Belcher, Jacob T | 16 | 0 | 272 | 0 | 272 | 20526 | 0 | 0
120 | Roughin Labor | PR | 777 | 07/25/18 | 07/27/18 | CR87 | Cruz Reyes, Jose | 12 | 0 | 288 | 0 | 288 | 20535 | 0 | 0
120 | Roughin Labor | PR | 806 | 07/25/18 | 07/27/18 | LU09 | Lucas Tzintzun, Rafael | 8 | 0 | 136 | 0 | 136 | 20563 | 0 | 0
120 | Roughin Labor | PR | 809 | 07/25/18 | 07/27/18 | ME52 | Mendoza, Edgar E | 40 | 0 | 880 | 0 | 880 | 20566 | 0 | 0
120 | Roughin Labor | PR | 817 | 07/25/18 | 07/27/18 | RE18 | Reed, Reuben H | 38 | 0 | 1558 | 0 | 1558 | 20574 | 0 | 0
120 | Roughin Labor | PR | 7 | 08/01/18 | 08/03/18 | BE45 | Belcher, Jacob T | 16 | 0 | 272 | 0 | 272 | 20598 | 0 | 0
120 | Roughin Labor | PR | 15 | 08/01/18 | 08/03/18 | CR79 | Cruz Guzman, Joel A | 24 | 0 | 552 | 0 | 552 | 20607 | 0 | 0
120 | Roughin Labor | PR | 16 | 08/01/18 | 08/03/18 | CR87 | Cruz Reyes, Jose | 24 | 0 | 576 | 0 | 576 | 20608 | 0 | 0
120 | Roughin Labor | PR | 47 | 08/01/18 | 08/03/18 | ME52 | Mendoza, Edgar E | 8 | 0 | 176 | 0 | 176 | 20638 | 0 | 0
120 | Roughin Labor | PR | 55 | 08/01/18 | 08/03/18 | RE18 | Reed, Reuben H | 40 | 0 | 1640 | 0 | 1640 | 20646 | 0 | 0
120 | Roughin Labor | PR | 216 | 08/08/18 | 08/10/18 | BA70 | Barnhart, Joseph N | 2 | 0 | 92 | 0 | 92 | 20669 | 0 | 0
120 | Roughin Labor | PR | 217 | 08/08/18 | 08/10/18 | BE45 | Belcher, Jacob T | 40 | 0 | 680 | 0 | 680 | 20670 | 0 | 0
120 | Roughin Labor | PR | 225 | 08/08/18 | 08/10/18 | CR79 | Cruz Guzman, Joel A | 32 | 0 | 736 | 0 | 736 | 20678 | 0 | 0
120 | Roughin Labor | PR | 226 | 08/08/18 | 08/10/18 | CR87 | Cruz Reyes, Jose | 36 | 0 | 864 | 0 | 864 | 20679 | 0 | 0
120 | Roughin Labor | PR | 246 | 08/08/18 | 08/10/18 | HU06 | Hubbard, Robert W | 11 | 0 | 517 | 0 | 517 | 20698 | 0 | 0
120 | Roughin Labor | PR | 255 | 08/08/18 | 08/10/18 | LU09 | Lucas Tzintzun, Rafael | 24 | 0 | 408 | 0 | 408 | 20707 | 0 | 0
120 | Roughin Labor | PR | 258 | 08/08/18 | 08/10/18 | ME52 | Mendoza, Edgar E | 22.5 | 0 | 495 | 0 | 495 | 20710 | 0 | 0
120 | Roughin Labor | PR | 266 | 08/08/18 | 08/10/18 | RE18 | Reed, Reuben H | 16 | 0 | 656 | 0 | 656 | 20718 | 0 | 0
120 | Roughin Labor | PR | 484 | 08/15/18 | 08/17/18 | BA70 | Barnhart, Joseph N | 1 | 0 | 46 | 0 | 46 | 20742 | 0 | 0
120 | Roughin Labor | PR | 485 | 08/15/18 | 08/17/18 | BE45 | Belcher, Jacob T | 40 | 0 | 680 | 0 | 680 | 20743 | 0 | 0
120 | Roughin Labor | PR | 493 | 08/15/18 | 08/17/18 | CR79 | Cruz Guzman, Joel A | 24 | 0 | 552 | 0 | 552 | 20751 | 0 | 0
120 | Roughin Labor | PR | 494 | 08/15/18 | 08/17/18 | CR87 | Cruz Reyes, Jose | 32 | 0 | 768 | 0 | 768 | 20752 | 0 | 0
120 | Roughin Labor | PR | 514 | 08/15/18 | 08/17/18 | HU06 | Hubbard, Robert W | 2 | 0 | 94 | 0 | 94 | 20771 | 0 | 0
120 | Roughin Labor | PR | 525 | 08/15/18 | 08/17/18 | ME52 | Mendoza, Edgar E | 40 | 0 | 880 | 0 | 880 | 20782 | 0 | 0
120 | Roughin Labor | PR | 533 | 08/15/18 | 08/17/18 | RE18 | Reed, Reuben H | 24 | 0 | 984 | 0 | 984 | 20790 | 0 | 0
120 | Roughin Labor | PR | 747 | 08/22/18 | 08/24/18 | BE45 | Belcher, Jacob T | 40 | 0 | 680 | 0 | 680 | 20815 | 0 | 0
120 | Roughin Labor | PR | 755 | 08/22/18 | 08/24/18 | CR79 | Cruz Guzman, Joel A | 40 | 0 | 920 | 0 | 920 | 20823 | 0 | 0
120 | Roughin Labor | PR | 756 | 08/22/18 | 08/24/18 | CR87 | Cruz Reyes, Jose | 40 | 0 | 960 | 0 | 960 | 20824 | 0 | 0
120 | Roughin Labor | PR | 786 | 08/22/18 | 08/24/18 | ME52 | Mendoza, Edgar E | 20 | 0 | 440 | 0 | 440 | 20853 | 0 | 0
120 | Roughin Labor | PR | 794 | 08/22/18 | 08/24/18 | RE18 | Reed, Reuben H | 38 | 0 | 1558 | 0 | 1558 | 20861 | 0 | 0
120 | Roughin Labor | PR | 1009 | 08/29/18 | 08/31/18 | CR79 | Cruz Guzman, Joel A | 40 | 0 | 920 | 0 | 920 | 20905 | 0 | 0
120 | Roughin Labor | PR | 1010 | 08/29/18 | 08/31/18 | CR87 | Cruz Reyes, Jose | 40 | 0 | 960 | 0 | 960 | 20906 | 0 | 0
120 | Roughin Labor | PR | 1040 | 08/29/18 | 08/31/18 | ME52 | Mendoza, Edgar E | 8 | 0 | 176 | 0 | 176 | 20935 | 0 | 0
120 | Roughin Labor | PR | 1048 | 08/29/18 | 08/31/18 | RE18 | Reed, Reuben H | 32 | 0 | 1312 | 0 | 1312 | 20943 | 0 | 0
120 | Roughin Labor | PR | 50 | 09/05/18 | 09/07/18 | CR79 | Cruz Guzman, Joel A | 16 | 0 | 368 | 0 | 368 | 20975 | 0 | 0
120 | Roughin Labor | PR | 51 | 09/05/18 | 09/07/18 | CR87 | Cruz Reyes, Jose | 16 | 0 | 384 | 0 | 384 | 20976 | 0 | 0
120 | Roughin Labor | PR | 88 | 09/05/18 | 09/07/18 | RE18 | Reed, Reuben H | 16 | 0 | 656 | 0 | 656 | 21013 | 0 | 0
120 | Roughin Labor | PR | 281 | 09/12/18 | 09/14/18 | CR79 | Cruz Guzman, Joel A | 40 | 0 | 920 | 0 | 920 | 21116 | 0 | 0
120 | Roughin Labor | PR | 282 | 09/12/18 | 09/14/18 | CR87 | Cruz Reyes, Jose | 40 | 0 | 960 | 0 | 960 | 21117 | 0 | 0
120 | Roughin Labor | PR | 302 | 09/12/18 | 09/14/18 | HU06 | Hubbard, Robert W | 2 | 0 | 94 | 0 | 94 | 21136 | 0 | 0
120 | Roughin Labor | PR | 320 | 09/12/18 | 09/14/18 | RE18 | Reed, Reuben H | 32 | 0 | 1312 | 0 | 1312 | 21154 | 0 | 0
120 | Roughin Labor | PR | 494 | 09/19/18 | 09/21/18 | CR79 | Cruz Guzman, Joel A | 32 | 0 | 736 | 0 | 736 | 21186 | 0 | 0
120 | Roughin Labor | PR | 495 | 09/19/18 | 09/21/18 | CR87 | Cruz Reyes, Jose | 40 | 0 | 960 | 0 | 960 | 21187 | 0 | 0
120 | Roughin Labor | PR | 533 | 09/19/18 | 09/21/18 | RE18 | Reed, Reuben H | 39 | 0 | 1599 | 0 | 1599 | 21224 | 0 | 0
120 | Roughin Labor | PR | 718 | 09/26/18 | 09/28/18 | RE18 | Reed, Reuben H | 35 | 0 | 1435 | 0 | 1435 | 21296 | 0 | 0
120 | Roughin Labor | PR | 728 | 09/26/18 | 09/28/18 | SI48 | Silva Morales, Jair J | 37 | 0 | 888 | 0 | 888 | 21306 | 0 | 0
120 | Roughin Labor | PR | 82 | 10/03/18 | 10/05/18 | RE18 | Reed, Reuben H | 40 | 0 | 1640 | 0 | 1640 | 21370 | 0 | 0
120 | Roughin Labor | PR | 92 | 10/03/18 | 10/05/18 | SI48 | Silva Morales, Jair J | 16 | 0 | 384 | 0 | 384 | 21380 | 0 | 0
120 | Roughin Labor | PR | 288 | 10/10/18 | 10/12/18 | RE18 | Reed, Reuben H | 7 | 0 | 287 | 0 | 287 | 21445 | 0 | 0
120 | Roughin Labor | PR | 751 | 10/24/18 | 10/26/18 | RE18 | Reed, Reuben H | 7 | 0 | 287 | 0 | 287 | 21591 | 0 | 0
120 | Roughin Labor | PR | 55 | 10/31/18 | 11/02/18 | RE18 | Reed, Reuben H | 2 | 0 | 82 | 0 | 82 | 21664 | 0 | 0
120 | Roughin Labor | PR | 234 | 11/07/18 | 11/09/18 | RE18 | Reed, Reuben H | 11 | 0 | 451 | 0 | 451 | 21737 | 0 | 0
120 | Roughin Labor | PR | 621 | 11/21/18 | 11/21/18 | BA70 | Barnhart, Joseph N | 8 | 0 | 368 | 0 | 368 | 21843 | 0 | 0
120 | Roughin Labor | PR | 879 | 11/28/18 | 11/30/18 | RE18 | Reed, Reuben H | 5 | 0 | 215 | 0 | 215 | 21961 | 0 | 0
120 | Roughin Labor | PR | 63 | 12/05/18 | 12/07/18 | FO55 | Fonseca Teruel, Eduardo | 0 | 0.5 | 0 | 13.5 | 13.5 | 22005 | 0 | 0
120 | Roughin Labor | PR | 91 | 12/05/18 | 12/07/18 | RE18 | Reed, Reuben H | 4 | 0 | 172 | 0 | 172 | 22033 | 0 | 0
120 | Roughin Labor | PR | 557 | 12/19/18 | 12/21/18 | RE91 | Reyes, Maria E | 32 | 0 | 576 | 0 | 576 | 22247 | 0 | 0
120 | Roughin Labor | PR | 776 | 12/26/18 | 12/28/18 | RE91 | Reyes, Maria E | 32 | 0 | -576 | 0 | -576 | 22348 | 0 | 0
120 | Roughin Labor | PR | 260 | 01/09/19 | 01/11/19 | RE18 | Reed, Reuben H | 1 | 0 | 43 | 0 | 43 | 22462 | 0 | 0
120 | Roughin Labor | PR | 516 | 01/16/19 | 01/18/19 | RE91 | Reyes, Maria E | 0 | 3 | 0 | 81 | 81 | 22537 | 0 | 0
120 | Roughin Labor | PR | 372 | 04/10/19 | 04/12/19 | RE18 | Reed, Reuben H | 7 | 0 | 315 | 0 | 315 | 23396 | 0 | 0
130 | Finish Labor | PR | 534 | 09/20/17 | 09/22/17 | SA54 | Sanders, Allen O | 1.5 | 0 | 60 | 0 | 60 | 17504 | 0 | 0
130 | Finish Labor | PR | 89 | 10/03/18 | 10/05/18 | SA54 | Sanders, Allen O | 2 | 0 | 88 | 0 | 88 | 21377 | 0 | 0
130 | Finish Labor | PR | 493 | 10/17/18 | 10/19/18 | SA54 | Sanders, Allen O | 1.5 | 0 | 66 | 0 | 66 | 21526 | 0 | 0
130 | Finish Labor | PR | 55 | 10/31/18 | 11/02/18 | RE18 | Reed, Reuben H | 2 | 0 | 82 | 0 | 82 | 21664 | 0 | 0
130 | Finish Labor | PR | 62 | 10/31/18 | 11/02/18 | SA54 | Sanders, Allen O | 2 | 0 | 88 | 0 | 88 | 21671 | 0 | 0
130 | Finish Labor | PR | 63 | 12/05/18 | 12/07/18 | FO55 | Fonseca Teruel, Eduardo | 8 | 0 | 144 | 0 | 144 | 22005 | 0 | 0
130 | Finish Labor | PR | 69 | 12/05/18 | 12/07/18 | GO51 | Gomez Reyes, Edith N | 0 | 0.5 | 0 | 17.25 | 17.25 | 22011 | 0 | 0
130 | Finish Labor | PR | 69 | 12/05/18 | 12/07/18 | GO51 | Gomez Reyes, Edith N | 8 | 0 | 184 | 0 | 184 | 22011 | 0 | 0
130 | Finish Labor | PR | 92 | 12/05/18 | 12/07/18 | RE91 | Reyes, Maria E | 0 | 0.5 | 0 | 13.5 | 13.5 | 22034 | 0 | 0
130 | Finish Labor | PR | 92 | 12/05/18 | 12/07/18 | RE91 | Reyes, Maria E | 8 | 0 | 144 | 0 | 144 | 22034 | 0 | 0
130 | Finish Labor | PR | 99 | 12/05/18 | 12/07/18 | SA54 | Sanders, Allen O | 6 | 0 | 282 | 0 | 282 | 22041 | 0 | 0
130 | Finish Labor | PR | 316 | 12/12/18 | 12/14/18 | RE18 | Reed, Reuben H | 5 | 0 | 215 | 0 | 215 | 22175 | 0 | 0
130 | Finish Labor | PR | 324 | 12/12/18 | 12/14/18 | SA54 | Sanders, Allen O | 2 | 0 | 94 | 0 | 94 | 22183 | 0 | 0
130 | Finish Labor | PR | 528 | 12/19/18 | 12/21/18 | FO55 | Fonseca Teruel, Eduardo | 8 | 0 | 144 | 0 | 144 | 22218 | 0 | 0
130 | Finish Labor | PR | 534 | 12/19/18 | 12/21/18 | GO51 | Gomez Reyes, Edith N | 24 | 0 | 552 | 0 | 552 | 22224 | 0 | 0
130 | Finish Labor | PR | 557 | 12/19/18 | 12/21/18 | RE91 | Reyes, Maria E | 0 | 2 | 0 | 54 | 54 | 22247 | 0 | 0
130 | Finish Labor | PR | 564 | 12/19/18 | 12/21/18 | SA54 | Sanders, Allen O | 0 | 2 | 0 | 141 | 141 | 22254 | 0 | 0
130 | Finish Labor | PR | 564 | 12/19/18 | 12/21/18 | SA54 | Sanders, Allen O | 16 | 0 | 752 | 0 | 752 | 22254 | 0 | 0
130 | Finish Labor | PR | 571 | 12/19/18 | 12/21/18 | TR60 | Trower-Kelly, Fidel D | 0 | 3 | 0 | 72 | 72 | 22261 | 0 | 0
130 | Finish Labor | PR | 571 | 12/19/18 | 12/21/18 | TR60 | Trower-Kelly, Fidel D | 16 | 0 | 256 | 0 | 256 | 22261 | 0 | 0
130 | Finish Labor | PR | 724 | 12/26/18 | 12/28/18 | GO51 | Gomez Reyes, Edith N | 8 | 0 | 184 | 0 | 184 | 22297 | 0 | 0
130 | Finish Labor | PR | 748 | 12/26/18 | 12/28/18 | RE91 | Reyes, Maria E | 26 | 0 | 468 | 0 | 468 | 22321 | 0 | 0
130 | Finish Labor | PR | 755 | 12/26/18 | 12/28/18 | SA54 | Sanders, Allen O | 4 | 0 | 188 | 0 | 188 | 22328 | 0 | 0
130 | Finish Labor | PR | 776 | 12/26/18 | 12/28/18 | RE91 | Reyes, Maria E | 32 | 0 | 576 | 0 | 576 | 22348 | 0 | 0
130 | Finish Labor | PR | 29 | 01/02/19 | 01/04/19 | GO51 | Gomez Reyes, Edith N | 8 | 0 | 184 | 0 | 184 | 22370 | 0 | 0
130 | Finish Labor | PR | 51 | 01/02/19 | 01/04/19 | RE91 | Reyes, Maria E | 8 | 0 | 144 | 0 | 144 | 22392 | 0 | 0
130 | Finish Labor | PR | 58 | 01/02/19 | 01/04/19 | SA54 | Sanders, Allen O | 2 | 0 | 94 | 0 | 94 | 22399 | 0 | 0
130 | Finish Labor | PR | 237 | 01/09/19 | 01/11/19 | GO51 | Gomez Reyes, Edith N | 0 | 1 | 0 | 34.5 | 34.5 | 22439 | 0 | 0
130 | Finish Labor | PR | 237 | 01/09/19 | 01/11/19 | GO51 | Gomez Reyes, Edith N | 24 | 0 | 552 | 0 | 552 | 22439 | 0 | 0
130 | Finish Labor | PR | 261 | 01/09/19 | 01/11/19 | RE91 | Reyes, Maria E | 0 | 1 | 0 | 27 | 27 | 22463 | 0 | 0
130 | Finish Labor | PR | 261 | 01/09/19 | 01/11/19 | RE91 | Reyes, Maria E | 24 | 0 | 432 | 0 | 432 | 22463 | 0 | 0
130 | Finish Labor | PR | 268 | 01/09/19 | 01/11/19 | SA54 | Sanders, Allen O | 9 | 0 | 423 | 0 | 423 | 22470 | 0 | 0
130 | Finish Labor | PR | 492 | 01/16/19 | 01/18/19 | GO51 | Gomez Reyes, Edith N | 0 | 3 | 0 | 103.5 | 103.5 | 22513 | 0 | 0
130 | Finish Labor | PR | 492 | 01/16/19 | 01/18/19 | GO51 | Gomez Reyes, Edith N | 32 | 0 | 736 | 0 | 736 | 22513 | 0 | 0
130 | Finish Labor | PR | 516 | 01/16/19 | 01/18/19 | RE91 | Reyes, Maria E | 32 | 0 | 576 | 0 | 576 | 22537 | 0 | 0
130 | Finish Labor | PR | 523 | 01/16/19 | 01/18/19 | SA54 | Sanders, Allen O | 1 | 0 | 47 | 0 | 47 | 22544 | 0 | 0
130 | Finish Labor | PR | 735 | 01/23/19 | 01/25/19 | FO55 | Fonseca Teruel, Eduardo | 8 | 0 | 144 | 0 | 144 | 22580 | 0 | 0
130 | Finish Labor | PR | 739 | 01/23/19 | 01/25/19 | GE70 | Gerard, Jordan E | 8 | 0 | 272 | 0 | 272 | 22584 | 0 | 0
130 | Finish Labor | PR | 741 | 01/23/19 | 01/25/19 | GO51 | Gomez Reyes, Edith N | 0 | 2 | 0 | 69 | 69 | 22586 | 0 | 0
130 | Finish Labor | PR | 741 | 01/23/19 | 01/25/19 | GO51 | Gomez Reyes, Edith N | 26 | 0 | 598 | 0 | 598 | 22586 | 0 | 0
130 | Finish Labor | PR | 765 | 01/23/19 | 01/25/19 | RE91 | Reyes, Maria E | 0 | 2 | 0 | 54 | 54 | 22610 | 0 | 0
130 | Finish Labor | PR | 765 | 01/23/19 | 01/25/19 | RE91 | Reyes, Maria E | 24 | 0 | 432 | 0 | 432 | 22610 | 0 | 0
130 | Finish Labor | PR | 772 | 01/23/19 | 01/25/19 | SA54 | Sanders, Allen O | 0 | 0.5 | 0 | 35.25 | 35.25 | 22617 | 0 | 0
130 | Finish Labor | PR | 772 | 01/23/19 | 01/25/19 | SA54 | Sanders, Allen O | 10.5 | 0 | 493.5 | 0 | 493.5 | 22617 | 0 | 0
130 | Finish Labor | PR | 776 | 01/23/19 | 01/25/19 | ST02 | Stahlschmidt, John P | 8 | 0 | 136 | 0 | 136 | 22621 | 0 | 0
130 | Finish Labor | PR | 29 | 01/30/19 | 02/01/19 | GO51 | Gomez Reyes, Edith N | 0 | 2 | 0 | 69 | 69 | 22658 | 0 | 0
130 | Finish Labor | PR | 29 | 01/30/19 | 02/01/19 | GO51 | Gomez Reyes, Edith N | 24 | 0 | 552 | 0 | 552 | 22658 | 0 | 0
130 | Finish Labor | PR | 51 | 01/30/19 | 02/01/19 | RE91 | Reyes, Maria E | 0 | 2 | 0 | 54 | 54 | 22680 | 0 | 0
130 | Finish Labor | PR | 51 | 01/30/19 | 02/01/19 | RE91 | Reyes, Maria E | 24 | 0 | 432 | 0 | 432 | 22680 | 0 | 0
130 | Finish Labor | PR | 57 | 01/30/19 | 02/01/19 | SA54 | Sanders, Allen O | 4 | 0 | 188 | 0 | 188 | 22686 | 0 | 0
130 | Finish Labor | PR | 58 | 01/30/19 | 02/01/19 | SE64 | Sepulveda Gonzalez, Alfredo | 2 | 0 | 64 | 0 | 64 | 22687 | 0 | 0
130 | Finish Labor | PR | 184 | 02/06/19 | 02/08/19 | GO51 | Gomez Reyes, Edith N | 16 | 0 | 368 | 0 | 368 | 22726 | 0 | 0
130 | Finish Labor | PR | 206 | 02/06/19 | 02/08/19 | RE91 | Reyes, Maria E | 16 | 0 | 288 | 0 | 288 | 22748 | 0 | 0
130 | Finish Labor | PR | 213 | 02/06/19 | 02/08/19 | SA54 | Sanders, Allen O | 3 | 0 | 141 | 0 | 141 | 22755 | 0 | 0
130 | Finish Labor | PR | 346 | 02/13/19 | 02/15/19 | GO51 | Gomez Reyes, Edith N | 14 | 0 | 322 | 0 | 322 | 22796 | 0 | 0
130 | Finish Labor | PR | 375 | 02/13/19 | 02/15/19 | SA54 | Sanders, Allen O | 0.5 | 0 | 23.5 | 0 | 23.5 | 22826 | 0 | 0
130 | Finish Labor | PR | 401 | 02/13/19 | 02/15/19 | RE91 | Reyes, Maria E | 14 | 0 | 252 | 0 | 252 | 922842 | 0 | 0
130 | Finish Labor | PR | 596 | 02/20/19 | 02/22/19 | EL33 | Eliassen, Cory H | 3 | 0 | 75 | 0 | 75 | 22858 | 0 | 0
130 | Finish Labor | PR | 634 | 02/20/19 | 02/22/19 | SA54 | Sanders, Allen O | 0 | 2 | 0 | 141 | 141 | 22896 | 0 | 0
130 | Finish Labor | PR | 641 | 02/20/19 | 02/22/19 | TR60 | Trower-Kelly, Fidel D | 11 | 0 | 176 | 0 | 176 | 22903 | 0 | 0
130 | Finish Labor | PR | 22 | 02/27/19 | 03/01/19 | EL33 | Eliassen, Cory H | 5.5 | 0 | 137.5 | 0 | 137.5 | 22929 | 0 | 0
130 | Finish Labor | PR | 61 | 02/27/19 | 03/01/19 | SA54 | Sanders, Allen O | 0 | 0.5 | 0 | 35.25 | 35.25 | 22968 | 0 | 0
130 | Finish Labor | PR | 61 | 02/27/19 | 03/01/19 | SA54 | Sanders, Allen O | 2.5 | 0 | 117.5 | 0 | 117.5 | 22968 | 0 | 0
130 | Finish Labor | PR | 68 | 02/27/19 | 03/01/19 | TR60 | Trower-Kelly, Fidel D | 2.5 | 0 | 40 | 0 | 40 | 22975 | 0 | 0
130 | Finish Labor | PR | 264 | 03/06/19 | 03/08/19 | EL33 | Eliassen, Cory H | 10 | 0 | 250 | 0 | 250 | 23003 | 0 | 0
130 | Finish Labor | PR | 307 | 03/06/19 | 03/08/19 | TR60 | Trower-Kelly, Fidel D | 5 | 0 | 80 | 0 | 80 | 23046 | 0 | 0
130 | Finish Labor | PR | 511 | 03/13/19 | 03/15/19 | EL33 | Eliassen, Cory H | 0 | 2 | 0 | 75 | 75 | 23073 | 0 | 0
130 | Finish Labor | PR | 511 | 03/13/19 | 03/15/19 | EL33 | Eliassen, Cory H | 7 | 0 | 175 | 0 | 175 | 23073 | 0 | 0
130 | Finish Labor | PR | 547 | 03/13/19 | 03/15/19 | SA54 | Sanders, Allen O | 7 | 0 | 329 | 0 | 329 | 23109 | 0 | 0
130 | Finish Labor | PR | 555 | 03/13/19 | 03/15/19 | TR60 | Trower-Kelly, Fidel D | 0 | 2 | 0 | 48 | 48 | 23117 | 0 | 0
130 | Finish Labor | PR | 555 | 03/13/19 | 03/15/19 | TR60 | Trower-Kelly, Fidel D | 4 | 0 | 64 | 0 | 64 | 23117 | 0 | 0
130 | Finish Labor | PR | 725 | 03/20/19 | 03/22/19 | EL33 | Eliassen, Cory H | 4 | 0 | 100 | 0 | 100 | 23146 | 0 | 0
130 | Finish Labor | PR | 731 | 03/20/19 | 03/22/19 | GE70 | Gerard, Jordan E | 5 | 0 | 170 | 0 | 170 | 23152 | 0 | 0
130 | Finish Labor | PR | 760 | 03/20/19 | 03/22/19 | SA54 | Sanders, Allen O | 10 | 0 | 470 | 0 | 470 | 23181 | 0 | 0
130 | Finish Labor | PR | 135 | 04/03/19 | 04/05/19 | SA54 | Sanders, Allen O | 0 | 5.5 | 0 | 387.75 | 387.75 | 23329 | 0 | 0
130 | Finish Labor | PR | 135 | 04/03/19 | 04/05/19 | SA54 | Sanders, Allen O | 1 | 0 | 47 | 0 | 47 | 23329 | 0 | 0
130 | Finish Labor | PR | 379 | 04/10/19 | 04/12/19 | SA54 | Sanders, Allen O | 10 | 0 | 490 | 0 | 490 | 23403 | 0 | 0
130 | Finish Labor | PR | 578 | 04/17/19 | 04/19/19 | SA54 | Sanders, Allen O | 1.5 | 0 | 73.5 | 0 | 73.5 | 23479 | 0 | 0
130 | Finish Labor | PR | 586 | 04/17/19 | 04/19/19 | TR60 | Trower-Kelly, Fidel D | 1.5 | 0 | 24 | 0 | 24 | 23487 | 0 | 0
130 | Finish Labor | PR | 797 | 04/24/19 | 04/26/19 | SA54 | Sanders, Allen O | 1 | 0 | 49 | 0 | 49 | 23554 | 0 | 0
130 | Finish Labor | PR | 66 | 05/01/19 | 05/03/19 | SA54 | Sanders, Allen O | 1 | 0 | 49 | 0 | 49 | 23628 | 0 | 0
130 | Finish Labor | PR | 164 | 05/08/19 | 05/10/19 | BA70 | Barnhart, Joseph N | 1 | 0 | 50 | 0 | 50 | 23648 | 0 | 0
130 | Finish Labor | PR | 219 | 05/08/19 | 05/10/19 | SA54 | Sanders, Allen O | 2 | 0 | 98 | 0 | 98 | 23704 | 0 | 0
140 | Gas Labor | PR | 1003 | 06/27/18 | 06/29/18 | RE18 | Reed, Reuben H | 0 | 1 | 0 | 61.5 | 61.5 | 20283 | 0 | 0
140 | Gas Labor | PR | 1003 | 06/27/18 | 06/29/18 | RE18 | Reed, Reuben H | 16 | 0 | 656 | 0 | 656 | 20283 | 0 | 0
140 | Gas Labor | PR | 91 | 12/05/18 | 12/07/18 | RE18 | Reed, Reuben H | 8 | 0 | 344 | 0 | 344 | 22033 | 0 | 0
140 | Gas Labor | PR | 252 | 01/09/19 | 01/11/19 | MC09 | McCabe, Thomas C | 4 | 0 | 132 | 0 | 132 | 22454 | 0 | 0
140 | Gas Labor | PR | 507 | 01/16/19 | 01/18/19 | MC09 | McCabe, Thomas C | 4 | 0 | 132 | 0 | 132 | 22528 | 0 | 0
140 | Gas Labor | PR | 524 | 01/16/19 | 01/18/19 | SE64 | Sepulveda Gonzalez, Alfredo | 4 | 0 | 128 | 0 | 128 | 22545 | 0 | 0
140 | Gas Labor | PR | 293 | 03/06/19 | 03/08/19 | RE18 | Reed, Reuben H | 4 | 0 | 172 | 0 | 172 | 23032 | 0 | 0
141 | Water Main/Insulation Lab | PR | 751 | 05/23/18 | 05/25/18 | CR87 | Cruz Reyes, Jose | 12 | 0 | 276 | 0 | 276 | 19880 | 0 | 0
141 | Water Main/Insulation Lab | PR | 774 | 05/23/18 | 05/25/18 | LO58 | Lopez Reyes, Boris O | 8 | 0 | 144 | 0 | 144 | 19903 | 0 | 0
141 | Water Main/Insulation Lab | PR | 41 | 05/30/18 | 06/01/18 | LO58 | Lopez Reyes, Boris O | 8 | 0 | 144 | 0 | 144 | 19975 | 0 | 0
141 | Water Main/Insulation Lab | PR | 283 | 06/06/18 | 06/08/18 | CR87 | Cruz Reyes, Jose | 27 | 0 | 621 | 0 | 621 | 20023 | 0 | 0
141 | Water Main/Insulation Lab | PR | 321 | 06/06/18 | 06/08/18 | RE18 | Reed, Reuben H | 0 | 2 | 0 | 120 | 120 | 20061 | 0 | 0
141 | Water Main/Insulation Lab | PR | 321 | 06/06/18 | 06/08/18 | RE18 | Reed, Reuben H | 16 | 0 | 640 | 0 | 640 | 20061 | 0 | 0
141 | Water Main/Insulation Lab | PR | 464 | 06/13/18 | 06/15/18 | BE45 | Belcher, Jacob T | 0 | 3 | 0 | 76.5 | 76.5 | 20099 | 0 | 0
141 | Water Main/Insulation Lab | PR | 464 | 06/13/18 | 06/15/18 | BE45 | Belcher, Jacob T | 24 | 0 | 408 | 0 | 408 | 20099 | 0 | 0
141 | Water Main/Insulation Lab | PR | 472 | 06/13/18 | 06/15/18 | CR79 | Cruz Guzman, Joel A | 18 | 0 | 414 | 0 | 414 | 20107 | 0 | 0
141 | Water Main/Insulation Lab | PR | 473 | 06/13/18 | 06/15/18 | CR87 | Cruz Reyes, Jose | 0 | 4 | 0 | 144 | 144 | 20108 | 0 | 0
141 | Water Main/Insulation Lab | PR | 473 | 06/13/18 | 06/15/18 | CR87 | Cruz Reyes, Jose | 40 | 0 | 960 | 0 | 960 | 20108 | 0 | 0
141 | Water Main/Insulation Lab | PR | 489 | 06/13/18 | 06/15/18 | HU06 | Hubbard, Robert W | 2 | 0 | 94 | 0 | 94 | 20124 | 0 | 0
141 | Water Main/Insulation Lab | PR | 498 | 06/13/18 | 06/15/18 | LU09 | Lucas Tzintzun, Rafael | 0 | 3 | 0 | 76.5 | 76.5 | 20133 | 0 | 0
141 | Water Main/Insulation Lab | PR | 498 | 06/13/18 | 06/15/18 | LU09 | Lucas Tzintzun, Rafael | 24 | 0 | 408 | 0 | 408 | 20133 | 0 | 0
141 | Water Main/Insulation Lab | PR | 510 | 06/13/18 | 06/15/18 | RE18 | Reed, Reuben H | 0 | 2 | 0 | 123 | 123 | 20145 | 0 | 0
141 | Water Main/Insulation Lab | PR | 510 | 06/13/18 | 06/15/18 | RE18 | Reed, Reuben H | 21 | 0 | 861 | 0 | 861 | 20145 | 0 | 0
141 | Water Main/Insulation Lab | PR | 690 | 06/20/18 | 06/22/18 | BE45 | Belcher, Jacob T | 18 | 0 | 306 | 0 | 306 | 20169 | 0 | 0
141 | Water Main/Insulation Lab | PR | 699 | 06/20/18 | 06/22/18 | CR87 | Cruz Reyes, Jose | 0 | 1 | 0 | 36 | 36 | 20178 | 0 | 0
141 | Water Main/Insulation Lab | PR | 699 | 06/20/18 | 06/22/18 | CR87 | Cruz Reyes, Jose | 16 | 0 | 384 | 0 | 384 | 20178 | 0 | 0
141 | Water Main/Insulation Lab | PR | 715 | 06/20/18 | 06/22/18 | HU06 | Hubbard, Robert W | 1.5 | 0 | 70.5 | 0 | 70.5 | 20194 | 0 | 0
141 | Water Main/Insulation Lab | PR | 958 | 06/27/18 | 06/29/18 | BE45 | Belcher, Jacob T | 0 | 2 | 0 | 51 | 51 | 20239 | 0 | 0
141 | Water Main/Insulation Lab | PR | 958 | 06/27/18 | 06/29/18 | BE45 | Belcher, Jacob T | 30 | 0 | 510 | 0 | 510 | 20239 | 0 | 0
141 | Water Main/Insulation Lab | PR | 965 | 06/27/18 | 06/29/18 | CR79 | Cruz Guzman, Joel A | 0 | 3 | 0 | 103.5 | 103.5 | 20246 | 0 | 0
141 | Water Main/Insulation Lab | PR | 965 | 06/27/18 | 06/29/18 | CR79 | Cruz Guzman, Joel A | 32 | 0 | 736 | 0 | 736 | 20246 | 0 | 0
141 | Water Main/Insulation Lab | PR | 1003 | 06/27/18 | 06/29/18 | RE18 | Reed, Reuben H | 5 | 0 | 205 | 0 | 205 | 20283 | 0 | 0
141 | Water Main/Insulation Lab | PR | 768 | 07/25/18 | 07/27/18 | BE45 | Belcher, Jacob T | 16 | 0 | 272 | 0 | 272 | 20526 | 0 | 0
141 | Water Main/Insulation Lab | PR | 776 | 07/25/18 | 07/27/18 | CR79 | Cruz Guzman, Joel A | 40 | 0 | 920 | 0 | 920 | 20534 | 0 | 0
141 | Water Main/Insulation Lab | PR | 777 | 07/25/18 | 07/27/18 | CR87 | Cruz Reyes, Jose | 28 | 0 | 672 | 0 | 672 | 20535 | 0 | 0
141 | Water Main/Insulation Lab | PR | 806 | 07/25/18 | 07/27/18 | LU09 | Lucas Tzintzun, Rafael | 32 | 0 | 544 | 0 | 544 | 20563 | 0 | 0
141 | Water Main/Insulation Lab | PR | 7 | 08/01/18 | 08/03/18 | BE45 | Belcher, Jacob T | 16 | 0 | 272 | 0 | 272 | 20598 | 0 | 0
141 | Water Main/Insulation Lab | PR | 15 | 08/01/18 | 08/03/18 | CR79 | Cruz Guzman, Joel A | 16 | 0 | 368 | 0 | 368 | 20607 | 0 | 0
141 | Water Main/Insulation Lab | PR | 16 | 08/01/18 | 08/03/18 | CR87 | Cruz Reyes, Jose | 16 | 0 | 384 | 0 | 384 | 20608 | 0 | 0
141 | Water Main/Insulation Lab | PR | 44 | 08/01/18 | 08/03/18 | LU09 | Lucas Tzintzun, Rafael | 39 | 0 | 663 | 0 | 663 | 20635 | 0 | 0
141 | Water Main/Insulation Lab | PR | 225 | 08/08/18 | 08/10/18 | CR79 | Cruz Guzman, Joel A | 8 | 0 | 184 | 0 | 184 | 20678 | 0 | 0
141 | Water Main/Insulation Lab | PR | 226 | 08/08/18 | 08/10/18 | CR87 | Cruz Reyes, Jose | 4 | 0 | 96 | 0 | 96 | 20679 | 0 | 0
141 | Water Main/Insulation Lab | PR | 484 | 08/15/18 | 08/17/18 | BA70 | Barnhart, Joseph N | 1 | 0 | 46 | 0 | 46 | 20742 | 0 | 0
141 | Water Main/Insulation Lab | PR | 493 | 08/15/18 | 08/17/18 | CR79 | Cruz Guzman, Joel A | 16 | 0 | 368 | 0 | 368 | 20751 | 0 | 0
141 | Water Main/Insulation Lab | PR | 494 | 08/15/18 | 08/17/18 | CR87 | Cruz Reyes, Jose | 8 | 0 | 192 | 0 | 192 | 20752 | 0 | 0
141 | Water Main/Insulation Lab | PR | 773 | 01/23/19 | 01/25/19 | SE64 | Sepulveda Gonzalez, Alfredo | 3 | 0 | 96 | 0 | 96 | 22618 | 0 | 0
141 | Water Main/Insulation Lab | PR | 44 | 01/30/19 | 02/01/19 | MC09 | McCabe, Thomas C | 12 | 0 | 396 | 0 | 396 | 22673 | 0 | 0
141 | Water Main/Insulation Lab | PR | 114 | 04/03/19 | 04/05/19 | HU06 | Hubbard, Robert W | 0 | 1 | 0 | 73.5 | 73.5 | 23308 | 0 | 0
141 | Water Main/Insulation Lab | PR | 114 | 04/03/19 | 04/05/19 | HU06 | Hubbard, Robert W | 1 | 0 | 49 | 0 | 49 | 23308 | 0 | 0
141 | Water Main/Insulation Lab | PR | 132 | 04/03/19 | 04/05/19 | RO06 | Roberts, Lake A | 0 | 2 | 0 | 54 | 54 | 23326 | 0 | 0
141 | Water Main/Insulation Lab | PR | 132 | 04/03/19 | 04/05/19 | RO06 | Roberts, Lake A | 4 | 0 | 72 | 0 | 72 | 23326 | 0 | 0
142 | Mech Room Labor | PR | 617 | 04/25/18 | 04/27/18 | BA70 | Barnhart, Joseph N | 1 | 0 | 44 | 0 | 44 | 19582 | 0 | 0
142 | Mech Room Labor | PR | 246 | 08/08/18 | 08/10/18 | HU06 | Hubbard, Robert W | 2 | 0 | 94 | 0 | 94 | 20698 | 0 | 0
142 | Mech Room Labor | PR | 1000 | 08/29/18 | 08/31/18 | BA70 | Barnhart, Joseph N | 1 | 0 | 46 | 0 | 46 | 20896 | 0 | 0
142 | Mech Room Labor | PR | 515 | 09/19/18 | 09/21/18 | HU06 | Hubbard, Robert W | 2 | 0 | 94 | 0 | 94 | 21206 | 0 | 0
142 | Mech Room Labor | PR | 700 | 09/26/18 | 09/28/18 | HU06 | Hubbard, Robert W | 2 | 0 | 94 | 0 | 94 | 21278 | 0 | 0
142 | Mech Room Labor | PR | 64 | 10/03/18 | 10/05/18 | HU06 | Hubbard, Robert W | 3 | 0 | 141 | 0 | 141 | 21352 | 0 | 0
142 | Mech Room Labor | PR | 270 | 10/10/18 | 10/12/18 | HU06 | Hubbard, Robert W | 2 | 0 | 94 | 0 | 94 | 21427 | 0 | 0
142 | Mech Room Labor | PR | 288 | 10/10/18 | 10/12/18 | RE18 | Reed, Reuben H | 30 | 0 | 1230 | 0 | 1230 | 21445 | 0 | 0
142 | Mech Room Labor | PR | 468 | 10/17/18 | 10/19/18 | HU06 | Hubbard, Robert W | 7 | 0 | 329 | 0 | 329 | 21501 | 0 | 0
142 | Mech Room Labor | PR | 486 | 10/17/18 | 10/19/18 | RE18 | Reed, Reuben H | 30 | 0 | 1230 | 0 | 1230 | 21519 | 0 | 0
142 | Mech Room Labor | PR | 687 | 10/24/18 | 10/25/18 | HU06 | Hubbard, Robert W | 2 | 0 | 94 | 0 | 94 | 21477 | 0 | 0
142 | Mech Room Labor | PR | 751 | 10/24/18 | 10/26/18 | RE18 | Reed, Reuben H | 9 | 0 | 369 | 0 | 369 | 21591 | 0 | 0
142 | Mech Room Labor | PR | 39 | 10/31/18 | 11/02/18 | HU06 | Hubbard, Robert W | 2 | 0 | 94 | 0 | 94 | 21648 | 0 | 0
142 | Mech Room Labor | PR | 55 | 10/31/18 | 11/02/18 | RE18 | Reed, Reuben H | 16 | 0 | 656 | 0 | 656 | 21664 | 0 | 0
142 | Mech Room Labor | PR | 217 | 11/07/18 | 11/09/18 | HU06 | Hubbard, Robert W | 10 | 0 | 470 | 0 | 470 | 21720 | 0 | 0
142 | Mech Room Labor | PR | 234 | 11/07/18 | 11/09/18 | RE18 | Reed, Reuben H | 21 | 0 | 861 | 0 | 861 | 21737 | 0 | 0
142 | Mech Room Labor | PR | 465 | 11/14/18 | 11/16/18 | HU06 | Hubbard, Robert W | 10 | 0 | 470 | 0 | 470 | 21793 | 0 | 0
142 | Mech Room Labor | PR | 482 | 11/14/18 | 11/16/18 | RE18 | Reed, Reuben H | 14 | 0 | 574 | 0 | 574 | 21810 | 0 | 0
142 | Mech Room Labor | PR | 504 | 11/14/18 | 11/16/18 | HU06 | Hubbard, Robert W | 10 | 0 | -470 | 0 | -470 | 21793 | 0 | 0
142 | Mech Room Labor | PR | 508 | 11/14/18 | 11/16/18 | HU06 | Hubbard, Robert W | 10 | 0 | 470 | 0 | 470 | 21833 | 0 | 0
142 | Mech Room Labor | PR | 863 | 11/28/18 | 11/30/18 | HU06 | Hubbard, Robert W | 2 | 0 | 98 | 0 | 98 | 21945 | 0 | 0
142 | Mech Room Labor | PR | 879 | 11/28/18 | 11/30/18 | RE18 | Reed, Reuben H | 11 | 0 | 473 | 0 | 473 | 21961 | 0 | 0
142 | Mech Room Labor | PR | 316 | 12/12/18 | 12/14/18 | RE18 | Reed, Reuben H | 3 | 0 | 129 | 0 | 129 | 22175 | 0 | 0
142 | Mech Room Labor | PR | 517 | 12/19/18 | 12/21/18 | CO71 | Cortes Mendiola, Victor H | 8 | 0 | 344 | 0 | 344 | 22208 | 0 | 0
142 | Mech Room Labor | PR | 708 | 12/26/18 | 12/28/18 | CO71 | Cortes Mendiola, Victor H | 8 | 0 | -344 | 0 | -344 | 22281 | 0 | 0
142 | Mech Room Labor | PR | 731 | 12/26/18 | 12/28/18 | HU06 | Hubbard, Robert W | 5 | 0 | 245 | 0 | 245 | 22304 | 0 | 0
142 | Mech Room Labor | PR | 35 | 01/02/19 | 01/04/19 | HU06 | Hubbard, Robert W | 8 | 0 | 392 | 0 | 392 | 22376 | 0 | 0
142 | Mech Room Labor | PR | 244 | 01/09/19 | 01/11/19 | HU06 | Hubbard, Robert W | 12 | 0 | 588 | 0 | 588 | 22446 | 0 | 0
142 | Mech Room Labor | PR | 252 | 01/09/19 | 01/11/19 | MC09 | McCabe, Thomas C | 18 | 0 | 594 | 0 | 594 | 22454 | 0 | 0
142 | Mech Room Labor | PR | 499 | 01/16/19 | 01/18/19 | HU06 | Hubbard, Robert W | 3 | 0 | 147 | 0 | 147 | 22520 | 0 | 0
142 | Mech Room Labor | PR | 507 | 01/16/19 | 01/18/19 | MC09 | McCabe, Thomas C | 12 | 0 | 396 | 0 | 396 | 22528 | 0 | 0
142 | Mech Room Labor | PR | 524 | 01/16/19 | 01/18/19 | SE64 | Sepulveda Gonzalez, Alfredo | 4 | 0 | 128 | 0 | 128 | 22545 | 0 | 0
142 | Mech Room Labor | PR | 748 | 01/23/19 | 01/25/19 | HU06 | Hubbard, Robert W | 7 | 0 | 343 | 0 | 343 | 22593 | 0 | 0
142 | Mech Room Labor | PR | 773 | 01/23/19 | 01/25/19 | SE64 | Sepulveda Gonzalez, Alfredo | 2 | 0 | 64 | 0 | 64 | 22618 | 0 | 0
142 | Mech Room Labor | PR | 36 | 01/30/19 | 02/01/19 | HU06 | Hubbard, Robert W | 4.5 | 0 | 220.5 | 0 | 220.5 | 22665 | 0 | 0
142 | Mech Room Labor | PR | 44 | 01/30/19 | 02/01/19 | MC09 | McCabe, Thomas C | 4 | 0 | 132 | 0 | 132 | 22673 | 0 | 0
142 | Mech Room Labor | PR | 58 | 01/30/19 | 02/01/19 | SE64 | Sepulveda Gonzalez, Alfredo | 4 | 0 | 128 | 0 | 128 | 22687 | 0 | 0
142 | Mech Room Labor | PR | 38 | 02/27/19 | 03/01/19 | HU06 | Hubbard, Robert W | 12 | 0 | 588 | 0 | 588 | 22945 | 0 | 0
142 | Mech Room Labor | PR | 525 | 03/13/19 | 03/15/19 | HU06 | Hubbard, Robert W | 5 | 0 | 245 | 0 | 245 | 23087 | 0 | 0
142 | Mech Room Labor | PR | 533 | 03/13/19 | 03/15/19 | MC09 | McCabe, Thomas C | 4 | 0 | 132 | 0 | 132 | 23095 | 0 | 0
210 | Underground Material | GL | 742 | 12/22/17 | 12/22/17 | Mat | Req 3379 |  |  |  |  | 70.5 |  | 0 | 0
210 | Underground Material | AP | 951 | 12/18/17 | 12/31/17 | 2042RS | Rosen Supply Company, Inc. $Metro Flats |  |  |  |  | 2172.41 | 4246057-00 | 0 | 0
210 | Underground Material | AP | 124 | 12/20/17 | 01/05/18 | 2042RS | Rosen Supply Company, Inc. $Metro Flats |  |  |  |  | 45.4 | 4246247-00 | 0 | 0
210 | Underground Material | AP | 144 | 12/27/17 | 01/08/18 | 2042RS | Rosen Supply Company, Inc. $Metro Flats |  |  |  |  | 987.72 | 4246348-00 | 0 | 0
210 | Underground Material | AP | 145 | 12/29/17 | 01/08/18 | 2042RS | Rosen Supply Company, Inc. $Metro Flats |  |  |  |  | 18.84 | 4246348-01 | 0 | 0
210 | Underground Material | AP | 184 | 12/18/17 | 01/09/18 | 2042CS | Consolidated Supply Co. $Metro Flats |  |  |  |  | 799.5 | S8501308.001 | 0 | 0
210 | Underground Material | AP | 185 | 12/21/17 | 01/09/18 | 2042CS | Consolidated Supply Co. $Metro Flats |  |  |  |  | 272.34 | S8552078.001 | 0 | 0
210 | Underground Material | AP | 170 | 01/03/17 | 01/10/18 | 2042FE | Ferguson Enterprises, Inc. $Metro Flats |  |  |  |  | 113.35 | 5847326 | 0 | 0
210 | Underground Material | AP | 219 | 01/05/18 | 01/11/18 | 2042FE | Ferguson Enterprises, Inc. $Metro Flats |  |  |  |  | 183.83 | 5855829 | 0 | 0
210 | Underground Material | AP | 352 | 01/04/18 | 01/16/18 | 2042RS | Rosen Supply Company, Inc. $Metro Flats |  |  |  |  | 562.95 | 4246616-00 | 0 | 0
211 | Garage Material | GL | 330 | 01/16/18 | 01/16/18 | Mat | Req 3423 |  |  |  |  | 47.22 |  | 0 | 0
211 | Garage Material | GL | 267 | 03/13/18 | 03/13/18 | Mat | Req 3516 |  |  |  |  | 930.06 |  | 0 | 0
211 | Garage Material | GL | 696 | 03/26/18 | 03/26/18 | Mat | Req 4244 |  |  |  |  | 573.6 |  | 0 | 0
211 | Garage Material | GL | 839 | 03/31/18 | 03/31/18 | Mat | Req 4277 |  |  |  |  | 123.5 |  | 0 | 0
211 | Garage Material | GL | 149 | 04/10/18 | 04/10/18 | Mat | Req 4313 |  |  |  |  | 154.85 |  | 0 | 0
211 | Garage Material | GL | 227 | 06/06/18 | 06/06/18 | Mat | Req 3667 |  |  |  |  | 36 |  | 0 | 0
211 | Garage Material | GL | 294 | 07/12/18 | 07/12/18 | Mat | Req 4468 |  |  |  |  | 200.5 |  | 0 | 0
211 | Garage Material | GL | 345 | 08/10/18 | 08/10/18 | Mat | Req 4566 |  |  |  |  | 30 |  | 0 | 0
211 | Garage Material | GL | 636 | 08/22/18 | 08/22/18 | Mat | Req 4659 |  |  |  |  | -896.43 |  | 0 | 0
211 | Garage Material | GL | 668 | 08/22/18 | 08/22/18 | Mat | Req 4635 |  |  |  |  | 357.26 |  | 0 | 0
211 | Garage Material | GL | 182 | 09/10/18 | 09/10/18 | Mat | Req 4692 |  |  |  |  | 51.96 |  | 0 | 0
211 | Garage Material | GL | 602 | 09/25/18 | 09/25/18 | Mat | Req 5395 |  |  |  |  | 33 |  | 0 | 0
211 | Garage Material | GL | 865 | 01/30/19 | 01/30/19 | Mat | Req 5010 |  |  |  |  | 10.63 |  | 0 | 0
211 | Garage Material | GL | 446 | 04/12/19 | 04/12/19 | Mat | Req 5162 |  |  |  |  | -45.04 |  | 0 | 0
212 | Canout Material | GL | 234 | 02/01/18 | 02/01/18 | CK#5048 | Joseph Barnhart |  |  |  |  | 37.35 |  | 0 | 0
212 | Canout Material | GL | 84 | 02/02/18 | 02/02/18 | Mat | Req 4144 |  |  |  |  | 441.17 |  | 0 | 0
212 | Canout Material | AP | 118 | 01/18/18 | 02/06/18 | 2042KS | Keller Supply Co. $Metro Flats |  |  |  |  | 2842.4 | S011522605.001 | 0 | 0
212 | Canout Material | GL | 491 | 02/16/18 | 02/16/18 | Mat | Req 4221 |  |  |  |  | -1074.2 |  | 0 | 0
212 | Canout Material | GL | 509 | 02/16/18 | 02/16/18 | Mat | Req 4205 |  |  |  |  | 1587.82 |  | 0 | 0
212 | Canout Material | GL | 769 | 02/21/18 | 02/21/18 | Mat | Req 3478 |  |  |  |  | 5.5 |  | 0 | 0
212 | Canout Material | GL | 731 | 02/26/18 | 02/26/18 | Mat | Req 3494 |  |  |  |  | -872.41 |  | 0 | 0
220 | Roughin Material | GL | 308 | 01/15/18 | 01/15/18 | Mat | Req 3402 |  |  |  |  | 323.33 |  | 0 | 0
220 | Roughin Material | GL | 770 | 02/21/18 | 02/21/18 | Mat | Req 3462 |  |  |  |  | 17.8 |  | 0 | 0
220 | Roughin Material | GL | 270 | 03/13/18 | 03/13/18 | Mat | Req 3531 |  |  |  |  | 291.43 |  | 0 | 0
220 | Roughin Material | AP | 507 | 03/02/18 | 03/14/18 | 2042RS | Rosen Supply Company, Inc. $Metro Flats |  |  |  |  | 6458.9 | 4248805-00 | 0 | 0
220 | Roughin Material | AP | 508 | 03/07/18 | 03/14/18 | 2042RS | Rosen Supply Company, Inc. $Metro Flats |  |  |  |  | 10257.88 | 4247446-00 | 0 | 0
220 | Roughin Material | AP | 509 | 03/07/18 | 03/14/18 | 2042RS | Rosen Supply Company, Inc. $Metro Flats |  |  |  |  | 886.06 | 4249044-00 | 0 | 0
220 | Roughin Material | AP | 593 | 03/09/18 | 03/23/18 | 2042RS | Rosen Supply Company, Inc. $Metro Flats |  |  |  |  | 559.28 | 4249207 | 0 | 0
220 | Roughin Material | AP | 728 | 03/19/18 | 03/28/18 | 2042RS | Rosen Supply Company, Inc. $Metro Flats |  |  |  |  | 8602.33 | 4247451-00 | 0 | 0
220 | Roughin Material | AP | 729 | 03/19/18 | 03/28/18 | 2042RS | Rosen Supply Company, Inc. $Metro Flats |  |  |  |  | 3799.35 | 4248941-00 | 0 | 0
220 | Roughin Material | AP | 730 | 03/21/18 | 03/28/18 | 2042RS | Rosen Supply Company, Inc. $Metro Flats |  |  |  |  | 74.46 | 4248805-01 | 0 | 0
220 | Roughin Material | GL | 840 | 03/31/18 | 03/31/18 | Mat | Req 4278 |  |  |  |  | 59.31 |  | 0 | 0
220 | Roughin Material | AP | 109 | 03/19/18 | 04/06/18 | 2042RS | Rosen Supply Company, Inc. $Metro Flats |  |  |  |  | 237.98 | 4247446-01 | 0 | 0
220 | Roughin Material | AP | 125 | 03/21/18 | 04/06/18 | 2042RS | Rosen Supply Company, Inc. $Metro Flats |  |  |  |  | -40.6 | 4249684-00 | 0 | 0
220 | Roughin Material | GL | 158 | 04/10/18 | 04/10/18 | Mat | Req 4298 |  |  |  |  | 48.14 |  | 0 | 0
220 | Roughin Material | AP | 360 | 03/28/18 | 04/13/18 | 2042RS | Rosen Supply Company, Inc. $Metro Flats |  |  |  |  | -85 | 4249966-00 | 0 | 0
220 | Roughin Material | AP | 361 | 03/29/18 | 04/13/18 | 2042RS | Rosen Supply Company, Inc. $Metro Flats |  |  |  |  | 1574.08 | 4249924-00 | 0 | 0
220 | Roughin Material | GL | 406 | 04/18/18 | 04/18/18 | Mat | Req 3570 |  |  |  |  | 665 |  | 0 | 0
220 | Roughin Material | AP | 430 | 04/13/18 | 04/18/18 | 1021AT | ACME Corp |  |  |  |  | 26.36 | S2968913.001 | 0 | 0
220 | Roughin Material | GL | 704 | 04/27/18 | 04/27/18 | Mat | Req 3607 |  |  |  |  | 68.82 |  | 0 | 0
220 | Roughin Material | AP | 23 | 04/19/18 | 05/03/18 | 2042CS | Consolidated Supply Co. $Metro Flats |  |  |  |  | 3833.7 | S8689209.001 | 0 | 0
220 | Roughin Material | GL | 303 | 05/11/18 | 05/11/18 | Mat | Req 4330 |  |  |  |  | 624.71 |  | 0 | 0
220 | Roughin Material | AP | 333 | 04/20/18 | 05/11/18 | 2042RS | Rosen Supply Company, Inc. $Metro Flats |  |  |  |  | 4291 | 4250933-00 | 0 | 0
220 | Roughin Material | AP | 334 | 04/24/18 | 05/11/18 | 2042RS | Rosen Supply Company, Inc. $Metro Flats |  |  |  |  | 1340.89 | 4251042-00 | 0 | 0
220 | Roughin Material | AP | 395 | 05/07/18 | 05/16/18 | 2042CS | Consolidated Supply Co. $Metro Flats |  |  |  |  | 3833.7 | S8689236.002 | 0 | 0
220 | Roughin Material | AP | 562 | 05/01/18 | 05/21/18 | 2042RS | Rosen Supply Company, Inc. $Metro Flats |  |  |  |  | 124.29 | 4251042-01 | 0 | 0
220 | Roughin Material | AP | 563 | 05/02/18 | 05/21/18 | 2042RS | Rosen Supply Company, Inc. $Metro Flats |  |  |  |  | 13.67 | 4250933-01 | 0 | 0
220 | Roughin Material | AP | 564 | 05/03/18 | 05/21/18 | 2042RS | Rosen Supply Company, Inc. $Metro Flats |  |  |  |  | 1571.97 | 4251473-00 | 0 | 0
220 | Roughin Material | AP | 636 | 05/07/18 | 05/22/18 | 2042RS | Rosen Supply Company, Inc. $Metro Flats |  |  |  |  | 61.69 | 4251473-01 | 0 | 0
220 | Roughin Material | GL | 91 | 06/01/18 | 06/01/18 | Mat | Req 4396 |  |  |  |  | 1771.45 |  | 0 | 0
220 | Roughin Material | GL | 113 | 06/01/18 | 06/01/18 | Mat | Req 4416 |  |  |  |  | 525 |  | 0 | 0
220 | Roughin Material | AP | 258 | 05/17/18 | 06/01/18 | 2042RS | Rosen Supply Company, Inc. $Metro Flats |  |  |  |  | 1689.25 | 4252086-00 | 0 | 0
220 | Roughin Material | GL | 374 | 06/07/18 | 06/07/18 | CK#5511 | Reuben Reed |  |  |  |  | 59.59 |  | 0 | 0
220 | Roughin Material | AP | 432 | 05/31/18 | 06/12/18 | 2042RS | Rosen Supply Company, Inc. $Metro Flats |  |  |  |  | 226.08 | 4252720-00 | 0 | 0
220 | Roughin Material | GL | 552 | 06/15/18 | 06/15/18 | Mat | Req 3696 |  |  |  |  | 1053.95 |  | 0 | 0
220 | Roughin Material | AP | 586 | 06/05/18 | 06/18/18 | 2042CS | Consolidated Supply Co. $Metro Flats |  |  |  |  | 3861.65 | S8776747.001 | 0 | 0
220 | Roughin Material | AP | 855 | 06/08/18 | 06/25/18 | 2042RS | Rosen Supply Company, Inc. $Metro Flats |  |  |  |  | 240.85 | 4253086-00 | 0 | 0
220 | Roughin Material | GL | 1051 | 06/30/18 | 06/30/18 | Mat | Req 3763 |  |  |  |  | 708.57 |  | 0 | 0
220 | Roughin Material | GL | 295 | 07/12/18 | 07/12/18 | Mat | Req 4469 |  |  |  |  | 352 |  | 0 | 0
220 | Roughin Material | AP | 379 | 06/15/18 | 07/13/18 | 2042CS | Consolidated Supply Co. $Metro Flats |  |  |  |  | 176.34 | S8794623.001 | 0 | 0
220 | Roughin Material | GL | 391 | 07/16/18 | 07/16/18 | Mat | Req 4475 |  |  |  |  | 375.35 |  | 0 | 0
220 | Roughin Material | GL | 572 | 07/23/18 | 07/23/18 | Mat | Req 5302 |  |  |  |  | 922.48 |  | 0 | 0
220 | Roughin Material | GL | 389 | 08/10/18 | 08/10/18 | Mat | Req 4515 |  |  |  |  | 371.54 |  | 0 | 0
220 | Roughin Material | GL | 670 | 08/22/18 | 08/22/18 | Mat | Req 4637 |  |  |  |  | 85.14 |  | 0 | 0
220 | Roughin Material | GL | 183 | 09/10/18 | 09/10/18 | Mat | Req 4693 |  |  |  |  | 34.03 |  | 0 | 0
220 | Roughin Material | GL | 601 | 09/25/18 | 09/25/18 | Mat | Req 5396 |  |  |  |  | 87.96 |  | 0 | 0
220 | Roughin Material | GL | 645 | 09/25/18 | 09/25/18 | Mat | Req 5363 |  |  |  |  | 14.6 |  | 0 | 0
220 | Roughin Material | AP | 163 | 09/12/18 | 10/10/18 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 38 | 4257169-00 | 0 | 0
220 | Roughin Material | GL | 364 | 10/16/18 | 10/16/18 | Mat | Req 5467 |  |  |  |  | 16.96 |  | 0 | 0
220 | Roughin Material | GL | 540 | 10/22/18 | 10/22/18 | Mat | Req 5477 |  |  |  |  | -9.52 |  | 0 | 0
220 | Roughin Material | GL | 667 | 01/23/19 | 01/23/19 | Mat | Req 4927 |  |  |  |  | 89.17 |  | 0 | 0
220 | Roughin Material | GL | 224 | 04/08/19 | 04/08/19 | Mat | Req 5115 |  |  |  |  | 13.8 |  | 0 | 0
220 | Roughin Material | GL | 269 | 04/08/19 | 04/08/19 | Mat | Req 5158 |  |  |  |  | -135.62 |  | 0 | 0
220 | Roughin Material | GL | 683 | 04/24/19 | 04/24/19 | Mat | Req 5912 |  |  |  |  | 39.25 |  | 0 | 0
230 | Finish Material | AP | 898 | 11/29/17 | 12/31/17 | 1234CO | Capital One Credit Card |  |  |  |  | 278.93 | 112917 | 0 | 0
230 | Finish Material | AP | 117 | 12/29/17 | 01/05/18 | 1609QC | Quality Concrete Products, Inc. $32 |  |  |  |  | 199 | 15995 | 0 | 0
230 | Finish Material | AP | 119 | 12/29/17 | 01/05/18 | 1609QC | Quality Concrete Products, Inc. $32 |  |  |  |  | 52 | 16020 | 0 | 0
230 | Finish Material | GL | 383 | 01/17/18 | 01/17/18 | Mat | Req 3425 |  |  |  |  | 120.86 |  | 0 | 0
230 | Finish Material | GL | 85 | 02/02/18 | 02/02/18 | Mat | Req 4147 |  |  |  |  | 52.15 |  | 0 | 0
230 | Finish Material | GL | 266 | 03/13/18 | 03/13/18 | Mat | Req 3515 |  |  |  |  | 52.15 |  | 0 | 0
230 | Finish Material | GL | 857 | 03/31/18 | 03/31/18 | Mat | Req 4291 |  |  |  |  | 408.9 |  | 0 | 0
230 | Finish Material | AP | 878 | 03/12/18 | 03/31/18 | 2042FE | Ferguson Enterprises, Inc. $Metro Flats |  |  |  |  | 3059.06 | 6020591 | 0 | 0
230 | Finish Material | GL | 160 | 04/10/18 | 04/10/18 | Mat | Req 4297 |  |  |  |  | 1990.8 |  | 0 | 0
230 | Finish Material | GL | 745 | 04/26/18 | 04/26/18 | Mat | Req 3619 |  |  |  |  | 1980.68 |  | 0 | 0
230 | Finish Material | GL | 314 | 05/11/18 | 05/11/18 | Mat | Req 4338 |  |  |  |  | 580.86 |  | 0 | 0
230 | Finish Material | GL | 107 | 06/01/18 | 06/01/18 | Mat | Req 4420 |  |  |  |  | 1340.8 |  | 0 | 0
230 | Finish Material | AP | 212 | 05/17/18 | 06/05/18 | 2042CS | Consolidated Supply Co. $Metro Flats |  |  |  |  | 5287.16 | S8634986.001 | 0 | 0
230 | Finish Material | AP | 213 | 05/18/18 | 06/05/18 | 2042CS | Consolidated Supply Co. $Metro Flats |  |  |  |  | 3888.38 | S8634986.002 | 0 | 0
230 | Finish Material | AP | 214 | 05/21/18 | 06/05/18 | 2042CS | Consolidated Supply Co. $Metro Flats |  |  |  |  | 4536.44 | S8634984.002 | 0 | 0
230 | Finish Material | AP | 215 | 05/23/18 | 06/05/18 | 2042CS | Consolidated Supply Co. $Metro Flats |  |  |  |  | 3291.66 | S8634984.003 | 0 | 0
230 | Finish Material | GL | 551 | 06/15/18 | 06/15/18 | Mat | Req 3698 |  |  |  |  | 1613 |  | 0 | 0
230 | Finish Material | AP | 584 | 05/29/18 | 06/18/18 | 2042CS | Consolidated Supply Co. $Metro Flats |  |  |  |  | 3240.32 | S8634793.002 | 0 | 0
230 | Finish Material | AP | 585 | 05/30/18 | 06/18/18 | 2042CS | Consolidated Supply Co. $Metro Flats |  |  |  |  | 3394.33 | S8634793.003 | 0 | 0
230 | Finish Material | AP | 588 | 06/12/18 | 06/18/18 | 2042CS | Consolidated Supply Co. $Metro Flats |  |  |  |  | 648.06 | S8634793.004 | 0 | 0
230 | Finish Material | GL | 762 | 06/22/18 | 06/22/18 | Mat | Req 3754 |  |  |  |  | -52.3 |  | 0 | 0
230 | Finish Material | GL | 1052 | 06/30/18 | 06/30/18 | Mat | Req 3764 |  |  |  |  | 475.98 |  | 0 | 0
230 | Finish Material | GL | 390 | 07/16/18 | 07/16/18 | Mat | Req 4476 |  |  |  |  | 679.66 |  | 0 | 0
230 | Finish Material | AP | 557 | 06/26/18 | 07/20/18 | 2042RS | Rosen Supply Company, Inc. $Metro Flats |  |  |  |  | 3690.94 | 4252723-00 | 0 | 0
230 | Finish Material | GL | 571 | 07/23/18 | 07/23/18 | Mat | Req 5303 |  |  |  |  | 449.9 |  | 0 | 0
230 | Finish Material | GL | 343 | 08/10/18 | 08/10/18 | Mat | Req 4568 |  |  |  |  | 57 |  | 0 | 0
230 | Finish Material | GL | 391 | 08/10/18 | 08/10/18 | Mat | Req 4513 |  |  |  |  | 271.09 |  | 0 | 0
230 | Finish Material | GL | 669 | 08/22/18 | 08/22/18 | Mat | Req 4636 |  |  |  |  | 484.08 |  | 0 | 0
230 | Finish Material | AP | 1158 | 08/13/18 | 08/30/18 | 1130CS | Consolidated Supply Co. |  |  |  |  | 58.33 | S8879389.001 | 0 | 0
230 | Finish Material | AP | 28 | 08/31/18 | 09/04/18 | 5560CH | California Hydronics Corp |  |  |  |  | 36590 | 2105739 | 0 | 0
230 | Finish Material | GL | 181 | 09/10/18 | 09/10/18 | Mat | Req 4691 |  |  |  |  | 515.91 |  | 0 | 0
230 | Finish Material | AP | 213 | 08/15/18 | 09/10/18 | 1231KS | Keller Supply Company |  |  |  |  | 72.27 | S012179787.001 | 0 | 0
230 | Finish Material | GL | 644 | 09/25/18 | 09/25/18 | Mat | Req 5360 |  |  |  |  | 184.36 |  | 0 | 0
230 | Finish Material | AP | 654 | 09/11/18 | 09/25/18 | 1231KS | Keller Supply Company |  |  |  |  | 88.93 | S012220598.003 | 0 | 0
230 | Finish Material | AP | 121 | 09/26/18 | 10/05/18 | 5560CH | California Hydronics Corp |  |  |  |  | 465 | 2108119 | 0 | 0
230 | Finish Material | GL | 366 | 10/16/18 | 10/16/18 | Mat | Req 5463 |  |  |  |  | 561.62 |  | 0 | 0
230 | Finish Material | GL | 541 | 10/22/18 | 10/22/18 | Mat | Req 5476 |  |  |  |  | -520.3 |  | 0 | 0
230 | Finish Material | AP | 853 | 10/02/18 | 10/25/18 | 1175FE | Ferguson Enterprises, Inc. #3007 |  |  |  |  | 86.16 | 6593899 | 0 | 0
230 | Finish Material | AP | 900 | 10/08/18 | 10/31/18 | 1175FE | Ferguson Enterprises, Inc. #3007 |  |  |  |  | 1080.64 | 6593476 | 0 | 0
230 | Finish Material | GL | 87 | 11/01/18 | 11/01/18 | Mat | Req 5513 |  |  |  |  | 23.16 |  | 0 | 0
230 | Finish Material | GL | 306 | 11/09/18 | 11/09/18 | Mat | Req 4774 |  |  |  |  | 503.25 |  | 0 | 0
230 | Finish Material | AP | 344 | 10/10/18 | 11/12/18 | 1175FE | Ferguson Enterprises, Inc. #3007 |  |  |  |  | 66.34 | 6593432 | 0 | 0
230 | Finish Material | AP | 345 | 10/10/18 | 11/12/18 | 1175FE | Ferguson Enterprises, Inc. #3007 |  |  |  |  | 1266.22 | 6593558-1 | 0 | 0
230 | Finish Material | AP | 353 | 10/17/18 | 11/12/18 | 1175FE | Ferguson Enterprises, Inc. #3007 |  |  |  |  | 141.36 | 6593476-1 | 0 | 0
230 | Finish Material | GL | 557 | 11/16/18 | 11/16/18 | Mat | Req 4806 |  |  |  |  | -168.26 |  | 0 | 0
230 | Finish Material | GL | 569 | 11/16/18 | 11/16/18 | Mat | Req 4793 |  |  |  |  | 44.56 |  | 0 | 0
230 | Finish Material | AP | 710 | 10/02/18 | 11/21/18 | 1175FE | Ferguson Enterprises, Inc. #3007 |  |  |  |  | 508.11 | 6593558 | 0 | 0
230 | Finish Material | AP | 816 | 11/02/18 | 11/28/18 | 5560CH | California Hydronics Corp |  |  |  |  | 12167 | 2112196 | 0 | 0
230 | Finish Material | AP | 932 | 10/26/18 | 11/30/18 | 1175FE | Ferguson Enterprises, Inc. #3007 |  |  |  |  | 26.51 | 6593476-2 | 0 | 0
230 | Finish Material | AP | 961 | 10/31/18 | 11/30/18 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 832 | 4255782-00 | 0 | 0
230 | Finish Material | AP | 1043 | 11/08/18 | 11/30/18 | 1175FE | Ferguson Enterprises, Inc. #3007 |  |  |  |  | 153.2 | 6593476-3 | 0 | 0
230 | Finish Material | AP | 6 | 10/31/18 | 12/04/18 | 1231KS | Keller Supply Company |  |  |  |  | 2312.58 | S012179787.002 | 0 | 0
230 | Finish Material | GL | 640 | 12/21/18 | 12/21/18 | Mat | Req 5623 |  |  |  |  | 1689.51 |  | 0 | 0
230 | Finish Material | AP | 124 | 12/13/18 | 01/07/19 | 1130CS | Consolidated Supply Co. |  |  |  |  | 4951.79 | S8879763.001 | 0 | 0
230 | Finish Material | AP | 125 | 12/13/18 | 01/07/19 | 1130CS | Consolidated Supply Co. |  |  |  |  | 3229.71 | S8879770.001 | 0 | 0
230 | Finish Material | AP | 183 | 12/05/18 | 01/09/19 | 1231KS | Keller Supply Company |  |  |  |  | 1967.35 | S012179787.003 | 0 | 0
230 | Finish Material | AP | 184 | 12/10/18 | 01/09/19 | 1231KS | Keller Supply Company |  |  |  |  | 7385.55 | S012543873.001 | 0 | 0
230 | Finish Material | AP | 185 | 12/12/18 | 01/09/19 | 1231KS | Keller Supply Company |  |  |  |  | -3757.94 | S012548013.001 | 0 | 0
230 | Finish Material | GL | 325 | 01/11/19 | 01/11/19 | Mat | Req 4866 |  |  |  |  | 6.82 |  | 0 | 0
230 | Finish Material | AP | 402 | 12/05/18 | 01/14/19 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 572 | 4258793-00 | 0 | 0
230 | Finish Material | GL | 406 | 01/15/19 | 01/15/19 | Mat | Req 4925 |  |  |  |  | 1757.14 |  | 0 | 0
230 | Finish Material | AP | 432 | 12/21/18 | 01/15/19 | 1231KS | Keller Supply Company |  |  |  |  | 1024.41 | S012530733.001 | 0 | 0
230 | Finish Material | AP | 437 | 12/19/18 | 01/15/19 | 1231KS | Keller Supply Company |  |  |  |  | 521.99 | S012179787.004 | 0 | 0
230 | Finish Material | AP | 438 | 12/19/18 | 01/15/19 | 1231KS | Keller Supply Company |  |  |  |  | 1454.7 | S012568381.001 | 0 | 0
230 | Finish Material | GL | 668 | 01/23/19 | 01/23/19 | Mat | Req 4926 |  |  |  |  | 30.6 |  | 0 | 0
230 | Finish Material | AP | 824 | 12/26/18 | 01/25/19 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 520 | 4258793-01 | 0 | 0
230 | Finish Material | GL | 862 | 01/30/19 | 01/30/19 | Mat | Req 5008 |  |  |  |  | 646.72 |  | 0 | 0
230 | Finish Material | AP | 903 | 01/14/19 | 01/30/19 | 3612MS | Mechanical Sales, Inc. |  |  |  |  | 145.29 | 700000 | 0 | 0
230 | Finish Material | AP | 921 | 12/26/18 | 01/30/19 | 1130CS | Consolidated Supply Co. |  |  |  |  | 4844.55 | S8879748.001 | 0 | 0
230 | Finish Material | AP | 927 | 12/26/18 | 01/30/19 | 1231KS | Keller Supply Company |  |  |  |  | 140.75 | S012530733.002 | 0 | 0
230 | Finish Material | AP | 79 | 01/09/19 | 02/01/19 | 1231KS | Keller Supply Company |  |  |  |  | 642.64 | S012586523.001 | 0 | 0
230 | Finish Material | AP | 80 | 01/14/19 | 02/01/19 | 1231KS | Keller Supply Company |  |  |  |  | 352.45 | S012530733.003 | 0 | 0
230 | Finish Material | AP | 92 | 01/16/19 | 02/01/19 | 1231KS | Keller Supply Company |  |  |  |  | 2036.58 | S012568381.002 | 0 | 0
230 | Finish Material | AP | 101 | 01/11/19 | 02/01/19 | 1130CS | Consolidated Supply Co. |  |  |  |  | 4951.79 | S8879699.001 | 0 | 0
230 | Finish Material | AP | 102 | 01/18/19 | 02/01/19 | 1130CS | Consolidated Supply Co. |  |  |  |  | 4869.9 | S8879664.001 | 0 | 0
230 | Finish Material | AP | 512 | 01/28/19 | 02/18/19 | 1130CS | Consolidated Supply Co. |  |  |  |  | 3066.97 | S8879389.002 | 0 | 0
230 | Finish Material | AP | 513 | 01/30/19 | 02/18/19 | 1130CS | Consolidated Supply Co. |  |  |  |  | 4456.26 | S8879620.001 | 0 | 0
230 | Finish Material | AP | 514 | 01/30/19 | 02/18/19 | 1130CS | Consolidated Supply Co. |  |  |  |  | 1767.8 | S8983035.001 | 0 | 0
230 | Finish Material | AP | 515 | 01/30/19 | 02/18/19 | 1130CS | Consolidated Supply Co. |  |  |  |  | 79.58 | S9114445.001 | 0 | 0
230 | Finish Material | AP | 547 | 02/15/19 | 02/19/19 | 1130CS | Consolidated Supply Co. |  |  |  |  | 134.21 | S9127778.001 | 0 | 0
230 | Finish Material | GL | 188 | 03/04/19 | 03/04/19 | Mat | Req 5710 |  |  |  |  | 508.68 |  | 0 | 0
230 | Finish Material | GL | 601 | 03/15/19 | 03/15/19 | Mat | Req 5804 |  |  |  |  | 59.08 |  | 0 | 0
230 | Finish Material | AP | 635 | 03/18/19 | 03/19/19 | 1231KS | Keller Supply Company |  |  |  |  | 15.94 | S012821411.001 | 0 | 0
230 | Finish Material | GL | 849 | 03/25/19 | 03/25/19 | Mat | Req 5107 |  |  |  |  | -74.99 |  | 0 | 0
230 | Finish Material | AP | 861 | 03/14/19 | 03/26/19 | 1130CS | Consolidated Supply Co. |  |  |  |  | 194.21 | S9168082.001 | 0 | 0
230 | Finish Material | AP | 906 | 03/19/19 | 03/26/19 | 1231KS | Keller Supply Company |  |  |  |  | 74.99 | S012833461.001 | 0 | 0
230 | Finish Material | AP | 1023 | 03/12/19 | 03/31/19 | 1234CO | Capital One Credit Card |  |  |  |  | 10.24 | 031219A | 0 | 0
230 | Finish Material | AP | 1026 | 03/19/19 | 03/31/19 | 1234CO | Capital One Credit Card |  |  |  |  | 19.64 | 031919A2 | 0 | 0
230 | Finish Material | AP | 489 | 04/02/19 | 04/15/19 | 1231KS | Keller Supply Company |  |  |  |  | 108.61 | S012872153.001 | 0 | 0
230 | Finish Material | AP | 724 | 04/11/19 | 04/24/19 | 1130CS | Consolidated Supply Co. |  |  |  |  | 49.22 | S9209691.001 | 0 | 0
230 | Finish Material | AP | 955 | 04/03/19 | 04/30/19 | 1234CO | Capital One Credit Card |  |  |  |  | 36 | 040319A2 | 0 | 0
230 | Finish Material | GL | 811 | 05/30/19 | 05/30/19 | Mat | Req 5230 |  |  |  |  | -1287.9 |  | 0 | 0
240 | Gas Material | GL | 761 | 06/22/18 | 06/22/18 | Mat | Req 3756 |  |  |  |  | -51.7 |  | 0 | 0
240 | Gas Material | AP | 944 | 06/20/18 | 06/27/18 | 2042KS | Keller Supply Co. $Metro Flats |  |  |  |  | 140.24 | S012008204.001 | 0 | 0
240 | Gas Material | GL | 85 | 11/01/18 | 11/01/18 | Mat | Req 5515 |  |  |  |  | 158.8 |  | 0 | 0
240 | Gas Material | GL | 567 | 11/16/18 | 11/16/18 | Mat | Req 4794 |  |  |  |  | 16.07 |  | 0 | 0
240 | Gas Material | GL | 639 | 12/21/18 | 12/21/18 | Mat | Req 5617 |  |  |  |  | 14.11 |  | 0 | 0
240 | Gas Material | GL | 665 | 01/23/19 | 01/23/19 | Mat | Req 4929 |  |  |  |  | 51.03 |  | 0 | 0
240 | Gas Material | AP | 850 | 01/04/19 | 01/29/19 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 274.12 | 4261005-00 | 0 | 0
240 | Gas Material | GL | 866 | 01/30/19 | 01/30/19 | Mat | Req 5009 |  |  |  |  | 16.35 |  | 0 | 0
240 | Gas Material | AP | 131 | 01/14/19 | 02/06/19 | 1231KS | Keller Supply Company |  |  |  |  | 46.65 | S012640107.001 | 0 | 0
241 | Water Main/Insulation Mat | GL | 382 | 01/17/18 | 01/17/18 | Mat | Req 3424 |  |  |  |  | 257.28 |  | 0 | 0
241 | Water Main/Insulation Mat | AP | 394 | 05/07/18 | 05/16/18 | 2042CS | Consolidated Supply Co. $Metro Flats |  |  |  |  | 2886.42 | S8636421.001 | 0 | 0
241 | Water Main/Insulation Mat | GL | 92 | 06/01/18 | 06/01/18 | Mat | Req 4400 |  |  |  |  | 165 |  | 0 | 0
241 | Water Main/Insulation Mat | GL | 549 | 06/15/18 | 06/15/18 | Mat | Req 3699 |  |  |  |  | 506.4 |  | 0 | 0
241 | Water Main/Insulation Mat | AP | 587 | 06/08/18 | 06/18/18 | 2042CS | Consolidated Supply Co. $Metro Flats |  |  |  |  | 302.29 | S8785937.001 | 0 | 0
241 | Water Main/Insulation Mat | GL | 293 | 07/12/18 | 07/12/18 | Mat | Req 4470 |  |  |  |  | 79.11 |  | 0 | 0
241 | Water Main/Insulation Mat | GL | 430 | 07/18/18 | 07/18/18 | Mat | Req 5304 |  |  |  |  | 2209.39 |  | 0 | 0
241 | Water Main/Insulation Mat | GL | 570 | 07/23/18 | 07/23/18 | Mat | Req 5305 |  |  |  |  | 33.6 |  | 0 | 0
241 | Water Main/Insulation Mat | AP | 662 | 07/12/18 | 07/24/18 | 2040CS | Consolidated Supply Co. $65th Apts |  |  |  |  | 3967.33 | S8831950.001 | 0 | 0
241 | Water Main/Insulation Mat | AP | 628 | 07/12/18 | 08/01/18 | 2040CS | Consolidated Supply Co. $65th Apts |  |  |  |  | -3967.33 | S8831950.001A | 0 | 0
241 | Water Main/Insulation Mat | AP | 629 | 07/12/18 | 08/01/18 | 2042CS | Consolidated Supply Co. $Metro Flats |  |  |  |  | 3967.33 | S8831950.001 | 0 | 0
241 | Water Main/Insulation Mat | GL | 344 | 08/10/18 | 08/10/18 | Mat | Req 4567 |  |  |  |  | 311 |  | 0 | 0
241 | Water Main/Insulation Mat | GL | 390 | 08/10/18 | 08/10/18 | Mat | Req 4514 |  |  |  |  | 417.65 |  | 0 | 0
241 | Water Main/Insulation Mat | AP | 606 | 07/24/18 | 08/21/18 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 1230.3 | 4254254-00 | 0 | 0
241 | Water Main/Insulation Mat | GL | 637 | 08/22/18 | 08/22/18 | Mat | Req 4658 |  |  |  |  | -420 |  | 0 | 0
241 | Water Main/Insulation Mat | GL | 671 | 08/22/18 | 08/22/18 | Mat | Req 4638 |  |  |  |  | 146.5 |  | 0 | 0
241 | Water Main/Insulation Mat | AP | 730 | 08/03/18 | 08/22/18 | 1130CS | Consolidated Supply Co. |  |  |  |  | 314.71 | S8866148.001 | 0 | 0
241 | Water Main/Insulation Mat | AP | 1159 | 08/22/18 | 08/30/18 | 1130CS | Consolidated Supply Co. |  |  |  |  | 140.61 | S8894975.001 | 0 | 0
241 | Water Main/Insulation Mat | AP | 17 | 08/14/18 | 09/04/18 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 378 | 4254254-01 | 0 | 0
241 | Water Main/Insulation Mat | GL | 129 | 09/07/18 | 09/07/18 | Mat | Req 4681 |  |  |  |  | 1656 |  | 0 | 0
241 | Water Main/Insulation Mat | GL | 180 | 09/10/18 | 09/10/18 | Mat | Req 4690 |  |  |  |  | 329.52 |  | 0 | 0
241 | Water Main/Insulation Mat | AP | 239 | 08/22/18 | 09/11/18 | 1175FE | Ferguson Enterprises, Inc. #3007 |  |  |  |  | 656.67 | 6486032 | 0 | 0
241 | Water Main/Insulation Mat | GL | 642 | 09/25/18 | 09/25/18 | Mat | Req 5362 |  |  |  |  | 54.81 |  | 0 | 0
241 | Water Main/Insulation Mat | GL | 764 | 09/30/18 | 09/30/18 | Mat | Req 5409 |  |  |  |  | 28.75 |  | 0 | 0
241 | Water Main/Insulation Mat | GL | 367 | 10/16/18 | 10/16/18 | Mat | Req 5461 |  |  |  |  | 351.34 |  | 0 | 0
241 | Water Main/Insulation Mat | GL | 584 | 10/22/18 | 10/22/18 | Mat | Req 5475 |  |  |  |  | -1368.77 |  | 0 | 0
241 | Water Main/Insulation Mat | AP | 673 | 09/28/18 | 10/24/18 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 252 | 4256484-00 | 0 | 0
241 | Water Main/Insulation Mat | GL | 88 | 11/01/18 | 11/01/18 | Mat | Req 5512 |  |  |  |  | 30.94 |  | 0 | 0
241 | Water Main/Insulation Mat | GL | 558 | 11/16/18 | 11/16/18 | Mat | Req 4805 |  |  |  |  | -813.48 |  | 0 | 0
241 | Water Main/Insulation Mat | GL | 666 | 01/23/19 | 01/23/19 | Mat | Req 4928 |  |  |  |  | 583.9 |  | 0 | 0
241 | Water Main/Insulation Mat | GL | 267 | 04/08/19 | 04/08/19 | Mat | Req 5159 |  |  |  |  | -1557.62 |  | 0 | 0
241 | Water Main/Insulation Mat | GL | 684 | 04/24/19 | 04/24/19 | Mat | Req 5911 |  |  |  |  | 33.75 |  | 0 | 0
242 | Mech Room Material | GL | 550 | 06/15/18 | 06/15/18 | Mat | Req 3697 |  |  |  |  | 148.05 |  | 0 | 0
242 | Mech Room Material | GL | 184 | 09/10/18 | 09/10/18 | Mat | Req 4694 |  |  |  |  | 344.68 |  | 0 | 0
242 | Mech Room Material | AP | 247 | 08/23/18 | 09/12/18 | 1231KS | Keller Supply Company |  |  |  |  | 62.34 | S012216712.001 | 0 | 0
242 | Mech Room Material | AP | 373 | 08/22/18 | 09/14/18 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 607.82 | 4256184-00 | 0 | 0
242 | Mech Room Material | GL | 643 | 09/25/18 | 09/25/18 | Mat | Req 5361 |  |  |  |  | 91.54 |  | 0 | 0
242 | Mech Room Material | AP | 349 | 09/25/18 | 10/15/18 | 1175FE | Ferguson Enterprises, Inc. #3007 |  |  |  |  | 8170.46 | 6565795 | 0 | 0
242 | Mech Room Material | GL | 356 | 10/16/18 | 10/16/18 | Mat | Req 5469 |  |  |  |  | 979.47 |  | 0 | 0
242 | Mech Room Material | GL | 368 | 10/16/18 | 10/16/18 | Mat | Req 5462 |  |  |  |  | 645.61 |  | 0 | 0
242 | Mech Room Material | GL | 545 | 10/22/18 | 10/22/18 | Mat | Req 4751 |  |  |  |  | 1033.1 |  | 0 | 0
242 | Mech Room Material | AP | 862 | 10/02/18 | 10/25/18 | 1175FE | Ferguson Enterprises, Inc. #3007 |  |  |  |  | 2543.78 | 6597730 | 0 | 0
242 | Mech Room Material | GL | 86 | 11/01/18 | 11/01/18 | Mat | Req 5514 |  |  |  |  | 188.47 |  | 0 | 0
242 | Mech Room Material | GL | 307 | 11/09/18 | 11/09/18 | Mat | Req 4775 |  |  |  |  | 131.74 |  | 0 | 0
242 | Mech Room Material | AP | 365 | 10/13/18 | 11/12/18 | 1175FE | Ferguson Enterprises, Inc. #3007 |  |  |  |  | 1080.47 | 6629139 | 0 | 0
242 | Mech Room Material | AP | 366 | 10/16/18 | 11/12/18 | 1175FE | Ferguson Enterprises, Inc. #3007 |  |  |  |  | 820.93 | 6629139-1 | 0 | 0
242 | Mech Room Material | GL | 566 | 11/16/18 | 11/16/18 | Mat | Req 4795 |  |  |  |  | 61.78 |  | 0 | 0
242 | Mech Room Material | AP | 452 | 12/27/19 | 01/15/19 | 1175FE | Ferguson Enterprises, Inc. #3007 |  |  |  |  | 184.81 | 6833209 | 0 | 0
242 | Mech Room Material | AP | 453 | 12/28/19 | 01/15/19 | 1175FE | Ferguson Enterprises, Inc. #3007 |  |  |  |  | 197.83 | 6833209-1 | 0 | 0
242 | Mech Room Material | GL | 669 | 01/23/19 | 01/23/19 | Mat | Req 4924 |  |  |  |  | 387.46 |  | 0 | 0
242 | Mech Room Material | GL | 408 | 02/14/19 | 02/14/19 | CK#5676 | Thomas McCabe |  |  |  |  | 18.69 |  | 0 | 0
242 | Mech Room Material | AP | 505 | 01/05/19 | 02/18/19 | 1175FE | Ferguson Enterprises, Inc. #3007 |  |  |  |  | 587.6 | 6789835 | 0 | 0
242 | Mech Room Material | GL | 197 | 03/01/19 | 03/01/19 | CK#5686 | Robert Hubbard |  |  |  |  | 33.07 |  | 0 | 0
242 | Mech Room Material | GL | 145 | 03/04/19 | 03/04/19 | Mat | Req 5048 |  |  |  |  | -3036.45 |  | 0 | 0
242 | Mech Room Material | GL | 146 | 03/04/19 | 03/04/19 | Mat | Req 5049 |  |  |  |  | -255.2 |  | 0 | 0
242 | Mech Room Material | AP | 54 | 03/13/19 | 04/03/19 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 1559.58 | 4263940-00 | 0 | 0
242 | Mech Room Material | GL | 705 | 04/24/19 | 04/24/19 | Mat | Req 5895 |  |  |  |  | -527.92 |  | 0 | 0
243 | Condensation Drains Mat | GL | 568 | 11/16/18 | 11/16/18 | Mat | Req 4791 |  |  |  |  | 110.46 |  | 0 | 0
243 | Condensation Drains Mat | GL | 664 | 01/23/19 | 01/23/19 | Mat | Req 4930 |  |  |  |  | 3.05 |  | 0 | 0
243 | Condensation Drains Mat | GL | 268 | 04/08/19 | 04/08/19 | Mat | Req 5160 |  |  |  |  | -22.44 |  | 0 | 0
600 | Subcontractor | AP | 217 | 03/04/19 | 03/06/19 | 1641AR | A.R. Brown Backflow Testing |  |  |  |  | 215 | INV01232 | 0 | 0
601 | Engineering/Plans | AP | 625 | 06/20/17 | 06/21/17 | 1625FE | Franklin Engineering |  |  |  |  | 343 | 6572 | 0 | 0
601 | Engineering/Plans | AP | 632 | 07/21/17 | 07/31/17 | 1625FE | Franklin Engineering |  |  |  |  | 3909 | 6607 | 0 | 0
601 | Engineering/Plans | AP | 119 | 08/18/17 | 09/05/17 | 1625FE | Franklin Engineering |  |  |  |  | 1969 | 6653 | 0 | 0
601 | Engineering/Plans | AP | 623 | 09/20/17 | 09/25/17 | 1625FE | Franklin Engineering |  |  |  |  | 2882.5 | 6664 | 0 | 0
601 | Engineering/Plans | AP | 576 | 10/19/17 | 10/27/17 | 1625FE | Franklin Engineering |  |  |  |  | 7211.25 | 6696 | 0 | 0
601 | Engineering/Plans | AP | 546 | 11/16/17 | 11/22/17 | 1625FE | Franklin Engineering |  |  |  |  | 281 | 6742 | 0 | 0
601 | Engineering/Plans | AP | 750 | 02/20/18 | 02/27/18 | 1625FE | Franklin Engineering |  |  |  |  | 5545.5 | 6845 | 0 | 0
601 | Engineering/Plans | AP | 644 | 03/21/18 | 03/26/18 | 1625FE | Franklin Engineering |  |  |  |  | 10251 | 6876 | 0 | 0
601 | Engineering/Plans | AP | 966 | 03/20/18 | 03/31/18 | 1288DR | DRSi |  |  |  |  | 248.64 | 460544 | 0 | 0
603 | Permits & Licenses | AP | 254 | 09/07/17 | 09/11/17 | 1234CO | Capital One Credit Card |  |  |  |  | 3485 | 090717A | 0 | 0
603 | Permits & Licenses | AP | 255 | 09/07/17 | 09/11/17 | 1234CO | Capital One Credit Card |  |  |  |  | 175 | 090717B | 0 | 0
603 | Permits & Licenses | AP | 256 | 09/07/17 | 09/11/17 | 1234CO | Capital One Credit Card |  |  |  |  | 210 | 090717C | 0 | 0
603 | Permits & Licenses | GL | 864 | 12/22/17 | 12/22/17 | CK#5033 | Seattle-King County Public Health |  |  |  |  | 201 |  | 0 | 0
603 | Permits & Licenses | AP | 771 | 04/03/18 | 04/30/18 | 1234BA | Bank of America CC |  |  |  |  | 502.5 | 040318B | 0 | 0
603 | Permits & Licenses | AP | 1019 | 03/19/19 | 03/31/19 | 1234CO | Capital One Credit Card |  |  |  |  | 201 | 031919J | 0 | 0
607 | Other Expenses | AP | 607 | 10/23/17 | 10/26/17 | 1234CO | Capital One Credit Card |  |  |  |  | 9 | 102317 | 0 | 0
607 | Other Expenses | AP | 615 | 10/15/17 | 10/26/17 | 1234CO | Capital One Credit Card |  |  |  |  | 460 | 101517B | 0 | 0
607 | Other Expenses | AP | 628 | 10/10/17 | 10/26/17 | 1234CO | Capital One Credit Card |  |  |  |  | 10.11 | 101017E | 0 | 0
607 | Other Expenses | GL | 130 | 12/01/17 | 12/01/17 | CK#5023 | Joseph Barnhart |  |  |  |  | 9.8 |  | 0 | 0
607 | Other Expenses | AP | 176 | 11/15/17 | 12/01/17 | 1234CO | Capital One Credit Card |  |  |  |  | 460 | 111517-2 | 0 | 0
607 | Other Expenses | AP | 900 | 12/15/17 | 12/31/17 | 1234CO | Capital One Credit Card |  |  |  |  | 460 | 121517B | 0 | 0
607 | Other Expenses | AP | 707 | 12/28/18 | 01/31/18 | 1234CO | Capital One Credit Card |  |  |  |  | 14.71 | 012818 | 0 | 0
607 | Other Expenses | AP | 720 | 01/15/18 | 01/31/18 | 1234CO | Capital One Credit Card |  |  |  |  | 460 | 011518B | 0 | 0
607 | Other Expenses | AP | 827 | 02/16/18 | 02/21/18 | 1234CO | Capital One Credit Card |  |  |  |  | 460 | 021618D | 0 | 0
607 | Other Expenses | AP | 921 | 02/27/18 | 03/31/18 | 1234CO | Capital One Credit Card |  |  |  |  | 10 | 022718G | 0 | 0
607 | Other Expenses | AP | 928 | 03/20/18 | 03/31/18 | 1234CO | Capital One Credit Card |  |  |  |  | 12.26 | 032018 | 0 | 0
607 | Other Expenses | AP | 945 | 03/15/18 | 03/31/18 | 1234CO | Capital One Credit Card |  |  |  |  | 460 | 031518C | 0 | 0
607 | Other Expenses | GL | 726 | 04/12/18 | 04/12/18 | CK#5081 | Reuben Reed |  |  |  |  | 22.07 |  | 0 | 0
607 | Other Expenses | GL | 733 | 04/26/18 | 04/26/18 | CK#5088 | Denis Velasquez Cruz |  |  |  |  | 44.14 |  | 0 | 0
607 | Other Expenses | AP | 772 | 04/03/18 | 04/30/18 | 1234BA | Bank of America CC |  |  |  |  | 14.71 | 040318C | 0 | 0
607 | Other Expenses | AP | 792 | 04/15/18 | 04/30/18 | 1234BA | Bank of America CC |  |  |  |  | 460 | 041518 | 0 | 0
607 | Other Expenses | GL | 156 | 05/03/18 | 05/03/18 | CK#5093 | Denis Velasquez Cruz |  |  |  |  | 110.35 |  | 0 | 0
607 | Other Expenses | GL | 572 | 05/22/18 | 05/22/18 | CK#5299 | Denis Velasquez Cruz |  |  |  |  | 44.14 |  | 0 | 0
607 | Other Expenses | AP | 854 | 05/07/18 | 05/30/18 | 1234CO | Capital One Credit Card |  |  |  |  | 309.78 | 050718 | 0 | 0
607 | Other Expenses | AP | 859 | 05/15/18 | 05/30/18 | 1234CO | Capital One Credit Card |  |  |  |  | 1 | 051518 | 0 | 0
607 | Other Expenses | AP | 863 | 05/15/18 | 05/30/18 | 1234CO | Capital One Credit Card |  |  |  |  | 224.78 | 051518D | 0 | 0
607 | Other Expenses | AP | 866 | 05/15/18 | 05/30/18 | 1234CO | Capital One Credit Card |  |  |  |  | 460 | 051518G | 0 | 0
607 | Other Expenses | GL | 245 | 06/01/18 | 06/01/18 | CK#5095 | Reuben Reed |  |  |  |  | 22.07 |  | 0 | 0
607 | Other Expenses | GL | 246 | 06/01/18 | 06/01/18 | CK#5096 | Denis Reyes Cruz |  |  |  |  | 154.49 |  | 0 | 0
607 | Other Expenses | AP | 216 | 06/15/18 | 07/10/18 | 1234CO | Capital One Credit Card |  |  |  |  | 224.78 | 061518R4 | 0 | 0
607 | Other Expenses | AP | 219 | 06/15/18 | 07/10/18 | 1234CO | Capital One Credit Card |  |  |  |  | 460 | 061518R7 | 0 | 0
607 | Other Expenses | AP | 135 | 06/27/18 | 08/07/18 | 1234CO | Capital One Credit Card |  |  |  |  | 5 | 062718R1 | 0 | 0
607 | Other Expenses | AP | 148 | 07/15/18 | 08/07/18 | 1234CO | Capital One Credit Card |  |  |  |  | 460 | 071518R6 | 0 | 0
607 | Other Expenses | AP | 149 | 07/15/18 | 08/07/18 | 1234CO | Capital One Credit Card |  |  |  |  | 224.78 | 071518R7 | 0 | 0
607 | Other Expenses | AP | 1132 | 08/15/18 | 08/30/18 | 1234CO | Capital One Credit Card |  |  |  |  | 460 | 081518R6 | 0 | 0
607 | Other Expenses | AP | 1133 | 08/15/18 | 08/30/18 | 1234CO | Capital One Credit Card |  |  |  |  | 224.78 | 081518R7 | 0 | 0
607 | Other Expenses | GL | 760 | 09/25/18 | 09/25/18 | CK#5579 | Robert Hubbard |  |  |  |  | 27.5 |  | 0 | 0
607 | Other Expenses | AP | 801 | 08/27/18 | 09/30/18 | 1234CO | Capital One Credit Card |  |  |  |  | 14.71 | 082718J | 0 | 0
607 | Other Expenses | AP | 827 | 09/15/18 | 09/30/18 | 1234CO | Capital One Credit Card |  |  |  |  | 460 | 091518R6 | 0 | 0
607 | Other Expenses | AP | 828 | 09/15/18 | 09/30/18 | 1234CO | Capital One Credit Card |  |  |  |  | 224.78 | 091518R7 | 0 | 0
607 | Other Expenses | AP | 801 | 10/02/18 | 10/30/18 | 1234CO | Capital One Credit Card |  |  |  |  | -219.78 | 100218R | 0 | 0
607 | Other Expenses | AP | 835 | 10/15/18 | 10/30/18 | 1234CO | Capital One Credit Card |  |  |  |  | 460 | 101518R6 | 0 | 0
607 | Other Expenses | AP | 475 | 11/01/18 | 12/14/18 | 1234CO | Capital One Credit Card |  |  |  |  | 341.99 | 110118R2 | 0 | 0
607 | Other Expenses | AP | 489 | 11/15/18 | 12/14/18 | 1234CO | Capital One Credit Card |  |  |  |  | 460 | 111518R6 | 0 | 0
607 | Other Expenses | AP | 498 | 11/01/18 | 12/14/18 | 1234CO | Capital One Credit Card |  |  |  |  | -181 | 110118R3 | 0 | 0
607 | Other Expenses | AP | 841 | 12/26/18 | 12/31/18 | 1234CO | Capital One Credit Card |  |  |  |  | 0.75 | 122618A | 0 | 0
607 | Other Expenses | AP | 844 | 12/04/18 | 12/31/18 | 1234CO | Capital One Credit Card |  |  |  |  | 341.99 | 120418R | 0 | 0
607 | Other Expenses | AP | 858 | 12/21/18 | 12/31/18 | 1234CO | Capital One Credit Card |  |  |  |  | 460 | 122118R3 | 0 | 0
607 | Other Expenses | AP | 118 | 12/26/18 | 01/04/19 | 1234CO | Capital One Credit Card |  |  |  |  | 6.03 | 122618 | 0 | 0
607 | Other Expenses | AP | 444 | 01/01/19 | 02/14/19 | 1234CO | Capital One Credit Card |  |  |  |  | 341.99 | 010119R | 0 | 0
607 | Other Expenses | AP | 455 | 01/15/19 | 02/14/19 | 1234CO | Capital One Credit Card |  |  |  |  | 460 | 011519R6 | 0 | 0
607 | Other Expenses | AP | 122 | 02/01/19 | 03/04/19 | 1234CO | Capital One Credit Card |  |  |  |  | 341.99 | 020119R1 | 0 | 0
607 | Other Expenses | AP | 1025 | 03/19/19 | 03/31/19 | 1234CO | Capital One Credit Card |  |  |  |  | 10 | 031919A1 | 0 | 0
607 | Other Expenses | AP | 954 | 04/03/19 | 04/30/19 | 1234CO | Capital One Credit Card |  |  |  |  | 9 | 040319A1 | 0 | 0
995 | Payroll Burden | PR | 184 | 09/06/17 | 09/08/17 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 22.18 |  | 0 | 0
995 | Payroll Burden | PR | 534 | 09/20/17 | 09/22/17 | SA54 | Sanders, Allen O | 0 | 0 | 0 | 0 | 26.61 |  | 0 | 0
995 | Payroll Burden | PR | 761 | 09/27/17 | 09/29/17 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 22.18 |  | 0 | 0
995 | Payroll Burden | PR | 762 | 09/27/17 | 09/29/17 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 62.53 |  | 0 | 0
995 | Payroll Burden | PR | 67 | 10/04/17 | 10/06/17 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 22.18 |  | 0 | 0
995 | Payroll Burden | PR | 67 | 10/04/17 | 10/06/17 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 88.7 |  | 0 | 0
995 | Payroll Burden | PR | 68 | 10/04/17 | 10/06/17 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 20.84 |  | 0 | 0
995 | Payroll Burden | PR | 225 | 10/11/17 | 10/13/17 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 199.58 |  | 0 | 0
995 | Payroll Burden | PR | 350 | 10/18/17 | 10/20/17 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 22.18 |  | 0 | 0
995 | Payroll Burden | PR | 488 | 10/25/17 | 10/27/17 | BA70 | Barnhart, Joseph N | 0 | 0 | 0 | 0 | 19.51 |  | 0 | 0
995 | Payroll Burden | PR | 547 | 10/25/17 | 10/27/17 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 44.35 |  | 0 | 0
995 | Payroll Burden | PR | 548 | 10/25/17 | 10/27/17 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 41.69 |  | 0 | 0
995 | Payroll Burden | PR | 548 | 10/25/17 | 10/27/17 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 41.69 |  | 0 | 0
995 | Payroll Burden | PR | 7 | 11/01/17 | 11/03/17 | BA70 | Barnhart, Joseph N | 0 | 0 | 0 | 0 | 19.51 |  | 0 | 0
995 | Payroll Burden | PR | 67 | 11/01/17 | 11/03/17 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 155.23 |  | 0 | 0
995 | Payroll Burden | PR | 68 | 11/01/17 | 11/03/17 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 20.84 |  | 0 | 0
995 | Payroll Burden | PR | 68 | 11/01/17 | 11/03/17 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 20.84 |  | 0 | 0
995 | Payroll Burden | PR | 154 | 11/08/17 | 11/10/17 | BA70 | Barnhart, Joseph N | 0 | 0 | 0 | 0 | 19.51 |  | 0 | 0
995 | Payroll Burden | PR | 343 | 11/15/17 | 11/17/17 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 44.35 |  | 0 | 0
995 | Payroll Burden | PR | 344 | 11/15/17 | 11/17/17 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 20.84 |  | 0 | 0
995 | Payroll Burden | PR | 430 | 11/22/17 | 11/22/17 | BA70 | Barnhart, Joseph N | 0 | 0 | 0 | 0 | 9.76 |  | 0 | 0
995 | Payroll Burden | PR | 66 | 11/29/17 | 12/01/17 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 44.35 |  | 0 | 0
995 | Payroll Burden | PR | 208 | 12/06/17 | 12/08/17 | BA70 | Barnhart, Joseph N | 0 | 0 | 0 | 0 | 19.51 |  | 0 | 0
995 | Payroll Burden | PR | 405 | 12/13/17 | 12/15/17 | BA70 | Barnhart, Joseph N | 0 | 0 | 0 | 0 | 39.03 |  | 0 | 0
995 | Payroll Burden | PR | 465 | 12/13/17 | 12/15/17 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 22.18 |  | 0 | 0
995 | Payroll Burden | PR | 466 | 12/13/17 | 12/15/17 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 62.53 |  | 0 | 0
995 | Payroll Burden | PR | 466 | 12/13/17 | 12/15/17 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 41.69 |  | 0 | 0
995 | Payroll Burden | PR | 591 | 12/20/17 | 12/22/17 | AN14 | Anderson, Richard P | 0 | 0 | 0 | 0 | 447.05 |  | 0 | 0
995 | Payroll Burden | PR | 595 | 12/20/17 | 12/22/17 | BA70 | Barnhart, Joseph N | 0 | 0 | 0 | 0 | 497.61 |  | 0 | 0
995 | Payroll Burden | PR | 622 | 12/20/17 | 12/22/17 | HU04 | Hubbard, Dustin R | 0 | 0 | 0 | 0 | 18.63 |  | 0 | 0
995 | Payroll Burden | PR | 625 | 12/20/17 | 12/22/17 | KI55 | Kinssies, Jr, John E | 0 | 0 | 0 | 0 | 133.05 |  | 0 | 0
995 | Payroll Burden | PR | 655 | 12/20/17 | 12/22/17 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 44.35 |  | 0 | 0
995 | Payroll Burden | PR | 656 | 12/20/17 | 12/22/17 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 125.07 |  | 0 | 0
995 | Payroll Burden | PR | 656 | 12/20/17 | 12/22/17 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 20.84 |  | 0 | 0
995 | Payroll Burden | PR | 782 | 12/27/17 | 12/29/17 | AN14 | Anderson, Richard P | 0 | 0 | 0 | 0 | 251.46 |  | 0 | 0
995 | Payroll Burden | PR | 785 | 12/27/17 | 12/29/17 | BA68 | Barbosa, Michael S | 0 | 0 | 0 | 0 | 74.51 |  | 0 | 0
995 | Payroll Burden | PR | 786 | 12/27/17 | 12/29/17 | BA70 | Barnhart, Joseph N | 0 | 0 | 0 | 0 | 273.2 |  | 0 | 0
995 | Payroll Burden | PR | 816 | 12/27/17 | 12/29/17 | KI55 | Kinssies, Jr, John E | 0 | 0 | 0 | 0 | 228.85 |  | 0 | 0
995 | Payroll Burden | PR | 847 | 12/27/17 | 12/29/17 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 41.69 |  | 0 | 0
995 | Payroll Burden | PR | 847 | 12/27/17 | 12/29/17 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 41.69 |  | 0 | 0
995 | Payroll Burden | PR | 2 | 01/03/18 | 01/05/18 | AN14 | Anderson, Richard P | 0 | 0 | 0 | 0 | 204.9 |  | 0 | 0
995 | Payroll Burden | PR | 6 | 01/03/18 | 01/05/18 | BA70 | Barnhart, Joseph N | 0 | 0 | 0 | 0 | 273.2 |  | 0 | 0
995 | Payroll Burden | PR | 36 | 01/03/18 | 01/05/18 | KI55 | Kinssies, Jr, John E | 0 | 0 | 0 | 0 | 170.3 |  | 0 | 0
995 | Payroll Burden | PR | 63 | 01/03/18 | 01/05/18 | WE55 | Wennig, Johnathan M | 0 | 0 | 0 | 0 | 138.37 |  | 0 | 0
995 | Payroll Burden | PR | 65 | 01/03/18 | 01/05/18 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 27.72 |  | 0 | 0
995 | Payroll Burden | PR | 66 | 01/03/18 | 01/05/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 83.38 |  | 0 | 0
995 | Payroll Burden | PR | 66 | 01/03/18 | 01/05/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 41.69 |  | 0 | 0
995 | Payroll Burden | PR | 225 | 01/10/18 | 01/12/18 | AN14 | Anderson, Richard P | 0 | 0 | 0 | 0 | 162.99 |  | 0 | 0
995 | Payroll Burden | PR | 229 | 01/10/18 | 01/12/18 | BA70 | Barnhart, Joseph N | 0 | 0 | 0 | 0 | 507.36 |  | 0 | 0
995 | Payroll Burden | PR | 256 | 01/10/18 | 01/12/18 | HU04 | Hubbard, Dustin R | 0 | 0 | 0 | 0 | 18.63 |  | 0 | 0
995 | Payroll Burden | PR | 256 | 01/10/18 | 01/12/18 | HU04 | Hubbard, Dustin R | 0 | 0 | 0 | 0 | -18.63 |  | 0 | 0
995 | Payroll Burden | PR | 259 | 01/10/18 | 01/12/18 | KI55 | Kinssies, Jr, John E | 0 | 0 | 0 | 0 | 234.17 |  | 0 | 0
995 | Payroll Burden | PR | 286 | 01/10/18 | 01/12/18 | WE55 | Wennig, Johnathan M | 0 | 0 | 0 | 0 | 100.9 |  | 0 | 0
995 | Payroll Burden | PR | 290 | 01/10/18 | 01/12/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 62.53 |  | 0 | 0
995 | Payroll Burden | PR | 290 | 01/10/18 | 01/12/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 41.69 |  | 0 | 0
995 | Payroll Burden | PR | 425 | 01/17/18 | 01/19/18 | KI55 | Kinssies, Jr, John E | 0 | 0 | 0 | 0 | 58.54 |  | 0 | 0
995 | Payroll Burden | PR | 425 | 01/17/18 | 01/19/18 | KI55 | Kinssies, Jr, John E | 0 | 0 | 0 | 0 | 21.29 |  | 0 | 0
995 | Payroll Burden | PR | 454 | 01/17/18 | 01/19/18 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 27.72 |  | 0 | 0
995 | Payroll Burden | PR | 455 | 01/17/18 | 01/19/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 41.69 |  | 0 | 0
995 | Payroll Burden | PR | 457 | 01/17/18 | 01/19/18 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | -27.72 |  | 0 | 0
995 | Payroll Burden | PR | 458 | 01/17/18 | 01/19/18 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 27.72 |  | 0 | 0
995 | Payroll Burden | PR | 589 | 01/24/18 | 01/26/18 | BA68 | Barbosa, Michael S | 0 | 0 | 0 | 0 | 130.39 |  | 0 | 0
995 | Payroll Burden | PR | 590 | 01/24/18 | 01/26/18 | BA70 | Barnhart, Joseph N | 0 | 0 | 0 | 0 | 160.99 |  | 0 | 0
995 | Payroll Burden | PR | 590 | 01/24/18 | 01/26/18 | BA70 | Barnhart, Joseph N | 0 | 0 | 0 | 0 | 331.74 |  | 0 | 0
995 | Payroll Burden | PR | 614 | 01/24/18 | 01/26/18 | HE70 | Hernandez Gonzalez, Osbaldo | 0 | 0 | 0 | 0 | 46.35 |  | 0 | 0
995 | Payroll Burden | PR | 650 | 01/24/18 | 01/26/18 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 27.72 |  | 0 | 0
995 | Payroll Burden | PR | 651 | 01/24/18 | 01/26/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 20.84 |  | 0 | 0
995 | Payroll Burden | PR | 651 | 01/24/18 | 01/26/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 41.69 |  | 0 | 0
995 | Payroll Burden | PR | 7 | 01/31/18 | 02/02/18 | BA68 | Barbosa, Michael S | 0 | 0 | 0 | 0 | 74.51 |  | 0 | 0
995 | Payroll Burden | PR | 8 | 01/31/18 | 02/02/18 | BA70 | Barnhart, Joseph N | 0 | 0 | 0 | 0 | 39.03 |  | 0 | 0
995 | Payroll Burden | PR | 8 | 01/31/18 | 02/02/18 | BA70 | Barnhart, Joseph N | 0 | 0 | 0 | 0 | 19.51 |  | 0 | 0
995 | Payroll Burden | PR | 71 | 01/31/18 | 02/02/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 41.69 |  | 0 | 0
995 | Payroll Burden | PR | 165 | 02/07/18 | 02/09/18 | BA70 | Barnhart, Joseph N | 0 | 0 | 0 | 0 | 39.03 |  | 0 | 0
995 | Payroll Burden | PR | 227 | 02/07/18 | 02/09/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 83.38 |  | 0 | 0
995 | Payroll Burden | PR | 227 | 02/07/18 | 02/09/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 20.84 |  | 0 | 0
995 | Payroll Burden | PR | 419 | 02/14/18 | 02/16/18 | BA70 | Barnhart, Joseph N | 0 | 0 | 0 | 0 | 351.25 |  | 0 | 0
995 | Payroll Burden | PR | 449 | 02/14/18 | 02/16/18 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 79.83 |  | 0 | 0
995 | Payroll Burden | PR | 456 | 02/14/18 | 02/16/18 | MA71 | Martinez Reyes, Juan C | 0 | 0 | 0 | 0 | 170.3 |  | 0 | 0
995 | Payroll Burden | PR | 483 | 02/14/18 | 02/16/18 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 27.72 |  | 0 | 0
995 | Payroll Burden | PR | 484 | 02/14/18 | 02/16/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 41.69 |  | 0 | 0
995 | Payroll Burden | PR | 607 | 02/21/18 | 02/23/18 | BA70 | Barnhart, Joseph N | 0 | 0 | 0 | 0 | 19.51 |  | 0 | 0
995 | Payroll Burden | PR | 643 | 02/21/18 | 02/23/18 | MA71 | Martinez Reyes, Juan C | 0 | 0 | 0 | 0 | 85.15 |  | 0 | 0
995 | Payroll Burden | PR | 669 | 02/21/18 | 02/23/18 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 55.44 |  | 0 | 0
995 | Payroll Burden | PR | 670 | 02/21/18 | 02/23/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 20.84 |  | 0 | 0
995 | Payroll Burden | PR | 6 | 02/28/18 | 03/02/18 | BA70 | Barnhart, Joseph N | 0 | 0 | 0 | 0 | 78.06 |  | 0 | 0
995 | Payroll Burden | PR | 6 | 02/28/18 | 03/02/18 | BA70 | Barnhart, Joseph N | 0 | 0 | 0 | 0 | 9.76 |  | 0 | 0
995 | Payroll Burden | PR | 26 | 02/28/18 | 03/02/18 | GA70 | Garcia, Jordan X | 0 | 0 | 0 | 0 | 206.23 |  | 0 | 0
995 | Payroll Burden | PR | 35 | 02/28/18 | 03/02/18 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 59.87 |  | 0 | 0
995 | Payroll Burden | PR | 42 | 02/28/18 | 03/02/18 | MA71 | Martinez Reyes, Juan C | 0 | 0 | 0 | 0 | 63.86 |  | 0 | 0
995 | Payroll Burden | PR | 44 | 02/28/18 | 03/02/18 | ME52 | Mendoza, Edgar E | 0 | 0 | 0 | 0 | 62.09 |  | 0 | 0
995 | Payroll Burden | PR | 53 | 02/28/18 | 03/02/18 | RE18 | Reed, Reuben H | 0 | 0 | 0 | 0 | 177.4 |  | 0 | 0
995 | Payroll Burden | PR | 67 | 02/28/18 | 03/02/18 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 55.44 |  | 0 | 0
995 | Payroll Burden | PR | 68 | 02/28/18 | 03/02/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 125.07 |  | 0 | 0
995 | Payroll Burden | PR | 68 | 02/28/18 | 03/02/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 20.84 |  | 0 | 0
995 | Payroll Burden | PR | 122 | 03/07/18 | 03/09/18 | BA70 | Barnhart, Joseph N | 0 | 0 | 0 | 0 | 78.06 |  | 0 | 0
995 | Payroll Burden | PR | 140 | 03/07/18 | 03/09/18 | GA70 | Garcia, Jordan X | 0 | 0 | 0 | 0 | 549.94 |  | 0 | 0
995 | Payroll Burden | PR | 158 | 03/07/18 | 03/09/18 | ME52 | Mendoza, Edgar E | 0 | 0 | 0 | 0 | 341.5 |  | 0 | 0
995 | Payroll Burden | PR | 167 | 03/07/18 | 03/09/18 | RE18 | Reed, Reuben H | 0 | 0 | 0 | 0 | 709.6 |  | 0 | 0
995 | Payroll Burden | PR | 184 | 03/07/18 | 03/09/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 41.69 |  | 0 | 0
995 | Payroll Burden | PR | 341 | 03/14/18 | 03/16/18 | GA70 | Garcia, Jordan X | 0 | 0 | 0 | 0 | 549.94 |  | 0 | 0
995 | Payroll Burden | PR | 359 | 03/14/18 | 03/16/18 | ME52 | Mendoza, Edgar E | 0 | 0 | 0 | 0 | 354.8 |  | 0 | 0
995 | Payroll Burden | PR | 369 | 03/14/18 | 03/16/18 | RE18 | Reed, Reuben H | 0 | 0 | 0 | 0 | 372.54 |  | 0 | 0
995 | Payroll Burden | PR | 385 | 03/14/18 | 03/16/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 44.35 |  | 0 | 0
995 | Payroll Burden | PR | 385 | 03/14/18 | 03/16/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 22.18 |  | 0 | 0
995 | Payroll Burden | PR | 539 | 03/21/18 | 03/23/18 | GA70 | Garcia, Jordan X | 0 | 0 | 0 | 0 | 439.95 |  | 0 | 0
995 | Payroll Burden | PR | 555 | 03/21/18 | 03/23/18 | LU09 | Lucas Tzintzun, Rafael | 0 | 0 | 0 | 0 | 170.3 |  | 0 | 0
995 | Payroll Burden | PR | 558 | 03/21/18 | 03/23/18 | ME52 | Mendoza, Edgar E | 0 | 0 | 0 | 0 | 283.84 |  | 0 | 0
995 | Payroll Burden | PR | 568 | 03/21/18 | 03/23/18 | RE18 | Reed, Reuben H | 0 | 0 | 0 | 0 | 567.68 |  | 0 | 0
995 | Payroll Burden | PR | 584 | 03/21/18 | 03/23/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 66.53 |  | 0 | 0
995 | Payroll Burden | PR | 758 | 03/28/18 | 03/30/18 | GA70 | Garcia, Jordan X | 0 | 0 | 0 | 0 | 549.94 |  | 0 | 0
995 | Payroll Burden | PR | 777 | 03/28/18 | 03/30/18 | LU09 | Lucas Tzintzun, Rafael | 0 | 0 | 0 | 0 | 276.74 |  | 0 | 0
995 | Payroll Burden | PR | 780 | 03/28/18 | 03/30/18 | ME52 | Mendoza, Edgar E | 0 | 0 | 0 | 0 | 341.5 |  | 0 | 0
995 | Payroll Burden | PR | 791 | 03/28/18 | 03/30/18 | RE18 | Reed, Reuben H | 0 | 0 | 0 | 0 | 709.6 |  | 0 | 0
995 | Payroll Burden | PR | 811 | 03/28/18 | 03/30/18 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 27.72 |  | 0 | 0
995 | Payroll Burden | PR | 811 | 03/28/18 | 03/30/18 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 27.72 |  | 0 | 0
995 | Payroll Burden | PR | 34 | 04/04/18 | 04/06/18 | GA70 | Garcia, Jordan X | 0 | 0 | 0 | 0 | 549.94 |  | 0 | 0
995 | Payroll Burden | PR | 52 | 04/04/18 | 04/06/18 | LU09 | Lucas Tzintzun, Rafael | 0 | 0 | 0 | 0 | 280.29 |  | 0 | 0
995 | Payroll Burden | PR | 55 | 04/04/18 | 04/06/18 | ME52 | Mendoza, Edgar E | 0 | 0 | 0 | 0 | 323.76 |  | 0 | 0
995 | Payroll Burden | PR | 65 | 04/04/18 | 04/06/18 | RE18 | Reed, Reuben H | 0 | 0 | 0 | 0 | 638.64 |  | 0 | 0
995 | Payroll Burden | PR | 85 | 04/04/18 | 04/06/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 22.18 |  | 0 | 0
995 | Payroll Burden | PR | 85 | 04/04/18 | 04/06/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 44.35 |  | 0 | 0
995 | Payroll Burden | PR | 263 | 04/11/18 | 04/13/18 | BA70 | Barnhart, Joseph N | 0 | 0 | 0 | 0 | 58.54 |  | 0 | 0
995 | Payroll Burden | PR | 282 | 04/11/18 | 04/13/18 | GA70 | Garcia, Jordan X | 0 | 0 | 0 | 0 | 274.97 |  | 0 | 0
995 | Payroll Burden | PR | 301 | 04/11/18 | 04/13/18 | LU09 | Lucas Tzintzun, Rafael | 0 | 0 | 0 | 0 | 212.88 |  | 0 | 0
995 | Payroll Burden | PR | 304 | 04/11/18 | 04/13/18 | ME52 | Mendoza, Edgar E | 0 | 0 | 0 | 0 | 212.88 |  | 0 | 0
995 | Payroll Burden | PR | 315 | 04/11/18 | 04/13/18 | RE18 | Reed, Reuben H | 0 | 0 | 0 | 0 | 425.76 |  | 0 | 0
995 | Payroll Burden | PR | 333 | 04/11/18 | 04/13/18 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 55.44 |  | 0 | 0
995 | Payroll Burden | PR | 467 | 04/18/18 | 04/20/18 | GA70 | Garcia, Jordan X | 0 | 0 | 0 | 0 | 494.95 |  | 0 | 0
995 | Payroll Burden | PR | 486 | 04/18/18 | 04/20/18 | LU09 | Lucas Tzintzun, Rafael | 0 | 0 | 0 | 0 | 223.52 |  | 0 | 0
995 | Payroll Burden | PR | 489 | 04/18/18 | 04/20/18 | ME52 | Mendoza, Edgar E | 0 | 0 | 0 | 0 | 283.84 |  | 0 | 0
995 | Payroll Burden | PR | 500 | 04/18/18 | 04/20/18 | RE18 | Reed, Reuben H | 0 | 0 | 0 | 0 | 709.6 |  | 0 | 0
995 | Payroll Burden | PR | 517 | 04/18/18 | 04/20/18 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 27.72 |  | 0 | 0
995 | Payroll Burden | PR | 518 | 04/18/18 | 04/20/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 66.53 |  | 0 | 0
995 | Payroll Burden | PR | 617 | 04/25/18 | 04/27/18 | BA70 | Barnhart, Joseph N | 0 | 0 | 0 | 0 | 19.51 |  | 0 | 0
995 | Payroll Burden | PR | 617 | 04/25/18 | 04/27/18 | BA70 | Barnhart, Joseph N | 0 | 0 | 0 | 0 | 19.51 |  | 0 | 0
995 | Payroll Burden | PR | 653 | 04/25/18 | 04/27/18 | LU09 | Lucas Tzintzun, Rafael | 0 | 0 | 0 | 0 | 276.74 |  | 0 | 0
995 | Payroll Burden | PR | 656 | 04/25/18 | 04/27/18 | ME52 | Mendoza, Edgar E | 0 | 0 | 0 | 0 | 354.8 |  | 0 | 0
995 | Payroll Burden | PR | 666 | 04/25/18 | 04/27/18 | RE18 | Reed, Reuben H | 0 | 0 | 0 | 0 | 567.68 |  | 0 | 0
995 | Payroll Burden | PR | 677 | 04/25/18 | 04/27/18 | VE42 | Velasquez Cruz, Denis M | 0 | 0 | 0 | 0 | 478.98 |  | 0 | 0
995 | Payroll Burden | PR | 678 | 04/25/18 | 04/27/18 | VE43 | Velasquez Cruz, Osman N | 0 | 0 | 0 | 0 | 337.06 |  | 0 | 0
995 | Payroll Burden | PR | 684 | 04/25/18 | 04/27/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 22.18 |  | 0 | 0
995 | Payroll Burden | PR | 31 | 05/02/18 | 05/04/18 | BA70 | Barnhart, Joseph N | 0 | 0 | 0 | 0 | 19.51 |  | 0 | 0
995 | Payroll Burden | PR | 67 | 05/02/18 | 05/04/18 | LU09 | Lucas Tzintzun, Rafael | 0 | 0 | 0 | 0 | 273.2 |  | 0 | 0
995 | Payroll Burden | PR | 70 | 05/02/18 | 05/04/18 | ME52 | Mendoza, Edgar E | 0 | 0 | 0 | 0 | 354.8 |  | 0 | 0
995 | Payroll Burden | PR | 81 | 05/02/18 | 05/04/18 | RE18 | Reed, Reuben H | 0 | 0 | 0 | 0 | 709.6 |  | 0 | 0
995 | Payroll Burden | PR | 92 | 05/02/18 | 05/04/18 | VE42 | Velasquez Cruz, Denis M | 0 | 0 | 0 | 0 | 478.98 |  | 0 | 0
995 | Payroll Burden | PR | 93 | 05/02/18 | 05/04/18 | VE43 | Velasquez Cruz, Osman N | 0 | 0 | 0 | 0 | 337.06 |  | 0 | 0
995 | Payroll Burden | PR | 260 | 05/09/18 | 05/11/18 | LU09 | Lucas Tzintzun, Rafael | 0 | 0 | 0 | 0 | 283.84 |  | 0 | 0
995 | Payroll Burden | PR | 263 | 05/09/18 | 05/11/18 | ME52 | Mendoza, Edgar E | 0 | 0 | 0 | 0 | 354.8 |  | 0 | 0
995 | Payroll Burden | PR | 273 | 05/09/18 | 05/11/18 | RE18 | Reed, Reuben H | 0 | 0 | 0 | 0 | 709.6 |  | 0 | 0
995 | Payroll Burden | PR | 281 | 05/09/18 | 05/11/18 | VE42 | Velasquez Cruz, Denis M | 0 | 0 | 0 | 0 | 478.98 |  | 0 | 0
995 | Payroll Burden | PR | 282 | 05/09/18 | 05/11/18 | VE43 | Velasquez Cruz, Osman N | 0 | 0 | 0 | 0 | 337.06 |  | 0 | 0
995 | Payroll Burden | PR | 286 | 05/09/18 | 05/11/18 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 110.88 |  | 0 | 0
995 | Payroll Burden | PR | 435 | 05/16/18 | 05/18/18 | CR79 | Cruz Guzman, Joel A | 0 | 0 | 0 | 0 | 234.17 |  | 0 | 0
995 | Payroll Burden | PR | 436 | 05/16/18 | 05/18/18 | CR87 | Cruz Reyes, Jose | 0 | 0 | 0 | 0 | 244.81 |  | 0 | 0
995 | Payroll Burden | PR | 452 | 05/16/18 | 05/18/18 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 229.51 |  | 0 | 0
995 | Payroll Burden | PR | 461 | 05/16/18 | 05/18/18 | LU09 | Lucas Tzintzun, Rafael | 0 | 0 | 0 | 0 | 283.84 |  | 0 | 0
995 | Payroll Burden | PR | 464 | 05/16/18 | 05/18/18 | ME52 | Mendoza, Edgar E | 0 | 0 | 0 | 0 | 354.8 |  | 0 | 0
995 | Payroll Burden | PR | 475 | 05/16/18 | 05/18/18 | RE18 | Reed, Reuben H | 0 | 0 | 0 | 0 | 425.76 |  | 0 | 0
995 | Payroll Burden | PR | 485 | 05/16/18 | 05/18/18 | VE42 | Velasquez Cruz, Denis M | 0 | 0 | 0 | 0 | 478.98 |  | 0 | 0
995 | Payroll Burden | PR | 486 | 05/16/18 | 05/18/18 | VE43 | Velasquez Cruz, Osman N | 0 | 0 | 0 | 0 | 269.65 |  | 0 | 0
995 | Payroll Burden | PR | 492 | 05/16/18 | 05/18/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 22.18 |  | 0 | 0
995 | Payroll Burden | PR | 742 | 05/23/18 | 05/25/18 | BE45 | Belcher, Jacob T | 0 | 0 | 0 | 0 | 21.29 |  | 0 | 0
995 | Payroll Burden | PR | 742 | 05/23/18 | 05/25/18 | BE45 | Belcher, Jacob T | 0 | 0 | 0 | 0 | 227.07 |  | 0 | 0
995 | Payroll Burden | PR | 750 | 05/23/18 | 05/25/18 | CR79 | Cruz Guzman, Joel A | 0 | 0 | 0 | 0 | 29.27 |  | 0 | 0
995 | Payroll Burden | PR | 750 | 05/23/18 | 05/25/18 | CR79 | Cruz Guzman, Joel A | 0 | 0 | 0 | 0 | 273.2 |  | 0 | 0
995 | Payroll Burden | PR | 751 | 05/23/18 | 05/25/18 | CR87 | Cruz Reyes, Jose | 0 | 0 | 0 | 0 | 30.6 |  | 0 | 0
995 | Payroll Burden | PR | 751 | 05/23/18 | 05/25/18 | CR87 | Cruz Reyes, Jose | 0 | 0 | 0 | 0 | 285.61 |  | 0 | 0
995 | Payroll Burden | PR | 751 | 05/23/18 | 05/25/18 | CR87 | Cruz Reyes, Jose | 0 | 0 | 0 | 0 | 122.41 |  | 0 | 0
995 | Payroll Burden | PR | 757 | 05/23/18 | 05/25/18 | GA70 | Garcia, Jordan X | 0 | 0 | 0 | 0 | 54.99 |  | 0 | 0
995 | Payroll Burden | PR | 764 | 05/23/18 | 05/25/18 | HO18 | Hoeg, Xavier A | 0 | 0 | 0 | 0 | 19.96 |  | 0 | 0
995 | Payroll Burden | PR | 764 | 05/23/18 | 05/25/18 | HO18 | Hoeg, Xavier A | 0 | 0 | 0 | 0 | 212.88 |  | 0 | 0
995 | Payroll Burden | PR | 774 | 05/23/18 | 05/25/18 | LO58 | Lopez Reyes, Boris O | 0 | 0 | 0 | 0 | 63.86 |  | 0 | 0
995 | Payroll Burden | PR | 776 | 05/23/18 | 05/25/18 | LU09 | Lucas Tzintzun, Rafael | 0 | 0 | 0 | 0 | 21.29 |  | 0 | 0
995 | Payroll Burden | PR | 776 | 05/23/18 | 05/25/18 | LU09 | Lucas Tzintzun, Rafael | 0 | 0 | 0 | 0 | 283.84 |  | 0 | 0
995 | Payroll Burden | PR | 779 | 05/23/18 | 05/25/18 | ME52 | Mendoza, Edgar E | 0 | 0 | 0 | 0 | 26.61 |  | 0 | 0
995 | Payroll Burden | PR | 779 | 05/23/18 | 05/25/18 | ME52 | Mendoza, Edgar E | 0 | 0 | 0 | 0 | 354.8 |  | 0 | 0
995 | Payroll Burden | PR | 790 | 05/23/18 | 05/25/18 | RE18 | Reed, Reuben H | 0 | 0 | 0 | 0 | 53.22 |  | 0 | 0
995 | Payroll Burden | PR | 790 | 05/23/18 | 05/25/18 | RE18 | Reed, Reuben H | 0 | 0 | 0 | 0 | 638.64 |  | 0 | 0
995 | Payroll Burden | PR | 800 | 05/23/18 | 05/25/18 | VE42 | Velasquez Cruz, Denis M | 0 | 0 | 0 | 0 | 35.92 |  | 0 | 0
995 | Payroll Burden | PR | 800 | 05/23/18 | 05/25/18 | VE42 | Velasquez Cruz, Denis M | 0 | 0 | 0 | 0 | 478.98 |  | 0 | 0
995 | Payroll Burden | PR | 801 | 05/23/18 | 05/25/18 | VE43 | Velasquez Cruz, Osman N | 0 | 0 | 0 | 0 | 25.28 |  | 0 | 0
995 | Payroll Burden | PR | 801 | 05/23/18 | 05/25/18 | VE43 | Velasquez Cruz, Osman N | 0 | 0 | 0 | 0 | 337.06 |  | 0 | 0
995 | Payroll Burden | PR | 806 | 05/23/18 | 05/25/18 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 27.72 |  | 0 | 0
995 | Payroll Burden | PR | 807 | 05/23/18 | 05/25/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 44.35 |  | 0 | 0
995 | Payroll Burden | PR | 807 | 05/23/18 | 05/25/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 44.35 |  | 0 | 0
995 | Payroll Burden | PR | 9 | 05/30/18 | 06/01/18 | BE45 | Belcher, Jacob T | 0 | 0 | 0 | 0 | 248.36 |  | 0 | 0
995 | Payroll Burden | PR | 17 | 05/30/18 | 06/01/18 | CR79 | Cruz Guzman, Joel A | 0 | 0 | 0 | 0 | 341.5 |  | 0 | 0
995 | Payroll Burden | PR | 18 | 05/30/18 | 06/01/18 | CR87 | Cruz Reyes, Jose | 0 | 0 | 0 | 0 | 357.02 |  | 0 | 0
995 | Payroll Burden | PR | 31 | 05/30/18 | 06/01/18 | HO18 | Hoeg, Xavier A | 0 | 0 | 0 | 0 | 232.84 |  | 0 | 0
995 | Payroll Burden | PR | 41 | 05/30/18 | 06/01/18 | LO58 | Lopez Reyes, Boris O | 0 | 0 | 0 | 0 | 63.86 |  | 0 | 0
995 | Payroll Burden | PR | 43 | 05/30/18 | 06/01/18 | LU09 | Lucas Tzintzun, Rafael | 0 | 0 | 0 | 0 | 248.36 |  | 0 | 0
995 | Payroll Burden | PR | 46 | 05/30/18 | 06/01/18 | ME52 | Mendoza, Edgar E | 0 | 0 | 0 | 0 | 310.45 |  | 0 | 0
995 | Payroll Burden | PR | 56 | 05/30/18 | 06/01/18 | RE18 | Reed, Reuben H | 0 | 0 | 0 | 0 | 567.68 |  | 0 | 0
995 | Payroll Burden | PR | 68 | 05/30/18 | 06/01/18 | VE43 | Velasquez Cruz, Osman N | 0 | 0 | 0 | 0 | 143.25 |  | 0 | 0
995 | Payroll Burden | PR | 76 | 05/30/18 | 06/01/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 22.18 |  | 0 | 0
995 | Payroll Burden | PR | 76 | 05/30/18 | 06/01/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 22.18 |  | 0 | 0
995 | Payroll Burden | PR | 274 | 06/06/18 | 06/08/18 | BE45 | Belcher, Jacob T | 0 | 0 | 0 | 0 | 42.58 |  | 0 | 0
995 | Payroll Burden | PR | 274 | 06/06/18 | 06/08/18 | BE45 | Belcher, Jacob T | 0 | 0 | 0 | 0 | 283.84 |  | 0 | 0
995 | Payroll Burden | PR | 282 | 06/06/18 | 06/08/18 | CR79 | Cruz Guzman, Joel A | 0 | 0 | 0 | 0 | 58.54 |  | 0 | 0
995 | Payroll Burden | PR | 282 | 06/06/18 | 06/08/18 | CR79 | Cruz Guzman, Joel A | 0 | 0 | 0 | 0 | 390.28 |  | 0 | 0
995 | Payroll Burden | PR | 283 | 06/06/18 | 06/08/18 | CR87 | Cruz Reyes, Jose | 0 | 0 | 0 | 0 | 91.8 |  | 0 | 0
995 | Payroll Burden | PR | 283 | 06/06/18 | 06/08/18 | CR87 | Cruz Reyes, Jose | 0 | 0 | 0 | 0 | 275.41 |  | 0 | 0
995 | Payroll Burden | PR | 296 | 06/06/18 | 06/08/18 | HO18 | Hoeg, Xavier A | 0 | 0 | 0 | 0 | 9.98 |  | 0 | 0
995 | Payroll Burden | PR | 296 | 06/06/18 | 06/08/18 | HO18 | Hoeg, Xavier A | 0 | 0 | 0 | 0 | 106.44 |  | 0 | 0
995 | Payroll Burden | PR | 308 | 06/06/18 | 06/08/18 | LU09 | Lucas Tzintzun, Rafael | 0 | 0 | 0 | 0 | 42.58 |  | 0 | 0
995 | Payroll Burden | PR | 308 | 06/06/18 | 06/08/18 | LU09 | Lucas Tzintzun, Rafael | 0 | 0 | 0 | 0 | 283.84 |  | 0 | 0
995 | Payroll Burden | PR | 311 | 06/06/18 | 06/08/18 | ME52 | Mendoza, Edgar E | 0 | 0 | 0 | 0 | 39.92 |  | 0 | 0
995 | Payroll Burden | PR | 311 | 06/06/18 | 06/08/18 | ME52 | Mendoza, Edgar E | 0 | 0 | 0 | 0 | 354.8 |  | 0 | 0
995 | Payroll Burden | PR | 321 | 06/06/18 | 06/08/18 | RE18 | Reed, Reuben H | 0 | 0 | 0 | 0 | 53.22 |  | 0 | 0
995 | Payroll Burden | PR | 321 | 06/06/18 | 06/08/18 | RE18 | Reed, Reuben H | 0 | 0 | 0 | 0 | 53.22 |  | 0 | 0
995 | Payroll Burden | PR | 321 | 06/06/18 | 06/08/18 | RE18 | Reed, Reuben H | 0 | 0 | 0 | 0 | 425.76 |  | 0 | 0
995 | Payroll Burden | PR | 321 | 06/06/18 | 06/08/18 | RE18 | Reed, Reuben H | 0 | 0 | 0 | 0 | 283.84 |  | 0 | 0
995 | Payroll Burden | PR | 334 | 06/06/18 | 06/08/18 | VE43 | Velasquez Cruz, Osman N | 0 | 0 | 0 | 0 | 67.41 |  | 0 | 0
995 | Payroll Burden | PR | 340 | 06/06/18 | 06/08/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 22.18 |  | 0 | 0
995 | Payroll Burden | PR | 350 | 06/06/18 | 06/08/18 | VE43 | Velasquez Cruz, Osman N | 0 | 0 | 0 | 0 | -67.41 |  | 0 | 0
995 | Payroll Burden | PR | 464 | 06/13/18 | 06/15/18 | BE45 | Belcher, Jacob T | 0 | 0 | 0 | 0 | 33.93 |  | 0 | 0
995 | Payroll Burden | PR | 464 | 06/13/18 | 06/15/18 | BE45 | Belcher, Jacob T | 0 | 0 | 0 | 0 | 11.31 |  | 0 | 0
995 | Payroll Burden | PR | 464 | 06/13/18 | 06/15/18 | BE45 | Belcher, Jacob T | 0 | 0 | 0 | 0 | 180.95 |  | 0 | 0
995 | Payroll Burden | PR | 464 | 06/13/18 | 06/15/18 | BE45 | Belcher, Jacob T | 0 | 0 | 0 | 0 | 120.63 |  | 0 | 0
995 | Payroll Burden | PR | 472 | 06/13/18 | 06/15/18 | CR79 | Cruz Guzman, Joel A | 0 | 0 | 0 | 0 | 183.61 |  | 0 | 0
995 | Payroll Burden | PR | 472 | 06/13/18 | 06/15/18 | CR79 | Cruz Guzman, Joel A | 0 | 0 | 0 | 0 | 173.41 |  | 0 | 0
995 | Payroll Burden | PR | 473 | 06/13/18 | 06/15/18 | CR87 | Cruz Reyes, Jose | 0 | 0 | 0 | 0 | 63.86 |  | 0 | 0
995 | Payroll Burden | PR | 473 | 06/13/18 | 06/15/18 | CR87 | Cruz Reyes, Jose | 0 | 0 | 0 | 0 | 425.76 |  | 0 | 0
995 | Payroll Burden | PR | 489 | 06/13/18 | 06/15/18 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 41.69 |  | 0 | 0
995 | Payroll Burden | PR | 498 | 06/13/18 | 06/15/18 | LU09 | Lucas Tzintzun, Rafael | 0 | 0 | 0 | 0 | 33.93 |  | 0 | 0
995 | Payroll Burden | PR | 498 | 06/13/18 | 06/15/18 | LU09 | Lucas Tzintzun, Rafael | 0 | 0 | 0 | 0 | 11.31 |  | 0 | 0
995 | Payroll Burden | PR | 498 | 06/13/18 | 06/15/18 | LU09 | Lucas Tzintzun, Rafael | 0 | 0 | 0 | 0 | 180.95 |  | 0 | 0
995 | Payroll Burden | PR | 498 | 06/13/18 | 06/15/18 | LU09 | Lucas Tzintzun, Rafael | 0 | 0 | 0 | 0 | 120.63 |  | 0 | 0
995 | Payroll Burden | PR | 501 | 06/13/18 | 06/15/18 | ME52 | Mendoza, Edgar E | 0 | 0 | 0 | 0 | 55.88 |  | 0 | 0
995 | Payroll Burden | PR | 501 | 06/13/18 | 06/15/18 | ME52 | Mendoza, Edgar E | 0 | 0 | 0 | 0 | 372.54 |  | 0 | 0
995 | Payroll Burden | PR | 510 | 06/13/18 | 06/15/18 | RE18 | Reed, Reuben H | 0 | 0 | 0 | 0 | 54.55 |  | 0 | 0
995 | Payroll Burden | PR | 510 | 06/13/18 | 06/15/18 | RE18 | Reed, Reuben H | 0 | 0 | 0 | 0 | 54.55 |  | 0 | 0
995 | Payroll Burden | PR | 510 | 06/13/18 | 06/15/18 | RE18 | Reed, Reuben H | 0 | 0 | 0 | 0 | 345.49 |  | 0 | 0
995 | Payroll Burden | PR | 510 | 06/13/18 | 06/15/18 | RE18 | Reed, Reuben H | 0 | 0 | 0 | 0 | 381.85 |  | 0 | 0
995 | Payroll Burden | PR | 690 | 06/20/18 | 06/22/18 | BE45 | Belcher, Jacob T | 0 | 0 | 0 | 0 | 135.71 |  | 0 | 0
995 | Payroll Burden | PR | 690 | 06/20/18 | 06/22/18 | BE45 | Belcher, Jacob T | 0 | 0 | 0 | 0 | 128.17 |  | 0 | 0
995 | Payroll Burden | PR | 698 | 06/20/18 | 06/22/18 | CR79 | Cruz Guzman, Joel A | 0 | 0 | 0 | 0 | 61.2 |  | 0 | 0
995 | Payroll Burden | PR | 698 | 06/20/18 | 06/22/18 | CR79 | Cruz Guzman, Joel A | 0 | 0 | 0 | 0 | 408.02 |  | 0 | 0
995 | Payroll Burden | PR | 699 | 06/20/18 | 06/22/18 | CR87 | Cruz Reyes, Jose | 0 | 0 | 0 | 0 | 47.9 |  | 0 | 0
995 | Payroll Burden | PR | 699 | 06/20/18 | 06/22/18 | CR87 | Cruz Reyes, Jose | 0 | 0 | 0 | 0 | 15.97 |  | 0 | 0
995 | Payroll Burden | PR | 699 | 06/20/18 | 06/22/18 | CR87 | Cruz Reyes, Jose | 0 | 0 | 0 | 0 | 255.46 |  | 0 | 0
995 | Payroll Burden | PR | 699 | 06/20/18 | 06/22/18 | CR87 | Cruz Reyes, Jose | 0 | 0 | 0 | 0 | 170.3 |  | 0 | 0
995 | Payroll Burden | PR | 715 | 06/20/18 | 06/22/18 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 31.27 |  | 0 | 0
995 | Payroll Burden | PR | 724 | 06/20/18 | 06/22/18 | LU09 | Lucas Tzintzun, Rafael | 0 | 0 | 0 | 0 | 196.03 |  | 0 | 0
995 | Payroll Burden | PR | 727 | 06/20/18 | 06/22/18 | ME52 | Mendoza, Edgar E | 0 | 0 | 0 | 0 | 27.94 |  | 0 | 0
995 | Payroll Burden | PR | 727 | 06/20/18 | 06/22/18 | ME52 | Mendoza, Edgar E | 0 | 0 | 0 | 0 | 372.54 |  | 0 | 0
995 | Payroll Burden | PR | 736 | 06/20/18 | 06/22/18 | RE18 | Reed, Reuben H | 0 | 0 | 0 | 0 | 81.83 |  | 0 | 0
995 | Payroll Burden | PR | 736 | 06/20/18 | 06/22/18 | RE18 | Reed, Reuben H | 0 | 0 | 0 | 0 | 727.34 |  | 0 | 0
995 | Payroll Burden | PR | 754 | 06/20/18 | 06/22/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 22.18 |  | 0 | 0
995 | Payroll Burden | PR | 958 | 06/27/18 | 06/29/18 | BE45 | Belcher, Jacob T | 0 | 0 | 0 | 0 | 22.62 |  | 0 | 0
995 | Payroll Burden | PR | 958 | 06/27/18 | 06/29/18 | BE45 | Belcher, Jacob T | 0 | 0 | 0 | 0 | 22.62 |  | 0 | 0
995 | Payroll Burden | PR | 958 | 06/27/18 | 06/29/18 | BE45 | Belcher, Jacob T | 0 | 0 | 0 | 0 | 226.19 |  | 0 | 0
995 | Payroll Burden | PR | 958 | 06/27/18 | 06/29/18 | BE45 | Belcher, Jacob T | 0 | 0 | 0 | 0 | 75.4 |  | 0 | 0
995 | Payroll Burden | PR | 965 | 06/27/18 | 06/29/18 | CR79 | Cruz Guzman, Joel A | 0 | 0 | 0 | 0 | 45.9 |  | 0 | 0
995 | Payroll Burden | PR | 965 | 06/27/18 | 06/29/18 | CR79 | Cruz Guzman, Joel A | 0 | 0 | 0 | 0 | 15.3 |  | 0 | 0
995 | Payroll Burden | PR | 965 | 06/27/18 | 06/29/18 | CR79 | Cruz Guzman, Joel A | 0 | 0 | 0 | 0 | 326.42 |  | 0 | 0
995 | Payroll Burden | PR | 965 | 06/27/18 | 06/29/18 | CR79 | Cruz Guzman, Joel A | 0 | 0 | 0 | 0 | 81.6 |  | 0 | 0
995 | Payroll Burden | PR | 966 | 06/27/18 | 06/29/18 | CR87 | Cruz Reyes, Jose | 0 | 0 | 0 | 0 | 95.8 |  | 0 | 0
995 | Payroll Burden | PR | 992 | 06/27/18 | 06/29/18 | LU09 | Lucas Tzintzun, Rafael | 0 | 0 | 0 | 0 | 45.24 |  | 0 | 0
995 | Payroll Burden | PR | 992 | 06/27/18 | 06/29/18 | LU09 | Lucas Tzintzun, Rafael | 0 | 0 | 0 | 0 | 301.58 |  | 0 | 0
995 | Payroll Burden | PR | 995 | 06/27/18 | 06/29/18 | ME52 | Mendoza, Edgar E | 0 | 0 | 0 | 0 | 43.91 |  | 0 | 0
995 | Payroll Burden | PR | 995 | 06/27/18 | 06/29/18 | ME52 | Mendoza, Edgar E | 0 | 0 | 0 | 0 | 390.28 |  | 0 | 0
995 | Payroll Burden | PR | 1003 | 06/27/18 | 06/29/18 | RE18 | Reed, Reuben H | 0 | 0 | 0 | 0 | 54.55 |  | 0 | 0
995 | Payroll Burden | PR | 1003 | 06/27/18 | 06/29/18 | RE18 | Reed, Reuben H | 0 | 0 | 0 | 0 | 27.28 |  | 0 | 0
995 | Payroll Burden | PR | 1003 | 06/27/18 | 06/29/18 | RE18 | Reed, Reuben H | 0 | 0 | 0 | 0 | 90.92 |  | 0 | 0
995 | Payroll Burden | PR | 1003 | 06/27/18 | 06/29/18 | RE18 | Reed, Reuben H | 0 | 0 | 0 | 0 | 290.94 |  | 0 | 0
995 | Payroll Burden | PR | 1003 | 06/27/18 | 06/29/18 | RE18 | Reed, Reuben H | 0 | 0 | 0 | 0 | 290.94 |  | 0 | 0
995 | Payroll Burden | PR | 1019 | 06/27/18 | 06/29/18 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 27.72 |  | 0 | 0
995 | Payroll Burden | PR | 11 | 07/04/18 | 07/06/18 | BE45 | Belcher, Jacob T | 0 | 0 | 0 | 0 | 241.26 |  | 0 | 0
995 | Payroll Burden | PR | 19 | 07/04/18 | 07/06/18 | CR79 | Cruz Guzman, Joel A | 0 | 0 | 0 | 0 | 173.41 |  | 0 | 0
995 | Payroll Burden | PR | 20 | 07/04/18 | 07/06/18 | CR87 | Cruz Reyes, Jose | 0 | 0 | 0 | 0 | 340.61 |  | 0 | 0
995 | Payroll Burden | PR | 47 | 07/04/18 | 07/06/18 | LU09 | Lucas Tzintzun, Rafael | 0 | 0 | 0 | 0 | 241.26 |  | 0 | 0
995 | Payroll Burden | PR | 50 | 07/04/18 | 07/06/18 | ME52 | Mendoza, Edgar E | 0 | 0 | 0 | 0 | 224.41 |  | 0 | 0
995 | Payroll Burden | PR | 58 | 07/04/18 | 07/06/18 | RE18 | Reed, Reuben H | 0 | 0 | 0 | 0 | 581.87 |  | 0 | 0
995 | Payroll Burden | PR | 241 | 07/11/18 | 07/13/18 | BA70 | Barnhart, Joseph N | 0 | 0 | 0 | 0 | 40.8 |  | 0 | 0
995 | Payroll Burden | PR | 302 | 07/11/18 | 07/13/18 | BE45 | Belcher, Jacob T | 0 | 0 | 0 | 0 | 301.58 |  | 0 | 0
995 | Payroll Burden | PR | 310 | 07/11/18 | 07/13/18 | CR79 | Cruz Guzman, Joel A | 0 | 0 | 0 | 0 | 244.81 |  | 0 | 0
995 | Payroll Burden | PR | 311 | 07/11/18 | 07/13/18 | CR87 | Cruz Reyes, Jose | 0 | 0 | 0 | 0 | 425.76 |  | 0 | 0
995 | Payroll Burden | PR | 338 | 07/11/18 | 07/13/18 | LU09 | Lucas Tzintzun, Rafael | 0 | 0 | 0 | 0 | 301.58 |  | 0 | 0
995 | Payroll Burden | PR | 341 | 07/11/18 | 07/13/18 | ME52 | Mendoza, Edgar E | 0 | 0 | 0 | 0 | 390.28 |  | 0 | 0
995 | Payroll Burden | PR | 350 | 07/11/18 | 07/13/18 | RE18 | Reed, Reuben H | 0 | 0 | 0 | 0 | 581.87 |  | 0 | 0
995 | Payroll Burden | PR | 442 | 07/18/18 | 07/20/18 | BE45 | Belcher, Jacob T | 0 | 0 | 0 | 0 | 301.58 |  | 0 | 0
995 | Payroll Burden | PR | 450 | 07/18/18 | 07/20/18 | CR79 | Cruz Guzman, Joel A | 0 | 0 | 0 | 0 | 408.02 |  | 0 | 0
995 | Payroll Burden | PR | 451 | 07/18/18 | 07/20/18 | CR87 | Cruz Reyes, Jose | 0 | 0 | 0 | 0 | 425.76 |  | 0 | 0
995 | Payroll Burden | PR | 470 | 07/18/18 | 07/20/18 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 31.27 |  | 0 | 0
995 | Payroll Burden | PR | 479 | 07/18/18 | 07/20/18 | LU09 | Lucas Tzintzun, Rafael | 0 | 0 | 0 | 0 | 301.58 |  | 0 | 0
995 | Payroll Burden | PR | 482 | 07/18/18 | 07/20/18 | ME52 | Mendoza, Edgar E | 0 | 0 | 0 | 0 | 390.28 |  | 0 | 0
995 | Payroll Burden | PR | 490 | 07/18/18 | 07/20/18 | RE18 | Reed, Reuben H | 0 | 0 | 0 | 0 | 727.34 |  | 0 | 0
995 | Payroll Burden | PR | 768 | 07/25/18 | 07/27/18 | BE45 | Belcher, Jacob T | 0 | 0 | 0 | 0 | 120.63 |  | 0 | 0
995 | Payroll Burden | PR | 768 | 07/25/18 | 07/27/18 | BE45 | Belcher, Jacob T | 0 | 0 | 0 | 0 | 120.63 |  | 0 | 0
995 | Payroll Burden | PR | 776 | 07/25/18 | 07/27/18 | CR79 | Cruz Guzman, Joel A | 0 | 0 | 0 | 0 | 408.02 |  | 0 | 0
995 | Payroll Burden | PR | 777 | 07/25/18 | 07/27/18 | CR87 | Cruz Reyes, Jose | 0 | 0 | 0 | 0 | 298.03 |  | 0 | 0
995 | Payroll Burden | PR | 777 | 07/25/18 | 07/27/18 | CR87 | Cruz Reyes, Jose | 0 | 0 | 0 | 0 | 127.73 |  | 0 | 0
995 | Payroll Burden | PR | 806 | 07/25/18 | 07/27/18 | LU09 | Lucas Tzintzun, Rafael | 0 | 0 | 0 | 0 | 241.26 |  | 0 | 0
995 | Payroll Burden | PR | 806 | 07/25/18 | 07/27/18 | LU09 | Lucas Tzintzun, Rafael | 0 | 0 | 0 | 0 | 60.32 |  | 0 | 0
995 | Payroll Burden | PR | 809 | 07/25/18 | 07/27/18 | ME52 | Mendoza, Edgar E | 0 | 0 | 0 | 0 | 390.28 |  | 0 | 0
995 | Payroll Burden | PR | 817 | 07/25/18 | 07/27/18 | RE18 | Reed, Reuben H | 0 | 0 | 0 | 0 | 690.97 |  | 0 | 0
995 | Payroll Burden | PR | 7 | 08/01/18 | 08/03/18 | BE45 | Belcher, Jacob T | 0 | 0 | 0 | 0 | 120.63 |  | 0 | 0
995 | Payroll Burden | PR | 7 | 08/01/18 | 08/03/18 | BE45 | Belcher, Jacob T | 0 | 0 | 0 | 0 | 120.63 |  | 0 | 0
995 | Payroll Burden | PR | 15 | 08/01/18 | 08/03/18 | CR79 | Cruz Guzman, Joel A | 0 | 0 | 0 | 0 | 244.81 |  | 0 | 0
995 | Payroll Burden | PR | 15 | 08/01/18 | 08/03/18 | CR79 | Cruz Guzman, Joel A | 0 | 0 | 0 | 0 | 163.21 |  | 0 | 0
995 | Payroll Burden | PR | 16 | 08/01/18 | 08/03/18 | CR87 | Cruz Reyes, Jose | 0 | 0 | 0 | 0 | 255.46 |  | 0 | 0
995 | Payroll Burden | PR | 16 | 08/01/18 | 08/03/18 | CR87 | Cruz Reyes, Jose | 0 | 0 | 0 | 0 | 170.3 |  | 0 | 0
995 | Payroll Burden | PR | 44 | 08/01/18 | 08/03/18 | LU09 | Lucas Tzintzun, Rafael | 0 | 0 | 0 | 0 | 294.04 |  | 0 | 0
995 | Payroll Burden | PR | 47 | 08/01/18 | 08/03/18 | ME52 | Mendoza, Edgar E | 0 | 0 | 0 | 0 | 78.06 |  | 0 | 0
995 | Payroll Burden | PR | 55 | 08/01/18 | 08/03/18 | RE18 | Reed, Reuben H | 0 | 0 | 0 | 0 | 727.34 |  | 0 | 0
995 | Payroll Burden | PR | 216 | 08/08/18 | 08/10/18 | BA70 | Barnhart, Joseph N | 0 | 0 | 0 | 0 | 40.8 |  | 0 | 0
995 | Payroll Burden | PR | 217 | 08/08/18 | 08/10/18 | BE45 | Belcher, Jacob T | 0 | 0 | 0 | 0 | 301.58 |  | 0 | 0
995 | Payroll Burden | PR | 225 | 08/08/18 | 08/10/18 | CR79 | Cruz Guzman, Joel A | 0 | 0 | 0 | 0 | 326.42 |  | 0 | 0
995 | Payroll Burden | PR | 225 | 08/08/18 | 08/10/18 | CR79 | Cruz Guzman, Joel A | 0 | 0 | 0 | 0 | 81.6 |  | 0 | 0
995 | Payroll Burden | PR | 226 | 08/08/18 | 08/10/18 | CR87 | Cruz Reyes, Jose | 0 | 0 | 0 | 0 | 383.18 |  | 0 | 0
995 | Payroll Burden | PR | 226 | 08/08/18 | 08/10/18 | CR87 | Cruz Reyes, Jose | 0 | 0 | 0 | 0 | 42.58 |  | 0 | 0
995 | Payroll Burden | PR | 246 | 08/08/18 | 08/10/18 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 229.29 |  | 0 | 0
995 | Payroll Burden | PR | 246 | 08/08/18 | 08/10/18 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 41.69 |  | 0 | 0
995 | Payroll Burden | PR | 255 | 08/08/18 | 08/10/18 | LU09 | Lucas Tzintzun, Rafael | 0 | 0 | 0 | 0 | 180.95 |  | 0 | 0
995 | Payroll Burden | PR | 258 | 08/08/18 | 08/10/18 | ME52 | Mendoza, Edgar E | 0 | 0 | 0 | 0 | 219.53 |  | 0 | 0
995 | Payroll Burden | PR | 266 | 08/08/18 | 08/10/18 | RE18 | Reed, Reuben H | 0 | 0 | 0 | 0 | 290.94 |  | 0 | 0
995 | Payroll Burden | PR | 484 | 08/15/18 | 08/17/18 | BA70 | Barnhart, Joseph N | 0 | 0 | 0 | 0 | 20.4 |  | 0 | 0
995 | Payroll Burden | PR | 484 | 08/15/18 | 08/17/18 | BA70 | Barnhart, Joseph N | 0 | 0 | 0 | 0 | 20.4 |  | 0 | 0
995 | Payroll Burden | PR | 485 | 08/15/18 | 08/17/18 | BE45 | Belcher, Jacob T | 0 | 0 | 0 | 0 | 301.58 |  | 0 | 0
995 | Payroll Burden | PR | 493 | 08/15/18 | 08/17/18 | CR79 | Cruz Guzman, Joel A | 0 | 0 | 0 | 0 | 244.81 |  | 0 | 0
995 | Payroll Burden | PR | 493 | 08/15/18 | 08/17/18 | CR79 | Cruz Guzman, Joel A | 0 | 0 | 0 | 0 | 163.21 |  | 0 | 0
995 | Payroll Burden | PR | 494 | 08/15/18 | 08/17/18 | CR87 | Cruz Reyes, Jose | 0 | 0 | 0 | 0 | 340.61 |  | 0 | 0
995 | Payroll Burden | PR | 494 | 08/15/18 | 08/17/18 | CR87 | Cruz Reyes, Jose | 0 | 0 | 0 | 0 | 85.15 |  | 0 | 0
995 | Payroll Burden | PR | 514 | 08/15/18 | 08/17/18 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 41.69 |  | 0 | 0
995 | Payroll Burden | PR | 525 | 08/15/18 | 08/17/18 | ME52 | Mendoza, Edgar E | 0 | 0 | 0 | 0 | 390.28 |  | 0 | 0
995 | Payroll Burden | PR | 533 | 08/15/18 | 08/17/18 | RE18 | Reed, Reuben H | 0 | 0 | 0 | 0 | 436.4 |  | 0 | 0
995 | Payroll Burden | PR | 550 | 08/15/18 | 08/17/18 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 194.03 |  | 0 | 0
995 | Payroll Burden | PR | 747 | 08/22/18 | 08/24/18 | BE45 | Belcher, Jacob T | 0 | 0 | 0 | 0 | 301.58 |  | 0 | 0
995 | Payroll Burden | PR | 755 | 08/22/18 | 08/24/18 | CR79 | Cruz Guzman, Joel A | 0 | 0 | 0 | 0 | 408.02 |  | 0 | 0
995 | Payroll Burden | PR | 756 | 08/22/18 | 08/24/18 | CR87 | Cruz Reyes, Jose | 0 | 0 | 0 | 0 | 425.76 |  | 0 | 0
995 | Payroll Burden | PR | 786 | 08/22/18 | 08/24/18 | ME52 | Mendoza, Edgar E | 0 | 0 | 0 | 0 | 195.14 |  | 0 | 0
995 | Payroll Burden | PR | 794 | 08/22/18 | 08/24/18 | RE18 | Reed, Reuben H | 0 | 0 | 0 | 0 | 690.97 |  | 0 | 0
995 | Payroll Burden | PR | 811 | 08/22/18 | 08/24/18 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 27.72 |  | 0 | 0
995 | Payroll Burden | PR | 1000 | 08/29/18 | 08/31/18 | BA70 | Barnhart, Joseph N | 0 | 0 | 0 | 0 | 20.4 |  | 0 | 0
995 | Payroll Burden | PR | 1009 | 08/29/18 | 08/31/18 | CR79 | Cruz Guzman, Joel A | 0 | 0 | 0 | 0 | 408.02 |  | 0 | 0
995 | Payroll Burden | PR | 1010 | 08/29/18 | 08/31/18 | CR87 | Cruz Reyes, Jose | 0 | 0 | 0 | 0 | 425.76 |  | 0 | 0
995 | Payroll Burden | PR | 1040 | 08/29/18 | 08/31/18 | ME52 | Mendoza, Edgar E | 0 | 0 | 0 | 0 | 78.06 |  | 0 | 0
995 | Payroll Burden | PR | 1048 | 08/29/18 | 08/31/18 | RE18 | Reed, Reuben H | 0 | 0 | 0 | 0 | 581.87 |  | 0 | 0
995 | Payroll Burden | PR | 1070 | 08/29/18 | 08/31/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 22.18 |  | 0 | 0
995 | Payroll Burden | PR | 50 | 09/05/18 | 09/07/18 | CR79 | Cruz Guzman, Joel A | 0 | 0 | 0 | 0 | 163.21 |  | 0 | 0
995 | Payroll Burden | PR | 51 | 09/05/18 | 09/07/18 | CR87 | Cruz Reyes, Jose | 0 | 0 | 0 | 0 | 170.3 |  | 0 | 0
995 | Payroll Burden | PR | 88 | 09/05/18 | 09/07/18 | RE18 | Reed, Reuben H | 0 | 0 | 0 | 0 | 290.94 |  | 0 | 0
995 | Payroll Burden | PR | 105 | 09/05/18 | 09/07/18 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 27.72 |  | 0 | 0
995 | Payroll Burden | PR | 281 | 09/12/18 | 09/14/18 | CR79 | Cruz Guzman, Joel A | 0 | 0 | 0 | 0 | 408.02 |  | 0 | 0
995 | Payroll Burden | PR | 282 | 09/12/18 | 09/14/18 | CR87 | Cruz Reyes, Jose | 0 | 0 | 0 | 0 | 425.76 |  | 0 | 0
995 | Payroll Burden | PR | 302 | 09/12/18 | 09/14/18 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 41.69 |  | 0 | 0
995 | Payroll Burden | PR | 320 | 09/12/18 | 09/14/18 | RE18 | Reed, Reuben H | 0 | 0 | 0 | 0 | 581.87 |  | 0 | 0
995 | Payroll Burden | PR | 494 | 09/19/18 | 09/21/18 | CR79 | Cruz Guzman, Joel A | 0 | 0 | 0 | 0 | 326.42 |  | 0 | 0
995 | Payroll Burden | PR | 495 | 09/19/18 | 09/21/18 | CR87 | Cruz Reyes, Jose | 0 | 0 | 0 | 0 | 425.76 |  | 0 | 0
995 | Payroll Burden | PR | 515 | 09/19/18 | 09/21/18 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 41.69 |  | 0 | 0
995 | Payroll Burden | PR | 533 | 09/19/18 | 09/21/18 | RE18 | Reed, Reuben H | 0 | 0 | 0 | 0 | 709.16 |  | 0 | 0
995 | Payroll Burden | PR | 700 | 09/26/18 | 09/28/18 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 41.69 |  | 0 | 0
995 | Payroll Burden | PR | 718 | 09/26/18 | 09/28/18 | RE18 | Reed, Reuben H | 0 | 0 | 0 | 0 | 636.42 |  | 0 | 0
995 | Payroll Burden | PR | 728 | 09/26/18 | 09/28/18 | SI48 | Silva Morales, Jair J | 0 | 0 | 0 | 0 | 393.83 |  | 0 | 0
995 | Payroll Burden | PR | 739 | 09/26/18 | 09/28/18 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 27.72 |  | 0 | 0
995 | Payroll Burden | PR | 64 | 10/03/18 | 10/05/18 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 62.53 |  | 0 | 0
995 | Payroll Burden | PR | 82 | 10/03/18 | 10/05/18 | RE18 | Reed, Reuben H | 0 | 0 | 0 | 0 | 727.34 |  | 0 | 0
995 | Payroll Burden | PR | 89 | 10/03/18 | 10/05/18 | SA54 | Sanders, Allen O | 0 | 0 | 0 | 0 | 39.03 |  | 0 | 0
995 | Payroll Burden | PR | 92 | 10/03/18 | 10/05/18 | SI48 | Silva Morales, Jair J | 0 | 0 | 0 | 0 | 170.3 |  | 0 | 0
995 | Payroll Burden | PR | 102 | 10/03/18 | 10/05/18 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 27.72 |  | 0 | 0
995 | Payroll Burden | PR | 270 | 10/10/18 | 10/12/18 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 41.69 |  | 0 | 0
995 | Payroll Burden | PR | 288 | 10/10/18 | 10/12/18 | RE18 | Reed, Reuben H | 0 | 0 | 0 | 0 | 545.51 |  | 0 | 0
995 | Payroll Burden | PR | 288 | 10/10/18 | 10/12/18 | RE18 | Reed, Reuben H | 0 | 0 | 0 | 0 | 127.28 |  | 0 | 0
995 | Payroll Burden | PR | 468 | 10/17/18 | 10/19/18 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 145.91 |  | 0 | 0
995 | Payroll Burden | PR | 486 | 10/17/18 | 10/19/18 | RE18 | Reed, Reuben H | 0 | 0 | 0 | 0 | 545.51 |  | 0 | 0
995 | Payroll Burden | PR | 493 | 10/17/18 | 10/19/18 | SA54 | Sanders, Allen O | 0 | 0 | 0 | 0 | 29.27 |  | 0 | 0
995 | Payroll Burden | PR | 507 | 10/17/18 | 10/19/18 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 83.16 |  | 0 | 0
995 | Payroll Burden | PR | 687 | 10/24/18 | 10/25/18 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 41.69 |  | 0 | 0
995 | Payroll Burden | PR | 751 | 10/24/18 | 10/26/18 | RE18 | Reed, Reuben H | 0 | 0 | 0 | 0 | 127.28 |  | 0 | 0
995 | Payroll Burden | PR | 751 | 10/24/18 | 10/26/18 | RE18 | Reed, Reuben H | 0 | 0 | 0 | 0 | 163.65 |  | 0 | 0
995 | Payroll Burden | PR | 39 | 10/31/18 | 11/02/18 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 41.69 |  | 0 | 0
995 | Payroll Burden | PR | 55 | 10/31/18 | 11/02/18 | RE18 | Reed, Reuben H | 0 | 0 | 0 | 0 | 290.94 |  | 0 | 0
995 | Payroll Burden | PR | 55 | 10/31/18 | 11/02/18 | RE18 | Reed, Reuben H | 0 | 0 | 0 | 0 | 36.37 |  | 0 | 0
995 | Payroll Burden | PR | 55 | 10/31/18 | 11/02/18 | RE18 | Reed, Reuben H | 0 | 0 | 0 | 0 | 36.37 |  | 0 | 0
995 | Payroll Burden | PR | 62 | 10/31/18 | 11/02/18 | SA54 | Sanders, Allen O | 0 | 0 | 0 | 0 | 39.03 |  | 0 | 0
995 | Payroll Burden | PR | 217 | 11/07/18 | 11/09/18 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 208.45 |  | 0 | 0
995 | Payroll Burden | PR | 234 | 11/07/18 | 11/09/18 | RE18 | Reed, Reuben H | 0 | 0 | 0 | 0 | 381.85 |  | 0 | 0
995 | Payroll Burden | PR | 234 | 11/07/18 | 11/09/18 | RE18 | Reed, Reuben H | 0 | 0 | 0 | 0 | 200.02 |  | 0 | 0
995 | Payroll Burden | PR | 257 | 11/07/18 | 11/09/18 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 27.72 |  | 0 | 0
995 | Payroll Burden | PR | 465 | 11/14/18 | 11/16/18 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 208.45 |  | 0 | 0
995 | Payroll Burden | PR | 482 | 11/14/18 | 11/16/18 | RE18 | Reed, Reuben H | 0 | 0 | 0 | 0 | 254.57 |  | 0 | 0
995 | Payroll Burden | PR | 504 | 11/14/18 | 11/16/18 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | -208.45 |  | 0 | 0
995 | Payroll Burden | PR | 508 | 11/14/18 | 11/16/18 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 208.45 |  | 0 | 0
995 | Payroll Burden | PR | 621 | 11/21/18 | 11/21/18 | BA70 | Barnhart, Joseph N | 0 | 0 | 0 | 0 | 163.21 |  | 0 | 0
995 | Payroll Burden | PR | 863 | 11/28/18 | 11/30/18 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 43.46 |  | 0 | 0
995 | Payroll Burden | PR | 879 | 11/28/18 | 11/30/18 | RE18 | Reed, Reuben H | 0 | 0 | 0 | 0 | 95.35 |  | 0 | 0
995 | Payroll Burden | PR | 879 | 11/28/18 | 11/30/18 | RE18 | Reed, Reuben H | 0 | 0 | 0 | 0 | 209.78 |  | 0 | 0
995 | Payroll Burden | PR | 63 | 12/05/18 | 12/07/18 | FO55 | Fonseca Teruel, Eduardo | 0 | 0 | 0 | 0 | 5.99 |  | 0 | 0
995 | Payroll Burden | PR | 63 | 12/05/18 | 12/07/18 | FO55 | Fonseca Teruel, Eduardo | 0 | 0 | 0 | 0 | 63.86 |  | 0 | 0
995 | Payroll Burden | PR | 69 | 12/05/18 | 12/07/18 | GO51 | Gomez Reyes, Edith N | 0 | 0 | 0 | 0 | 7.65 |  | 0 | 0
995 | Payroll Burden | PR | 69 | 12/05/18 | 12/07/18 | GO51 | Gomez Reyes, Edith N | 0 | 0 | 0 | 0 | 81.6 |  | 0 | 0
995 | Payroll Burden | PR | 91 | 12/05/18 | 12/07/18 | RE18 | Reed, Reuben H | 0 | 0 | 0 | 0 | 152.56 |  | 0 | 0
995 | Payroll Burden | PR | 91 | 12/05/18 | 12/07/18 | RE18 | Reed, Reuben H | 0 | 0 | 0 | 0 | 76.28 |  | 0 | 0
995 | Payroll Burden | PR | 92 | 12/05/18 | 12/07/18 | RE91 | Reyes, Maria E | 0 | 0 | 0 | 0 | 5.99 |  | 0 | 0
995 | Payroll Burden | PR | 92 | 12/05/18 | 12/07/18 | RE91 | Reyes, Maria E | 0 | 0 | 0 | 0 | 63.86 |  | 0 | 0
995 | Payroll Burden | PR | 99 | 12/05/18 | 12/07/18 | SA54 | Sanders, Allen O | 0 | 0 | 0 | 0 | 125.07 |  | 0 | 0
995 | Payroll Burden | PR | 113 | 12/05/18 | 12/07/18 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 55.44 |  | 0 | 0
995 | Payroll Burden | PR | 316 | 12/12/18 | 12/14/18 | RE18 | Reed, Reuben H | 0 | 0 | 0 | 0 | 95.35 |  | 0 | 0
995 | Payroll Burden | PR | 316 | 12/12/18 | 12/14/18 | RE18 | Reed, Reuben H | 0 | 0 | 0 | 0 | 57.21 |  | 0 | 0
995 | Payroll Burden | PR | 324 | 12/12/18 | 12/14/18 | SA54 | Sanders, Allen O | 0 | 0 | 0 | 0 | 41.69 |  | 0 | 0
995 | Payroll Burden | PR | 337 | 12/12/18 | 12/14/18 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 55.44 |  | 0 | 0
995 | Payroll Burden | PR | 517 | 12/19/18 | 12/21/18 | CO71 | Cortes Mendiola, Victor H | 0 | 0 | 0 | 0 | 152.56 |  | 0 | 0
995 | Payroll Burden | PR | 528 | 12/19/18 | 12/21/18 | FO55 | Fonseca Teruel, Eduardo | 0 | 0 | 0 | 0 | 63.86 |  | 0 | 0
995 | Payroll Burden | PR | 534 | 12/19/18 | 12/21/18 | GO51 | Gomez Reyes, Edith N | 0 | 0 | 0 | 0 | 244.81 |  | 0 | 0
995 | Payroll Burden | PR | 557 | 12/19/18 | 12/21/18 | RE91 | Reyes, Maria E | 0 | 0 | 0 | 0 | 23.95 |  | 0 | 0
995 | Payroll Burden | PR | 557 | 12/19/18 | 12/21/18 | RE91 | Reyes, Maria E | 0 | 0 | 0 | 0 | 255.46 |  | 0 | 0
995 | Payroll Burden | PR | 564 | 12/19/18 | 12/21/18 | SA54 | Sanders, Allen O | 0 | 0 | 0 | 0 | 62.53 |  | 0 | 0
995 | Payroll Burden | PR | 564 | 12/19/18 | 12/21/18 | SA54 | Sanders, Allen O | 0 | 0 | 0 | 0 | 333.51 |  | 0 | 0
995 | Payroll Burden | PR | 571 | 12/19/18 | 12/21/18 | TR60 | Trower-Kelly, Fidel D | 0 | 0 | 0 | 0 | 31.93 |  | 0 | 0
995 | Payroll Burden | PR | 571 | 12/19/18 | 12/21/18 | TR60 | Trower-Kelly, Fidel D | 0 | 0 | 0 | 0 | 113.54 |  | 0 | 0
995 | Payroll Burden | PR | 577 | 12/19/18 | 12/21/18 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 110.88 |  | 0 | 0
995 | Payroll Burden | PR | 708 | 12/26/18 | 12/28/18 | CO71 | Cortes Mendiola, Victor H | 0 | 0 | 0 | 0 | -152.56 |  | 0 | 0
995 | Payroll Burden | PR | 724 | 12/26/18 | 12/28/18 | GO51 | Gomez Reyes, Edith N | 0 | 0 | 0 | 0 | 81.6 |  | 0 | 0
995 | Payroll Burden | PR | 731 | 12/26/18 | 12/28/18 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 108.66 |  | 0 | 0
995 | Payroll Burden | PR | 748 | 12/26/18 | 12/28/18 | RE91 | Reyes, Maria E | 0 | 0 | 0 | 0 | 207.56 |  | 0 | 0
995 | Payroll Burden | PR | 755 | 12/26/18 | 12/28/18 | SA54 | Sanders, Allen O | 0 | 0 | 0 | 0 | 83.38 |  | 0 | 0
995 | Payroll Burden | PR | 776 | 12/26/18 | 12/28/18 | RE91 | Reyes, Maria E | 0 | 0 | 0 | 0 | 255.46 |  | 0 | 0
995 | Payroll Burden | PR | 776 | 12/26/18 | 12/28/18 | RE91 | Reyes, Maria E | 0 | 0 | 0 | 0 | -255.46 |  | 0 | 0
995 | Payroll Burden | PR | 29 | 01/02/19 | 01/04/19 | GO51 | Gomez Reyes, Edith N | 0 | 0 | 0 | 0 | 81.6 |  | 0 | 0
995 | Payroll Burden | PR | 35 | 01/02/19 | 01/04/19 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 173.85 |  | 0 | 0
995 | Payroll Burden | PR | 51 | 01/02/19 | 01/04/19 | RE91 | Reyes, Maria E | 0 | 0 | 0 | 0 | 63.86 |  | 0 | 0
995 | Payroll Burden | PR | 58 | 01/02/19 | 01/04/19 | SA54 | Sanders, Allen O | 0 | 0 | 0 | 0 | 41.69 |  | 0 | 0
995 | Payroll Burden | PR | 237 | 01/09/19 | 01/11/19 | GO51 | Gomez Reyes, Edith N | 0 | 0 | 0 | 0 | 15.3 |  | 0 | 0
995 | Payroll Burden | PR | 237 | 01/09/19 | 01/11/19 | GO51 | Gomez Reyes, Edith N | 0 | 0 | 0 | 0 | 244.81 |  | 0 | 0
995 | Payroll Burden | PR | 244 | 01/09/19 | 01/11/19 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 260.78 |  | 0 | 0
995 | Payroll Burden | PR | 252 | 01/09/19 | 01/11/19 | MC09 | McCabe, Thomas C | 0 | 0 | 0 | 0 | 263.44 |  | 0 | 0
995 | Payroll Burden | PR | 252 | 01/09/19 | 01/11/19 | MC09 | McCabe, Thomas C | 0 | 0 | 0 | 0 | 58.54 |  | 0 | 0
995 | Payroll Burden | PR | 260 | 01/09/19 | 01/11/19 | RE18 | Reed, Reuben H | 0 | 0 | 0 | 0 | 19.07 |  | 0 | 0
995 | Payroll Burden | PR | 261 | 01/09/19 | 01/11/19 | RE91 | Reyes, Maria E | 0 | 0 | 0 | 0 | 11.97 |  | 0 | 0
995 | Payroll Burden | PR | 261 | 01/09/19 | 01/11/19 | RE91 | Reyes, Maria E | 0 | 0 | 0 | 0 | 191.59 |  | 0 | 0
995 | Payroll Burden | PR | 268 | 01/09/19 | 01/11/19 | SA54 | Sanders, Allen O | 0 | 0 | 0 | 0 | 187.6 |  | 0 | 0
995 | Payroll Burden | PR | 492 | 01/16/19 | 01/18/19 | GO51 | Gomez Reyes, Edith N | 0 | 0 | 0 | 0 | 45.9 |  | 0 | 0
995 | Payroll Burden | PR | 492 | 01/16/19 | 01/18/19 | GO51 | Gomez Reyes, Edith N | 0 | 0 | 0 | 0 | 326.42 |  | 0 | 0
995 | Payroll Burden | PR | 499 | 01/16/19 | 01/18/19 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 65.19 |  | 0 | 0
995 | Payroll Burden | PR | 507 | 01/16/19 | 01/18/19 | MC09 | McCabe, Thomas C | 0 | 0 | 0 | 0 | 175.63 |  | 0 | 0
995 | Payroll Burden | PR | 507 | 01/16/19 | 01/18/19 | MC09 | McCabe, Thomas C | 0 | 0 | 0 | 0 | 58.54 |  | 0 | 0
995 | Payroll Burden | PR | 516 | 01/16/19 | 01/18/19 | RE91 | Reyes, Maria E | 0 | 0 | 0 | 0 | 35.92 |  | 0 | 0
995 | Payroll Burden | PR | 516 | 01/16/19 | 01/18/19 | RE91 | Reyes, Maria E | 0 | 0 | 0 | 0 | 255.46 |  | 0 | 0
995 | Payroll Burden | PR | 523 | 01/16/19 | 01/18/19 | SA54 | Sanders, Allen O | 0 | 0 | 0 | 0 | 20.84 |  | 0 | 0
995 | Payroll Burden | PR | 524 | 01/16/19 | 01/18/19 | SE64 | Sepulveda Gonzalez, Alfredo | 0 | 0 | 0 | 0 | 56.77 |  | 0 | 0
995 | Payroll Burden | PR | 524 | 01/16/19 | 01/18/19 | SE64 | Sepulveda Gonzalez, Alfredo | 0 | 0 | 0 | 0 | 56.77 |  | 0 | 0
995 | Payroll Burden | PR | 735 | 01/23/19 | 01/25/19 | FO55 | Fonseca Teruel, Eduardo | 0 | 0 | 0 | 0 | 63.86 |  | 0 | 0
995 | Payroll Burden | PR | 739 | 01/23/19 | 01/25/19 | GE70 | Gerard, Jordan E | 0 | 0 | 0 | 0 | 120.63 |  | 0 | 0
995 | Payroll Burden | PR | 741 | 01/23/19 | 01/25/19 | GO51 | Gomez Reyes, Edith N | 0 | 0 | 0 | 0 | 30.6 |  | 0 | 0
995 | Payroll Burden | PR | 741 | 01/23/19 | 01/25/19 | GO51 | Gomez Reyes, Edith N | 0 | 0 | 0 | 0 | 265.21 |  | 0 | 0
995 | Payroll Burden | PR | 748 | 01/23/19 | 01/25/19 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 152.12 |  | 0 | 0
995 | Payroll Burden | PR | 765 | 01/23/19 | 01/25/19 | RE91 | Reyes, Maria E | 0 | 0 | 0 | 0 | 23.95 |  | 0 | 0
995 | Payroll Burden | PR | 765 | 01/23/19 | 01/25/19 | RE91 | Reyes, Maria E | 0 | 0 | 0 | 0 | 191.59 |  | 0 | 0
995 | Payroll Burden | PR | 772 | 01/23/19 | 01/25/19 | SA54 | Sanders, Allen O | 0 | 0 | 0 | 0 | 15.63 |  | 0 | 0
995 | Payroll Burden | PR | 772 | 01/23/19 | 01/25/19 | SA54 | Sanders, Allen O | 0 | 0 | 0 | 0 | 218.87 |  | 0 | 0
995 | Payroll Burden | PR | 773 | 01/23/19 | 01/25/19 | SE64 | Sepulveda Gonzalez, Alfredo | 0 | 0 | 0 | 0 | 28.38 |  | 0 | 0
995 | Payroll Burden | PR | 773 | 01/23/19 | 01/25/19 | SE64 | Sepulveda Gonzalez, Alfredo | 0 | 0 | 0 | 0 | 42.58 |  | 0 | 0
995 | Payroll Burden | PR | 776 | 01/23/19 | 01/25/19 | ST02 | Stahlschmidt, John P | 0 | 0 | 0 | 0 | 60.32 |  | 0 | 0
995 | Payroll Burden | PR | 29 | 01/30/19 | 02/01/19 | GO51 | Gomez Reyes, Edith N | 0 | 0 | 0 | 0 | 30.6 |  | 0 | 0
995 | Payroll Burden | PR | 29 | 01/30/19 | 02/01/19 | GO51 | Gomez Reyes, Edith N | 0 | 0 | 0 | 0 | 244.81 |  | 0 | 0
995 | Payroll Burden | PR | 36 | 01/30/19 | 02/01/19 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 97.79 |  | 0 | 0
995 | Payroll Burden | PR | 44 | 01/30/19 | 02/01/19 | MC09 | McCabe, Thomas C | 0 | 0 | 0 | 0 | 58.54 |  | 0 | 0
995 | Payroll Burden | PR | 44 | 01/30/19 | 02/01/19 | MC09 | McCabe, Thomas C | 0 | 0 | 0 | 0 | 175.63 |  | 0 | 0
995 | Payroll Burden | PR | 51 | 01/30/19 | 02/01/19 | RE91 | Reyes, Maria E | 0 | 0 | 0 | 0 | 23.95 |  | 0 | 0
995 | Payroll Burden | PR | 51 | 01/30/19 | 02/01/19 | RE91 | Reyes, Maria E | 0 | 0 | 0 | 0 | 191.59 |  | 0 | 0
995 | Payroll Burden | PR | 57 | 01/30/19 | 02/01/19 | SA54 | Sanders, Allen O | 0 | 0 | 0 | 0 | 83.38 |  | 0 | 0
995 | Payroll Burden | PR | 58 | 01/30/19 | 02/01/19 | SE64 | Sepulveda Gonzalez, Alfredo | 0 | 0 | 0 | 0 | 56.77 |  | 0 | 0
995 | Payroll Burden | PR | 58 | 01/30/19 | 02/01/19 | SE64 | Sepulveda Gonzalez, Alfredo | 0 | 0 | 0 | 0 | 28.38 |  | 0 | 0
995 | Payroll Burden | PR | 70 | 01/30/19 | 02/01/19 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 55.44 |  | 0 | 0
995 | Payroll Burden | PR | 184 | 02/06/19 | 02/08/19 | GO51 | Gomez Reyes, Edith N | 0 | 0 | 0 | 0 | 163.21 |  | 0 | 0
995 | Payroll Burden | PR | 206 | 02/06/19 | 02/08/19 | RE91 | Reyes, Maria E | 0 | 0 | 0 | 0 | 127.73 |  | 0 | 0
995 | Payroll Burden | PR | 213 | 02/06/19 | 02/08/19 | SA54 | Sanders, Allen O | 0 | 0 | 0 | 0 | 62.53 |  | 0 | 0
995 | Payroll Burden | PR | 226 | 02/06/19 | 02/08/19 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 27.72 |  | 0 | 0
995 | Payroll Burden | PR | 346 | 02/13/19 | 02/15/19 | GO51 | Gomez Reyes, Edith N | 0 | 0 | 0 | 0 | 142.81 |  | 0 | 0
995 | Payroll Burden | PR | 375 | 02/13/19 | 02/15/19 | SA54 | Sanders, Allen O | 0 | 0 | 0 | 0 | 10.42 |  | 0 | 0
995 | Payroll Burden | PR | 388 | 02/13/19 | 02/15/19 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 27.72 |  | 0 | 0
995 | Payroll Burden | PR | 401 | 02/13/19 | 02/15/19 | RE91 | Reyes, Maria E | 0 | 0 | 0 | 0 | 111.76 |  | 0 | 0
995 | Payroll Burden | PR | 596 | 02/20/19 | 02/22/19 | EL33 | Eliassen, Cory H | 0 | 0 | 0 | 0 | 33.26 |  | 0 | 0
995 | Payroll Burden | PR | 634 | 02/20/19 | 02/22/19 | SA54 | Sanders, Allen O | 0 | 0 | 0 | 0 | 62.53 |  | 0 | 0
995 | Payroll Burden | PR | 641 | 02/20/19 | 02/22/19 | TR60 | Trower-Kelly, Fidel D | 0 | 0 | 0 | 0 | 78.06 |  | 0 | 0
995 | Payroll Burden | PR | 647 | 02/20/19 | 02/22/19 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 55.44 |  | 0 | 0
995 | Payroll Burden | PR | 22 | 02/27/19 | 03/01/19 | EL33 | Eliassen, Cory H | 0 | 0 | 0 | 0 | 60.98 |  | 0 | 0
995 | Payroll Burden | PR | 38 | 02/27/19 | 03/01/19 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 260.78 |  | 0 | 0
995 | Payroll Burden | PR | 61 | 02/27/19 | 03/01/19 | SA54 | Sanders, Allen O | 0 | 0 | 0 | 0 | 15.63 |  | 0 | 0
995 | Payroll Burden | PR | 61 | 02/27/19 | 03/01/19 | SA54 | Sanders, Allen O | 0 | 0 | 0 | 0 | 52.11 |  | 0 | 0
995 | Payroll Burden | PR | 68 | 02/27/19 | 03/01/19 | TR60 | Trower-Kelly, Fidel D | 0 | 0 | 0 | 0 | 17.74 |  | 0 | 0
995 | Payroll Burden | PR | 264 | 03/06/19 | 03/08/19 | EL33 | Eliassen, Cory H | 0 | 0 | 0 | 0 | 110.88 |  | 0 | 0
995 | Payroll Burden | PR | 293 | 03/06/19 | 03/08/19 | RE18 | Reed, Reuben H | 0 | 0 | 0 | 0 | 76.28 |  | 0 | 0
995 | Payroll Burden | PR | 307 | 03/06/19 | 03/08/19 | TR60 | Trower-Kelly, Fidel D | 0 | 0 | 0 | 0 | 35.48 |  | 0 | 0
995 | Payroll Burden | PR | 314 | 03/06/19 | 03/08/19 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 27.72 |  | 0 | 0
995 | Payroll Burden | PR | 511 | 03/13/19 | 03/15/19 | EL33 | Eliassen, Cory H | 0 | 0 | 0 | 0 | 33.26 |  | 0 | 0
995 | Payroll Burden | PR | 511 | 03/13/19 | 03/15/19 | EL33 | Eliassen, Cory H | 0 | 0 | 0 | 0 | 77.61 |  | 0 | 0
995 | Payroll Burden | PR | 525 | 03/13/19 | 03/15/19 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 108.66 |  | 0 | 0
995 | Payroll Burden | PR | 533 | 03/13/19 | 03/15/19 | MC09 | McCabe, Thomas C | 0 | 0 | 0 | 0 | 58.54 |  | 0 | 0
995 | Payroll Burden | PR | 547 | 03/13/19 | 03/15/19 | SA54 | Sanders, Allen O | 0 | 0 | 0 | 0 | 145.91 |  | 0 | 0
995 | Payroll Burden | PR | 555 | 03/13/19 | 03/15/19 | TR60 | Trower-Kelly, Fidel D | 0 | 0 | 0 | 0 | 21.29 |  | 0 | 0
995 | Payroll Burden | PR | 555 | 03/13/19 | 03/15/19 | TR60 | Trower-Kelly, Fidel D | 0 | 0 | 0 | 0 | 28.38 |  | 0 | 0
995 | Payroll Burden | PR | 562 | 03/13/19 | 03/15/19 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 27.72 |  | 0 | 0
995 | Payroll Burden | PR | 725 | 03/20/19 | 03/22/19 | EL33 | Eliassen, Cory H | 0 | 0 | 0 | 0 | 44.35 |  | 0 | 0
995 | Payroll Burden | PR | 731 | 03/20/19 | 03/22/19 | GE70 | Gerard, Jordan E | 0 | 0 | 0 | 0 | 75.4 |  | 0 | 0
995 | Payroll Burden | PR | 760 | 03/20/19 | 03/22/19 | SA54 | Sanders, Allen O | 0 | 0 | 0 | 0 | 208.45 |  | 0 | 0
995 | Payroll Burden | PR | 776 | 03/20/19 | 03/22/19 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 83.16 |  | 0 | 0
995 | Payroll Burden | PR | 777 | 03/20/19 | 03/22/19 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 23.06 |  | 0 | 0
995 | Payroll Burden | PR | 989 | 03/27/19 | 03/29/19 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 83.16 |  | 0 | 0
995 | Payroll Burden | PR | 114 | 04/03/19 | 04/05/19 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 32.6 |  | 0 | 0
995 | Payroll Burden | PR | 114 | 04/03/19 | 04/05/19 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 21.73 |  | 0 | 0
995 | Payroll Burden | PR | 132 | 04/03/19 | 04/05/19 | RO06 | Roberts, Lake A | 0 | 0 | 0 | 0 | 23.95 |  | 0 | 0
995 | Payroll Burden | PR | 132 | 04/03/19 | 04/05/19 | RO06 | Roberts, Lake A | 0 | 0 | 0 | 0 | 31.93 |  | 0 | 0
995 | Payroll Burden | PR | 135 | 04/03/19 | 04/05/19 | SA54 | Sanders, Allen O | 0 | 0 | 0 | 0 | 171.97 |  | 0 | 0
995 | Payroll Burden | PR | 135 | 04/03/19 | 04/05/19 | SA54 | Sanders, Allen O | 0 | 0 | 0 | 0 | 20.84 |  | 0 | 0
995 | Payroll Burden | PR | 151 | 04/03/19 | 04/05/19 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 83.16 |  | 0 | 0
995 | Payroll Burden | PR | 372 | 04/10/19 | 04/12/19 | RE18 | Reed, Reuben H | 0 | 0 | 0 | 0 | 139.7 |  | 0 | 0
995 | Payroll Burden | PR | 379 | 04/10/19 | 04/12/19 | SA54 | Sanders, Allen O | 0 | 0 | 0 | 0 | 217.32 |  | 0 | 0
995 | Payroll Burden | PR | 578 | 04/17/19 | 04/19/19 | SA54 | Sanders, Allen O | 0 | 0 | 0 | 0 | 32.6 |  | 0 | 0
995 | Payroll Burden | PR | 586 | 04/17/19 | 04/19/19 | TR60 | Trower-Kelly, Fidel D | 0 | 0 | 0 | 0 | 10.64 |  | 0 | 0
995 | Payroll Burden | PR | 797 | 04/24/19 | 04/26/19 | SA54 | Sanders, Allen O | 0 | 0 | 0 | 0 | 21.73 |  | 0 | 0
995 | Payroll Burden | PR | 66 | 05/01/19 | 05/03/19 | SA54 | Sanders, Allen O | 0 | 0 | 0 | 0 | 21.73 |  | 0 | 0
995 | Payroll Burden | PR | 81 | 05/01/19 | 05/03/19 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 27.72 |  | 0 | 0
995 | Payroll Burden | PR | 164 | 05/08/19 | 05/10/19 | BA70 | Barnhart, Joseph N | 0 | 0 | 0 | 0 | 22.18 |  | 0 | 0
995 | Payroll Burden | PR | 219 | 05/08/19 | 05/10/19 | SA54 | Sanders, Allen O | 0 | 0 | 0 | 0 | 43.46 |  | 0 | 0
995 | Payroll Burden | PR | 952 | 05/29/19 | 05/31/19 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 55.44 |  | 0 | 0
998 | Payroll Taxes | PR | 184 | 09/06/17 | 09/08/17 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 3.83 |  | 0 | 0
998 | Payroll Taxes | PR | 534 | 09/20/17 | 09/22/17 | SA54 | Sanders, Allen O | 0 | 0 | 0 | 0 | 4.59 |  | 0 | 0
998 | Payroll Taxes | PR | 761 | 09/27/17 | 09/29/17 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 3.83 |  | 0 | 0
998 | Payroll Taxes | PR | 762 | 09/27/17 | 09/29/17 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 10.79 |  | 0 | 0
998 | Payroll Taxes | PR | 67 | 10/04/17 | 10/06/17 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 3.83 |  | 0 | 0
998 | Payroll Taxes | PR | 67 | 10/04/17 | 10/06/17 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 15.3 |  | 0 | 0
998 | Payroll Taxes | PR | 68 | 10/04/17 | 10/06/17 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 3.6 |  | 0 | 0
998 | Payroll Taxes | PR | 225 | 10/11/17 | 10/13/17 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 34.43 |  | 0 | 0
998 | Payroll Taxes | PR | 350 | 10/18/17 | 10/20/17 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 3.83 |  | 0 | 0
998 | Payroll Taxes | PR | 488 | 10/25/17 | 10/27/17 | BA70 | Barnhart, Joseph N | 0 | 0 | 0 | 0 | 3.37 |  | 0 | 0
998 | Payroll Taxes | PR | 547 | 10/25/17 | 10/27/17 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 7.65 |  | 0 | 0
998 | Payroll Taxes | PR | 548 | 10/25/17 | 10/27/17 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 7.19 |  | 0 | 0
998 | Payroll Taxes | PR | 548 | 10/25/17 | 10/27/17 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 7.19 |  | 0 | 0
998 | Payroll Taxes | PR | 7 | 11/01/17 | 11/03/17 | BA70 | Barnhart, Joseph N | 0 | 0 | 0 | 0 | 3.37 |  | 0 | 0
998 | Payroll Taxes | PR | 67 | 11/01/17 | 11/03/17 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 26.78 |  | 0 | 0
998 | Payroll Taxes | PR | 68 | 11/01/17 | 11/03/17 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 3.6 |  | 0 | 0
998 | Payroll Taxes | PR | 68 | 11/01/17 | 11/03/17 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 3.6 |  | 0 | 0
998 | Payroll Taxes | PR | 154 | 11/08/17 | 11/10/17 | BA70 | Barnhart, Joseph N | 0 | 0 | 0 | 0 | 3.37 |  | 0 | 0
998 | Payroll Taxes | PR | 343 | 11/15/17 | 11/17/17 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 7.65 |  | 0 | 0
998 | Payroll Taxes | PR | 344 | 11/15/17 | 11/17/17 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 3.6 |  | 0 | 0
998 | Payroll Taxes | PR | 430 | 11/22/17 | 11/22/17 | BA70 | Barnhart, Joseph N | 0 | 0 | 0 | 0 | 1.68 |  | 0 | 0
998 | Payroll Taxes | PR | 66 | 11/29/17 | 12/01/17 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 7.65 |  | 0 | 0
998 | Payroll Taxes | PR | 208 | 12/06/17 | 12/08/17 | BA70 | Barnhart, Joseph N | 0 | 0 | 0 | 0 | 3.37 |  | 0 | 0
998 | Payroll Taxes | PR | 405 | 12/13/17 | 12/15/17 | BA70 | Barnhart, Joseph N | 0 | 0 | 0 | 0 | 6.73 |  | 0 | 0
998 | Payroll Taxes | PR | 465 | 12/13/17 | 12/15/17 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 3.83 |  | 0 | 0
998 | Payroll Taxes | PR | 466 | 12/13/17 | 12/15/17 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 10.79 |  | 0 | 0
998 | Payroll Taxes | PR | 466 | 12/13/17 | 12/15/17 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 7.19 |  | 0 | 0
998 | Payroll Taxes | PR | 591 | 12/20/17 | 12/22/17 | AN14 | Anderson, Richard P | 0 | 0 | 0 | 0 | 77.11 |  | 0 | 0
998 | Payroll Taxes | PR | 595 | 12/20/17 | 12/22/17 | BA70 | Barnhart, Joseph N | 0 | 0 | 0 | 0 | 85.83 |  | 0 | 0
998 | Payroll Taxes | PR | 622 | 12/20/17 | 12/22/17 | HU04 | Hubbard, Dustin R | 0 | 0 | 0 | 0 | 3.21 |  | 0 | 0
998 | Payroll Taxes | PR | 625 | 12/20/17 | 12/22/17 | KI55 | Kinssies, Jr, John E | 0 | 0 | 0 | 0 | 22.95 |  | 0 | 0
998 | Payroll Taxes | PR | 655 | 12/20/17 | 12/22/17 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 7.65 |  | 0 | 0
998 | Payroll Taxes | PR | 656 | 12/20/17 | 12/22/17 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 21.57 |  | 0 | 0
998 | Payroll Taxes | PR | 656 | 12/20/17 | 12/22/17 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 3.6 |  | 0 | 0
998 | Payroll Taxes | PR | 782 | 12/27/17 | 12/29/17 | AN14 | Anderson, Richard P | 0 | 0 | 0 | 0 | 43.38 |  | 0 | 0
998 | Payroll Taxes | PR | 785 | 12/27/17 | 12/29/17 | BA68 | Barbosa, Michael S | 0 | 0 | 0 | 0 | 12.85 |  | 0 | 0
998 | Payroll Taxes | PR | 786 | 12/27/17 | 12/29/17 | BA70 | Barnhart, Joseph N | 0 | 0 | 0 | 0 | 47.12 |  | 0 | 0
998 | Payroll Taxes | PR | 816 | 12/27/17 | 12/29/17 | KI55 | Kinssies, Jr, John E | 0 | 0 | 0 | 0 | 39.47 |  | 0 | 0
998 | Payroll Taxes | PR | 847 | 12/27/17 | 12/29/17 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 7.19 |  | 0 | 0
998 | Payroll Taxes | PR | 847 | 12/27/17 | 12/29/17 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 7.19 |  | 0 | 0
998 | Payroll Taxes | PR | 2 | 01/03/18 | 01/05/18 | AN14 | Anderson, Richard P | 0 | 0 | 0 | 0 | 35.34 |  | 0 | 0
998 | Payroll Taxes | PR | 6 | 01/03/18 | 01/05/18 | BA70 | Barnhart, Joseph N | 0 | 0 | 0 | 0 | 47.12 |  | 0 | 0
998 | Payroll Taxes | PR | 36 | 01/03/18 | 01/05/18 | KI55 | Kinssies, Jr, John E | 0 | 0 | 0 | 0 | 29.38 |  | 0 | 0
998 | Payroll Taxes | PR | 63 | 01/03/18 | 01/05/18 | WE55 | Wennig, Johnathan M | 0 | 0 | 0 | 0 | 23.87 |  | 0 | 0
998 | Payroll Taxes | PR | 65 | 01/03/18 | 01/05/18 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 4.78 |  | 0 | 0
998 | Payroll Taxes | PR | 66 | 01/03/18 | 01/05/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 14.38 |  | 0 | 0
998 | Payroll Taxes | PR | 66 | 01/03/18 | 01/05/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 7.19 |  | 0 | 0
998 | Payroll Taxes | PR | 225 | 01/10/18 | 01/12/18 | AN14 | Anderson, Richard P | 0 | 0 | 0 | 0 | 28.11 |  | 0 | 0
998 | Payroll Taxes | PR | 229 | 01/10/18 | 01/12/18 | BA70 | Barnhart, Joseph N | 0 | 0 | 0 | 0 | 87.52 |  | 0 | 0
998 | Payroll Taxes | PR | 256 | 01/10/18 | 01/12/18 | HU04 | Hubbard, Dustin R | 0 | 0 | 0 | 0 | 3.21 |  | 0 | 0
998 | Payroll Taxes | PR | 256 | 01/10/18 | 01/12/18 | HU04 | Hubbard, Dustin R | 0 | 0 | 0 | 0 | -3.21 |  | 0 | 0
998 | Payroll Taxes | PR | 259 | 01/10/18 | 01/12/18 | KI55 | Kinssies, Jr, John E | 0 | 0 | 0 | 0 | 40.39 |  | 0 | 0
998 | Payroll Taxes | PR | 286 | 01/10/18 | 01/12/18 | WE55 | Wennig, Johnathan M | 0 | 0 | 0 | 0 | 17.4 |  | 0 | 0
998 | Payroll Taxes | PR | 290 | 01/10/18 | 01/12/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 10.79 |  | 0 | 0
998 | Payroll Taxes | PR | 290 | 01/10/18 | 01/12/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 7.19 |  | 0 | 0
998 | Payroll Taxes | PR | 425 | 01/17/18 | 01/19/18 | KI55 | Kinssies, Jr, John E | 0 | 0 | 0 | 0 | 10.1 |  | 0 | 0
998 | Payroll Taxes | PR | 425 | 01/17/18 | 01/19/18 | KI55 | Kinssies, Jr, John E | 0 | 0 | 0 | 0 | 3.67 |  | 0 | 0
998 | Payroll Taxes | PR | 454 | 01/17/18 | 01/19/18 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 4.78 |  | 0 | 0
998 | Payroll Taxes | PR | 455 | 01/17/18 | 01/19/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 7.19 |  | 0 | 0
998 | Payroll Taxes | PR | 457 | 01/17/18 | 01/19/18 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | -4.78 |  | 0 | 0
998 | Payroll Taxes | PR | 458 | 01/17/18 | 01/19/18 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 4.78 |  | 0 | 0
998 | Payroll Taxes | PR | 589 | 01/24/18 | 01/26/18 | BA68 | Barbosa, Michael S | 0 | 0 | 0 | 0 | 22.49 |  | 0 | 0
998 | Payroll Taxes | PR | 590 | 01/24/18 | 01/26/18 | BA70 | Barnhart, Joseph N | 0 | 0 | 0 | 0 | 27.77 |  | 0 | 0
998 | Payroll Taxes | PR | 590 | 01/24/18 | 01/26/18 | BA70 | Barnhart, Joseph N | 0 | 0 | 0 | 0 | 57.22 |  | 0 | 0
998 | Payroll Taxes | PR | 614 | 01/24/18 | 01/26/18 | HE70 | Hernandez Gonzalez, Osbaldo | 0 | 0 | 0 | 0 | 7.99 |  | 0 | 0
998 | Payroll Taxes | PR | 650 | 01/24/18 | 01/26/18 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 4.78 |  | 0 | 0
998 | Payroll Taxes | PR | 651 | 01/24/18 | 01/26/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 3.6 |  | 0 | 0
998 | Payroll Taxes | PR | 651 | 01/24/18 | 01/26/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 7.19 |  | 0 | 0
998 | Payroll Taxes | PR | 7 | 01/31/18 | 02/02/18 | BA68 | Barbosa, Michael S | 0 | 0 | 0 | 0 | 12.85 |  | 0 | 0
998 | Payroll Taxes | PR | 8 | 01/31/18 | 02/02/18 | BA70 | Barnhart, Joseph N | 0 | 0 | 0 | 0 | 6.73 |  | 0 | 0
998 | Payroll Taxes | PR | 8 | 01/31/18 | 02/02/18 | BA70 | Barnhart, Joseph N | 0 | 0 | 0 | 0 | 3.37 |  | 0 | 0
998 | Payroll Taxes | PR | 71 | 01/31/18 | 02/02/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 7.19 |  | 0 | 0
998 | Payroll Taxes | PR | 165 | 02/07/18 | 02/09/18 | BA70 | Barnhart, Joseph N | 0 | 0 | 0 | 0 | 6.73 |  | 0 | 0
998 | Payroll Taxes | PR | 227 | 02/07/18 | 02/09/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 14.38 |  | 0 | 0
998 | Payroll Taxes | PR | 227 | 02/07/18 | 02/09/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 3.6 |  | 0 | 0
998 | Payroll Taxes | PR | 419 | 02/14/18 | 02/16/18 | BA70 | Barnhart, Joseph N | 0 | 0 | 0 | 0 | 60.59 |  | 0 | 0
998 | Payroll Taxes | PR | 449 | 02/14/18 | 02/16/18 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 13.77 |  | 0 | 0
998 | Payroll Taxes | PR | 456 | 02/14/18 | 02/16/18 | MA71 | Martinez Reyes, Juan C | 0 | 0 | 0 | 0 | 29.38 |  | 0 | 0
998 | Payroll Taxes | PR | 483 | 02/14/18 | 02/16/18 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 4.78 |  | 0 | 0
998 | Payroll Taxes | PR | 484 | 02/14/18 | 02/16/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 7.19 |  | 0 | 0
998 | Payroll Taxes | PR | 607 | 02/21/18 | 02/23/18 | BA70 | Barnhart, Joseph N | 0 | 0 | 0 | 0 | 3.37 |  | 0 | 0
998 | Payroll Taxes | PR | 643 | 02/21/18 | 02/23/18 | MA71 | Martinez Reyes, Juan C | 0 | 0 | 0 | 0 | 14.69 |  | 0 | 0
998 | Payroll Taxes | PR | 669 | 02/21/18 | 02/23/18 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 9.56 |  | 0 | 0
998 | Payroll Taxes | PR | 670 | 02/21/18 | 02/23/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 3.6 |  | 0 | 0
998 | Payroll Taxes | PR | 6 | 02/28/18 | 03/02/18 | BA70 | Barnhart, Joseph N | 0 | 0 | 0 | 0 | 13.46 |  | 0 | 0
998 | Payroll Taxes | PR | 6 | 02/28/18 | 03/02/18 | BA70 | Barnhart, Joseph N | 0 | 0 | 0 | 0 | 1.68 |  | 0 | 0
998 | Payroll Taxes | PR | 26 | 02/28/18 | 03/02/18 | GA70 | Garcia, Jordan X | 0 | 0 | 0 | 0 | 35.57 |  | 0 | 0
998 | Payroll Taxes | PR | 35 | 02/28/18 | 03/02/18 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 10.33 |  | 0 | 0
998 | Payroll Taxes | PR | 42 | 02/28/18 | 03/02/18 | MA71 | Martinez Reyes, Juan C | 0 | 0 | 0 | 0 | 11.02 |  | 0 | 0
998 | Payroll Taxes | PR | 44 | 02/28/18 | 03/02/18 | ME52 | Mendoza, Edgar E | 0 | 0 | 0 | 0 | 10.71 |  | 0 | 0
998 | Payroll Taxes | PR | 53 | 02/28/18 | 03/02/18 | RE18 | Reed, Reuben H | 0 | 0 | 0 | 0 | 30.6 |  | 0 | 0
998 | Payroll Taxes | PR | 67 | 02/28/18 | 03/02/18 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 9.56 |  | 0 | 0
998 | Payroll Taxes | PR | 68 | 02/28/18 | 03/02/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 21.57 |  | 0 | 0
998 | Payroll Taxes | PR | 68 | 02/28/18 | 03/02/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 3.6 |  | 0 | 0
998 | Payroll Taxes | PR | 122 | 03/07/18 | 03/09/18 | BA70 | Barnhart, Joseph N | 0 | 0 | 0 | 0 | 13.46 |  | 0 | 0
998 | Payroll Taxes | PR | 140 | 03/07/18 | 03/09/18 | GA70 | Garcia, Jordan X | 0 | 0 | 0 | 0 | 94.86 |  | 0 | 0
998 | Payroll Taxes | PR | 158 | 03/07/18 | 03/09/18 | ME52 | Mendoza, Edgar E | 0 | 0 | 0 | 0 | 58.91 |  | 0 | 0
998 | Payroll Taxes | PR | 167 | 03/07/18 | 03/09/18 | RE18 | Reed, Reuben H | 0 | 0 | 0 | 0 | 122.4 |  | 0 | 0
998 | Payroll Taxes | PR | 184 | 03/07/18 | 03/09/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 7.19 |  | 0 | 0
998 | Payroll Taxes | PR | 341 | 03/14/18 | 03/16/18 | GA70 | Garcia, Jordan X | 0 | 0 | 0 | 0 | 94.86 |  | 0 | 0
998 | Payroll Taxes | PR | 359 | 03/14/18 | 03/16/18 | ME52 | Mendoza, Edgar E | 0 | 0 | 0 | 0 | 61.2 |  | 0 | 0
998 | Payroll Taxes | PR | 369 | 03/14/18 | 03/16/18 | RE18 | Reed, Reuben H | 0 | 0 | 0 | 0 | 64.26 |  | 0 | 0
998 | Payroll Taxes | PR | 385 | 03/14/18 | 03/16/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 7.65 |  | 0 | 0
998 | Payroll Taxes | PR | 385 | 03/14/18 | 03/16/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 3.83 |  | 0 | 0
998 | Payroll Taxes | PR | 539 | 03/21/18 | 03/23/18 | GA70 | Garcia, Jordan X | 0 | 0 | 0 | 0 | 75.89 |  | 0 | 0
998 | Payroll Taxes | PR | 555 | 03/21/18 | 03/23/18 | LU09 | Lucas Tzintzun, Rafael | 0 | 0 | 0 | 0 | 29.38 |  | 0 | 0
998 | Payroll Taxes | PR | 558 | 03/21/18 | 03/23/18 | ME52 | Mendoza, Edgar E | 0 | 0 | 0 | 0 | 48.96 |  | 0 | 0
998 | Payroll Taxes | PR | 568 | 03/21/18 | 03/23/18 | RE18 | Reed, Reuben H | 0 | 0 | 0 | 0 | 97.92 |  | 0 | 0
998 | Payroll Taxes | PR | 584 | 03/21/18 | 03/23/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 11.48 |  | 0 | 0
998 | Payroll Taxes | PR | 758 | 03/28/18 | 03/30/18 | GA70 | Garcia, Jordan X | 0 | 0 | 0 | 0 | 94.86 |  | 0 | 0
998 | Payroll Taxes | PR | 777 | 03/28/18 | 03/30/18 | LU09 | Lucas Tzintzun, Rafael | 0 | 0 | 0 | 0 | 47.74 |  | 0 | 0
998 | Payroll Taxes | PR | 780 | 03/28/18 | 03/30/18 | ME52 | Mendoza, Edgar E | 0 | 0 | 0 | 0 | 58.91 |  | 0 | 0
998 | Payroll Taxes | PR | 791 | 03/28/18 | 03/30/18 | RE18 | Reed, Reuben H | 0 | 0 | 0 | 0 | 122.4 |  | 0 | 0
998 | Payroll Taxes | PR | 811 | 03/28/18 | 03/30/18 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 4.78 |  | 0 | 0
998 | Payroll Taxes | PR | 811 | 03/28/18 | 03/30/18 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 4.78 |  | 0 | 0
998 | Payroll Taxes | PR | 34 | 04/04/18 | 04/06/18 | GA70 | Garcia, Jordan X | 0 | 0 | 0 | 0 | 94.86 |  | 0 | 0
998 | Payroll Taxes | PR | 52 | 04/04/18 | 04/06/18 | LU09 | Lucas Tzintzun, Rafael | 0 | 0 | 0 | 0 | 48.35 |  | 0 | 0
998 | Payroll Taxes | PR | 55 | 04/04/18 | 04/06/18 | ME52 | Mendoza, Edgar E | 0 | 0 | 0 | 0 | 55.85 |  | 0 | 0
998 | Payroll Taxes | PR | 65 | 04/04/18 | 04/06/18 | RE18 | Reed, Reuben H | 0 | 0 | 0 | 0 | 110.16 |  | 0 | 0
998 | Payroll Taxes | PR | 85 | 04/04/18 | 04/06/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 3.83 |  | 0 | 0
998 | Payroll Taxes | PR | 85 | 04/04/18 | 04/06/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 7.65 |  | 0 | 0
998 | Payroll Taxes | PR | 263 | 04/11/18 | 04/13/18 | BA70 | Barnhart, Joseph N | 0 | 0 | 0 | 0 | 10.1 |  | 0 | 0
998 | Payroll Taxes | PR | 282 | 04/11/18 | 04/13/18 | GA70 | Garcia, Jordan X | 0 | 0 | 0 | 0 | 47.43 |  | 0 | 0
998 | Payroll Taxes | PR | 301 | 04/11/18 | 04/13/18 | LU09 | Lucas Tzintzun, Rafael | 0 | 0 | 0 | 0 | 36.72 |  | 0 | 0
998 | Payroll Taxes | PR | 304 | 04/11/18 | 04/13/18 | ME52 | Mendoza, Edgar E | 0 | 0 | 0 | 0 | 36.72 |  | 0 | 0
998 | Payroll Taxes | PR | 315 | 04/11/18 | 04/13/18 | RE18 | Reed, Reuben H | 0 | 0 | 0 | 0 | 73.44 |  | 0 | 0
998 | Payroll Taxes | PR | 333 | 04/11/18 | 04/13/18 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 9.56 |  | 0 | 0
998 | Payroll Taxes | PR | 467 | 04/18/18 | 04/20/18 | GA70 | Garcia, Jordan X | 0 | 0 | 0 | 0 | 85.37 |  | 0 | 0
998 | Payroll Taxes | PR | 486 | 04/18/18 | 04/20/18 | LU09 | Lucas Tzintzun, Rafael | 0 | 0 | 0 | 0 | 38.56 |  | 0 | 0
998 | Payroll Taxes | PR | 489 | 04/18/18 | 04/20/18 | ME52 | Mendoza, Edgar E | 0 | 0 | 0 | 0 | 48.96 |  | 0 | 0
998 | Payroll Taxes | PR | 500 | 04/18/18 | 04/20/18 | RE18 | Reed, Reuben H | 0 | 0 | 0 | 0 | 122.4 |  | 0 | 0
998 | Payroll Taxes | PR | 517 | 04/18/18 | 04/20/18 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 4.78 |  | 0 | 0
998 | Payroll Taxes | PR | 518 | 04/18/18 | 04/20/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 11.48 |  | 0 | 0
998 | Payroll Taxes | PR | 617 | 04/25/18 | 04/27/18 | BA70 | Barnhart, Joseph N | 0 | 0 | 0 | 0 | 3.37 |  | 0 | 0
998 | Payroll Taxes | PR | 617 | 04/25/18 | 04/27/18 | BA70 | Barnhart, Joseph N | 0 | 0 | 0 | 0 | 3.37 |  | 0 | 0
998 | Payroll Taxes | PR | 653 | 04/25/18 | 04/27/18 | LU09 | Lucas Tzintzun, Rafael | 0 | 0 | 0 | 0 | 47.74 |  | 0 | 0
998 | Payroll Taxes | PR | 656 | 04/25/18 | 04/27/18 | ME52 | Mendoza, Edgar E | 0 | 0 | 0 | 0 | 61.2 |  | 0 | 0
998 | Payroll Taxes | PR | 666 | 04/25/18 | 04/27/18 | RE18 | Reed, Reuben H | 0 | 0 | 0 | 0 | 97.92 |  | 0 | 0
998 | Payroll Taxes | PR | 677 | 04/25/18 | 04/27/18 | VE42 | Velasquez Cruz, Denis M | 0 | 0 | 0 | 0 | 82.62 |  | 0 | 0
998 | Payroll Taxes | PR | 678 | 04/25/18 | 04/27/18 | VE43 | Velasquez Cruz, Osman N | 0 | 0 | 0 | 0 | 58.14 |  | 0 | 0
998 | Payroll Taxes | PR | 684 | 04/25/18 | 04/27/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 3.83 |  | 0 | 0
998 | Payroll Taxes | PR | 31 | 05/02/18 | 05/04/18 | BA70 | Barnhart, Joseph N | 0 | 0 | 0 | 0 | 3.37 |  | 0 | 0
998 | Payroll Taxes | PR | 67 | 05/02/18 | 05/04/18 | LU09 | Lucas Tzintzun, Rafael | 0 | 0 | 0 | 0 | 47.12 |  | 0 | 0
998 | Payroll Taxes | PR | 70 | 05/02/18 | 05/04/18 | ME52 | Mendoza, Edgar E | 0 | 0 | 0 | 0 | 61.2 |  | 0 | 0
998 | Payroll Taxes | PR | 81 | 05/02/18 | 05/04/18 | RE18 | Reed, Reuben H | 0 | 0 | 0 | 0 | 122.4 |  | 0 | 0
998 | Payroll Taxes | PR | 92 | 05/02/18 | 05/04/18 | VE42 | Velasquez Cruz, Denis M | 0 | 0 | 0 | 0 | 82.62 |  | 0 | 0
998 | Payroll Taxes | PR | 93 | 05/02/18 | 05/04/18 | VE43 | Velasquez Cruz, Osman N | 0 | 0 | 0 | 0 | 58.14 |  | 0 | 0
998 | Payroll Taxes | PR | 260 | 05/09/18 | 05/11/18 | LU09 | Lucas Tzintzun, Rafael | 0 | 0 | 0 | 0 | 48.96 |  | 0 | 0
998 | Payroll Taxes | PR | 263 | 05/09/18 | 05/11/18 | ME52 | Mendoza, Edgar E | 0 | 0 | 0 | 0 | 61.2 |  | 0 | 0
998 | Payroll Taxes | PR | 273 | 05/09/18 | 05/11/18 | RE18 | Reed, Reuben H | 0 | 0 | 0 | 0 | 122.4 |  | 0 | 0
998 | Payroll Taxes | PR | 281 | 05/09/18 | 05/11/18 | VE42 | Velasquez Cruz, Denis M | 0 | 0 | 0 | 0 | 82.62 |  | 0 | 0
998 | Payroll Taxes | PR | 282 | 05/09/18 | 05/11/18 | VE43 | Velasquez Cruz, Osman N | 0 | 0 | 0 | 0 | 58.14 |  | 0 | 0
998 | Payroll Taxes | PR | 286 | 05/09/18 | 05/11/18 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 19.13 |  | 0 | 0
998 | Payroll Taxes | PR | 435 | 05/16/18 | 05/18/18 | CR79 | Cruz Guzman, Joel A | 0 | 0 | 0 | 0 | 40.39 |  | 0 | 0
998 | Payroll Taxes | PR | 436 | 05/16/18 | 05/18/18 | CR87 | Cruz Reyes, Jose | 0 | 0 | 0 | 0 | 42.23 |  | 0 | 0
998 | Payroll Taxes | PR | 452 | 05/16/18 | 05/18/18 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 39.59 |  | 0 | 0
998 | Payroll Taxes | PR | 461 | 05/16/18 | 05/18/18 | LU09 | Lucas Tzintzun, Rafael | 0 | 0 | 0 | 0 | 48.96 |  | 0 | 0
998 | Payroll Taxes | PR | 464 | 05/16/18 | 05/18/18 | ME52 | Mendoza, Edgar E | 0 | 0 | 0 | 0 | 61.2 |  | 0 | 0
998 | Payroll Taxes | PR | 475 | 05/16/18 | 05/18/18 | RE18 | Reed, Reuben H | 0 | 0 | 0 | 0 | 73.44 |  | 0 | 0
998 | Payroll Taxes | PR | 485 | 05/16/18 | 05/18/18 | VE42 | Velasquez Cruz, Denis M | 0 | 0 | 0 | 0 | 82.62 |  | 0 | 0
998 | Payroll Taxes | PR | 486 | 05/16/18 | 05/18/18 | VE43 | Velasquez Cruz, Osman N | 0 | 0 | 0 | 0 | 46.51 |  | 0 | 0
998 | Payroll Taxes | PR | 492 | 05/16/18 | 05/18/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 3.83 |  | 0 | 0
998 | Payroll Taxes | PR | 742 | 05/23/18 | 05/25/18 | BE45 | Belcher, Jacob T | 0 | 0 | 0 | 0 | 3.67 |  | 0 | 0
998 | Payroll Taxes | PR | 742 | 05/23/18 | 05/25/18 | BE45 | Belcher, Jacob T | 0 | 0 | 0 | 0 | 39.17 |  | 0 | 0
998 | Payroll Taxes | PR | 750 | 05/23/18 | 05/25/18 | CR79 | Cruz Guzman, Joel A | 0 | 0 | 0 | 0 | 5.05 |  | 0 | 0
998 | Payroll Taxes | PR | 750 | 05/23/18 | 05/25/18 | CR79 | Cruz Guzman, Joel A | 0 | 0 | 0 | 0 | 47.12 |  | 0 | 0
998 | Payroll Taxes | PR | 751 | 05/23/18 | 05/25/18 | CR87 | Cruz Reyes, Jose | 0 | 0 | 0 | 0 | 5.28 |  | 0 | 0
998 | Payroll Taxes | PR | 751 | 05/23/18 | 05/25/18 | CR87 | Cruz Reyes, Jose | 0 | 0 | 0 | 0 | 49.27 |  | 0 | 0
998 | Payroll Taxes | PR | 751 | 05/23/18 | 05/25/18 | CR87 | Cruz Reyes, Jose | 0 | 0 | 0 | 0 | 21.11 |  | 0 | 0
998 | Payroll Taxes | PR | 757 | 05/23/18 | 05/25/18 | GA70 | Garcia, Jordan X | 0 | 0 | 0 | 0 | 9.49 |  | 0 | 0
998 | Payroll Taxes | PR | 764 | 05/23/18 | 05/25/18 | HO18 | Hoeg, Xavier A | 0 | 0 | 0 | 0 | 3.44 |  | 0 | 0
998 | Payroll Taxes | PR | 764 | 05/23/18 | 05/25/18 | HO18 | Hoeg, Xavier A | 0 | 0 | 0 | 0 | 36.72 |  | 0 | 0
998 | Payroll Taxes | PR | 774 | 05/23/18 | 05/25/18 | LO58 | Lopez Reyes, Boris O | 0 | 0 | 0 | 0 | 11.02 |  | 0 | 0
998 | Payroll Taxes | PR | 776 | 05/23/18 | 05/25/18 | LU09 | Lucas Tzintzun, Rafael | 0 | 0 | 0 | 0 | 3.67 |  | 0 | 0
998 | Payroll Taxes | PR | 776 | 05/23/18 | 05/25/18 | LU09 | Lucas Tzintzun, Rafael | 0 | 0 | 0 | 0 | 48.96 |  | 0 | 0
998 | Payroll Taxes | PR | 779 | 05/23/18 | 05/25/18 | ME52 | Mendoza, Edgar E | 0 | 0 | 0 | 0 | 4.59 |  | 0 | 0
998 | Payroll Taxes | PR | 779 | 05/23/18 | 05/25/18 | ME52 | Mendoza, Edgar E | 0 | 0 | 0 | 0 | 61.2 |  | 0 | 0
998 | Payroll Taxes | PR | 790 | 05/23/18 | 05/25/18 | RE18 | Reed, Reuben H | 0 | 0 | 0 | 0 | 9.18 |  | 0 | 0
998 | Payroll Taxes | PR | 790 | 05/23/18 | 05/25/18 | RE18 | Reed, Reuben H | 0 | 0 | 0 | 0 | 110.16 |  | 0 | 0
998 | Payroll Taxes | PR | 800 | 05/23/18 | 05/25/18 | VE42 | Velasquez Cruz, Denis M | 0 | 0 | 0 | 0 | 6.2 |  | 0 | 0
998 | Payroll Taxes | PR | 800 | 05/23/18 | 05/25/18 | VE42 | Velasquez Cruz, Denis M | 0 | 0 | 0 | 0 | 82.62 |  | 0 | 0
998 | Payroll Taxes | PR | 801 | 05/23/18 | 05/25/18 | VE43 | Velasquez Cruz, Osman N | 0 | 0 | 0 | 0 | 4.36 |  | 0 | 0
998 | Payroll Taxes | PR | 801 | 05/23/18 | 05/25/18 | VE43 | Velasquez Cruz, Osman N | 0 | 0 | 0 | 0 | 58.14 |  | 0 | 0
998 | Payroll Taxes | PR | 806 | 05/23/18 | 05/25/18 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 4.78 |  | 0 | 0
998 | Payroll Taxes | PR | 807 | 05/23/18 | 05/25/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 7.65 |  | 0 | 0
998 | Payroll Taxes | PR | 807 | 05/23/18 | 05/25/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 7.65 |  | 0 | 0
998 | Payroll Taxes | PR | 9 | 05/30/18 | 06/01/18 | BE45 | Belcher, Jacob T | 0 | 0 | 0 | 0 | 42.84 |  | 0 | 0
998 | Payroll Taxes | PR | 17 | 05/30/18 | 06/01/18 | CR79 | Cruz Guzman, Joel A | 0 | 0 | 0 | 0 | 58.91 |  | 0 | 0
998 | Payroll Taxes | PR | 18 | 05/30/18 | 06/01/18 | CR87 | Cruz Reyes, Jose | 0 | 0 | 0 | 0 | 61.58 |  | 0 | 0
998 | Payroll Taxes | PR | 31 | 05/30/18 | 06/01/18 | HO18 | Hoeg, Xavier A | 0 | 0 | 0 | 0 | 40.16 |  | 0 | 0
998 | Payroll Taxes | PR | 41 | 05/30/18 | 06/01/18 | LO58 | Lopez Reyes, Boris O | 0 | 0 | 0 | 0 | 11.02 |  | 0 | 0
998 | Payroll Taxes | PR | 43 | 05/30/18 | 06/01/18 | LU09 | Lucas Tzintzun, Rafael | 0 | 0 | 0 | 0 | 42.84 |  | 0 | 0
998 | Payroll Taxes | PR | 46 | 05/30/18 | 06/01/18 | ME52 | Mendoza, Edgar E | 0 | 0 | 0 | 0 | 53.55 |  | 0 | 0
998 | Payroll Taxes | PR | 56 | 05/30/18 | 06/01/18 | RE18 | Reed, Reuben H | 0 | 0 | 0 | 0 | 97.92 |  | 0 | 0
998 | Payroll Taxes | PR | 68 | 05/30/18 | 06/01/18 | VE43 | Velasquez Cruz, Osman N | 0 | 0 | 0 | 0 | 24.71 |  | 0 | 0
998 | Payroll Taxes | PR | 76 | 05/30/18 | 06/01/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 3.83 |  | 0 | 0
998 | Payroll Taxes | PR | 76 | 05/30/18 | 06/01/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 3.83 |  | 0 | 0
998 | Payroll Taxes | PR | 274 | 06/06/18 | 06/08/18 | BE45 | Belcher, Jacob T | 0 | 0 | 0 | 0 | 7.34 |  | 0 | 0
998 | Payroll Taxes | PR | 274 | 06/06/18 | 06/08/18 | BE45 | Belcher, Jacob T | 0 | 0 | 0 | 0 | 48.96 |  | 0 | 0
998 | Payroll Taxes | PR | 282 | 06/06/18 | 06/08/18 | CR79 | Cruz Guzman, Joel A | 0 | 0 | 0 | 0 | 10.1 |  | 0 | 0
998 | Payroll Taxes | PR | 282 | 06/06/18 | 06/08/18 | CR79 | Cruz Guzman, Joel A | 0 | 0 | 0 | 0 | 67.32 |  | 0 | 0
998 | Payroll Taxes | PR | 283 | 06/06/18 | 06/08/18 | CR87 | Cruz Reyes, Jose | 0 | 0 | 0 | 0 | 15.84 |  | 0 | 0
998 | Payroll Taxes | PR | 283 | 06/06/18 | 06/08/18 | CR87 | Cruz Reyes, Jose | 0 | 0 | 0 | 0 | 47.51 |  | 0 | 0
998 | Payroll Taxes | PR | 296 | 06/06/18 | 06/08/18 | HO18 | Hoeg, Xavier A | 0 | 0 | 0 | 0 | 1.72 |  | 0 | 0
998 | Payroll Taxes | PR | 296 | 06/06/18 | 06/08/18 | HO18 | Hoeg, Xavier A | 0 | 0 | 0 | 0 | 18.36 |  | 0 | 0
998 | Payroll Taxes | PR | 308 | 06/06/18 | 06/08/18 | LU09 | Lucas Tzintzun, Rafael | 0 | 0 | 0 | 0 | 7.34 |  | 0 | 0
998 | Payroll Taxes | PR | 308 | 06/06/18 | 06/08/18 | LU09 | Lucas Tzintzun, Rafael | 0 | 0 | 0 | 0 | 48.96 |  | 0 | 0
998 | Payroll Taxes | PR | 311 | 06/06/18 | 06/08/18 | ME52 | Mendoza, Edgar E | 0 | 0 | 0 | 0 | 6.89 |  | 0 | 0
998 | Payroll Taxes | PR | 311 | 06/06/18 | 06/08/18 | ME52 | Mendoza, Edgar E | 0 | 0 | 0 | 0 | 61.2 |  | 0 | 0
998 | Payroll Taxes | PR | 321 | 06/06/18 | 06/08/18 | RE18 | Reed, Reuben H | 0 | 0 | 0 | 0 | 9.18 |  | 0 | 0
998 | Payroll Taxes | PR | 321 | 06/06/18 | 06/08/18 | RE18 | Reed, Reuben H | 0 | 0 | 0 | 0 | 9.18 |  | 0 | 0
998 | Payroll Taxes | PR | 321 | 06/06/18 | 06/08/18 | RE18 | Reed, Reuben H | 0 | 0 | 0 | 0 | 73.44 |  | 0 | 0
998 | Payroll Taxes | PR | 321 | 06/06/18 | 06/08/18 | RE18 | Reed, Reuben H | 0 | 0 | 0 | 0 | 48.96 |  | 0 | 0
998 | Payroll Taxes | PR | 334 | 06/06/18 | 06/08/18 | VE43 | Velasquez Cruz, Osman N | 0 | 0 | 0 | 0 | 11.63 |  | 0 | 0
998 | Payroll Taxes | PR | 340 | 06/06/18 | 06/08/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 3.83 |  | 0 | 0
998 | Payroll Taxes | PR | 350 | 06/06/18 | 06/08/18 | VE43 | Velasquez Cruz, Osman N | 0 | 0 | 0 | 0 | -11.63 |  | 0 | 0
998 | Payroll Taxes | PR | 464 | 06/13/18 | 06/15/18 | BE45 | Belcher, Jacob T | 0 | 0 | 0 | 0 | 5.85 |  | 0 | 0
998 | Payroll Taxes | PR | 464 | 06/13/18 | 06/15/18 | BE45 | Belcher, Jacob T | 0 | 0 | 0 | 0 | 1.95 |  | 0 | 0
998 | Payroll Taxes | PR | 464 | 06/13/18 | 06/15/18 | BE45 | Belcher, Jacob T | 0 | 0 | 0 | 0 | 31.21 |  | 0 | 0
998 | Payroll Taxes | PR | 464 | 06/13/18 | 06/15/18 | BE45 | Belcher, Jacob T | 0 | 0 | 0 | 0 | 20.81 |  | 0 | 0
998 | Payroll Taxes | PR | 472 | 06/13/18 | 06/15/18 | CR79 | Cruz Guzman, Joel A | 0 | 0 | 0 | 0 | 31.67 |  | 0 | 0
998 | Payroll Taxes | PR | 472 | 06/13/18 | 06/15/18 | CR79 | Cruz Guzman, Joel A | 0 | 0 | 0 | 0 | 29.91 |  | 0 | 0
998 | Payroll Taxes | PR | 473 | 06/13/18 | 06/15/18 | CR87 | Cruz Reyes, Jose | 0 | 0 | 0 | 0 | 11.02 |  | 0 | 0
998 | Payroll Taxes | PR | 473 | 06/13/18 | 06/15/18 | CR87 | Cruz Reyes, Jose | 0 | 0 | 0 | 0 | 73.44 |  | 0 | 0
998 | Payroll Taxes | PR | 489 | 06/13/18 | 06/15/18 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 7.19 |  | 0 | 0
998 | Payroll Taxes | PR | 498 | 06/13/18 | 06/15/18 | LU09 | Lucas Tzintzun, Rafael | 0 | 0 | 0 | 0 | 5.85 |  | 0 | 0
998 | Payroll Taxes | PR | 498 | 06/13/18 | 06/15/18 | LU09 | Lucas Tzintzun, Rafael | 0 | 0 | 0 | 0 | 1.95 |  | 0 | 0
998 | Payroll Taxes | PR | 498 | 06/13/18 | 06/15/18 | LU09 | Lucas Tzintzun, Rafael | 0 | 0 | 0 | 0 | 31.21 |  | 0 | 0
998 | Payroll Taxes | PR | 498 | 06/13/18 | 06/15/18 | LU09 | Lucas Tzintzun, Rafael | 0 | 0 | 0 | 0 | 20.81 |  | 0 | 0
998 | Payroll Taxes | PR | 501 | 06/13/18 | 06/15/18 | ME52 | Mendoza, Edgar E | 0 | 0 | 0 | 0 | 9.64 |  | 0 | 0
998 | Payroll Taxes | PR | 501 | 06/13/18 | 06/15/18 | ME52 | Mendoza, Edgar E | 0 | 0 | 0 | 0 | 64.26 |  | 0 | 0
998 | Payroll Taxes | PR | 510 | 06/13/18 | 06/15/18 | RE18 | Reed, Reuben H | 0 | 0 | 0 | 0 | 9.41 |  | 0 | 0
998 | Payroll Taxes | PR | 510 | 06/13/18 | 06/15/18 | RE18 | Reed, Reuben H | 0 | 0 | 0 | 0 | 9.41 |  | 0 | 0
998 | Payroll Taxes | PR | 510 | 06/13/18 | 06/15/18 | RE18 | Reed, Reuben H | 0 | 0 | 0 | 0 | 59.59 |  | 0 | 0
998 | Payroll Taxes | PR | 510 | 06/13/18 | 06/15/18 | RE18 | Reed, Reuben H | 0 | 0 | 0 | 0 | 65.87 |  | 0 | 0
998 | Payroll Taxes | PR | 690 | 06/20/18 | 06/22/18 | BE45 | Belcher, Jacob T | 0 | 0 | 0 | 0 | 23.41 |  | 0 | 0
998 | Payroll Taxes | PR | 690 | 06/20/18 | 06/22/18 | BE45 | Belcher, Jacob T | 0 | 0 | 0 | 0 | 22.11 |  | 0 | 0
998 | Payroll Taxes | PR | 698 | 06/20/18 | 06/22/18 | CR79 | Cruz Guzman, Joel A | 0 | 0 | 0 | 0 | 10.56 |  | 0 | 0
998 | Payroll Taxes | PR | 698 | 06/20/18 | 06/22/18 | CR79 | Cruz Guzman, Joel A | 0 | 0 | 0 | 0 | 70.38 |  | 0 | 0
998 | Payroll Taxes | PR | 699 | 06/20/18 | 06/22/18 | CR87 | Cruz Reyes, Jose | 0 | 0 | 0 | 0 | 8.26 |  | 0 | 0
998 | Payroll Taxes | PR | 699 | 06/20/18 | 06/22/18 | CR87 | Cruz Reyes, Jose | 0 | 0 | 0 | 0 | 2.75 |  | 0 | 0
998 | Payroll Taxes | PR | 699 | 06/20/18 | 06/22/18 | CR87 | Cruz Reyes, Jose | 0 | 0 | 0 | 0 | 44.06 |  | 0 | 0
998 | Payroll Taxes | PR | 699 | 06/20/18 | 06/22/18 | CR87 | Cruz Reyes, Jose | 0 | 0 | 0 | 0 | 29.38 |  | 0 | 0
998 | Payroll Taxes | PR | 715 | 06/20/18 | 06/22/18 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 5.39 |  | 0 | 0
998 | Payroll Taxes | PR | 724 | 06/20/18 | 06/22/18 | LU09 | Lucas Tzintzun, Rafael | 0 | 0 | 0 | 0 | 33.81 |  | 0 | 0
998 | Payroll Taxes | PR | 727 | 06/20/18 | 06/22/18 | ME52 | Mendoza, Edgar E | 0 | 0 | 0 | 0 | 4.82 |  | 0 | 0
998 | Payroll Taxes | PR | 727 | 06/20/18 | 06/22/18 | ME52 | Mendoza, Edgar E | 0 | 0 | 0 | 0 | 64.26 |  | 0 | 0
998 | Payroll Taxes | PR | 736 | 06/20/18 | 06/22/18 | RE18 | Reed, Reuben H | 0 | 0 | 0 | 0 | 14.11 |  | 0 | 0
998 | Payroll Taxes | PR | 736 | 06/20/18 | 06/22/18 | RE18 | Reed, Reuben H | 0 | 0 | 0 | 0 | 125.46 |  | 0 | 0
998 | Payroll Taxes | PR | 754 | 06/20/18 | 06/22/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 3.83 |  | 0 | 0
998 | Payroll Taxes | PR | 958 | 06/27/18 | 06/29/18 | BE45 | Belcher, Jacob T | 0 | 0 | 0 | 0 | 3.9 |  | 0 | 0
998 | Payroll Taxes | PR | 958 | 06/27/18 | 06/29/18 | BE45 | Belcher, Jacob T | 0 | 0 | 0 | 0 | 3.9 |  | 0 | 0
998 | Payroll Taxes | PR | 958 | 06/27/18 | 06/29/18 | BE45 | Belcher, Jacob T | 0 | 0 | 0 | 0 | 39.02 |  | 0 | 0
998 | Payroll Taxes | PR | 958 | 06/27/18 | 06/29/18 | BE45 | Belcher, Jacob T | 0 | 0 | 0 | 0 | 13.01 |  | 0 | 0
998 | Payroll Taxes | PR | 965 | 06/27/18 | 06/29/18 | CR79 | Cruz Guzman, Joel A | 0 | 0 | 0 | 0 | 7.92 |  | 0 | 0
998 | Payroll Taxes | PR | 965 | 06/27/18 | 06/29/18 | CR79 | Cruz Guzman, Joel A | 0 | 0 | 0 | 0 | 2.64 |  | 0 | 0
998 | Payroll Taxes | PR | 965 | 06/27/18 | 06/29/18 | CR79 | Cruz Guzman, Joel A | 0 | 0 | 0 | 0 | 56.3 |  | 0 | 0
998 | Payroll Taxes | PR | 965 | 06/27/18 | 06/29/18 | CR79 | Cruz Guzman, Joel A | 0 | 0 | 0 | 0 | 14.08 |  | 0 | 0
998 | Payroll Taxes | PR | 966 | 06/27/18 | 06/29/18 | CR87 | Cruz Reyes, Jose | 0 | 0 | 0 | 0 | 16.52 |  | 0 | 0
998 | Payroll Taxes | PR | 992 | 06/27/18 | 06/29/18 | LU09 | Lucas Tzintzun, Rafael | 0 | 0 | 0 | 0 | 7.8 |  | 0 | 0
998 | Payroll Taxes | PR | 992 | 06/27/18 | 06/29/18 | LU09 | Lucas Tzintzun, Rafael | 0 | 0 | 0 | 0 | 52.02 |  | 0 | 0
998 | Payroll Taxes | PR | 995 | 06/27/18 | 06/29/18 | ME52 | Mendoza, Edgar E | 0 | 0 | 0 | 0 | 7.57 |  | 0 | 0
998 | Payroll Taxes | PR | 995 | 06/27/18 | 06/29/18 | ME52 | Mendoza, Edgar E | 0 | 0 | 0 | 0 | 67.32 |  | 0 | 0
998 | Payroll Taxes | PR | 1003 | 06/27/18 | 06/29/18 | RE18 | Reed, Reuben H | 0 | 0 | 0 | 0 | 9.41 |  | 0 | 0
998 | Payroll Taxes | PR | 1003 | 06/27/18 | 06/29/18 | RE18 | Reed, Reuben H | 0 | 0 | 0 | 0 | 4.7 |  | 0 | 0
998 | Payroll Taxes | PR | 1003 | 06/27/18 | 06/29/18 | RE18 | Reed, Reuben H | 0 | 0 | 0 | 0 | 15.68 |  | 0 | 0
998 | Payroll Taxes | PR | 1003 | 06/27/18 | 06/29/18 | RE18 | Reed, Reuben H | 0 | 0 | 0 | 0 | 50.18 |  | 0 | 0
998 | Payroll Taxes | PR | 1003 | 06/27/18 | 06/29/18 | RE18 | Reed, Reuben H | 0 | 0 | 0 | 0 | 50.18 |  | 0 | 0
998 | Payroll Taxes | PR | 1019 | 06/27/18 | 06/29/18 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 4.78 |  | 0 | 0
998 | Payroll Taxes | PR | 11 | 07/04/18 | 07/06/18 | BE45 | Belcher, Jacob T | 0 | 0 | 0 | 0 | 41.62 |  | 0 | 0
998 | Payroll Taxes | PR | 19 | 07/04/18 | 07/06/18 | CR79 | Cruz Guzman, Joel A | 0 | 0 | 0 | 0 | 29.91 |  | 0 | 0
998 | Payroll Taxes | PR | 20 | 07/04/18 | 07/06/18 | CR87 | Cruz Reyes, Jose | 0 | 0 | 0 | 0 | 58.75 |  | 0 | 0
998 | Payroll Taxes | PR | 47 | 07/04/18 | 07/06/18 | LU09 | Lucas Tzintzun, Rafael | 0 | 0 | 0 | 0 | 41.62 |  | 0 | 0
998 | Payroll Taxes | PR | 50 | 07/04/18 | 07/06/18 | ME52 | Mendoza, Edgar E | 0 | 0 | 0 | 0 | 38.71 |  | 0 | 0
998 | Payroll Taxes | PR | 58 | 07/04/18 | 07/06/18 | RE18 | Reed, Reuben H | 0 | 0 | 0 | 0 | 100.37 |  | 0 | 0
998 | Payroll Taxes | PR | 241 | 07/11/18 | 07/13/18 | BA70 | Barnhart, Joseph N | 0 | 0 | 0 | 0 | 7.04 |  | 0 | 0
998 | Payroll Taxes | PR | 302 | 07/11/18 | 07/13/18 | BE45 | Belcher, Jacob T | 0 | 0 | 0 | 0 | 52.02 |  | 0 | 0
998 | Payroll Taxes | PR | 310 | 07/11/18 | 07/13/18 | CR79 | Cruz Guzman, Joel A | 0 | 0 | 0 | 0 | 42.23 |  | 0 | 0
998 | Payroll Taxes | PR | 311 | 07/11/18 | 07/13/18 | CR87 | Cruz Reyes, Jose | 0 | 0 | 0 | 0 | 73.44 |  | 0 | 0
998 | Payroll Taxes | PR | 338 | 07/11/18 | 07/13/18 | LU09 | Lucas Tzintzun, Rafael | 0 | 0 | 0 | 0 | 52.02 |  | 0 | 0
998 | Payroll Taxes | PR | 341 | 07/11/18 | 07/13/18 | ME52 | Mendoza, Edgar E | 0 | 0 | 0 | 0 | 67.32 |  | 0 | 0
998 | Payroll Taxes | PR | 350 | 07/11/18 | 07/13/18 | RE18 | Reed, Reuben H | 0 | 0 | 0 | 0 | 100.37 |  | 0 | 0
998 | Payroll Taxes | PR | 442 | 07/18/18 | 07/20/18 | BE45 | Belcher, Jacob T | 0 | 0 | 0 | 0 | 52.02 |  | 0 | 0
998 | Payroll Taxes | PR | 450 | 07/18/18 | 07/20/18 | CR79 | Cruz Guzman, Joel A | 0 | 0 | 0 | 0 | 70.38 |  | 0 | 0
998 | Payroll Taxes | PR | 451 | 07/18/18 | 07/20/18 | CR87 | Cruz Reyes, Jose | 0 | 0 | 0 | 0 | 73.44 |  | 0 | 0
998 | Payroll Taxes | PR | 470 | 07/18/18 | 07/20/18 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 5.39 |  | 0 | 0
998 | Payroll Taxes | PR | 479 | 07/18/18 | 07/20/18 | LU09 | Lucas Tzintzun, Rafael | 0 | 0 | 0 | 0 | 52.02 |  | 0 | 0
998 | Payroll Taxes | PR | 482 | 07/18/18 | 07/20/18 | ME52 | Mendoza, Edgar E | 0 | 0 | 0 | 0 | 67.32 |  | 0 | 0
998 | Payroll Taxes | PR | 490 | 07/18/18 | 07/20/18 | RE18 | Reed, Reuben H | 0 | 0 | 0 | 0 | 125.46 |  | 0 | 0
998 | Payroll Taxes | PR | 768 | 07/25/18 | 07/27/18 | BE45 | Belcher, Jacob T | 0 | 0 | 0 | 0 | 20.81 |  | 0 | 0
998 | Payroll Taxes | PR | 768 | 07/25/18 | 07/27/18 | BE45 | Belcher, Jacob T | 0 | 0 | 0 | 0 | 20.81 |  | 0 | 0
998 | Payroll Taxes | PR | 776 | 07/25/18 | 07/27/18 | CR79 | Cruz Guzman, Joel A | 0 | 0 | 0 | 0 | 70.38 |  | 0 | 0
998 | Payroll Taxes | PR | 777 | 07/25/18 | 07/27/18 | CR87 | Cruz Reyes, Jose | 0 | 0 | 0 | 0 | 51.41 |  | 0 | 0
998 | Payroll Taxes | PR | 777 | 07/25/18 | 07/27/18 | CR87 | Cruz Reyes, Jose | 0 | 0 | 0 | 0 | 22.03 |  | 0 | 0
998 | Payroll Taxes | PR | 806 | 07/25/18 | 07/27/18 | LU09 | Lucas Tzintzun, Rafael | 0 | 0 | 0 | 0 | 41.62 |  | 0 | 0
998 | Payroll Taxes | PR | 806 | 07/25/18 | 07/27/18 | LU09 | Lucas Tzintzun, Rafael | 0 | 0 | 0 | 0 | 10.4 |  | 0 | 0
998 | Payroll Taxes | PR | 809 | 07/25/18 | 07/27/18 | ME52 | Mendoza, Edgar E | 0 | 0 | 0 | 0 | 67.32 |  | 0 | 0
998 | Payroll Taxes | PR | 817 | 07/25/18 | 07/27/18 | RE18 | Reed, Reuben H | 0 | 0 | 0 | 0 | 119.19 |  | 0 | 0
998 | Payroll Taxes | PR | 7 | 08/01/18 | 08/03/18 | BE45 | Belcher, Jacob T | 0 | 0 | 0 | 0 | 20.81 |  | 0 | 0
998 | Payroll Taxes | PR | 7 | 08/01/18 | 08/03/18 | BE45 | Belcher, Jacob T | 0 | 0 | 0 | 0 | 20.81 |  | 0 | 0
998 | Payroll Taxes | PR | 15 | 08/01/18 | 08/03/18 | CR79 | Cruz Guzman, Joel A | 0 | 0 | 0 | 0 | 42.23 |  | 0 | 0
998 | Payroll Taxes | PR | 15 | 08/01/18 | 08/03/18 | CR79 | Cruz Guzman, Joel A | 0 | 0 | 0 | 0 | 28.15 |  | 0 | 0
998 | Payroll Taxes | PR | 16 | 08/01/18 | 08/03/18 | CR87 | Cruz Reyes, Jose | 0 | 0 | 0 | 0 | 44.06 |  | 0 | 0
998 | Payroll Taxes | PR | 16 | 08/01/18 | 08/03/18 | CR87 | Cruz Reyes, Jose | 0 | 0 | 0 | 0 | 29.38 |  | 0 | 0
998 | Payroll Taxes | PR | 44 | 08/01/18 | 08/03/18 | LU09 | Lucas Tzintzun, Rafael | 0 | 0 | 0 | 0 | 50.72 |  | 0 | 0
998 | Payroll Taxes | PR | 47 | 08/01/18 | 08/03/18 | ME52 | Mendoza, Edgar E | 0 | 0 | 0 | 0 | 13.46 |  | 0 | 0
998 | Payroll Taxes | PR | 55 | 08/01/18 | 08/03/18 | RE18 | Reed, Reuben H | 0 | 0 | 0 | 0 | 125.46 |  | 0 | 0
998 | Payroll Taxes | PR | 216 | 08/08/18 | 08/10/18 | BA70 | Barnhart, Joseph N | 0 | 0 | 0 | 0 | 7.04 |  | 0 | 0
998 | Payroll Taxes | PR | 217 | 08/08/18 | 08/10/18 | BE45 | Belcher, Jacob T | 0 | 0 | 0 | 0 | 52.02 |  | 0 | 0
998 | Payroll Taxes | PR | 225 | 08/08/18 | 08/10/18 | CR79 | Cruz Guzman, Joel A | 0 | 0 | 0 | 0 | 56.3 |  | 0 | 0
998 | Payroll Taxes | PR | 225 | 08/08/18 | 08/10/18 | CR79 | Cruz Guzman, Joel A | 0 | 0 | 0 | 0 | 14.08 |  | 0 | 0
998 | Payroll Taxes | PR | 226 | 08/08/18 | 08/10/18 | CR87 | Cruz Reyes, Jose | 0 | 0 | 0 | 0 | 66.1 |  | 0 | 0
998 | Payroll Taxes | PR | 226 | 08/08/18 | 08/10/18 | CR87 | Cruz Reyes, Jose | 0 | 0 | 0 | 0 | 7.34 |  | 0 | 0
998 | Payroll Taxes | PR | 246 | 08/08/18 | 08/10/18 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 39.55 |  | 0 | 0
998 | Payroll Taxes | PR | 246 | 08/08/18 | 08/10/18 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 7.19 |  | 0 | 0
998 | Payroll Taxes | PR | 255 | 08/08/18 | 08/10/18 | LU09 | Lucas Tzintzun, Rafael | 0 | 0 | 0 | 0 | 31.21 |  | 0 | 0
998 | Payroll Taxes | PR | 258 | 08/08/18 | 08/10/18 | ME52 | Mendoza, Edgar E | 0 | 0 | 0 | 0 | 37.87 |  | 0 | 0
998 | Payroll Taxes | PR | 266 | 08/08/18 | 08/10/18 | RE18 | Reed, Reuben H | 0 | 0 | 0 | 0 | 50.18 |  | 0 | 0
998 | Payroll Taxes | PR | 484 | 08/15/18 | 08/17/18 | BA70 | Barnhart, Joseph N | 0 | 0 | 0 | 0 | 3.52 |  | 0 | 0
998 | Payroll Taxes | PR | 484 | 08/15/18 | 08/17/18 | BA70 | Barnhart, Joseph N | 0 | 0 | 0 | 0 | 3.52 |  | 0 | 0
998 | Payroll Taxes | PR | 485 | 08/15/18 | 08/17/18 | BE45 | Belcher, Jacob T | 0 | 0 | 0 | 0 | 52.02 |  | 0 | 0
998 | Payroll Taxes | PR | 493 | 08/15/18 | 08/17/18 | CR79 | Cruz Guzman, Joel A | 0 | 0 | 0 | 0 | 42.23 |  | 0 | 0
998 | Payroll Taxes | PR | 493 | 08/15/18 | 08/17/18 | CR79 | Cruz Guzman, Joel A | 0 | 0 | 0 | 0 | 28.15 |  | 0 | 0
998 | Payroll Taxes | PR | 494 | 08/15/18 | 08/17/18 | CR87 | Cruz Reyes, Jose | 0 | 0 | 0 | 0 | 58.75 |  | 0 | 0
998 | Payroll Taxes | PR | 494 | 08/15/18 | 08/17/18 | CR87 | Cruz Reyes, Jose | 0 | 0 | 0 | 0 | 14.69 |  | 0 | 0
998 | Payroll Taxes | PR | 514 | 08/15/18 | 08/17/18 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 7.19 |  | 0 | 0
998 | Payroll Taxes | PR | 525 | 08/15/18 | 08/17/18 | ME52 | Mendoza, Edgar E | 0 | 0 | 0 | 0 | 67.32 |  | 0 | 0
998 | Payroll Taxes | PR | 533 | 08/15/18 | 08/17/18 | RE18 | Reed, Reuben H | 0 | 0 | 0 | 0 | 75.28 |  | 0 | 0
998 | Payroll Taxes | PR | 550 | 08/15/18 | 08/17/18 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 33.47 |  | 0 | 0
998 | Payroll Taxes | PR | 747 | 08/22/18 | 08/24/18 | BE45 | Belcher, Jacob T | 0 | 0 | 0 | 0 | 52.02 |  | 0 | 0
998 | Payroll Taxes | PR | 755 | 08/22/18 | 08/24/18 | CR79 | Cruz Guzman, Joel A | 0 | 0 | 0 | 0 | 70.38 |  | 0 | 0
998 | Payroll Taxes | PR | 756 | 08/22/18 | 08/24/18 | CR87 | Cruz Reyes, Jose | 0 | 0 | 0 | 0 | 73.44 |  | 0 | 0
998 | Payroll Taxes | PR | 786 | 08/22/18 | 08/24/18 | ME52 | Mendoza, Edgar E | 0 | 0 | 0 | 0 | 33.66 |  | 0 | 0
998 | Payroll Taxes | PR | 794 | 08/22/18 | 08/24/18 | RE18 | Reed, Reuben H | 0 | 0 | 0 | 0 | 119.19 |  | 0 | 0
998 | Payroll Taxes | PR | 811 | 08/22/18 | 08/24/18 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 4.78 |  | 0 | 0
998 | Payroll Taxes | PR | 1000 | 08/29/18 | 08/31/18 | BA70 | Barnhart, Joseph N | 0 | 0 | 0 | 0 | 3.52 |  | 0 | 0
998 | Payroll Taxes | PR | 1009 | 08/29/18 | 08/31/18 | CR79 | Cruz Guzman, Joel A | 0 | 0 | 0 | 0 | 70.38 |  | 0 | 0
998 | Payroll Taxes | PR | 1010 | 08/29/18 | 08/31/18 | CR87 | Cruz Reyes, Jose | 0 | 0 | 0 | 0 | 73.44 |  | 0 | 0
998 | Payroll Taxes | PR | 1040 | 08/29/18 | 08/31/18 | ME52 | Mendoza, Edgar E | 0 | 0 | 0 | 0 | 13.46 |  | 0 | 0
998 | Payroll Taxes | PR | 1048 | 08/29/18 | 08/31/18 | RE18 | Reed, Reuben H | 0 | 0 | 0 | 0 | 100.37 |  | 0 | 0
998 | Payroll Taxes | PR | 1070 | 08/29/18 | 08/31/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 3.83 |  | 0 | 0
998 | Payroll Taxes | PR | 50 | 09/05/18 | 09/07/18 | CR79 | Cruz Guzman, Joel A | 0 | 0 | 0 | 0 | 28.15 |  | 0 | 0
998 | Payroll Taxes | PR | 51 | 09/05/18 | 09/07/18 | CR87 | Cruz Reyes, Jose | 0 | 0 | 0 | 0 | 29.38 |  | 0 | 0
998 | Payroll Taxes | PR | 88 | 09/05/18 | 09/07/18 | RE18 | Reed, Reuben H | 0 | 0 | 0 | 0 | 50.18 |  | 0 | 0
998 | Payroll Taxes | PR | 105 | 09/05/18 | 09/07/18 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 4.78 |  | 0 | 0
998 | Payroll Taxes | PR | 281 | 09/12/18 | 09/14/18 | CR79 | Cruz Guzman, Joel A | 0 | 0 | 0 | 0 | 70.38 |  | 0 | 0
998 | Payroll Taxes | PR | 282 | 09/12/18 | 09/14/18 | CR87 | Cruz Reyes, Jose | 0 | 0 | 0 | 0 | 73.44 |  | 0 | 0
998 | Payroll Taxes | PR | 302 | 09/12/18 | 09/14/18 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 7.19 |  | 0 | 0
998 | Payroll Taxes | PR | 320 | 09/12/18 | 09/14/18 | RE18 | Reed, Reuben H | 0 | 0 | 0 | 0 | 100.37 |  | 0 | 0
998 | Payroll Taxes | PR | 494 | 09/19/18 | 09/21/18 | CR79 | Cruz Guzman, Joel A | 0 | 0 | 0 | 0 | 56.3 |  | 0 | 0
998 | Payroll Taxes | PR | 495 | 09/19/18 | 09/21/18 | CR87 | Cruz Reyes, Jose | 0 | 0 | 0 | 0 | 73.44 |  | 0 | 0
998 | Payroll Taxes | PR | 515 | 09/19/18 | 09/21/18 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 7.19 |  | 0 | 0
998 | Payroll Taxes | PR | 533 | 09/19/18 | 09/21/18 | RE18 | Reed, Reuben H | 0 | 0 | 0 | 0 | 122.32 |  | 0 | 0
998 | Payroll Taxes | PR | 700 | 09/26/18 | 09/28/18 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 7.19 |  | 0 | 0
998 | Payroll Taxes | PR | 718 | 09/26/18 | 09/28/18 | RE18 | Reed, Reuben H | 0 | 0 | 0 | 0 | 109.78 |  | 0 | 0
998 | Payroll Taxes | PR | 728 | 09/26/18 | 09/28/18 | SI48 | Silva Morales, Jair J | 0 | 0 | 0 | 0 | 67.93 |  | 0 | 0
998 | Payroll Taxes | PR | 739 | 09/26/18 | 09/28/18 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 4.78 |  | 0 | 0
998 | Payroll Taxes | PR | 64 | 10/03/18 | 10/05/18 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 10.79 |  | 0 | 0
998 | Payroll Taxes | PR | 82 | 10/03/18 | 10/05/18 | RE18 | Reed, Reuben H | 0 | 0 | 0 | 0 | 125.46 |  | 0 | 0
998 | Payroll Taxes | PR | 89 | 10/03/18 | 10/05/18 | SA54 | Sanders, Allen O | 0 | 0 | 0 | 0 | 6.73 |  | 0 | 0
998 | Payroll Taxes | PR | 92 | 10/03/18 | 10/05/18 | SI48 | Silva Morales, Jair J | 0 | 0 | 0 | 0 | 29.38 |  | 0 | 0
998 | Payroll Taxes | PR | 102 | 10/03/18 | 10/05/18 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 4.78 |  | 0 | 0
998 | Payroll Taxes | PR | 270 | 10/10/18 | 10/12/18 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 7.19 |  | 0 | 0
998 | Payroll Taxes | PR | 288 | 10/10/18 | 10/12/18 | RE18 | Reed, Reuben H | 0 | 0 | 0 | 0 | 94.1 |  | 0 | 0
998 | Payroll Taxes | PR | 288 | 10/10/18 | 10/12/18 | RE18 | Reed, Reuben H | 0 | 0 | 0 | 0 | 21.96 |  | 0 | 0
998 | Payroll Taxes | PR | 468 | 10/17/18 | 10/19/18 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 25.17 |  | 0 | 0
998 | Payroll Taxes | PR | 486 | 10/17/18 | 10/19/18 | RE18 | Reed, Reuben H | 0 | 0 | 0 | 0 | 94.1 |  | 0 | 0
998 | Payroll Taxes | PR | 493 | 10/17/18 | 10/19/18 | SA54 | Sanders, Allen O | 0 | 0 | 0 | 0 | 5.05 |  | 0 | 0
998 | Payroll Taxes | PR | 507 | 10/17/18 | 10/19/18 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 14.34 |  | 0 | 0
998 | Payroll Taxes | PR | 687 | 10/24/18 | 10/25/18 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 7.19 |  | 0 | 0
998 | Payroll Taxes | PR | 751 | 10/24/18 | 10/26/18 | RE18 | Reed, Reuben H | 0 | 0 | 0 | 0 | 21.96 |  | 0 | 0
998 | Payroll Taxes | PR | 751 | 10/24/18 | 10/26/18 | RE18 | Reed, Reuben H | 0 | 0 | 0 | 0 | 28.23 |  | 0 | 0
998 | Payroll Taxes | PR | 39 | 10/31/18 | 11/02/18 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 7.19 |  | 0 | 0
998 | Payroll Taxes | PR | 55 | 10/31/18 | 11/02/18 | RE18 | Reed, Reuben H | 0 | 0 | 0 | 0 | 50.18 |  | 0 | 0
998 | Payroll Taxes | PR | 55 | 10/31/18 | 11/02/18 | RE18 | Reed, Reuben H | 0 | 0 | 0 | 0 | 6.27 |  | 0 | 0
998 | Payroll Taxes | PR | 55 | 10/31/18 | 11/02/18 | RE18 | Reed, Reuben H | 0 | 0 | 0 | 0 | 6.27 |  | 0 | 0
998 | Payroll Taxes | PR | 62 | 10/31/18 | 11/02/18 | SA54 | Sanders, Allen O | 0 | 0 | 0 | 0 | 6.73 |  | 0 | 0
998 | Payroll Taxes | PR | 217 | 11/07/18 | 11/09/18 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 35.96 |  | 0 | 0
998 | Payroll Taxes | PR | 234 | 11/07/18 | 11/09/18 | RE18 | Reed, Reuben H | 0 | 0 | 0 | 0 | 65.87 |  | 0 | 0
998 | Payroll Taxes | PR | 234 | 11/07/18 | 11/09/18 | RE18 | Reed, Reuben H | 0 | 0 | 0 | 0 | 34.5 |  | 0 | 0
998 | Payroll Taxes | PR | 257 | 11/07/18 | 11/09/18 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 4.78 |  | 0 | 0
998 | Payroll Taxes | PR | 465 | 11/14/18 | 11/16/18 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 35.96 |  | 0 | 0
998 | Payroll Taxes | PR | 482 | 11/14/18 | 11/16/18 | RE18 | Reed, Reuben H | 0 | 0 | 0 | 0 | 43.91 |  | 0 | 0
998 | Payroll Taxes | PR | 504 | 11/14/18 | 11/16/18 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | -35.96 |  | 0 | 0
998 | Payroll Taxes | PR | 508 | 11/14/18 | 11/16/18 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 35.96 |  | 0 | 0
998 | Payroll Taxes | PR | 621 | 11/21/18 | 11/21/18 | BA70 | Barnhart, Joseph N | 0 | 0 | 0 | 0 | 28.15 |  | 0 | 0
998 | Payroll Taxes | PR | 863 | 11/28/18 | 11/30/18 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 7.5 |  | 0 | 0
998 | Payroll Taxes | PR | 879 | 11/28/18 | 11/30/18 | RE18 | Reed, Reuben H | 0 | 0 | 0 | 0 | 16.45 |  | 0 | 0
998 | Payroll Taxes | PR | 879 | 11/28/18 | 11/30/18 | RE18 | Reed, Reuben H | 0 | 0 | 0 | 0 | 36.18 |  | 0 | 0
998 | Payroll Taxes | PR | 63 | 12/05/18 | 12/07/18 | FO55 | Fonseca Teruel, Eduardo | 0 | 0 | 0 | 0 | 1.03 |  | 0 | 0
998 | Payroll Taxes | PR | 63 | 12/05/18 | 12/07/18 | FO55 | Fonseca Teruel, Eduardo | 0 | 0 | 0 | 0 | 11.02 |  | 0 | 0
998 | Payroll Taxes | PR | 69 | 12/05/18 | 12/07/18 | GO51 | Gomez Reyes, Edith N | 0 | 0 | 0 | 0 | 1.32 |  | 0 | 0
998 | Payroll Taxes | PR | 69 | 12/05/18 | 12/07/18 | GO51 | Gomez Reyes, Edith N | 0 | 0 | 0 | 0 | 14.08 |  | 0 | 0
998 | Payroll Taxes | PR | 91 | 12/05/18 | 12/07/18 | RE18 | Reed, Reuben H | 0 | 0 | 0 | 0 | 26.32 |  | 0 | 0
998 | Payroll Taxes | PR | 91 | 12/05/18 | 12/07/18 | RE18 | Reed, Reuben H | 0 | 0 | 0 | 0 | 13.16 |  | 0 | 0
998 | Payroll Taxes | PR | 92 | 12/05/18 | 12/07/18 | RE91 | Reyes, Maria E | 0 | 0 | 0 | 0 | 1.03 |  | 0 | 0
998 | Payroll Taxes | PR | 92 | 12/05/18 | 12/07/18 | RE91 | Reyes, Maria E | 0 | 0 | 0 | 0 | 11.02 |  | 0 | 0
998 | Payroll Taxes | PR | 99 | 12/05/18 | 12/07/18 | SA54 | Sanders, Allen O | 0 | 0 | 0 | 0 | 21.57 |  | 0 | 0
998 | Payroll Taxes | PR | 113 | 12/05/18 | 12/07/18 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 9.56 |  | 0 | 0
998 | Payroll Taxes | PR | 316 | 12/12/18 | 12/14/18 | RE18 | Reed, Reuben H | 0 | 0 | 0 | 0 | 16.45 |  | 0 | 0
998 | Payroll Taxes | PR | 316 | 12/12/18 | 12/14/18 | RE18 | Reed, Reuben H | 0 | 0 | 0 | 0 | 9.87 |  | 0 | 0
998 | Payroll Taxes | PR | 324 | 12/12/18 | 12/14/18 | SA54 | Sanders, Allen O | 0 | 0 | 0 | 0 | 7.19 |  | 0 | 0
998 | Payroll Taxes | PR | 337 | 12/12/18 | 12/14/18 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 9.56 |  | 0 | 0
998 | Payroll Taxes | PR | 517 | 12/19/18 | 12/21/18 | CO71 | Cortes Mendiola, Victor H | 0 | 0 | 0 | 0 | 26.32 |  | 0 | 0
998 | Payroll Taxes | PR | 528 | 12/19/18 | 12/21/18 | FO55 | Fonseca Teruel, Eduardo | 0 | 0 | 0 | 0 | 11.02 |  | 0 | 0
998 | Payroll Taxes | PR | 534 | 12/19/18 | 12/21/18 | GO51 | Gomez Reyes, Edith N | 0 | 0 | 0 | 0 | 42.23 |  | 0 | 0
998 | Payroll Taxes | PR | 557 | 12/19/18 | 12/21/18 | RE91 | Reyes, Maria E | 0 | 0 | 0 | 0 | 4.13 |  | 0 | 0
998 | Payroll Taxes | PR | 557 | 12/19/18 | 12/21/18 | RE91 | Reyes, Maria E | 0 | 0 | 0 | 0 | 44.06 |  | 0 | 0
998 | Payroll Taxes | PR | 564 | 12/19/18 | 12/21/18 | SA54 | Sanders, Allen O | 0 | 0 | 0 | 0 | 10.79 |  | 0 | 0
998 | Payroll Taxes | PR | 564 | 12/19/18 | 12/21/18 | SA54 | Sanders, Allen O | 0 | 0 | 0 | 0 | 57.53 |  | 0 | 0
998 | Payroll Taxes | PR | 571 | 12/19/18 | 12/21/18 | TR60 | Trower-Kelly, Fidel D | 0 | 0 | 0 | 0 | 5.51 |  | 0 | 0
998 | Payroll Taxes | PR | 571 | 12/19/18 | 12/21/18 | TR60 | Trower-Kelly, Fidel D | 0 | 0 | 0 | 0 | 19.58 |  | 0 | 0
998 | Payroll Taxes | PR | 577 | 12/19/18 | 12/21/18 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 19.13 |  | 0 | 0
998 | Payroll Taxes | PR | 708 | 12/26/18 | 12/28/18 | CO71 | Cortes Mendiola, Victor H | 0 | 0 | 0 | 0 | -26.32 |  | 0 | 0
998 | Payroll Taxes | PR | 724 | 12/26/18 | 12/28/18 | GO51 | Gomez Reyes, Edith N | 0 | 0 | 0 | 0 | 14.08 |  | 0 | 0
998 | Payroll Taxes | PR | 731 | 12/26/18 | 12/28/18 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 18.74 |  | 0 | 0
998 | Payroll Taxes | PR | 748 | 12/26/18 | 12/28/18 | RE91 | Reyes, Maria E | 0 | 0 | 0 | 0 | 35.8 |  | 0 | 0
998 | Payroll Taxes | PR | 755 | 12/26/18 | 12/28/18 | SA54 | Sanders, Allen O | 0 | 0 | 0 | 0 | 14.38 |  | 0 | 0
998 | Payroll Taxes | PR | 776 | 12/26/18 | 12/28/18 | RE91 | Reyes, Maria E | 0 | 0 | 0 | 0 | 44.06 |  | 0 | 0
998 | Payroll Taxes | PR | 776 | 12/26/18 | 12/28/18 | RE91 | Reyes, Maria E | 0 | 0 | 0 | 0 | -44.06 |  | 0 | 0
998 | Payroll Taxes | PR | 29 | 01/02/19 | 01/04/19 | GO51 | Gomez Reyes, Edith N | 0 | 0 | 0 | 0 | 14.08 |  | 0 | 0
998 | Payroll Taxes | PR | 35 | 01/02/19 | 01/04/19 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 29.99 |  | 0 | 0
998 | Payroll Taxes | PR | 51 | 01/02/19 | 01/04/19 | RE91 | Reyes, Maria E | 0 | 0 | 0 | 0 | 11.02 |  | 0 | 0
998 | Payroll Taxes | PR | 58 | 01/02/19 | 01/04/19 | SA54 | Sanders, Allen O | 0 | 0 | 0 | 0 | 7.19 |  | 0 | 0
998 | Payroll Taxes | PR | 237 | 01/09/19 | 01/11/19 | GO51 | Gomez Reyes, Edith N | 0 | 0 | 0 | 0 | 2.64 |  | 0 | 0
998 | Payroll Taxes | PR | 237 | 01/09/19 | 01/11/19 | GO51 | Gomez Reyes, Edith N | 0 | 0 | 0 | 0 | 42.23 |  | 0 | 0
998 | Payroll Taxes | PR | 244 | 01/09/19 | 01/11/19 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 44.98 |  | 0 | 0
998 | Payroll Taxes | PR | 252 | 01/09/19 | 01/11/19 | MC09 | McCabe, Thomas C | 0 | 0 | 0 | 0 | 45.44 |  | 0 | 0
998 | Payroll Taxes | PR | 252 | 01/09/19 | 01/11/19 | MC09 | McCabe, Thomas C | 0 | 0 | 0 | 0 | 10.1 |  | 0 | 0
998 | Payroll Taxes | PR | 260 | 01/09/19 | 01/11/19 | RE18 | Reed, Reuben H | 0 | 0 | 0 | 0 | 3.29 |  | 0 | 0
998 | Payroll Taxes | PR | 261 | 01/09/19 | 01/11/19 | RE91 | Reyes, Maria E | 0 | 0 | 0 | 0 | 2.07 |  | 0 | 0
998 | Payroll Taxes | PR | 261 | 01/09/19 | 01/11/19 | RE91 | Reyes, Maria E | 0 | 0 | 0 | 0 | 33.05 |  | 0 | 0
998 | Payroll Taxes | PR | 268 | 01/09/19 | 01/11/19 | SA54 | Sanders, Allen O | 0 | 0 | 0 | 0 | 32.36 |  | 0 | 0
998 | Payroll Taxes | PR | 492 | 01/16/19 | 01/18/19 | GO51 | Gomez Reyes, Edith N | 0 | 0 | 0 | 0 | 7.92 |  | 0 | 0
998 | Payroll Taxes | PR | 492 | 01/16/19 | 01/18/19 | GO51 | Gomez Reyes, Edith N | 0 | 0 | 0 | 0 | 56.3 |  | 0 | 0
998 | Payroll Taxes | PR | 499 | 01/16/19 | 01/18/19 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 11.25 |  | 0 | 0
998 | Payroll Taxes | PR | 507 | 01/16/19 | 01/18/19 | MC09 | McCabe, Thomas C | 0 | 0 | 0 | 0 | 30.29 |  | 0 | 0
998 | Payroll Taxes | PR | 507 | 01/16/19 | 01/18/19 | MC09 | McCabe, Thomas C | 0 | 0 | 0 | 0 | 10.1 |  | 0 | 0
998 | Payroll Taxes | PR | 516 | 01/16/19 | 01/18/19 | RE91 | Reyes, Maria E | 0 | 0 | 0 | 0 | 6.2 |  | 0 | 0
998 | Payroll Taxes | PR | 516 | 01/16/19 | 01/18/19 | RE91 | Reyes, Maria E | 0 | 0 | 0 | 0 | 44.06 |  | 0 | 0
998 | Payroll Taxes | PR | 523 | 01/16/19 | 01/18/19 | SA54 | Sanders, Allen O | 0 | 0 | 0 | 0 | 3.6 |  | 0 | 0
998 | Payroll Taxes | PR | 524 | 01/16/19 | 01/18/19 | SE64 | Sepulveda Gonzalez, Alfredo | 0 | 0 | 0 | 0 | 9.79 |  | 0 | 0
998 | Payroll Taxes | PR | 524 | 01/16/19 | 01/18/19 | SE64 | Sepulveda Gonzalez, Alfredo | 0 | 0 | 0 | 0 | 9.79 |  | 0 | 0
998 | Payroll Taxes | PR | 735 | 01/23/19 | 01/25/19 | FO55 | Fonseca Teruel, Eduardo | 0 | 0 | 0 | 0 | 11.02 |  | 0 | 0
998 | Payroll Taxes | PR | 739 | 01/23/19 | 01/25/19 | GE70 | Gerard, Jordan E | 0 | 0 | 0 | 0 | 20.81 |  | 0 | 0
998 | Payroll Taxes | PR | 741 | 01/23/19 | 01/25/19 | GO51 | Gomez Reyes, Edith N | 0 | 0 | 0 | 0 | 5.28 |  | 0 | 0
998 | Payroll Taxes | PR | 741 | 01/23/19 | 01/25/19 | GO51 | Gomez Reyes, Edith N | 0 | 0 | 0 | 0 | 45.75 |  | 0 | 0
998 | Payroll Taxes | PR | 748 | 01/23/19 | 01/25/19 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 26.24 |  | 0 | 0
998 | Payroll Taxes | PR | 765 | 01/23/19 | 01/25/19 | RE91 | Reyes, Maria E | 0 | 0 | 0 | 0 | 4.13 |  | 0 | 0
998 | Payroll Taxes | PR | 765 | 01/23/19 | 01/25/19 | RE91 | Reyes, Maria E | 0 | 0 | 0 | 0 | 33.05 |  | 0 | 0
998 | Payroll Taxes | PR | 772 | 01/23/19 | 01/25/19 | SA54 | Sanders, Allen O | 0 | 0 | 0 | 0 | 2.7 |  | 0 | 0
998 | Payroll Taxes | PR | 772 | 01/23/19 | 01/25/19 | SA54 | Sanders, Allen O | 0 | 0 | 0 | 0 | 37.75 |  | 0 | 0
998 | Payroll Taxes | PR | 773 | 01/23/19 | 01/25/19 | SE64 | Sepulveda Gonzalez, Alfredo | 0 | 0 | 0 | 0 | 4.9 |  | 0 | 0
998 | Payroll Taxes | PR | 773 | 01/23/19 | 01/25/19 | SE64 | Sepulveda Gonzalez, Alfredo | 0 | 0 | 0 | 0 | 7.34 |  | 0 | 0
998 | Payroll Taxes | PR | 776 | 01/23/19 | 01/25/19 | ST02 | Stahlschmidt, John P | 0 | 0 | 0 | 0 | 10.4 |  | 0 | 0
998 | Payroll Taxes | PR | 29 | 01/30/19 | 02/01/19 | GO51 | Gomez Reyes, Edith N | 0 | 0 | 0 | 0 | 5.28 |  | 0 | 0
998 | Payroll Taxes | PR | 29 | 01/30/19 | 02/01/19 | GO51 | Gomez Reyes, Edith N | 0 | 0 | 0 | 0 | 42.23 |  | 0 | 0
998 | Payroll Taxes | PR | 36 | 01/30/19 | 02/01/19 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 16.87 |  | 0 | 0
998 | Payroll Taxes | PR | 44 | 01/30/19 | 02/01/19 | MC09 | McCabe, Thomas C | 0 | 0 | 0 | 0 | 10.1 |  | 0 | 0
998 | Payroll Taxes | PR | 44 | 01/30/19 | 02/01/19 | MC09 | McCabe, Thomas C | 0 | 0 | 0 | 0 | 30.29 |  | 0 | 0
998 | Payroll Taxes | PR | 51 | 01/30/19 | 02/01/19 | RE91 | Reyes, Maria E | 0 | 0 | 0 | 0 | 4.13 |  | 0 | 0
998 | Payroll Taxes | PR | 51 | 01/30/19 | 02/01/19 | RE91 | Reyes, Maria E | 0 | 0 | 0 | 0 | 33.05 |  | 0 | 0
998 | Payroll Taxes | PR | 57 | 01/30/19 | 02/01/19 | SA54 | Sanders, Allen O | 0 | 0 | 0 | 0 | 14.38 |  | 0 | 0
998 | Payroll Taxes | PR | 58 | 01/30/19 | 02/01/19 | SE64 | Sepulveda Gonzalez, Alfredo | 0 | 0 | 0 | 0 | 9.79 |  | 0 | 0
998 | Payroll Taxes | PR | 58 | 01/30/19 | 02/01/19 | SE64 | Sepulveda Gonzalez, Alfredo | 0 | 0 | 0 | 0 | 4.9 |  | 0 | 0
998 | Payroll Taxes | PR | 70 | 01/30/19 | 02/01/19 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 9.56 |  | 0 | 0
998 | Payroll Taxes | PR | 184 | 02/06/19 | 02/08/19 | GO51 | Gomez Reyes, Edith N | 0 | 0 | 0 | 0 | 28.15 |  | 0 | 0
998 | Payroll Taxes | PR | 206 | 02/06/19 | 02/08/19 | RE91 | Reyes, Maria E | 0 | 0 | 0 | 0 | 22.03 |  | 0 | 0
998 | Payroll Taxes | PR | 213 | 02/06/19 | 02/08/19 | SA54 | Sanders, Allen O | 0 | 0 | 0 | 0 | 10.79 |  | 0 | 0
998 | Payroll Taxes | PR | 226 | 02/06/19 | 02/08/19 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 4.78 |  | 0 | 0
998 | Payroll Taxes | PR | 346 | 02/13/19 | 02/15/19 | GO51 | Gomez Reyes, Edith N | 0 | 0 | 0 | 0 | 24.63 |  | 0 | 0
998 | Payroll Taxes | PR | 375 | 02/13/19 | 02/15/19 | SA54 | Sanders, Allen O | 0 | 0 | 0 | 0 | 1.8 |  | 0 | 0
998 | Payroll Taxes | PR | 388 | 02/13/19 | 02/15/19 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 4.78 |  | 0 | 0
998 | Payroll Taxes | PR | 401 | 02/13/19 | 02/15/19 | RE91 | Reyes, Maria E | 0 | 0 | 0 | 0 | 19.28 |  | 0 | 0
998 | Payroll Taxes | PR | 596 | 02/20/19 | 02/22/19 | EL33 | Eliassen, Cory H | 0 | 0 | 0 | 0 | 5.74 |  | 0 | 0
998 | Payroll Taxes | PR | 634 | 02/20/19 | 02/22/19 | SA54 | Sanders, Allen O | 0 | 0 | 0 | 0 | 10.79 |  | 0 | 0
998 | Payroll Taxes | PR | 641 | 02/20/19 | 02/22/19 | TR60 | Trower-Kelly, Fidel D | 0 | 0 | 0 | 0 | 13.46 |  | 0 | 0
998 | Payroll Taxes | PR | 647 | 02/20/19 | 02/22/19 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 9.56 |  | 0 | 0
998 | Payroll Taxes | PR | 22 | 02/27/19 | 03/01/19 | EL33 | Eliassen, Cory H | 0 | 0 | 0 | 0 | 10.52 |  | 0 | 0
998 | Payroll Taxes | PR | 38 | 02/27/19 | 03/01/19 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 44.98 |  | 0 | 0
998 | Payroll Taxes | PR | 61 | 02/27/19 | 03/01/19 | SA54 | Sanders, Allen O | 0 | 0 | 0 | 0 | 2.7 |  | 0 | 0
998 | Payroll Taxes | PR | 61 | 02/27/19 | 03/01/19 | SA54 | Sanders, Allen O | 0 | 0 | 0 | 0 | 8.99 |  | 0 | 0
998 | Payroll Taxes | PR | 68 | 02/27/19 | 03/01/19 | TR60 | Trower-Kelly, Fidel D | 0 | 0 | 0 | 0 | 3.06 |  | 0 | 0
998 | Payroll Taxes | PR | 264 | 03/06/19 | 03/08/19 | EL33 | Eliassen, Cory H | 0 | 0 | 0 | 0 | 19.13 |  | 0 | 0
998 | Payroll Taxes | PR | 293 | 03/06/19 | 03/08/19 | RE18 | Reed, Reuben H | 0 | 0 | 0 | 0 | 13.16 |  | 0 | 0
998 | Payroll Taxes | PR | 307 | 03/06/19 | 03/08/19 | TR60 | Trower-Kelly, Fidel D | 0 | 0 | 0 | 0 | 6.12 |  | 0 | 0
998 | Payroll Taxes | PR | 314 | 03/06/19 | 03/08/19 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 4.78 |  | 0 | 0
998 | Payroll Taxes | PR | 511 | 03/13/19 | 03/15/19 | EL33 | Eliassen, Cory H | 0 | 0 | 0 | 0 | 5.74 |  | 0 | 0
998 | Payroll Taxes | PR | 511 | 03/13/19 | 03/15/19 | EL33 | Eliassen, Cory H | 0 | 0 | 0 | 0 | 13.39 |  | 0 | 0
998 | Payroll Taxes | PR | 525 | 03/13/19 | 03/15/19 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 18.74 |  | 0 | 0
998 | Payroll Taxes | PR | 533 | 03/13/19 | 03/15/19 | MC09 | McCabe, Thomas C | 0 | 0 | 0 | 0 | 10.1 |  | 0 | 0
998 | Payroll Taxes | PR | 547 | 03/13/19 | 03/15/19 | SA54 | Sanders, Allen O | 0 | 0 | 0 | 0 | 25.17 |  | 0 | 0
998 | Payroll Taxes | PR | 555 | 03/13/19 | 03/15/19 | TR60 | Trower-Kelly, Fidel D | 0 | 0 | 0 | 0 | 3.67 |  | 0 | 0
998 | Payroll Taxes | PR | 555 | 03/13/19 | 03/15/19 | TR60 | Trower-Kelly, Fidel D | 0 | 0 | 0 | 0 | 4.9 |  | 0 | 0
998 | Payroll Taxes | PR | 562 | 03/13/19 | 03/15/19 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 4.78 |  | 0 | 0
998 | Payroll Taxes | PR | 725 | 03/20/19 | 03/22/19 | EL33 | Eliassen, Cory H | 0 | 0 | 0 | 0 | 7.65 |  | 0 | 0
998 | Payroll Taxes | PR | 731 | 03/20/19 | 03/22/19 | GE70 | Gerard, Jordan E | 0 | 0 | 0 | 0 | 13.01 |  | 0 | 0
998 | Payroll Taxes | PR | 760 | 03/20/19 | 03/22/19 | SA54 | Sanders, Allen O | 0 | 0 | 0 | 0 | 35.96 |  | 0 | 0
998 | Payroll Taxes | PR | 776 | 03/20/19 | 03/22/19 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 14.34 |  | 0 | 0
998 | Payroll Taxes | PR | 777 | 03/20/19 | 03/22/19 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 3.98 |  | 0 | 0
998 | Payroll Taxes | PR | 989 | 03/27/19 | 03/29/19 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 14.34 |  | 0 | 0
998 | Payroll Taxes | PR | 114 | 04/03/19 | 04/05/19 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 5.62 |  | 0 | 0
998 | Payroll Taxes | PR | 114 | 04/03/19 | 04/05/19 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 3.75 |  | 0 | 0
998 | Payroll Taxes | PR | 132 | 04/03/19 | 04/05/19 | RO06 | Roberts, Lake A | 0 | 0 | 0 | 0 | 4.13 |  | 0 | 0
998 | Payroll Taxes | PR | 132 | 04/03/19 | 04/05/19 | RO06 | Roberts, Lake A | 0 | 0 | 0 | 0 | 5.51 |  | 0 | 0
998 | Payroll Taxes | PR | 135 | 04/03/19 | 04/05/19 | SA54 | Sanders, Allen O | 0 | 0 | 0 | 0 | 29.66 |  | 0 | 0
998 | Payroll Taxes | PR | 135 | 04/03/19 | 04/05/19 | SA54 | Sanders, Allen O | 0 | 0 | 0 | 0 | 3.6 |  | 0 | 0
998 | Payroll Taxes | PR | 151 | 04/03/19 | 04/05/19 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 14.34 |  | 0 | 0
998 | Payroll Taxes | PR | 372 | 04/10/19 | 04/12/19 | RE18 | Reed, Reuben H | 0 | 0 | 0 | 0 | 24.1 |  | 0 | 0
998 | Payroll Taxes | PR | 379 | 04/10/19 | 04/12/19 | SA54 | Sanders, Allen O | 0 | 0 | 0 | 0 | 37.49 |  | 0 | 0
998 | Payroll Taxes | PR | 578 | 04/17/19 | 04/19/19 | SA54 | Sanders, Allen O | 0 | 0 | 0 | 0 | 5.62 |  | 0 | 0
998 | Payroll Taxes | PR | 586 | 04/17/19 | 04/19/19 | TR60 | Trower-Kelly, Fidel D | 0 | 0 | 0 | 0 | 1.84 |  | 0 | 0
998 | Payroll Taxes | PR | 797 | 04/24/19 | 04/26/19 | SA54 | Sanders, Allen O | 0 | 0 | 0 | 0 | 3.75 |  | 0 | 0
998 | Payroll Taxes | PR | 66 | 05/01/19 | 05/03/19 | SA54 | Sanders, Allen O | 0 | 0 | 0 | 0 | 3.75 |  | 0 | 0
998 | Payroll Taxes | PR | 81 | 05/01/19 | 05/03/19 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 4.78 |  | 0 | 0
998 | Payroll Taxes | PR | 164 | 05/08/19 | 05/10/19 | BA70 | Barnhart, Joseph N | 0 | 0 | 0 | 0 | 3.83 |  | 0 | 0
998 | Payroll Taxes | PR | 219 | 05/08/19 | 05/10/19 | SA54 | Sanders, Allen O | 0 | 0 | 0 | 0 | 7.5 |  | 0 | 0
998 | Payroll Taxes | PR | 952 | 05/29/19 | 05/31/19 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 9.56 |  | 0 | 0
999 | Sales | AR | 373 | 10/20/17 | 10/20/17 | 2042SH | Boren and Spruce, LLC $Metro Line Flats |  |  |  |  | -30100 | 036973 | 0 | -1505
999 | Sales | AR | 373 | 10/20/17 | 10/20/17 | 2042SH | Boren and Spruce, LLC $Metro Line Flats |  |  |  |  | -4300 | 036973 | 0 | -215
999 | Sales | AR | 536 | 12/15/17 | 12/15/17 | 2042SH | Boren and Spruce, LLC $Metro Line Flats |  |  |  |  | -56800 | 036992 | 0 | -2840
999 | Sales | AR | 467 | 01/19/18 | 01/19/18 | 2042SH | Boren and Spruce, LLC $Metro Line Flats |  |  |  |  | -12100 | 037002 | 0 | -605
999 | Sales | AR | 585 | 02/20/18 | 02/20/18 | 2042SH | Boren and Spruce, LLC $Metro Line Flats |  |  |  |  | -14000 | 037027 | 0 | -700
999 | Sales | AR | 436 | 03/20/18 | 03/20/18 | 2042SH | Boren and Spruce, LLC $Metro Line Flats |  |  |  |  | -24950 | 037041 | 0 | -1247.5
999 | Sales | AR | 436 | 03/20/18 | 03/20/18 | 2042SH | Boren and Spruce, LLC $Metro Line Flats |  |  |  |  | -35650 | 037041 | 0 | -1782.5
999 | Sales | AR | 436 | 03/20/18 | 03/20/18 | 2042SH | Boren and Spruce, LLC $Metro Line Flats |  |  |  |  | -8560 | 037041 | 0 | -428
999 | Sales | AR | 545 | 04/20/18 | 04/20/18 | 2042SH | Boren and Spruce, LLC $Metro Line Flats |  |  |  |  | -7485 | 037066 | 0 | -374.25
999 | Sales | AR | 545 | 04/20/18 | 04/20/18 | 2042SH | Boren and Spruce, LLC $Metro Line Flats |  |  |  |  | -10695 | 037066 | 0 | -534.75
999 | Sales | AR | 545 | 04/20/18 | 04/20/18 | 2042SH | Boren and Spruce, LLC $Metro Line Flats |  |  |  |  | -47073 | 037066 | 0 | -2353.65
999 | Sales | AR | 545 | 04/20/18 | 04/20/18 | 2042SH | Boren and Spruce, LLC $Metro Line Flats |  |  |  |  | -34236 | 037066 | 0 | -1711.8
999 | Sales | AR | 545 | 04/20/18 | 04/20/18 | 2042SH | Boren and Spruce, LLC $Metro Line Flats |  |  |  |  | -8600 | 037066 | 0 | -430
999 | Sales | AR | 503 | 05/18/18 | 05/18/18 | 2042SH | Boren and Spruce, LLC $Metro Line Flats |  |  |  |  | -4720 | 037081 | 0 | -236
999 | Sales | AR | 503 | 05/18/18 | 05/18/18 | 2042SH | Boren and Spruce, LLC $Metro Line Flats |  |  |  |  | -6800 | 037081 | 0 | -340
999 | Sales | AR | 503 | 05/18/18 | 05/18/18 | 2042SH | Boren and Spruce, LLC $Metro Line Flats |  |  |  |  | -12839 | 037081 | 0 | -641.95
999 | Sales | AR | 503 | 05/18/18 | 05/18/18 | 2042SH | Boren and Spruce, LLC $Metro Line Flats |  |  |  |  | -8100 | 037081 | 0 | -405
999 | Sales | AR | 503 | 05/18/18 | 05/18/18 | 2042SH | Boren and Spruce, LLC $Metro Line Flats |  |  |  |  | -34236 | 037081 | 0 | -1711.8
999 | Sales | AR | 503 | 05/18/18 | 05/18/18 | 2042SH | Boren and Spruce, LLC $Metro Line Flats |  |  |  |  | -8100 | 037081 | 0 | -405
999 | Sales | AR | 503 | 05/18/18 | 05/18/18 | 2042SH | Boren and Spruce, LLC $Metro Line Flats |  |  |  |  | -34195 | 037081 | 0 | -1709.75
999 | Sales | AR | 503 | 05/18/18 | 05/18/18 | 2042SH | Boren and Spruce, LLC $Metro Line Flats |  |  |  |  | -8100 | 037081 | 0 | -405
999 | Sales | AR | 503 | 05/18/18 | 05/18/18 | 2042SH | Boren and Spruce, LLC $Metro Line Flats |  |  |  |  | -40800 | 037081 | 0 | -2040
999 | Sales | AR | 503 | 05/18/18 | 05/18/18 | 2042SH | Boren and Spruce, LLC $Metro Line Flats |  |  |  |  | -8100 | 037081 | 0 | -405
999 | Sales | AR | 503 | 05/18/18 | 05/18/18 | 2042SH | Boren and Spruce, LLC $Metro Line Flats |  |  |  |  | -18079 | 037081 | 0 | -903.95
999 | Sales | AR | 503 | 05/18/18 | 05/18/18 | 2042SH | Boren and Spruce, LLC $Metro Line Flats |  |  |  |  | -5400 | 037081 | 0 | -270
999 | Sales | AR | 676 | 06/20/18 | 06/20/18 | 2042SH | Boren and Spruce, LLC $Metro Line Flats |  |  |  |  | -3320 | 037115 | 0 | -166
999 | Sales | AR | 676 | 06/20/18 | 06/20/18 | 2042SH | Boren and Spruce, LLC $Metro Line Flats |  |  |  |  | -4220 | 037115 | 0 | -211
999 | Sales | AR | 676 | 06/20/18 | 06/20/18 | 2042SH | Boren and Spruce, LLC $Metro Line Flats |  |  |  |  | -8559 | 037115 | 0 | -427.95
999 | Sales | AR | 676 | 06/20/18 | 06/20/18 | 2042SH | Boren and Spruce, LLC $Metro Line Flats |  |  |  |  | -8558 | 037115 | 0 | -427.9
999 | Sales | AR | 676 | 06/20/18 | 06/20/18 | 2042SH | Boren and Spruce, LLC $Metro Line Flats |  |  |  |  | -34235 | 037115 | 0 | -1711.75
999 | Sales | AR | 676 | 06/20/18 | 06/20/18 | 2042SH | Boren and Spruce, LLC $Metro Line Flats |  |  |  |  | -9060 | 037115 | 0 | -453
999 | Sales | AR | 676 | 06/20/18 | 06/20/18 | 2042SH | Boren and Spruce, LLC $Metro Line Flats |  |  |  |  | -32640 | 037115 | 0 | -1632
999 | Sales | AR | 676 | 06/20/18 | 06/20/18 | 2042SH | Boren and Spruce, LLC $Metro Line Flats |  |  |  |  | -22598 | 037115 | 0 | -1129.9
999 | Sales | AR | 676 | 06/20/18 | 06/20/18 | 2042SH | Boren and Spruce, LLC $Metro Line Flats |  |  |  |  | -942 | 037115 | 0 | -47.1
999 | Sales | AR | 513 | 07/19/18 | 07/19/18 | 2042SH | Boren and Spruce, LLC $Metro Line Flats |  |  |  |  | -5500 | 037125 | 0 | -275
999 | Sales | AR | 513 | 07/19/18 | 07/19/18 | 2042SH | Boren and Spruce, LLC $Metro Line Flats |  |  |  |  | -13280 | 037125 | 0 | -664
999 | Sales | AR | 513 | 07/19/18 | 07/19/18 | 2042SH | Boren and Spruce, LLC $Metro Line Flats |  |  |  |  | -6330 | 037125 | 0 | -316.5
999 | Sales | AR | 513 | 07/19/18 | 07/19/18 | 2042SH | Boren and Spruce, LLC $Metro Line Flats |  |  |  |  | -17465 | 037125 | 0 | -873.25
999 | Sales | AR | 513 | 07/19/18 | 07/19/18 | 2042SH | Boren and Spruce, LLC $Metro Line Flats |  |  |  |  | -9000 | 037125 | 0 | -450
999 | Sales | AR | 513 | 07/19/18 | 07/19/18 | 2042SH | Boren and Spruce, LLC $Metro Line Flats |  |  |  |  | -24955 | 037125 | 0 | -1247.75
999 | Sales | AR | 513 | 07/19/18 | 07/19/18 | 2042SH | Boren and Spruce, LLC $Metro Line Flats |  |  |  |  | -8559 | 037125 | 0 | -427.95
999 | Sales | AR | 513 | 07/19/18 | 07/19/18 | 2042SH | Boren and Spruce, LLC $Metro Line Flats |  |  |  |  | -8560 | 037125 | 0 | -428
999 | Sales | AR | 513 | 07/19/18 | 07/19/18 | 2042SH | Boren and Spruce, LLC $Metro Line Flats |  |  |  |  | -8560 | 037125 | 0 | -428
999 | Sales | AR | 513 | 07/19/18 | 07/19/18 | 2042SH | Boren and Spruce, LLC $Metro Line Flats |  |  |  |  | -6040 | 037125 | 0 | -302
999 | Sales | AR | 513 | 07/19/18 | 07/19/18 | 2042SH | Boren and Spruce, LLC $Metro Line Flats |  |  |  |  | -8160 | 037125 | 0 | -408
999 | Sales | AR | 513 | 07/19/18 | 07/19/18 | 2042SH | Boren and Spruce, LLC $Metro Line Flats |  |  |  |  | -4400 | 037125 | 0 | -220
999 | Sales | AR | 513 | 07/19/18 | 07/19/18 | 2042SH | Boren and Spruce, LLC $Metro Line Flats |  |  |  |  | -4520 | 037125 | 0 | -226
999 | Sales | AR | 513 | 07/19/18 | 07/19/18 | 2042SH | Boren and Spruce, LLC $Metro Line Flats |  |  |  |  | -3000 | 037125 | 0 | -150
999 | Sales | AR | 594 | 08/20/18 | 08/20/18 | 2042SH | Boren and Spruce, LLC $Metro Line Flats |  |  |  |  | -5500 | 037165 | 0 | -275
999 | Sales | AR | 594 | 08/20/18 | 08/20/18 | 2042SH | Boren and Spruce, LLC $Metro Line Flats |  |  |  |  | -10550 | 037165 | 0 | -527.5
999 | Sales | AR | 594 | 08/20/18 | 08/20/18 | 2042SH | Boren and Spruce, LLC $Metro Line Flats |  |  |  |  | -2600 | 037165 | 0 | -130
999 | Sales | AR | 594 | 08/20/18 | 08/20/18 | 2042SH | Boren and Spruce, LLC $Metro Line Flats |  |  |  |  | -9000 | 037165 | 0 | -450
999 | Sales | AR | 594 | 08/20/18 | 08/20/18 | 2042SH | Boren and Spruce, LLC $Metro Line Flats |  |  |  |  | -3700 | 037165 | 0 | -185
999 | Sales | AR | 594 | 08/20/18 | 08/20/18 | 2042SH | Boren and Spruce, LLC $Metro Line Flats |  |  |  |  | -4400 | 037165 | 0 | -220
999 | Sales | AR | 594 | 08/20/18 | 08/20/18 | 2042SH | Boren and Spruce, LLC $Metro Line Flats |  |  |  |  | -4400 | 037165 | 0 | -220
999 | Sales | AR | 594 | 08/20/18 | 08/20/18 | 2042SH | Boren and Spruce, LLC $Metro Line Flats |  |  |  |  | -4400 | 037165 | 0 | -220
999 | Sales | AR | 470 | 09/19/18 | 09/19/18 | 2042SH | Boren and Spruce, LLC $Metro Line Flats |  |  |  |  | -42100 | 037186 | 0 | -2105
999 | Sales | AR | 470 | 09/19/18 | 09/19/18 | 2042SH | Boren and Spruce, LLC $Metro Line Flats |  |  |  |  | -20000 | 037186 | 0 | -1000
999 | Sales | AR | 525 | 10/19/18 | 10/19/18 | 2042SH | Boren and Spruce, LLC $Metro Line Flats |  |  |  |  | -2000 | 037211 | 0 | -100
999 | Sales | AR | 525 | 10/19/18 | 10/19/18 | 2042SH | Boren and Spruce, LLC $Metro Line Flats |  |  |  |  | -1560 | 037211 | 0 | -78
999 | Sales | AR | 525 | 10/19/18 | 10/19/18 | 2042SH | Boren and Spruce, LLC $Metro Line Flats |  |  |  |  | -1560 | 037211 | 0 | -78
999 | Sales | AR | 525 | 10/19/18 | 10/19/18 | 2042SH | Boren and Spruce, LLC $Metro Line Flats |  |  |  |  | -1035 | 037211 | 0 | -51.75
999 | Sales | AR | 356 | 12/14/18 | 12/14/18 | 2042SH | Boren and Spruce, LLC $Metro Line Flats |  |  |  |  | -1560 | 037259 | 0 | -78
999 | Sales | AR | 356 | 12/14/18 | 12/14/18 | 2042SH | Boren and Spruce, LLC $Metro Line Flats |  |  |  |  | -1560 | 037259 | 0 | -78
999 | Sales | AR | 356 | 12/14/18 | 12/14/18 | 2042SH | Boren and Spruce, LLC $Metro Line Flats |  |  |  |  | -8840 | 037259 | 0 | -442
999 | Sales | AR | 356 | 12/14/18 | 12/14/18 | 2042SH | Boren and Spruce, LLC $Metro Line Flats |  |  |  |  | -5865 | 037259 | 0 | -293.25
999 | Sales | AR | 554 | 01/18/19 | 01/18/19 | 2042SH | Boren and Spruce, LLC $Metro Line Flats |  |  |  |  | -6100 | 037272 | 0 | -305
999 | Sales | AR | 554 | 01/18/19 | 01/18/19 | 2042SH | Boren and Spruce, LLC $Metro Line Flats |  |  |  |  | -8840 | 037272 | 0 | -442
999 | Sales | AR | 554 | 01/18/19 | 01/18/19 | 2042SH | Boren and Spruce, LLC $Metro Line Flats |  |  |  |  | -8840 | 037272 | 0 | -442
999 | Sales | AR | 554 | 01/18/19 | 01/18/19 | 2042SH | Boren and Spruce, LLC $Metro Line Flats |  |  |  |  | -8840 | 037272 | 0 | -442
999 | Sales | AR | 554 | 01/18/19 | 01/18/19 | 2042SH | Boren and Spruce, LLC $Metro Line Flats |  |  |  |  | -4783 | 037272 | 0 | -239.15
999 | Sales | AR | 686 | 03/20/19 | 03/20/19 | 2042SH | Boren and Spruce, LLC $Metro Line Flats |  |  |  |  | -644 | 037307 | 0 | -32.2
999 | Sales | AR | 797 | 03/25/19 | 03/25/19 | 2042SH | Boren and Spruce, LLC $Metro Line Flats |  |  |  |  | -14770 | 037312 | 0 | -738.5
999 | Sales | AR | 510 | 05/20/19 | 05/20/19 | 2042SH | Boren and Spruce, LLC $Metro Line Flats |  |  |  |  | -1398 | 037343 | 0 | -69.9
999 | Sales | AR | 510 | 05/20/19 | 05/20/19 | 2042SH | Boren and Spruce, LLC $Metro Line Flats |  |  |  |  | -780 | 037343 | 0 | -39

## Cost Code Summaries
COST CODE SUMMARIES — 25 CODES
cost_code | description | original_budget | current_budget | plus_minus_budget | actual_amount | net_due | retainage | regular_hours | overtime_hours | doubletime_hours
100 | Supervision | 5760 | 5760 | -4084 | 1676 | 0 | 0 | 33 | 0 | 0
101 | Takeoff & Purchase Labor | 10440 | 10440 | -2537.5 | 7902.5 | 0 | 0 | 147 | 0 | 0
110 | Underground Labor | 20608 | 20608 | -11831.5 | 8776.5 | 0 | 0 | 249 | 0 | 0
112 | Canout Labor | 3110 | 3550 | 148.5 | 3698.5 | 0 | 0 | 106.5 | 5.5 | 0
120 | Roughin Labor | 105400 | 106060 | 21985 | 128045 | 0 | 0 | 4918.5 | 71.5 | 0
130 | Finish Labor | 21840 | 22595 | -5638.5 | 16956.5 | 0 | 0 | 617.5 | 33.5 | 0
140 | Gas Labor | 2400 | 2400 | -774.5 | 1625.5 | 0 | 0 | 40 | 1 | 0
141 | Water Main/Insulation Lab | 26080 | 26080 | -12446.5 | 13633.5 | 0 | 0 | 562.5 | 23 | 0
142 | Mech Room Labor | 17500 | 17750 | -5723.5 | 12026.5 | 0 | 0 | 284.5 | 0 | 0
210 | Underground Material | 15383 | 15383 | -10156.16 | 5226.84 | 0 | 0 | 0 | 0 | 0
211 | Garage Material | 0 | 0 | 1607.11 | 1607.11 | 0 | 0 | 0 | 0 | 0
212 | Canout Material | 3480 | 3480 | -512.37 | 2967.63 | 0 | 0 | 0 | 0 | 0
220 | Roughin Material | 74450 | 74650 | -12521.6 | 62128.4 | 0 | 0 | 0 | 0 | 0
230 | Finish Material | 162699 | 168539 | -20205.32 | 148333.68 | 0 | 0 | 0 | 0 | 0
240 | Gas Material | 7150 | 7150 | -6484.33 | 665.67 | 0 | 0 | 0 | 0 | 0
241 | Water Main/Insulation Mat | 8935 | 8935 | 4228.4 | 13163.4 | 0 | 0 | 0 | 0 | 0
242 | Mech Room Material | 38400 | 38653 | -22593.29 | 16059.71 | 0 | 0 | 0 | 0 | 0
243 | Condensation Drains Mat | 0 | 0 | 91.07 | 91.07 | 0 | 0 | 0 | 0 | 0
600 | Subcontractor | 1000 | 1000 | -785 | 215 | 0 | 0 | 0 | 0 | 0
601 | Engineering/Plans | 27000 | 27000 | 5640.89 | 32640.89 | 0 | 0 | 0 | 0 | 0
603 | Permits & Licenses | 5930 | 5930 | -1155.5 | 4774.5 | 0 | 0 | 0 | 0 | 0
607 | Other Expenses | 8500 | 8500 | 1812.7 | 10312.7 | 0 | 0 | 0 | 0 | 0
995 | Payroll Burden | 94526.7 | 95452.9 | -9262.75 | 86190.15 | 0 | 0 | 0 | 0 | 0
998 | Payroll Taxes | 16305.06 | 16466.1 | -1598.83 | 14867.27 | 0 | 0 | 0 | 0 | 0
999 | Sales | -906587 | -922104 | 0 | -922104 | 0 | -46105.2 | 0 | 0 | 0

## Worker Wages
WORKER NOMINAL WAGES — 35 WORKERS
Per-worker wage data derived from Line Items (source=PR). nominal_rate = regular_amount ÷ regular_hours — the worker's declared hourly rate as booked by Sage PR. Sorted by nominal rate (ascending) within tier.
Worker (Last, First) | Reg Hours | OT Hours | Reg Amount | OT Amount | Nominal Rate ($/hr)
APPRENTICE/HELPER
Hubbard, Dustin R | 6 | 0 | 42 | 0 | 7
Reyes, Maria E | 272 | 10.5 | 3744 | 283.5 | 13.7647
Hoeg, Xavier A | 83 | 3 | 1245 | 67.5 | 15
Trower-Kelly, Fidel D | 40 | 5 | 640 | 120 | 16
Lucas Tzintzun, Rafael | 757.5 | 14 | 12441 | 348 | 16.4238
Belcher, Jacob T | 518 | 14 | 8699 | 348 | 16.7934
Stahlschmidt, John P | 8 | 0 | 136 | 0 | 17
Velasquez Cruz, Osman N | 225 | 2 | 3971 | 57 | 17.6489
Fonseca Teruel, Eduardo | 24 | 0.5 | 432 | 13.5 | 18
Lopez Reyes, Boris O | 16 | 0 | 288 | 0 | 18
Roberts, Lake A | 4 | 2 | 72 | 54 | 18
Hernandez Gonzalez, Osbaldo | 5.5 | 0 | 104.5 | 0 | 19
Cortes Mendiola, Victor H | 16 | 0 | 0 | 0 | 0
JOURNEYMAN
Mendoza, Edgar E | 885 | 14 | 18343 | 438 | 20.7266
Barbosa, Michael S | 30 | 0 | 630 | 0 | 21
Cruz Guzman, Joel A | 651 | 14 | 14846 | 474 | 22.8049
Gomez Reyes, Edith N | 184 | 8.5 | 4232 | 293.25 | 23
Cruz Reyes, Jose | 672 | 10 | 15993 | 357 | 23.7991
Kinssies, Jr, John E | 79.5 | 0 | 1908 | 0 | 24
Martinez Reyes, Juan C | 30 | 0 | 720 | 0 | 24
Silva Morales, Jair J | 53 | 0 | 1272 | 0 | 24
Eliassen, Cory H | 29.5 | 2 | 737.5 | 75 | 25
Wennig, Johnathan M | 20.75 | 0 | 539.5 | 0 | 26
Velasquez Cruz, Denis M | 200 | 2 | 5400 | 81 | 27
Garcia, Jordan X | 267 | 0 | 8277 | 0 | 31
Sepulveda Gonzalez, Alfredo | 19 | 0 | 608 | 0 | 32
McCabe, Thomas C | 58 | 0 | 1914 | 0 | 33
Gerard, Jordan E | 13 | 0 | 442 | 0 | 34
LEAD/SUPERVISOR
Reed, Reuben H | 1255 | 16 | 51078 | 975 | 40.6996
Hubbard, Robert W | 160 | 1 | 6662 | 73.5 | 41.6375
Anderson, Richard P | 57.25 | 0 | 2404.5 | 0 | 42
Barnhart, Joseph N | 157.5 | 5.5 | 6966 | 363 | 44.2286
Sanders, Allen O | 101 | 10.5 | 4751 | 740.25 | 47.0396
Gerard, Jeffrey S | 86 | 0 | 4116 | 0 | 47.8605
Donelson, Richard T | 97 | 0 | 5525 | 0 | 56.9588

## Derived Fields
DERIVED FIELDS — 40 CALCULATIONS
All derived values computed from parsed data. v4 schema (2026-04-18): Reconciliation Actions #1, #2, #3, #7, #8, #9 applied. Fields mirror Job 2020 test-labels.
Field | Value | Formula / Logic
PROJECT-LEVEL BENCHMARKS (Action #8, trade-agnostic)
project_duration_months | pending (requires project_start_date) | (COALESCE(project_end_date, MAX(line_items[].document_date)) − project_start_date) ÷ 30.4
scope_benchmarks | pending (requires scope_metrics input) | One object per scope_metrics entry: {label, dollars_per_unit, hours_per_unit, units_per_month, revenue_per_unit}
COST-BY-SOURCE ROLLUPS
cost_by_source_pr_amount | 295397.92 | SUM(line_items[].actual_amount WHERE source=PR)
cost_by_source_ap_amount | 268713.5 | SUM(line_items[].actual_amount WHERE source=AP)
cost_by_source_gl_amount | 29473.1 | SUM(line_items[].actual_amount WHERE source=GL)
direct_cost | 593584.52 | PR + AP + GL totals
net_profit | 328519.48 | abs(revenue) − direct_cost. Sage stores revenue as negative (credit); we use absolute value.
pr_pct_of_revenue | 0.32035 | PR total ÷ abs(revenue)
ap_pct_of_revenue | 0.29141 | AP total ÷ abs(revenue)
direct_cost_pct_of_revenue | 0.64373 | direct_cost ÷ abs(revenue). Complement of gross margin.
LABOR ANALYTICS
total_labor_hours | 7215 | SUM(regular + overtime hours, PR only)
pr_src_cost_per_hr | 40.9422 | PR total ÷ total_labor_hours (includes OT premium)
fully_loaded_wage | 54.9488 | (PR + burden) ÷ total_labor_hours — includes burden & taxes on top of pr_src_cost_per_hr
burden_multiplier | 1.3421 | fully_loaded_wage ÷ pr_src_cost_per_hr
straight_time_rate | 26.7183 | SUM(regular_amount) ÷ SUM(regular_hours). Weighted straight-time rate; excludes OT premium.
worker_nominal_wages | 35 workers (see Worker Wages tab) | GROUP BY name WHERE source=PR; per-worker {reg_h, ot_h, reg_a, ot_a, nominal_rate=reg_a÷reg_h}
nominal_wage_percentiles | p10=$15.40 ¦ p25=$17.82 ¦ p50=$23.80 ¦ p75=$32.50 ¦ p90=$43.34 | Percentile snapshot across worker_nominal_wages[].nominal_rate
total_workers | 35 | COUNT DISTINCT(name WHERE source=PR)
burden_total | 101057.42 | SUM(actual WHERE cost_code IN 995,998)
MATERIAL ANALYTICS
material_spend_total | 250243.51 | SUM(actual WHERE code LIKE 2xx)
material_budget_total | 316790 | SUM(current_budget WHERE code LIKE 2xx)
material_codes_tracked | 9 | COUNT material cost codes
material_codes_over_budget | 3 | COUNT material codes WHERE plus_minus_budget > 0 [convention: actual − current_budget, positive = over]
material_codes_under_budget | 6 | COUNT material codes WHERE plus_minus <= 0
largest_material_overrun | 241 Water Main/Insulation Mat: $13,163 vs $8,935 budget (+$4,228) | Material code with largest positive plus_minus (biggest overrun)
largest_material_savings | 242 Mech Room Material: $16,060 vs $38,653 budget ($-22,593) | Material code with largest negative plus_minus (biggest savings)
material_vendor_count | 18 | COUNT DISTINCT(name WHERE source=AP)
top_vendor_spend | Rosen Supply Company, Inc. $Metro Flats: $49,363 (18% of AP) | Vendor with highest AP spend
PHASE ANALYTICS
phases_over_budget | 7 | COUNT phases WHERE plus_minus > 0 AND code != 999 (sales)
phases_under_budget | 17 | COUNT phases WHERE plus_minus <= 0 AND code != 999 (sales)
largest_overrun | 120 Roughin Labor: $128,045 vs $106,060 budget (+$21,985) | Phase with largest positive plus_minus (biggest overrun)
largest_savings | 242 Mech Room Material: $16,060 vs $38,653 budget ($-22,593) | Phase with largest negative plus_minus (biggest savings)
BUDGET & FORECAST
total_jtd_cost | 593584.52 | SUM(actual) all expense codes (excludes 999 revenue)
total_budget | 686382 | SUM(current_budget) all expense codes (excludes 999 revenue)
overall_pct_budget_consumed | 0.8648 | total_jtd ÷ total_budget
total_over_under_budget | 92797.48 | total_budget − total_jtd. Negative = over budget.
variance_trend | N/A (single snapshot) | Requires prior period comparison
labor_unit_cost_per_hr | 26.9356 | labor-code JTD ÷ total_labor_hours. Unit cost per labor hour (NOT throughput).
revenue_per_labor_hour | 127.8037 | abs(job_totals_revenue) ÷ total_labor_hours. Labor throughput — revenue generated per labor hour.
material_price_variance | 66546.49 | material_budget − material_spend. Positive = under budget.

## Reconciliation
RECONCILIATION — PER COST CODE
Parsed line item sums vs. cost code totals from the PDF
Cost Code | Description | PDF Total | Parsed Sum | Difference | Status
100 | Supervision | 1676 | 1676 | 0 | ✓
101 | Takeoff & Purchase Labor | 7902.5 | 7902.5 | 0 | ✓
110 | Underground Labor | 8776.5 | 8776.5 | 0 | ✓
112 | Canout Labor | 3698.5 | 3698.5 | 0 | ✓
120 | Roughin Labor | 128045 | 128045 | 0 | ✓
130 | Finish Labor | 16956.5 | 16956.5 | 0 | ✓
140 | Gas Labor | 1625.5 | 1625.5 | 0 | ✓
141 | Water Main/Insulation Lab | 13633.5 | 13633.5 | 0 | ✓
142 | Mech Room Labor | 12026.5 | 12026.5 | 0 | ✓
210 | Underground Material | 5226.84 | 5226.84 | 0 | ✓
211 | Garage Material | 1607.11 | 1607.11 | 0 | ✓
212 | Canout Material | 2967.63 | 2967.63 | 0 | ✓
220 | Roughin Material | 62128.4 | 62128.4 | 0 | ✓
230 | Finish Material | 148333.68 | 148333.68 | 0 | ✓
240 | Gas Material | 665.67 | 665.67 | 0 | ✓
241 | Water Main/Insulation Mat | 13163.4 | 13163.4 | 0 | ✓
242 | Mech Room Material | 16059.71 | 16059.71 | 0 | ✓
243 | Condensation Drains Mat | 91.07 | 91.07 | 0 | ✓
600 | Subcontractor | 215 | 215 | 0 | ✓
601 | Engineering/Plans | 32640.89 | 32640.89 | 0 | ✓
603 | Permits & Licenses | 4774.5 | 4774.5 | 0 | ✓
607 | Other Expenses | 10312.7 | 10312.7 | 0 | ✓
995 | Payroll Burden | 86190.15 | 86190.15 | 0 | ✓
998 | Payroll Taxes | 14867.27 | 14867.27 | 0 | ✓
999 | Sales | -922104 | -922104 | 0 | ✓
RESULT: 25/25 codes reconciled

## Reconciliation Log
RECONCILIATION LOG — Job 2042
Worked example of the Reconciliation Protocol running against Job 2042 (JCR-only — no external cross-checks). Each row shows the JCR-derived value, the cross-check value, and the observed status. Protocol contract lives in JCR Schema v4 → Reconciliation Protocol tab.
check_id | field_name | JCR-derived value | cross-check value | cross-check source | status | notes
RC-01 | plus_minus_budget | Row summary: 120 Roughin Labor: $128,045 vs $106,060 budget (+$21,985) | Largest overrun spot-check: actual − current_budget ties to cent | Cost Code Summaries (internal recomputation) | PASS | Action #1 sign convention: positive = over-budget. Spot-check recomputes plus_minus from actual − current_budget; matches PDF value to the cent.
RC-02 | current_budget / original_budget | current_budget total = $686,382; original_budget carried per cost code (see Cost Code Summaries tab) | Sum of org_budget across expense codes differs where COs shifted budget | Cost Code Summaries tab (column C vs column D) | PASS | Both budgets carried distinctly per Action #2. Current budget differs from original on codes that had change orders.
RC-03 | pr_src_cost_per_hr | $40.94 / hr (all PR-source cost ÷ total labor hours) | Manual recomputation: PR total $295,397.92 ÷ 7,215.00 hrs = $40.94 | Derived Fields tab (line items → source=PR) | PASS | Phase-code filter: include all phases incl. 995 burden and 998 taxes; exclude only 999 Sales. Matches Action #3 convention from Job 2020.
RC-04 | worker_nominal_wages[] / nominal_wage_percentiles | p10=$15.40 ¦ p25=$17.82 ¦ p50=$23.80 ¦ p75=$32.50 ¦ p90=$43.34 (35 workers) | straight_time_rate = $26.72 (weighted average) | Worker Wages tab + straight_time_rate derived field | PASS | Population-slice sanity: weighted straight_time_rate falls within p25–p75 range, which is expected for this workforce composition.
RC-05 | labor_unit_cost_per_hr vs revenue_per_labor_hour | cost = $26.94/hr ¦ revenue = $127.80/hr ¦ ratio = 4.74x | Recompute: labor-code total ÷ 7,215.00 hrs | Derived Fields tab (Action #7 split) | PASS | Split into two fields per Action #7. Cost and throughput are distinct metrics; their ratio is the productivity signal.
RC-06 | scope_metrics[] / scope_benchmarks | pending | — | project-attribute input (trade-declared) | PENDING | Awaiting plumbing scope-metric declarations for Job 2042 (e.g., fixture count, DFU total, linear feet of main). Labeler should not emit scope_benchmarks until scope_metrics is populated.
RC-07 | reconciliation (per-code parse tie-out) | 25/25 codes tie to PDF to the cent | PR: $295,397.92 ¦ AP: $268,713.50 ¦ GL: $29,473.10 all match by_source | Reconciliation tab | PASS | Independent sum of line_items[] by cost_code vs. Cost Code Totals row for each code. Status PASS if ¦diff¦ < $0.02 for all codes.
SUMMARY
Total checks | 7
PASS | 6
PENDING | 1
FAIL | 0
How to use: when a labeler produces a new set of derived values for Job 2042, update columns C and D in the rows above and set status per the Protocol contract.