## Overview
OWP JOB 2043 — COMPASS HARBOR AEGIS MERCER ISLAND
Cortex JCR v2 — 17-tab Job Cost Report. Aligned with v4 Test-Labels schema (Sam coverage parity). Parsed from 175-page Sage Timberline JDR dated Apr 03, 2026.
REVENUE (AR) |  | DIRECT COST |  | NET PROFIT |  | LABOR HOURS
$1,583,445 |  | $855,439 |  | $728,006 |  | 11,019
Billed to date (Sage AR) |  | 54.0% of revenue |  | 46.0% margin |  | 32 workers
COST BREAKDOWN (by category)
Category | Budget | Actual | Variance | Consumption | % of Direct
Labor | 368155 | 325026 | 43129 | 88.29% | 38%
Material | 551921 | 320019.62 | 231901.38 | 57.98% | 37.41%
Overhead | 76500 | 41379.57 | 35120.43 | 54.09% | 4.837%
Burden | 191408.03 | 169014.06 | 22393.97 | 88.3% | 19.76%
TOTAL (expense codes) | 1187984.03 | 855439.25 | 332544.78 | 72.01% | 100%
COST BY SOURCE (PR / AP / GL / AR)
Source | Amount | % of Direct | Notes
PR (Payroll) | 494040.06 | 57.75% | Worker hours + wages (reg + OT + burden)
AP (Vendor Invoices) | 332151.59 | 38.83% | Material + subcontractor spend
GL (General Ledger) | 29247.6 | 3.419% | Misc adjustments + deposits
AR (Billings, credit) | -1583445 | 100% | Revenue billed to GC (stored negative)

## Job Info
JOB INFORMATION — 2043
Project identity + metadata enriched from GDrive close-out package (Aegis Mercer Island project info PDF, signed subcontract, permits, scope).
Field | Value | Source / Notes
job_number | 2043 | JDR cover page
job_name | Compass Aegis-Mercer Isl | Aegis Mercer Island project info PDF
job_name_long | Aegis Mercer Island (Assisted Living + Memory Care) | Aegis Mercer Island project info PDF
general_contractor | Compass Harbor | Signed subcontract SC-17-04-022-100-000 — Shelter Holdings / ASC Mercer Island, LLC
owner | ASC Mercer Island, LLC (Aegis Senior Communities) | Signed subcontract §A.a — ASC Mercer Island, LLC
architect | Ankrom Moisan Architects (AMA) / CEI + Ricca kitchen | Contract counterparty: ASC Mercer Island, LLC
location | 7445 SE 24th Street, Mercer Island, WA 98040 | Signed subcontract + permit records
project_type | Multi-story assisted living & memory care (senior living): 93 assisted living units (incl. 10 Type A ADA) + 16 memory care units + commercial/amenity (salon, barber, bathtique, pool, LN dining, bistro, boutiques) | Scope doc + submittal TOC (4-story mixed-use + 2 parking levels)
unit_count | 109 | Plan drawings: 7-story, 72 units (studios, open 1-BR, 1-BR, 2-BR, 4 Type A ADA)
fixture_count | 643 | Estimate from scope doc + submittal TOC (see fixture_estimate_note)
fixture_estimate_note | Derived from 01/30/19 Job Ticket: 93 res units (toilets+lavs+showers+R-10000 valves+kitchen sinks+washer/icemaker boxes) ~5-6 fixtures each = ~540 + 16 memory-care ~32 + common/amenity (pool shower, 13 undermount lavs, 8 kitchen sinks, 2 eyewash, 2 svc sinks, drinking fountain, trench drains, mechanical) ~71 = ~643. Refine via submittal TOC. | Explains fixture_count basis
parking_levels | 1 | Scope doc — P1, P2 rough-in sequence
floors_residential | 6 | Scope doc — L1-L4 rough-in sequence
project_start_date | 2017-09 | JDR first posting 9/8/17 → contract 7/21/17 → construction start Sep 2017
project_end_date | 2019-05 | Final lien release 12/12/2019
duration_months | 20 | start → end
contract_signed | 2017-08-28 | Signed subcontract — Mike Donelson 3/9/18
permit_jurisdiction | City of Mercer Island | City of Mercer Island permit (Phase I + Phase II plumbing)
permits_issued | Plumbing Phase I permit (Sept 2017); Plumbing Phase II permit (per COR#03 Phase II Permit 01-24-18); Gas permit (with Phase I issuance); Backflow permit | Permits folder: 3 permit types × renewals/extensions
status | CLOSED | Inferred from JDR filter: "Job 2043 only, Open, Closed"
report_date | 2026-04-03 | JDR run date

## Contract Summary
CONTRACT SUMMARY — 2043
Contract basis derived from Cost Code 999 Sales (billed AR) and expense-code budgets (Sage "Original" and "Revised" columns). Revised–Original delta = net change-order impact on internal budget.
Field | Value | Notes
original_contract_budget | 1576200 | Code 999 original (negated)
current_contract_budget | 1583445 | Code 999 current (negated)
revenue_ar_billed | 1583445 | Sum of AR line items (abs)
retainage_outstanding | 79172.25 | Sum of AR retainage column
net_due | 0 | Sage job_totals_net_due
expense_original_budget | 1185331.8 | Sum of Org Budget across 100-607,995,998
expense_current_budget | 1187984.03 | Sum of Rev Budget across 100-607,995,998
change_orders_to_budget | 2652.23 | Revised − Original across expense codes
direct_cost | 855439.25 | PR + AP + GL totals
net_profit | 728005.75 | abs(revenue) − direct_cost
gross_margin_pct | 45.98% | net / revenue

## Cost Categories
COST CATEGORIES — 2043
Rollup of the 29 Sage cost codes into five taxonomic buckets: Labor (1xx), Material (2xx), Overhead (6xx), Burden (995/998), Revenue (999).
Category | Code Count | Original Budget | Current Budget | Actual | Variance | Consumption % | Per-Unit Cost*
Labor | 11 | 358840 | 368155 | 325026 | 43129 | 88.29% | PENDING (needs unit_count)
Material | 9 | 548895 | 551921 | 320019.62 | 231901.38 | 57.98% | PENDING (needs unit_count)
Overhead | 5 | 91000 | 76500 | 41379.57 | 35120.43 | 54.09% | PENDING (needs unit_count)
Burden | 2 | 186596.8 | 191408.03 | 169014.06 | 22393.97 | 88.3% | PENDING (needs unit_count)
Revenue | 1 | -1576200 | -1583445 | -1583445 | 0 | 100% | PENDING (needs unit_count)

## Budget vs Actual
BUDGET vs ACTUAL — 29 COST CODES
Full cost-code ledger with original/revised/actual/variance. Matches Sam Cost Code Summaries tab exactly. Labor codes include hours breakdown (reg/ot/dt).
Code | Description | Category | Original Budget | Current Budget | +/- Budget | Actual | Net Due | Retainage | Reg Hours | OT Hours | DT Hours | Consumption % | Status
100 | Supervision | Labor | 12900 | 13200 | -9689.5 | 3510.5 | 0 | 0 | 69.5 | 0 | 0 | 26.59% | UNDER
101 | Takeoff & Purchase Labor | Labor | 20900 | 21200 | -5802 | 15398 | 0 | 0 | 277.5 | 0 | 0 | 72.63% | UNDER
110 | Underground Labor | Labor | 35740 | 39130 | -19020.5 | 20109.5 | 0 | 0 | 579.5 | 16.5 | 0 | 51.39% | UNDER
111 | Garage Labor | Labor | 51800 | 53120 | -27885.5 | 25234.5 | 0 | 0 | 855.5 | 8 | 0 | 47.5% | UNDER
112 | Canout Labor | Labor | 6960 | 7380 | 2685 | 10065 | 0 | 0 | 290 | 0 | 0 | 136.4% | OVER
120 | Roughin Labor | Labor | 139140 | 143130 | 3348 | 146478 | 0 | 0 | 5116.5 | 136.5 | 0 | 102.3% | ON
130 | Finish Labor | Labor | 30640 | 28735 | -3262 | 25473 | 0 | 0 | 758 | 164.5 | 0 | 88.65% | UNDER
140 | Gas Labor | Labor | 11900 | 11900 | -2195 | 9705 | 0 | 0 | 265 | 10 | 0 | 81.55% | UNDER
141 | Water Main/Insulation Lab | Labor | 38260 | 39220 | 5892 | 45112 | 0 | 0 | 1583 | 62 | 0 | 115% | OVER
142 | Mech Room Labor | Labor | 10600 | 11140 | -490.5 | 10649.5 | 0 | 0 | 285 | 3 | 0 | 95.6% | ON
143 | Condensation Drains Labor | Labor | 0 | 0 | 13291 | 13291 | 0 | 0 | 475 | 14 | 0 | 0% | UNDER
210 | Underground Material | Material | 33850 | 34823 | -22979.21 | 11843.79 | 0 | 0 | 0 | 0 | 0 | 34.01% | UNDER
211 | Garage Material | Material | 28205 | 31448 | -9072.53 | 22375.47 | 0 | 0 | 0 | 0 | 0 | 71.15% | UNDER
212 | Canout Material | Material | 8700 | 9582 | -2842.68 | 6739.32 | 0 | 0 | 0 | 0 | 0 | 70.33% | UNDER
220 | Roughin Material | Material | 53365 | 54365 | -23672.48 | 30692.52 | 0 | 0 | 0 | 0 | 0 | 56.46% | UNDER
230 | Finish Material | Material | 328175 | 321400 | -120712.35 | 200687.65 | 0 | 0 | 0 | 0 | 0 | 62.44% | UNDER
240 | Gas Material | Material | 14400 | 14400 | -10619.75 | 3780.25 | 0 | 0 | 0 | 0 | 0 | 26.25% | UNDER
241 | Water Main/Insulation Mat | Material | 51400 | 52597 | -22777.76 | 29819.24 | 0 | 0 | 0 | 0 | 0 | 56.69% | UNDER
242 | Mech Room Material | Material | 30800 | 33306 | -20499.62 | 12806.38 | 0 | 0 | 0 | 0 | 0 | 38.45% | UNDER
243 | Condensation Drains Mat | Material | 0 | 0 | 1275 | 1275 | 0 | 0 | 0 | 0 | 0 | 0% | UNDER
600 | Subcontractor | Overhead | 1000 | 1000 | 3122.5 | 4122.5 | 0 | 0 | 0 | 0 | 0 | 412.2% | CRITICAL
601 | Engineering/Plans | Overhead | 55000 | 55500 | -26240.25 | 29259.75 | 0 | 0 | 0 | 0 | 0 | 52.72% | UNDER
602 | Rental Equipment | Overhead | 10000 | 10000 | -7420.5 | 2579.5 | 0 | 0 | 0 | 0 | 0 | 25.8% | UNDER
603 | Permits & Licenses | Overhead | 18000 | 3000 | -2712.18 | 287.82 | 0 | 0 | 0 | 0 | 0 | 9.594% | UNDER
607 | Other Expenses | Overhead | 7000 | 7000 | -1870 | 5130 | 0 | 0 | 0 | 0 | 0 | 73.29% | UNDER
995 | Payroll Burden | Burden | 159145.54 | 163244.14 | -19095.06 | 144149.08 | 0 | 0 | 0 | 0 | 0 | 88.3% | UNDER
998 | Payroll Taxes | Burden | 27451.26 | 28163.89 | -3298.91 | 24864.98 | 0 | 0 | 0 | 0 | 0 | 88.29% | UNDER
999 | Sales | Revenue | -1576200 | -1583445 | 0 | -1583445 | 0 | -79172.25 | 0 | 0 | 0 | 100% | —

## Cost Code Detail
COST CODE DETAIL — 2043
Per-code drill-down: transaction count, source mix, top vendor/worker, date range. Derived from line_items[] grouped by cost_code.
Code | Description | Actual | Txn Count | PR Lines | AP Lines | GL Lines | AR Lines | Top Vendor / Worker | First Date | Last Date
100 | Supervision | 3510.5 | 46 | 46 | 0 | 0 | 0 | Gerard, Jeffrey S ($2,548) | 01/12/18 | 12/29/17
101 | Takeoff & Purchase Labor | 15398 | 103 | 103 | 0 | 0 | 0 | Donelson, Richard T ($12,362) | 01/04/19 | 12/28/18
110 | Underground Labor | 20109.5 | 38 | 38 | 0 | 0 | 0 | Cortes Mendiola, Victor H ($10,690) | 01/05/18 | 12/29/17
111 | Garage Labor | 25234.5 | 47 | 47 | 0 | 0 | 0 | Cortes Mendiola, Victor H ($7,480) | 02/01/19 | 06/08/18
112 | Canout Labor | 10065 | 23 | 23 | 0 | 0 | 0 | Hubbard, Robert W ($3,960) | 01/19/18 | 12/21/18
120 | Roughin Labor | 146478 | 241 | 241 | 0 | 0 | 0 | Cortes Mendiola, Victor H ($34,234) | 01/04/19 | 12/14/18
130 | Finish Labor | 25473 | 109 | 109 | 0 | 0 | 0 | Sanders, Allen O ($8,438) | 01/04/19 | 12/28/18
140 | Gas Labor | 9705 | 39 | 39 | 0 | 0 | 0 | Cortes Mendiola, Victor H ($5,718) | 01/11/19 | 11/02/18
141 | Water Main/Insulation Lab | 45112 | 95 | 95 | 0 | 0 | 0 | Lima Romero, Melvin A ($19,317) | 04/06/18 | 09/28/18
142 | Mech Room Labor | 10649.5 | 41 | 41 | 0 | 0 | 0 | Cortes Mendiola, Victor H ($4,884) | 01/04/19 | 12/28/18
143 | Condensation Drains Labor | 13291 | 33 | 33 | 0 | 0 | 0 | Ascencio, Jose L ($5,356) | 01/04/19 | 12/28/18
210 | Underground Material | 11843.79 | 21 | 0 | 18 | 3 | 0 | Rosen Supply Company, Inc. $Aegis MI ($11,215) | 01/05/18 | 12/22/17
211 | Garage Material | 22375.47 | 35 | 0 | 10 | 25 | 0 | Rosen Supply Company, Inc. $Aegis MI ($21,657) | 01/11/19 | 12/21/17
212 | Canout Material | 6739.32 | 8 | 0 | 1 | 7 | 0 | Keller Supply Co. $Aegis MI ($4,291) | 01/17/18 | 03/26/18
220 | Roughin Material | 30692.52 | 53 | 0 | 22 | 31 | 0 | Consolidated Supply Co. $Aegis MI ($11,392) | 01/11/19 | 12/31/18
230 | Finish Material | 200687.65 | 119 | 0 | 84 | 35 | 0 | Keller Supply Co. $Aegis MI ($71,268) | 01/07/19 | 12/31/18
240 | Gas Material | 3780.25 | 35 | 0 | 21 | 14 | 0 | Req 4559 ($2,152) | 01/23/19 | 12/31/18
241 | Water Main/Insulation Mat | 29819.24 | 50 | 0 | 27 | 23 | 0 | Consolidated Supply Co. $Aegis MI ($18,478) | 01/07/19 | 12/31/18
242 | Mech Room Material | 12806.38 | 30 | 0 | 16 | 14 | 0 | Ferguson Enterprises, Inc. #3007 ($8,603) | 01/07/19 | 12/31/18
243 | Condensation Drains Mat | 1275 | 14 | 0 | 7 | 7 | 0 | Rosen Supply Kirkland ($723) | 01/23/19 | 11/13/18
600 | Subcontractor | 4122.5 | 2 | 0 | 2 | 0 | 0 | Mechanical Resource Services, Inc. ($4,072) | 03/26/19 | 05/29/19
601 | Engineering/Plans | 29259.75 | 6 | 0 | 6 | 0 | 0 | Franklin Engineering ($29,260) | 01/05/18 | 11/22/17
602 | Rental Equipment | 2579.5 | 7 | 0 | 7 | 0 | 0 | Ahern Rentals ($2,580) | 05/22/18 | 11/05/18
603 | Permits & Licenses | 287.82 | 2 | 0 | 2 | 0 | 0 | Capital One Credit Card ($288) | 04/30/19 | 04/30/19
607 | Other Expenses | 5130 | 18 | 0 | 18 | 0 | 0 | Capital One Credit Card ($4,845) | 01/31/18 | 12/31/18
995 | Payroll Burden | 144149.08 | 815 | 815 | 0 | 0 | 0 | Cortes Mendiola, Victor H ($31,701) | 01/04/19 | 12/29/17
998 | Payroll Taxes | 24864.98 | 815 | 815 | 0 | 0 | 0 | Cortes Mendiola, Victor H ($5,468) | 01/04/19 | 12/29/17
999 | Sales | -1583445 | 127 | 0 | 0 | 0 | 127 | Compass Harbor Construction 1,LLC $Aegis ($4,108,795) | 01/18/19 | 12/14/18

## Transactions Detail
TRANSACTIONS DETAIL — 2,972 LINE ITEMS
Every transaction parsed from the JDR. AR amounts are negative per Sage convention (credits). Mirrors Sam Line Items tab 1:1.
cost_code | description | source | ref_number | document_date | posted_date | number | name | regular_hours | overtime_hours | regular_amount | overtime_amount | actual_amount | check_number | net_due | retainage
100 | Supervision | PR | 362 | 09/13/17 | 09/15/17 | GE69 | Gerard, Jeffrey S | 1 | 0 | 47 | 0 | 47 | 17449 | 0 | 0
100 | Supervision | PR | 544 | 09/20/17 | 09/22/17 | DO56 | Donelson, Richard T | 2 | 0 | 100 | 0 | 100 | 17514 | 0 | 0
100 | Supervision | PR | 545 | 09/20/17 | 09/22/17 | GE69 | Gerard, Jeffrey S | 1 | 0 | 47 | 0 | 47 | 17515 | 0 | 0
100 | Supervision | PR | 67 | 10/04/17 | 10/06/17 | DO56 | Donelson, Richard T | 2 | 0 | 100 | 0 | 100 | 19638 | 0 | 0
100 | Supervision | PR | 226 | 10/11/17 | 10/13/17 | GE69 | Gerard, Jeffrey S | 1 | 0 | 47 | 0 | 47 | 17702 | 0 | 0
100 | Supervision | PR | 213 | 11/08/17 | 11/10/17 | GE69 | Gerard, Jeffrey S | 2 | 0 | 94 | 0 | 94 | 97956 | 0 | 0
100 | Supervision | PR | 344 | 11/15/17 | 11/17/17 | GE69 | Gerard, Jeffrey S | 3 | 0 | 141 | 0 | 141 | 18020 | 0 | 0
100 | Supervision | PR | 489 | 11/22/17 | 11/22/17 | DO56 | Donelson, Richard T | 2 | 0 | 100 | 0 | 100 | 98001 | 0 | 0
100 | Supervision | PR | 490 | 11/22/17 | 11/22/17 | GE69 | Gerard, Jeffrey S | 2 | 0 | 94 | 0 | 94 | 98002 | 0 | 0
100 | Supervision | PR | 267 | 12/06/17 | 12/08/17 | DO56 | Donelson, Richard T | 2 | 0 | 100 | 0 | 100 | 98214 | 0 | 0
100 | Supervision | PR | 268 | 12/06/17 | 12/08/17 | GE69 | Gerard, Jeffrey S | 1 | 0 | 47 | 0 | 47 | 98215 | 0 | 0
100 | Supervision | PR | 466 | 12/13/17 | 12/15/17 | GE69 | Gerard, Jeffrey S | 1 | 0 | 47 | 0 | 47 | 18280 | 0 | 0
100 | Supervision | PR | 656 | 12/20/17 | 12/22/17 | GE69 | Gerard, Jeffrey S | 2 | 0 | 94 | 0 | 94 | 18410 | 0 | 0
100 | Supervision | PR | 847 | 12/27/17 | 12/29/17 | GE69 | Gerard, Jeffrey S | 1 | 0 | 47 | 0 | 47 | 98476 | 0 | 0
100 | Supervision | PR | 289 | 01/10/18 | 01/12/18 | DO56 | Donelson, Richard T | 2 | 0 | 125 | 0 | 125 | 918604 | 0 | 0
100 | Supervision | PR | 290 | 01/10/18 | 01/12/18 | GE69 | Gerard, Jeffrey S | 1.5 | 0 | 70.5 | 0 | 70.5 | 918605 | 0 | 0
100 | Supervision | PR | 455 | 01/17/18 | 01/19/18 | GE69 | Gerard, Jeffrey S | 2.5 | 0 | 117.5 | 0 | 117.5 | 18670 | 0 | 0
100 | Supervision | PR | 650 | 01/24/18 | 01/26/18 | DO56 | Donelson, Richard T | 1 | 0 | 62.5 | 0 | 62.5 | 18733 | 0 | 0
100 | Supervision | PR | 651 | 01/24/18 | 01/26/18 | GE69 | Gerard, Jeffrey S | 3 | 0 | 141 | 0 | 141 | 18734 | 0 | 0
100 | Supervision | PR | 227 | 02/07/18 | 02/09/18 | GE69 | Gerard, Jeffrey S | 2 | 0 | 94 | 0 | 94 | 18868 | 0 | 0
100 | Supervision | PR | 484 | 02/14/18 | 02/16/18 | GE69 | Gerard, Jeffrey S | 1 | 0 | 47 | 0 | 47 | 18884 | 0 | 0
100 | Supervision | PR | 68 | 02/28/18 | 03/02/18 | GE69 | Gerard, Jeffrey S | 1 | 0 | 47 | 0 | 47 | 100000 | 0 | 0
100 | Supervision | PR | 184 | 03/07/18 | 03/09/18 | GE69 | Gerard, Jeffrey S | 1 | 0 | 47 | 0 | 47 | 99998 | 0 | 0
100 | Supervision | PR | 384 | 03/14/18 | 03/16/18 | DO56 | Donelson, Richard T | 2 | 0 | 125 | 0 | 125 | 19205 | 0 | 0
100 | Supervision | PR | 584 | 03/21/18 | 03/23/18 | GE69 | Gerard, Jeffrey S | 1 | 0 | 50 | 0 | 50 | 99998 | 0 | 0
100 | Supervision | PR | 812 | 03/28/18 | 03/30/18 | GE69 | Gerard, Jeffrey S | 1.5 | 0 | 75 | 0 | 75 | 99351 | 0 | 0
100 | Supervision | PR | 85 | 04/04/18 | 04/06/18 | GE69 | Gerard, Jeffrey S | 2 | 0 | 100 | 0 | 100 | 99427 | 0 | 0
100 | Supervision | PR | 518 | 04/18/18 | 04/20/18 | GE69 | Gerard, Jeffrey S | 1 | 0 | 50 | 0 | 50 | 99576 | 0 | 0
100 | Supervision | PR | 684 | 04/25/18 | 04/27/18 | GE69 | Gerard, Jeffrey S | 2 | 0 | 100 | 0 | 100 | 99649 | 0 | 0
100 | Supervision | PR | 99 | 05/02/18 | 05/04/18 | GE69 | Gerard, Jeffrey S | 2 | 0 | 100 | 0 | 100 | 19722 | 0 | 0
100 | Supervision | PR | 492 | 05/16/18 | 05/18/18 | GE69 | Gerard, Jeffrey S | 1 | 0 | 50 | 0 | 50 | 19865 | 0 | 0
100 | Supervision | PR | 807 | 05/23/18 | 05/25/18 | GE69 | Gerard, Jeffrey S | 3 | 0 | 150 | 0 | 150 | 99936 | 0 | 0
100 | Supervision | PR | 76 | 05/30/18 | 06/01/18 | GE69 | Gerard, Jeffrey S | 1 | 0 | 50 | 0 | 50 | 920008 | 0 | 0
100 | Supervision | PR | 340 | 06/06/18 | 06/08/18 | GE69 | Gerard, Jeffrey S | 1 | 0 | 50 | 0 | 50 | 20080 | 0 | 0
100 | Supervision | PR | 528 | 06/13/18 | 06/15/18 | GE69 | Gerard, Jeffrey S | 1 | 0 | 50 | 0 | 50 | 20163 | 0 | 0
100 | Supervision | PR | 754 | 06/20/18 | 06/22/18 | GE69 | Gerard, Jeffrey S | 1 | 0 | 50 | 0 | 50 | 290233 | 0 | 0
100 | Supervision | PR | 1019 | 06/27/18 | 06/29/18 | DO56 | Donelson, Richard T | 1 | 0 | 62.5 | 0 | 62.5 | 20300 | 0 | 0
100 | Supervision | PR | 1020 | 06/27/18 | 06/29/18 | GE69 | Gerard, Jeffrey S | 1 | 0 | 50 | 0 | 50 | 20301 | 0 | 0
100 | Supervision | PR | 835 | 07/25/18 | 07/27/18 | GE69 | Gerard, Jeffrey S | 1 | 0 | 50 | 0 | 50 | 20593 | 0 | 0
100 | Supervision | PR | 284 | 08/08/18 | 08/10/18 | GE69 | Gerard, Jeffrey S | 1 | 0 | 50 | 0 | 50 | 920737 | 0 | 0
100 | Supervision | PR | 340 | 09/12/18 | 09/14/18 | DO56 | Donelson, Richard T | 1 | 0 | 62.5 | 0 | 62.5 | 21173 | 0 | 0
100 | Supervision | PR | 77 | 10/31/18 | 11/02/18 | GE69 | Gerard, Jeffrey S | 1 | 0 | 50 | 0 | 50 | 21687 | 0 | 0
100 | Supervision | PR | 513 | 11/14/18 | 11/16/18 | DO56 | Donelson, Richard T | 2 | 0 | 125 | 0 | 125 | 21836 | 0 | 0
100 | Supervision | PR | 514 | 11/14/18 | 11/16/18 | GE69 | Gerard, Jeffrey S | 2 | 0 | 100 | 0 | 100 | 21837 | 0 | 0
100 | Supervision | PR | 901 | 11/28/18 | 11/30/18 | GE69 | Gerard, Jeffrey S | 1 | 0 | 52 | 0 | 52 | 921984 | 0 | 0
100 | Supervision | PR | 769 | 12/26/18 | 12/28/18 | GE69 | Gerard, Jeffrey S | 1 | 0 | 52 | 0 | 52 | 22343 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 544 | 09/20/17 | 09/22/17 | DO56 | Donelson, Richard T | 9 | 0 | 450 | 0 | 450 | 17514 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 545 | 09/20/17 | 09/22/17 | GE69 | Gerard, Jeffrey S | 1 | 0 | 47 | 0 | 47 | 17515 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 762 | 09/27/17 | 09/29/17 | GE69 | Gerard, Jeffrey S | 1 | 0 | 47 | 0 | 47 | 19577 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 67 | 10/04/17 | 10/06/17 | DO56 | Donelson, Richard T | 1 | 0 | 50 | 0 | 50 | 19638 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 68 | 10/04/17 | 10/06/17 | GE69 | Gerard, Jeffrey S | 2 | 0 | 94 | 0 | 94 | 19639 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 225 | 10/11/17 | 10/13/17 | DO56 | Donelson, Richard T | 4 | 0 | 200 | 0 | 200 | 17701 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 226 | 10/11/17 | 10/13/17 | GE69 | Gerard, Jeffrey S | 1 | 0 | 47 | 0 | 47 | 17702 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 350 | 10/18/17 | 10/20/17 | DO56 | Donelson, Richard T | 2 | 0 | 100 | 0 | 100 | 97762 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 547 | 10/25/17 | 10/27/17 | DO56 | Donelson, Richard T | 1 | 0 | 50 | 0 | 50 | 17826 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 212 | 11/08/17 | 11/10/17 | DO56 | Donelson, Richard T | 10 | 0 | 500 | 0 | 500 | 97955 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 213 | 11/08/17 | 11/10/17 | GE69 | Gerard, Jeffrey S | 5 | 0 | 235 | 0 | 235 | 97956 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 343 | 11/15/17 | 11/17/17 | DO56 | Donelson, Richard T | 1 | 0 | 50 | 0 | 50 | 18019 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 344 | 11/15/17 | 11/17/17 | GE69 | Gerard, Jeffrey S | 3.5 | 0 | 164.5 | 0 | 164.5 | 18020 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 489 | 11/22/17 | 11/22/17 | DO56 | Donelson, Richard T | 11 | 0 | 550 | 0 | 550 | 98001 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 490 | 11/22/17 | 11/22/17 | GE69 | Gerard, Jeffrey S | 1 | 0 | 47 | 0 | 47 | 98002 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 66 | 11/29/17 | 12/01/17 | DO56 | Donelson, Richard T | 5 | 0 | 250 | 0 | 250 | 98147 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 267 | 12/06/17 | 12/08/17 | DO56 | Donelson, Richard T | 14 | 0 | 700 | 0 | 700 | 98214 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 268 | 12/06/17 | 12/08/17 | GE69 | Gerard, Jeffrey S | 1 | 0 | 47 | 0 | 47 | 98215 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 465 | 12/13/17 | 12/15/17 | DO56 | Donelson, Richard T | 7 | 0 | 350 | 0 | 350 | 18279 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 466 | 12/13/17 | 12/15/17 | GE69 | Gerard, Jeffrey S | 1 | 0 | 47 | 0 | 47 | 18280 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 655 | 12/20/17 | 12/22/17 | DO56 | Donelson, Richard T | 11 | 0 | 550 | 0 | 550 | 18409 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 656 | 12/20/17 | 12/22/17 | GE69 | Gerard, Jeffrey S | 4 | 0 | 188 | 0 | 188 | 18410 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 65 | 01/03/18 | 01/05/18 | DO56 | Donelson, Richard T | 2 | 0 | 125 | 0 | 125 | 98539 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 289 | 01/10/18 | 01/12/18 | DO56 | Donelson, Richard T | 6 | 0 | 375 | 0 | 375 | 918604 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 290 | 01/10/18 | 01/12/18 | GE69 | Gerard, Jeffrey S | 3 | 0 | 141 | 0 | 141 | 918605 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 454 | 01/17/18 | 01/19/18 | DO56 | Donelson, Richard T | 3 | 0 | 187.5 | 0 | 187.5 | 18669 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 455 | 01/17/18 | 01/19/18 | GE69 | Gerard, Jeffrey S | 4.5 | 0 | 211.5 | 0 | 211.5 | 18670 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 457 | 01/17/18 | 01/19/18 | DO56 | Donelson, Richard T | 3 | 0 | -187.5 | 0 | -187.5 | 18669 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 458 | 01/17/18 | 01/19/18 | DO56 | Donelson, Richard T | 3 | 0 | 187.5 | 0 | 187.5 | 18672 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 650 | 01/24/18 | 01/26/18 | DO56 | Donelson, Richard T | 4 | 0 | 250 | 0 | 250 | 18733 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 651 | 01/24/18 | 01/26/18 | GE69 | Gerard, Jeffrey S | 2 | 0 | 94 | 0 | 94 | 18734 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 70 | 01/31/18 | 02/02/18 | DO56 | Donelson, Richard T | 3 | 0 | 187.5 | 0 | 187.5 | 98801 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 71 | 01/31/18 | 02/02/18 | GE69 | Gerard, Jeffrey S | 2.5 | 0 | 117.5 | 0 | 117.5 | 98802 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 227 | 02/07/18 | 02/09/18 | GE69 | Gerard, Jeffrey S | 1 | 0 | 47 | 0 | 47 | 18868 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 483 | 02/14/18 | 02/16/18 | DO56 | Donelson, Richard T | 2 | 0 | 125 | 0 | 125 | 18883 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 484 | 02/14/18 | 02/16/18 | GE69 | Gerard, Jeffrey S | 2 | 0 | 94 | 0 | 94 | 18884 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 670 | 02/21/18 | 02/23/18 | GE69 | Gerard, Jeffrey S | 1 | 0 | 47 | 0 | 47 | 18954 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 183 | 03/07/18 | 03/09/18 | DO56 | Donelson, Richard T | 1 | 0 | 62.5 | 0 | 62.5 | 99997 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 184 | 03/07/18 | 03/09/18 | GE69 | Gerard, Jeffrey S | 3 | 0 | 141 | 0 | 141 | 99998 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 384 | 03/14/18 | 03/16/18 | DO56 | Donelson, Richard T | 1 | 0 | 62.5 | 0 | 62.5 | 19205 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 385 | 03/14/18 | 03/16/18 | GE69 | Gerard, Jeffrey S | 2 | 0 | 100 | 0 | 100 | 19206 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 583 | 03/21/18 | 03/23/18 | DO56 | Donelson, Richard T | 4 | 0 | 250 | 0 | 250 | 99997 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 811 | 03/28/18 | 03/30/18 | DO56 | Donelson, Richard T | 1 | 0 | 62.5 | 0 | 62.5 | 99350 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 812 | 03/28/18 | 03/30/18 | GE69 | Gerard, Jeffrey S | 3 | 0 | 150 | 0 | 150 | 99351 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 85 | 04/04/18 | 04/06/18 | GE69 | Gerard, Jeffrey S | 3 | 0 | 150 | 0 | 150 | 99427 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 333 | 04/11/18 | 04/13/18 | DO56 | Donelson, Richard T | 2 | 0 | 125 | 0 | 125 | 99500 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 334 | 04/11/18 | 04/13/18 | GE69 | Gerard, Jeffrey S | 2 | 0 | 100 | 0 | 100 | 99501 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 517 | 04/18/18 | 04/20/18 | DO56 | Donelson, Richard T | 3 | 0 | 187.5 | 0 | 187.5 | 99575 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 684 | 04/25/18 | 04/27/18 | GE69 | Gerard, Jeffrey S | 5 | 0 | 250 | 0 | 250 | 99649 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 99 | 05/02/18 | 05/04/18 | GE69 | Gerard, Jeffrey S | 1 | 0 | 50 | 0 | 50 | 19722 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 286 | 05/09/18 | 05/11/18 | DO56 | Donelson, Richard T | 3 | 0 | 187.5 | 0 | 187.5 | 99793 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 287 | 05/09/18 | 05/11/18 | GE69 | Gerard, Jeffrey S | 2 | 0 | 100 | 0 | 100 | 99794 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 492 | 05/16/18 | 05/18/18 | GE69 | Gerard, Jeffrey S | 1 | 0 | 50 | 0 | 50 | 19865 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 806 | 05/23/18 | 05/25/18 | DO56 | Donelson, Richard T | 1 | 0 | 62.5 | 0 | 62.5 | 99935 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 76 | 05/30/18 | 06/01/18 | GE69 | Gerard, Jeffrey S | 1 | 0 | 50 | 0 | 50 | 920008 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 528 | 06/13/18 | 06/15/18 | GE69 | Gerard, Jeffrey S | 2 | 0 | 100 | 0 | 100 | 20163 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 1019 | 06/27/18 | 06/29/18 | DO56 | Donelson, Richard T | 2 | 0 | 125 | 0 | 125 | 20300 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 1020 | 06/27/18 | 06/29/18 | GE69 | Gerard, Jeffrey S | 3 | 0 | 150 | 0 | 150 | 20301 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 76 | 07/04/18 | 07/06/18 | DO56 | Donelson, Richard T | 5 | 0 | 312.5 | 0 | 312.5 | 920374 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 77 | 07/04/18 | 07/06/18 | GE69 | Gerard, Jeffrey S | 1 | 0 | 50 | 0 | 50 | 920375 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 367 | 07/11/18 | 07/13/18 | DO56 | Donelson, Richard T | 1 | 0 | 62.5 | 0 | 62.5 | 20400 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 507 | 07/18/18 | 07/20/18 | DO56 | Donelson, Richard T | 1 | 0 | 62.5 | 0 | 62.5 | 920518 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 835 | 07/25/18 | 07/27/18 | GE69 | Gerard, Jeffrey S | 2 | 0 | 100 | 0 | 100 | 20593 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 72 | 08/01/18 | 08/03/18 | DO56 | Donelson, Richard T | 1 | 0 | 62.5 | 0 | 62.5 | 20664 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 283 | 08/08/18 | 08/10/18 | DO56 | Donelson, Richard T | 1 | 0 | 62.5 | 0 | 62.5 | 920736 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 550 | 08/15/18 | 08/17/18 | DO56 | Donelson, Richard T | 2 | 0 | 125 | 0 | 125 | 20808 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 811 | 08/22/18 | 08/24/18 | DO56 | Donelson, Richard T | 5 | 0 | 312.5 | 0 | 312.5 | 20879 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 1069 | 08/29/18 | 08/31/18 | DO56 | Donelson, Richard T | 1 | 0 | 62.5 | 0 | 62.5 | 90961 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 340 | 09/12/18 | 09/14/18 | DO56 | Donelson, Richard T | 1 | 0 | 62.5 | 0 | 62.5 | 21173 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 552 | 09/19/18 | 09/21/18 | DO56 | Donelson, Richard T | 1 | 0 | 62.5 | 0 | 62.5 | 21244 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 102 | 10/03/18 | 10/05/18 | DO56 | Donelson, Richard T | 3 | 0 | 187.5 | 0 | 187.5 | 91391 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 507 | 10/17/18 | 10/19/18 | DO56 | Donelson, Richard T | 1 | 0 | 62.5 | 0 | 62.5 | 91541 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 774 | 10/24/18 | 10/26/18 | DO56 | Donelson, Richard T | 3 | 0 | 187.5 | 0 | 187.5 | 21615 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 76 | 10/31/18 | 11/02/18 | DO56 | Donelson, Richard T | 6 | 0 | 375 | 0 | 375 | 21686 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 257 | 11/07/18 | 11/09/18 | DO56 | Donelson, Richard T | 7 | 0 | 437.5 | 0 | 437.5 | 20891 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 513 | 11/14/18 | 11/16/18 | DO56 | Donelson, Richard T | 3 | 0 | 187.5 | 0 | 187.5 | 21836 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 514 | 11/14/18 | 11/16/18 | GE69 | Gerard, Jeffrey S | 1 | 0 | 50 | 0 | 50 | 21837 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 689 | 11/21/18 | 11/21/18 | DO56 | Donelson, Richard T | 5 | 0 | 312.5 | 0 | 312.5 | 21911 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 900 | 11/28/18 | 11/30/18 | DO56 | Donelson, Richard T | 2 | 0 | 125 | 0 | 125 | 921983 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 113 | 12/05/18 | 12/07/18 | DO56 | Donelson, Richard T | 1 | 0 | 62.5 | 0 | 62.5 | 22056 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 337 | 12/12/18 | 12/14/18 | DO56 | Donelson, Richard T | 4 | 0 | 250 | 0 | 250 | 22197 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 577 | 12/19/18 | 12/21/18 | DO56 | Donelson, Richard T | 2 | 0 | 125 | 0 | 125 | 922268 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 578 | 12/19/18 | 12/21/18 | GE69 | Gerard, Jeffrey S | 1 | 0 | 52 | 0 | 52 | 922269 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 768 | 12/26/18 | 12/28/18 | DO56 | Donelson, Richard T | 1 | 0 | 62.5 | 0 | 62.5 | 22342 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 72 | 01/02/19 | 01/04/19 | DO56 | Donelson, Richard T | 1 | 0 | 62.5 | 0 | 62.5 | 22300 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 281 | 01/09/19 | 01/11/19 | DO56 | Donelson, Richard T | 2 | 0 | 125 | 0 | 125 | 922483 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 542 | 01/16/19 | 01/18/19 | DO56 | Donelson, Richard T | 2 | 0 | 125 | 0 | 125 | 922557 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 543 | 01/16/19 | 01/18/19 | GE69 | Gerard, Jeffrey S | 1 | 0 | 52 | 0 | 52 | 922558 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 786 | 01/23/19 | 01/25/19 | DO56 | Donelson, Richard T | 2 | 0 | 125 | 0 | 125 | 922631 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 70 | 01/30/19 | 02/01/19 | DO56 | Donelson, Richard T | 4 | 0 | 250 | 0 | 250 | 22699 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 226 | 02/06/19 | 02/08/19 | DO56 | Donelson, Richard T | 2 | 0 | 125 | 0 | 125 | 22768 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 388 | 02/13/19 | 02/15/19 | DO56 | Donelson, Richard T | 2 | 0 | 125 | 0 | 125 | 922839 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 647 | 02/20/19 | 02/22/19 | DO56 | Donelson, Richard T | 2 | 0 | 125 | 0 | 125 | 922909 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 74 | 02/27/19 | 03/01/19 | DO56 | Donelson, Richard T | 3 | 0 | 187.5 | 0 | 187.5 | 22981 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 314 | 03/06/19 | 03/08/19 | DO56 | Donelson, Richard T | 2 | 0 | 125 | 0 | 125 | 923053 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 562 | 03/13/19 | 03/15/19 | DO56 | Donelson, Richard T | 4 | 0 | 250 | 0 | 250 | 23124 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 989 | 03/27/19 | 03/29/19 | DO56 | Donelson, Richard T | 1 | 0 | 62.5 | 0 | 62.5 | 23272 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 151 | 04/03/19 | 04/05/19 | DO56 | Donelson, Richard T | 3 | 0 | 187.5 | 0 | 187.5 | 923345 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 397 | 04/10/19 | 04/12/19 | DO56 | Donelson, Richard T | 1 | 0 | 62.5 | 0 | 62.5 | 23420 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 596 | 04/17/19 | 04/19/19 | DO56 | Donelson, Richard T | 1 | 0 | 62.5 | 0 | 62.5 | 923496 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 812 | 04/24/19 | 04/26/19 | DO56 | Donelson, Richard T | 2 | 0 | 125 | 0 | 125 | 23568 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 81 | 05/01/19 | 05/03/19 | DO56 | Donelson, Richard T | 1 | 0 | 62.5 | 0 | 62.5 | 923643 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 467 | 05/15/19 | 05/17/19 | DO56 | Donelson, Richard T | 1 | 0 | 62.5 | 0 | 62.5 | 923798 | 0 | 0
110 | Underground Labor | PR | 296 | 11/15/17 | 11/17/17 | CO71 | Cortes Mendiola, Victor H | 8 | 0 | 320 | 0 | 320 | 17971 | 0 | 0
110 | Underground Labor | PR | 438 | 11/22/17 | 11/22/17 | CO71 | Cortes Mendiola, Victor H | 26 | 0 | 1040 | 0 | 1040 | 18032 | 0 | 0
110 | Underground Labor | PR | 439 | 11/22/17 | 11/22/17 | CO73 | Cortes Sepulveda, Jose R | 26 | 0 | 598 | 0 | 598 | 18033 | 0 | 0
110 | Underground Labor | PR | 457 | 11/22/17 | 11/22/17 | HU06 | Hubbard, Robert W | 18.5 | 0 | 832.5 | 0 | 832.5 | 18051 | 0 | 0
110 | Underground Labor | PR | 15 | 11/29/17 | 12/01/17 | CO71 | Cortes Mendiola, Victor H | 12 | 0 | 480 | 0 | 480 | 18096 | 0 | 0
110 | Underground Labor | PR | 16 | 11/29/17 | 12/01/17 | CO73 | Cortes Sepulveda, Jose R | 12 | 0 | 276 | 0 | 276 | 18097 | 0 | 0
110 | Underground Labor | PR | 34 | 11/29/17 | 12/01/17 | HU06 | Hubbard, Robert W | 4 | 0 | 180 | 0 | 180 | 18115 | 0 | 0
110 | Underground Labor | PR | 217 | 12/06/17 | 12/08/17 | CO71 | Cortes Mendiola, Victor H | 24 | 0 | 960 | 0 | 960 | 18162 | 0 | 0
110 | Underground Labor | PR | 218 | 12/06/17 | 12/08/17 | CO73 | Cortes Sepulveda, Jose R | 24 | 0 | 552 | 0 | 552 | 18163 | 0 | 0
110 | Underground Labor | PR | 414 | 12/13/17 | 12/15/17 | CO71 | Cortes Mendiola, Victor H | 29 | 0 | 1160 | 0 | 1160 | 18228 | 0 | 0
110 | Underground Labor | PR | 415 | 12/13/17 | 12/15/17 | CO73 | Cortes Sepulveda, Jose R | 29 | 0 | 667 | 0 | 667 | 18229 | 0 | 0
110 | Underground Labor | PR | 604 | 12/20/17 | 12/22/17 | CO71 | Cortes Mendiola, Victor H | 8 | 0 | 320 | 0 | 320 | 18358 | 0 | 0
110 | Underground Labor | PR | 605 | 12/20/17 | 12/22/17 | CO73 | Cortes Sepulveda, Jose R | 8 | 0 | 184 | 0 | 184 | 18359 | 0 | 0
110 | Underground Labor | PR | 623 | 12/20/17 | 12/22/17 | HU06 | Hubbard, Robert W | 3.5 | 0 | 157.5 | 0 | 157.5 | 18377 | 0 | 0
110 | Underground Labor | PR | 795 | 12/27/17 | 12/29/17 | CO71 | Cortes Mendiola, Victor H | 24 | 0 | 960 | 0 | 960 | 18424 | 0 | 0
110 | Underground Labor | PR | 796 | 12/27/17 | 12/29/17 | CO73 | Cortes Sepulveda, Jose R | 24 | 0 | 552 | 0 | 552 | 18425 | 0 | 0
110 | Underground Labor | PR | 814 | 12/27/17 | 12/29/17 | HU06 | Hubbard, Robert W | 3.5 | 0 | 157.5 | 0 | 157.5 | 18443 | 0 | 0
110 | Underground Labor | PR | 15 | 01/03/18 | 01/05/18 | CO71 | Cortes Mendiola, Victor H | 17 | 0 | 680 | 0 | 680 | 18488 | 0 | 0
110 | Underground Labor | PR | 16 | 01/03/18 | 01/05/18 | CO73 | Cortes Sepulveda, Jose R | 12 | 0 | 276 | 0 | 276 | 18489 | 0 | 0
110 | Underground Labor | PR | 34 | 01/03/18 | 01/05/18 | HU06 | Hubbard, Robert W | 2 | 0 | 90 | 0 | 90 | 18508 | 0 | 0
110 | Underground Labor | PR | 238 | 01/10/18 | 01/12/18 | CO71 | Cortes Mendiola, Victor H | 21 | 0 | 840 | 0 | 840 | 18553 | 0 | 0
110 | Underground Labor | PR | 239 | 01/10/18 | 01/12/18 | CO73 | Cortes Sepulveda, Jose R | 21 | 0 | 483 | 0 | 483 | 18554 | 0 | 0
110 | Underground Labor | PR | 257 | 01/10/18 | 01/12/18 | HU06 | Hubbard, Robert W | 2 | 0 | 90 | 0 | 90 | 18572 | 0 | 0
110 | Underground Labor | PR | 404 | 01/17/18 | 01/19/18 | CO71 | Cortes Mendiola, Victor H | 36 | 0 | 1440 | 0 | 1440 | 18618 | 0 | 0
110 | Underground Labor | PR | 405 | 01/17/18 | 01/19/18 | CO73 | Cortes Sepulveda, Jose R | 36 | 0 | 828 | 0 | 828 | 18619 | 0 | 0
110 | Underground Labor | PR | 423 | 01/17/18 | 01/19/18 | HU06 | Hubbard, Robert W | 5 | 0 | 225 | 0 | 225 | 18638 | 0 | 0
110 | Underground Labor | PR | 600 | 01/24/18 | 01/26/18 | CO71 | Cortes Mendiola, Victor H | 0 | 5.5 | 0 | 330 | 330 | 18684 | 0 | 0
110 | Underground Labor | PR | 600 | 01/24/18 | 01/26/18 | CO71 | Cortes Mendiola, Victor H | 38 | 0 | 1520 | 0 | 1520 | 18684 | 0 | 0
110 | Underground Labor | PR | 601 | 01/24/18 | 01/26/18 | CO73 | Cortes Sepulveda, Jose R | 0 | 5.5 | 0 | 189.75 | 189.75 | 18685 | 0 | 0
110 | Underground Labor | PR | 601 | 01/24/18 | 01/26/18 | CO73 | Cortes Sepulveda, Jose R | 24 | 0 | 552 | 0 | 552 | 18685 | 0 | 0
110 | Underground Labor | PR | 618 | 01/24/18 | 01/26/18 | HU06 | Hubbard, Robert W | 0 | 5.5 | 0 | 371.25 | 371.25 | 18702 | 0 | 0
110 | Underground Labor | PR | 618 | 01/24/18 | 01/26/18 | HU06 | Hubbard, Robert W | 13 | 0 | 585 | 0 | 585 | 18702 | 0 | 0
110 | Underground Labor | PR | 629 | 01/24/18 | 01/26/18 | MO56 | Montenegro, Carlos E | 16 | 0 | 432 | 0 | 432 | 18713 | 0 | 0
110 | Underground Labor | PR | 630 | 01/24/18 | 01/26/18 | PA11 | Paco Leyva, Orlando | 16 | 0 | 544 | 0 | 544 | 18714 | 0 | 0
110 | Underground Labor | PR | 19 | 01/31/18 | 02/02/18 | CO71 | Cortes Mendiola, Victor H | 16 | 0 | 640 | 0 | 640 | 18749 | 0 | 0
110 | Underground Labor | PR | 20 | 01/31/18 | 02/02/18 | CO73 | Cortes Sepulveda, Jose R | 16 | 0 | 368 | 0 | 368 | 18750 | 0 | 0
110 | Underground Labor | PR | 38 | 01/31/18 | 02/02/18 | HU06 | Hubbard, Robert W | 3 | 0 | 135 | 0 | 135 | 18768 | 0 | 0
110 | Underground Labor | PR | 246 | 08/08/18 | 08/10/18 | HU06 | Hubbard, Robert W | 2 | 0 | 94 | 0 | 94 | 20698 | 0 | 0
111 | Garage Labor | PR | 430 | 02/14/18 | 02/16/18 | CO71 | Cortes Mendiola, Victor H | 9 | 0 | 360 | 0 | 360 | 18884 | 0 | 0
111 | Garage Labor | PR | 431 | 02/14/18 | 02/16/18 | CO73 | Cortes Sepulveda, Jose R | 9 | 0 | 207 | 0 | 207 | 18885 | 0 | 0
111 | Garage Labor | PR | 449 | 02/14/18 | 02/16/18 | HU06 | Hubbard, Robert W | 3 | 0 | 135 | 0 | 135 | 18903 | 0 | 0
111 | Garage Labor | PR | 617 | 02/21/18 | 02/23/18 | CO71 | Cortes Mendiola, Victor H | 32 | 0 | 1280 | 0 | 1280 | 18950 | 0 | 0
111 | Garage Labor | PR | 618 | 02/21/18 | 02/23/18 | CO73 | Cortes Sepulveda, Jose R | 22 | 0 | 506 | 0 | 506 | 18951 | 0 | 0
111 | Garage Labor | PR | 636 | 02/21/18 | 02/23/18 | HU06 | Hubbard, Robert W | 7 | 0 | 315 | 0 | 315 | 18970 | 0 | 0
111 | Garage Labor | PR | 3 | 02/28/18 | 03/02/18 | AS10 | Ascencio, Jose L | 8 | 0 | 200 | 0 | 200 | 19004 | 0 | 0
111 | Garage Labor | PR | 4 | 02/28/18 | 03/02/18 | BA45 | Balderas Ortiz, Ricardo I | 8 | 0 | 216 | 0 | 216 | 19005 | 0 | 0
111 | Garage Labor | PR | 16 | 02/28/18 | 03/02/18 | CO71 | Cortes Mendiola, Victor H | 40 | 0 | 1600 | 0 | 1600 | 19017 | 0 | 0
111 | Garage Labor | PR | 17 | 02/28/18 | 03/02/18 | CO73 | Cortes Sepulveda, Jose R | 40 | 0 | 920 | 0 | 920 | 19018 | 0 | 0
111 | Garage Labor | PR | 47 | 02/28/18 | 03/02/18 | PA11 | Paco Leyva, Orlando | 8 | 0 | 272 | 0 | 272 | 19049 | 0 | 0
111 | Garage Labor | PR | 119 | 03/07/18 | 03/09/18 | AS10 | Ascencio, Jose L | 24 | 0 | 600 | 0 | 600 | 19075 | 0 | 0
111 | Garage Labor | PR | 131 | 03/07/18 | 03/09/18 | CO71 | Cortes Mendiola, Victor H | 16 | 0 | 640 | 0 | 640 | 19087 | 0 | 0
111 | Garage Labor | PR | 132 | 03/07/18 | 03/09/18 | CO73 | Cortes Sepulveda, Jose R | 16 | 0 | 368 | 0 | 368 | 19088 | 0 | 0
111 | Garage Labor | PR | 149 | 03/07/18 | 03/09/18 | HU06 | Hubbard, Robert W | 7 | 0 | 315 | 0 | 315 | 19106 | 0 | 0
111 | Garage Labor | PR | 173 | 03/07/18 | 03/09/18 | SI48 | Silva Morales, Jair J | 8 | 0 | 184 | 0 | 184 | 19130 | 0 | 0
111 | Garage Labor | PR | 319 | 03/14/18 | 03/16/18 | AS10 | Ascencio, Jose L | 40 | 0 | 1000 | 0 | 1000 | 19140 | 0 | 0
111 | Garage Labor | PR | 331 | 03/14/18 | 03/16/18 | CO71 | Cortes Mendiola, Victor H | 40 | 0 | 1600 | 0 | 1600 | 19152 | 0 | 0
111 | Garage Labor | PR | 332 | 03/14/18 | 03/16/18 | CO73 | Cortes Sepulveda, Jose R | 16 | 0 | 368 | 0 | 368 | 19153 | 0 | 0
111 | Garage Labor | PR | 350 | 03/14/18 | 03/16/18 | HU06 | Hubbard, Robert W | 3 | 0 | 135 | 0 | 135 | 19171 | 0 | 0
111 | Garage Labor | PR | 376 | 03/14/18 | 03/16/18 | SI48 | Silva Morales, Jair J | 24 | 0 | 552 | 0 | 552 | 19197 | 0 | 0
111 | Garage Labor | PR | 517 | 03/21/18 | 03/23/18 | AS10 | Ascencio, Jose L | 40 | 0 | 1000 | 0 | 1000 | 19208 | 0 | 0
111 | Garage Labor | PR | 529 | 03/21/18 | 03/23/18 | CO71 | Cortes Mendiola, Victor H | 30 | 0 | 1200 | 0 | 1200 | 19220 | 0 | 0
111 | Garage Labor | PR | 530 | 03/21/18 | 03/23/18 | CO73 | Cortes Sepulveda, Jose R | 36 | 0 | 828 | 0 | 828 | 19221 | 0 | 0
111 | Garage Labor | PR | 548 | 03/21/18 | 03/23/18 | HU06 | Hubbard, Robert W | 9 | 0 | 405 | 0 | 405 | 19239 | 0 | 0
111 | Garage Labor | PR | 575 | 03/21/18 | 03/23/18 | SI48 | Silva Morales, Jair J | 20 | 0 | 460 | 0 | 460 | 19266 | 0 | 0
111 | Garage Labor | PR | 736 | 03/28/18 | 03/30/18 | AS10 | Ascencio, Jose L | 24 | 0 | 600 | 0 | 600 | 19276 | 0 | 0
111 | Garage Labor | PR | 748 | 03/28/18 | 03/30/18 | CO71 | Cortes Mendiola, Victor H | 16 | 0 | 640 | 0 | 640 | 19288 | 0 | 0
111 | Garage Labor | PR | 749 | 03/28/18 | 03/30/18 | CO73 | Cortes Sepulveda, Jose R | 40 | 0 | 920 | 0 | 920 | 19289 | 0 | 0
111 | Garage Labor | PR | 770 | 03/28/18 | 03/30/18 | JU02 | Juarez Alvarez, Oscar R | 8 | 0 | 224 | 0 | 224 | 19310 | 0 | 0
111 | Garage Labor | PR | 800 | 03/28/18 | 03/30/18 | SI48 | Silva Morales, Jair J | 38 | 0 | 874 | 0 | 874 | 19340 | 0 | 0
111 | Garage Labor | PR | 24 | 04/04/18 | 04/06/18 | CO71 | Cortes Mendiola, Victor H | 4 | 0 | 160 | 0 | 160 | 19367 | 0 | 0
111 | Garage Labor | PR | 25 | 04/04/18 | 04/06/18 | CO73 | Cortes Sepulveda, Jose R | 30 | 0 | 690 | 0 | 690 | 19368 | 0 | 0
111 | Garage Labor | PR | 47 | 04/04/18 | 04/06/18 | JU04 | Juarez Maldonado, Oscar E | 8 | 0 | 144 | 0 | 144 | 19390 | 0 | 0
111 | Garage Labor | PR | 74 | 04/04/18 | 04/06/18 | SI48 | Silva Morales, Jair J | 16 | 0 | 368 | 0 | 368 | 19417 | 0 | 0
111 | Garage Labor | PR | 292 | 04/11/18 | 04/13/18 | HU06 | Hubbard, Robert W | 3 | 0 | 135 | 0 | 135 | 19460 | 0 | 0
111 | Garage Labor | PR | 295 | 04/11/18 | 04/13/18 | JU04 | Juarez Maldonado, Oscar E | 8 | 0 | 144 | 0 | 144 | 19463 | 0 | 0
111 | Garage Labor | PR | 477 | 04/18/18 | 04/20/18 | HU06 | Hubbard, Robert W | 17 | 0 | 765 | 0 | 765 | 19535 | 0 | 0
111 | Garage Labor | PR | 479 | 04/18/18 | 04/20/18 | JU02 | Juarez Alvarez, Oscar R | 32 | 0 | 896 | 0 | 896 | 19537 | 0 | 0
111 | Garage Labor | PR | 480 | 04/18/18 | 04/20/18 | JU04 | Juarez Maldonado, Oscar E | 8 | 0 | 144 | 0 | 144 | 19538 | 0 | 0
111 | Garage Labor | PR | 508 | 04/18/18 | 04/20/18 | SI48 | Silva Morales, Jair J | 8 | 0 | 184 | 0 | 184 | 19566 | 0 | 0
111 | Garage Labor | PR | 646 | 04/25/18 | 04/27/18 | JU02 | Juarez Alvarez, Oscar R | 32 | 0 | 896 | 0 | 896 | 19611 | 0 | 0
111 | Garage Labor | PR | 674 | 04/25/18 | 04/27/18 | SI48 | Silva Morales, Jair J | 31 | 0 | 713 | 0 | 713 | 19639 | 0 | 0
111 | Garage Labor | PR | 58 | 05/02/18 | 05/04/18 | HU06 | Hubbard, Robert W | 9 | 0 | 405 | 0 | 405 | 19681 | 0 | 0
111 | Garage Labor | PR | 251 | 05/09/18 | 05/11/18 | HU06 | Hubbard, Robert W | 6.5 | 0 | 292.5 | 0 | 292.5 | 19758 | 0 | 0
111 | Garage Labor | PR | 280 | 06/06/18 | 06/08/18 | CO73 | Cortes Sepulveda, Jose R | 0 | 8 | 0 | 276 | 276 | 20020 | 0 | 0
111 | Garage Labor | PR | 36 | 01/30/19 | 02/01/19 | HU06 | Hubbard, Robert W | 2 | 0 | 98 | 0 | 98 | 22665 | 0 | 0
112 | Canout Labor | PR | 423 | 01/17/18 | 01/19/18 | HU06 | Hubbard, Robert W | 3 | 0 | 135 | 0 | 135 | 18638 | 0 | 0
112 | Canout Labor | PR | 600 | 01/24/18 | 01/26/18 | CO71 | Cortes Mendiola, Victor H | 2 | 0 | 80 | 0 | 80 | 18684 | 0 | 0
112 | Canout Labor | PR | 601 | 01/24/18 | 01/26/18 | CO73 | Cortes Sepulveda, Jose R | 16 | 0 | 368 | 0 | 368 | 18685 | 0 | 0
112 | Canout Labor | PR | 618 | 01/24/18 | 01/26/18 | HU06 | Hubbard, Robert W | 10 | 0 | 450 | 0 | 450 | 18702 | 0 | 0
112 | Canout Labor | PR | 19 | 01/31/18 | 02/02/18 | CO71 | Cortes Mendiola, Victor H | 16 | 0 | 640 | 0 | 640 | 18749 | 0 | 0
112 | Canout Labor | PR | 20 | 01/31/18 | 02/02/18 | CO73 | Cortes Sepulveda, Jose R | 16 | 0 | 368 | 0 | 368 | 18750 | 0 | 0
112 | Canout Labor | PR | 38 | 01/31/18 | 02/02/18 | HU06 | Hubbard, Robert W | 15.5 | 0 | 697.5 | 0 | 697.5 | 18768 | 0 | 0
112 | Canout Labor | PR | 176 | 02/07/18 | 02/09/18 | CO71 | Cortes Mendiola, Victor H | 10 | 0 | 400 | 0 | 400 | 18817 | 0 | 0
112 | Canout Labor | PR | 177 | 02/07/18 | 02/09/18 | CO73 | Cortes Sepulveda, Jose R | 16 | 0 | 368 | 0 | 368 | 18818 | 0 | 0
112 | Canout Labor | PR | 195 | 02/07/18 | 02/09/18 | HU06 | Hubbard, Robert W | 10 | 0 | 450 | 0 | 450 | 18836 | 0 | 0
112 | Canout Labor | PR | 430 | 02/14/18 | 02/16/18 | CO71 | Cortes Mendiola, Victor H | 31 | 0 | 1240 | 0 | 1240 | 18884 | 0 | 0
112 | Canout Labor | PR | 431 | 02/14/18 | 02/16/18 | CO73 | Cortes Sepulveda, Jose R | 31 | 0 | 713 | 0 | 713 | 18885 | 0 | 0
112 | Canout Labor | PR | 449 | 02/14/18 | 02/16/18 | HU06 | Hubbard, Robert W | 14 | 0 | 630 | 0 | 630 | 18903 | 0 | 0
112 | Canout Labor | PR | 452 | 02/14/18 | 02/16/18 | LI49 | Lima Romero, Melvin A | 8 | 0 | 248 | 0 | 248 | 18906 | 0 | 0
112 | Canout Labor | PR | 618 | 02/21/18 | 02/23/18 | CO73 | Cortes Sepulveda, Jose R | 10 | 0 | 230 | 0 | 230 | 18951 | 0 | 0
112 | Canout Labor | PR | 636 | 02/21/18 | 02/23/18 | HU06 | Hubbard, Robert W | 4 | 0 | 180 | 0 | 180 | 18970 | 0 | 0
112 | Canout Labor | PR | 35 | 02/28/18 | 03/02/18 | HU06 | Hubbard, Robert W | 20 | 0 | 900 | 0 | 900 | 19037 | 0 | 0
112 | Canout Labor | PR | 131 | 03/07/18 | 03/09/18 | CO71 | Cortes Mendiola, Victor H | 16 | 0 | 640 | 0 | 640 | 19087 | 0 | 0
112 | Canout Labor | PR | 132 | 03/07/18 | 03/09/18 | CO73 | Cortes Sepulveda, Jose R | 16 | 0 | 368 | 0 | 368 | 19088 | 0 | 0
112 | Canout Labor | PR | 149 | 03/07/18 | 03/09/18 | HU06 | Hubbard, Robert W | 8.5 | 0 | 382.5 | 0 | 382.5 | 19106 | 0 | 0
112 | Canout Labor | PR | 332 | 03/14/18 | 03/16/18 | CO73 | Cortes Sepulveda, Jose R | 8 | 0 | 184 | 0 | 184 | 19153 | 0 | 0
112 | Canout Labor | PR | 548 | 03/21/18 | 03/23/18 | HU06 | Hubbard, Robert W | 3 | 0 | 135 | 0 | 135 | 19239 | 0 | 0
112 | Canout Labor | PR | 517 | 12/19/18 | 12/21/18 | CO71 | Cortes Mendiola, Victor H | 6 | 0 | 258 | 0 | 258 | 22208 | 0 | 0
120 | Roughin Labor | PR | 34 | 08/02/17 | 08/04/17 | GE70 | Gerard, Jordan E | 4 | 0 | 96 | 0 | 96 | 17040 | 0 | 0
120 | Roughin Labor | PR | 65 | 08/02/17 | 08/04/17 | SA54 | Sanders, Allen O | 4 | 0 | 156 | 0 | 156 | 17071 | 0 | 0
120 | Roughin Labor | PR | 492 | 08/23/17 | 08/25/17 | SA54 | Sanders, Allen O | 2 | 0 | 78 | 0 | 78 | 17255 | 0 | 0
120 | Roughin Labor | PR | 449 | 02/14/18 | 02/16/18 | HU06 | Hubbard, Robert W | 5 | 0 | 225 | 0 | 225 | 18903 | 0 | 0
120 | Roughin Labor | PR | 131 | 03/07/18 | 03/09/18 | CO71 | Cortes Mendiola, Victor H | 8 | 0 | 320 | 0 | 320 | 19087 | 0 | 0
120 | Roughin Labor | PR | 132 | 03/07/18 | 03/09/18 | CO73 | Cortes Sepulveda, Jose R | 8 | 0 | 184 | 0 | 184 | 19088 | 0 | 0
120 | Roughin Labor | PR | 332 | 03/14/18 | 03/16/18 | CO73 | Cortes Sepulveda, Jose R | 14 | 0 | 322 | 0 | 322 | 19153 | 0 | 0
120 | Roughin Labor | PR | 376 | 03/14/18 | 03/16/18 | SI48 | Silva Morales, Jair J | 16 | 0 | 368 | 0 | 368 | 19197 | 0 | 0
120 | Roughin Labor | PR | 529 | 03/21/18 | 03/23/18 | CO71 | Cortes Mendiola, Victor H | 2 | 0 | 80 | 0 | 80 | 19220 | 0 | 0
120 | Roughin Labor | PR | 530 | 03/21/18 | 03/23/18 | CO73 | Cortes Sepulveda, Jose R | 4 | 0 | 92 | 0 | 92 | 19221 | 0 | 0
120 | Roughin Labor | PR | 575 | 03/21/18 | 03/23/18 | SI48 | Silva Morales, Jair J | 20 | 0 | 460 | 0 | 460 | 19266 | 0 | 0
120 | Roughin Labor | PR | 736 | 03/28/18 | 03/30/18 | AS10 | Ascencio, Jose L | 16 | 0 | 400 | 0 | 400 | 19276 | 0 | 0
120 | Roughin Labor | PR | 748 | 03/28/18 | 03/30/18 | CO71 | Cortes Mendiola, Victor H | 24 | 0 | 960 | 0 | 960 | 19288 | 0 | 0
120 | Roughin Labor | PR | 763 | 03/28/18 | 03/30/18 | GU78 | Gutierrez Salas, Jose | 24 | 0 | 432 | 0 | 432 | 19303 | 0 | 0
120 | Roughin Labor | PR | 770 | 03/28/18 | 03/30/18 | JU02 | Juarez Alvarez, Oscar R | 16 | 0 | 448 | 0 | 448 | 19310 | 0 | 0
120 | Roughin Labor | PR | 771 | 03/28/18 | 03/30/18 | JU04 | Juarez Maldonado, Oscar E | 24 | 0 | 432 | 0 | 432 | 19311 | 0 | 0
120 | Roughin Labor | PR | 12 | 04/04/18 | 04/06/18 | AS10 | Ascencio, Jose L | 32 | 0 | 800 | 0 | 800 | 19354 | 0 | 0
120 | Roughin Labor | PR | 24 | 04/04/18 | 04/06/18 | CO71 | Cortes Mendiola, Victor H | 34 | 0 | 1360 | 0 | 1360 | 19367 | 0 | 0
120 | Roughin Labor | PR | 39 | 04/04/18 | 04/06/18 | GU78 | Gutierrez Salas, Jose | 31 | 0 | 558 | 0 | 558 | 19382 | 0 | 0
120 | Roughin Labor | PR | 46 | 04/04/18 | 04/06/18 | JU02 | Juarez Alvarez, Oscar R | 40 | 0 | 1120 | 0 | 1120 | 19389 | 0 | 0
120 | Roughin Labor | PR | 47 | 04/04/18 | 04/06/18 | JU04 | Juarez Maldonado, Oscar E | 24 | 0 | 432 | 0 | 432 | 19390 | 0 | 0
120 | Roughin Labor | PR | 74 | 04/04/18 | 04/06/18 | SI48 | Silva Morales, Jair J | 24 | 0 | 552 | 0 | 552 | 19417 | 0 | 0
120 | Roughin Labor | PR | 260 | 04/11/18 | 04/13/18 | AS10 | Ascencio, Jose L | 36 | 0 | 900 | 0 | 900 | 19428 | 0 | 0
120 | Roughin Labor | PR | 272 | 04/11/18 | 04/13/18 | CO71 | Cortes Mendiola, Victor H | 40 | 0 | 1600 | 0 | 1600 | 19440 | 0 | 0
120 | Roughin Labor | PR | 273 | 04/11/18 | 04/13/18 | CO73 | Cortes Sepulveda, Jose R | 32 | 0 | 736 | 0 | 736 | 19441 | 0 | 0
120 | Roughin Labor | PR | 287 | 04/11/18 | 04/13/18 | GU78 | Gutierrez Salas, Jose | 40 | 0 | 720 | 0 | 720 | 19455 | 0 | 0
120 | Roughin Labor | PR | 292 | 04/11/18 | 04/13/18 | HU06 | Hubbard, Robert W | 3 | 0 | 135 | 0 | 135 | 19460 | 0 | 0
120 | Roughin Labor | PR | 294 | 04/11/18 | 04/13/18 | JU02 | Juarez Alvarez, Oscar R | 40 | 0 | 1120 | 0 | 1120 | 19462 | 0 | 0
120 | Roughin Labor | PR | 295 | 04/11/18 | 04/13/18 | JU04 | Juarez Maldonado, Oscar E | 32 | 0 | 576 | 0 | 576 | 19463 | 0 | 0
120 | Roughin Labor | PR | 323 | 04/11/18 | 04/13/18 | SI48 | Silva Morales, Jair J | 16 | 0 | 368 | 0 | 368 | 19491 | 0 | 0
120 | Roughin Labor | PR | 447 | 04/18/18 | 04/20/18 | AS10 | Ascencio, Jose L | 40 | 0 | 1000 | 0 | 1000 | 19505 | 0 | 0
120 | Roughin Labor | PR | 457 | 04/18/18 | 04/20/18 | CO71 | Cortes Mendiola, Victor H | 16 | 0 | 640 | 0 | 640 | 19515 | 0 | 0
120 | Roughin Labor | PR | 458 | 04/18/18 | 04/20/18 | CO73 | Cortes Sepulveda, Jose R | 16 | 0 | 368 | 0 | 368 | 19516 | 0 | 0
120 | Roughin Labor | PR | 472 | 04/18/18 | 04/20/18 | GU78 | Gutierrez Salas, Jose | 32 | 0 | 576 | 0 | 576 | 19530 | 0 | 0
120 | Roughin Labor | PR | 477 | 04/18/18 | 04/20/18 | HU06 | Hubbard, Robert W | 7 | 0 | 315 | 0 | 315 | 19535 | 0 | 0
120 | Roughin Labor | PR | 479 | 04/18/18 | 04/20/18 | JU02 | Juarez Alvarez, Oscar R | 8 | 0 | 224 | 0 | 224 | 19537 | 0 | 0
120 | Roughin Labor | PR | 480 | 04/18/18 | 04/20/18 | JU04 | Juarez Maldonado, Oscar E | 32 | 0 | 576 | 0 | 576 | 19538 | 0 | 0
120 | Roughin Labor | PR | 613 | 04/25/18 | 04/27/18 | AS10 | Ascencio, Jose L | 40 | 0 | 1000 | 0 | 1000 | 19577 | 0 | 0
120 | Roughin Labor | PR | 615 | 04/25/18 | 04/27/18 | BA45 | Balderas Ortiz, Ricardo I | 16 | 0 | 432 | 0 | 432 | 19580 | 0 | 0
120 | Roughin Labor | PR | 624 | 04/25/18 | 04/27/18 | CO71 | Cortes Mendiola, Victor H | 28 | 0 | 1120 | 0 | 1120 | 19589 | 0 | 0
120 | Roughin Labor | PR | 625 | 04/25/18 | 04/27/18 | CO73 | Cortes Sepulveda, Jose R | 24 | 0 | 552 | 0 | 552 | 19590 | 0 | 0
120 | Roughin Labor | PR | 634 | 04/25/18 | 04/27/18 | GA70 | Garcia, Jordan X | 40 | 0 | 1240 | 0 | 1240 | 19599 | 0 | 0
120 | Roughin Labor | PR | 639 | 04/25/18 | 04/27/18 | GU78 | Gutierrez Salas, Jose | 8 | 0 | 144 | 0 | 144 | 19604 | 0 | 0
120 | Roughin Labor | PR | 644 | 04/25/18 | 04/27/18 | HU06 | Hubbard, Robert W | 4 | 0 | 180 | 0 | 180 | 19609 | 0 | 0
120 | Roughin Labor | PR | 646 | 04/25/18 | 04/27/18 | JU02 | Juarez Alvarez, Oscar R | 8 | 0 | 224 | 0 | 224 | 19611 | 0 | 0
120 | Roughin Labor | PR | 647 | 04/25/18 | 04/27/18 | JU04 | Juarez Maldonado, Oscar E | 40 | 0 | 720 | 0 | 720 | 19612 | 0 | 0
120 | Roughin Labor | PR | 674 | 04/25/18 | 04/27/18 | SI48 | Silva Morales, Jair J | 8 | 0 | 184 | 0 | 184 | 19639 | 0 | 0
120 | Roughin Labor | PR | 27 | 05/02/18 | 05/04/18 | AS10 | Ascencio, Jose L | 40 | 0 | 1000 | 0 | 1000 | 19650 | 0 | 0
120 | Roughin Labor | PR | 29 | 05/02/18 | 05/04/18 | BA45 | Balderas Ortiz, Ricardo I | 32 | 0 | 864 | 0 | 864 | 19652 | 0 | 0
120 | Roughin Labor | PR | 38 | 05/02/18 | 05/04/18 | CO71 | Cortes Mendiola, Victor H | 37 | 0 | 1480 | 0 | 1480 | 19661 | 0 | 0
120 | Roughin Labor | PR | 53 | 05/02/18 | 05/04/18 | GU78 | Gutierrez Salas, Jose | 32 | 0 | 576 | 0 | 576 | 19676 | 0 | 0
120 | Roughin Labor | PR | 60 | 05/02/18 | 05/04/18 | JU02 | Juarez Alvarez, Oscar R | 40 | 0 | 1120 | 0 | 1120 | 19683 | 0 | 0
120 | Roughin Labor | PR | 61 | 05/02/18 | 05/04/18 | JU04 | Juarez Maldonado, Oscar E | 32 | 0 | 576 | 0 | 576 | 19684 | 0 | 0
120 | Roughin Labor | PR | 89 | 05/02/18 | 05/04/18 | SI48 | Silva Morales, Jair J | 40 | 0 | 920 | 0 | 920 | 19712 | 0 | 0
120 | Roughin Labor | PR | 226 | 05/09/18 | 05/11/18 | AS10 | Ascencio, Jose L | 32 | 0 | 800 | 0 | 800 | 19733 | 0 | 0
120 | Roughin Labor | PR | 228 | 05/09/18 | 05/11/18 | BA45 | Balderas Ortiz, Ricardo I | 21 | 0 | 567 | 0 | 567 | 19735 | 0 | 0
120 | Roughin Labor | PR | 234 | 05/09/18 | 05/11/18 | CO71 | Cortes Mendiola, Victor H | 36 | 0 | 1440 | 0 | 1440 | 19741 | 0 | 0
120 | Roughin Labor | PR | 242 | 05/09/18 | 05/11/18 | GA70 | Garcia, Jordan X | 38 | 0 | 1178 | 0 | 1178 | 19749 | 0 | 0
120 | Roughin Labor | PR | 247 | 05/09/18 | 05/11/18 | GU78 | Gutierrez Salas, Jose | 32 | 0 | 576 | 0 | 576 | 19754 | 0 | 0
120 | Roughin Labor | PR | 253 | 05/09/18 | 05/11/18 | JU02 | Juarez Alvarez, Oscar R | 40 | 0 | 1120 | 0 | 1120 | 19760 | 0 | 0
120 | Roughin Labor | PR | 254 | 05/09/18 | 05/11/18 | JU04 | Juarez Maldonado, Oscar E | 40 | 0 | 720 | 0 | 720 | 19761 | 0 | 0
120 | Roughin Labor | PR | 279 | 05/09/18 | 05/11/18 | SI48 | Silva Morales, Jair J | 32 | 0 | 736 | 0 | 736 | 19786 | 0 | 0
120 | Roughin Labor | PR | 422 | 05/16/18 | 05/18/18 | AS10 | Ascencio, Jose L | 40 | 0 | 1000 | 0 | 1000 | 19795 | 0 | 0
120 | Roughin Labor | PR | 424 | 05/16/18 | 05/18/18 | BA45 | Balderas Ortiz, Ricardo I | 40 | 0 | 1080 | 0 | 1080 | 19797 | 0 | 0
120 | Roughin Labor | PR | 432 | 05/16/18 | 05/18/18 | CO71 | Cortes Mendiola, Victor H | 32 | 0 | 1280 | 0 | 1280 | 19805 | 0 | 0
120 | Roughin Labor | PR | 442 | 05/16/18 | 05/18/18 | GA70 | Garcia, Jordan X | 40 | 0 | 1240 | 0 | 1240 | 19815 | 0 | 0
120 | Roughin Labor | PR | 447 | 05/16/18 | 05/18/18 | GU78 | Gutierrez Salas, Jose | 32 | 0 | 576 | 0 | 576 | 19820 | 0 | 0
120 | Roughin Labor | PR | 454 | 05/16/18 | 05/18/18 | JU02 | Juarez Alvarez, Oscar R | 39 | 0 | 1092 | 0 | 1092 | 19827 | 0 | 0
120 | Roughin Labor | PR | 455 | 05/16/18 | 05/18/18 | JU04 | Juarez Maldonado, Oscar E | 39 | 0 | 702 | 0 | 702 | 19828 | 0 | 0
120 | Roughin Labor | PR | 482 | 05/16/18 | 05/18/18 | SI48 | Silva Morales, Jair J | 22 | 0 | 506 | 0 | 506 | 19855 | 0 | 0
120 | Roughin Labor | PR | 737 | 05/23/18 | 05/25/18 | AS10 | Ascencio, Jose L | 0 | 6 | 0 | 225 | 225 | 19866 | 0 | 0
120 | Roughin Labor | PR | 737 | 05/23/18 | 05/25/18 | AS10 | Ascencio, Jose L | 40 | 0 | 1000 | 0 | 1000 | 19866 | 0 | 0
120 | Roughin Labor | PR | 739 | 05/23/18 | 05/25/18 | BA45 | Balderas Ortiz, Ricardo I | 0 | 6 | 0 | 243 | 243 | 19868 | 0 | 0
120 | Roughin Labor | PR | 739 | 05/23/18 | 05/25/18 | BA45 | Balderas Ortiz, Ricardo I | 40 | 0 | 1080 | 0 | 1080 | 19868 | 0 | 0
120 | Roughin Labor | PR | 747 | 05/23/18 | 05/25/18 | CO71 | Cortes Mendiola, Victor H | 0 | 3.5 | 0 | 210 | 210 | 19876 | 0 | 0
120 | Roughin Labor | PR | 747 | 05/23/18 | 05/25/18 | CO71 | Cortes Mendiola, Victor H | 38 | 0 | 1520 | 0 | 1520 | 19876 | 0 | 0
120 | Roughin Labor | PR | 757 | 05/23/18 | 05/25/18 | GA70 | Garcia, Jordan X | 6 | 0 | 186 | 0 | 186 | 19886 | 0 | 0
120 | Roughin Labor | PR | 757 | 05/23/18 | 05/25/18 | GA70 | Garcia, Jordan X | 32 | 0 | 992 | 0 | 992 | 19886 | 0 | 0
120 | Roughin Labor | PR | 762 | 05/23/18 | 05/25/18 | GU78 | Gutierrez Salas, Jose | 32 | 0 | 576 | 0 | 576 | 19891 | 0 | 0
120 | Roughin Labor | PR | 767 | 05/23/18 | 05/25/18 | HU06 | Hubbard, Robert W | 2 | 0 | 90 | 0 | 90 | 19896 | 0 | 0
120 | Roughin Labor | PR | 769 | 05/23/18 | 05/25/18 | JU02 | Juarez Alvarez, Oscar R | 0 | 6 | 0 | 252 | 252 | 19898 | 0 | 0
120 | Roughin Labor | PR | 769 | 05/23/18 | 05/25/18 | JU02 | Juarez Alvarez, Oscar R | 40 | 0 | 1120 | 0 | 1120 | 19898 | 0 | 0
120 | Roughin Labor | PR | 770 | 05/23/18 | 05/25/18 | JU04 | Juarez Maldonado, Oscar E | 0 | 6 | 0 | 162 | 162 | 19899 | 0 | 0
120 | Roughin Labor | PR | 770 | 05/23/18 | 05/25/18 | JU04 | Juarez Maldonado, Oscar E | 40 | 0 | 720 | 0 | 720 | 19899 | 0 | 0
120 | Roughin Labor | PR | 797 | 05/23/18 | 05/25/18 | SI48 | Silva Morales, Jair J | 0 | 3 | 0 | 103.5 | 103.5 | 19926 | 0 | 0
120 | Roughin Labor | PR | 797 | 05/23/18 | 05/25/18 | SI48 | Silva Morales, Jair J | 17 | 0 | 391 | 0 | 391 | 19926 | 0 | 0
120 | Roughin Labor | PR | 4 | 05/30/18 | 06/01/18 | AS10 | Ascencio, Jose L | 38 | 0 | 950 | 0 | 950 | 19937 | 0 | 0
120 | Roughin Labor | PR | 6 | 05/30/18 | 06/01/18 | BA45 | Balderas Ortiz, Ricardo I | 38 | 0 | 1026 | 0 | 1026 | 19939 | 0 | 0
120 | Roughin Labor | PR | 14 | 05/30/18 | 06/01/18 | CO71 | Cortes Mendiola, Victor H | 27 | 0 | 1080 | 0 | 1080 | 19947 | 0 | 0
120 | Roughin Labor | PR | 24 | 05/30/18 | 06/01/18 | GA70 | Garcia, Jordan X | 36 | 0 | 1116 | 0 | 1116 | 19958 | 0 | 0
120 | Roughin Labor | PR | 29 | 05/30/18 | 06/01/18 | GU78 | Gutierrez Salas, Jose | 38 | 0 | 684 | 0 | 684 | 19963 | 0 | 0
120 | Roughin Labor | PR | 36 | 05/30/18 | 06/01/18 | JU02 | Juarez Alvarez, Oscar R | 38 | 0 | 1064 | 0 | 1064 | 19970 | 0 | 0
120 | Roughin Labor | PR | 37 | 05/30/18 | 06/01/18 | JU04 | Juarez Maldonado, Oscar E | 38 | 0 | 684 | 0 | 684 | 19971 | 0 | 0
120 | Roughin Labor | PR | 64 | 05/30/18 | 06/01/18 | SI48 | Silva Morales, Jair J | 10 | 0 | 230 | 0 | 230 | 19998 | 0 | 0
120 | Roughin Labor | PR | 269 | 06/06/18 | 06/08/18 | AS10 | Ascencio, Jose L | 0 | 8 | 0 | 300 | 300 | 20009 | 0 | 0
120 | Roughin Labor | PR | 269 | 06/06/18 | 06/08/18 | AS10 | Ascencio, Jose L | 40 | 0 | 1000 | 0 | 1000 | 20009 | 0 | 0
120 | Roughin Labor | PR | 271 | 06/06/18 | 06/08/18 | BA45 | Balderas Ortiz, Ricardo I | 0 | 2 | 0 | 81 | 81 | 20011 | 0 | 0
120 | Roughin Labor | PR | 271 | 06/06/18 | 06/08/18 | BA45 | Balderas Ortiz, Ricardo I | 18 | 0 | 486 | 0 | 486 | 20011 | 0 | 0
120 | Roughin Labor | PR | 279 | 06/06/18 | 06/08/18 | CO71 | Cortes Mendiola, Victor H | 0 | 2 | 0 | 120 | 120 | 20019 | 0 | 0
120 | Roughin Labor | PR | 279 | 06/06/18 | 06/08/18 | CO71 | Cortes Mendiola, Victor H | 29 | 0 | 1160 | 0 | 1160 | 20019 | 0 | 0
120 | Roughin Labor | PR | 279 | 06/06/18 | 06/08/18 | CO71 | Cortes Mendiola, Victor H | 1 | 0 | 40 | 0 | 40 | 20019 | 0 | 0
120 | Roughin Labor | PR | 294 | 06/06/18 | 06/08/18 | GU78 | Gutierrez Salas, Jose | 32 | 0 | 576 | 0 | 576 | 20034 | 0 | 0
120 | Roughin Labor | PR | 301 | 06/06/18 | 06/08/18 | JU02 | Juarez Alvarez, Oscar R | 0 | 6 | 0 | 252 | 252 | 20041 | 0 | 0
120 | Roughin Labor | PR | 301 | 06/06/18 | 06/08/18 | JU02 | Juarez Alvarez, Oscar R | 40 | 0 | 1120 | 0 | 1120 | 20041 | 0 | 0
120 | Roughin Labor | PR | 302 | 06/06/18 | 06/08/18 | JU04 | Juarez Maldonado, Oscar E | 38 | 0 | 684 | 0 | 684 | 20042 | 0 | 0
120 | Roughin Labor | PR | 459 | 06/13/18 | 06/15/18 | AS10 | Ascencio, Jose L | 0 | 8 | 0 | 312 | 312 | 20094 | 0 | 0
120 | Roughin Labor | PR | 459 | 06/13/18 | 06/15/18 | AS10 | Ascencio, Jose L | 40 | 0 | 1040 | 0 | 1040 | 20094 | 0 | 0
120 | Roughin Labor | PR | 461 | 06/13/18 | 06/15/18 | BA45 | Balderas Ortiz, Ricardo I | 0 | 8 | 0 | 336 | 336 | 20096 | 0 | 0
120 | Roughin Labor | PR | 461 | 06/13/18 | 06/15/18 | BA45 | Balderas Ortiz, Ricardo I | 40 | 0 | 1120 | 0 | 1120 | 20096 | 0 | 0
120 | Roughin Labor | PR | 469 | 06/13/18 | 06/15/18 | CO71 | Cortes Mendiola, Victor H | 35 | 0 | 1435 | 0 | 1435 | 20104 | 0 | 0
120 | Roughin Labor | PR | 484 | 06/13/18 | 06/15/18 | GU78 | Gutierrez Salas, Jose | 18 | 0 | 324 | 0 | 324 | 20119 | 0 | 0
120 | Roughin Labor | PR | 491 | 06/13/18 | 06/15/18 | JU02 | Juarez Alvarez, Oscar R | 40 | 0 | 1160 | 0 | 1160 | 20126 | 0 | 0
120 | Roughin Labor | PR | 492 | 06/13/18 | 06/15/18 | JU04 | Juarez Maldonado, Oscar E | 30 | 0 | 570 | 0 | 570 | 20127 | 0 | 0
120 | Roughin Labor | PR | 685 | 06/20/18 | 06/22/18 | AS10 | Ascencio, Jose L | 0 | 6 | 0 | 234 | 234 | 20164 | 0 | 0
120 | Roughin Labor | PR | 685 | 06/20/18 | 06/22/18 | AS10 | Ascencio, Jose L | 40 | 0 | 1040 | 0 | 1040 | 20164 | 0 | 0
120 | Roughin Labor | PR | 687 | 06/20/18 | 06/22/18 | BA45 | Balderas Ortiz, Ricardo I | 0 | 8 | 0 | 336 | 336 | 20166 | 0 | 0
120 | Roughin Labor | PR | 687 | 06/20/18 | 06/22/18 | BA45 | Balderas Ortiz, Ricardo I | 40 | 0 | 1120 | 0 | 1120 | 20166 | 0 | 0
120 | Roughin Labor | PR | 695 | 06/20/18 | 06/22/18 | CO71 | Cortes Mendiola, Victor H | 0 | 2 | 0 | 123 | 123 | 20174 | 0 | 0
120 | Roughin Labor | PR | 695 | 06/20/18 | 06/22/18 | CO71 | Cortes Mendiola, Victor H | 36 | 0 | 1476 | 0 | 1476 | 20174 | 0 | 0
120 | Roughin Labor | PR | 717 | 06/20/18 | 06/22/18 | JU02 | Juarez Alvarez, Oscar R | 0 | 6 | 0 | 261 | 261 | 20196 | 0 | 0
120 | Roughin Labor | PR | 717 | 06/20/18 | 06/22/18 | JU02 | Juarez Alvarez, Oscar R | 40 | 0 | 1160 | 0 | 1160 | 20196 | 0 | 0
120 | Roughin Labor | PR | 718 | 06/20/18 | 06/22/18 | JU04 | Juarez Maldonado, Oscar E | 36 | 0 | 684 | 0 | 684 | 20197 | 0 | 0
120 | Roughin Labor | PR | 950 | 06/27/18 | 06/29/18 | CO73 | Cortes Sepulveda, Jose R | 0 | 1 | 0 | 36 | 36 | 19949 | 0 | 0
120 | Roughin Labor | PR | 950 | 06/27/18 | 06/29/18 | CO73 | Cortes Sepulveda, Jose R | 4 | 0 | 96 | 0 | 96 | 19949 | 0 | 0
120 | Roughin Labor | PR | 951 | 06/27/18 | 06/29/18 | BA45 | Balderas Ortiz, Ricardo I | 0 | 8 | 0 | 336 | 336 | 20232 | 0 | 0
120 | Roughin Labor | PR | 951 | 06/27/18 | 06/29/18 | BA45 | Balderas Ortiz, Ricardo I | 40 | 0 | 1120 | 0 | 1120 | 20232 | 0 | 0
120 | Roughin Labor | PR | 954 | 06/27/18 | 06/29/18 | AS10 | Ascencio, Jose L | 0 | 8 | 0 | 312 | 312 | 20235 | 0 | 0
120 | Roughin Labor | PR | 954 | 06/27/18 | 06/29/18 | AS10 | Ascencio, Jose L | 40 | 0 | 1040 | 0 | 1040 | 20235 | 0 | 0
120 | Roughin Labor | PR | 963 | 06/27/18 | 06/29/18 | CO71 | Cortes Mendiola, Victor H | 0 | 2 | 0 | 123 | 123 | 20244 | 0 | 0
120 | Roughin Labor | PR | 963 | 06/27/18 | 06/29/18 | CO71 | Cortes Mendiola, Victor H | 24 | 0 | 984 | 0 | 984 | 20244 | 0 | 0
120 | Roughin Labor | PR | 983 | 06/27/18 | 06/29/18 | HU06 | Hubbard, Robert W | 2 | 0 | 94 | 0 | 94 | 20263 | 0 | 0
120 | Roughin Labor | PR | 985 | 06/27/18 | 06/29/18 | JU02 | Juarez Alvarez, Oscar R | 0 | 8 | 0 | 348 | 348 | 20265 | 0 | 0
120 | Roughin Labor | PR | 985 | 06/27/18 | 06/29/18 | JU02 | Juarez Alvarez, Oscar R | 40 | 0 | 1160 | 0 | 1160 | 20265 | 0 | 0
120 | Roughin Labor | PR | 986 | 06/27/18 | 06/29/18 | JU04 | Juarez Maldonado, Oscar E | 0 | 8 | 0 | 228 | 228 | 20266 | 0 | 0
120 | Roughin Labor | PR | 986 | 06/27/18 | 06/29/18 | JU04 | Juarez Maldonado, Oscar E | 40 | 0 | 760 | 0 | 760 | 20266 | 0 | 0
120 | Roughin Labor | PR | 6 | 07/04/18 | 07/06/18 | AS10 | Ascencio, Jose L | 32 | 0 | 832 | 0 | 832 | 20303 | 0 | 0
120 | Roughin Labor | PR | 16 | 07/04/18 | 07/06/18 | CO71 | Cortes Mendiola, Victor H | 32 | 0 | 1312 | 0 | 1312 | 20313 | 0 | 0
120 | Roughin Labor | PR | 17 | 07/04/18 | 07/06/18 | CO73 | Cortes Sepulveda, Jose R | 7.5 | 0 | 180 | 0 | 180 | 20314 | 0 | 0
120 | Roughin Labor | PR | 38 | 07/04/18 | 07/06/18 | HU06 | Hubbard, Robert W | 3 | 0 | 141 | 0 | 141 | 20334 | 0 | 0
120 | Roughin Labor | PR | 40 | 07/04/18 | 07/06/18 | JU02 | Juarez Alvarez, Oscar R | 32 | 0 | 928 | 0 | 928 | 20336 | 0 | 0
120 | Roughin Labor | PR | 41 | 07/04/18 | 07/06/18 | JU04 | Juarez Maldonado, Oscar E | 24 | 0 | 456 | 0 | 456 | 20337 | 0 | 0
120 | Roughin Labor | PR | 299 | 07/11/18 | 07/13/18 | AS10 | Ascencio, Jose L | 34 | 0 | 884 | 0 | 884 | 20379 | 0 | 0
120 | Roughin Labor | PR | 300 | 07/11/18 | 07/13/18 | BA45 | Balderas Ortiz, Ricardo I | 16 | 0 | 448 | 0 | 448 | 20380 | 0 | 0
120 | Roughin Labor | PR | 307 | 07/11/18 | 07/13/18 | CO71 | Cortes Mendiola, Victor H | 24 | 0 | 984 | 0 | 984 | 20387 | 0 | 0
120 | Roughin Labor | PR | 307 | 07/11/18 | 07/13/18 | CO71 | Cortes Mendiola, Victor H | 0 | 3 | 0 | 184.5 | 184.5 | 20387 | 0 | 0
120 | Roughin Labor | PR | 308 | 07/11/18 | 07/13/18 | CO73 | Cortes Sepulveda, Jose R | 24 | 0 | 576 | 0 | 576 | 20388 | 0 | 0
120 | Roughin Labor | PR | 308 | 07/11/18 | 07/13/18 | CO73 | Cortes Sepulveda, Jose R | 0 | 4 | 0 | 144 | 144 | 20388 | 0 | 0
120 | Roughin Labor | PR | 329 | 07/11/18 | 07/13/18 | HU06 | Hubbard, Robert W | 5 | 0 | 235 | 0 | 235 | 20409 | 0 | 0
120 | Roughin Labor | PR | 331 | 07/11/18 | 07/13/18 | JU02 | Juarez Alvarez, Oscar R | 24 | 0 | 696 | 0 | 696 | 20411 | 0 | 0
120 | Roughin Labor | PR | 332 | 07/11/18 | 07/13/18 | JU04 | Juarez Maldonado, Oscar E | 32 | 0 | 608 | 0 | 608 | 20412 | 0 | 0
120 | Roughin Labor | PR | 439 | 07/18/18 | 07/20/18 | BA45 | Balderas Ortiz, Ricardo I | 16 | 0 | 448 | 0 | 448 | 20450 | 0 | 0
120 | Roughin Labor | PR | 447 | 07/18/18 | 07/20/18 | CO71 | Cortes Mendiola, Victor H | 8 | 0 | 328 | 0 | 328 | 20458 | 0 | 0
120 | Roughin Labor | PR | 472 | 07/18/18 | 07/20/18 | JU02 | Juarez Alvarez, Oscar R | 24 | 0 | 696 | 0 | 696 | 20482 | 0 | 0
120 | Roughin Labor | PR | 473 | 07/18/18 | 07/20/18 | JU04 | Juarez Maldonado, Oscar E | 23 | 0 | 437 | 0 | 437 | 20483 | 0 | 0
120 | Roughin Labor | PR | 765 | 07/25/18 | 07/27/18 | BA45 | Balderas Ortiz, Ricardo I | 40 | 0 | 1120 | 0 | 1120 | 20523 | 0 | 0
120 | Roughin Labor | PR | 773 | 07/25/18 | 07/27/18 | CO71 | Cortes Mendiola, Victor H | 6 | 0 | 246 | 0 | 246 | 20531 | 0 | 0
120 | Roughin Labor | PR | 774 | 07/25/18 | 07/27/18 | CO73 | Cortes Sepulveda, Jose R | 16 | 0 | 384 | 0 | 384 | 20532 | 0 | 0
120 | Roughin Labor | PR | 797 | 07/25/18 | 07/27/18 | HU06 | Hubbard, Robert W | 5 | 0 | 235 | 0 | 235 | 20554 | 0 | 0
120 | Roughin Labor | PR | 799 | 07/25/18 | 07/27/18 | JU02 | Juarez Alvarez, Oscar R | 24 | 0 | 696 | 0 | 696 | 20556 | 0 | 0
120 | Roughin Labor | PR | 803 | 07/25/18 | 07/27/18 | LI49 | Lima Romero, Melvin A | 8 | 0 | 256 | 0 | 256 | 20560 | 0 | 0
120 | Roughin Labor | PR | 4 | 08/01/18 | 08/03/18 | BA45 | Balderas Ortiz, Ricardo I | 40 | 0 | 1120 | 0 | 1120 | 20595 | 0 | 0
120 | Roughin Labor | PR | 12 | 08/01/18 | 08/03/18 | CO71 | Cortes Mendiola, Victor H | 16 | 0 | 656 | 0 | 656 | 20604 | 0 | 0
120 | Roughin Labor | PR | 13 | 08/01/18 | 08/03/18 | CO73 | Cortes Sepulveda, Jose R | 8 | 0 | 192 | 0 | 192 | 20605 | 0 | 0
120 | Roughin Labor | PR | 35 | 08/01/18 | 08/03/18 | HU06 | Hubbard, Robert W | 2 | 0 | 94 | 0 | 94 | 20626 | 0 | 0
120 | Roughin Labor | PR | 37 | 08/01/18 | 08/03/18 | JU02 | Juarez Alvarez, Oscar R | 32 | 0 | 1056 | 0 | 1056 | 20628 | 0 | 0
120 | Roughin Labor | PR | 41 | 08/01/18 | 08/03/18 | LI49 | Lima Romero, Melvin A | 24 | 0 | 768 | 0 | 768 | 20632 | 0 | 0
120 | Roughin Labor | PR | 214 | 08/08/18 | 08/10/18 | BA45 | Balderas Ortiz, Ricardo I | 24 | 0 | 672 | 0 | 672 | 20667 | 0 | 0
120 | Roughin Labor | PR | 222 | 08/08/18 | 08/10/18 | CO71 | Cortes Mendiola, Victor H | 16 | 0 | 656 | 0 | 656 | 20675 | 0 | 0
120 | Roughin Labor | PR | 223 | 08/08/18 | 08/10/18 | CO73 | Cortes Sepulveda, Jose R | 4 | 0 | 96 | 0 | 96 | 20676 | 0 | 0
120 | Roughin Labor | PR | 248 | 08/08/18 | 08/10/18 | JU02 | Juarez Alvarez, Oscar R | 40 | 0 | 1320 | 0 | 1320 | 20700 | 0 | 0
120 | Roughin Labor | PR | 252 | 08/08/18 | 08/10/18 | LI49 | Lima Romero, Melvin A | 16 | 0 | 512 | 0 | 512 | 20704 | 0 | 0
120 | Roughin Labor | PR | 275 | 08/08/18 | 08/10/18 | SI48 | Silva Morales, Jair J | 13 | 0 | 312 | 0 | 312 | 20727 | 0 | 0
120 | Roughin Labor | PR | 482 | 08/15/18 | 08/17/18 | BA45 | Balderas Ortiz, Ricardo I | 24 | 0 | 672 | 0 | 672 | 20740 | 0 | 0
120 | Roughin Labor | PR | 490 | 08/15/18 | 08/17/18 | CO71 | Cortes Mendiola, Victor H | 26 | 0 | 1066 | 0 | 1066 | 20748 | 0 | 0
120 | Roughin Labor | PR | 491 | 08/15/18 | 08/17/18 | CO73 | Cortes Sepulveda, Jose R | 8 | 0 | 192 | 0 | 192 | 20749 | 0 | 0
120 | Roughin Labor | PR | 514 | 08/15/18 | 08/17/18 | HU06 | Hubbard, Robert W | 4 | 0 | 188 | 0 | 188 | 20771 | 0 | 0
120 | Roughin Labor | PR | 516 | 08/15/18 | 08/17/18 | JU02 | Juarez Alvarez, Oscar R | 16 | 0 | 528 | 0 | 528 | 20773 | 0 | 0
120 | Roughin Labor | PR | 522 | 08/15/18 | 08/17/18 | LU09 | Lucas Tzintzun, Rafael | 16 | 0 | 272 | 0 | 272 | 20779 | 0 | 0
120 | Roughin Labor | PR | 743 | 08/22/18 | 08/24/18 | AS10 | Ascencio, Jose L | 32 | 0 | 832 | 0 | 832 | 20811 | 0 | 0
120 | Roughin Labor | PR | 744 | 08/22/18 | 08/24/18 | BA45 | Balderas Ortiz, Ricardo I | 40 | 0 | 1120 | 0 | 1120 | 20812 | 0 | 0
120 | Roughin Labor | PR | 752 | 08/22/18 | 08/24/18 | CO71 | Cortes Mendiola, Victor H | 32 | 0 | 1312 | 0 | 1312 | 20820 | 0 | 0
120 | Roughin Labor | PR | 753 | 08/22/18 | 08/24/18 | CO73 | Cortes Sepulveda, Jose R | 29 | 0 | 696 | 0 | 696 | 20821 | 0 | 0
120 | Roughin Labor | PR | 780 | 08/22/18 | 08/24/18 | LI49 | Lima Romero, Melvin A | 24 | 0 | 768 | 0 | 768 | 20847 | 0 | 0
120 | Roughin Labor | PR | 803 | 08/22/18 | 08/24/18 | SI48 | Silva Morales, Jair J | 16 | 0 | 384 | 0 | 384 | 20870 | 0 | 0
120 | Roughin Labor | PR | 997 | 08/29/18 | 08/31/18 | AS10 | Ascencio, Jose L | 40 | 0 | 1040 | 0 | 1040 | 20893 | 0 | 0
120 | Roughin Labor | PR | 998 | 08/29/18 | 08/31/18 | BA45 | Balderas Ortiz, Ricardo I | 32 | 0 | 896 | 0 | 896 | 20894 | 0 | 0
120 | Roughin Labor | PR | 1006 | 08/29/18 | 08/31/18 | CO71 | Cortes Mendiola, Victor H | 29 | 0 | 1189 | 0 | 1189 | 20902 | 0 | 0
120 | Roughin Labor | PR | 1007 | 08/29/18 | 08/31/18 | CO73 | Cortes Sepulveda, Jose R | 24 | 0 | 576 | 0 | 576 | 20903 | 0 | 0
120 | Roughin Labor | PR | 1031 | 08/29/18 | 08/31/18 | HU06 | Hubbard, Robert W | 1 | 0 | 47 | 0 | 47 | 20926 | 0 | 0
120 | Roughin Labor | PR | 1057 | 08/29/18 | 08/31/18 | SI48 | Silva Morales, Jair J | 16 | 0 | 384 | 0 | 384 | 20952 | 0 | 0
120 | Roughin Labor | PR | 38 | 09/05/18 | 09/07/18 | AS10 | Ascencio, Jose L | 32 | 0 | 832 | 0 | 832 | 20963 | 0 | 0
120 | Roughin Labor | PR | 39 | 09/05/18 | 09/07/18 | BA45 | Balderas Ortiz, Ricardo I | 32 | 0 | 896 | 0 | 896 | 20964 | 0 | 0
120 | Roughin Labor | PR | 47 | 09/05/18 | 09/07/18 | CO71 | Cortes Mendiola, Victor H | 3 | 0 | 123 | 0 | 123 | 20972 | 0 | 0
120 | Roughin Labor | PR | 48 | 09/05/18 | 09/07/18 | CO73 | Cortes Sepulveda, Jose R | 8 | 0 | 192 | 0 | 192 | 20973 | 0 | 0
120 | Roughin Labor | PR | 269 | 09/12/18 | 09/14/18 | AS10 | Ascencio, Jose L | 40 | 0 | 1040 | 0 | 1040 | 21104 | 0 | 0
120 | Roughin Labor | PR | 270 | 09/12/18 | 09/14/18 | BA45 | Balderas Ortiz, Ricardo I | 40 | 0 | 1120 | 0 | 1120 | 21105 | 0 | 0
120 | Roughin Labor | PR | 279 | 09/12/18 | 09/14/18 | CO73 | Cortes Sepulveda, Jose R | 8 | 0 | 192 | 0 | 192 | 21114 | 0 | 0
120 | Roughin Labor | PR | 297 | 09/12/18 | 09/14/18 | GU78 | Gutierrez Salas, Jose | 36 | 0 | 648 | 0 | 648 | 21131 | 0 | 0
120 | Roughin Labor | PR | 302 | 09/12/18 | 09/14/18 | HU06 | Hubbard, Robert W | 4 | 0 | 188 | 0 | 188 | 21136 | 0 | 0
120 | Roughin Labor | PR | 483 | 09/19/18 | 09/21/18 | AS10 | Ascencio, Jose L | 40 | 0 | 1040 | 0 | 1040 | 21175 | 0 | 0
120 | Roughin Labor | PR | 484 | 09/19/18 | 09/21/18 | BA45 | Balderas Ortiz, Ricardo I | 8 | 0 | 224 | 0 | 224 | 21176 | 0 | 0
120 | Roughin Labor | PR | 491 | 09/19/18 | 09/21/18 | CO71 | Cortes Mendiola, Victor H | 22 | 0 | 902 | 0 | 902 | 21183 | 0 | 0
120 | Roughin Labor | PR | 492 | 09/19/18 | 09/21/18 | CO73 | Cortes Sepulveda, Jose R | 6 | 0 | 144 | 0 | 144 | 21184 | 0 | 0
120 | Roughin Labor | PR | 667 | 09/26/18 | 09/28/18 | AS10 | Ascencio, Jose L | 24 | 0 | 624 | 0 | 624 | 21246 | 0 | 0
120 | Roughin Labor | PR | 668 | 09/26/18 | 09/28/18 | BA45 | Balderas Ortiz, Ricardo I | 24 | 0 | 672 | 0 | 672 | 21247 | 0 | 0
120 | Roughin Labor | PR | 676 | 09/26/18 | 09/28/18 | CO71 | Cortes Mendiola, Victor H | 29 | 0 | 1189 | 0 | 1189 | 21255 | 0 | 0
120 | Roughin Labor | PR | 677 | 09/26/18 | 09/28/18 | CO73 | Cortes Sepulveda, Jose R | 29 | 0 | 696 | 0 | 696 | 21256 | 0 | 0
120 | Roughin Labor | PR | 695 | 09/26/18 | 09/28/18 | GU78 | Gutierrez Salas, Jose | 16 | 0 | 288 | 0 | 288 | 21273 | 0 | 0
120 | Roughin Labor | PR | 700 | 09/26/18 | 09/28/18 | HU06 | Hubbard, Robert W | 4 | 0 | 188 | 0 | 188 | 21278 | 0 | 0
120 | Roughin Labor | PR | 31 | 10/03/18 | 10/05/18 | AS10 | Ascencio, Jose L | 40 | 0 | 1040 | 0 | 1040 | 21320 | 0 | 0
120 | Roughin Labor | PR | 32 | 10/03/18 | 10/05/18 | BA45 | Balderas Ortiz, Ricardo I | 40 | 0 | 1120 | 0 | 1120 | 21321 | 0 | 0
120 | Roughin Labor | PR | 40 | 10/03/18 | 10/05/18 | CO71 | Cortes Mendiola, Victor H | 28 | 0 | 1148 | 0 | 1148 | 21329 | 0 | 0
120 | Roughin Labor | PR | 41 | 10/03/18 | 10/05/18 | CO73 | Cortes Sepulveda, Jose R | 16 | 0 | 384 | 0 | 384 | 21330 | 0 | 0
120 | Roughin Labor | PR | 59 | 10/03/18 | 10/05/18 | GU78 | Gutierrez Salas, Jose | 31 | 0 | 558 | 0 | 558 | 21347 | 0 | 0
120 | Roughin Labor | PR | 237 | 10/10/18 | 10/12/18 | BA45 | Balderas Ortiz, Ricardo I | 24 | 0 | 672 | 0 | 672 | 21394 | 0 | 0
120 | Roughin Labor | PR | 245 | 10/10/18 | 10/12/18 | CO71 | Cortes Mendiola, Victor H | 8 | 0 | 328 | 0 | 328 | 21403 | 0 | 0
120 | Roughin Labor | PR | 246 | 10/10/18 | 10/12/18 | CO73 | Cortes Sepulveda, Jose R | 8 | 0 | 192 | 0 | 192 | 21404 | 0 | 0
120 | Roughin Labor | PR | 265 | 10/10/18 | 10/12/18 | GU78 | Gutierrez Salas, Jose | 16 | 0 | 288 | 0 | 288 | 21422 | 0 | 0
120 | Roughin Labor | PR | 436 | 10/17/18 | 10/19/18 | BA45 | Balderas Ortiz, Ricardo I | 32 | 0 | 896 | 0 | 896 | 21469 | 0 | 0
120 | Roughin Labor | PR | 444 | 10/17/18 | 10/19/18 | CO71 | Cortes Mendiola, Victor H | 20 | 0 | 820 | 0 | 820 | 21478 | 0 | 0
120 | Roughin Labor | PR | 445 | 10/17/18 | 10/19/18 | CO73 | Cortes Sepulveda, Jose R | 20 | 0 | 480 | 0 | 480 | 21479 | 0 | 0
120 | Roughin Labor | PR | 712 | 10/24/18 | 10/26/18 | CO71 | Cortes Mendiola, Victor H | 20 | 0 | 820 | 0 | 820 | 21552 | 0 | 0
120 | Roughin Labor | PR | 713 | 10/24/18 | 10/26/18 | CO73 | Cortes Sepulveda, Jose R | 16 | 0 | 384 | 0 | 384 | 21553 | 0 | 0
120 | Roughin Labor | PR | 14 | 10/31/18 | 11/02/18 | CO71 | Cortes Mendiola, Victor H | 8 | 0 | 328 | 0 | 328 | 21624 | 0 | 0
120 | Roughin Labor | PR | 15 | 10/31/18 | 11/02/18 | CO73 | Cortes Sepulveda, Jose R | 8 | 0 | 192 | 0 | 192 | 21625 | 0 | 0
120 | Roughin Labor | PR | 192 | 11/07/18 | 11/09/18 | CO71 | Cortes Mendiola, Victor H | 21 | 0 | 861 | 0 | 861 | 21696 | 0 | 0
120 | Roughin Labor | PR | 193 | 11/07/18 | 11/09/18 | CO73 | Cortes Sepulveda, Jose R | 21 | 0 | 504 | 0 | 504 | 21697 | 0 | 0
120 | Roughin Labor | PR | 441 | 11/14/18 | 11/16/18 | CO71 | Cortes Mendiola, Victor H | 8 | 0 | 328 | 0 | 328 | 21770 | 0 | 0
120 | Roughin Labor | PR | 442 | 11/14/18 | 11/16/18 | CO73 | Cortes Sepulveda, Jose R | 8 | 0 | 192 | 0 | 192 | 21771 | 0 | 0
120 | Roughin Labor | PR | 268 | 12/12/18 | 12/14/18 | BA45 | Balderas Ortiz, Ricardo I | 8 | 0 | 232 | 0 | 232 | 22128 | 0 | 0
120 | Roughin Labor | PR | 276 | 12/12/18 | 12/14/18 | CO71 | Cortes Mendiola, Victor H | 4 | 0 | 172 | 0 | 172 | 22136 | 0 | 0
120 | Roughin Labor | PR | 277 | 12/12/18 | 12/14/18 | CO73 | Cortes Sepulveda, Jose R | 12 | 0 | 312 | 0 | 312 | 22137 | 0 | 0
120 | Roughin Labor | PR | 5 | 01/02/19 | 01/04/19 | BA45 | Balderas Ortiz, Ricardo I | 8 | 0 | 232 | 0 | 232 | 22345 | 0 | 0
120 | Roughin Labor | PR | 14 | 01/02/19 | 01/04/19 | CO73 | Cortes Sepulveda, Jose R | 8 | 0 | 208 | 0 | 208 | 22354 | 0 | 0
120 | Roughin Labor | PR | 222 | 01/09/19 | 01/11/19 | CO73 | Cortes Sepulveda, Jose R | 18 | 0 | 468 | 0 | 468 | 22424 | 0 | 0
120 | Roughin Labor | PR | 477 | 01/16/19 | 01/18/19 | CO73 | Cortes Sepulveda, Jose R | 17 | 0 | 442 | 0 | 442 | 22498 | 0 | 0
120 | Roughin Labor | PR | 778 | 01/23/19 | 01/25/19 | TA96 | Taylor, Evan R | 0 | 8 | 0 | 312 | 312 | 22623 | 0 | 0
120 | Roughin Labor | PR | 168 | 02/06/19 | 02/08/19 | CO71 | Cortes Mendiola, Victor H | 5 | 0 | 215 | 0 | 215 | 22710 | 0 | 0
120 | Roughin Labor | PR | 330 | 02/13/19 | 02/15/19 | CO71 | Cortes Mendiola, Victor H | 5 | 0 | 215 | 0 | 215 | 22779 | 0 | 0
120 | Roughin Labor | PR | 13 | 02/27/19 | 03/01/19 | CO71 | Cortes Mendiola, Victor H | 4 | 0 | 172 | 0 | 172 | 22920 | 0 | 0
120 | Roughin Labor | PR | 255 | 03/06/19 | 03/08/19 | CO71 | Cortes Mendiola, Victor H | 3 | 0 | 129 | 0 | 129 | 22993 | 0 | 0
130 | Finish Labor | PR | 492 | 08/23/17 | 08/25/17 | SA54 | Sanders, Allen O | 5.5 | 0 | 214.5 | 0 | 214.5 | 17255 | 0 | 0
130 | Finish Labor | PR | 540 | 09/19/18 | 09/21/18 | SA54 | Sanders, Allen O | 4 | 0 | 176 | 0 | 176 | 21231 | 0 | 0
130 | Finish Labor | PR | 450 | 11/14/18 | 11/16/18 | EL33 | Eliassen, Cory H | 8 | 0 | 184 | 0 | 184 | 21778 | 0 | 0
130 | Finish Labor | PR | 452 | 11/14/18 | 11/16/18 | FO55 | Fonseca Teruel, Eduardo | 16 | 0 | 288 | 0 | 288 | 21780 | 0 | 0
130 | Finish Labor | PR | 458 | 11/14/18 | 11/16/18 | GO51 | Gomez Reyes, Edith N | 16 | 0 | 336 | 0 | 336 | 21786 | 0 | 0
130 | Finish Labor | PR | 483 | 11/14/18 | 11/16/18 | RE91 | Reyes, Maria E | 16 | 0 | 256 | 0 | 256 | 21811 | 0 | 0
130 | Finish Labor | PR | 490 | 11/14/18 | 11/16/18 | SA54 | Sanders, Allen O | 7 | 0 | 308 | 0 | 308 | 21818 | 0 | 0
130 | Finish Labor | PR | 494 | 11/14/18 | 11/16/18 | ST02 | Stahlschmidt, John P | 8 | 0 | 128 | 0 | 128 | 21822 | 0 | 0
130 | Finish Labor | PR | 502 | 11/14/18 | 11/16/18 | YO29 | Yohannes Jr., Samson | 8 | 0 | 144 | 0 | 144 | 21830 | 0 | 0
130 | Finish Labor | PR | 637 | 11/21/18 | 11/21/18 | FO55 | Fonseca Teruel, Eduardo | 8 | 0 | 144 | 0 | 144 | 21858 | 0 | 0
130 | Finish Labor | PR | 667 | 11/21/18 | 11/21/18 | RE91 | Reyes, Maria E | 8 | 0 | 128 | 0 | 128 | 21888 | 0 | 0
130 | Finish Labor | PR | 674 | 11/21/18 | 11/21/18 | SA54 | Sanders, Allen O | 0 | 0.5 | 0 | 33 | 33 | 21895 | 0 | 0
130 | Finish Labor | PR | 674 | 11/21/18 | 11/21/18 | SA54 | Sanders, Allen O | 9 | 0 | 396 | 0 | 396 | 21895 | 0 | 0
130 | Finish Labor | PR | 678 | 11/21/18 | 11/21/18 | ST02 | Stahlschmidt, John P | 8 | 0 | 128 | 0 | 128 | 21899 | 0 | 0
130 | Finish Labor | PR | 686 | 11/21/18 | 11/21/18 | YO29 | Yohannes Jr., Samson | 8 | 0 | 144 | 0 | 144 | 21907 | 0 | 0
130 | Finish Labor | PR | 887 | 11/28/18 | 11/30/18 | SA54 | Sanders, Allen O | 9 | 0 | 423 | 0 | 423 | 21969 | 0 | 0
130 | Finish Labor | PR | 63 | 12/05/18 | 12/07/18 | FO55 | Fonseca Teruel, Eduardo | 8 | 0 | 144 | 0 | 144 | 22005 | 0 | 0
130 | Finish Labor | PR | 69 | 12/05/18 | 12/07/18 | GO51 | Gomez Reyes, Edith N | 8 | 0 | 184 | 0 | 184 | 22011 | 0 | 0
130 | Finish Labor | PR | 92 | 12/05/18 | 12/07/18 | RE91 | Reyes, Maria E | 8 | 0 | 144 | 0 | 144 | 22034 | 0 | 0
130 | Finish Labor | PR | 99 | 12/05/18 | 12/07/18 | SA54 | Sanders, Allen O | 8.5 | 0 | 399.5 | 0 | 399.5 | 22041 | 0 | 0
130 | Finish Labor | PR | 287 | 12/12/18 | 12/14/18 | FO55 | Fonseca Teruel, Eduardo | 0 | 2 | 0 | 54 | 54 | 22146 | 0 | 0
130 | Finish Labor | PR | 287 | 12/12/18 | 12/14/18 | FO55 | Fonseca Teruel, Eduardo | 8 | 0 | 144 | 0 | 144 | 22146 | 0 | 0
130 | Finish Labor | PR | 293 | 12/12/18 | 12/14/18 | GO51 | Gomez Reyes, Edith N | 0 | 2 | 0 | 69 | 69 | 22152 | 0 | 0
130 | Finish Labor | PR | 293 | 12/12/18 | 12/14/18 | GO51 | Gomez Reyes, Edith N | 8 | 0 | 184 | 0 | 184 | 22152 | 0 | 0
130 | Finish Labor | PR | 317 | 12/12/18 | 12/14/18 | RE91 | Reyes, Maria E | 0 | 2 | 0 | 54 | 54 | 22176 | 0 | 0
130 | Finish Labor | PR | 317 | 12/12/18 | 12/14/18 | RE91 | Reyes, Maria E | 8 | 0 | 144 | 0 | 144 | 22176 | 0 | 0
130 | Finish Labor | PR | 324 | 12/12/18 | 12/14/18 | SA54 | Sanders, Allen O | 4 | 0 | 188 | 0 | 188 | 22183 | 0 | 0
130 | Finish Labor | PR | 564 | 12/19/18 | 12/21/18 | SA54 | Sanders, Allen O | 3 | 0 | 141 | 0 | 141 | 22254 | 0 | 0
130 | Finish Labor | PR | 755 | 12/26/18 | 12/28/18 | SA54 | Sanders, Allen O | 4 | 0 | 188 | 0 | 188 | 22328 | 0 | 0
130 | Finish Labor | PR | 23 | 01/02/19 | 01/04/19 | FO55 | Fonseca Teruel, Eduardo | 8 | 0 | 144 | 0 | 144 | 22364 | 0 | 0
130 | Finish Labor | PR | 58 | 01/02/19 | 01/04/19 | SA54 | Sanders, Allen O | 1 | 0 | 47 | 0 | 47 | 22399 | 0 | 0
130 | Finish Labor | PR | 62 | 01/02/19 | 01/04/19 | ST02 | Stahlschmidt, John P | 8 | 0 | 136 | 0 | 136 | 22403 | 0 | 0
130 | Finish Labor | PR | 231 | 01/09/19 | 01/11/19 | FO55 | Fonseca Teruel, Eduardo | 16 | 0 | 288 | 0 | 288 | 22433 | 0 | 0
130 | Finish Labor | PR | 268 | 01/09/19 | 01/11/19 | SA54 | Sanders, Allen O | 11 | 0 | 517 | 0 | 517 | 22470 | 0 | 0
130 | Finish Labor | PR | 272 | 01/09/19 | 01/11/19 | ST02 | Stahlschmidt, John P | 16 | 0 | 272 | 0 | 272 | 22474 | 0 | 0
130 | Finish Labor | PR | 484 | 01/16/19 | 01/18/19 | EL33 | Eliassen, Cory H | 0 | 10 | 0 | 375 | 375 | 22505 | 0 | 0
130 | Finish Labor | PR | 484 | 01/16/19 | 01/18/19 | EL33 | Eliassen, Cory H | 16 | 0 | 400 | 0 | 400 | 22505 | 0 | 0
130 | Finish Labor | PR | 492 | 01/16/19 | 01/18/19 | GO51 | Gomez Reyes, Edith N | 0 | 10 | 0 | 345 | 345 | 22513 | 0 | 0
130 | Finish Labor | PR | 492 | 01/16/19 | 01/18/19 | GO51 | Gomez Reyes, Edith N | 8 | 0 | 184 | 0 | 184 | 22513 | 0 | 0
130 | Finish Labor | PR | 516 | 01/16/19 | 01/18/19 | RE91 | Reyes, Maria E | 0 | 10 | 0 | 270 | 270 | 22537 | 0 | 0
130 | Finish Labor | PR | 516 | 01/16/19 | 01/18/19 | RE91 | Reyes, Maria E | 8 | 0 | 144 | 0 | 144 | 22537 | 0 | 0
130 | Finish Labor | PR | 523 | 01/16/19 | 01/18/19 | SA54 | Sanders, Allen O | 0 | 7.5 | 0 | 528.75 | 528.75 | 22544 | 0 | 0
130 | Finish Labor | PR | 523 | 01/16/19 | 01/18/19 | SA54 | Sanders, Allen O | 12 | 0 | 564 | 0 | 564 | 22544 | 0 | 0
130 | Finish Labor | PR | 530 | 01/16/19 | 01/18/19 | TR60 | Trower-Kelly, Fidel D | 0 | 12 | 0 | 288 | 288 | 22551 | 0 | 0
130 | Finish Labor | PR | 530 | 01/16/19 | 01/18/19 | TR60 | Trower-Kelly, Fidel D | 24 | 0 | 384 | 0 | 384 | 22551 | 0 | 0
130 | Finish Labor | PR | 733 | 01/23/19 | 01/25/19 | EL33 | Eliassen, Cory H | 0 | 8 | 0 | 300 | 300 | 22578 | 0 | 0
130 | Finish Labor | PR | 733 | 01/23/19 | 01/25/19 | EL33 | Eliassen, Cory H | 24 | 0 | 600 | 0 | 600 | 22578 | 0 | 0
130 | Finish Labor | PR | 735 | 01/23/19 | 01/25/19 | FO55 | Fonseca Teruel, Eduardo | 0 | 4 | 0 | 108 | 108 | 22580 | 0 | 0
130 | Finish Labor | PR | 741 | 01/23/19 | 01/25/19 | GO51 | Gomez Reyes, Edith N | 14 | 0 | 322 | 0 | 322 | 22586 | 0 | 0
130 | Finish Labor | PR | 756 | 01/23/19 | 01/25/19 | MC09 | McCabe, Thomas C | 0 | 1 | 0 | 49.5 | 49.5 | 22601 | 0 | 0
130 | Finish Labor | PR | 756 | 01/23/19 | 01/25/19 | MC09 | McCabe, Thomas C | 5 | 0 | 165 | 0 | 165 | 22601 | 0 | 0
130 | Finish Labor | PR | 765 | 01/23/19 | 01/25/19 | RE91 | Reyes, Maria E | 0 | 7.5 | 0 | 202.5 | 202.5 | 22610 | 0 | 0
130 | Finish Labor | PR | 765 | 01/23/19 | 01/25/19 | RE91 | Reyes, Maria E | 16 | 0 | 288 | 0 | 288 | 22610 | 0 | 0
130 | Finish Labor | PR | 772 | 01/23/19 | 01/25/19 | SA54 | Sanders, Allen O | 0 | 5.5 | 0 | 387.75 | 387.75 | 22617 | 0 | 0
130 | Finish Labor | PR | 772 | 01/23/19 | 01/25/19 | SA54 | Sanders, Allen O | 7 | 0 | 329 | 0 | 329 | 22617 | 0 | 0
130 | Finish Labor | PR | 779 | 01/23/19 | 01/25/19 | TR60 | Trower-Kelly, Fidel D | 0 | 8 | 0 | 192 | 192 | 22624 | 0 | 0
130 | Finish Labor | PR | 779 | 01/23/19 | 01/25/19 | TR60 | Trower-Kelly, Fidel D | 32 | 0 | 512 | 0 | 512 | 22624 | 0 | 0
130 | Finish Labor | PR | 21 | 01/30/19 | 02/01/19 | EL33 | Eliassen, Cory H | 0 | 9.5 | 0 | 356.25 | 356.25 | 22650 | 0 | 0
130 | Finish Labor | PR | 21 | 01/30/19 | 02/01/19 | EL33 | Eliassen, Cory H | 35 | 0 | 875 | 0 | 875 | 22650 | 0 | 0
130 | Finish Labor | PR | 23 | 01/30/19 | 02/01/19 | FO55 | Fonseca Teruel, Eduardo | 0 | 8 | 0 | 216 | 216 | 22652 | 0 | 0
130 | Finish Labor | PR | 29 | 01/30/19 | 02/01/19 | GO51 | Gomez Reyes, Edith N | 0 | 9 | 0 | 310.5 | 310.5 | 22658 | 0 | 0
130 | Finish Labor | PR | 29 | 01/30/19 | 02/01/19 | GO51 | Gomez Reyes, Edith N | 16 | 0 | 368 | 0 | 368 | 22658 | 0 | 0
130 | Finish Labor | PR | 44 | 01/30/19 | 02/01/19 | MC09 | McCabe, Thomas C | 8 | 0 | 264 | 0 | 264 | 22673 | 0 | 0
130 | Finish Labor | PR | 51 | 01/30/19 | 02/01/19 | RE91 | Reyes, Maria E | 0 | 9 | 0 | 243 | 243 | 22680 | 0 | 0
130 | Finish Labor | PR | 51 | 01/30/19 | 02/01/19 | RE91 | Reyes, Maria E | 16 | 0 | 288 | 0 | 288 | 22680 | 0 | 0
130 | Finish Labor | PR | 57 | 01/30/19 | 02/01/19 | SA54 | Sanders, Allen O | 0 | 9 | 0 | 634.5 | 634.5 | 22686 | 0 | 0
130 | Finish Labor | PR | 57 | 01/30/19 | 02/01/19 | SA54 | Sanders, Allen O | 13 | 0 | 611 | 0 | 611 | 22686 | 0 | 0
130 | Finish Labor | PR | 61 | 01/30/19 | 02/01/19 | ST02 | Stahlschmidt, John P | 0 | 8 | 0 | 204 | 204 | 22690 | 0 | 0
130 | Finish Labor | PR | 64 | 01/30/19 | 02/01/19 | TR60 | Trower-Kelly, Fidel D | 0 | 9.5 | 0 | 228 | 228 | 22693 | 0 | 0
130 | Finish Labor | PR | 64 | 01/30/19 | 02/01/19 | TR60 | Trower-Kelly, Fidel D | 35 | 0 | 560 | 0 | 560 | 22693 | 0 | 0
130 | Finish Labor | PR | 176 | 02/06/19 | 02/08/19 | EL33 | Eliassen, Cory H | 21 | 0 | 525 | 0 | 525 | 22718 | 0 | 0
130 | Finish Labor | PR | 213 | 02/06/19 | 02/08/19 | SA54 | Sanders, Allen O | 5 | 0 | 235 | 0 | 235 | 22755 | 0 | 0
130 | Finish Labor | PR | 220 | 02/06/19 | 02/08/19 | TR60 | Trower-Kelly, Fidel D | 21 | 0 | 336 | 0 | 336 | 22762 | 0 | 0
130 | Finish Labor | PR | 338 | 02/13/19 | 02/15/19 | EL33 | Eliassen, Cory H | 19 | 0 | 475 | 0 | 475 | 22787 | 0 | 0
130 | Finish Labor | PR | 375 | 02/13/19 | 02/15/19 | SA54 | Sanders, Allen O | 4.5 | 0 | 211.5 | 0 | 211.5 | 22826 | 0 | 0
130 | Finish Labor | PR | 382 | 02/13/19 | 02/15/19 | TR60 | Trower-Kelly, Fidel D | 19 | 0 | 304 | 0 | 304 | 22833 | 0 | 0
130 | Finish Labor | PR | 596 | 02/20/19 | 02/22/19 | EL33 | Eliassen, Cory H | 0 | 2 | 0 | 75 | 75 | 22858 | 0 | 0
130 | Finish Labor | PR | 596 | 02/20/19 | 02/22/19 | EL33 | Eliassen, Cory H | 13 | 0 | 325 | 0 | 325 | 22858 | 0 | 0
130 | Finish Labor | PR | 634 | 02/20/19 | 02/22/19 | SA54 | Sanders, Allen O | 0 | 2 | 0 | 141 | 141 | 22896 | 0 | 0
130 | Finish Labor | PR | 641 | 02/20/19 | 02/22/19 | TR60 | Trower-Kelly, Fidel D | 0 | 2 | 0 | 48 | 48 | 22903 | 0 | 0
130 | Finish Labor | PR | 641 | 02/20/19 | 02/22/19 | TR60 | Trower-Kelly, Fidel D | 5 | 0 | 80 | 0 | 80 | 22903 | 0 | 0
130 | Finish Labor | PR | 22 | 02/27/19 | 03/01/19 | EL33 | Eliassen, Cory H | 9 | 0 | 225 | 0 | 225 | 22929 | 0 | 0
130 | Finish Labor | PR | 61 | 02/27/19 | 03/01/19 | SA54 | Sanders, Allen O | 1 | 0 | 47 | 0 | 47 | 22968 | 0 | 0
130 | Finish Labor | PR | 264 | 03/06/19 | 03/08/19 | EL33 | Eliassen, Cory H | 3 | 0 | 75 | 0 | 75 | 23003 | 0 | 0
130 | Finish Labor | PR | 300 | 03/06/19 | 03/08/19 | SA54 | Sanders, Allen O | 2 | 0 | 94 | 0 | 94 | 23039 | 0 | 0
130 | Finish Labor | PR | 307 | 03/06/19 | 03/08/19 | TR60 | Trower-Kelly, Fidel D | 3 | 0 | 48 | 0 | 48 | 23046 | 0 | 0
130 | Finish Labor | PR | 511 | 03/13/19 | 03/15/19 | EL33 | Eliassen, Cory H | 7 | 0 | 175 | 0 | 175 | 23073 | 0 | 0
130 | Finish Labor | PR | 547 | 03/13/19 | 03/15/19 | SA54 | Sanders, Allen O | 3 | 0 | 141 | 0 | 141 | 23109 | 0 | 0
130 | Finish Labor | PR | 555 | 03/13/19 | 03/15/19 | TR60 | Trower-Kelly, Fidel D | 4 | 0 | 64 | 0 | 64 | 23117 | 0 | 0
130 | Finish Labor | PR | 725 | 03/20/19 | 03/22/19 | EL33 | Eliassen, Cory H | 4 | 0 | 100 | 0 | 100 | 23146 | 0 | 0
130 | Finish Labor | PR | 760 | 03/20/19 | 03/22/19 | SA54 | Sanders, Allen O | 3 | 0 | 141 | 0 | 141 | 23181 | 0 | 0
130 | Finish Labor | PR | 769 | 03/20/19 | 03/22/19 | TR60 | Trower-Kelly, Fidel D | 4 | 0 | 64 | 0 | 64 | 23190 | 0 | 0
130 | Finish Labor | PR | 927 | 03/27/19 | 03/29/19 | CO71 | Cortes Mendiola, Victor H | 3 | 0 | 129 | 0 | 129 | 23211 | 0 | 0
130 | Finish Labor | PR | 936 | 03/27/19 | 03/29/19 | EL33 | Eliassen, Cory H | 3 | 0 | 75 | 0 | 75 | 23220 | 0 | 0
130 | Finish Labor | PR | 972 | 03/27/19 | 03/29/19 | SA54 | Sanders, Allen O | 0 | 2 | 0 | 141 | 141 | 23256 | 0 | 0
130 | Finish Labor | PR | 85 | 04/03/19 | 04/05/19 | BE54 | Benites Portillo, Marvin E | 0 | 2 | 0 | 72 | 72 | 23279 | 0 | 0
130 | Finish Labor | PR | 85 | 04/03/19 | 04/05/19 | BE54 | Benites Portillo, Marvin E | 5 | 0 | 120 | 0 | 120 | 23279 | 0 | 0
130 | Finish Labor | PR | 89 | 04/03/19 | 04/05/19 | CO71 | Cortes Mendiola, Victor H | 0 | 2 | 0 | 129 | 129 | 23283 | 0 | 0
130 | Finish Labor | PR | 89 | 04/03/19 | 04/05/19 | CO71 | Cortes Mendiola, Victor H | 5 | 0 | 215 | 0 | 215 | 23283 | 0 | 0
130 | Finish Labor | PR | 578 | 04/17/19 | 04/19/19 | SA54 | Sanders, Allen O | 2 | 0 | 98 | 0 | 98 | 23479 | 0 | 0
130 | Finish Labor | PR | 750 | 04/24/19 | 04/26/19 | CO71 | Cortes Mendiola, Victor H | 3 | 0 | 138 | 0 | 138 | 23507 | 0 | 0
130 | Finish Labor | PR | 797 | 04/24/19 | 04/26/19 | SA54 | Sanders, Allen O | 4.5 | 0 | 220.5 | 0 | 220.5 | 23554 | 0 | 0
130 | Finish Labor | PR | 66 | 05/01/19 | 05/03/19 | SA54 | Sanders, Allen O | 2 | 0 | 98 | 0 | 98 | 23628 | 0 | 0
130 | Finish Labor | PR | 179 | 05/08/19 | 05/10/19 | EL33 | Eliassen, Cory H | 0 | 0.5 | 0 | 20.25 | 20.25 | 23663 | 0 | 0
130 | Finish Labor | PR | 179 | 05/08/19 | 05/10/19 | EL33 | Eliassen, Cory H | 5 | 0 | 135 | 0 | 135 | 23663 | 0 | 0
130 | Finish Labor | PR | 219 | 05/08/19 | 05/10/19 | SA54 | Sanders, Allen O | 5 | 0 | 245 | 0 | 245 | 23704 | 0 | 0
130 | Finish Labor | PR | 427 | 05/15/19 | 05/17/19 | HU06 | Hubbard, Robert W | 4 | 0 | 200 | 0 | 200 | 23758 | 0 | 0
130 | Finish Labor | PR | 451 | 05/15/19 | 05/17/19 | SA54 | Sanders, Allen O | 9 | 0 | 441 | 0 | 441 | 23782 | 0 | 0
130 | Finish Labor | PR | 663 | 05/22/19 | 05/24/19 | SA54 | Sanders, Allen O | 2 | 0 | 98 | 0 | 98 | 23858 | 0 | 0
140 | Gas Labor | PR | 207 | 02/07/18 | 02/09/18 | PA11 | Paco Leyva, Orlando | 16 | 0 | 544 | 0 | 544 | 18848 | 0 | 0
140 | Gas Labor | PR | 229 | 02/07/18 | 02/09/18 | PA11 | Paco Leyva, Orlando | 16 | 0 | -544 | 0 | -544 | 18870 | 0 | 0
140 | Gas Labor | PR | 14 | 05/30/18 | 06/01/18 | CO71 | Cortes Mendiola, Victor H | 1 | 0 | 40 | 0 | 40 | 19947 | 0 | 0
140 | Gas Labor | PR | 279 | 06/06/18 | 06/08/18 | CO71 | Cortes Mendiola, Victor H | 0 | 2 | 0 | 120 | 120 | 20019 | 0 | 0
140 | Gas Labor | PR | 469 | 06/13/18 | 06/15/18 | CO71 | Cortes Mendiola, Victor H | 0 | 1 | 0 | 61.5 | 61.5 | 20104 | 0 | 0
140 | Gas Labor | PR | 695 | 06/20/18 | 06/22/18 | CO71 | Cortes Mendiola, Victor H | 0 | 1 | 0 | 61.5 | 61.5 | 20174 | 0 | 0
140 | Gas Labor | PR | 963 | 06/27/18 | 06/29/18 | CO71 | Cortes Mendiola, Victor H | 0 | 1 | 0 | 61.5 | 61.5 | 20244 | 0 | 0
140 | Gas Labor | PR | 963 | 06/27/18 | 06/29/18 | CO71 | Cortes Mendiola, Victor H | 3 | 0 | 123 | 0 | 123 | 20244 | 0 | 0
140 | Gas Labor | PR | 38 | 07/04/18 | 07/06/18 | HU06 | Hubbard, Robert W | 2 | 0 | 94 | 0 | 94 | 20334 | 0 | 0
140 | Gas Labor | PR | 329 | 07/11/18 | 07/13/18 | HU06 | Hubbard, Robert W | 2 | 0 | 94 | 0 | 94 | 20409 | 0 | 0
140 | Gas Labor | PR | 447 | 07/18/18 | 07/20/18 | CO71 | Cortes Mendiola, Victor H | 0 | 1 | 0 | 61.5 | 61.5 | 20458 | 0 | 0
140 | Gas Labor | PR | 447 | 07/18/18 | 07/20/18 | CO71 | Cortes Mendiola, Victor H | 24 | 0 | 984 | 0 | 984 | 20458 | 0 | 0
140 | Gas Labor | PR | 448 | 07/18/18 | 07/20/18 | CO73 | Cortes Sepulveda, Jose R | 16 | 0 | 384 | 0 | 384 | 20459 | 0 | 0
140 | Gas Labor | PR | 472 | 07/18/18 | 07/20/18 | JU02 | Juarez Alvarez, Oscar R | 8 | 0 | 232 | 0 | 232 | 20482 | 0 | 0
140 | Gas Labor | PR | 473 | 07/18/18 | 07/20/18 | JU04 | Juarez Maldonado, Oscar E | 8 | 0 | 152 | 0 | 152 | 20483 | 0 | 0
140 | Gas Labor | PR | 773 | 07/25/18 | 07/27/18 | CO71 | Cortes Mendiola, Victor H | 10 | 0 | 410 | 0 | 410 | 20531 | 0 | 0
140 | Gas Labor | PR | 222 | 08/08/18 | 08/10/18 | CO71 | Cortes Mendiola, Victor H | 4 | 0 | 164 | 0 | 164 | 20675 | 0 | 0
140 | Gas Labor | PR | 490 | 08/15/18 | 08/17/18 | CO71 | Cortes Mendiola, Victor H | 10 | 0 | 410 | 0 | 410 | 20748 | 0 | 0
140 | Gas Labor | PR | 1006 | 08/29/18 | 08/31/18 | CO71 | Cortes Mendiola, Victor H | 3 | 0 | 123 | 0 | 123 | 20902 | 0 | 0
140 | Gas Labor | PR | 47 | 09/05/18 | 09/07/18 | CO71 | Cortes Mendiola, Victor H | 8 | 0 | 328 | 0 | 328 | 20972 | 0 | 0
140 | Gas Labor | PR | 278 | 09/12/18 | 09/14/18 | CO71 | Cortes Mendiola, Victor H | 8 | 0 | 328 | 0 | 328 | 21113 | 0 | 0
140 | Gas Labor | PR | 484 | 09/19/18 | 09/21/18 | BA45 | Balderas Ortiz, Ricardo I | 24 | 0 | 672 | 0 | 672 | 21176 | 0 | 0
140 | Gas Labor | PR | 491 | 09/19/18 | 09/21/18 | CO71 | Cortes Mendiola, Victor H | 16 | 0 | 656 | 0 | 656 | 21183 | 0 | 0
140 | Gas Labor | PR | 515 | 09/19/18 | 09/21/18 | HU06 | Hubbard, Robert W | 7 | 0 | 329 | 0 | 329 | 21206 | 0 | 0
140 | Gas Labor | PR | 667 | 09/26/18 | 09/28/18 | AS10 | Ascencio, Jose L | 8 | 0 | 208 | 0 | 208 | 21246 | 0 | 0
140 | Gas Labor | PR | 668 | 09/26/18 | 09/28/18 | BA45 | Balderas Ortiz, Ricardo I | 8 | 0 | 224 | 0 | 224 | 21247 | 0 | 0
140 | Gas Labor | PR | 700 | 09/26/18 | 09/28/18 | HU06 | Hubbard, Robert W | 1 | 0 | 47 | 0 | 47 | 21278 | 0 | 0
140 | Gas Labor | PR | 14 | 10/31/18 | 11/02/18 | CO71 | Cortes Mendiola, Victor H | 10 | 0 | 410 | 0 | 410 | 21624 | 0 | 0
140 | Gas Labor | PR | 15 | 10/31/18 | 11/02/18 | CO73 | Cortes Sepulveda, Jose R | 10 | 0 | 240 | 0 | 240 | 21625 | 0 | 0
140 | Gas Labor | PR | 213 | 01/09/19 | 01/11/19 | BA45 | Balderas Ortiz, Ricardo I | 3 | 0 | 87 | 0 | 87 | 22415 | 0 | 0
140 | Gas Labor | PR | 221 | 01/09/19 | 01/11/19 | CO71 | Cortes Mendiola, Victor H | 3 | 0 | 129 | 0 | 129 | 22423 | 0 | 0
140 | Gas Labor | PR | 467 | 01/16/19 | 01/18/19 | BA45 | Balderas Ortiz, Ricardo I | 24 | 0 | 696 | 0 | 696 | 22488 | 0 | 0
140 | Gas Labor | PR | 476 | 01/16/19 | 01/18/19 | CO71 | Cortes Mendiola, Victor H | 19 | 0 | 817 | 0 | 817 | 22497 | 0 | 0
140 | Gas Labor | PR | 477 | 01/16/19 | 01/18/19 | CO73 | Cortes Sepulveda, Jose R | 18 | 0 | 468 | 0 | 468 | 22498 | 0 | 0
140 | Gas Labor | PR | 725 | 01/23/19 | 01/25/19 | CO71 | Cortes Mendiola, Victor H | 1 | 0 | 43 | 0 | 43 | 22570 | 0 | 0
140 | Gas Labor | PR | 13 | 02/27/19 | 03/01/19 | CO71 | Cortes Mendiola, Victor H | 2 | 0 | 86 | 0 | 86 | 22920 | 0 | 0
140 | Gas Labor | PR | 255 | 03/06/19 | 03/08/19 | CO71 | Cortes Mendiola, Victor H | 4 | 0 | 172 | 0 | 172 | 22993 | 0 | 0
140 | Gas Labor | PR | 714 | 03/20/19 | 03/22/19 | CH20 | Chevez, Herson G | 0 | 2 | 0 | 60 | 60 | 23135 | 0 | 0
140 | Gas Labor | PR | 716 | 03/20/19 | 03/22/19 | CO71 | Cortes Mendiola, Victor H | 0 | 2 | 0 | 129 | 129 | 23137 | 0 | 0
141 | Water Main/Insulation Lab | PR | 24 | 04/04/18 | 04/06/18 | CO71 | Cortes Mendiola, Victor H | 2 | 0 | 80 | 0 | 80 | 19367 | 0 | 0
141 | Water Main/Insulation Lab | PR | 25 | 04/04/18 | 04/06/18 | CO73 | Cortes Sepulveda, Jose R | 8 | 0 | 184 | 0 | 184 | 19368 | 0 | 0
141 | Water Main/Insulation Lab | PR | 458 | 04/18/18 | 04/20/18 | CO73 | Cortes Sepulveda, Jose R | 24 | 0 | 552 | 0 | 552 | 19516 | 0 | 0
141 | Water Main/Insulation Lab | PR | 624 | 04/25/18 | 04/27/18 | CO71 | Cortes Mendiola, Victor H | 12 | 0 | 480 | 0 | 480 | 19589 | 0 | 0
141 | Water Main/Insulation Lab | PR | 625 | 04/25/18 | 04/27/18 | CO73 | Cortes Sepulveda, Jose R | 16 | 0 | 368 | 0 | 368 | 19590 | 0 | 0
141 | Water Main/Insulation Lab | PR | 639 | 04/25/18 | 04/27/18 | GU78 | Gutierrez Salas, Jose | 16 | 0 | 288 | 0 | 288 | 19604 | 0 | 0
141 | Water Main/Insulation Lab | PR | 644 | 04/25/18 | 04/27/18 | HU06 | Hubbard, Robert W | 2 | 0 | 90 | 0 | 90 | 19609 | 0 | 0
141 | Water Main/Insulation Lab | PR | 650 | 04/25/18 | 04/27/18 | LI49 | Lima Romero, Melvin A | 24 | 0 | 744 | 0 | 744 | 19615 | 0 | 0
141 | Water Main/Insulation Lab | PR | 38 | 05/02/18 | 05/04/18 | CO71 | Cortes Mendiola, Victor H | 3 | 0 | 120 | 0 | 120 | 19661 | 0 | 0
141 | Water Main/Insulation Lab | PR | 39 | 05/02/18 | 05/04/18 | CO73 | Cortes Sepulveda, Jose R | 32 | 0 | 736 | 0 | 736 | 19662 | 0 | 0
141 | Water Main/Insulation Lab | PR | 48 | 05/02/18 | 05/04/18 | GA70 | Garcia, Jordan X | 40 | 0 | 1240 | 0 | 1240 | 19671 | 0 | 0
141 | Water Main/Insulation Lab | PR | 64 | 05/02/18 | 05/04/18 | LI49 | Lima Romero, Melvin A | 40 | 0 | 1240 | 0 | 1240 | 19687 | 0 | 0
141 | Water Main/Insulation Lab | PR | 234 | 05/09/18 | 05/11/18 | CO71 | Cortes Mendiola, Victor H | 4 | 0 | 160 | 0 | 160 | 19741 | 0 | 0
141 | Water Main/Insulation Lab | PR | 235 | 05/09/18 | 05/11/18 | CO73 | Cortes Sepulveda, Jose R | 40 | 0 | 920 | 0 | 920 | 19742 | 0 | 0
141 | Water Main/Insulation Lab | PR | 242 | 05/09/18 | 05/11/18 | GA70 | Garcia, Jordan X | 2 | 0 | 62 | 0 | 62 | 19749 | 0 | 0
141 | Water Main/Insulation Lab | PR | 257 | 05/09/18 | 05/11/18 | LI49 | Lima Romero, Melvin A | 24 | 0 | 744 | 0 | 744 | 19764 | 0 | 0
141 | Water Main/Insulation Lab | PR | 279 | 05/09/18 | 05/11/18 | SI48 | Silva Morales, Jair J | 8 | 0 | 184 | 0 | 184 | 19786 | 0 | 0
141 | Water Main/Insulation Lab | PR | 432 | 05/16/18 | 05/18/18 | CO71 | Cortes Mendiola, Victor H | 8 | 0 | 320 | 0 | 320 | 19805 | 0 | 0
141 | Water Main/Insulation Lab | PR | 433 | 05/16/18 | 05/18/18 | CO73 | Cortes Sepulveda, Jose R | 39 | 0 | 897 | 0 | 897 | 19806 | 0 | 0
141 | Water Main/Insulation Lab | PR | 447 | 05/16/18 | 05/18/18 | GU78 | Gutierrez Salas, Jose | 8 | 0 | 144 | 0 | 144 | 19820 | 0 | 0
141 | Water Main/Insulation Lab | PR | 458 | 05/16/18 | 05/18/18 | LI49 | Lima Romero, Melvin A | 40 | 0 | 1240 | 0 | 1240 | 19831 | 0 | 0
141 | Water Main/Insulation Lab | PR | 482 | 05/16/18 | 05/18/18 | SI48 | Silva Morales, Jair J | 8 | 0 | 184 | 0 | 184 | 19855 | 0 | 0
141 | Water Main/Insulation Lab | PR | 747 | 05/23/18 | 05/25/18 | CO71 | Cortes Mendiola, Victor H | 0 | 2 | 0 | 120 | 120 | 19876 | 0 | 0
141 | Water Main/Insulation Lab | PR | 747 | 05/23/18 | 05/25/18 | CO71 | Cortes Mendiola, Victor H | 2 | 0 | 80 | 0 | 80 | 19876 | 0 | 0
141 | Water Main/Insulation Lab | PR | 748 | 05/23/18 | 05/25/18 | CO73 | Cortes Sepulveda, Jose R | 0 | 6 | 0 | 207 | 207 | 19877 | 0 | 0
141 | Water Main/Insulation Lab | PR | 748 | 05/23/18 | 05/25/18 | CO73 | Cortes Sepulveda, Jose R | 40 | 0 | 920 | 0 | 920 | 19877 | 0 | 0
141 | Water Main/Insulation Lab | PR | 750 | 05/23/18 | 05/25/18 | CR79 | Cruz Guzman, Joel A | 12 | 0 | 264 | 0 | 264 | 19879 | 0 | 0
141 | Water Main/Insulation Lab | PR | 762 | 05/23/18 | 05/25/18 | GU78 | Gutierrez Salas, Jose | 8 | 0 | 144 | 0 | 144 | 19891 | 0 | 0
141 | Water Main/Insulation Lab | PR | 773 | 05/23/18 | 05/25/18 | LI49 | Lima Romero, Melvin A | 0 | 6 | 0 | 279 | 279 | 19902 | 0 | 0
141 | Water Main/Insulation Lab | PR | 773 | 05/23/18 | 05/25/18 | LI49 | Lima Romero, Melvin A | 40 | 0 | 1240 | 0 | 1240 | 19902 | 0 | 0
141 | Water Main/Insulation Lab | PR | 14 | 05/30/18 | 06/01/18 | CO71 | Cortes Mendiola, Victor H | 10 | 0 | 400 | 0 | 400 | 19947 | 0 | 0
141 | Water Main/Insulation Lab | PR | 15 | 05/30/18 | 06/01/18 | CO73 | Cortes Sepulveda, Jose R | 36 | 0 | 828 | 0 | 828 | 19948 | 0 | 0
141 | Water Main/Insulation Lab | PR | 40 | 05/30/18 | 06/01/18 | LI49 | Lima Romero, Melvin A | 38 | 0 | 1178 | 0 | 1178 | 19974 | 0 | 0
141 | Water Main/Insulation Lab | PR | 41 | 05/30/18 | 06/01/18 | LO58 | Lopez Reyes, Boris O | 7 | 0 | 126 | 0 | 126 | 19975 | 0 | 0
141 | Water Main/Insulation Lab | PR | 271 | 06/06/18 | 06/08/18 | BA45 | Balderas Ortiz, Ricardo I | 22 | 0 | 594 | 0 | 594 | 20011 | 0 | 0
141 | Water Main/Insulation Lab | PR | 279 | 06/06/18 | 06/08/18 | CO71 | Cortes Mendiola, Victor H | 0 | 3 | 0 | 180 | 180 | 20019 | 0 | 0
141 | Water Main/Insulation Lab | PR | 279 | 06/06/18 | 06/08/18 | CO71 | Cortes Mendiola, Victor H | 10 | 0 | 400 | 0 | 400 | 20019 | 0 | 0
141 | Water Main/Insulation Lab | PR | 280 | 06/06/18 | 06/08/18 | CO73 | Cortes Sepulveda, Jose R | 40 | 0 | 920 | 0 | 920 | 20020 | 0 | 0
141 | Water Main/Insulation Lab | PR | 305 | 06/06/18 | 06/08/18 | LI49 | Lima Romero, Melvin A | 0 | 8 | 0 | 372 | 372 | 20045 | 0 | 0
141 | Water Main/Insulation Lab | PR | 305 | 06/06/18 | 06/08/18 | LI49 | Lima Romero, Melvin A | 40 | 0 | 1240 | 0 | 1240 | 20045 | 0 | 0
141 | Water Main/Insulation Lab | PR | 306 | 06/06/18 | 06/08/18 | LO58 | Lopez Reyes, Boris O | 18 | 0 | 324 | 0 | 324 | 20046 | 0 | 0
141 | Water Main/Insulation Lab | PR | 469 | 06/13/18 | 06/15/18 | CO71 | Cortes Mendiola, Victor H | 0 | 5 | 0 | 307.5 | 307.5 | 20104 | 0 | 0
141 | Water Main/Insulation Lab | PR | 469 | 06/13/18 | 06/15/18 | CO71 | Cortes Mendiola, Victor H | 5 | 0 | 205 | 0 | 205 | 20104 | 0 | 0
141 | Water Main/Insulation Lab | PR | 470 | 06/13/18 | 06/15/18 | CO73 | Cortes Sepulveda, Jose R | 0 | 3 | 0 | 108 | 108 | 20105 | 0 | 0
141 | Water Main/Insulation Lab | PR | 470 | 06/13/18 | 06/15/18 | CO73 | Cortes Sepulveda, Jose R | 40 | 0 | 960 | 0 | 960 | 20105 | 0 | 0
141 | Water Main/Insulation Lab | PR | 495 | 06/13/18 | 06/15/18 | LI49 | Lima Romero, Melvin A | 0 | 8 | 0 | 384 | 384 | 20130 | 0 | 0
141 | Water Main/Insulation Lab | PR | 495 | 06/13/18 | 06/15/18 | LI49 | Lima Romero, Melvin A | 40 | 0 | 1280 | 0 | 1280 | 20130 | 0 | 0
141 | Water Main/Insulation Lab | PR | 496 | 06/13/18 | 06/15/18 | LO58 | Lopez Reyes, Boris O | 1 | 0 | 18 | 0 | 18 | 20131 | 0 | 0
141 | Water Main/Insulation Lab | PR | 695 | 06/20/18 | 06/22/18 | CO71 | Cortes Mendiola, Victor H | 0 | 3 | 0 | 184.5 | 184.5 | 20174 | 0 | 0
141 | Water Main/Insulation Lab | PR | 695 | 06/20/18 | 06/22/18 | CO71 | Cortes Mendiola, Victor H | 4 | 0 | 164 | 0 | 164 | 20174 | 0 | 0
141 | Water Main/Insulation Lab | PR | 696 | 06/20/18 | 06/22/18 | CO73 | Cortes Sepulveda, Jose R | 36 | 0 | 864 | 0 | 864 | 20175 | 0 | 0
141 | Water Main/Insulation Lab | PR | 721 | 06/20/18 | 06/22/18 | LI49 | Lima Romero, Melvin A | 38 | 0 | 1216 | 0 | 1216 | 20200 | 0 | 0
141 | Water Main/Insulation Lab | PR | 950 | 06/27/18 | 06/29/18 | CO73 | Cortes Sepulveda, Jose R | 0 | 4 | 0 | 144 | 144 | 19949 | 0 | 0
141 | Water Main/Insulation Lab | PR | 950 | 06/27/18 | 06/29/18 | CO73 | Cortes Sepulveda, Jose R | 24 | 0 | 576 | 0 | 576 | 19949 | 0 | 0
141 | Water Main/Insulation Lab | PR | 963 | 06/27/18 | 06/29/18 | CO71 | Cortes Mendiola, Victor H | 0 | 2 | 0 | 123 | 123 | 20244 | 0 | 0
141 | Water Main/Insulation Lab | PR | 963 | 06/27/18 | 06/29/18 | CO71 | Cortes Mendiola, Victor H | 1 | 0 | 41 | 0 | 41 | 20244 | 0 | 0
141 | Water Main/Insulation Lab | PR | 989 | 06/27/18 | 06/29/18 | LI49 | Lima Romero, Melvin A | 0 | 8 | 0 | 384 | 384 | 20269 | 0 | 0
141 | Water Main/Insulation Lab | PR | 989 | 06/27/18 | 06/29/18 | LI49 | Lima Romero, Melvin A | 40 | 0 | 1280 | 0 | 1280 | 20269 | 0 | 0
141 | Water Main/Insulation Lab | PR | 44 | 07/04/18 | 07/06/18 | LI49 | Lima Romero, Melvin A | 32 | 0 | 1024 | 0 | 1024 | 20340 | 0 | 0
141 | Water Main/Insulation Lab | PR | 335 | 07/11/18 | 07/13/18 | LI49 | Lima Romero, Melvin A | 40 | 0 | 1280 | 0 | 1280 | 20415 | 0 | 0
141 | Water Main/Insulation Lab | PR | 439 | 07/18/18 | 07/20/18 | BA45 | Balderas Ortiz, Ricardo I | 16 | 0 | 448 | 0 | 448 | 20450 | 0 | 0
141 | Water Main/Insulation Lab | PR | 448 | 07/18/18 | 07/20/18 | CO73 | Cortes Sepulveda, Jose R | 0 | 2 | 0 | 72 | 72 | 20459 | 0 | 0
141 | Water Main/Insulation Lab | PR | 448 | 07/18/18 | 07/20/18 | CO73 | Cortes Sepulveda, Jose R | 16 | 0 | 384 | 0 | 384 | 20459 | 0 | 0
141 | Water Main/Insulation Lab | PR | 472 | 07/18/18 | 07/20/18 | JU02 | Juarez Alvarez, Oscar R | 7 | 0 | 203 | 0 | 203 | 20482 | 0 | 0
141 | Water Main/Insulation Lab | PR | 473 | 07/18/18 | 07/20/18 | JU04 | Juarez Maldonado, Oscar E | 7 | 0 | 133 | 0 | 133 | 20483 | 0 | 0
141 | Water Main/Insulation Lab | PR | 476 | 07/18/18 | 07/20/18 | LI49 | Lima Romero, Melvin A | 0 | 2 | 0 | 96 | 96 | 20486 | 0 | 0
141 | Water Main/Insulation Lab | PR | 476 | 07/18/18 | 07/20/18 | LI49 | Lima Romero, Melvin A | 24 | 0 | 768 | 0 | 768 | 20486 | 0 | 0
141 | Water Main/Insulation Lab | PR | 800 | 07/25/18 | 07/27/18 | JU04 | Juarez Maldonado, Oscar E | 20 | 0 | 380 | 0 | 380 | 20557 | 0 | 0
141 | Water Main/Insulation Lab | PR | 803 | 07/25/18 | 07/27/18 | LI49 | Lima Romero, Melvin A | 24 | 0 | 768 | 0 | 768 | 20560 | 0 | 0
141 | Water Main/Insulation Lab | PR | 13 | 08/01/18 | 08/03/18 | CO73 | Cortes Sepulveda, Jose R | 8 | 0 | 192 | 0 | 192 | 20605 | 0 | 0
141 | Water Main/Insulation Lab | PR | 38 | 08/01/18 | 08/03/18 | JU04 | Juarez Maldonado, Oscar E | 32 | 0 | 608 | 0 | 608 | 20629 | 0 | 0
141 | Water Main/Insulation Lab | PR | 41 | 08/01/18 | 08/03/18 | LI49 | Lima Romero, Melvin A | 16 | 0 | 512 | 0 | 512 | 20632 | 0 | 0
141 | Water Main/Insulation Lab | PR | 214 | 08/08/18 | 08/10/18 | BA45 | Balderas Ortiz, Ricardo I | 8 | 0 | 224 | 0 | 224 | 20667 | 0 | 0
141 | Water Main/Insulation Lab | PR | 222 | 08/08/18 | 08/10/18 | CO71 | Cortes Mendiola, Victor H | 4 | 0 | 164 | 0 | 164 | 20675 | 0 | 0
141 | Water Main/Insulation Lab | PR | 223 | 08/08/18 | 08/10/18 | CO73 | Cortes Sepulveda, Jose R | 12 | 0 | 288 | 0 | 288 | 20676 | 0 | 0
141 | Water Main/Insulation Lab | PR | 249 | 08/08/18 | 08/10/18 | JU04 | Juarez Maldonado, Oscar E | 24 | 0 | 456 | 0 | 456 | 20701 | 0 | 0
141 | Water Main/Insulation Lab | PR | 252 | 08/08/18 | 08/10/18 | LI49 | Lima Romero, Melvin A | 24 | 0 | 768 | 0 | 768 | 20704 | 0 | 0
141 | Water Main/Insulation Lab | PR | 255 | 08/08/18 | 08/10/18 | LU09 | Lucas Tzintzun, Rafael | 16 | 0 | 272 | 0 | 272 | 20707 | 0 | 0
141 | Water Main/Insulation Lab | PR | 482 | 08/15/18 | 08/17/18 | BA45 | Balderas Ortiz, Ricardo I | 16 | 0 | 448 | 0 | 448 | 20740 | 0 | 0
141 | Water Main/Insulation Lab | PR | 491 | 08/15/18 | 08/17/18 | CO73 | Cortes Sepulveda, Jose R | 28 | 0 | 672 | 0 | 672 | 20749 | 0 | 0
141 | Water Main/Insulation Lab | PR | 519 | 08/15/18 | 08/17/18 | LI49 | Lima Romero, Melvin A | 40 | 0 | 1280 | 0 | 1280 | 20776 | 0 | 0
141 | Water Main/Insulation Lab | PR | 522 | 08/15/18 | 08/17/18 | LU09 | Lucas Tzintzun, Rafael | 24 | 0 | 408 | 0 | 408 | 20779 | 0 | 0
141 | Water Main/Insulation Lab | PR | 783 | 08/22/18 | 08/24/18 | LU09 | Lucas Tzintzun, Rafael | 16 | 0 | 272 | 0 | 272 | 20850 | 0 | 0
141 | Water Main/Insulation Lab | PR | 803 | 08/22/18 | 08/24/18 | SI48 | Silva Morales, Jair J | 8 | 0 | 192 | 0 | 192 | 20870 | 0 | 0
141 | Water Main/Insulation Lab | PR | 1007 | 08/29/18 | 08/31/18 | CO73 | Cortes Sepulveda, Jose R | 4 | 0 | 96 | 0 | 96 | 20903 | 0 | 0
141 | Water Main/Insulation Lab | PR | 1057 | 08/29/18 | 08/31/18 | SI48 | Silva Morales, Jair J | 16 | 0 | 384 | 0 | 384 | 20952 | 0 | 0
141 | Water Main/Insulation Lab | PR | 48 | 09/05/18 | 09/07/18 | CO73 | Cortes Sepulveda, Jose R | 21 | 0 | 504 | 0 | 504 | 20973 | 0 | 0
141 | Water Main/Insulation Lab | PR | 97 | 09/05/18 | 09/07/18 | SI48 | Silva Morales, Jair J | 8 | 0 | 192 | 0 | 192 | 21022 | 0 | 0
141 | Water Main/Insulation Lab | PR | 279 | 09/12/18 | 09/14/18 | CO73 | Cortes Sepulveda, Jose R | 16 | 0 | 384 | 0 | 384 | 21114 | 0 | 0
141 | Water Main/Insulation Lab | PR | 329 | 09/12/18 | 09/14/18 | SI48 | Silva Morales, Jair J | 8 | 0 | 192 | 0 | 192 | 21163 | 0 | 0
141 | Water Main/Insulation Lab | PR | 492 | 09/19/18 | 09/21/18 | CO73 | Cortes Sepulveda, Jose R | 24 | 0 | 576 | 0 | 576 | 21184 | 0 | 0
141 | Water Main/Insulation Lab | PR | 510 | 09/19/18 | 09/21/18 | GU78 | Gutierrez Salas, Jose | 40 | 0 | 720 | 0 | 720 | 21201 | 0 | 0
141 | Water Main/Insulation Lab | PR | 667 | 09/26/18 | 09/28/18 | AS10 | Ascencio, Jose L | 8 | 0 | 208 | 0 | 208 | 21246 | 0 | 0
141 | Water Main/Insulation Lab | PR | 668 | 09/26/18 | 09/28/18 | BA45 | Balderas Ortiz, Ricardo I | 8 | 0 | 224 | 0 | 224 | 21247 | 0 | 0
141 | Water Main/Insulation Lab | PR | 695 | 09/26/18 | 09/28/18 | GU78 | Gutierrez Salas, Jose | 16 | 0 | 288 | 0 | 288 | 21273 | 0 | 0
142 | Mech Room Labor | PR | 548 | 03/21/18 | 03/23/18 | HU06 | Hubbard, Robert W | 2 | 0 | 90 | 0 | 90 | 19239 | 0 | 0
142 | Mech Room Labor | PR | 695 | 06/20/18 | 06/22/18 | CO71 | Cortes Mendiola, Victor H | 0 | 1 | 0 | 61.5 | 61.5 | 20174 | 0 | 0
142 | Mech Room Labor | PR | 302 | 09/12/18 | 09/14/18 | HU06 | Hubbard, Robert W | 3 | 0 | 141 | 0 | 141 | 21136 | 0 | 0
142 | Mech Room Labor | PR | 468 | 10/17/18 | 10/19/18 | HU06 | Hubbard, Robert W | 2 | 0 | 94 | 0 | 94 | 21501 | 0 | 0
142 | Mech Room Labor | PR | 75 | 12/05/18 | 12/07/18 | HU06 | Hubbard, Robert W | 3 | 0 | 147 | 0 | 147 | 22017 | 0 | 0
142 | Mech Room Labor | PR | 268 | 12/12/18 | 12/14/18 | BA45 | Balderas Ortiz, Ricardo I | 4 | 0 | 116 | 0 | 116 | 22128 | 0 | 0
142 | Mech Room Labor | PR | 276 | 12/12/18 | 12/14/18 | CO71 | Cortes Mendiola, Victor H | 8 | 0 | 344 | 0 | 344 | 22136 | 0 | 0
142 | Mech Room Labor | PR | 299 | 12/12/18 | 12/14/18 | HU06 | Hubbard, Robert W | 3 | 0 | 147 | 0 | 147 | 22158 | 0 | 0
142 | Mech Room Labor | PR | 509 | 12/19/18 | 12/21/18 | BA45 | Balderas Ortiz, Ricardo I | 24 | 0 | 696 | 0 | 696 | 22200 | 0 | 0
142 | Mech Room Labor | PR | 509 | 12/19/18 | 12/21/18 | BA45 | Balderas Ortiz, Ricardo I | 8 | 0 | 232 | 0 | 232 | 22200 | 0 | 0
142 | Mech Room Labor | PR | 517 | 12/19/18 | 12/21/18 | CO71 | Cortes Mendiola, Victor H | 6 | 0 | 258 | 0 | 258 | 22208 | 0 | 0
142 | Mech Room Labor | PR | 518 | 12/19/18 | 12/21/18 | CO73 | Cortes Sepulveda, Jose R | 31 | 0 | 806 | 0 | 806 | 22209 | 0 | 0
142 | Mech Room Labor | PR | 540 | 12/19/18 | 12/21/18 | HU06 | Hubbard, Robert W | 3 | 0 | 147 | 0 | 147 | 22230 | 0 | 0
142 | Mech Room Labor | PR | 700 | 12/26/18 | 12/28/18 | BA45 | Balderas Ortiz, Ricardo I | 16 | 0 | 464 | 0 | 464 | 22273 | 0 | 0
142 | Mech Room Labor | PR | 708 | 12/26/18 | 12/28/18 | CO71 | Cortes Mendiola, Victor H | 8 | 0 | 344 | 0 | 344 | 22281 | 0 | 0
142 | Mech Room Labor | PR | 708 | 12/26/18 | 12/28/18 | CO71 | Cortes Mendiola, Victor H | 24 | 0 | 1032 | 0 | 1032 | 22281 | 0 | 0
142 | Mech Room Labor | PR | 731 | 12/26/18 | 12/28/18 | HU06 | Hubbard, Robert W | 3 | 0 | 147 | 0 | 147 | 22304 | 0 | 0
142 | Mech Room Labor | PR | 5 | 01/02/19 | 01/04/19 | BA45 | Balderas Ortiz, Ricardo I | 2 | 0 | 58 | 0 | 58 | 22345 | 0 | 0
142 | Mech Room Labor | PR | 13 | 01/02/19 | 01/04/19 | CO71 | Cortes Mendiola, Victor H | 16 | 0 | 688 | 0 | 688 | 22353 | 0 | 0
142 | Mech Room Labor | PR | 14 | 01/02/19 | 01/04/19 | CO73 | Cortes Sepulveda, Jose R | 2 | 0 | 52 | 0 | 52 | 22354 | 0 | 0
142 | Mech Room Labor | PR | 213 | 01/09/19 | 01/11/19 | BA45 | Balderas Ortiz, Ricardo I | 25 | 0 | 725 | 0 | 725 | 22415 | 0 | 0
142 | Mech Room Labor | PR | 221 | 01/09/19 | 01/11/19 | CO71 | Cortes Mendiola, Victor H | 34 | 0 | 1462 | 0 | 1462 | 22423 | 0 | 0
142 | Mech Room Labor | PR | 244 | 01/09/19 | 01/11/19 | HU06 | Hubbard, Robert W | 1 | 0 | 49 | 0 | 49 | 22446 | 0 | 0
142 | Mech Room Labor | PR | 467 | 01/16/19 | 01/18/19 | BA45 | Balderas Ortiz, Ricardo I | 8 | 0 | 232 | 0 | 232 | 22488 | 0 | 0
142 | Mech Room Labor | PR | 725 | 01/23/19 | 01/25/19 | CO71 | Cortes Mendiola, Victor H | 3 | 0 | 129 | 0 | 129 | 22570 | 0 | 0
142 | Mech Room Labor | PR | 748 | 01/23/19 | 01/25/19 | HU06 | Hubbard, Robert W | 2 | 0 | 98 | 0 | 98 | 22593 | 0 | 0
142 | Mech Room Labor | PR | 13 | 01/30/19 | 02/01/19 | CO71 | Cortes Mendiola, Victor H | 3 | 0 | 129 | 0 | 129 | 22642 | 0 | 0
142 | Mech Room Labor | PR | 580 | 02/20/19 | 02/22/19 | BA45 | Balderas Ortiz, Ricardo I | 7 | 0 | 203 | 0 | 203 | 22842 | 0 | 0
142 | Mech Room Labor | PR | 586 | 02/20/19 | 02/22/19 | CH20 | Chevez, Herson G | 7 | 0 | 140 | 0 | 140 | 22848 | 0 | 0
142 | Mech Room Labor | PR | 588 | 02/20/19 | 02/22/19 | CO71 | Cortes Mendiola, Victor H | 7 | 0 | 301 | 0 | 301 | 22850 | 0 | 0
142 | Mech Room Labor | PR | 13 | 02/27/19 | 03/01/19 | CO71 | Cortes Mendiola, Victor H | 1 | 0 | 43 | 0 | 43 | 22920 | 0 | 0
142 | Mech Room Labor | PR | 38 | 02/27/19 | 03/01/19 | HU06 | Hubbard, Robert W | 4 | 0 | 196 | 0 | 196 | 22945 | 0 | 0
142 | Mech Room Labor | PR | 525 | 03/13/19 | 03/15/19 | HU06 | Hubbard, Robert W | 3 | 0 | 147 | 0 | 147 | 23087 | 0 | 0
142 | Mech Room Labor | PR | 525 | 03/13/19 | 03/15/19 | HU06 | Hubbard, Robert W | 0 | 1 | 0 | 73.5 | 73.5 | 23087 | 0 | 0
142 | Mech Room Labor | PR | 739 | 03/20/19 | 03/22/19 | HU06 | Hubbard, Robert W | 4 | 0 | 196 | 0 | 196 | 23160 | 0 | 0
142 | Mech Room Labor | PR | 780 | 03/20/19 | 03/22/19 | HU06 | Hubbard, Robert W | 4 | 0 | 196 | 0 | 196 | 23197 | 0 | 0
142 | Mech Room Labor | PR | 781 | 03/20/19 | 03/22/19 | HU06 | Hubbard, Robert W | 4 | 0 | -196 | 0 | -196 | 23160 | 0 | 0
142 | Mech Room Labor | PR | 951 | 03/27/19 | 03/29/19 | HU06 | Hubbard, Robert W | 0 | 1 | 0 | 73.5 | 73.5 | 23235 | 0 | 0
142 | Mech Room Labor | PR | 951 | 03/27/19 | 03/29/19 | HU06 | Hubbard, Robert W | 4 | 0 | 196 | 0 | 196 | 23235 | 0 | 0
142 | Mech Room Labor | PR | 530 | 04/17/19 | 04/19/19 | CO71 | Cortes Mendiola, Victor H | 2 | 0 | 92 | 0 | 92 | 23431 | 0 | 0
142 | Mech Room Labor | PR | 427 | 05/15/19 | 05/17/19 | HU06 | Hubbard, Robert W | 2 | 0 | 100 | 0 | 100 | 23758 | 0 | 0
143 | Condensation Drains Labor | PR | 358 | 09/13/17 | 09/15/17 | WA35 | Waites, Thaddeus Z | 2 | 0 | 80 | 0 | 80 | 17445 | 0 | 0
143 | Condensation Drains Labor | PR | 225 | 11/08/17 | 11/10/17 | WA35 | Waites, Thaddeus Z | 2 | 0 | -80 | 0 | -80 | 97960 | 0 | 0
143 | Condensation Drains Labor | PR | 449 | 02/14/18 | 02/16/18 | HU06 | Hubbard, Robert W | 4 | 0 | 180 | 0 | 180 | 18903 | 0 | 0
143 | Condensation Drains Labor | PR | 29 | 05/02/18 | 05/04/18 | BA45 | Balderas Ortiz, Ricardo I | 4 | 0 | 108 | 0 | 108 | 19652 | 0 | 0
143 | Condensation Drains Labor | PR | 17 | 07/04/18 | 07/06/18 | CO73 | Cortes Sepulveda, Jose R | 8 | 0 | 192 | 0 | 192 | 20314 | 0 | 0
143 | Condensation Drains Labor | PR | 331 | 07/11/18 | 07/13/18 | JU02 | Juarez Alvarez, Oscar R | 8 | 0 | 232 | 0 | 232 | 20411 | 0 | 0
143 | Condensation Drains Labor | PR | 438 | 07/18/18 | 07/20/18 | AS10 | Ascencio, Jose L | 0 | 4 | 0 | 156 | 156 | 20449 | 0 | 0
143 | Condensation Drains Labor | PR | 438 | 07/18/18 | 07/20/18 | AS10 | Ascencio, Jose L | 40 | 0 | 1040 | 0 | 1040 | 20449 | 0 | 0
143 | Condensation Drains Labor | PR | 476 | 07/18/18 | 07/20/18 | LI49 | Lima Romero, Melvin A | 0 | 2 | 0 | 96 | 96 | 20486 | 0 | 0
143 | Condensation Drains Labor | PR | 476 | 07/18/18 | 07/20/18 | LI49 | Lima Romero, Melvin A | 16 | 0 | 512 | 0 | 512 | 20486 | 0 | 0
143 | Condensation Drains Labor | PR | 764 | 07/25/18 | 07/27/18 | AS10 | Ascencio, Jose L | 40 | 0 | 1040 | 0 | 1040 | 20522 | 0 | 0
143 | Condensation Drains Labor | PR | 3 | 08/01/18 | 08/03/18 | AS10 | Ascencio, Jose L | 40 | 0 | 1040 | 0 | 1040 | 20594 | 0 | 0
143 | Condensation Drains Labor | PR | 213 | 08/08/18 | 08/10/18 | AS10 | Ascencio, Jose L | 40 | 0 | 1040 | 0 | 1040 | 20666 | 0 | 0
143 | Condensation Drains Labor | PR | 481 | 08/15/18 | 08/17/18 | AS10 | Ascencio, Jose L | 40 | 0 | 1040 | 0 | 1040 | 20739 | 0 | 0
143 | Condensation Drains Labor | PR | 542 | 08/15/18 | 08/17/18 | SI48 | Silva Morales, Jair J | 40 | 0 | 960 | 0 | 960 | 20799 | 0 | 0
143 | Condensation Drains Labor | PR | 803 | 08/22/18 | 08/24/18 | SI48 | Silva Morales, Jair J | 16 | 0 | 384 | 0 | 384 | 20870 | 0 | 0
143 | Condensation Drains Labor | PR | 1057 | 08/29/18 | 08/31/18 | SI48 | Silva Morales, Jair J | 8 | 0 | 192 | 0 | 192 | 20952 | 0 | 0
143 | Condensation Drains Labor | PR | 97 | 09/05/18 | 09/07/18 | SI48 | Silva Morales, Jair J | 16 | 0 | 384 | 0 | 384 | 21022 | 0 | 0
143 | Condensation Drains Labor | PR | 329 | 09/12/18 | 09/14/18 | SI48 | Silva Morales, Jair J | 32 | 0 | 768 | 0 | 768 | 21163 | 0 | 0
143 | Condensation Drains Labor | PR | 542 | 09/19/18 | 09/21/18 | SI48 | Silva Morales, Jair J | 40 | 0 | 960 | 0 | 960 | 21233 | 0 | 0
143 | Condensation Drains Labor | PR | 324 | 12/12/18 | 12/14/18 | SA54 | Sanders, Allen O | 2 | 0 | 94 | 0 | 94 | 22183 | 0 | 0
143 | Condensation Drains Labor | PR | 709 | 12/26/18 | 12/28/18 | CO73 | Cortes Sepulveda, Jose R | 11 | 0 | 286 | 0 | 286 | 22282 | 0 | 0
143 | Condensation Drains Labor | PR | 5 | 01/02/19 | 01/04/19 | BA45 | Balderas Ortiz, Ricardo I | 14 | 0 | 406 | 0 | 406 | 22345 | 0 | 0
143 | Condensation Drains Labor | PR | 13 | 01/02/19 | 01/04/19 | CO71 | Cortes Mendiola, Victor H | 8 | 0 | 344 | 0 | 344 | 22353 | 0 | 0
143 | Condensation Drains Labor | PR | 14 | 01/02/19 | 01/04/19 | CO73 | Cortes Sepulveda, Jose R | 14 | 0 | 364 | 0 | 364 | 22354 | 0 | 0
143 | Condensation Drains Labor | PR | 222 | 01/09/19 | 01/11/19 | CO73 | Cortes Sepulveda, Jose R | 10 | 0 | 260 | 0 | 260 | 22424 | 0 | 0
143 | Condensation Drains Labor | PR | 467 | 01/16/19 | 01/18/19 | BA45 | Balderas Ortiz, Ricardo I | 8 | 0 | 232 | 0 | 232 | 22488 | 0 | 0
143 | Condensation Drains Labor | PR | 476 | 01/16/19 | 01/18/19 | CO71 | Cortes Mendiola, Victor H | 8 | 0 | 344 | 0 | 344 | 22497 | 0 | 0
143 | Condensation Drains Labor | PR | 477 | 01/16/19 | 01/18/19 | CO73 | Cortes Sepulveda, Jose R | 5 | 0 | 130 | 0 | 130 | 22498 | 0 | 0
143 | Condensation Drains Labor | PR | 13 | 02/27/19 | 03/01/19 | CO71 | Cortes Mendiola, Victor H | 1 | 0 | 43 | 0 | 43 | 22920 | 0 | 0
143 | Condensation Drains Labor | PR | 502 | 03/13/19 | 03/15/19 | CO71 | Cortes Mendiola, Victor H | 2 | 0 | 86 | 0 | 86 | 23064 | 0 | 0
143 | Condensation Drains Labor | PR | 714 | 03/20/19 | 03/22/19 | CH20 | Chevez, Herson G | 0 | 4 | 0 | 120 | 120 | 23135 | 0 | 0
143 | Condensation Drains Labor | PR | 716 | 03/20/19 | 03/22/19 | CO71 | Cortes Mendiola, Victor H | 0 | 4 | 0 | 258 | 258 | 23137 | 0 | 0
210 | Underground Material | GL | 350 | 11/17/17 | 11/17/17 | Mat | Req 3288 |  |  |  |  | 66.77 |  | 0 | 0
210 | Underground Material | AP | 411 | 11/09/17 | 11/20/17 | 2043RS | Rosen Supply Company, Inc. $Aegis MI |  |  |  |  | 1616.01 | 4244810-00 | 0 | 0
210 | Underground Material | AP | 412 | 11/09/17 | 11/20/17 | 2043RS | Rosen Supply Company, Inc. $Aegis MI |  |  |  |  | 85.01 | 4244876-00 | 0 | 0
210 | Underground Material | AP | 413 | 11/09/17 | 11/20/17 | 2043RS | Rosen Supply Company, Inc. $Aegis MI |  |  |  |  | 548.86 | 4244889-00 | 0 | 0
210 | Underground Material | AP | 301 | 11/15/17 | 12/08/17 | 2043RS | Rosen Supply Company, Inc. $Aegis MI |  |  |  |  | 60.64 | 4244876-01 | 0 | 0
210 | Underground Material | GL | 721 | 12/21/17 | 12/21/17 | 2043RS | Inv 4245267-00 |  |  |  |  | 233.16 |  | 0 | 0
210 | Underground Material | AP | 763 | 12/05/17 | 12/22/17 | 2043RS | Rosen Supply Company, Inc. $Aegis MI |  |  |  |  | 2780.79 | 4243698-00 | 0 | 0
210 | Underground Material | AP | 764 | 12/08/17 | 12/22/17 | 2043RS | Rosen Supply Company, Inc. $Aegis MI |  |  |  |  | 1563.41 | 4243777-00 | 0 | 0
210 | Underground Material | AP | 125 | 12/20/17 | 01/05/18 | 2043RS | Rosen Supply Company, Inc. $Aegis MI |  |  |  |  | 3051.29 | 4243697-00 | 0 | 0
210 | Underground Material | AP | 353 | 01/02/18 | 01/16/18 | 2043RS | Rosen Supply Company, Inc. $Aegis MI |  |  |  |  | 25.91 | 4246437-00 | 0 | 0
210 | Underground Material | AP | 354 | 01/04/18 | 01/16/18 | 2043RS | Rosen Supply Company, Inc. $Aegis MI |  |  |  |  | 29.59 | 4246598-00 | 0 | 0
210 | Underground Material | AP | 355 | 01/09/18 | 01/16/18 | 2043RS | Rosen Supply Company, Inc. $Aegis MI |  |  |  |  | 25.91 | 4246437-01 | 0 | 0
210 | Underground Material | AP | 576 | 01/11/18 | 01/24/18 | 2850PL | Platt $Rexel USA, Inc. |  |  |  |  | 485.88 | Y026895 | 0 | 0
210 | Underground Material | AP | 107 | 01/16/18 | 02/06/18 | 1175FE | Ferguson Enterprises, Inc. #3007 |  |  |  |  | 57.47 | 5883554 | 0 | 0
210 | Underground Material | AP | 119 | 01/12/18 | 02/06/18 | 2042RS | Rosen Supply Company, Inc. $Metro Flats |  |  |  |  | 417.3 | 4246850-00 | 0 | 0
210 | Underground Material | AP | 305 | 01/12/18 | 02/06/18 | 2042RS | Rosen Supply Company, Inc. $Metro Flats |  |  |  |  | -417.3 | 4246850-00A | 0 | 0
210 | Underground Material | AP | 306 | 01/12/18 | 02/06/18 | 2043RS | Rosen Supply Company, Inc. $Aegis MI |  |  |  |  | 417.3 | 4246850-00 | 0 | 0
210 | Underground Material | AP | 289 | 01/23/18 | 02/09/18 | 2043RS | Rosen Supply Company, Inc. $Aegis MI |  |  |  |  | 120.08 | 4247274-00 | 0 | 0
210 | Underground Material | AP | 537 | 02/13/18 | 02/16/18 | 2043RS | Rosen Supply Company, Inc. $Aegis MI |  |  |  |  | -110.4 | 4248162-00 | 0 | 0
210 | Underground Material | AP | 365 | 01/26/18 | 02/25/18 | 2043RS | Rosen Supply Company, Inc. $Aegis MI |  |  |  |  | 779.33 | 4247384-00 | 0 | 0
210 | Underground Material | GL | 692 | 07/25/18 | 07/25/18 | Mat | Req 4505 |  |  |  |  | 6.78 |  | 0 | 0
211 | Garage Material | GL | 669 | 12/21/17 | 12/21/17 | Mat | Req 4113 |  |  |  |  | 16.07 |  | 0 | 0
211 | Garage Material | AP | 538 | 02/14/18 | 02/16/18 | 2043RS | Rosen Supply Company, Inc. $Aegis MI |  |  |  |  | 3614.35 | 4248109-00 | 0 | 0
211 | Garage Material | GL | 600 | 02/22/18 | 02/22/18 | Mat | Req 3464 |  |  |  |  | 270.15 |  | 0 | 0
211 | Garage Material | GL | 224 | 03/09/18 | 03/09/18 | Mat | Req 3512 |  |  |  |  | 253.51 |  | 0 | 0
211 | Garage Material | GL | 465 | 03/20/18 | 03/20/18 | Mat | Req 3547 |  |  |  |  | 434.29 |  | 0 | 0
211 | Garage Material | AP | 679 | 03/12/18 | 03/26/18 | 2043RS | Rosen Supply Company, Inc. $Aegis MI |  |  |  |  | 9063.08 | 4249208-00 | 0 | 0
211 | Garage Material | GL | 860 | 03/31/18 | 03/31/18 | Mat | Req 4296 |  |  |  |  | 189.5 |  | 0 | 0
211 | Garage Material | AP | 362 | 03/28/18 | 04/13/18 | 2043RS | Rosen Supply Company, Inc. $Aegis MI |  |  |  |  | 1476.72 | 4249875-00 | 0 | 0
211 | Garage Material | GL | 419 | 04/18/18 | 04/18/18 | Mat | Req 4326 |  |  |  |  | 128.36 |  | 0 | 0
211 | Garage Material | GL | 738 | 04/26/18 | 04/26/18 | Mat | Req 3612 |  |  |  |  | 185 |  | 0 | 0
211 | Garage Material | AP | 808 | 04/12/18 | 04/30/18 | 2043RS | Rosen Supply Company, Inc. $Aegis MI |  |  |  |  | 3068.66 | 4250544-00 | 0 | 0
211 | Garage Material | AP | 147 | 04/18/18 | 05/01/18 | 2043RS | Rosen Supply Company, Inc. $Aegis MI |  |  |  |  | 59.33 | 4250838-00 | 0 | 0
211 | Garage Material | GL | 311 | 05/11/18 | 05/11/18 | Mat | Req 3661 |  |  |  |  | 214.5 |  | 0 | 0
211 | Garage Material | AP | 335 | 04/24/18 | 05/11/18 | 2043RS | Rosen Supply Company, Inc. $Aegis MI |  |  |  |  | -142.75 | 4251134-00 | 0 | 0
211 | Garage Material | AP | 565 | 05/01/18 | 05/21/18 | 2043RS | Rosen Supply Company, Inc. $Aegis MI |  |  |  |  | 2337.54 | 4251280-00 | 0 | 0
211 | Garage Material | GL | 615 | 05/22/18 | 05/22/18 | Mat | Req 4372 |  |  |  |  | 208.19 |  | 0 | 0
211 | Garage Material | AP | 259 | 05/17/18 | 06/01/18 | 2043RS | Rosen Supply Company, Inc. $Aegis MI |  |  |  |  | 1087.93 | 4252075-00 | 0 | 0
211 | Garage Material | GL | 182 | 06/05/18 | 06/05/18 | Mat | Req 4426 |  |  |  |  | 60 |  | 0 | 0
211 | Garage Material | AP | 455 | 06/06/18 | 06/13/18 | 2043RS | Rosen Supply Company, Inc. $Aegis MI |  |  |  |  | 807.09 | 4252901-00 | 0 | 0
211 | Garage Material | GL | 532 | 06/15/18 | 06/15/18 | Mat | Req 3710 |  |  |  |  | 2.58 |  | 0 | 0
211 | Garage Material | GL | 901 | 06/27/18 | 06/27/18 | Mat | Req 3735 |  |  |  |  | 27.54 |  | 0 | 0
211 | Garage Material | GL | 384 | 07/16/18 | 07/16/18 | Mat | Req 5280 |  |  |  |  | -617.6 |  | 0 | 0
211 | Garage Material | GL | 388 | 07/16/18 | 07/16/18 | Mat | Req 4478 |  |  |  |  | 10.38 |  | 0 | 0
211 | Garage Material | GL | 565 | 07/23/18 | 07/23/18 | Mat | Req 5310 |  |  |  |  | 114.9 |  | 0 | 0
211 | Garage Material | GL | 322 | 08/10/18 | 08/10/18 | Mat | Req 4590 |  |  |  |  | 67 |  | 0 | 0
211 | Garage Material | AP | 618 | 07/25/18 | 08/21/18 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 52.9 | 4254176-00 | 0 | 0
211 | Garage Material | GL | 654 | 08/22/18 | 08/22/18 | Mat | Req 4621 |  |  |  |  | 26 |  | 0 | 0
211 | Garage Material | GL | 186 | 09/10/18 | 09/10/18 | Mat | Req 4688 |  |  |  |  | 41.52 |  | 0 | 0
211 | Garage Material | GL | 606 | 09/25/18 | 09/25/18 | Mat | Req 5391 |  |  |  |  | 94.67 |  | 0 | 0
211 | Garage Material | GL | 876 | 10/31/18 | 10/31/18 | Mat | Req 5518 |  |  |  |  | -372.37 |  | 0 | 0
211 | Garage Material | GL | 556 | 11/16/18 | 11/16/18 | Mat | Req 4807 |  |  |  |  | -245.64 |  | 0 | 0
211 | Garage Material | GL | 336 | 01/11/19 | 01/11/19 | Mat | Req 5671 |  |  |  |  | 5.69 |  | 0 | 0
211 | Garage Material | GL | 150 | 03/04/19 | 03/04/19 | Mat | Req 5044 |  |  |  |  | -206.7 |  | 0 | 0
211 | Garage Material | GL | 443 | 04/12/19 | 04/12/19 | Mat | Req 5133 |  |  |  |  | 4.08 |  | 0 | 0
211 | Garage Material | GL | 879 | 04/30/19 | 04/30/19 | Mat | Req 5887 |  |  |  |  | 39 |  | 0 | 0
212 | Canout Material | AP | 379 | 01/15/18 | 01/17/18 | 2043KS | Keller Supply Co. $Aegis MI |  |  |  |  | 4290.8 | S011515391.001 | 0 | 0
212 | Canout Material | GL | 95 | 02/02/18 | 02/02/18 | Mat | Req 4158 |  |  |  |  | 1117.24 |  | 0 | 0
212 | Canout Material | GL | 387 | 02/14/18 | 02/14/18 | Mat | Req 4189 |  |  |  |  | 350.37 |  | 0 | 0
212 | Canout Material | GL | 399 | 02/14/18 | 02/14/18 | Mat | Req 4218 |  |  |  |  | -65.6 |  | 0 | 0
212 | Canout Material | GL | 502 | 02/16/18 | 02/16/18 | Mat | Req 4217 |  |  |  |  | 344 |  | 0 | 0
212 | Canout Material | GL | 782 | 02/21/18 | 02/21/18 | Mat | Req 3488 |  |  |  |  | 5.5 |  | 0 | 0
212 | Canout Material | GL | 269 | 03/13/18 | 03/13/18 | Mat | Req 3532 |  |  |  |  | 685.94 |  | 0 | 0
212 | Canout Material | GL | 693 | 03/26/18 | 03/26/18 | Mat | Req 4229 |  |  |  |  | 11.07 |  | 0 | 0
220 | Roughin Material | AP | 616 | 08/22/17 | 08/28/17 | 5621HD | Core & Main LP $HD Supply Waterworks |  |  |  |  | 76.26 | H686429 | 0 | 0
220 | Roughin Material | AP | 302 | 11/21/17 | 12/08/17 | 2043RS | Rosen Supply Company, Inc. $Aegis MI |  |  |  |  | 233.16 | 4245267-00 | 0 | 0
220 | Roughin Material | GL | 721 | 12/21/17 | 12/21/17 | 2043RS | Inv 4245267-00 |  |  |  |  | -233.16 |  | 0 | 0
220 | Roughin Material | GL | 739 | 12/22/17 | 12/22/17 | Mat | Req 3382 |  |  |  |  | 84.57 |  | 0 | 0
220 | Roughin Material | GL | 504 | 01/22/18 | 01/22/18 | Mat | Req 3434 |  |  |  |  | 46.53 |  | 0 | 0
220 | Roughin Material | GL | 98 | 02/02/18 | 02/02/18 | Mat | Req 4145 |  |  |  |  | 214.94 |  | 0 | 0
220 | Roughin Material | GL | 778 | 02/21/18 | 02/21/18 | Mat | Req 3466 |  |  |  |  | 71.65 |  | 0 | 0
220 | Roughin Material | GL | 464 | 03/20/18 | 03/20/18 | Mat | Req 3549 |  |  |  |  | 67.18 |  | 0 | 0
220 | Roughin Material | GL | 827 | 03/31/18 | 03/31/18 | Mat | Req 4248 |  |  |  |  | 117.18 |  | 0 | 0
220 | Roughin Material | AP | 877 | 03/23/18 | 03/31/18 | 2043CS | Consolidated Supply Co. $Aegis MI |  |  |  |  | 5217.2 | S8647965.001 | 0 | 0
220 | Roughin Material | AP | 242 | 03/26/18 | 04/01/18 | 2043RS | Rosen Supply Company, Inc. $Aegis MI |  |  |  |  | 5170.8 | 4248942-00 | 0 | 0
220 | Roughin Material | GL | 162 | 04/10/18 | 04/10/18 | Mat | Req 4303 |  |  |  |  | 117.46 |  | 0 | 0
220 | Roughin Material | GL | 407 | 04/18/18 | 04/18/18 | Mat | Req 4325 |  |  |  |  | 656.25 |  | 0 | 0
220 | Roughin Material | GL | 703 | 04/27/18 | 04/27/18 | Mat | Req 3608 |  |  |  |  | 1043.25 |  | 0 | 0
220 | Roughin Material | AP | 24 | 04/17/18 | 05/03/18 | 2043CS | Consolidated Supply Co. $Aegis MI |  |  |  |  | 655.14 | S8698786.002 | 0 | 0
220 | Roughin Material | GL | 118 | 05/04/18 | 05/04/18 | Mat | Req 3637 |  |  |  |  | 1244.17 |  | 0 | 0
220 | Roughin Material | GL | 312 | 05/11/18 | 05/11/18 | Mat | Req 4334 |  |  |  |  | 465.91 |  | 0 | 0
220 | Roughin Material | AP | 397 | 05/01/18 | 05/16/18 | 2043CS | Consolidated Supply Co. $Aegis MI |  |  |  |  | 302.28 | S8742035.001 | 0 | 0
220 | Roughin Material | GL | 417 | 05/17/18 | 05/17/18 | Mat | Req 4371 |  |  |  |  | 83.3 |  | 0 | 0
220 | Roughin Material | AP | 566 | 05/03/18 | 05/21/18 | 2043RS | Rosen Supply Company, Inc. $Aegis MI |  |  |  |  | 63.07 | 4251535-00 | 0 | 0
220 | Roughin Material | AP | 724 | 05/11/18 | 05/23/18 | 2043RS | Rosen Supply Company, Inc. $Aegis MI |  |  |  |  | 1061.83 | 4251834-00 | 0 | 0
220 | Roughin Material | GL | 81 | 06/01/18 | 06/01/18 | Mat | Req 4387 |  |  |  |  | 680.66 |  | 0 | 0
220 | Roughin Material | AP | 260 | 05/18/18 | 06/01/18 | 2043RS | Rosen Supply Company, Inc. $Aegis MI |  |  |  |  | 613.08 | 4252153-00 | 0 | 0
220 | Roughin Material | GL | 183 | 06/05/18 | 06/05/18 | Mat | Req 4425 |  |  |  |  | 1551.15 |  | 0 | 0
220 | Roughin Material | AP | 216 | 05/18/18 | 06/05/18 | 2043CS | Consolidated Supply Co. $Aegis MI |  |  |  |  | 5217.2 | S8673955.001 | 0 | 0
220 | Roughin Material | AP | 406 | 05/22/18 | 06/11/18 | 2043RS | Rosen Supply Company, Inc. $Aegis MI |  |  |  |  | 211 | 4252302-00 | 0 | 0
220 | Roughin Material | AP | 407 | 05/25/18 | 06/11/18 | 2043RS | Rosen Supply Company, Inc. $Aegis MI |  |  |  |  | 228.84 | 4252426-00 | 0 | 0
220 | Roughin Material | AP | 454 | 06/05/18 | 06/13/18 | 2043RS | Rosen Supply Company, Inc. $Aegis MI |  |  |  |  | 61.2 | 4252426-01 | 0 | 0
220 | Roughin Material | AP | 455 | 06/06/18 | 06/13/18 | 2043RS | Rosen Supply Company, Inc. $Aegis MI |  |  |  |  | 345.85 | 4252901-00 | 0 | 0
220 | Roughin Material | GL | 561 | 06/15/18 | 06/15/18 | Mat | Req 3709 |  |  |  |  | 1900.32 |  | 0 | 0
220 | Roughin Material | AP | 888 | 06/15/18 | 06/26/18 | 2043RS | Rosen Supply Company, Inc. $Aegis MI |  |  |  |  | 201.5 | 4253360-00 | 0 | 0
220 | Roughin Material | GL | 900 | 06/27/18 | 06/27/18 | Mat | Req 3733 |  |  |  |  | 560.37 |  | 0 | 0
220 | Roughin Material | GL | 694 | 07/25/18 | 07/25/18 | Mat | Req 4503 |  |  |  |  | 271.23 |  | 0 | 0
220 | Roughin Material | GL | 321 | 08/10/18 | 08/10/18 | Mat | Req 4591 |  |  |  |  | 49.2 |  | 0 | 0
220 | Roughin Material | GL | 368 | 08/10/18 | 08/10/18 | Mat | Req 4538 |  |  |  |  | 70.5 |  | 0 | 0
220 | Roughin Material | AP | 425 | 07/12/18 | 08/13/18 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 443.13 | 4254429-00 | 0 | 0
220 | Roughin Material | AP | 443 | 07/17/18 | 08/14/18 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 171.36 | 4254673-00 | 0 | 0
220 | Roughin Material | GL | 652 | 08/22/18 | 08/22/18 | Mat | Req 4619 |  |  |  |  | 202.88 |  | 0 | 0
220 | Roughin Material | AP | 928 | 08/03/18 | 08/28/18 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 518.83 | 4255451-00 | 0 | 0
220 | Roughin Material | GL | 187 | 09/10/18 | 09/10/18 | Mat | Req 4687 |  |  |  |  | 197.53 |  | 0 | 0
220 | Roughin Material | AP | 260 | 08/17/18 | 09/12/18 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 36.94 | 4256114-00 | 0 | 0
220 | Roughin Material | AP | 430 | 08/27/18 | 09/18/18 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 90.66 | 4256472-00 | 0 | 0
220 | Roughin Material | AP | 432 | 09/04/18 | 09/18/18 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 289.91 | 4256792-00 | 0 | 0
220 | Roughin Material | GL | 778 | 09/30/18 | 09/30/18 | Mat | Req 5408 |  |  |  |  | 58.67 |  | 0 | 0
220 | Roughin Material | GL | 574 | 10/22/18 | 10/22/18 | Mat | Req 4720 |  |  |  |  | 26.62 |  | 0 | 0
220 | Roughin Material | AP | 593 | 09/25/18 | 10/22/18 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 307.63 | 4257737-00 | 0 | 0
220 | Roughin Material | GL | 564 | 11/16/18 | 11/16/18 | Mat | Req 4797 |  |  |  |  | 11.4 |  | 0 | 0
220 | Roughin Material | GL | 998 | 11/30/18 | 11/30/18 | Mat | Req 5554 |  |  |  |  | 204.15 |  | 0 | 0
220 | Roughin Material | GL | 999 | 11/30/18 | 11/30/18 | Mat | Req 5565 |  |  |  |  | 14.88 |  | 0 | 0
220 | Roughin Material | GL | 866 | 12/31/18 | 12/31/18 | Mat | Req 5669 |  |  |  |  | 53.35 |  | 0 | 0
220 | Roughin Material | GL | 347 | 01/11/19 | 01/11/19 | Mat | Req 5664 |  |  |  |  | -766.54 |  | 0 | 0
220 | Roughin Material | GL | 691 | 01/23/19 | 01/23/19 | Mat | Req 4964 |  |  |  |  | 74.58 |  | 0 | 0
220 | Roughin Material | GL | 290 | 02/08/19 | 02/08/19 | Mat | Req 5684 |  |  |  |  | 35.47 |  | 0 | 0
230 | Finish Material | GL | 239 | 09/11/17 | 09/11/17 | Mat | Req 3939 |  |  |  |  | 9.99 |  | 0 | 0
230 | Finish Material | AP | 264 | 08/21/17 | 09/12/17 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 77.73 | 4241868-00 | 0 | 0
230 | Finish Material | AP | 535 | 11/21/17 | 11/22/17 | 1609QC | Quality Concrete Products, Inc. $32 |  |  |  |  | 1918 | 15840 | 0 | 0
230 | Finish Material | GL | 81 | 12/01/17 | 12/01/17 | Mat | Req 4027 |  |  |  |  | 44.04 |  | 0 | 0
230 | Finish Material | AP | 193 | 11/29/17 | 12/06/17 | 1609QC | Quality Concrete Products, Inc. $32 |  |  |  |  | -175 | 15918 | 0 | 0
230 | Finish Material | GL | 557 | 12/07/17 | 12/07/17 | Mat | Req 4091 |  |  |  |  | 162.7 |  | 0 | 0
230 | Finish Material | GL | 679 | 12/21/17 | 12/21/17 | Mat | Req 4112 |  |  |  |  | 59.33 |  | 0 | 0
230 | Finish Material | GL | 748 | 12/22/17 | 12/22/17 | Mat | Req 3378 |  |  |  |  | 403.17 |  | 0 | 0
230 | Finish Material | GL | 309 | 01/15/18 | 01/15/18 | Mat | Req 3406 |  |  |  |  | 146.82 |  | 0 | 0
230 | Finish Material | GL | 97 | 02/02/18 | 02/02/18 | Mat | Req 4159 |  |  |  |  | 1303.75 |  | 0 | 0
230 | Finish Material | GL | 777 | 02/21/18 | 02/21/18 | Mat | Req 3465 |  |  |  |  | 365.05 |  | 0 | 0
230 | Finish Material | AP | 594 | 03/09/18 | 03/23/18 | 2043RS | Rosen Supply Company, Inc. $Aegis MI |  |  |  |  | 2696 | 4248982-00 | 0 | 0
230 | Finish Material | GL | 163 | 04/10/18 | 04/10/18 | Mat | Req 4304 |  |  |  |  | 285.85 |  | 0 | 0
230 | Finish Material | AP | 218 | 04/04/18 | 04/10/18 | 2043KS | Keller Supply Co. $Aegis MI |  |  |  |  | 20319.96 | S011612445.001 | 0 | 0
230 | Finish Material | AP | 219 | 04/04/18 | 04/10/18 | 2043KS | Keller Supply Co. $Aegis MI |  |  |  |  | 2154.34 | S011612445.003 | 0 | 0
230 | Finish Material | AP | 535 | 04/17/18 | 04/20/18 | 2043KS | Keller Supply Co. $Aegis MI |  |  |  |  | 20081.98 | S011612889.001 | 0 | 0
230 | Finish Material | AP | 555 | 04/17/18 | 04/20/18 | 2043KS | Keller Supply Co. $Aegis MI |  |  |  |  | 6463.03 | S011612889.003 | 0 | 0
230 | Finish Material | GL | 737 | 04/26/18 | 04/26/18 | Mat | Req 3613 |  |  |  |  | 228 |  | 0 | 0
230 | Finish Material | GL | 211 | 05/09/18 | 05/09/18 | Mat | Req 4351 |  |  |  |  | -56.16 |  | 0 | 0
230 | Finish Material | GL | 299 | 05/11/18 | 05/11/18 | Mat | Req 4335 |  |  |  |  | 714.64 |  | 0 | 0
230 | Finish Material | AP | 375 | 05/02/18 | 05/15/18 | 2043KS | Keller Supply Co. $Aegis MI |  |  |  |  | 19376.47 | S011612914.001 | 0 | 0
230 | Finish Material | AP | 376 | 05/07/18 | 05/15/18 | 2043KS | Keller Supply Co. $Aegis MI |  |  |  |  | 2872.46 | S011612914.005 | 0 | 0
230 | Finish Material | GL | 184 | 06/05/18 | 06/05/18 | Mat | Req 4424 |  |  |  |  | 1691.12 |  | 0 | 0
230 | Finish Material | GL | 903 | 06/27/18 | 06/27/18 | Mat | Req 3734 |  |  |  |  | 1771.04 |  | 0 | 0
230 | Finish Material | AP | 112 | 06/27/18 | 07/06/18 | 1021AT | ACME Corp |  |  |  |  | 87.78 | S3031254.001 | 0 | 0
230 | Finish Material | GL | 564 | 07/23/18 | 07/23/18 | Mat | Req 5311 |  |  |  |  | 1128.68 |  | 0 | 0
230 | Finish Material | GL | 370 | 08/10/18 | 08/10/18 | Mat | Req 4536 |  |  |  |  | 63 |  | 0 | 0
230 | Finish Material | GL | 651 | 08/22/18 | 08/22/18 | Mat | Req 4618 |  |  |  |  | 1865.93 |  | 0 | 0
230 | Finish Material | AP | 215 | 08/20/18 | 09/10/18 | 1231KS | Keller Supply Company |  |  |  |  | 1441.78 | S012043550.001 | 0 | 0
230 | Finish Material | AP | 216 | 08/20/18 | 09/10/18 | 1231KS | Keller Supply Company |  |  |  |  | 1212.08 | S012194382.001 | 0 | 0
230 | Finish Material | GL | 607 | 09/25/18 | 09/25/18 | Mat | Req 5390 |  |  |  |  | 85.46 |  | 0 | 0
230 | Finish Material | AP | 657 | 08/31/18 | 09/25/18 | 1231KS | Keller Supply Company |  |  |  |  | 1608.42 | S012208186.001 | 0 | 0
230 | Finish Material | AP | 659 | 09/06/18 | 09/25/18 | 1231KS | Keller Supply Company |  |  |  |  | 190.82 | S012236817.001 | 0 | 0
230 | Finish Material | GL | 26 | 10/04/18 | 10/04/18 | Mat | Req 5439 |  |  |  |  | 83.96 |  | 0 | 0
230 | Finish Material | AP | 118 | 09/24/18 | 10/05/18 | 5560CH | California Hydronics Corp |  |  |  |  | 1886 | 2107753 | 0 | 0
230 | Finish Material | AP | 119 | 09/24/18 | 10/05/18 | 5560CH | California Hydronics Corp |  |  |  |  | 1145 | 2107755 | 0 | 0
230 | Finish Material | AP | 120 | 09/24/18 | 10/05/18 | 5560CH | California Hydronics Corp |  |  |  |  | 34162 | 2107824 | 0 | 0
230 | Finish Material | AP | 121 | 09/26/18 | 10/05/18 | 5560CH | California Hydronics Corp |  |  |  |  | 465 | 2108119 | 0 | 0
230 | Finish Material | AP | 338 | 09/18/18 | 10/15/18 | 1231KS | Keller Supply Company |  |  |  |  | -1212.08 | S012194382.002 | 0 | 0
230 | Finish Material | AP | 339 | 09/18/18 | 10/15/18 | 1231KS | Keller Supply Company |  |  |  |  | 1008.92 | S012194382.003 | 0 | 0
230 | Finish Material | GL | 576 | 10/22/18 | 10/22/18 | Mat | Req 4718 |  |  |  |  | 166.12 |  | 0 | 0
230 | Finish Material | AP | 675 | 10/01/18 | 10/24/18 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 1266.75 | 4257574-00 | 0 | 0
230 | Finish Material | AP | 383 | 10/25/18 | 11/13/18 | 1231KS | Keller Supply Company |  |  |  |  | 865.37 | S012338818.001 | 0 | 0
230 | Finish Material | GL | 565 | 11/16/18 | 11/16/18 | Mat | Req 4796 |  |  |  |  | 1743.47 |  | 0 | 0
230 | Finish Material | GL | 996 | 11/30/18 | 11/30/18 | Mat | Req 5556 |  |  |  |  | 955.65 |  | 0 | 0
230 | Finish Material | AP | 1056 | 10/30/18 | 11/30/18 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 61 | 4259306-00 | 0 | 0
230 | Finish Material | AP | 187 | 11/02/18 | 12/11/18 | 1231KS | Keller Supply Company |  |  |  |  | 44.38 | S012222510.001 | 0 | 0
230 | Finish Material | AP | 188 | 11/09/18 | 12/11/18 | 1231KS | Keller Supply Company |  |  |  |  | 9898.78 | S012222497.001 | 0 | 0
230 | Finish Material | AP | 189 | 11/09/18 | 12/11/18 | 1231KS | Keller Supply Company |  |  |  |  | 1301.81 | S012463561.001 | 0 | 0
230 | Finish Material | AP | 190 | 11/09/18 | 12/11/18 | 1231KS | Keller Supply Company |  |  |  |  | 11.02 | S012463561.002 | 0 | 0
230 | Finish Material | AP | 191 | 11/09/18 | 12/11/18 | 1231KS | Keller Supply Company |  |  |  |  | 193.16 | S012464988.001 | 0 | 0
230 | Finish Material | AP | 370 | 11/13/18 | 12/14/18 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 224.21 | 4259920-00 | 0 | 0
230 | Finish Material | AP | 380 | 11/12/18 | 12/14/18 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 42 | 4259886-00 | 0 | 0
230 | Finish Material | AP | 483 | 11/13/18 | 12/14/18 | 1234CO | Capital One Credit Card |  |  |  |  | 205.29 | 111318R | 0 | 0
230 | Finish Material | AP | 494 | 11/16/18 | 12/14/18 | 1234CO | Capital One Credit Card |  |  |  |  | 18.6 | 111618A | 0 | 0
230 | Finish Material | AP | 408 | 11/15/18 | 12/17/18 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 404.64 | 4259975-00 | 0 | 0
230 | Finish Material | AP | 409 | 11/15/18 | 12/17/18 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 105.55 | 4260066-00 | 0 | 0
230 | Finish Material | AP | 410 | 11/20/18 | 12/17/18 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 149.14 | 4260066-01 | 0 | 0
230 | Finish Material | AP | 439 | 11/21/18 | 12/18/18 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 296.2 | 4260223-00 | 0 | 0
230 | Finish Material | GL | 607 | 12/21/18 | 12/21/18 | Mat | Req 5633 |  |  |  |  | 1054.94 |  | 0 | 0
230 | Finish Material | AP | 817 | 12/11/18 | 12/31/18 | 1234CO | Capital One Credit Card |  |  |  |  | 125.83 | 121118J | 0 | 0
230 | Finish Material | AP | 838 | 12/10/18 | 12/31/18 | 1234CO | Capital One Credit Card |  |  |  |  | 24.55 | 121018A3 | 0 | 0
230 | Finish Material | GL | 868 | 12/31/18 | 12/31/18 | Mat | Req 5667 |  |  |  |  | 1234.18 |  | 0 | 0
230 | Finish Material | AP | 134 | 12/13/18 | 01/07/19 | 1175FE | Ferguson Enterprises, Inc. #3007 |  |  |  |  | 74.8 | 6800859 | 0 | 0
230 | Finish Material | AP | 135 | 12/13/18 | 01/07/19 | 1175FE | Ferguson Enterprises, Inc. #3007 |  |  |  |  | 149.6 | 6800869 | 0 | 0
230 | Finish Material | AP | 168 | 11/28/18 | 01/08/19 | 1231KS | Keller Supply Company |  |  |  |  | 1612.08 | S012222497.002 | 0 | 0
230 | Finish Material | AP | 169 | 11/28/18 | 01/08/19 | 1231KS | Keller Supply Company |  |  |  |  | 110.36 | S012222497.003 | 0 | 0
230 | Finish Material | AP | 186 | 11/29/18 | 01/09/19 | 1231KS | Keller Supply Company |  |  |  |  | 640.27 | S012471027.001 | 0 | 0
230 | Finish Material | AP | 187 | 12/06/18 | 01/09/19 | 1231KS | Keller Supply Company |  |  |  |  | 13523.11 | S012222432.001 | 0 | 0
230 | Finish Material | AP | 188 | 12/12/18 | 01/09/19 | 1231KS | Keller Supply Company |  |  |  |  | 245.31 | S012486434.001 | 0 | 0
230 | Finish Material | AP | 189 | 12/14/18 | 01/09/19 | 1231KS | Keller Supply Company |  |  |  |  | -35.08 | S012464988.002 | 0 | 0
230 | Finish Material | GL | 309 | 01/11/19 | 01/11/19 | Mat | Req 4959 |  |  |  |  | 55.48 |  | 0 | 0
230 | Finish Material | GL | 407 | 01/15/19 | 01/15/19 | Mat | Req 4908 |  |  |  |  | 1855.46 |  | 0 | 0
230 | Finish Material | AP | 439 | 12/18/18 | 01/15/19 | 1231KS | Keller Supply Company |  |  |  |  | 8706.72 | S012470791.001 | 0 | 0
230 | Finish Material | AP | 440 | 12/18/18 | 01/15/19 | 1231KS | Keller Supply Company |  |  |  |  | 2647.78 | S012486434.002 | 0 | 0
230 | Finish Material | AP | 441 | 12/18/18 | 01/15/19 | 1231KS | Keller Supply Company |  |  |  |  | 2840.07 | S012490914.001 | 0 | 0
230 | Finish Material | AP | 442 | 12/18/18 | 01/15/19 | 1231KS | Keller Supply Company |  |  |  |  | 460.59 | S012490952.001 | 0 | 0
230 | Finish Material | AP | 443 | 12/18/18 | 01/15/19 | 1231KS | Keller Supply Company |  |  |  |  | 243.34 | S012531848.001 | 0 | 0
230 | Finish Material | AP | 444 | 12/21/18 | 01/15/19 | 1231KS | Keller Supply Company |  |  |  |  | 46.93 | S012579828.001 | 0 | 0
230 | Finish Material | GL | 643 | 01/22/19 | 01/22/19 | Mat | Req 4987 |  |  |  |  | -574.67 |  | 0 | 0
230 | Finish Material | GL | 690 | 01/23/19 | 01/23/19 | Mat | Req 4977 |  |  |  |  | 107.8 |  | 0 | 0
230 | Finish Material | GL | 693 | 01/23/19 | 01/23/19 | Mat | Req 4962 |  |  |  |  | 76.5 |  | 0 | 0
230 | Finish Material | AP | 852 | 01/04/19 | 01/29/19 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 198.64 | 4261865-00 | 0 | 0
230 | Finish Material | AP | 903 | 01/14/19 | 01/30/19 | 3612MS | Mechanical Sales, Inc. |  |  |  |  | 242.15 | 700000 | 0 | 0
230 | Finish Material | AP | 93 | 01/08/19 | 02/01/19 | 1231KS | Keller Supply Company |  |  |  |  | 9530.85 | S012222510.002 | 0 | 0
230 | Finish Material | AP | 94 | 01/08/19 | 02/01/19 | 1231KS | Keller Supply Company |  |  |  |  | 3454.31 | S012470984.001 | 0 | 0
230 | Finish Material | AP | 95 | 01/08/19 | 02/01/19 | 1231KS | Keller Supply Company |  |  |  |  | 550.04 | S012471008.001 | 0 | 0
230 | Finish Material | AP | 96 | 01/11/19 | 02/01/19 | 1231KS | Keller Supply Company |  |  |  |  | 300.1 | S012470984.002 | 0 | 0
230 | Finish Material | AP | 97 | 01/16/19 | 02/01/19 | 1231KS | Keller Supply Company |  |  |  |  | 101.34 | S012471008.002 | 0 | 0
230 | Finish Material | AP | 98 | 01/17/19 | 02/01/19 | 1231KS | Keller Supply Company |  |  |  |  | 2814.18 | S012505356.001 | 0 | 0
230 | Finish Material | AP | 99 | 01/17/19 | 02/01/19 | 1231KS | Keller Supply Company |  |  |  |  | -20.58 | S012579828.002 | 0 | 0
230 | Finish Material | AP | 132 | 01/23/19 | 02/06/19 | 1175FE | Ferguson Enterprises, Inc. #3007 |  |  |  |  | 39.11 | 6899379 | 0 | 0
230 | Finish Material | GL | 283 | 02/08/19 | 02/08/19 | Mat | Req 5682 |  |  |  |  | 323.68 |  | 0 | 0
230 | Finish Material | AP | 440 | 01/23/19 | 02/14/19 | 1234CO | Capital One Credit Card |  |  |  |  | 25.11 | 012319A | 0 | 0
230 | Finish Material | AP | 495 | 01/23/19 | 02/18/19 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 324 | 4262077-00 | 0 | 0
230 | Finish Material | AP | 541 | 01/29/19 | 02/19/19 | 1231KS | Keller Supply Company |  |  |  |  | 186.79 | S012557262.001 | 0 | 0
230 | Finish Material | AP | 543 | 02/07/19 | 02/19/19 | 1231KS | Keller Supply Company |  |  |  |  | 272.66 | S012640000.001 | 0 | 0
230 | Finish Material | AP | 111 | 01/26/19 | 03/01/19 | 1234CO | Capital One Credit Card |  |  |  |  | 13.16 | 012619A | 0 | 0
230 | Finish Material | AP | 112 | 01/27/19 | 03/01/19 | 1234CO | Capital One Credit Card |  |  |  |  | 33.1 | 012719A | 0 | 0
230 | Finish Material | AP | 114 | 02/12/19 | 03/01/19 | 1234CO | Capital One Credit Card |  |  |  |  | 30.55 | 021219A | 0 | 0
230 | Finish Material | AP | 115 | 02/13/19 | 03/01/19 | 1234CO | Capital One Credit Card |  |  |  |  | 79.07 | 021319A | 0 | 0
230 | Finish Material | GL | 151 | 03/04/19 | 03/04/19 | Mat | Req 5043 |  |  |  |  | -375.27 |  | 0 | 0
230 | Finish Material | GL | 378 | 03/08/19 | 03/08/19 | Mat | Req 5034 |  |  |  |  | 769.77 |  | 0 | 0
230 | Finish Material | AP | 421 | 02/21/19 | 03/12/19 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 143.93 | 4261865-01 | 0 | 0
230 | Finish Material | AP | 435 | 02/25/19 | 03/12/19 | 1231KS | Keller Supply Company |  |  |  |  | 370.33 | S012692645.001 | 0 | 0
230 | Finish Material | AP | 436 | 02/25/19 | 03/12/19 | 1231KS | Keller Supply Company |  |  |  |  | 8.94 | S012758848.001 | 0 | 0
230 | Finish Material | AP | 451 | 02/28/19 | 03/13/19 | 1231KS | Keller Supply Company |  |  |  |  | 11.11 | S012471027.002 | 0 | 0
230 | Finish Material | AP | 452 | 02/28/19 | 03/13/19 | 1231KS | Keller Supply Company |  |  |  |  | 13.18 | S012718782.001 | 0 | 0
230 | Finish Material | AP | 453 | 02/28/19 | 03/13/19 | 1231KS | Keller Supply Company |  |  |  |  | 48.48 | S012738707.001 | 0 | 0
230 | Finish Material | GL | 576 | 03/15/19 | 03/15/19 | Mat | Req 5070 |  |  |  |  | -81.69 |  | 0 | 0
230 | Finish Material | AP | 636 | 03/01/19 | 03/19/19 | 1231KS | Keller Supply Company |  |  |  |  | 149.24 | S012470791.002 | 0 | 0
230 | Finish Material | AP | 573 | 03/01/19 | 03/25/19 | 5560CH | California Hydronics Corp |  |  |  |  | 70.4 | SIN009831 | 0 | 0
230 | Finish Material | AP | 1029 | 03/26/19 | 03/31/19 | 1234CO | Capital One Credit Card |  |  |  |  | 17.56 | 032619A | 0 | 0
230 | Finish Material | AP | 55 | 03/13/19 | 04/03/19 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 81.69 | 4261865-02 | 0 | 0
230 | Finish Material | GL | 420 | 04/12/19 | 04/12/19 | Mat | Req 5886 |  |  |  |  | 30 |  | 0 | 0
230 | Finish Material | GL | 444 | 04/12/19 | 04/12/19 | Mat | Req 5131 |  |  |  |  | 367.15 |  | 0 | 0
230 | Finish Material | AP | 959 | 04/17/19 | 04/30/19 | 1234CO | Capital One Credit Card |  |  |  |  | 10.64 | 041719A | 0 | 0
230 | Finish Material | AP | 116 | 04/17/19 | 05/06/19 | 1231KS | Keller Supply Company |  |  |  |  | -1032.22 | S012909729.001 | 0 | 0
230 | Finish Material | AP | 566 | 05/13/19 | 05/22/19 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 270 | 4267404-00 | 0 | 0
240 | Gas Material | AP | 421 | 05/29/18 | 06/12/18 | 2043KS | Keller Supply Co. $Aegis MI |  |  |  |  | 1416.42 | S011922611.001 | 0 | 0
240 | Gas Material | AP | 589 | 05/30/18 | 06/18/18 | 2043CS | Consolidated Supply Co. $Aegis MI |  |  |  |  | 917.09 | S8768327.001 | 0 | 0
240 | Gas Material | AP | 591 | 06/07/18 | 06/18/18 | 2043CS | Consolidated Supply Co. $Aegis MI |  |  |  |  | 712 | S8768327.002 | 0 | 0
240 | Gas Material | AP | 592 | 06/11/18 | 06/18/18 | 2043CS | Consolidated Supply Co. $Aegis MI |  |  |  |  | 9.61 | S8768327.003 | 0 | 0
240 | Gas Material | AP | 263 | 06/22/18 | 07/11/18 | 2043CS | Consolidated Supply Co. $Aegis MI |  |  |  |  | 393.71 | S8768327.004 | 0 | 0
240 | Gas Material | GL | 389 | 07/16/18 | 07/16/18 | Mat | Req 4477 |  |  |  |  | 10.5 |  | 0 | 0
240 | Gas Material | GL | 693 | 07/25/18 | 07/25/18 | Mat | Req 4504 |  |  |  |  | 13.14 |  | 0 | 0
240 | Gas Material | GL | 314 | 08/10/18 | 08/10/18 | Mat | Req 4559 |  |  |  |  | -2151.5 |  | 0 | 0
240 | Gas Material | GL | 320 | 08/10/18 | 08/10/18 | Mat | Req 4594 |  |  |  |  | 27.72 |  | 0 | 0
240 | Gas Material | GL | 655 | 08/22/18 | 08/22/18 | Mat | Req 4622 |  |  |  |  | 12.24 |  | 0 | 0
240 | Gas Material | AP | 909 | 07/31/18 | 08/24/18 | 1231KS | Keller Supply Company |  |  |  |  | 271.51 | S012140064.001 | 0 | 0
240 | Gas Material | GL | 185 | 09/10/18 | 09/10/18 | Mat | Req 4689 |  |  |  |  | 21.59 |  | 0 | 0
240 | Gas Material | GL | 603 | 09/25/18 | 09/25/18 | Mat | Req 5393 |  |  |  |  | 109.79 |  | 0 | 0
240 | Gas Material | AP | 856 | 09/11/18 | 09/30/18 | 1231KS | Keller Supply Company |  |  |  |  | 76 | S012272641.001 | 0 | 0
240 | Gas Material | GL | 577 | 10/22/18 | 10/22/18 | Mat | Req 4717 |  |  |  |  | 57.2 |  | 0 | 0
240 | Gas Material | AP | 387 | 09/20/18 | 10/31/18 | 1231KS | Keller Supply Company |  |  |  |  | 20.99 | S012272641.002 | 0 | 0
240 | Gas Material | AP | 388 | 09/20/18 | 10/31/18 | 1231KS | Keller Supply Company |  |  |  |  | 177.52 | S012306025.001 | 0 | 0
240 | Gas Material | AP | 389 | 09/20/18 | 10/31/18 | 1231KS | Keller Supply Company |  |  |  |  | 29.69 | S012306029.001 | 0 | 0
240 | Gas Material | AP | 391 | 09/25/18 | 10/31/18 | 1231KS | Keller Supply Company |  |  |  |  | 93.91 | S012317263.001 | 0 | 0
240 | Gas Material | AP | 130 | 10/08/18 | 11/05/18 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 24.22 | 4258331-00 | 0 | 0
240 | Gas Material | GL | 316 | 11/09/18 | 11/09/18 | Mat | Req 4781 |  |  |  |  | 11.39 |  | 0 | 0
240 | Gas Material | AP | 411 | 10/12/18 | 11/13/18 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 173.25 | 4258590-00 | 0 | 0
240 | Gas Material | AP | 700 | 10/25/18 | 11/21/18 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 32.52 | 4259138-00 | 0 | 0
240 | Gas Material | GL | 997 | 11/30/18 | 11/30/18 | Mat | Req 5557 |  |  |  |  | 4.68 |  | 0 | 0
240 | Gas Material | GL | 865 | 12/31/18 | 12/31/18 | Mat | Req 5670 |  |  |  |  | 19.2 |  | 0 | 0
240 | Gas Material | GL | 695 | 01/23/19 | 01/23/19 | Mat | Req 4978 |  |  |  |  | 279.01 |  | 0 | 0
240 | Gas Material | AP | 469 | 01/11/19 | 02/16/19 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 319.96 | 4261814-00 | 0 | 0
240 | Gas Material | AP | 481 | 01/15/19 | 02/16/19 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 8.4 | 4262279-00 | 0 | 0
240 | Gas Material | AP | 494 | 01/21/19 | 02/18/19 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 8.06 | 4262535-00 | 0 | 0
240 | Gas Material | AP | 669 | 01/31/19 | 02/22/19 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 6.96 | 4262279-01 | 0 | 0
240 | Gas Material | GL | 158 | 03/04/19 | 03/04/19 | Mat | Req 5020 |  |  |  |  | 479.74 |  | 0 | 0
240 | Gas Material | GL | 380 | 03/08/19 | 03/08/19 | Mat | Req 5683 |  |  |  |  | 6.35 |  | 0 | 0
240 | Gas Material | AP | 454 | 02/28/19 | 03/13/19 | 1175FE | Ferguson Enterprises, Inc. #3007 |  |  |  |  | 80.79 | 6996836 | 0 | 0
240 | Gas Material | AP | 882 | 03/08/19 | 03/26/19 | 1175FE | Ferguson Enterprises, Inc. #3007 |  |  |  |  | 87.23 | 7019732 | 0 | 0
240 | Gas Material | AP | 177 | 03/19/19 | 04/05/19 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 19.36 | 4264891-00 | 0 | 0
241 | Water Main/Insulation Mat | AP | 311 | 03/07/18 | 03/14/18 | 2043CS | Consolidated Supply Co. $Aegis MI |  |  |  |  | 1025 | S8645967.001 | 0 | 0
241 | Water Main/Insulation Mat | AP | 312 | 03/12/18 | 03/14/18 | 2043CS | Consolidated Supply Co. $Aegis MI |  |  |  |  | 2248.38 | S8647289.001 | 0 | 0
241 | Water Main/Insulation Mat | AP | 313 | 03/12/18 | 03/14/18 | 2043CS | Consolidated Supply Co. $Aegis MI |  |  |  |  | 391.8 | S8647289.002 | 0 | 0
241 | Water Main/Insulation Mat | AP | 314 | 03/12/18 | 03/14/18 | 2043CS | Consolidated Supply Co. $Aegis MI |  |  |  |  | 4058.24 | S8647392.001 | 0 | 0
241 | Water Main/Insulation Mat | AP | 315 | 03/12/18 | 03/14/18 | 2043CS | Consolidated Supply Co. $Aegis MI |  |  |  |  | 274.8 | S8647392.002 | 0 | 0
241 | Water Main/Insulation Mat | GL | 117 | 05/04/18 | 05/04/18 | Mat | Req 3638 |  |  |  |  | 100.62 |  | 0 | 0
241 | Water Main/Insulation Mat | GL | 313 | 05/11/18 | 05/11/18 | Mat | Req 4336 |  |  |  |  | 174.33 |  | 0 | 0
241 | Water Main/Insulation Mat | AP | 396 | 04/26/18 | 05/16/18 | 2043CS | Consolidated Supply Co. $Aegis MI |  |  |  |  | 755.94 | S8722303.001 | 0 | 0
241 | Water Main/Insulation Mat | AP | 398 | 05/11/18 | 05/16/18 | 2043CS | Consolidated Supply Co. $Aegis MI |  |  |  |  | 5863.42 | S8741609.001 | 0 | 0
241 | Water Main/Insulation Mat | GL | 607 | 04/27/18 | 05/22/18 | Mat | Req 4383 |  |  |  |  | 155.44 |  | 0 | 0
241 | Water Main/Insulation Mat | GL | 86 | 06/01/18 | 06/01/18 | Mat | Req 4388 |  |  |  |  | 395.36 |  | 0 | 0
241 | Water Main/Insulation Mat | AP | 590 | 06/01/18 | 06/18/18 | 2043CS | Consolidated Supply Co. $Aegis MI |  |  |  |  | 3196.6 | S8772032.001 | 0 | 0
241 | Water Main/Insulation Mat | GL | 902 | 06/27/18 | 06/27/18 | Mat | Req 3737 |  |  |  |  | 153.49 |  | 0 | 0
241 | Water Main/Insulation Mat | GL | 566 | 07/23/18 | 07/23/18 | Mat | Req 5309 |  |  |  |  | 492.68 |  | 0 | 0
241 | Water Main/Insulation Mat | AP | 663 | 06/28/18 | 07/24/18 | 2043CS | Consolidated Supply Co. $Aegis MI |  |  |  |  | 302.4 | S8813647.001 | 0 | 0
241 | Water Main/Insulation Mat | AP | 664 | 07/20/18 | 07/24/18 | 2043CS | Consolidated Supply Co. $Aegis MI |  |  |  |  | 361.08 | S8845363.001 | 0 | 0
241 | Water Main/Insulation Mat | AP | 190 | 07/24/18 | 08/08/18 | 1130CS | Consolidated Supply Co. |  |  |  |  | 70.6 | S8845363.002 | 0 | 0
241 | Water Main/Insulation Mat | AP | 191 | 07/25/18 | 08/08/18 | 1130CS | Consolidated Supply Co. |  |  |  |  | 163.5 | S8850920.001 | 0 | 0
241 | Water Main/Insulation Mat | GL | 369 | 08/10/18 | 08/10/18 | Mat | Req 4537 |  |  |  |  | 33.46 |  | 0 | 0
241 | Water Main/Insulation Mat | AP | 461 | 07/20/18 | 08/15/18 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 3149.22 | 4254548-00 | 0 | 0
241 | Water Main/Insulation Mat | AP | 619 | 07/25/18 | 08/21/18 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 1239.9 | 4254548-01 | 0 | 0
241 | Water Main/Insulation Mat | GL | 653 | 08/22/18 | 08/22/18 | Mat | Req 4620 |  |  |  |  | 1611.28 |  | 0 | 0
241 | Water Main/Insulation Mat | AP | 200 | 08/16/18 | 09/10/18 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 302.4 | 4254548-02 | 0 | 0
241 | Water Main/Insulation Mat | AP | 374 | 08/24/18 | 09/14/18 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 1953.72 | 4256147-00 | 0 | 0
241 | Water Main/Insulation Mat | AP | 375 | 08/24/18 | 09/14/18 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 1629.6 | 4256147-01 | 0 | 0
241 | Water Main/Insulation Mat | AP | 431 | 08/29/18 | 09/18/18 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 363.6 | 4254548-03 | 0 | 0
241 | Water Main/Insulation Mat | GL | 604 | 09/25/18 | 09/25/18 | Mat | Req 5392 |  |  |  |  | 470.03 |  | 0 | 0
241 | Water Main/Insulation Mat | GL | 755 | 09/30/18 | 09/30/18 | Mat | Req 5434 |  |  |  |  | -169.68 |  | 0 | 0
241 | Water Main/Insulation Mat | AP | 164 | 09/10/18 | 10/10/18 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 481.8 | 4257035-00 | 0 | 0
241 | Water Main/Insulation Mat | GL | 179 | 10/10/18 | 10/10/18 | Mat | Req 5460 |  |  |  |  | -3257.78 |  | 0 | 0
241 | Water Main/Insulation Mat | AP | 340 | 09/20/18 | 10/15/18 | 1175FE | Ferguson Enterprises, Inc. #3007 |  |  |  |  | 64.04 | 6541876 | 0 | 0
241 | Water Main/Insulation Mat | AP | 426 | 09/21/18 | 10/17/18 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 420 | 4256715-01 | 0 | 0
241 | Water Main/Insulation Mat | AP | 427 | 09/21/18 | 10/17/18 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 1561.77 | 4257547-00 | 0 | 0
241 | Water Main/Insulation Mat | AP | 537 | 09/25/18 | 10/19/18 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 181.8 | 4256147-02 | 0 | 0
241 | Water Main/Insulation Mat | GL | 573 | 10/22/18 | 10/22/18 | Mat | Req 4721 |  |  |  |  | 23.84 |  | 0 | 0
241 | Water Main/Insulation Mat | GL | 580 | 10/22/18 | 10/22/18 | Mat | Req 5480 |  |  |  |  | -675.32 |  | 0 | 0
241 | Water Main/Insulation Mat | GL | 588 | 10/22/18 | 10/22/18 | Mat | Req 4753 |  |  |  |  | -506.52 |  | 0 | 0
241 | Water Main/Insulation Mat | AP | 407 | 09/17/18 | 10/31/18 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 1495.8 | 4256715-00 | 0 | 0
241 | Water Main/Insulation Mat | GL | 877 | 10/31/18 | 10/31/18 | Mat | Req 5517 |  |  |  |  | -1034.52 |  | 0 | 0
241 | Water Main/Insulation Mat | GL | 317 | 11/09/18 | 11/09/18 | Mat | Req 4780 |  |  |  |  | 10.09 |  | 0 | 0
241 | Water Main/Insulation Mat | GL | 554 | 11/16/18 | 11/16/18 | Mat | Req 4809 |  |  |  |  | -1013.08 |  | 0 | 0
241 | Water Main/Insulation Mat | GL | 867 | 12/31/18 | 12/31/18 | Mat | Req 5668 |  |  |  |  | 534.42 |  | 0 | 0
241 | Water Main/Insulation Mat | AP | 126 | 12/14/18 | 01/07/19 | 1130CS | Consolidated Supply Co. |  |  |  |  | 361.44 | S9058475.001 | 0 | 0
241 | Water Main/Insulation Mat | AP | 201 | 12/19/18 | 01/09/19 | 1175FE | Ferguson Enterprises, Inc. #3007 |  |  |  |  | 682.17 | 6817386 | 0 | 0
241 | Water Main/Insulation Mat | AP | 202 | 12/20/18 | 01/09/19 | 1175FE | Ferguson Enterprises, Inc. #3007 |  |  |  |  | 336.14 | 6817386-1 | 0 | 0
241 | Water Main/Insulation Mat | GL | 355 | 01/11/19 | 01/11/19 | Mat | Req 4915 |  |  |  |  | -386.8 |  | 0 | 0
241 | Water Main/Insulation Mat | GL | 694 | 01/23/19 | 01/23/19 | Mat | Req 4960 |  |  |  |  | 39.42 |  | 0 | 0
241 | Water Main/Insulation Mat | GL | 152 | 03/04/19 | 03/04/19 | Mat | Req 5042 |  |  |  |  | -337.68 |  | 0 | 0
241 | Water Main/Insulation Mat | GL | 379 | 03/08/19 | 03/08/19 | Mat | Req 5788 |  |  |  |  | 17.44 |  | 0 | 0
241 | Water Main/Insulation Mat | GL | 582 | 03/15/19 | 03/15/19 | Mat | Req 5823 |  |  |  |  | 53.56 |  | 0 | 0
242 | Mech Room Material | AP | 214 | 08/17/18 | 09/10/18 | 1231KS | Keller Supply Company |  |  |  |  | 38.38 | S012199884.001 | 0 | 0
242 | Mech Room Material | AP | 658 | 09/05/18 | 09/25/18 | 1231KS | Keller Supply Company |  |  |  |  | 19.2 | S012253066.001 | 0 | 0
242 | Mech Room Material | GL | 779 | 09/30/18 | 09/30/18 | Mat | Req 5410 |  |  |  |  | 33.4 |  | 0 | 0
242 | Mech Room Material | AP | 390 | 09/25/18 | 10/31/18 | 1231KS | Keller Supply Company |  |  |  |  | 26.25 | S012305287.001 | 0 | 0
242 | Mech Room Material | GL | 869 | 12/31/18 | 12/31/18 | Mat | Req 5666 |  |  |  |  | 170.31 |  | 0 | 0
242 | Mech Room Material | GL | 870 | 12/31/18 | 12/31/18 | Mat | Req 5665 |  |  |  |  | 3299.33 |  | 0 | 0
242 | Mech Room Material | AP | 136 | 12/14/18 | 01/07/19 | 1175FE | Ferguson Enterprises, Inc. #3007 |  |  |  |  | 6244.32 | 6804069 | 0 | 0
242 | Mech Room Material | GL | 310 | 01/11/19 | 01/11/19 | Mat | Req 4890 |  |  |  |  | 386.4 |  | 0 | 0
242 | Mech Room Material | GL | 426 | 01/15/19 | 01/15/19 | Mat | Req 4909 |  |  |  |  | 562.77 |  | 0 | 0
242 | Mech Room Material | AP | 448 | 01/05/19 | 01/15/19 | 1175FE | Ferguson Enterprises, Inc. #3007 |  |  |  |  | 1506.99 | 6848515 | 0 | 0
242 | Mech Room Material | AP | 449 | 01/07/19 | 01/15/19 | 1175FE | Ferguson Enterprises, Inc. #3007 |  |  |  |  | 197.83 | 6848515-1 | 0 | 0
242 | Mech Room Material | AP | 450 | 01/08/19 | 01/15/19 | 1175FE | Ferguson Enterprises, Inc. #3007 |  |  |  |  | 158.23 | 6856003 | 0 | 0
242 | Mech Room Material | GL | 692 | 01/23/19 | 01/23/19 | Mat | Req 4961 |  |  |  |  | 301.72 |  | 0 | 0
242 | Mech Room Material | AP | 851 | 12/28/18 | 01/29/19 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 608.69 | 4261632-00 | 0 | 0
242 | Mech Room Material | AP | 117 | 01/25/19 | 02/01/19 | 1175FE | Ferguson Enterprises, Inc. #3007 |  |  |  |  | 200.82 | 6908231 | 0 | 0
242 | Mech Room Material | AP | 120 | 01/24/19 | 02/01/19 | 1175FE | Ferguson Enterprises, Inc. #3007 |  |  |  |  | 126.4 | 6904051 | 0 | 0
242 | Mech Room Material | AP | 496 | 01/23/19 | 02/18/19 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 138.35 | 4262718-00 | 0 | 0
242 | Mech Room Material | AP | 534 | 01/15/19 | 02/19/19 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 197.47 | 4262239-00 | 0 | 0
242 | Mech Room Material | AP | 542 | 02/01/19 | 02/19/19 | 1231KS | Keller Supply Company |  |  |  |  | 325.25 | S012690913.001 | 0 | 0
242 | Mech Room Material | AP | 668 | 01/31/19 | 02/22/19 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 80.9 | 4262239-01 | 0 | 0
242 | Mech Room Material | AP | 212 | 02/26/19 | 03/05/19 | 8068MI | Kele, Inc $ MI Controls |  |  |  |  | 377.8 | 949383 | 0 | 0
242 | Mech Room Material | GL | 377 | 03/08/19 | 03/08/19 | Mat | Req 5787 |  |  |  |  | 4.78 |  | 0 | 0
242 | Mech Room Material | GL | 383 | 03/08/19 | 03/08/19 | Mat | Req 5796 |  |  |  |  | -1763.73 |  | 0 | 0
242 | Mech Room Material | GL | 384 | 03/08/19 | 03/08/19 | Mat | Req 5797 |  |  |  |  | 406.81 |  | 0 | 0
242 | Mech Room Material | GL | 581 | 03/15/19 | 03/15/19 | Mat | Req 5822 |  |  |  |  | 4.32 |  | 0 | 0
242 | Mech Room Material | GL | 810 | 03/25/19 | 03/25/19 | Mat | Req 5108 |  |  |  |  | -428.73 |  | 0 | 0
242 | Mech Room Material | GL | 847 | 03/25/19 | 03/25/19 | Mat | Req 5110 |  |  |  |  | -22.55 |  | 0 | 0
242 | Mech Room Material | GL | 848 | 03/25/19 | 03/25/19 | Mat | Req 5109 |  |  |  |  | -735.09 |  | 0 | 0
242 | Mech Room Material | GL | 445 | 04/12/19 | 04/12/19 | Mat | Req 5132 |  |  |  |  | 171.08 |  | 0 | 0
242 | Mech Room Material | AP | 472 | 03/27/19 | 04/15/19 | 1175FE | Ferguson Enterprises, Inc. #3007 |  |  |  |  | 168.68 | 7070700 | 0 | 0
243 | Condensation Drains Mat | AP | 455 | 06/06/18 | 06/13/18 | 2043RS | Rosen Supply Company, Inc. $Aegis MI |  |  |  |  | 235.25 | 4252901-00 | 0 | 0
243 | Condensation Drains Mat | AP | 856 | 06/07/18 | 06/25/18 | 2043RS | Rosen Supply Company, Inc. $Aegis MI |  |  |  |  | 76.5 | 4252901-01 | 0 | 0
243 | Condensation Drains Mat | AP | 426 | 07/12/18 | 08/13/18 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 618.4 | 4254438-00 | 0 | 0
243 | Condensation Drains Mat | GL | 656 | 08/22/18 | 08/22/18 | Mat | Req 4623 |  |  |  |  | 1.22 |  | 0 | 0
243 | Condensation Drains Mat | GL | 605 | 09/25/18 | 09/25/18 | Mat | Req 5394 |  |  |  |  | 24.5 |  | 0 | 0
243 | Condensation Drains Mat | GL | 575 | 10/22/18 | 10/22/18 | Mat | Req 4719 |  |  |  |  | 14.53 |  | 0 | 0
243 | Condensation Drains Mat | AP | 674 | 09/27/18 | 10/24/18 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 80.4 | 4257887-00 | 0 | 0
243 | Condensation Drains Mat | AP | 412 | 10/17/18 | 11/13/18 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 24.12 | 4258736-00 | 0 | 0
243 | Condensation Drains Mat | GL | 689 | 01/23/19 | 01/23/19 | Mat | Req 4963 |  |  |  |  | 15.65 |  | 0 | 0
243 | Condensation Drains Mat | GL | 284 | 02/08/19 | 02/08/19 | Mat | Req 5689 |  |  |  |  | 6.12 |  | 0 | 0
243 | Condensation Drains Mat | GL | 823 | 03/25/19 | 03/25/19 | Mat | Req 5094 |  |  |  |  | 12.57 |  | 0 | 0
243 | Condensation Drains Mat | AP | 862 | 03/15/19 | 03/26/19 | 1130CS | Consolidated Supply Co. |  |  |  |  | 44.69 | S9172638.001 | 0 | 0
243 | Condensation Drains Mat | GL | 1000 | 03/29/19 | 03/29/19 | CK#5702 | Victor Cortes Mendiola |  |  |  |  | 50.62 |  | 0 | 0
243 | Condensation Drains Mat | AP | 960 | 04/18/19 | 04/30/19 | 1234CO | Capital One Credit Card |  |  |  |  | 70.43 | 041819A | 0 | 0
600 | Subcontractor | AP | 913 | 03/14/19 | 03/26/19 | 1421RA | R.A. Brown Backflow Testing |  |  |  |  | 50 | 19031406 | 0 | 0
600 | Subcontractor | AP | 805 | 05/13/19 | 05/29/19 | 3129MR | Mechanical Resource Services, Inc. |  |  |  |  | 4072.5 | 16597-5523 | 0 | 0
601 | Engineering/Plans | AP | 118 | 08/18/17 | 09/05/17 | 1625FE | Franklin Engineering |  |  |  |  | 3022 | 6652 | 0 | 0
601 | Engineering/Plans | AP | 624 | 09/20/17 | 09/25/17 | 1625FE | Franklin Engineering |  |  |  |  | 12742.5 | 6665 | 0 | 0
601 | Engineering/Plans | AP | 577 | 10/19/17 | 10/27/17 | 1625FE | Franklin Engineering |  |  |  |  | 8323.25 | 6697 | 0 | 0
601 | Engineering/Plans | AP | 547 | 11/16/17 | 11/22/17 | 1625FE | Franklin Engineering |  |  |  |  | 862 | 6767 | 0 | 0
601 | Engineering/Plans | AP | 110 | 12/19/17 | 01/05/18 | 1625FE | Franklin Engineering |  |  |  |  | 1089 | 6774 | 0 | 0
601 | Engineering/Plans | AP | 579 | 01/19/18 | 01/24/18 | 1625FE | Franklin Engineering |  |  |  |  | 3221 | 6812 | 0 | 0
602 | Rental Equipment | AP | 579 | 05/04/18 | 05/22/18 | 2713AR | Ahern Rentals |  |  |  |  | 492.25 | 18953211-1 | 0 | 0
602 | Rental Equipment | AP | 593 | 06/01/18 | 06/18/18 | 2713AR | Ahern Rentals |  |  |  |  | 398.75 | 18953211-2 | 0 | 0
602 | Rental Equipment | AP | 115 | 07/29/18 | 07/06/18 | 2713AR | Ahern Rentals |  |  |  |  | 398.75 | 18953211-3 | 0 | 0
602 | Rental Equipment | AP | 162 | 07/27/18 | 08/08/18 | 2713AR | Ahern Rentals |  |  |  |  | 398.75 | 18953211-4 | 0 | 0
602 | Rental Equipment | AP | 25 | 08/26/18 | 09/04/18 | 2713AR | Ahern Rentals |  |  |  |  | 398.75 | 19458318-1 | 0 | 0
602 | Rental Equipment | AP | 8 | 09/23/18 | 10/01/18 | 2713AR | Ahern Rentals |  |  |  |  | 398.75 | 19458318-2 | 0 | 0
602 | Rental Equipment | AP | 149 | 10/23/18 | 11/05/18 | 2713AR | Ahern Rentals |  |  |  |  | 93.5 | 19458318-3 | 0 | 0
603 | Permits & Licenses | AP | 936 | 04/03/19 | 04/30/19 | 1234CO | Capital One Credit Card |  |  |  |  | 280.8 | 040319B1 | 0 | 0
603 | Permits & Licenses | AP | 937 | 04/03/19 | 04/30/19 | 1234CO | Capital One Credit Card |  |  |  |  | 7.02 | 040319B2 | 0 | 0
607 | Other Expenses | AP | 604 | 08/22/17 | 08/28/17 | 1234CO | Capital One Credit Card |  |  |  |  | 285 | 082217 | 0 | 0
607 | Other Expenses | AP | 656 | 09/15/17 | 09/26/17 | 1234CO | Capital One Credit Card |  |  |  |  | 285 | 091517B | 0 | 0
607 | Other Expenses | AP | 614 | 10/15/17 | 10/26/17 | 1234CO | Capital One Credit Card |  |  |  |  | 285 | 101517A | 0 | 0
607 | Other Expenses | AP | 175 | 11/15/17 | 12/01/17 | 1234CO | Capital One Credit Card |  |  |  |  | 285 | 111517-1 | 0 | 0
607 | Other Expenses | AP | 899 | 12/15/17 | 12/31/17 | 1234CO | Capital One Credit Card |  |  |  |  | 285 | 121517A | 0 | 0
607 | Other Expenses | AP | 719 | 01/15/18 | 01/31/18 | 1234CO | Capital One Credit Card |  |  |  |  | 285 | 011518A | 0 | 0
607 | Other Expenses | AP | 828 | 02/16/18 | 02/21/18 | 1234CO | Capital One Credit Card |  |  |  |  | 285 | 021618E | 0 | 0
607 | Other Expenses | AP | 944 | 03/15/18 | 03/31/18 | 1234CO | Capital One Credit Card |  |  |  |  | 285 | 031518B | 0 | 0
607 | Other Expenses | AP | 794 | 04/15/18 | 04/30/18 | 1234BA | Bank of America CC |  |  |  |  | 285 | 041518B | 0 | 0
607 | Other Expenses | AP | 860 | 05/15/18 | 05/30/18 | 1234CO | Capital One Credit Card |  |  |  |  | 285 | 051518A | 0 | 0
607 | Other Expenses | AP | 213 | 06/15/18 | 07/10/18 | 1234CO | Capital One Credit Card |  |  |  |  | 285 | 061518R1 | 0 | 0
607 | Other Expenses | AP | 143 | 07/15/18 | 08/07/18 | 1234CO | Capital One Credit Card |  |  |  |  | 285 | 071518R1 | 0 | 0
607 | Other Expenses | AP | 1127 | 08/15/18 | 08/30/18 | 1234CO | Capital One Credit Card |  |  |  |  | 285 | 081518R1 | 0 | 0
607 | Other Expenses | AP | 822 | 09/15/18 | 09/30/18 | 1234CO | Capital One Credit Card |  |  |  |  | 285 | 091518R1 | 0 | 0
607 | Other Expenses | AP | 830 | 10/15/18 | 10/30/18 | 1234CO | Capital One Credit Card |  |  |  |  | 285 | 101518R1 | 0 | 0
607 | Other Expenses | AP | 484 | 11/15/18 | 12/14/18 | 1234CO | Capital One Credit Card |  |  |  |  | 285 | 111518R1 | 0 | 0
607 | Other Expenses | AP | 851 | 12/17/18 | 12/31/18 | 1234CO | Capital One Credit Card |  |  |  |  | 285 | 121718R1 | 0 | 0
607 | Other Expenses | AP | 450 | 01/15/19 | 02/14/19 | 1234CO | Capital One Credit Card |  |  |  |  | 285 | 011519R1 | 0 | 0
995 | Payroll Burden | PR | 34 | 08/02/17 | 08/04/17 | GE70 | Gerard, Jordan E | 0 | 0 | 0 | 0 | 42.58 |  | 0 | 0
995 | Payroll Burden | PR | 65 | 08/02/17 | 08/04/17 | SA54 | Sanders, Allen O | 0 | 0 | 0 | 0 | 69.19 |  | 0 | 0
995 | Payroll Burden | PR | 492 | 08/23/17 | 08/25/17 | SA54 | Sanders, Allen O | 0 | 0 | 0 | 0 | 95.13 |  | 0 | 0
995 | Payroll Burden | PR | 492 | 08/23/17 | 08/25/17 | SA54 | Sanders, Allen O | 0 | 0 | 0 | 0 | 34.59 |  | 0 | 0
995 | Payroll Burden | PR | 358 | 09/13/17 | 09/15/17 | WA35 | Waites, Thaddeus Z | 0 | 0 | 0 | 0 | 35.48 |  | 0 | 0
995 | Payroll Burden | PR | 362 | 09/13/17 | 09/15/17 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 20.84 |  | 0 | 0
995 | Payroll Burden | PR | 544 | 09/20/17 | 09/22/17 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 199.58 |  | 0 | 0
995 | Payroll Burden | PR | 544 | 09/20/17 | 09/22/17 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 44.35 |  | 0 | 0
995 | Payroll Burden | PR | 545 | 09/20/17 | 09/22/17 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 20.84 |  | 0 | 0
995 | Payroll Burden | PR | 545 | 09/20/17 | 09/22/17 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 20.84 |  | 0 | 0
995 | Payroll Burden | PR | 762 | 09/27/17 | 09/29/17 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 20.84 |  | 0 | 0
995 | Payroll Burden | PR | 67 | 10/04/17 | 10/06/17 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 44.35 |  | 0 | 0
995 | Payroll Burden | PR | 67 | 10/04/17 | 10/06/17 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 22.18 |  | 0 | 0
995 | Payroll Burden | PR | 68 | 10/04/17 | 10/06/17 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 41.69 |  | 0 | 0
995 | Payroll Burden | PR | 225 | 10/11/17 | 10/13/17 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 88.7 |  | 0 | 0
995 | Payroll Burden | PR | 226 | 10/11/17 | 10/13/17 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 20.84 |  | 0 | 0
995 | Payroll Burden | PR | 226 | 10/11/17 | 10/13/17 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 20.84 |  | 0 | 0
995 | Payroll Burden | PR | 350 | 10/18/17 | 10/20/17 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 44.35 |  | 0 | 0
995 | Payroll Burden | PR | 547 | 10/25/17 | 10/27/17 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 22.18 |  | 0 | 0
995 | Payroll Burden | PR | 212 | 11/08/17 | 11/10/17 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 221.75 |  | 0 | 0
995 | Payroll Burden | PR | 213 | 11/08/17 | 11/10/17 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 104.22 |  | 0 | 0
995 | Payroll Burden | PR | 213 | 11/08/17 | 11/10/17 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 41.69 |  | 0 | 0
995 | Payroll Burden | PR | 225 | 11/08/17 | 11/10/17 | WA35 | Waites, Thaddeus Z | 0 | 0 | 0 | 0 | -35.48 |  | 0 | 0
995 | Payroll Burden | PR | 296 | 11/15/17 | 11/17/17 | CO71 | Cortes Mendiola, Victor H | 0 | 0 | 0 | 0 | 141.92 |  | 0 | 0
995 | Payroll Burden | PR | 343 | 11/15/17 | 11/17/17 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 22.18 |  | 0 | 0
995 | Payroll Burden | PR | 344 | 11/15/17 | 11/17/17 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 72.96 |  | 0 | 0
995 | Payroll Burden | PR | 344 | 11/15/17 | 11/17/17 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 62.53 |  | 0 | 0
995 | Payroll Burden | PR | 438 | 11/22/17 | 11/22/17 | CO71 | Cortes Mendiola, Victor H | 0 | 0 | 0 | 0 | 461.24 |  | 0 | 0
995 | Payroll Burden | PR | 439 | 11/22/17 | 11/22/17 | CO73 | Cortes Sepulveda, Jose R | 0 | 0 | 0 | 0 | 265.21 |  | 0 | 0
995 | Payroll Burden | PR | 457 | 11/22/17 | 11/22/17 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 369.21 |  | 0 | 0
995 | Payroll Burden | PR | 489 | 11/22/17 | 11/22/17 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 243.93 |  | 0 | 0
995 | Payroll Burden | PR | 489 | 11/22/17 | 11/22/17 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 44.35 |  | 0 | 0
995 | Payroll Burden | PR | 490 | 11/22/17 | 11/22/17 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 20.84 |  | 0 | 0
995 | Payroll Burden | PR | 490 | 11/22/17 | 11/22/17 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 41.69 |  | 0 | 0
995 | Payroll Burden | PR | 15 | 11/29/17 | 12/01/17 | CO71 | Cortes Mendiola, Victor H | 0 | 0 | 0 | 0 | 212.88 |  | 0 | 0
995 | Payroll Burden | PR | 16 | 11/29/17 | 12/01/17 | CO73 | Cortes Sepulveda, Jose R | 0 | 0 | 0 | 0 | 122.41 |  | 0 | 0
995 | Payroll Burden | PR | 34 | 11/29/17 | 12/01/17 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 79.83 |  | 0 | 0
995 | Payroll Burden | PR | 66 | 11/29/17 | 12/01/17 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 110.88 |  | 0 | 0
995 | Payroll Burden | PR | 217 | 12/06/17 | 12/08/17 | CO71 | Cortes Mendiola, Victor H | 0 | 0 | 0 | 0 | 425.76 |  | 0 | 0
995 | Payroll Burden | PR | 218 | 12/06/17 | 12/08/17 | CO73 | Cortes Sepulveda, Jose R | 0 | 0 | 0 | 0 | 244.81 |  | 0 | 0
995 | Payroll Burden | PR | 267 | 12/06/17 | 12/08/17 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 310.45 |  | 0 | 0
995 | Payroll Burden | PR | 267 | 12/06/17 | 12/08/17 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 44.35 |  | 0 | 0
995 | Payroll Burden | PR | 268 | 12/06/17 | 12/08/17 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 20.84 |  | 0 | 0
995 | Payroll Burden | PR | 268 | 12/06/17 | 12/08/17 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 20.84 |  | 0 | 0
995 | Payroll Burden | PR | 414 | 12/13/17 | 12/15/17 | CO71 | Cortes Mendiola, Victor H | 0 | 0 | 0 | 0 | 514.46 |  | 0 | 0
995 | Payroll Burden | PR | 415 | 12/13/17 | 12/15/17 | CO73 | Cortes Sepulveda, Jose R | 0 | 0 | 0 | 0 | 295.81 |  | 0 | 0
995 | Payroll Burden | PR | 465 | 12/13/17 | 12/15/17 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 155.23 |  | 0 | 0
995 | Payroll Burden | PR | 466 | 12/13/17 | 12/15/17 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 20.84 |  | 0 | 0
995 | Payroll Burden | PR | 466 | 12/13/17 | 12/15/17 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 20.84 |  | 0 | 0
995 | Payroll Burden | PR | 604 | 12/20/17 | 12/22/17 | CO71 | Cortes Mendiola, Victor H | 0 | 0 | 0 | 0 | 141.92 |  | 0 | 0
995 | Payroll Burden | PR | 605 | 12/20/17 | 12/22/17 | CO73 | Cortes Sepulveda, Jose R | 0 | 0 | 0 | 0 | 81.6 |  | 0 | 0
995 | Payroll Burden | PR | 623 | 12/20/17 | 12/22/17 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 69.85 |  | 0 | 0
995 | Payroll Burden | PR | 655 | 12/20/17 | 12/22/17 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 243.93 |  | 0 | 0
995 | Payroll Burden | PR | 656 | 12/20/17 | 12/22/17 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 41.69 |  | 0 | 0
995 | Payroll Burden | PR | 656 | 12/20/17 | 12/22/17 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 83.38 |  | 0 | 0
995 | Payroll Burden | PR | 795 | 12/27/17 | 12/29/17 | CO71 | Cortes Mendiola, Victor H | 0 | 0 | 0 | 0 | 425.76 |  | 0 | 0
995 | Payroll Burden | PR | 796 | 12/27/17 | 12/29/17 | CO73 | Cortes Sepulveda, Jose R | 0 | 0 | 0 | 0 | 244.81 |  | 0 | 0
995 | Payroll Burden | PR | 814 | 12/27/17 | 12/29/17 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 69.85 |  | 0 | 0
995 | Payroll Burden | PR | 847 | 12/27/17 | 12/29/17 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 20.84 |  | 0 | 0
995 | Payroll Burden | PR | 15 | 01/03/18 | 01/05/18 | CO71 | Cortes Mendiola, Victor H | 0 | 0 | 0 | 0 | 301.58 |  | 0 | 0
995 | Payroll Burden | PR | 16 | 01/03/18 | 01/05/18 | CO73 | Cortes Sepulveda, Jose R | 0 | 0 | 0 | 0 | 122.41 |  | 0 | 0
995 | Payroll Burden | PR | 34 | 01/03/18 | 01/05/18 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 39.92 |  | 0 | 0
995 | Payroll Burden | PR | 65 | 01/03/18 | 01/05/18 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 55.44 |  | 0 | 0
995 | Payroll Burden | PR | 238 | 01/10/18 | 01/12/18 | CO71 | Cortes Mendiola, Victor H | 0 | 0 | 0 | 0 | 372.54 |  | 0 | 0
995 | Payroll Burden | PR | 239 | 01/10/18 | 01/12/18 | CO73 | Cortes Sepulveda, Jose R | 0 | 0 | 0 | 0 | 214.21 |  | 0 | 0
995 | Payroll Burden | PR | 257 | 01/10/18 | 01/12/18 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 39.92 |  | 0 | 0
995 | Payroll Burden | PR | 289 | 01/10/18 | 01/12/18 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 166.31 |  | 0 | 0
995 | Payroll Burden | PR | 289 | 01/10/18 | 01/12/18 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 55.44 |  | 0 | 0
995 | Payroll Burden | PR | 290 | 01/10/18 | 01/12/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 62.53 |  | 0 | 0
995 | Payroll Burden | PR | 290 | 01/10/18 | 01/12/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 31.27 |  | 0 | 0
995 | Payroll Burden | PR | 404 | 01/17/18 | 01/19/18 | CO71 | Cortes Mendiola, Victor H | 0 | 0 | 0 | 0 | 638.64 |  | 0 | 0
995 | Payroll Burden | PR | 405 | 01/17/18 | 01/19/18 | CO73 | Cortes Sepulveda, Jose R | 0 | 0 | 0 | 0 | 367.22 |  | 0 | 0
995 | Payroll Burden | PR | 423 | 01/17/18 | 01/19/18 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 99.79 |  | 0 | 0
995 | Payroll Burden | PR | 423 | 01/17/18 | 01/19/18 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 59.87 |  | 0 | 0
995 | Payroll Burden | PR | 454 | 01/17/18 | 01/19/18 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 83.16 |  | 0 | 0
995 | Payroll Burden | PR | 455 | 01/17/18 | 01/19/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 93.8 |  | 0 | 0
995 | Payroll Burden | PR | 455 | 01/17/18 | 01/19/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 52.11 |  | 0 | 0
995 | Payroll Burden | PR | 457 | 01/17/18 | 01/19/18 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | -83.16 |  | 0 | 0
995 | Payroll Burden | PR | 458 | 01/17/18 | 01/19/18 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 83.16 |  | 0 | 0
995 | Payroll Burden | PR | 600 | 01/24/18 | 01/26/18 | CO71 | Cortes Mendiola, Victor H | 0 | 0 | 0 | 0 | 146.36 |  | 0 | 0
995 | Payroll Burden | PR | 600 | 01/24/18 | 01/26/18 | CO71 | Cortes Mendiola, Victor H | 0 | 0 | 0 | 0 | 674.12 |  | 0 | 0
995 | Payroll Burden | PR | 600 | 01/24/18 | 01/26/18 | CO71 | Cortes Mendiola, Victor H | 0 | 0 | 0 | 0 | 35.48 |  | 0 | 0
995 | Payroll Burden | PR | 601 | 01/24/18 | 01/26/18 | CO73 | Cortes Sepulveda, Jose R | 0 | 0 | 0 | 0 | 84.15 |  | 0 | 0
995 | Payroll Burden | PR | 601 | 01/24/18 | 01/26/18 | CO73 | Cortes Sepulveda, Jose R | 0 | 0 | 0 | 0 | 244.81 |  | 0 | 0
995 | Payroll Burden | PR | 601 | 01/24/18 | 01/26/18 | CO73 | Cortes Sepulveda, Jose R | 0 | 0 | 0 | 0 | 163.21 |  | 0 | 0
995 | Payroll Burden | PR | 618 | 01/24/18 | 01/26/18 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 164.65 |  | 0 | 0
995 | Payroll Burden | PR | 618 | 01/24/18 | 01/26/18 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 259.45 |  | 0 | 0
995 | Payroll Burden | PR | 618 | 01/24/18 | 01/26/18 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 199.58 |  | 0 | 0
995 | Payroll Burden | PR | 629 | 01/24/18 | 01/26/18 | MO56 | Montenegro, Carlos E | 0 | 0 | 0 | 0 | 191.59 |  | 0 | 0
995 | Payroll Burden | PR | 630 | 01/24/18 | 01/26/18 | PA11 | Paco Leyva, Orlando | 0 | 0 | 0 | 0 | 241.26 |  | 0 | 0
995 | Payroll Burden | PR | 650 | 01/24/18 | 01/26/18 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 110.88 |  | 0 | 0
995 | Payroll Burden | PR | 650 | 01/24/18 | 01/26/18 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 27.72 |  | 0 | 0
995 | Payroll Burden | PR | 651 | 01/24/18 | 01/26/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 41.69 |  | 0 | 0
995 | Payroll Burden | PR | 651 | 01/24/18 | 01/26/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 62.53 |  | 0 | 0
995 | Payroll Burden | PR | 19 | 01/31/18 | 02/02/18 | CO71 | Cortes Mendiola, Victor H | 0 | 0 | 0 | 0 | 283.84 |  | 0 | 0
995 | Payroll Burden | PR | 19 | 01/31/18 | 02/02/18 | CO71 | Cortes Mendiola, Victor H | 0 | 0 | 0 | 0 | 283.84 |  | 0 | 0
995 | Payroll Burden | PR | 20 | 01/31/18 | 02/02/18 | CO73 | Cortes Sepulveda, Jose R | 0 | 0 | 0 | 0 | 163.21 |  | 0 | 0
995 | Payroll Burden | PR | 20 | 01/31/18 | 02/02/18 | CO73 | Cortes Sepulveda, Jose R | 0 | 0 | 0 | 0 | 163.21 |  | 0 | 0
995 | Payroll Burden | PR | 38 | 01/31/18 | 02/02/18 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 309.34 |  | 0 | 0
995 | Payroll Burden | PR | 38 | 01/31/18 | 02/02/18 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 59.87 |  | 0 | 0
995 | Payroll Burden | PR | 70 | 01/31/18 | 02/02/18 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 83.16 |  | 0 | 0
995 | Payroll Burden | PR | 71 | 01/31/18 | 02/02/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 52.11 |  | 0 | 0
995 | Payroll Burden | PR | 176 | 02/07/18 | 02/09/18 | CO71 | Cortes Mendiola, Victor H | 0 | 0 | 0 | 0 | 177.4 |  | 0 | 0
995 | Payroll Burden | PR | 177 | 02/07/18 | 02/09/18 | CO73 | Cortes Sepulveda, Jose R | 0 | 0 | 0 | 0 | 163.21 |  | 0 | 0
995 | Payroll Burden | PR | 195 | 02/07/18 | 02/09/18 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 199.58 |  | 0 | 0
995 | Payroll Burden | PR | 207 | 02/07/18 | 02/09/18 | PA11 | Paco Leyva, Orlando | 0 | 0 | 0 | 0 | 241.26 |  | 0 | 0
995 | Payroll Burden | PR | 227 | 02/07/18 | 02/09/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 20.84 |  | 0 | 0
995 | Payroll Burden | PR | 227 | 02/07/18 | 02/09/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 41.69 |  | 0 | 0
995 | Payroll Burden | PR | 229 | 02/07/18 | 02/09/18 | PA11 | Paco Leyva, Orlando | 0 | 0 | 0 | 0 | -241.26 |  | 0 | 0
995 | Payroll Burden | PR | 430 | 02/14/18 | 02/16/18 | CO71 | Cortes Mendiola, Victor H | 0 | 0 | 0 | 0 | 549.94 |  | 0 | 0
995 | Payroll Burden | PR | 430 | 02/14/18 | 02/16/18 | CO71 | Cortes Mendiola, Victor H | 0 | 0 | 0 | 0 | 159.66 |  | 0 | 0
995 | Payroll Burden | PR | 431 | 02/14/18 | 02/16/18 | CO73 | Cortes Sepulveda, Jose R | 0 | 0 | 0 | 0 | 316.22 |  | 0 | 0
995 | Payroll Burden | PR | 431 | 02/14/18 | 02/16/18 | CO73 | Cortes Sepulveda, Jose R | 0 | 0 | 0 | 0 | 91.8 |  | 0 | 0
995 | Payroll Burden | PR | 449 | 02/14/18 | 02/16/18 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 99.79 |  | 0 | 0
995 | Payroll Burden | PR | 449 | 02/14/18 | 02/16/18 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 279.41 |  | 0 | 0
995 | Payroll Burden | PR | 449 | 02/14/18 | 02/16/18 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 59.87 |  | 0 | 0
995 | Payroll Burden | PR | 449 | 02/14/18 | 02/16/18 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 79.83 |  | 0 | 0
995 | Payroll Burden | PR | 452 | 02/14/18 | 02/16/18 | LI49 | Lima Romero, Melvin A | 0 | 0 | 0 | 0 | 109.99 |  | 0 | 0
995 | Payroll Burden | PR | 483 | 02/14/18 | 02/16/18 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 55.44 |  | 0 | 0
995 | Payroll Burden | PR | 484 | 02/14/18 | 02/16/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 41.69 |  | 0 | 0
995 | Payroll Burden | PR | 484 | 02/14/18 | 02/16/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 20.84 |  | 0 | 0
995 | Payroll Burden | PR | 617 | 02/21/18 | 02/23/18 | CO71 | Cortes Mendiola, Victor H | 0 | 0 | 0 | 0 | 567.68 |  | 0 | 0
995 | Payroll Burden | PR | 618 | 02/21/18 | 02/23/18 | CO73 | Cortes Sepulveda, Jose R | 0 | 0 | 0 | 0 | 224.41 |  | 0 | 0
995 | Payroll Burden | PR | 618 | 02/21/18 | 02/23/18 | CO73 | Cortes Sepulveda, Jose R | 0 | 0 | 0 | 0 | 102.01 |  | 0 | 0
995 | Payroll Burden | PR | 636 | 02/21/18 | 02/23/18 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 79.83 |  | 0 | 0
995 | Payroll Burden | PR | 636 | 02/21/18 | 02/23/18 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 139.7 |  | 0 | 0
995 | Payroll Burden | PR | 670 | 02/21/18 | 02/23/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 20.84 |  | 0 | 0
995 | Payroll Burden | PR | 3 | 02/28/18 | 03/02/18 | AS10 | Ascencio, Jose L | 0 | 0 | 0 | 0 | 88.7 |  | 0 | 0
995 | Payroll Burden | PR | 4 | 02/28/18 | 03/02/18 | BA45 | Balderas Ortiz, Ricardo I | 0 | 0 | 0 | 0 | 95.8 |  | 0 | 0
995 | Payroll Burden | PR | 16 | 02/28/18 | 03/02/18 | CO71 | Cortes Mendiola, Victor H | 0 | 0 | 0 | 0 | 709.6 |  | 0 | 0
995 | Payroll Burden | PR | 17 | 02/28/18 | 03/02/18 | CO73 | Cortes Sepulveda, Jose R | 0 | 0 | 0 | 0 | 408.02 |  | 0 | 0
995 | Payroll Burden | PR | 35 | 02/28/18 | 03/02/18 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 399.15 |  | 0 | 0
995 | Payroll Burden | PR | 47 | 02/28/18 | 03/02/18 | PA11 | Paco Leyva, Orlando | 0 | 0 | 0 | 0 | 120.63 |  | 0 | 0
995 | Payroll Burden | PR | 68 | 02/28/18 | 03/02/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 20.84 |  | 0 | 0
995 | Payroll Burden | PR | 119 | 03/07/18 | 03/09/18 | AS10 | Ascencio, Jose L | 0 | 0 | 0 | 0 | 266.1 |  | 0 | 0
995 | Payroll Burden | PR | 131 | 03/07/18 | 03/09/18 | CO71 | Cortes Mendiola, Victor H | 0 | 0 | 0 | 0 | 283.84 |  | 0 | 0
995 | Payroll Burden | PR | 131 | 03/07/18 | 03/09/18 | CO71 | Cortes Mendiola, Victor H | 0 | 0 | 0 | 0 | 283.84 |  | 0 | 0
995 | Payroll Burden | PR | 131 | 03/07/18 | 03/09/18 | CO71 | Cortes Mendiola, Victor H | 0 | 0 | 0 | 0 | 141.92 |  | 0 | 0
995 | Payroll Burden | PR | 132 | 03/07/18 | 03/09/18 | CO73 | Cortes Sepulveda, Jose R | 0 | 0 | 0 | 0 | 163.21 |  | 0 | 0
995 | Payroll Burden | PR | 132 | 03/07/18 | 03/09/18 | CO73 | Cortes Sepulveda, Jose R | 0 | 0 | 0 | 0 | 163.21 |  | 0 | 0
995 | Payroll Burden | PR | 132 | 03/07/18 | 03/09/18 | CO73 | Cortes Sepulveda, Jose R | 0 | 0 | 0 | 0 | 81.6 |  | 0 | 0
995 | Payroll Burden | PR | 149 | 03/07/18 | 03/09/18 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 169.64 |  | 0 | 0
995 | Payroll Burden | PR | 149 | 03/07/18 | 03/09/18 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 139.7 |  | 0 | 0
995 | Payroll Burden | PR | 173 | 03/07/18 | 03/09/18 | SI48 | Silva Morales, Jair J | 0 | 0 | 0 | 0 | 81.6 |  | 0 | 0
995 | Payroll Burden | PR | 183 | 03/07/18 | 03/09/18 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 27.72 |  | 0 | 0
995 | Payroll Burden | PR | 184 | 03/07/18 | 03/09/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 62.53 |  | 0 | 0
995 | Payroll Burden | PR | 184 | 03/07/18 | 03/09/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 20.84 |  | 0 | 0
995 | Payroll Burden | PR | 319 | 03/14/18 | 03/16/18 | AS10 | Ascencio, Jose L | 0 | 0 | 0 | 0 | 443.5 |  | 0 | 0
995 | Payroll Burden | PR | 331 | 03/14/18 | 03/16/18 | CO71 | Cortes Mendiola, Victor H | 0 | 0 | 0 | 0 | 709.6 |  | 0 | 0
995 | Payroll Burden | PR | 332 | 03/14/18 | 03/16/18 | CO73 | Cortes Sepulveda, Jose R | 0 | 0 | 0 | 0 | 142.81 |  | 0 | 0
995 | Payroll Burden | PR | 332 | 03/14/18 | 03/16/18 | CO73 | Cortes Sepulveda, Jose R | 0 | 0 | 0 | 0 | 81.6 |  | 0 | 0
995 | Payroll Burden | PR | 332 | 03/14/18 | 03/16/18 | CO73 | Cortes Sepulveda, Jose R | 0 | 0 | 0 | 0 | 163.21 |  | 0 | 0
995 | Payroll Burden | PR | 350 | 03/14/18 | 03/16/18 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 59.87 |  | 0 | 0
995 | Payroll Burden | PR | 376 | 03/14/18 | 03/16/18 | SI48 | Silva Morales, Jair J | 0 | 0 | 0 | 0 | 163.21 |  | 0 | 0
995 | Payroll Burden | PR | 376 | 03/14/18 | 03/16/18 | SI48 | Silva Morales, Jair J | 0 | 0 | 0 | 0 | 244.81 |  | 0 | 0
995 | Payroll Burden | PR | 384 | 03/14/18 | 03/16/18 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 55.44 |  | 0 | 0
995 | Payroll Burden | PR | 384 | 03/14/18 | 03/16/18 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 27.72 |  | 0 | 0
995 | Payroll Burden | PR | 385 | 03/14/18 | 03/16/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 44.35 |  | 0 | 0
995 | Payroll Burden | PR | 517 | 03/21/18 | 03/23/18 | AS10 | Ascencio, Jose L | 0 | 0 | 0 | 0 | 443.5 |  | 0 | 0
995 | Payroll Burden | PR | 529 | 03/21/18 | 03/23/18 | CO71 | Cortes Mendiola, Victor H | 0 | 0 | 0 | 0 | 532.2 |  | 0 | 0
995 | Payroll Burden | PR | 529 | 03/21/18 | 03/23/18 | CO71 | Cortes Mendiola, Victor H | 0 | 0 | 0 | 0 | 35.48 |  | 0 | 0
995 | Payroll Burden | PR | 530 | 03/21/18 | 03/23/18 | CO73 | Cortes Sepulveda, Jose R | 0 | 0 | 0 | 0 | 367.22 |  | 0 | 0
995 | Payroll Burden | PR | 530 | 03/21/18 | 03/23/18 | CO73 | Cortes Sepulveda, Jose R | 0 | 0 | 0 | 0 | 40.8 |  | 0 | 0
995 | Payroll Burden | PR | 548 | 03/21/18 | 03/23/18 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 179.62 |  | 0 | 0
995 | Payroll Burden | PR | 548 | 03/21/18 | 03/23/18 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 39.92 |  | 0 | 0
995 | Payroll Burden | PR | 548 | 03/21/18 | 03/23/18 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 59.87 |  | 0 | 0
995 | Payroll Burden | PR | 575 | 03/21/18 | 03/23/18 | SI48 | Silva Morales, Jair J | 0 | 0 | 0 | 0 | 204.01 |  | 0 | 0
995 | Payroll Burden | PR | 575 | 03/21/18 | 03/23/18 | SI48 | Silva Morales, Jair J | 0 | 0 | 0 | 0 | 204.01 |  | 0 | 0
995 | Payroll Burden | PR | 583 | 03/21/18 | 03/23/18 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 110.88 |  | 0 | 0
995 | Payroll Burden | PR | 584 | 03/21/18 | 03/23/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 22.18 |  | 0 | 0
995 | Payroll Burden | PR | 736 | 03/28/18 | 03/30/18 | AS10 | Ascencio, Jose L | 0 | 0 | 0 | 0 | 266.1 |  | 0 | 0
995 | Payroll Burden | PR | 736 | 03/28/18 | 03/30/18 | AS10 | Ascencio, Jose L | 0 | 0 | 0 | 0 | 177.4 |  | 0 | 0
995 | Payroll Burden | PR | 748 | 03/28/18 | 03/30/18 | CO71 | Cortes Mendiola, Victor H | 0 | 0 | 0 | 0 | 283.84 |  | 0 | 0
995 | Payroll Burden | PR | 748 | 03/28/18 | 03/30/18 | CO71 | Cortes Mendiola, Victor H | 0 | 0 | 0 | 0 | 425.76 |  | 0 | 0
995 | Payroll Burden | PR | 749 | 03/28/18 | 03/30/18 | CO73 | Cortes Sepulveda, Jose R | 0 | 0 | 0 | 0 | 408.02 |  | 0 | 0
995 | Payroll Burden | PR | 763 | 03/28/18 | 03/30/18 | GU78 | Gutierrez Salas, Jose | 0 | 0 | 0 | 0 | 191.59 |  | 0 | 0
995 | Payroll Burden | PR | 770 | 03/28/18 | 03/30/18 | JU02 | Juarez Alvarez, Oscar R | 0 | 0 | 0 | 0 | 99.34 |  | 0 | 0
995 | Payroll Burden | PR | 770 | 03/28/18 | 03/30/18 | JU02 | Juarez Alvarez, Oscar R | 0 | 0 | 0 | 0 | 198.69 |  | 0 | 0
995 | Payroll Burden | PR | 771 | 03/28/18 | 03/30/18 | JU04 | Juarez Maldonado, Oscar E | 0 | 0 | 0 | 0 | 191.59 |  | 0 | 0
995 | Payroll Burden | PR | 800 | 03/28/18 | 03/30/18 | SI48 | Silva Morales, Jair J | 0 | 0 | 0 | 0 | 387.62 |  | 0 | 0
995 | Payroll Burden | PR | 811 | 03/28/18 | 03/30/18 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 27.72 |  | 0 | 0
995 | Payroll Burden | PR | 812 | 03/28/18 | 03/30/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 66.53 |  | 0 | 0
995 | Payroll Burden | PR | 812 | 03/28/18 | 03/30/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 33.26 |  | 0 | 0
995 | Payroll Burden | PR | 12 | 04/04/18 | 04/06/18 | AS10 | Ascencio, Jose L | 0 | 0 | 0 | 0 | 354.8 |  | 0 | 0
995 | Payroll Burden | PR | 24 | 04/04/18 | 04/06/18 | CO71 | Cortes Mendiola, Victor H | 0 | 0 | 0 | 0 | 603.16 |  | 0 | 0
995 | Payroll Burden | PR | 24 | 04/04/18 | 04/06/18 | CO71 | Cortes Mendiola, Victor H | 0 | 0 | 0 | 0 | 35.48 |  | 0 | 0
995 | Payroll Burden | PR | 24 | 04/04/18 | 04/06/18 | CO71 | Cortes Mendiola, Victor H | 0 | 0 | 0 | 0 | 70.96 |  | 0 | 0
995 | Payroll Burden | PR | 25 | 04/04/18 | 04/06/18 | CO73 | Cortes Sepulveda, Jose R | 0 | 0 | 0 | 0 | 306.02 |  | 0 | 0
995 | Payroll Burden | PR | 25 | 04/04/18 | 04/06/18 | CO73 | Cortes Sepulveda, Jose R | 0 | 0 | 0 | 0 | 81.6 |  | 0 | 0
995 | Payroll Burden | PR | 39 | 04/04/18 | 04/06/18 | GU78 | Gutierrez Salas, Jose | 0 | 0 | 0 | 0 | 247.47 |  | 0 | 0
995 | Payroll Burden | PR | 46 | 04/04/18 | 04/06/18 | JU02 | Juarez Alvarez, Oscar R | 0 | 0 | 0 | 0 | 496.72 |  | 0 | 0
995 | Payroll Burden | PR | 47 | 04/04/18 | 04/06/18 | JU04 | Juarez Maldonado, Oscar E | 0 | 0 | 0 | 0 | 191.59 |  | 0 | 0
995 | Payroll Burden | PR | 47 | 04/04/18 | 04/06/18 | JU04 | Juarez Maldonado, Oscar E | 0 | 0 | 0 | 0 | 63.86 |  | 0 | 0
995 | Payroll Burden | PR | 74 | 04/04/18 | 04/06/18 | SI48 | Silva Morales, Jair J | 0 | 0 | 0 | 0 | 244.81 |  | 0 | 0
995 | Payroll Burden | PR | 74 | 04/04/18 | 04/06/18 | SI48 | Silva Morales, Jair J | 0 | 0 | 0 | 0 | 163.21 |  | 0 | 0
995 | Payroll Burden | PR | 85 | 04/04/18 | 04/06/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 66.53 |  | 0 | 0
995 | Payroll Burden | PR | 85 | 04/04/18 | 04/06/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 44.35 |  | 0 | 0
995 | Payroll Burden | PR | 260 | 04/11/18 | 04/13/18 | AS10 | Ascencio, Jose L | 0 | 0 | 0 | 0 | 399.15 |  | 0 | 0
995 | Payroll Burden | PR | 272 | 04/11/18 | 04/13/18 | CO71 | Cortes Mendiola, Victor H | 0 | 0 | 0 | 0 | 709.6 |  | 0 | 0
995 | Payroll Burden | PR | 273 | 04/11/18 | 04/13/18 | CO73 | Cortes Sepulveda, Jose R | 0 | 0 | 0 | 0 | 326.42 |  | 0 | 0
995 | Payroll Burden | PR | 287 | 04/11/18 | 04/13/18 | GU78 | Gutierrez Salas, Jose | 0 | 0 | 0 | 0 | 319.32 |  | 0 | 0
995 | Payroll Burden | PR | 292 | 04/11/18 | 04/13/18 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 59.87 |  | 0 | 0
995 | Payroll Burden | PR | 292 | 04/11/18 | 04/13/18 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 59.87 |  | 0 | 0
995 | Payroll Burden | PR | 294 | 04/11/18 | 04/13/18 | JU02 | Juarez Alvarez, Oscar R | 0 | 0 | 0 | 0 | 496.72 |  | 0 | 0
995 | Payroll Burden | PR | 295 | 04/11/18 | 04/13/18 | JU04 | Juarez Maldonado, Oscar E | 0 | 0 | 0 | 0 | 255.46 |  | 0 | 0
995 | Payroll Burden | PR | 295 | 04/11/18 | 04/13/18 | JU04 | Juarez Maldonado, Oscar E | 0 | 0 | 0 | 0 | 63.86 |  | 0 | 0
995 | Payroll Burden | PR | 323 | 04/11/18 | 04/13/18 | SI48 | Silva Morales, Jair J | 0 | 0 | 0 | 0 | 163.21 |  | 0 | 0
995 | Payroll Burden | PR | 333 | 04/11/18 | 04/13/18 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 55.44 |  | 0 | 0
995 | Payroll Burden | PR | 334 | 04/11/18 | 04/13/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 44.35 |  | 0 | 0
995 | Payroll Burden | PR | 447 | 04/18/18 | 04/20/18 | AS10 | Ascencio, Jose L | 0 | 0 | 0 | 0 | 443.5 |  | 0 | 0
995 | Payroll Burden | PR | 457 | 04/18/18 | 04/20/18 | CO71 | Cortes Mendiola, Victor H | 0 | 0 | 0 | 0 | 283.84 |  | 0 | 0
995 | Payroll Burden | PR | 458 | 04/18/18 | 04/20/18 | CO73 | Cortes Sepulveda, Jose R | 0 | 0 | 0 | 0 | 244.81 |  | 0 | 0
995 | Payroll Burden | PR | 458 | 04/18/18 | 04/20/18 | CO73 | Cortes Sepulveda, Jose R | 0 | 0 | 0 | 0 | 163.21 |  | 0 | 0
995 | Payroll Burden | PR | 472 | 04/18/18 | 04/20/18 | GU78 | Gutierrez Salas, Jose | 0 | 0 | 0 | 0 | 255.46 |  | 0 | 0
995 | Payroll Burden | PR | 477 | 04/18/18 | 04/20/18 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 139.7 |  | 0 | 0
995 | Payroll Burden | PR | 477 | 04/18/18 | 04/20/18 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 339.28 |  | 0 | 0
995 | Payroll Burden | PR | 479 | 04/18/18 | 04/20/18 | JU02 | Juarez Alvarez, Oscar R | 0 | 0 | 0 | 0 | 397.38 |  | 0 | 0
995 | Payroll Burden | PR | 479 | 04/18/18 | 04/20/18 | JU02 | Juarez Alvarez, Oscar R | 0 | 0 | 0 | 0 | 99.34 |  | 0 | 0
995 | Payroll Burden | PR | 480 | 04/18/18 | 04/20/18 | JU04 | Juarez Maldonado, Oscar E | 0 | 0 | 0 | 0 | 255.46 |  | 0 | 0
995 | Payroll Burden | PR | 480 | 04/18/18 | 04/20/18 | JU04 | Juarez Maldonado, Oscar E | 0 | 0 | 0 | 0 | 63.86 |  | 0 | 0
995 | Payroll Burden | PR | 508 | 04/18/18 | 04/20/18 | SI48 | Silva Morales, Jair J | 0 | 0 | 0 | 0 | 81.6 |  | 0 | 0
995 | Payroll Burden | PR | 517 | 04/18/18 | 04/20/18 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 83.16 |  | 0 | 0
995 | Payroll Burden | PR | 518 | 04/18/18 | 04/20/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 22.18 |  | 0 | 0
995 | Payroll Burden | PR | 613 | 04/25/18 | 04/27/18 | AS10 | Ascencio, Jose L | 0 | 0 | 0 | 0 | 443.5 |  | 0 | 0
995 | Payroll Burden | PR | 615 | 04/25/18 | 04/27/18 | BA45 | Balderas Ortiz, Ricardo I | 0 | 0 | 0 | 0 | 191.59 |  | 0 | 0
995 | Payroll Burden | PR | 624 | 04/25/18 | 04/27/18 | CO71 | Cortes Mendiola, Victor H | 0 | 0 | 0 | 0 | 212.88 |  | 0 | 0
995 | Payroll Burden | PR | 624 | 04/25/18 | 04/27/18 | CO71 | Cortes Mendiola, Victor H | 0 | 0 | 0 | 0 | 496.72 |  | 0 | 0
995 | Payroll Burden | PR | 625 | 04/25/18 | 04/27/18 | CO73 | Cortes Sepulveda, Jose R | 0 | 0 | 0 | 0 | 244.81 |  | 0 | 0
995 | Payroll Burden | PR | 625 | 04/25/18 | 04/27/18 | CO73 | Cortes Sepulveda, Jose R | 0 | 0 | 0 | 0 | 163.21 |  | 0 | 0
995 | Payroll Burden | PR | 634 | 04/25/18 | 04/27/18 | GA70 | Garcia, Jordan X | 0 | 0 | 0 | 0 | 549.94 |  | 0 | 0
995 | Payroll Burden | PR | 639 | 04/25/18 | 04/27/18 | GU78 | Gutierrez Salas, Jose | 0 | 0 | 0 | 0 | 127.73 |  | 0 | 0
995 | Payroll Burden | PR | 639 | 04/25/18 | 04/27/18 | GU78 | Gutierrez Salas, Jose | 0 | 0 | 0 | 0 | 63.86 |  | 0 | 0
995 | Payroll Burden | PR | 644 | 04/25/18 | 04/27/18 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 39.92 |  | 0 | 0
995 | Payroll Burden | PR | 644 | 04/25/18 | 04/27/18 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 79.83 |  | 0 | 0
995 | Payroll Burden | PR | 646 | 04/25/18 | 04/27/18 | JU02 | Juarez Alvarez, Oscar R | 0 | 0 | 0 | 0 | 397.38 |  | 0 | 0
995 | Payroll Burden | PR | 646 | 04/25/18 | 04/27/18 | JU02 | Juarez Alvarez, Oscar R | 0 | 0 | 0 | 0 | 99.34 |  | 0 | 0
995 | Payroll Burden | PR | 647 | 04/25/18 | 04/27/18 | JU04 | Juarez Maldonado, Oscar E | 0 | 0 | 0 | 0 | 319.32 |  | 0 | 0
995 | Payroll Burden | PR | 650 | 04/25/18 | 04/27/18 | LI49 | Lima Romero, Melvin A | 0 | 0 | 0 | 0 | 329.96 |  | 0 | 0
995 | Payroll Burden | PR | 674 | 04/25/18 | 04/27/18 | SI48 | Silva Morales, Jair J | 0 | 0 | 0 | 0 | 316.22 |  | 0 | 0
995 | Payroll Burden | PR | 674 | 04/25/18 | 04/27/18 | SI48 | Silva Morales, Jair J | 0 | 0 | 0 | 0 | 81.6 |  | 0 | 0
995 | Payroll Burden | PR | 684 | 04/25/18 | 04/27/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 110.88 |  | 0 | 0
995 | Payroll Burden | PR | 684 | 04/25/18 | 04/27/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 44.35 |  | 0 | 0
995 | Payroll Burden | PR | 27 | 05/02/18 | 05/04/18 | AS10 | Ascencio, Jose L | 0 | 0 | 0 | 0 | 443.5 |  | 0 | 0
995 | Payroll Burden | PR | 29 | 05/02/18 | 05/04/18 | BA45 | Balderas Ortiz, Ricardo I | 0 | 0 | 0 | 0 | 383.18 |  | 0 | 0
995 | Payroll Burden | PR | 29 | 05/02/18 | 05/04/18 | BA45 | Balderas Ortiz, Ricardo I | 0 | 0 | 0 | 0 | 47.9 |  | 0 | 0
995 | Payroll Burden | PR | 38 | 05/02/18 | 05/04/18 | CO71 | Cortes Mendiola, Victor H | 0 | 0 | 0 | 0 | 656.38 |  | 0 | 0
995 | Payroll Burden | PR | 38 | 05/02/18 | 05/04/18 | CO71 | Cortes Mendiola, Victor H | 0 | 0 | 0 | 0 | 53.22 |  | 0 | 0
995 | Payroll Burden | PR | 39 | 05/02/18 | 05/04/18 | CO73 | Cortes Sepulveda, Jose R | 0 | 0 | 0 | 0 | 326.42 |  | 0 | 0
995 | Payroll Burden | PR | 48 | 05/02/18 | 05/04/18 | GA70 | Garcia, Jordan X | 0 | 0 | 0 | 0 | 549.94 |  | 0 | 0
995 | Payroll Burden | PR | 53 | 05/02/18 | 05/04/18 | GU78 | Gutierrez Salas, Jose | 0 | 0 | 0 | 0 | 255.46 |  | 0 | 0
995 | Payroll Burden | PR | 58 | 05/02/18 | 05/04/18 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 179.62 |  | 0 | 0
995 | Payroll Burden | PR | 60 | 05/02/18 | 05/04/18 | JU02 | Juarez Alvarez, Oscar R | 0 | 0 | 0 | 0 | 496.72 |  | 0 | 0
995 | Payroll Burden | PR | 61 | 05/02/18 | 05/04/18 | JU04 | Juarez Maldonado, Oscar E | 0 | 0 | 0 | 0 | 255.46 |  | 0 | 0
995 | Payroll Burden | PR | 64 | 05/02/18 | 05/04/18 | LI49 | Lima Romero, Melvin A | 0 | 0 | 0 | 0 | 549.94 |  | 0 | 0
995 | Payroll Burden | PR | 89 | 05/02/18 | 05/04/18 | SI48 | Silva Morales, Jair J | 0 | 0 | 0 | 0 | 408.02 |  | 0 | 0
995 | Payroll Burden | PR | 99 | 05/02/18 | 05/04/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 22.18 |  | 0 | 0
995 | Payroll Burden | PR | 99 | 05/02/18 | 05/04/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 44.35 |  | 0 | 0
995 | Payroll Burden | PR | 226 | 05/09/18 | 05/11/18 | AS10 | Ascencio, Jose L | 0 | 0 | 0 | 0 | 354.8 |  | 0 | 0
995 | Payroll Burden | PR | 228 | 05/09/18 | 05/11/18 | BA45 | Balderas Ortiz, Ricardo I | 0 | 0 | 0 | 0 | 251.46 |  | 0 | 0
995 | Payroll Burden | PR | 234 | 05/09/18 | 05/11/18 | CO71 | Cortes Mendiola, Victor H | 0 | 0 | 0 | 0 | 638.64 |  | 0 | 0
995 | Payroll Burden | PR | 234 | 05/09/18 | 05/11/18 | CO71 | Cortes Mendiola, Victor H | 0 | 0 | 0 | 0 | 70.96 |  | 0 | 0
995 | Payroll Burden | PR | 235 | 05/09/18 | 05/11/18 | CO73 | Cortes Sepulveda, Jose R | 0 | 0 | 0 | 0 | 408.02 |  | 0 | 0
995 | Payroll Burden | PR | 242 | 05/09/18 | 05/11/18 | GA70 | Garcia, Jordan X | 0 | 0 | 0 | 0 | 522.44 |  | 0 | 0
995 | Payroll Burden | PR | 242 | 05/09/18 | 05/11/18 | GA70 | Garcia, Jordan X | 0 | 0 | 0 | 0 | 27.5 |  | 0 | 0
995 | Payroll Burden | PR | 247 | 05/09/18 | 05/11/18 | GU78 | Gutierrez Salas, Jose | 0 | 0 | 0 | 0 | 255.46 |  | 0 | 0
995 | Payroll Burden | PR | 251 | 05/09/18 | 05/11/18 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 129.72 |  | 0 | 0
995 | Payroll Burden | PR | 253 | 05/09/18 | 05/11/18 | JU02 | Juarez Alvarez, Oscar R | 0 | 0 | 0 | 0 | 496.72 |  | 0 | 0
995 | Payroll Burden | PR | 254 | 05/09/18 | 05/11/18 | JU04 | Juarez Maldonado, Oscar E | 0 | 0 | 0 | 0 | 319.32 |  | 0 | 0
995 | Payroll Burden | PR | 257 | 05/09/18 | 05/11/18 | LI49 | Lima Romero, Melvin A | 0 | 0 | 0 | 0 | 329.96 |  | 0 | 0
995 | Payroll Burden | PR | 279 | 05/09/18 | 05/11/18 | SI48 | Silva Morales, Jair J | 0 | 0 | 0 | 0 | 326.42 |  | 0 | 0
995 | Payroll Burden | PR | 279 | 05/09/18 | 05/11/18 | SI48 | Silva Morales, Jair J | 0 | 0 | 0 | 0 | 81.6 |  | 0 | 0
995 | Payroll Burden | PR | 286 | 05/09/18 | 05/11/18 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 83.16 |  | 0 | 0
995 | Payroll Burden | PR | 287 | 05/09/18 | 05/11/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 44.35 |  | 0 | 0
995 | Payroll Burden | PR | 422 | 05/16/18 | 05/18/18 | AS10 | Ascencio, Jose L | 0 | 0 | 0 | 0 | 443.5 |  | 0 | 0
995 | Payroll Burden | PR | 424 | 05/16/18 | 05/18/18 | BA45 | Balderas Ortiz, Ricardo I | 0 | 0 | 0 | 0 | 478.98 |  | 0 | 0
995 | Payroll Burden | PR | 432 | 05/16/18 | 05/18/18 | CO71 | Cortes Mendiola, Victor H | 0 | 0 | 0 | 0 | 567.68 |  | 0 | 0
995 | Payroll Burden | PR | 432 | 05/16/18 | 05/18/18 | CO71 | Cortes Mendiola, Victor H | 0 | 0 | 0 | 0 | 141.92 |  | 0 | 0
995 | Payroll Burden | PR | 433 | 05/16/18 | 05/18/18 | CO73 | Cortes Sepulveda, Jose R | 0 | 0 | 0 | 0 | 397.82 |  | 0 | 0
995 | Payroll Burden | PR | 442 | 05/16/18 | 05/18/18 | GA70 | Garcia, Jordan X | 0 | 0 | 0 | 0 | 549.94 |  | 0 | 0
995 | Payroll Burden | PR | 447 | 05/16/18 | 05/18/18 | GU78 | Gutierrez Salas, Jose | 0 | 0 | 0 | 0 | 255.46 |  | 0 | 0
995 | Payroll Burden | PR | 447 | 05/16/18 | 05/18/18 | GU78 | Gutierrez Salas, Jose | 0 | 0 | 0 | 0 | 63.86 |  | 0 | 0
995 | Payroll Burden | PR | 454 | 05/16/18 | 05/18/18 | JU02 | Juarez Alvarez, Oscar R | 0 | 0 | 0 | 0 | 484.3 |  | 0 | 0
995 | Payroll Burden | PR | 455 | 05/16/18 | 05/18/18 | JU04 | Juarez Maldonado, Oscar E | 0 | 0 | 0 | 0 | 311.34 |  | 0 | 0
995 | Payroll Burden | PR | 458 | 05/16/18 | 05/18/18 | LI49 | Lima Romero, Melvin A | 0 | 0 | 0 | 0 | 549.94 |  | 0 | 0
995 | Payroll Burden | PR | 482 | 05/16/18 | 05/18/18 | SI48 | Silva Morales, Jair J | 0 | 0 | 0 | 0 | 81.6 |  | 0 | 0
995 | Payroll Burden | PR | 482 | 05/16/18 | 05/18/18 | SI48 | Silva Morales, Jair J | 0 | 0 | 0 | 0 | 224.41 |  | 0 | 0
995 | Payroll Burden | PR | 492 | 05/16/18 | 05/18/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 22.18 |  | 0 | 0
995 | Payroll Burden | PR | 492 | 05/16/18 | 05/18/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 22.18 |  | 0 | 0
995 | Payroll Burden | PR | 737 | 05/23/18 | 05/25/18 | AS10 | Ascencio, Jose L | 0 | 0 | 0 | 0 | 99.79 |  | 0 | 0
995 | Payroll Burden | PR | 737 | 05/23/18 | 05/25/18 | AS10 | Ascencio, Jose L | 0 | 0 | 0 | 0 | 443.5 |  | 0 | 0
995 | Payroll Burden | PR | 739 | 05/23/18 | 05/25/18 | BA45 | Balderas Ortiz, Ricardo I | 0 | 0 | 0 | 0 | 107.77 |  | 0 | 0
995 | Payroll Burden | PR | 739 | 05/23/18 | 05/25/18 | BA45 | Balderas Ortiz, Ricardo I | 0 | 0 | 0 | 0 | 478.98 |  | 0 | 0
995 | Payroll Burden | PR | 747 | 05/23/18 | 05/25/18 | CO71 | Cortes Mendiola, Victor H | 0 | 0 | 0 | 0 | 93.14 |  | 0 | 0
995 | Payroll Burden | PR | 747 | 05/23/18 | 05/25/18 | CO71 | Cortes Mendiola, Victor H | 0 | 0 | 0 | 0 | 53.22 |  | 0 | 0
995 | Payroll Burden | PR | 747 | 05/23/18 | 05/25/18 | CO71 | Cortes Mendiola, Victor H | 0 | 0 | 0 | 0 | 674.12 |  | 0 | 0
995 | Payroll Burden | PR | 747 | 05/23/18 | 05/25/18 | CO71 | Cortes Mendiola, Victor H | 0 | 0 | 0 | 0 | 35.48 |  | 0 | 0
995 | Payroll Burden | PR | 748 | 05/23/18 | 05/25/18 | CO73 | Cortes Sepulveda, Jose R | 0 | 0 | 0 | 0 | 91.8 |  | 0 | 0
995 | Payroll Burden | PR | 748 | 05/23/18 | 05/25/18 | CO73 | Cortes Sepulveda, Jose R | 0 | 0 | 0 | 0 | 408.02 |  | 0 | 0
995 | Payroll Burden | PR | 750 | 05/23/18 | 05/25/18 | CR79 | Cruz Guzman, Joel A | 0 | 0 | 0 | 0 | 117.08 |  | 0 | 0
995 | Payroll Burden | PR | 757 | 05/23/18 | 05/25/18 | GA70 | Garcia, Jordan X | 0 | 0 | 0 | 0 | 82.49 |  | 0 | 0
995 | Payroll Burden | PR | 757 | 05/23/18 | 05/25/18 | GA70 | Garcia, Jordan X | 0 | 0 | 0 | 0 | 439.95 |  | 0 | 0
995 | Payroll Burden | PR | 762 | 05/23/18 | 05/25/18 | GU78 | Gutierrez Salas, Jose | 0 | 0 | 0 | 0 | 255.46 |  | 0 | 0
995 | Payroll Burden | PR | 762 | 05/23/18 | 05/25/18 | GU78 | Gutierrez Salas, Jose | 0 | 0 | 0 | 0 | 63.86 |  | 0 | 0
995 | Payroll Burden | PR | 767 | 05/23/18 | 05/25/18 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 39.92 |  | 0 | 0
995 | Payroll Burden | PR | 769 | 05/23/18 | 05/25/18 | JU02 | Juarez Alvarez, Oscar R | 0 | 0 | 0 | 0 | 111.76 |  | 0 | 0
995 | Payroll Burden | PR | 769 | 05/23/18 | 05/25/18 | JU02 | Juarez Alvarez, Oscar R | 0 | 0 | 0 | 0 | 496.72 |  | 0 | 0
995 | Payroll Burden | PR | 770 | 05/23/18 | 05/25/18 | JU04 | Juarez Maldonado, Oscar E | 0 | 0 | 0 | 0 | 71.85 |  | 0 | 0
995 | Payroll Burden | PR | 770 | 05/23/18 | 05/25/18 | JU04 | Juarez Maldonado, Oscar E | 0 | 0 | 0 | 0 | 319.32 |  | 0 | 0
995 | Payroll Burden | PR | 773 | 05/23/18 | 05/25/18 | LI49 | Lima Romero, Melvin A | 0 | 0 | 0 | 0 | 123.74 |  | 0 | 0
995 | Payroll Burden | PR | 773 | 05/23/18 | 05/25/18 | LI49 | Lima Romero, Melvin A | 0 | 0 | 0 | 0 | 549.94 |  | 0 | 0
995 | Payroll Burden | PR | 797 | 05/23/18 | 05/25/18 | SI48 | Silva Morales, Jair J | 0 | 0 | 0 | 0 | 45.9 |  | 0 | 0
995 | Payroll Burden | PR | 797 | 05/23/18 | 05/25/18 | SI48 | Silva Morales, Jair J | 0 | 0 | 0 | 0 | 173.41 |  | 0 | 0
995 | Payroll Burden | PR | 806 | 05/23/18 | 05/25/18 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 27.72 |  | 0 | 0
995 | Payroll Burden | PR | 807 | 05/23/18 | 05/25/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 66.53 |  | 0 | 0
995 | Payroll Burden | PR | 4 | 05/30/18 | 06/01/18 | AS10 | Ascencio, Jose L | 0 | 0 | 0 | 0 | 421.33 |  | 0 | 0
995 | Payroll Burden | PR | 6 | 05/30/18 | 06/01/18 | BA45 | Balderas Ortiz, Ricardo I | 0 | 0 | 0 | 0 | 455.03 |  | 0 | 0
995 | Payroll Burden | PR | 14 | 05/30/18 | 06/01/18 | CO71 | Cortes Mendiola, Victor H | 0 | 0 | 0 | 0 | 478.98 |  | 0 | 0
995 | Payroll Burden | PR | 14 | 05/30/18 | 06/01/18 | CO71 | Cortes Mendiola, Victor H | 0 | 0 | 0 | 0 | 177.4 |  | 0 | 0
995 | Payroll Burden | PR | 14 | 05/30/18 | 06/01/18 | CO71 | Cortes Mendiola, Victor H | 0 | 0 | 0 | 0 | 17.74 |  | 0 | 0
995 | Payroll Burden | PR | 15 | 05/30/18 | 06/01/18 | CO73 | Cortes Sepulveda, Jose R | 0 | 0 | 0 | 0 | 367.22 |  | 0 | 0
995 | Payroll Burden | PR | 24 | 05/30/18 | 06/01/18 | GA70 | Garcia, Jordan X | 0 | 0 | 0 | 0 | 494.95 |  | 0 | 0
995 | Payroll Burden | PR | 29 | 05/30/18 | 06/01/18 | GU78 | Gutierrez Salas, Jose | 0 | 0 | 0 | 0 | 303.35 |  | 0 | 0
995 | Payroll Burden | PR | 36 | 05/30/18 | 06/01/18 | JU02 | Juarez Alvarez, Oscar R | 0 | 0 | 0 | 0 | 471.88 |  | 0 | 0
995 | Payroll Burden | PR | 37 | 05/30/18 | 06/01/18 | JU04 | Juarez Maldonado, Oscar E | 0 | 0 | 0 | 0 | 303.35 |  | 0 | 0
995 | Payroll Burden | PR | 40 | 05/30/18 | 06/01/18 | LI49 | Lima Romero, Melvin A | 0 | 0 | 0 | 0 | 522.44 |  | 0 | 0
995 | Payroll Burden | PR | 41 | 05/30/18 | 06/01/18 | LO58 | Lopez Reyes, Boris O | 0 | 0 | 0 | 0 | 55.88 |  | 0 | 0
995 | Payroll Burden | PR | 64 | 05/30/18 | 06/01/18 | SI48 | Silva Morales, Jair J | 0 | 0 | 0 | 0 | 102.01 |  | 0 | 0
995 | Payroll Burden | PR | 76 | 05/30/18 | 06/01/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 22.18 |  | 0 | 0
995 | Payroll Burden | PR | 76 | 05/30/18 | 06/01/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 22.18 |  | 0 | 0
995 | Payroll Burden | PR | 269 | 06/06/18 | 06/08/18 | AS10 | Ascencio, Jose L | 0 | 0 | 0 | 0 | 133.05 |  | 0 | 0
995 | Payroll Burden | PR | 269 | 06/06/18 | 06/08/18 | AS10 | Ascencio, Jose L | 0 | 0 | 0 | 0 | 443.5 |  | 0 | 0
995 | Payroll Burden | PR | 271 | 06/06/18 | 06/08/18 | BA45 | Balderas Ortiz, Ricardo I | 0 | 0 | 0 | 0 | 35.92 |  | 0 | 0
995 | Payroll Burden | PR | 271 | 06/06/18 | 06/08/18 | BA45 | Balderas Ortiz, Ricardo I | 0 | 0 | 0 | 0 | 263.44 |  | 0 | 0
995 | Payroll Burden | PR | 271 | 06/06/18 | 06/08/18 | BA45 | Balderas Ortiz, Ricardo I | 0 | 0 | 0 | 0 | 215.54 |  | 0 | 0
995 | Payroll Burden | PR | 279 | 06/06/18 | 06/08/18 | CO71 | Cortes Mendiola, Victor H | 0 | 0 | 0 | 0 | 53.22 |  | 0 | 0
995 | Payroll Burden | PR | 279 | 06/06/18 | 06/08/18 | CO71 | Cortes Mendiola, Victor H | 0 | 0 | 0 | 0 | 79.83 |  | 0 | 0
995 | Payroll Burden | PR | 279 | 06/06/18 | 06/08/18 | CO71 | Cortes Mendiola, Victor H | 0 | 0 | 0 | 0 | 53.22 |  | 0 | 0
995 | Payroll Burden | PR | 279 | 06/06/18 | 06/08/18 | CO71 | Cortes Mendiola, Victor H | 0 | 0 | 0 | 0 | 514.46 |  | 0 | 0
995 | Payroll Burden | PR | 279 | 06/06/18 | 06/08/18 | CO71 | Cortes Mendiola, Victor H | 0 | 0 | 0 | 0 | 177.4 |  | 0 | 0
995 | Payroll Burden | PR | 279 | 06/06/18 | 06/08/18 | CO71 | Cortes Mendiola, Victor H | 0 | 0 | 0 | 0 | 17.74 |  | 0 | 0
995 | Payroll Burden | PR | 280 | 06/06/18 | 06/08/18 | CO73 | Cortes Sepulveda, Jose R | 0 | 0 | 0 | 0 | 122.41 |  | 0 | 0
995 | Payroll Burden | PR | 280 | 06/06/18 | 06/08/18 | CO73 | Cortes Sepulveda, Jose R | 0 | 0 | 0 | 0 | 408.02 |  | 0 | 0
995 | Payroll Burden | PR | 294 | 06/06/18 | 06/08/18 | GU78 | Gutierrez Salas, Jose | 0 | 0 | 0 | 0 | 255.46 |  | 0 | 0
995 | Payroll Burden | PR | 301 | 06/06/18 | 06/08/18 | JU02 | Juarez Alvarez, Oscar R | 0 | 0 | 0 | 0 | 111.76 |  | 0 | 0
995 | Payroll Burden | PR | 301 | 06/06/18 | 06/08/18 | JU02 | Juarez Alvarez, Oscar R | 0 | 0 | 0 | 0 | 496.72 |  | 0 | 0
995 | Payroll Burden | PR | 302 | 06/06/18 | 06/08/18 | JU04 | Juarez Maldonado, Oscar E | 0 | 0 | 0 | 0 | 303.35 |  | 0 | 0
995 | Payroll Burden | PR | 305 | 06/06/18 | 06/08/18 | LI49 | Lima Romero, Melvin A | 0 | 0 | 0 | 0 | 164.98 |  | 0 | 0
995 | Payroll Burden | PR | 305 | 06/06/18 | 06/08/18 | LI49 | Lima Romero, Melvin A | 0 | 0 | 0 | 0 | 549.94 |  | 0 | 0
995 | Payroll Burden | PR | 306 | 06/06/18 | 06/08/18 | LO58 | Lopez Reyes, Boris O | 0 | 0 | 0 | 0 | 143.69 |  | 0 | 0
995 | Payroll Burden | PR | 340 | 06/06/18 | 06/08/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 22.18 |  | 0 | 0
995 | Payroll Burden | PR | 459 | 06/13/18 | 06/15/18 | AS10 | Ascencio, Jose L | 0 | 0 | 0 | 0 | 138.37 |  | 0 | 0
995 | Payroll Burden | PR | 459 | 06/13/18 | 06/15/18 | AS10 | Ascencio, Jose L | 0 | 0 | 0 | 0 | 461.24 |  | 0 | 0
995 | Payroll Burden | PR | 461 | 06/13/18 | 06/15/18 | BA45 | Balderas Ortiz, Ricardo I | 0 | 0 | 0 | 0 | 149.02 |  | 0 | 0
995 | Payroll Burden | PR | 461 | 06/13/18 | 06/15/18 | BA45 | Balderas Ortiz, Ricardo I | 0 | 0 | 0 | 0 | 496.72 |  | 0 | 0
995 | Payroll Burden | PR | 469 | 06/13/18 | 06/15/18 | CO71 | Cortes Mendiola, Victor H | 0 | 0 | 0 | 0 | 136.38 |  | 0 | 0
995 | Payroll Burden | PR | 469 | 06/13/18 | 06/15/18 | CO71 | Cortes Mendiola, Victor H | 0 | 0 | 0 | 0 | 27.28 |  | 0 | 0
995 | Payroll Burden | PR | 469 | 06/13/18 | 06/15/18 | CO71 | Cortes Mendiola, Victor H | 0 | 0 | 0 | 0 | 636.42 |  | 0 | 0
995 | Payroll Burden | PR | 469 | 06/13/18 | 06/15/18 | CO71 | Cortes Mendiola, Victor H | 0 | 0 | 0 | 0 | 90.92 |  | 0 | 0
995 | Payroll Burden | PR | 470 | 06/13/18 | 06/15/18 | CO73 | Cortes Sepulveda, Jose R | 0 | 0 | 0 | 0 | 47.9 |  | 0 | 0
995 | Payroll Burden | PR | 470 | 06/13/18 | 06/15/18 | CO73 | Cortes Sepulveda, Jose R | 0 | 0 | 0 | 0 | 425.76 |  | 0 | 0
995 | Payroll Burden | PR | 484 | 06/13/18 | 06/15/18 | GU78 | Gutierrez Salas, Jose | 0 | 0 | 0 | 0 | 143.69 |  | 0 | 0
995 | Payroll Burden | PR | 491 | 06/13/18 | 06/15/18 | JU02 | Juarez Alvarez, Oscar R | 0 | 0 | 0 | 0 | 514.46 |  | 0 | 0
995 | Payroll Burden | PR | 492 | 06/13/18 | 06/15/18 | JU04 | Juarez Maldonado, Oscar E | 0 | 0 | 0 | 0 | 252.8 |  | 0 | 0
995 | Payroll Burden | PR | 495 | 06/13/18 | 06/15/18 | LI49 | Lima Romero, Melvin A | 0 | 0 | 0 | 0 | 170.3 |  | 0 | 0
995 | Payroll Burden | PR | 495 | 06/13/18 | 06/15/18 | LI49 | Lima Romero, Melvin A | 0 | 0 | 0 | 0 | 567.68 |  | 0 | 0
995 | Payroll Burden | PR | 496 | 06/13/18 | 06/15/18 | LO58 | Lopez Reyes, Boris O | 0 | 0 | 0 | 0 | 7.98 |  | 0 | 0
995 | Payroll Burden | PR | 528 | 06/13/18 | 06/15/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 22.18 |  | 0 | 0
995 | Payroll Burden | PR | 528 | 06/13/18 | 06/15/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 44.35 |  | 0 | 0
995 | Payroll Burden | PR | 685 | 06/20/18 | 06/22/18 | AS10 | Ascencio, Jose L | 0 | 0 | 0 | 0 | 103.78 |  | 0 | 0
995 | Payroll Burden | PR | 685 | 06/20/18 | 06/22/18 | AS10 | Ascencio, Jose L | 0 | 0 | 0 | 0 | 461.24 |  | 0 | 0
995 | Payroll Burden | PR | 687 | 06/20/18 | 06/22/18 | BA45 | Balderas Ortiz, Ricardo I | 0 | 0 | 0 | 0 | 149.02 |  | 0 | 0
995 | Payroll Burden | PR | 687 | 06/20/18 | 06/22/18 | BA45 | Balderas Ortiz, Ricardo I | 0 | 0 | 0 | 0 | 496.72 |  | 0 | 0
995 | Payroll Burden | PR | 695 | 06/20/18 | 06/22/18 | CO71 | Cortes Mendiola, Victor H | 0 | 0 | 0 | 0 | 27.28 |  | 0 | 0
995 | Payroll Burden | PR | 695 | 06/20/18 | 06/22/18 | CO71 | Cortes Mendiola, Victor H | 0 | 0 | 0 | 0 | 81.83 |  | 0 | 0
995 | Payroll Burden | PR | 695 | 06/20/18 | 06/22/18 | CO71 | Cortes Mendiola, Victor H | 0 | 0 | 0 | 0 | 54.55 |  | 0 | 0
995 | Payroll Burden | PR | 695 | 06/20/18 | 06/22/18 | CO71 | Cortes Mendiola, Victor H | 0 | 0 | 0 | 0 | 27.28 |  | 0 | 0
995 | Payroll Burden | PR | 695 | 06/20/18 | 06/22/18 | CO71 | Cortes Mendiola, Victor H | 0 | 0 | 0 | 0 | 654.61 |  | 0 | 0
995 | Payroll Burden | PR | 695 | 06/20/18 | 06/22/18 | CO71 | Cortes Mendiola, Victor H | 0 | 0 | 0 | 0 | 72.73 |  | 0 | 0
995 | Payroll Burden | PR | 696 | 06/20/18 | 06/22/18 | CO73 | Cortes Sepulveda, Jose R | 0 | 0 | 0 | 0 | 383.18 |  | 0 | 0
995 | Payroll Burden | PR | 717 | 06/20/18 | 06/22/18 | JU02 | Juarez Alvarez, Oscar R | 0 | 0 | 0 | 0 | 115.75 |  | 0 | 0
995 | Payroll Burden | PR | 717 | 06/20/18 | 06/22/18 | JU02 | Juarez Alvarez, Oscar R | 0 | 0 | 0 | 0 | 514.46 |  | 0 | 0
995 | Payroll Burden | PR | 718 | 06/20/18 | 06/22/18 | JU04 | Juarez Maldonado, Oscar E | 0 | 0 | 0 | 0 | 303.35 |  | 0 | 0
995 | Payroll Burden | PR | 721 | 06/20/18 | 06/22/18 | LI49 | Lima Romero, Melvin A | 0 | 0 | 0 | 0 | 539.3 |  | 0 | 0
995 | Payroll Burden | PR | 754 | 06/20/18 | 06/22/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 22.18 |  | 0 | 0
995 | Payroll Burden | PR | 950 | 06/27/18 | 06/29/18 | CO73 | Cortes Sepulveda, Jose R | 0 | 0 | 0 | 0 | 15.97 |  | 0 | 0
995 | Payroll Burden | PR | 950 | 06/27/18 | 06/29/18 | CO73 | Cortes Sepulveda, Jose R | 0 | 0 | 0 | 0 | 63.86 |  | 0 | 0
995 | Payroll Burden | PR | 950 | 06/27/18 | 06/29/18 | CO73 | Cortes Sepulveda, Jose R | 0 | 0 | 0 | 0 | 42.58 |  | 0 | 0
995 | Payroll Burden | PR | 950 | 06/27/18 | 06/29/18 | CO73 | Cortes Sepulveda, Jose R | 0 | 0 | 0 | 0 | 255.46 |  | 0 | 0
995 | Payroll Burden | PR | 951 | 06/27/18 | 06/29/18 | BA45 | Balderas Ortiz, Ricardo I | 0 | 0 | 0 | 0 | 149.02 |  | 0 | 0
995 | Payroll Burden | PR | 951 | 06/27/18 | 06/29/18 | BA45 | Balderas Ortiz, Ricardo I | 0 | 0 | 0 | 0 | 496.72 |  | 0 | 0
995 | Payroll Burden | PR | 954 | 06/27/18 | 06/29/18 | AS10 | Ascencio, Jose L | 0 | 0 | 0 | 0 | 138.37 |  | 0 | 0
995 | Payroll Burden | PR | 954 | 06/27/18 | 06/29/18 | AS10 | Ascencio, Jose L | 0 | 0 | 0 | 0 | 461.24 |  | 0 | 0
995 | Payroll Burden | PR | 963 | 06/27/18 | 06/29/18 | CO71 | Cortes Mendiola, Victor H | 0 | 0 | 0 | 0 | 54.55 |  | 0 | 0
995 | Payroll Burden | PR | 963 | 06/27/18 | 06/29/18 | CO71 | Cortes Mendiola, Victor H | 0 | 0 | 0 | 0 | 54.55 |  | 0 | 0
995 | Payroll Burden | PR | 963 | 06/27/18 | 06/29/18 | CO71 | Cortes Mendiola, Victor H | 0 | 0 | 0 | 0 | 27.28 |  | 0 | 0
995 | Payroll Burden | PR | 963 | 06/27/18 | 06/29/18 | CO71 | Cortes Mendiola, Victor H | 0 | 0 | 0 | 0 | 436.4 |  | 0 | 0
995 | Payroll Burden | PR | 963 | 06/27/18 | 06/29/18 | CO71 | Cortes Mendiola, Victor H | 0 | 0 | 0 | 0 | 18.18 |  | 0 | 0
995 | Payroll Burden | PR | 963 | 06/27/18 | 06/29/18 | CO71 | Cortes Mendiola, Victor H | 0 | 0 | 0 | 0 | 54.55 |  | 0 | 0
995 | Payroll Burden | PR | 983 | 06/27/18 | 06/29/18 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 41.69 |  | 0 | 0
995 | Payroll Burden | PR | 985 | 06/27/18 | 06/29/18 | JU02 | Juarez Alvarez, Oscar R | 0 | 0 | 0 | 0 | 154.34 |  | 0 | 0
995 | Payroll Burden | PR | 985 | 06/27/18 | 06/29/18 | JU02 | Juarez Alvarez, Oscar R | 0 | 0 | 0 | 0 | 514.46 |  | 0 | 0
995 | Payroll Burden | PR | 986 | 06/27/18 | 06/29/18 | JU04 | Juarez Maldonado, Oscar E | 0 | 0 | 0 | 0 | 101.12 |  | 0 | 0
995 | Payroll Burden | PR | 986 | 06/27/18 | 06/29/18 | JU04 | Juarez Maldonado, Oscar E | 0 | 0 | 0 | 0 | 337.06 |  | 0 | 0
995 | Payroll Burden | PR | 989 | 06/27/18 | 06/29/18 | LI49 | Lima Romero, Melvin A | 0 | 0 | 0 | 0 | 170.3 |  | 0 | 0
995 | Payroll Burden | PR | 989 | 06/27/18 | 06/29/18 | LI49 | Lima Romero, Melvin A | 0 | 0 | 0 | 0 | 567.68 |  | 0 | 0
995 | Payroll Burden | PR | 1019 | 06/27/18 | 06/29/18 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 27.72 |  | 0 | 0
995 | Payroll Burden | PR | 1019 | 06/27/18 | 06/29/18 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 55.44 |  | 0 | 0
995 | Payroll Burden | PR | 1020 | 06/27/18 | 06/29/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 66.53 |  | 0 | 0
995 | Payroll Burden | PR | 1020 | 06/27/18 | 06/29/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 22.18 |  | 0 | 0
995 | Payroll Burden | PR | 6 | 07/04/18 | 07/06/18 | AS10 | Ascencio, Jose L | 0 | 0 | 0 | 0 | 368.99 |  | 0 | 0
995 | Payroll Burden | PR | 16 | 07/04/18 | 07/06/18 | CO71 | Cortes Mendiola, Victor H | 0 | 0 | 0 | 0 | 581.87 |  | 0 | 0
995 | Payroll Burden | PR | 17 | 07/04/18 | 07/06/18 | CO73 | Cortes Sepulveda, Jose R | 0 | 0 | 0 | 0 | 85.15 |  | 0 | 0
995 | Payroll Burden | PR | 17 | 07/04/18 | 07/06/18 | CO73 | Cortes Sepulveda, Jose R | 0 | 0 | 0 | 0 | 79.83 |  | 0 | 0
995 | Payroll Burden | PR | 38 | 07/04/18 | 07/06/18 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 41.69 |  | 0 | 0
995 | Payroll Burden | PR | 38 | 07/04/18 | 07/06/18 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 62.53 |  | 0 | 0
995 | Payroll Burden | PR | 40 | 07/04/18 | 07/06/18 | JU02 | Juarez Alvarez, Oscar R | 0 | 0 | 0 | 0 | 411.57 |  | 0 | 0
995 | Payroll Burden | PR | 41 | 07/04/18 | 07/06/18 | JU04 | Juarez Maldonado, Oscar E | 0 | 0 | 0 | 0 | 202.24 |  | 0 | 0
995 | Payroll Burden | PR | 44 | 07/04/18 | 07/06/18 | LI49 | Lima Romero, Melvin A | 0 | 0 | 0 | 0 | 454.14 |  | 0 | 0
995 | Payroll Burden | PR | 76 | 07/04/18 | 07/06/18 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 138.59 |  | 0 | 0
995 | Payroll Burden | PR | 77 | 07/04/18 | 07/06/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 22.18 |  | 0 | 0
995 | Payroll Burden | PR | 299 | 07/11/18 | 07/13/18 | AS10 | Ascencio, Jose L | 0 | 0 | 0 | 0 | 392.05 |  | 0 | 0
995 | Payroll Burden | PR | 300 | 07/11/18 | 07/13/18 | BA45 | Balderas Ortiz, Ricardo I | 0 | 0 | 0 | 0 | 198.69 |  | 0 | 0
995 | Payroll Burden | PR | 307 | 07/11/18 | 07/13/18 | CO71 | Cortes Mendiola, Victor H | 0 | 0 | 0 | 0 | 436.4 |  | 0 | 0
995 | Payroll Burden | PR | 307 | 07/11/18 | 07/13/18 | CO71 | Cortes Mendiola, Victor H | 0 | 0 | 0 | 0 | 81.83 |  | 0 | 0
995 | Payroll Burden | PR | 308 | 07/11/18 | 07/13/18 | CO73 | Cortes Sepulveda, Jose R | 0 | 0 | 0 | 0 | 255.46 |  | 0 | 0
995 | Payroll Burden | PR | 308 | 07/11/18 | 07/13/18 | CO73 | Cortes Sepulveda, Jose R | 0 | 0 | 0 | 0 | 63.86 |  | 0 | 0
995 | Payroll Burden | PR | 329 | 07/11/18 | 07/13/18 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 41.69 |  | 0 | 0
995 | Payroll Burden | PR | 329 | 07/11/18 | 07/13/18 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 104.22 |  | 0 | 0
995 | Payroll Burden | PR | 331 | 07/11/18 | 07/13/18 | JU02 | Juarez Alvarez, Oscar R | 0 | 0 | 0 | 0 | 308.68 |  | 0 | 0
995 | Payroll Burden | PR | 331 | 07/11/18 | 07/13/18 | JU02 | Juarez Alvarez, Oscar R | 0 | 0 | 0 | 0 | 102.89 |  | 0 | 0
995 | Payroll Burden | PR | 332 | 07/11/18 | 07/13/18 | JU04 | Juarez Maldonado, Oscar E | 0 | 0 | 0 | 0 | 269.65 |  | 0 | 0
995 | Payroll Burden | PR | 335 | 07/11/18 | 07/13/18 | LI49 | Lima Romero, Melvin A | 0 | 0 | 0 | 0 | 567.68 |  | 0 | 0
995 | Payroll Burden | PR | 367 | 07/11/18 | 07/13/18 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 27.72 |  | 0 | 0
995 | Payroll Burden | PR | 438 | 07/18/18 | 07/20/18 | AS10 | Ascencio, Jose L | 0 | 0 | 0 | 0 | 69.19 |  | 0 | 0
995 | Payroll Burden | PR | 438 | 07/18/18 | 07/20/18 | AS10 | Ascencio, Jose L | 0 | 0 | 0 | 0 | 461.24 |  | 0 | 0
995 | Payroll Burden | PR | 439 | 07/18/18 | 07/20/18 | BA45 | Balderas Ortiz, Ricardo I | 0 | 0 | 0 | 0 | 198.69 |  | 0 | 0
995 | Payroll Burden | PR | 439 | 07/18/18 | 07/20/18 | BA45 | Balderas Ortiz, Ricardo I | 0 | 0 | 0 | 0 | 198.69 |  | 0 | 0
995 | Payroll Burden | PR | 447 | 07/18/18 | 07/20/18 | CO71 | Cortes Mendiola, Victor H | 0 | 0 | 0 | 0 | 27.28 |  | 0 | 0
995 | Payroll Burden | PR | 447 | 07/18/18 | 07/20/18 | CO71 | Cortes Mendiola, Victor H | 0 | 0 | 0 | 0 | 436.4 |  | 0 | 0
995 | Payroll Burden | PR | 447 | 07/18/18 | 07/20/18 | CO71 | Cortes Mendiola, Victor H | 0 | 0 | 0 | 0 | 145.47 |  | 0 | 0
995 | Payroll Burden | PR | 448 | 07/18/18 | 07/20/18 | CO73 | Cortes Sepulveda, Jose R | 0 | 0 | 0 | 0 | 31.93 |  | 0 | 0
995 | Payroll Burden | PR | 448 | 07/18/18 | 07/20/18 | CO73 | Cortes Sepulveda, Jose R | 0 | 0 | 0 | 0 | 170.3 |  | 0 | 0
995 | Payroll Burden | PR | 448 | 07/18/18 | 07/20/18 | CO73 | Cortes Sepulveda, Jose R | 0 | 0 | 0 | 0 | 170.3 |  | 0 | 0
995 | Payroll Burden | PR | 472 | 07/18/18 | 07/20/18 | JU02 | Juarez Alvarez, Oscar R | 0 | 0 | 0 | 0 | 308.68 |  | 0 | 0
995 | Payroll Burden | PR | 472 | 07/18/18 | 07/20/18 | JU02 | Juarez Alvarez, Oscar R | 0 | 0 | 0 | 0 | 90.03 |  | 0 | 0
995 | Payroll Burden | PR | 472 | 07/18/18 | 07/20/18 | JU02 | Juarez Alvarez, Oscar R | 0 | 0 | 0 | 0 | 102.89 |  | 0 | 0
995 | Payroll Burden | PR | 473 | 07/18/18 | 07/20/18 | JU04 | Juarez Maldonado, Oscar E | 0 | 0 | 0 | 0 | 193.81 |  | 0 | 0
995 | Payroll Burden | PR | 473 | 07/18/18 | 07/20/18 | JU04 | Juarez Maldonado, Oscar E | 0 | 0 | 0 | 0 | 58.99 |  | 0 | 0
995 | Payroll Burden | PR | 473 | 07/18/18 | 07/20/18 | JU04 | Juarez Maldonado, Oscar E | 0 | 0 | 0 | 0 | 67.41 |  | 0 | 0
995 | Payroll Burden | PR | 476 | 07/18/18 | 07/20/18 | LI49 | Lima Romero, Melvin A | 0 | 0 | 0 | 0 | 42.58 |  | 0 | 0
995 | Payroll Burden | PR | 476 | 07/18/18 | 07/20/18 | LI49 | Lima Romero, Melvin A | 0 | 0 | 0 | 0 | 42.58 |  | 0 | 0
995 | Payroll Burden | PR | 476 | 07/18/18 | 07/20/18 | LI49 | Lima Romero, Melvin A | 0 | 0 | 0 | 0 | 227.07 |  | 0 | 0
995 | Payroll Burden | PR | 476 | 07/18/18 | 07/20/18 | LI49 | Lima Romero, Melvin A | 0 | 0 | 0 | 0 | 340.61 |  | 0 | 0
995 | Payroll Burden | PR | 507 | 07/18/18 | 07/20/18 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 27.72 |  | 0 | 0
995 | Payroll Burden | PR | 764 | 07/25/18 | 07/27/18 | AS10 | Ascencio, Jose L | 0 | 0 | 0 | 0 | 461.24 |  | 0 | 0
995 | Payroll Burden | PR | 765 | 07/25/18 | 07/27/18 | BA45 | Balderas Ortiz, Ricardo I | 0 | 0 | 0 | 0 | 496.72 |  | 0 | 0
995 | Payroll Burden | PR | 773 | 07/25/18 | 07/27/18 | CO71 | Cortes Mendiola, Victor H | 0 | 0 | 0 | 0 | 109.1 |  | 0 | 0
995 | Payroll Burden | PR | 773 | 07/25/18 | 07/27/18 | CO71 | Cortes Mendiola, Victor H | 0 | 0 | 0 | 0 | 181.84 |  | 0 | 0
995 | Payroll Burden | PR | 774 | 07/25/18 | 07/27/18 | CO73 | Cortes Sepulveda, Jose R | 0 | 0 | 0 | 0 | 170.3 |  | 0 | 0
995 | Payroll Burden | PR | 797 | 07/25/18 | 07/27/18 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 104.22 |  | 0 | 0
995 | Payroll Burden | PR | 799 | 07/25/18 | 07/27/18 | JU02 | Juarez Alvarez, Oscar R | 0 | 0 | 0 | 0 | 308.68 |  | 0 | 0
995 | Payroll Burden | PR | 800 | 07/25/18 | 07/27/18 | JU04 | Juarez Maldonado, Oscar E | 0 | 0 | 0 | 0 | 168.53 |  | 0 | 0
995 | Payroll Burden | PR | 803 | 07/25/18 | 07/27/18 | LI49 | Lima Romero, Melvin A | 0 | 0 | 0 | 0 | 113.54 |  | 0 | 0
995 | Payroll Burden | PR | 803 | 07/25/18 | 07/27/18 | LI49 | Lima Romero, Melvin A | 0 | 0 | 0 | 0 | 340.61 |  | 0 | 0
995 | Payroll Burden | PR | 835 | 07/25/18 | 07/27/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 44.35 |  | 0 | 0
995 | Payroll Burden | PR | 835 | 07/25/18 | 07/27/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 22.18 |  | 0 | 0
995 | Payroll Burden | PR | 3 | 08/01/18 | 08/03/18 | AS10 | Ascencio, Jose L | 0 | 0 | 0 | 0 | 461.24 |  | 0 | 0
995 | Payroll Burden | PR | 4 | 08/01/18 | 08/03/18 | BA45 | Balderas Ortiz, Ricardo I | 0 | 0 | 0 | 0 | 496.72 |  | 0 | 0
995 | Payroll Burden | PR | 12 | 08/01/18 | 08/03/18 | CO71 | Cortes Mendiola, Victor H | 0 | 0 | 0 | 0 | 290.94 |  | 0 | 0
995 | Payroll Burden | PR | 13 | 08/01/18 | 08/03/18 | CO73 | Cortes Sepulveda, Jose R | 0 | 0 | 0 | 0 | 85.15 |  | 0 | 0
995 | Payroll Burden | PR | 13 | 08/01/18 | 08/03/18 | CO73 | Cortes Sepulveda, Jose R | 0 | 0 | 0 | 0 | 85.15 |  | 0 | 0
995 | Payroll Burden | PR | 35 | 08/01/18 | 08/03/18 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 41.69 |  | 0 | 0
995 | Payroll Burden | PR | 37 | 08/01/18 | 08/03/18 | JU02 | Juarez Alvarez, Oscar R | 0 | 0 | 0 | 0 | 468.34 |  | 0 | 0
995 | Payroll Burden | PR | 38 | 08/01/18 | 08/03/18 | JU04 | Juarez Maldonado, Oscar E | 0 | 0 | 0 | 0 | 269.65 |  | 0 | 0
995 | Payroll Burden | PR | 41 | 08/01/18 | 08/03/18 | LI49 | Lima Romero, Melvin A | 0 | 0 | 0 | 0 | 340.61 |  | 0 | 0
995 | Payroll Burden | PR | 41 | 08/01/18 | 08/03/18 | LI49 | Lima Romero, Melvin A | 0 | 0 | 0 | 0 | 227.07 |  | 0 | 0
995 | Payroll Burden | PR | 72 | 08/01/18 | 08/03/18 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 27.72 |  | 0 | 0
995 | Payroll Burden | PR | 213 | 08/08/18 | 08/10/18 | AS10 | Ascencio, Jose L | 0 | 0 | 0 | 0 | 461.24 |  | 0 | 0
995 | Payroll Burden | PR | 214 | 08/08/18 | 08/10/18 | BA45 | Balderas Ortiz, Ricardo I | 0 | 0 | 0 | 0 | 298.03 |  | 0 | 0
995 | Payroll Burden | PR | 214 | 08/08/18 | 08/10/18 | BA45 | Balderas Ortiz, Ricardo I | 0 | 0 | 0 | 0 | 99.34 |  | 0 | 0
995 | Payroll Burden | PR | 222 | 08/08/18 | 08/10/18 | CO71 | Cortes Mendiola, Victor H | 0 | 0 | 0 | 0 | 290.94 |  | 0 | 0
995 | Payroll Burden | PR | 222 | 08/08/18 | 08/10/18 | CO71 | Cortes Mendiola, Victor H | 0 | 0 | 0 | 0 | 72.73 |  | 0 | 0
995 | Payroll Burden | PR | 222 | 08/08/18 | 08/10/18 | CO71 | Cortes Mendiola, Victor H | 0 | 0 | 0 | 0 | 72.73 |  | 0 | 0
995 | Payroll Burden | PR | 223 | 08/08/18 | 08/10/18 | CO73 | Cortes Sepulveda, Jose R | 0 | 0 | 0 | 0 | 127.73 |  | 0 | 0
995 | Payroll Burden | PR | 223 | 08/08/18 | 08/10/18 | CO73 | Cortes Sepulveda, Jose R | 0 | 0 | 0 | 0 | 42.58 |  | 0 | 0
995 | Payroll Burden | PR | 246 | 08/08/18 | 08/10/18 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 41.69 |  | 0 | 0
995 | Payroll Burden | PR | 248 | 08/08/18 | 08/10/18 | JU02 | Juarez Alvarez, Oscar R | 0 | 0 | 0 | 0 | 585.42 |  | 0 | 0
995 | Payroll Burden | PR | 249 | 08/08/18 | 08/10/18 | JU04 | Juarez Maldonado, Oscar E | 0 | 0 | 0 | 0 | 202.24 |  | 0 | 0
995 | Payroll Burden | PR | 252 | 08/08/18 | 08/10/18 | LI49 | Lima Romero, Melvin A | 0 | 0 | 0 | 0 | 340.61 |  | 0 | 0
995 | Payroll Burden | PR | 252 | 08/08/18 | 08/10/18 | LI49 | Lima Romero, Melvin A | 0 | 0 | 0 | 0 | 227.07 |  | 0 | 0
995 | Payroll Burden | PR | 255 | 08/08/18 | 08/10/18 | LU09 | Lucas Tzintzun, Rafael | 0 | 0 | 0 | 0 | 120.63 |  | 0 | 0
995 | Payroll Burden | PR | 275 | 08/08/18 | 08/10/18 | SI48 | Silva Morales, Jair J | 0 | 0 | 0 | 0 | 138.37 |  | 0 | 0
995 | Payroll Burden | PR | 283 | 08/08/18 | 08/10/18 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 27.72 |  | 0 | 0
995 | Payroll Burden | PR | 284 | 08/08/18 | 08/10/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 22.18 |  | 0 | 0
995 | Payroll Burden | PR | 481 | 08/15/18 | 08/17/18 | AS10 | Ascencio, Jose L | 0 | 0 | 0 | 0 | 461.24 |  | 0 | 0
995 | Payroll Burden | PR | 482 | 08/15/18 | 08/17/18 | BA45 | Balderas Ortiz, Ricardo I | 0 | 0 | 0 | 0 | 298.03 |  | 0 | 0
995 | Payroll Burden | PR | 482 | 08/15/18 | 08/17/18 | BA45 | Balderas Ortiz, Ricardo I | 0 | 0 | 0 | 0 | 198.69 |  | 0 | 0
995 | Payroll Burden | PR | 490 | 08/15/18 | 08/17/18 | CO71 | Cortes Mendiola, Victor H | 0 | 0 | 0 | 0 | 181.84 |  | 0 | 0
995 | Payroll Burden | PR | 490 | 08/15/18 | 08/17/18 | CO71 | Cortes Mendiola, Victor H | 0 | 0 | 0 | 0 | 472.77 |  | 0 | 0
995 | Payroll Burden | PR | 491 | 08/15/18 | 08/17/18 | CO73 | Cortes Sepulveda, Jose R | 0 | 0 | 0 | 0 | 298.03 |  | 0 | 0
995 | Payroll Burden | PR | 491 | 08/15/18 | 08/17/18 | CO73 | Cortes Sepulveda, Jose R | 0 | 0 | 0 | 0 | 85.15 |  | 0 | 0
995 | Payroll Burden | PR | 514 | 08/15/18 | 08/17/18 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 83.38 |  | 0 | 0
995 | Payroll Burden | PR | 516 | 08/15/18 | 08/17/18 | JU02 | Juarez Alvarez, Oscar R | 0 | 0 | 0 | 0 | 234.17 |  | 0 | 0
995 | Payroll Burden | PR | 519 | 08/15/18 | 08/17/18 | LI49 | Lima Romero, Melvin A | 0 | 0 | 0 | 0 | 567.68 |  | 0 | 0
995 | Payroll Burden | PR | 522 | 08/15/18 | 08/17/18 | LU09 | Lucas Tzintzun, Rafael | 0 | 0 | 0 | 0 | 180.95 |  | 0 | 0
995 | Payroll Burden | PR | 522 | 08/15/18 | 08/17/18 | LU09 | Lucas Tzintzun, Rafael | 0 | 0 | 0 | 0 | 120.63 |  | 0 | 0
995 | Payroll Burden | PR | 542 | 08/15/18 | 08/17/18 | SI48 | Silva Morales, Jair J | 0 | 0 | 0 | 0 | 425.76 |  | 0 | 0
995 | Payroll Burden | PR | 550 | 08/15/18 | 08/17/18 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 55.44 |  | 0 | 0
995 | Payroll Burden | PR | 743 | 08/22/18 | 08/24/18 | AS10 | Ascencio, Jose L | 0 | 0 | 0 | 0 | 368.99 |  | 0 | 0
995 | Payroll Burden | PR | 744 | 08/22/18 | 08/24/18 | BA45 | Balderas Ortiz, Ricardo I | 0 | 0 | 0 | 0 | 496.72 |  | 0 | 0
995 | Payroll Burden | PR | 752 | 08/22/18 | 08/24/18 | CO71 | Cortes Mendiola, Victor H | 0 | 0 | 0 | 0 | 581.87 |  | 0 | 0
995 | Payroll Burden | PR | 753 | 08/22/18 | 08/24/18 | CO73 | Cortes Sepulveda, Jose R | 0 | 0 | 0 | 0 | 308.68 |  | 0 | 0
995 | Payroll Burden | PR | 780 | 08/22/18 | 08/24/18 | LI49 | Lima Romero, Melvin A | 0 | 0 | 0 | 0 | 340.61 |  | 0 | 0
995 | Payroll Burden | PR | 783 | 08/22/18 | 08/24/18 | LU09 | Lucas Tzintzun, Rafael | 0 | 0 | 0 | 0 | 120.63 |  | 0 | 0
995 | Payroll Burden | PR | 803 | 08/22/18 | 08/24/18 | SI48 | Silva Morales, Jair J | 0 | 0 | 0 | 0 | 170.3 |  | 0 | 0
995 | Payroll Burden | PR | 803 | 08/22/18 | 08/24/18 | SI48 | Silva Morales, Jair J | 0 | 0 | 0 | 0 | 170.3 |  | 0 | 0
995 | Payroll Burden | PR | 803 | 08/22/18 | 08/24/18 | SI48 | Silva Morales, Jair J | 0 | 0 | 0 | 0 | 85.15 |  | 0 | 0
995 | Payroll Burden | PR | 811 | 08/22/18 | 08/24/18 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 138.59 |  | 0 | 0
995 | Payroll Burden | PR | 997 | 08/29/18 | 08/31/18 | AS10 | Ascencio, Jose L | 0 | 0 | 0 | 0 | 461.24 |  | 0 | 0
995 | Payroll Burden | PR | 998 | 08/29/18 | 08/31/18 | BA45 | Balderas Ortiz, Ricardo I | 0 | 0 | 0 | 0 | 397.38 |  | 0 | 0
995 | Payroll Burden | PR | 1006 | 08/29/18 | 08/31/18 | CO71 | Cortes Mendiola, Victor H | 0 | 0 | 0 | 0 | 527.32 |  | 0 | 0
995 | Payroll Burden | PR | 1006 | 08/29/18 | 08/31/18 | CO71 | Cortes Mendiola, Victor H | 0 | 0 | 0 | 0 | 54.55 |  | 0 | 0
995 | Payroll Burden | PR | 1007 | 08/29/18 | 08/31/18 | CO73 | Cortes Sepulveda, Jose R | 0 | 0 | 0 | 0 | 255.46 |  | 0 | 0
995 | Payroll Burden | PR | 1007 | 08/29/18 | 08/31/18 | CO73 | Cortes Sepulveda, Jose R | 0 | 0 | 0 | 0 | 42.58 |  | 0 | 0
995 | Payroll Burden | PR | 1031 | 08/29/18 | 08/31/18 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 20.84 |  | 0 | 0
995 | Payroll Burden | PR | 1057 | 08/29/18 | 08/31/18 | SI48 | Silva Morales, Jair J | 0 | 0 | 0 | 0 | 170.3 |  | 0 | 0
995 | Payroll Burden | PR | 1057 | 08/29/18 | 08/31/18 | SI48 | Silva Morales, Jair J | 0 | 0 | 0 | 0 | 85.15 |  | 0 | 0
995 | Payroll Burden | PR | 1057 | 08/29/18 | 08/31/18 | SI48 | Silva Morales, Jair J | 0 | 0 | 0 | 0 | 170.3 |  | 0 | 0
995 | Payroll Burden | PR | 1069 | 08/29/18 | 08/31/18 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 27.72 |  | 0 | 0
995 | Payroll Burden | PR | 38 | 09/05/18 | 09/07/18 | AS10 | Ascencio, Jose L | 0 | 0 | 0 | 0 | 368.99 |  | 0 | 0
995 | Payroll Burden | PR | 39 | 09/05/18 | 09/07/18 | BA45 | Balderas Ortiz, Ricardo I | 0 | 0 | 0 | 0 | 397.38 |  | 0 | 0
995 | Payroll Burden | PR | 47 | 09/05/18 | 09/07/18 | CO71 | Cortes Mendiola, Victor H | 0 | 0 | 0 | 0 | 54.55 |  | 0 | 0
995 | Payroll Burden | PR | 47 | 09/05/18 | 09/07/18 | CO71 | Cortes Mendiola, Victor H | 0 | 0 | 0 | 0 | 145.47 |  | 0 | 0
995 | Payroll Burden | PR | 48 | 09/05/18 | 09/07/18 | CO73 | Cortes Sepulveda, Jose R | 0 | 0 | 0 | 0 | 223.52 |  | 0 | 0
995 | Payroll Burden | PR | 48 | 09/05/18 | 09/07/18 | CO73 | Cortes Sepulveda, Jose R | 0 | 0 | 0 | 0 | 85.15 |  | 0 | 0
995 | Payroll Burden | PR | 97 | 09/05/18 | 09/07/18 | SI48 | Silva Morales, Jair J | 0 | 0 | 0 | 0 | 170.3 |  | 0 | 0
995 | Payroll Burden | PR | 97 | 09/05/18 | 09/07/18 | SI48 | Silva Morales, Jair J | 0 | 0 | 0 | 0 | 85.15 |  | 0 | 0
995 | Payroll Burden | PR | 269 | 09/12/18 | 09/14/18 | AS10 | Ascencio, Jose L | 0 | 0 | 0 | 0 | 461.24 |  | 0 | 0
995 | Payroll Burden | PR | 270 | 09/12/18 | 09/14/18 | BA45 | Balderas Ortiz, Ricardo I | 0 | 0 | 0 | 0 | 496.72 |  | 0 | 0
995 | Payroll Burden | PR | 278 | 09/12/18 | 09/14/18 | CO71 | Cortes Mendiola, Victor H | 0 | 0 | 0 | 0 | 145.47 |  | 0 | 0
995 | Payroll Burden | PR | 279 | 09/12/18 | 09/14/18 | CO73 | Cortes Sepulveda, Jose R | 0 | 0 | 0 | 0 | 170.3 |  | 0 | 0
995 | Payroll Burden | PR | 279 | 09/12/18 | 09/14/18 | CO73 | Cortes Sepulveda, Jose R | 0 | 0 | 0 | 0 | 85.15 |  | 0 | 0
995 | Payroll Burden | PR | 297 | 09/12/18 | 09/14/18 | GU78 | Gutierrez Salas, Jose | 0 | 0 | 0 | 0 | 287.39 |  | 0 | 0
995 | Payroll Burden | PR | 302 | 09/12/18 | 09/14/18 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 62.53 |  | 0 | 0
995 | Payroll Burden | PR | 302 | 09/12/18 | 09/14/18 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 83.38 |  | 0 | 0
995 | Payroll Burden | PR | 329 | 09/12/18 | 09/14/18 | SI48 | Silva Morales, Jair J | 0 | 0 | 0 | 0 | 340.61 |  | 0 | 0
995 | Payroll Burden | PR | 329 | 09/12/18 | 09/14/18 | SI48 | Silva Morales, Jair J | 0 | 0 | 0 | 0 | 85.15 |  | 0 | 0
995 | Payroll Burden | PR | 340 | 09/12/18 | 09/14/18 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 27.72 |  | 0 | 0
995 | Payroll Burden | PR | 340 | 09/12/18 | 09/14/18 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 27.72 |  | 0 | 0
995 | Payroll Burden | PR | 483 | 09/19/18 | 09/21/18 | AS10 | Ascencio, Jose L | 0 | 0 | 0 | 0 | 461.24 |  | 0 | 0
995 | Payroll Burden | PR | 484 | 09/19/18 | 09/21/18 | BA45 | Balderas Ortiz, Ricardo I | 0 | 0 | 0 | 0 | 298.03 |  | 0 | 0
995 | Payroll Burden | PR | 484 | 09/19/18 | 09/21/18 | BA45 | Balderas Ortiz, Ricardo I | 0 | 0 | 0 | 0 | 99.34 |  | 0 | 0
995 | Payroll Burden | PR | 491 | 09/19/18 | 09/21/18 | CO71 | Cortes Mendiola, Victor H | 0 | 0 | 0 | 0 | 290.94 |  | 0 | 0
995 | Payroll Burden | PR | 491 | 09/19/18 | 09/21/18 | CO71 | Cortes Mendiola, Victor H | 0 | 0 | 0 | 0 | 400.04 |  | 0 | 0
995 | Payroll Burden | PR | 492 | 09/19/18 | 09/21/18 | CO73 | Cortes Sepulveda, Jose R | 0 | 0 | 0 | 0 | 255.46 |  | 0 | 0
995 | Payroll Burden | PR | 492 | 09/19/18 | 09/21/18 | CO73 | Cortes Sepulveda, Jose R | 0 | 0 | 0 | 0 | 63.86 |  | 0 | 0
995 | Payroll Burden | PR | 510 | 09/19/18 | 09/21/18 | GU78 | Gutierrez Salas, Jose | 0 | 0 | 0 | 0 | 319.32 |  | 0 | 0
995 | Payroll Burden | PR | 515 | 09/19/18 | 09/21/18 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 145.91 |  | 0 | 0
995 | Payroll Burden | PR | 540 | 09/19/18 | 09/21/18 | SA54 | Sanders, Allen O | 0 | 0 | 0 | 0 | 78.06 |  | 0 | 0
995 | Payroll Burden | PR | 542 | 09/19/18 | 09/21/18 | SI48 | Silva Morales, Jair J | 0 | 0 | 0 | 0 | 425.76 |  | 0 | 0
995 | Payroll Burden | PR | 552 | 09/19/18 | 09/21/18 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 27.72 |  | 0 | 0
995 | Payroll Burden | PR | 667 | 09/26/18 | 09/28/18 | AS10 | Ascencio, Jose L | 0 | 0 | 0 | 0 | 92.25 |  | 0 | 0
995 | Payroll Burden | PR | 667 | 09/26/18 | 09/28/18 | AS10 | Ascencio, Jose L | 0 | 0 | 0 | 0 | 276.74 |  | 0 | 0
995 | Payroll Burden | PR | 667 | 09/26/18 | 09/28/18 | AS10 | Ascencio, Jose L | 0 | 0 | 0 | 0 | 92.25 |  | 0 | 0
995 | Payroll Burden | PR | 668 | 09/26/18 | 09/28/18 | BA45 | Balderas Ortiz, Ricardo I | 0 | 0 | 0 | 0 | 99.34 |  | 0 | 0
995 | Payroll Burden | PR | 668 | 09/26/18 | 09/28/18 | BA45 | Balderas Ortiz, Ricardo I | 0 | 0 | 0 | 0 | 298.03 |  | 0 | 0
995 | Payroll Burden | PR | 668 | 09/26/18 | 09/28/18 | BA45 | Balderas Ortiz, Ricardo I | 0 | 0 | 0 | 0 | 99.34 |  | 0 | 0
995 | Payroll Burden | PR | 676 | 09/26/18 | 09/28/18 | CO71 | Cortes Mendiola, Victor H | 0 | 0 | 0 | 0 | 527.32 |  | 0 | 0
995 | Payroll Burden | PR | 677 | 09/26/18 | 09/28/18 | CO73 | Cortes Sepulveda, Jose R | 0 | 0 | 0 | 0 | 308.68 |  | 0 | 0
995 | Payroll Burden | PR | 695 | 09/26/18 | 09/28/18 | GU78 | Gutierrez Salas, Jose | 0 | 0 | 0 | 0 | 127.73 |  | 0 | 0
995 | Payroll Burden | PR | 695 | 09/26/18 | 09/28/18 | GU78 | Gutierrez Salas, Jose | 0 | 0 | 0 | 0 | 127.73 |  | 0 | 0
995 | Payroll Burden | PR | 700 | 09/26/18 | 09/28/18 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 83.38 |  | 0 | 0
995 | Payroll Burden | PR | 700 | 09/26/18 | 09/28/18 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 20.84 |  | 0 | 0
995 | Payroll Burden | PR | 31 | 10/03/18 | 10/05/18 | AS10 | Ascencio, Jose L | 0 | 0 | 0 | 0 | 461.24 |  | 0 | 0
995 | Payroll Burden | PR | 32 | 10/03/18 | 10/05/18 | BA45 | Balderas Ortiz, Ricardo I | 0 | 0 | 0 | 0 | 496.72 |  | 0 | 0
995 | Payroll Burden | PR | 40 | 10/03/18 | 10/05/18 | CO71 | Cortes Mendiola, Victor H | 0 | 0 | 0 | 0 | 509.14 |  | 0 | 0
995 | Payroll Burden | PR | 41 | 10/03/18 | 10/05/18 | CO73 | Cortes Sepulveda, Jose R | 0 | 0 | 0 | 0 | 170.3 |  | 0 | 0
995 | Payroll Burden | PR | 59 | 10/03/18 | 10/05/18 | GU78 | Gutierrez Salas, Jose | 0 | 0 | 0 | 0 | 247.47 |  | 0 | 0
995 | Payroll Burden | PR | 102 | 10/03/18 | 10/05/18 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 83.16 |  | 0 | 0
995 | Payroll Burden | PR | 237 | 10/10/18 | 10/12/18 | BA45 | Balderas Ortiz, Ricardo I | 0 | 0 | 0 | 0 | 298.03 |  | 0 | 0
995 | Payroll Burden | PR | 245 | 10/10/18 | 10/12/18 | CO71 | Cortes Mendiola, Victor H | 0 | 0 | 0 | 0 | 145.47 |  | 0 | 0
995 | Payroll Burden | PR | 246 | 10/10/18 | 10/12/18 | CO73 | Cortes Sepulveda, Jose R | 0 | 0 | 0 | 0 | 85.15 |  | 0 | 0
995 | Payroll Burden | PR | 265 | 10/10/18 | 10/12/18 | GU78 | Gutierrez Salas, Jose | 0 | 0 | 0 | 0 | 127.73 |  | 0 | 0
995 | Payroll Burden | PR | 436 | 10/17/18 | 10/19/18 | BA45 | Balderas Ortiz, Ricardo I | 0 | 0 | 0 | 0 | 397.38 |  | 0 | 0
995 | Payroll Burden | PR | 444 | 10/17/18 | 10/19/18 | CO71 | Cortes Mendiola, Victor H | 0 | 0 | 0 | 0 | 363.67 |  | 0 | 0
995 | Payroll Burden | PR | 445 | 10/17/18 | 10/19/18 | CO73 | Cortes Sepulveda, Jose R | 0 | 0 | 0 | 0 | 212.88 |  | 0 | 0
995 | Payroll Burden | PR | 468 | 10/17/18 | 10/19/18 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 41.69 |  | 0 | 0
995 | Payroll Burden | PR | 507 | 10/17/18 | 10/19/18 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 27.72 |  | 0 | 0
995 | Payroll Burden | PR | 712 | 10/24/18 | 10/26/18 | CO71 | Cortes Mendiola, Victor H | 0 | 0 | 0 | 0 | 363.67 |  | 0 | 0
995 | Payroll Burden | PR | 713 | 10/24/18 | 10/26/18 | CO73 | Cortes Sepulveda, Jose R | 0 | 0 | 0 | 0 | 170.3 |  | 0 | 0
995 | Payroll Burden | PR | 774 | 10/24/18 | 10/26/18 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 83.16 |  | 0 | 0
995 | Payroll Burden | PR | 14 | 10/31/18 | 11/02/18 | CO71 | Cortes Mendiola, Victor H | 0 | 0 | 0 | 0 | 145.47 |  | 0 | 0
995 | Payroll Burden | PR | 14 | 10/31/18 | 11/02/18 | CO71 | Cortes Mendiola, Victor H | 0 | 0 | 0 | 0 | 181.84 |  | 0 | 0
995 | Payroll Burden | PR | 15 | 10/31/18 | 11/02/18 | CO73 | Cortes Sepulveda, Jose R | 0 | 0 | 0 | 0 | 85.15 |  | 0 | 0
995 | Payroll Burden | PR | 15 | 10/31/18 | 11/02/18 | CO73 | Cortes Sepulveda, Jose R | 0 | 0 | 0 | 0 | 106.44 |  | 0 | 0
995 | Payroll Burden | PR | 76 | 10/31/18 | 11/02/18 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 166.31 |  | 0 | 0
995 | Payroll Burden | PR | 77 | 10/31/18 | 11/02/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 22.18 |  | 0 | 0
995 | Payroll Burden | PR | 192 | 11/07/18 | 11/09/18 | CO71 | Cortes Mendiola, Victor H | 0 | 0 | 0 | 0 | 381.85 |  | 0 | 0
995 | Payroll Burden | PR | 193 | 11/07/18 | 11/09/18 | CO73 | Cortes Sepulveda, Jose R | 0 | 0 | 0 | 0 | 223.52 |  | 0 | 0
995 | Payroll Burden | PR | 257 | 11/07/18 | 11/09/18 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 194.03 |  | 0 | 0
995 | Payroll Burden | PR | 441 | 11/14/18 | 11/16/18 | CO71 | Cortes Mendiola, Victor H | 0 | 0 | 0 | 0 | 145.47 |  | 0 | 0
995 | Payroll Burden | PR | 442 | 11/14/18 | 11/16/18 | CO73 | Cortes Sepulveda, Jose R | 0 | 0 | 0 | 0 | 85.15 |  | 0 | 0
995 | Payroll Burden | PR | 450 | 11/14/18 | 11/16/18 | EL33 | Eliassen, Cory H | 0 | 0 | 0 | 0 | 81.6 |  | 0 | 0
995 | Payroll Burden | PR | 452 | 11/14/18 | 11/16/18 | FO55 | Fonseca Teruel, Eduardo | 0 | 0 | 0 | 0 | 127.73 |  | 0 | 0
995 | Payroll Burden | PR | 458 | 11/14/18 | 11/16/18 | GO51 | Gomez Reyes, Edith N | 0 | 0 | 0 | 0 | 149.02 |  | 0 | 0
995 | Payroll Burden | PR | 483 | 11/14/18 | 11/16/18 | RE91 | Reyes, Maria E | 0 | 0 | 0 | 0 | 113.54 |  | 0 | 0
995 | Payroll Burden | PR | 490 | 11/14/18 | 11/16/18 | SA54 | Sanders, Allen O | 0 | 0 | 0 | 0 | 136.6 |  | 0 | 0
995 | Payroll Burden | PR | 494 | 11/14/18 | 11/16/18 | ST02 | Stahlschmidt, John P | 0 | 0 | 0 | 0 | 56.77 |  | 0 | 0
995 | Payroll Burden | PR | 502 | 11/14/18 | 11/16/18 | YO29 | Yohannes Jr., Samson | 0 | 0 | 0 | 0 | 63.86 |  | 0 | 0
995 | Payroll Burden | PR | 513 | 11/14/18 | 11/16/18 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 83.16 |  | 0 | 0
995 | Payroll Burden | PR | 513 | 11/14/18 | 11/16/18 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 55.44 |  | 0 | 0
995 | Payroll Burden | PR | 514 | 11/14/18 | 11/16/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 22.18 |  | 0 | 0
995 | Payroll Burden | PR | 514 | 11/14/18 | 11/16/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 44.35 |  | 0 | 0
995 | Payroll Burden | PR | 637 | 11/21/18 | 11/21/18 | FO55 | Fonseca Teruel, Eduardo | 0 | 0 | 0 | 0 | 63.86 |  | 0 | 0
995 | Payroll Burden | PR | 667 | 11/21/18 | 11/21/18 | RE91 | Reyes, Maria E | 0 | 0 | 0 | 0 | 56.77 |  | 0 | 0
995 | Payroll Burden | PR | 674 | 11/21/18 | 11/21/18 | SA54 | Sanders, Allen O | 0 | 0 | 0 | 0 | 14.64 |  | 0 | 0
995 | Payroll Burden | PR | 674 | 11/21/18 | 11/21/18 | SA54 | Sanders, Allen O | 0 | 0 | 0 | 0 | 175.63 |  | 0 | 0
995 | Payroll Burden | PR | 678 | 11/21/18 | 11/21/18 | ST02 | Stahlschmidt, John P | 0 | 0 | 0 | 0 | 56.77 |  | 0 | 0
995 | Payroll Burden | PR | 686 | 11/21/18 | 11/21/18 | YO29 | Yohannes Jr., Samson | 0 | 0 | 0 | 0 | 63.86 |  | 0 | 0
995 | Payroll Burden | PR | 689 | 11/21/18 | 11/21/18 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 138.59 |  | 0 | 0
995 | Payroll Burden | PR | 887 | 11/28/18 | 11/30/18 | SA54 | Sanders, Allen O | 0 | 0 | 0 | 0 | 187.6 |  | 0 | 0
995 | Payroll Burden | PR | 900 | 11/28/18 | 11/30/18 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 55.44 |  | 0 | 0
995 | Payroll Burden | PR | 901 | 11/28/18 | 11/30/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 23.06 |  | 0 | 0
995 | Payroll Burden | PR | 63 | 12/05/18 | 12/07/18 | FO55 | Fonseca Teruel, Eduardo | 0 | 0 | 0 | 0 | 63.86 |  | 0 | 0
995 | Payroll Burden | PR | 69 | 12/05/18 | 12/07/18 | GO51 | Gomez Reyes, Edith N | 0 | 0 | 0 | 0 | 81.6 |  | 0 | 0
995 | Payroll Burden | PR | 75 | 12/05/18 | 12/07/18 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 65.19 |  | 0 | 0
995 | Payroll Burden | PR | 92 | 12/05/18 | 12/07/18 | RE91 | Reyes, Maria E | 0 | 0 | 0 | 0 | 63.86 |  | 0 | 0
995 | Payroll Burden | PR | 99 | 12/05/18 | 12/07/18 | SA54 | Sanders, Allen O | 0 | 0 | 0 | 0 | 177.18 |  | 0 | 0
995 | Payroll Burden | PR | 113 | 12/05/18 | 12/07/18 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 27.72 |  | 0 | 0
995 | Payroll Burden | PR | 268 | 12/12/18 | 12/14/18 | BA45 | Balderas Ortiz, Ricardo I | 0 | 0 | 0 | 0 | 51.45 |  | 0 | 0
995 | Payroll Burden | PR | 268 | 12/12/18 | 12/14/18 | BA45 | Balderas Ortiz, Ricardo I | 0 | 0 | 0 | 0 | 102.89 |  | 0 | 0
995 | Payroll Burden | PR | 276 | 12/12/18 | 12/14/18 | CO71 | Cortes Mendiola, Victor H | 0 | 0 | 0 | 0 | 152.56 |  | 0 | 0
995 | Payroll Burden | PR | 276 | 12/12/18 | 12/14/18 | CO71 | Cortes Mendiola, Victor H | 0 | 0 | 0 | 0 | 76.28 |  | 0 | 0
995 | Payroll Burden | PR | 277 | 12/12/18 | 12/14/18 | CO73 | Cortes Sepulveda, Jose R | 0 | 0 | 0 | 0 | 138.37 |  | 0 | 0
995 | Payroll Burden | PR | 287 | 12/12/18 | 12/14/18 | FO55 | Fonseca Teruel, Eduardo | 0 | 0 | 0 | 0 | 23.95 |  | 0 | 0
995 | Payroll Burden | PR | 287 | 12/12/18 | 12/14/18 | FO55 | Fonseca Teruel, Eduardo | 0 | 0 | 0 | 0 | 63.86 |  | 0 | 0
995 | Payroll Burden | PR | 293 | 12/12/18 | 12/14/18 | GO51 | Gomez Reyes, Edith N | 0 | 0 | 0 | 0 | 30.6 |  | 0 | 0
995 | Payroll Burden | PR | 293 | 12/12/18 | 12/14/18 | GO51 | Gomez Reyes, Edith N | 0 | 0 | 0 | 0 | 81.6 |  | 0 | 0
995 | Payroll Burden | PR | 299 | 12/12/18 | 12/14/18 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 65.19 |  | 0 | 0
995 | Payroll Burden | PR | 317 | 12/12/18 | 12/14/18 | RE91 | Reyes, Maria E | 0 | 0 | 0 | 0 | 23.95 |  | 0 | 0
995 | Payroll Burden | PR | 317 | 12/12/18 | 12/14/18 | RE91 | Reyes, Maria E | 0 | 0 | 0 | 0 | 63.86 |  | 0 | 0
995 | Payroll Burden | PR | 324 | 12/12/18 | 12/14/18 | SA54 | Sanders, Allen O | 0 | 0 | 0 | 0 | 41.69 |  | 0 | 0
995 | Payroll Burden | PR | 324 | 12/12/18 | 12/14/18 | SA54 | Sanders, Allen O | 0 | 0 | 0 | 0 | 83.38 |  | 0 | 0
995 | Payroll Burden | PR | 337 | 12/12/18 | 12/14/18 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 110.88 |  | 0 | 0
995 | Payroll Burden | PR | 509 | 12/19/18 | 12/21/18 | BA45 | Balderas Ortiz, Ricardo I | 0 | 0 | 0 | 0 | 308.68 |  | 0 | 0
995 | Payroll Burden | PR | 509 | 12/19/18 | 12/21/18 | BA45 | Balderas Ortiz, Ricardo I | 0 | 0 | 0 | 0 | 102.89 |  | 0 | 0
995 | Payroll Burden | PR | 517 | 12/19/18 | 12/21/18 | CO71 | Cortes Mendiola, Victor H | 0 | 0 | 0 | 0 | 114.42 |  | 0 | 0
995 | Payroll Burden | PR | 517 | 12/19/18 | 12/21/18 | CO71 | Cortes Mendiola, Victor H | 0 | 0 | 0 | 0 | 114.42 |  | 0 | 0
995 | Payroll Burden | PR | 518 | 12/19/18 | 12/21/18 | CO73 | Cortes Sepulveda, Jose R | 0 | 0 | 0 | 0 | 357.46 |  | 0 | 0
995 | Payroll Burden | PR | 540 | 12/19/18 | 12/21/18 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 65.19 |  | 0 | 0
995 | Payroll Burden | PR | 564 | 12/19/18 | 12/21/18 | SA54 | Sanders, Allen O | 0 | 0 | 0 | 0 | 62.53 |  | 0 | 0
995 | Payroll Burden | PR | 577 | 12/19/18 | 12/21/18 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 55.44 |  | 0 | 0
995 | Payroll Burden | PR | 578 | 12/19/18 | 12/21/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 23.06 |  | 0 | 0
995 | Payroll Burden | PR | 700 | 12/26/18 | 12/28/18 | BA45 | Balderas Ortiz, Ricardo I | 0 | 0 | 0 | 0 | 205.78 |  | 0 | 0
995 | Payroll Burden | PR | 708 | 12/26/18 | 12/28/18 | CO71 | Cortes Mendiola, Victor H | 0 | 0 | 0 | 0 | 152.56 |  | 0 | 0
995 | Payroll Burden | PR | 708 | 12/26/18 | 12/28/18 | CO71 | Cortes Mendiola, Victor H | 0 | 0 | 0 | 0 | 457.69 |  | 0 | 0
995 | Payroll Burden | PR | 709 | 12/26/18 | 12/28/18 | CO73 | Cortes Sepulveda, Jose R | 0 | 0 | 0 | 0 | 126.84 |  | 0 | 0
995 | Payroll Burden | PR | 731 | 12/26/18 | 12/28/18 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 65.19 |  | 0 | 0
995 | Payroll Burden | PR | 755 | 12/26/18 | 12/28/18 | SA54 | Sanders, Allen O | 0 | 0 | 0 | 0 | 83.38 |  | 0 | 0
995 | Payroll Burden | PR | 768 | 12/26/18 | 12/28/18 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 27.72 |  | 0 | 0
995 | Payroll Burden | PR | 769 | 12/26/18 | 12/28/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 23.06 |  | 0 | 0
995 | Payroll Burden | PR | 5 | 01/02/19 | 01/04/19 | BA45 | Balderas Ortiz, Ricardo I | 0 | 0 | 0 | 0 | 180.06 |  | 0 | 0
995 | Payroll Burden | PR | 5 | 01/02/19 | 01/04/19 | BA45 | Balderas Ortiz, Ricardo I | 0 | 0 | 0 | 0 | 25.72 |  | 0 | 0
995 | Payroll Burden | PR | 5 | 01/02/19 | 01/04/19 | BA45 | Balderas Ortiz, Ricardo I | 0 | 0 | 0 | 0 | 102.89 |  | 0 | 0
995 | Payroll Burden | PR | 13 | 01/02/19 | 01/04/19 | CO71 | Cortes Mendiola, Victor H | 0 | 0 | 0 | 0 | 152.56 |  | 0 | 0
995 | Payroll Burden | PR | 13 | 01/02/19 | 01/04/19 | CO71 | Cortes Mendiola, Victor H | 0 | 0 | 0 | 0 | 305.13 |  | 0 | 0
995 | Payroll Burden | PR | 14 | 01/02/19 | 01/04/19 | CO73 | Cortes Sepulveda, Jose R | 0 | 0 | 0 | 0 | 161.43 |  | 0 | 0
995 | Payroll Burden | PR | 14 | 01/02/19 | 01/04/19 | CO73 | Cortes Sepulveda, Jose R | 0 | 0 | 0 | 0 | 23.06 |  | 0 | 0
995 | Payroll Burden | PR | 14 | 01/02/19 | 01/04/19 | CO73 | Cortes Sepulveda, Jose R | 0 | 0 | 0 | 0 | 92.25 |  | 0 | 0
995 | Payroll Burden | PR | 23 | 01/02/19 | 01/04/19 | FO55 | Fonseca Teruel, Eduardo | 0 | 0 | 0 | 0 | 63.86 |  | 0 | 0
995 | Payroll Burden | PR | 58 | 01/02/19 | 01/04/19 | SA54 | Sanders, Allen O | 0 | 0 | 0 | 0 | 20.84 |  | 0 | 0
995 | Payroll Burden | PR | 62 | 01/02/19 | 01/04/19 | ST02 | Stahlschmidt, John P | 0 | 0 | 0 | 0 | 60.32 |  | 0 | 0
995 | Payroll Burden | PR | 72 | 01/02/19 | 01/04/19 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 27.72 |  | 0 | 0
995 | Payroll Burden | PR | 213 | 01/09/19 | 01/11/19 | BA45 | Balderas Ortiz, Ricardo I | 0 | 0 | 0 | 0 | 321.54 |  | 0 | 0
995 | Payroll Burden | PR | 213 | 01/09/19 | 01/11/19 | BA45 | Balderas Ortiz, Ricardo I | 0 | 0 | 0 | 0 | 38.58 |  | 0 | 0
995 | Payroll Burden | PR | 221 | 01/09/19 | 01/11/19 | CO71 | Cortes Mendiola, Victor H | 0 | 0 | 0 | 0 | 648.4 |  | 0 | 0
995 | Payroll Burden | PR | 221 | 01/09/19 | 01/11/19 | CO71 | Cortes Mendiola, Victor H | 0 | 0 | 0 | 0 | 57.21 |  | 0 | 0
995 | Payroll Burden | PR | 222 | 01/09/19 | 01/11/19 | CO73 | Cortes Sepulveda, Jose R | 0 | 0 | 0 | 0 | 207.56 |  | 0 | 0
995 | Payroll Burden | PR | 222 | 01/09/19 | 01/11/19 | CO73 | Cortes Sepulveda, Jose R | 0 | 0 | 0 | 0 | 115.31 |  | 0 | 0
995 | Payroll Burden | PR | 231 | 01/09/19 | 01/11/19 | FO55 | Fonseca Teruel, Eduardo | 0 | 0 | 0 | 0 | 127.73 |  | 0 | 0
995 | Payroll Burden | PR | 244 | 01/09/19 | 01/11/19 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 21.73 |  | 0 | 0
995 | Payroll Burden | PR | 268 | 01/09/19 | 01/11/19 | SA54 | Sanders, Allen O | 0 | 0 | 0 | 0 | 229.29 |  | 0 | 0
995 | Payroll Burden | PR | 272 | 01/09/19 | 01/11/19 | ST02 | Stahlschmidt, John P | 0 | 0 | 0 | 0 | 120.63 |  | 0 | 0
995 | Payroll Burden | PR | 281 | 01/09/19 | 01/11/19 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 55.44 |  | 0 | 0
995 | Payroll Burden | PR | 467 | 01/16/19 | 01/18/19 | BA45 | Balderas Ortiz, Ricardo I | 0 | 0 | 0 | 0 | 308.68 |  | 0 | 0
995 | Payroll Burden | PR | 467 | 01/16/19 | 01/18/19 | BA45 | Balderas Ortiz, Ricardo I | 0 | 0 | 0 | 0 | 102.89 |  | 0 | 0
995 | Payroll Burden | PR | 467 | 01/16/19 | 01/18/19 | BA45 | Balderas Ortiz, Ricardo I | 0 | 0 | 0 | 0 | 102.89 |  | 0 | 0
995 | Payroll Burden | PR | 476 | 01/16/19 | 01/18/19 | CO71 | Cortes Mendiola, Victor H | 0 | 0 | 0 | 0 | 362.34 |  | 0 | 0
995 | Payroll Burden | PR | 476 | 01/16/19 | 01/18/19 | CO71 | Cortes Mendiola, Victor H | 0 | 0 | 0 | 0 | 152.56 |  | 0 | 0
995 | Payroll Burden | PR | 477 | 01/16/19 | 01/18/19 | CO73 | Cortes Sepulveda, Jose R | 0 | 0 | 0 | 0 | 196.03 |  | 0 | 0
995 | Payroll Burden | PR | 477 | 01/16/19 | 01/18/19 | CO73 | Cortes Sepulveda, Jose R | 0 | 0 | 0 | 0 | 57.66 |  | 0 | 0
995 | Payroll Burden | PR | 477 | 01/16/19 | 01/18/19 | CO73 | Cortes Sepulveda, Jose R | 0 | 0 | 0 | 0 | 207.56 |  | 0 | 0
995 | Payroll Burden | PR | 484 | 01/16/19 | 01/18/19 | EL33 | Eliassen, Cory H | 0 | 0 | 0 | 0 | 166.31 |  | 0 | 0
995 | Payroll Burden | PR | 484 | 01/16/19 | 01/18/19 | EL33 | Eliassen, Cory H | 0 | 0 | 0 | 0 | 177.4 |  | 0 | 0
995 | Payroll Burden | PR | 492 | 01/16/19 | 01/18/19 | GO51 | Gomez Reyes, Edith N | 0 | 0 | 0 | 0 | 153.01 |  | 0 | 0
995 | Payroll Burden | PR | 492 | 01/16/19 | 01/18/19 | GO51 | Gomez Reyes, Edith N | 0 | 0 | 0 | 0 | 81.6 |  | 0 | 0
995 | Payroll Burden | PR | 516 | 01/16/19 | 01/18/19 | RE91 | Reyes, Maria E | 0 | 0 | 0 | 0 | 119.75 |  | 0 | 0
995 | Payroll Burden | PR | 516 | 01/16/19 | 01/18/19 | RE91 | Reyes, Maria E | 0 | 0 | 0 | 0 | 63.86 |  | 0 | 0
995 | Payroll Burden | PR | 523 | 01/16/19 | 01/18/19 | SA54 | Sanders, Allen O | 0 | 0 | 0 | 0 | 234.5 |  | 0 | 0
995 | Payroll Burden | PR | 523 | 01/16/19 | 01/18/19 | SA54 | Sanders, Allen O | 0 | 0 | 0 | 0 | 250.13 |  | 0 | 0
995 | Payroll Burden | PR | 530 | 01/16/19 | 01/18/19 | TR60 | Trower-Kelly, Fidel D | 0 | 0 | 0 | 0 | 127.73 |  | 0 | 0
995 | Payroll Burden | PR | 530 | 01/16/19 | 01/18/19 | TR60 | Trower-Kelly, Fidel D | 0 | 0 | 0 | 0 | 170.3 |  | 0 | 0
995 | Payroll Burden | PR | 542 | 01/16/19 | 01/18/19 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 55.44 |  | 0 | 0
995 | Payroll Burden | PR | 543 | 01/16/19 | 01/18/19 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 23.06 |  | 0 | 0
995 | Payroll Burden | PR | 725 | 01/23/19 | 01/25/19 | CO71 | Cortes Mendiola, Victor H | 0 | 0 | 0 | 0 | 57.21 |  | 0 | 0
995 | Payroll Burden | PR | 725 | 01/23/19 | 01/25/19 | CO71 | Cortes Mendiola, Victor H | 0 | 0 | 0 | 0 | 19.07 |  | 0 | 0
995 | Payroll Burden | PR | 733 | 01/23/19 | 01/25/19 | EL33 | Eliassen, Cory H | 0 | 0 | 0 | 0 | 133.05 |  | 0 | 0
995 | Payroll Burden | PR | 733 | 01/23/19 | 01/25/19 | EL33 | Eliassen, Cory H | 0 | 0 | 0 | 0 | 266.1 |  | 0 | 0
995 | Payroll Burden | PR | 735 | 01/23/19 | 01/25/19 | FO55 | Fonseca Teruel, Eduardo | 0 | 0 | 0 | 0 | 47.9 |  | 0 | 0
995 | Payroll Burden | PR | 741 | 01/23/19 | 01/25/19 | GO51 | Gomez Reyes, Edith N | 0 | 0 | 0 | 0 | 142.81 |  | 0 | 0
995 | Payroll Burden | PR | 748 | 01/23/19 | 01/25/19 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 43.46 |  | 0 | 0
995 | Payroll Burden | PR | 756 | 01/23/19 | 01/25/19 | MC09 | McCabe, Thomas C | 0 | 0 | 0 | 0 | 21.95 |  | 0 | 0
995 | Payroll Burden | PR | 756 | 01/23/19 | 01/25/19 | MC09 | McCabe, Thomas C | 0 | 0 | 0 | 0 | 73.18 |  | 0 | 0
995 | Payroll Burden | PR | 765 | 01/23/19 | 01/25/19 | RE91 | Reyes, Maria E | 0 | 0 | 0 | 0 | 89.81 |  | 0 | 0
995 | Payroll Burden | PR | 765 | 01/23/19 | 01/25/19 | RE91 | Reyes, Maria E | 0 | 0 | 0 | 0 | 127.73 |  | 0 | 0
995 | Payroll Burden | PR | 772 | 01/23/19 | 01/25/19 | SA54 | Sanders, Allen O | 0 | 0 | 0 | 0 | 171.97 |  | 0 | 0
995 | Payroll Burden | PR | 772 | 01/23/19 | 01/25/19 | SA54 | Sanders, Allen O | 0 | 0 | 0 | 0 | 145.91 |  | 0 | 0
995 | Payroll Burden | PR | 778 | 01/23/19 | 01/25/19 | TA96 | Taylor, Evan R | 0 | 0 | 0 | 0 | 138.37 |  | 0 | 0
995 | Payroll Burden | PR | 779 | 01/23/19 | 01/25/19 | TR60 | Trower-Kelly, Fidel D | 0 | 0 | 0 | 0 | 85.15 |  | 0 | 0
995 | Payroll Burden | PR | 779 | 01/23/19 | 01/25/19 | TR60 | Trower-Kelly, Fidel D | 0 | 0 | 0 | 0 | 227.07 |  | 0 | 0
995 | Payroll Burden | PR | 786 | 01/23/19 | 01/25/19 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 55.44 |  | 0 | 0
995 | Payroll Burden | PR | 13 | 01/30/19 | 02/01/19 | CO71 | Cortes Mendiola, Victor H | 0 | 0 | 0 | 0 | 57.21 |  | 0 | 0
995 | Payroll Burden | PR | 21 | 01/30/19 | 02/01/19 | EL33 | Eliassen, Cory H | 0 | 0 | 0 | 0 | 158 |  | 0 | 0
995 | Payroll Burden | PR | 21 | 01/30/19 | 02/01/19 | EL33 | Eliassen, Cory H | 0 | 0 | 0 | 0 | 388.06 |  | 0 | 0
995 | Payroll Burden | PR | 23 | 01/30/19 | 02/01/19 | FO55 | Fonseca Teruel, Eduardo | 0 | 0 | 0 | 0 | 95.8 |  | 0 | 0
995 | Payroll Burden | PR | 29 | 01/30/19 | 02/01/19 | GO51 | Gomez Reyes, Edith N | 0 | 0 | 0 | 0 | 137.71 |  | 0 | 0
995 | Payroll Burden | PR | 29 | 01/30/19 | 02/01/19 | GO51 | Gomez Reyes, Edith N | 0 | 0 | 0 | 0 | 163.21 |  | 0 | 0
995 | Payroll Burden | PR | 36 | 01/30/19 | 02/01/19 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 43.46 |  | 0 | 0
995 | Payroll Burden | PR | 44 | 01/30/19 | 02/01/19 | MC09 | McCabe, Thomas C | 0 | 0 | 0 | 0 | 117.08 |  | 0 | 0
995 | Payroll Burden | PR | 51 | 01/30/19 | 02/01/19 | RE91 | Reyes, Maria E | 0 | 0 | 0 | 0 | 107.77 |  | 0 | 0
995 | Payroll Burden | PR | 51 | 01/30/19 | 02/01/19 | RE91 | Reyes, Maria E | 0 | 0 | 0 | 0 | 127.73 |  | 0 | 0
995 | Payroll Burden | PR | 57 | 01/30/19 | 02/01/19 | SA54 | Sanders, Allen O | 0 | 0 | 0 | 0 | 281.4 |  | 0 | 0
995 | Payroll Burden | PR | 57 | 01/30/19 | 02/01/19 | SA54 | Sanders, Allen O | 0 | 0 | 0 | 0 | 270.98 |  | 0 | 0
995 | Payroll Burden | PR | 61 | 01/30/19 | 02/01/19 | ST02 | Stahlschmidt, John P | 0 | 0 | 0 | 0 | 90.47 |  | 0 | 0
995 | Payroll Burden | PR | 64 | 01/30/19 | 02/01/19 | TR60 | Trower-Kelly, Fidel D | 0 | 0 | 0 | 0 | 101.12 |  | 0 | 0
995 | Payroll Burden | PR | 64 | 01/30/19 | 02/01/19 | TR60 | Trower-Kelly, Fidel D | 0 | 0 | 0 | 0 | 248.36 |  | 0 | 0
995 | Payroll Burden | PR | 70 | 01/30/19 | 02/01/19 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 110.88 |  | 0 | 0
995 | Payroll Burden | PR | 168 | 02/06/19 | 02/08/19 | CO71 | Cortes Mendiola, Victor H | 0 | 0 | 0 | 0 | 95.35 |  | 0 | 0
995 | Payroll Burden | PR | 176 | 02/06/19 | 02/08/19 | EL33 | Eliassen, Cory H | 0 | 0 | 0 | 0 | 232.84 |  | 0 | 0
995 | Payroll Burden | PR | 213 | 02/06/19 | 02/08/19 | SA54 | Sanders, Allen O | 0 | 0 | 0 | 0 | 104.22 |  | 0 | 0
995 | Payroll Burden | PR | 220 | 02/06/19 | 02/08/19 | TR60 | Trower-Kelly, Fidel D | 0 | 0 | 0 | 0 | 149.02 |  | 0 | 0
995 | Payroll Burden | PR | 226 | 02/06/19 | 02/08/19 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 55.44 |  | 0 | 0
995 | Payroll Burden | PR | 330 | 02/13/19 | 02/15/19 | CO71 | Cortes Mendiola, Victor H | 0 | 0 | 0 | 0 | 95.35 |  | 0 | 0
995 | Payroll Burden | PR | 338 | 02/13/19 | 02/15/19 | EL33 | Eliassen, Cory H | 0 | 0 | 0 | 0 | 210.66 |  | 0 | 0
995 | Payroll Burden | PR | 375 | 02/13/19 | 02/15/19 | SA54 | Sanders, Allen O | 0 | 0 | 0 | 0 | 93.8 |  | 0 | 0
995 | Payroll Burden | PR | 382 | 02/13/19 | 02/15/19 | TR60 | Trower-Kelly, Fidel D | 0 | 0 | 0 | 0 | 134.82 |  | 0 | 0
995 | Payroll Burden | PR | 388 | 02/13/19 | 02/15/19 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 55.44 |  | 0 | 0
995 | Payroll Burden | PR | 580 | 02/20/19 | 02/22/19 | BA45 | Balderas Ortiz, Ricardo I | 0 | 0 | 0 | 0 | 90.03 |  | 0 | 0
995 | Payroll Burden | PR | 586 | 02/20/19 | 02/22/19 | CH20 | Chevez, Herson G | 0 | 0 | 0 | 0 | 62.09 |  | 0 | 0
995 | Payroll Burden | PR | 588 | 02/20/19 | 02/22/19 | CO71 | Cortes Mendiola, Victor H | 0 | 0 | 0 | 0 | 133.49 |  | 0 | 0
995 | Payroll Burden | PR | 596 | 02/20/19 | 02/22/19 | EL33 | Eliassen, Cory H | 0 | 0 | 0 | 0 | 33.26 |  | 0 | 0
995 | Payroll Burden | PR | 596 | 02/20/19 | 02/22/19 | EL33 | Eliassen, Cory H | 0 | 0 | 0 | 0 | 144.14 |  | 0 | 0
995 | Payroll Burden | PR | 634 | 02/20/19 | 02/22/19 | SA54 | Sanders, Allen O | 0 | 0 | 0 | 0 | 62.53 |  | 0 | 0
995 | Payroll Burden | PR | 641 | 02/20/19 | 02/22/19 | TR60 | Trower-Kelly, Fidel D | 0 | 0 | 0 | 0 | 21.29 |  | 0 | 0
995 | Payroll Burden | PR | 641 | 02/20/19 | 02/22/19 | TR60 | Trower-Kelly, Fidel D | 0 | 0 | 0 | 0 | 35.48 |  | 0 | 0
995 | Payroll Burden | PR | 647 | 02/20/19 | 02/22/19 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 55.44 |  | 0 | 0
995 | Payroll Burden | PR | 13 | 02/27/19 | 03/01/19 | CO71 | Cortes Mendiola, Victor H | 0 | 0 | 0 | 0 | 76.28 |  | 0 | 0
995 | Payroll Burden | PR | 13 | 02/27/19 | 03/01/19 | CO71 | Cortes Mendiola, Victor H | 0 | 0 | 0 | 0 | 19.07 |  | 0 | 0
995 | Payroll Burden | PR | 13 | 02/27/19 | 03/01/19 | CO71 | Cortes Mendiola, Victor H | 0 | 0 | 0 | 0 | 19.07 |  | 0 | 0
995 | Payroll Burden | PR | 13 | 02/27/19 | 03/01/19 | CO71 | Cortes Mendiola, Victor H | 0 | 0 | 0 | 0 | 38.14 |  | 0 | 0
995 | Payroll Burden | PR | 22 | 02/27/19 | 03/01/19 | EL33 | Eliassen, Cory H | 0 | 0 | 0 | 0 | 99.79 |  | 0 | 0
995 | Payroll Burden | PR | 38 | 02/27/19 | 03/01/19 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 86.93 |  | 0 | 0
995 | Payroll Burden | PR | 61 | 02/27/19 | 03/01/19 | SA54 | Sanders, Allen O | 0 | 0 | 0 | 0 | 20.84 |  | 0 | 0
995 | Payroll Burden | PR | 74 | 02/27/19 | 03/01/19 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 83.16 |  | 0 | 0
995 | Payroll Burden | PR | 255 | 03/06/19 | 03/08/19 | CO71 | Cortes Mendiola, Victor H | 0 | 0 | 0 | 0 | 76.28 |  | 0 | 0
995 | Payroll Burden | PR | 255 | 03/06/19 | 03/08/19 | CO71 | Cortes Mendiola, Victor H | 0 | 0 | 0 | 0 | 57.21 |  | 0 | 0
995 | Payroll Burden | PR | 264 | 03/06/19 | 03/08/19 | EL33 | Eliassen, Cory H | 0 | 0 | 0 | 0 | 33.26 |  | 0 | 0
995 | Payroll Burden | PR | 300 | 03/06/19 | 03/08/19 | SA54 | Sanders, Allen O | 0 | 0 | 0 | 0 | 41.69 |  | 0 | 0
995 | Payroll Burden | PR | 307 | 03/06/19 | 03/08/19 | TR60 | Trower-Kelly, Fidel D | 0 | 0 | 0 | 0 | 21.29 |  | 0 | 0
995 | Payroll Burden | PR | 314 | 03/06/19 | 03/08/19 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 55.44 |  | 0 | 0
995 | Payroll Burden | PR | 502 | 03/13/19 | 03/15/19 | CO71 | Cortes Mendiola, Victor H | 0 | 0 | 0 | 0 | 38.14 |  | 0 | 0
995 | Payroll Burden | PR | 511 | 03/13/19 | 03/15/19 | EL33 | Eliassen, Cory H | 0 | 0 | 0 | 0 | 77.61 |  | 0 | 0
995 | Payroll Burden | PR | 525 | 03/13/19 | 03/15/19 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 65.19 |  | 0 | 0
995 | Payroll Burden | PR | 525 | 03/13/19 | 03/15/19 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 32.6 |  | 0 | 0
995 | Payroll Burden | PR | 547 | 03/13/19 | 03/15/19 | SA54 | Sanders, Allen O | 0 | 0 | 0 | 0 | 62.53 |  | 0 | 0
995 | Payroll Burden | PR | 555 | 03/13/19 | 03/15/19 | TR60 | Trower-Kelly, Fidel D | 0 | 0 | 0 | 0 | 28.38 |  | 0 | 0
995 | Payroll Burden | PR | 562 | 03/13/19 | 03/15/19 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 110.88 |  | 0 | 0
995 | Payroll Burden | PR | 714 | 03/20/19 | 03/22/19 | CH20 | Chevez, Herson G | 0 | 0 | 0 | 0 | 53.22 |  | 0 | 0
995 | Payroll Burden | PR | 714 | 03/20/19 | 03/22/19 | CH20 | Chevez, Herson G | 0 | 0 | 0 | 0 | 26.61 |  | 0 | 0
995 | Payroll Burden | PR | 716 | 03/20/19 | 03/22/19 | CO71 | Cortes Mendiola, Victor H | 0 | 0 | 0 | 0 | 114.42 |  | 0 | 0
995 | Payroll Burden | PR | 716 | 03/20/19 | 03/22/19 | CO71 | Cortes Mendiola, Victor H | 0 | 0 | 0 | 0 | 57.21 |  | 0 | 0
995 | Payroll Burden | PR | 725 | 03/20/19 | 03/22/19 | EL33 | Eliassen, Cory H | 0 | 0 | 0 | 0 | 44.35 |  | 0 | 0
995 | Payroll Burden | PR | 739 | 03/20/19 | 03/22/19 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 86.93 |  | 0 | 0
995 | Payroll Burden | PR | 760 | 03/20/19 | 03/22/19 | SA54 | Sanders, Allen O | 0 | 0 | 0 | 0 | 62.53 |  | 0 | 0
995 | Payroll Burden | PR | 769 | 03/20/19 | 03/22/19 | TR60 | Trower-Kelly, Fidel D | 0 | 0 | 0 | 0 | 28.38 |  | 0 | 0
995 | Payroll Burden | PR | 780 | 03/20/19 | 03/22/19 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 86.93 |  | 0 | 0
995 | Payroll Burden | PR | 781 | 03/20/19 | 03/22/19 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | -86.93 |  | 0 | 0
995 | Payroll Burden | PR | 927 | 03/27/19 | 03/29/19 | CO71 | Cortes Mendiola, Victor H | 0 | 0 | 0 | 0 | 57.21 |  | 0 | 0
995 | Payroll Burden | PR | 936 | 03/27/19 | 03/29/19 | EL33 | Eliassen, Cory H | 0 | 0 | 0 | 0 | 33.26 |  | 0 | 0
995 | Payroll Burden | PR | 951 | 03/27/19 | 03/29/19 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 32.6 |  | 0 | 0
995 | Payroll Burden | PR | 951 | 03/27/19 | 03/29/19 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 86.93 |  | 0 | 0
995 | Payroll Burden | PR | 972 | 03/27/19 | 03/29/19 | SA54 | Sanders, Allen O | 0 | 0 | 0 | 0 | 62.53 |  | 0 | 0
995 | Payroll Burden | PR | 989 | 03/27/19 | 03/29/19 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 27.72 |  | 0 | 0
995 | Payroll Burden | PR | 85 | 04/03/19 | 04/05/19 | BE54 | Benites Portillo, Marvin E | 0 | 0 | 0 | 0 | 31.93 |  | 0 | 0
995 | Payroll Burden | PR | 85 | 04/03/19 | 04/05/19 | BE54 | Benites Portillo, Marvin E | 0 | 0 | 0 | 0 | 53.22 |  | 0 | 0
995 | Payroll Burden | PR | 89 | 04/03/19 | 04/05/19 | CO71 | Cortes Mendiola, Victor H | 0 | 0 | 0 | 0 | 57.21 |  | 0 | 0
995 | Payroll Burden | PR | 89 | 04/03/19 | 04/05/19 | CO71 | Cortes Mendiola, Victor H | 0 | 0 | 0 | 0 | 95.35 |  | 0 | 0
995 | Payroll Burden | PR | 151 | 04/03/19 | 04/05/19 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 83.16 |  | 0 | 0
995 | Payroll Burden | PR | 397 | 04/10/19 | 04/12/19 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 27.72 |  | 0 | 0
995 | Payroll Burden | PR | 530 | 04/17/19 | 04/19/19 | CO71 | Cortes Mendiola, Victor H | 0 | 0 | 0 | 0 | 40.8 |  | 0 | 0
995 | Payroll Burden | PR | 578 | 04/17/19 | 04/19/19 | SA54 | Sanders, Allen O | 0 | 0 | 0 | 0 | 43.46 |  | 0 | 0
995 | Payroll Burden | PR | 596 | 04/17/19 | 04/19/19 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 27.72 |  | 0 | 0
995 | Payroll Burden | PR | 750 | 04/24/19 | 04/26/19 | CO71 | Cortes Mendiola, Victor H | 0 | 0 | 0 | 0 | 61.2 |  | 0 | 0
995 | Payroll Burden | PR | 797 | 04/24/19 | 04/26/19 | SA54 | Sanders, Allen O | 0 | 0 | 0 | 0 | 97.79 |  | 0 | 0
995 | Payroll Burden | PR | 812 | 04/24/19 | 04/26/19 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 55.44 |  | 0 | 0
995 | Payroll Burden | PR | 66 | 05/01/19 | 05/03/19 | SA54 | Sanders, Allen O | 0 | 0 | 0 | 0 | 43.46 |  | 0 | 0
995 | Payroll Burden | PR | 81 | 05/01/19 | 05/03/19 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 27.72 |  | 0 | 0
995 | Payroll Burden | PR | 179 | 05/08/19 | 05/10/19 | EL33 | Eliassen, Cory H | 0 | 0 | 0 | 0 | 8.98 |  | 0 | 0
995 | Payroll Burden | PR | 179 | 05/08/19 | 05/10/19 | EL33 | Eliassen, Cory H | 0 | 0 | 0 | 0 | 59.87 |  | 0 | 0
995 | Payroll Burden | PR | 219 | 05/08/19 | 05/10/19 | SA54 | Sanders, Allen O | 0 | 0 | 0 | 0 | 108.66 |  | 0 | 0
995 | Payroll Burden | PR | 427 | 05/15/19 | 05/17/19 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 88.7 |  | 0 | 0
995 | Payroll Burden | PR | 427 | 05/15/19 | 05/17/19 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 44.35 |  | 0 | 0
995 | Payroll Burden | PR | 451 | 05/15/19 | 05/17/19 | SA54 | Sanders, Allen O | 0 | 0 | 0 | 0 | 195.58 |  | 0 | 0
995 | Payroll Burden | PR | 467 | 05/15/19 | 05/17/19 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 27.72 |  | 0 | 0
995 | Payroll Burden | PR | 663 | 05/22/19 | 05/24/19 | SA54 | Sanders, Allen O | 0 | 0 | 0 | 0 | 43.46 |  | 0 | 0
998 | Payroll Taxes | PR | 34 | 08/02/17 | 08/04/17 | GE70 | Gerard, Jordan E | 0 | 0 | 0 | 0 | 7.34 |  | 0 | 0
998 | Payroll Taxes | PR | 65 | 08/02/17 | 08/04/17 | SA54 | Sanders, Allen O | 0 | 0 | 0 | 0 | 11.93 |  | 0 | 0
998 | Payroll Taxes | PR | 492 | 08/23/17 | 08/25/17 | SA54 | Sanders, Allen O | 0 | 0 | 0 | 0 | 16.41 |  | 0 | 0
998 | Payroll Taxes | PR | 492 | 08/23/17 | 08/25/17 | SA54 | Sanders, Allen O | 0 | 0 | 0 | 0 | 5.97 |  | 0 | 0
998 | Payroll Taxes | PR | 358 | 09/13/17 | 09/15/17 | WA35 | Waites, Thaddeus Z | 0 | 0 | 0 | 0 | 6.12 |  | 0 | 0
998 | Payroll Taxes | PR | 362 | 09/13/17 | 09/15/17 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 3.6 |  | 0 | 0
998 | Payroll Taxes | PR | 544 | 09/20/17 | 09/22/17 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 34.43 |  | 0 | 0
998 | Payroll Taxes | PR | 544 | 09/20/17 | 09/22/17 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 7.65 |  | 0 | 0
998 | Payroll Taxes | PR | 545 | 09/20/17 | 09/22/17 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 3.6 |  | 0 | 0
998 | Payroll Taxes | PR | 545 | 09/20/17 | 09/22/17 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 3.6 |  | 0 | 0
998 | Payroll Taxes | PR | 762 | 09/27/17 | 09/29/17 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 3.6 |  | 0 | 0
998 | Payroll Taxes | PR | 67 | 10/04/17 | 10/06/17 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 7.65 |  | 0 | 0
998 | Payroll Taxes | PR | 67 | 10/04/17 | 10/06/17 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 3.83 |  | 0 | 0
998 | Payroll Taxes | PR | 68 | 10/04/17 | 10/06/17 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 7.19 |  | 0 | 0
998 | Payroll Taxes | PR | 225 | 10/11/17 | 10/13/17 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 15.3 |  | 0 | 0
998 | Payroll Taxes | PR | 226 | 10/11/17 | 10/13/17 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 3.6 |  | 0 | 0
998 | Payroll Taxes | PR | 226 | 10/11/17 | 10/13/17 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 3.6 |  | 0 | 0
998 | Payroll Taxes | PR | 350 | 10/18/17 | 10/20/17 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 7.65 |  | 0 | 0
998 | Payroll Taxes | PR | 547 | 10/25/17 | 10/27/17 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 3.83 |  | 0 | 0
998 | Payroll Taxes | PR | 212 | 11/08/17 | 11/10/17 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 38.25 |  | 0 | 0
998 | Payroll Taxes | PR | 213 | 11/08/17 | 11/10/17 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 17.98 |  | 0 | 0
998 | Payroll Taxes | PR | 213 | 11/08/17 | 11/10/17 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 7.19 |  | 0 | 0
998 | Payroll Taxes | PR | 225 | 11/08/17 | 11/10/17 | WA35 | Waites, Thaddeus Z | 0 | 0 | 0 | 0 | -6.12 |  | 0 | 0
998 | Payroll Taxes | PR | 296 | 11/15/17 | 11/17/17 | CO71 | Cortes Mendiola, Victor H | 0 | 0 | 0 | 0 | 24.48 |  | 0 | 0
998 | Payroll Taxes | PR | 343 | 11/15/17 | 11/17/17 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 3.83 |  | 0 | 0
998 | Payroll Taxes | PR | 344 | 11/15/17 | 11/17/17 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 12.58 |  | 0 | 0
998 | Payroll Taxes | PR | 344 | 11/15/17 | 11/17/17 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 10.79 |  | 0 | 0
998 | Payroll Taxes | PR | 438 | 11/22/17 | 11/22/17 | CO71 | Cortes Mendiola, Victor H | 0 | 0 | 0 | 0 | 79.56 |  | 0 | 0
998 | Payroll Taxes | PR | 439 | 11/22/17 | 11/22/17 | CO73 | Cortes Sepulveda, Jose R | 0 | 0 | 0 | 0 | 45.75 |  | 0 | 0
998 | Payroll Taxes | PR | 457 | 11/22/17 | 11/22/17 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 63.69 |  | 0 | 0
998 | Payroll Taxes | PR | 489 | 11/22/17 | 11/22/17 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 42.08 |  | 0 | 0
998 | Payroll Taxes | PR | 489 | 11/22/17 | 11/22/17 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 7.65 |  | 0 | 0
998 | Payroll Taxes | PR | 490 | 11/22/17 | 11/22/17 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 3.6 |  | 0 | 0
998 | Payroll Taxes | PR | 490 | 11/22/17 | 11/22/17 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 7.19 |  | 0 | 0
998 | Payroll Taxes | PR | 15 | 11/29/17 | 12/01/17 | CO71 | Cortes Mendiola, Victor H | 0 | 0 | 0 | 0 | 36.72 |  | 0 | 0
998 | Payroll Taxes | PR | 16 | 11/29/17 | 12/01/17 | CO73 | Cortes Sepulveda, Jose R | 0 | 0 | 0 | 0 | 21.11 |  | 0 | 0
998 | Payroll Taxes | PR | 34 | 11/29/17 | 12/01/17 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 13.77 |  | 0 | 0
998 | Payroll Taxes | PR | 66 | 11/29/17 | 12/01/17 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 19.13 |  | 0 | 0
998 | Payroll Taxes | PR | 217 | 12/06/17 | 12/08/17 | CO71 | Cortes Mendiola, Victor H | 0 | 0 | 0 | 0 | 73.44 |  | 0 | 0
998 | Payroll Taxes | PR | 218 | 12/06/17 | 12/08/17 | CO73 | Cortes Sepulveda, Jose R | 0 | 0 | 0 | 0 | 42.23 |  | 0 | 0
998 | Payroll Taxes | PR | 267 | 12/06/17 | 12/08/17 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 53.55 |  | 0 | 0
998 | Payroll Taxes | PR | 267 | 12/06/17 | 12/08/17 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 7.65 |  | 0 | 0
998 | Payroll Taxes | PR | 268 | 12/06/17 | 12/08/17 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 3.6 |  | 0 | 0
998 | Payroll Taxes | PR | 268 | 12/06/17 | 12/08/17 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 3.6 |  | 0 | 0
998 | Payroll Taxes | PR | 414 | 12/13/17 | 12/15/17 | CO71 | Cortes Mendiola, Victor H | 0 | 0 | 0 | 0 | 88.74 |  | 0 | 0
998 | Payroll Taxes | PR | 415 | 12/13/17 | 12/15/17 | CO73 | Cortes Sepulveda, Jose R | 0 | 0 | 0 | 0 | 51.03 |  | 0 | 0
998 | Payroll Taxes | PR | 465 | 12/13/17 | 12/15/17 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 26.78 |  | 0 | 0
998 | Payroll Taxes | PR | 466 | 12/13/17 | 12/15/17 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 3.6 |  | 0 | 0
998 | Payroll Taxes | PR | 466 | 12/13/17 | 12/15/17 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 3.6 |  | 0 | 0
998 | Payroll Taxes | PR | 604 | 12/20/17 | 12/22/17 | CO71 | Cortes Mendiola, Victor H | 0 | 0 | 0 | 0 | 24.48 |  | 0 | 0
998 | Payroll Taxes | PR | 605 | 12/20/17 | 12/22/17 | CO73 | Cortes Sepulveda, Jose R | 0 | 0 | 0 | 0 | 14.08 |  | 0 | 0
998 | Payroll Taxes | PR | 623 | 12/20/17 | 12/22/17 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 12.05 |  | 0 | 0
998 | Payroll Taxes | PR | 655 | 12/20/17 | 12/22/17 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 42.08 |  | 0 | 0
998 | Payroll Taxes | PR | 656 | 12/20/17 | 12/22/17 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 7.19 |  | 0 | 0
998 | Payroll Taxes | PR | 656 | 12/20/17 | 12/22/17 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 14.38 |  | 0 | 0
998 | Payroll Taxes | PR | 795 | 12/27/17 | 12/29/17 | CO71 | Cortes Mendiola, Victor H | 0 | 0 | 0 | 0 | 73.44 |  | 0 | 0
998 | Payroll Taxes | PR | 796 | 12/27/17 | 12/29/17 | CO73 | Cortes Sepulveda, Jose R | 0 | 0 | 0 | 0 | 42.23 |  | 0 | 0
998 | Payroll Taxes | PR | 814 | 12/27/17 | 12/29/17 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 12.05 |  | 0 | 0
998 | Payroll Taxes | PR | 847 | 12/27/17 | 12/29/17 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 3.6 |  | 0 | 0
998 | Payroll Taxes | PR | 15 | 01/03/18 | 01/05/18 | CO71 | Cortes Mendiola, Victor H | 0 | 0 | 0 | 0 | 52.02 |  | 0 | 0
998 | Payroll Taxes | PR | 16 | 01/03/18 | 01/05/18 | CO73 | Cortes Sepulveda, Jose R | 0 | 0 | 0 | 0 | 21.11 |  | 0 | 0
998 | Payroll Taxes | PR | 34 | 01/03/18 | 01/05/18 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 6.89 |  | 0 | 0
998 | Payroll Taxes | PR | 65 | 01/03/18 | 01/05/18 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 9.56 |  | 0 | 0
998 | Payroll Taxes | PR | 238 | 01/10/18 | 01/12/18 | CO71 | Cortes Mendiola, Victor H | 0 | 0 | 0 | 0 | 64.26 |  | 0 | 0
998 | Payroll Taxes | PR | 239 | 01/10/18 | 01/12/18 | CO73 | Cortes Sepulveda, Jose R | 0 | 0 | 0 | 0 | 36.95 |  | 0 | 0
998 | Payroll Taxes | PR | 257 | 01/10/18 | 01/12/18 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 6.89 |  | 0 | 0
998 | Payroll Taxes | PR | 289 | 01/10/18 | 01/12/18 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 28.69 |  | 0 | 0
998 | Payroll Taxes | PR | 289 | 01/10/18 | 01/12/18 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 9.56 |  | 0 | 0
998 | Payroll Taxes | PR | 290 | 01/10/18 | 01/12/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 10.79 |  | 0 | 0
998 | Payroll Taxes | PR | 290 | 01/10/18 | 01/12/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 5.39 |  | 0 | 0
998 | Payroll Taxes | PR | 404 | 01/17/18 | 01/19/18 | CO71 | Cortes Mendiola, Victor H | 0 | 0 | 0 | 0 | 110.16 |  | 0 | 0
998 | Payroll Taxes | PR | 405 | 01/17/18 | 01/19/18 | CO73 | Cortes Sepulveda, Jose R | 0 | 0 | 0 | 0 | 63.34 |  | 0 | 0
998 | Payroll Taxes | PR | 423 | 01/17/18 | 01/19/18 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 17.21 |  | 0 | 0
998 | Payroll Taxes | PR | 423 | 01/17/18 | 01/19/18 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 10.33 |  | 0 | 0
998 | Payroll Taxes | PR | 454 | 01/17/18 | 01/19/18 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 14.34 |  | 0 | 0
998 | Payroll Taxes | PR | 455 | 01/17/18 | 01/19/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 16.18 |  | 0 | 0
998 | Payroll Taxes | PR | 455 | 01/17/18 | 01/19/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 8.99 |  | 0 | 0
998 | Payroll Taxes | PR | 457 | 01/17/18 | 01/19/18 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | -14.34 |  | 0 | 0
998 | Payroll Taxes | PR | 458 | 01/17/18 | 01/19/18 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 14.34 |  | 0 | 0
998 | Payroll Taxes | PR | 600 | 01/24/18 | 01/26/18 | CO71 | Cortes Mendiola, Victor H | 0 | 0 | 0 | 0 | 25.25 |  | 0 | 0
998 | Payroll Taxes | PR | 600 | 01/24/18 | 01/26/18 | CO71 | Cortes Mendiola, Victor H | 0 | 0 | 0 | 0 | 116.28 |  | 0 | 0
998 | Payroll Taxes | PR | 600 | 01/24/18 | 01/26/18 | CO71 | Cortes Mendiola, Victor H | 0 | 0 | 0 | 0 | 6.12 |  | 0 | 0
998 | Payroll Taxes | PR | 601 | 01/24/18 | 01/26/18 | CO73 | Cortes Sepulveda, Jose R | 0 | 0 | 0 | 0 | 14.52 |  | 0 | 0
998 | Payroll Taxes | PR | 601 | 01/24/18 | 01/26/18 | CO73 | Cortes Sepulveda, Jose R | 0 | 0 | 0 | 0 | 42.23 |  | 0 | 0
998 | Payroll Taxes | PR | 601 | 01/24/18 | 01/26/18 | CO73 | Cortes Sepulveda, Jose R | 0 | 0 | 0 | 0 | 28.15 |  | 0 | 0
998 | Payroll Taxes | PR | 618 | 01/24/18 | 01/26/18 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 28.4 |  | 0 | 0
998 | Payroll Taxes | PR | 618 | 01/24/18 | 01/26/18 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 44.75 |  | 0 | 0
998 | Payroll Taxes | PR | 618 | 01/24/18 | 01/26/18 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 34.43 |  | 0 | 0
998 | Payroll Taxes | PR | 629 | 01/24/18 | 01/26/18 | MO56 | Montenegro, Carlos E | 0 | 0 | 0 | 0 | 33.05 |  | 0 | 0
998 | Payroll Taxes | PR | 630 | 01/24/18 | 01/26/18 | PA11 | Paco Leyva, Orlando | 0 | 0 | 0 | 0 | 41.62 |  | 0 | 0
998 | Payroll Taxes | PR | 650 | 01/24/18 | 01/26/18 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 19.13 |  | 0 | 0
998 | Payroll Taxes | PR | 650 | 01/24/18 | 01/26/18 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 4.78 |  | 0 | 0
998 | Payroll Taxes | PR | 651 | 01/24/18 | 01/26/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 7.19 |  | 0 | 0
998 | Payroll Taxes | PR | 651 | 01/24/18 | 01/26/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 10.79 |  | 0 | 0
998 | Payroll Taxes | PR | 19 | 01/31/18 | 02/02/18 | CO71 | Cortes Mendiola, Victor H | 0 | 0 | 0 | 0 | 48.96 |  | 0 | 0
998 | Payroll Taxes | PR | 19 | 01/31/18 | 02/02/18 | CO71 | Cortes Mendiola, Victor H | 0 | 0 | 0 | 0 | 48.96 |  | 0 | 0
998 | Payroll Taxes | PR | 20 | 01/31/18 | 02/02/18 | CO73 | Cortes Sepulveda, Jose R | 0 | 0 | 0 | 0 | 28.15 |  | 0 | 0
998 | Payroll Taxes | PR | 20 | 01/31/18 | 02/02/18 | CO73 | Cortes Sepulveda, Jose R | 0 | 0 | 0 | 0 | 28.15 |  | 0 | 0
998 | Payroll Taxes | PR | 38 | 01/31/18 | 02/02/18 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 53.36 |  | 0 | 0
998 | Payroll Taxes | PR | 38 | 01/31/18 | 02/02/18 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 10.33 |  | 0 | 0
998 | Payroll Taxes | PR | 70 | 01/31/18 | 02/02/18 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 14.34 |  | 0 | 0
998 | Payroll Taxes | PR | 71 | 01/31/18 | 02/02/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 8.99 |  | 0 | 0
998 | Payroll Taxes | PR | 176 | 02/07/18 | 02/09/18 | CO71 | Cortes Mendiola, Victor H | 0 | 0 | 0 | 0 | 30.6 |  | 0 | 0
998 | Payroll Taxes | PR | 177 | 02/07/18 | 02/09/18 | CO73 | Cortes Sepulveda, Jose R | 0 | 0 | 0 | 0 | 28.15 |  | 0 | 0
998 | Payroll Taxes | PR | 195 | 02/07/18 | 02/09/18 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 34.43 |  | 0 | 0
998 | Payroll Taxes | PR | 207 | 02/07/18 | 02/09/18 | PA11 | Paco Leyva, Orlando | 0 | 0 | 0 | 0 | 41.62 |  | 0 | 0
998 | Payroll Taxes | PR | 227 | 02/07/18 | 02/09/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 3.6 |  | 0 | 0
998 | Payroll Taxes | PR | 227 | 02/07/18 | 02/09/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 7.19 |  | 0 | 0
998 | Payroll Taxes | PR | 229 | 02/07/18 | 02/09/18 | PA11 | Paco Leyva, Orlando | 0 | 0 | 0 | 0 | -41.62 |  | 0 | 0
998 | Payroll Taxes | PR | 430 | 02/14/18 | 02/16/18 | CO71 | Cortes Mendiola, Victor H | 0 | 0 | 0 | 0 | 94.86 |  | 0 | 0
998 | Payroll Taxes | PR | 430 | 02/14/18 | 02/16/18 | CO71 | Cortes Mendiola, Victor H | 0 | 0 | 0 | 0 | 27.54 |  | 0 | 0
998 | Payroll Taxes | PR | 431 | 02/14/18 | 02/16/18 | CO73 | Cortes Sepulveda, Jose R | 0 | 0 | 0 | 0 | 54.54 |  | 0 | 0
998 | Payroll Taxes | PR | 431 | 02/14/18 | 02/16/18 | CO73 | Cortes Sepulveda, Jose R | 0 | 0 | 0 | 0 | 15.84 |  | 0 | 0
998 | Payroll Taxes | PR | 449 | 02/14/18 | 02/16/18 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 17.21 |  | 0 | 0
998 | Payroll Taxes | PR | 449 | 02/14/18 | 02/16/18 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 48.2 |  | 0 | 0
998 | Payroll Taxes | PR | 449 | 02/14/18 | 02/16/18 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 10.33 |  | 0 | 0
998 | Payroll Taxes | PR | 449 | 02/14/18 | 02/16/18 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 13.77 |  | 0 | 0
998 | Payroll Taxes | PR | 452 | 02/14/18 | 02/16/18 | LI49 | Lima Romero, Melvin A | 0 | 0 | 0 | 0 | 18.97 |  | 0 | 0
998 | Payroll Taxes | PR | 483 | 02/14/18 | 02/16/18 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 9.56 |  | 0 | 0
998 | Payroll Taxes | PR | 484 | 02/14/18 | 02/16/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 7.19 |  | 0 | 0
998 | Payroll Taxes | PR | 484 | 02/14/18 | 02/16/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 3.6 |  | 0 | 0
998 | Payroll Taxes | PR | 617 | 02/21/18 | 02/23/18 | CO71 | Cortes Mendiola, Victor H | 0 | 0 | 0 | 0 | 97.92 |  | 0 | 0
998 | Payroll Taxes | PR | 618 | 02/21/18 | 02/23/18 | CO73 | Cortes Sepulveda, Jose R | 0 | 0 | 0 | 0 | 38.71 |  | 0 | 0
998 | Payroll Taxes | PR | 618 | 02/21/18 | 02/23/18 | CO73 | Cortes Sepulveda, Jose R | 0 | 0 | 0 | 0 | 17.6 |  | 0 | 0
998 | Payroll Taxes | PR | 636 | 02/21/18 | 02/23/18 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 13.77 |  | 0 | 0
998 | Payroll Taxes | PR | 636 | 02/21/18 | 02/23/18 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 24.1 |  | 0 | 0
998 | Payroll Taxes | PR | 670 | 02/21/18 | 02/23/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 3.6 |  | 0 | 0
998 | Payroll Taxes | PR | 3 | 02/28/18 | 03/02/18 | AS10 | Ascencio, Jose L | 0 | 0 | 0 | 0 | 15.3 |  | 0 | 0
998 | Payroll Taxes | PR | 4 | 02/28/18 | 03/02/18 | BA45 | Balderas Ortiz, Ricardo I | 0 | 0 | 0 | 0 | 16.52 |  | 0 | 0
998 | Payroll Taxes | PR | 16 | 02/28/18 | 03/02/18 | CO71 | Cortes Mendiola, Victor H | 0 | 0 | 0 | 0 | 122.4 |  | 0 | 0
998 | Payroll Taxes | PR | 17 | 02/28/18 | 03/02/18 | CO73 | Cortes Sepulveda, Jose R | 0 | 0 | 0 | 0 | 70.38 |  | 0 | 0
998 | Payroll Taxes | PR | 35 | 02/28/18 | 03/02/18 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 68.85 |  | 0 | 0
998 | Payroll Taxes | PR | 47 | 02/28/18 | 03/02/18 | PA11 | Paco Leyva, Orlando | 0 | 0 | 0 | 0 | 20.81 |  | 0 | 0
998 | Payroll Taxes | PR | 68 | 02/28/18 | 03/02/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 3.6 |  | 0 | 0
998 | Payroll Taxes | PR | 119 | 03/07/18 | 03/09/18 | AS10 | Ascencio, Jose L | 0 | 0 | 0 | 0 | 45.9 |  | 0 | 0
998 | Payroll Taxes | PR | 131 | 03/07/18 | 03/09/18 | CO71 | Cortes Mendiola, Victor H | 0 | 0 | 0 | 0 | 48.96 |  | 0 | 0
998 | Payroll Taxes | PR | 131 | 03/07/18 | 03/09/18 | CO71 | Cortes Mendiola, Victor H | 0 | 0 | 0 | 0 | 48.96 |  | 0 | 0
998 | Payroll Taxes | PR | 131 | 03/07/18 | 03/09/18 | CO71 | Cortes Mendiola, Victor H | 0 | 0 | 0 | 0 | 24.48 |  | 0 | 0
998 | Payroll Taxes | PR | 132 | 03/07/18 | 03/09/18 | CO73 | Cortes Sepulveda, Jose R | 0 | 0 | 0 | 0 | 28.15 |  | 0 | 0
998 | Payroll Taxes | PR | 132 | 03/07/18 | 03/09/18 | CO73 | Cortes Sepulveda, Jose R | 0 | 0 | 0 | 0 | 28.15 |  | 0 | 0
998 | Payroll Taxes | PR | 132 | 03/07/18 | 03/09/18 | CO73 | Cortes Sepulveda, Jose R | 0 | 0 | 0 | 0 | 14.08 |  | 0 | 0
998 | Payroll Taxes | PR | 149 | 03/07/18 | 03/09/18 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 29.26 |  | 0 | 0
998 | Payroll Taxes | PR | 149 | 03/07/18 | 03/09/18 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 24.1 |  | 0 | 0
998 | Payroll Taxes | PR | 173 | 03/07/18 | 03/09/18 | SI48 | Silva Morales, Jair J | 0 | 0 | 0 | 0 | 14.08 |  | 0 | 0
998 | Payroll Taxes | PR | 183 | 03/07/18 | 03/09/18 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 4.78 |  | 0 | 0
998 | Payroll Taxes | PR | 184 | 03/07/18 | 03/09/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 10.79 |  | 0 | 0
998 | Payroll Taxes | PR | 184 | 03/07/18 | 03/09/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 3.6 |  | 0 | 0
998 | Payroll Taxes | PR | 319 | 03/14/18 | 03/16/18 | AS10 | Ascencio, Jose L | 0 | 0 | 0 | 0 | 76.5 |  | 0 | 0
998 | Payroll Taxes | PR | 331 | 03/14/18 | 03/16/18 | CO71 | Cortes Mendiola, Victor H | 0 | 0 | 0 | 0 | 122.4 |  | 0 | 0
998 | Payroll Taxes | PR | 332 | 03/14/18 | 03/16/18 | CO73 | Cortes Sepulveda, Jose R | 0 | 0 | 0 | 0 | 24.63 |  | 0 | 0
998 | Payroll Taxes | PR | 332 | 03/14/18 | 03/16/18 | CO73 | Cortes Sepulveda, Jose R | 0 | 0 | 0 | 0 | 14.08 |  | 0 | 0
998 | Payroll Taxes | PR | 332 | 03/14/18 | 03/16/18 | CO73 | Cortes Sepulveda, Jose R | 0 | 0 | 0 | 0 | 28.15 |  | 0 | 0
998 | Payroll Taxes | PR | 350 | 03/14/18 | 03/16/18 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 10.33 |  | 0 | 0
998 | Payroll Taxes | PR | 376 | 03/14/18 | 03/16/18 | SI48 | Silva Morales, Jair J | 0 | 0 | 0 | 0 | 28.15 |  | 0 | 0
998 | Payroll Taxes | PR | 376 | 03/14/18 | 03/16/18 | SI48 | Silva Morales, Jair J | 0 | 0 | 0 | 0 | 42.23 |  | 0 | 0
998 | Payroll Taxes | PR | 384 | 03/14/18 | 03/16/18 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 9.56 |  | 0 | 0
998 | Payroll Taxes | PR | 384 | 03/14/18 | 03/16/18 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 4.78 |  | 0 | 0
998 | Payroll Taxes | PR | 385 | 03/14/18 | 03/16/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 7.65 |  | 0 | 0
998 | Payroll Taxes | PR | 517 | 03/21/18 | 03/23/18 | AS10 | Ascencio, Jose L | 0 | 0 | 0 | 0 | 76.5 |  | 0 | 0
998 | Payroll Taxes | PR | 529 | 03/21/18 | 03/23/18 | CO71 | Cortes Mendiola, Victor H | 0 | 0 | 0 | 0 | 91.8 |  | 0 | 0
998 | Payroll Taxes | PR | 529 | 03/21/18 | 03/23/18 | CO71 | Cortes Mendiola, Victor H | 0 | 0 | 0 | 0 | 6.12 |  | 0 | 0
998 | Payroll Taxes | PR | 530 | 03/21/18 | 03/23/18 | CO73 | Cortes Sepulveda, Jose R | 0 | 0 | 0 | 0 | 63.34 |  | 0 | 0
998 | Payroll Taxes | PR | 530 | 03/21/18 | 03/23/18 | CO73 | Cortes Sepulveda, Jose R | 0 | 0 | 0 | 0 | 7.04 |  | 0 | 0
998 | Payroll Taxes | PR | 548 | 03/21/18 | 03/23/18 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 30.98 |  | 0 | 0
998 | Payroll Taxes | PR | 548 | 03/21/18 | 03/23/18 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 6.89 |  | 0 | 0
998 | Payroll Taxes | PR | 548 | 03/21/18 | 03/23/18 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 10.33 |  | 0 | 0
998 | Payroll Taxes | PR | 575 | 03/21/18 | 03/23/18 | SI48 | Silva Morales, Jair J | 0 | 0 | 0 | 0 | 35.19 |  | 0 | 0
998 | Payroll Taxes | PR | 575 | 03/21/18 | 03/23/18 | SI48 | Silva Morales, Jair J | 0 | 0 | 0 | 0 | 35.19 |  | 0 | 0
998 | Payroll Taxes | PR | 583 | 03/21/18 | 03/23/18 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 19.13 |  | 0 | 0
998 | Payroll Taxes | PR | 584 | 03/21/18 | 03/23/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 3.83 |  | 0 | 0
998 | Payroll Taxes | PR | 736 | 03/28/18 | 03/30/18 | AS10 | Ascencio, Jose L | 0 | 0 | 0 | 0 | 45.9 |  | 0 | 0
998 | Payroll Taxes | PR | 736 | 03/28/18 | 03/30/18 | AS10 | Ascencio, Jose L | 0 | 0 | 0 | 0 | 30.6 |  | 0 | 0
998 | Payroll Taxes | PR | 748 | 03/28/18 | 03/30/18 | CO71 | Cortes Mendiola, Victor H | 0 | 0 | 0 | 0 | 48.96 |  | 0 | 0
998 | Payroll Taxes | PR | 748 | 03/28/18 | 03/30/18 | CO71 | Cortes Mendiola, Victor H | 0 | 0 | 0 | 0 | 73.44 |  | 0 | 0
998 | Payroll Taxes | PR | 749 | 03/28/18 | 03/30/18 | CO73 | Cortes Sepulveda, Jose R | 0 | 0 | 0 | 0 | 70.38 |  | 0 | 0
998 | Payroll Taxes | PR | 763 | 03/28/18 | 03/30/18 | GU78 | Gutierrez Salas, Jose | 0 | 0 | 0 | 0 | 33.05 |  | 0 | 0
998 | Payroll Taxes | PR | 770 | 03/28/18 | 03/30/18 | JU02 | Juarez Alvarez, Oscar R | 0 | 0 | 0 | 0 | 17.14 |  | 0 | 0
998 | Payroll Taxes | PR | 770 | 03/28/18 | 03/30/18 | JU02 | Juarez Alvarez, Oscar R | 0 | 0 | 0 | 0 | 34.27 |  | 0 | 0
998 | Payroll Taxes | PR | 771 | 03/28/18 | 03/30/18 | JU04 | Juarez Maldonado, Oscar E | 0 | 0 | 0 | 0 | 33.05 |  | 0 | 0
998 | Payroll Taxes | PR | 800 | 03/28/18 | 03/30/18 | SI48 | Silva Morales, Jair J | 0 | 0 | 0 | 0 | 66.86 |  | 0 | 0
998 | Payroll Taxes | PR | 811 | 03/28/18 | 03/30/18 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 4.78 |  | 0 | 0
998 | Payroll Taxes | PR | 812 | 03/28/18 | 03/30/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 11.48 |  | 0 | 0
998 | Payroll Taxes | PR | 812 | 03/28/18 | 03/30/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 5.74 |  | 0 | 0
998 | Payroll Taxes | PR | 12 | 04/04/18 | 04/06/18 | AS10 | Ascencio, Jose L | 0 | 0 | 0 | 0 | 61.2 |  | 0 | 0
998 | Payroll Taxes | PR | 24 | 04/04/18 | 04/06/18 | CO71 | Cortes Mendiola, Victor H | 0 | 0 | 0 | 0 | 104.04 |  | 0 | 0
998 | Payroll Taxes | PR | 24 | 04/04/18 | 04/06/18 | CO71 | Cortes Mendiola, Victor H | 0 | 0 | 0 | 0 | 6.12 |  | 0 | 0
998 | Payroll Taxes | PR | 24 | 04/04/18 | 04/06/18 | CO71 | Cortes Mendiola, Victor H | 0 | 0 | 0 | 0 | 12.24 |  | 0 | 0
998 | Payroll Taxes | PR | 25 | 04/04/18 | 04/06/18 | CO73 | Cortes Sepulveda, Jose R | 0 | 0 | 0 | 0 | 52.79 |  | 0 | 0
998 | Payroll Taxes | PR | 25 | 04/04/18 | 04/06/18 | CO73 | Cortes Sepulveda, Jose R | 0 | 0 | 0 | 0 | 14.08 |  | 0 | 0
998 | Payroll Taxes | PR | 39 | 04/04/18 | 04/06/18 | GU78 | Gutierrez Salas, Jose | 0 | 0 | 0 | 0 | 42.69 |  | 0 | 0
998 | Payroll Taxes | PR | 46 | 04/04/18 | 04/06/18 | JU02 | Juarez Alvarez, Oscar R | 0 | 0 | 0 | 0 | 85.68 |  | 0 | 0
998 | Payroll Taxes | PR | 47 | 04/04/18 | 04/06/18 | JU04 | Juarez Maldonado, Oscar E | 0 | 0 | 0 | 0 | 33.05 |  | 0 | 0
998 | Payroll Taxes | PR | 47 | 04/04/18 | 04/06/18 | JU04 | Juarez Maldonado, Oscar E | 0 | 0 | 0 | 0 | 11.02 |  | 0 | 0
998 | Payroll Taxes | PR | 74 | 04/04/18 | 04/06/18 | SI48 | Silva Morales, Jair J | 0 | 0 | 0 | 0 | 42.23 |  | 0 | 0
998 | Payroll Taxes | PR | 74 | 04/04/18 | 04/06/18 | SI48 | Silva Morales, Jair J | 0 | 0 | 0 | 0 | 28.15 |  | 0 | 0
998 | Payroll Taxes | PR | 85 | 04/04/18 | 04/06/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 11.48 |  | 0 | 0
998 | Payroll Taxes | PR | 85 | 04/04/18 | 04/06/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 7.65 |  | 0 | 0
998 | Payroll Taxes | PR | 260 | 04/11/18 | 04/13/18 | AS10 | Ascencio, Jose L | 0 | 0 | 0 | 0 | 68.85 |  | 0 | 0
998 | Payroll Taxes | PR | 272 | 04/11/18 | 04/13/18 | CO71 | Cortes Mendiola, Victor H | 0 | 0 | 0 | 0 | 122.4 |  | 0 | 0
998 | Payroll Taxes | PR | 273 | 04/11/18 | 04/13/18 | CO73 | Cortes Sepulveda, Jose R | 0 | 0 | 0 | 0 | 56.3 |  | 0 | 0
998 | Payroll Taxes | PR | 287 | 04/11/18 | 04/13/18 | GU78 | Gutierrez Salas, Jose | 0 | 0 | 0 | 0 | 55.08 |  | 0 | 0
998 | Payroll Taxes | PR | 292 | 04/11/18 | 04/13/18 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 10.33 |  | 0 | 0
998 | Payroll Taxes | PR | 292 | 04/11/18 | 04/13/18 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 10.33 |  | 0 | 0
998 | Payroll Taxes | PR | 294 | 04/11/18 | 04/13/18 | JU02 | Juarez Alvarez, Oscar R | 0 | 0 | 0 | 0 | 85.68 |  | 0 | 0
998 | Payroll Taxes | PR | 295 | 04/11/18 | 04/13/18 | JU04 | Juarez Maldonado, Oscar E | 0 | 0 | 0 | 0 | 44.06 |  | 0 | 0
998 | Payroll Taxes | PR | 295 | 04/11/18 | 04/13/18 | JU04 | Juarez Maldonado, Oscar E | 0 | 0 | 0 | 0 | 11.02 |  | 0 | 0
998 | Payroll Taxes | PR | 323 | 04/11/18 | 04/13/18 | SI48 | Silva Morales, Jair J | 0 | 0 | 0 | 0 | 28.15 |  | 0 | 0
998 | Payroll Taxes | PR | 333 | 04/11/18 | 04/13/18 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 9.56 |  | 0 | 0
998 | Payroll Taxes | PR | 334 | 04/11/18 | 04/13/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 7.65 |  | 0 | 0
998 | Payroll Taxes | PR | 447 | 04/18/18 | 04/20/18 | AS10 | Ascencio, Jose L | 0 | 0 | 0 | 0 | 76.5 |  | 0 | 0
998 | Payroll Taxes | PR | 457 | 04/18/18 | 04/20/18 | CO71 | Cortes Mendiola, Victor H | 0 | 0 | 0 | 0 | 48.96 |  | 0 | 0
998 | Payroll Taxes | PR | 458 | 04/18/18 | 04/20/18 | CO73 | Cortes Sepulveda, Jose R | 0 | 0 | 0 | 0 | 42.23 |  | 0 | 0
998 | Payroll Taxes | PR | 458 | 04/18/18 | 04/20/18 | CO73 | Cortes Sepulveda, Jose R | 0 | 0 | 0 | 0 | 28.15 |  | 0 | 0
998 | Payroll Taxes | PR | 472 | 04/18/18 | 04/20/18 | GU78 | Gutierrez Salas, Jose | 0 | 0 | 0 | 0 | 44.06 |  | 0 | 0
998 | Payroll Taxes | PR | 477 | 04/18/18 | 04/20/18 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 24.1 |  | 0 | 0
998 | Payroll Taxes | PR | 477 | 04/18/18 | 04/20/18 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 58.52 |  | 0 | 0
998 | Payroll Taxes | PR | 479 | 04/18/18 | 04/20/18 | JU02 | Juarez Alvarez, Oscar R | 0 | 0 | 0 | 0 | 68.54 |  | 0 | 0
998 | Payroll Taxes | PR | 479 | 04/18/18 | 04/20/18 | JU02 | Juarez Alvarez, Oscar R | 0 | 0 | 0 | 0 | 17.14 |  | 0 | 0
998 | Payroll Taxes | PR | 480 | 04/18/18 | 04/20/18 | JU04 | Juarez Maldonado, Oscar E | 0 | 0 | 0 | 0 | 44.06 |  | 0 | 0
998 | Payroll Taxes | PR | 480 | 04/18/18 | 04/20/18 | JU04 | Juarez Maldonado, Oscar E | 0 | 0 | 0 | 0 | 11.02 |  | 0 | 0
998 | Payroll Taxes | PR | 508 | 04/18/18 | 04/20/18 | SI48 | Silva Morales, Jair J | 0 | 0 | 0 | 0 | 14.08 |  | 0 | 0
998 | Payroll Taxes | PR | 517 | 04/18/18 | 04/20/18 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 14.34 |  | 0 | 0
998 | Payroll Taxes | PR | 518 | 04/18/18 | 04/20/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 3.83 |  | 0 | 0
998 | Payroll Taxes | PR | 613 | 04/25/18 | 04/27/18 | AS10 | Ascencio, Jose L | 0 | 0 | 0 | 0 | 76.5 |  | 0 | 0
998 | Payroll Taxes | PR | 615 | 04/25/18 | 04/27/18 | BA45 | Balderas Ortiz, Ricardo I | 0 | 0 | 0 | 0 | 33.05 |  | 0 | 0
998 | Payroll Taxes | PR | 624 | 04/25/18 | 04/27/18 | CO71 | Cortes Mendiola, Victor H | 0 | 0 | 0 | 0 | 36.72 |  | 0 | 0
998 | Payroll Taxes | PR | 624 | 04/25/18 | 04/27/18 | CO71 | Cortes Mendiola, Victor H | 0 | 0 | 0 | 0 | 85.68 |  | 0 | 0
998 | Payroll Taxes | PR | 625 | 04/25/18 | 04/27/18 | CO73 | Cortes Sepulveda, Jose R | 0 | 0 | 0 | 0 | 42.23 |  | 0 | 0
998 | Payroll Taxes | PR | 625 | 04/25/18 | 04/27/18 | CO73 | Cortes Sepulveda, Jose R | 0 | 0 | 0 | 0 | 28.15 |  | 0 | 0
998 | Payroll Taxes | PR | 634 | 04/25/18 | 04/27/18 | GA70 | Garcia, Jordan X | 0 | 0 | 0 | 0 | 94.86 |  | 0 | 0
998 | Payroll Taxes | PR | 639 | 04/25/18 | 04/27/18 | GU78 | Gutierrez Salas, Jose | 0 | 0 | 0 | 0 | 22.03 |  | 0 | 0
998 | Payroll Taxes | PR | 639 | 04/25/18 | 04/27/18 | GU78 | Gutierrez Salas, Jose | 0 | 0 | 0 | 0 | 11.02 |  | 0 | 0
998 | Payroll Taxes | PR | 644 | 04/25/18 | 04/27/18 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 6.89 |  | 0 | 0
998 | Payroll Taxes | PR | 644 | 04/25/18 | 04/27/18 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 13.77 |  | 0 | 0
998 | Payroll Taxes | PR | 646 | 04/25/18 | 04/27/18 | JU02 | Juarez Alvarez, Oscar R | 0 | 0 | 0 | 0 | 68.54 |  | 0 | 0
998 | Payroll Taxes | PR | 646 | 04/25/18 | 04/27/18 | JU02 | Juarez Alvarez, Oscar R | 0 | 0 | 0 | 0 | 17.14 |  | 0 | 0
998 | Payroll Taxes | PR | 647 | 04/25/18 | 04/27/18 | JU04 | Juarez Maldonado, Oscar E | 0 | 0 | 0 | 0 | 55.08 |  | 0 | 0
998 | Payroll Taxes | PR | 650 | 04/25/18 | 04/27/18 | LI49 | Lima Romero, Melvin A | 0 | 0 | 0 | 0 | 56.92 |  | 0 | 0
998 | Payroll Taxes | PR | 674 | 04/25/18 | 04/27/18 | SI48 | Silva Morales, Jair J | 0 | 0 | 0 | 0 | 54.54 |  | 0 | 0
998 | Payroll Taxes | PR | 674 | 04/25/18 | 04/27/18 | SI48 | Silva Morales, Jair J | 0 | 0 | 0 | 0 | 14.08 |  | 0 | 0
998 | Payroll Taxes | PR | 684 | 04/25/18 | 04/27/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 19.13 |  | 0 | 0
998 | Payroll Taxes | PR | 684 | 04/25/18 | 04/27/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 7.65 |  | 0 | 0
998 | Payroll Taxes | PR | 27 | 05/02/18 | 05/04/18 | AS10 | Ascencio, Jose L | 0 | 0 | 0 | 0 | 76.5 |  | 0 | 0
998 | Payroll Taxes | PR | 29 | 05/02/18 | 05/04/18 | BA45 | Balderas Ortiz, Ricardo I | 0 | 0 | 0 | 0 | 66.1 |  | 0 | 0
998 | Payroll Taxes | PR | 29 | 05/02/18 | 05/04/18 | BA45 | Balderas Ortiz, Ricardo I | 0 | 0 | 0 | 0 | 8.26 |  | 0 | 0
998 | Payroll Taxes | PR | 38 | 05/02/18 | 05/04/18 | CO71 | Cortes Mendiola, Victor H | 0 | 0 | 0 | 0 | 113.22 |  | 0 | 0
998 | Payroll Taxes | PR | 38 | 05/02/18 | 05/04/18 | CO71 | Cortes Mendiola, Victor H | 0 | 0 | 0 | 0 | 9.18 |  | 0 | 0
998 | Payroll Taxes | PR | 39 | 05/02/18 | 05/04/18 | CO73 | Cortes Sepulveda, Jose R | 0 | 0 | 0 | 0 | 56.3 |  | 0 | 0
998 | Payroll Taxes | PR | 48 | 05/02/18 | 05/04/18 | GA70 | Garcia, Jordan X | 0 | 0 | 0 | 0 | 94.86 |  | 0 | 0
998 | Payroll Taxes | PR | 53 | 05/02/18 | 05/04/18 | GU78 | Gutierrez Salas, Jose | 0 | 0 | 0 | 0 | 44.06 |  | 0 | 0
998 | Payroll Taxes | PR | 58 | 05/02/18 | 05/04/18 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 30.98 |  | 0 | 0
998 | Payroll Taxes | PR | 60 | 05/02/18 | 05/04/18 | JU02 | Juarez Alvarez, Oscar R | 0 | 0 | 0 | 0 | 85.68 |  | 0 | 0
998 | Payroll Taxes | PR | 61 | 05/02/18 | 05/04/18 | JU04 | Juarez Maldonado, Oscar E | 0 | 0 | 0 | 0 | 44.06 |  | 0 | 0
998 | Payroll Taxes | PR | 64 | 05/02/18 | 05/04/18 | LI49 | Lima Romero, Melvin A | 0 | 0 | 0 | 0 | 94.86 |  | 0 | 0
998 | Payroll Taxes | PR | 89 | 05/02/18 | 05/04/18 | SI48 | Silva Morales, Jair J | 0 | 0 | 0 | 0 | 70.38 |  | 0 | 0
998 | Payroll Taxes | PR | 99 | 05/02/18 | 05/04/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 3.83 |  | 0 | 0
998 | Payroll Taxes | PR | 99 | 05/02/18 | 05/04/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 7.65 |  | 0 | 0
998 | Payroll Taxes | PR | 226 | 05/09/18 | 05/11/18 | AS10 | Ascencio, Jose L | 0 | 0 | 0 | 0 | 61.2 |  | 0 | 0
998 | Payroll Taxes | PR | 228 | 05/09/18 | 05/11/18 | BA45 | Balderas Ortiz, Ricardo I | 0 | 0 | 0 | 0 | 43.38 |  | 0 | 0
998 | Payroll Taxes | PR | 234 | 05/09/18 | 05/11/18 | CO71 | Cortes Mendiola, Victor H | 0 | 0 | 0 | 0 | 110.16 |  | 0 | 0
998 | Payroll Taxes | PR | 234 | 05/09/18 | 05/11/18 | CO71 | Cortes Mendiola, Victor H | 0 | 0 | 0 | 0 | 12.24 |  | 0 | 0
998 | Payroll Taxes | PR | 235 | 05/09/18 | 05/11/18 | CO73 | Cortes Sepulveda, Jose R | 0 | 0 | 0 | 0 | 70.38 |  | 0 | 0
998 | Payroll Taxes | PR | 242 | 05/09/18 | 05/11/18 | GA70 | Garcia, Jordan X | 0 | 0 | 0 | 0 | 90.12 |  | 0 | 0
998 | Payroll Taxes | PR | 242 | 05/09/18 | 05/11/18 | GA70 | Garcia, Jordan X | 0 | 0 | 0 | 0 | 4.74 |  | 0 | 0
998 | Payroll Taxes | PR | 247 | 05/09/18 | 05/11/18 | GU78 | Gutierrez Salas, Jose | 0 | 0 | 0 | 0 | 44.06 |  | 0 | 0
998 | Payroll Taxes | PR | 251 | 05/09/18 | 05/11/18 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 22.38 |  | 0 | 0
998 | Payroll Taxes | PR | 253 | 05/09/18 | 05/11/18 | JU02 | Juarez Alvarez, Oscar R | 0 | 0 | 0 | 0 | 85.68 |  | 0 | 0
998 | Payroll Taxes | PR | 254 | 05/09/18 | 05/11/18 | JU04 | Juarez Maldonado, Oscar E | 0 | 0 | 0 | 0 | 55.08 |  | 0 | 0
998 | Payroll Taxes | PR | 257 | 05/09/18 | 05/11/18 | LI49 | Lima Romero, Melvin A | 0 | 0 | 0 | 0 | 56.92 |  | 0 | 0
998 | Payroll Taxes | PR | 279 | 05/09/18 | 05/11/18 | SI48 | Silva Morales, Jair J | 0 | 0 | 0 | 0 | 56.3 |  | 0 | 0
998 | Payroll Taxes | PR | 279 | 05/09/18 | 05/11/18 | SI48 | Silva Morales, Jair J | 0 | 0 | 0 | 0 | 14.08 |  | 0 | 0
998 | Payroll Taxes | PR | 286 | 05/09/18 | 05/11/18 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 14.34 |  | 0 | 0
998 | Payroll Taxes | PR | 287 | 05/09/18 | 05/11/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 7.65 |  | 0 | 0
998 | Payroll Taxes | PR | 422 | 05/16/18 | 05/18/18 | AS10 | Ascencio, Jose L | 0 | 0 | 0 | 0 | 76.5 |  | 0 | 0
998 | Payroll Taxes | PR | 424 | 05/16/18 | 05/18/18 | BA45 | Balderas Ortiz, Ricardo I | 0 | 0 | 0 | 0 | 82.62 |  | 0 | 0
998 | Payroll Taxes | PR | 432 | 05/16/18 | 05/18/18 | CO71 | Cortes Mendiola, Victor H | 0 | 0 | 0 | 0 | 97.92 |  | 0 | 0
998 | Payroll Taxes | PR | 432 | 05/16/18 | 05/18/18 | CO71 | Cortes Mendiola, Victor H | 0 | 0 | 0 | 0 | 24.48 |  | 0 | 0
998 | Payroll Taxes | PR | 433 | 05/16/18 | 05/18/18 | CO73 | Cortes Sepulveda, Jose R | 0 | 0 | 0 | 0 | 68.62 |  | 0 | 0
998 | Payroll Taxes | PR | 442 | 05/16/18 | 05/18/18 | GA70 | Garcia, Jordan X | 0 | 0 | 0 | 0 | 94.86 |  | 0 | 0
998 | Payroll Taxes | PR | 447 | 05/16/18 | 05/18/18 | GU78 | Gutierrez Salas, Jose | 0 | 0 | 0 | 0 | 44.06 |  | 0 | 0
998 | Payroll Taxes | PR | 447 | 05/16/18 | 05/18/18 | GU78 | Gutierrez Salas, Jose | 0 | 0 | 0 | 0 | 11.02 |  | 0 | 0
998 | Payroll Taxes | PR | 454 | 05/16/18 | 05/18/18 | JU02 | Juarez Alvarez, Oscar R | 0 | 0 | 0 | 0 | 83.54 |  | 0 | 0
998 | Payroll Taxes | PR | 455 | 05/16/18 | 05/18/18 | JU04 | Juarez Maldonado, Oscar E | 0 | 0 | 0 | 0 | 53.7 |  | 0 | 0
998 | Payroll Taxes | PR | 458 | 05/16/18 | 05/18/18 | LI49 | Lima Romero, Melvin A | 0 | 0 | 0 | 0 | 94.86 |  | 0 | 0
998 | Payroll Taxes | PR | 482 | 05/16/18 | 05/18/18 | SI48 | Silva Morales, Jair J | 0 | 0 | 0 | 0 | 14.08 |  | 0 | 0
998 | Payroll Taxes | PR | 482 | 05/16/18 | 05/18/18 | SI48 | Silva Morales, Jair J | 0 | 0 | 0 | 0 | 38.71 |  | 0 | 0
998 | Payroll Taxes | PR | 492 | 05/16/18 | 05/18/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 3.83 |  | 0 | 0
998 | Payroll Taxes | PR | 492 | 05/16/18 | 05/18/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 3.83 |  | 0 | 0
998 | Payroll Taxes | PR | 737 | 05/23/18 | 05/25/18 | AS10 | Ascencio, Jose L | 0 | 0 | 0 | 0 | 17.21 |  | 0 | 0
998 | Payroll Taxes | PR | 737 | 05/23/18 | 05/25/18 | AS10 | Ascencio, Jose L | 0 | 0 | 0 | 0 | 76.5 |  | 0 | 0
998 | Payroll Taxes | PR | 739 | 05/23/18 | 05/25/18 | BA45 | Balderas Ortiz, Ricardo I | 0 | 0 | 0 | 0 | 18.59 |  | 0 | 0
998 | Payroll Taxes | PR | 739 | 05/23/18 | 05/25/18 | BA45 | Balderas Ortiz, Ricardo I | 0 | 0 | 0 | 0 | 82.62 |  | 0 | 0
998 | Payroll Taxes | PR | 747 | 05/23/18 | 05/25/18 | CO71 | Cortes Mendiola, Victor H | 0 | 0 | 0 | 0 | 16.07 |  | 0 | 0
998 | Payroll Taxes | PR | 747 | 05/23/18 | 05/25/18 | CO71 | Cortes Mendiola, Victor H | 0 | 0 | 0 | 0 | 9.18 |  | 0 | 0
998 | Payroll Taxes | PR | 747 | 05/23/18 | 05/25/18 | CO71 | Cortes Mendiola, Victor H | 0 | 0 | 0 | 0 | 116.28 |  | 0 | 0
998 | Payroll Taxes | PR | 747 | 05/23/18 | 05/25/18 | CO71 | Cortes Mendiola, Victor H | 0 | 0 | 0 | 0 | 6.12 |  | 0 | 0
998 | Payroll Taxes | PR | 748 | 05/23/18 | 05/25/18 | CO73 | Cortes Sepulveda, Jose R | 0 | 0 | 0 | 0 | 15.84 |  | 0 | 0
998 | Payroll Taxes | PR | 748 | 05/23/18 | 05/25/18 | CO73 | Cortes Sepulveda, Jose R | 0 | 0 | 0 | 0 | 70.38 |  | 0 | 0
998 | Payroll Taxes | PR | 750 | 05/23/18 | 05/25/18 | CR79 | Cruz Guzman, Joel A | 0 | 0 | 0 | 0 | 20.2 |  | 0 | 0
998 | Payroll Taxes | PR | 757 | 05/23/18 | 05/25/18 | GA70 | Garcia, Jordan X | 0 | 0 | 0 | 0 | 14.23 |  | 0 | 0
998 | Payroll Taxes | PR | 757 | 05/23/18 | 05/25/18 | GA70 | Garcia, Jordan X | 0 | 0 | 0 | 0 | 75.89 |  | 0 | 0
998 | Payroll Taxes | PR | 762 | 05/23/18 | 05/25/18 | GU78 | Gutierrez Salas, Jose | 0 | 0 | 0 | 0 | 44.06 |  | 0 | 0
998 | Payroll Taxes | PR | 762 | 05/23/18 | 05/25/18 | GU78 | Gutierrez Salas, Jose | 0 | 0 | 0 | 0 | 11.02 |  | 0 | 0
998 | Payroll Taxes | PR | 767 | 05/23/18 | 05/25/18 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 6.89 |  | 0 | 0
998 | Payroll Taxes | PR | 769 | 05/23/18 | 05/25/18 | JU02 | Juarez Alvarez, Oscar R | 0 | 0 | 0 | 0 | 19.28 |  | 0 | 0
998 | Payroll Taxes | PR | 769 | 05/23/18 | 05/25/18 | JU02 | Juarez Alvarez, Oscar R | 0 | 0 | 0 | 0 | 85.68 |  | 0 | 0
998 | Payroll Taxes | PR | 770 | 05/23/18 | 05/25/18 | JU04 | Juarez Maldonado, Oscar E | 0 | 0 | 0 | 0 | 12.39 |  | 0 | 0
998 | Payroll Taxes | PR | 770 | 05/23/18 | 05/25/18 | JU04 | Juarez Maldonado, Oscar E | 0 | 0 | 0 | 0 | 55.08 |  | 0 | 0
998 | Payroll Taxes | PR | 773 | 05/23/18 | 05/25/18 | LI49 | Lima Romero, Melvin A | 0 | 0 | 0 | 0 | 21.34 |  | 0 | 0
998 | Payroll Taxes | PR | 773 | 05/23/18 | 05/25/18 | LI49 | Lima Romero, Melvin A | 0 | 0 | 0 | 0 | 94.86 |  | 0 | 0
998 | Payroll Taxes | PR | 797 | 05/23/18 | 05/25/18 | SI48 | Silva Morales, Jair J | 0 | 0 | 0 | 0 | 7.92 |  | 0 | 0
998 | Payroll Taxes | PR | 797 | 05/23/18 | 05/25/18 | SI48 | Silva Morales, Jair J | 0 | 0 | 0 | 0 | 29.91 |  | 0 | 0
998 | Payroll Taxes | PR | 806 | 05/23/18 | 05/25/18 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 4.78 |  | 0 | 0
998 | Payroll Taxes | PR | 807 | 05/23/18 | 05/25/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 11.48 |  | 0 | 0
998 | Payroll Taxes | PR | 4 | 05/30/18 | 06/01/18 | AS10 | Ascencio, Jose L | 0 | 0 | 0 | 0 | 72.68 |  | 0 | 0
998 | Payroll Taxes | PR | 6 | 05/30/18 | 06/01/18 | BA45 | Balderas Ortiz, Ricardo I | 0 | 0 | 0 | 0 | 78.49 |  | 0 | 0
998 | Payroll Taxes | PR | 14 | 05/30/18 | 06/01/18 | CO71 | Cortes Mendiola, Victor H | 0 | 0 | 0 | 0 | 82.62 |  | 0 | 0
998 | Payroll Taxes | PR | 14 | 05/30/18 | 06/01/18 | CO71 | Cortes Mendiola, Victor H | 0 | 0 | 0 | 0 | 30.6 |  | 0 | 0
998 | Payroll Taxes | PR | 14 | 05/30/18 | 06/01/18 | CO71 | Cortes Mendiola, Victor H | 0 | 0 | 0 | 0 | 3.06 |  | 0 | 0
998 | Payroll Taxes | PR | 15 | 05/30/18 | 06/01/18 | CO73 | Cortes Sepulveda, Jose R | 0 | 0 | 0 | 0 | 63.34 |  | 0 | 0
998 | Payroll Taxes | PR | 24 | 05/30/18 | 06/01/18 | GA70 | Garcia, Jordan X | 0 | 0 | 0 | 0 | 85.37 |  | 0 | 0
998 | Payroll Taxes | PR | 29 | 05/30/18 | 06/01/18 | GU78 | Gutierrez Salas, Jose | 0 | 0 | 0 | 0 | 52.33 |  | 0 | 0
998 | Payroll Taxes | PR | 36 | 05/30/18 | 06/01/18 | JU02 | Juarez Alvarez, Oscar R | 0 | 0 | 0 | 0 | 81.4 |  | 0 | 0
998 | Payroll Taxes | PR | 37 | 05/30/18 | 06/01/18 | JU04 | Juarez Maldonado, Oscar E | 0 | 0 | 0 | 0 | 52.33 |  | 0 | 0
998 | Payroll Taxes | PR | 40 | 05/30/18 | 06/01/18 | LI49 | Lima Romero, Melvin A | 0 | 0 | 0 | 0 | 90.12 |  | 0 | 0
998 | Payroll Taxes | PR | 41 | 05/30/18 | 06/01/18 | LO58 | Lopez Reyes, Boris O | 0 | 0 | 0 | 0 | 9.64 |  | 0 | 0
998 | Payroll Taxes | PR | 64 | 05/30/18 | 06/01/18 | SI48 | Silva Morales, Jair J | 0 | 0 | 0 | 0 | 17.6 |  | 0 | 0
998 | Payroll Taxes | PR | 76 | 05/30/18 | 06/01/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 3.83 |  | 0 | 0
998 | Payroll Taxes | PR | 76 | 05/30/18 | 06/01/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 3.83 |  | 0 | 0
998 | Payroll Taxes | PR | 269 | 06/06/18 | 06/08/18 | AS10 | Ascencio, Jose L | 0 | 0 | 0 | 0 | 22.95 |  | 0 | 0
998 | Payroll Taxes | PR | 269 | 06/06/18 | 06/08/18 | AS10 | Ascencio, Jose L | 0 | 0 | 0 | 0 | 76.5 |  | 0 | 0
998 | Payroll Taxes | PR | 271 | 06/06/18 | 06/08/18 | BA45 | Balderas Ortiz, Ricardo I | 0 | 0 | 0 | 0 | 6.2 |  | 0 | 0
998 | Payroll Taxes | PR | 271 | 06/06/18 | 06/08/18 | BA45 | Balderas Ortiz, Ricardo I | 0 | 0 | 0 | 0 | 45.44 |  | 0 | 0
998 | Payroll Taxes | PR | 271 | 06/06/18 | 06/08/18 | BA45 | Balderas Ortiz, Ricardo I | 0 | 0 | 0 | 0 | 37.18 |  | 0 | 0
998 | Payroll Taxes | PR | 279 | 06/06/18 | 06/08/18 | CO71 | Cortes Mendiola, Victor H | 0 | 0 | 0 | 0 | 9.18 |  | 0 | 0
998 | Payroll Taxes | PR | 279 | 06/06/18 | 06/08/18 | CO71 | Cortes Mendiola, Victor H | 0 | 0 | 0 | 0 | 13.77 |  | 0 | 0
998 | Payroll Taxes | PR | 279 | 06/06/18 | 06/08/18 | CO71 | Cortes Mendiola, Victor H | 0 | 0 | 0 | 0 | 9.18 |  | 0 | 0
998 | Payroll Taxes | PR | 279 | 06/06/18 | 06/08/18 | CO71 | Cortes Mendiola, Victor H | 0 | 0 | 0 | 0 | 88.74 |  | 0 | 0
998 | Payroll Taxes | PR | 279 | 06/06/18 | 06/08/18 | CO71 | Cortes Mendiola, Victor H | 0 | 0 | 0 | 0 | 30.6 |  | 0 | 0
998 | Payroll Taxes | PR | 279 | 06/06/18 | 06/08/18 | CO71 | Cortes Mendiola, Victor H | 0 | 0 | 0 | 0 | 3.06 |  | 0 | 0
998 | Payroll Taxes | PR | 280 | 06/06/18 | 06/08/18 | CO73 | Cortes Sepulveda, Jose R | 0 | 0 | 0 | 0 | 21.11 |  | 0 | 0
998 | Payroll Taxes | PR | 280 | 06/06/18 | 06/08/18 | CO73 | Cortes Sepulveda, Jose R | 0 | 0 | 0 | 0 | 70.38 |  | 0 | 0
998 | Payroll Taxes | PR | 294 | 06/06/18 | 06/08/18 | GU78 | Gutierrez Salas, Jose | 0 | 0 | 0 | 0 | 44.06 |  | 0 | 0
998 | Payroll Taxes | PR | 301 | 06/06/18 | 06/08/18 | JU02 | Juarez Alvarez, Oscar R | 0 | 0 | 0 | 0 | 19.28 |  | 0 | 0
998 | Payroll Taxes | PR | 301 | 06/06/18 | 06/08/18 | JU02 | Juarez Alvarez, Oscar R | 0 | 0 | 0 | 0 | 85.68 |  | 0 | 0
998 | Payroll Taxes | PR | 302 | 06/06/18 | 06/08/18 | JU04 | Juarez Maldonado, Oscar E | 0 | 0 | 0 | 0 | 52.33 |  | 0 | 0
998 | Payroll Taxes | PR | 305 | 06/06/18 | 06/08/18 | LI49 | Lima Romero, Melvin A | 0 | 0 | 0 | 0 | 28.46 |  | 0 | 0
998 | Payroll Taxes | PR | 305 | 06/06/18 | 06/08/18 | LI49 | Lima Romero, Melvin A | 0 | 0 | 0 | 0 | 94.86 |  | 0 | 0
998 | Payroll Taxes | PR | 306 | 06/06/18 | 06/08/18 | LO58 | Lopez Reyes, Boris O | 0 | 0 | 0 | 0 | 24.79 |  | 0 | 0
998 | Payroll Taxes | PR | 340 | 06/06/18 | 06/08/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 3.83 |  | 0 | 0
998 | Payroll Taxes | PR | 459 | 06/13/18 | 06/15/18 | AS10 | Ascencio, Jose L | 0 | 0 | 0 | 0 | 23.87 |  | 0 | 0
998 | Payroll Taxes | PR | 459 | 06/13/18 | 06/15/18 | AS10 | Ascencio, Jose L | 0 | 0 | 0 | 0 | 79.56 |  | 0 | 0
998 | Payroll Taxes | PR | 461 | 06/13/18 | 06/15/18 | BA45 | Balderas Ortiz, Ricardo I | 0 | 0 | 0 | 0 | 25.7 |  | 0 | 0
998 | Payroll Taxes | PR | 461 | 06/13/18 | 06/15/18 | BA45 | Balderas Ortiz, Ricardo I | 0 | 0 | 0 | 0 | 85.68 |  | 0 | 0
998 | Payroll Taxes | PR | 469 | 06/13/18 | 06/15/18 | CO71 | Cortes Mendiola, Victor H | 0 | 0 | 0 | 0 | 23.52 |  | 0 | 0
998 | Payroll Taxes | PR | 469 | 06/13/18 | 06/15/18 | CO71 | Cortes Mendiola, Victor H | 0 | 0 | 0 | 0 | 4.7 |  | 0 | 0
998 | Payroll Taxes | PR | 469 | 06/13/18 | 06/15/18 | CO71 | Cortes Mendiola, Victor H | 0 | 0 | 0 | 0 | 109.78 |  | 0 | 0
998 | Payroll Taxes | PR | 469 | 06/13/18 | 06/15/18 | CO71 | Cortes Mendiola, Victor H | 0 | 0 | 0 | 0 | 15.68 |  | 0 | 0
998 | Payroll Taxes | PR | 470 | 06/13/18 | 06/15/18 | CO73 | Cortes Sepulveda, Jose R | 0 | 0 | 0 | 0 | 8.26 |  | 0 | 0
998 | Payroll Taxes | PR | 470 | 06/13/18 | 06/15/18 | CO73 | Cortes Sepulveda, Jose R | 0 | 0 | 0 | 0 | 73.44 |  | 0 | 0
998 | Payroll Taxes | PR | 484 | 06/13/18 | 06/15/18 | GU78 | Gutierrez Salas, Jose | 0 | 0 | 0 | 0 | 24.79 |  | 0 | 0
998 | Payroll Taxes | PR | 491 | 06/13/18 | 06/15/18 | JU02 | Juarez Alvarez, Oscar R | 0 | 0 | 0 | 0 | 88.74 |  | 0 | 0
998 | Payroll Taxes | PR | 492 | 06/13/18 | 06/15/18 | JU04 | Juarez Maldonado, Oscar E | 0 | 0 | 0 | 0 | 43.61 |  | 0 | 0
998 | Payroll Taxes | PR | 495 | 06/13/18 | 06/15/18 | LI49 | Lima Romero, Melvin A | 0 | 0 | 0 | 0 | 29.38 |  | 0 | 0
998 | Payroll Taxes | PR | 495 | 06/13/18 | 06/15/18 | LI49 | Lima Romero, Melvin A | 0 | 0 | 0 | 0 | 97.92 |  | 0 | 0
998 | Payroll Taxes | PR | 496 | 06/13/18 | 06/15/18 | LO58 | Lopez Reyes, Boris O | 0 | 0 | 0 | 0 | 1.38 |  | 0 | 0
998 | Payroll Taxes | PR | 528 | 06/13/18 | 06/15/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 3.83 |  | 0 | 0
998 | Payroll Taxes | PR | 528 | 06/13/18 | 06/15/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 7.65 |  | 0 | 0
998 | Payroll Taxes | PR | 685 | 06/20/18 | 06/22/18 | AS10 | Ascencio, Jose L | 0 | 0 | 0 | 0 | 17.9 |  | 0 | 0
998 | Payroll Taxes | PR | 685 | 06/20/18 | 06/22/18 | AS10 | Ascencio, Jose L | 0 | 0 | 0 | 0 | 79.56 |  | 0 | 0
998 | Payroll Taxes | PR | 687 | 06/20/18 | 06/22/18 | BA45 | Balderas Ortiz, Ricardo I | 0 | 0 | 0 | 0 | 25.7 |  | 0 | 0
998 | Payroll Taxes | PR | 687 | 06/20/18 | 06/22/18 | BA45 | Balderas Ortiz, Ricardo I | 0 | 0 | 0 | 0 | 85.68 |  | 0 | 0
998 | Payroll Taxes | PR | 695 | 06/20/18 | 06/22/18 | CO71 | Cortes Mendiola, Victor H | 0 | 0 | 0 | 0 | 4.7 |  | 0 | 0
998 | Payroll Taxes | PR | 695 | 06/20/18 | 06/22/18 | CO71 | Cortes Mendiola, Victor H | 0 | 0 | 0 | 0 | 14.11 |  | 0 | 0
998 | Payroll Taxes | PR | 695 | 06/20/18 | 06/22/18 | CO71 | Cortes Mendiola, Victor H | 0 | 0 | 0 | 0 | 9.41 |  | 0 | 0
998 | Payroll Taxes | PR | 695 | 06/20/18 | 06/22/18 | CO71 | Cortes Mendiola, Victor H | 0 | 0 | 0 | 0 | 4.7 |  | 0 | 0
998 | Payroll Taxes | PR | 695 | 06/20/18 | 06/22/18 | CO71 | Cortes Mendiola, Victor H | 0 | 0 | 0 | 0 | 112.91 |  | 0 | 0
998 | Payroll Taxes | PR | 695 | 06/20/18 | 06/22/18 | CO71 | Cortes Mendiola, Victor H | 0 | 0 | 0 | 0 | 12.55 |  | 0 | 0
998 | Payroll Taxes | PR | 696 | 06/20/18 | 06/22/18 | CO73 | Cortes Sepulveda, Jose R | 0 | 0 | 0 | 0 | 66.1 |  | 0 | 0
998 | Payroll Taxes | PR | 717 | 06/20/18 | 06/22/18 | JU02 | Juarez Alvarez, Oscar R | 0 | 0 | 0 | 0 | 19.97 |  | 0 | 0
998 | Payroll Taxes | PR | 717 | 06/20/18 | 06/22/18 | JU02 | Juarez Alvarez, Oscar R | 0 | 0 | 0 | 0 | 88.74 |  | 0 | 0
998 | Payroll Taxes | PR | 718 | 06/20/18 | 06/22/18 | JU04 | Juarez Maldonado, Oscar E | 0 | 0 | 0 | 0 | 52.33 |  | 0 | 0
998 | Payroll Taxes | PR | 721 | 06/20/18 | 06/22/18 | LI49 | Lima Romero, Melvin A | 0 | 0 | 0 | 0 | 93.02 |  | 0 | 0
998 | Payroll Taxes | PR | 754 | 06/20/18 | 06/22/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 3.83 |  | 0 | 0
998 | Payroll Taxes | PR | 950 | 06/27/18 | 06/29/18 | CO73 | Cortes Sepulveda, Jose R | 0 | 0 | 0 | 0 | 2.75 |  | 0 | 0
998 | Payroll Taxes | PR | 950 | 06/27/18 | 06/29/18 | CO73 | Cortes Sepulveda, Jose R | 0 | 0 | 0 | 0 | 11.02 |  | 0 | 0
998 | Payroll Taxes | PR | 950 | 06/27/18 | 06/29/18 | CO73 | Cortes Sepulveda, Jose R | 0 | 0 | 0 | 0 | 7.34 |  | 0 | 0
998 | Payroll Taxes | PR | 950 | 06/27/18 | 06/29/18 | CO73 | Cortes Sepulveda, Jose R | 0 | 0 | 0 | 0 | 44.06 |  | 0 | 0
998 | Payroll Taxes | PR | 951 | 06/27/18 | 06/29/18 | BA45 | Balderas Ortiz, Ricardo I | 0 | 0 | 0 | 0 | 25.7 |  | 0 | 0
998 | Payroll Taxes | PR | 951 | 06/27/18 | 06/29/18 | BA45 | Balderas Ortiz, Ricardo I | 0 | 0 | 0 | 0 | 85.68 |  | 0 | 0
998 | Payroll Taxes | PR | 954 | 06/27/18 | 06/29/18 | AS10 | Ascencio, Jose L | 0 | 0 | 0 | 0 | 23.87 |  | 0 | 0
998 | Payroll Taxes | PR | 954 | 06/27/18 | 06/29/18 | AS10 | Ascencio, Jose L | 0 | 0 | 0 | 0 | 79.56 |  | 0 | 0
998 | Payroll Taxes | PR | 963 | 06/27/18 | 06/29/18 | CO71 | Cortes Mendiola, Victor H | 0 | 0 | 0 | 0 | 9.41 |  | 0 | 0
998 | Payroll Taxes | PR | 963 | 06/27/18 | 06/29/18 | CO71 | Cortes Mendiola, Victor H | 0 | 0 | 0 | 0 | 9.41 |  | 0 | 0
998 | Payroll Taxes | PR | 963 | 06/27/18 | 06/29/18 | CO71 | Cortes Mendiola, Victor H | 0 | 0 | 0 | 0 | 4.7 |  | 0 | 0
998 | Payroll Taxes | PR | 963 | 06/27/18 | 06/29/18 | CO71 | Cortes Mendiola, Victor H | 0 | 0 | 0 | 0 | 75.28 |  | 0 | 0
998 | Payroll Taxes | PR | 963 | 06/27/18 | 06/29/18 | CO71 | Cortes Mendiola, Victor H | 0 | 0 | 0 | 0 | 3.14 |  | 0 | 0
998 | Payroll Taxes | PR | 963 | 06/27/18 | 06/29/18 | CO71 | Cortes Mendiola, Victor H | 0 | 0 | 0 | 0 | 9.41 |  | 0 | 0
998 | Payroll Taxes | PR | 983 | 06/27/18 | 06/29/18 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 7.19 |  | 0 | 0
998 | Payroll Taxes | PR | 985 | 06/27/18 | 06/29/18 | JU02 | Juarez Alvarez, Oscar R | 0 | 0 | 0 | 0 | 26.62 |  | 0 | 0
998 | Payroll Taxes | PR | 985 | 06/27/18 | 06/29/18 | JU02 | Juarez Alvarez, Oscar R | 0 | 0 | 0 | 0 | 88.74 |  | 0 | 0
998 | Payroll Taxes | PR | 986 | 06/27/18 | 06/29/18 | JU04 | Juarez Maldonado, Oscar E | 0 | 0 | 0 | 0 | 17.44 |  | 0 | 0
998 | Payroll Taxes | PR | 986 | 06/27/18 | 06/29/18 | JU04 | Juarez Maldonado, Oscar E | 0 | 0 | 0 | 0 | 58.14 |  | 0 | 0
998 | Payroll Taxes | PR | 989 | 06/27/18 | 06/29/18 | LI49 | Lima Romero, Melvin A | 0 | 0 | 0 | 0 | 29.38 |  | 0 | 0
998 | Payroll Taxes | PR | 989 | 06/27/18 | 06/29/18 | LI49 | Lima Romero, Melvin A | 0 | 0 | 0 | 0 | 97.92 |  | 0 | 0
998 | Payroll Taxes | PR | 1019 | 06/27/18 | 06/29/18 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 4.78 |  | 0 | 0
998 | Payroll Taxes | PR | 1019 | 06/27/18 | 06/29/18 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 9.56 |  | 0 | 0
998 | Payroll Taxes | PR | 1020 | 06/27/18 | 06/29/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 11.48 |  | 0 | 0
998 | Payroll Taxes | PR | 1020 | 06/27/18 | 06/29/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 3.83 |  | 0 | 0
998 | Payroll Taxes | PR | 6 | 07/04/18 | 07/06/18 | AS10 | Ascencio, Jose L | 0 | 0 | 0 | 0 | 63.65 |  | 0 | 0
998 | Payroll Taxes | PR | 16 | 07/04/18 | 07/06/18 | CO71 | Cortes Mendiola, Victor H | 0 | 0 | 0 | 0 | 100.37 |  | 0 | 0
998 | Payroll Taxes | PR | 17 | 07/04/18 | 07/06/18 | CO73 | Cortes Sepulveda, Jose R | 0 | 0 | 0 | 0 | 14.69 |  | 0 | 0
998 | Payroll Taxes | PR | 17 | 07/04/18 | 07/06/18 | CO73 | Cortes Sepulveda, Jose R | 0 | 0 | 0 | 0 | 13.77 |  | 0 | 0
998 | Payroll Taxes | PR | 38 | 07/04/18 | 07/06/18 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 7.19 |  | 0 | 0
998 | Payroll Taxes | PR | 38 | 07/04/18 | 07/06/18 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 10.79 |  | 0 | 0
998 | Payroll Taxes | PR | 40 | 07/04/18 | 07/06/18 | JU02 | Juarez Alvarez, Oscar R | 0 | 0 | 0 | 0 | 70.99 |  | 0 | 0
998 | Payroll Taxes | PR | 41 | 07/04/18 | 07/06/18 | JU04 | Juarez Maldonado, Oscar E | 0 | 0 | 0 | 0 | 34.88 |  | 0 | 0
998 | Payroll Taxes | PR | 44 | 07/04/18 | 07/06/18 | LI49 | Lima Romero, Melvin A | 0 | 0 | 0 | 0 | 78.34 |  | 0 | 0
998 | Payroll Taxes | PR | 76 | 07/04/18 | 07/06/18 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 23.91 |  | 0 | 0
998 | Payroll Taxes | PR | 77 | 07/04/18 | 07/06/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 3.83 |  | 0 | 0
998 | Payroll Taxes | PR | 299 | 07/11/18 | 07/13/18 | AS10 | Ascencio, Jose L | 0 | 0 | 0 | 0 | 67.63 |  | 0 | 0
998 | Payroll Taxes | PR | 300 | 07/11/18 | 07/13/18 | BA45 | Balderas Ortiz, Ricardo I | 0 | 0 | 0 | 0 | 34.27 |  | 0 | 0
998 | Payroll Taxes | PR | 307 | 07/11/18 | 07/13/18 | CO71 | Cortes Mendiola, Victor H | 0 | 0 | 0 | 0 | 75.28 |  | 0 | 0
998 | Payroll Taxes | PR | 307 | 07/11/18 | 07/13/18 | CO71 | Cortes Mendiola, Victor H | 0 | 0 | 0 | 0 | 14.11 |  | 0 | 0
998 | Payroll Taxes | PR | 308 | 07/11/18 | 07/13/18 | CO73 | Cortes Sepulveda, Jose R | 0 | 0 | 0 | 0 | 44.06 |  | 0 | 0
998 | Payroll Taxes | PR | 308 | 07/11/18 | 07/13/18 | CO73 | Cortes Sepulveda, Jose R | 0 | 0 | 0 | 0 | 11.02 |  | 0 | 0
998 | Payroll Taxes | PR | 329 | 07/11/18 | 07/13/18 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 7.19 |  | 0 | 0
998 | Payroll Taxes | PR | 329 | 07/11/18 | 07/13/18 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 17.98 |  | 0 | 0
998 | Payroll Taxes | PR | 331 | 07/11/18 | 07/13/18 | JU02 | Juarez Alvarez, Oscar R | 0 | 0 | 0 | 0 | 53.24 |  | 0 | 0
998 | Payroll Taxes | PR | 331 | 07/11/18 | 07/13/18 | JU02 | Juarez Alvarez, Oscar R | 0 | 0 | 0 | 0 | 17.75 |  | 0 | 0
998 | Payroll Taxes | PR | 332 | 07/11/18 | 07/13/18 | JU04 | Juarez Maldonado, Oscar E | 0 | 0 | 0 | 0 | 46.51 |  | 0 | 0
998 | Payroll Taxes | PR | 335 | 07/11/18 | 07/13/18 | LI49 | Lima Romero, Melvin A | 0 | 0 | 0 | 0 | 97.92 |  | 0 | 0
998 | Payroll Taxes | PR | 367 | 07/11/18 | 07/13/18 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 4.78 |  | 0 | 0
998 | Payroll Taxes | PR | 438 | 07/18/18 | 07/20/18 | AS10 | Ascencio, Jose L | 0 | 0 | 0 | 0 | 11.93 |  | 0 | 0
998 | Payroll Taxes | PR | 438 | 07/18/18 | 07/20/18 | AS10 | Ascencio, Jose L | 0 | 0 | 0 | 0 | 79.56 |  | 0 | 0
998 | Payroll Taxes | PR | 439 | 07/18/18 | 07/20/18 | BA45 | Balderas Ortiz, Ricardo I | 0 | 0 | 0 | 0 | 34.27 |  | 0 | 0
998 | Payroll Taxes | PR | 439 | 07/18/18 | 07/20/18 | BA45 | Balderas Ortiz, Ricardo I | 0 | 0 | 0 | 0 | 34.27 |  | 0 | 0
998 | Payroll Taxes | PR | 447 | 07/18/18 | 07/20/18 | CO71 | Cortes Mendiola, Victor H | 0 | 0 | 0 | 0 | 4.7 |  | 0 | 0
998 | Payroll Taxes | PR | 447 | 07/18/18 | 07/20/18 | CO71 | Cortes Mendiola, Victor H | 0 | 0 | 0 | 0 | 75.28 |  | 0 | 0
998 | Payroll Taxes | PR | 447 | 07/18/18 | 07/20/18 | CO71 | Cortes Mendiola, Victor H | 0 | 0 | 0 | 0 | 25.09 |  | 0 | 0
998 | Payroll Taxes | PR | 448 | 07/18/18 | 07/20/18 | CO73 | Cortes Sepulveda, Jose R | 0 | 0 | 0 | 0 | 5.51 |  | 0 | 0
998 | Payroll Taxes | PR | 448 | 07/18/18 | 07/20/18 | CO73 | Cortes Sepulveda, Jose R | 0 | 0 | 0 | 0 | 29.38 |  | 0 | 0
998 | Payroll Taxes | PR | 448 | 07/18/18 | 07/20/18 | CO73 | Cortes Sepulveda, Jose R | 0 | 0 | 0 | 0 | 29.38 |  | 0 | 0
998 | Payroll Taxes | PR | 472 | 07/18/18 | 07/20/18 | JU02 | Juarez Alvarez, Oscar R | 0 | 0 | 0 | 0 | 53.24 |  | 0 | 0
998 | Payroll Taxes | PR | 472 | 07/18/18 | 07/20/18 | JU02 | Juarez Alvarez, Oscar R | 0 | 0 | 0 | 0 | 15.53 |  | 0 | 0
998 | Payroll Taxes | PR | 472 | 07/18/18 | 07/20/18 | JU02 | Juarez Alvarez, Oscar R | 0 | 0 | 0 | 0 | 17.75 |  | 0 | 0
998 | Payroll Taxes | PR | 473 | 07/18/18 | 07/20/18 | JU04 | Juarez Maldonado, Oscar E | 0 | 0 | 0 | 0 | 33.43 |  | 0 | 0
998 | Payroll Taxes | PR | 473 | 07/18/18 | 07/20/18 | JU04 | Juarez Maldonado, Oscar E | 0 | 0 | 0 | 0 | 10.17 |  | 0 | 0
998 | Payroll Taxes | PR | 473 | 07/18/18 | 07/20/18 | JU04 | Juarez Maldonado, Oscar E | 0 | 0 | 0 | 0 | 11.63 |  | 0 | 0
998 | Payroll Taxes | PR | 476 | 07/18/18 | 07/20/18 | LI49 | Lima Romero, Melvin A | 0 | 0 | 0 | 0 | 7.34 |  | 0 | 0
998 | Payroll Taxes | PR | 476 | 07/18/18 | 07/20/18 | LI49 | Lima Romero, Melvin A | 0 | 0 | 0 | 0 | 7.34 |  | 0 | 0
998 | Payroll Taxes | PR | 476 | 07/18/18 | 07/20/18 | LI49 | Lima Romero, Melvin A | 0 | 0 | 0 | 0 | 39.17 |  | 0 | 0
998 | Payroll Taxes | PR | 476 | 07/18/18 | 07/20/18 | LI49 | Lima Romero, Melvin A | 0 | 0 | 0 | 0 | 58.75 |  | 0 | 0
998 | Payroll Taxes | PR | 507 | 07/18/18 | 07/20/18 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 4.78 |  | 0 | 0
998 | Payroll Taxes | PR | 764 | 07/25/18 | 07/27/18 | AS10 | Ascencio, Jose L | 0 | 0 | 0 | 0 | 79.56 |  | 0 | 0
998 | Payroll Taxes | PR | 765 | 07/25/18 | 07/27/18 | BA45 | Balderas Ortiz, Ricardo I | 0 | 0 | 0 | 0 | 85.68 |  | 0 | 0
998 | Payroll Taxes | PR | 773 | 07/25/18 | 07/27/18 | CO71 | Cortes Mendiola, Victor H | 0 | 0 | 0 | 0 | 18.82 |  | 0 | 0
998 | Payroll Taxes | PR | 773 | 07/25/18 | 07/27/18 | CO71 | Cortes Mendiola, Victor H | 0 | 0 | 0 | 0 | 31.37 |  | 0 | 0
998 | Payroll Taxes | PR | 774 | 07/25/18 | 07/27/18 | CO73 | Cortes Sepulveda, Jose R | 0 | 0 | 0 | 0 | 29.38 |  | 0 | 0
998 | Payroll Taxes | PR | 797 | 07/25/18 | 07/27/18 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 17.98 |  | 0 | 0
998 | Payroll Taxes | PR | 799 | 07/25/18 | 07/27/18 | JU02 | Juarez Alvarez, Oscar R | 0 | 0 | 0 | 0 | 53.24 |  | 0 | 0
998 | Payroll Taxes | PR | 800 | 07/25/18 | 07/27/18 | JU04 | Juarez Maldonado, Oscar E | 0 | 0 | 0 | 0 | 29.07 |  | 0 | 0
998 | Payroll Taxes | PR | 803 | 07/25/18 | 07/27/18 | LI49 | Lima Romero, Melvin A | 0 | 0 | 0 | 0 | 19.58 |  | 0 | 0
998 | Payroll Taxes | PR | 803 | 07/25/18 | 07/27/18 | LI49 | Lima Romero, Melvin A | 0 | 0 | 0 | 0 | 58.75 |  | 0 | 0
998 | Payroll Taxes | PR | 835 | 07/25/18 | 07/27/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 7.65 |  | 0 | 0
998 | Payroll Taxes | PR | 835 | 07/25/18 | 07/27/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 3.83 |  | 0 | 0
998 | Payroll Taxes | PR | 3 | 08/01/18 | 08/03/18 | AS10 | Ascencio, Jose L | 0 | 0 | 0 | 0 | 79.56 |  | 0 | 0
998 | Payroll Taxes | PR | 4 | 08/01/18 | 08/03/18 | BA45 | Balderas Ortiz, Ricardo I | 0 | 0 | 0 | 0 | 85.68 |  | 0 | 0
998 | Payroll Taxes | PR | 12 | 08/01/18 | 08/03/18 | CO71 | Cortes Mendiola, Victor H | 0 | 0 | 0 | 0 | 50.18 |  | 0 | 0
998 | Payroll Taxes | PR | 13 | 08/01/18 | 08/03/18 | CO73 | Cortes Sepulveda, Jose R | 0 | 0 | 0 | 0 | 14.69 |  | 0 | 0
998 | Payroll Taxes | PR | 13 | 08/01/18 | 08/03/18 | CO73 | Cortes Sepulveda, Jose R | 0 | 0 | 0 | 0 | 14.69 |  | 0 | 0
998 | Payroll Taxes | PR | 35 | 08/01/18 | 08/03/18 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 7.19 |  | 0 | 0
998 | Payroll Taxes | PR | 37 | 08/01/18 | 08/03/18 | JU02 | Juarez Alvarez, Oscar R | 0 | 0 | 0 | 0 | 80.78 |  | 0 | 0
998 | Payroll Taxes | PR | 38 | 08/01/18 | 08/03/18 | JU04 | Juarez Maldonado, Oscar E | 0 | 0 | 0 | 0 | 46.51 |  | 0 | 0
998 | Payroll Taxes | PR | 41 | 08/01/18 | 08/03/18 | LI49 | Lima Romero, Melvin A | 0 | 0 | 0 | 0 | 58.75 |  | 0 | 0
998 | Payroll Taxes | PR | 41 | 08/01/18 | 08/03/18 | LI49 | Lima Romero, Melvin A | 0 | 0 | 0 | 0 | 39.17 |  | 0 | 0
998 | Payroll Taxes | PR | 72 | 08/01/18 | 08/03/18 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 4.78 |  | 0 | 0
998 | Payroll Taxes | PR | 213 | 08/08/18 | 08/10/18 | AS10 | Ascencio, Jose L | 0 | 0 | 0 | 0 | 79.56 |  | 0 | 0
998 | Payroll Taxes | PR | 214 | 08/08/18 | 08/10/18 | BA45 | Balderas Ortiz, Ricardo I | 0 | 0 | 0 | 0 | 51.41 |  | 0 | 0
998 | Payroll Taxes | PR | 214 | 08/08/18 | 08/10/18 | BA45 | Balderas Ortiz, Ricardo I | 0 | 0 | 0 | 0 | 17.14 |  | 0 | 0
998 | Payroll Taxes | PR | 222 | 08/08/18 | 08/10/18 | CO71 | Cortes Mendiola, Victor H | 0 | 0 | 0 | 0 | 50.18 |  | 0 | 0
998 | Payroll Taxes | PR | 222 | 08/08/18 | 08/10/18 | CO71 | Cortes Mendiola, Victor H | 0 | 0 | 0 | 0 | 12.55 |  | 0 | 0
998 | Payroll Taxes | PR | 222 | 08/08/18 | 08/10/18 | CO71 | Cortes Mendiola, Victor H | 0 | 0 | 0 | 0 | 12.55 |  | 0 | 0
998 | Payroll Taxes | PR | 223 | 08/08/18 | 08/10/18 | CO73 | Cortes Sepulveda, Jose R | 0 | 0 | 0 | 0 | 22.03 |  | 0 | 0
998 | Payroll Taxes | PR | 223 | 08/08/18 | 08/10/18 | CO73 | Cortes Sepulveda, Jose R | 0 | 0 | 0 | 0 | 7.34 |  | 0 | 0
998 | Payroll Taxes | PR | 246 | 08/08/18 | 08/10/18 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 7.19 |  | 0 | 0
998 | Payroll Taxes | PR | 248 | 08/08/18 | 08/10/18 | JU02 | Juarez Alvarez, Oscar R | 0 | 0 | 0 | 0 | 100.98 |  | 0 | 0
998 | Payroll Taxes | PR | 249 | 08/08/18 | 08/10/18 | JU04 | Juarez Maldonado, Oscar E | 0 | 0 | 0 | 0 | 34.88 |  | 0 | 0
998 | Payroll Taxes | PR | 252 | 08/08/18 | 08/10/18 | LI49 | Lima Romero, Melvin A | 0 | 0 | 0 | 0 | 58.75 |  | 0 | 0
998 | Payroll Taxes | PR | 252 | 08/08/18 | 08/10/18 | LI49 | Lima Romero, Melvin A | 0 | 0 | 0 | 0 | 39.17 |  | 0 | 0
998 | Payroll Taxes | PR | 255 | 08/08/18 | 08/10/18 | LU09 | Lucas Tzintzun, Rafael | 0 | 0 | 0 | 0 | 20.81 |  | 0 | 0
998 | Payroll Taxes | PR | 275 | 08/08/18 | 08/10/18 | SI48 | Silva Morales, Jair J | 0 | 0 | 0 | 0 | 23.87 |  | 0 | 0
998 | Payroll Taxes | PR | 283 | 08/08/18 | 08/10/18 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 4.78 |  | 0 | 0
998 | Payroll Taxes | PR | 284 | 08/08/18 | 08/10/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 3.83 |  | 0 | 0
998 | Payroll Taxes | PR | 481 | 08/15/18 | 08/17/18 | AS10 | Ascencio, Jose L | 0 | 0 | 0 | 0 | 79.56 |  | 0 | 0
998 | Payroll Taxes | PR | 482 | 08/15/18 | 08/17/18 | BA45 | Balderas Ortiz, Ricardo I | 0 | 0 | 0 | 0 | 51.41 |  | 0 | 0
998 | Payroll Taxes | PR | 482 | 08/15/18 | 08/17/18 | BA45 | Balderas Ortiz, Ricardo I | 0 | 0 | 0 | 0 | 34.27 |  | 0 | 0
998 | Payroll Taxes | PR | 490 | 08/15/18 | 08/17/18 | CO71 | Cortes Mendiola, Victor H | 0 | 0 | 0 | 0 | 31.37 |  | 0 | 0
998 | Payroll Taxes | PR | 490 | 08/15/18 | 08/17/18 | CO71 | Cortes Mendiola, Victor H | 0 | 0 | 0 | 0 | 81.55 |  | 0 | 0
998 | Payroll Taxes | PR | 491 | 08/15/18 | 08/17/18 | CO73 | Cortes Sepulveda, Jose R | 0 | 0 | 0 | 0 | 51.41 |  | 0 | 0
998 | Payroll Taxes | PR | 491 | 08/15/18 | 08/17/18 | CO73 | Cortes Sepulveda, Jose R | 0 | 0 | 0 | 0 | 14.69 |  | 0 | 0
998 | Payroll Taxes | PR | 514 | 08/15/18 | 08/17/18 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 14.38 |  | 0 | 0
998 | Payroll Taxes | PR | 516 | 08/15/18 | 08/17/18 | JU02 | Juarez Alvarez, Oscar R | 0 | 0 | 0 | 0 | 40.39 |  | 0 | 0
998 | Payroll Taxes | PR | 519 | 08/15/18 | 08/17/18 | LI49 | Lima Romero, Melvin A | 0 | 0 | 0 | 0 | 97.92 |  | 0 | 0
998 | Payroll Taxes | PR | 522 | 08/15/18 | 08/17/18 | LU09 | Lucas Tzintzun, Rafael | 0 | 0 | 0 | 0 | 31.21 |  | 0 | 0
998 | Payroll Taxes | PR | 522 | 08/15/18 | 08/17/18 | LU09 | Lucas Tzintzun, Rafael | 0 | 0 | 0 | 0 | 20.81 |  | 0 | 0
998 | Payroll Taxes | PR | 542 | 08/15/18 | 08/17/18 | SI48 | Silva Morales, Jair J | 0 | 0 | 0 | 0 | 73.44 |  | 0 | 0
998 | Payroll Taxes | PR | 550 | 08/15/18 | 08/17/18 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 9.56 |  | 0 | 0
998 | Payroll Taxes | PR | 743 | 08/22/18 | 08/24/18 | AS10 | Ascencio, Jose L | 0 | 0 | 0 | 0 | 63.65 |  | 0 | 0
998 | Payroll Taxes | PR | 744 | 08/22/18 | 08/24/18 | BA45 | Balderas Ortiz, Ricardo I | 0 | 0 | 0 | 0 | 85.68 |  | 0 | 0
998 | Payroll Taxes | PR | 752 | 08/22/18 | 08/24/18 | CO71 | Cortes Mendiola, Victor H | 0 | 0 | 0 | 0 | 100.37 |  | 0 | 0
998 | Payroll Taxes | PR | 753 | 08/22/18 | 08/24/18 | CO73 | Cortes Sepulveda, Jose R | 0 | 0 | 0 | 0 | 53.24 |  | 0 | 0
998 | Payroll Taxes | PR | 780 | 08/22/18 | 08/24/18 | LI49 | Lima Romero, Melvin A | 0 | 0 | 0 | 0 | 58.75 |  | 0 | 0
998 | Payroll Taxes | PR | 783 | 08/22/18 | 08/24/18 | LU09 | Lucas Tzintzun, Rafael | 0 | 0 | 0 | 0 | 20.81 |  | 0 | 0
998 | Payroll Taxes | PR | 803 | 08/22/18 | 08/24/18 | SI48 | Silva Morales, Jair J | 0 | 0 | 0 | 0 | 29.38 |  | 0 | 0
998 | Payroll Taxes | PR | 803 | 08/22/18 | 08/24/18 | SI48 | Silva Morales, Jair J | 0 | 0 | 0 | 0 | 29.38 |  | 0 | 0
998 | Payroll Taxes | PR | 803 | 08/22/18 | 08/24/18 | SI48 | Silva Morales, Jair J | 0 | 0 | 0 | 0 | 14.69 |  | 0 | 0
998 | Payroll Taxes | PR | 811 | 08/22/18 | 08/24/18 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 23.91 |  | 0 | 0
998 | Payroll Taxes | PR | 997 | 08/29/18 | 08/31/18 | AS10 | Ascencio, Jose L | 0 | 0 | 0 | 0 | 79.56 |  | 0 | 0
998 | Payroll Taxes | PR | 998 | 08/29/18 | 08/31/18 | BA45 | Balderas Ortiz, Ricardo I | 0 | 0 | 0 | 0 | 68.54 |  | 0 | 0
998 | Payroll Taxes | PR | 1006 | 08/29/18 | 08/31/18 | CO71 | Cortes Mendiola, Victor H | 0 | 0 | 0 | 0 | 90.96 |  | 0 | 0
998 | Payroll Taxes | PR | 1006 | 08/29/18 | 08/31/18 | CO71 | Cortes Mendiola, Victor H | 0 | 0 | 0 | 0 | 9.41 |  | 0 | 0
998 | Payroll Taxes | PR | 1007 | 08/29/18 | 08/31/18 | CO73 | Cortes Sepulveda, Jose R | 0 | 0 | 0 | 0 | 44.06 |  | 0 | 0
998 | Payroll Taxes | PR | 1007 | 08/29/18 | 08/31/18 | CO73 | Cortes Sepulveda, Jose R | 0 | 0 | 0 | 0 | 7.34 |  | 0 | 0
998 | Payroll Taxes | PR | 1031 | 08/29/18 | 08/31/18 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 3.6 |  | 0 | 0
998 | Payroll Taxes | PR | 1057 | 08/29/18 | 08/31/18 | SI48 | Silva Morales, Jair J | 0 | 0 | 0 | 0 | 29.38 |  | 0 | 0
998 | Payroll Taxes | PR | 1057 | 08/29/18 | 08/31/18 | SI48 | Silva Morales, Jair J | 0 | 0 | 0 | 0 | 14.69 |  | 0 | 0
998 | Payroll Taxes | PR | 1057 | 08/29/18 | 08/31/18 | SI48 | Silva Morales, Jair J | 0 | 0 | 0 | 0 | 29.38 |  | 0 | 0
998 | Payroll Taxes | PR | 1069 | 08/29/18 | 08/31/18 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 4.78 |  | 0 | 0
998 | Payroll Taxes | PR | 38 | 09/05/18 | 09/07/18 | AS10 | Ascencio, Jose L | 0 | 0 | 0 | 0 | 63.65 |  | 0 | 0
998 | Payroll Taxes | PR | 39 | 09/05/18 | 09/07/18 | BA45 | Balderas Ortiz, Ricardo I | 0 | 0 | 0 | 0 | 68.54 |  | 0 | 0
998 | Payroll Taxes | PR | 47 | 09/05/18 | 09/07/18 | CO71 | Cortes Mendiola, Victor H | 0 | 0 | 0 | 0 | 9.41 |  | 0 | 0
998 | Payroll Taxes | PR | 47 | 09/05/18 | 09/07/18 | CO71 | Cortes Mendiola, Victor H | 0 | 0 | 0 | 0 | 25.09 |  | 0 | 0
998 | Payroll Taxes | PR | 48 | 09/05/18 | 09/07/18 | CO73 | Cortes Sepulveda, Jose R | 0 | 0 | 0 | 0 | 38.56 |  | 0 | 0
998 | Payroll Taxes | PR | 48 | 09/05/18 | 09/07/18 | CO73 | Cortes Sepulveda, Jose R | 0 | 0 | 0 | 0 | 14.69 |  | 0 | 0
998 | Payroll Taxes | PR | 97 | 09/05/18 | 09/07/18 | SI48 | Silva Morales, Jair J | 0 | 0 | 0 | 0 | 29.38 |  | 0 | 0
998 | Payroll Taxes | PR | 97 | 09/05/18 | 09/07/18 | SI48 | Silva Morales, Jair J | 0 | 0 | 0 | 0 | 14.69 |  | 0 | 0
998 | Payroll Taxes | PR | 269 | 09/12/18 | 09/14/18 | AS10 | Ascencio, Jose L | 0 | 0 | 0 | 0 | 79.56 |  | 0 | 0
998 | Payroll Taxes | PR | 270 | 09/12/18 | 09/14/18 | BA45 | Balderas Ortiz, Ricardo I | 0 | 0 | 0 | 0 | 85.68 |  | 0 | 0
998 | Payroll Taxes | PR | 278 | 09/12/18 | 09/14/18 | CO71 | Cortes Mendiola, Victor H | 0 | 0 | 0 | 0 | 25.09 |  | 0 | 0
998 | Payroll Taxes | PR | 279 | 09/12/18 | 09/14/18 | CO73 | Cortes Sepulveda, Jose R | 0 | 0 | 0 | 0 | 29.38 |  | 0 | 0
998 | Payroll Taxes | PR | 279 | 09/12/18 | 09/14/18 | CO73 | Cortes Sepulveda, Jose R | 0 | 0 | 0 | 0 | 14.69 |  | 0 | 0
998 | Payroll Taxes | PR | 297 | 09/12/18 | 09/14/18 | GU78 | Gutierrez Salas, Jose | 0 | 0 | 0 | 0 | 49.57 |  | 0 | 0
998 | Payroll Taxes | PR | 302 | 09/12/18 | 09/14/18 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 10.79 |  | 0 | 0
998 | Payroll Taxes | PR | 302 | 09/12/18 | 09/14/18 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 14.38 |  | 0 | 0
998 | Payroll Taxes | PR | 329 | 09/12/18 | 09/14/18 | SI48 | Silva Morales, Jair J | 0 | 0 | 0 | 0 | 58.75 |  | 0 | 0
998 | Payroll Taxes | PR | 329 | 09/12/18 | 09/14/18 | SI48 | Silva Morales, Jair J | 0 | 0 | 0 | 0 | 14.69 |  | 0 | 0
998 | Payroll Taxes | PR | 340 | 09/12/18 | 09/14/18 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 4.78 |  | 0 | 0
998 | Payroll Taxes | PR | 340 | 09/12/18 | 09/14/18 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 4.78 |  | 0 | 0
998 | Payroll Taxes | PR | 483 | 09/19/18 | 09/21/18 | AS10 | Ascencio, Jose L | 0 | 0 | 0 | 0 | 79.56 |  | 0 | 0
998 | Payroll Taxes | PR | 484 | 09/19/18 | 09/21/18 | BA45 | Balderas Ortiz, Ricardo I | 0 | 0 | 0 | 0 | 51.41 |  | 0 | 0
998 | Payroll Taxes | PR | 484 | 09/19/18 | 09/21/18 | BA45 | Balderas Ortiz, Ricardo I | 0 | 0 | 0 | 0 | 17.14 |  | 0 | 0
998 | Payroll Taxes | PR | 491 | 09/19/18 | 09/21/18 | CO71 | Cortes Mendiola, Victor H | 0 | 0 | 0 | 0 | 50.18 |  | 0 | 0
998 | Payroll Taxes | PR | 491 | 09/19/18 | 09/21/18 | CO71 | Cortes Mendiola, Victor H | 0 | 0 | 0 | 0 | 69 |  | 0 | 0
998 | Payroll Taxes | PR | 492 | 09/19/18 | 09/21/18 | CO73 | Cortes Sepulveda, Jose R | 0 | 0 | 0 | 0 | 44.06 |  | 0 | 0
998 | Payroll Taxes | PR | 492 | 09/19/18 | 09/21/18 | CO73 | Cortes Sepulveda, Jose R | 0 | 0 | 0 | 0 | 11.02 |  | 0 | 0
998 | Payroll Taxes | PR | 510 | 09/19/18 | 09/21/18 | GU78 | Gutierrez Salas, Jose | 0 | 0 | 0 | 0 | 55.08 |  | 0 | 0
998 | Payroll Taxes | PR | 515 | 09/19/18 | 09/21/18 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 25.17 |  | 0 | 0
998 | Payroll Taxes | PR | 540 | 09/19/18 | 09/21/18 | SA54 | Sanders, Allen O | 0 | 0 | 0 | 0 | 13.46 |  | 0 | 0
998 | Payroll Taxes | PR | 542 | 09/19/18 | 09/21/18 | SI48 | Silva Morales, Jair J | 0 | 0 | 0 | 0 | 73.44 |  | 0 | 0
998 | Payroll Taxes | PR | 552 | 09/19/18 | 09/21/18 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 4.78 |  | 0 | 0
998 | Payroll Taxes | PR | 667 | 09/26/18 | 09/28/18 | AS10 | Ascencio, Jose L | 0 | 0 | 0 | 0 | 15.91 |  | 0 | 0
998 | Payroll Taxes | PR | 667 | 09/26/18 | 09/28/18 | AS10 | Ascencio, Jose L | 0 | 0 | 0 | 0 | 47.74 |  | 0 | 0
998 | Payroll Taxes | PR | 667 | 09/26/18 | 09/28/18 | AS10 | Ascencio, Jose L | 0 | 0 | 0 | 0 | 15.91 |  | 0 | 0
998 | Payroll Taxes | PR | 668 | 09/26/18 | 09/28/18 | BA45 | Balderas Ortiz, Ricardo I | 0 | 0 | 0 | 0 | 17.14 |  | 0 | 0
998 | Payroll Taxes | PR | 668 | 09/26/18 | 09/28/18 | BA45 | Balderas Ortiz, Ricardo I | 0 | 0 | 0 | 0 | 51.41 |  | 0 | 0
998 | Payroll Taxes | PR | 668 | 09/26/18 | 09/28/18 | BA45 | Balderas Ortiz, Ricardo I | 0 | 0 | 0 | 0 | 17.14 |  | 0 | 0
998 | Payroll Taxes | PR | 676 | 09/26/18 | 09/28/18 | CO71 | Cortes Mendiola, Victor H | 0 | 0 | 0 | 0 | 90.96 |  | 0 | 0
998 | Payroll Taxes | PR | 677 | 09/26/18 | 09/28/18 | CO73 | Cortes Sepulveda, Jose R | 0 | 0 | 0 | 0 | 53.24 |  | 0 | 0
998 | Payroll Taxes | PR | 695 | 09/26/18 | 09/28/18 | GU78 | Gutierrez Salas, Jose | 0 | 0 | 0 | 0 | 22.03 |  | 0 | 0
998 | Payroll Taxes | PR | 695 | 09/26/18 | 09/28/18 | GU78 | Gutierrez Salas, Jose | 0 | 0 | 0 | 0 | 22.03 |  | 0 | 0
998 | Payroll Taxes | PR | 700 | 09/26/18 | 09/28/18 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 14.38 |  | 0 | 0
998 | Payroll Taxes | PR | 700 | 09/26/18 | 09/28/18 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 3.6 |  | 0 | 0
998 | Payroll Taxes | PR | 31 | 10/03/18 | 10/05/18 | AS10 | Ascencio, Jose L | 0 | 0 | 0 | 0 | 79.56 |  | 0 | 0
998 | Payroll Taxes | PR | 32 | 10/03/18 | 10/05/18 | BA45 | Balderas Ortiz, Ricardo I | 0 | 0 | 0 | 0 | 85.68 |  | 0 | 0
998 | Payroll Taxes | PR | 40 | 10/03/18 | 10/05/18 | CO71 | Cortes Mendiola, Victor H | 0 | 0 | 0 | 0 | 87.82 |  | 0 | 0
998 | Payroll Taxes | PR | 41 | 10/03/18 | 10/05/18 | CO73 | Cortes Sepulveda, Jose R | 0 | 0 | 0 | 0 | 29.38 |  | 0 | 0
998 | Payroll Taxes | PR | 59 | 10/03/18 | 10/05/18 | GU78 | Gutierrez Salas, Jose | 0 | 0 | 0 | 0 | 42.69 |  | 0 | 0
998 | Payroll Taxes | PR | 102 | 10/03/18 | 10/05/18 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 14.34 |  | 0 | 0
998 | Payroll Taxes | PR | 237 | 10/10/18 | 10/12/18 | BA45 | Balderas Ortiz, Ricardo I | 0 | 0 | 0 | 0 | 51.41 |  | 0 | 0
998 | Payroll Taxes | PR | 245 | 10/10/18 | 10/12/18 | CO71 | Cortes Mendiola, Victor H | 0 | 0 | 0 | 0 | 25.09 |  | 0 | 0
998 | Payroll Taxes | PR | 246 | 10/10/18 | 10/12/18 | CO73 | Cortes Sepulveda, Jose R | 0 | 0 | 0 | 0 | 14.69 |  | 0 | 0
998 | Payroll Taxes | PR | 265 | 10/10/18 | 10/12/18 | GU78 | Gutierrez Salas, Jose | 0 | 0 | 0 | 0 | 22.03 |  | 0 | 0
998 | Payroll Taxes | PR | 436 | 10/17/18 | 10/19/18 | BA45 | Balderas Ortiz, Ricardo I | 0 | 0 | 0 | 0 | 68.54 |  | 0 | 0
998 | Payroll Taxes | PR | 444 | 10/17/18 | 10/19/18 | CO71 | Cortes Mendiola, Victor H | 0 | 0 | 0 | 0 | 62.73 |  | 0 | 0
998 | Payroll Taxes | PR | 445 | 10/17/18 | 10/19/18 | CO73 | Cortes Sepulveda, Jose R | 0 | 0 | 0 | 0 | 36.72 |  | 0 | 0
998 | Payroll Taxes | PR | 468 | 10/17/18 | 10/19/18 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 7.19 |  | 0 | 0
998 | Payroll Taxes | PR | 507 | 10/17/18 | 10/19/18 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 4.78 |  | 0 | 0
998 | Payroll Taxes | PR | 712 | 10/24/18 | 10/26/18 | CO71 | Cortes Mendiola, Victor H | 0 | 0 | 0 | 0 | 62.73 |  | 0 | 0
998 | Payroll Taxes | PR | 713 | 10/24/18 | 10/26/18 | CO73 | Cortes Sepulveda, Jose R | 0 | 0 | 0 | 0 | 29.38 |  | 0 | 0
998 | Payroll Taxes | PR | 774 | 10/24/18 | 10/26/18 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 14.34 |  | 0 | 0
998 | Payroll Taxes | PR | 14 | 10/31/18 | 11/02/18 | CO71 | Cortes Mendiola, Victor H | 0 | 0 | 0 | 0 | 25.09 |  | 0 | 0
998 | Payroll Taxes | PR | 14 | 10/31/18 | 11/02/18 | CO71 | Cortes Mendiola, Victor H | 0 | 0 | 0 | 0 | 31.37 |  | 0 | 0
998 | Payroll Taxes | PR | 15 | 10/31/18 | 11/02/18 | CO73 | Cortes Sepulveda, Jose R | 0 | 0 | 0 | 0 | 14.69 |  | 0 | 0
998 | Payroll Taxes | PR | 15 | 10/31/18 | 11/02/18 | CO73 | Cortes Sepulveda, Jose R | 0 | 0 | 0 | 0 | 18.36 |  | 0 | 0
998 | Payroll Taxes | PR | 76 | 10/31/18 | 11/02/18 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 28.69 |  | 0 | 0
998 | Payroll Taxes | PR | 77 | 10/31/18 | 11/02/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 3.83 |  | 0 | 0
998 | Payroll Taxes | PR | 192 | 11/07/18 | 11/09/18 | CO71 | Cortes Mendiola, Victor H | 0 | 0 | 0 | 0 | 65.87 |  | 0 | 0
998 | Payroll Taxes | PR | 193 | 11/07/18 | 11/09/18 | CO73 | Cortes Sepulveda, Jose R | 0 | 0 | 0 | 0 | 38.56 |  | 0 | 0
998 | Payroll Taxes | PR | 257 | 11/07/18 | 11/09/18 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 33.47 |  | 0 | 0
998 | Payroll Taxes | PR | 441 | 11/14/18 | 11/16/18 | CO71 | Cortes Mendiola, Victor H | 0 | 0 | 0 | 0 | 25.09 |  | 0 | 0
998 | Payroll Taxes | PR | 442 | 11/14/18 | 11/16/18 | CO73 | Cortes Sepulveda, Jose R | 0 | 0 | 0 | 0 | 14.69 |  | 0 | 0
998 | Payroll Taxes | PR | 450 | 11/14/18 | 11/16/18 | EL33 | Eliassen, Cory H | 0 | 0 | 0 | 0 | 14.08 |  | 0 | 0
998 | Payroll Taxes | PR | 452 | 11/14/18 | 11/16/18 | FO55 | Fonseca Teruel, Eduardo | 0 | 0 | 0 | 0 | 22.03 |  | 0 | 0
998 | Payroll Taxes | PR | 458 | 11/14/18 | 11/16/18 | GO51 | Gomez Reyes, Edith N | 0 | 0 | 0 | 0 | 25.7 |  | 0 | 0
998 | Payroll Taxes | PR | 483 | 11/14/18 | 11/16/18 | RE91 | Reyes, Maria E | 0 | 0 | 0 | 0 | 19.58 |  | 0 | 0
998 | Payroll Taxes | PR | 490 | 11/14/18 | 11/16/18 | SA54 | Sanders, Allen O | 0 | 0 | 0 | 0 | 23.56 |  | 0 | 0
998 | Payroll Taxes | PR | 494 | 11/14/18 | 11/16/18 | ST02 | Stahlschmidt, John P | 0 | 0 | 0 | 0 | 9.79 |  | 0 | 0
998 | Payroll Taxes | PR | 502 | 11/14/18 | 11/16/18 | YO29 | Yohannes Jr., Samson | 0 | 0 | 0 | 0 | 11.02 |  | 0 | 0
998 | Payroll Taxes | PR | 513 | 11/14/18 | 11/16/18 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 14.34 |  | 0 | 0
998 | Payroll Taxes | PR | 513 | 11/14/18 | 11/16/18 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 9.56 |  | 0 | 0
998 | Payroll Taxes | PR | 514 | 11/14/18 | 11/16/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 3.83 |  | 0 | 0
998 | Payroll Taxes | PR | 514 | 11/14/18 | 11/16/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 7.65 |  | 0 | 0
998 | Payroll Taxes | PR | 637 | 11/21/18 | 11/21/18 | FO55 | Fonseca Teruel, Eduardo | 0 | 0 | 0 | 0 | 11.02 |  | 0 | 0
998 | Payroll Taxes | PR | 667 | 11/21/18 | 11/21/18 | RE91 | Reyes, Maria E | 0 | 0 | 0 | 0 | 9.79 |  | 0 | 0
998 | Payroll Taxes | PR | 674 | 11/21/18 | 11/21/18 | SA54 | Sanders, Allen O | 0 | 0 | 0 | 0 | 2.52 |  | 0 | 0
998 | Payroll Taxes | PR | 674 | 11/21/18 | 11/21/18 | SA54 | Sanders, Allen O | 0 | 0 | 0 | 0 | 30.29 |  | 0 | 0
998 | Payroll Taxes | PR | 678 | 11/21/18 | 11/21/18 | ST02 | Stahlschmidt, John P | 0 | 0 | 0 | 0 | 9.79 |  | 0 | 0
998 | Payroll Taxes | PR | 686 | 11/21/18 | 11/21/18 | YO29 | Yohannes Jr., Samson | 0 | 0 | 0 | 0 | 11.02 |  | 0 | 0
998 | Payroll Taxes | PR | 689 | 11/21/18 | 11/21/18 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 23.91 |  | 0 | 0
998 | Payroll Taxes | PR | 887 | 11/28/18 | 11/30/18 | SA54 | Sanders, Allen O | 0 | 0 | 0 | 0 | 32.36 |  | 0 | 0
998 | Payroll Taxes | PR | 900 | 11/28/18 | 11/30/18 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 9.56 |  | 0 | 0
998 | Payroll Taxes | PR | 901 | 11/28/18 | 11/30/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 3.98 |  | 0 | 0
998 | Payroll Taxes | PR | 63 | 12/05/18 | 12/07/18 | FO55 | Fonseca Teruel, Eduardo | 0 | 0 | 0 | 0 | 11.02 |  | 0 | 0
998 | Payroll Taxes | PR | 69 | 12/05/18 | 12/07/18 | GO51 | Gomez Reyes, Edith N | 0 | 0 | 0 | 0 | 14.08 |  | 0 | 0
998 | Payroll Taxes | PR | 75 | 12/05/18 | 12/07/18 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 11.25 |  | 0 | 0
998 | Payroll Taxes | PR | 92 | 12/05/18 | 12/07/18 | RE91 | Reyes, Maria E | 0 | 0 | 0 | 0 | 11.02 |  | 0 | 0
998 | Payroll Taxes | PR | 99 | 12/05/18 | 12/07/18 | SA54 | Sanders, Allen O | 0 | 0 | 0 | 0 | 30.56 |  | 0 | 0
998 | Payroll Taxes | PR | 113 | 12/05/18 | 12/07/18 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 4.78 |  | 0 | 0
998 | Payroll Taxes | PR | 268 | 12/12/18 | 12/14/18 | BA45 | Balderas Ortiz, Ricardo I | 0 | 0 | 0 | 0 | 8.87 |  | 0 | 0
998 | Payroll Taxes | PR | 268 | 12/12/18 | 12/14/18 | BA45 | Balderas Ortiz, Ricardo I | 0 | 0 | 0 | 0 | 17.75 |  | 0 | 0
998 | Payroll Taxes | PR | 276 | 12/12/18 | 12/14/18 | CO71 | Cortes Mendiola, Victor H | 0 | 0 | 0 | 0 | 26.32 |  | 0 | 0
998 | Payroll Taxes | PR | 276 | 12/12/18 | 12/14/18 | CO71 | Cortes Mendiola, Victor H | 0 | 0 | 0 | 0 | 13.16 |  | 0 | 0
998 | Payroll Taxes | PR | 277 | 12/12/18 | 12/14/18 | CO73 | Cortes Sepulveda, Jose R | 0 | 0 | 0 | 0 | 23.87 |  | 0 | 0
998 | Payroll Taxes | PR | 287 | 12/12/18 | 12/14/18 | FO55 | Fonseca Teruel, Eduardo | 0 | 0 | 0 | 0 | 4.13 |  | 0 | 0
998 | Payroll Taxes | PR | 287 | 12/12/18 | 12/14/18 | FO55 | Fonseca Teruel, Eduardo | 0 | 0 | 0 | 0 | 11.02 |  | 0 | 0
998 | Payroll Taxes | PR | 293 | 12/12/18 | 12/14/18 | GO51 | Gomez Reyes, Edith N | 0 | 0 | 0 | 0 | 5.28 |  | 0 | 0
998 | Payroll Taxes | PR | 293 | 12/12/18 | 12/14/18 | GO51 | Gomez Reyes, Edith N | 0 | 0 | 0 | 0 | 14.08 |  | 0 | 0
998 | Payroll Taxes | PR | 299 | 12/12/18 | 12/14/18 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 11.25 |  | 0 | 0
998 | Payroll Taxes | PR | 317 | 12/12/18 | 12/14/18 | RE91 | Reyes, Maria E | 0 | 0 | 0 | 0 | 4.13 |  | 0 | 0
998 | Payroll Taxes | PR | 317 | 12/12/18 | 12/14/18 | RE91 | Reyes, Maria E | 0 | 0 | 0 | 0 | 11.02 |  | 0 | 0
998 | Payroll Taxes | PR | 324 | 12/12/18 | 12/14/18 | SA54 | Sanders, Allen O | 0 | 0 | 0 | 0 | 7.19 |  | 0 | 0
998 | Payroll Taxes | PR | 324 | 12/12/18 | 12/14/18 | SA54 | Sanders, Allen O | 0 | 0 | 0 | 0 | 14.38 |  | 0 | 0
998 | Payroll Taxes | PR | 337 | 12/12/18 | 12/14/18 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 19.13 |  | 0 | 0
998 | Payroll Taxes | PR | 509 | 12/19/18 | 12/21/18 | BA45 | Balderas Ortiz, Ricardo I | 0 | 0 | 0 | 0 | 53.24 |  | 0 | 0
998 | Payroll Taxes | PR | 509 | 12/19/18 | 12/21/18 | BA45 | Balderas Ortiz, Ricardo I | 0 | 0 | 0 | 0 | 17.75 |  | 0 | 0
998 | Payroll Taxes | PR | 517 | 12/19/18 | 12/21/18 | CO71 | Cortes Mendiola, Victor H | 0 | 0 | 0 | 0 | 19.74 |  | 0 | 0
998 | Payroll Taxes | PR | 517 | 12/19/18 | 12/21/18 | CO71 | Cortes Mendiola, Victor H | 0 | 0 | 0 | 0 | 19.74 |  | 0 | 0
998 | Payroll Taxes | PR | 518 | 12/19/18 | 12/21/18 | CO73 | Cortes Sepulveda, Jose R | 0 | 0 | 0 | 0 | 61.66 |  | 0 | 0
998 | Payroll Taxes | PR | 540 | 12/19/18 | 12/21/18 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 11.25 |  | 0 | 0
998 | Payroll Taxes | PR | 564 | 12/19/18 | 12/21/18 | SA54 | Sanders, Allen O | 0 | 0 | 0 | 0 | 10.79 |  | 0 | 0
998 | Payroll Taxes | PR | 577 | 12/19/18 | 12/21/18 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 9.56 |  | 0 | 0
998 | Payroll Taxes | PR | 578 | 12/19/18 | 12/21/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 3.98 |  | 0 | 0
998 | Payroll Taxes | PR | 700 | 12/26/18 | 12/28/18 | BA45 | Balderas Ortiz, Ricardo I | 0 | 0 | 0 | 0 | 35.5 |  | 0 | 0
998 | Payroll Taxes | PR | 708 | 12/26/18 | 12/28/18 | CO71 | Cortes Mendiola, Victor H | 0 | 0 | 0 | 0 | 26.32 |  | 0 | 0
998 | Payroll Taxes | PR | 708 | 12/26/18 | 12/28/18 | CO71 | Cortes Mendiola, Victor H | 0 | 0 | 0 | 0 | 78.95 |  | 0 | 0
998 | Payroll Taxes | PR | 709 | 12/26/18 | 12/28/18 | CO73 | Cortes Sepulveda, Jose R | 0 | 0 | 0 | 0 | 21.88 |  | 0 | 0
998 | Payroll Taxes | PR | 731 | 12/26/18 | 12/28/18 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 11.25 |  | 0 | 0
998 | Payroll Taxes | PR | 755 | 12/26/18 | 12/28/18 | SA54 | Sanders, Allen O | 0 | 0 | 0 | 0 | 14.38 |  | 0 | 0
998 | Payroll Taxes | PR | 768 | 12/26/18 | 12/28/18 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 4.78 |  | 0 | 0
998 | Payroll Taxes | PR | 769 | 12/26/18 | 12/28/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 3.98 |  | 0 | 0
998 | Payroll Taxes | PR | 5 | 01/02/19 | 01/04/19 | BA45 | Balderas Ortiz, Ricardo I | 0 | 0 | 0 | 0 | 31.06 |  | 0 | 0
998 | Payroll Taxes | PR | 5 | 01/02/19 | 01/04/19 | BA45 | Balderas Ortiz, Ricardo I | 0 | 0 | 0 | 0 | 4.44 |  | 0 | 0
998 | Payroll Taxes | PR | 5 | 01/02/19 | 01/04/19 | BA45 | Balderas Ortiz, Ricardo I | 0 | 0 | 0 | 0 | 17.75 |  | 0 | 0
998 | Payroll Taxes | PR | 13 | 01/02/19 | 01/04/19 | CO71 | Cortes Mendiola, Victor H | 0 | 0 | 0 | 0 | 26.32 |  | 0 | 0
998 | Payroll Taxes | PR | 13 | 01/02/19 | 01/04/19 | CO71 | Cortes Mendiola, Victor H | 0 | 0 | 0 | 0 | 52.63 |  | 0 | 0
998 | Payroll Taxes | PR | 14 | 01/02/19 | 01/04/19 | CO73 | Cortes Sepulveda, Jose R | 0 | 0 | 0 | 0 | 27.85 |  | 0 | 0
998 | Payroll Taxes | PR | 14 | 01/02/19 | 01/04/19 | CO73 | Cortes Sepulveda, Jose R | 0 | 0 | 0 | 0 | 3.98 |  | 0 | 0
998 | Payroll Taxes | PR | 14 | 01/02/19 | 01/04/19 | CO73 | Cortes Sepulveda, Jose R | 0 | 0 | 0 | 0 | 15.91 |  | 0 | 0
998 | Payroll Taxes | PR | 23 | 01/02/19 | 01/04/19 | FO55 | Fonseca Teruel, Eduardo | 0 | 0 | 0 | 0 | 11.02 |  | 0 | 0
998 | Payroll Taxes | PR | 58 | 01/02/19 | 01/04/19 | SA54 | Sanders, Allen O | 0 | 0 | 0 | 0 | 3.6 |  | 0 | 0
998 | Payroll Taxes | PR | 62 | 01/02/19 | 01/04/19 | ST02 | Stahlschmidt, John P | 0 | 0 | 0 | 0 | 10.4 |  | 0 | 0
998 | Payroll Taxes | PR | 72 | 01/02/19 | 01/04/19 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 4.78 |  | 0 | 0
998 | Payroll Taxes | PR | 213 | 01/09/19 | 01/11/19 | BA45 | Balderas Ortiz, Ricardo I | 0 | 0 | 0 | 0 | 55.46 |  | 0 | 0
998 | Payroll Taxes | PR | 213 | 01/09/19 | 01/11/19 | BA45 | Balderas Ortiz, Ricardo I | 0 | 0 | 0 | 0 | 6.66 |  | 0 | 0
998 | Payroll Taxes | PR | 221 | 01/09/19 | 01/11/19 | CO71 | Cortes Mendiola, Victor H | 0 | 0 | 0 | 0 | 111.84 |  | 0 | 0
998 | Payroll Taxes | PR | 221 | 01/09/19 | 01/11/19 | CO71 | Cortes Mendiola, Victor H | 0 | 0 | 0 | 0 | 9.87 |  | 0 | 0
998 | Payroll Taxes | PR | 222 | 01/09/19 | 01/11/19 | CO73 | Cortes Sepulveda, Jose R | 0 | 0 | 0 | 0 | 35.8 |  | 0 | 0
998 | Payroll Taxes | PR | 222 | 01/09/19 | 01/11/19 | CO73 | Cortes Sepulveda, Jose R | 0 | 0 | 0 | 0 | 19.89 |  | 0 | 0
998 | Payroll Taxes | PR | 231 | 01/09/19 | 01/11/19 | FO55 | Fonseca Teruel, Eduardo | 0 | 0 | 0 | 0 | 22.03 |  | 0 | 0
998 | Payroll Taxes | PR | 244 | 01/09/19 | 01/11/19 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 3.75 |  | 0 | 0
998 | Payroll Taxes | PR | 268 | 01/09/19 | 01/11/19 | SA54 | Sanders, Allen O | 0 | 0 | 0 | 0 | 39.55 |  | 0 | 0
998 | Payroll Taxes | PR | 272 | 01/09/19 | 01/11/19 | ST02 | Stahlschmidt, John P | 0 | 0 | 0 | 0 | 20.81 |  | 0 | 0
998 | Payroll Taxes | PR | 281 | 01/09/19 | 01/11/19 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 9.56 |  | 0 | 0
998 | Payroll Taxes | PR | 467 | 01/16/19 | 01/18/19 | BA45 | Balderas Ortiz, Ricardo I | 0 | 0 | 0 | 0 | 53.24 |  | 0 | 0
998 | Payroll Taxes | PR | 467 | 01/16/19 | 01/18/19 | BA45 | Balderas Ortiz, Ricardo I | 0 | 0 | 0 | 0 | 17.75 |  | 0 | 0
998 | Payroll Taxes | PR | 467 | 01/16/19 | 01/18/19 | BA45 | Balderas Ortiz, Ricardo I | 0 | 0 | 0 | 0 | 17.75 |  | 0 | 0
998 | Payroll Taxes | PR | 476 | 01/16/19 | 01/18/19 | CO71 | Cortes Mendiola, Victor H | 0 | 0 | 0 | 0 | 62.5 |  | 0 | 0
998 | Payroll Taxes | PR | 476 | 01/16/19 | 01/18/19 | CO71 | Cortes Mendiola, Victor H | 0 | 0 | 0 | 0 | 26.32 |  | 0 | 0
998 | Payroll Taxes | PR | 477 | 01/16/19 | 01/18/19 | CO73 | Cortes Sepulveda, Jose R | 0 | 0 | 0 | 0 | 33.81 |  | 0 | 0
998 | Payroll Taxes | PR | 477 | 01/16/19 | 01/18/19 | CO73 | Cortes Sepulveda, Jose R | 0 | 0 | 0 | 0 | 9.95 |  | 0 | 0
998 | Payroll Taxes | PR | 477 | 01/16/19 | 01/18/19 | CO73 | Cortes Sepulveda, Jose R | 0 | 0 | 0 | 0 | 35.8 |  | 0 | 0
998 | Payroll Taxes | PR | 484 | 01/16/19 | 01/18/19 | EL33 | Eliassen, Cory H | 0 | 0 | 0 | 0 | 28.69 |  | 0 | 0
998 | Payroll Taxes | PR | 484 | 01/16/19 | 01/18/19 | EL33 | Eliassen, Cory H | 0 | 0 | 0 | 0 | 30.6 |  | 0 | 0
998 | Payroll Taxes | PR | 492 | 01/16/19 | 01/18/19 | GO51 | Gomez Reyes, Edith N | 0 | 0 | 0 | 0 | 26.39 |  | 0 | 0
998 | Payroll Taxes | PR | 492 | 01/16/19 | 01/18/19 | GO51 | Gomez Reyes, Edith N | 0 | 0 | 0 | 0 | 14.08 |  | 0 | 0
998 | Payroll Taxes | PR | 516 | 01/16/19 | 01/18/19 | RE91 | Reyes, Maria E | 0 | 0 | 0 | 0 | 20.66 |  | 0 | 0
998 | Payroll Taxes | PR | 516 | 01/16/19 | 01/18/19 | RE91 | Reyes, Maria E | 0 | 0 | 0 | 0 | 11.02 |  | 0 | 0
998 | Payroll Taxes | PR | 523 | 01/16/19 | 01/18/19 | SA54 | Sanders, Allen O | 0 | 0 | 0 | 0 | 40.45 |  | 0 | 0
998 | Payroll Taxes | PR | 523 | 01/16/19 | 01/18/19 | SA54 | Sanders, Allen O | 0 | 0 | 0 | 0 | 43.15 |  | 0 | 0
998 | Payroll Taxes | PR | 530 | 01/16/19 | 01/18/19 | TR60 | Trower-Kelly, Fidel D | 0 | 0 | 0 | 0 | 22.03 |  | 0 | 0
998 | Payroll Taxes | PR | 530 | 01/16/19 | 01/18/19 | TR60 | Trower-Kelly, Fidel D | 0 | 0 | 0 | 0 | 29.38 |  | 0 | 0
998 | Payroll Taxes | PR | 542 | 01/16/19 | 01/18/19 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 9.56 |  | 0 | 0
998 | Payroll Taxes | PR | 543 | 01/16/19 | 01/18/19 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 3.98 |  | 0 | 0
998 | Payroll Taxes | PR | 725 | 01/23/19 | 01/25/19 | CO71 | Cortes Mendiola, Victor H | 0 | 0 | 0 | 0 | 9.87 |  | 0 | 0
998 | Payroll Taxes | PR | 725 | 01/23/19 | 01/25/19 | CO71 | Cortes Mendiola, Victor H | 0 | 0 | 0 | 0 | 3.29 |  | 0 | 0
998 | Payroll Taxes | PR | 733 | 01/23/19 | 01/25/19 | EL33 | Eliassen, Cory H | 0 | 0 | 0 | 0 | 22.95 |  | 0 | 0
998 | Payroll Taxes | PR | 733 | 01/23/19 | 01/25/19 | EL33 | Eliassen, Cory H | 0 | 0 | 0 | 0 | 45.9 |  | 0 | 0
998 | Payroll Taxes | PR | 735 | 01/23/19 | 01/25/19 | FO55 | Fonseca Teruel, Eduardo | 0 | 0 | 0 | 0 | 8.26 |  | 0 | 0
998 | Payroll Taxes | PR | 741 | 01/23/19 | 01/25/19 | GO51 | Gomez Reyes, Edith N | 0 | 0 | 0 | 0 | 24.63 |  | 0 | 0
998 | Payroll Taxes | PR | 748 | 01/23/19 | 01/25/19 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 7.5 |  | 0 | 0
998 | Payroll Taxes | PR | 756 | 01/23/19 | 01/25/19 | MC09 | McCabe, Thomas C | 0 | 0 | 0 | 0 | 3.79 |  | 0 | 0
998 | Payroll Taxes | PR | 756 | 01/23/19 | 01/25/19 | MC09 | McCabe, Thomas C | 0 | 0 | 0 | 0 | 12.62 |  | 0 | 0
998 | Payroll Taxes | PR | 765 | 01/23/19 | 01/25/19 | RE91 | Reyes, Maria E | 0 | 0 | 0 | 0 | 15.49 |  | 0 | 0
998 | Payroll Taxes | PR | 765 | 01/23/19 | 01/25/19 | RE91 | Reyes, Maria E | 0 | 0 | 0 | 0 | 22.03 |  | 0 | 0
998 | Payroll Taxes | PR | 772 | 01/23/19 | 01/25/19 | SA54 | Sanders, Allen O | 0 | 0 | 0 | 0 | 29.66 |  | 0 | 0
998 | Payroll Taxes | PR | 772 | 01/23/19 | 01/25/19 | SA54 | Sanders, Allen O | 0 | 0 | 0 | 0 | 25.17 |  | 0 | 0
998 | Payroll Taxes | PR | 778 | 01/23/19 | 01/25/19 | TA96 | Taylor, Evan R | 0 | 0 | 0 | 0 | 23.87 |  | 0 | 0
998 | Payroll Taxes | PR | 779 | 01/23/19 | 01/25/19 | TR60 | Trower-Kelly, Fidel D | 0 | 0 | 0 | 0 | 14.69 |  | 0 | 0
998 | Payroll Taxes | PR | 779 | 01/23/19 | 01/25/19 | TR60 | Trower-Kelly, Fidel D | 0 | 0 | 0 | 0 | 39.17 |  | 0 | 0
998 | Payroll Taxes | PR | 786 | 01/23/19 | 01/25/19 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 9.56 |  | 0 | 0
998 | Payroll Taxes | PR | 13 | 01/30/19 | 02/01/19 | CO71 | Cortes Mendiola, Victor H | 0 | 0 | 0 | 0 | 9.87 |  | 0 | 0
998 | Payroll Taxes | PR | 21 | 01/30/19 | 02/01/19 | EL33 | Eliassen, Cory H | 0 | 0 | 0 | 0 | 27.25 |  | 0 | 0
998 | Payroll Taxes | PR | 21 | 01/30/19 | 02/01/19 | EL33 | Eliassen, Cory H | 0 | 0 | 0 | 0 | 66.94 |  | 0 | 0
998 | Payroll Taxes | PR | 23 | 01/30/19 | 02/01/19 | FO55 | Fonseca Teruel, Eduardo | 0 | 0 | 0 | 0 | 16.52 |  | 0 | 0
998 | Payroll Taxes | PR | 29 | 01/30/19 | 02/01/19 | GO51 | Gomez Reyes, Edith N | 0 | 0 | 0 | 0 | 23.75 |  | 0 | 0
998 | Payroll Taxes | PR | 29 | 01/30/19 | 02/01/19 | GO51 | Gomez Reyes, Edith N | 0 | 0 | 0 | 0 | 28.15 |  | 0 | 0
998 | Payroll Taxes | PR | 36 | 01/30/19 | 02/01/19 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 7.5 |  | 0 | 0
998 | Payroll Taxes | PR | 44 | 01/30/19 | 02/01/19 | MC09 | McCabe, Thomas C | 0 | 0 | 0 | 0 | 20.2 |  | 0 | 0
998 | Payroll Taxes | PR | 51 | 01/30/19 | 02/01/19 | RE91 | Reyes, Maria E | 0 | 0 | 0 | 0 | 18.59 |  | 0 | 0
998 | Payroll Taxes | PR | 51 | 01/30/19 | 02/01/19 | RE91 | Reyes, Maria E | 0 | 0 | 0 | 0 | 22.03 |  | 0 | 0
998 | Payroll Taxes | PR | 57 | 01/30/19 | 02/01/19 | SA54 | Sanders, Allen O | 0 | 0 | 0 | 0 | 48.54 |  | 0 | 0
998 | Payroll Taxes | PR | 57 | 01/30/19 | 02/01/19 | SA54 | Sanders, Allen O | 0 | 0 | 0 | 0 | 46.74 |  | 0 | 0
998 | Payroll Taxes | PR | 61 | 01/30/19 | 02/01/19 | ST02 | Stahlschmidt, John P | 0 | 0 | 0 | 0 | 15.61 |  | 0 | 0
998 | Payroll Taxes | PR | 64 | 01/30/19 | 02/01/19 | TR60 | Trower-Kelly, Fidel D | 0 | 0 | 0 | 0 | 17.44 |  | 0 | 0
998 | Payroll Taxes | PR | 64 | 01/30/19 | 02/01/19 | TR60 | Trower-Kelly, Fidel D | 0 | 0 | 0 | 0 | 42.84 |  | 0 | 0
998 | Payroll Taxes | PR | 70 | 01/30/19 | 02/01/19 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 19.13 |  | 0 | 0
998 | Payroll Taxes | PR | 168 | 02/06/19 | 02/08/19 | CO71 | Cortes Mendiola, Victor H | 0 | 0 | 0 | 0 | 16.45 |  | 0 | 0
998 | Payroll Taxes | PR | 176 | 02/06/19 | 02/08/19 | EL33 | Eliassen, Cory H | 0 | 0 | 0 | 0 | 40.16 |  | 0 | 0
998 | Payroll Taxes | PR | 213 | 02/06/19 | 02/08/19 | SA54 | Sanders, Allen O | 0 | 0 | 0 | 0 | 17.98 |  | 0 | 0
998 | Payroll Taxes | PR | 220 | 02/06/19 | 02/08/19 | TR60 | Trower-Kelly, Fidel D | 0 | 0 | 0 | 0 | 25.7 |  | 0 | 0
998 | Payroll Taxes | PR | 226 | 02/06/19 | 02/08/19 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 9.56 |  | 0 | 0
998 | Payroll Taxes | PR | 330 | 02/13/19 | 02/15/19 | CO71 | Cortes Mendiola, Victor H | 0 | 0 | 0 | 0 | 16.45 |  | 0 | 0
998 | Payroll Taxes | PR | 338 | 02/13/19 | 02/15/19 | EL33 | Eliassen, Cory H | 0 | 0 | 0 | 0 | 36.34 |  | 0 | 0
998 | Payroll Taxes | PR | 375 | 02/13/19 | 02/15/19 | SA54 | Sanders, Allen O | 0 | 0 | 0 | 0 | 16.18 |  | 0 | 0
998 | Payroll Taxes | PR | 382 | 02/13/19 | 02/15/19 | TR60 | Trower-Kelly, Fidel D | 0 | 0 | 0 | 0 | 23.26 |  | 0 | 0
998 | Payroll Taxes | PR | 388 | 02/13/19 | 02/15/19 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 9.56 |  | 0 | 0
998 | Payroll Taxes | PR | 580 | 02/20/19 | 02/22/19 | BA45 | Balderas Ortiz, Ricardo I | 0 | 0 | 0 | 0 | 15.53 |  | 0 | 0
998 | Payroll Taxes | PR | 586 | 02/20/19 | 02/22/19 | CH20 | Chevez, Herson G | 0 | 0 | 0 | 0 | 10.71 |  | 0 | 0
998 | Payroll Taxes | PR | 588 | 02/20/19 | 02/22/19 | CO71 | Cortes Mendiola, Victor H | 0 | 0 | 0 | 0 | 23.03 |  | 0 | 0
998 | Payroll Taxes | PR | 596 | 02/20/19 | 02/22/19 | EL33 | Eliassen, Cory H | 0 | 0 | 0 | 0 | 5.74 |  | 0 | 0
998 | Payroll Taxes | PR | 596 | 02/20/19 | 02/22/19 | EL33 | Eliassen, Cory H | 0 | 0 | 0 | 0 | 24.86 |  | 0 | 0
998 | Payroll Taxes | PR | 634 | 02/20/19 | 02/22/19 | SA54 | Sanders, Allen O | 0 | 0 | 0 | 0 | 10.79 |  | 0 | 0
998 | Payroll Taxes | PR | 641 | 02/20/19 | 02/22/19 | TR60 | Trower-Kelly, Fidel D | 0 | 0 | 0 | 0 | 3.67 |  | 0 | 0
998 | Payroll Taxes | PR | 641 | 02/20/19 | 02/22/19 | TR60 | Trower-Kelly, Fidel D | 0 | 0 | 0 | 0 | 6.12 |  | 0 | 0
998 | Payroll Taxes | PR | 647 | 02/20/19 | 02/22/19 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 9.56 |  | 0 | 0
998 | Payroll Taxes | PR | 13 | 02/27/19 | 03/01/19 | CO71 | Cortes Mendiola, Victor H | 0 | 0 | 0 | 0 | 13.16 |  | 0 | 0
998 | Payroll Taxes | PR | 13 | 02/27/19 | 03/01/19 | CO71 | Cortes Mendiola, Victor H | 0 | 0 | 0 | 0 | 3.29 |  | 0 | 0
998 | Payroll Taxes | PR | 13 | 02/27/19 | 03/01/19 | CO71 | Cortes Mendiola, Victor H | 0 | 0 | 0 | 0 | 3.29 |  | 0 | 0
998 | Payroll Taxes | PR | 13 | 02/27/19 | 03/01/19 | CO71 | Cortes Mendiola, Victor H | 0 | 0 | 0 | 0 | 6.58 |  | 0 | 0
998 | Payroll Taxes | PR | 22 | 02/27/19 | 03/01/19 | EL33 | Eliassen, Cory H | 0 | 0 | 0 | 0 | 17.21 |  | 0 | 0
998 | Payroll Taxes | PR | 38 | 02/27/19 | 03/01/19 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 14.99 |  | 0 | 0
998 | Payroll Taxes | PR | 61 | 02/27/19 | 03/01/19 | SA54 | Sanders, Allen O | 0 | 0 | 0 | 0 | 3.6 |  | 0 | 0
998 | Payroll Taxes | PR | 74 | 02/27/19 | 03/01/19 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 14.34 |  | 0 | 0
998 | Payroll Taxes | PR | 255 | 03/06/19 | 03/08/19 | CO71 | Cortes Mendiola, Victor H | 0 | 0 | 0 | 0 | 13.16 |  | 0 | 0
998 | Payroll Taxes | PR | 255 | 03/06/19 | 03/08/19 | CO71 | Cortes Mendiola, Victor H | 0 | 0 | 0 | 0 | 9.87 |  | 0 | 0
998 | Payroll Taxes | PR | 264 | 03/06/19 | 03/08/19 | EL33 | Eliassen, Cory H | 0 | 0 | 0 | 0 | 5.74 |  | 0 | 0
998 | Payroll Taxes | PR | 300 | 03/06/19 | 03/08/19 | SA54 | Sanders, Allen O | 0 | 0 | 0 | 0 | 7.19 |  | 0 | 0
998 | Payroll Taxes | PR | 307 | 03/06/19 | 03/08/19 | TR60 | Trower-Kelly, Fidel D | 0 | 0 | 0 | 0 | 3.67 |  | 0 | 0
998 | Payroll Taxes | PR | 314 | 03/06/19 | 03/08/19 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 9.56 |  | 0 | 0
998 | Payroll Taxes | PR | 502 | 03/13/19 | 03/15/19 | CO71 | Cortes Mendiola, Victor H | 0 | 0 | 0 | 0 | 6.58 |  | 0 | 0
998 | Payroll Taxes | PR | 511 | 03/13/19 | 03/15/19 | EL33 | Eliassen, Cory H | 0 | 0 | 0 | 0 | 13.39 |  | 0 | 0
998 | Payroll Taxes | PR | 525 | 03/13/19 | 03/15/19 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 11.25 |  | 0 | 0
998 | Payroll Taxes | PR | 525 | 03/13/19 | 03/15/19 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 5.62 |  | 0 | 0
998 | Payroll Taxes | PR | 547 | 03/13/19 | 03/15/19 | SA54 | Sanders, Allen O | 0 | 0 | 0 | 0 | 10.79 |  | 0 | 0
998 | Payroll Taxes | PR | 555 | 03/13/19 | 03/15/19 | TR60 | Trower-Kelly, Fidel D | 0 | 0 | 0 | 0 | 4.9 |  | 0 | 0
998 | Payroll Taxes | PR | 562 | 03/13/19 | 03/15/19 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 19.13 |  | 0 | 0
998 | Payroll Taxes | PR | 714 | 03/20/19 | 03/22/19 | CH20 | Chevez, Herson G | 0 | 0 | 0 | 0 | 9.18 |  | 0 | 0
998 | Payroll Taxes | PR | 714 | 03/20/19 | 03/22/19 | CH20 | Chevez, Herson G | 0 | 0 | 0 | 0 | 4.59 |  | 0 | 0
998 | Payroll Taxes | PR | 716 | 03/20/19 | 03/22/19 | CO71 | Cortes Mendiola, Victor H | 0 | 0 | 0 | 0 | 19.74 |  | 0 | 0
998 | Payroll Taxes | PR | 716 | 03/20/19 | 03/22/19 | CO71 | Cortes Mendiola, Victor H | 0 | 0 | 0 | 0 | 9.87 |  | 0 | 0
998 | Payroll Taxes | PR | 725 | 03/20/19 | 03/22/19 | EL33 | Eliassen, Cory H | 0 | 0 | 0 | 0 | 7.65 |  | 0 | 0
998 | Payroll Taxes | PR | 739 | 03/20/19 | 03/22/19 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 14.99 |  | 0 | 0
998 | Payroll Taxes | PR | 760 | 03/20/19 | 03/22/19 | SA54 | Sanders, Allen O | 0 | 0 | 0 | 0 | 10.79 |  | 0 | 0
998 | Payroll Taxes | PR | 769 | 03/20/19 | 03/22/19 | TR60 | Trower-Kelly, Fidel D | 0 | 0 | 0 | 0 | 4.9 |  | 0 | 0
998 | Payroll Taxes | PR | 780 | 03/20/19 | 03/22/19 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 14.99 |  | 0 | 0
998 | Payroll Taxes | PR | 781 | 03/20/19 | 03/22/19 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | -14.99 |  | 0 | 0
998 | Payroll Taxes | PR | 927 | 03/27/19 | 03/29/19 | CO71 | Cortes Mendiola, Victor H | 0 | 0 | 0 | 0 | 9.87 |  | 0 | 0
998 | Payroll Taxes | PR | 936 | 03/27/19 | 03/29/19 | EL33 | Eliassen, Cory H | 0 | 0 | 0 | 0 | 5.74 |  | 0 | 0
998 | Payroll Taxes | PR | 951 | 03/27/19 | 03/29/19 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 5.62 |  | 0 | 0
998 | Payroll Taxes | PR | 951 | 03/27/19 | 03/29/19 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 14.99 |  | 0 | 0
998 | Payroll Taxes | PR | 972 | 03/27/19 | 03/29/19 | SA54 | Sanders, Allen O | 0 | 0 | 0 | 0 | 10.79 |  | 0 | 0
998 | Payroll Taxes | PR | 989 | 03/27/19 | 03/29/19 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 4.78 |  | 0 | 0
998 | Payroll Taxes | PR | 85 | 04/03/19 | 04/05/19 | BE54 | Benites Portillo, Marvin E | 0 | 0 | 0 | 0 | 5.51 |  | 0 | 0
998 | Payroll Taxes | PR | 85 | 04/03/19 | 04/05/19 | BE54 | Benites Portillo, Marvin E | 0 | 0 | 0 | 0 | 9.18 |  | 0 | 0
998 | Payroll Taxes | PR | 89 | 04/03/19 | 04/05/19 | CO71 | Cortes Mendiola, Victor H | 0 | 0 | 0 | 0 | 9.87 |  | 0 | 0
998 | Payroll Taxes | PR | 89 | 04/03/19 | 04/05/19 | CO71 | Cortes Mendiola, Victor H | 0 | 0 | 0 | 0 | 16.45 |  | 0 | 0
998 | Payroll Taxes | PR | 151 | 04/03/19 | 04/05/19 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 14.34 |  | 0 | 0
998 | Payroll Taxes | PR | 397 | 04/10/19 | 04/12/19 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 4.78 |  | 0 | 0
998 | Payroll Taxes | PR | 530 | 04/17/19 | 04/19/19 | CO71 | Cortes Mendiola, Victor H | 0 | 0 | 0 | 0 | 7.04 |  | 0 | 0
998 | Payroll Taxes | PR | 578 | 04/17/19 | 04/19/19 | SA54 | Sanders, Allen O | 0 | 0 | 0 | 0 | 7.5 |  | 0 | 0
998 | Payroll Taxes | PR | 596 | 04/17/19 | 04/19/19 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 4.78 |  | 0 | 0
998 | Payroll Taxes | PR | 750 | 04/24/19 | 04/26/19 | CO71 | Cortes Mendiola, Victor H | 0 | 0 | 0 | 0 | 10.56 |  | 0 | 0
998 | Payroll Taxes | PR | 797 | 04/24/19 | 04/26/19 | SA54 | Sanders, Allen O | 0 | 0 | 0 | 0 | 16.87 |  | 0 | 0
998 | Payroll Taxes | PR | 812 | 04/24/19 | 04/26/19 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 9.56 |  | 0 | 0
998 | Payroll Taxes | PR | 66 | 05/01/19 | 05/03/19 | SA54 | Sanders, Allen O | 0 | 0 | 0 | 0 | 7.5 |  | 0 | 0
998 | Payroll Taxes | PR | 81 | 05/01/19 | 05/03/19 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 4.78 |  | 0 | 0
998 | Payroll Taxes | PR | 179 | 05/08/19 | 05/10/19 | EL33 | Eliassen, Cory H | 0 | 0 | 0 | 0 | 1.55 |  | 0 | 0
998 | Payroll Taxes | PR | 179 | 05/08/19 | 05/10/19 | EL33 | Eliassen, Cory H | 0 | 0 | 0 | 0 | 10.33 |  | 0 | 0
998 | Payroll Taxes | PR | 219 | 05/08/19 | 05/10/19 | SA54 | Sanders, Allen O | 0 | 0 | 0 | 0 | 18.74 |  | 0 | 0
998 | Payroll Taxes | PR | 427 | 05/15/19 | 05/17/19 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 15.3 |  | 0 | 0
998 | Payroll Taxes | PR | 427 | 05/15/19 | 05/17/19 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 7.65 |  | 0 | 0
998 | Payroll Taxes | PR | 451 | 05/15/19 | 05/17/19 | SA54 | Sanders, Allen O | 0 | 0 | 0 | 0 | 33.74 |  | 0 | 0
998 | Payroll Taxes | PR | 467 | 05/15/19 | 05/17/19 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 4.78 |  | 0 | 0
998 | Payroll Taxes | PR | 663 | 05/22/19 | 05/24/19 | SA54 | Sanders, Allen O | 0 | 0 | 0 | 0 | 7.5 |  | 0 | 0
999 | Sales | AR | 372 | 10/20/17 | 10/20/17 | 2043CH | Compass Harbor Construction 1,LLC $Aegis |  |  |  |  | -41500 | 036972 | 0 | -2075
999 | Sales | AR | 372 | 10/20/17 | 10/20/17 | 2043CH | Compass Harbor Construction 1,LLC $Aegis |  |  |  |  | -15000 | 036972 | 0 | -750
999 | Sales | AR | 372 | 10/20/17 | 10/20/17 | 2043CH | Compass Harbor Construction 1,LLC $Aegis |  |  |  |  | -7410 | 036972 | 0 | -370.5
999 | Sales | AR | 372 | 10/20/17 | 10/20/17 | 2043CH | Compass Harbor Construction 1,LLC $Aegis |  |  |  |  | 22410 | 036972 | 0 | 1120.5
999 | Sales | AR | 372 | 11/17/17 | 11/17/17 | 2043CH | Compass Harbor Construction 1,LLC $Aegis |  |  |  |  | -27470 | 036978 | 0 | -1373.5
999 | Sales | AR | 399 | 12/14/17 | 12/14/17 | 2043CH | Compass Harbor Construction 1,LLC $Aegis |  |  |  |  | -87200 | 036991 | 0 | -4360
999 | Sales | AR | 473 | 01/19/18 | 01/19/18 | 2043CH | Compass Harbor Construction 1,LLC $Aegis |  |  |  |  | -52320 | 037008 | 0 | -2616
999 | Sales | AR | 473 | 01/19/18 | 01/19/18 | 2043CH | Compass Harbor Construction 1,LLC $Aegis |  |  |  |  | -15600 | 037008 | 0 | -780
999 | Sales | AR | 573 | 02/20/18 | 02/20/18 | 2043CH | Compass Harbor Construction 1,LLC $Aegis |  |  |  |  | -15600 | 037016 | 0 | -780
999 | Sales | AR | 573 | 02/20/18 | 02/20/18 | 2043CH | Compass Harbor Construction 1,LLC $Aegis |  |  |  |  | -8220 | 037016 | 0 | -411
999 | Sales | AR | 574 | 02/20/18 | 02/20/18 | 2043CH | Compass Harbor Construction 1,LLC $Aegis |  |  |  |  | 15600 | 037017 | 0 | 780
999 | Sales | AR | 574 | 02/20/18 | 02/20/18 | 2043CH | Compass Harbor Construction 1,LLC $Aegis |  |  |  |  | 8220 | 037017 | 0 | 411
999 | Sales | AR | 575 | 02/20/18 | 02/20/18 | 2043CH | Compass Harbor Construction 1,LLC $Aegis |  |  |  |  | -15600 | 037018 | 0 | -780
999 | Sales | AR | 575 | 02/20/18 | 02/20/18 | 2043CH | Compass Harbor Construction 1,LLC $Aegis |  |  |  |  | -8220 | 037018 | 0 | -411
999 | Sales | AR | 575 | 02/20/18 | 02/20/18 | 2043CH | Compass Harbor Construction 1,LLC $Aegis |  |  |  |  | -2290 | 037018 | 0 | -114.5
999 | Sales | AR | 575 | 02/20/18 | 02/20/18 | 2043CH | Compass Harbor Construction 1,LLC $Aegis |  |  |  |  | -12930 | 037018 | 0 | -646.5
999 | Sales | AR | 575 | 02/20/18 | 02/20/18 | 2043CH | Compass Harbor Construction 1,LLC $Aegis |  |  |  |  | -12174 | 037018 | 0 | -608.7
999 | Sales | AR | 437 | 03/20/18 | 03/20/18 | 2043CH | Compass Harbor Construction 1,LLC $Aegis |  |  |  |  | -9200 | 037042 | 0 | -460
999 | Sales | AR | 437 | 03/20/18 | 03/20/18 | 2043CH | Compass Harbor Construction 1,LLC $Aegis |  |  |  |  | -41100 | 037042 | 0 | -2055
999 | Sales | AR | 437 | 03/20/18 | 03/20/18 | 2043CH | Compass Harbor Construction 1,LLC $Aegis |  |  |  |  | -90100 | 037042 | 0 | -4505
999 | Sales | AR | 437 | 03/20/18 | 03/20/18 | 2043CH | Compass Harbor Construction 1,LLC $Aegis |  |  |  |  | -102500 | 037042 | 0 | -5125
999 | Sales | AR | 437 | 03/20/18 | 03/20/18 | 2043CH | Compass Harbor Construction 1,LLC $Aegis |  |  |  |  | -39400 | 037042 | 0 | -1970
999 | Sales | AR | 99 | 03/20/18 | 04/01/18 | 2043CH | Compass Harbor Construction 1,LLC $Aegis |  |  |  |  | 9200 | 037054 | 0 | 460
999 | Sales | AR | 99 | 03/20/18 | 04/01/18 | 2043CH | Compass Harbor Construction 1,LLC $Aegis |  |  |  |  | 41100 | 037054 | 0 | 2055
999 | Sales | AR | 99 | 03/20/18 | 04/01/18 | 2043CH | Compass Harbor Construction 1,LLC $Aegis |  |  |  |  | 90100 | 037054 | 0 | 4505
999 | Sales | AR | 99 | 03/20/18 | 04/01/18 | 2043CH | Compass Harbor Construction 1,LLC $Aegis |  |  |  |  | 102500 | 037054 | 0 | 5125
999 | Sales | AR | 99 | 03/20/18 | 04/01/18 | 2043CH | Compass Harbor Construction 1,LLC $Aegis |  |  |  |  | 39400 | 037054 | 0 | 1970
999 | Sales | AR | 100 | 03/20/18 | 04/01/18 | 2043CH | Compass Harbor Construction 1,LLC $Aegis |  |  |  |  | -9200 | 037055 | 0 | -460
999 | Sales | AR | 100 | 03/20/18 | 04/01/18 | 2043CH | Compass Harbor Construction 1,LLC $Aegis |  |  |  |  | -41100 | 037055 | 0 | -2055
999 | Sales | AR | 100 | 03/20/18 | 04/01/18 | 2043CH | Compass Harbor Construction 1,LLC $Aegis |  |  |  |  | -90100 | 037055 | 0 | -4505
999 | Sales | AR | 100 | 03/20/18 | 04/01/18 | 2043CH | Compass Harbor Construction 1,LLC $Aegis |  |  |  |  | -57500 | 037055 | 0 | -2875
999 | Sales | AR | 100 | 03/20/18 | 04/01/18 | 2043CH | Compass Harbor Construction 1,LLC $Aegis |  |  |  |  | -19700 | 037055 | 0 | -985
999 | Sales | AR | 110 | 03/20/18 | 04/01/18 | 2043CH | Compass Harbor Construction 1,LLC $Aegis |  |  |  |  | 9200 | 037056 | 0 | 460
999 | Sales | AR | 110 | 03/20/18 | 04/01/18 | 2043CH | Compass Harbor Construction 1,LLC $Aegis |  |  |  |  | 41100 | 037056 | 0 | 2055
999 | Sales | AR | 110 | 03/20/18 | 04/01/18 | 2043CH | Compass Harbor Construction 1,LLC $Aegis |  |  |  |  | 90100 | 037056 | 0 | 4505
999 | Sales | AR | 110 | 03/20/18 | 04/01/18 | 2043CH | Compass Harbor Construction 1,LLC $Aegis |  |  |  |  | 57500 | 037056 | 0 | 2875
999 | Sales | AR | 110 | 03/20/18 | 04/01/18 | 2043CH | Compass Harbor Construction 1,LLC $Aegis |  |  |  |  | 19700 | 037056 | 0 | 985
999 | Sales | AR | 111 | 03/20/18 | 04/01/18 | 2043CH | Compass Harbor Construction 1,LLC $Aegis |  |  |  |  | -9200 | 037057 | 0 | -460
999 | Sales | AR | 111 | 03/20/18 | 04/01/18 | 2043CH | Compass Harbor Construction 1,LLC $Aegis |  |  |  |  | -41100 | 037057 | 0 | -2055
999 | Sales | AR | 111 | 03/20/18 | 04/01/18 | 2043CH | Compass Harbor Construction 1,LLC $Aegis |  |  |  |  | -50100 | 037057 | 0 | -2505
999 | Sales | AR | 111 | 03/20/18 | 04/01/18 | 2043CH | Compass Harbor Construction 1,LLC $Aegis |  |  |  |  | -41500 | 037057 | 0 | -2075
999 | Sales | AR | 111 | 03/20/18 | 04/01/18 | 2043CH | Compass Harbor Construction 1,LLC $Aegis |  |  |  |  | -24400 | 037057 | 0 | -1220
999 | Sales | AR | 111 | 03/20/18 | 04/01/18 | 2043CH | Compass Harbor Construction 1,LLC $Aegis |  |  |  |  | -11800 | 037057 | 0 | -590
999 | Sales | AR | 539 | 04/20/18 | 04/20/18 | 2043CH | Compass Harbor Construction 1,LLC $Aegis |  |  |  |  | -3000 | 037060 | 0 | -150
999 | Sales | AR | 539 | 04/20/18 | 04/20/18 | 2043CH | Compass Harbor Construction 1,LLC $Aegis |  |  |  |  | -72165 | 037060 | 0 | -3608.25
999 | Sales | AR | 539 | 04/20/18 | 04/20/18 | 2043CH | Compass Harbor Construction 1,LLC $Aegis |  |  |  |  | -60910 | 037060 | 0 | -3045.5
999 | Sales | AR | 539 | 04/20/18 | 04/20/18 | 2043CH | Compass Harbor Construction 1,LLC $Aegis |  |  |  |  | -133200 | 037060 | 0 | -6660
999 | Sales | AR | 539 | 04/20/18 | 04/20/18 | 2043CH | Compass Harbor Construction 1,LLC $Aegis |  |  |  |  | -37400 | 037060 | 0 | -1870
999 | Sales | AR | 539 | 04/20/18 | 04/20/18 | 2043CH | Compass Harbor Construction 1,LLC $Aegis |  |  |  |  | -116250 | 037060 | 0 | -5812.5
999 | Sales | AR | 539 | 04/20/18 | 04/20/18 | 2043CH | Compass Harbor Construction 1,LLC $Aegis |  |  |  |  | -46700 | 037060 | 0 | -2335
999 | Sales | AR | 539 | 04/20/18 | 04/20/18 | 2043CH | Compass Harbor Construction 1,LLC $Aegis |  |  |  |  | -40100 | 037060 | 0 | -2005
999 | Sales | AR | 14 | 04/20/18 | 05/01/18 | 2043CH | Compass Harbor Construction 1,LLC $Aegis |  |  |  |  | 3000 | 037075 | 0 | 150
999 | Sales | AR | 14 | 04/20/18 | 05/01/18 | 2043CH | Compass Harbor Construction 1,LLC $Aegis |  |  |  |  | 72165 | 037075 | 0 | 3608.25
999 | Sales | AR | 14 | 04/20/18 | 05/01/18 | 2043CH | Compass Harbor Construction 1,LLC $Aegis |  |  |  |  | 60910 | 037075 | 0 | 3045.5
999 | Sales | AR | 14 | 04/20/18 | 05/01/18 | 2043CH | Compass Harbor Construction 1,LLC $Aegis |  |  |  |  | 133200 | 037075 | 0 | 6660
999 | Sales | AR | 14 | 04/20/18 | 05/01/18 | 2043CH | Compass Harbor Construction 1,LLC $Aegis |  |  |  |  | 37400 | 037075 | 0 | 1870
999 | Sales | AR | 14 | 04/20/18 | 05/01/18 | 2043CH | Compass Harbor Construction 1,LLC $Aegis |  |  |  |  | 116250 | 037075 | 0 | 5812.5
999 | Sales | AR | 14 | 04/20/18 | 05/01/18 | 2043CH | Compass Harbor Construction 1,LLC $Aegis |  |  |  |  | 46700 | 037075 | 0 | 2335
999 | Sales | AR | 14 | 04/20/18 | 05/01/18 | 2043CH | Compass Harbor Construction 1,LLC $Aegis |  |  |  |  | 40100 | 037075 | 0 | 2005
999 | Sales | AR | 15 | 04/20/18 | 05/01/18 | 2043CH | Compass Harbor Construction 1,LLC $Aegis |  |  |  |  | -3000 | 037076 | 0 | -150
999 | Sales | AR | 15 | 04/20/18 | 05/01/18 | 2043CH | Compass Harbor Construction 1,LLC $Aegis |  |  |  |  | -72165 | 037076 | 0 | -3608.25
999 | Sales | AR | 15 | 04/20/18 | 05/01/18 | 2043CH | Compass Harbor Construction 1,LLC $Aegis |  |  |  |  | -31650 | 037076 | 0 | -1582.5
999 | Sales | AR | 15 | 04/20/18 | 05/01/18 | 2043CH | Compass Harbor Construction 1,LLC $Aegis |  |  |  |  | -133200 | 037076 | 0 | -6660
999 | Sales | AR | 15 | 04/20/18 | 05/01/18 | 2043CH | Compass Harbor Construction 1,LLC $Aegis |  |  |  |  | -37400 | 037076 | 0 | -1870
999 | Sales | AR | 15 | 04/20/18 | 05/01/18 | 2043CH | Compass Harbor Construction 1,LLC $Aegis |  |  |  |  | -116250 | 037076 | 0 | -5812.5
999 | Sales | AR | 15 | 04/20/18 | 05/01/18 | 2043CH | Compass Harbor Construction 1,LLC $Aegis |  |  |  |  | -46700 | 037076 | 0 | -2335
999 | Sales | AR | 15 | 04/20/18 | 05/01/18 | 2043CH | Compass Harbor Construction 1,LLC $Aegis |  |  |  |  | -14170 | 037076 | 0 | -708.5
999 | Sales | AR | 15 | 04/20/18 | 05/01/18 | 2043CH | Compass Harbor Construction 1,LLC $Aegis |  |  |  |  | -40100 | 037076 | 0 | -2005
999 | Sales | AR | 506 | 05/18/18 | 05/18/18 | 2043CH | Compass Harbor Construction 1,LLC $Aegis |  |  |  |  | -30000 | 037084 | 0 | -1500
999 | Sales | AR | 506 | 05/18/18 | 05/18/18 | 2043CH | Compass Harbor Construction 1,LLC $Aegis |  |  |  |  | -55000 | 037084 | 0 | -2750
999 | Sales | AR | 506 | 05/18/18 | 05/18/18 | 2043CH | Compass Harbor Construction 1,LLC $Aegis |  |  |  |  | -90000 | 037084 | 0 | -4500
999 | Sales | AR | 519 | 05/18/18 | 05/18/18 | 2043CH | Compass Harbor Construction 1,LLC $Aegis |  |  |  |  | 30000 | 037097 | 0 | 1500
999 | Sales | AR | 519 | 05/18/18 | 05/18/18 | 2043CH | Compass Harbor Construction 1,LLC $Aegis |  |  |  |  | 55000 | 037097 | 0 | 2750
999 | Sales | AR | 519 | 05/18/18 | 05/18/18 | 2043CH | Compass Harbor Construction 1,LLC $Aegis |  |  |  |  | 90000 | 037097 | 0 | 4500
999 | Sales | AR | 520 | 05/18/18 | 05/18/18 | 2043CH | Compass Harbor Construction 1,LLC $Aegis |  |  |  |  | -36575 | 037098 | 0 | -1828.75
999 | Sales | AR | 520 | 05/18/18 | 05/18/18 | 2043CH | Compass Harbor Construction 1,LLC $Aegis |  |  |  |  | -30000 | 037098 | 0 | -1500
999 | Sales | AR | 520 | 05/18/18 | 05/18/18 | 2043CH | Compass Harbor Construction 1,LLC $Aegis |  |  |  |  | -55000 | 037098 | 0 | -2750
999 | Sales | AR | 520 | 05/18/18 | 05/18/18 | 2043CH | Compass Harbor Construction 1,LLC $Aegis |  |  |  |  | -90000 | 037098 | 0 | -4500
999 | Sales | AR | 670 | 06/20/18 | 06/20/18 | 2043CH | Compass Harbor Construction 1,LLC $Aegis |  |  |  |  | -29260 | 037109 | 0 | -1463
999 | Sales | AR | 670 | 06/20/18 | 06/20/18 | 2043CH | Compass Harbor Construction 1,LLC $Aegis |  |  |  |  | -11070 | 037109 | 0 | -553.5
999 | Sales | AR | 670 | 06/20/18 | 06/20/18 | 2043CH | Compass Harbor Construction 1,LLC $Aegis |  |  |  |  | -30445 | 037109 | 0 | -1522.25
999 | Sales | AR | 520 | 07/20/18 | 07/20/18 | 2043CH | Compass Harbor Construction 1,LLC $Aegis |  |  |  |  | -2480 | 037132 | 0 | -124
999 | Sales | AR | 520 | 07/20/18 | 07/20/18 | 2043CH | Compass Harbor Construction 1,LLC $Aegis |  |  |  |  | -7315 | 037132 | 0 | -365.75
999 | Sales | AR | 520 | 07/20/18 | 07/20/18 | 2043CH | Compass Harbor Construction 1,LLC $Aegis |  |  |  |  | -12000 | 037132 | 0 | -600
999 | Sales | AR | 520 | 07/20/18 | 07/20/18 | 2043CH | Compass Harbor Construction 1,LLC $Aegis |  |  |  |  | -9400 | 037132 | 0 | -470
999 | Sales | AR | 520 | 07/20/18 | 07/20/18 | 2043CH | Compass Harbor Construction 1,LLC $Aegis |  |  |  |  | -13950 | 037132 | 0 | -697.5
999 | Sales | AR | 520 | 07/20/18 | 07/20/18 | 2043CH | Compass Harbor Construction 1,LLC $Aegis |  |  |  |  | -11400 | 037132 | 0 | -570
999 | Sales | AR | 520 | 07/20/18 | 07/20/18 | 2043CH | Compass Harbor Construction 1,LLC $Aegis |  |  |  |  | -7085 | 037132 | 0 | -354.25
999 | Sales | AR | 520 | 07/20/18 | 07/20/18 | 2043CH | Compass Harbor Construction 1,LLC $Aegis |  |  |  |  | -9700 | 037132 | 0 | -485
999 | Sales | AR | 583 | 08/20/18 | 08/20/18 | 2043CH | Compass Harbor Construction 1,LLC $Aegis |  |  |  |  | -6435 | 037154 | 0 | -321.75
999 | Sales | AR | 583 | 08/20/18 | 08/20/18 | 2043CH | Compass Harbor Construction 1,LLC $Aegis |  |  |  |  | -13830 | 037154 | 0 | -691.5
999 | Sales | AR | 583 | 08/20/18 | 08/20/18 | 2043CH | Compass Harbor Construction 1,LLC $Aegis |  |  |  |  | -9100 | 037154 | 0 | -455
999 | Sales | AR | 583 | 08/20/18 | 08/20/18 | 2043CH | Compass Harbor Construction 1,LLC $Aegis |  |  |  |  | -2061 | 037154 | 0 | -103.05
999 | Sales | AR | 583 | 08/20/18 | 08/20/18 | 2043CH | Compass Harbor Construction 1,LLC $Aegis |  |  |  |  | 8620 | 037154 | 0 | 431
999 | Sales | AR | 583 | 08/20/18 | 08/20/18 | 2043CH | Compass Harbor Construction 1,LLC $Aegis |  |  |  |  | -2348 | 037154 | 0 | -117.4
999 | Sales | AR | 583 | 08/20/18 | 08/20/18 | 2043CH | Compass Harbor Construction 1,LLC $Aegis |  |  |  |  | -3600 | 037154 | 0 | -180
999 | Sales | AR | 583 | 08/20/18 | 08/20/18 | 2043CH | Compass Harbor Construction 1,LLC $Aegis |  |  |  |  | -1346 | 037154 | 0 | -67.3
999 | Sales | AR | 463 | 09/19/18 | 09/19/18 | 2043CH | Compass Harbor Construction 1,LLC $Aegis |  |  |  |  | -57300 | 037179 | 0 | -2865
999 | Sales | AR | 518 | 10/19/18 | 10/19/18 | 2043CH | Compass Harbor Construction 1,LLC $Aegis |  |  |  |  | -21600 | 037204 | 0 | -1080
999 | Sales | AR | 522 | 11/16/18 | 11/16/18 | 2043CH | Compass Harbor Construction 1,LLC $Aegis |  |  |  |  | -4800 | 037228 | 0 | -240
999 | Sales | AR | 522 | 11/16/18 | 11/16/18 | 2043CH | Compass Harbor Construction 1,LLC $Aegis |  |  |  |  | -21750 | 037228 | 0 | -1087.5
999 | Sales | AR | 347 | 12/14/18 | 12/14/18 | 2043CH | Compass Harbor Construction 1,LLC $Aegis |  |  |  |  | -13400 | 037250 | 0 | -670
999 | Sales | AR | 347 | 12/14/18 | 12/14/18 | 2043CH | Compass Harbor Construction 1,LLC $Aegis |  |  |  |  | -16320 | 037250 | 0 | -816
999 | Sales | AR | 347 | 12/14/18 | 12/14/18 | 2043CH | Compass Harbor Construction 1,LLC $Aegis |  |  |  |  | -8800 | 037250 | 0 | -440
999 | Sales | AR | 347 | 12/14/18 | 12/14/18 | 2043CH | Compass Harbor Construction 1,LLC $Aegis |  |  |  |  | -3600 | 037250 | 0 | -180
999 | Sales | AR | 347 | 12/14/18 | 12/14/18 | 2043CH | Compass Harbor Construction 1,LLC $Aegis |  |  |  |  | -24750 | 037250 | 0 | -1237.5
999 | Sales | AR | 347 | 12/14/18 | 12/14/18 | 2043CH | Compass Harbor Construction 1,LLC $Aegis |  |  |  |  | -420 | 037250 | 0 | -21
999 | Sales | AR | 553 | 01/18/19 | 01/18/19 | 2043CH | Compass Harbor Construction 1,LLC $Aegis |  |  |  |  | -20100 | 037271 | 0 | -1005
999 | Sales | AR | 553 | 01/18/19 | 01/18/19 | 2043CH | Compass Harbor Construction 1,LLC $Aegis |  |  |  |  | -23200 | 037271 | 0 | -1160
999 | Sales | AR | 553 | 01/18/19 | 01/18/19 | 2043CH | Compass Harbor Construction 1,LLC $Aegis |  |  |  |  | -4080 | 037271 | 0 | -204
999 | Sales | AR | 553 | 01/18/19 | 01/18/19 | 2043CH | Compass Harbor Construction 1,LLC $Aegis |  |  |  |  | -2200 | 037271 | 0 | -110
999 | Sales | AR | 553 | 01/18/19 | 01/18/19 | 2043CH | Compass Harbor Construction 1,LLC $Aegis |  |  |  |  | -5950 | 037271 | 0 | -297.5
999 | Sales | AR | 553 | 01/18/19 | 01/18/19 | 2043CH | Compass Harbor Construction 1,LLC $Aegis |  |  |  |  | -20250 | 037271 | 0 | -1012.5
999 | Sales | AR | 553 | 01/18/19 | 01/18/19 | 2043CH | Compass Harbor Construction 1,LLC $Aegis |  |  |  |  | -4308 | 037271 | 0 | -215.4
999 | Sales | AR | 553 | 01/18/19 | 01/18/19 | 2043CH | Compass Harbor Construction 1,LLC $Aegis |  |  |  |  | -441 | 037271 | 0 | -22.05
999 | Sales | AR | 553 | 01/18/19 | 01/18/19 | 2043CH | Compass Harbor Construction 1,LLC $Aegis |  |  |  |  | -8474 | 037271 | 0 | -423.7
999 | Sales | AR | 553 | 01/18/19 | 01/18/19 | 2043CH | Compass Harbor Construction 1,LLC $Aegis |  |  |  |  | -95 | 037271 | 0 | -4.75
999 | Sales | AR | 553 | 01/18/19 | 01/18/19 | 2043CH | Compass Harbor Construction 1,LLC $Aegis |  |  |  |  | -2775 | 037271 | 0 | -138.75
999 | Sales | AR | 553 | 01/18/19 | 01/18/19 | 2043CH | Compass Harbor Construction 1,LLC $Aegis |  |  |  |  | -70 | 037271 | 0 | -3.5
999 | Sales | AR | 553 | 01/18/19 | 01/18/19 | 2043CH | Compass Harbor Construction 1,LLC $Aegis |  |  |  |  | -571 | 037271 | 0 | -28.55
999 | Sales | AR | 553 | 01/18/19 | 01/18/19 | 2043CH | Compass Harbor Construction 1,LLC $Aegis |  |  |  |  | -748 | 037271 | 0 | -37.4
999 | Sales | AR | 553 | 01/18/19 | 01/18/19 | 2043CH | Compass Harbor Construction 1,LLC $Aegis |  |  |  |  | 23200 | 037271 | 0 | 1160
999 | Sales | AR | 567 | 02/20/19 | 02/20/19 | 2043CH | Compass Harbor Construction 1,LLC $Aegis |  |  |  |  | -609 | 037289 | 0 | -30.45
999 | Sales | AR | 567 | 02/20/19 | 02/20/19 | 2043CH | Compass Harbor Construction 1,LLC $Aegis |  |  |  |  | -831 | 037289 | 0 | -41.55
999 | Sales | AR | 567 | 02/20/19 | 02/20/19 | 2043CH | Compass Harbor Construction 1,LLC $Aegis |  |  |  |  | -490 | 037289 | 0 | -24.5
999 | Sales | AR | 567 | 02/20/19 | 02/20/19 | 2043CH | Compass Harbor Construction 1,LLC $Aegis |  |  |  |  | -2480 | 037289 | 0 | -124
999 | Sales | AR | 607 | 04/19/19 | 04/19/19 | 2043CH | Compass Harbor Construction 1,LLC $Aegis |  |  |  |  | -2414 | 037323 | 0 | -120.7

## Crew Roster
CREW ROSTER — 32 WORKERS
Per-worker hours + wages grouped by tier (APPRENTICE / JOURNEYMAN / LEAD / OT-ONLY). nominal_rate = regular_amount ÷ regular_hours. Mirrors Sam Worker Wages tab.
Tier | Worker (Last, First) | Reg Hours | OT Hours | DT Hours | Reg Amount | OT Amount | Nominal Rate ($/hr)
APPRENTICE/HELPER | Paco Leyva, Orlando | 56 | 0 | 0 | 816 | 0 | 14.5714
APPRENTICE/HELPER | Trower-Kelly, Fidel D | 147 | 31.5 | 0 | 2352 | 756 | 16
APPRENTICE/HELPER | Stahlschmidt, John P | 40 | 8 | 0 | 664 | 204 | 16.6
APPRENTICE/HELPER | Lucas Tzintzun, Rafael | 72 | 0 | 0 | 1224 | 0 | 17
APPRENTICE/HELPER | Reyes, Maria E | 80 | 28.5 | 0 | 1392 | 769.5 | 17.4
APPRENTICE/HELPER | Gutierrez Salas, Jose | 538 | 0 | 0 | 9684 | 0 | 18
APPRENTICE/HELPER | Fonseca Teruel, Eduardo | 64 | 14 | 0 | 1152 | 378 | 18
APPRENTICE/HELPER | Yohannes Jr., Samson | 16 | 0 | 0 | 288 | 0 | 18
APPRENTICE/HELPER | Lopez Reyes, Boris O | 26 | 0 | 0 | 468 | 0 | 18
APPRENTICE/HELPER | Juarez Maldonado, Oscar E | 679 | 14 | 0 | 12498 | 390 | 18.4065
APPRENTICE/HELPER | Waites, Thaddeus Z | 4 | 0 | 0 | 0 | 0 | 0
JOURNEYMAN | Chevez, Herson G | 7 | 6 | 0 | 140 | 180 | 20
JOURNEYMAN | Cruz Guzman, Joel A | 12 | 0 | 0 | 264 | 0 | 22
JOURNEYMAN | Gomez Reyes, Edith N | 70 | 21 | 0 | 1578 | 724.5 | 22.5429
JOURNEYMAN | Silva Morales, Jair J | 603 | 3 | 0 | 14106 | 103.5 | 23.393
JOURNEYMAN | Cortes Sepulveda, Jose R | 1608.5 | 33.5 | 0 | 37969 | 1176.75 | 23.6052
JOURNEYMAN | Gerard, Jordan E | 4 | 0 | 0 | 96 | 0 | 24
JOURNEYMAN | Benites Portillo, Marvin E | 5 | 2 | 0 | 120 | 72 | 24
JOURNEYMAN | Eliassen, Cory H | 167 | 30 | 0 | 4169 | 1126.5 | 24.9641
JOURNEYMAN | Ascencio, Jose L | 1180 | 40 | 0 | 30150 | 1539 | 25.5508
JOURNEYMAN | Montenegro, Carlos E | 16 | 0 | 0 | 432 | 0 | 27
JOURNEYMAN | Balderas Ortiz, Ricardo I | 1030 | 32 | 0 | 28760 | 1332 | 27.9223
JOURNEYMAN | Juarez Alvarez, Oscar R | 756 | 26 | 0 | 21855 | 1113 | 28.9087
JOURNEYMAN | Garcia, Jordan X | 234 | 0 | 0 | 7254 | 0 | 31
JOURNEYMAN | Lima Romero, Melvin A | 660 | 34 | 0 | 20866 | 1611 | 31.6152
JOURNEYMAN | McCabe, Thomas C | 13 | 1 | 0 | 429 | 49.5 | 33
LEAD/SUPERVISOR | Cortes Mendiola, Victor H | 1684 | 48 | 0 | 68530 | 2949 | 40.6948
LEAD/SUPERVISOR | Hubbard, Robert W | 331 | 7.5 | 0 | 14791 | 518.25 | 44.6858
LEAD/SUPERVISOR | Sanders, Allen O | 149 | 26.5 | 0 | 6900 | 1866 | 46.3087
LEAD/SUPERVISOR | Gerard, Jeffrey S | 123 | 0 | 0 | 5958.5 | 0 | 48.4431
LEAD/SUPERVISOR | Donelson, Richard T | 230 | 0 | 0 | 12950 | 0 | 56.3043
OT-ONLY | Taylor, Evan R | 0 | 8 | 0 | 0 | 312 | — (no reg hours)

## Wage Tiers
WAGE TIERS & PERCENTILES — 2043
Tier distribution + percentile snapshot across worker_nominal_wages. Tier thresholds: Apprentice <$20, Journeyman $20–$36, Lead $36+. OT-only = no regular hours booked.
Tier | Worker Count | Total Reg Hours | Total OT Hours | Total Labor $ | Avg Nominal Rate
APPRENTICE/HELPER | 11 | 1722 | 96 | 33035.5 | 15.6344
JOURNEYMAN | 15 | 6365.5 | 228.5 | 177215.75 | 25.9668
LEAD/SUPERVISOR | 5 | 2517 | 82 | 114462.75 | 47.2873
OT-ONLY | 1 | 0 | 8 | 312 | 0
PERCENTILES (nominal wage)
Percentile | Rate
p10 | 16.6
p25 | 18
p50 | 23.61
p75 | 29.95
p90 | 44.69
WAGE METHODOLOGY (Sam v4 Action #3)
Metric | Value | Formula
straight_time_rate | 29.0306 | SUM(regular_amount) / SUM(regular_hours)
pr_src_cost_per_hr | 44.8353 | PR total / total_labor_hours (includes OT premium)
fully_loaded_wage | 60.1737 | (PR + 995 + 998) / total_labor_hours
burden_multiplier | 1.3421 | fully_loaded / pr_src_cost_per_hr

## Productivity
PRODUCTIVITY METRICS — 2043
Labor throughput + unit-economics indicators. Per-unit / per-fixture / per-month now populated from GDrive-enriched project attributes.
Metric | Value | Formula / Notes
Total Labor Hours | 11,019.00 | SUM(reg+ot+dt+other) where source=PR
Revenue per Labor Hour | $143.70 | abs(revenue) ÷ labor hours — throughput
Labor Unit Cost per Hour | $29.50 | Labor-code JTD ÷ labor hours
Revenue ÷ Labor-Cost Ratio | 4.87x | Throughput ÷ unit cost — productivity signal
Units (residential) | 109 | Aegis Mercer Island scope doc: 81 Type B + 10 Type A + 16 memory care + 2 special
Fixtures (estimate) | 643 | Scope doc estimate — see Job Info fixture_estimate_note
Duration (months) | 20 | start_date → end_date from GDrive enrichment
Hours per Unit | 101.09 | total_labor_hours ÷ units
Hours per Fixture | 17.14 | total_labor_hours ÷ fixtures
Revenue per Unit | $14,527 | revenue ÷ units
Profit per Unit | $6,679 | net_profit ÷ units
Hours per Month | 551 | total_labor_hours ÷ duration_months
Revenue per Month | $79,172 | revenue ÷ duration_months

## Vendor Analysis
VENDOR ANALYSIS — 21 VENDORS ($332,152 AP)
AP-source vendor spend concentration. Sorted by descending spend. Top-vendor % surfaces concentration risk. Matches Sam derived_field.top_vendor_spend.
Rank | Vendor | Spend | Invoice Count | Avg Invoice | % of AP | Net Due | Retainage
1 | Keller Supply Co. $Aegis MI | 76975.46 | 8 | 9621.9325 | 23.17% | 0 | 0
2 | Keller Supply Company | 65443.39 | 50 | 1308.8678 | 19.7% | 0 | 0
3 | Rosen Supply Company, Inc. $Aegis MI | 43563.76 | 36 | 1210.1044 | 13.12% | 0 | 0
4 | California Hydronics Corp | 37728.4 | 5 | 7545.68 | 11.36% | 0 | 0
5 | Consolidated Supply Co. $Aegis MI | 31901.89 | 18 | 1772.3272 | 9.605% | 0 | 0
6 | Franklin Engineering | 29259.75 | 6 | 4876.625 | 8.809% | 0 | 0
7 | Rosen Supply Kirkland | 20677.51 | 48 | 430.7815 | 6.225% | 0 | 0
8 | Ferguson Enterprises, Inc. #3007 | 10174.62 | 16 | 635.9138 | 3.063% | 0 | 0
9 | Capital One Credit Card | 5786.71 | 31 | 186.6681 | 1.742% | 0 | 0
10 | Mechanical Resource Services, Inc. | 4072.5 | 1 | 4072.5 | 1.226% | 0 | 0
11 | Ahern Rentals | 2579.5 | 7 | 368.5 | 0.7766% | 0 | 0
12 | Quality Concrete Products, Inc. $32 | 1743 | 2 | 871.5 | 0.5248% | 0 | 0
13 | Consolidated Supply Co. | 640.23 | 4 | 160.0575 | 0.1928% | 0 | 0
14 | Platt $Rexel USA, Inc. | 485.88 | 1 | 485.88 | 0.1463% | 0 | 0
15 | Kele, Inc $ MI Controls | 377.8 | 1 | 377.8 | 0.1137% | 0 | 0
16 | Bank of America CC | 285 | 1 | 285 | 0.0858% | 0 | 0
17 | Mechanical Sales, Inc. | 242.15 | 1 | 242.15 | 0.0729% | 0 | 0
18 | ACME Corp | 87.78 | 1 | 87.78 | 0.02643% | 0 | 0
19 | Core & Main LP $HD Supply Waterworks | 76.26 | 1 | 76.26 | 0.02296% | 0 | 0
20 | R.A. Brown Backflow Testing | 50 | 1 | 50 | 0.01505% | 0 | 0
21 | Rosen Supply Company, Inc. $Metro Flats | 0 | 2 | 0 | 0% | 0 | 0

## Change Orders
CHANGE ORDER LOG — 2043
CO / COR register reconciled against internal Budget Transfer xlsx files in the Change Orders/BUDGET TRANSFERS/ GDrive folder. Executed CO sum ties to JDR-implied CO within $90.
CO # | COR # | Description | Amount | Status | Signed PDF
1 | BT CO#01 | Credit for Permits and Grease Interceptor | -22410 | executed | Y
2 | BT CO#02 | Garage trench drain | 2290 | executed | Y
3 | BT CO#03 UPDATED (supersedes CO#03 $26,453) | Backwater Valves, Courtyard Drains, Booster Pump Provisions, Pool Shower Stall, Delete Pool Trench Drain | 22853 | executed | Y
4 | BT CO#04 | Green Toilet Seats @ Memory Care Units | 441 | executed | Y
5 | BT CO#05 | 48" Shower Stalls Units 224 & 330 (ASI-09) | 2348 | executed | Y
6 | BT CO#06 | Added Irrigation Line | 3600 | executed | Y
7 | BT CO#07 | Nails & Screws in PVC Pipes | 1346 | executed | Y
8 | BT CO#08 (CO#08 originally cancelled as duplicate of CO#05, re-issued 11/21/18) | Icemakers in units 222 & 328 | 420 | executed | Y
9 | BT CO#09 | Exterior Trench Drains | 8474 | executed | Y
10 | BT CO#10 | Sink changes, Condensate Final Hookups | 2940 | executed | Y
11 | BT CO#11 | Replace Vandalized Sinks | 571 | executed | Y
12 | BT CO#12 | Install Kitchen Equipment | 748 | executed | Y
13 | BT CO#13 | Delete Access Panels (credit) | -23200 | executed | Y
14 | BT CO#14 | Display Kitchen Sink & Faucet | 609 | executed | Y
15 | BT CO#15 | Gusher Plumbing (Internal Piping for Dishwasher) | 831 | executed | Y
16 | BT CO#16 | Pull & Reset Toilets due to fire sprinkler leak | 490 | executed | Y
17 | BT CO#17 | LN Area Changes, Kitchen Faucet Credit | 2480 | executed | Y
18 | BT CO#18 | Fix Storm Line in Boiler Room, Add icemaker drain, revise washer piping | 2414 | executed | Y
19 | Final Closeout CO | Final Closeout 05-14-19 (admin closeout, zero impact to contract) | 0 | executed | Y
Executed subtotal |  |  | 7245
Budget-transfer total (incl. extras) |  |  | 7245
JDR-implied CO (revenue − original contract) |  |  | 7245
Reconciliation gap |  |  | 0
UNEXECUTED / SUPERSEDED COR_s
COR # | Description

## Project Team
PROJECT TEAM — 2043
Primary contacts extracted from Aegis Mercer Island project start-up PDF + signed subcontract.
Role | Name | Email | Phone
GC Project Manager | Howard (Compass PM — approved insurance cert + contract execution) | TBD | TBD
GC Superintendent | TBD | TBD | TBD
OWP Signatory | Mike Donelson (OWP Vice President) | mike@onewayplumbing.com | 425-968-8314
Architect | Ankrom Moisan Architects (AMA) / CEI + Ricca kitchen
Owner | ASC Mercer Island, LLC (Aegis Senior Communities)
Inspecting Authority | City of Mercer Island

## Document Pipeline
DOCUMENT PIPELINE — 2043
Quantitative document counts from the Aegis Mercer Island GDrive close-out package — used by the Cortex dashboard for CO/RFI/Submittal density metrics.
Category | Count | Source folder
Executed Change Orders | 18 | Change Orders/CO_s/ + BUDGET TRANSFERS/
CORs submitted | 30 | Change Orders/COR_s/
Budget transfer entries | 18 | Change Orders/BUDGET TRANSFERS/
ASI / RFI responses | 20 | ASI-RFI/
Submittals | 0 | Submittals/ (PDF count)
POs — placed | 0 | PO_s/1 Placed/
POs — scheduled | 0 | PO_s/2 Scheduled/
POs — completed | 0 | PO_s/3 Completed/
POs — total | 0 | PO_s/ (all three subfolders)
Vendor invoices | 187 | Invoices/
Lien releases | 0 | Billing/ (LUNA Ave Lien Release #1–19 minus gaps)
Permits issued | 4 | Permits/
Backcharges | 0 | Change Orders/COR_s/ (COR #11 Damaged Scissor Lift)

## Benchmarks & Derived
BENCHMARKS & DERIVED FIELDS — 2043
All 45+ derived values that Sam Test-Labels v4 ships — carried forward field-for-field. Sections: cost-by-source, labor analytics, material analytics, phase analytics, budget/forecast.
COST-BY-SOURCE ROLLUPS
Field | Value | Formula / Logic
cost_by_source_pr_amount | 494040.06 | SUM(line_items where source=PR)
cost_by_source_ap_amount | 332151.59 | SUM(line_items where source=AP)
cost_by_source_gl_amount | 29247.6 | SUM(line_items where source=GL)
direct_cost | 855439.25 | PR + AP + GL
net_profit | 728005.75 | abs(revenue) − direct_cost
pr_pct_of_revenue | 0.312 | PR / abs(revenue)
ap_pct_of_revenue | 0.20977 | AP / abs(revenue)
direct_cost_pct_of_revenue | 0.54024 | direct / abs(revenue)
LABOR ANALYTICS
Field | Value | Formula / Logic
total_labor_hours | 11019 | SUM(reg+ot+dt+other) source=PR
pr_src_cost_per_hr | 44.8353 | PR / labor hours
fully_loaded_wage | 60.1737 | (PR + burden) / labor hours
burden_multiplier | 1.3421 | fully_loaded / pr_src
straight_time_rate | 29.0306 | SUM(reg_amount) / SUM(reg_hours)
total_workers | 32 | COUNT DISTINCT(name) source=PR
burden_total | 169014.06 | SUM(actual) codes 995+998
wage_percentiles (p10/p25/p50/p75/p90) | $16.60 ¦ $18.00 ¦ $23.61 ¦ $29.95 ¦ $44.69 | Percentile snapshot across worker_nominal_wages
MATERIAL ANALYTICS
Field | Value | Formula / Logic
material_spend_total | 320019.62 | SUM(actual) codes 2xx
material_budget_total | 551921 | SUM(current_budget) codes 2xx
material_codes_tracked | 9 | COUNT material codes
material_codes_over_budget | 1 | COUNT where plus_minus > 0
material_codes_under_budget | 8 | COUNT where plus_minus ≤ 0
largest_material_overrun | 243 Condensation Drains Mat: $1,275 vs $0 budget (+$1,275) | Material code with largest +plus_minus
largest_material_savings | 230 Finish Material: $200,688 vs $321,400 budget ($-120,712) | Material code with largest −plus_minus
material_vendor_count | 21 | COUNT DISTINCT vendors source=AP
top_vendor_spend | Keller Supply Co. $Aegis MI: $76,975 (23% of AP) | Vendor with highest AP spend
PHASE ANALYTICS
Field | Value | Formula / Logic
phases_over_budget | 6 | COUNT codes where plus_minus>0 (excl 999)
phases_under_budget | 21 | COUNT codes where plus_minus≤0 (excl 999)
largest_overrun | 143 Condensation Drains Labor: $13,291 vs $0 budget (+$13,291) | Phase with largest +plus_minus
largest_savings | 230 Finish Material: $200,688 vs $321,400 budget ($-120,712) | Phase with largest −plus_minus
BUDGET & FORECAST
Field | Value | Formula / Logic
total_jtd_cost | 855439.25 | SUM(actual) expense codes
total_budget | 1187984.03 | SUM(current_budget) expense codes
overall_pct_budget_consumed | 0.7201 | JTD / budget
total_over_under_budget | 332544.78 | budget − JTD
labor_unit_cost_per_hr | 29.4969 | Labor JTD / labor hours
revenue_per_labor_hour | 143.7013 | abs(revenue) / labor hours
material_price_variance | 231901.38 | mat_budget − mat_spend
variance_trend | N/A (single snapshot) | Requires prior-period comparison
PROJECT-LEVEL BENCHMARKS (pending)
Field | Value | Formula / Logic
project_duration_months | PENDING | (end_date − start_date) / 30.4
scope_benchmarks | PENDING | One object per scope_metrics entry

## Predictive Signals
PREDICTIVE SIGNALS — 2043
Rule-based health indicators derived from the parsed data. Green = good, yellow = watch, red = flag.
Signal | Status | Value | Threshold / Notes
Gross margin | GREEN | 46.0% | Green >25%, Yellow 10–25%, Red <10%
Phases over budget | GREEN | 6/27 | Red >50%, Yellow 25–50%, Green <25%
Material price variance | GREEN | $231,901 | Positive = under material budget
Burden multiplier | GREEN | 1.34x | Normal range 1.25–1.45x (OWP)
Revenue per labor hour | GREEN | $143.70 | Green >$100, Yellow $70–$100, Red <$70
Retainage outstanding | YELLOW | $79,172 | Monitor for collection
Top vendor concentration | GREEN | 23.2% (Keller Supply Co. $Aegis MI) | Yellow >50% (single-vendor risk)
Unused-budget codes | GREEN | 0 codes | Codes with budget but no spend

## Insights
KEY INSIGHTS — 2043
Narrative rollup — the 10 most important things a Cortex user should know about this job at a glance.
01 | Revenue billed $1,583,445, net profit $728,006 at 46.0% margin.
02 | Parsed 2,972 transactions across 29 cost codes — reconciliation PASS on all codes.
03 | 32 distinct PR-booked workers over 11,019 labor hours ($44.84/hr PR-src, $60.17/hr fully-loaded, 1.34x burden).
04 | Largest phase overrun: 143 Condensation Drains Labor: $13,291 vs $0 budget (+$13,291).
05 | Largest phase savings: 230 Finish Material: $200,688 vs $321,400 budget ($-120,712).
06 | Material spend $320,020 vs budget $551,921 ($231,901 favorable).
07 | Top AP vendor: Keller Supply Co. $Aegis MI: $76,975 (23% of AP); 21 total AP vendors.
08 | Retainage outstanding: $79,172.
09 | 6 of 27 expense phases over budget ($332,545 net vs budget).
10 | Revenue per labor hour $143.70, labor unit cost $29.50 (ratio 4.87x).

## Reconciliation
RECONCILIATION — PER COST CODE
Parsed line-item sums vs. Cost Code Totals row in the JDR. Matches Sam Reconciliation tab 1:1. Overall status: 28/28 codes tie to the cent.
Code | Description | PDF Total | Parsed Sum | Difference | Status
100 | Supervision | 3510.5 | 3510.5 | 0 | ✓
101 | Takeoff & Purchase Labor | 15398 | 15398 | 0 | ✓
110 | Underground Labor | 20109.5 | 20109.5 | 0 | ✓
111 | Garage Labor | 25234.5 | 25234.5 | 0 | ✓
112 | Canout Labor | 10065 | 10065 | 0 | ✓
120 | Roughin Labor | 146478 | 146478 | 0 | ✓
130 | Finish Labor | 25473 | 25473 | 0 | ✓
140 | Gas Labor | 9705 | 9705 | 0 | ✓
141 | Water Main/Insulation Lab | 45112 | 45112 | 0 | ✓
142 | Mech Room Labor | 10649.5 | 10649.5 | 0 | ✓
143 | Condensation Drains Labor | 13291 | 13291 | 0 | ✓
210 | Underground Material | 11843.79 | 11843.79 | 0 | ✓
211 | Garage Material | 22375.47 | 22375.47 | 0 | ✓
212 | Canout Material | 6739.32 | 6739.32 | 0 | ✓
220 | Roughin Material | 30692.52 | 30692.52 | 0 | ✓
230 | Finish Material | 200687.65 | 200687.65 | 0 | ✓
240 | Gas Material | 3780.25 | 3780.25 | 0 | ✓
241 | Water Main/Insulation Mat | 29819.24 | 29819.24 | 0 | ✓
242 | Mech Room Material | 12806.38 | 12806.38 | 0 | ✓
243 | Condensation Drains Mat | 1275 | 1275 | 0 | ✓
600 | Subcontractor | 4122.5 | 4122.5 | 0 | ✓
601 | Engineering/Plans | 29259.75 | 29259.75 | 0 | ✓
602 | Rental Equipment | 2579.5 | 2579.5 | 0 | ✓
603 | Permits & Licenses | 287.82 | 287.82 | 0 | ✓
607 | Other Expenses | 5130 | 5130 | 0 | ✓
995 | Payroll Burden | 144149.08 | 144149.08 | 0 | ✓
998 | Payroll Taxes | 24864.98 | 24864.98 | 0 | ✓
999 | Sales | -1583445 | -1583445 | 0 | ✓
RESULT: 28/28 codes reconciled

## Reconciliation Log
RECONCILIATION LOG — JOB 2043
Worked example of the Reconciliation Protocol running against Job 2043 (JCR-only, no external cross-checks). Mirrors Sam Test-Labels v4 Reconciliation Log tab.
check_id | field_name | JCR-derived value | cross-check value | cross-check source | status | notes
RC-01 | plus_minus_budget | 143 Condensation Drains Labor: $13,291 vs $0 budget (+$13,291) | actual − current_budget reconciled per code | Cost Code Summaries (internal recomputation) | PASS | Action #1 sign convention: positive = over-budget. Spot-check recomputes plus_minus from actual − current_budget; matches PDF to the cent.
RC-02 | current_budget / original_budget | current_budget total = $1,187,984; original_budget also carried per cost code | Budget totals sum across expense codes (code != 999) | BVA tab (Original vs Current columns) | PASS | Both budgets carried distinctly per Action #2. Current budget differs from original on codes that had change orders.
RC-03 | pr_src_cost_per_hr | $44.84/hr (all PR-source cost ÷ total labor hours) | Manual recomputation: PR total $494,040.06 ÷ 11,019.00 hrs | Derived Fields tab (line items → source=PR) | PASS | Phase-code filter: include all phases incl. 995 burden and 998 taxes; exclude only 999 Sales.
RC-04 | worker_nominal_wages / nominal_wage_percentiles | p10=$16.60 ¦ p25=$18.00 ¦ p50=$23.61 ¦ p75=$29.95 ¦ p90=$44.69 (32 workers) | straight_time_rate $29.03 falls within p25–p75 band | Crew Roster tab | PASS | Population-slice sanity: weighted straight_time_rate falls within the p25–p75 range, expected for this workforce composition.
RC-05 | labor_unit_cost_per_hr vs revenue_per_labor_hour | cost $29.50/hr ¦ revenue $143.70/hr ¦ ratio 4.87x | Recompute from labor-code JTD ÷ labor hours | Productivity tab (Action #7 split) | PASS | Split into two fields per Action #7. Cost and throughput are distinct metrics; their ratio is the productivity signal.
RC-06 | scope_metrics / scope_benchmarks | pending | — | project-attribute input (trade-declared) | PENDING | Awaiting plumbing scope-metric declarations for Job 2043 (fixture count, DFU total, linear feet of main). Same status as Job 2020.
RC-07 | reconciliation (per-code parse tie-out) | 28/28 codes tie to PDF to the cent | PR $494,040.06 + AP $332,151.59 + GL $29,247.60 = $855,439.25 matches direct cost | Reconciliation tab | PASS | Independent sum of line_items[] by cost_code vs. Cost Code Totals row for each code. PASS if ¦diff¦ < $0.02 for all codes.
SUMMARY
Total checks | 7
PASS | 6
PENDING | 1
FAIL | 0

## Metric Registry
METRIC REGISTRY — 2043
Canonical registry of every named metric in the workbook. Acts as a machine-readable table of contents + field dictionary. Every Sam Test-Labels v4 field has a row here.
Key | Label | Value | Source / Notes
job_number | Job Number | 2043 | JDR cover page
job_name | Job Name | Compass Aegis-Mercer Isl | JDR cover page
general_contractor | General Contractor | Compass Harbor | From AR client code
report_date | Report Date | 2026-04-03 | JDR run date
line_items_count | Line Item Count | 2972 | Length of line_items[]
cost_code_count | Cost Code Count | 28 | Length of cost_code_summaries[]
job_totals_revenue | Revenue (AR, negative) | -1583445 | Sage stores credit as negative
job_totals_revenue_abs | Revenue (absolute) | 1583445 | abs(job_totals_revenue)
job_totals_expenses | Expenses | 855439.25 | Sage job_totals_expenses
job_totals_net | Net | -728005.75 | Sage job_totals_net
job_totals_retainage | Retainage | -79172.25 | Sage job_totals_retainage
job_totals_net_due | Net Due | 0 | Sage job_totals_net_due
cost_by_source_pr_amount | PR Source Amount | 494040.06 | SUM(line_items source=PR)
cost_by_source_ap_amount | AP Source Amount | 332151.59 | SUM(line_items source=AP)
cost_by_source_gl_amount | GL Source Amount | 29247.6 | SUM(line_items source=GL)
cost_by_source_ar_amount | AR Source Amount | -1583445 | SUM(line_items source=AR)
direct_cost | Direct Cost | 855439.25 | PR + AP + GL
net_profit | Net Profit | 728005.75 | abs(revenue) − direct_cost
gross_margin_pct | Gross Margin % | 45.98% | net / abs(revenue)
labor_cost | Labor Cost (codes 1xx) | 325026 | SUM(actual) category=Labor
material_cost | Material Cost (codes 2xx) | 320019.62 | SUM(actual) category=Material
overhead_cost | Overhead Cost (codes 6xx) | 41379.57 | SUM(actual) category=Overhead
burden_cost | Burden Cost (995+998) | 169014.06 | SUM(actual) category=Burden
total_labor_hours | Total Labor Hours | 11019 | SUM(reg+ot+dt+other) source=PR
total_workers | Total Workers | 32 | COUNT DISTINCT(name) source=PR
straight_time_rate | Straight-Time Rate | 29.0306 | reg_amount ÷ reg_hours
pr_src_cost_per_hr | PR-Source Cost/Hour | 44.8353 | PR total ÷ labor hours
fully_loaded_wage | Fully-Loaded Wage | 60.1737 | (PR + burden) ÷ labor hours
burden_multiplier | Burden Multiplier | 1.3421 | fully-loaded ÷ pr-src
burden_total | Burden Total | 169014.06 | SUM(actual) codes 995+998
wage_percentile_p10 | Wage Percentile p10 | 16.6 | Percentile across workers
wage_percentile_p25 | Wage Percentile p25 | 18 | Percentile across workers
wage_percentile_p50 | Wage Percentile p50 | 23.61 | Percentile across workers
wage_percentile_p75 | Wage Percentile p75 | 29.95 | Percentile across workers
wage_percentile_p90 | Wage Percentile p90 | 44.69 | Percentile across workers
material_spend_total | Material Spend Total | 320019.62 | SUM(actual) codes 2xx
material_budget_total | Material Budget Total | 551921 | SUM(current_budget) codes 2xx
material_codes_tracked | Material Codes Tracked | 9 | COUNT codes 2xx
material_codes_over_budget | Material Codes Over Budget | 1 | COUNT where plus_minus>0
material_codes_under_budget | Material Codes Under Budget | 8 | COUNT where plus_minus≤0
material_vendor_count | Material Vendor Count | 21 | COUNT DISTINCT vendors
material_price_variance | Material Price Variance | 231901.38 | mat_budget − mat_spend
largest_material_overrun | Largest Material Overrun | 243 Condensation Drains Mat: $1,275 vs $0 budget (+$1,275)
largest_material_savings | Largest Material Savings | 230 Finish Material: $200,688 vs $321,400 budget ($-120,712)
top_vendor_spend | Top Vendor Spend | Keller Supply Co. $Aegis MI: $76,975 (23% of AP)
phases_over_budget | Phases Over Budget | 6 | COUNT codes (excl 999)
phases_under_budget | Phases Under Budget | 21 | COUNT codes (excl 999)
largest_overrun | Largest Overrun | 143 Condensation Drains Labor: $13,291 vs $0 budget (+$13,291)
largest_savings | Largest Savings | 230 Finish Material: $200,688 vs $321,400 budget ($-120,712)
total_jtd_cost | Total JTD Cost | 855439.25 | SUM(actual) expense codes
total_budget | Total Current Budget | 1187984.03 | SUM(current_budget) expense codes
overall_pct_budget_consumed | Overall % Budget Consumed | 72.01% | JTD ÷ budget
total_over_under_budget | Total Over/Under Budget | 332544.78 | budget − JTD
labor_unit_cost_per_hr | Labor Unit Cost / Hour | 29.4969 | labor JTD ÷ labor hours
revenue_per_labor_hour | Revenue per Labor Hour | 143.7013 | abs(revenue) ÷ labor hours
unit_count | Unit Count | PENDING | Project-attribute input required
fixture_count | Fixture Count | PENDING | Project-attribute input required
project_start_date | Project Start Date | PENDING | Project-attribute input required
project_end_date | Project End Date | PENDING | Project-attribute input required
duration_months | Duration (months) | PENDING | Project-attribute input required
scope_metrics | Scope Metrics | PENDING | Trade-declared {label, count, desc} array