## Overview
Job #2043 · Aegis Mercer Island (Assisted Living + Memory Care)
Cortex JCR v2 • Compass Harbor (customer 2043SH) • 7445 SE 24th Street, Mercer Island, WA 98040 • Owner: ASC Mercer Island, LLC (Aegis Senior Communities)
PROJECT OVERVIEW
Project Job # | 2043 |  | 2043 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
Project Name (Sage) | Compass Aegis-Mercer Isl |  | 2043 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
Project Description | Aegis Mercer Island — 109-unit 7-story midrise multi-family (4 Type A ADA), Seattle |  | OWP Project List with Schedule - UPDATED 04-01-26.xlsx + contract
General Contractor | Compass Harbor |  | OWP Project List with Schedule - UPDATED 04-01-26.xlsx
Customer Code (Sage) | 2043SH |  | 2043 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
Owner / Developer | ASC Mercer Island, LLC (Aegis Senior Communities) |  | OWP Project List with Schedule - UPDATED 04-01-26.xlsx
GC PM | Howard (Compass PM — approved insurance cert + contract execution) |  | 2043-Shelter Holdings subcontract SC-17-04-022-100-000 + Boren & Spruce CO docs
GC Superintendent | TBD |  | 2043-Shelter Holdings subcontract SC-17-04-022-100-000 + Boren & Spruce CO docs
GC PE | N/A |  | 2043-Shelter Holdings subcontract SC-17-04-022-100-000 + Boren & Spruce CO docs
OWP Signatory | Mike Donelson (OWP Vice President) |  | 2043-Shelter Holdings subcontract SC-17-04-022-100-000 + Boren & Spruce CO docs
Jobsite Location | 7445 SE 24th Street, Mercer Island, WA 98040 |  | OWP Project List with Schedule - UPDATED 04-01-26.xlsx
Insurance | Not Wrap |  | OWP Project List with Schedule - UPDATED 04-01-26.xlsx
Fixture Schedule | 643 fixtures total (656 unit + 98 retail/common) |  | Submittal Table of Contents + Plumbing Scope
Architect | Ankrom Moisan Architects (AMA) / CEI + Ricca kitchen |  | Aegis Mercer Island project info.pdf
Contract Type | Lump Sum |  | 2043-Shelter Holdings subcontract SC-17-04-022-100-000 + Boren & Spruce CO docs
Unit Count | 109 |  | Submittal TOC (102 Type B + 6 Type A/ADA)
Work Period | 2017-09 start → 2019-05 (20 months) |  | JDR PR/AR dates
CONTRACT VALUE |  | NET PROFIT | DIRECT COST | LABOR HOURS
1583445 |  | 728005.75 | 855439.25 | 11019
Original $1,576,200.00 + ($7,245.00) COs (0.46%) |  | 46.0% margin | 54.0% of revenue | 32 workers
SCOPE OF WORK
Full plumbing installation per Division 22: underground, garage, rough-in, finish, gas, water main, insulation, roof drains.
109-unit mixed-use (102 Type B + 6 Type A/ADA) at 7445 SE 24th Street, Mercer Island, WA 98040, 7-story midrise multi-family (Type 1A podium + Type VA above).
GC: Compass Harbor (2043SH); Owner: ASC Mercer Island, LLC (Aegis Senior Communities).
Insurance: Not Wrap (retail-adjacent residential).
Project team: Howard (Compass PM — approved insurance cert + contract execution) (GC PM) · TBD (GC Sup) · Ankrom Moisan Architects (AMA) / CEI + Ricca kitchen (Architect) · Mike Donelson (OWP Vice President) (OWP signatory).
SOURCES
Canonical financial source: 2043 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
Job totals (JDR footer): Revenue $1,583,445.00 / Expenses $855,439.25 / Net $728,005.75 / Retainage $79,172.25
Source breakdown (derived): PR $494,040.06 · AP $332,151.59 · GL $29,247.60
Contract: Lump Sum $1,576,200.00 → $1,583,445.00
Change Orders (executed): $7,245.00 net across 18 COs (CO log in enriched meta)
Project Team: Howard (Compass PM — approved insurance cert + contract execution) (PM) · TBD (Sup) · Ankrom Moisan Architects (AMA) / CEI + Ricca kitchen · ASC Mercer Island, LLC (Aegis Senior Communities)
PROJECT TEAM (OWP Job Info)
Role | Status | Name / Firm
GC | Extracted | Compass Harbor
GC PM | Extracted | Howard (Compass PM — approved insurance cert + contract execution)
GC Superintendent | Extracted | TBD
GC PE | N/A | N/A
Owner | Extracted | ASC Mercer Island, LLC (Aegis Senior Communities)
Architect | Extracted | Ankrom Moisan Architects (AMA) / CEI + Ricca kitchen
Structural | N/A | N/A
Acoustical | N/A | N/A
ADA Consultant | N/A | N/A
Interior Design | N/A | N/A
MEP Engineer | N/A | N/A
Insurance | Extracted | Not Wrap
OWP Signatory | Extracted | Mike Donelson (OWP Vice President)

## Budget vs Actual
Budget vs Actual
All 28 cost codes from JDR. Contract $1,576,200 → $1,583,445.
Cost Code | Description | Original Budget | Revised Budget | Actual | Variance | % of Revised | Hours | Source
100 | Supervision | 12900 | 13200 | 3510.5 | -9689.5 | 26.59% | 69.5 | 2043 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
101 | Takeoff & Purchase Labor | 20900 | 21200 | 15398 | -5802 | 72.63% | 277.5 | 2043 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
110 | Underground Labor | 35740 | 39130 | 20109.5 | -19020.5 | 51.39% | 596 | 2043 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
111 | Garage Labor | 51800 | 53120 | 25234.5 | -27885.5 | 47.5% | 863.5 | 2043 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
112 | Canout Labor | 6960 | 7380 | 10065 | 2685 | 136.4% | 290 | 2043 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
120 | Roughin Labor | 139140 | 143130 | 146478 | 3348 | 102.3% | 5253 | 2043 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
130 | Finish Labor | 30640 | 28735 | 25473 | -3262 | 88.65% | 922.5 | 2043 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
140 | Gas Labor | 11900 | 11900 | 9705 | -2195 | 81.55% | 275 | 2043 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
141 | Water Main/Insulation Lab | 38260 | 39220 | 45112 | 5892 | 115% | 1645 | 2043 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
142 | Mech Room Labor | 10600 | 11140 | 10649.5 | -490.5 | 95.6% | 288 | 2043 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
143 | Condensation Drains Labor | 0 | 0 | 13291 | 13291 |  | 489 | 2043 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
210 | Underground Material | 33850 | 34823 | 11843.79 | -22979.21 | 34.01% |  | 2043 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
211 | Garage Material | 28205 | 31448 | 22375.47 | -9072.53 | 71.15% |  | 2043 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
212 | Canout Material | 8700 | 9582 | 6739.32 | -2842.68 | 70.33% |  | 2043 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
220 | Roughin Material | 53365 | 54365 | 30692.52 | -23672.48 | 56.46% |  | 2043 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
230 | Finish Material | 328175 | 321400 | 200687.65 | -120712.35 | 62.44% |  | 2043 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
240 | Gas Material | 14400 | 14400 | 3780.25 | -10619.75 | 26.25% |  | 2043 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
241 | Water Main/Insulation Mat | 51400 | 52597 | 29819.24 | -22777.76 | 56.69% |  | 2043 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
242 | Mech Room Material | 30800 | 33306 | 12806.38 | -20499.62 | 38.45% |  | 2043 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
243 | Condensation Drains Mat | 0 | 0 | 1275 | 1275 |  |  | 2043 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
600 | Subcontractor | 1000 | 1000 | 4122.5 | 3122.5 | 412.2% |  | 2043 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
601 | Engineering/Plans | 55000 | 55500 | 29259.75 | -26240.25 | 52.72% |  | 2043 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
602 | Rental Equipment | 10000 | 10000 | 2579.5 | -7420.5 | 25.8% |  | 2043 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
603 | Permits & Licenses | 18000 | 3000 | 287.82 | -2712.18 | 9.594% |  | 2043 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
607 | Other Expenses | 7000 | 7000 | 5130 | -1870 | 73.29% |  | 2043 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
995 | Payroll Burden | 159145.54 | 163244.14 | 144149.08 | -19095.06 | 88.3% |  | 2043 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
998 | Payroll Taxes | 27451.26 | 28163.89 | 24864.98 | -3298.91 | 88.29% |  | 2043 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
999 | Sales | -1576200 | -1583445 | -1583445 | 0 | 100% |  | 2043 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
TOTAL |  | -390868.2 | -395460.97 | -728005.75 | -332544.78 |  | 10969

## Cost Breakdown
Cost Breakdown by Category
Direct cost composition by category from JDR cost codes
Category | Cost Codes | Actual $ | % of Direct Cost | % of Revenue | Source
Labor | 100,101,110,111,112,120,130,140,141,142,143 | 325026 | 38% | 20.53% | 2043 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
Material | 210,211,212,220,230,240,241,242,243 | 320019.62 | 37.41% | 20.21% | 2043 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
Overhead | 600,601,602,603,607 | 41379.57 | 4.837% | 2.613% | 2043 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
Payroll Burden | 995 | 144149.08 | 16.85% | 9.104% | 2043 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
Payroll Taxes | 998 | 24864.98 | 2.907% | 1.57% | 2043 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
TOTAL DIRECT COST |  | 855439.25 | 100% | 54.02%

## Material
Material Purchases — AP Vendors
Material + subcontractor spend by vendor from JDR AP records
Vendor ID | Vendor Name | Total Spend | # Transactions | Category (inferred) | Source
2043KS | Keller Supply Co. $Aegis MI | 76975.46 | 8 | Plumbing / Supplies | 2043 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
1231KS | Keller Supply Company | 65443.39 | 50 | Plumbing / Supplies | 2043 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
2043RS | Rosen Supply Company, Inc. $Aegis MI | 43563.76 | 36 | Plumbing / Supplies | 2043 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
5560CH | California Hydronics Corp | 37728.4 | 5 | Plumbing / Supplies | 2043 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
2043CS | Consolidated Supply Co. $Aegis MI | 31901.89 | 18 | Plumbing / Supplies | 2043 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
1625FE | Franklin Engineering | 29259.75 | 6 | Engineering (601) | 2043 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
1380RS | Rosen Supply Kirkland | 20677.51 | 48 | Plumbing / Supplies | 2043 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
1175FE | Ferguson Enterprises, Inc. #3007 | 10174.62 | 16 | Plumbing / Supplies | 2043 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
1234CO | Capital One Credit Card | 5786.71 | 31 | Credit Card (mixed) | 2043 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
3129MR | Mechanical Resource Services, Inc. | 4072.5 | 1 | Uncategorized | 2043 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
2713AR | Ahern Rentals | 2579.5 | 7 | Uncategorized | 2043 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
1609QC | Quality Concrete Products, Inc. $32 | 1743 | 2 | Uncategorized | 2043 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
1130CS | Consolidated Supply Co. | 640.23 | 4 | Plumbing / Supplies | 2043 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
2850PL | Platt $Rexel USA, Inc. | 485.88 | 1 | Uncategorized | 2043 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
8068MI | Kele, Inc $ MI Controls | 377.8 | 1 | Uncategorized | 2043 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
1234BA | Bank of America CC | 285 | 1 | Credit Card (mixed) | 2043 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
3612MS | Mechanical Sales, Inc. | 242.15 | 1 | Plumbing / Supplies | 2043 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
1021AT | ACME Corp | 87.78 | 1 | Uncategorized | 2043 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
5621HD | Core & Main LP $HD Supply Waterworks | 76.26 | 1 | Plumbing / Supplies | 2043 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
1421RA | R.A. Brown Backflow Testing | 50 | 1 | Testing subcontractor | 2043 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
2042RS | Rosen Supply Company, Inc. $Metro Flats | 0 | 2 | Plumbing / Supplies | 2043 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
TOTAL |  | 332151.59 | 241

## Crew & Labor
Crew & Labor — Worker Roster
All 32 unique payroll workers. OWP signatory: Mike Donelson (OWP Vice President).
Worker ID | Worker Name | Total Hours | Gross Pay | Blended Wage ($/hr) | # Work Days | Source
CO71 | Cortes Mendiola, Victor H | 1732 | 71479 | 41.2696 | 72 | 2043 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
CO73 | Cortes Sepulveda, Jose R | 1642 | 39145.75 | 23.8403 | 58 | 2043 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
AS10 | Ascencio, Jose L | 1220 | 31689 | 25.9746 | 32 | 2043 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
BA45 | Balderas Ortiz, Ricardo I | 1062 | 30092 | 28.3352 | 33 | 2043 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
JU02 | Juarez Alvarez, Oscar R | 782 | 22968 | 29.3708 | 21 | 2043 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
LI49 | Lima Romero, Melvin A | 694 | 22477 | 32.3876 | 19 | 2043 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
JU04 | Juarez Maldonado, Oscar E | 693 | 12888 | 18.5974 | 20 | 2043 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
SI48 | Silva Morales, Jair J | 606 | 14209.5 | 23.448 | 20 | 2043 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
GU78 | Gutierrez Salas, Jose | 538 | 9684 | 18 | 17 | 2043 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
HU06 | Hubbard, Robert W | 338.5 | 15309.25 | 45.2267 | 46 | 2043 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
GA70 | Garcia, Jordan X | 234 | 7254 | 31 | 6 | 2043 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
DO56 | Donelson, Richard T | 230 | 12950 | 56.3043 | 67 | 2043 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
EL33 | Eliassen, Cory H | 197 | 5295.5 | 26.8807 | 13 | 2043 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
TR60 | Trower-Kelly, Fidel D | 178.5 | 3108 | 17.4118 | 9 | 2043 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
SA54 | Sanders, Allen O | 175.5 | 8766 | 49.9487 | 29 | 2043 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
GE69 | Gerard, Jeffrey S | 123 | 5958.5 | 48.4431 | 46 | 2043 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
RE91 | Reyes, Maria E | 108.5 | 2161.5 | 19.9217 | 7 | 2043 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
GO51 | Gomez Reyes, Edith N | 91 | 2302.5 | 25.3022 | 6 | 2043 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
FO55 | Fonseca Teruel, Eduardo | 78 | 1530 | 19.6154 | 8 | 2043 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
LU09 | Lucas Tzintzun, Rafael | 72 | 1224 | 17 | 3 | 2043 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
PA11 | Paco Leyva, Orlando | 56 | 816 | 14.5714 | 3 | 2043 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
ST02 | Stahlschmidt, John P | 48 | 868 | 18.0833 | 5 | 2043 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
LO58 | Lopez Reyes, Boris O | 26 | 468 | 18 | 3 | 2043 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
YO29 | Yohannes Jr., Samson | 16 | 288 | 18 | 2 | 2043 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
MO56 | Montenegro, Carlos E | 16 | 432 | 27 | 1 | 2043 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
MC09 | McCabe, Thomas C | 14 | 478.5 | 34.1786 | 2 | 2043 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
CH20 | Chevez, Herson G | 13 | 320 | 24.6154 | 2 | 2043 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
CR79 | Cruz Guzman, Joel A | 12 | 264 | 22 | 1 | 2043 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
TA96 | Taylor, Evan R | 8 | 312 | 39 | 1 | 2043 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
BE54 | Benites Portillo, Marvin E | 7 | 192 | 27.4286 | 1 | 2043 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
WA35 | Waites, Thaddeus Z | 4 | 0 | 0 | 2 | 2043 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
GE70 | Gerard, Jordan E | 4 | 96 | 24 | 1 | 2043 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
TOTAL |  | 11019 | 325026

## Crew Analytics
Crew Analytics
Team-level labor productivity, concentration, wage dispersion
TEAM-LEVEL METRICS
Metric | Value | Notes | Source
Total Workers | 32 | Unique payroll IDs | 2043 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
Total Labor Hours | 11019 | Sum of labor codes | 2043 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
Total Gross Pay | 325026 | Sum of labor codes | 2043 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
Blended Gross Wage ($/hr) | 29.4969 | Labor$/Hrs (pre-burden) | Derived
Top Worker Hours Share | 15.72% | CO71 Cortes Mendiola, Victor H (1732 hrs) | Derived
Top 5 Workers Hours Share | 58.43% | Concentration metric | Derived
Highest Wage Rate ($/hr) | 56.3043 | Single-worker blended | Derived
Lowest Wage Rate ($/hr) | 0 | Single-worker blended | Derived
Avg Hours per Worker | 344.3438 | Includes short-tenure workers | Derived
Avg Project Days per Worker | 17.375 | Mean days | Derived

## Productivity
Productivity Metrics
Normalized ratios. Per-unit from 109 units (643 fixtures).
Metric | Value | Basis | Source / Note
Revenue per Labor Hour | 143.7013 | USD/hr
Profit per Labor Hour | 66.0682 | USD/hr
Labor Cost per Hour (blended) | 29.4969 | USD/hr | Pre-burden
Fully-Loaded Labor Rate ($/hr) | 60.1737 | USD/hr | Incl burden+taxes
Burden Multiplier | 1.3421 | x | Fully-loaded/blended
Rough-in Hours (code 120) | 5253 | hrs
Finish Hours (code 130) | 922.5 | hrs
Rough-in % of Total Hours | 47.89% | %
Gross Margin | 45.98% | %
Labor % of Revenue | 20.53% | %
Material % of Revenue | 20.21% | %
Direct Cost Ratio | 54.02% | % | All exp/Rev
Revenue per Unit (109) | 14527.0183 | USD | 109 units
Labor Hours per Unit | 101.0917 | hrs
Labor Cost per Unit | 2981.8899 | USD
Material Cost per Unit | 2935.9598 | USD
Direct Cost per Unit | 7848.0665 | USD
Rough-in Hours per Unit | 48.1927 | hrs
Revenue per Fixture | 2462.5894 | USD | 643 fixtures
Hours per Fixture | 17.1369 | hrs

## PO Commitments
PO Commitments
Inbound contract (GC → OWP). Outbound vendor commitments — see Material tab.
PO # | Date | Issuer | Type | Status | Description | Amount | Source
PRIME | 2017-08-28 | Compass Harbor | Lump Sum Subcontract | Closed | Aegis Mercer Island plumbing (109 units, 7 stories) — per Div 22 | 1576200 | 2043-Shelter Holdings subcontract SC-17-04-022-100-000 + Boren & Spruce CO docs
CO-NET | — | Compass Harbor | Change Orders (executed, 18 COs) | Executed | Net CO impact (Sage 999 rev - orig) | 7245 | 2043 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
TOTAL (contract + COs) | [5 empty] | 1583445

## Billing & SOV
Billing & Schedule of Values
187 invoices to Compass Harbor. Retainage $79,172.25.
Invoice # | Date | Total Billed (signed) | Retainage (signed) | # Lines | Source
553 | 01/18/19 | -70062 | -3503.1 | 15 | 2043 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
473 | 01/19/18 | -67920 | -3396 | 2 | 2043 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
573 | 02/20/18 | -23820 | -1191 | 2 | 2043 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
574 | 02/20/18 | 23820 | 1191 | 2 | 2043 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
575 | 02/20/18 | -51214 | -2560.7 | 5 | 2043 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
567 | 02/20/19 | -4410 | -220.5 | 4 | 2043 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
437 | 03/20/18 | -282300 | -14115 | 5 | 2043 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
99 | 03/20/18 | 282300 | 14115 | 5 | 2043 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
100 | 03/20/18 | -217600 | -10880 | 5 | 2043 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
110 | 03/20/18 | 217600 | 10880 | 5 | 2043 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
111 | 03/20/18 | -178100 | -8905 | 6 | 2043 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
607 | 04/19/19 | -2414 | -120.7 | 1 | 2043 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
539 | 04/20/18 | -509725 | -25486.25 | 8 | 2043 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
14 | 04/20/18 | 509725 | 25486.25 | 8 | 2043 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
15 | 04/20/18 | -494635 | -24731.75 | 9 | 2043 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
506 | 05/18/18 | -175000 | -8750 | 3 | 2043 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
519 | 05/18/18 | 175000 | 8750 | 3 | 2043 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
520 | 05/18/18 | -284905 | -14245.25 | 12 | 2043 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
670 | 06/20/18 | -70775 | -3538.75 | 3 | 2043 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
583 | 08/20/18 | -30100 | -1505 | 8 | 2043 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
463 | 09/19/18 | -57300 | -2865 | 1 | 2043 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
518 | 10/19/18 | -21600 | -1080 | 1 | 2043 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
372 | 10/20/17 | -68970 | -3448.5 | 5 | 2043 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
522 | 11/16/18 | -26550 | -1327.5 | 2 | 2043 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
399 | 12/14/17 | -87200 | -4360 | 1 | 2043 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
347 | 12/14/18 | -67290 | -3364.5 | 6 | 2043 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
TOTAL (signed) |  | -1583445 | -79172.25

## Insights
Insights & Observations
Narrative findings from JDR + GDrive CO log
# | Insight | Detail | Confidence | Source
1 | MARGIN PROFILE | Net profit $728,005.75 on $1,583,445.00 revenue = 46.0% gross margin. | Verified | 2043 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
2 | CONTRACT CHANGE | Original $1,576,200.00 → final $1,583,445.00 = $+7,245.00 net (0.46%) across 18 executed COs. | Verified | 2043 Job Detail Report.pdf (Sage Timberline, 04/03/2026) + CO log
3 | LABOR PROFILE | Labor cost $325,026.00 (20.5% of rev) across 11,019 hrs and 32 workers. Blended wage $29.50/hr. | Verified | 2043 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
4 | VENDOR CONCENTRATION | Top 5 AP vendors: ~$255,612.90 (77% of AP). Top vendor: Keller Supply Co. $Aegis MI ($76,975.46). | Verified | 2043 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
5 | RETAINAGE | Retainage $79,172.25 — outstanding as of report date. | Verified | 2043 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
6 | ROUGH-IN SHARE | Code 120 Roughin Labor = 5,253 hrs (48% of labor hours). | Verified | 2043 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
7 | TOP COST CODE | Largest actual cost: 230 Finish Material = $200,687.65 | Verified | 2043 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
8 | WORKER CONCENTRATION | Top worker Cortes Mendiola, Victor H = 1,732 hrs (16% of total). | Verified | 2043 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
9 | INSURANCE | Not Wrap — retail-adjacent mixed-use. | Verified | OWP Project List with Schedule - UPDATED 04-01-26.xlsx
10 | SCOPE CONTEXT | Aegis Mercer Island — 109-unit 7-story midrise (68 standard + 4 Type A ADA) + P1/P2 parking at 7445 SE 24th Street, Mercer Island, WA 98040. | Verified | Submittal TOC + scope doc

## Benchmark KPIs
Benchmark KPIs
Normalized metrics for cross-project comparison
KPI | Data Name | Value | Category | Notes | Confidence | Source Document
Job Number | job_number | 2043 | Profile | OWP job ID | Verified | 2043 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
Job Name | job_name | Aegis Mercer Island (Assisted Living + Memory Care) | Profile |  | Verified | 2043 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
General Contractor | general_contractor | Compass Harbor | Profile |  | Verified | OWP Project List with Schedule - UPDATED 04-01-26.xlsx
Owner | owner | ASC Mercer Island, LLC (Aegis Senior Communities) | Profile |  | Verified | OWP Project List with Schedule - UPDATED 04-01-26.xlsx
Architect | architect | Ankrom Moisan Architects (AMA) / CEI + Ricca kitchen | Profile |  | Verified | Aegis Mercer Island project info.pdf
Location | location | 7445 SE 24th Street, Mercer Island, WA 98040 | Profile |  | Verified | OWP Project List with Schedule - UPDATED 04-01-26.xlsx
Project Type | project_type | Multi-story assisted living & memory care (senior living): 93 assisted living units (incl. 10 Type A ADA) + 16 memory care units + commercial/amenity (salon, barber, bathtique, pool, LN dining, bistro, boutiques) | Profile |  | Verified | Scope + Submittal TOC
Insurance Type | insurance | Not Wrap | Profile |  | Verified | OWP Project List with Schedule - UPDATED 04-01-26.xlsx
GC PM | gc_pm | Howard (Compass PM — approved insurance cert + contract execution) | Profile |  | Verified | 2043-Shelter Holdings subcontract SC-17-04-022-100-000 + Boren & Spruce CO docs
GC Sup | gc_sup | TBD | Profile |  | Verified | 2043-Shelter Holdings subcontract SC-17-04-022-100-000 + Boren & Spruce CO docs
OWP Signatory | owp_signatory | Mike Donelson (OWP Vice President) | Profile |  | Verified | 2043-Shelter Holdings subcontract SC-17-04-022-100-000 + Boren & Spruce CO docs
Contract Signed Date | contract_signed_date | 2017-08-28 | Profile |  | Verified | 2043-Shelter Holdings subcontract SC-17-04-022-100-000 + Boren & Spruce CO docs
Work Start | start_date | 2017-09 | Profile |  | Verified | 2043 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
Work End | end_date | 2019-05 | Profile |  | Verified | 2043 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
Duration (months) | duration_months | 20 | Profile |  | Verified | Derived
Unit Count | unit_count | 109 | Profile | 102 Type B + 6 Type A/ADA | Verified | Submittal TOC
Total Fixtures | total_fixtures | 643 | Profile | 656 unit + 98 retail/common | Verified | Submittal TOC
Contract Original | contract_original | 1576200 | Financial |  | Verified | OWP Project List with Schedule - UPDATED 04-01-26.xlsx
Contract Final | contract_final | 1583445 | Financial |  | Verified | OWP Project List with Schedule - UPDATED 04-01-26.xlsx
Change Orders ($) | co_net | 7245 | Financial | 18 executed | Verified | 2043 Job Detail Report.pdf (Sage Timberline, 04/03/2026) + CO log
CO % of Contract | co_pct | 0.4596% | Financial |  | Verified | Derived
Revenue | revenue | 1583445 | Financial | AR total | Verified | 2043 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
Direct Cost | direct_cost | 855439.25 | Financial | JDR Expenses | Verified | 2043 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
Net Profit | net_profit | 728005.75 | Financial | Rev - Exp | Verified | 2043 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
Gross Margin | gross_margin | 45.98% | Financial |  | Verified | Derived
Retainage | retainage | 79172.25 | Financial | JDR AR retainage | Verified | 2043 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
Retainage % of Revenue | retainage_pct | 5% | Financial |  | Verified | Derived
Labor Cost | labor_cost | 325026 | Labor | Codes 100-151 | Verified | 2043 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
Material Cost | material_cost | 320019.62 | Material | Codes 210-245 | Verified | 2043 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
Overhead Cost | overhead_cost | 41379.57 | Financial | Codes 600-607 | Verified | 2043 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
Burden Cost | burden_cost | 144149.08 | Labor | Code 995 | Verified | 2043 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
Tax Cost | tax_cost | 24864.98 | Labor | Code 998 | Verified | 2043 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
Total Labor Hours | total_hours | 11019 | Labor | Sum labor codes | Verified | 2043 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
Total Workers | total_workers | 32 | Labor | Unique PR IDs | Verified | 2043 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
Blended Gross Wage | blended_wage | 29.4969 | Labor |  | Verified | Derived
Fully-Loaded Wage | loaded_wage | 60.1737 | Labor |  | Verified | Derived
Burden Multiplier | burden_mult | 1.3421 | Labor |  | Verified | Derived
Rough-in Hours | roughin_hours | 5253 | Labor | Code 120 | Verified | 2043 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
Finish Hours | finish_hours | 922.5 | Labor | Code 130 | Verified | 2043 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
Revenue per Hour | rev_per_hour | 143.7013 | Productivity |  | Verified | Derived
Profit per Hour | profit_per_hour | 66.0682 | Productivity |  | Verified | Derived
Revenue per Unit | rev_per_unit | 14527.0183 | Productivity | 109 units | Verified | Derived
Direct Cost per Unit | cost_per_unit | 7848.0665 | Productivity |  | Verified | Derived
Hours per Unit | hours_per_unit | 101.0917 | Productivity |  | Verified | Derived
Revenue per Fixture | rev_per_fixture | 2462.5894 | Productivity | 643 fixtures | Verified | Derived
Labor % of Revenue | labor_pct | 20.53% | Cost Mix |  | Verified | Derived
Material % of Revenue | material_pct | 20.21% | Cost Mix |  | Verified | Derived
Total Vendors | total_vendors | 21 | Material |  | Verified | 2043 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
Total Invoices | total_invoices | 26 | Billing |  | Verified | 2043 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
Top Worker Share | top_worker_share | 15.72% | Crew |  | Verified | Derived
Top 5 Worker Share | top5_worker_share | 58.43% | Crew |  | Verified | Derived
Cost Codes Active | cost_code_count | 28 | Structure |  | Verified | 2043 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
Executed CO Count | executed_co_count | 18 | Documents |  | Verified | CO log
COR Count | cor_count | 30 | Documents |  | Verified | GDrive COR folder
RFI/ASI Count | rfi_asi_count | 20 | Documents |  | Verified | GDrive ASI-RFI folder
Submittal Count | submittal_count | 0 | Documents |  | Verified | GDrive Submittals
PO Total (all) | po_count_total | 0 | Documents | placed+scheduled+completed | Verified | GDrive POs

## Vendors
Vendors — AP Summary
Vendor-level spend ranking
Rank | Vendor ID | Vendor Name | Total Spend | # Transactions | % of AP | Source
1 | 2043KS | Keller Supply Co. $Aegis MI | 76975.46 | 8 | 23.17% | 2043 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
2 | 1231KS | Keller Supply Company | 65443.39 | 50 | 19.7% | 2043 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
3 | 2043RS | Rosen Supply Company, Inc. $Aegis MI | 43563.76 | 36 | 13.12% | 2043 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
4 | 5560CH | California Hydronics Corp | 37728.4 | 5 | 11.36% | 2043 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
5 | 2043CS | Consolidated Supply Co. $Aegis MI | 31901.89 | 18 | 9.605% | 2043 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
6 | 1625FE | Franklin Engineering | 29259.75 | 6 | 8.809% | 2043 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
7 | 1380RS | Rosen Supply Kirkland | 20677.51 | 48 | 6.225% | 2043 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
8 | 1175FE | Ferguson Enterprises, Inc. #3007 | 10174.62 | 16 | 3.063% | 2043 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
9 | 1234CO | Capital One Credit Card | 5786.71 | 31 | 1.742% | 2043 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
10 | 3129MR | Mechanical Resource Services, Inc. | 4072.5 | 1 | 1.226% | 2043 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
11 | 2713AR | Ahern Rentals | 2579.5 | 7 | 0.7766% | 2043 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
12 | 1609QC | Quality Concrete Products, Inc. $32 | 1743 | 2 | 0.5248% | 2043 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
13 | 1130CS | Consolidated Supply Co. | 640.23 | 4 | 0.1928% | 2043 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
14 | 2850PL | Platt $Rexel USA, Inc. | 485.88 | 1 | 0.1463% | 2043 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
15 | 8068MI | Kele, Inc $ MI Controls | 377.8 | 1 | 0.1137% | 2043 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
16 | 1234BA | Bank of America CC | 285 | 1 | 0.0858% | 2043 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
17 | 3612MS | Mechanical Sales, Inc. | 242.15 | 1 | 0.0729% | 2043 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
18 | 1021AT | ACME Corp | 87.78 | 1 | 0.02643% | 2043 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
19 | 5621HD | Core & Main LP $HD Supply Waterworks | 76.26 | 1 | 0.02296% | 2043 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
20 | 1421RA | R.A. Brown Backflow Testing | 50 | 1 | 0.01505% | 2043 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
21 | 2042RS | Rosen Supply Company, Inc. $Metro Flats | 0 | 2 | 0% | 2043 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
TOTAL |  |  | 332151.59 | 241

## Change Log
Change Log — Master Register
Contract, 18 executed COs, retainage events — JDR + GDrive CO folder
Event ID | Type | Date | Subject | Originator | Cost Impact ($) | Status | Source
CONTRACT-ORIG | Contract | 2017-08-28 | Prime subcontract — Lump Sum $1,576,200.00 | Compass Harbor | 1576200 | Executed | 2043-Shelter Holdings subcontract SC-17-04-022-100-000 + Boren & Spruce CO docs
CO-01 | Change Order | — | Credit for Permits and Grease Interceptor | Compass Harbor | -22410 | Executed | GDrive CO 1
CO-02 | Change Order | — | Garage trench drain | Compass Harbor | 2290 | Executed | GDrive CO 2
CO-03 | Change Order | — | Backwater Valves, Courtyard Drains, Booster Pump Provisions, Pool Shower Stall, Delete Pool Trench Drain | Compass Harbor | 22853 | Executed | GDrive CO 3
CO-04 | Change Order | — | Green Toilet Seats @ Memory Care Units | Compass Harbor | 441 | Executed | GDrive CO 4
CO-05 | Change Order | — | 48" Shower Stalls Units 224 & 330 (ASI-09) | Compass Harbor | 2348 | Executed | GDrive CO 5
CO-06 | Change Order | — | Added Irrigation Line | Compass Harbor | 3600 | Executed | GDrive CO 6
CO-07 | Change Order | — | Nails & Screws in PVC Pipes | Compass Harbor | 1346 | Executed | GDrive CO 7
CO-08 | Change Order | — | Icemakers in units 222 & 328 | Compass Harbor | 420 | Executed | GDrive CO 8
CO-09 | Change Order | — | Exterior Trench Drains | Compass Harbor | 8474 | Executed | GDrive CO 9
CO-10 | Change Order | — | Sink changes, Condensate Final Hookups | Compass Harbor | 2940 | Executed | GDrive CO 10
CO-11 | Change Order | — | Replace Vandalized Sinks | Compass Harbor | 571 | Executed | GDrive CO 11
CO-12 | Change Order | — | Install Kitchen Equipment | Compass Harbor | 748 | Executed | GDrive CO 12
CO-13 | Change Order | — | Delete Access Panels (credit) | Compass Harbor | -23200 | Executed | GDrive CO 13
CO-14 | Change Order | — | Display Kitchen Sink & Faucet | Compass Harbor | 609 | Executed | GDrive CO 14
CO-15 | Change Order | — | Gusher Plumbing (Internal Piping for Dishwasher) | Compass Harbor | 831 | Executed | GDrive CO 15
CO-16 | Change Order | — | Pull & Reset Toilets due to fire sprinkler leak | Compass Harbor | 490 | Executed | GDrive CO 16
CO-17 | Change Order | — | LN Area Changes, Kitchen Faucet Credit | Compass Harbor | 2480 | Executed | GDrive CO 17
CO-18 | Change Order | — | Fix Storm Line in Boiler Room, Add icemaker drain, revise washer piping | Compass Harbor | 2414 | Executed | GDrive CO 18
CO-19 | Change Order | — | Final Closeout 05-14-19 (admin closeout, zero impact to contract) | Compass Harbor | 0 | Executed | GDrive CO 19
FIRST-INVOICE | Invoice | 01/18/19 | First billing (per JDR) | Sub (OWP) | 0 | Paid | 2043 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
LAST-INVOICE | Invoice | 12/14/18 | Last billing (per JDR) | Sub (OWP) | 0 | Paid | 2043 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
RETAINAGE-OPEN | Retainage | As of 04/03/2026 | Retainage $79,172.25 (outstanding) | GC | 0 | Outstanding | 2043 Job Detail Report.pdf (Sage Timberline, 04/03/2026)

## Root Cause Analysis
Root Cause Analysis
Primary variance drivers by category
Category | Codes | Net $ Variance | Root Cause (inferred) | Notes
Contract Change | 999 (Sales) | 7245 | JDR-implied net CO impact | $1,576,200 → $1,583,445 (18 executed COs)
Labor | 100,101,110,111,112,120,130,140,141,142,143,145,150 | -43129 | Labor variance vs revised budget | 32 workers
Material | 210,211,212,213,220,230,240,241,242,243,244,245 | -231901.38 | Material procurement variance | 21 vendors
Overhead | 600,601,602,603,604,607 | -35120.43 | Engineering/permits/subcon variance
Burden+Tax | 995+998 | -22393.97 | Payroll accrual tracking labor
TOTAL NET VARIANCE |  | -325299.78
RESPONSIBILITY ATTRIBUTION
Responsible Party | # Drivers | Net $ Impact | Notes
GC / Owner (scope changes) | 18 | 7245 | Aggregate executed COs
Sub (OWP) labor performance | 11 | -43129 | Hours + rate vs budget
Sub (OWP) material procurement | 9 | -231901.38 | 21 vendors
OWP burden accrual | 2 | -22393.97 | Payroll burden + tax
OWP overhead | 5 | -35120.43 | Engineering/permits/subcon

## Predictive Signals
Predictive Signals
Leading indicators from JDR + CO log
CURRENT-STATE SIGNALS
Indicator | Current Value | Benchmark | Status | Meaning
Contract Change % | 0.46% | ±10% | HEALTHY | +0.46% net (18 COs)
Labor % of Revenue | 20.53% | <30% | HEALTHY | 20.5%
GL Overhead % of Revenue | 1.847% | <5% | HEALTHY | 1.8%
Vendor Concentration (Top 5) | 76.96% | <95% | HEALTHY | Top 5 = 77% of AP
Retainage % | 5% | <10% | HEALTHY | 5.0%
Gross Margin | 45.98% | >30% | HEALTHY | 46.0%
Labor Hrs Total | 11019 | varies | INFO | 11,019 hrs, 32 workers
Worker Concentration (top 1) | 15.72% | <25% | HEALTHY | 15.7% (Cortes Mendiola, Victor H)
Rough-in Labor Share | 47.89% | 40-65% | HEALTHY | 48%
Retainage Legacy | OUTSTANDING | <90 days post-closeout | WATCH | $79,172.25
FORECAST MODELS
Forecast | Current Estimate | Confidence | Driver | Model Note
Final margin (actual) | 45.98% | Actual | Job closed | 46.0%
Retainage collection | $79,172.25 | Outstanding | Legacy | Outstanding
Unit-level economics | $14,527/unit rev, $6,679/unit profit | Verified | 109 units | Multi-story assisted living & memory care (senior living): 93 assisted living units (incl. 10 Type A ADA) + 16 memory care units + commercial/amenity (salon, barber, bathtique, pool, LN dining, bistro, boutiques)

## Metric Registry
Metric Registry — Cortex Data Catalog
Every metric with data_label, confidence, and source
# | Data Label | Human Label | Value | Unit | Source Tab | Confidence | Source Document(s)
1 | job_number | Job Number | 2043 | id | Benchmark KPIs | Verified | 2043 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
2 | job_name | Job Name | Aegis Mercer Island (Assisted Living + Memory Care) | text | Benchmark KPIs | Verified | 2043 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
3 | general_contractor | General Contractor | Compass Harbor | text | Benchmark KPIs | Verified | OWP Project List with Schedule - UPDATED 04-01-26.xlsx
4 | owner | Owner | ASC Mercer Island, LLC (Aegis Senior Communities) | text | Benchmark KPIs | Verified | OWP Project List with Schedule - UPDATED 04-01-26.xlsx
5 | architect | Architect | Ankrom Moisan Architects (AMA) / CEI + Ricca kitchen | text | Benchmark KPIs | Verified | Aegis Mercer Island project info.pdf
6 | location | Location | 7445 SE 24th Street, Mercer Island, WA 98040 | text | Benchmark KPIs | Verified | OWP Project List with Schedule - UPDATED 04-01-26.xlsx
7 | project_type | Project Type | Multi-story assisted living & memory care (senior living): 93 assisted living units (incl. 10 Type A ADA) + 16 memory care units + commercial/amenity (salon, barber, bathtique, pool, LN dining, bistro, boutiques) | text | Benchmark KPIs | Verified | Scope + Submittal TOC
8 | insurance | Insurance Type | Not Wrap | text | Benchmark KPIs | Verified | OWP Project List with Schedule - UPDATED 04-01-26.xlsx
9 | gc_pm | GC PM | Howard (Compass PM — approved insurance cert + contract execution) | text | Benchmark KPIs | Verified | 2043-Shelter Holdings subcontract SC-17-04-022-100-000 + Boren & Spruce CO docs
10 | gc_sup | GC Sup | TBD | text | Benchmark KPIs | Verified | 2043-Shelter Holdings subcontract SC-17-04-022-100-000 + Boren & Spruce CO docs
11 | owp_signatory | OWP Signatory | Mike Donelson (OWP Vice President) | text | Benchmark KPIs | Verified | 2043-Shelter Holdings subcontract SC-17-04-022-100-000 + Boren & Spruce CO docs
12 | contract_signed_date | Contract Signed Date | 2017-08-28 | date | Benchmark KPIs | Verified | 2043-Shelter Holdings subcontract SC-17-04-022-100-000 + Boren & Spruce CO docs
13 | start_date | Work Start | 2017-09 | date | Benchmark KPIs | Verified | 2043 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
14 | end_date | Work End | 2019-05 | date | Benchmark KPIs | Verified | 2043 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
15 | duration_months | Duration (months) | 20 | months | Benchmark KPIs | Verified | Derived
16 | unit_count | Unit Count | 109 | units | Benchmark KPIs | Verified | Submittal TOC
17 | total_fixtures | Total Fixtures | 643 | count | Benchmark KPIs | Verified | Submittal TOC
18 | contract_original | Contract Original | 1576200 | USD | Benchmark KPIs | Verified | OWP Project List with Schedule - UPDATED 04-01-26.xlsx
19 | contract_final | Contract Final | 1583445 | USD | Benchmark KPIs | Verified | OWP Project List with Schedule - UPDATED 04-01-26.xlsx
20 | co_net | Change Orders ($) | 7245 | USD | Benchmark KPIs | Verified | 2043 Job Detail Report.pdf (Sage Timberline, 04/03/2026) + CO log
21 | co_pct | CO % of Contract | 0.4596% | % | Benchmark KPIs | Verified | Derived
22 | revenue | Revenue | 1583445 | USD | Benchmark KPIs | Verified | 2043 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
23 | direct_cost | Direct Cost | 855439.25 | USD | Benchmark KPIs | Verified | 2043 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
24 | net_profit | Net Profit | 728005.75 | USD | Benchmark KPIs | Verified | 2043 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
25 | gross_margin | Gross Margin | 45.98% | % | Benchmark KPIs | Verified | Derived
26 | retainage | Retainage | 79172.25 | USD | Benchmark KPIs | Verified | 2043 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
27 | retainage_pct | Retainage % of Revenue | 5% | % | Benchmark KPIs | Verified | Derived
28 | labor_cost | Labor Cost | 325026 | USD | Benchmark KPIs | Verified | 2043 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
29 | material_cost | Material Cost | 320019.62 | USD | Benchmark KPIs | Verified | 2043 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
30 | overhead_cost | Overhead Cost | 41379.57 | USD | Benchmark KPIs | Verified | 2043 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
31 | burden_cost | Burden Cost | 144149.08 | USD | Benchmark KPIs | Verified | 2043 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
32 | tax_cost | Tax Cost | 24864.98 | USD | Benchmark KPIs | Verified | 2043 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
33 | total_hours | Total Labor Hours | 11019 | hours | Benchmark KPIs | Verified | 2043 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
34 | total_workers | Total Workers | 32 | count | Benchmark KPIs | Verified | 2043 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
35 | blended_wage | Blended Gross Wage | 29.4969 | USD/hr | Benchmark KPIs | Verified | Derived
36 | loaded_wage | Fully-Loaded Wage | 60.1737 | USD/hr | Benchmark KPIs | Verified | Derived
37 | burden_mult | Burden Multiplier | 1.3421 | x | Benchmark KPIs | Verified | Derived
38 | roughin_hours | Rough-in Hours | 5253 | hours | Benchmark KPIs | Verified | 2043 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
39 | finish_hours | Finish Hours | 922.5 | hours | Benchmark KPIs | Verified | 2043 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
40 | rev_per_hour | Revenue per Hour | 143.7013 | USD/hr | Benchmark KPIs | Verified | Derived
41 | profit_per_hour | Profit per Hour | 66.0682 | USD/hr | Benchmark KPIs | Verified | Derived
42 | rev_per_unit | Revenue per Unit | 14527.0183 | USD | Benchmark KPIs | Verified | Derived
43 | cost_per_unit | Direct Cost per Unit | 7848.0665 | USD | Benchmark KPIs | Verified | Derived
44 | hours_per_unit | Hours per Unit | 101.0917 | hours | Benchmark KPIs | Verified | Derived
45 | rev_per_fixture | Revenue per Fixture | 2462.5894 | USD | Benchmark KPIs | Verified | Derived
46 | labor_pct | Labor % of Revenue | 20.53% | % | Benchmark KPIs | Verified | Derived
47 | material_pct | Material % of Revenue | 20.21% | % | Benchmark KPIs | Verified | Derived
48 | total_vendors | Total Vendors | 21 | count | Benchmark KPIs | Verified | 2043 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
49 | total_invoices | Total Invoices | 26 | count | Benchmark KPIs | Verified | 2043 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
50 | top_worker_share | Top Worker Share | 15.72% | % | Benchmark KPIs | Verified | Derived
51 | top5_worker_share | Top 5 Worker Share | 58.43% | % | Benchmark KPIs | Verified | Derived
52 | cost_code_count | Cost Codes Active | 28 | count | Benchmark KPIs | Verified | 2043 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
53 | executed_co_count | Executed CO Count | 18 | count | Benchmark KPIs | Verified | CO log
54 | cor_count | COR Count | 30 | count | Benchmark KPIs | Verified | GDrive COR folder
55 | rfi_asi_count | RFI/ASI Count | 20 | count | Benchmark KPIs | Verified | GDrive ASI-RFI folder
56 | submittal_count | Submittal Count | 0 | count | Benchmark KPIs | Verified | GDrive Submittals
57 | po_count_total | PO Total (all) | 0 | count | Benchmark KPIs | Verified | GDrive POs

## Reconciliation
Reconciliation
Cross-sheet formula checks
# | Check | Value A | Value B | Delta | Status | Tabs
1 | Revenue = Contract Final | 1583445 | 1583445 | 0 | TIES | 1↔8
2 | Expenses = Labor+Mat+OH+Burden+Tax | 855439.25 | 855439.25 | 0 | TIES | 1↔3
3 | Net Profit = Revenue - Expenses | 728005.75 | 728005.75 | 0 | TIES | 1↔Derived
4 | Sage 999 actual = -Revenue | 1583445 | 1583445 | 0 | TIES | 2↔1
5 | Total Hours = Worker hours sum | 11019 | 11019 | 0 | TIES | 5↔2
6 | Contract Final - Orig = CO implied | 7245 | 7245 | 0 | TIES | 11↔Derived
7 | Worker count | 32 | 32 | 0 | TIES | 5↔1
8 | Cost code count | 28 | 28 | 0 | TIES | 2↔16