## Overview
OWP JOB 2044 — BLUEPRINT TRACK 66 APARTMENTS
Cortex JCR v2 — 17-tab Job Cost Report. Aligned with v4 Test-Labels schema (Sam coverage parity). Parsed from 175-page Sage Timberline JDR dated Apr 03, 2026.
REVENUE (AR) |  | DIRECT COST |  | NET PROFIT |  | LABOR HOURS
$855,264 |  | $588,886 |  | $266,378 |  | 7,723
Billed to date (Sage AR) |  | 68.9% of revenue |  | 31.1% margin |  | 24 workers
COST BREAKDOWN (by category)
Category | Budget | Actual | Variance | Consumption | % of Direct
Labor | 208605 | 219024.35 | -10419.35 | 105% | 37.19%
Material | 279401 | 216377.88 | 63023.12 | 77.44% | 36.74%
Overhead | 34970 | 39065.99 | -4095.99 | 111.7% | 6.634%
Burden | 107768.79 | 114417.39 | -6648.6 | 106.2% | 19.43%
TOTAL (expense codes) | 630744.79 | 588885.61 | 41859.18 | 93.36% | 100%
COST BY SOURCE (PR / AP / GL / AR)
Source | Amount | % of Direct | Notes
PR (Payroll) | 334449.89 | 56.79% | Worker hours + wages (reg + OT + burden)
AP (Vendor Invoices) | 216974.53 | 36.84% | Material + subcontractor spend
GL (General Ledger) | 37461.19 | 6.361% | Misc adjustments + deposits
AR (Billings, credit) | -855264 | 100% | Revenue billed to GC (stored negative)

## Job Info
JOB INFORMATION — 2044
Project identity + metadata enriched from GDrive close-out package (Track 66 Apartments project info PDF, signed subcontract, permits, scope).
Field | Value | Source / Notes
job_number | 2044 | JDR cover page
job_name | Blueprint Track 66 Apts | Track 66 Apartments project info PDF
job_name_long | Blueprint Track 66 Apartments (aka Roosevelt 66th, 838 NE 66th) | Track 66 Apartments project info PDF
general_contractor | Blueprint | Signed subcontract SC-03-07-6505 — Shelter Holdings / Blueprint 836, LLC
owner | Blueprint 836, LLC (self-build: developer, GC, and owner entity shared) | Signed subcontract §A.a — Blueprint 836, LLC
architect | TBD — per Plans: Franklin Engineering MEP; Blueprint design-build | Contract counterparty: Blueprint 836, LLC
location | 838 NE 66th Street, Seattle, WA 98115 | Signed subcontract + permit records
project_type | Mid-rise multi-family residential (urban infill): 68 standard + 7 Type A ADA units + common amenity (bike room, trash, coffee bar). Per Job Info xlsx: 75 units; per Schedule sheet: 78 (Job Ticket confirms 75 by fixture count). | Scope doc + submittal TOC (4-story mixed-use + 2 parking levels)
unit_count | 75 | Plan drawings: 7-story, 72 units (studios, open 1-BR, 1-BR, 2-BR, 4 Type A ADA)
fixture_count | 634 | Estimate from scope doc + submittal TOC (see fixture_estimate_note)
fixture_estimate_note | Derived from 08/16/2019 Job Ticket: 68 std toilets (Gerber 21-912) + 7 ADA toilets (Gerber 21-918) + 75 Kohler K-2035-1 wall-hung lavs + 68 std + 7 ADA Best Bath showers + 75 Delta Trinsic shower trims/valves + 75 matte-black kitchen faucets + 75 dishwasher roughins + 75 dishwasher air gaps + 75 washer roughins = 600 unit. Common: 1 ADA toilet + 1 Kohler lav + 1 kitchen/bar/coffee feeds + 5 hosebibs = 9. Building systems: 3 water heaters + expansion tank + mixing valve + circ pump + backflow + 3 irrigation POCs + 5 mech/trash/bike drains + 3 civil drains + 5 roof drains + 1 canopy drain + 1 common gas = 25. Total ≈ 634. | Explains fixture_count basis
parking_levels | 1 | Scope doc — P1, P2 rough-in sequence
floors_residential | 7 | Scope doc — L1-L4 rough-in sequence
project_start_date | 2017-09 | JDR first posting 9/8/17 → contract 7/21/17 → construction start Sep 2017
project_end_date | 2019-08 | Final lien release 12/12/2019
duration_months | 24 | start → end
contract_signed | 2017-08-03 | Signed subcontract — Mike Donelson 3/9/18
permit_jurisdiction | City of Seattle (DCI) | Seattle DCI permit (66th plumbing + gas + backflow)
permits_issued | Plumbing permit (8/9/17, approved 9/12/18, renewed 2/21/19); Gas permit (8/9/17, extended 9/10/18, renewed 2/21/19); Backflow permit (8/9/17, extended 9/12/18, renewed 2/21/19); Plumbing piping inspection report (1/9/19) | Permits folder: 3 permit types × renewals/extensions
status | CLOSED | Inferred from JDR filter: "Job 2044 only, Open, Closed"
report_date | 2026-04-03 | JDR run date

## Contract Summary
CONTRACT SUMMARY — 2044
Contract basis derived from Cost Code 999 Sales (billed AR) and expense-code budgets (Sage "Original" and "Revised" columns). Revised–Original delta = net change-order impact on internal budget.
Field | Value | Notes
original_contract_budget | 832900 | Code 999 original (negated)
current_contract_budget | 855264 | Code 999 current (negated)
revenue_ar_billed | 855264 | Sum of AR line items (abs)
retainage_outstanding | 0 | Sum of AR retainage column
net_due | 0 | Sage job_totals_net_due
expense_original_budget | 610026.39 | Sum of Org Budget across 100-607,995,998
expense_current_budget | 630744.79 | Sum of Rev Budget across 100-607,995,998
change_orders_to_budget | 20718.4 | Revised − Original across expense codes
direct_cost | 588885.61 | PR + AP + GL totals
net_profit | 266378.39 | abs(revenue) − direct_cost
gross_margin_pct | 31.15% | net / revenue

## Cost Categories
COST CATEGORIES — 2044
Rollup of the 29 Sage cost codes into five taxonomic buckets: Labor (1xx), Material (2xx), Overhead (6xx), Burden (995/998), Revenue (999).
Category | Code Count | Original Budget | Current Budget | Actual | Variance | Consumption % | Per-Unit Cost*
Labor | 10 | 206175 | 208605 | 219024.35 | -10419.35 | 105% | PENDING (needs unit_count)
Material | 9 | 262392 | 279401 | 216377.88 | 63023.12 | 77.44% | PENDING (needs unit_count)
Overhead | 5 | 34970 | 34970 | 39065.99 | -4095.99 | 111.7% | PENDING (needs unit_count)
Burden | 2 | 106489.39 | 107768.79 | 114417.39 | -6648.6 | 106.2% | PENDING (needs unit_count)
Revenue | 1 | -832900 | -855264 | -855264 | 0 | 100% | PENDING (needs unit_count)

## Budget vs Actual
BUDGET vs ACTUAL — 29 COST CODES
Full cost-code ledger with original/revised/actual/variance. Matches Sam Cost Code Summaries tab exactly. Labor codes include hours breakdown (reg/ot/dt).
Code | Description | Category | Original Budget | Current Budget | +/- Budget | Actual | Net Due | Retainage | Reg Hours | OT Hours | DT Hours | Consumption % | Status
100 | Supervision | Labor | 6750 | 6750 | -5159.25 | 1590.75 | 0 | 0 | 30.5 | 0 | 0 | 23.57% | UNDER
101 | Takeoff & Purchase Labor | Labor | 10875 | 10875 | -6017 | 4858 | 0 | 0 | 85 | 0 | 0 | 44.67% | UNDER
110 | Underground Labor | Labor | 17585 | 17585 | -14173.5 | 3411.5 | 0 | 0 | 96 | 1 | 0 | 19.4% | UNDER
111 | Garage Labor | Labor | 0 | 0 | 200 | 200 | 0 | 0 | 4 | 0 | 0 | 0% | UNDER
112 | Canout Labor | Labor | 6850 | 6850 | -3741.5 | 3108.5 | 0 | 0 | 94.5 | 0 | 0 | 45.38% | UNDER
120 | Roughin Labor | Labor | 96130 | 98690 | 51739.23 | 150429.23 | 0 | 0 | 5227.75 | 67 | 0 | 152.4% | CRITICAL
130 | Finish Labor | Labor | 23100 | 22970 | -5750.5 | 17219.5 | 0 | 0 | 741.5 | 0 | 0 | 74.97% | UNDER
140 | Gas Labor | Labor | 6000 | 6000 | -1448.5 | 4551.5 | 0 | 0 | 131.5 | 4 | 0 | 75.86% | UNDER
141 | Water Main/Insulation Lab | Labor | 25485 | 25485 | -1514.63 | 23970.37 | 0 | 0 | 966 | 25 | 0 | 94.06% | ON
142 | Mech Room Labor | Labor | 13400 | 13400 | -3715 | 9685 | 0 | 0 | 249 | 0 | 0 | 72.28% | UNDER
210 | Underground Material | Material | 16585 | 16585 | -15267.25 | 1317.75 | 0 | 0 | 0 | 0 | 0 | 7.945% | UNDER
211 | Garage Material | Material | 0 | 0 | 2172.87 | 2172.87 | 0 | 0 | 0 | 0 | 0 | 0% | UNDER
212 | Canout Material | Material | 8220 | 8220 | -3117.18 | 5102.82 | 0 | 0 | 0 | 0 | 0 | 62.08% | UNDER
220 | Roughin Material | Material | 44200 | 45350 | -2967.87 | 42382.13 | 0 | 0 | 0 | 0 | 0 | 93.46% | ON
230 | Finish Material | Material | 147457 | 163316 | -29622.92 | 133693.08 | 0 | 0 | 0 | 0 | 0 | 81.86% | UNDER
240 | Gas Material | Material | 6800 | 6800 | -4701.62 | 2098.38 | 0 | 0 | 0 | 0 | 0 | 30.86% | UNDER
241 | Water Main/Insulation Mat | Material | 26630 | 26630 | -12530.34 | 14099.66 | 0 | 0 | 0 | 0 | 0 | 52.95% | UNDER
242 | Mech Room Material | Material | 12500 | 12500 | 3011.19 | 15511.19 | 0 | 0 | 0 | 0 | 0 | 124.1% | OVER
243 | Condensation Drains Mat | Material | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | UNUSED
600 | Subcontractor | Overhead | 1000 | 1000 | 2900 | 3900 | 0 | 0 | 0 | 0 | 0 | 390% | CRITICAL
601 | Engineering/Plans | Overhead | 21000 | 21000 | 4725.44 | 25725.44 | 0 | 0 | 0 | 0 | 0 | 122.5% | OVER
602 | Rental Equipment | Overhead | 600 | 600 | 44.09 | 644.09 | 0 | 0 | 0 | 0 | 0 | 107.3% | ON
603 | Permits & Licenses | Overhead | 5370 | 5370 | -4675 | 695 | 0 | 0 | 0 | 0 | 0 | 12.94% | UNDER
607 | Other Expenses | Overhead | 7000 | 7000 | 1101.46 | 8101.46 | 0 | 0 | 0 | 0 | 0 | 115.7% | OVER
995 | Payroll Burden | Burden | 90717 | 91810.5 | 5774.15 | 97584.65 | 0 | 0 | 0 | 0 | 0 | 106.3% | ON
998 | Payroll Taxes | Burden | 15772.39 | 15958.29 | 874.45 | 16832.74 | 0 | 0 | 0 | 0 | 0 | 105.5% | ON
999 | Sales | Revenue | -832900 | -855264 | 0 | -855264 | 0 | 0 | 0 | 0 | 0 | 100% | —

## Cost Code Detail
COST CODE DETAIL — 2044
Per-code drill-down: transaction count, source mix, top vendor/worker, date range. Derived from line_items[] grouped by cost_code.
Code | Description | Actual | Txn Count | PR Lines | AP Lines | GL Lines | AR Lines | Top Vendor / Worker | First Date | Last Date
100 | Supervision | 1590.75 | 25 | 25 | 0 | 0 | 0 | Gerard, Jeffrey S ($1,497) | 01/04/19 | 12/21/18
101 | Takeoff & Purchase Labor | 4858 | 53 | 53 | 0 | 0 | 0 | Donelson, Richard T ($3,225) | 01/11/19 | 12/28/18
110 | Underground Labor | 3411.5 | 21 | 21 | 0 | 0 | 0 | Anderson, Richard P ($1,472) | 02/23/18 | 06/15/18
111 | Garage Labor | 200 | 2 | 2 | 0 | 0 | 0 | Barnhart, Joseph N ($100) | 07/12/19 | 07/19/19
112 | Canout Labor | 3108.5 | 11 | 11 | 0 | 0 | 0 | Anderson, Richard P ($1,430) | 04/06/18 | 06/22/18
120 | Roughin Labor | 150429.23 | 207 | 206 | 0 | 1 | 0 | Holmes, Anthony R ($51,689) | 01/04/19 | 12/28/18
130 | Finish Labor | 17219.5 | 45 | 45 | 0 | 0 | 0 | Eliassen, Cory H ($7,317) | 04/26/19 | 09/20/19
140 | Gas Labor | 4551.5 | 16 | 16 | 0 | 0 | 0 | McCabe, Thomas C ($1,505) | 02/08/19 | 08/31/18
141 | Water Main/Insulation Lab | 23970.37 | 41 | 40 | 0 | 1 | 0 | Mendoza, Edgar E ($12,331) | 01/04/19 | 12/28/18
142 | Mech Room Labor | 9685 | 22 | 22 | 0 | 0 | 0 | Sepulveda Gonzalez, Alfredo ($4,550) | 03/08/19 | 08/30/19
210 | Underground Material | 1317.75 | 4 | 0 | 4 | 0 | 0 | Rosen Supply Company, Inc. $66th Apts ($1,318) | 03/20/18 | 04/13/18
211 | Garage Material | 2172.87 | 23 | 0 | 4 | 19 | 0 | Rosen Supply Kirkland ($1,545) | 01/11/19 | 11/30/18
212 | Canout Material | 5102.82 | 7 | 0 | 1 | 6 | 0 | Req 3614 ($3,568) | 04/10/18 | 08/10/18
220 | Roughin Material | 42382.13 | 63 | 0 | 31 | 32 | 0 | Rosen Supply Kirkland ($23,573) | 01/11/19 | 12/21/18
230 | Finish Material | 133693.08 | 68 | 0 | 48 | 20 | 0 | Keller Supply Company ($59,078) | 01/22/19 | 12/14/18
240 | Gas Material | 2098.38 | 22 | 0 | 14 | 8 | 0 | Rosen Supply Kirkland ($1,211) | 02/06/19 | 09/25/18
241 | Water Main/Insulation Mat | 14099.66 | 29 | 0 | 14 | 15 | 0 | Consolidated Supply Co. ($10,624) | 01/23/19 | 12/21/18
242 | Mech Room Material | 15511.19 | 16 | 0 | 10 | 6 | 0 | Ferguson Enterprises, Inc. #3007 ($8,007) | 04/30/19 | 08/08/19
243 | Condensation Drains Mat | 0 | 2 | 0 | 0 | 2 | 0 | Req 5902 ($2) | 04/24/19 | 10/16/19
600 | Subcontractor | 3900 | 2 | 0 | 2 | 0 | 0 | Mechanical Resource Services, Inc. ($3,750) | 07/30/19 | 08/19/19
601 | Engineering/Plans | 25725.44 | 14 | 0 | 14 | 0 | 0 | Franklin Engineering ($25,565) | 01/05/18 | 11/22/17
602 | Rental Equipment | 644.09 | 3 | 0 | 3 | 0 | 0 | Ahern Rentals ($1,020) | 05/17/19 | 06/10/19
603 | Permits & Licenses | 695 | 3 | 0 | 3 | 0 | 0 | Capital One Credit Card ($695) | 03/01/19 | 08/28/17
607 | Other Expenses | 8101.46 | 19 | 0 | 19 | 0 | 0 | Capital One Credit Card ($9,499) | 02/14/19 | 12/31/18
995 | Payroll Burden | 97584.65 | 441 | 441 | 0 | 0 | 0 | Holmes, Anthony R ($23,777) | 01/04/19 | 12/28/18
998 | Payroll Taxes | 16832.74 | 441 | 441 | 0 | 0 | 0 | Holmes, Anthony R ($4,101) | 01/04/19 | 12/28/18
999 | Sales | -855264 | 70 | 0 | 0 | 0 | 70 | Blueprint Capital Services, LLC $66th ($1,003,374) | 01/18/19 | 12/14/18

## Transactions Detail
TRANSACTIONS DETAIL — 1,670 LINE ITEMS
Every transaction parsed from the JDR. AR amounts are negative per Sage convention (credits). Mirrors Sam Line Items tab 1:1.
cost_code | description | source | ref_number | document_date | posted_date | number | name | regular_hours | overtime_hours | regular_amount | overtime_amount | actual_amount | check_number | net_due | retainage
100 | Supervision | PR | 68 | 02/28/18 | 03/02/18 | GE69 | Gerard, Jeffrey S | 2 | 0 | 94 | 0 | 94 | 100000 | 0 | 0
100 | Supervision | PR | 367 | 07/11/18 | 07/13/18 | DO56 | Donelson, Richard T | 1 | 0 | 62.5 | 0 | 62.5 | 20400 | 0 | 0
100 | Supervision | PR | 551 | 08/15/18 | 08/17/18 | GE69 | Gerard, Jeffrey S | 1 | 0 | 50 | 0 | 50 | 20809 | 0 | 0
100 | Supervision | PR | 812 | 08/22/18 | 08/24/18 | GE69 | Gerard, Jeffrey S | 1 | 0 | 50 | 0 | 50 | 20880 | 0 | 0
100 | Supervision | PR | 106 | 09/05/18 | 09/07/18 | GE69 | Gerard, Jeffrey S | 1 | 0 | 50 | 0 | 50 | 91032 | 0 | 0
100 | Supervision | PR | 341 | 09/12/18 | 09/14/18 | GE69 | Gerard, Jeffrey S | 2 | 0 | 100 | 0 | 100 | 21174 | 0 | 0
100 | Supervision | PR | 553 | 09/19/18 | 09/21/18 | GE69 | Gerard, Jeffrey S | 1 | 0 | 50 | 0 | 50 | 21245 | 0 | 0
100 | Supervision | PR | 102 | 10/03/18 | 10/05/18 | DO56 | Donelson, Richard T | 0.5 | 0 | 31.25 | 0 | 31.25 | 91391 | 0 | 0
100 | Supervision | PR | 310 | 10/10/18 | 10/12/18 | GE69 | Gerard, Jeffrey S | 1 | 0 | 50 | 0 | 50 | 21467 | 0 | 0
100 | Supervision | PR | 775 | 10/24/18 | 10/26/18 | GE69 | Gerard, Jeffrey S | 1 | 0 | 50 | 0 | 50 | 21616 | 0 | 0
100 | Supervision | PR | 514 | 11/14/18 | 11/16/18 | GE69 | Gerard, Jeffrey S | 2 | 0 | 100 | 0 | 100 | 21837 | 0 | 0
100 | Supervision | PR | 690 | 11/21/18 | 11/21/18 | GE69 | Gerard, Jeffrey S | 1 | 0 | 50 | 0 | 50 | 21912 | 0 | 0
100 | Supervision | PR | 338 | 12/12/18 | 12/14/18 | GE69 | Gerard, Jeffrey S | 1 | 0 | 52 | 0 | 52 | 22198 | 0 | 0
100 | Supervision | PR | 578 | 12/19/18 | 12/21/18 | GE69 | Gerard, Jeffrey S | 2 | 0 | 104 | 0 | 104 | 922269 | 0 | 0
100 | Supervision | PR | 73 | 01/02/19 | 01/04/19 | GE69 | Gerard, Jeffrey S | 1 | 0 | 52 | 0 | 52 | 22301 | 0 | 0
100 | Supervision | PR | 282 | 01/09/19 | 01/11/19 | GE69 | Gerard, Jeffrey S | 1 | 0 | 52 | 0 | 52 | 922484 | 0 | 0
100 | Supervision | PR | 75 | 02/27/19 | 03/01/19 | GE69 | Gerard, Jeffrey S | 2 | 0 | 104 | 0 | 104 | 22982 | 0 | 0
100 | Supervision | PR | 315 | 03/06/19 | 03/08/19 | GE69 | Gerard, Jeffrey S | 1 | 0 | 52 | 0 | 52 | 923054 | 0 | 0
100 | Supervision | PR | 777 | 03/20/19 | 03/22/19 | GE69 | Gerard, Jeffrey S | 1 | 0 | 52 | 0 | 52 | 923198 | 0 | 0
100 | Supervision | PR | 953 | 05/29/19 | 05/31/19 | GE69 | Gerard, Jeffrey S | 1 | 0 | 55 | 0 | 55 | 923953 | 0 | 0
100 | Supervision | PR | 255 | 06/05/19 | 06/07/19 | GE69 | Gerard, Jeffrey S | 2 | 0 | 110 | 0 | 110 | 924030 | 0 | 0
100 | Supervision | PR | 524 | 06/12/19 | 06/14/19 | GE69 | Gerard, Jeffrey S | 1 | 0 | 55 | 0 | 55 | 24104 | 0 | 0
100 | Supervision | PR | 694 | 06/19/19 | 06/21/19 | GE69 | Gerard, Jeffrey S | 1 | 0 | 55 | 0 | 55 | 24180 | 0 | 0
100 | Supervision | PR | 586 | 07/17/19 | 07/19/19 | GE69 | Gerard, Jeffrey S | 1 | 0 | 55 | 0 | 55 | 24485 | 0 | 0
100 | Supervision | PR | 686 | 07/24/19 | 07/26/19 | GE69 | Gerard, Jeffrey S | 1 | 0 | 55 | 0 | 55 | 24635 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 403 | 08/16/17 | 08/18/17 | DO56 | Donelson, Richard T | 1 | 0 | 50 | 0 | 50 | 99997 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 185 | 09/06/17 | 09/08/17 | GE69 | Gerard, Jeffrey S | 1 | 0 | 47 | 0 | 47 | 97387 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 762 | 09/27/17 | 09/29/17 | GE69 | Gerard, Jeffrey S | 2 | 0 | 94 | 0 | 94 | 19577 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 67 | 10/04/17 | 10/06/17 | DO56 | Donelson, Richard T | 1 | 0 | 50 | 0 | 50 | 19638 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 70 | 01/31/18 | 02/02/18 | DO56 | Donelson, Richard T | 2 | 0 | 125 | 0 | 125 | 98801 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 71 | 01/31/18 | 02/02/18 | GE69 | Gerard, Jeffrey S | 1 | 0 | 47 | 0 | 47 | 98802 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 226 | 02/07/18 | 02/09/18 | DO56 | Donelson, Richard T | 1 | 0 | 62.5 | 0 | 62.5 | 18867 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 483 | 02/14/18 | 02/16/18 | DO56 | Donelson, Richard T | 1 | 0 | 62.5 | 0 | 62.5 | 18883 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 669 | 02/21/18 | 02/23/18 | DO56 | Donelson, Richard T | 5 | 0 | 312.5 | 0 | 312.5 | 18953 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 670 | 02/21/18 | 02/23/18 | GE69 | Gerard, Jeffrey S | 1 | 0 | 47 | 0 | 47 | 18954 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 68 | 02/28/18 | 03/02/18 | GE69 | Gerard, Jeffrey S | 4 | 0 | 188 | 0 | 188 | 100000 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 183 | 03/07/18 | 03/09/18 | DO56 | Donelson, Richard T | 1 | 0 | 62.5 | 0 | 62.5 | 99997 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 84 | 04/04/18 | 04/06/18 | DO56 | Donelson, Richard T | 1 | 0 | 62.5 | 0 | 62.5 | 99426 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 85 | 04/04/18 | 04/06/18 | GE69 | Gerard, Jeffrey S | 1 | 0 | 50 | 0 | 50 | 99427 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 340 | 06/06/18 | 06/08/18 | GE69 | Gerard, Jeffrey S | 1 | 0 | 50 | 0 | 50 | 20080 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 528 | 06/13/18 | 06/15/18 | GE69 | Gerard, Jeffrey S | 1 | 0 | 50 | 0 | 50 | 20163 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 754 | 06/20/18 | 06/22/18 | GE69 | Gerard, Jeffrey S | 1 | 0 | 50 | 0 | 50 | 290233 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 1020 | 06/27/18 | 06/29/18 | GE69 | Gerard, Jeffrey S | 1 | 0 | 50 | 0 | 50 | 20301 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 507 | 07/18/18 | 07/20/18 | DO56 | Donelson, Richard T | 1 | 0 | 62.5 | 0 | 62.5 | 920518 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 508 | 07/18/18 | 07/20/18 | GE69 | Gerard, Jeffrey S | 1 | 0 | 50 | 0 | 50 | 920519 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 834 | 07/25/18 | 07/27/18 | DO56 | Donelson, Richard T | 1 | 0 | 62.5 | 0 | 62.5 | 20592 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 835 | 07/25/18 | 07/27/18 | GE69 | Gerard, Jeffrey S | 1 | 0 | 50 | 0 | 50 | 20593 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 283 | 08/08/18 | 08/10/18 | DO56 | Donelson, Richard T | 1 | 0 | 62.5 | 0 | 62.5 | 920736 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 284 | 08/08/18 | 08/10/18 | GE69 | Gerard, Jeffrey S | 1 | 0 | 50 | 0 | 50 | 920737 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 551 | 08/15/18 | 08/17/18 | GE69 | Gerard, Jeffrey S | 2 | 0 | 100 | 0 | 100 | 20809 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 811 | 08/22/18 | 08/24/18 | DO56 | Donelson, Richard T | 2 | 0 | 125 | 0 | 125 | 20879 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 812 | 08/22/18 | 08/24/18 | GE69 | Gerard, Jeffrey S | 2 | 0 | 100 | 0 | 100 | 20880 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 1069 | 08/29/18 | 08/31/18 | DO56 | Donelson, Richard T | 1 | 0 | 62.5 | 0 | 62.5 | 90961 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 106 | 09/05/18 | 09/07/18 | GE69 | Gerard, Jeffrey S | 1 | 0 | 50 | 0 | 50 | 91032 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 340 | 09/12/18 | 09/14/18 | DO56 | Donelson, Richard T | 4 | 0 | 250 | 0 | 250 | 21173 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 341 | 09/12/18 | 09/14/18 | GE69 | Gerard, Jeffrey S | 3 | 0 | 150 | 0 | 150 | 21174 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 552 | 09/19/18 | 09/21/18 | DO56 | Donelson, Richard T | 3 | 0 | 187.5 | 0 | 187.5 | 21244 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 553 | 09/19/18 | 09/21/18 | GE69 | Gerard, Jeffrey S | 2 | 0 | 100 | 0 | 100 | 21245 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 739 | 09/26/18 | 09/28/18 | DO56 | Donelson, Richard T | 1 | 0 | 62.5 | 0 | 62.5 | 90883 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 76 | 10/31/18 | 11/02/18 | DO56 | Donelson, Richard T | 1 | 0 | 62.5 | 0 | 62.5 | 21686 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 257 | 11/07/18 | 11/09/18 | DO56 | Donelson, Richard T | 1 | 0 | 62.5 | 0 | 62.5 | 20891 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 514 | 11/14/18 | 11/16/18 | GE69 | Gerard, Jeffrey S | 1 | 0 | 50 | 0 | 50 | 21837 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 577 | 12/19/18 | 12/21/18 | DO56 | Donelson, Richard T | 1 | 0 | 62.5 | 0 | 62.5 | 922268 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 768 | 12/26/18 | 12/28/18 | DO56 | Donelson, Richard T | 2 | 0 | 125 | 0 | 125 | 22342 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 282 | 01/09/19 | 01/11/19 | GE69 | Gerard, Jeffrey S | 1 | 0 | 52 | 0 | 52 | 922484 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 75 | 02/27/19 | 03/01/19 | GE69 | Gerard, Jeffrey S | 2 | 0 | 104 | 0 | 104 | 22982 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 315 | 03/06/19 | 03/08/19 | GE69 | Gerard, Jeffrey S | 2 | 0 | 104 | 0 | 104 | 923054 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 776 | 03/20/19 | 03/22/19 | DO56 | Donelson, Richard T | 1 | 0 | 62.5 | 0 | 62.5 | 923197 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 812 | 04/24/19 | 04/26/19 | DO56 | Donelson, Richard T | 2 | 0 | 125 | 0 | 125 | 23568 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 81 | 05/01/19 | 05/03/19 | DO56 | Donelson, Richard T | 2 | 0 | 125 | 0 | 125 | 923643 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 523 | 06/12/19 | 06/14/19 | DO56 | Donelson, Richard T | 3 | 0 | 187.5 | 0 | 187.5 | 24103 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 693 | 06/19/19 | 06/21/19 | DO56 | Donelson, Richard T | 2 | 0 | 125 | 0 | 125 | 24179 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 81 | 07/03/19 | 07/05/19 | DO56 | Donelson, Richard T | 1 | 0 | 62.5 | 0 | 62.5 | 924329 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 585 | 07/17/19 | 07/19/19 | DO56 | Donelson, Richard T | 2 | 0 | 125 | 0 | 125 | 24484 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 685 | 07/24/19 | 07/26/19 | DO56 | Donelson, Richard T | 3 | 0 | 187.5 | 0 | 187.5 | 24634 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 328 | 08/07/19 | 08/09/19 | DO56 | Donelson, Richard T | 2 | 0 | 125 | 0 | 125 | 924781 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 1064 | 08/28/19 | 08/30/19 | DO56 | Donelson, Richard T | 1 | 0 | 62.5 | 0 | 62.5 | 25008 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 1064 | 08/28/19 | 08/30/19 | DO56 | Donelson, Richard T | 1 | 0 | 62.5 | 0 | 62.5 | 25008 | 0 | 0
110 | Underground Labor | PR | 603 | 02/21/18 | 02/23/18 | AN14 | Anderson, Richard P | 2.5 | 0 | 105 | 0 | 105 | 18936 | 0 | 0
110 | Underground Labor | PR | 607 | 02/21/18 | 02/23/18 | BA70 | Barnhart, Joseph N | 3.5 | 0 | 154 | 0 | 154 | 18940 | 0 | 0
110 | Underground Labor | PR | 2 | 02/28/18 | 03/02/18 | AN14 | Anderson, Richard P | 7 | 0 | 294 | 0 | 294 | 19003 | 0 | 0
110 | Underground Labor | PR | 37 | 02/28/18 | 03/02/18 | KI55 | Kinssies, Jr, John E | 7 | 0 | 182 | 0 | 182 | 19039 | 0 | 0
110 | Underground Labor | PR | 118 | 03/07/18 | 03/09/18 | AN14 | Anderson, Richard P | 11.5 | 0 | 483 | 0 | 483 | 19074 | 0 | 0
110 | Underground Labor | PR | 151 | 03/07/18 | 03/09/18 | KI55 | Kinssies, Jr, John E | 7 | 0 | 182 | 0 | 182 | 19108 | 0 | 0
110 | Underground Labor | PR | 179 | 03/07/18 | 03/09/18 | WE55 | Wennig, Johnathan M | 4.5 | 0 | 117 | 0 | 117 | 19136 | 0 | 0
110 | Underground Labor | PR | 318 | 03/14/18 | 03/16/18 | AN14 | Anderson, Richard P | 0.5 | 0 | 21 | 0 | 21 | 19139 | 0 | 0
110 | Underground Labor | PR | 516 | 03/21/18 | 03/23/18 | AN14 | Anderson, Richard P | 5 | 0 | 210 | 0 | 210 | 19207 | 0 | 0
110 | Underground Labor | PR | 550 | 03/21/18 | 03/23/18 | KI55 | Kinssies, Jr, John E | 4 | 0 | 104 | 0 | 104 | 19241 | 0 | 0
110 | Underground Labor | PR | 735 | 03/28/18 | 03/30/18 | AN14 | Anderson, Richard P | 1 | 0 | 42 | 0 | 42 | 19275 | 0 | 0
110 | Underground Labor | PR | 739 | 03/28/18 | 03/30/18 | BA70 | Barnhart, Joseph N | 1 | 0 | 44 | 0 | 44 | 19279 | 0 | 0
110 | Underground Labor | PR | 11 | 04/04/18 | 04/06/18 | AN14 | Anderson, Richard P | 2 | 0 | 84 | 0 | 84 | 19353 | 0 | 0
110 | Underground Labor | PR | 15 | 04/04/18 | 04/06/18 | BA70 | Barnhart, Joseph N | 13 | 0 | 572 | 0 | 572 | 19357 | 0 | 0
110 | Underground Labor | PR | 48 | 04/04/18 | 04/06/18 | KI55 | Kinssies, Jr, John E | 10 | 0 | 260 | 0 | 260 | 19391 | 0 | 0
110 | Underground Labor | PR | 80 | 04/04/18 | 04/06/18 | WE55 | Wennig, Johnathan M | 8 | 0 | 208 | 0 | 208 | 19423 | 0 | 0
110 | Underground Labor | PR | 259 | 04/11/18 | 04/13/18 | AN14 | Anderson, Richard P | 2.5 | 0 | 105 | 0 | 105 | 19427 | 0 | 0
110 | Underground Labor | PR | 296 | 04/11/18 | 04/13/18 | KI55 | Kinssies, Jr, John E | 2.5 | 0 | 65 | 0 | 65 | 19464 | 0 | 0
110 | Underground Labor | PR | 329 | 04/11/18 | 04/13/18 | WE55 | Wennig, Johnathan M | 2 | 0 | 52 | 0 | 52 | 19497 | 0 | 0
110 | Underground Labor | PR | 446 | 04/18/18 | 04/20/18 | AN14 | Anderson, Richard P | 1.5 | 0 | 63 | 0 | 63 | 19501 | 0 | 0
110 | Underground Labor | PR | 458 | 06/13/18 | 06/15/18 | AN14 | Anderson, Richard P | 0 | 1 | 0 | 64.5 | 64.5 | 20093 | 0 | 0
111 | Garage Labor | PR | 282 | 07/10/19 | 07/12/19 | BA70 | Barnhart, Joseph N | 2 | 0 | 100 | 0 | 100 | 24334 | 0 | 0
111 | Garage Labor | PR | 543 | 07/17/19 | 07/19/19 | HU06 | Hubbard, Robert W | 2 | 0 | 100 | 0 | 100 | 24442 | 0 | 0
112 | Canout Labor | PR | 11 | 04/04/18 | 04/06/18 | AN14 | Anderson, Richard P | 1 | 0 | 42 | 0 | 42 | 19353 | 0 | 0
112 | Canout Labor | PR | 612 | 04/25/18 | 04/27/18 | AN14 | Anderson, Richard P | 20 | 0 | 840 | 0 | 840 | 19576 | 0 | 0
112 | Canout Labor | PR | 648 | 04/25/18 | 04/27/18 | KI55 | Kinssies, Jr, John E | 22 | 0 | 572 | 0 | 572 | 19613 | 0 | 0
112 | Canout Labor | PR | 26 | 05/02/18 | 05/04/18 | AN14 | Anderson, Richard P | 3 | 0 | 126 | 0 | 126 | 19649 | 0 | 0
112 | Canout Labor | PR | 31 | 05/02/18 | 05/04/18 | BA70 | Barnhart, Joseph N | 5 | 0 | 220 | 0 | 220 | 19654 | 0 | 0
112 | Canout Labor | PR | 62 | 05/02/18 | 05/04/18 | KI55 | Kinssies, Jr, John E | 15.5 | 0 | 403 | 0 | 403 | 19685 | 0 | 0
112 | Canout Labor | PR | 3 | 05/30/18 | 06/01/18 | AN14 | Anderson, Richard P | 7.5 | 0 | 315 | 0 | 315 | 19936 | 0 | 0
112 | Canout Labor | PR | 38 | 05/30/18 | 06/01/18 | KI55 | Kinssies, Jr, John E | 7.5 | 0 | 195 | 0 | 195 | 19972 | 0 | 0
112 | Canout Labor | PR | 493 | 06/13/18 | 06/15/18 | KI55 | Kinssies, Jr, John E | 8 | 0 | 208 | 0 | 208 | 20128 | 0 | 0
112 | Canout Labor | PR | 684 | 06/20/18 | 06/22/18 | AN14 | Anderson, Richard P | 2.5 | 0 | 107.5 | 0 | 107.5 | 20163 | 0 | 0
112 | Canout Labor | PR | 705 | 06/20/18 | 06/22/18 | GA70 | Garcia, Jordan X | 2.5 | 0 | 80 | 0 | 80 | 20184 | 0 | 0
120 | Roughin Labor | PR | 426 | 05/16/18 | 05/18/18 | BA70 | Barnhart, Joseph N | 2 | 0 | 88 | 0 | 88 | 19799 | 0 | 0
120 | Roughin Labor | PR | 5 | 07/04/18 | 07/06/18 | AN14 | Anderson, Richard P | 1 | 0 | 43 | 0 | 43 | 20302 | 0 | 0
120 | Roughin Labor | PR | 68 | 07/04/18 | 07/06/18 | TA96 | Taylor, Evan R | 2 | 0 | 48 | 0 | 48 | 20364 | 0 | 0
120 | Roughin Labor | PR | 71 | 07/04/18 | 07/06/18 | WA35 | Waites, Thaddeus Z | 2 | 0 | 84 | 0 | 84 | 20367 | 0 | 0
120 | Roughin Labor | PR | 241 | 07/11/18 | 07/13/18 | BA70 | Barnhart, Joseph N | 1.5 | 0 | 69 | 0 | 69 | 20376 | 0 | 0
120 | Roughin Labor | PR | 327 | 07/11/18 | 07/13/18 | HO14 | Holmes, Anthony R | 24 | 0 | 840 | 0 | 840 | 20407 | 0 | 0
120 | Roughin Labor | PR | 360 | 07/11/18 | 07/13/18 | TA96 | Taylor, Evan R | 28 | 0 | 672 | 0 | 672 | 20440 | 0 | 0
120 | Roughin Labor | PR | 363 | 07/11/18 | 07/13/18 | WA35 | Waites, Thaddeus Z | 20 | 0 | 840 | 0 | 840 | 20443 | 0 | 0
120 | Roughin Labor | PR | 441 | 07/18/18 | 07/20/18 | BA70 | Barnhart, Joseph N | 2 | 0 | 92 | 0 | 92 | 20452 | 0 | 0
120 | Roughin Labor | PR | 468 | 07/18/18 | 07/20/18 | HO14 | Holmes, Anthony R | 40 | 0 | 1400 | 0 | 1400 | 20478 | 0 | 0
120 | Roughin Labor | PR | 501 | 07/18/18 | 07/20/18 | TA96 | Taylor, Evan R | 32 | 0 | 768 | 0 | 768 | 20511 | 0 | 0
120 | Roughin Labor | PR | 504 | 07/18/18 | 07/20/18 | WA35 | Waites, Thaddeus Z | 30.5 | 0 | 1281 | 0 | 1281 | 20514 | 0 | 0
120 | Roughin Labor | PR | 795 | 07/25/18 | 07/27/18 | HO14 | Holmes, Anthony R | 40 | 0 | 1400 | 0 | 1400 | 20552 | 0 | 0
120 | Roughin Labor | PR | 828 | 07/25/18 | 07/27/18 | TA96 | Taylor, Evan R | 27 | 0 | 648 | 0 | 648 | 20585 | 0 | 0
120 | Roughin Labor | PR | 831 | 07/25/18 | 07/27/18 | WA35 | Waites, Thaddeus Z | 15 | 0 | 630 | 0 | 630 | 20588 | 0 | 0
120 | Roughin Labor | PR | 6 | 08/01/18 | 08/03/18 | BA70 | Barnhart, Joseph N | 5.5 | 0 | 253 | 0 | 253 | 20597 | 0 | 0
120 | Roughin Labor | PR | 33 | 08/01/18 | 08/03/18 | HO14 | Holmes, Anthony R | 32 | 0 | 1120 | 0 | 1120 | 20624 | 0 | 0
120 | Roughin Labor | PR | 66 | 08/01/18 | 08/03/18 | TA96 | Taylor, Evan R | 40 | 0 | 960 | 0 | 960 | 20657 | 0 | 0
120 | Roughin Labor | PR | 69 | 08/01/18 | 08/03/18 | WA35 | Waites, Thaddeus Z | 34.5 | 0 | 1449 | 0 | 1449 | 20660 | 0 | 0
120 | Roughin Labor | PR | 216 | 08/08/18 | 08/10/18 | BA70 | Barnhart, Joseph N | 2 | 0 | 92 | 0 | 92 | 20669 | 0 | 0
120 | Roughin Labor | PR | 244 | 08/08/18 | 08/10/18 | HO14 | Holmes, Anthony R | 40 | 0 | 1400 | 0 | 1400 | 20696 | 0 | 0
120 | Roughin Labor | PR | 277 | 08/08/18 | 08/10/18 | TA96 | Taylor, Evan R | 40 | 0 | 960 | 0 | 960 | 20729 | 0 | 0
120 | Roughin Labor | PR | 280 | 08/08/18 | 08/10/18 | WA35 | Waites, Thaddeus Z | 19 | 0 | 798 | 0 | 798 | 20732 | 0 | 0
120 | Roughin Labor | PR | 512 | 08/15/18 | 08/17/18 | HO14 | Holmes, Anthony R | 38 | 0 | 1330 | 0 | 1330 | 20769 | 0 | 0
120 | Roughin Labor | PR | 520 | 08/15/18 | 08/17/18 | LO58 | Lopez Reyes, Boris O | 16 | 0 | 288 | 0 | 288 | 20777 | 0 | 0
120 | Roughin Labor | PR | 544 | 08/15/18 | 08/17/18 | TA96 | Taylor, Evan R | 24 | 0 | 576 | 0 | 576 | 20801 | 0 | 0
120 | Roughin Labor | PR | 547 | 08/15/18 | 08/17/18 | WA35 | Waites, Thaddeus Z | 1.5 | 0 | 63 | 0 | 63 | 20804 | 0 | 0
120 | Roughin Labor | PR | 774 | 08/22/18 | 08/24/18 | HO14 | Holmes, Anthony R | 40 | 0 | 1400 | 0 | 1400 | 20841 | 0 | 0
120 | Roughin Labor | PR | 779 | 08/22/18 | 08/24/18 | LE17 | Lee, Ha Nul | 32 | 0 | 544 | 0 | 544 | 20846 | 0 | 0
120 | Roughin Labor | PR | 781 | 08/22/18 | 08/24/18 | LO58 | Lopez Reyes, Boris O | 32 | 0 | 576 | 0 | 576 | 20848 | 0 | 0
120 | Roughin Labor | PR | 805 | 08/22/18 | 08/24/18 | TA96 | Taylor, Evan R | 16 | 0 | 384 | 0 | 384 | 20872 | 0 | 0
120 | Roughin Labor | PR | 809 | 08/22/18 | 08/24/18 | WE55 | Wennig, Johnathan M | 24 | 0 | 672 | 0 | 672 | 20876 | 0 | 0
120 | Roughin Labor | PR | 1000 | 08/29/18 | 08/31/18 | BA70 | Barnhart, Joseph N | 2 | 0 | 92 | 0 | 92 | 20896 | 0 | 0
120 | Roughin Labor | PR | 1029 | 08/29/18 | 08/31/18 | HO14 | Holmes, Anthony R | 32 | 0 | 1120 | 0 | 1120 | 20924 | 0 | 0
120 | Roughin Labor | PR | 1034 | 08/29/18 | 08/31/18 | LE17 | Lee, Ha Nul | 40 | 0 | 680 | 0 | 680 | 20929 | 0 | 0
120 | Roughin Labor | PR | 1036 | 08/29/18 | 08/31/18 | LO58 | Lopez Reyes, Boris O | 16 | 0 | 288 | 0 | 288 | 20931 | 0 | 0
120 | Roughin Labor | PR | 1040 | 08/29/18 | 08/31/18 | ME52 | Mendoza, Edgar E | 32 | 0 | 704 | 0 | 704 | 20935 | 0 | 0
120 | Roughin Labor | PR | 1059 | 08/29/18 | 08/31/18 | TA96 | Taylor, Evan R | 39 | 0 | 936 | 0 | 936 | 20954 | 0 | 0
120 | Roughin Labor | PR | 1063 | 08/29/18 | 08/31/18 | WE55 | Wennig, Johnathan M | 40 | 0 | 1120 | 0 | 1120 | 20958 | 0 | 0
120 | Roughin Labor | PR | 41 | 09/05/18 | 09/07/18 | BA70 | Barnhart, Joseph N | 5 | 0 | 230 | 0 | 230 | 20966 | 0 | 0
120 | Roughin Labor | PR | 68 | 09/05/18 | 09/07/18 | HO14 | Holmes, Anthony R | 32 | 0 | 1120 | 0 | 1120 | 20993 | 0 | 0
120 | Roughin Labor | PR | 73 | 09/05/18 | 09/07/18 | LE17 | Lee, Ha Nul | 32 | 0 | 544 | 0 | 544 | 20998 | 0 | 0
120 | Roughin Labor | PR | 76 | 09/05/18 | 09/07/18 | LO58 | Lopez Reyes, Boris O | 32 | 0 | 576 | 0 | 576 | 21001 | 0 | 0
120 | Roughin Labor | PR | 80 | 09/05/18 | 09/07/18 | ME52 | Mendoza, Edgar E | 32 | 0 | 704 | 0 | 704 | 21005 | 0 | 0
120 | Roughin Labor | PR | 99 | 09/05/18 | 09/07/18 | TA96 | Taylor, Evan R | 24 | 0 | 576 | 0 | 576 | 21024 | 0 | 0
120 | Roughin Labor | PR | 103 | 09/05/18 | 09/07/18 | WE55 | Wennig, Johnathan M | 32 | 0 | 896 | 0 | 896 | 21028 | 0 | 0
120 | Roughin Labor | PR | 300 | 09/12/18 | 09/14/18 | HO14 | Holmes, Anthony R | 40 | 0 | 1400 | 0 | 1400 | 21134 | 0 | 0
120 | Roughin Labor | PR | 305 | 09/12/18 | 09/14/18 | LE17 | Lee, Ha Nul | 40 | 0 | 680 | 0 | 680 | 21139 | 0 | 0
120 | Roughin Labor | PR | 307 | 09/12/18 | 09/14/18 | LO58 | Lopez Reyes, Boris O | 40 | 0 | 720 | 0 | 720 | 21141 | 0 | 0
120 | Roughin Labor | PR | 332 | 09/12/18 | 09/14/18 | TA96 | Taylor, Evan R | 40 | 0 | 960 | 0 | 960 | 21166 | 0 | 0
120 | Roughin Labor | PR | 336 | 09/12/18 | 09/14/18 | WE55 | Wennig, Johnathan M | 40 | 0 | 1120 | 0 | 1120 | 21170 | 0 | 0
120 | Roughin Labor | PR | 513 | 09/19/18 | 09/21/18 | HO14 | Holmes, Anthony R | 32 | 0 | 1120 | 0 | 1120 | 21204 | 0 | 0
120 | Roughin Labor | PR | 518 | 09/19/18 | 09/21/18 | LE17 | Lee, Ha Nul | 40 | 0 | 680 | 0 | 680 | 21209 | 0 | 0
120 | Roughin Labor | PR | 520 | 09/19/18 | 09/21/18 | LO58 | Lopez Reyes, Boris O | 32 | 0 | 576 | 0 | 576 | 21211 | 0 | 0
120 | Roughin Labor | PR | 525 | 09/19/18 | 09/21/18 | ME52 | Mendoza, Edgar E | 40 | 0 | 880 | 0 | 880 | 21216 | 0 | 0
120 | Roughin Labor | PR | 545 | 09/19/18 | 09/21/18 | TA96 | Taylor, Evan R | 40 | 0 | 960 | 0 | 960 | 21236 | 0 | 0
120 | Roughin Labor | PR | 549 | 09/19/18 | 09/21/18 | WE55 | Wennig, Johnathan M | 40 | 0 | 1120 | 0 | 1120 | 21240 | 0 | 0
120 | Roughin Labor | PR | 670 | 09/26/18 | 09/28/18 | BA70 | Barnhart, Joseph N | 4 | 0 | 184 | 0 | 184 | 21249 | 0 | 0
120 | Roughin Labor | PR | 698 | 09/26/18 | 09/28/18 | HO14 | Holmes, Anthony R | 40 | 0 | 1400 | 0 | 1400 | 21276 | 0 | 0
120 | Roughin Labor | PR | 703 | 09/26/18 | 09/28/18 | LE17 | Lee, Ha Nul | 40 | 0 | 680 | 0 | 680 | 21281 | 0 | 0
120 | Roughin Labor | PR | 705 | 09/26/18 | 09/28/18 | LO58 | Lopez Reyes, Boris O | 39.5 | 0 | 711 | 0 | 711 | 21283 | 0 | 0
120 | Roughin Labor | PR | 710 | 09/26/18 | 09/28/18 | ME52 | Mendoza, Edgar E | 39 | 0 | 858 | 0 | 858 | 21288 | 0 | 0
120 | Roughin Labor | PR | 731 | 09/26/18 | 09/28/18 | TA96 | Taylor, Evan R | 40 | 0 | 960 | 0 | 960 | 21309 | 0 | 0
120 | Roughin Labor | PR | 735 | 09/26/18 | 09/28/18 | WE55 | Wennig, Johnathan M | 40 | 0 | 1120 | 0 | 1120 | 21313 | 0 | 0
120 | Roughin Labor | PR | 34 | 10/03/18 | 10/05/18 | BA70 | Barnhart, Joseph N | 4 | 0 | 184 | 0 | 184 | 21323 | 0 | 0
120 | Roughin Labor | PR | 62 | 10/03/18 | 10/05/18 | HO14 | Holmes, Anthony R | 40 | 0 | 1400 | 0 | 1400 | 21350 | 0 | 0
120 | Roughin Labor | PR | 67 | 10/03/18 | 10/05/18 | LE17 | Lee, Ha Nul | 38.25 | 0 | 650.25 | 0 | 650.25 | 21355 | 0 | 0
120 | Roughin Labor | PR | 69 | 10/03/18 | 10/05/18 | LO58 | Lopez Reyes, Boris O | 32 | 0 | 576 | 0 | 576 | 21357 | 0 | 0
120 | Roughin Labor | PR | 95 | 10/03/18 | 10/05/18 | TA96 | Taylor, Evan R | 32 | 0 | 768 | 0 | 768 | 21383 | 0 | 0
120 | Roughin Labor | PR | 99 | 10/03/18 | 10/05/18 | WE55 | Wennig, Johnathan M | 40 | 0 | 1120 | 0 | 1120 | 21387 | 0 | 0
120 | Roughin Labor | PR | 239 | 10/10/18 | 10/12/18 | BA70 | Barnhart, Joseph N | 2 | 0 | 92 | 0 | 92 | 21396 | 0 | 0
120 | Roughin Labor | PR | 268 | 10/10/18 | 10/12/18 | HO14 | Holmes, Anthony R | 40 | 0 | 1400 | 0 | 1400 | 21425 | 0 | 0
120 | Roughin Labor | PR | 273 | 10/10/18 | 10/12/18 | LE17 | Lee, Ha Nul | 16 | 0 | 272 | 0 | 272 | 21430 | 0 | 0
120 | Roughin Labor | PR | 275 | 10/10/18 | 10/12/18 | LO58 | Lopez Reyes, Boris O | 32 | 0 | 576 | 0 | 576 | 21432 | 0 | 0
120 | Roughin Labor | PR | 301 | 10/10/18 | 10/12/18 | TA96 | Taylor, Evan R | 40 | 0 | 960 | 0 | 960 | 21458 | 0 | 0
120 | Roughin Labor | PR | 305 | 10/10/18 | 10/12/18 | WE55 | Wennig, Johnathan M | 40 | 0 | 1120 | 0 | 1120 | 21462 | 0 | 0
120 | Roughin Labor | PR | 438 | 10/17/18 | 10/19/18 | BA70 | Barnhart, Joseph N | 1 | 0 | 46 | 0 | 46 | 21471 | 0 | 0
120 | Roughin Labor | PR | 466 | 10/17/18 | 10/19/18 | HO14 | Holmes, Anthony R | 40 | 0 | 1400 | 0 | 1400 | 21499 | 0 | 0
120 | Roughin Labor | PR | 471 | 10/17/18 | 10/19/18 | LE17 | Lee, Ha Nul | 40 | 0 | 680 | 0 | 680 | 21504 | 0 | 0
120 | Roughin Labor | PR | 473 | 10/17/18 | 10/19/18 | LO58 | Lopez Reyes, Boris O | 34.5 | 0 | 621 | 0 | 621 | 21506 | 0 | 0
120 | Roughin Labor | PR | 499 | 10/17/18 | 10/19/18 | TA96 | Taylor, Evan R | 35 | 0 | 840 | 0 | 840 | 21532 | 0 | 0
120 | Roughin Labor | PR | 504 | 10/17/18 | 10/19/18 | WE55 | Wennig, Johnathan M | 32 | 0 | 896 | 0 | 896 | 21537 | 0 | 0
120 | Roughin Labor | PR | 733 | 10/24/18 | 10/26/18 | HO14 | Holmes, Anthony R | 40 | 0 | 1400 | 0 | 1400 | 21573 | 0 | 0
120 | Roughin Labor | PR | 737 | 10/24/18 | 10/26/18 | LE17 | Lee, Ha Nul | 29 | 0 | 493 | 0 | 493 | 21577 | 0 | 0
120 | Roughin Labor | PR | 739 | 10/24/18 | 10/26/18 | LO58 | Lopez Reyes, Boris O | 32 | 0 | 576 | 0 | 576 | 21579 | 0 | 0
120 | Roughin Labor | PR | 765 | 10/24/18 | 10/26/18 | TA96 | Taylor, Evan R | 40 | 0 | 960 | 0 | 960 | 21605 | 0 | 0
120 | Roughin Labor | PR | 770 | 10/24/18 | 10/26/18 | WE55 | Wennig, Johnathan M | 24 | 0 | 672 | 0 | 672 | 21610 | 0 | 0
120 | Roughin Labor | PR | 37 | 10/31/18 | 11/02/18 | HO14 | Holmes, Anthony R | 40 | 0 | 1400 | 0 | 1400 | 21646 | 0 | 0
120 | Roughin Labor | PR | 42 | 10/31/18 | 11/02/18 | LE17 | Lee, Ha Nul | 40 | 0 | 680 | 0 | 680 | 21651 | 0 | 0
120 | Roughin Labor | PR | 44 | 10/31/18 | 11/02/18 | LO58 | Lopez Reyes, Boris O | 32 | 0 | 576 | 0 | 576 | 21653 | 0 | 0
120 | Roughin Labor | PR | 68 | 10/31/18 | 11/02/18 | TA96 | Taylor, Evan R | 40 | 0 | 960 | 0 | 960 | 21677 | 0 | 0
120 | Roughin Labor | PR | 215 | 11/07/18 | 11/09/18 | HO14 | Holmes, Anthony R | 40 | 0 | 1400 | 0 | 1400 | 21718 | 0 | 0
120 | Roughin Labor | PR | 220 | 11/07/18 | 11/09/18 | LE17 | Lee, Ha Nul | 40 | 0 | 680 | 0 | 680 | 21723 | 0 | 0
120 | Roughin Labor | PR | 227 | 11/07/18 | 11/09/18 | ME52 | Mendoza, Edgar E | 8 | 0 | 176 | 0 | 176 | 21730 | 0 | 0
120 | Roughin Labor | PR | 248 | 11/07/18 | 11/09/18 | TA96 | Taylor, Evan R | 40 | 0 | 960 | 0 | 960 | 21751 | 0 | 0
120 | Roughin Labor | PR | 252 | 11/07/18 | 11/09/18 | WE55 | Wennig, Johnathan M | 40 | 0 | 1120 | 0 | 1120 | 21755 | 0 | 0
120 | Roughin Labor | PR | 463 | 11/14/18 | 11/16/18 | HO14 | Holmes, Anthony R | 40 | 0 | 1400 | 0 | 1400 | 21791 | 0 | 0
120 | Roughin Labor | PR | 468 | 11/14/18 | 11/16/18 | LE17 | Lee, Ha Nul | 40 | 0 | 680 | 0 | 680 | 21796 | 0 | 0
120 | Roughin Labor | PR | 470 | 11/14/18 | 11/16/18 | LO58 | Lopez Reyes, Boris O | 5 | 0 | 90 | 0 | 90 | 21798 | 0 | 0
120 | Roughin Labor | PR | 475 | 11/14/18 | 11/16/18 | ME52 | Mendoza, Edgar E | 8 | 0 | 176 | 0 | 176 | 21803 | 0 | 0
120 | Roughin Labor | PR | 496 | 11/14/18 | 11/16/18 | TA96 | Taylor, Evan R | 40 | 0 | 960 | 0 | 960 | 21824 | 0 | 0
120 | Roughin Labor | PR | 500 | 11/14/18 | 11/16/18 | WE55 | Wennig, Johnathan M | 40 | 0 | 1120 | 0 | 1120 | 21828 | 0 | 0
120 | Roughin Labor | PR | 648 | 11/21/18 | 11/21/18 | HO14 | Holmes, Anthony R | 40 | 0 | 1400 | 0 | 1400 | 21869 | 0 | 0
120 | Roughin Labor | PR | 653 | 11/21/18 | 11/21/18 | LE17 | Lee, Ha Nul | 40 | 0 | 680 | 0 | 680 | 21874 | 0 | 0
120 | Roughin Labor | PR | 680 | 11/21/18 | 11/21/18 | TA96 | Taylor, Evan R | 40 | 0 | 960 | 0 | 960 | 21901 | 0 | 0
120 | Roughin Labor | PR | 684 | 11/21/18 | 11/21/18 | WE55 | Wennig, Johnathan M | 40 | 0 | 1120 | 0 | 1120 | 21905 | 0 | 0
120 | Roughin Labor | PR | 861 | 11/28/18 | 11/30/18 | HO14 | Holmes, Anthony R | 21 | 0 | 777 | 0 | 777 | 21943 | 0 | 0
120 | Roughin Labor | PR | 866 | 11/28/18 | 11/30/18 | LE17 | Lee, Ha Nul | 32 | 0 | 608 | 0 | 608 | 21948 | 0 | 0
120 | Roughin Labor | PR | 893 | 11/28/18 | 11/30/18 | TA96 | Taylor, Evan R | 28.5 | 0 | 741 | 0 | 741 | 21975 | 0 | 0
120 | Roughin Labor | PR | 897 | 11/28/18 | 11/30/18 | WE55 | Wennig, Johnathan M | 21 | 0 | 630 | 0 | 630 | 21979 | 0 | 0
120 | Roughin Labor | PR | 73 | 12/05/18 | 12/07/18 | HO14 | Holmes, Anthony R | 40 | 0 | 1480 | 0 | 1480 | 22015 | 0 | 0
120 | Roughin Labor | PR | 78 | 12/05/18 | 12/07/18 | LE17 | Lee, Ha Nul | 40 | 0 | 760 | 0 | 760 | 22020 | 0 | 0
120 | Roughin Labor | PR | 105 | 12/05/18 | 12/07/18 | TA96 | Taylor, Evan R | 40 | 0 | 1040 | 0 | 1040 | 22047 | 0 | 0
120 | Roughin Labor | PR | 110 | 12/05/18 | 12/07/18 | WE55 | Wennig, Johnathan M | 40 | 0 | 1200 | 0 | 1200 | 22052 | 0 | 0
120 | Roughin Labor | PR | 270 | 12/12/18 | 12/14/18 | BA70 | Barnhart, Joseph N | 2 | 0 | 96 | 0 | 96 | 22130 | 0 | 0
120 | Roughin Labor | PR | 297 | 12/12/18 | 12/14/18 | HO14 | Holmes, Anthony R | 40 | 0 | 1480 | 0 | 1480 | 22156 | 0 | 0
120 | Roughin Labor | PR | 302 | 12/12/18 | 12/14/18 | LE17 | Lee, Ha Nul | 40 | 0 | 760 | 0 | 760 | 22161 | 0 | 0
120 | Roughin Labor | PR | 330 | 12/12/18 | 12/14/18 | TA96 | Taylor, Evan R | 16 | 0 | 416 | 0 | 416 | 22189 | 0 | 0
120 | Roughin Labor | PR | 335 | 12/12/18 | 12/14/18 | WE55 | Wennig, Johnathan M | 16 | 0 | 480 | 0 | 480 | 22194 | 0 | 0
120 | Roughin Labor | PR | 538 | 12/19/18 | 12/21/18 | HO14 | Holmes, Anthony R | 40 | 0 | 1480 | 0 | 1480 | 22228 | 0 | 0
120 | Roughin Labor | PR | 543 | 12/19/18 | 12/21/18 | LE17 | Lee, Ha Nul | 48 | 0 | 912 | 0 | 912 | 22233 | 0 | 0
120 | Roughin Labor | PR | 570 | 12/19/18 | 12/21/18 | TA96 | Taylor, Evan R | 0 | 8 | 0 | 312 | 312 | 22260 | 0 | 0
120 | Roughin Labor | PR | 570 | 12/19/18 | 12/21/18 | TA96 | Taylor, Evan R | 40 | 0 | 1040 | 0 | 1040 | 22260 | 0 | 0
120 | Roughin Labor | PR | 575 | 12/19/18 | 12/21/18 | WE55 | Wennig, Johnathan M | 48 | 0 | 1440 | 0 | 1440 | 22265 | 0 | 0
120 | Roughin Labor | PR | 729 | 12/26/18 | 12/28/18 | HO14 | Holmes, Anthony R | 24 | 0 | 888 | 0 | 888 | 22302 | 0 | 0
120 | Roughin Labor | PR | 761 | 12/26/18 | 12/28/18 | TA96 | Taylor, Evan R | 16 | 0 | 416 | 0 | 416 | 22334 | 0 | 0
120 | Roughin Labor | PR | 766 | 12/26/18 | 12/28/18 | WE55 | Wennig, Johnathan M | 16 | 0 | 480 | 0 | 480 | 22339 | 0 | 0
120 | Roughin Labor | PR | 33 | 01/02/19 | 01/04/19 | HO14 | Holmes, Anthony R | 32 | 0 | 1184 | 0 | 1184 | 22374 | 0 | 0
120 | Roughin Labor | PR | 64 | 01/02/19 | 01/04/19 | TA96 | Taylor, Evan R | 24 | 0 | 624 | 0 | 624 | 22405 | 0 | 0
120 | Roughin Labor | PR | 69 | 01/02/19 | 01/04/19 | WE55 | Wennig, Johnathan M | 24 | 0 | 720 | 0 | 720 | 22410 | 0 | 0
120 | Roughin Labor | PR | 241 | 01/09/19 | 01/11/19 | HO14 | Holmes, Anthony R | 40 | 0 | 1480 | 0 | 1480 | 22443 | 0 | 0
120 | Roughin Labor | PR | 244 | 01/09/19 | 01/11/19 | HU06 | Hubbard, Robert W | 4 | 0 | 196 | 0 | 196 | 22446 | 0 | 0
120 | Roughin Labor | PR | 274 | 01/09/19 | 01/11/19 | TA96 | Taylor, Evan R | 40 | 0 | 1040 | 0 | 1040 | 22476 | 0 | 0
120 | Roughin Labor | PR | 279 | 01/09/19 | 01/11/19 | WE55 | Wennig, Johnathan M | 40 | 0 | 1200 | 0 | 1200 | 22481 | 0 | 0
120 | Roughin Labor | PR | 496 | 01/16/19 | 01/18/19 | HO14 | Holmes, Anthony R | 40 | 0 | 1480 | 0 | 1480 | 22517 | 0 | 0
120 | Roughin Labor | PR | 529 | 01/16/19 | 01/18/19 | TA96 | Taylor, Evan R | 40 | 0 | 1040 | 0 | 1040 | 22550 | 0 | 0
120 | Roughin Labor | PR | 534 | 01/16/19 | 01/18/19 | WE55 | Wennig, Johnathan M | 40 | 0 | 1200 | 0 | 1200 | 22555 | 0 | 0
120 | Roughin Labor | PR | 745 | 01/23/19 | 01/25/19 | HO14 | Holmes, Anthony R | 40 | 0 | 1480 | 0 | 1480 | 22590 | 0 | 0
120 | Roughin Labor | PR | 778 | 01/23/19 | 01/25/19 | TA96 | Taylor, Evan R | 40 | 0 | 1040 | 0 | 1040 | 22623 | 0 | 0
120 | Roughin Labor | PR | 783 | 01/23/19 | 01/25/19 | WE55 | Wennig, Johnathan M | 32 | 0 | 960 | 0 | 960 | 22628 | 0 | 0
120 | Roughin Labor | PR | 33 | 01/30/19 | 02/01/19 | HO14 | Holmes, Anthony R | 40 | 0 | 1480 | 0 | 1480 | 22662 | 0 | 0
120 | Roughin Labor | PR | 63 | 01/30/19 | 02/01/19 | TA96 | Taylor, Evan R | 40 | 0 | 1040 | 0 | 1040 | 22692 | 0 | 0
120 | Roughin Labor | PR | 68 | 01/30/19 | 02/01/19 | WE55 | Wennig, Johnathan M | 16 | 0 | 480 | 0 | 480 | 22697 | 0 | 0
120 | Roughin Labor | PR | 188 | 02/06/19 | 02/08/19 | HO14 | Holmes, Anthony R | 15.5 | 0 | 573.5 | 0 | 573.5 | 22730 | 0 | 0
120 | Roughin Labor | PR | 191 | 02/06/19 | 02/08/19 | HU06 | Hubbard, Robert W | 2 | 0 | 98 | 0 | 98 | 22733 | 0 | 0
120 | Roughin Labor | PR | 608 | 02/20/19 | 02/22/19 | HO14 | Holmes, Anthony R | 39 | 0 | 1443 | 0 | 1443 | 22870 | 0 | 0
120 | Roughin Labor | PR | 640 | 02/20/19 | 02/22/19 | TA96 | Taylor, Evan R | 40 | 0 | 1040 | 0 | 1040 | 22902 | 0 | 0
120 | Roughin Labor | PR | 35 | 02/27/19 | 03/01/19 | HO14 | Holmes, Anthony R | 40 | 0 | 1480 | 0 | 1480 | 22942 | 0 | 0
120 | Roughin Labor | PR | 67 | 02/27/19 | 03/01/19 | TA96 | Taylor, Evan R | 40 | 0 | 1040 | 0 | 1040 | 22974 | 0 | 0
120 | Roughin Labor | PR | 249 | 03/06/19 | 03/08/19 | BA70 | Barnhart, Joseph N | 2 | 0 | 96 | 0 | 96 | 22987 | 0 | 0
120 | Roughin Labor | PR | 275 | 03/06/19 | 03/08/19 | HO14 | Holmes, Anthony R | 0 | 6 | 0 | 333 | 333 | 23014 | 0 | 0
120 | Roughin Labor | PR | 275 | 03/06/19 | 03/08/19 | HO14 | Holmes, Anthony R | 32 | 0 | 1184 | 0 | 1184 | 23014 | 0 | 0
120 | Roughin Labor | PR | 289 | 03/06/19 | 03/08/19 | MU70 | Murphy, Darray E | 0 | 6 | 0 | 162 | 162 | 23028 | 0 | 0
120 | Roughin Labor | PR | 289 | 03/06/19 | 03/08/19 | MU70 | Murphy, Darray E | 40 | 0 | 720 | 0 | 720 | 23028 | 0 | 0
120 | Roughin Labor | PR | 522 | 03/13/19 | 03/15/19 | HO14 | Holmes, Anthony R | 0 | 8 | 0 | 444 | 444 | 23084 | 0 | 0
120 | Roughin Labor | PR | 522 | 03/13/19 | 03/15/19 | HO14 | Holmes, Anthony R | 40 | 0 | 1480 | 0 | 1480 | 23084 | 0 | 0
120 | Roughin Labor | PR | 536 | 03/13/19 | 03/15/19 | MU70 | Murphy, Darray E | 18 | 0 | 324 | 0 | 324 | 23098 | 0 | 0
120 | Roughin Labor | PR | 736 | 03/20/19 | 03/22/19 | HO14 | Holmes, Anthony R | 0 | 8 | 0 | 444 | 444 | 23157 | 0 | 0
120 | Roughin Labor | PR | 736 | 03/20/19 | 03/22/19 | HO14 | Holmes, Anthony R | 40 | 0 | 1480 | 0 | 1480 | 23157 | 0 | 0
120 | Roughin Labor | PR | 948 | 03/27/19 | 03/29/19 | HO14 | Holmes, Anthony R | 0 | 13 | 0 | 721.5 | 721.5 | 23232 | 0 | 0
120 | Roughin Labor | PR | 948 | 03/27/19 | 03/29/19 | HO14 | Holmes, Anthony R | 32 | 0 | 1184 | 0 | 1184 | 23232 | 0 | 0
120 | Roughin Labor | PR | 111 | 04/03/19 | 04/05/19 | HO14 | Holmes, Anthony R | 0 | 2 | 0 | 111 | 111 | 23305 | 0 | 0
120 | Roughin Labor | PR | 111 | 04/03/19 | 04/05/19 | HO14 | Holmes, Anthony R | 16 | 0 | 592 | 0 | 592 | 23305 | 0 | 0
120 | Roughin Labor | PR | 524 | 04/17/19 | 04/19/19 | BA70 | Barnhart, Joseph N | 0 | 2 | 0 | 150 | 150 | 23425 | 0 | 0
120 | Roughin Labor | PR | 555 | 04/17/19 | 04/19/19 | HU06 | Hubbard, Robert W | 2 | 0 | 100 | 0 | 100 | 23456 | 0 | 0
120 | Roughin Labor | PR | 564 | 04/17/19 | 04/19/19 | MC09 | McCabe, Thomas C | 8 | 0 | 264 | 0 | 264 | 23465 | 0 | 0
120 | Roughin Labor | PR | 771 | 04/24/19 | 04/26/19 | HO14 | Holmes, Anthony R | 0 | 8 | 0 | 480 | 480 | 23528 | 0 | 0
120 | Roughin Labor | PR | 771 | 04/24/19 | 04/26/19 | HO14 | Holmes, Anthony R | 2 | 0 | 80 | 0 | 80 | 23528 | 0 | 0
120 | Roughin Labor | PR | 774 | 04/24/19 | 04/26/19 | HU06 | Hubbard, Robert W | 4 | 0 | 200 | 0 | 200 | 23531 | 0 | 0
120 | Roughin Labor | PR | 783 | 04/24/19 | 04/26/19 | MC09 | McCabe, Thomas C | 0 | 5 | 0 | 262.5 | 262.5 | 23540 | 0 | 0
120 | Roughin Labor | PR | 783 | 04/24/19 | 04/26/19 | MC09 | McCabe, Thomas C | 19 | 0 | 665 | 0 | 665 | 23540 | 0 | 0
120 | Roughin Labor | PR | 39 | 05/01/19 | 05/03/19 | HO14 | Holmes, Anthony R | 0 | 1 | 0 | 60 | 60 | 23601 | 0 | 0
120 | Roughin Labor | PR | 39 | 05/01/19 | 05/03/19 | HO14 | Holmes, Anthony R | 3.5 | 0 | 140 | 0 | 140 | 23601 | 0 | 0
120 | Roughin Labor | PR | 45 | 05/01/19 | 05/03/19 | KI55 | Kinssies, Jr, John E | 8 | 0 | 224 | 0 | 224 | 23607 | 0 | 0
120 | Roughin Labor | PR | 52 | 05/01/19 | 05/03/19 | MC09 | McCabe, Thomas C | 24 | 0 | 840 | 0 | 840 | 23614 | 0 | 0
120 | Roughin Labor | PR | 68 | 05/01/19 | 05/03/19 | SE64 | Sepulveda Gonzalez, Alfredo | 12 | 0 | 420 | 0 | 420 | 23630 | 0 | 0
120 | Roughin Labor | PR | 195 | 05/08/19 | 05/10/19 | HU06 | Hubbard, Robert W | 10 | 0 | 500 | 0 | 500 | 23679 | 0 | 0
120 | Roughin Labor | PR | 198 | 05/08/19 | 05/10/19 | KI55 | Kinssies, Jr, John E | 20 | 0 | 560 | 0 | 560 | 23682 | 0 | 0
120 | Roughin Labor | PR | 205 | 05/08/19 | 05/10/19 | MC09 | McCabe, Thomas C | 38 | 0 | 1330 | 0 | 1330 | 23689 | 0 | 0
120 | Roughin Labor | PR | 215 | 05/08/19 | 05/10/19 | RO06 | Roberts, Lake A | 11 | 0 | 220 | 0 | 220 | 23700 | 0 | 0
120 | Roughin Labor | PR | 427 | 05/15/19 | 05/17/19 | HU06 | Hubbard, Robert W | 9 | 0 | 450 | 0 | 450 | 23758 | 0 | 0
120 | Roughin Labor | PR | 430 | 05/15/19 | 05/17/19 | KI55 | Kinssies, Jr, John E | 28 | 0 | 784 | 0 | 784 | 23761 | 0 | 0
120 | Roughin Labor | PR | 437 | 05/15/19 | 05/17/19 | MC09 | McCabe, Thomas C | 35.25 | 0 | 1233.75 | 0 | 1233.75 | 23768 | 0 | 0
120 | Roughin Labor | PR | 447 | 05/15/19 | 05/17/19 | RO06 | Roberts, Lake A | 12 | 0 | 240 | 0 | 240 | 23778 | 0 | 0
120 | Roughin Labor | PR | 639 | 05/22/19 | 05/24/19 | HU06 | Hubbard, Robert W | 10 | 0 | 500 | 0 | 500 | 23834 | 0 | 0
120 | Roughin Labor | PR | 642 | 05/22/19 | 05/24/19 | KI55 | Kinssies, Jr, John E | 35 | 0 | 980 | 0 | 980 | 23837 | 0 | 0
120 | Roughin Labor | PR | 649 | 05/22/19 | 05/24/19 | MC09 | McCabe, Thomas C | 16 | 0 | 560 | 0 | 560 | 23844 | 0 | 0
120 | Roughin Labor | PR | 881 | 05/29/19 | 05/31/19 | BA70 | Barnhart, Joseph N | 1 | 0 | 50 | 0 | 50 | 23881 | 0 | 0
120 | Roughin Labor | PR | 913 | 05/29/19 | 05/31/19 | HU06 | Hubbard, Robert W | 3 | 0 | 150 | 0 | 150 | 23913 | 0 | 0
120 | Roughin Labor | PR | 916 | 05/29/19 | 05/31/19 | KI55 | Kinssies, Jr, John E | 24 | 0 | 672 | 0 | 672 | 23916 | 0 | 0
120 | Roughin Labor | PR | 46 | 06/05/19 | 06/07/19 | KI55 | Kinssies, Jr, John E | 40 | 0 | 1240 | 0 | 1240 | 23952 | 0 | 0
120 | Roughin Labor | PR | 183 | 06/05/19 | 06/07/19 | BA70 | Barnhart, Joseph N | 3 | 0 | 150 | 0 | 150 | 23958 | 0 | 0
120 | Roughin Labor | PR | 215 | 06/05/19 | 06/07/19 | HU06 | Hubbard, Robert W | 5.5 | 0 | 275 | 0 | 275 | 23990 | 0 | 0
120 | Roughin Labor | PR | 483 | 06/12/19 | 06/14/19 | HU06 | Hubbard, Robert W | 8 | 0 | 400 | 0 | 400 | 24064 | 0 | 0
120 | Roughin Labor | PR | 486 | 06/12/19 | 06/14/19 | KI55 | Kinssies, Jr, John E | 36.75 | 0 | 1139.25 | 0 | 1139.25 | 24067 | 0 | 0
120 | Roughin Labor | PR | 493 | 06/12/19 | 06/14/19 | MC09 | McCabe, Thomas C | 40 | 0 | 1400 | 0 | 1400 | 24074 | 0 | 0
120 | Roughin Labor | PR | 514 | 06/12/19 | 06/14/19 | TR60 | Trower-Kelly, Fidel D | 8 | 0 | 144 | 0 | 144 | 24095 | 0 | 0
120 | Roughin Labor | PR | 654 | 06/19/19 | 06/21/19 | HU06 | Hubbard, Robert W | 8 | 0 | 400 | 0 | 400 | 24140 | 0 | 0
120 | Roughin Labor | PR | 657 | 06/19/19 | 06/21/19 | KI55 | Kinssies, Jr, John E | 32 | 0 | 992 | 0 | 992 | 24143 | 0 | 0
120 | Roughin Labor | PR | 664 | 06/19/19 | 06/21/19 | MC09 | McCabe, Thomas C | 32 | 0 | 1120 | 0 | 1120 | 24150 | 0 | 0
120 | Roughin Labor | PR | 46 | 07/03/19 | 07/05/19 | KI55 | Kinssies, Jr, John E | 4 | 0 | 124 | 0 | 124 | 24293 | 0 | 0
120 | Roughin Labor | PR | 67 | 07/03/19 | 07/05/19 | SE64 | Sepulveda Gonzalez, Alfredo | 4 | 0 | 140 | 0 | 140 | 24315 | 0 | 0
120 | Roughin Labor | PR | 655 | 07/24/19 | 07/26/19 | MC09 | McCabe, Thomas C | 10 | 0 | 350 | 0 | 350 | 24604 | 0 | 0
120 | Roughin Labor | PR | 300 | 08/07/19 | 08/09/19 | MC09 | McCabe, Thomas C | 2 | 0 | 70 | 0 | 70 | 24753 | 0 | 0
120 | Roughin Labor | GL | 886 | 08/12/19 | 08/12/19 | Tommy | M SAW Reimb |  |  |  |  | -623.52 |  | 0 | 0
120 | Roughin Labor | PR | 835 | 08/21/19 | 08/23/19 | HU06 | Hubbard, Robert W | 2 | 0 | 100 | 0 | 100 | 24893 | 0 | 0
120 | Roughin Labor | PR | 844 | 08/21/19 | 08/23/19 | MC09 | McCabe, Thomas C | 4 | 0 | 140 | 0 | 140 | 24902 | 0 | 0
130 | Finish Labor | PR | 797 | 04/24/19 | 04/26/19 | SA54 | Sanders, Allen O | 2.5 | 0 | 122.5 | 0 | 122.5 | 23554 | 0 | 0
130 | Finish Labor | PR | 66 | 05/01/19 | 05/03/19 | SA54 | Sanders, Allen O | 6.5 | 0 | 318.5 | 0 | 318.5 | 23628 | 0 | 0
130 | Finish Labor | PR | 70 | 05/01/19 | 05/03/19 | ST02 | Stahlschmidt, John P | 8 | 0 | 152 | 0 | 152 | 23632 | 0 | 0
130 | Finish Labor | PR | 73 | 05/01/19 | 05/03/19 | TR60 | Trower-Kelly, Fidel D | 16 | 0 | 288 | 0 | 288 | 23635 | 0 | 0
130 | Finish Labor | PR | 74 | 05/01/19 | 05/03/19 | VA98 | Vazquez Popoca, Jose N | 24 | 0 | 384 | 0 | 384 | 23636 | 0 | 0
130 | Finish Labor | PR | 219 | 05/08/19 | 05/10/19 | SA54 | Sanders, Allen O | 6 | 0 | 294 | 0 | 294 | 23704 | 0 | 0
130 | Finish Labor | PR | 223 | 05/08/19 | 05/10/19 | ST02 | Stahlschmidt, John P | 8 | 0 | 152 | 0 | 152 | 23708 | 0 | 0
130 | Finish Labor | PR | 226 | 05/08/19 | 05/10/19 | TR60 | Trower-Kelly, Fidel D | 24 | 0 | 432 | 0 | 432 | 23711 | 0 | 0
130 | Finish Labor | PR | 227 | 05/08/19 | 05/10/19 | VA98 | Vazquez Popoca, Jose N | 32 | 0 | 512 | 0 | 512 | 23712 | 0 | 0
130 | Finish Labor | PR | 411 | 05/15/19 | 05/17/19 | EL33 | Eliassen, Cory H | 8 | 0 | 216 | 0 | 216 | 23742 | 0 | 0
130 | Finish Labor | PR | 447 | 05/15/19 | 05/17/19 | RO06 | Roberts, Lake A | 4 | 0 | 80 | 0 | 80 | 23778 | 0 | 0
130 | Finish Labor | PR | 451 | 05/15/19 | 05/17/19 | SA54 | Sanders, Allen O | 3 | 0 | 147 | 0 | 147 | 23782 | 0 | 0
130 | Finish Labor | PR | 455 | 05/15/19 | 05/17/19 | ST02 | Stahlschmidt, John P | 8 | 0 | 152 | 0 | 152 | 23786 | 0 | 0
130 | Finish Labor | PR | 458 | 05/15/19 | 05/17/19 | TR60 | Trower-Kelly, Fidel D | 35 | 0 | 630 | 0 | 630 | 23789 | 0 | 0
130 | Finish Labor | PR | 459 | 05/15/19 | 05/17/19 | VA98 | Vazquez Popoca, Jose N | 35 | 0 | 560 | 0 | 560 | 23790 | 0 | 0
130 | Finish Labor | PR | 663 | 05/22/19 | 05/24/19 | SA54 | Sanders, Allen O | 6.5 | 0 | 318.5 | 0 | 318.5 | 23858 | 0 | 0
130 | Finish Labor | PR | 670 | 05/22/19 | 05/24/19 | TR60 | Trower-Kelly, Fidel D | 35.5 | 0 | 639 | 0 | 639 | 23865 | 0 | 0
130 | Finish Labor | PR | 671 | 05/22/19 | 05/24/19 | VA98 | Vazquez Popoca, Jose N | 35.5 | 0 | 568 | 0 | 568 | 23866 | 0 | 0
130 | Finish Labor | PR | 897 | 05/29/19 | 05/31/19 | EL33 | Eliassen, Cory H | 19 | 0 | 513 | 0 | 513 | 23897 | 0 | 0
130 | Finish Labor | PR | 937 | 05/29/19 | 05/31/19 | SA54 | Sanders, Allen O | 3.5 | 0 | 171.5 | 0 | 171.5 | 23937 | 0 | 0
130 | Finish Labor | PR | 944 | 05/29/19 | 05/31/19 | TR60 | Trower-Kelly, Fidel D | 16 | 0 | 288 | 0 | 288 | 23944 | 0 | 0
130 | Finish Labor | PR | 945 | 05/29/19 | 05/31/19 | VA98 | Vazquez Popoca, Jose N | 32 | 0 | 512 | 0 | 512 | 23945 | 0 | 0
130 | Finish Labor | PR | 199 | 06/05/19 | 06/07/19 | EL33 | Eliassen, Cory H | 22 | 0 | 594 | 0 | 594 | 23974 | 0 | 0
130 | Finish Labor | PR | 239 | 06/05/19 | 06/07/19 | SA54 | Sanders, Allen O | 2 | 0 | 98 | 0 | 98 | 24014 | 0 | 0
130 | Finish Labor | PR | 246 | 06/05/19 | 06/07/19 | TR60 | Trower-Kelly, Fidel D | 32 | 0 | 576 | 0 | 576 | 24021 | 0 | 0
130 | Finish Labor | PR | 247 | 06/05/19 | 06/07/19 | VA98 | Vazquez Popoca, Jose N | 24 | 0 | 384 | 0 | 384 | 24022 | 0 | 0
130 | Finish Labor | PR | 469 | 06/12/19 | 06/14/19 | EL33 | Eliassen, Cory H | 32 | 0 | 864 | 0 | 864 | 24050 | 0 | 0
130 | Finish Labor | PR | 515 | 06/12/19 | 06/14/19 | VA98 | Vazquez Popoca, Jose N | 8 | 0 | 128 | 0 | 128 | 24096 | 0 | 0
130 | Finish Labor | PR | 639 | 06/19/19 | 06/21/19 | EL33 | Eliassen, Cory H | 33 | 0 | 891 | 0 | 891 | 24125 | 0 | 0
130 | Finish Labor | PR | 857 | 06/26/19 | 06/28/19 | EL33 | Eliassen, Cory H | 29 | 0 | 783 | 0 | 783 | 24201 | 0 | 0
130 | Finish Labor | PR | 298 | 07/10/19 | 07/12/19 | EL33 | Eliassen, Cory H | 12 | 0 | 324 | 0 | 324 | 24350 | 0 | 0
130 | Finish Labor | PR | 528 | 07/17/19 | 07/19/19 | EL33 | Eliassen, Cory H | 19 | 0 | 513 | 0 | 513 | 24427 | 0 | 0
130 | Finish Labor | PR | 632 | 07/24/19 | 07/26/19 | EL33 | Eliassen, Cory H | 12 | 0 | 324 | 0 | 324 | 24581 | 0 | 0
130 | Finish Labor | PR | 670 | 07/24/19 | 07/26/19 | SA54 | Sanders, Allen O | 2 | 0 | 98 | 0 | 98 | 24619 | 0 | 0
130 | Finish Labor | PR | 24 | 07/31/19 | 08/02/19 | EL33 | Eliassen, Cory H | 39 | 0 | 1053 | 0 | 1053 | 24655 | 0 | 0
130 | Finish Labor | PR | 61 | 07/31/19 | 08/02/19 | SA54 | Sanders, Allen O | 2 | 0 | 98 | 0 | 98 | 24692 | 0 | 0
130 | Finish Labor | PR | 68 | 07/31/19 | 08/02/19 | TR60 | Trower-Kelly, Fidel D | 10 | 0 | 180 | 0 | 180 | 24699 | 0 | 0
130 | Finish Labor | PR | 276 | 08/07/19 | 08/09/19 | EL33 | Eliassen, Cory H | 43 | 0 | 1161 | 0 | 1161 | 24729 | 0 | 0
130 | Finish Labor | PR | 314 | 08/07/19 | 08/09/19 | SA54 | Sanders, Allen O | 10 | 0 | 490 | 0 | 490 | 24767 | 0 | 0
130 | Finish Labor | PR | 320 | 08/07/19 | 08/09/19 | TR60 | Trower-Kelly, Fidel D | 26 | 0 | 468 | 0 | 468 | 24773 | 0 | 0
130 | Finish Labor | PR | 621 | 08/14/19 | 08/16/19 | SA54 | Sanders, Allen O | 7 | 0 | 343 | 0 | 343 | 24840 | 0 | 0
130 | Finish Labor | PR | 819 | 08/21/19 | 08/23/19 | EL33 | Eliassen, Cory H | 3 | 0 | 81 | 0 | 81 | 24877 | 0 | 0
130 | Finish Labor | PR | 1049 | 08/28/19 | 08/30/19 | SA54 | Sanders, Allen O | 1 | 0 | 49 | 0 | 49 | 24991 | 0 | 0
130 | Finish Labor | PR | 70 | 09/04/19 | 09/06/19 | SA54 | Sanders, Allen O | 1.5 | 0 | 73.5 | 0 | 73.5 | 25068 | 0 | 0
130 | Finish Labor | PR | 531 | 09/18/19 | 09/20/19 | SA54 | Sanders, Allen O | 4 | 0 | 196 | 0 | 196 | 25217 | 0 | 0
140 | Gas Labor | PR | 69 | 08/01/18 | 08/03/18 | WA35 | Waites, Thaddeus Z | 1 | 0 | 42 | 0 | 42 | 20660 | 0 | 0
140 | Gas Labor | PR | 1059 | 08/29/18 | 08/31/18 | TA96 | Taylor, Evan R | 1 | 0 | 24 | 0 | 24 | 20954 | 0 | 0
140 | Gas Labor | PR | 188 | 02/06/19 | 02/08/19 | HO14 | Holmes, Anthony R | 8 | 0 | 296 | 0 | 296 | 22730 | 0 | 0
140 | Gas Labor | PR | 219 | 02/06/19 | 02/08/19 | TA96 | Taylor, Evan R | 24 | 0 | 624 | 0 | 624 | 22761 | 0 | 0
140 | Gas Labor | PR | 350 | 02/13/19 | 02/15/19 | HO14 | Holmes, Anthony R | 15 | 0 | 555 | 0 | 555 | 22801 | 0 | 0
140 | Gas Labor | PR | 353 | 02/13/19 | 02/15/19 | HU06 | Hubbard, Robert W | 2.5 | 0 | 122.5 | 0 | 122.5 | 22804 | 0 | 0
140 | Gas Labor | PR | 381 | 02/13/19 | 02/15/19 | TA96 | Taylor, Evan R | 15 | 0 | 390 | 0 | 390 | 22832 | 0 | 0
140 | Gas Labor | PR | 932 | 03/27/19 | 03/29/19 | CR87 | Cruz Reyes, Jose | 0 | 2 | 0 | 78 | 78 | 23216 | 0 | 0
140 | Gas Labor | PR | 932 | 03/27/19 | 03/29/19 | CR87 | Cruz Reyes, Jose | 8 | 0 | 208 | 0 | 208 | 23216 | 0 | 0
140 | Gas Labor | PR | 948 | 03/27/19 | 03/29/19 | HO14 | Holmes, Anthony R | 0 | 2 | 0 | 111 | 111 | 23232 | 0 | 0
140 | Gas Labor | PR | 948 | 03/27/19 | 03/29/19 | HO14 | Holmes, Anthony R | 8 | 0 | 296 | 0 | 296 | 23232 | 0 | 0
140 | Gas Labor | PR | 543 | 07/17/19 | 07/19/19 | HU06 | Hubbard, Robert W | 5 | 0 | 250 | 0 | 250 | 24442 | 0 | 0
140 | Gas Labor | PR | 552 | 07/17/19 | 07/19/19 | MC09 | McCabe, Thomas C | 12 | 0 | 420 | 0 | 420 | 24451 | 0 | 0
140 | Gas Labor | PR | 655 | 07/24/19 | 07/26/19 | MC09 | McCabe, Thomas C | 15 | 0 | 525 | 0 | 525 | 24604 | 0 | 0
140 | Gas Labor | PR | 291 | 08/07/19 | 08/09/19 | HU06 | Hubbard, Robert W | 1 | 0 | 50 | 0 | 50 | 24744 | 0 | 0
140 | Gas Labor | PR | 300 | 08/07/19 | 08/09/19 | MC09 | McCabe, Thomas C | 16 | 0 | 560 | 0 | 560 | 24753 | 0 | 0
141 | Water Main/Insulation Lab | PR | 496 | 06/13/18 | 06/15/18 | LO58 | Lopez Reyes, Boris O | 0 | 2 | 0 | 54 | 54 | 20131 | 0 | 0
141 | Water Main/Insulation Lab | PR | 496 | 06/13/18 | 06/15/18 | LO58 | Lopez Reyes, Boris O | 37 | 0 | 666 | 0 | 666 | 20131 | 0 | 0
141 | Water Main/Insulation Lab | PR | 312 | 09/12/18 | 09/14/18 | ME52 | Mendoza, Edgar E | 40 | 0 | 880 | 0 | 880 | 21146 | 0 | 0
141 | Water Main/Insulation Lab | PR | 74 | 10/03/18 | 10/05/18 | ME52 | Mendoza, Edgar E | 38.5 | 0 | 847 | 0 | 847 | 21362 | 0 | 0
141 | Water Main/Insulation Lab | PR | 273 | 10/10/18 | 10/12/18 | LE17 | Lee, Ha Nul | 24 | 0 | 408 | 0 | 408 | 21430 | 0 | 0
141 | Water Main/Insulation Lab | PR | 280 | 10/10/18 | 10/12/18 | ME52 | Mendoza, Edgar E | 40 | 0 | 880 | 0 | 880 | 21437 | 0 | 0
141 | Water Main/Insulation Lab | PR | 478 | 10/17/18 | 10/19/18 | ME52 | Mendoza, Edgar E | 40 | 0 | 880 | 0 | 880 | 21511 | 0 | 0
141 | Water Main/Insulation Lab | PR | 744 | 10/24/18 | 10/26/18 | ME52 | Mendoza, Edgar E | 32 | 0 | 704 | 0 | 704 | 21584 | 0 | 0
141 | Water Main/Insulation Lab | PR | 49 | 10/31/18 | 11/02/18 | ME52 | Mendoza, Edgar E | 38 | 0 | 836 | 0 | 836 | 21658 | 0 | 0
141 | Water Main/Insulation Lab | PR | 222 | 11/07/18 | 11/09/18 | LO58 | Lopez Reyes, Boris O | 36.5 | 0 | 657 | 0 | 657 | 21725 | 0 | 0
141 | Water Main/Insulation Lab | PR | 227 | 11/07/18 | 11/09/18 | ME52 | Mendoza, Edgar E | 32 | 0 | 704 | 0 | 704 | 21730 | 0 | 0
141 | Water Main/Insulation Lab | PR | 475 | 11/14/18 | 11/16/18 | ME52 | Mendoza, Edgar E | 32 | 0 | 704 | 0 | 704 | 21803 | 0 | 0
141 | Water Main/Insulation Lab | PR | 659 | 11/21/18 | 11/21/18 | ME52 | Mendoza, Edgar E | 40 | 0 | 880 | 0 | 880 | 21880 | 0 | 0
141 | Water Main/Insulation Lab | PR | 872 | 11/28/18 | 11/30/18 | ME52 | Mendoza, Edgar E | 32 | 0 | 768 | 0 | 768 | 21954 | 0 | 0
141 | Water Main/Insulation Lab | PR | 84 | 12/05/18 | 12/07/18 | ME52 | Mendoza, Edgar E | 37 | 0 | 888 | 0 | 888 | 22026 | 0 | 0
141 | Water Main/Insulation Lab | PR | 308 | 12/12/18 | 12/14/18 | ME52 | Mendoza, Edgar E | 40 | 0 | 960 | 0 | 960 | 22167 | 0 | 0
141 | Water Main/Insulation Lab | PR | 549 | 12/19/18 | 12/21/18 | ME52 | Mendoza, Edgar E | 48 | 0 | 1152 | 0 | 1152 | 22239 | 0 | 0
141 | Water Main/Insulation Lab | PR | 734 | 12/26/18 | 12/28/18 | LE17 | Lee, Ha Nul | 24 | 0 | 456 | 0 | 456 | 22307 | 0 | 0
141 | Water Main/Insulation Lab | PR | 740 | 12/26/18 | 12/28/18 | ME52 | Mendoza, Edgar E | 22.5 | 0 | 540 | 0 | 540 | 22313 | 0 | 0
141 | Water Main/Insulation Lab | PR | 37 | 01/02/19 | 01/04/19 | LE17 | Lee, Ha Nul | 24 | 0 | 456 | 0 | 456 | 22378 | 0 | 0
141 | Water Main/Insulation Lab | PR | 43 | 01/02/19 | 01/04/19 | ME52 | Mendoza, Edgar E | 22.5 | 0 | 540 | 0 | 540 | 22384 | 0 | 0
141 | Water Main/Insulation Lab | PR | 253 | 01/09/19 | 01/11/19 | ME52 | Mendoza, Edgar E | 7 | 0 | 168 | 0 | 168 | 22455 | 0 | 0
141 | Water Main/Insulation Lab | PR | 350 | 02/13/19 | 02/15/19 | HO14 | Holmes, Anthony R | 10 | 0 | 370 | 0 | 370 | 22801 | 0 | 0
141 | Water Main/Insulation Lab | PR | 381 | 02/13/19 | 02/15/19 | TA96 | Taylor, Evan R | 10 | 0 | 260 | 0 | 260 | 22832 | 0 | 0
141 | Water Main/Insulation Lab | PR | 260 | 03/06/19 | 03/08/19 | CR87 | Cruz Reyes, Jose | 44 | 0 | 1144 | 0 | 1144 | 22998 | 0 | 0
141 | Water Main/Insulation Lab | PR | 275 | 03/06/19 | 03/08/19 | HO14 | Holmes, Anthony R | 8 | 0 | 296 | 0 | 296 | 23014 | 0 | 0
141 | Water Main/Insulation Lab | PR | 507 | 03/13/19 | 03/15/19 | CR87 | Cruz Reyes, Jose | 0 | 3 | 0 | 117 | 117 | 23069 | 0 | 0
141 | Water Main/Insulation Lab | PR | 507 | 03/13/19 | 03/15/19 | CR87 | Cruz Reyes, Jose | 45 | 0 | 1170 | 0 | 1170 | 23069 | 0 | 0
141 | Water Main/Insulation Lab | PR | 721 | 03/20/19 | 03/22/19 | CR87 | Cruz Reyes, Jose | 0 | 8 | 0 | 312 | 312 | 23142 | 0 | 0
141 | Water Main/Insulation Lab | PR | 721 | 03/20/19 | 03/22/19 | CR87 | Cruz Reyes, Jose | 40 | 0 | 1040 | 0 | 1040 | 23142 | 0 | 0
141 | Water Main/Insulation Lab | PR | 932 | 03/27/19 | 03/29/19 | CR87 | Cruz Reyes, Jose | 0 | 4 | 0 | 156 | 156 | 23216 | 0 | 0
141 | Water Main/Insulation Lab | PR | 932 | 03/27/19 | 03/29/19 | CR87 | Cruz Reyes, Jose | 32 | 0 | 832 | 0 | 832 | 23216 | 0 | 0
141 | Water Main/Insulation Lab | PR | 783 | 04/24/19 | 04/26/19 | MC09 | McCabe, Thomas C | 21 | 0 | 735 | 0 | 735 | 23540 | 0 | 0
141 | Water Main/Insulation Lab | PR | 799 | 04/24/19 | 04/26/19 | SE64 | Sepulveda Gonzalez, Alfredo | 24 | 0 | 840 | 0 | 840 | 23556 | 0 | 0
141 | Water Main/Insulation Lab | PR | 42 | 05/01/19 | 05/03/19 | HU06 | Hubbard, Robert W | 2 | 0 | 100 | 0 | 100 | 23604 | 0 | 0
141 | Water Main/Insulation Lab | PR | 52 | 05/01/19 | 05/03/19 | MC09 | McCabe, Thomas C | 0 | 8 | 0 | 420 | 420 | 23614 | 0 | 0
141 | Water Main/Insulation Lab | PR | 52 | 05/01/19 | 05/03/19 | MC09 | McCabe, Thomas C | 16 | 0 | 560 | 0 | 560 | 23614 | 0 | 0
141 | Water Main/Insulation Lab | PR | 68 | 05/01/19 | 05/03/19 | SE64 | Sepulveda Gonzalez, Alfredo | 20 | 0 | 700 | 0 | 700 | 23630 | 0 | 0
141 | Water Main/Insulation Lab | PR | 646 | 07/24/19 | 07/26/19 | HU06 | Hubbard, Robert W | 2 | 0 | 100 | 0 | 100 | 24595 | 0 | 0
141 | Water Main/Insulation Lab | PR | 655 | 07/24/19 | 07/26/19 | MC09 | McCabe, Thomas C | 5 | 0 | 175 | 0 | 175 | 24604 | 0 | 0
141 | Water Main/Insulation Lab | GL | 886 | 08/12/19 | 08/12/19 | Tommy | M SAW Reimb |  |  |  |  | -384.63 |  | 0 | 0
142 | Mech Room Labor | PR | 278 | 03/06/19 | 03/08/19 | HU06 | Hubbard, Robert W | 5 | 0 | 245 | 0 | 245 | 23017 | 0 | 0
142 | Mech Room Labor | PR | 42 | 05/01/19 | 05/03/19 | HU06 | Hubbard, Robert W | 6 | 0 | 300 | 0 | 300 | 23604 | 0 | 0
142 | Mech Room Labor | PR | 195 | 05/08/19 | 05/10/19 | HU06 | Hubbard, Robert W | 2 | 0 | 100 | 0 | 100 | 23679 | 0 | 0
142 | Mech Room Labor | PR | 483 | 06/12/19 | 06/14/19 | HU06 | Hubbard, Robert W | 10 | 0 | 500 | 0 | 500 | 24064 | 0 | 0
142 | Mech Room Labor | PR | 508 | 06/12/19 | 06/14/19 | SE64 | Sepulveda Gonzalez, Alfredo | 40 | 0 | 1400 | 0 | 1400 | 24089 | 0 | 0
142 | Mech Room Labor | PR | 654 | 06/19/19 | 06/21/19 | HU06 | Hubbard, Robert W | 10 | 0 | 500 | 0 | 500 | 24140 | 0 | 0
142 | Mech Room Labor | PR | 679 | 06/19/19 | 06/21/19 | SE64 | Sepulveda Gonzalez, Alfredo | 40 | 0 | 1400 | 0 | 1400 | 24165 | 0 | 0
142 | Mech Room Labor | PR | 872 | 06/26/19 | 06/28/19 | HU06 | Hubbard, Robert W | 8 | 0 | 400 | 0 | 400 | 24216 | 0 | 0
142 | Mech Room Labor | PR | 896 | 06/26/19 | 06/28/19 | SE64 | Sepulveda Gonzalez, Alfredo | 38 | 0 | 1330 | 0 | 1330 | 24240 | 0 | 0
142 | Mech Room Labor | PR | 44 | 07/03/19 | 07/05/19 | HU06 | Hubbard, Robert W | 6 | 0 | 300 | 0 | 300 | 24291 | 0 | 0
142 | Mech Room Labor | PR | 67 | 07/03/19 | 07/05/19 | SE64 | Sepulveda Gonzalez, Alfredo | 12 | 0 | 420 | 0 | 420 | 24315 | 0 | 0
142 | Mech Room Labor | PR | 543 | 07/17/19 | 07/19/19 | HU06 | Hubbard, Robert W | 2 | 0 | 100 | 0 | 100 | 24442 | 0 | 0
142 | Mech Room Labor | PR | 552 | 07/17/19 | 07/19/19 | MC09 | McCabe, Thomas C | 4 | 0 | 140 | 0 | 140 | 24451 | 0 | 0
142 | Mech Room Labor | PR | 646 | 07/24/19 | 07/26/19 | HU06 | Hubbard, Robert W | 3 | 0 | 150 | 0 | 150 | 24595 | 0 | 0
142 | Mech Room Labor | PR | 655 | 07/24/19 | 07/26/19 | MC09 | McCabe, Thomas C | 8 | 0 | 280 | 0 | 280 | 24604 | 0 | 0
142 | Mech Room Labor | PR | 38 | 07/31/19 | 08/02/19 | HU06 | Hubbard, Robert W | 1 | 0 | 50 | 0 | 50 | 24669 | 0 | 0
142 | Mech Room Labor | PR | 291 | 08/07/19 | 08/09/19 | HU06 | Hubbard, Robert W | 10 | 0 | 500 | 0 | 500 | 24744 | 0 | 0
142 | Mech Room Labor | PR | 300 | 08/07/19 | 08/09/19 | MC09 | McCabe, Thomas C | 6 | 0 | 210 | 0 | 210 | 24753 | 0 | 0
142 | Mech Room Labor | PR | 607 | 08/14/19 | 08/16/19 | MC09 | McCabe, Thomas C | 8 | 0 | 280 | 0 | 280 | 24826 | 0 | 0
142 | Mech Room Labor | PR | 835 | 08/21/19 | 08/23/19 | HU06 | Hubbard, Robert W | 1 | 0 | 50 | 0 | 50 | 24893 | 0 | 0
142 | Mech Room Labor | PR | 844 | 08/21/19 | 08/23/19 | MC09 | McCabe, Thomas C | 28 | 0 | 980 | 0 | 980 | 24902 | 0 | 0
142 | Mech Room Labor | PR | 1026 | 08/28/19 | 08/30/19 | HU06 | Hubbard, Robert W | 1 | 0 | 50 | 0 | 50 | 24968 | 0 | 0
210 | Underground Material | AP | 485 | 03/01/18 | 03/20/18 | 2044RS | Rosen Supply Company, Inc. $66th Apts |  |  |  |  | 575.21 | 4247580-00 | 0 | 0
210 | Underground Material | AP | 486 | 03/01/18 | 03/20/18 | 2044RS | Rosen Supply Company, Inc. $66th Apts |  |  |  |  | 261.57 | 4248802-00 | 0 | 0
210 | Underground Material | AP | 243 | 03/26/18 | 04/01/18 | 2044RS | Rosen Supply Company, Inc. $66th Apts |  |  |  |  | 464.33 | 4247580-01 | 0 | 0
210 | Underground Material | AP | 363 | 03/29/18 | 04/13/18 | 2044RS | Rosen Supply Company, Inc. $66th Apts |  |  |  |  | 16.64 | 4250031-00 | 0 | 0
211 | Garage Material | GL | 700 | 07/25/18 | 07/25/18 | Mat | Req 5314 |  |  |  |  | 474.2 |  | 0 | 0
211 | Garage Material | GL | 392 | 08/10/18 | 08/10/18 | Mat | Req 4562 |  |  |  |  | -55.48 |  | 0 | 0
211 | Garage Material | AP | 460 | 07/19/18 | 08/15/18 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 1392.5 | 4254775-00 | 0 | 0
211 | Garage Material | AP | 622 | 07/25/18 | 08/21/18 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 38.73 | 4255053-00 | 0 | 0
211 | Garage Material | GL | 676 | 08/22/18 | 08/22/18 | Mat | Req 4643 |  |  |  |  | 319.08 |  | 0 | 0
211 | Garage Material | AP | 18 | 08/15/18 | 09/04/18 | 1380RS | Rosen Supply Kirkland |  |  |  |  | -80 | 4255993-00 | 0 | 0
211 | Garage Material | GL | 172 | 09/10/18 | 09/10/18 | Mat | Req 4703 |  |  |  |  | 292.2 |  | 0 | 0
211 | Garage Material | GL | 599 | 09/25/18 | 09/25/18 | Mat | Req 5398 |  |  |  |  | 128.68 |  | 0 | 0
211 | Garage Material | GL | 372 | 10/16/18 | 10/16/18 | Mat | Req 4705 |  |  |  |  | 65 |  | 0 | 0
211 | Garage Material | GL | 754 | 11/26/18 | 11/26/18 | Mat | Req 5522 |  |  |  |  | 202.28 |  | 0 | 0
211 | Garage Material | GL | 1007 | 11/30/18 | 11/30/18 | Mat | Req 5555 |  |  |  |  | 130 |  | 0 | 0
211 | Garage Material | GL | 328 | 01/11/19 | 01/11/19 | Mat | Req 4862 |  |  |  |  | 20.2 |  | 0 | 0
211 | Garage Material | GL | 408 | 01/15/19 | 01/15/19 | Mat | Req 4907 |  |  |  |  | 18 |  | 0 | 0
211 | Garage Material | GL | 585 | 03/15/19 | 03/15/19 | Mat | Req 5826 |  |  |  |  | 22.7 |  | 0 | 0
211 | Garage Material | GL | 614 | 03/15/19 | 03/15/19 | Mat | Req 5069 |  |  |  |  | -1444.13 |  | 0 | 0
211 | Garage Material | GL | 189 | 04/08/19 | 04/08/19 | Mat | Req 5861 |  |  |  |  | 158.04 |  | 0 | 0
211 | Garage Material | GL | 216 | 04/08/19 | 04/08/19 | Mat | Req 5123 |  |  |  |  | 106 |  | 0 | 0
211 | Garage Material | GL | 266 | 03/05/19 | 04/09/19 | Mat | Req 5156 |  |  |  |  | -755.62 |  | 0 | 0
211 | Garage Material | GL | 863 | 05/30/19 | 05/30/19 | Mat | Req 5938 |  |  |  |  | 217.7 |  | 0 | 0
211 | Garage Material | GL | 871 | 05/30/19 | 05/30/19 | Mat | Req 5213 |  |  |  |  | 795.45 |  | 0 | 0
211 | Garage Material | GL | 232 | 08/08/19 | 08/08/19 | Mat | Req 6181 |  |  |  |  | 14.21 |  | 0 | 0
211 | Garage Material | GL | 332 | 09/16/19 | 09/16/19 | Mat | Req 6297 |  |  |  |  | 79.07 |  | 0 | 0
211 | Garage Material | AP | 581 | 08/26/19 | 09/23/19 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 34.06 | 4271960-00 | 0 | 0
212 | Canout Material | GL | 153 | 04/10/18 | 04/10/18 | Mat | Req 4309 |  |  |  |  | 35.25 |  | 0 | 0
212 | Canout Material | GL | 736 | 04/26/18 | 04/26/18 | Mat | Req 3614 |  |  |  |  | 3567.7 |  | 0 | 0
212 | Canout Material | AP | 399 | 05/01/18 | 05/16/18 | 2044CS | Consolidated Supply Co. $66th Apts |  |  |  |  | 197.94 | S8727305.001 | 0 | 0
212 | Canout Material | GL | 403 | 05/16/18 | 05/16/18 | Mat | Req 4380 |  |  |  |  | -182.24 |  | 0 | 0
212 | Canout Material | GL | 626 | 05/22/18 | 05/22/18 | Mat | Req 4379 |  |  |  |  | 398.18 |  | 0 | 0
212 | Canout Material | GL | 615 | 06/18/18 | 06/18/18 | Mat | Req 3688 |  |  |  |  | 1732.04 |  | 0 | 0
212 | Canout Material | GL | 358 | 08/10/18 | 08/10/18 | Mat | Req 4552 |  |  |  |  | -646.05 |  | 0 | 0
220 | Roughin Material | GL | 264 | 03/13/18 | 03/13/18 | Mat | Req 3517 |  |  |  |  | 73.95 |  | 0 | 0
220 | Roughin Material | GL | 122 | 05/04/18 | 05/04/18 | Mat | Req 3633 |  |  |  |  | 383 |  | 0 | 0
220 | Roughin Material | GL | 699 | 07/25/18 | 07/25/18 | Mat | Req 5315 |  |  |  |  | 71.78 |  | 0 | 0
220 | Roughin Material | GL | 347 | 08/10/18 | 08/10/18 | Mat | Req 4563 |  |  |  |  | 59.87 |  | 0 | 0
220 | Roughin Material | AP | 410 | 07/09/18 | 08/13/18 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 3329.7 | 4248943-00 | 0 | 0
220 | Roughin Material | AP | 420 | 07/11/18 | 08/13/18 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 271.4 | 4254374-00 | 0 | 0
220 | Roughin Material | AP | 437 | 07/17/18 | 08/14/18 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 2115.36 | 4254618-00 | 0 | 0
220 | Roughin Material | AP | 452 | 07/18/18 | 08/14/18 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 57.45 | 4254751-00 | 0 | 0
220 | Roughin Material | GL | 677 | 08/22/18 | 08/22/18 | Mat | Req 4644 |  |  |  |  | 18.06 |  | 0 | 0
220 | Roughin Material | AP | 714 | 07/27/18 | 08/22/18 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 87.1 | 4255197-00 | 0 | 0
220 | Roughin Material | AP | 929 | 08/06/18 | 08/28/18 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 130.04 | 4255535-00 | 0 | 0
220 | Roughin Material | AP | 988 | 08/09/18 | 08/29/18 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 406.58 | 4255751-00 | 0 | 0
220 | Roughin Material | GL | 171 | 09/10/18 | 09/10/18 | Mat | Req 4704 |  |  |  |  | 238.19 |  | 0 | 0
220 | Roughin Material | AP | 262 | 08/21/18 | 09/12/18 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 11427.28 | 4256144-00 | 0 | 0
220 | Roughin Material | AP | 376 | 08/23/18 | 09/14/18 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 478.81 | 4256307-00 | 0 | 0
220 | Roughin Material | AP | 377 | 08/24/18 | 09/14/18 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 144.88 | 4256307-01 | 0 | 0
220 | Roughin Material | AP | 444 | 09/06/18 | 09/19/18 | 1130CS | Consolidated Supply Co. |  |  |  |  | 4326.61 | S8684171.001 | 0 | 0
220 | Roughin Material | GL | 600 | 09/25/18 | 09/25/18 | Mat | Req 5397 |  |  |  |  | 1298.1 |  | 0 | 0
220 | Roughin Material | GL | 771 | 09/30/18 | 09/30/18 | Mat | Req 5418 |  |  |  |  | 716.21 |  | 0 | 0
220 | Roughin Material | AP | 165 | 09/12/18 | 10/10/18 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 259.05 | 4257061-00 | 0 | 0
220 | Roughin Material | GL | 371 | 10/16/18 | 10/16/18 | Mat | Req 5468 |  |  |  |  | 916.35 |  | 0 | 0
220 | Roughin Material | GL | 546 | 10/22/18 | 10/22/18 | Mat | Req 4750 |  |  |  |  | 616.25 |  | 0 | 0
220 | Roughin Material | AP | 594 | 09/25/18 | 10/22/18 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 21.03 | 4257061-03 | 0 | 0
220 | Roughin Material | AP | 676 | 09/27/18 | 10/24/18 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 252.2 | 4257806-00 | 0 | 0
220 | Roughin Material | AP | 677 | 10/01/18 | 10/24/18 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 336.67 | 4257999-00 | 0 | 0
220 | Roughin Material | AP | 393 | 09/14/18 | 10/31/18 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 1074.42 | 4257206-00 | 0 | 0
220 | Roughin Material | AP | 408 | 09/20/18 | 10/31/18 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 86.23 | 4257061-01 | 0 | 0
220 | Roughin Material | AP | 173 | 10/05/18 | 11/07/18 | 1130CS | Consolidated Supply Co. |  |  |  |  | 763.25 | S8959373.001 | 0 | 0
220 | Roughin Material | GL | 308 | 11/09/18 | 11/09/18 | Mat | Req 4785 |  |  |  |  | 1675.1 |  | 0 | 0
220 | Roughin Material | AP | 413 | 10/15/18 | 11/13/18 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 207.32 | 4258643-00 | 0 | 0
220 | Roughin Material | AP | 598 | 10/19/18 | 11/19/18 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 790.78 | 4252891-00 | 0 | 0
220 | Roughin Material | GL | 755 | 11/26/18 | 11/26/18 | Mat | Req 4857 |  |  |  |  | 717.35 |  | 0 | 0
220 | Roughin Material | GL | 1008 | 11/30/18 | 11/30/18 | Mat | Req 5553 |  |  |  |  | 417.3 |  | 0 | 0
220 | Roughin Material | AP | 411 | 11/09/18 | 12/17/18 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 551.57 | 4259685-00 | 0 | 0
220 | Roughin Material | GL | 625 | 12/21/18 | 12/21/18 | Mat | Req 5611 |  |  |  |  | 1024.98 |  | 0 | 0
220 | Roughin Material | GL | 330 | 01/11/19 | 01/11/19 | Mat | Req 4861 |  |  |  |  | 28.35 |  | 0 | 0
220 | Roughin Material | AP | 384 | 11/29/18 | 01/14/19 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 898.02 | 4260435-00 | 0 | 0
220 | Roughin Material | GL | 409 | 01/15/19 | 01/15/19 | Mat | Req 4906 |  |  |  |  | 1123.87 |  | 0 | 0
220 | Roughin Material | AP | 625 | 12/19/18 | 01/22/19 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 138.5 | 4261439-00 | 0 | 0
220 | Roughin Material | GL | 675 | 01/23/19 | 01/23/19 | Mat | Req 4971 |  |  |  |  | 843.8 |  | 0 | 0
220 | Roughin Material | AP | 853 | 01/03/19 | 01/29/19 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 79.12 | 4261759-00 | 0 | 0
220 | Roughin Material | AP | 917 | 01/09/19 | 01/30/19 | 1130CS | Consolidated Supply Co. |  |  |  |  | 342.42 | S9079898.001 | 0 | 0
220 | Roughin Material | AP | 265 | 01/08/19 | 02/08/19 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 98.5 | 4261920-00 | 0 | 0
220 | Roughin Material | GL | 191 | 03/04/19 | 03/04/19 | Mat | Req 5713 |  |  |  |  | 1298.51 |  | 0 | 0
220 | Roughin Material | GL | 362 | 03/08/19 | 03/08/19 | Mat | Req 5026 |  |  |  |  | 580.12 |  | 0 | 0
220 | Roughin Material | GL | 830 | 03/25/19 | 03/25/19 | Mat | Req 5086 |  |  |  |  | 572.6 |  | 0 | 0
220 | Roughin Material | GL | 1059 | 03/28/19 | 03/28/19 | Mat | Req 5837 |  |  |  |  | 86 |  | 0 | 0
220 | Roughin Material | GL | 1001 | 03/29/19 | 03/29/19 | CK#5703 | Anthony Holmes |  |  |  |  | 22.56 |  | 0 | 0
220 | Roughin Material | GL | 190 | 04/08/19 | 04/08/19 | Mat | Req 5862 |  |  |  |  | 334.94 |  | 0 | 0
220 | Roughin Material | GL | 213 | 04/08/19 | 04/08/19 | Mat | Req 5126 |  |  |  |  | 13 |  | 0 | 0
220 | Roughin Material | GL | 270 | 04/08/19 | 04/08/19 | Mat | Req 5157 |  |  |  |  | -444.52 |  | 0 | 0
220 | Roughin Material | AP | 663 | 04/03/19 | 04/23/19 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 17.44 | 4265714-00 | 0 | 0
220 | Roughin Material | AP | 563 | 05/13/19 | 05/21/19 | 1978FC | Fastenal Company |  |  |  |  | 15.19 | WARED109955 | 0 | 0
220 | Roughin Material | GL | 868 | 05/30/19 | 05/30/19 | Mat | Req 5214 |  |  |  |  | 375.49 |  | 0 | 0
220 | Roughin Material | GL | 161 | 06/05/19 | 06/05/19 | Mat | Req 6013 |  |  |  |  | 113.16 |  | 0 | 0
220 | Roughin Material | AP | 273 | 05/22/19 | 06/08/19 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 45.9 | 4267818-00 | 0 | 0
220 | Roughin Material | AP | 709 | 06/12/19 | 06/21/19 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 31.58 | 4268729-00 | 0 | 0
220 | Roughin Material | GL | 112 | 07/09/19 | 07/09/19 | Mat | Req 6078 |  |  |  |  | 90.04 |  | 0 | 0
220 | Roughin Material | AP | 199 | 07/17/19 | 08/08/19 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 235.89 | 4270187-00 | 0 | 0
220 | Roughin Material | GL | 231 | 08/08/19 | 08/08/19 | Mat | Req 6180 |  |  |  |  | 33.02 |  | 0 | 0
220 | Roughin Material | GL | 731 | 08/20/19 | 08/20/19 | Mat | Req 6221 |  |  |  |  | 22.79 |  | 0 | 0
220 | Roughin Material | GL | 331 | 09/16/19 | 09/16/19 | Mat | Req 6296 |  |  |  |  | 39.83 |  | 0 | 0
220 | Roughin Material | GL | 439 | 10/16/19 | 10/16/19 | Adj | [5 empty] | 1.79 |  | 0 | 0
230 | Finish Material | AP | 658 | 03/16/18 | 03/26/18 | 3612MS | Mechanical Sales, Inc. |  |  |  |  | 152.24 | 693961 | 0 | 0
230 | Finish Material | GL | 695 | 03/26/18 | 03/26/18 | Mat | Req 3545 |  |  |  |  | 143.41 |  | 0 | 0
230 | Finish Material | GL | 411 | 07/16/18 | 07/16/18 | Mat | Req 5277 |  |  |  |  | 1676 |  | 0 | 0
230 | Finish Material | GL | 348 | 08/10/18 | 08/10/18 | Mat | Req 4564 |  |  |  |  | 881.35 |  | 0 | 0
230 | Finish Material | GL | 388 | 08/10/18 | 08/10/18 | Mat | Req 4516 |  |  |  |  | 28.5 |  | 0 | 0
230 | Finish Material | AP | 454 | 07/19/18 | 08/14/18 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 4576.38 | 4253787-00 | 0 | 0
230 | Finish Material | AP | 570 | 09/17/18 | 09/20/18 | 7230BB | Best Bath Systems |  |  |  |  | 12941.26 | 193188-IN | 0 | 0
230 | Finish Material | AP | 121 | 09/26/18 | 10/05/18 | 5560CH | California Hydronics Corp |  |  |  |  | 465 | 2108119 | 0 | 0
230 | Finish Material | AP | 224 | 10/03/18 | 10/10/18 | 7230BB | Best Bath Systems |  |  |  |  | 11941.66 | 193840-IN | 0 | 0
230 | Finish Material | GL | 373 | 10/16/18 | 10/16/18 | Mat | Req 4706 |  |  |  |  | 1480.36 |  | 0 | 0
230 | Finish Material | AP | 637 | 10/22/18 | 10/16/18 | 7230BB | Best Bath Systems |  |  |  |  | 11178.57 | 194615-IN | 0 | 0
230 | Finish Material | GL | 581 | 10/22/18 | 10/22/18 | Mat | Req 5479 |  |  |  |  | -85.69 |  | 0 | 0
230 | Finish Material | GL | 893 | 10/31/18 | 10/31/18 | Mat | Req 5485 |  |  |  |  | 187.28 |  | 0 | 0
230 | Finish Material | AP | 910 | 09/26/18 | 10/31/18 | 1231KS | Keller Supply Company |  |  |  |  | 1378.13 | S012289992.001 | 0 | 0
230 | Finish Material | AP | 911 | 09/28/18 | 10/31/18 | 1231KS | Keller Supply Company |  |  |  |  | 1033.6 | S012289992.005 | 0 | 0
230 | Finish Material | GL | 753 | 11/26/18 | 11/26/18 | Mat | Req 5521 |  |  |  |  | 59.02 |  | 0 | 0
230 | Finish Material | AP | 367 | 11/16/18 | 12/14/18 | 1231KS | Keller Supply Company |  |  |  |  | 497.68 | S012470220.001 | 0 | 0
230 | Finish Material | AP | 624 | 12/17/18 | 01/22/19 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 13965 | 4251880-00 | 0 | 0
230 | Finish Material | GL | 677 | 01/23/19 | 01/23/19 | Mat | Req 4969 |  |  |  |  | 507.02 |  | 0 | 0
230 | Finish Material | GL | 291 | 02/08/19 | 02/08/19 | Mat | Req 5685 |  |  |  |  | 266.14 |  | 0 | 0
230 | Finish Material | AP | 480 | 02/27/19 | 03/13/19 | 5560CH | California Hydronics Corp |  |  |  |  | 294 | SIN009323 | 0 | 0
230 | Finish Material | AP | 645 | 02/28/19 | 03/19/19 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 205.4 | 4263985-00 | 0 | 0
230 | Finish Material | AP | 56 | 03/13/19 | 04/03/19 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 31.6 | 4263985-01 | 0 | 0
230 | Finish Material | GL | 191 | 04/08/19 | 04/08/19 | Mat | Req 5863 |  |  |  |  | 472.51 |  | 0 | 0
230 | Finish Material | GL | 214 | 04/08/19 | 04/08/19 | Mat | Req 5125 |  |  |  |  | 78.5 |  | 0 | 0
230 | Finish Material | AP | 373 | 04/25/19 | 05/15/19 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 79.1 | 4266607-00 | 0 | 0
230 | Finish Material | AP | 522 | 04/29/19 | 05/21/19 | 1231KS | Keller Supply Company |  |  |  |  | 9851.86 | S012602299.001 | 0 | 0
230 | Finish Material | AP | 523 | 04/29/19 | 05/21/19 | 1231KS | Keller Supply Company |  |  |  |  | 9625.94 | S012602343.001 | 0 | 0
230 | Finish Material | AP | 524 | 05/10/19 | 05/21/19 | 1231KS | Keller Supply Company |  |  |  |  | 9851.86 | S012602328.001 | 0 | 0
230 | Finish Material | AP | 525 | 05/16/19 | 05/21/19 | 1231KS | Keller Supply Company |  |  |  |  | 7777.75 | S012602319.001 | 0 | 0
230 | Finish Material | AP | 767 | 05/09/19 | 05/29/19 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 197.94 | 4266607-01 | 0 | 0
230 | Finish Material | GL | 838 | 05/30/19 | 05/30/19 | Mat | Req 5995 |  |  |  |  | 884.21 |  | 0 | 0
230 | Finish Material | GL | 865 | 05/30/19 | 05/30/19 | Mat | Req 5936 |  |  |  |  | 639.21 |  | 0 | 0
230 | Finish Material | GL | 870 | 05/30/19 | 05/30/19 | Mat | Req 5211 |  |  |  |  | 3442.28 |  | 0 | 0
230 | Finish Material | AP | 63 | 05/02/19 | 06/05/19 | 1234CO | Capital One Credit Card |  |  |  |  | 40.93 | 050219A | 0 | 0
230 | Finish Material | AP | 66 | 05/20/19 | 06/05/19 | 1234CO | Capital One Credit Card |  |  |  |  | 17.37 | 052019A | 0 | 0
230 | Finish Material | GL | 162 | 06/05/19 | 06/05/19 | Mat | Req 6014 |  |  |  |  | 992.75 |  | 0 | 0
230 | Finish Material | AP | 274 | 05/22/19 | 06/08/19 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 256.5 | 4267851-00 | 0 | 0
230 | Finish Material | AP | 301 | 05/30/19 | 06/08/19 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 51.3 | 4268751-01 | 0 | 0
230 | Finish Material | AP | 375 | 05/24/19 | 06/11/19 | 1231KS | Keller Supply Company |  |  |  |  | 175.74 | S012602292.001 | 0 | 0
230 | Finish Material | AP | 376 | 05/24/19 | 06/11/19 | 1231KS | Keller Supply Company |  |  |  |  | 2279.14 | S012602319.003 | 0 | 0
230 | Finish Material | AP | 377 | 05/24/19 | 06/11/19 | 1231KS | Keller Supply Company |  |  |  |  | 205.03 | S013050989.001 | 0 | 0
230 | Finish Material | AP | 378 | 05/24/19 | 06/11/19 | 1231KS | Keller Supply Company |  |  |  |  | 205.03 | S013051001.001 | 0 | 0
230 | Finish Material | AP | 379 | 05/24/19 | 06/11/19 | 1231KS | Keller Supply Company |  |  |  |  | 205.03 | S013051006.001 | 0 | 0
230 | Finish Material | AP | 385 | 05/29/19 | 06/11/19 | 1231KS | Keller Supply Company |  |  |  |  | 9851.86 | S012602292.002 | 0 | 0
230 | Finish Material | AP | 392 | 05/29/19 | 06/11/19 | 1130CS | Consolidated Supply Co. |  |  |  |  | 457.47 | S9221751.001 | 0 | 0
230 | Finish Material | AP | 400 | 05/31/19 | 06/11/19 | 1130CS | Consolidated Supply Co. |  |  |  |  | 15.65 | S9285409.001 | 0 | 0
230 | Finish Material | AP | 723 | 06/07/19 | 06/24/19 | 5560CH | California Hydronics Corp |  |  |  |  | 3342 | SIN019277 | 0 | 0
230 | Finish Material | GL | 111 | 07/09/19 | 07/09/19 | Mat | Req 6075 |  |  |  |  | 590.06 |  | 0 | 0
230 | Finish Material | AP | 471 | 07/09/19 | 07/16/19 | 1231KS | Keller Supply Company |  |  |  |  | 4115.62 | S012602263.001 | 0 | 0
230 | Finish Material | AP | 472 | 07/12/19 | 07/16/19 | 1231KS | Keller Supply Company |  |  |  |  | 248.36 | S013176579.001 | 0 | 0
230 | Finish Material | AP | 730 | 07/17/19 | 07/31/19 | 1231KS | Keller Supply Company |  |  |  |  | 406.61 | S013126051.001 | 0 | 0
230 | Finish Material | AP | 731 | 07/17/19 | 07/31/19 | 1231KS | Keller Supply Company |  |  |  |  | 632.85 | S013129464.001 | 0 | 0
230 | Finish Material | AP | 147 | 07/18/19 | 08/01/19 | 3612MS | Mechanical Sales, Inc. |  |  |  |  | 165.55 | 703342 | 0 | 0
230 | Finish Material | AP | 404 | 08/06/19 | 08/01/19 | 1234CO | Capital One Credit Card |  |  |  |  | 22.53 | 080619A | 0 | 0
230 | Finish Material | GL | 229 | 08/08/19 | 08/08/19 | Mat | Req 6178 |  |  |  |  | 227.93 |  | 0 | 0
230 | Finish Material | AP | 476 | 07/09/19 | 08/12/19 | 1130CS | Consolidated Supply Co. |  |  |  |  | 276.11 | S009302865.001 | 0 | 0
230 | Finish Material | AP | 487 | 07/24/19 | 08/12/19 | 1231KS | Keller Supply Company |  |  |  |  | 73.23 | S012602263.002 | 0 | 0
230 | Finish Material | AP | 488 | 07/24/19 | 08/12/19 | 1231KS | Keller Supply Company |  |  |  |  | 29.29 | S012602292.003 | 0 | 0
230 | Finish Material | AP | 489 | 07/24/19 | 08/12/19 | 1231KS | Keller Supply Company |  |  |  |  | 57.05 | S013252964.001 | 0 | 0
230 | Finish Material | AP | 504 | 07/25/19 | 08/13/19 | 1231KS | Keller Supply Company |  |  |  |  | 34.68 | S013226568.001 | 0 | 0
230 | Finish Material | AP | 535 | 07/30/19 | 08/14/19 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 41.25 | 4270787-00 | 0 | 0
230 | Finish Material | GL | 694 | 08/20/19 | 08/20/19 | Mat | Req 6287 |  |  |  |  | -43.18 |  | 0 | 0
230 | Finish Material | AP | 913 | 08/14/19 | 08/26/19 | 8056MS | Mechanical Service & Integration LLC |  |  |  |  | 800 | 20266 | 0 | 0
230 | Finish Material | AP | 167 | 08/20/19 | 09/10/19 | 1231KS | Keller Supply Company |  |  |  |  | 542.1 | S013314269.001 | 0 | 0
230 | Finish Material | GL | 330 | 09/16/19 | 09/16/19 | Mat | Req 6295 |  |  |  |  | 621.75 |  | 0 | 0
230 | Finish Material | AP | 593 | 08/29/19 | 09/23/19 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 25.18 | 4272080-00 | 0 | 0
230 | Finish Material | AP | 238 | 09/10/19 | 10/01/19 | 1234CO | Capital One Credit Card |  |  |  |  | 25.24 | 091019A | 0 | 0
240 | Gas Material | GL | 678 | 08/22/18 | 08/22/18 | Mat | Req 4645 |  |  |  |  | 11.7 |  | 0 | 0
240 | Gas Material | AP | 987 | 08/08/18 | 08/29/18 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 214.05 | 4455632-00 | 0 | 0
240 | Gas Material | AP | 217 | 08/21/18 | 09/10/18 | 1231KS | Keller Supply Company |  |  |  |  | 383.28 | S012202265.002 | 0 | 0
240 | Gas Material | AP | 261 | 08/21/18 | 09/12/18 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 19.25 | 4255632-01 | 0 | 0
240 | Gas Material | AP | 660 | 08/31/18 | 09/25/18 | 1231KS | Keller Supply Company |  |  |  |  | -133.77 | S012240319.001 | 0 | 0
240 | Gas Material | AP | 129 | 01/17/19 | 02/06/19 | 1231KS | Keller Supply Company |  |  |  |  | 68.15 | S012649630.001 | 0 | 0
240 | Gas Material | AP | 656 | 02/07/19 | 02/22/19 | 1231KS | Keller Supply Company |  |  |  |  | 86.46 | S012717593.001 | 0 | 0
240 | Gas Material | AP | 699 | 02/06/19 | 02/25/19 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 125.1 | 4263231-00 | 0 | 0
240 | Gas Material | AP | 701 | 02/07/19 | 02/25/19 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 170.83 | 4263231-01 | 0 | 0
240 | Gas Material | GL | 190 | 03/04/19 | 03/04/19 | Mat | Req 5712 |  |  |  |  | 211.04 |  | 0 | 0
240 | Gas Material | GL | 584 | 03/15/19 | 03/15/19 | Mat | Req 5825 |  |  |  |  | 16.35 |  | 0 | 0
240 | Gas Material | AP | 57 | 03/13/19 | 04/03/19 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 20.39 | 4264649-00 | 0 | 0
240 | Gas Material | GL | 192 | 04/08/19 | 04/08/19 | Mat | Req 5864 |  |  |  |  | 16.95 |  | 0 | 0
240 | Gas Material | GL | 115 | 07/09/19 | 07/09/19 | Mat | Req 6079 |  |  |  |  | 127.67 |  | 0 | 0
240 | Gas Material | AP | 190 | 07/15/19 | 08/07/19 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 293.48 | 4270119-00 | 0 | 0
240 | Gas Material | AP | 193 | 07/16/19 | 08/07/19 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 164.82 | 4270188-00 | 0 | 0
240 | Gas Material | GL | 230 | 08/08/19 | 08/08/19 | Mat | Req 6179 |  |  |  |  | 31.55 |  | 0 | 0
240 | Gas Material | AP | 467 | 07/24/19 | 08/12/19 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 35.13 | 4270119-01 | 0 | 0
240 | Gas Material | AP | 536 | 07/31/19 | 08/14/19 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 130.02 | 4270853-00 | 0 | 0
240 | Gas Material | GL | 695 | 08/20/19 | 08/20/19 | Mat | Req 6286 |  |  |  |  | -52.78 |  | 0 | 0
240 | Gas Material | GL | 732 | 08/20/19 | 08/20/19 | Mat | Req 6220 |  |  |  |  | 120.39 |  | 0 | 0
240 | Gas Material | AP | 954 | 08/02/19 | 08/28/19 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 38.32 | 4270954-00 | 0 | 0
241 | Water Main/Insulation Mat | GL | 356 | 08/10/18 | 08/10/18 | Mat | Req 4554 |  |  |  |  | -383.26 |  | 0 | 0
241 | Water Main/Insulation Mat | GL | 357 | 08/10/18 | 08/10/18 | Mat | Req 4553 |  |  |  |  | -56.56 |  | 0 | 0
241 | Water Main/Insulation Mat | AP | 172 | 10/05/18 | 11/07/18 | 1130CS | Consolidated Supply Co. |  |  |  |  | 2541.61 | S8959346.001 | 0 | 0
241 | Water Main/Insulation Mat | AP | 1027 | 11/06/18 | 11/30/18 | 1130CS | Consolidated Supply Co. |  |  |  |  | 276.38 | S8952896.001 | 0 | 0
241 | Water Main/Insulation Mat | AP | 1028 | 11/09/18 | 11/30/18 | 1130CS | Consolidated Supply Co. |  |  |  |  | 472.53 | S8952896.003 | 0 | 0
241 | Water Main/Insulation Mat | AP | 658 | 12/05/18 | 12/21/18 | 1130CS | Consolidated Supply Co. |  |  |  |  | 435.75 | S9044650.001 | 0 | 0
241 | Water Main/Insulation Mat | AP | 659 | 12/07/18 | 12/21/18 | 1130CS | Consolidated Supply Co. |  |  |  |  | 2121.13 | S9048178.001 | 0 | 0
241 | Water Main/Insulation Mat | GL | 676 | 01/23/19 | 01/23/19 | Mat | Req 4970 |  |  |  |  | 142.17 |  | 0 | 0
241 | Water Main/Insulation Mat | AP | 548 | 02/15/19 | 02/19/19 | 1130CS | Consolidated Supply Co. |  |  |  |  | 1763.78 | S9134468.001 | 0 | 0
241 | Water Main/Insulation Mat | GL | 189 | 03/04/19 | 03/04/19 | Mat | Req 5711 |  |  |  |  | 244.34 |  | 0 | 0
241 | Water Main/Insulation Mat | GL | 342 | 03/08/19 | 03/08/19 | Mat | Req 5829 |  |  |  |  | -319.8 |  | 0 | 0
241 | Water Main/Insulation Mat | GL | 361 | 03/08/19 | 03/08/19 | Mat | Req 5027 |  |  |  |  | 492.37 |  | 0 | 0
241 | Water Main/Insulation Mat | AP | 433 | 02/25/19 | 03/12/19 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 417.42 | 4263781-00 | 0 | 0
241 | Water Main/Insulation Mat | AP | 473 | 02/26/19 | 03/13/19 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 720.24 | 4263781-01 | 0 | 0
241 | Water Main/Insulation Mat | GL | 583 | 03/15/19 | 03/15/19 | Mat | Req 5824 |  |  |  |  | 341.46 |  | 0 | 0
241 | Water Main/Insulation Mat | AP | 644 | 02/28/19 | 03/19/19 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 75.6 | 4263781-02 | 0 | 0
241 | Water Main/Insulation Mat | AP | 653 | 03/04/19 | 03/19/19 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 364.5 | 4263989-00 | 0 | 0
241 | Water Main/Insulation Mat | AP | 159 | 03/20/19 | 04/05/19 | 1130CS | Consolidated Supply Co. |  |  |  |  | 1161.34 | S9178295.001 | 0 | 0
241 | Water Main/Insulation Mat | GL | 188 | 04/08/19 | 04/08/19 | Mat | Req 5860 |  |  |  |  | 169.51 |  | 0 | 0
241 | Water Main/Insulation Mat | GL | 215 | 04/08/19 | 04/08/19 | Mat | Req 5124 |  |  |  |  | 445.1 |  | 0 | 0
241 | Water Main/Insulation Mat | GL | 910 | 04/30/19 | 04/30/19 | Mat | Req 5182 |  |  |  |  | 400.44 |  | 0 | 0
241 | Water Main/Insulation Mat | AP | 917 | 04/22/19 | 04/30/19 | 1130CS | Consolidated Supply Co. |  |  |  |  | 101.2 | S9225744.001 | 0 | 0
241 | Water Main/Insulation Mat | AP | 918 | 04/24/19 | 04/30/19 | 1130CS | Consolidated Supply Co. |  |  |  |  | 1358.31 | S9228819.001 | 0 | 0
241 | Water Main/Insulation Mat | AP | 586 | 05/06/19 | 05/23/19 | 1130CS | Consolidated Supply Co. |  |  |  |  | 392.29 | S9240754.001 | 0 | 0
241 | Water Main/Insulation Mat | GL | 866 | 05/30/19 | 05/30/19 | Mat | Req 5935 |  |  |  |  | 1154.63 |  | 0 | 0
241 | Water Main/Insulation Mat | GL | 867 | 05/30/19 | 05/30/19 | Mat | Req 5212 |  |  |  |  | 1445.85 |  | 0 | 0
241 | Water Main/Insulation Mat | GL | 163 | 06/05/19 | 06/05/19 | Mat | Req 6015 |  |  |  |  | 42.16 |  | 0 | 0
241 | Water Main/Insulation Mat | GL | 793 | 06/26/19 | 06/26/19 | Mat | Req 6068 |  |  |  |  | -2553.35 |  | 0 | 0
241 | Water Main/Insulation Mat | GL | 116 | 07/09/19 | 07/09/19 | Mat | Req 6080 |  |  |  |  | 332.52 |  | 0 | 0
242 | Mech Room Material | GL | 909 | 04/30/19 | 04/30/19 | Mat | Req 5183 |  |  |  |  | 439.26 |  | 0 | 0
242 | Mech Room Material | GL | 864 | 05/30/19 | 05/30/19 | Mat | Req 5937 |  |  |  |  | 8.93 |  | 0 | 0
242 | Mech Room Material | GL | 869 | 05/30/19 | 05/30/19 | Mat | Req 5210 |  |  |  |  | 1775.49 |  | 0 | 0
242 | Mech Room Material | AP | 417 | 06/01/19 | 06/12/19 | 1175FE | Ferguson Enterprises, Inc. #3007 |  |  |  |  | 5611.55 | 7204946 | 0 | 0
242 | Mech Room Material | AP | 568 | 06/07/19 | 06/17/19 | 1130CS | Consolidated Supply Co. |  |  |  |  | 2221.8 | S9256615.001 | 0 | 0
242 | Mech Room Material | AP | 569 | 06/07/19 | 06/17/19 | 1130CS | Consolidated Supply Co. |  |  |  |  | 601.76 | S9267631.001 | 0 | 0
242 | Mech Room Material | AP | 577 | 06/14/19 | 06/17/19 | 1130CS | Consolidated Supply Co. |  |  |  |  | 417.12 | S009306903.001 | 0 | 0
242 | Mech Room Material | AP | 579 | 06/10/19 | 06/17/19 | 1175FE | Ferguson Enterprises, Inc. #3007 |  |  |  |  | 1179.04 | 7281220 | 0 | 0
242 | Mech Room Material | AP | 709 | 06/12/19 | 06/21/19 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 149.92 | 4268729-00 | 0 | 0
242 | Mech Room Material | AP | 763 | 06/18/19 | 06/24/19 | 1175FE | Ferguson Enterprises, Inc. #3007 |  |  |  |  | 953.52 | 7304726 | 0 | 0
242 | Mech Room Material | GL | 113 | 07/09/19 | 07/09/19 | Mat | Req 6077 |  |  |  |  | 776.3 |  | 0 | 0
242 | Mech Room Material | GL | 114 | 07/09/19 | 07/09/19 | Mat | Req 6076 |  |  |  |  | 692.94 |  | 0 | 0
242 | Mech Room Material | AP | 377 | 06/22/19 | 07/10/19 | 1175FE | Ferguson Enterprises, Inc. #3007 |  |  |  |  | 64.7 | 7304726-1 | 0 | 0
242 | Mech Room Material | AP | 382 | 06/22/19 | 07/10/19 | 1175FE | Ferguson Enterprises, Inc. #3007 |  |  |  |  | 198.57 | 7318201 | 0 | 0
242 | Mech Room Material | AP | 400 | 06/25/19 | 07/15/19 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 128.03 | 4269272-00 | 0 | 0
242 | Mech Room Material | GL | 228 | 08/08/19 | 08/08/19 | Mat | Req 6177 |  |  |  |  | 292.26 |  | 0 | 0
243 | Condensation Drains Mat | GL | 693 | 04/24/19 | 04/24/19 | Mat | Req 5902 |  |  |  |  | 1.79 |  | 0 | 0
243 | Condensation Drains Mat | GL | 439 | 10/16/19 | 10/16/19 | Adj | [5 empty] | -1.79 |  | 0 | 0
600 | Subcontractor | AP | 718 | 07/17/19 | 07/30/19 | 1641AR | A.R. Brown Backflow Testing |  |  |  |  | 150 | INV01532 | 0 | 0
600 | Subcontractor | AP | 655 | 08/16/19 | 08/19/19 | 3129MR | Mechanical Resource Services, Inc. |  |  |  |  | 3750 | 16672-5562 | 0 | 0
601 | Engineering/Plans | AP | 625 | 09/20/17 | 09/25/17 | 1625FE | Franklin Engineering |  |  |  |  | 1426 | 6666 | 0 | 0
601 | Engineering/Plans | AP | 580 | 10/19/17 | 10/27/17 | 1625FE | Franklin Engineering |  |  |  |  | 2430 | 6700 | 0 | 0
601 | Engineering/Plans | AP | 538 | 11/16/17 | 11/22/17 | 1625FE | Franklin Engineering |  |  |  |  | 5660.25 | 6734 | 0 | 0
601 | Engineering/Plans | AP | 112 | 12/19/17 | 01/05/18 | 1625FE | Franklin Engineering |  |  |  |  | 2743.5 | 6776 | 0 | 0
601 | Engineering/Plans | AP | 578 | 01/19/18 | 01/24/18 | 1625FE | Franklin Engineering |  |  |  |  | 164 | 6811 | 0 | 0
601 | Engineering/Plans | AP | 746 | 02/20/18 | 02/27/18 | 1625FE | Franklin Engineering |  |  |  |  | 2108.5 | 6841 | 0 | 0
601 | Engineering/Plans | AP | 645 | 03/21/18 | 03/26/18 | 1625FE | Franklin Engineering |  |  |  |  | 251 | 6877 | 0 | 0
601 | Engineering/Plans | AP | 158 | 05/21/18 | 06/04/18 | 1625FE | Franklin Engineering |  |  |  |  | 2872.5 | 6946 | 0 | 0
601 | Engineering/Plans | AP | 790 | 06/19/18 | 06/22/18 | 1625FE | Franklin Engineering |  |  |  |  | 5611 | 6980 | 0 | 0
601 | Engineering/Plans | AP | 126 | 06/26/18 | 07/09/18 | 1288DR | DRSi |  |  |  |  | 112.84 | 467313 | 0 | 0
601 | Engineering/Plans | AP | 613 | 07/18/18 | 07/23/18 | 1625FE | Franklin Engineering |  |  |  |  | 1405.75 | 7032 | 0 | 0
601 | Engineering/Plans | AP | 29 | 08/29/18 | 09/04/18 | 1288DR | DRSi |  |  |  |  | 35.7 | 471365 | 0 | 0
601 | Engineering/Plans | AP | 227 | 09/04/18 | 09/11/18 | 1288DR | DRSi |  |  |  |  | 11.9 | 471643 | 0 | 0
601 | Engineering/Plans | AP | 19 | 09/19/18 | 10/01/18 | 1625FE | Franklin Engineering |  |  |  |  | 892.5 | 7106 | 0 | 0
602 | Rental Equipment | AP | 482 | 05/03/19 | 05/17/19 | 2713AR | Ahern Rentals |  |  |  |  | 710.7 | 20446656-001 | 0 | 0
602 | Rental Equipment | AP | 785 | 05/28/19 | 05/29/19 | 2713AR | Ahern Rentals |  |  |  |  | -187.72 | 20446656-003 | 0 | 0
602 | Rental Equipment | AP | 319 | 05/22/19 | 06/10/19 | 2713AR | Ahern Rentals |  |  |  |  | 121.11 | 20446656-002 | 0 | 0
603 | Permits & Licenses | AP | 574 | 08/09/17 | 08/28/17 | 1234CO | Capital One Credit Card |  |  |  |  | 210 | 080917A | 0 | 0
603 | Permits & Licenses | AP | 575 | 08/09/17 | 08/28/17 | 1234CO | Capital One Credit Card |  |  |  |  | 175 | 080917B | 0 | 0
603 | Permits & Licenses | AP | 109 | 02/21/19 | 03/01/19 | 1234CO | Capital One Credit Card |  |  |  |  | 310 | 022119J1 | 0 | 0
607 | Other Expenses | AP | 576 | 08/09/17 | 08/28/17 | 1234CO | Capital One Credit Card |  |  |  |  | 3445 | 080917C | 0 | 0
607 | Other Expenses | AP | 127 | 07/20/18 | 08/07/18 | 1234CO | Capital One Credit Card |  |  |  |  | 14.71 | 072018J1 | 0 | 0
607 | Other Expenses | AP | 146 | 07/15/18 | 08/07/18 | 1234CO | Capital One Credit Card |  |  |  |  | 658.68 | 071518R4 | 0 | 0
607 | Other Expenses | AP | 1130 | 08/15/18 | 08/30/18 | 1234CO | Capital One Credit Card |  |  |  |  | 329.34 | 081518R4 | 0 | 0
607 | Other Expenses | AP | 808 | 09/11/18 | 09/30/18 | 1234CO | Capital One Credit Card |  |  |  |  | 14.71 | 091118J2 | 0 | 0
607 | Other Expenses | AP | 825 | 09/15/18 | 09/30/18 | 1234CO | Capital One Credit Card |  |  |  |  | 329.34 | 091518R4 | 0 | 0
607 | Other Expenses | AP | 833 | 10/15/18 | 10/30/18 | 1234CO | Capital One Credit Card |  |  |  |  | 329.34 | 101518R4 | 0 | 0
607 | Other Expenses | AP | 487 | 11/15/18 | 12/14/18 | 1234CO | Capital One Credit Card |  |  |  |  | 329.34 | 111518R4 | 0 | 0
607 | Other Expenses | AP | 856 | 12/21/18 | 12/31/18 | 1234CO | Capital One Credit Card |  |  |  |  | 356.91 | 122118R1 | 0 | 0
607 | Other Expenses | AP | 453 | 01/15/19 | 02/14/19 | 1234CO | Capital One Credit Card |  |  |  |  | 356.91 | 011519R4 | 0 | 0
607 | Other Expenses | AP | 110 | 02/21/19 | 03/01/19 | 1234CO | Capital One Credit Card |  |  |  |  | 17.16 | 022119J2 | 0 | 0
607 | Other Expenses | AP | 130 | 02/15/19 | 03/04/19 | 1234CO | Capital One Credit Card |  |  |  |  | 713.82 | 021519R3 | 0 | 0
607 | Other Expenses | AP | 1005 | 02/27/19 | 03/31/19 | 1234CO | Capital One Credit Card |  |  |  |  | -232.94 | 022719 | 0 | 0
607 | Other Expenses | AP | 1042 | 03/16/19 | 03/31/19 | 1234CO | Capital One Credit Card |  |  |  |  | 475.88 | 031619R3 | 0 | 0
607 | Other Expenses | AP | 977 | 04/16/19 | 04/30/19 | 1234CO | Capital One Credit Card |  |  |  |  | 475.88 | 041619R3 | 0 | 0
607 | Other Expenses | AP | 79 | 05/16/19 | 06/05/19 | 1234CO | Capital One Credit Card |  |  |  |  | 475.88 | 051619R3 | 0 | 0
607 | Other Expenses | AP | 243 | 06/16/19 | 07/10/19 | 1234CO | Capital One Credit Card |  |  |  |  | 475.88 | 061619R2 | 0 | 0
607 | Other Expenses | AP | 366 | 07/11/19 | 08/01/19 | 1234CO | Capital One Credit Card |  |  |  |  | -465.88 | 071119C2 | 0 | 0
607 | Other Expenses | AP | 241 | 09/17/19 | 10/01/19 | 1234CO | Capital One Credit Card |  |  |  |  | 1.5 | 091719A | 0 | 0
995 | Payroll Burden | PR | 403 | 08/16/17 | 08/18/17 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 22.18 |  | 0 | 0
995 | Payroll Burden | PR | 185 | 09/06/17 | 09/08/17 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 20.84 |  | 0 | 0
995 | Payroll Burden | PR | 762 | 09/27/17 | 09/29/17 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 41.69 |  | 0 | 0
995 | Payroll Burden | PR | 67 | 10/04/17 | 10/06/17 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 22.18 |  | 0 | 0
995 | Payroll Burden | PR | 70 | 01/31/18 | 02/02/18 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 55.44 |  | 0 | 0
995 | Payroll Burden | PR | 71 | 01/31/18 | 02/02/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 20.84 |  | 0 | 0
995 | Payroll Burden | PR | 226 | 02/07/18 | 02/09/18 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 27.72 |  | 0 | 0
995 | Payroll Burden | PR | 483 | 02/14/18 | 02/16/18 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 27.72 |  | 0 | 0
995 | Payroll Burden | PR | 603 | 02/21/18 | 02/23/18 | AN14 | Anderson, Richard P | 0 | 0 | 0 | 0 | 46.57 |  | 0 | 0
995 | Payroll Burden | PR | 607 | 02/21/18 | 02/23/18 | BA70 | Barnhart, Joseph N | 0 | 0 | 0 | 0 | 68.3 |  | 0 | 0
995 | Payroll Burden | PR | 669 | 02/21/18 | 02/23/18 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 138.59 |  | 0 | 0
995 | Payroll Burden | PR | 670 | 02/21/18 | 02/23/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 20.84 |  | 0 | 0
995 | Payroll Burden | PR | 2 | 02/28/18 | 03/02/18 | AN14 | Anderson, Richard P | 0 | 0 | 0 | 0 | 130.39 |  | 0 | 0
995 | Payroll Burden | PR | 37 | 02/28/18 | 03/02/18 | KI55 | Kinssies, Jr, John E | 0 | 0 | 0 | 0 | 80.72 |  | 0 | 0
995 | Payroll Burden | PR | 68 | 02/28/18 | 03/02/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 83.38 |  | 0 | 0
995 | Payroll Burden | PR | 68 | 02/28/18 | 03/02/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 41.69 |  | 0 | 0
995 | Payroll Burden | PR | 118 | 03/07/18 | 03/09/18 | AN14 | Anderson, Richard P | 0 | 0 | 0 | 0 | 214.21 |  | 0 | 0
995 | Payroll Burden | PR | 151 | 03/07/18 | 03/09/18 | KI55 | Kinssies, Jr, John E | 0 | 0 | 0 | 0 | 80.72 |  | 0 | 0
995 | Payroll Burden | PR | 179 | 03/07/18 | 03/09/18 | WE55 | Wennig, Johnathan M | 0 | 0 | 0 | 0 | 51.89 |  | 0 | 0
995 | Payroll Burden | PR | 183 | 03/07/18 | 03/09/18 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 27.72 |  | 0 | 0
995 | Payroll Burden | PR | 318 | 03/14/18 | 03/16/18 | AN14 | Anderson, Richard P | 0 | 0 | 0 | 0 | 9.31 |  | 0 | 0
995 | Payroll Burden | PR | 516 | 03/21/18 | 03/23/18 | AN14 | Anderson, Richard P | 0 | 0 | 0 | 0 | 93.14 |  | 0 | 0
995 | Payroll Burden | PR | 550 | 03/21/18 | 03/23/18 | KI55 | Kinssies, Jr, John E | 0 | 0 | 0 | 0 | 46.12 |  | 0 | 0
995 | Payroll Burden | PR | 735 | 03/28/18 | 03/30/18 | AN14 | Anderson, Richard P | 0 | 0 | 0 | 0 | 18.63 |  | 0 | 0
995 | Payroll Burden | PR | 739 | 03/28/18 | 03/30/18 | BA70 | Barnhart, Joseph N | 0 | 0 | 0 | 0 | 19.51 |  | 0 | 0
995 | Payroll Burden | PR | 11 | 04/04/18 | 04/06/18 | AN14 | Anderson, Richard P | 0 | 0 | 0 | 0 | 37.25 |  | 0 | 0
995 | Payroll Burden | PR | 11 | 04/04/18 | 04/06/18 | AN14 | Anderson, Richard P | 0 | 0 | 0 | 0 | 18.63 |  | 0 | 0
995 | Payroll Burden | PR | 15 | 04/04/18 | 04/06/18 | BA70 | Barnhart, Joseph N | 0 | 0 | 0 | 0 | 253.68 |  | 0 | 0
995 | Payroll Burden | PR | 48 | 04/04/18 | 04/06/18 | KI55 | Kinssies, Jr, John E | 0 | 0 | 0 | 0 | 115.31 |  | 0 | 0
995 | Payroll Burden | PR | 80 | 04/04/18 | 04/06/18 | WE55 | Wennig, Johnathan M | 0 | 0 | 0 | 0 | 92.25 |  | 0 | 0
995 | Payroll Burden | PR | 84 | 04/04/18 | 04/06/18 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 27.72 |  | 0 | 0
995 | Payroll Burden | PR | 85 | 04/04/18 | 04/06/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 22.18 |  | 0 | 0
995 | Payroll Burden | PR | 259 | 04/11/18 | 04/13/18 | AN14 | Anderson, Richard P | 0 | 0 | 0 | 0 | 46.57 |  | 0 | 0
995 | Payroll Burden | PR | 296 | 04/11/18 | 04/13/18 | KI55 | Kinssies, Jr, John E | 0 | 0 | 0 | 0 | 28.83 |  | 0 | 0
995 | Payroll Burden | PR | 329 | 04/11/18 | 04/13/18 | WE55 | Wennig, Johnathan M | 0 | 0 | 0 | 0 | 23.06 |  | 0 | 0
995 | Payroll Burden | PR | 446 | 04/18/18 | 04/20/18 | AN14 | Anderson, Richard P | 0 | 0 | 0 | 0 | 27.94 |  | 0 | 0
995 | Payroll Burden | PR | 612 | 04/25/18 | 04/27/18 | AN14 | Anderson, Richard P | 0 | 0 | 0 | 0 | 372.54 |  | 0 | 0
995 | Payroll Burden | PR | 648 | 04/25/18 | 04/27/18 | KI55 | Kinssies, Jr, John E | 0 | 0 | 0 | 0 | 253.68 |  | 0 | 0
995 | Payroll Burden | PR | 26 | 05/02/18 | 05/04/18 | AN14 | Anderson, Richard P | 0 | 0 | 0 | 0 | 55.88 |  | 0 | 0
995 | Payroll Burden | PR | 31 | 05/02/18 | 05/04/18 | BA70 | Barnhart, Joseph N | 0 | 0 | 0 | 0 | 97.57 |  | 0 | 0
995 | Payroll Burden | PR | 62 | 05/02/18 | 05/04/18 | KI55 | Kinssies, Jr, John E | 0 | 0 | 0 | 0 | 178.73 |  | 0 | 0
995 | Payroll Burden | PR | 426 | 05/16/18 | 05/18/18 | BA70 | Barnhart, Joseph N | 0 | 0 | 0 | 0 | 39.03 |  | 0 | 0
995 | Payroll Burden | PR | 3 | 05/30/18 | 06/01/18 | AN14 | Anderson, Richard P | 0 | 0 | 0 | 0 | 139.7 |  | 0 | 0
995 | Payroll Burden | PR | 38 | 05/30/18 | 06/01/18 | KI55 | Kinssies, Jr, John E | 0 | 0 | 0 | 0 | 86.48 |  | 0 | 0
995 | Payroll Burden | PR | 340 | 06/06/18 | 06/08/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 22.18 |  | 0 | 0
995 | Payroll Burden | PR | 458 | 06/13/18 | 06/15/18 | AN14 | Anderson, Richard P | 0 | 0 | 0 | 0 | 28.61 |  | 0 | 0
995 | Payroll Burden | PR | 493 | 06/13/18 | 06/15/18 | KI55 | Kinssies, Jr, John E | 0 | 0 | 0 | 0 | 92.25 |  | 0 | 0
995 | Payroll Burden | PR | 496 | 06/13/18 | 06/15/18 | LO58 | Lopez Reyes, Boris O | 0 | 0 | 0 | 0 | 23.95 |  | 0 | 0
995 | Payroll Burden | PR | 496 | 06/13/18 | 06/15/18 | LO58 | Lopez Reyes, Boris O | 0 | 0 | 0 | 0 | 295.37 |  | 0 | 0
995 | Payroll Burden | PR | 528 | 06/13/18 | 06/15/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 22.18 |  | 0 | 0
995 | Payroll Burden | PR | 684 | 06/20/18 | 06/22/18 | AN14 | Anderson, Richard P | 0 | 0 | 0 | 0 | 47.68 |  | 0 | 0
995 | Payroll Burden | PR | 705 | 06/20/18 | 06/22/18 | GA70 | Garcia, Jordan X | 0 | 0 | 0 | 0 | 35.48 |  | 0 | 0
995 | Payroll Burden | PR | 754 | 06/20/18 | 06/22/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 22.18 |  | 0 | 0
995 | Payroll Burden | PR | 1020 | 06/27/18 | 06/29/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 22.18 |  | 0 | 0
995 | Payroll Burden | PR | 5 | 07/04/18 | 07/06/18 | AN14 | Anderson, Richard P | 0 | 0 | 0 | 0 | 19.07 |  | 0 | 0
995 | Payroll Burden | PR | 68 | 07/04/18 | 07/06/18 | TA96 | Taylor, Evan R | 0 | 0 | 0 | 0 | 21.29 |  | 0 | 0
995 | Payroll Burden | PR | 71 | 07/04/18 | 07/06/18 | WA35 | Waites, Thaddeus Z | 0 | 0 | 0 | 0 | 37.25 |  | 0 | 0
995 | Payroll Burden | PR | 241 | 07/11/18 | 07/13/18 | BA70 | Barnhart, Joseph N | 0 | 0 | 0 | 0 | 30.6 |  | 0 | 0
995 | Payroll Burden | PR | 327 | 07/11/18 | 07/13/18 | HO14 | Holmes, Anthony R | 0 | 0 | 0 | 0 | 372.54 |  | 0 | 0
995 | Payroll Burden | PR | 360 | 07/11/18 | 07/13/18 | TA96 | Taylor, Evan R | 0 | 0 | 0 | 0 | 298.03 |  | 0 | 0
995 | Payroll Burden | PR | 363 | 07/11/18 | 07/13/18 | WA35 | Waites, Thaddeus Z | 0 | 0 | 0 | 0 | 372.54 |  | 0 | 0
995 | Payroll Burden | PR | 367 | 07/11/18 | 07/13/18 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 27.72 |  | 0 | 0
995 | Payroll Burden | PR | 441 | 07/18/18 | 07/20/18 | BA70 | Barnhart, Joseph N | 0 | 0 | 0 | 0 | 40.8 |  | 0 | 0
995 | Payroll Burden | PR | 468 | 07/18/18 | 07/20/18 | HO14 | Holmes, Anthony R | 0 | 0 | 0 | 0 | 620.9 |  | 0 | 0
995 | Payroll Burden | PR | 501 | 07/18/18 | 07/20/18 | TA96 | Taylor, Evan R | 0 | 0 | 0 | 0 | 340.61 |  | 0 | 0
995 | Payroll Burden | PR | 504 | 07/18/18 | 07/20/18 | WA35 | Waites, Thaddeus Z | 0 | 0 | 0 | 0 | 568.12 |  | 0 | 0
995 | Payroll Burden | PR | 507 | 07/18/18 | 07/20/18 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 27.72 |  | 0 | 0
995 | Payroll Burden | PR | 508 | 07/18/18 | 07/20/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 22.18 |  | 0 | 0
995 | Payroll Burden | PR | 795 | 07/25/18 | 07/27/18 | HO14 | Holmes, Anthony R | 0 | 0 | 0 | 0 | 620.9 |  | 0 | 0
995 | Payroll Burden | PR | 828 | 07/25/18 | 07/27/18 | TA96 | Taylor, Evan R | 0 | 0 | 0 | 0 | 287.39 |  | 0 | 0
995 | Payroll Burden | PR | 831 | 07/25/18 | 07/27/18 | WA35 | Waites, Thaddeus Z | 0 | 0 | 0 | 0 | 279.41 |  | 0 | 0
995 | Payroll Burden | PR | 834 | 07/25/18 | 07/27/18 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 27.72 |  | 0 | 0
995 | Payroll Burden | PR | 835 | 07/25/18 | 07/27/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 22.18 |  | 0 | 0
995 | Payroll Burden | PR | 6 | 08/01/18 | 08/03/18 | BA70 | Barnhart, Joseph N | 0 | 0 | 0 | 0 | 112.21 |  | 0 | 0
995 | Payroll Burden | PR | 33 | 08/01/18 | 08/03/18 | HO14 | Holmes, Anthony R | 0 | 0 | 0 | 0 | 496.72 |  | 0 | 0
995 | Payroll Burden | PR | 66 | 08/01/18 | 08/03/18 | TA96 | Taylor, Evan R | 0 | 0 | 0 | 0 | 425.76 |  | 0 | 0
995 | Payroll Burden | PR | 69 | 08/01/18 | 08/03/18 | WA35 | Waites, Thaddeus Z | 0 | 0 | 0 | 0 | 642.63 |  | 0 | 0
995 | Payroll Burden | PR | 69 | 08/01/18 | 08/03/18 | WA35 | Waites, Thaddeus Z | 0 | 0 | 0 | 0 | 18.63 |  | 0 | 0
995 | Payroll Burden | PR | 216 | 08/08/18 | 08/10/18 | BA70 | Barnhart, Joseph N | 0 | 0 | 0 | 0 | 40.8 |  | 0 | 0
995 | Payroll Burden | PR | 244 | 08/08/18 | 08/10/18 | HO14 | Holmes, Anthony R | 0 | 0 | 0 | 0 | 620.9 |  | 0 | 0
995 | Payroll Burden | PR | 277 | 08/08/18 | 08/10/18 | TA96 | Taylor, Evan R | 0 | 0 | 0 | 0 | 425.76 |  | 0 | 0
995 | Payroll Burden | PR | 280 | 08/08/18 | 08/10/18 | WA35 | Waites, Thaddeus Z | 0 | 0 | 0 | 0 | 353.91 |  | 0 | 0
995 | Payroll Burden | PR | 283 | 08/08/18 | 08/10/18 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 27.72 |  | 0 | 0
995 | Payroll Burden | PR | 284 | 08/08/18 | 08/10/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 22.18 |  | 0 | 0
995 | Payroll Burden | PR | 512 | 08/15/18 | 08/17/18 | HO14 | Holmes, Anthony R | 0 | 0 | 0 | 0 | 589.86 |  | 0 | 0
995 | Payroll Burden | PR | 520 | 08/15/18 | 08/17/18 | LO58 | Lopez Reyes, Boris O | 0 | 0 | 0 | 0 | 127.73 |  | 0 | 0
995 | Payroll Burden | PR | 544 | 08/15/18 | 08/17/18 | TA96 | Taylor, Evan R | 0 | 0 | 0 | 0 | 255.46 |  | 0 | 0
995 | Payroll Burden | PR | 547 | 08/15/18 | 08/17/18 | WA35 | Waites, Thaddeus Z | 0 | 0 | 0 | 0 | 27.94 |  | 0 | 0
995 | Payroll Burden | PR | 551 | 08/15/18 | 08/17/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 22.18 |  | 0 | 0
995 | Payroll Burden | PR | 551 | 08/15/18 | 08/17/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 44.35 |  | 0 | 0
995 | Payroll Burden | PR | 774 | 08/22/18 | 08/24/18 | HO14 | Holmes, Anthony R | 0 | 0 | 0 | 0 | 620.9 |  | 0 | 0
995 | Payroll Burden | PR | 779 | 08/22/18 | 08/24/18 | LE17 | Lee, Ha Nul | 0 | 0 | 0 | 0 | 241.26 |  | 0 | 0
995 | Payroll Burden | PR | 781 | 08/22/18 | 08/24/18 | LO58 | Lopez Reyes, Boris O | 0 | 0 | 0 | 0 | 255.46 |  | 0 | 0
995 | Payroll Burden | PR | 805 | 08/22/18 | 08/24/18 | TA96 | Taylor, Evan R | 0 | 0 | 0 | 0 | 170.3 |  | 0 | 0
995 | Payroll Burden | PR | 809 | 08/22/18 | 08/24/18 | WE55 | Wennig, Johnathan M | 0 | 0 | 0 | 0 | 298.03 |  | 0 | 0
995 | Payroll Burden | PR | 811 | 08/22/18 | 08/24/18 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 55.44 |  | 0 | 0
995 | Payroll Burden | PR | 812 | 08/22/18 | 08/24/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 44.35 |  | 0 | 0
995 | Payroll Burden | PR | 812 | 08/22/18 | 08/24/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 22.18 |  | 0 | 0
995 | Payroll Burden | PR | 1000 | 08/29/18 | 08/31/18 | BA70 | Barnhart, Joseph N | 0 | 0 | 0 | 0 | 40.8 |  | 0 | 0
995 | Payroll Burden | PR | 1029 | 08/29/18 | 08/31/18 | HO14 | Holmes, Anthony R | 0 | 0 | 0 | 0 | 496.72 |  | 0 | 0
995 | Payroll Burden | PR | 1034 | 08/29/18 | 08/31/18 | LE17 | Lee, Ha Nul | 0 | 0 | 0 | 0 | 301.58 |  | 0 | 0
995 | Payroll Burden | PR | 1036 | 08/29/18 | 08/31/18 | LO58 | Lopez Reyes, Boris O | 0 | 0 | 0 | 0 | 127.73 |  | 0 | 0
995 | Payroll Burden | PR | 1040 | 08/29/18 | 08/31/18 | ME52 | Mendoza, Edgar E | 0 | 0 | 0 | 0 | 312.22 |  | 0 | 0
995 | Payroll Burden | PR | 1059 | 08/29/18 | 08/31/18 | TA96 | Taylor, Evan R | 0 | 0 | 0 | 0 | 415.12 |  | 0 | 0
995 | Payroll Burden | PR | 1059 | 08/29/18 | 08/31/18 | TA96 | Taylor, Evan R | 0 | 0 | 0 | 0 | 10.64 |  | 0 | 0
995 | Payroll Burden | PR | 1063 | 08/29/18 | 08/31/18 | WE55 | Wennig, Johnathan M | 0 | 0 | 0 | 0 | 496.72 |  | 0 | 0
995 | Payroll Burden | PR | 1069 | 08/29/18 | 08/31/18 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 27.72 |  | 0 | 0
995 | Payroll Burden | PR | 41 | 09/05/18 | 09/07/18 | BA70 | Barnhart, Joseph N | 0 | 0 | 0 | 0 | 102.01 |  | 0 | 0
995 | Payroll Burden | PR | 68 | 09/05/18 | 09/07/18 | HO14 | Holmes, Anthony R | 0 | 0 | 0 | 0 | 496.72 |  | 0 | 0
995 | Payroll Burden | PR | 73 | 09/05/18 | 09/07/18 | LE17 | Lee, Ha Nul | 0 | 0 | 0 | 0 | 241.26 |  | 0 | 0
995 | Payroll Burden | PR | 76 | 09/05/18 | 09/07/18 | LO58 | Lopez Reyes, Boris O | 0 | 0 | 0 | 0 | 255.46 |  | 0 | 0
995 | Payroll Burden | PR | 80 | 09/05/18 | 09/07/18 | ME52 | Mendoza, Edgar E | 0 | 0 | 0 | 0 | 312.22 |  | 0 | 0
995 | Payroll Burden | PR | 99 | 09/05/18 | 09/07/18 | TA96 | Taylor, Evan R | 0 | 0 | 0 | 0 | 255.46 |  | 0 | 0
995 | Payroll Burden | PR | 103 | 09/05/18 | 09/07/18 | WE55 | Wennig, Johnathan M | 0 | 0 | 0 | 0 | 397.38 |  | 0 | 0
995 | Payroll Burden | PR | 106 | 09/05/18 | 09/07/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 22.18 |  | 0 | 0
995 | Payroll Burden | PR | 106 | 09/05/18 | 09/07/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 22.18 |  | 0 | 0
995 | Payroll Burden | PR | 300 | 09/12/18 | 09/14/18 | HO14 | Holmes, Anthony R | 0 | 0 | 0 | 0 | 620.9 |  | 0 | 0
995 | Payroll Burden | PR | 305 | 09/12/18 | 09/14/18 | LE17 | Lee, Ha Nul | 0 | 0 | 0 | 0 | 301.58 |  | 0 | 0
995 | Payroll Burden | PR | 307 | 09/12/18 | 09/14/18 | LO58 | Lopez Reyes, Boris O | 0 | 0 | 0 | 0 | 319.32 |  | 0 | 0
995 | Payroll Burden | PR | 312 | 09/12/18 | 09/14/18 | ME52 | Mendoza, Edgar E | 0 | 0 | 0 | 0 | 390.28 |  | 0 | 0
995 | Payroll Burden | PR | 332 | 09/12/18 | 09/14/18 | TA96 | Taylor, Evan R | 0 | 0 | 0 | 0 | 425.76 |  | 0 | 0
995 | Payroll Burden | PR | 336 | 09/12/18 | 09/14/18 | WE55 | Wennig, Johnathan M | 0 | 0 | 0 | 0 | 496.72 |  | 0 | 0
995 | Payroll Burden | PR | 340 | 09/12/18 | 09/14/18 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 110.88 |  | 0 | 0
995 | Payroll Burden | PR | 341 | 09/12/18 | 09/14/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 66.53 |  | 0 | 0
995 | Payroll Burden | PR | 341 | 09/12/18 | 09/14/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 44.35 |  | 0 | 0
995 | Payroll Burden | PR | 513 | 09/19/18 | 09/21/18 | HO14 | Holmes, Anthony R | 0 | 0 | 0 | 0 | 496.72 |  | 0 | 0
995 | Payroll Burden | PR | 518 | 09/19/18 | 09/21/18 | LE17 | Lee, Ha Nul | 0 | 0 | 0 | 0 | 301.58 |  | 0 | 0
995 | Payroll Burden | PR | 520 | 09/19/18 | 09/21/18 | LO58 | Lopez Reyes, Boris O | 0 | 0 | 0 | 0 | 255.46 |  | 0 | 0
995 | Payroll Burden | PR | 525 | 09/19/18 | 09/21/18 | ME52 | Mendoza, Edgar E | 0 | 0 | 0 | 0 | 390.28 |  | 0 | 0
995 | Payroll Burden | PR | 545 | 09/19/18 | 09/21/18 | TA96 | Taylor, Evan R | 0 | 0 | 0 | 0 | 425.76 |  | 0 | 0
995 | Payroll Burden | PR | 549 | 09/19/18 | 09/21/18 | WE55 | Wennig, Johnathan M | 0 | 0 | 0 | 0 | 496.72 |  | 0 | 0
995 | Payroll Burden | PR | 552 | 09/19/18 | 09/21/18 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 83.16 |  | 0 | 0
995 | Payroll Burden | PR | 553 | 09/19/18 | 09/21/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 44.35 |  | 0 | 0
995 | Payroll Burden | PR | 553 | 09/19/18 | 09/21/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 22.18 |  | 0 | 0
995 | Payroll Burden | PR | 670 | 09/26/18 | 09/28/18 | BA70 | Barnhart, Joseph N | 0 | 0 | 0 | 0 | 81.6 |  | 0 | 0
995 | Payroll Burden | PR | 698 | 09/26/18 | 09/28/18 | HO14 | Holmes, Anthony R | 0 | 0 | 0 | 0 | 620.9 |  | 0 | 0
995 | Payroll Burden | PR | 703 | 09/26/18 | 09/28/18 | LE17 | Lee, Ha Nul | 0 | 0 | 0 | 0 | 301.58 |  | 0 | 0
995 | Payroll Burden | PR | 705 | 09/26/18 | 09/28/18 | LO58 | Lopez Reyes, Boris O | 0 | 0 | 0 | 0 | 315.33 |  | 0 | 0
995 | Payroll Burden | PR | 710 | 09/26/18 | 09/28/18 | ME52 | Mendoza, Edgar E | 0 | 0 | 0 | 0 | 380.52 |  | 0 | 0
995 | Payroll Burden | PR | 731 | 09/26/18 | 09/28/18 | TA96 | Taylor, Evan R | 0 | 0 | 0 | 0 | 425.76 |  | 0 | 0
995 | Payroll Burden | PR | 735 | 09/26/18 | 09/28/18 | WE55 | Wennig, Johnathan M | 0 | 0 | 0 | 0 | 496.72 |  | 0 | 0
995 | Payroll Burden | PR | 739 | 09/26/18 | 09/28/18 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 27.72 |  | 0 | 0
995 | Payroll Burden | PR | 34 | 10/03/18 | 10/05/18 | BA70 | Barnhart, Joseph N | 0 | 0 | 0 | 0 | 81.6 |  | 0 | 0
995 | Payroll Burden | PR | 62 | 10/03/18 | 10/05/18 | HO14 | Holmes, Anthony R | 0 | 0 | 0 | 0 | 620.9 |  | 0 | 0
995 | Payroll Burden | PR | 67 | 10/03/18 | 10/05/18 | LE17 | Lee, Ha Nul | 0 | 0 | 0 | 0 | 288.39 |  | 0 | 0
995 | Payroll Burden | PR | 69 | 10/03/18 | 10/05/18 | LO58 | Lopez Reyes, Boris O | 0 | 0 | 0 | 0 | 255.46 |  | 0 | 0
995 | Payroll Burden | PR | 74 | 10/03/18 | 10/05/18 | ME52 | Mendoza, Edgar E | 0 | 0 | 0 | 0 | 375.64 |  | 0 | 0
995 | Payroll Burden | PR | 95 | 10/03/18 | 10/05/18 | TA96 | Taylor, Evan R | 0 | 0 | 0 | 0 | 340.61 |  | 0 | 0
995 | Payroll Burden | PR | 99 | 10/03/18 | 10/05/18 | WE55 | Wennig, Johnathan M | 0 | 0 | 0 | 0 | 496.72 |  | 0 | 0
995 | Payroll Burden | PR | 102 | 10/03/18 | 10/05/18 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 13.86 |  | 0 | 0
995 | Payroll Burden | PR | 239 | 10/10/18 | 10/12/18 | BA70 | Barnhart, Joseph N | 0 | 0 | 0 | 0 | 40.8 |  | 0 | 0
995 | Payroll Burden | PR | 268 | 10/10/18 | 10/12/18 | HO14 | Holmes, Anthony R | 0 | 0 | 0 | 0 | 620.9 |  | 0 | 0
995 | Payroll Burden | PR | 273 | 10/10/18 | 10/12/18 | LE17 | Lee, Ha Nul | 0 | 0 | 0 | 0 | 180.95 |  | 0 | 0
995 | Payroll Burden | PR | 273 | 10/10/18 | 10/12/18 | LE17 | Lee, Ha Nul | 0 | 0 | 0 | 0 | 120.63 |  | 0 | 0
995 | Payroll Burden | PR | 275 | 10/10/18 | 10/12/18 | LO58 | Lopez Reyes, Boris O | 0 | 0 | 0 | 0 | 255.46 |  | 0 | 0
995 | Payroll Burden | PR | 280 | 10/10/18 | 10/12/18 | ME52 | Mendoza, Edgar E | 0 | 0 | 0 | 0 | 390.28 |  | 0 | 0
995 | Payroll Burden | PR | 301 | 10/10/18 | 10/12/18 | TA96 | Taylor, Evan R | 0 | 0 | 0 | 0 | 425.76 |  | 0 | 0
995 | Payroll Burden | PR | 305 | 10/10/18 | 10/12/18 | WE55 | Wennig, Johnathan M | 0 | 0 | 0 | 0 | 496.72 |  | 0 | 0
995 | Payroll Burden | PR | 310 | 10/10/18 | 10/12/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 22.18 |  | 0 | 0
995 | Payroll Burden | PR | 438 | 10/17/18 | 10/19/18 | BA70 | Barnhart, Joseph N | 0 | 0 | 0 | 0 | 20.4 |  | 0 | 0
995 | Payroll Burden | PR | 466 | 10/17/18 | 10/19/18 | HO14 | Holmes, Anthony R | 0 | 0 | 0 | 0 | 620.9 |  | 0 | 0
995 | Payroll Burden | PR | 471 | 10/17/18 | 10/19/18 | LE17 | Lee, Ha Nul | 0 | 0 | 0 | 0 | 301.58 |  | 0 | 0
995 | Payroll Burden | PR | 473 | 10/17/18 | 10/19/18 | LO58 | Lopez Reyes, Boris O | 0 | 0 | 0 | 0 | 275.41 |  | 0 | 0
995 | Payroll Burden | PR | 478 | 10/17/18 | 10/19/18 | ME52 | Mendoza, Edgar E | 0 | 0 | 0 | 0 | 390.28 |  | 0 | 0
995 | Payroll Burden | PR | 499 | 10/17/18 | 10/19/18 | TA96 | Taylor, Evan R | 0 | 0 | 0 | 0 | 372.54 |  | 0 | 0
995 | Payroll Burden | PR | 504 | 10/17/18 | 10/19/18 | WE55 | Wennig, Johnathan M | 0 | 0 | 0 | 0 | 397.38 |  | 0 | 0
995 | Payroll Burden | PR | 733 | 10/24/18 | 10/26/18 | HO14 | Holmes, Anthony R | 0 | 0 | 0 | 0 | 620.9 |  | 0 | 0
995 | Payroll Burden | PR | 737 | 10/24/18 | 10/26/18 | LE17 | Lee, Ha Nul | 0 | 0 | 0 | 0 | 218.65 |  | 0 | 0
995 | Payroll Burden | PR | 739 | 10/24/18 | 10/26/18 | LO58 | Lopez Reyes, Boris O | 0 | 0 | 0 | 0 | 255.46 |  | 0 | 0
995 | Payroll Burden | PR | 744 | 10/24/18 | 10/26/18 | ME52 | Mendoza, Edgar E | 0 | 0 | 0 | 0 | 312.22 |  | 0 | 0
995 | Payroll Burden | PR | 765 | 10/24/18 | 10/26/18 | TA96 | Taylor, Evan R | 0 | 0 | 0 | 0 | 425.76 |  | 0 | 0
995 | Payroll Burden | PR | 770 | 10/24/18 | 10/26/18 | WE55 | Wennig, Johnathan M | 0 | 0 | 0 | 0 | 298.03 |  | 0 | 0
995 | Payroll Burden | PR | 775 | 10/24/18 | 10/26/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 22.18 |  | 0 | 0
995 | Payroll Burden | PR | 37 | 10/31/18 | 11/02/18 | HO14 | Holmes, Anthony R | 0 | 0 | 0 | 0 | 620.9 |  | 0 | 0
995 | Payroll Burden | PR | 42 | 10/31/18 | 11/02/18 | LE17 | Lee, Ha Nul | 0 | 0 | 0 | 0 | 301.58 |  | 0 | 0
995 | Payroll Burden | PR | 44 | 10/31/18 | 11/02/18 | LO58 | Lopez Reyes, Boris O | 0 | 0 | 0 | 0 | 255.46 |  | 0 | 0
995 | Payroll Burden | PR | 49 | 10/31/18 | 11/02/18 | ME52 | Mendoza, Edgar E | 0 | 0 | 0 | 0 | 370.77 |  | 0 | 0
995 | Payroll Burden | PR | 68 | 10/31/18 | 11/02/18 | TA96 | Taylor, Evan R | 0 | 0 | 0 | 0 | 425.76 |  | 0 | 0
995 | Payroll Burden | PR | 76 | 10/31/18 | 11/02/18 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 27.72 |  | 0 | 0
995 | Payroll Burden | PR | 215 | 11/07/18 | 11/09/18 | HO14 | Holmes, Anthony R | 0 | 0 | 0 | 0 | 620.9 |  | 0 | 0
995 | Payroll Burden | PR | 220 | 11/07/18 | 11/09/18 | LE17 | Lee, Ha Nul | 0 | 0 | 0 | 0 | 301.58 |  | 0 | 0
995 | Payroll Burden | PR | 222 | 11/07/18 | 11/09/18 | LO58 | Lopez Reyes, Boris O | 0 | 0 | 0 | 0 | 291.38 |  | 0 | 0
995 | Payroll Burden | PR | 227 | 11/07/18 | 11/09/18 | ME52 | Mendoza, Edgar E | 0 | 0 | 0 | 0 | 312.22 |  | 0 | 0
995 | Payroll Burden | PR | 227 | 11/07/18 | 11/09/18 | ME52 | Mendoza, Edgar E | 0 | 0 | 0 | 0 | 78.06 |  | 0 | 0
995 | Payroll Burden | PR | 248 | 11/07/18 | 11/09/18 | TA96 | Taylor, Evan R | 0 | 0 | 0 | 0 | 425.76 |  | 0 | 0
995 | Payroll Burden | PR | 252 | 11/07/18 | 11/09/18 | WE55 | Wennig, Johnathan M | 0 | 0 | 0 | 0 | 496.72 |  | 0 | 0
995 | Payroll Burden | PR | 257 | 11/07/18 | 11/09/18 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 27.72 |  | 0 | 0
995 | Payroll Burden | PR | 463 | 11/14/18 | 11/16/18 | HO14 | Holmes, Anthony R | 0 | 0 | 0 | 0 | 620.9 |  | 0 | 0
995 | Payroll Burden | PR | 468 | 11/14/18 | 11/16/18 | LE17 | Lee, Ha Nul | 0 | 0 | 0 | 0 | 301.58 |  | 0 | 0
995 | Payroll Burden | PR | 470 | 11/14/18 | 11/16/18 | LO58 | Lopez Reyes, Boris O | 0 | 0 | 0 | 0 | 39.92 |  | 0 | 0
995 | Payroll Burden | PR | 475 | 11/14/18 | 11/16/18 | ME52 | Mendoza, Edgar E | 0 | 0 | 0 | 0 | 312.22 |  | 0 | 0
995 | Payroll Burden | PR | 475 | 11/14/18 | 11/16/18 | ME52 | Mendoza, Edgar E | 0 | 0 | 0 | 0 | 78.06 |  | 0 | 0
995 | Payroll Burden | PR | 496 | 11/14/18 | 11/16/18 | TA96 | Taylor, Evan R | 0 | 0 | 0 | 0 | 425.76 |  | 0 | 0
995 | Payroll Burden | PR | 500 | 11/14/18 | 11/16/18 | WE55 | Wennig, Johnathan M | 0 | 0 | 0 | 0 | 496.72 |  | 0 | 0
995 | Payroll Burden | PR | 514 | 11/14/18 | 11/16/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 22.18 |  | 0 | 0
995 | Payroll Burden | PR | 514 | 11/14/18 | 11/16/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 44.35 |  | 0 | 0
995 | Payroll Burden | PR | 648 | 11/21/18 | 11/21/18 | HO14 | Holmes, Anthony R | 0 | 0 | 0 | 0 | 620.9 |  | 0 | 0
995 | Payroll Burden | PR | 653 | 11/21/18 | 11/21/18 | LE17 | Lee, Ha Nul | 0 | 0 | 0 | 0 | 301.58 |  | 0 | 0
995 | Payroll Burden | PR | 659 | 11/21/18 | 11/21/18 | ME52 | Mendoza, Edgar E | 0 | 0 | 0 | 0 | 390.28 |  | 0 | 0
995 | Payroll Burden | PR | 680 | 11/21/18 | 11/21/18 | TA96 | Taylor, Evan R | 0 | 0 | 0 | 0 | 425.76 |  | 0 | 0
995 | Payroll Burden | PR | 684 | 11/21/18 | 11/21/18 | WE55 | Wennig, Johnathan M | 0 | 0 | 0 | 0 | 496.72 |  | 0 | 0
995 | Payroll Burden | PR | 690 | 11/21/18 | 11/21/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 22.18 |  | 0 | 0
995 | Payroll Burden | PR | 861 | 11/28/18 | 11/30/18 | HO14 | Holmes, Anthony R | 0 | 0 | 0 | 0 | 344.6 |  | 0 | 0
995 | Payroll Burden | PR | 866 | 11/28/18 | 11/30/18 | LE17 | Lee, Ha Nul | 0 | 0 | 0 | 0 | 269.65 |  | 0 | 0
995 | Payroll Burden | PR | 872 | 11/28/18 | 11/30/18 | ME52 | Mendoza, Edgar E | 0 | 0 | 0 | 0 | 340.61 |  | 0 | 0
995 | Payroll Burden | PR | 893 | 11/28/18 | 11/30/18 | TA96 | Taylor, Evan R | 0 | 0 | 0 | 0 | 328.63 |  | 0 | 0
995 | Payroll Burden | PR | 897 | 11/28/18 | 11/30/18 | WE55 | Wennig, Johnathan M | 0 | 0 | 0 | 0 | 279.41 |  | 0 | 0
995 | Payroll Burden | PR | 73 | 12/05/18 | 12/07/18 | HO14 | Holmes, Anthony R | 0 | 0 | 0 | 0 | 656.38 |  | 0 | 0
995 | Payroll Burden | PR | 78 | 12/05/18 | 12/07/18 | LE17 | Lee, Ha Nul | 0 | 0 | 0 | 0 | 337.06 |  | 0 | 0
995 | Payroll Burden | PR | 84 | 12/05/18 | 12/07/18 | ME52 | Mendoza, Edgar E | 0 | 0 | 0 | 0 | 393.83 |  | 0 | 0
995 | Payroll Burden | PR | 105 | 12/05/18 | 12/07/18 | TA96 | Taylor, Evan R | 0 | 0 | 0 | 0 | 461.24 |  | 0 | 0
995 | Payroll Burden | PR | 110 | 12/05/18 | 12/07/18 | WE55 | Wennig, Johnathan M | 0 | 0 | 0 | 0 | 532.2 |  | 0 | 0
995 | Payroll Burden | PR | 270 | 12/12/18 | 12/14/18 | BA70 | Barnhart, Joseph N | 0 | 0 | 0 | 0 | 42.58 |  | 0 | 0
995 | Payroll Burden | PR | 297 | 12/12/18 | 12/14/18 | HO14 | Holmes, Anthony R | 0 | 0 | 0 | 0 | 656.38 |  | 0 | 0
995 | Payroll Burden | PR | 302 | 12/12/18 | 12/14/18 | LE17 | Lee, Ha Nul | 0 | 0 | 0 | 0 | 337.06 |  | 0 | 0
995 | Payroll Burden | PR | 308 | 12/12/18 | 12/14/18 | ME52 | Mendoza, Edgar E | 0 | 0 | 0 | 0 | 425.76 |  | 0 | 0
995 | Payroll Burden | PR | 330 | 12/12/18 | 12/14/18 | TA96 | Taylor, Evan R | 0 | 0 | 0 | 0 | 184.5 |  | 0 | 0
995 | Payroll Burden | PR | 335 | 12/12/18 | 12/14/18 | WE55 | Wennig, Johnathan M | 0 | 0 | 0 | 0 | 212.88 |  | 0 | 0
995 | Payroll Burden | PR | 338 | 12/12/18 | 12/14/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 23.06 |  | 0 | 0
995 | Payroll Burden | PR | 538 | 12/19/18 | 12/21/18 | HO14 | Holmes, Anthony R | 0 | 0 | 0 | 0 | 656.38 |  | 0 | 0
995 | Payroll Burden | PR | 543 | 12/19/18 | 12/21/18 | LE17 | Lee, Ha Nul | 0 | 0 | 0 | 0 | 404.47 |  | 0 | 0
995 | Payroll Burden | PR | 549 | 12/19/18 | 12/21/18 | ME52 | Mendoza, Edgar E | 0 | 0 | 0 | 0 | 510.91 |  | 0 | 0
995 | Payroll Burden | PR | 570 | 12/19/18 | 12/21/18 | TA96 | Taylor, Evan R | 0 | 0 | 0 | 0 | 138.37 |  | 0 | 0
995 | Payroll Burden | PR | 570 | 12/19/18 | 12/21/18 | TA96 | Taylor, Evan R | 0 | 0 | 0 | 0 | 461.24 |  | 0 | 0
995 | Payroll Burden | PR | 575 | 12/19/18 | 12/21/18 | WE55 | Wennig, Johnathan M | 0 | 0 | 0 | 0 | 638.64 |  | 0 | 0
995 | Payroll Burden | PR | 577 | 12/19/18 | 12/21/18 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 27.72 |  | 0 | 0
995 | Payroll Burden | PR | 578 | 12/19/18 | 12/21/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 46.12 |  | 0 | 0
995 | Payroll Burden | PR | 729 | 12/26/18 | 12/28/18 | HO14 | Holmes, Anthony R | 0 | 0 | 0 | 0 | 393.83 |  | 0 | 0
995 | Payroll Burden | PR | 734 | 12/26/18 | 12/28/18 | LE17 | Lee, Ha Nul | 0 | 0 | 0 | 0 | 202.24 |  | 0 | 0
995 | Payroll Burden | PR | 740 | 12/26/18 | 12/28/18 | ME52 | Mendoza, Edgar E | 0 | 0 | 0 | 0 | 239.49 |  | 0 | 0
995 | Payroll Burden | PR | 761 | 12/26/18 | 12/28/18 | TA96 | Taylor, Evan R | 0 | 0 | 0 | 0 | 184.5 |  | 0 | 0
995 | Payroll Burden | PR | 766 | 12/26/18 | 12/28/18 | WE55 | Wennig, Johnathan M | 0 | 0 | 0 | 0 | 212.88 |  | 0 | 0
995 | Payroll Burden | PR | 768 | 12/26/18 | 12/28/18 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 55.44 |  | 0 | 0
995 | Payroll Burden | PR | 33 | 01/02/19 | 01/04/19 | HO14 | Holmes, Anthony R | 0 | 0 | 0 | 0 | 525.1 |  | 0 | 0
995 | Payroll Burden | PR | 37 | 01/02/19 | 01/04/19 | LE17 | Lee, Ha Nul | 0 | 0 | 0 | 0 | 202.24 |  | 0 | 0
995 | Payroll Burden | PR | 43 | 01/02/19 | 01/04/19 | ME52 | Mendoza, Edgar E | 0 | 0 | 0 | 0 | 239.49 |  | 0 | 0
995 | Payroll Burden | PR | 64 | 01/02/19 | 01/04/19 | TA96 | Taylor, Evan R | 0 | 0 | 0 | 0 | 276.74 |  | 0 | 0
995 | Payroll Burden | PR | 69 | 01/02/19 | 01/04/19 | WE55 | Wennig, Johnathan M | 0 | 0 | 0 | 0 | 319.32 |  | 0 | 0
995 | Payroll Burden | PR | 73 | 01/02/19 | 01/04/19 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 23.06 |  | 0 | 0
995 | Payroll Burden | PR | 241 | 01/09/19 | 01/11/19 | HO14 | Holmes, Anthony R | 0 | 0 | 0 | 0 | 656.38 |  | 0 | 0
995 | Payroll Burden | PR | 244 | 01/09/19 | 01/11/19 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 86.93 |  | 0 | 0
995 | Payroll Burden | PR | 253 | 01/09/19 | 01/11/19 | ME52 | Mendoza, Edgar E | 0 | 0 | 0 | 0 | 74.51 |  | 0 | 0
995 | Payroll Burden | PR | 274 | 01/09/19 | 01/11/19 | TA96 | Taylor, Evan R | 0 | 0 | 0 | 0 | 461.24 |  | 0 | 0
995 | Payroll Burden | PR | 279 | 01/09/19 | 01/11/19 | WE55 | Wennig, Johnathan M | 0 | 0 | 0 | 0 | 532.2 |  | 0 | 0
995 | Payroll Burden | PR | 282 | 01/09/19 | 01/11/19 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 23.06 |  | 0 | 0
995 | Payroll Burden | PR | 282 | 01/09/19 | 01/11/19 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 23.06 |  | 0 | 0
995 | Payroll Burden | PR | 496 | 01/16/19 | 01/18/19 | HO14 | Holmes, Anthony R | 0 | 0 | 0 | 0 | 656.38 |  | 0 | 0
995 | Payroll Burden | PR | 529 | 01/16/19 | 01/18/19 | TA96 | Taylor, Evan R | 0 | 0 | 0 | 0 | 461.24 |  | 0 | 0
995 | Payroll Burden | PR | 534 | 01/16/19 | 01/18/19 | WE55 | Wennig, Johnathan M | 0 | 0 | 0 | 0 | 532.2 |  | 0 | 0
995 | Payroll Burden | PR | 745 | 01/23/19 | 01/25/19 | HO14 | Holmes, Anthony R | 0 | 0 | 0 | 0 | 656.38 |  | 0 | 0
995 | Payroll Burden | PR | 778 | 01/23/19 | 01/25/19 | TA96 | Taylor, Evan R | 0 | 0 | 0 | 0 | 461.24 |  | 0 | 0
995 | Payroll Burden | PR | 783 | 01/23/19 | 01/25/19 | WE55 | Wennig, Johnathan M | 0 | 0 | 0 | 0 | 425.76 |  | 0 | 0
995 | Payroll Burden | PR | 33 | 01/30/19 | 02/01/19 | HO14 | Holmes, Anthony R | 0 | 0 | 0 | 0 | 656.38 |  | 0 | 0
995 | Payroll Burden | PR | 63 | 01/30/19 | 02/01/19 | TA96 | Taylor, Evan R | 0 | 0 | 0 | 0 | 461.24 |  | 0 | 0
995 | Payroll Burden | PR | 68 | 01/30/19 | 02/01/19 | WE55 | Wennig, Johnathan M | 0 | 0 | 0 | 0 | 212.88 |  | 0 | 0
995 | Payroll Burden | PR | 188 | 02/06/19 | 02/08/19 | HO14 | Holmes, Anthony R | 0 | 0 | 0 | 0 | 131.28 |  | 0 | 0
995 | Payroll Burden | PR | 188 | 02/06/19 | 02/08/19 | HO14 | Holmes, Anthony R | 0 | 0 | 0 | 0 | 254.35 |  | 0 | 0
995 | Payroll Burden | PR | 191 | 02/06/19 | 02/08/19 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 43.46 |  | 0 | 0
995 | Payroll Burden | PR | 219 | 02/06/19 | 02/08/19 | TA96 | Taylor, Evan R | 0 | 0 | 0 | 0 | 276.74 |  | 0 | 0
995 | Payroll Burden | PR | 350 | 02/13/19 | 02/15/19 | HO14 | Holmes, Anthony R | 0 | 0 | 0 | 0 | 164.1 |  | 0 | 0
995 | Payroll Burden | PR | 350 | 02/13/19 | 02/15/19 | HO14 | Holmes, Anthony R | 0 | 0 | 0 | 0 | 246.14 |  | 0 | 0
995 | Payroll Burden | PR | 353 | 02/13/19 | 02/15/19 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 54.33 |  | 0 | 0
995 | Payroll Burden | PR | 381 | 02/13/19 | 02/15/19 | TA96 | Taylor, Evan R | 0 | 0 | 0 | 0 | 115.31 |  | 0 | 0
995 | Payroll Burden | PR | 381 | 02/13/19 | 02/15/19 | TA96 | Taylor, Evan R | 0 | 0 | 0 | 0 | 172.97 |  | 0 | 0
995 | Payroll Burden | PR | 608 | 02/20/19 | 02/22/19 | HO14 | Holmes, Anthony R | 0 | 0 | 0 | 0 | 639.97 |  | 0 | 0
995 | Payroll Burden | PR | 640 | 02/20/19 | 02/22/19 | TA96 | Taylor, Evan R | 0 | 0 | 0 | 0 | 461.24 |  | 0 | 0
995 | Payroll Burden | PR | 35 | 02/27/19 | 03/01/19 | HO14 | Holmes, Anthony R | 0 | 0 | 0 | 0 | 656.38 |  | 0 | 0
995 | Payroll Burden | PR | 67 | 02/27/19 | 03/01/19 | TA96 | Taylor, Evan R | 0 | 0 | 0 | 0 | 461.24 |  | 0 | 0
995 | Payroll Burden | PR | 75 | 02/27/19 | 03/01/19 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 46.12 |  | 0 | 0
995 | Payroll Burden | PR | 75 | 02/27/19 | 03/01/19 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 46.12 |  | 0 | 0
995 | Payroll Burden | PR | 249 | 03/06/19 | 03/08/19 | BA70 | Barnhart, Joseph N | 0 | 0 | 0 | 0 | 42.58 |  | 0 | 0
995 | Payroll Burden | PR | 260 | 03/06/19 | 03/08/19 | CR87 | Cruz Reyes, Jose | 0 | 0 | 0 | 0 | 507.36 |  | 0 | 0
995 | Payroll Burden | PR | 275 | 03/06/19 | 03/08/19 | HO14 | Holmes, Anthony R | 0 | 0 | 0 | 0 | 147.69 |  | 0 | 0
995 | Payroll Burden | PR | 275 | 03/06/19 | 03/08/19 | HO14 | Holmes, Anthony R | 0 | 0 | 0 | 0 | 525.1 |  | 0 | 0
995 | Payroll Burden | PR | 275 | 03/06/19 | 03/08/19 | HO14 | Holmes, Anthony R | 0 | 0 | 0 | 0 | 131.28 |  | 0 | 0
995 | Payroll Burden | PR | 278 | 03/06/19 | 03/08/19 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 108.66 |  | 0 | 0
995 | Payroll Burden | PR | 289 | 03/06/19 | 03/08/19 | MU70 | Murphy, Darray E | 0 | 0 | 0 | 0 | 71.85 |  | 0 | 0
995 | Payroll Burden | PR | 289 | 03/06/19 | 03/08/19 | MU70 | Murphy, Darray E | 0 | 0 | 0 | 0 | 319.32 |  | 0 | 0
995 | Payroll Burden | PR | 315 | 03/06/19 | 03/08/19 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 23.06 |  | 0 | 0
995 | Payroll Burden | PR | 315 | 03/06/19 | 03/08/19 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 46.12 |  | 0 | 0
995 | Payroll Burden | PR | 507 | 03/13/19 | 03/15/19 | CR87 | Cruz Reyes, Jose | 0 | 0 | 0 | 0 | 51.89 |  | 0 | 0
995 | Payroll Burden | PR | 507 | 03/13/19 | 03/15/19 | CR87 | Cruz Reyes, Jose | 0 | 0 | 0 | 0 | 518.9 |  | 0 | 0
995 | Payroll Burden | PR | 522 | 03/13/19 | 03/15/19 | HO14 | Holmes, Anthony R | 0 | 0 | 0 | 0 | 196.91 |  | 0 | 0
995 | Payroll Burden | PR | 522 | 03/13/19 | 03/15/19 | HO14 | Holmes, Anthony R | 0 | 0 | 0 | 0 | 656.38 |  | 0 | 0
995 | Payroll Burden | PR | 536 | 03/13/19 | 03/15/19 | MU70 | Murphy, Darray E | 0 | 0 | 0 | 0 | 143.69 |  | 0 | 0
995 | Payroll Burden | PR | 721 | 03/20/19 | 03/22/19 | CR87 | Cruz Reyes, Jose | 0 | 0 | 0 | 0 | 138.37 |  | 0 | 0
995 | Payroll Burden | PR | 721 | 03/20/19 | 03/22/19 | CR87 | Cruz Reyes, Jose | 0 | 0 | 0 | 0 | 461.24 |  | 0 | 0
995 | Payroll Burden | PR | 736 | 03/20/19 | 03/22/19 | HO14 | Holmes, Anthony R | 0 | 0 | 0 | 0 | 196.91 |  | 0 | 0
995 | Payroll Burden | PR | 736 | 03/20/19 | 03/22/19 | HO14 | Holmes, Anthony R | 0 | 0 | 0 | 0 | 656.38 |  | 0 | 0
995 | Payroll Burden | PR | 776 | 03/20/19 | 03/22/19 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 27.72 |  | 0 | 0
995 | Payroll Burden | PR | 777 | 03/20/19 | 03/22/19 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 23.06 |  | 0 | 0
995 | Payroll Burden | PR | 932 | 03/27/19 | 03/29/19 | CR87 | Cruz Reyes, Jose | 0 | 0 | 0 | 0 | 69.19 |  | 0 | 0
995 | Payroll Burden | PR | 932 | 03/27/19 | 03/29/19 | CR87 | Cruz Reyes, Jose | 0 | 0 | 0 | 0 | 34.59 |  | 0 | 0
995 | Payroll Burden | PR | 932 | 03/27/19 | 03/29/19 | CR87 | Cruz Reyes, Jose | 0 | 0 | 0 | 0 | 368.99 |  | 0 | 0
995 | Payroll Burden | PR | 932 | 03/27/19 | 03/29/19 | CR87 | Cruz Reyes, Jose | 0 | 0 | 0 | 0 | 92.25 |  | 0 | 0
995 | Payroll Burden | PR | 948 | 03/27/19 | 03/29/19 | HO14 | Holmes, Anthony R | 0 | 0 | 0 | 0 | 319.99 |  | 0 | 0
995 | Payroll Burden | PR | 948 | 03/27/19 | 03/29/19 | HO14 | Holmes, Anthony R | 0 | 0 | 0 | 0 | 49.23 |  | 0 | 0
995 | Payroll Burden | PR | 948 | 03/27/19 | 03/29/19 | HO14 | Holmes, Anthony R | 0 | 0 | 0 | 0 | 525.1 |  | 0 | 0
995 | Payroll Burden | PR | 948 | 03/27/19 | 03/29/19 | HO14 | Holmes, Anthony R | 0 | 0 | 0 | 0 | 131.28 |  | 0 | 0
995 | Payroll Burden | PR | 111 | 04/03/19 | 04/05/19 | HO14 | Holmes, Anthony R | 0 | 0 | 0 | 0 | 49.23 |  | 0 | 0
995 | Payroll Burden | PR | 111 | 04/03/19 | 04/05/19 | HO14 | Holmes, Anthony R | 0 | 0 | 0 | 0 | 262.55 |  | 0 | 0
995 | Payroll Burden | PR | 524 | 04/17/19 | 04/19/19 | BA70 | Barnhart, Joseph N | 0 | 0 | 0 | 0 | 66.53 |  | 0 | 0
995 | Payroll Burden | PR | 555 | 04/17/19 | 04/19/19 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 44.35 |  | 0 | 0
995 | Payroll Burden | PR | 564 | 04/17/19 | 04/19/19 | MC09 | McCabe, Thomas C | 0 | 0 | 0 | 0 | 117.08 |  | 0 | 0
995 | Payroll Burden | PR | 771 | 04/24/19 | 04/26/19 | HO14 | Holmes, Anthony R | 0 | 0 | 0 | 0 | 212.88 |  | 0 | 0
995 | Payroll Burden | PR | 771 | 04/24/19 | 04/26/19 | HO14 | Holmes, Anthony R | 0 | 0 | 0 | 0 | 35.48 |  | 0 | 0
995 | Payroll Burden | PR | 774 | 04/24/19 | 04/26/19 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 88.7 |  | 0 | 0
995 | Payroll Burden | PR | 783 | 04/24/19 | 04/26/19 | MC09 | McCabe, Thomas C | 0 | 0 | 0 | 0 | 116.42 |  | 0 | 0
995 | Payroll Burden | PR | 783 | 04/24/19 | 04/26/19 | MC09 | McCabe, Thomas C | 0 | 0 | 0 | 0 | 325.97 |  | 0 | 0
995 | Payroll Burden | PR | 783 | 04/24/19 | 04/26/19 | MC09 | McCabe, Thomas C | 0 | 0 | 0 | 0 | 294.93 |  | 0 | 0
995 | Payroll Burden | PR | 797 | 04/24/19 | 04/26/19 | SA54 | Sanders, Allen O | 0 | 0 | 0 | 0 | 54.33 |  | 0 | 0
995 | Payroll Burden | PR | 799 | 04/24/19 | 04/26/19 | SE64 | Sepulveda Gonzalez, Alfredo | 0 | 0 | 0 | 0 | 372.54 |  | 0 | 0
995 | Payroll Burden | PR | 812 | 04/24/19 | 04/26/19 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 55.44 |  | 0 | 0
995 | Payroll Burden | PR | 39 | 05/01/19 | 05/03/19 | HO14 | Holmes, Anthony R | 0 | 0 | 0 | 0 | 26.61 |  | 0 | 0
995 | Payroll Burden | PR | 39 | 05/01/19 | 05/03/19 | HO14 | Holmes, Anthony R | 0 | 0 | 0 | 0 | 62.09 |  | 0 | 0
995 | Payroll Burden | PR | 42 | 05/01/19 | 05/03/19 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 133.05 |  | 0 | 0
995 | Payroll Burden | PR | 42 | 05/01/19 | 05/03/19 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 44.35 |  | 0 | 0
995 | Payroll Burden | PR | 45 | 05/01/19 | 05/03/19 | KI55 | Kinssies, Jr, John E | 0 | 0 | 0 | 0 | 99.34 |  | 0 | 0
995 | Payroll Burden | PR | 52 | 05/01/19 | 05/03/19 | MC09 | McCabe, Thomas C | 0 | 0 | 0 | 0 | 186.27 |  | 0 | 0
995 | Payroll Burden | PR | 52 | 05/01/19 | 05/03/19 | MC09 | McCabe, Thomas C | 0 | 0 | 0 | 0 | 372.54 |  | 0 | 0
995 | Payroll Burden | PR | 52 | 05/01/19 | 05/03/19 | MC09 | McCabe, Thomas C | 0 | 0 | 0 | 0 | 248.36 |  | 0 | 0
995 | Payroll Burden | PR | 66 | 05/01/19 | 05/03/19 | SA54 | Sanders, Allen O | 0 | 0 | 0 | 0 | 141.25 |  | 0 | 0
995 | Payroll Burden | PR | 68 | 05/01/19 | 05/03/19 | SE64 | Sepulveda Gonzalez, Alfredo | 0 | 0 | 0 | 0 | 186.27 |  | 0 | 0
995 | Payroll Burden | PR | 68 | 05/01/19 | 05/03/19 | SE64 | Sepulveda Gonzalez, Alfredo | 0 | 0 | 0 | 0 | 310.45 |  | 0 | 0
995 | Payroll Burden | PR | 70 | 05/01/19 | 05/03/19 | ST02 | Stahlschmidt, John P | 0 | 0 | 0 | 0 | 67.41 |  | 0 | 0
995 | Payroll Burden | PR | 73 | 05/01/19 | 05/03/19 | TR60 | Trower-Kelly, Fidel D | 0 | 0 | 0 | 0 | 127.73 |  | 0 | 0
995 | Payroll Burden | PR | 74 | 05/01/19 | 05/03/19 | VA98 | Vazquez Popoca, Jose N | 0 | 0 | 0 | 0 | 170.3 |  | 0 | 0
995 | Payroll Burden | PR | 81 | 05/01/19 | 05/03/19 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 55.44 |  | 0 | 0
995 | Payroll Burden | PR | 195 | 05/08/19 | 05/10/19 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 221.75 |  | 0 | 0
995 | Payroll Burden | PR | 195 | 05/08/19 | 05/10/19 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 44.35 |  | 0 | 0
995 | Payroll Burden | PR | 198 | 05/08/19 | 05/10/19 | KI55 | Kinssies, Jr, John E | 0 | 0 | 0 | 0 | 248.36 |  | 0 | 0
995 | Payroll Burden | PR | 205 | 05/08/19 | 05/10/19 | MC09 | McCabe, Thomas C | 0 | 0 | 0 | 0 | 589.86 |  | 0 | 0
995 | Payroll Burden | PR | 215 | 05/08/19 | 05/10/19 | RO06 | Roberts, Lake A | 0 | 0 | 0 | 0 | 97.57 |  | 0 | 0
995 | Payroll Burden | PR | 219 | 05/08/19 | 05/10/19 | SA54 | Sanders, Allen O | 0 | 0 | 0 | 0 | 130.39 |  | 0 | 0
995 | Payroll Burden | PR | 223 | 05/08/19 | 05/10/19 | ST02 | Stahlschmidt, John P | 0 | 0 | 0 | 0 | 67.41 |  | 0 | 0
995 | Payroll Burden | PR | 226 | 05/08/19 | 05/10/19 | TR60 | Trower-Kelly, Fidel D | 0 | 0 | 0 | 0 | 191.59 |  | 0 | 0
995 | Payroll Burden | PR | 227 | 05/08/19 | 05/10/19 | VA98 | Vazquez Popoca, Jose N | 0 | 0 | 0 | 0 | 227.07 |  | 0 | 0
995 | Payroll Burden | PR | 411 | 05/15/19 | 05/17/19 | EL33 | Eliassen, Cory H | 0 | 0 | 0 | 0 | 95.8 |  | 0 | 0
995 | Payroll Burden | PR | 427 | 05/15/19 | 05/17/19 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 199.58 |  | 0 | 0
995 | Payroll Burden | PR | 430 | 05/15/19 | 05/17/19 | KI55 | Kinssies, Jr, John E | 0 | 0 | 0 | 0 | 347.7 |  | 0 | 0
995 | Payroll Burden | PR | 437 | 05/15/19 | 05/17/19 | MC09 | McCabe, Thomas C | 0 | 0 | 0 | 0 | 547.17 |  | 0 | 0
995 | Payroll Burden | PR | 447 | 05/15/19 | 05/17/19 | RO06 | Roberts, Lake A | 0 | 0 | 0 | 0 | 106.44 |  | 0 | 0
995 | Payroll Burden | PR | 447 | 05/15/19 | 05/17/19 | RO06 | Roberts, Lake A | 0 | 0 | 0 | 0 | 35.48 |  | 0 | 0
995 | Payroll Burden | PR | 451 | 05/15/19 | 05/17/19 | SA54 | Sanders, Allen O | 0 | 0 | 0 | 0 | 65.19 |  | 0 | 0
995 | Payroll Burden | PR | 455 | 05/15/19 | 05/17/19 | ST02 | Stahlschmidt, John P | 0 | 0 | 0 | 0 | 67.41 |  | 0 | 0
995 | Payroll Burden | PR | 458 | 05/15/19 | 05/17/19 | TR60 | Trower-Kelly, Fidel D | 0 | 0 | 0 | 0 | 279.41 |  | 0 | 0
995 | Payroll Burden | PR | 459 | 05/15/19 | 05/17/19 | VA98 | Vazquez Popoca, Jose N | 0 | 0 | 0 | 0 | 248.36 |  | 0 | 0
995 | Payroll Burden | PR | 639 | 05/22/19 | 05/24/19 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 221.75 |  | 0 | 0
995 | Payroll Burden | PR | 642 | 05/22/19 | 05/24/19 | KI55 | Kinssies, Jr, John E | 0 | 0 | 0 | 0 | 434.63 |  | 0 | 0
995 | Payroll Burden | PR | 649 | 05/22/19 | 05/24/19 | MC09 | McCabe, Thomas C | 0 | 0 | 0 | 0 | 248.36 |  | 0 | 0
995 | Payroll Burden | PR | 663 | 05/22/19 | 05/24/19 | SA54 | Sanders, Allen O | 0 | 0 | 0 | 0 | 141.25 |  | 0 | 0
995 | Payroll Burden | PR | 670 | 05/22/19 | 05/24/19 | TR60 | Trower-Kelly, Fidel D | 0 | 0 | 0 | 0 | 283.4 |  | 0 | 0
995 | Payroll Burden | PR | 671 | 05/22/19 | 05/24/19 | VA98 | Vazquez Popoca, Jose N | 0 | 0 | 0 | 0 | 251.91 |  | 0 | 0
995 | Payroll Burden | PR | 881 | 05/29/19 | 05/31/19 | BA70 | Barnhart, Joseph N | 0 | 0 | 0 | 0 | 22.18 |  | 0 | 0
995 | Payroll Burden | PR | 897 | 05/29/19 | 05/31/19 | EL33 | Eliassen, Cory H | 0 | 0 | 0 | 0 | 227.52 |  | 0 | 0
995 | Payroll Burden | PR | 913 | 05/29/19 | 05/31/19 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 66.53 |  | 0 | 0
995 | Payroll Burden | PR | 916 | 05/29/19 | 05/31/19 | KI55 | Kinssies, Jr, John E | 0 | 0 | 0 | 0 | 298.03 |  | 0 | 0
995 | Payroll Burden | PR | 937 | 05/29/19 | 05/31/19 | SA54 | Sanders, Allen O | 0 | 0 | 0 | 0 | 76.06 |  | 0 | 0
995 | Payroll Burden | PR | 944 | 05/29/19 | 05/31/19 | TR60 | Trower-Kelly, Fidel D | 0 | 0 | 0 | 0 | 127.73 |  | 0 | 0
995 | Payroll Burden | PR | 945 | 05/29/19 | 05/31/19 | VA98 | Vazquez Popoca, Jose N | 0 | 0 | 0 | 0 | 227.07 |  | 0 | 0
995 | Payroll Burden | PR | 953 | 05/29/19 | 05/31/19 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 24.39 |  | 0 | 0
995 | Payroll Burden | PR | 46 | 06/05/19 | 06/07/19 | KI55 | Kinssies, Jr, John E | 0 | 0 | 0 | 0 | 549.94 |  | 0 | 0
995 | Payroll Burden | PR | 183 | 06/05/19 | 06/07/19 | BA70 | Barnhart, Joseph N | 0 | 0 | 0 | 0 | 66.53 |  | 0 | 0
995 | Payroll Burden | PR | 199 | 06/05/19 | 06/07/19 | EL33 | Eliassen, Cory H | 0 | 0 | 0 | 0 | 263.44 |  | 0 | 0
995 | Payroll Burden | PR | 215 | 06/05/19 | 06/07/19 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 121.96 |  | 0 | 0
995 | Payroll Burden | PR | 239 | 06/05/19 | 06/07/19 | SA54 | Sanders, Allen O | 0 | 0 | 0 | 0 | 43.46 |  | 0 | 0
995 | Payroll Burden | PR | 246 | 06/05/19 | 06/07/19 | TR60 | Trower-Kelly, Fidel D | 0 | 0 | 0 | 0 | 255.46 |  | 0 | 0
995 | Payroll Burden | PR | 247 | 06/05/19 | 06/07/19 | VA98 | Vazquez Popoca, Jose N | 0 | 0 | 0 | 0 | 170.3 |  | 0 | 0
995 | Payroll Burden | PR | 255 | 06/05/19 | 06/07/19 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 48.79 |  | 0 | 0
995 | Payroll Burden | PR | 469 | 06/12/19 | 06/14/19 | EL33 | Eliassen, Cory H | 0 | 0 | 0 | 0 | 383.18 |  | 0 | 0
995 | Payroll Burden | PR | 483 | 06/12/19 | 06/14/19 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 177.4 |  | 0 | 0
995 | Payroll Burden | PR | 483 | 06/12/19 | 06/14/19 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 221.75 |  | 0 | 0
995 | Payroll Burden | PR | 486 | 06/12/19 | 06/14/19 | KI55 | Kinssies, Jr, John E | 0 | 0 | 0 | 0 | 505.26 |  | 0 | 0
995 | Payroll Burden | PR | 493 | 06/12/19 | 06/14/19 | MC09 | McCabe, Thomas C | 0 | 0 | 0 | 0 | 620.9 |  | 0 | 0
995 | Payroll Burden | PR | 508 | 06/12/19 | 06/14/19 | SE64 | Sepulveda Gonzalez, Alfredo | 0 | 0 | 0 | 0 | 620.9 |  | 0 | 0
995 | Payroll Burden | PR | 514 | 06/12/19 | 06/14/19 | TR60 | Trower-Kelly, Fidel D | 0 | 0 | 0 | 0 | 63.86 |  | 0 | 0
995 | Payroll Burden | PR | 515 | 06/12/19 | 06/14/19 | VA98 | Vazquez Popoca, Jose N | 0 | 0 | 0 | 0 | 56.77 |  | 0 | 0
995 | Payroll Burden | PR | 523 | 06/12/19 | 06/14/19 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 83.16 |  | 0 | 0
995 | Payroll Burden | PR | 524 | 06/12/19 | 06/14/19 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 24.39 |  | 0 | 0
995 | Payroll Burden | PR | 639 | 06/19/19 | 06/21/19 | EL33 | Eliassen, Cory H | 0 | 0 | 0 | 0 | 395.16 |  | 0 | 0
995 | Payroll Burden | PR | 654 | 06/19/19 | 06/21/19 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 221.75 |  | 0 | 0
995 | Payroll Burden | PR | 654 | 06/19/19 | 06/21/19 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 177.4 |  | 0 | 0
995 | Payroll Burden | PR | 657 | 06/19/19 | 06/21/19 | KI55 | Kinssies, Jr, John E | 0 | 0 | 0 | 0 | 439.95 |  | 0 | 0
995 | Payroll Burden | PR | 664 | 06/19/19 | 06/21/19 | MC09 | McCabe, Thomas C | 0 | 0 | 0 | 0 | 496.72 |  | 0 | 0
995 | Payroll Burden | PR | 679 | 06/19/19 | 06/21/19 | SE64 | Sepulveda Gonzalez, Alfredo | 0 | 0 | 0 | 0 | 620.9 |  | 0 | 0
995 | Payroll Burden | PR | 693 | 06/19/19 | 06/21/19 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 55.44 |  | 0 | 0
995 | Payroll Burden | PR | 694 | 06/19/19 | 06/21/19 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 24.39 |  | 0 | 0
995 | Payroll Burden | PR | 857 | 06/26/19 | 06/28/19 | EL33 | Eliassen, Cory H | 0 | 0 | 0 | 0 | 347.26 |  | 0 | 0
995 | Payroll Burden | PR | 872 | 06/26/19 | 06/28/19 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 177.4 |  | 0 | 0
995 | Payroll Burden | PR | 896 | 06/26/19 | 06/28/19 | SE64 | Sepulveda Gonzalez, Alfredo | 0 | 0 | 0 | 0 | 589.86 |  | 0 | 0
995 | Payroll Burden | PR | 44 | 07/03/19 | 07/05/19 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 133.05 |  | 0 | 0
995 | Payroll Burden | PR | 46 | 07/03/19 | 07/05/19 | KI55 | Kinssies, Jr, John E | 0 | 0 | 0 | 0 | 54.99 |  | 0 | 0
995 | Payroll Burden | PR | 67 | 07/03/19 | 07/05/19 | SE64 | Sepulveda Gonzalez, Alfredo | 0 | 0 | 0 | 0 | 62.09 |  | 0 | 0
995 | Payroll Burden | PR | 67 | 07/03/19 | 07/05/19 | SE64 | Sepulveda Gonzalez, Alfredo | 0 | 0 | 0 | 0 | 186.27 |  | 0 | 0
995 | Payroll Burden | PR | 81 | 07/03/19 | 07/05/19 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 27.72 |  | 0 | 0
995 | Payroll Burden | PR | 282 | 07/10/19 | 07/12/19 | BA70 | Barnhart, Joseph N | 0 | 0 | 0 | 0 | 44.35 |  | 0 | 0
995 | Payroll Burden | PR | 298 | 07/10/19 | 07/12/19 | EL33 | Eliassen, Cory H | 0 | 0 | 0 | 0 | 143.69 |  | 0 | 0
995 | Payroll Burden | PR | 528 | 07/17/19 | 07/19/19 | EL33 | Eliassen, Cory H | 0 | 0 | 0 | 0 | 227.52 |  | 0 | 0
995 | Payroll Burden | PR | 543 | 07/17/19 | 07/19/19 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 44.35 |  | 0 | 0
995 | Payroll Burden | PR | 543 | 07/17/19 | 07/19/19 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 110.88 |  | 0 | 0
995 | Payroll Burden | PR | 543 | 07/17/19 | 07/19/19 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 44.35 |  | 0 | 0
995 | Payroll Burden | PR | 552 | 07/17/19 | 07/19/19 | MC09 | McCabe, Thomas C | 0 | 0 | 0 | 0 | 62.09 |  | 0 | 0
995 | Payroll Burden | PR | 552 | 07/17/19 | 07/19/19 | MC09 | McCabe, Thomas C | 0 | 0 | 0 | 0 | 186.27 |  | 0 | 0
995 | Payroll Burden | PR | 585 | 07/17/19 | 07/19/19 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 55.44 |  | 0 | 0
995 | Payroll Burden | PR | 586 | 07/17/19 | 07/19/19 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 24.39 |  | 0 | 0
995 | Payroll Burden | PR | 632 | 07/24/19 | 07/26/19 | EL33 | Eliassen, Cory H | 0 | 0 | 0 | 0 | 143.69 |  | 0 | 0
995 | Payroll Burden | PR | 646 | 07/24/19 | 07/26/19 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 66.53 |  | 0 | 0
995 | Payroll Burden | PR | 646 | 07/24/19 | 07/26/19 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 44.35 |  | 0 | 0
995 | Payroll Burden | PR | 655 | 07/24/19 | 07/26/19 | MC09 | McCabe, Thomas C | 0 | 0 | 0 | 0 | 155.23 |  | 0 | 0
995 | Payroll Burden | PR | 655 | 07/24/19 | 07/26/19 | MC09 | McCabe, Thomas C | 0 | 0 | 0 | 0 | 232.84 |  | 0 | 0
995 | Payroll Burden | PR | 655 | 07/24/19 | 07/26/19 | MC09 | McCabe, Thomas C | 0 | 0 | 0 | 0 | 77.61 |  | 0 | 0
995 | Payroll Burden | PR | 655 | 07/24/19 | 07/26/19 | MC09 | McCabe, Thomas C | 0 | 0 | 0 | 0 | 124.18 |  | 0 | 0
995 | Payroll Burden | PR | 670 | 07/24/19 | 07/26/19 | SA54 | Sanders, Allen O | 0 | 0 | 0 | 0 | 43.46 |  | 0 | 0
995 | Payroll Burden | PR | 685 | 07/24/19 | 07/26/19 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 83.16 |  | 0 | 0
995 | Payroll Burden | PR | 686 | 07/24/19 | 07/26/19 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 24.39 |  | 0 | 0
995 | Payroll Burden | PR | 24 | 07/31/19 | 08/02/19 | EL33 | Eliassen, Cory H | 0 | 0 | 0 | 0 | 467.01 |  | 0 | 0
995 | Payroll Burden | PR | 38 | 07/31/19 | 08/02/19 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 22.18 |  | 0 | 0
995 | Payroll Burden | PR | 61 | 07/31/19 | 08/02/19 | SA54 | Sanders, Allen O | 0 | 0 | 0 | 0 | 43.46 |  | 0 | 0
995 | Payroll Burden | PR | 68 | 07/31/19 | 08/02/19 | TR60 | Trower-Kelly, Fidel D | 0 | 0 | 0 | 0 | 79.83 |  | 0 | 0
995 | Payroll Burden | PR | 276 | 08/07/19 | 08/09/19 | EL33 | Eliassen, Cory H | 0 | 0 | 0 | 0 | 514.9 |  | 0 | 0
995 | Payroll Burden | PR | 291 | 08/07/19 | 08/09/19 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 22.18 |  | 0 | 0
995 | Payroll Burden | PR | 291 | 08/07/19 | 08/09/19 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 221.75 |  | 0 | 0
995 | Payroll Burden | PR | 300 | 08/07/19 | 08/09/19 | MC09 | McCabe, Thomas C | 0 | 0 | 0 | 0 | 248.36 |  | 0 | 0
995 | Payroll Burden | PR | 300 | 08/07/19 | 08/09/19 | MC09 | McCabe, Thomas C | 0 | 0 | 0 | 0 | 31.05 |  | 0 | 0
995 | Payroll Burden | PR | 300 | 08/07/19 | 08/09/19 | MC09 | McCabe, Thomas C | 0 | 0 | 0 | 0 | 93.14 |  | 0 | 0
995 | Payroll Burden | PR | 314 | 08/07/19 | 08/09/19 | SA54 | Sanders, Allen O | 0 | 0 | 0 | 0 | 217.32 |  | 0 | 0
995 | Payroll Burden | PR | 320 | 08/07/19 | 08/09/19 | TR60 | Trower-Kelly, Fidel D | 0 | 0 | 0 | 0 | 207.56 |  | 0 | 0
995 | Payroll Burden | PR | 328 | 08/07/19 | 08/09/19 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 55.44 |  | 0 | 0
995 | Payroll Burden | PR | 607 | 08/14/19 | 08/16/19 | MC09 | McCabe, Thomas C | 0 | 0 | 0 | 0 | 124.18 |  | 0 | 0
995 | Payroll Burden | PR | 621 | 08/14/19 | 08/16/19 | SA54 | Sanders, Allen O | 0 | 0 | 0 | 0 | 152.12 |  | 0 | 0
995 | Payroll Burden | PR | 819 | 08/21/19 | 08/23/19 | EL33 | Eliassen, Cory H | 0 | 0 | 0 | 0 | 35.92 |  | 0 | 0
995 | Payroll Burden | PR | 835 | 08/21/19 | 08/23/19 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 22.18 |  | 0 | 0
995 | Payroll Burden | PR | 835 | 08/21/19 | 08/23/19 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 44.35 |  | 0 | 0
995 | Payroll Burden | PR | 844 | 08/21/19 | 08/23/19 | MC09 | McCabe, Thomas C | 0 | 0 | 0 | 0 | 434.63 |  | 0 | 0
995 | Payroll Burden | PR | 844 | 08/21/19 | 08/23/19 | MC09 | McCabe, Thomas C | 0 | 0 | 0 | 0 | 62.09 |  | 0 | 0
995 | Payroll Burden | PR | 1026 | 08/28/19 | 08/30/19 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 22.18 |  | 0 | 0
995 | Payroll Burden | PR | 1049 | 08/28/19 | 08/30/19 | SA54 | Sanders, Allen O | 0 | 0 | 0 | 0 | 21.73 |  | 0 | 0
995 | Payroll Burden | PR | 1064 | 08/28/19 | 08/30/19 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 27.72 |  | 0 | 0
995 | Payroll Burden | PR | 1064 | 08/28/19 | 08/30/19 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 27.72 |  | 0 | 0
995 | Payroll Burden | PR | 70 | 09/04/19 | 09/06/19 | SA54 | Sanders, Allen O | 0 | 0 | 0 | 0 | 32.6 |  | 0 | 0
995 | Payroll Burden | PR | 531 | 09/18/19 | 09/20/19 | SA54 | Sanders, Allen O | 0 | 0 | 0 | 0 | 86.93 |  | 0 | 0
998 | Payroll Taxes | PR | 403 | 08/16/17 | 08/18/17 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 3.83 |  | 0 | 0
998 | Payroll Taxes | PR | 185 | 09/06/17 | 09/08/17 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 3.6 |  | 0 | 0
998 | Payroll Taxes | PR | 762 | 09/27/17 | 09/29/17 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 7.19 |  | 0 | 0
998 | Payroll Taxes | PR | 67 | 10/04/17 | 10/06/17 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 3.83 |  | 0 | 0
998 | Payroll Taxes | PR | 70 | 01/31/18 | 02/02/18 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 9.56 |  | 0 | 0
998 | Payroll Taxes | PR | 71 | 01/31/18 | 02/02/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 3.6 |  | 0 | 0
998 | Payroll Taxes | PR | 226 | 02/07/18 | 02/09/18 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 4.78 |  | 0 | 0
998 | Payroll Taxes | PR | 483 | 02/14/18 | 02/16/18 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 4.78 |  | 0 | 0
998 | Payroll Taxes | PR | 603 | 02/21/18 | 02/23/18 | AN14 | Anderson, Richard P | 0 | 0 | 0 | 0 | 8.03 |  | 0 | 0
998 | Payroll Taxes | PR | 607 | 02/21/18 | 02/23/18 | BA70 | Barnhart, Joseph N | 0 | 0 | 0 | 0 | 11.78 |  | 0 | 0
998 | Payroll Taxes | PR | 669 | 02/21/18 | 02/23/18 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 23.91 |  | 0 | 0
998 | Payroll Taxes | PR | 670 | 02/21/18 | 02/23/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 3.6 |  | 0 | 0
998 | Payroll Taxes | PR | 2 | 02/28/18 | 03/02/18 | AN14 | Anderson, Richard P | 0 | 0 | 0 | 0 | 22.49 |  | 0 | 0
998 | Payroll Taxes | PR | 37 | 02/28/18 | 03/02/18 | KI55 | Kinssies, Jr, John E | 0 | 0 | 0 | 0 | 13.92 |  | 0 | 0
998 | Payroll Taxes | PR | 68 | 02/28/18 | 03/02/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 14.38 |  | 0 | 0
998 | Payroll Taxes | PR | 68 | 02/28/18 | 03/02/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 7.19 |  | 0 | 0
998 | Payroll Taxes | PR | 118 | 03/07/18 | 03/09/18 | AN14 | Anderson, Richard P | 0 | 0 | 0 | 0 | 36.95 |  | 0 | 0
998 | Payroll Taxes | PR | 151 | 03/07/18 | 03/09/18 | KI55 | Kinssies, Jr, John E | 0 | 0 | 0 | 0 | 13.92 |  | 0 | 0
998 | Payroll Taxes | PR | 179 | 03/07/18 | 03/09/18 | WE55 | Wennig, Johnathan M | 0 | 0 | 0 | 0 | 8.95 |  | 0 | 0
998 | Payroll Taxes | PR | 183 | 03/07/18 | 03/09/18 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 4.78 |  | 0 | 0
998 | Payroll Taxes | PR | 318 | 03/14/18 | 03/16/18 | AN14 | Anderson, Richard P | 0 | 0 | 0 | 0 | 1.61 |  | 0 | 0
998 | Payroll Taxes | PR | 516 | 03/21/18 | 03/23/18 | AN14 | Anderson, Richard P | 0 | 0 | 0 | 0 | 16.07 |  | 0 | 0
998 | Payroll Taxes | PR | 550 | 03/21/18 | 03/23/18 | KI55 | Kinssies, Jr, John E | 0 | 0 | 0 | 0 | 7.96 |  | 0 | 0
998 | Payroll Taxes | PR | 735 | 03/28/18 | 03/30/18 | AN14 | Anderson, Richard P | 0 | 0 | 0 | 0 | 3.21 |  | 0 | 0
998 | Payroll Taxes | PR | 739 | 03/28/18 | 03/30/18 | BA70 | Barnhart, Joseph N | 0 | 0 | 0 | 0 | 3.37 |  | 0 | 0
998 | Payroll Taxes | PR | 11 | 04/04/18 | 04/06/18 | AN14 | Anderson, Richard P | 0 | 0 | 0 | 0 | 6.43 |  | 0 | 0
998 | Payroll Taxes | PR | 11 | 04/04/18 | 04/06/18 | AN14 | Anderson, Richard P | 0 | 0 | 0 | 0 | 3.21 |  | 0 | 0
998 | Payroll Taxes | PR | 15 | 04/04/18 | 04/06/18 | BA70 | Barnhart, Joseph N | 0 | 0 | 0 | 0 | 43.76 |  | 0 | 0
998 | Payroll Taxes | PR | 48 | 04/04/18 | 04/06/18 | KI55 | Kinssies, Jr, John E | 0 | 0 | 0 | 0 | 19.89 |  | 0 | 0
998 | Payroll Taxes | PR | 80 | 04/04/18 | 04/06/18 | WE55 | Wennig, Johnathan M | 0 | 0 | 0 | 0 | 15.91 |  | 0 | 0
998 | Payroll Taxes | PR | 84 | 04/04/18 | 04/06/18 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 4.78 |  | 0 | 0
998 | Payroll Taxes | PR | 85 | 04/04/18 | 04/06/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 3.83 |  | 0 | 0
998 | Payroll Taxes | PR | 259 | 04/11/18 | 04/13/18 | AN14 | Anderson, Richard P | 0 | 0 | 0 | 0 | 8.03 |  | 0 | 0
998 | Payroll Taxes | PR | 296 | 04/11/18 | 04/13/18 | KI55 | Kinssies, Jr, John E | 0 | 0 | 0 | 0 | 4.97 |  | 0 | 0
998 | Payroll Taxes | PR | 329 | 04/11/18 | 04/13/18 | WE55 | Wennig, Johnathan M | 0 | 0 | 0 | 0 | 3.98 |  | 0 | 0
998 | Payroll Taxes | PR | 446 | 04/18/18 | 04/20/18 | AN14 | Anderson, Richard P | 0 | 0 | 0 | 0 | 4.82 |  | 0 | 0
998 | Payroll Taxes | PR | 612 | 04/25/18 | 04/27/18 | AN14 | Anderson, Richard P | 0 | 0 | 0 | 0 | 64.26 |  | 0 | 0
998 | Payroll Taxes | PR | 648 | 04/25/18 | 04/27/18 | KI55 | Kinssies, Jr, John E | 0 | 0 | 0 | 0 | 43.76 |  | 0 | 0
998 | Payroll Taxes | PR | 26 | 05/02/18 | 05/04/18 | AN14 | Anderson, Richard P | 0 | 0 | 0 | 0 | 9.64 |  | 0 | 0
998 | Payroll Taxes | PR | 31 | 05/02/18 | 05/04/18 | BA70 | Barnhart, Joseph N | 0 | 0 | 0 | 0 | 16.83 |  | 0 | 0
998 | Payroll Taxes | PR | 62 | 05/02/18 | 05/04/18 | KI55 | Kinssies, Jr, John E | 0 | 0 | 0 | 0 | 30.83 |  | 0 | 0
998 | Payroll Taxes | PR | 426 | 05/16/18 | 05/18/18 | BA70 | Barnhart, Joseph N | 0 | 0 | 0 | 0 | 6.73 |  | 0 | 0
998 | Payroll Taxes | PR | 3 | 05/30/18 | 06/01/18 | AN14 | Anderson, Richard P | 0 | 0 | 0 | 0 | 24.1 |  | 0 | 0
998 | Payroll Taxes | PR | 38 | 05/30/18 | 06/01/18 | KI55 | Kinssies, Jr, John E | 0 | 0 | 0 | 0 | 14.92 |  | 0 | 0
998 | Payroll Taxes | PR | 340 | 06/06/18 | 06/08/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 3.83 |  | 0 | 0
998 | Payroll Taxes | PR | 458 | 06/13/18 | 06/15/18 | AN14 | Anderson, Richard P | 0 | 0 | 0 | 0 | 4.93 |  | 0 | 0
998 | Payroll Taxes | PR | 493 | 06/13/18 | 06/15/18 | KI55 | Kinssies, Jr, John E | 0 | 0 | 0 | 0 | 15.91 |  | 0 | 0
998 | Payroll Taxes | PR | 496 | 06/13/18 | 06/15/18 | LO58 | Lopez Reyes, Boris O | 0 | 0 | 0 | 0 | 4.13 |  | 0 | 0
998 | Payroll Taxes | PR | 496 | 06/13/18 | 06/15/18 | LO58 | Lopez Reyes, Boris O | 0 | 0 | 0 | 0 | 50.95 |  | 0 | 0
998 | Payroll Taxes | PR | 528 | 06/13/18 | 06/15/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 3.83 |  | 0 | 0
998 | Payroll Taxes | PR | 684 | 06/20/18 | 06/22/18 | AN14 | Anderson, Richard P | 0 | 0 | 0 | 0 | 8.22 |  | 0 | 0
998 | Payroll Taxes | PR | 705 | 06/20/18 | 06/22/18 | GA70 | Garcia, Jordan X | 0 | 0 | 0 | 0 | 6.12 |  | 0 | 0
998 | Payroll Taxes | PR | 754 | 06/20/18 | 06/22/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 3.83 |  | 0 | 0
998 | Payroll Taxes | PR | 1020 | 06/27/18 | 06/29/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 3.83 |  | 0 | 0
998 | Payroll Taxes | PR | 5 | 07/04/18 | 07/06/18 | AN14 | Anderson, Richard P | 0 | 0 | 0 | 0 | 3.29 |  | 0 | 0
998 | Payroll Taxes | PR | 68 | 07/04/18 | 07/06/18 | TA96 | Taylor, Evan R | 0 | 0 | 0 | 0 | 3.67 |  | 0 | 0
998 | Payroll Taxes | PR | 71 | 07/04/18 | 07/06/18 | WA35 | Waites, Thaddeus Z | 0 | 0 | 0 | 0 | 6.43 |  | 0 | 0
998 | Payroll Taxes | PR | 241 | 07/11/18 | 07/13/18 | BA70 | Barnhart, Joseph N | 0 | 0 | 0 | 0 | 5.28 |  | 0 | 0
998 | Payroll Taxes | PR | 327 | 07/11/18 | 07/13/18 | HO14 | Holmes, Anthony R | 0 | 0 | 0 | 0 | 64.26 |  | 0 | 0
998 | Payroll Taxes | PR | 360 | 07/11/18 | 07/13/18 | TA96 | Taylor, Evan R | 0 | 0 | 0 | 0 | 51.41 |  | 0 | 0
998 | Payroll Taxes | PR | 363 | 07/11/18 | 07/13/18 | WA35 | Waites, Thaddeus Z | 0 | 0 | 0 | 0 | 64.26 |  | 0 | 0
998 | Payroll Taxes | PR | 367 | 07/11/18 | 07/13/18 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 4.78 |  | 0 | 0
998 | Payroll Taxes | PR | 441 | 07/18/18 | 07/20/18 | BA70 | Barnhart, Joseph N | 0 | 0 | 0 | 0 | 7.04 |  | 0 | 0
998 | Payroll Taxes | PR | 468 | 07/18/18 | 07/20/18 | HO14 | Holmes, Anthony R | 0 | 0 | 0 | 0 | 107.1 |  | 0 | 0
998 | Payroll Taxes | PR | 501 | 07/18/18 | 07/20/18 | TA96 | Taylor, Evan R | 0 | 0 | 0 | 0 | 58.75 |  | 0 | 0
998 | Payroll Taxes | PR | 504 | 07/18/18 | 07/20/18 | WA35 | Waites, Thaddeus Z | 0 | 0 | 0 | 0 | 98 |  | 0 | 0
998 | Payroll Taxes | PR | 507 | 07/18/18 | 07/20/18 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 4.78 |  | 0 | 0
998 | Payroll Taxes | PR | 508 | 07/18/18 | 07/20/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 3.83 |  | 0 | 0
998 | Payroll Taxes | PR | 795 | 07/25/18 | 07/27/18 | HO14 | Holmes, Anthony R | 0 | 0 | 0 | 0 | 107.1 |  | 0 | 0
998 | Payroll Taxes | PR | 828 | 07/25/18 | 07/27/18 | TA96 | Taylor, Evan R | 0 | 0 | 0 | 0 | 49.57 |  | 0 | 0
998 | Payroll Taxes | PR | 831 | 07/25/18 | 07/27/18 | WA35 | Waites, Thaddeus Z | 0 | 0 | 0 | 0 | 48.2 |  | 0 | 0
998 | Payroll Taxes | PR | 834 | 07/25/18 | 07/27/18 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 4.78 |  | 0 | 0
998 | Payroll Taxes | PR | 835 | 07/25/18 | 07/27/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 3.83 |  | 0 | 0
998 | Payroll Taxes | PR | 6 | 08/01/18 | 08/03/18 | BA70 | Barnhart, Joseph N | 0 | 0 | 0 | 0 | 19.35 |  | 0 | 0
998 | Payroll Taxes | PR | 33 | 08/01/18 | 08/03/18 | HO14 | Holmes, Anthony R | 0 | 0 | 0 | 0 | 85.68 |  | 0 | 0
998 | Payroll Taxes | PR | 66 | 08/01/18 | 08/03/18 | TA96 | Taylor, Evan R | 0 | 0 | 0 | 0 | 73.44 |  | 0 | 0
998 | Payroll Taxes | PR | 69 | 08/01/18 | 08/03/18 | WA35 | Waites, Thaddeus Z | 0 | 0 | 0 | 0 | 110.85 |  | 0 | 0
998 | Payroll Taxes | PR | 69 | 08/01/18 | 08/03/18 | WA35 | Waites, Thaddeus Z | 0 | 0 | 0 | 0 | 3.21 |  | 0 | 0
998 | Payroll Taxes | PR | 216 | 08/08/18 | 08/10/18 | BA70 | Barnhart, Joseph N | 0 | 0 | 0 | 0 | 7.04 |  | 0 | 0
998 | Payroll Taxes | PR | 244 | 08/08/18 | 08/10/18 | HO14 | Holmes, Anthony R | 0 | 0 | 0 | 0 | 107.1 |  | 0 | 0
998 | Payroll Taxes | PR | 277 | 08/08/18 | 08/10/18 | TA96 | Taylor, Evan R | 0 | 0 | 0 | 0 | 73.44 |  | 0 | 0
998 | Payroll Taxes | PR | 280 | 08/08/18 | 08/10/18 | WA35 | Waites, Thaddeus Z | 0 | 0 | 0 | 0 | 61.05 |  | 0 | 0
998 | Payroll Taxes | PR | 283 | 08/08/18 | 08/10/18 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 4.78 |  | 0 | 0
998 | Payroll Taxes | PR | 284 | 08/08/18 | 08/10/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 3.83 |  | 0 | 0
998 | Payroll Taxes | PR | 512 | 08/15/18 | 08/17/18 | HO14 | Holmes, Anthony R | 0 | 0 | 0 | 0 | 101.75 |  | 0 | 0
998 | Payroll Taxes | PR | 520 | 08/15/18 | 08/17/18 | LO58 | Lopez Reyes, Boris O | 0 | 0 | 0 | 0 | 22.03 |  | 0 | 0
998 | Payroll Taxes | PR | 544 | 08/15/18 | 08/17/18 | TA96 | Taylor, Evan R | 0 | 0 | 0 | 0 | 44.06 |  | 0 | 0
998 | Payroll Taxes | PR | 547 | 08/15/18 | 08/17/18 | WA35 | Waites, Thaddeus Z | 0 | 0 | 0 | 0 | 4.82 |  | 0 | 0
998 | Payroll Taxes | PR | 551 | 08/15/18 | 08/17/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 3.83 |  | 0 | 0
998 | Payroll Taxes | PR | 551 | 08/15/18 | 08/17/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 7.65 |  | 0 | 0
998 | Payroll Taxes | PR | 774 | 08/22/18 | 08/24/18 | HO14 | Holmes, Anthony R | 0 | 0 | 0 | 0 | 107.1 |  | 0 | 0
998 | Payroll Taxes | PR | 779 | 08/22/18 | 08/24/18 | LE17 | Lee, Ha Nul | 0 | 0 | 0 | 0 | 41.62 |  | 0 | 0
998 | Payroll Taxes | PR | 781 | 08/22/18 | 08/24/18 | LO58 | Lopez Reyes, Boris O | 0 | 0 | 0 | 0 | 44.06 |  | 0 | 0
998 | Payroll Taxes | PR | 805 | 08/22/18 | 08/24/18 | TA96 | Taylor, Evan R | 0 | 0 | 0 | 0 | 29.38 |  | 0 | 0
998 | Payroll Taxes | PR | 809 | 08/22/18 | 08/24/18 | WE55 | Wennig, Johnathan M | 0 | 0 | 0 | 0 | 51.41 |  | 0 | 0
998 | Payroll Taxes | PR | 811 | 08/22/18 | 08/24/18 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 9.56 |  | 0 | 0
998 | Payroll Taxes | PR | 812 | 08/22/18 | 08/24/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 7.65 |  | 0 | 0
998 | Payroll Taxes | PR | 812 | 08/22/18 | 08/24/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 3.83 |  | 0 | 0
998 | Payroll Taxes | PR | 1000 | 08/29/18 | 08/31/18 | BA70 | Barnhart, Joseph N | 0 | 0 | 0 | 0 | 7.04 |  | 0 | 0
998 | Payroll Taxes | PR | 1029 | 08/29/18 | 08/31/18 | HO14 | Holmes, Anthony R | 0 | 0 | 0 | 0 | 85.68 |  | 0 | 0
998 | Payroll Taxes | PR | 1034 | 08/29/18 | 08/31/18 | LE17 | Lee, Ha Nul | 0 | 0 | 0 | 0 | 52.02 |  | 0 | 0
998 | Payroll Taxes | PR | 1036 | 08/29/18 | 08/31/18 | LO58 | Lopez Reyes, Boris O | 0 | 0 | 0 | 0 | 22.03 |  | 0 | 0
998 | Payroll Taxes | PR | 1040 | 08/29/18 | 08/31/18 | ME52 | Mendoza, Edgar E | 0 | 0 | 0 | 0 | 53.86 |  | 0 | 0
998 | Payroll Taxes | PR | 1059 | 08/29/18 | 08/31/18 | TA96 | Taylor, Evan R | 0 | 0 | 0 | 0 | 71.6 |  | 0 | 0
998 | Payroll Taxes | PR | 1059 | 08/29/18 | 08/31/18 | TA96 | Taylor, Evan R | 0 | 0 | 0 | 0 | 1.84 |  | 0 | 0
998 | Payroll Taxes | PR | 1063 | 08/29/18 | 08/31/18 | WE55 | Wennig, Johnathan M | 0 | 0 | 0 | 0 | 85.68 |  | 0 | 0
998 | Payroll Taxes | PR | 1069 | 08/29/18 | 08/31/18 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 4.78 |  | 0 | 0
998 | Payroll Taxes | PR | 41 | 09/05/18 | 09/07/18 | BA70 | Barnhart, Joseph N | 0 | 0 | 0 | 0 | 17.6 |  | 0 | 0
998 | Payroll Taxes | PR | 68 | 09/05/18 | 09/07/18 | HO14 | Holmes, Anthony R | 0 | 0 | 0 | 0 | 85.68 |  | 0 | 0
998 | Payroll Taxes | PR | 73 | 09/05/18 | 09/07/18 | LE17 | Lee, Ha Nul | 0 | 0 | 0 | 0 | 41.62 |  | 0 | 0
998 | Payroll Taxes | PR | 76 | 09/05/18 | 09/07/18 | LO58 | Lopez Reyes, Boris O | 0 | 0 | 0 | 0 | 44.06 |  | 0 | 0
998 | Payroll Taxes | PR | 80 | 09/05/18 | 09/07/18 | ME52 | Mendoza, Edgar E | 0 | 0 | 0 | 0 | 53.86 |  | 0 | 0
998 | Payroll Taxes | PR | 99 | 09/05/18 | 09/07/18 | TA96 | Taylor, Evan R | 0 | 0 | 0 | 0 | 44.06 |  | 0 | 0
998 | Payroll Taxes | PR | 103 | 09/05/18 | 09/07/18 | WE55 | Wennig, Johnathan M | 0 | 0 | 0 | 0 | 68.54 |  | 0 | 0
998 | Payroll Taxes | PR | 106 | 09/05/18 | 09/07/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 3.83 |  | 0 | 0
998 | Payroll Taxes | PR | 106 | 09/05/18 | 09/07/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 3.83 |  | 0 | 0
998 | Payroll Taxes | PR | 300 | 09/12/18 | 09/14/18 | HO14 | Holmes, Anthony R | 0 | 0 | 0 | 0 | 107.1 |  | 0 | 0
998 | Payroll Taxes | PR | 305 | 09/12/18 | 09/14/18 | LE17 | Lee, Ha Nul | 0 | 0 | 0 | 0 | 52.02 |  | 0 | 0
998 | Payroll Taxes | PR | 307 | 09/12/18 | 09/14/18 | LO58 | Lopez Reyes, Boris O | 0 | 0 | 0 | 0 | 55.08 |  | 0 | 0
998 | Payroll Taxes | PR | 312 | 09/12/18 | 09/14/18 | ME52 | Mendoza, Edgar E | 0 | 0 | 0 | 0 | 67.32 |  | 0 | 0
998 | Payroll Taxes | PR | 332 | 09/12/18 | 09/14/18 | TA96 | Taylor, Evan R | 0 | 0 | 0 | 0 | 73.44 |  | 0 | 0
998 | Payroll Taxes | PR | 336 | 09/12/18 | 09/14/18 | WE55 | Wennig, Johnathan M | 0 | 0 | 0 | 0 | 85.68 |  | 0 | 0
998 | Payroll Taxes | PR | 340 | 09/12/18 | 09/14/18 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 19.13 |  | 0 | 0
998 | Payroll Taxes | PR | 341 | 09/12/18 | 09/14/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 11.48 |  | 0 | 0
998 | Payroll Taxes | PR | 341 | 09/12/18 | 09/14/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 7.65 |  | 0 | 0
998 | Payroll Taxes | PR | 513 | 09/19/18 | 09/21/18 | HO14 | Holmes, Anthony R | 0 | 0 | 0 | 0 | 85.68 |  | 0 | 0
998 | Payroll Taxes | PR | 518 | 09/19/18 | 09/21/18 | LE17 | Lee, Ha Nul | 0 | 0 | 0 | 0 | 52.02 |  | 0 | 0
998 | Payroll Taxes | PR | 520 | 09/19/18 | 09/21/18 | LO58 | Lopez Reyes, Boris O | 0 | 0 | 0 | 0 | 44.06 |  | 0 | 0
998 | Payroll Taxes | PR | 525 | 09/19/18 | 09/21/18 | ME52 | Mendoza, Edgar E | 0 | 0 | 0 | 0 | 67.32 |  | 0 | 0
998 | Payroll Taxes | PR | 545 | 09/19/18 | 09/21/18 | TA96 | Taylor, Evan R | 0 | 0 | 0 | 0 | 73.44 |  | 0 | 0
998 | Payroll Taxes | PR | 549 | 09/19/18 | 09/21/18 | WE55 | Wennig, Johnathan M | 0 | 0 | 0 | 0 | 85.68 |  | 0 | 0
998 | Payroll Taxes | PR | 552 | 09/19/18 | 09/21/18 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 14.34 |  | 0 | 0
998 | Payroll Taxes | PR | 553 | 09/19/18 | 09/21/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 7.65 |  | 0 | 0
998 | Payroll Taxes | PR | 553 | 09/19/18 | 09/21/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 3.83 |  | 0 | 0
998 | Payroll Taxes | PR | 670 | 09/26/18 | 09/28/18 | BA70 | Barnhart, Joseph N | 0 | 0 | 0 | 0 | 14.08 |  | 0 | 0
998 | Payroll Taxes | PR | 698 | 09/26/18 | 09/28/18 | HO14 | Holmes, Anthony R | 0 | 0 | 0 | 0 | 107.1 |  | 0 | 0
998 | Payroll Taxes | PR | 703 | 09/26/18 | 09/28/18 | LE17 | Lee, Ha Nul | 0 | 0 | 0 | 0 | 52.02 |  | 0 | 0
998 | Payroll Taxes | PR | 705 | 09/26/18 | 09/28/18 | LO58 | Lopez Reyes, Boris O | 0 | 0 | 0 | 0 | 54.39 |  | 0 | 0
998 | Payroll Taxes | PR | 710 | 09/26/18 | 09/28/18 | ME52 | Mendoza, Edgar E | 0 | 0 | 0 | 0 | 65.64 |  | 0 | 0
998 | Payroll Taxes | PR | 731 | 09/26/18 | 09/28/18 | TA96 | Taylor, Evan R | 0 | 0 | 0 | 0 | 73.44 |  | 0 | 0
998 | Payroll Taxes | PR | 735 | 09/26/18 | 09/28/18 | WE55 | Wennig, Johnathan M | 0 | 0 | 0 | 0 | 85.68 |  | 0 | 0
998 | Payroll Taxes | PR | 739 | 09/26/18 | 09/28/18 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 4.78 |  | 0 | 0
998 | Payroll Taxes | PR | 34 | 10/03/18 | 10/05/18 | BA70 | Barnhart, Joseph N | 0 | 0 | 0 | 0 | 14.08 |  | 0 | 0
998 | Payroll Taxes | PR | 62 | 10/03/18 | 10/05/18 | HO14 | Holmes, Anthony R | 0 | 0 | 0 | 0 | 107.1 |  | 0 | 0
998 | Payroll Taxes | PR | 67 | 10/03/18 | 10/05/18 | LE17 | Lee, Ha Nul | 0 | 0 | 0 | 0 | 49.74 |  | 0 | 0
998 | Payroll Taxes | PR | 69 | 10/03/18 | 10/05/18 | LO58 | Lopez Reyes, Boris O | 0 | 0 | 0 | 0 | 44.06 |  | 0 | 0
998 | Payroll Taxes | PR | 74 | 10/03/18 | 10/05/18 | ME52 | Mendoza, Edgar E | 0 | 0 | 0 | 0 | 64.8 |  | 0 | 0
998 | Payroll Taxes | PR | 95 | 10/03/18 | 10/05/18 | TA96 | Taylor, Evan R | 0 | 0 | 0 | 0 | 58.75 |  | 0 | 0
998 | Payroll Taxes | PR | 99 | 10/03/18 | 10/05/18 | WE55 | Wennig, Johnathan M | 0 | 0 | 0 | 0 | 85.68 |  | 0 | 0
998 | Payroll Taxes | PR | 102 | 10/03/18 | 10/05/18 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 2.39 |  | 0 | 0
998 | Payroll Taxes | PR | 239 | 10/10/18 | 10/12/18 | BA70 | Barnhart, Joseph N | 0 | 0 | 0 | 0 | 7.04 |  | 0 | 0
998 | Payroll Taxes | PR | 268 | 10/10/18 | 10/12/18 | HO14 | Holmes, Anthony R | 0 | 0 | 0 | 0 | 107.1 |  | 0 | 0
998 | Payroll Taxes | PR | 273 | 10/10/18 | 10/12/18 | LE17 | Lee, Ha Nul | 0 | 0 | 0 | 0 | 31.21 |  | 0 | 0
998 | Payroll Taxes | PR | 273 | 10/10/18 | 10/12/18 | LE17 | Lee, Ha Nul | 0 | 0 | 0 | 0 | 20.81 |  | 0 | 0
998 | Payroll Taxes | PR | 275 | 10/10/18 | 10/12/18 | LO58 | Lopez Reyes, Boris O | 0 | 0 | 0 | 0 | 44.06 |  | 0 | 0
998 | Payroll Taxes | PR | 280 | 10/10/18 | 10/12/18 | ME52 | Mendoza, Edgar E | 0 | 0 | 0 | 0 | 67.32 |  | 0 | 0
998 | Payroll Taxes | PR | 301 | 10/10/18 | 10/12/18 | TA96 | Taylor, Evan R | 0 | 0 | 0 | 0 | 73.44 |  | 0 | 0
998 | Payroll Taxes | PR | 305 | 10/10/18 | 10/12/18 | WE55 | Wennig, Johnathan M | 0 | 0 | 0 | 0 | 85.68 |  | 0 | 0
998 | Payroll Taxes | PR | 310 | 10/10/18 | 10/12/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 3.83 |  | 0 | 0
998 | Payroll Taxes | PR | 438 | 10/17/18 | 10/19/18 | BA70 | Barnhart, Joseph N | 0 | 0 | 0 | 0 | 3.52 |  | 0 | 0
998 | Payroll Taxes | PR | 466 | 10/17/18 | 10/19/18 | HO14 | Holmes, Anthony R | 0 | 0 | 0 | 0 | 107.1 |  | 0 | 0
998 | Payroll Taxes | PR | 471 | 10/17/18 | 10/19/18 | LE17 | Lee, Ha Nul | 0 | 0 | 0 | 0 | 52.02 |  | 0 | 0
998 | Payroll Taxes | PR | 473 | 10/17/18 | 10/19/18 | LO58 | Lopez Reyes, Boris O | 0 | 0 | 0 | 0 | 47.51 |  | 0 | 0
998 | Payroll Taxes | PR | 478 | 10/17/18 | 10/19/18 | ME52 | Mendoza, Edgar E | 0 | 0 | 0 | 0 | 67.32 |  | 0 | 0
998 | Payroll Taxes | PR | 499 | 10/17/18 | 10/19/18 | TA96 | Taylor, Evan R | 0 | 0 | 0 | 0 | 64.26 |  | 0 | 0
998 | Payroll Taxes | PR | 504 | 10/17/18 | 10/19/18 | WE55 | Wennig, Johnathan M | 0 | 0 | 0 | 0 | 68.54 |  | 0 | 0
998 | Payroll Taxes | PR | 733 | 10/24/18 | 10/26/18 | HO14 | Holmes, Anthony R | 0 | 0 | 0 | 0 | 107.1 |  | 0 | 0
998 | Payroll Taxes | PR | 737 | 10/24/18 | 10/26/18 | LE17 | Lee, Ha Nul | 0 | 0 | 0 | 0 | 37.71 |  | 0 | 0
998 | Payroll Taxes | PR | 739 | 10/24/18 | 10/26/18 | LO58 | Lopez Reyes, Boris O | 0 | 0 | 0 | 0 | 44.06 |  | 0 | 0
998 | Payroll Taxes | PR | 744 | 10/24/18 | 10/26/18 | ME52 | Mendoza, Edgar E | 0 | 0 | 0 | 0 | 53.86 |  | 0 | 0
998 | Payroll Taxes | PR | 765 | 10/24/18 | 10/26/18 | TA96 | Taylor, Evan R | 0 | 0 | 0 | 0 | 73.44 |  | 0 | 0
998 | Payroll Taxes | PR | 770 | 10/24/18 | 10/26/18 | WE55 | Wennig, Johnathan M | 0 | 0 | 0 | 0 | 51.41 |  | 0 | 0
998 | Payroll Taxes | PR | 775 | 10/24/18 | 10/26/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 3.83 |  | 0 | 0
998 | Payroll Taxes | PR | 37 | 10/31/18 | 11/02/18 | HO14 | Holmes, Anthony R | 0 | 0 | 0 | 0 | 107.1 |  | 0 | 0
998 | Payroll Taxes | PR | 42 | 10/31/18 | 11/02/18 | LE17 | Lee, Ha Nul | 0 | 0 | 0 | 0 | 52.02 |  | 0 | 0
998 | Payroll Taxes | PR | 44 | 10/31/18 | 11/02/18 | LO58 | Lopez Reyes, Boris O | 0 | 0 | 0 | 0 | 44.06 |  | 0 | 0
998 | Payroll Taxes | PR | 49 | 10/31/18 | 11/02/18 | ME52 | Mendoza, Edgar E | 0 | 0 | 0 | 0 | 63.95 |  | 0 | 0
998 | Payroll Taxes | PR | 68 | 10/31/18 | 11/02/18 | TA96 | Taylor, Evan R | 0 | 0 | 0 | 0 | 73.44 |  | 0 | 0
998 | Payroll Taxes | PR | 76 | 10/31/18 | 11/02/18 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 4.78 |  | 0 | 0
998 | Payroll Taxes | PR | 215 | 11/07/18 | 11/09/18 | HO14 | Holmes, Anthony R | 0 | 0 | 0 | 0 | 107.1 |  | 0 | 0
998 | Payroll Taxes | PR | 220 | 11/07/18 | 11/09/18 | LE17 | Lee, Ha Nul | 0 | 0 | 0 | 0 | 52.02 |  | 0 | 0
998 | Payroll Taxes | PR | 222 | 11/07/18 | 11/09/18 | LO58 | Lopez Reyes, Boris O | 0 | 0 | 0 | 0 | 50.26 |  | 0 | 0
998 | Payroll Taxes | PR | 227 | 11/07/18 | 11/09/18 | ME52 | Mendoza, Edgar E | 0 | 0 | 0 | 0 | 53.86 |  | 0 | 0
998 | Payroll Taxes | PR | 227 | 11/07/18 | 11/09/18 | ME52 | Mendoza, Edgar E | 0 | 0 | 0 | 0 | 13.46 |  | 0 | 0
998 | Payroll Taxes | PR | 248 | 11/07/18 | 11/09/18 | TA96 | Taylor, Evan R | 0 | 0 | 0 | 0 | 73.44 |  | 0 | 0
998 | Payroll Taxes | PR | 252 | 11/07/18 | 11/09/18 | WE55 | Wennig, Johnathan M | 0 | 0 | 0 | 0 | 85.68 |  | 0 | 0
998 | Payroll Taxes | PR | 257 | 11/07/18 | 11/09/18 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 4.78 |  | 0 | 0
998 | Payroll Taxes | PR | 463 | 11/14/18 | 11/16/18 | HO14 | Holmes, Anthony R | 0 | 0 | 0 | 0 | 107.1 |  | 0 | 0
998 | Payroll Taxes | PR | 468 | 11/14/18 | 11/16/18 | LE17 | Lee, Ha Nul | 0 | 0 | 0 | 0 | 52.02 |  | 0 | 0
998 | Payroll Taxes | PR | 470 | 11/14/18 | 11/16/18 | LO58 | Lopez Reyes, Boris O | 0 | 0 | 0 | 0 | 6.89 |  | 0 | 0
998 | Payroll Taxes | PR | 475 | 11/14/18 | 11/16/18 | ME52 | Mendoza, Edgar E | 0 | 0 | 0 | 0 | 53.86 |  | 0 | 0
998 | Payroll Taxes | PR | 475 | 11/14/18 | 11/16/18 | ME52 | Mendoza, Edgar E | 0 | 0 | 0 | 0 | 13.46 |  | 0 | 0
998 | Payroll Taxes | PR | 496 | 11/14/18 | 11/16/18 | TA96 | Taylor, Evan R | 0 | 0 | 0 | 0 | 73.44 |  | 0 | 0
998 | Payroll Taxes | PR | 500 | 11/14/18 | 11/16/18 | WE55 | Wennig, Johnathan M | 0 | 0 | 0 | 0 | 85.68 |  | 0 | 0
998 | Payroll Taxes | PR | 514 | 11/14/18 | 11/16/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 3.83 |  | 0 | 0
998 | Payroll Taxes | PR | 514 | 11/14/18 | 11/16/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 7.65 |  | 0 | 0
998 | Payroll Taxes | PR | 648 | 11/21/18 | 11/21/18 | HO14 | Holmes, Anthony R | 0 | 0 | 0 | 0 | 107.1 |  | 0 | 0
998 | Payroll Taxes | PR | 653 | 11/21/18 | 11/21/18 | LE17 | Lee, Ha Nul | 0 | 0 | 0 | 0 | 52.02 |  | 0 | 0
998 | Payroll Taxes | PR | 659 | 11/21/18 | 11/21/18 | ME52 | Mendoza, Edgar E | 0 | 0 | 0 | 0 | 67.32 |  | 0 | 0
998 | Payroll Taxes | PR | 680 | 11/21/18 | 11/21/18 | TA96 | Taylor, Evan R | 0 | 0 | 0 | 0 | 73.44 |  | 0 | 0
998 | Payroll Taxes | PR | 684 | 11/21/18 | 11/21/18 | WE55 | Wennig, Johnathan M | 0 | 0 | 0 | 0 | 85.68 |  | 0 | 0
998 | Payroll Taxes | PR | 690 | 11/21/18 | 11/21/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 3.83 |  | 0 | 0
998 | Payroll Taxes | PR | 861 | 11/28/18 | 11/30/18 | HO14 | Holmes, Anthony R | 0 | 0 | 0 | 0 | 59.44 |  | 0 | 0
998 | Payroll Taxes | PR | 866 | 11/28/18 | 11/30/18 | LE17 | Lee, Ha Nul | 0 | 0 | 0 | 0 | 46.51 |  | 0 | 0
998 | Payroll Taxes | PR | 872 | 11/28/18 | 11/30/18 | ME52 | Mendoza, Edgar E | 0 | 0 | 0 | 0 | 58.75 |  | 0 | 0
998 | Payroll Taxes | PR | 893 | 11/28/18 | 11/30/18 | TA96 | Taylor, Evan R | 0 | 0 | 0 | 0 | 56.69 |  | 0 | 0
998 | Payroll Taxes | PR | 897 | 11/28/18 | 11/30/18 | WE55 | Wennig, Johnathan M | 0 | 0 | 0 | 0 | 48.2 |  | 0 | 0
998 | Payroll Taxes | PR | 73 | 12/05/18 | 12/07/18 | HO14 | Holmes, Anthony R | 0 | 0 | 0 | 0 | 113.22 |  | 0 | 0
998 | Payroll Taxes | PR | 78 | 12/05/18 | 12/07/18 | LE17 | Lee, Ha Nul | 0 | 0 | 0 | 0 | 58.14 |  | 0 | 0
998 | Payroll Taxes | PR | 84 | 12/05/18 | 12/07/18 | ME52 | Mendoza, Edgar E | 0 | 0 | 0 | 0 | 67.93 |  | 0 | 0
998 | Payroll Taxes | PR | 105 | 12/05/18 | 12/07/18 | TA96 | Taylor, Evan R | 0 | 0 | 0 | 0 | 79.56 |  | 0 | 0
998 | Payroll Taxes | PR | 110 | 12/05/18 | 12/07/18 | WE55 | Wennig, Johnathan M | 0 | 0 | 0 | 0 | 91.8 |  | 0 | 0
998 | Payroll Taxes | PR | 270 | 12/12/18 | 12/14/18 | BA70 | Barnhart, Joseph N | 0 | 0 | 0 | 0 | 7.34 |  | 0 | 0
998 | Payroll Taxes | PR | 297 | 12/12/18 | 12/14/18 | HO14 | Holmes, Anthony R | 0 | 0 | 0 | 0 | 113.22 |  | 0 | 0
998 | Payroll Taxes | PR | 302 | 12/12/18 | 12/14/18 | LE17 | Lee, Ha Nul | 0 | 0 | 0 | 0 | 58.14 |  | 0 | 0
998 | Payroll Taxes | PR | 308 | 12/12/18 | 12/14/18 | ME52 | Mendoza, Edgar E | 0 | 0 | 0 | 0 | 73.44 |  | 0 | 0
998 | Payroll Taxes | PR | 330 | 12/12/18 | 12/14/18 | TA96 | Taylor, Evan R | 0 | 0 | 0 | 0 | 31.82 |  | 0 | 0
998 | Payroll Taxes | PR | 335 | 12/12/18 | 12/14/18 | WE55 | Wennig, Johnathan M | 0 | 0 | 0 | 0 | 36.72 |  | 0 | 0
998 | Payroll Taxes | PR | 338 | 12/12/18 | 12/14/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 3.98 |  | 0 | 0
998 | Payroll Taxes | PR | 538 | 12/19/18 | 12/21/18 | HO14 | Holmes, Anthony R | 0 | 0 | 0 | 0 | 113.22 |  | 0 | 0
998 | Payroll Taxes | PR | 543 | 12/19/18 | 12/21/18 | LE17 | Lee, Ha Nul | 0 | 0 | 0 | 0 | 69.77 |  | 0 | 0
998 | Payroll Taxes | PR | 549 | 12/19/18 | 12/21/18 | ME52 | Mendoza, Edgar E | 0 | 0 | 0 | 0 | 88.13 |  | 0 | 0
998 | Payroll Taxes | PR | 570 | 12/19/18 | 12/21/18 | TA96 | Taylor, Evan R | 0 | 0 | 0 | 0 | 23.87 |  | 0 | 0
998 | Payroll Taxes | PR | 570 | 12/19/18 | 12/21/18 | TA96 | Taylor, Evan R | 0 | 0 | 0 | 0 | 79.56 |  | 0 | 0
998 | Payroll Taxes | PR | 575 | 12/19/18 | 12/21/18 | WE55 | Wennig, Johnathan M | 0 | 0 | 0 | 0 | 110.16 |  | 0 | 0
998 | Payroll Taxes | PR | 577 | 12/19/18 | 12/21/18 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 4.78 |  | 0 | 0
998 | Payroll Taxes | PR | 578 | 12/19/18 | 12/21/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 7.96 |  | 0 | 0
998 | Payroll Taxes | PR | 729 | 12/26/18 | 12/28/18 | HO14 | Holmes, Anthony R | 0 | 0 | 0 | 0 | 67.93 |  | 0 | 0
998 | Payroll Taxes | PR | 734 | 12/26/18 | 12/28/18 | LE17 | Lee, Ha Nul | 0 | 0 | 0 | 0 | 34.88 |  | 0 | 0
998 | Payroll Taxes | PR | 740 | 12/26/18 | 12/28/18 | ME52 | Mendoza, Edgar E | 0 | 0 | 0 | 0 | 41.31 |  | 0 | 0
998 | Payroll Taxes | PR | 761 | 12/26/18 | 12/28/18 | TA96 | Taylor, Evan R | 0 | 0 | 0 | 0 | 31.82 |  | 0 | 0
998 | Payroll Taxes | PR | 766 | 12/26/18 | 12/28/18 | WE55 | Wennig, Johnathan M | 0 | 0 | 0 | 0 | 36.72 |  | 0 | 0
998 | Payroll Taxes | PR | 768 | 12/26/18 | 12/28/18 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 9.56 |  | 0 | 0
998 | Payroll Taxes | PR | 33 | 01/02/19 | 01/04/19 | HO14 | Holmes, Anthony R | 0 | 0 | 0 | 0 | 90.58 |  | 0 | 0
998 | Payroll Taxes | PR | 37 | 01/02/19 | 01/04/19 | LE17 | Lee, Ha Nul | 0 | 0 | 0 | 0 | 34.88 |  | 0 | 0
998 | Payroll Taxes | PR | 43 | 01/02/19 | 01/04/19 | ME52 | Mendoza, Edgar E | 0 | 0 | 0 | 0 | 41.31 |  | 0 | 0
998 | Payroll Taxes | PR | 64 | 01/02/19 | 01/04/19 | TA96 | Taylor, Evan R | 0 | 0 | 0 | 0 | 47.74 |  | 0 | 0
998 | Payroll Taxes | PR | 69 | 01/02/19 | 01/04/19 | WE55 | Wennig, Johnathan M | 0 | 0 | 0 | 0 | 55.08 |  | 0 | 0
998 | Payroll Taxes | PR | 73 | 01/02/19 | 01/04/19 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 3.98 |  | 0 | 0
998 | Payroll Taxes | PR | 241 | 01/09/19 | 01/11/19 | HO14 | Holmes, Anthony R | 0 | 0 | 0 | 0 | 113.22 |  | 0 | 0
998 | Payroll Taxes | PR | 244 | 01/09/19 | 01/11/19 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 14.99 |  | 0 | 0
998 | Payroll Taxes | PR | 253 | 01/09/19 | 01/11/19 | ME52 | Mendoza, Edgar E | 0 | 0 | 0 | 0 | 12.85 |  | 0 | 0
998 | Payroll Taxes | PR | 274 | 01/09/19 | 01/11/19 | TA96 | Taylor, Evan R | 0 | 0 | 0 | 0 | 79.56 |  | 0 | 0
998 | Payroll Taxes | PR | 279 | 01/09/19 | 01/11/19 | WE55 | Wennig, Johnathan M | 0 | 0 | 0 | 0 | 91.8 |  | 0 | 0
998 | Payroll Taxes | PR | 282 | 01/09/19 | 01/11/19 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 3.98 |  | 0 | 0
998 | Payroll Taxes | PR | 282 | 01/09/19 | 01/11/19 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 3.98 |  | 0 | 0
998 | Payroll Taxes | PR | 496 | 01/16/19 | 01/18/19 | HO14 | Holmes, Anthony R | 0 | 0 | 0 | 0 | 113.22 |  | 0 | 0
998 | Payroll Taxes | PR | 529 | 01/16/19 | 01/18/19 | TA96 | Taylor, Evan R | 0 | 0 | 0 | 0 | 79.56 |  | 0 | 0
998 | Payroll Taxes | PR | 534 | 01/16/19 | 01/18/19 | WE55 | Wennig, Johnathan M | 0 | 0 | 0 | 0 | 91.8 |  | 0 | 0
998 | Payroll Taxes | PR | 745 | 01/23/19 | 01/25/19 | HO14 | Holmes, Anthony R | 0 | 0 | 0 | 0 | 113.22 |  | 0 | 0
998 | Payroll Taxes | PR | 778 | 01/23/19 | 01/25/19 | TA96 | Taylor, Evan R | 0 | 0 | 0 | 0 | 79.56 |  | 0 | 0
998 | Payroll Taxes | PR | 783 | 01/23/19 | 01/25/19 | WE55 | Wennig, Johnathan M | 0 | 0 | 0 | 0 | 73.44 |  | 0 | 0
998 | Payroll Taxes | PR | 33 | 01/30/19 | 02/01/19 | HO14 | Holmes, Anthony R | 0 | 0 | 0 | 0 | 113.22 |  | 0 | 0
998 | Payroll Taxes | PR | 63 | 01/30/19 | 02/01/19 | TA96 | Taylor, Evan R | 0 | 0 | 0 | 0 | 79.56 |  | 0 | 0
998 | Payroll Taxes | PR | 68 | 01/30/19 | 02/01/19 | WE55 | Wennig, Johnathan M | 0 | 0 | 0 | 0 | 36.72 |  | 0 | 0
998 | Payroll Taxes | PR | 188 | 02/06/19 | 02/08/19 | HO14 | Holmes, Anthony R | 0 | 0 | 0 | 0 | 22.64 |  | 0 | 0
998 | Payroll Taxes | PR | 188 | 02/06/19 | 02/08/19 | HO14 | Holmes, Anthony R | 0 | 0 | 0 | 0 | 43.87 |  | 0 | 0
998 | Payroll Taxes | PR | 191 | 02/06/19 | 02/08/19 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 7.5 |  | 0 | 0
998 | Payroll Taxes | PR | 219 | 02/06/19 | 02/08/19 | TA96 | Taylor, Evan R | 0 | 0 | 0 | 0 | 47.74 |  | 0 | 0
998 | Payroll Taxes | PR | 350 | 02/13/19 | 02/15/19 | HO14 | Holmes, Anthony R | 0 | 0 | 0 | 0 | 28.31 |  | 0 | 0
998 | Payroll Taxes | PR | 350 | 02/13/19 | 02/15/19 | HO14 | Holmes, Anthony R | 0 | 0 | 0 | 0 | 42.46 |  | 0 | 0
998 | Payroll Taxes | PR | 353 | 02/13/19 | 02/15/19 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 9.37 |  | 0 | 0
998 | Payroll Taxes | PR | 381 | 02/13/19 | 02/15/19 | TA96 | Taylor, Evan R | 0 | 0 | 0 | 0 | 19.89 |  | 0 | 0
998 | Payroll Taxes | PR | 381 | 02/13/19 | 02/15/19 | TA96 | Taylor, Evan R | 0 | 0 | 0 | 0 | 29.84 |  | 0 | 0
998 | Payroll Taxes | PR | 608 | 02/20/19 | 02/22/19 | HO14 | Holmes, Anthony R | 0 | 0 | 0 | 0 | 110.39 |  | 0 | 0
998 | Payroll Taxes | PR | 640 | 02/20/19 | 02/22/19 | TA96 | Taylor, Evan R | 0 | 0 | 0 | 0 | 79.56 |  | 0 | 0
998 | Payroll Taxes | PR | 35 | 02/27/19 | 03/01/19 | HO14 | Holmes, Anthony R | 0 | 0 | 0 | 0 | 113.22 |  | 0 | 0
998 | Payroll Taxes | PR | 67 | 02/27/19 | 03/01/19 | TA96 | Taylor, Evan R | 0 | 0 | 0 | 0 | 79.56 |  | 0 | 0
998 | Payroll Taxes | PR | 75 | 02/27/19 | 03/01/19 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 7.96 |  | 0 | 0
998 | Payroll Taxes | PR | 75 | 02/27/19 | 03/01/19 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 7.96 |  | 0 | 0
998 | Payroll Taxes | PR | 249 | 03/06/19 | 03/08/19 | BA70 | Barnhart, Joseph N | 0 | 0 | 0 | 0 | 7.34 |  | 0 | 0
998 | Payroll Taxes | PR | 260 | 03/06/19 | 03/08/19 | CR87 | Cruz Reyes, Jose | 0 | 0 | 0 | 0 | 87.52 |  | 0 | 0
998 | Payroll Taxes | PR | 275 | 03/06/19 | 03/08/19 | HO14 | Holmes, Anthony R | 0 | 0 | 0 | 0 | 25.47 |  | 0 | 0
998 | Payroll Taxes | PR | 275 | 03/06/19 | 03/08/19 | HO14 | Holmes, Anthony R | 0 | 0 | 0 | 0 | 90.58 |  | 0 | 0
998 | Payroll Taxes | PR | 275 | 03/06/19 | 03/08/19 | HO14 | Holmes, Anthony R | 0 | 0 | 0 | 0 | 22.64 |  | 0 | 0
998 | Payroll Taxes | PR | 278 | 03/06/19 | 03/08/19 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 18.74 |  | 0 | 0
998 | Payroll Taxes | PR | 289 | 03/06/19 | 03/08/19 | MU70 | Murphy, Darray E | 0 | 0 | 0 | 0 | 12.39 |  | 0 | 0
998 | Payroll Taxes | PR | 289 | 03/06/19 | 03/08/19 | MU70 | Murphy, Darray E | 0 | 0 | 0 | 0 | 55.08 |  | 0 | 0
998 | Payroll Taxes | PR | 315 | 03/06/19 | 03/08/19 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 3.98 |  | 0 | 0
998 | Payroll Taxes | PR | 315 | 03/06/19 | 03/08/19 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 7.96 |  | 0 | 0
998 | Payroll Taxes | PR | 507 | 03/13/19 | 03/15/19 | CR87 | Cruz Reyes, Jose | 0 | 0 | 0 | 0 | 8.95 |  | 0 | 0
998 | Payroll Taxes | PR | 507 | 03/13/19 | 03/15/19 | CR87 | Cruz Reyes, Jose | 0 | 0 | 0 | 0 | 89.51 |  | 0 | 0
998 | Payroll Taxes | PR | 522 | 03/13/19 | 03/15/19 | HO14 | Holmes, Anthony R | 0 | 0 | 0 | 0 | 33.97 |  | 0 | 0
998 | Payroll Taxes | PR | 522 | 03/13/19 | 03/15/19 | HO14 | Holmes, Anthony R | 0 | 0 | 0 | 0 | 113.22 |  | 0 | 0
998 | Payroll Taxes | PR | 536 | 03/13/19 | 03/15/19 | MU70 | Murphy, Darray E | 0 | 0 | 0 | 0 | 24.79 |  | 0 | 0
998 | Payroll Taxes | PR | 721 | 03/20/19 | 03/22/19 | CR87 | Cruz Reyes, Jose | 0 | 0 | 0 | 0 | 23.87 |  | 0 | 0
998 | Payroll Taxes | PR | 721 | 03/20/19 | 03/22/19 | CR87 | Cruz Reyes, Jose | 0 | 0 | 0 | 0 | 79.56 |  | 0 | 0
998 | Payroll Taxes | PR | 736 | 03/20/19 | 03/22/19 | HO14 | Holmes, Anthony R | 0 | 0 | 0 | 0 | 33.97 |  | 0 | 0
998 | Payroll Taxes | PR | 736 | 03/20/19 | 03/22/19 | HO14 | Holmes, Anthony R | 0 | 0 | 0 | 0 | 113.22 |  | 0 | 0
998 | Payroll Taxes | PR | 776 | 03/20/19 | 03/22/19 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 4.78 |  | 0 | 0
998 | Payroll Taxes | PR | 777 | 03/20/19 | 03/22/19 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 3.98 |  | 0 | 0
998 | Payroll Taxes | PR | 932 | 03/27/19 | 03/29/19 | CR87 | Cruz Reyes, Jose | 0 | 0 | 0 | 0 | 11.93 |  | 0 | 0
998 | Payroll Taxes | PR | 932 | 03/27/19 | 03/29/19 | CR87 | Cruz Reyes, Jose | 0 | 0 | 0 | 0 | 5.97 |  | 0 | 0
998 | Payroll Taxes | PR | 932 | 03/27/19 | 03/29/19 | CR87 | Cruz Reyes, Jose | 0 | 0 | 0 | 0 | 63.65 |  | 0 | 0
998 | Payroll Taxes | PR | 932 | 03/27/19 | 03/29/19 | CR87 | Cruz Reyes, Jose | 0 | 0 | 0 | 0 | 15.91 |  | 0 | 0
998 | Payroll Taxes | PR | 948 | 03/27/19 | 03/29/19 | HO14 | Holmes, Anthony R | 0 | 0 | 0 | 0 | 55.19 |  | 0 | 0
998 | Payroll Taxes | PR | 948 | 03/27/19 | 03/29/19 | HO14 | Holmes, Anthony R | 0 | 0 | 0 | 0 | 8.49 |  | 0 | 0
998 | Payroll Taxes | PR | 948 | 03/27/19 | 03/29/19 | HO14 | Holmes, Anthony R | 0 | 0 | 0 | 0 | 90.58 |  | 0 | 0
998 | Payroll Taxes | PR | 948 | 03/27/19 | 03/29/19 | HO14 | Holmes, Anthony R | 0 | 0 | 0 | 0 | 22.64 |  | 0 | 0
998 | Payroll Taxes | PR | 111 | 04/03/19 | 04/05/19 | HO14 | Holmes, Anthony R | 0 | 0 | 0 | 0 | 8.49 |  | 0 | 0
998 | Payroll Taxes | PR | 111 | 04/03/19 | 04/05/19 | HO14 | Holmes, Anthony R | 0 | 0 | 0 | 0 | 45.29 |  | 0 | 0
998 | Payroll Taxes | PR | 524 | 04/17/19 | 04/19/19 | BA70 | Barnhart, Joseph N | 0 | 0 | 0 | 0 | 11.48 |  | 0 | 0
998 | Payroll Taxes | PR | 555 | 04/17/19 | 04/19/19 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 7.65 |  | 0 | 0
998 | Payroll Taxes | PR | 564 | 04/17/19 | 04/19/19 | MC09 | McCabe, Thomas C | 0 | 0 | 0 | 0 | 20.2 |  | 0 | 0
998 | Payroll Taxes | PR | 771 | 04/24/19 | 04/26/19 | HO14 | Holmes, Anthony R | 0 | 0 | 0 | 0 | 36.72 |  | 0 | 0
998 | Payroll Taxes | PR | 771 | 04/24/19 | 04/26/19 | HO14 | Holmes, Anthony R | 0 | 0 | 0 | 0 | 6.12 |  | 0 | 0
998 | Payroll Taxes | PR | 774 | 04/24/19 | 04/26/19 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 15.3 |  | 0 | 0
998 | Payroll Taxes | PR | 783 | 04/24/19 | 04/26/19 | MC09 | McCabe, Thomas C | 0 | 0 | 0 | 0 | 20.08 |  | 0 | 0
998 | Payroll Taxes | PR | 783 | 04/24/19 | 04/26/19 | MC09 | McCabe, Thomas C | 0 | 0 | 0 | 0 | 56.23 |  | 0 | 0
998 | Payroll Taxes | PR | 783 | 04/24/19 | 04/26/19 | MC09 | McCabe, Thomas C | 0 | 0 | 0 | 0 | 50.87 |  | 0 | 0
998 | Payroll Taxes | PR | 797 | 04/24/19 | 04/26/19 | SA54 | Sanders, Allen O | 0 | 0 | 0 | 0 | 9.37 |  | 0 | 0
998 | Payroll Taxes | PR | 799 | 04/24/19 | 04/26/19 | SE64 | Sepulveda Gonzalez, Alfredo | 0 | 0 | 0 | 0 | 64.26 |  | 0 | 0
998 | Payroll Taxes | PR | 812 | 04/24/19 | 04/26/19 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 9.56 |  | 0 | 0
998 | Payroll Taxes | PR | 39 | 05/01/19 | 05/03/19 | HO14 | Holmes, Anthony R | 0 | 0 | 0 | 0 | 4.59 |  | 0 | 0
998 | Payroll Taxes | PR | 39 | 05/01/19 | 05/03/19 | HO14 | Holmes, Anthony R | 0 | 0 | 0 | 0 | 10.71 |  | 0 | 0
998 | Payroll Taxes | PR | 42 | 05/01/19 | 05/03/19 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 22.95 |  | 0 | 0
998 | Payroll Taxes | PR | 42 | 05/01/19 | 05/03/19 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 7.65 |  | 0 | 0
998 | Payroll Taxes | PR | 45 | 05/01/19 | 05/03/19 | KI55 | Kinssies, Jr, John E | 0 | 0 | 0 | 0 | 17.14 |  | 0 | 0
998 | Payroll Taxes | PR | 52 | 05/01/19 | 05/03/19 | MC09 | McCabe, Thomas C | 0 | 0 | 0 | 0 | 32.13 |  | 0 | 0
998 | Payroll Taxes | PR | 52 | 05/01/19 | 05/03/19 | MC09 | McCabe, Thomas C | 0 | 0 | 0 | 0 | 64.26 |  | 0 | 0
998 | Payroll Taxes | PR | 52 | 05/01/19 | 05/03/19 | MC09 | McCabe, Thomas C | 0 | 0 | 0 | 0 | 42.84 |  | 0 | 0
998 | Payroll Taxes | PR | 66 | 05/01/19 | 05/03/19 | SA54 | Sanders, Allen O | 0 | 0 | 0 | 0 | 24.37 |  | 0 | 0
998 | Payroll Taxes | PR | 68 | 05/01/19 | 05/03/19 | SE64 | Sepulveda Gonzalez, Alfredo | 0 | 0 | 0 | 0 | 32.13 |  | 0 | 0
998 | Payroll Taxes | PR | 68 | 05/01/19 | 05/03/19 | SE64 | Sepulveda Gonzalez, Alfredo | 0 | 0 | 0 | 0 | 53.55 |  | 0 | 0
998 | Payroll Taxes | PR | 70 | 05/01/19 | 05/03/19 | ST02 | Stahlschmidt, John P | 0 | 0 | 0 | 0 | 11.63 |  | 0 | 0
998 | Payroll Taxes | PR | 73 | 05/01/19 | 05/03/19 | TR60 | Trower-Kelly, Fidel D | 0 | 0 | 0 | 0 | 22.03 |  | 0 | 0
998 | Payroll Taxes | PR | 74 | 05/01/19 | 05/03/19 | VA98 | Vazquez Popoca, Jose N | 0 | 0 | 0 | 0 | 29.38 |  | 0 | 0
998 | Payroll Taxes | PR | 81 | 05/01/19 | 05/03/19 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 9.56 |  | 0 | 0
998 | Payroll Taxes | PR | 195 | 05/08/19 | 05/10/19 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 38.25 |  | 0 | 0
998 | Payroll Taxes | PR | 195 | 05/08/19 | 05/10/19 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 7.65 |  | 0 | 0
998 | Payroll Taxes | PR | 198 | 05/08/19 | 05/10/19 | KI55 | Kinssies, Jr, John E | 0 | 0 | 0 | 0 | 42.84 |  | 0 | 0
998 | Payroll Taxes | PR | 205 | 05/08/19 | 05/10/19 | MC09 | McCabe, Thomas C | 0 | 0 | 0 | 0 | 101.75 |  | 0 | 0
998 | Payroll Taxes | PR | 215 | 05/08/19 | 05/10/19 | RO06 | Roberts, Lake A | 0 | 0 | 0 | 0 | 16.83 |  | 0 | 0
998 | Payroll Taxes | PR | 219 | 05/08/19 | 05/10/19 | SA54 | Sanders, Allen O | 0 | 0 | 0 | 0 | 22.49 |  | 0 | 0
998 | Payroll Taxes | PR | 223 | 05/08/19 | 05/10/19 | ST02 | Stahlschmidt, John P | 0 | 0 | 0 | 0 | 11.63 |  | 0 | 0
998 | Payroll Taxes | PR | 226 | 05/08/19 | 05/10/19 | TR60 | Trower-Kelly, Fidel D | 0 | 0 | 0 | 0 | 33.05 |  | 0 | 0
998 | Payroll Taxes | PR | 227 | 05/08/19 | 05/10/19 | VA98 | Vazquez Popoca, Jose N | 0 | 0 | 0 | 0 | 39.17 |  | 0 | 0
998 | Payroll Taxes | PR | 411 | 05/15/19 | 05/17/19 | EL33 | Eliassen, Cory H | 0 | 0 | 0 | 0 | 16.52 |  | 0 | 0
998 | Payroll Taxes | PR | 427 | 05/15/19 | 05/17/19 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 34.43 |  | 0 | 0
998 | Payroll Taxes | PR | 430 | 05/15/19 | 05/17/19 | KI55 | Kinssies, Jr, John E | 0 | 0 | 0 | 0 | 59.98 |  | 0 | 0
998 | Payroll Taxes | PR | 437 | 05/15/19 | 05/17/19 | MC09 | McCabe, Thomas C | 0 | 0 | 0 | 0 | 94.38 |  | 0 | 0
998 | Payroll Taxes | PR | 447 | 05/15/19 | 05/17/19 | RO06 | Roberts, Lake A | 0 | 0 | 0 | 0 | 18.36 |  | 0 | 0
998 | Payroll Taxes | PR | 447 | 05/15/19 | 05/17/19 | RO06 | Roberts, Lake A | 0 | 0 | 0 | 0 | 6.12 |  | 0 | 0
998 | Payroll Taxes | PR | 451 | 05/15/19 | 05/17/19 | SA54 | Sanders, Allen O | 0 | 0 | 0 | 0 | 11.25 |  | 0 | 0
998 | Payroll Taxes | PR | 455 | 05/15/19 | 05/17/19 | ST02 | Stahlschmidt, John P | 0 | 0 | 0 | 0 | 11.63 |  | 0 | 0
998 | Payroll Taxes | PR | 458 | 05/15/19 | 05/17/19 | TR60 | Trower-Kelly, Fidel D | 0 | 0 | 0 | 0 | 48.2 |  | 0 | 0
998 | Payroll Taxes | PR | 459 | 05/15/19 | 05/17/19 | VA98 | Vazquez Popoca, Jose N | 0 | 0 | 0 | 0 | 42.84 |  | 0 | 0
998 | Payroll Taxes | PR | 639 | 05/22/19 | 05/24/19 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 38.25 |  | 0 | 0
998 | Payroll Taxes | PR | 642 | 05/22/19 | 05/24/19 | KI55 | Kinssies, Jr, John E | 0 | 0 | 0 | 0 | 74.97 |  | 0 | 0
998 | Payroll Taxes | PR | 649 | 05/22/19 | 05/24/19 | MC09 | McCabe, Thomas C | 0 | 0 | 0 | 0 | 42.84 |  | 0 | 0
998 | Payroll Taxes | PR | 663 | 05/22/19 | 05/24/19 | SA54 | Sanders, Allen O | 0 | 0 | 0 | 0 | 24.37 |  | 0 | 0
998 | Payroll Taxes | PR | 670 | 05/22/19 | 05/24/19 | TR60 | Trower-Kelly, Fidel D | 0 | 0 | 0 | 0 | 48.88 |  | 0 | 0
998 | Payroll Taxes | PR | 671 | 05/22/19 | 05/24/19 | VA98 | Vazquez Popoca, Jose N | 0 | 0 | 0 | 0 | 43.45 |  | 0 | 0
998 | Payroll Taxes | PR | 881 | 05/29/19 | 05/31/19 | BA70 | Barnhart, Joseph N | 0 | 0 | 0 | 0 | 3.83 |  | 0 | 0
998 | Payroll Taxes | PR | 897 | 05/29/19 | 05/31/19 | EL33 | Eliassen, Cory H | 0 | 0 | 0 | 0 | 39.24 |  | 0 | 0
998 | Payroll Taxes | PR | 913 | 05/29/19 | 05/31/19 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 11.48 |  | 0 | 0
998 | Payroll Taxes | PR | 916 | 05/29/19 | 05/31/19 | KI55 | Kinssies, Jr, John E | 0 | 0 | 0 | 0 | 51.41 |  | 0 | 0
998 | Payroll Taxes | PR | 937 | 05/29/19 | 05/31/19 | SA54 | Sanders, Allen O | 0 | 0 | 0 | 0 | 13.12 |  | 0 | 0
998 | Payroll Taxes | PR | 944 | 05/29/19 | 05/31/19 | TR60 | Trower-Kelly, Fidel D | 0 | 0 | 0 | 0 | 22.03 |  | 0 | 0
998 | Payroll Taxes | PR | 945 | 05/29/19 | 05/31/19 | VA98 | Vazquez Popoca, Jose N | 0 | 0 | 0 | 0 | 39.17 |  | 0 | 0
998 | Payroll Taxes | PR | 953 | 05/29/19 | 05/31/19 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 4.21 |  | 0 | 0
998 | Payroll Taxes | PR | 46 | 06/05/19 | 06/07/19 | KI55 | Kinssies, Jr, John E | 0 | 0 | 0 | 0 | 94.86 |  | 0 | 0
998 | Payroll Taxes | PR | 183 | 06/05/19 | 06/07/19 | BA70 | Barnhart, Joseph N | 0 | 0 | 0 | 0 | 11.48 |  | 0 | 0
998 | Payroll Taxes | PR | 199 | 06/05/19 | 06/07/19 | EL33 | Eliassen, Cory H | 0 | 0 | 0 | 0 | 45.44 |  | 0 | 0
998 | Payroll Taxes | PR | 215 | 06/05/19 | 06/07/19 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 21.04 |  | 0 | 0
998 | Payroll Taxes | PR | 239 | 06/05/19 | 06/07/19 | SA54 | Sanders, Allen O | 0 | 0 | 0 | 0 | 7.5 |  | 0 | 0
998 | Payroll Taxes | PR | 246 | 06/05/19 | 06/07/19 | TR60 | Trower-Kelly, Fidel D | 0 | 0 | 0 | 0 | 44.06 |  | 0 | 0
998 | Payroll Taxes | PR | 247 | 06/05/19 | 06/07/19 | VA98 | Vazquez Popoca, Jose N | 0 | 0 | 0 | 0 | 29.38 |  | 0 | 0
998 | Payroll Taxes | PR | 255 | 06/05/19 | 06/07/19 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 8.42 |  | 0 | 0
998 | Payroll Taxes | PR | 469 | 06/12/19 | 06/14/19 | EL33 | Eliassen, Cory H | 0 | 0 | 0 | 0 | 66.1 |  | 0 | 0
998 | Payroll Taxes | PR | 483 | 06/12/19 | 06/14/19 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 30.6 |  | 0 | 0
998 | Payroll Taxes | PR | 483 | 06/12/19 | 06/14/19 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 38.25 |  | 0 | 0
998 | Payroll Taxes | PR | 486 | 06/12/19 | 06/14/19 | KI55 | Kinssies, Jr, John E | 0 | 0 | 0 | 0 | 87.15 |  | 0 | 0
998 | Payroll Taxes | PR | 493 | 06/12/19 | 06/14/19 | MC09 | McCabe, Thomas C | 0 | 0 | 0 | 0 | 107.1 |  | 0 | 0
998 | Payroll Taxes | PR | 508 | 06/12/19 | 06/14/19 | SE64 | Sepulveda Gonzalez, Alfredo | 0 | 0 | 0 | 0 | 107.1 |  | 0 | 0
998 | Payroll Taxes | PR | 514 | 06/12/19 | 06/14/19 | TR60 | Trower-Kelly, Fidel D | 0 | 0 | 0 | 0 | 11.02 |  | 0 | 0
998 | Payroll Taxes | PR | 515 | 06/12/19 | 06/14/19 | VA98 | Vazquez Popoca, Jose N | 0 | 0 | 0 | 0 | 9.79 |  | 0 | 0
998 | Payroll Taxes | PR | 523 | 06/12/19 | 06/14/19 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 14.34 |  | 0 | 0
998 | Payroll Taxes | PR | 524 | 06/12/19 | 06/14/19 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 4.21 |  | 0 | 0
998 | Payroll Taxes | PR | 639 | 06/19/19 | 06/21/19 | EL33 | Eliassen, Cory H | 0 | 0 | 0 | 0 | 68.16 |  | 0 | 0
998 | Payroll Taxes | PR | 654 | 06/19/19 | 06/21/19 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 38.25 |  | 0 | 0
998 | Payroll Taxes | PR | 654 | 06/19/19 | 06/21/19 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 30.6 |  | 0 | 0
998 | Payroll Taxes | PR | 657 | 06/19/19 | 06/21/19 | KI55 | Kinssies, Jr, John E | 0 | 0 | 0 | 0 | 75.89 |  | 0 | 0
998 | Payroll Taxes | PR | 664 | 06/19/19 | 06/21/19 | MC09 | McCabe, Thomas C | 0 | 0 | 0 | 0 | 85.68 |  | 0 | 0
998 | Payroll Taxes | PR | 679 | 06/19/19 | 06/21/19 | SE64 | Sepulveda Gonzalez, Alfredo | 0 | 0 | 0 | 0 | 107.1 |  | 0 | 0
998 | Payroll Taxes | PR | 693 | 06/19/19 | 06/21/19 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 9.56 |  | 0 | 0
998 | Payroll Taxes | PR | 694 | 06/19/19 | 06/21/19 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 4.21 |  | 0 | 0
998 | Payroll Taxes | PR | 857 | 06/26/19 | 06/28/19 | EL33 | Eliassen, Cory H | 0 | 0 | 0 | 0 | 59.9 |  | 0 | 0
998 | Payroll Taxes | PR | 872 | 06/26/19 | 06/28/19 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 30.6 |  | 0 | 0
998 | Payroll Taxes | PR | 896 | 06/26/19 | 06/28/19 | SE64 | Sepulveda Gonzalez, Alfredo | 0 | 0 | 0 | 0 | 101.75 |  | 0 | 0
998 | Payroll Taxes | PR | 44 | 07/03/19 | 07/05/19 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 22.95 |  | 0 | 0
998 | Payroll Taxes | PR | 46 | 07/03/19 | 07/05/19 | KI55 | Kinssies, Jr, John E | 0 | 0 | 0 | 0 | 9.49 |  | 0 | 0
998 | Payroll Taxes | PR | 67 | 07/03/19 | 07/05/19 | SE64 | Sepulveda Gonzalez, Alfredo | 0 | 0 | 0 | 0 | 10.71 |  | 0 | 0
998 | Payroll Taxes | PR | 67 | 07/03/19 | 07/05/19 | SE64 | Sepulveda Gonzalez, Alfredo | 0 | 0 | 0 | 0 | 32.13 |  | 0 | 0
998 | Payroll Taxes | PR | 81 | 07/03/19 | 07/05/19 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 4.78 |  | 0 | 0
998 | Payroll Taxes | PR | 282 | 07/10/19 | 07/12/19 | BA70 | Barnhart, Joseph N | 0 | 0 | 0 | 0 | 7.65 |  | 0 | 0
998 | Payroll Taxes | PR | 298 | 07/10/19 | 07/12/19 | EL33 | Eliassen, Cory H | 0 | 0 | 0 | 0 | 24.79 |  | 0 | 0
998 | Payroll Taxes | PR | 528 | 07/17/19 | 07/19/19 | EL33 | Eliassen, Cory H | 0 | 0 | 0 | 0 | 39.24 |  | 0 | 0
998 | Payroll Taxes | PR | 543 | 07/17/19 | 07/19/19 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 7.65 |  | 0 | 0
998 | Payroll Taxes | PR | 543 | 07/17/19 | 07/19/19 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 19.13 |  | 0 | 0
998 | Payroll Taxes | PR | 543 | 07/17/19 | 07/19/19 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 7.65 |  | 0 | 0
998 | Payroll Taxes | PR | 552 | 07/17/19 | 07/19/19 | MC09 | McCabe, Thomas C | 0 | 0 | 0 | 0 | 10.71 |  | 0 | 0
998 | Payroll Taxes | PR | 552 | 07/17/19 | 07/19/19 | MC09 | McCabe, Thomas C | 0 | 0 | 0 | 0 | 32.13 |  | 0 | 0
998 | Payroll Taxes | PR | 585 | 07/17/19 | 07/19/19 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 9.56 |  | 0 | 0
998 | Payroll Taxes | PR | 586 | 07/17/19 | 07/19/19 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 4.21 |  | 0 | 0
998 | Payroll Taxes | PR | 632 | 07/24/19 | 07/26/19 | EL33 | Eliassen, Cory H | 0 | 0 | 0 | 0 | 24.79 |  | 0 | 0
998 | Payroll Taxes | PR | 646 | 07/24/19 | 07/26/19 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 11.48 |  | 0 | 0
998 | Payroll Taxes | PR | 646 | 07/24/19 | 07/26/19 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 7.65 |  | 0 | 0
998 | Payroll Taxes | PR | 655 | 07/24/19 | 07/26/19 | MC09 | McCabe, Thomas C | 0 | 0 | 0 | 0 | 26.78 |  | 0 | 0
998 | Payroll Taxes | PR | 655 | 07/24/19 | 07/26/19 | MC09 | McCabe, Thomas C | 0 | 0 | 0 | 0 | 40.16 |  | 0 | 0
998 | Payroll Taxes | PR | 655 | 07/24/19 | 07/26/19 | MC09 | McCabe, Thomas C | 0 | 0 | 0 | 0 | 13.39 |  | 0 | 0
998 | Payroll Taxes | PR | 655 | 07/24/19 | 07/26/19 | MC09 | McCabe, Thomas C | 0 | 0 | 0 | 0 | 21.42 |  | 0 | 0
998 | Payroll Taxes | PR | 670 | 07/24/19 | 07/26/19 | SA54 | Sanders, Allen O | 0 | 0 | 0 | 0 | 7.5 |  | 0 | 0
998 | Payroll Taxes | PR | 685 | 07/24/19 | 07/26/19 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 14.34 |  | 0 | 0
998 | Payroll Taxes | PR | 686 | 07/24/19 | 07/26/19 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 4.21 |  | 0 | 0
998 | Payroll Taxes | PR | 24 | 07/31/19 | 08/02/19 | EL33 | Eliassen, Cory H | 0 | 0 | 0 | 0 | 80.55 |  | 0 | 0
998 | Payroll Taxes | PR | 38 | 07/31/19 | 08/02/19 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 3.83 |  | 0 | 0
998 | Payroll Taxes | PR | 61 | 07/31/19 | 08/02/19 | SA54 | Sanders, Allen O | 0 | 0 | 0 | 0 | 7.5 |  | 0 | 0
998 | Payroll Taxes | PR | 68 | 07/31/19 | 08/02/19 | TR60 | Trower-Kelly, Fidel D | 0 | 0 | 0 | 0 | 13.77 |  | 0 | 0
998 | Payroll Taxes | PR | 276 | 08/07/19 | 08/09/19 | EL33 | Eliassen, Cory H | 0 | 0 | 0 | 0 | 88.82 |  | 0 | 0
998 | Payroll Taxes | PR | 291 | 08/07/19 | 08/09/19 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 3.83 |  | 0 | 0
998 | Payroll Taxes | PR | 291 | 08/07/19 | 08/09/19 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 38.25 |  | 0 | 0
998 | Payroll Taxes | PR | 300 | 08/07/19 | 08/09/19 | MC09 | McCabe, Thomas C | 0 | 0 | 0 | 0 | 42.84 |  | 0 | 0
998 | Payroll Taxes | PR | 300 | 08/07/19 | 08/09/19 | MC09 | McCabe, Thomas C | 0 | 0 | 0 | 0 | 5.36 |  | 0 | 0
998 | Payroll Taxes | PR | 300 | 08/07/19 | 08/09/19 | MC09 | McCabe, Thomas C | 0 | 0 | 0 | 0 | 16.07 |  | 0 | 0
998 | Payroll Taxes | PR | 314 | 08/07/19 | 08/09/19 | SA54 | Sanders, Allen O | 0 | 0 | 0 | 0 | 37.49 |  | 0 | 0
998 | Payroll Taxes | PR | 320 | 08/07/19 | 08/09/19 | TR60 | Trower-Kelly, Fidel D | 0 | 0 | 0 | 0 | 35.8 |  | 0 | 0
998 | Payroll Taxes | PR | 328 | 08/07/19 | 08/09/19 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 9.56 |  | 0 | 0
998 | Payroll Taxes | PR | 607 | 08/14/19 | 08/16/19 | MC09 | McCabe, Thomas C | 0 | 0 | 0 | 0 | 21.42 |  | 0 | 0
998 | Payroll Taxes | PR | 621 | 08/14/19 | 08/16/19 | SA54 | Sanders, Allen O | 0 | 0 | 0 | 0 | 26.24 |  | 0 | 0
998 | Payroll Taxes | PR | 819 | 08/21/19 | 08/23/19 | EL33 | Eliassen, Cory H | 0 | 0 | 0 | 0 | 6.2 |  | 0 | 0
998 | Payroll Taxes | PR | 835 | 08/21/19 | 08/23/19 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 3.83 |  | 0 | 0
998 | Payroll Taxes | PR | 835 | 08/21/19 | 08/23/19 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 7.65 |  | 0 | 0
998 | Payroll Taxes | PR | 844 | 08/21/19 | 08/23/19 | MC09 | McCabe, Thomas C | 0 | 0 | 0 | 0 | 74.97 |  | 0 | 0
998 | Payroll Taxes | PR | 844 | 08/21/19 | 08/23/19 | MC09 | McCabe, Thomas C | 0 | 0 | 0 | 0 | 10.71 |  | 0 | 0
998 | Payroll Taxes | PR | 1026 | 08/28/19 | 08/30/19 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 3.83 |  | 0 | 0
998 | Payroll Taxes | PR | 1049 | 08/28/19 | 08/30/19 | SA54 | Sanders, Allen O | 0 | 0 | 0 | 0 | 3.75 |  | 0 | 0
998 | Payroll Taxes | PR | 1064 | 08/28/19 | 08/30/19 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 4.78 |  | 0 | 0
998 | Payroll Taxes | PR | 1064 | 08/28/19 | 08/30/19 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 4.78 |  | 0 | 0
998 | Payroll Taxes | PR | 70 | 09/04/19 | 09/06/19 | SA54 | Sanders, Allen O | 0 | 0 | 0 | 0 | 5.62 |  | 0 | 0
998 | Payroll Taxes | PR | 531 | 09/18/19 | 09/20/19 | SA54 | Sanders, Allen O | 0 | 0 | 0 | 0 | 14.99 |  | 0 | 0
999 | Sales | AR | 593 | 02/21/18 | 02/21/18 | 2044BC | Blueprint Capital Services, LLC $66th |  |  |  |  | -37400 | 037032 | 0 | 0
999 | Sales | AR | 593 | 02/21/18 | 02/21/18 | 2044BC | Blueprint Capital Services, LLC $66th |  |  |  |  | -8150 | 037032 | 0 | 0
999 | Sales | AR | 431 | 03/20/18 | 03/20/18 | 2044BC | Blueprint Capital Services, LLC $66th |  |  |  |  | -12090 | 037036 | 0 | 0
999 | Sales | AR | 431 | 03/20/18 | 03/20/18 | 2044BC | Blueprint Capital Services, LLC $66th |  |  |  |  | -25720 | 037036 | 0 | 0
999 | Sales | AR | 431 | 03/20/18 | 03/20/18 | 2044BC | Blueprint Capital Services, LLC $66th |  |  |  |  | -25600 | 037036 | 0 | 0
999 | Sales | AR | 432 | 03/20/18 | 03/20/18 | 2044BC | Blueprint Capital Services, LLC $66th |  |  |  |  | -27500 | 037037 | 0 | 0
999 | Sales | AR | 448 | 03/20/18 | 03/20/18 | 2044BC | Blueprint Capital Services, LLC $66th |  |  |  |  | 12090 | 037052 | 0 | 0
999 | Sales | AR | 448 | 03/20/18 | 03/20/18 | 2044BC | Blueprint Capital Services, LLC $66th |  |  |  |  | 25720 | 037052 | 0 | 0
999 | Sales | AR | 448 | 03/20/18 | 03/20/18 | 2044BC | Blueprint Capital Services, LLC $66th |  |  |  |  | 25600 | 037052 | 0 | 0
999 | Sales | AR | 502 | 05/18/18 | 05/18/18 | 2044BC | Blueprint Capital Services, LLC $66th |  |  |  |  | -3000 | 037080 | 0 | 0
999 | Sales | AR | 502 | 05/18/18 | 05/18/18 | 2044BC | Blueprint Capital Services, LLC $66th |  |  |  |  | -4000 | 037080 | 0 | 0
999 | Sales | AR | 502 | 05/18/18 | 05/18/18 | 2044BC | Blueprint Capital Services, LLC $66th |  |  |  |  | -6000 | 037080 | 0 | 0
999 | Sales | AR | 525 | 07/20/18 | 07/20/18 | 2044BC | Blueprint Capital Services, LLC $66th |  |  |  |  | -17300 | 037137 | 0 | 0
999 | Sales | AR | 590 | 08/20/18 | 08/20/18 | 2044BC | Blueprint Capital Services, LLC $66th |  |  |  |  | -11850 | 037161 | 0 | 0
999 | Sales | AR | 590 | 08/20/18 | 08/20/18 | 2044BC | Blueprint Capital Services, LLC $66th |  |  |  |  | -36540 | 037161 | 0 | 0
999 | Sales | AR | 590 | 08/20/18 | 08/20/18 | 2044BC | Blueprint Capital Services, LLC $66th |  |  |  |  | -11100 | 037161 | 0 | 0
999 | Sales | AR | 590 | 08/20/18 | 08/20/18 | 2044BC | Blueprint Capital Services, LLC $66th |  |  |  |  | -5325 | 037161 | 0 | 0
999 | Sales | AR | 473 | 09/19/18 | 09/19/18 | 2044BC | Blueprint Capital Services, LLC $66th |  |  |  |  | -37750 | 037189 | 0 | 0
999 | Sales | AR | 473 | 09/19/18 | 09/19/18 | 2044BC | Blueprint Capital Services, LLC $66th |  |  |  |  | -41525 | 037189 | 0 | 0
999 | Sales | AR | 473 | 09/19/18 | 09/19/18 | 2044BC | Blueprint Capital Services, LLC $66th |  |  |  |  | -37750 | 037189 | 0 | 0
999 | Sales | AR | 473 | 09/19/18 | 09/19/18 | 2044BC | Blueprint Capital Services, LLC $66th |  |  |  |  | -15100 | 037189 | 0 | 0
999 | Sales | AR | 473 | 09/19/18 | 09/19/18 | 2044BC | Blueprint Capital Services, LLC $66th |  |  |  |  | 4841 | 037189 | 0 | 0
999 | Sales | AR | 473 | 09/19/18 | 09/19/18 | 2044BC | Blueprint Capital Services, LLC $66th |  |  |  |  | -4000 | 037189 | 0 | 0
999 | Sales | AR | 528 | 10/19/18 | 10/19/18 | 2044BC | Blueprint Capital Services, LLC $66th |  |  |  |  | -11750 | 037214 | 0 | 0
999 | Sales | AR | 528 | 10/19/18 | 10/19/18 | 2044BC | Blueprint Capital Services, LLC $66th |  |  |  |  | -43450 | 037214 | 0 | 0
999 | Sales | AR | 528 | 10/19/18 | 10/19/18 | 2044BC | Blueprint Capital Services, LLC $66th |  |  |  |  | -7550 | 037214 | 0 | 0
999 | Sales | AR | 528 | 10/19/18 | 10/19/18 | 2044BC | Blueprint Capital Services, LLC $66th |  |  |  |  | -7550 | 037214 | 0 | 0
999 | Sales | AR | 528 | 10/19/18 | 10/19/18 | 2044BC | Blueprint Capital Services, LLC $66th |  |  |  |  | -22650 | 037214 | 0 | 0
999 | Sales | AR | 528 | 10/19/18 | 10/19/18 | 2044BC | Blueprint Capital Services, LLC $66th |  |  |  |  | -45300 | 037214 | 0 | 0
999 | Sales | AR | 528 | 10/19/18 | 10/19/18 | 2044BC | Blueprint Capital Services, LLC $66th |  |  |  |  | -37750 | 037214 | 0 | 0
999 | Sales | AR | 528 | 10/19/18 | 10/19/18 | 2044BC | Blueprint Capital Services, LLC $66th |  |  |  |  | -11652 | 037214 | 0 | 0
999 | Sales | AR | 528 | 10/19/18 | 10/19/18 | 2044BC | Blueprint Capital Services, LLC $66th |  |  |  |  | -2209 | 037214 | 0 | 0
999 | Sales | AR | 525 | 11/16/18 | 11/16/18 | 2044BC | Blueprint Capital Services, LLC $66th |  |  |  |  | -7550 | 037231 | 0 | 0
999 | Sales | AR | 525 | 11/16/18 | 11/16/18 | 2044BC | Blueprint Capital Services, LLC $66th |  |  |  |  | -7550 | 037231 | 0 | 0
999 | Sales | AR | 525 | 11/16/18 | 11/16/18 | 2044BC | Blueprint Capital Services, LLC $66th |  |  |  |  | -7550 | 037231 | 0 | 0
999 | Sales | AR | 525 | 11/16/18 | 11/16/18 | 2044BC | Blueprint Capital Services, LLC $66th |  |  |  |  | -30200 | 037231 | 0 | 0
999 | Sales | AR | 525 | 11/16/18 | 11/16/18 | 2044BC | Blueprint Capital Services, LLC $66th |  |  |  |  | -16375 | 037231 | 0 | 0
999 | Sales | AR | 353 | 12/14/18 | 12/14/18 | 2044BC | Blueprint Capital Services, LLC $66th |  |  |  |  | -7050 | 037256 | 0 | 0
999 | Sales | AR | 353 | 12/14/18 | 12/14/18 | 2044BC | Blueprint Capital Services, LLC $66th |  |  |  |  | -26070 | 037256 | 0 | 0
999 | Sales | AR | 353 | 12/14/18 | 12/14/18 | 2044BC | Blueprint Capital Services, LLC $66th |  |  |  |  | -16240 | 037256 | 0 | 0
999 | Sales | AR | 353 | 12/14/18 | 12/14/18 | 2044BC | Blueprint Capital Services, LLC $66th |  |  |  |  | -7550 | 037256 | 0 | 0
999 | Sales | AR | 353 | 12/14/18 | 12/14/18 | 2044BC | Blueprint Capital Services, LLC $66th |  |  |  |  | -13100 | 037256 | 0 | 0
999 | Sales | AR | 559 | 01/18/19 | 01/18/19 | 2044BC | Blueprint Capital Services, LLC $66th |  |  |  |  | -2350 | 037277 | 0 | 0
999 | Sales | AR | 559 | 01/18/19 | 01/18/19 | 2044BC | Blueprint Capital Services, LLC $66th |  |  |  |  | -17380 | 037277 | 0 | 0
999 | Sales | AR | 559 | 01/18/19 | 01/18/19 | 2044BC | Blueprint Capital Services, LLC $66th |  |  |  |  | -8120 | 037277 | 0 | 0
999 | Sales | AR | 559 | 01/18/19 | 01/18/19 | 2044BC | Blueprint Capital Services, LLC $66th |  |  |  |  | -7550 | 037277 | 0 | 0
999 | Sales | AR | 559 | 01/18/19 | 01/18/19 | 2044BC | Blueprint Capital Services, LLC $66th |  |  |  |  | -7550 | 037277 | 0 | 0
999 | Sales | AR | 559 | 01/18/19 | 01/18/19 | 2044BC | Blueprint Capital Services, LLC $66th |  |  |  |  | -7550 | 037277 | 0 | 0
999 | Sales | AR | 559 | 01/18/19 | 01/18/19 | 2044BC | Blueprint Capital Services, LLC $66th |  |  |  |  | -7550 | 037277 | 0 | 0
999 | Sales | AR | 559 | 01/18/19 | 01/18/19 | 2044BC | Blueprint Capital Services, LLC $66th |  |  |  |  | -7550 | 037277 | 0 | 0
999 | Sales | AR | 559 | 01/18/19 | 01/18/19 | 2044BC | Blueprint Capital Services, LLC $66th |  |  |  |  | -3275 | 037277 | 0 | 0
999 | Sales | AR | 566 | 02/20/19 | 02/20/19 | 2044BC | Blueprint Capital Services, LLC $66th |  |  |  |  | -27000 | 037288 | 0 | 0
999 | Sales | AR | 566 | 02/20/19 | 02/20/19 | 2044BC | Blueprint Capital Services, LLC $66th |  |  |  |  | -2350 | 037288 | 0 | 0
999 | Sales | AR | 508 | 05/20/19 | 05/20/19 | 2044BC | Blueprint Capital Services, LLC $66th |  |  |  |  | -7900 | 037341 | 0 | 0
999 | Sales | AR | 508 | 05/20/19 | 05/20/19 | 2044BC | Blueprint Capital Services, LLC $66th |  |  |  |  | -9000 | 037341 | 0 | 0
999 | Sales | AR | 508 | 05/20/19 | 05/20/19 | 2044BC | Blueprint Capital Services, LLC $66th |  |  |  |  | -16250 | 037341 | 0 | 0
999 | Sales | AR | 508 | 05/20/19 | 05/20/19 | 2044BC | Blueprint Capital Services, LLC $66th |  |  |  |  | -16250 | 037341 | 0 | 0
999 | Sales | AR | 508 | 05/20/19 | 05/20/19 | 2044BC | Blueprint Capital Services, LLC $66th |  |  |  |  | -16250 | 037341 | 0 | 0
999 | Sales | AR | 508 | 05/20/19 | 05/20/19 | 2044BC | Blueprint Capital Services, LLC $66th |  |  |  |  | -16250 | 037341 | 0 | 0
999 | Sales | AR | 508 | 05/20/19 | 05/20/19 | 2044BC | Blueprint Capital Services, LLC $66th |  |  |  |  | 5154 | 037341 | 0 | 0
999 | Sales | AR | 508 | 05/20/19 | 05/20/19 | 2044BC | Blueprint Capital Services, LLC $66th |  |  |  |  | -11790 | 037341 | 0 | 0
999 | Sales | AR | 613 | 06/19/19 | 06/19/19 | 2044BC | Blueprint Capital Services, LLC $66th |  |  |  |  | -8800 | 037369 | 0 | 0
999 | Sales | AR | 613 | 06/19/19 | 06/19/19 | 2044BC | Blueprint Capital Services, LLC $66th |  |  |  |  | -16250 | 037369 | 0 | 0
999 | Sales | AR | 613 | 06/19/19 | 06/19/19 | 2044BC | Blueprint Capital Services, LLC $66th |  |  |  |  | -708 | 037369 | 0 | 0
999 | Sales | AR | 602 | 07/19/19 | 07/19/19 | 2044BC | Blueprint Capital Services, LLC $66th |  |  |  |  | -8700 | 037377 | 0 | 0
999 | Sales | AR | 602 | 07/19/19 | 07/19/19 | 2044BC | Blueprint Capital Services, LLC $66th |  |  |  |  | -3500 | 037377 | 0 | 0
999 | Sales | AR | 753 | 08/20/19 | 08/15/19 | 2044BC | Blueprint Capital Services, LLC $66th |  |  |  |  | -650 | 037390 | 0 | 0
999 | Sales | AR | 756 | 08/20/19 | 08/15/19 | 2044BC | Blueprint Capital Services, LLC $66th |  |  |  |  | 650 | 037393 | 0 | 0
999 | Sales | AR | 757 | 08/20/19 | 08/15/19 | 2044BC | Blueprint Capital Services, LLC $66th |  |  |  |  | -650 | 037394 | 0 | 0
999 | Sales | AR | 757 | 08/20/19 | 08/15/19 | 2044BC | Blueprint Capital Services, LLC $66th |  |  |  |  | -1350 | 037394 | 0 | 0

## Crew Roster
CREW ROSTER — 24 WORKERS
Per-worker hours + wages grouped by tier (APPRENTICE / JOURNEYMAN / LEAD / OT-ONLY). nominal_rate = regular_amount ÷ regular_hours. Mirrors Sam Worker Wages tab.
Tier | Worker (Last, First) | Reg Hours | OT Hours | DT Hours | Reg Amount | OT Amount | Nominal Rate ($/hr)
APPRENTICE/HELPER | Vazquez Popoca, Jose N | 190.5 | 0 | 0 | 3048 | 0 | 16
APPRENTICE/HELPER | Lee, Ha Nul | 739.25 | 0 | 0 | 12983.25 | 0 | 17.5627
APPRENTICE/HELPER | Lopez Reyes, Boris O | 448.5 | 2 | 0 | 8073 | 54 | 18
APPRENTICE/HELPER | Murphy, Darray E | 58 | 6 | 0 | 1044 | 162 | 18
APPRENTICE/HELPER | Trower-Kelly, Fidel D | 202.5 | 0 | 0 | 3645 | 0 | 18
APPRENTICE/HELPER | Stahlschmidt, John P | 24 | 0 | 0 | 456 | 0 | 19
JOURNEYMAN | Roberts, Lake A | 27 | 0 | 0 | 540 | 0 | 20
JOURNEYMAN | Mendoza, Edgar E | 700.5 | 0 | 0 | 15829 | 0 | 22.5967
JOURNEYMAN | Taylor, Evan R | 1153.5 | 8 | 0 | 28591 | 312 | 24.7863
JOURNEYMAN | Cruz Reyes, Jose | 169 | 17 | 0 | 4394 | 663 | 26
JOURNEYMAN | Eliassen, Cory H | 271 | 0 | 0 | 7317 | 0 | 27
JOURNEYMAN | Kinssies, Jr, John E | 311.25 | 0 | 0 | 8886.25 | 0 | 28.5502
JOURNEYMAN | Wennig, Johnathan M | 779.5 | 0 | 0 | 22383 | 0 | 28.7146
JOURNEYMAN | Garcia, Jordan X | 2.5 | 0 | 0 | 80 | 0 | 32
JOURNEYMAN | McCabe, Thomas C | 367.25 | 13 | 0 | 12837.75 | 682.5 | 34.9564
JOURNEYMAN | Sepulveda Gonzalez, Alfredo | 190 | 0 | 0 | 6650 | 0 | 35
JOURNEYMAN | Holmes, Anthony R | 1416 | 48 | 0 | 50908.5 | 2704.5 | 35.9523
LEAD/SUPERVISOR | Waites, Thaddeus Z | 123.5 | 0 | 0 | 5187 | 0 | 42
LEAD/SUPERVISOR | Anderson, Richard P | 68.5 | 1 | 0 | 2880.5 | 64.5 | 42.0511
LEAD/SUPERVISOR | Barnhart, Joseph N | 63.5 | 2 | 0 | 2904 | 150 | 45.7323
LEAD/SUPERVISOR | Sanders, Allen O | 57.5 | 0 | 0 | 2817.5 | 0 | 49
LEAD/SUPERVISOR | Hubbard, Robert W | 147 | 0 | 0 | 7336.5 | 0 | 49.9082
LEAD/SUPERVISOR | Gerard, Jeffrey S | 62 | 0 | 0 | 3130 | 0 | 50.4839
LEAD/SUPERVISOR | Donelson, Richard T | 53.5 | 0 | 0 | 3318.75 | 0 | 62.0327

## Wage Tiers
WAGE TIERS & PERCENTILES — 2044
Tier distribution + percentile snapshot across worker_nominal_wages. Tier thresholds: Apprentice <$20, Journeyman $20–$36, Lead $36+. OT-only = no regular hours booked.
Tier | Worker Count | Total Reg Hours | Total OT Hours | Total Labor $ | Avg Nominal Rate
APPRENTICE/HELPER | 6 | 1662.75 | 8 | 29465.25 | 17.7605
JOURNEYMAN | 11 | 5387.5 | 86 | 162778.5 | 28.687
LEAD/SUPERVISOR | 7 | 575.5 | 3 | 27788.75 | 48.744
PERCENTILES (nominal wage)
Percentile | Rate
p10 | 18
p25 | 19.75
p50 | 28.63
p75 | 42.01
p90 | 49.64
WAGE METHODOLOGY (Sam v4 Action #3)
Metric | Value | Formula
straight_time_rate | 28.2254 | SUM(regular_amount) / SUM(regular_hours)
pr_src_cost_per_hr | 43.3071 | PR total / total_labor_hours (includes OT premium)
fully_loaded_wage | 58.1227 | (PR + 995 + 998) / total_labor_hours
burden_multiplier | 1.3421 | fully_loaded / pr_src_cost_per_hr

## Productivity
PRODUCTIVITY METRICS — 2044
Labor throughput + unit-economics indicators. Per-unit / per-fixture / per-month now populated from GDrive-enriched project attributes.
Metric | Value | Formula / Notes
Total Labor Hours | 7,722.75 | SUM(reg+ot+dt+other) where source=PR
Revenue per Labor Hour | $110.75 | abs(revenue) ÷ labor hours — throughput
Labor Unit Cost per Hour | $28.36 | Labor-code JTD ÷ labor hours
Revenue ÷ Labor-Cost Ratio | 3.90x | Throughput ÷ unit cost — productivity signal
Units (residential) | 75 | Track 66 Apartments scope doc: 68 Type B + 7 Type A ADA
Fixtures (estimate) | 634 | Scope doc estimate — see Job Info fixture_estimate_note
Duration (months) | 24 | start_date → end_date from GDrive enrichment
Hours per Unit | 102.97 | total_labor_hours ÷ units
Hours per Fixture | 12.18 | total_labor_hours ÷ fixtures
Revenue per Unit | $11,404 | revenue ÷ units
Profit per Unit | $3,552 | net_profit ÷ units
Hours per Month | 322 | total_labor_hours ÷ duration_months
Revenue per Month | $35,636 | revenue ÷ duration_months

## Vendor Analysis
VENDOR ANALYSIS — 17 VENDORS ($216,975 AP)
AP-source vendor spend concentration. Sorted by descending spend. Top-vendor % surfaces concentration risk. Matches Sam derived_field.top_vendor_spend.
Rank | Vendor | Spend | Invoice Count | Avg Invoice | % of AP | Net Due | Retainage
1 | Keller Supply Company | 59482.56 | 26 | 2287.7908 | 27.41% | 0 | 0
2 | Rosen Supply Kirkland | 47454.86 | 57 | 832.5414 | 21.87% | 0 | 0
3 | Best Bath Systems | 36061.49 | 3 | 12020.4967 | 16.62% | 0 | 0
4 | Franklin Engineering | 25565 | 11 | 2324.0909 | 11.78% | 0 | 0
5 | Consolidated Supply Co. | 20046.51 | 19 | 1055.0795 | 9.239% | 0 | 0
6 | Capital One Credit Card | 8902.53 | 26 | 342.405 | 4.103% | 0 | 0
7 | Ferguson Enterprises, Inc. #3007 | 8007.38 | 5 | 1601.476 | 3.69% | 0 | 0
8 | California Hydronics Corp | 4101 | 3 | 1367 | 1.89% | 0 | 0
9 | Mechanical Resource Services, Inc. | 3750 | 1 | 3750 | 1.728% | 0 | 0
10 | Rosen Supply Company, Inc. $66th Apts | 1317.75 | 4 | 329.4375 | 0.6073% | 0 | 0
11 | Mechanical Service & Integration LLC | 800 | 1 | 800 | 0.3687% | 0 | 0
12 | Ahern Rentals | 644.09 | 3 | 214.6967 | 0.2969% | 0 | 0
13 | Mechanical Sales, Inc. | 317.79 | 2 | 158.895 | 0.1465% | 0 | 0
14 | Consolidated Supply Co. $66th Apts | 197.94 | 1 | 197.94 | 0.09123% | 0 | 0
15 | DRSi | 160.44 | 3 | 53.48 | 0.07394% | 0 | 0
16 | A.R. Brown Backflow Testing | 150 | 1 | 150 | 0.06913% | 0 | 0
17 | Fastenal Company | 15.19 | 1 | 15.19 | 0.007001% | 0 | 0

## Change Orders
CHANGE ORDER LOG — 2044
CO / COR register reconciled against internal Budget Transfer xlsx files in the Change Orders/BUDGET TRANSFERS/ GDrive folder. Executed CO sum ties to JDR-implied CO within $90.
CO # | COR # | Description | Amount | Status | Signed PDF
1 | BT CO#01 | Delete 2 Common Area Baths (credit) | -4841 | executed | Y
2 | BT CO#02 | Remove kitchen sinks from scope (credit — kitchen sinks by others) | -5154 | executed | Y
3 | BT CO#03 | Best Bath Shower Pans & Stalls (upgrade from base) | 11652 | executed | Y
4 | BT CO#04 | Matte Black Delta Trinsic Fixtures (upgrade) | 11790 | executed | Y
5 | BT CO#05 | Supply loose drains, cast iron in bathroom dropped lids (added scope) | 6209 | executed | Y
6 | BT CO#06 | Amenity Lav Upgrade (common area lav/faucet change) | 708 | executed | Y
7 | BT CO#07 | Canopy Drain (entrance canopy with piping within canopy) | 650 | executed | Y
8 | BT CO#08 | Add Sink L7 (L7 Kitchen Faucet added) | 1350 | executed | Y
Executed subtotal |  |  | 22364
Budget-transfer total (incl. extras) |  |  | 22364
JDR-implied CO (revenue − original contract) |  |  | 22364
Reconciliation gap |  |  | 0
UNEXECUTED / SUPERSEDED COR_s
COR # | Description

## Project Team
PROJECT TEAM — 2044
Primary contacts extracted from Track 66 Apartments project start-up PDF + signed subcontract.
Role | Name | Email | Phone
GC Project Manager | Andrew Withnell | TBD | TBD
GC Superintendent | Scott McSpadden / Stefan Fjeldsted | TBD | TBD
OWP Signatory | Mike Donelson (OWP Dir Const / VP per signed subcontract) | mike@onewayplumbing.com | 425-968-8314
Architect | TBD — per Plans: Franklin Engineering MEP; Blueprint design-build
Owner | Blueprint 836, LLC (self-build: developer, GC, and owner entity shared)
Inspecting Authority | City of Seattle (DCI)

## Document Pipeline
DOCUMENT PIPELINE — 2044
Quantitative document counts from the Track 66 Apartments GDrive close-out package — used by the Cortex dashboard for CO/RFI/Submittal density metrics.
Category | Count | Source folder
Executed Change Orders | 8 | Change Orders/CO_s/ + BUDGET TRANSFERS/
CORs submitted | 10 | Change Orders/COR_s/
Budget transfer entries | 8 | Change Orders/BUDGET TRANSFERS/
ASI / RFI responses | 0 | ASI-RFI/
Submittals | 2 | Submittals/ (PDF count)
POs — placed | 10 | PO_s/1 Placed/
POs — scheduled | 31 | PO_s/2 Scheduled/
POs — completed | 69 | PO_s/3 Completed/
POs — total | 110 | PO_s/ (all three subfolders)
Vendor invoices | 133 | Invoices/
Lien releases | 0 | Billing/ (LUNA Ave Lien Release #1–19 minus gaps)
Permits issued | 4 | Permits/
Backcharges | 0 | Change Orders/COR_s/ (COR #11 Damaged Scissor Lift)

## Benchmarks & Derived
BENCHMARKS & DERIVED FIELDS — 2044
All 45+ derived values that Sam Test-Labels v4 ships — carried forward field-for-field. Sections: cost-by-source, labor analytics, material analytics, phase analytics, budget/forecast.
COST-BY-SOURCE ROLLUPS
Field | Value | Formula / Logic
cost_by_source_pr_amount | 334449.89 | SUM(line_items where source=PR)
cost_by_source_ap_amount | 216974.53 | SUM(line_items where source=AP)
cost_by_source_gl_amount | 37461.19 | SUM(line_items where source=GL)
direct_cost | 588885.61 | PR + AP + GL
net_profit | 266378.39 | abs(revenue) − direct_cost
pr_pct_of_revenue | 0.39105 | PR / abs(revenue)
ap_pct_of_revenue | 0.25369 | AP / abs(revenue)
direct_cost_pct_of_revenue | 0.68854 | direct / abs(revenue)
LABOR ANALYTICS
Field | Value | Formula / Logic
total_labor_hours | 7722.75 | SUM(reg+ot+dt+other) source=PR
pr_src_cost_per_hr | 43.3071 | PR / labor hours
fully_loaded_wage | 58.1227 | (PR + burden) / labor hours
burden_multiplier | 1.3421 | fully_loaded / pr_src
straight_time_rate | 28.2254 | SUM(reg_amount) / SUM(reg_hours)
total_workers | 24 | COUNT DISTINCT(name) source=PR
burden_total | 114417.39 | SUM(actual) codes 995+998
wage_percentiles (p10/p25/p50/p75/p90) | $18.00 ¦ $19.75 ¦ $28.63 ¦ $42.01 ¦ $49.64 | Percentile snapshot across worker_nominal_wages
MATERIAL ANALYTICS
Field | Value | Formula / Logic
material_spend_total | 216377.88 | SUM(actual) codes 2xx
material_budget_total | 279401 | SUM(current_budget) codes 2xx
material_codes_tracked | 9 | COUNT material codes
material_codes_over_budget | 2 | COUNT where plus_minus > 0
material_codes_under_budget | 7 | COUNT where plus_minus ≤ 0
largest_material_overrun | 242 Mech Room Material: $15,511 vs $12,500 budget (+$3,011) | Material code with largest +plus_minus
largest_material_savings | 230 Finish Material: $133,693 vs $163,316 budget ($-29,623) | Material code with largest −plus_minus
material_vendor_count | 17 | COUNT DISTINCT vendors source=AP
top_vendor_spend | Keller Supply Company: $59,483 (27% of AP) | Vendor with highest AP spend
PHASE ANALYTICS
Field | Value | Formula / Logic
phases_over_budget | 10 | COUNT codes where plus_minus>0 (excl 999)
phases_under_budget | 16 | COUNT codes where plus_minus≤0 (excl 999)
largest_overrun | 120 Roughin Labor: $150,429 vs $98,690 budget (+$51,739) | Phase with largest +plus_minus
largest_savings | 230 Finish Material: $133,693 vs $163,316 budget ($-29,623) | Phase with largest −plus_minus
BUDGET & FORECAST
Field | Value | Formula / Logic
total_jtd_cost | 588885.61 | SUM(actual) expense codes
total_budget | 630744.79 | SUM(current_budget) expense codes
overall_pct_budget_consumed | 0.9336 | JTD / budget
total_over_under_budget | 41859.18 | budget − JTD
labor_unit_cost_per_hr | 28.3609 | Labor JTD / labor hours
revenue_per_labor_hour | 110.746 | abs(revenue) / labor hours
material_price_variance | 63023.12 | mat_budget − mat_spend
variance_trend | N/A (single snapshot) | Requires prior-period comparison
PROJECT-LEVEL BENCHMARKS (pending)
Field | Value | Formula / Logic
project_duration_months | PENDING | (end_date − start_date) / 30.4
scope_benchmarks | PENDING | One object per scope_metrics entry

## Predictive Signals
PREDICTIVE SIGNALS — 2044
Rule-based health indicators derived from the parsed data. Green = good, yellow = watch, red = flag.
Signal | Status | Value | Threshold / Notes
Gross margin | GREEN | 31.1% | Green >25%, Yellow 10–25%, Red <10%
Phases over budget | YELLOW | 10/26 | Red >50%, Yellow 25–50%, Green <25%
Material price variance | GREEN | $63,023 | Positive = under material budget
Burden multiplier | GREEN | 1.34x | Normal range 1.25–1.45x (OWP)
Revenue per labor hour | GREEN | $110.75 | Green >$100, Yellow $70–$100, Red <$70
Retainage outstanding | GREEN | $0 | Monitor for collection
Top vendor concentration | GREEN | 27.4% (Keller Supply Company) | Yellow >50% (single-vendor risk)
Unused-budget codes | GREEN | 0 codes | Codes with budget but no spend

## Insights
KEY INSIGHTS — 2044
Narrative rollup — the 10 most important things a Cortex user should know about this job at a glance.
01 | Revenue billed $855,264, net profit $266,378 at 31.1% margin.
02 | Parsed 1,670 transactions across 29 cost codes — reconciliation PASS on all codes.
03 | 24 distinct PR-booked workers over 7,723 labor hours ($43.31/hr PR-src, $58.12/hr fully-loaded, 1.34x burden).
04 | Largest phase overrun: 120 Roughin Labor: $150,429 vs $98,690 budget (+$51,739).
05 | Largest phase savings: 230 Finish Material: $133,693 vs $163,316 budget ($-29,623).
06 | Material spend $216,378 vs budget $279,401 ($63,023 favorable).
07 | Top AP vendor: Keller Supply Company: $59,483 (27% of AP); 17 total AP vendors.
08 | Retainage outstanding: $0.
09 | 10 of 26 expense phases over budget ($41,859 net vs budget).
10 | Revenue per labor hour $110.75, labor unit cost $28.36 (ratio 3.90x).

## Reconciliation
RECONCILIATION — PER COST CODE
Parsed line-item sums vs. Cost Code Totals row in the JDR. Matches Sam Reconciliation tab 1:1. Overall status: 27/27 codes tie to the cent.
Code | Description | PDF Total | Parsed Sum | Difference | Status
100 | Supervision | 1590.75 | 1590.75 | 0 | ✓
101 | Takeoff & Purchase Labor | 4858 | 4858 | 0 | ✓
110 | Underground Labor | 3411.5 | 3411.5 | 0 | ✓
111 | Garage Labor | 200 | 200 | 0 | ✓
112 | Canout Labor | 3108.5 | 3108.5 | 0 | ✓
120 | Roughin Labor | 150429.23 | 150429.23 | 0 | ✓
130 | Finish Labor | 17219.5 | 17219.5 | 0 | ✓
140 | Gas Labor | 4551.5 | 4551.5 | 0 | ✓
141 | Water Main/Insulation Lab | 23970.37 | 23970.37 | 0 | ✓
142 | Mech Room Labor | 9685 | 9685 | 0 | ✓
210 | Underground Material | 1317.75 | 1317.75 | 0 | ✓
211 | Garage Material | 2172.87 | 2172.87 | 0 | ✓
212 | Canout Material | 5102.82 | 5102.82 | 0 | ✓
220 | Roughin Material | 42382.13 | 42382.13 | 0 | ✓
230 | Finish Material | 133693.08 | 133693.08 | 0 | ✓
240 | Gas Material | 2098.38 | 2098.38 | 0 | ✓
241 | Water Main/Insulation Mat | 14099.66 | 14099.66 | 0 | ✓
242 | Mech Room Material | 15511.19 | 15511.19 | 0 | ✓
243 | Condensation Drains Mat | 0 | 0 | 0 | ✓
600 | Subcontractor | 3900 | 3900 | 0 | ✓
601 | Engineering/Plans | 25725.44 | 25725.44 | 0 | ✓
602 | Rental Equipment | 644.09 | 644.09 | 0 | ✓
603 | Permits & Licenses | 695 | 695 | 0 | ✓
607 | Other Expenses | 8101.46 | 8101.46 | 0 | ✓
995 | Payroll Burden | 97584.65 | 97584.65 | 0 | ✓
998 | Payroll Taxes | 16832.74 | 16832.74 | 0 | ✓
999 | Sales | -855264 | -855264 | 0 | ✓
RESULT: 27/27 codes reconciled

## Reconciliation Log
RECONCILIATION LOG — JOB 2044
Worked example of the Reconciliation Protocol running against Job 2044 (JCR-only, no external cross-checks). Mirrors Sam Test-Labels v4 Reconciliation Log tab.
check_id | field_name | JCR-derived value | cross-check value | cross-check source | status | notes
RC-01 | plus_minus_budget | 120 Roughin Labor: $150,429 vs $98,690 budget (+$51,739) | actual − current_budget reconciled per code | Cost Code Summaries (internal recomputation) | PASS | Action #1 sign convention: positive = over-budget. Spot-check recomputes plus_minus from actual − current_budget; matches PDF to the cent.
RC-02 | current_budget / original_budget | current_budget total = $630,745; original_budget also carried per cost code | Budget totals sum across expense codes (code != 999) | BVA tab (Original vs Current columns) | PASS | Both budgets carried distinctly per Action #2. Current budget differs from original on codes that had change orders.
RC-03 | pr_src_cost_per_hr | $43.31/hr (all PR-source cost ÷ total labor hours) | Manual recomputation: PR total $334,449.89 ÷ 7,722.75 hrs | Derived Fields tab (line items → source=PR) | PASS | Phase-code filter: include all phases incl. 995 burden and 998 taxes; exclude only 999 Sales.
RC-04 | worker_nominal_wages / nominal_wage_percentiles | p10=$18.00 ¦ p25=$19.75 ¦ p50=$28.63 ¦ p75=$42.01 ¦ p90=$49.64 (24 workers) | straight_time_rate $28.23 falls within p25–p75 band | Crew Roster tab | PASS | Population-slice sanity: weighted straight_time_rate falls within the p25–p75 range, expected for this workforce composition.
RC-05 | labor_unit_cost_per_hr vs revenue_per_labor_hour | cost $28.36/hr ¦ revenue $110.75/hr ¦ ratio 3.90x | Recompute from labor-code JTD ÷ labor hours | Productivity tab (Action #7 split) | PASS | Split into two fields per Action #7. Cost and throughput are distinct metrics; their ratio is the productivity signal.
RC-06 | scope_metrics / scope_benchmarks | pending | — | project-attribute input (trade-declared) | PENDING | Awaiting plumbing scope-metric declarations for Job 2044 (fixture count, DFU total, linear feet of main). Same status as Job 2020.
RC-07 | reconciliation (per-code parse tie-out) | 27/27 codes tie to PDF to the cent | PR $334,449.89 + AP $216,974.53 + GL $37,461.19 = $588,885.61 matches direct cost | Reconciliation tab | PASS | Independent sum of line_items[] by cost_code vs. Cost Code Totals row for each code. PASS if ¦diff¦ < $0.02 for all codes.
SUMMARY
Total checks | 7
PASS | 6
PENDING | 1
FAIL | 0

## Metric Registry
METRIC REGISTRY — 2044
Canonical registry of every named metric in the workbook. Acts as a machine-readable table of contents + field dictionary. Every Sam Test-Labels v4 field has a row here.
Key | Label | Value | Source / Notes
job_number | Job Number | 2044 | JDR cover page
job_name | Job Name | Blueprint Track 66 Apts | JDR cover page
general_contractor | General Contractor | Blueprint | From AR client code
report_date | Report Date | 2026-04-03 | JDR run date
line_items_count | Line Item Count | 1670 | Length of line_items[]
cost_code_count | Cost Code Count | 27 | Length of cost_code_summaries[]
job_totals_revenue | Revenue (AR, negative) | -855264 | Sage stores credit as negative
job_totals_revenue_abs | Revenue (absolute) | 855264 | abs(job_totals_revenue)
job_totals_expenses | Expenses | 588885.61 | Sage job_totals_expenses
job_totals_net | Net | -266378.39 | Sage job_totals_net
job_totals_retainage | Retainage | 0 | Sage job_totals_retainage
job_totals_net_due | Net Due | 0 | Sage job_totals_net_due
cost_by_source_pr_amount | PR Source Amount | 334449.89 | SUM(line_items source=PR)
cost_by_source_ap_amount | AP Source Amount | 216974.53 | SUM(line_items source=AP)
cost_by_source_gl_amount | GL Source Amount | 37461.19 | SUM(line_items source=GL)
cost_by_source_ar_amount | AR Source Amount | -855264 | SUM(line_items source=AR)
direct_cost | Direct Cost | 588885.61 | PR + AP + GL
net_profit | Net Profit | 266378.39 | abs(revenue) − direct_cost
gross_margin_pct | Gross Margin % | 31.15% | net / abs(revenue)
labor_cost | Labor Cost (codes 1xx) | 219024.35 | SUM(actual) category=Labor
material_cost | Material Cost (codes 2xx) | 216377.88 | SUM(actual) category=Material
overhead_cost | Overhead Cost (codes 6xx) | 39065.99 | SUM(actual) category=Overhead
burden_cost | Burden Cost (995+998) | 114417.39 | SUM(actual) category=Burden
total_labor_hours | Total Labor Hours | 7722.75 | SUM(reg+ot+dt+other) source=PR
total_workers | Total Workers | 24 | COUNT DISTINCT(name) source=PR
straight_time_rate | Straight-Time Rate | 28.2254 | reg_amount ÷ reg_hours
pr_src_cost_per_hr | PR-Source Cost/Hour | 43.3071 | PR total ÷ labor hours
fully_loaded_wage | Fully-Loaded Wage | 58.1227 | (PR + burden) ÷ labor hours
burden_multiplier | Burden Multiplier | 1.3421 | fully-loaded ÷ pr-src
burden_total | Burden Total | 114417.39 | SUM(actual) codes 995+998
wage_percentile_p10 | Wage Percentile p10 | 18 | Percentile across workers
wage_percentile_p25 | Wage Percentile p25 | 19.75 | Percentile across workers
wage_percentile_p50 | Wage Percentile p50 | 28.63 | Percentile across workers
wage_percentile_p75 | Wage Percentile p75 | 42.01 | Percentile across workers
wage_percentile_p90 | Wage Percentile p90 | 49.64 | Percentile across workers
material_spend_total | Material Spend Total | 216377.88 | SUM(actual) codes 2xx
material_budget_total | Material Budget Total | 279401 | SUM(current_budget) codes 2xx
material_codes_tracked | Material Codes Tracked | 9 | COUNT codes 2xx
material_codes_over_budget | Material Codes Over Budget | 2 | COUNT where plus_minus>0
material_codes_under_budget | Material Codes Under Budget | 7 | COUNT where plus_minus≤0
material_vendor_count | Material Vendor Count | 17 | COUNT DISTINCT vendors
material_price_variance | Material Price Variance | 63023.12 | mat_budget − mat_spend
largest_material_overrun | Largest Material Overrun | 242 Mech Room Material: $15,511 vs $12,500 budget (+$3,011)
largest_material_savings | Largest Material Savings | 230 Finish Material: $133,693 vs $163,316 budget ($-29,623)
top_vendor_spend | Top Vendor Spend | Keller Supply Company: $59,483 (27% of AP)
phases_over_budget | Phases Over Budget | 10 | COUNT codes (excl 999)
phases_under_budget | Phases Under Budget | 16 | COUNT codes (excl 999)
largest_overrun | Largest Overrun | 120 Roughin Labor: $150,429 vs $98,690 budget (+$51,739)
largest_savings | Largest Savings | 230 Finish Material: $133,693 vs $163,316 budget ($-29,623)
total_jtd_cost | Total JTD Cost | 588885.61 | SUM(actual) expense codes
total_budget | Total Current Budget | 630744.79 | SUM(current_budget) expense codes
overall_pct_budget_consumed | Overall % Budget Consumed | 93.36% | JTD ÷ budget
total_over_under_budget | Total Over/Under Budget | 41859.18 | budget − JTD
labor_unit_cost_per_hr | Labor Unit Cost / Hour | 28.3609 | labor JTD ÷ labor hours
revenue_per_labor_hour | Revenue per Labor Hour | 110.746 | abs(revenue) ÷ labor hours
unit_count | Unit Count | PENDING | Project-attribute input required
fixture_count | Fixture Count | PENDING | Project-attribute input required
project_start_date | Project Start Date | PENDING | Project-attribute input required
project_end_date | Project End Date | PENDING | Project-attribute input required
duration_months | Duration (months) | PENDING | Project-attribute input required
scope_metrics | Scope Metrics | PENDING | Trade-declared {label, count, desc} array