## Overview
Job #2044 · Blueprint Track 66 Apartments (aka Roosevelt 66th, 838 NE 66th)
Cortex JCR v2 • Blueprint (customer 2044SH) • 838 NE 66th Street, Seattle, WA 98115 • Owner: Blueprint 836, LLC (self-build: developer, GC, and owner entity shared)
PROJECT OVERVIEW
Project Job # | 2044 |  | 2044 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
Project Name (Sage) | Blueprint Track 66 Apts |  | 2044 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
Project Description | Track 66 Apartments — 75-unit 7-story midrise multi-family (4 Type A ADA), Seattle |  | OWP Project List with Schedule - UPDATED 04-01-26.xlsx + contract
General Contractor | Blueprint |  | OWP Project List with Schedule - UPDATED 04-01-26.xlsx
Customer Code (Sage) | 2044SH |  | 2044 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
Owner / Developer | Blueprint 836, LLC (self-build: developer, GC, and owner entity shared) |  | OWP Project List with Schedule - UPDATED 04-01-26.xlsx
GC PM | Andrew Withnell |  | 2044-Shelter Holdings subcontract SC-03-07-6505 + Boren & Spruce CO docs
GC Superintendent | Scott McSpadden / Stefan Fjeldsted |  | 2044-Shelter Holdings subcontract SC-03-07-6505 + Boren & Spruce CO docs
GC PE | N/A |  | 2044-Shelter Holdings subcontract SC-03-07-6505 + Boren & Spruce CO docs
OWP Signatory | Mike Donelson (OWP Dir Const / VP per signed subcontract) |  | 2044-Shelter Holdings subcontract SC-03-07-6505 + Boren & Spruce CO docs
Jobsite Location | 838 NE 66th Street, Seattle, WA 98115 |  | OWP Project List with Schedule - UPDATED 04-01-26.xlsx
Insurance | Not Wrap |  | OWP Project List with Schedule - UPDATED 04-01-26.xlsx
Fixture Schedule | 634 fixtures total (656 unit + 98 retail/common) |  | Submittal Table of Contents + Plumbing Scope
Architect | TBD — per Plans: Franklin Engineering MEP; Blueprint design-build |  | Track 66 Apartments project info.pdf
Contract Type | Lump Sum |  | 2044-Shelter Holdings subcontract SC-03-07-6505 + Boren & Spruce CO docs
Unit Count | 75 |  | Submittal TOC (102 Type B + 6 Type A/ADA)
Work Period | 2017-09 start → 2019-08 (24 months) |  | JDR PR/AR dates
CONTRACT VALUE |  | NET PROFIT | DIRECT COST | LABOR HOURS
855264 |  | 266378.39 | 588885.61 | 7722.75
Original $832,900.00 + ($22,364.00) COs (2.69%) |  | 31.1% margin | 68.9% of revenue | 24 workers
SCOPE OF WORK
Full plumbing installation per Division 22: underground, garage, rough-in, finish, gas, water main, insulation, roof drains.
75-unit mixed-use (102 Type B + 6 Type A/ADA) at 838 NE 66th Street, Seattle, WA 98115, 7-story midrise multi-family (Type 1A podium + Type VA above).
GC: Blueprint (2044SH); Owner: Blueprint 836, LLC (self-build: developer, GC, and owner entity shared).
Insurance: Not Wrap (retail-adjacent residential).
Project team: Andrew Withnell (GC PM) · Scott McSpadden / Stefan Fjeldsted (GC Sup) · TBD — per Plans: Franklin Engineering MEP; Blueprint design-build (Architect) · Mike Donelson (OWP Dir Const / VP per signed subcontract) (OWP signatory).
SOURCES
Canonical financial source: 2044 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
Job totals (JDR footer): Revenue $855,264.00 / Expenses $588,885.61 / Net $266,378.39 / Retainage $0.00
Source breakdown (derived): PR $334,449.89 · AP $216,974.53 · GL $37,461.19
Contract: Lump Sum $832,900.00 → $855,264.00
Change Orders (executed): $22,364.00 net across 8 COs (CO log in enriched meta)
Project Team: Andrew Withnell (PM) · Scott McSpadden / Stefan Fjeldsted (Sup) · TBD — per Plans: Franklin Engineering MEP; Blueprint design-build · Blueprint 836, LLC (self-build: developer, GC, and owner entity shared)
PROJECT TEAM (OWP Job Info)
Role | Status | Name / Firm
GC | Extracted | Blueprint
GC PM | Extracted | Andrew Withnell
GC Superintendent | Extracted | Scott McSpadden / Stefan Fjeldsted
GC PE | N/A | N/A
Owner | Extracted | Blueprint 836, LLC (self-build: developer, GC, and owner entity shared)
Architect | Extracted | TBD — per Plans: Franklin Engineering MEP; Blueprint design-build
Structural | N/A | N/A
Acoustical | N/A | N/A
ADA Consultant | N/A | N/A
Interior Design | N/A | N/A
MEP Engineer | N/A | N/A
Insurance | Extracted | Not Wrap
OWP Signatory | Extracted | Mike Donelson (OWP Dir Const / VP per signed subcontract)

## Budget vs Actual
Budget vs Actual
All 27 cost codes from JDR. Contract $832,900 → $855,264.
Cost Code | Description | Original Budget | Revised Budget | Actual | Variance | % of Revised | Hours | Source
100 | Supervision | 6750 | 6750 | 1590.75 | -5159.25 | 23.57% | 30.5 | 2044 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
101 | Takeoff & Purchase Labor | 10875 | 10875 | 4858 | -6017 | 44.67% | 85 | 2044 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
110 | Underground Labor | 17585 | 17585 | 3411.5 | -14173.5 | 19.4% | 97 | 2044 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
111 | Garage Labor | 0 | 0 | 200 | 200 |  | 4 | 2044 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
112 | Canout Labor | 6850 | 6850 | 3108.5 | -3741.5 | 45.38% | 94.5 | 2044 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
120 | Roughin Labor | 96130 | 98690 | 150429.23 | 51739.23 | 152.4% | 5294.75 | 2044 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
130 | Finish Labor | 23100 | 22970 | 17219.5 | -5750.5 | 74.97% | 741.5 | 2044 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
140 | Gas Labor | 6000 | 6000 | 4551.5 | -1448.5 | 75.86% | 135.5 | 2044 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
141 | Water Main/Insulation Lab | 25485 | 25485 | 23970.37 | -1514.63 | 94.06% | 991 | 2044 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
142 | Mech Room Labor | 13400 | 13400 | 9685 | -3715 | 72.28% | 249 | 2044 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
210 | Underground Material | 16585 | 16585 | 1317.75 | -15267.25 | 7.945% |  | 2044 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
211 | Garage Material | 0 | 0 | 2172.87 | 2172.87 |  |  | 2044 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
212 | Canout Material | 8220 | 8220 | 5102.82 | -3117.18 | 62.08% |  | 2044 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
220 | Roughin Material | 44200 | 45350 | 42382.13 | -2967.87 | 93.46% |  | 2044 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
230 | Finish Material | 147457 | 163316 | 133693.08 | -29622.92 | 81.86% |  | 2044 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
240 | Gas Material | 6800 | 6800 | 2098.38 | -4701.62 | 30.86% |  | 2044 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
241 | Water Main/Insulation Mat | 26630 | 26630 | 14099.66 | -12530.34 | 52.95% |  | 2044 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
242 | Mech Room Material | 12500 | 12500 | 15511.19 | 3011.19 | 124.1% |  | 2044 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
243 | Condensation Drains Mat | 0 | 0 | 0 | 0 |  |  | 2044 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
600 | Subcontractor | 1000 | 1000 | 3900 | 2900 | 390% |  | 2044 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
601 | Engineering/Plans | 21000 | 21000 | 25725.44 | 4725.44 | 122.5% |  | 2044 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
602 | Rental Equipment | 600 | 600 | 644.09 | 44.09 | 107.3% |  | 2044 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
603 | Permits & Licenses | 5370 | 5370 | 695 | -4675 | 12.94% |  | 2044 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
607 | Other Expenses | 7000 | 7000 | 8101.46 | 1101.46 | 115.7% |  | 2044 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
995 | Payroll Burden | 90717 | 91810.5 | 97584.65 | 5774.15 | 106.3% |  | 2044 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
998 | Payroll Taxes | 15772.39 | 15958.29 | 16832.74 | 874.45 | 105.5% |  | 2044 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
999 | Sales | -832900 | -855264 | -855264 | 0 | 100% |  | 2044 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
TOTAL |  | -222873.61 | -224519.21 | -266378.39 | -41859.18 |  | 7722.75

## Cost Breakdown
Cost Breakdown by Category
Direct cost composition by category from JDR cost codes
Category | Cost Codes | Actual $ | % of Direct Cost | % of Revenue | Source
Labor | 100,101,110,111,112,120,130,140,141,142 | 219024.35 | 37.19% | 25.61% | 2044 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
Material | 210,211,212,220,230,240,241,242,243 | 216377.88 | 36.74% | 25.3% | 2044 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
Overhead | 600,601,602,603,607 | 39065.99 | 6.634% | 4.568% | 2044 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
Payroll Burden | 995 | 97584.65 | 16.57% | 11.41% | 2044 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
Payroll Taxes | 998 | 16832.74 | 2.858% | 1.968% | 2044 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
TOTAL DIRECT COST |  | 588885.61 | 100% | 68.85%

## Material
Material Purchases — AP Vendors
Material + subcontractor spend by vendor from JDR AP records
Vendor ID | Vendor Name | Total Spend | # Transactions | Category (inferred) | Source
1231KS | Keller Supply Company | 59482.56 | 26 | Plumbing / Supplies | 2044 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
1380RS | Rosen Supply Kirkland | 47454.86 | 57 | Plumbing / Supplies | 2044 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
7230BB | Best Bath Systems | 36061.49 | 3 | Uncategorized | 2044 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
1625FE | Franklin Engineering | 25565 | 11 | Engineering (601) | 2044 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
1130CS | Consolidated Supply Co. | 20046.51 | 19 | Plumbing / Supplies | 2044 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
1234CO | Capital One Credit Card | 8902.53 | 26 | Credit Card (mixed) | 2044 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
1175FE | Ferguson Enterprises, Inc. #3007 | 8007.38 | 5 | Plumbing / Supplies | 2044 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
5560CH | California Hydronics Corp | 4101 | 3 | Plumbing / Supplies | 2044 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
3129MR | Mechanical Resource Services, Inc. | 3750 | 1 | Uncategorized | 2044 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
2044RS | Rosen Supply Company, Inc. $66th Apts | 1317.75 | 4 | Plumbing / Supplies | 2044 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
8056MS | Mechanical Service & Integration LLC | 800 | 1 | Uncategorized | 2044 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
2713AR | Ahern Rentals | 644.09 | 3 | Uncategorized | 2044 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
3612MS | Mechanical Sales, Inc. | 317.79 | 2 | Plumbing / Supplies | 2044 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
2044CS | Consolidated Supply Co. $66th Apts | 197.94 | 1 | Plumbing / Supplies | 2044 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
1288DR | DRSi | 160.44 | 3 | Uncategorized | 2044 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
1641AR | A.R. Brown Backflow Testing | 150 | 1 | Testing subcontractor | 2044 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
1978FC | Fastenal Company | 15.19 | 1 | Uncategorized | 2044 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
TOTAL |  | 216974.53 | 167

## Crew & Labor
Crew & Labor — Worker Roster
All 24 unique payroll workers. OWP signatory: Mike Donelson (OWP Dir Const / VP per signed subcontract).
Worker ID | Worker Name | Total Hours | Gross Pay | Blended Wage ($/hr) | # Work Days | Source
HO14 | Holmes, Anthony R | 1464 | 53613 | 36.6209 | 41 | 2044 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
TA96 | Taylor, Evan R | 1161.5 | 28903 | 24.8842 | 35 | 2044 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
WE55 | Wennig, Johnathan M | 779.5 | 22383 | 28.7146 | 26 | 2044 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
LE17 | Lee, Ha Nul | 739.25 | 12983.25 | 17.5627 | 20 | 2044 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
ME52 | Mendoza, Edgar E | 700.5 | 15829 | 22.5967 | 20 | 2044 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
LO58 | Lopez Reyes, Boris O | 450.5 | 8127 | 18.04 | 15 | 2044 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
MC09 | McCabe, Thomas C | 380.25 | 13520.25 | 35.5562 | 13 | 2044 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
KI55 | Kinssies, Jr, John E | 311.25 | 8886.25 | 28.5502 | 18 | 2044 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
EL33 | Eliassen, Cory H | 271 | 7317 | 27 | 12 | 2044 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
TR60 | Trower-Kelly, Fidel D | 202.5 | 3645 | 18 | 9 | 2044 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
VA98 | Vazquez Popoca, Jose N | 190.5 | 3048 | 16 | 7 | 2044 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
SE64 | Sepulveda Gonzalez, Alfredo | 190 | 6650 | 35 | 6 | 2044 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
CR87 | Cruz Reyes, Jose | 186 | 5057 | 27.1882 | 4 | 2044 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
HU06 | Hubbard, Robert W | 147 | 7336.5 | 49.9082 | 22 | 2044 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
WA35 | Waites, Thaddeus Z | 123.5 | 5187 | 42 | 7 | 2044 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
AN14 | Anderson, Richard P | 69.5 | 2945 | 42.3741 | 15 | 2044 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
BA70 | Barnhart, Joseph N | 65.5 | 3054 | 46.626 | 21 | 2044 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
MU70 | Murphy, Darray E | 64 | 1206 | 18.8438 | 2 | 2044 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
GE69 | Gerard, Jeffrey S | 62 | 3130 | 50.4839 | 35 | 2044 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
SA54 | Sanders, Allen O | 57.5 | 2817.5 | 49 | 14 | 2044 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
DO56 | Donelson, Richard T | 53.5 | 3318.75 | 62.0327 | 32 | 2044 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
RO06 | Roberts, Lake A | 27 | 540 | 20 | 2 | 2044 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
ST02 | Stahlschmidt, John P | 24 | 456 | 19 | 3 | 2044 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
GA70 | Garcia, Jordan X | 2.5 | 80 | 32 | 1 | 2044 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
TOTAL |  | 7722.75 | 220032.5

## Crew Analytics
Crew Analytics
Team-level labor productivity, concentration, wage dispersion
TEAM-LEVEL METRICS
Metric | Value | Notes | Source
Total Workers | 24 | Unique payroll IDs | 2044 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
Total Labor Hours | 7722.75 | Sum of labor codes | 2044 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
Total Gross Pay | 220032.5 | Sum of labor codes | 2044 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
Blended Gross Wage ($/hr) | 28.4915 | Labor$/Hrs (pre-burden) | Derived
Top Worker Hours Share | 18.96% | HO14 Holmes, Anthony R (1464 hrs) | Derived
Top 5 Workers Hours Share | 62.73% | Concentration metric | Derived
Highest Wage Rate ($/hr) | 62.0327 | Single-worker blended | Derived
Lowest Wage Rate ($/hr) | 16 | Single-worker blended | Derived
Avg Hours per Worker | 321.7812 | Includes short-tenure workers | Derived
Avg Project Days per Worker | 15.8333 | Mean days | Derived

## Productivity
Productivity Metrics
Normalized ratios. Per-unit from 75 units (634 fixtures).
Metric | Value | Basis | Source / Note
Revenue per Labor Hour | 110.746 | USD/hr
Profit per Labor Hour | 34.4927 | USD/hr
Labor Cost per Hour (blended) | 28.3609 | USD/hr | Pre-burden
Fully-Loaded Labor Rate ($/hr) | 58.1227 | USD/hr | Incl burden+taxes
Burden Multiplier | 1.3421 | x | Fully-loaded/blended
Rough-in Hours (code 120) | 5294.75 | hrs
Finish Hours (code 130) | 741.5 | hrs
Rough-in % of Total Hours | 68.56% | %
Gross Margin | 31.15% | %
Labor % of Revenue | 25.61% | %
Material % of Revenue | 25.3% | %
Direct Cost Ratio | 68.85% | % | All exp/Rev
Revenue per Unit (75) | 11403.52 | USD | 75 units
Labor Hours per Unit | 102.97 | hrs
Labor Cost per Unit | 2920.3247 | USD
Material Cost per Unit | 2885.0384 | USD
Direct Cost per Unit | 7851.8081 | USD
Rough-in Hours per Unit | 70.5967 | hrs
Revenue per Fixture | 1348.9968 | USD | 634 fixtures
Hours per Fixture | 12.181 | hrs

## PO Commitments
PO Commitments
Inbound contract (GC → OWP). Outbound vendor commitments — see Material tab.
PO # | Date | Issuer | Type | Status | Description | Amount | Source
PRIME | 2017-08-03 | Blueprint | Lump Sum Subcontract | Closed | Track 66 Apartments plumbing (75 units, 7 stories) — per Div 22 | 832900 | 2044-Shelter Holdings subcontract SC-03-07-6505 + Boren & Spruce CO docs
CO-NET | — | Blueprint | Change Orders (executed, 8 COs) | Executed | Net CO impact (Sage 999 rev - orig) | 22364 | 2044 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
TOTAL (contract + COs) | [5 empty] | 855264

## Billing & SOV
Billing & Schedule of Values
133 invoices to Blueprint. Retainage $0.00.
Invoice # | Date | Total Billed (signed) | Retainage (signed) | # Lines | Source
559 | 01/18/19 | -68875 | 0 | 9 | 2044 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
566 | 02/20/19 | -29350 | 0 | 2 | 2044 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
593 | 02/21/18 | -45550 | 0 | 2 | 2044 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
431 | 03/20/18 | -63410 | 0 | 3 | 2044 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
432 | 03/20/18 | -27500 | 0 | 1 | 2044 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
448 | 03/20/18 | 63410 | 0 | 3 | 2044 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
502 | 05/18/18 | -13000 | 0 | 3 | 2044 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
508 | 05/20/19 | -88536 | 0 | 8 | 2044 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
613 | 06/19/19 | -25758 | 0 | 3 | 2044 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
602 | 07/19/19 | -12200 | 0 | 2 | 2044 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
525 | 07/20/18 | -86525 | 0 | 6 | 2044 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
590 | 08/20/18 | -64815 | 0 | 4 | 2044 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
753 | 08/20/19 | -650 | 0 | 1 | 2044 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
756 | 08/20/19 | 650 | 0 | 1 | 2044 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
757 | 08/20/19 | -2000 | 0 | 2 | 2044 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
473 | 09/19/18 | -131284 | 0 | 6 | 2044 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
528 | 10/19/18 | -189861 | 0 | 9 | 2044 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
353 | 12/14/18 | -70010 | 0 | 5 | 2044 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
TOTAL (signed) |  | -855264 | 0

## Insights
Insights & Observations
Narrative findings from JDR + GDrive CO log
# | Insight | Detail | Confidence | Source
1 | MARGIN PROFILE | Net profit $266,378.39 on $855,264.00 revenue = 31.1% gross margin. | Verified | 2044 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
2 | CONTRACT CHANGE | Original $832,900.00 → final $855,264.00 = $+22,364.00 net (2.69%) across 8 executed COs. | Verified | 2044 Job Detail Report.pdf (Sage Timberline, 04/03/2026) + CO log
3 | LABOR PROFILE | Labor cost $219,024.35 (25.6% of rev) across 7,723 hrs and 24 workers. Blended wage $28.36/hr. | Verified | 2044 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
4 | VENDOR CONCENTRATION | Top 5 AP vendors: ~$188,610.42 (87% of AP). Top vendor: Keller Supply Company ($59,482.56). | Verified | 2044 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
5 | RETAINAGE | Retainage $0.00 — cleared. | Verified | 2044 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
6 | ROUGH-IN SHARE | Code 120 Roughin Labor = 5,295 hrs (69% of labor hours). | Verified | 2044 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
7 | TOP COST CODE | Largest actual cost: 120 Roughin Labor = $150,429.23 | Verified | 2044 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
8 | WORKER CONCENTRATION | Top worker Holmes, Anthony R = 1,464 hrs (19% of total). | Verified | 2044 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
9 | INSURANCE | Not Wrap — retail-adjacent mixed-use. | Verified | OWP Project List with Schedule - UPDATED 04-01-26.xlsx
10 | SCOPE CONTEXT | Track 66 Apartments — 75-unit 7-story midrise (68 standard + 4 Type A ADA) + P1/P2 parking at 838 NE 66th Street, Seattle, WA 98115. | Verified | Submittal TOC + scope doc

## Benchmark KPIs
Benchmark KPIs
Normalized metrics for cross-project comparison
KPI | Data Name | Value | Category | Notes | Confidence | Source Document
Job Number | job_number | 2044 | Profile | OWP job ID | Verified | 2044 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
Job Name | job_name | Blueprint Track 66 Apartments (aka Roosevelt 66th, 838 NE 66th) | Profile |  | Verified | 2044 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
General Contractor | general_contractor | Blueprint | Profile |  | Verified | OWP Project List with Schedule - UPDATED 04-01-26.xlsx
Owner | owner | Blueprint 836, LLC (self-build: developer, GC, and owner entity shared) | Profile |  | Verified | OWP Project List with Schedule - UPDATED 04-01-26.xlsx
Architect | architect | TBD — per Plans: Franklin Engineering MEP; Blueprint design-build | Profile |  | Verified | Track 66 Apartments project info.pdf
Location | location | 838 NE 66th Street, Seattle, WA 98115 | Profile |  | Verified | OWP Project List with Schedule - UPDATED 04-01-26.xlsx
Project Type | project_type | Mid-rise multi-family residential (urban infill): 68 standard + 7 Type A ADA units + common amenity (bike room, trash, coffee bar). Per Job Info xlsx: 75 units; per Schedule sheet: 78 (Job Ticket confirms 75 by fixture count). | Profile |  | Verified | Scope + Submittal TOC
Insurance Type | insurance | Not Wrap | Profile |  | Verified | OWP Project List with Schedule - UPDATED 04-01-26.xlsx
GC PM | gc_pm | Andrew Withnell | Profile |  | Verified | 2044-Shelter Holdings subcontract SC-03-07-6505 + Boren & Spruce CO docs
GC Sup | gc_sup | Scott McSpadden / Stefan Fjeldsted | Profile |  | Verified | 2044-Shelter Holdings subcontract SC-03-07-6505 + Boren & Spruce CO docs
OWP Signatory | owp_signatory | Mike Donelson (OWP Dir Const / VP per signed subcontract) | Profile |  | Verified | 2044-Shelter Holdings subcontract SC-03-07-6505 + Boren & Spruce CO docs
Contract Signed Date | contract_signed_date | 2017-08-03 | Profile |  | Verified | 2044-Shelter Holdings subcontract SC-03-07-6505 + Boren & Spruce CO docs
Work Start | start_date | 2017-09 | Profile |  | Verified | 2044 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
Work End | end_date | 2019-08 | Profile |  | Verified | 2044 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
Duration (months) | duration_months | 24 | Profile |  | Verified | Derived
Unit Count | unit_count | 75 | Profile | 102 Type B + 6 Type A/ADA | Verified | Submittal TOC
Total Fixtures | total_fixtures | 634 | Profile | 656 unit + 98 retail/common | Verified | Submittal TOC
Contract Original | contract_original | 832900 | Financial |  | Verified | OWP Project List with Schedule - UPDATED 04-01-26.xlsx
Contract Final | contract_final | 855264 | Financial |  | Verified | OWP Project List with Schedule - UPDATED 04-01-26.xlsx
Change Orders ($) | co_net | 22364 | Financial | 8 executed | Verified | 2044 Job Detail Report.pdf (Sage Timberline, 04/03/2026) + CO log
CO % of Contract | co_pct | 2.685% | Financial |  | Verified | Derived
Revenue | revenue | 855264 | Financial | AR total | Verified | 2044 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
Direct Cost | direct_cost | 588885.61 | Financial | JDR Expenses | Verified | 2044 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
Net Profit | net_profit | 266378.39 | Financial | Rev - Exp | Verified | 2044 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
Gross Margin | gross_margin | 31.15% | Financial |  | Verified | Derived
Retainage | retainage | 0 | Financial | JDR AR retainage | Verified | 2044 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
Retainage % of Revenue | retainage_pct | 0% | Financial |  | Verified | Derived
Labor Cost | labor_cost | 219024.35 | Labor | Codes 100-151 | Verified | 2044 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
Material Cost | material_cost | 216377.88 | Material | Codes 210-245 | Verified | 2044 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
Overhead Cost | overhead_cost | 39065.99 | Financial | Codes 600-607 | Verified | 2044 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
Burden Cost | burden_cost | 97584.65 | Labor | Code 995 | Verified | 2044 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
Tax Cost | tax_cost | 16832.74 | Labor | Code 998 | Verified | 2044 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
Total Labor Hours | total_hours | 7722.75 | Labor | Sum labor codes | Verified | 2044 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
Total Workers | total_workers | 24 | Labor | Unique PR IDs | Verified | 2044 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
Blended Gross Wage | blended_wage | 28.3609 | Labor |  | Verified | Derived
Fully-Loaded Wage | loaded_wage | 58.1227 | Labor |  | Verified | Derived
Burden Multiplier | burden_mult | 1.3421 | Labor |  | Verified | Derived
Rough-in Hours | roughin_hours | 5294.75 | Labor | Code 120 | Verified | 2044 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
Finish Hours | finish_hours | 741.5 | Labor | Code 130 | Verified | 2044 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
Revenue per Hour | rev_per_hour | 110.746 | Productivity |  | Verified | Derived
Profit per Hour | profit_per_hour | 34.4927 | Productivity |  | Verified | Derived
Revenue per Unit | rev_per_unit | 11403.52 | Productivity | 75 units | Verified | Derived
Direct Cost per Unit | cost_per_unit | 7851.8081 | Productivity |  | Verified | Derived
Hours per Unit | hours_per_unit | 102.97 | Productivity |  | Verified | Derived
Revenue per Fixture | rev_per_fixture | 1348.9968 | Productivity | 634 fixtures | Verified | Derived
Labor % of Revenue | labor_pct | 25.61% | Cost Mix |  | Verified | Derived
Material % of Revenue | material_pct | 25.3% | Cost Mix |  | Verified | Derived
Total Vendors | total_vendors | 17 | Material |  | Verified | 2044 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
Total Invoices | total_invoices | 18 | Billing |  | Verified | 2044 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
Top Worker Share | top_worker_share | 18.96% | Crew |  | Verified | Derived
Top 5 Worker Share | top5_worker_share | 62.73% | Crew |  | Verified | Derived
Cost Codes Active | cost_code_count | 27 | Structure |  | Verified | 2044 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
Executed CO Count | executed_co_count | 8 | Documents |  | Verified | CO log
COR Count | cor_count | 10 | Documents |  | Verified | GDrive COR folder
RFI/ASI Count | rfi_asi_count | 0 | Documents |  | Verified | GDrive ASI-RFI folder
Submittal Count | submittal_count | 2 | Documents |  | Verified | GDrive Submittals
PO Total (all) | po_count_total | 110 | Documents | placed+scheduled+completed | Verified | GDrive POs

## Vendors
Vendors — AP Summary
Vendor-level spend ranking
Rank | Vendor ID | Vendor Name | Total Spend | # Transactions | % of AP | Source
1 | 1231KS | Keller Supply Company | 59482.56 | 26 | 27.41% | 2044 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
2 | 1380RS | Rosen Supply Kirkland | 47454.86 | 57 | 21.87% | 2044 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
3 | 7230BB | Best Bath Systems | 36061.49 | 3 | 16.62% | 2044 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
4 | 1625FE | Franklin Engineering | 25565 | 11 | 11.78% | 2044 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
5 | 1130CS | Consolidated Supply Co. | 20046.51 | 19 | 9.239% | 2044 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
6 | 1234CO | Capital One Credit Card | 8902.53 | 26 | 4.103% | 2044 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
7 | 1175FE | Ferguson Enterprises, Inc. #3007 | 8007.38 | 5 | 3.69% | 2044 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
8 | 5560CH | California Hydronics Corp | 4101 | 3 | 1.89% | 2044 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
9 | 3129MR | Mechanical Resource Services, Inc. | 3750 | 1 | 1.728% | 2044 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
10 | 2044RS | Rosen Supply Company, Inc. $66th Apts | 1317.75 | 4 | 0.6073% | 2044 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
11 | 8056MS | Mechanical Service & Integration LLC | 800 | 1 | 0.3687% | 2044 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
12 | 2713AR | Ahern Rentals | 644.09 | 3 | 0.2969% | 2044 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
13 | 3612MS | Mechanical Sales, Inc. | 317.79 | 2 | 0.1465% | 2044 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
14 | 2044CS | Consolidated Supply Co. $66th Apts | 197.94 | 1 | 0.09123% | 2044 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
15 | 1288DR | DRSi | 160.44 | 3 | 0.07394% | 2044 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
16 | 1641AR | A.R. Brown Backflow Testing | 150 | 1 | 0.06913% | 2044 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
17 | 1978FC | Fastenal Company | 15.19 | 1 | 0.007001% | 2044 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
TOTAL |  |  | 216974.53 | 167

## Change Log
Change Log — Master Register
Contract, 8 executed COs, retainage events — JDR + GDrive CO folder
Event ID | Type | Date | Subject | Originator | Cost Impact ($) | Status | Source
CONTRACT-ORIG | Contract | 2017-08-03 | Prime subcontract — Lump Sum $832,900.00 | Blueprint | 832900 | Executed | 2044-Shelter Holdings subcontract SC-03-07-6505 + Boren & Spruce CO docs
CO-01 | Change Order | — | Delete 2 Common Area Baths (credit) | Blueprint | -4841 | Executed | GDrive CO 1
CO-02 | Change Order | — | Remove kitchen sinks from scope (credit — kitchen sinks by others) | Blueprint | -5154 | Executed | GDrive CO 2
CO-03 | Change Order | — | Best Bath Shower Pans & Stalls (upgrade from base) | Blueprint | 11652 | Executed | GDrive CO 3
CO-04 | Change Order | — | Matte Black Delta Trinsic Fixtures (upgrade) | Blueprint | 11790 | Executed | GDrive CO 4
CO-05 | Change Order | — | Supply loose drains, cast iron in bathroom dropped lids (added scope) | Blueprint | 6209 | Executed | GDrive CO 5
CO-06 | Change Order | — | Amenity Lav Upgrade (common area lav/faucet change) | Blueprint | 708 | Executed | GDrive CO 6
CO-07 | Change Order | — | Canopy Drain (entrance canopy with piping within canopy) | Blueprint | 650 | Executed | GDrive CO 7
CO-08 | Change Order | — | Add Sink L7 (L7 Kitchen Faucet added) | Blueprint | 1350 | Executed | GDrive CO 8
FIRST-INVOICE | Invoice | 01/18/19 | First billing (per JDR) | Sub (OWP) | 0 | Paid | 2044 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
LAST-INVOICE | Invoice | 12/14/18 | Last billing (per JDR) | Sub (OWP) | 0 | Paid | 2044 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
RETAINAGE-OPEN | Retainage | As of 04/03/2026 | Retainage $0.00 (cleared) | GC | 0 | Cleared | 2044 Job Detail Report.pdf (Sage Timberline, 04/03/2026)

## Root Cause Analysis
Root Cause Analysis
Primary variance drivers by category
Category | Codes | Net $ Variance | Root Cause (inferred) | Notes
Contract Change | 999 (Sales) | 22364 | JDR-implied net CO impact | $832,900 → $855,264 (8 executed COs)
Labor | 100,101,110,111,112,120,130,140,141,142,143,145,150 | 10419.35 | Labor variance vs revised budget | 24 workers
Material | 210,211,212,213,220,230,240,241,242,243,244,245 | -63023.12 | Material procurement variance | 17 vendors
Overhead | 600,601,602,603,604,607 | 4095.99 | Engineering/permits/subcon variance
Burden+Tax | 995+998 | 6648.6 | Payroll accrual tracking labor
TOTAL NET VARIANCE |  | -19495.18
RESPONSIBILITY ATTRIBUTION
Responsible Party | # Drivers | Net $ Impact | Notes
GC / Owner (scope changes) | 8 | 22364 | Aggregate executed COs
Sub (OWP) labor performance | 10 | 10419.35 | Hours + rate vs budget
Sub (OWP) material procurement | 9 | -63023.12 | 17 vendors
OWP burden accrual | 2 | 6648.6 | Payroll burden + tax
OWP overhead | 5 | 4095.99 | Engineering/permits/subcon

## Predictive Signals
Predictive Signals
Leading indicators from JDR + CO log
CURRENT-STATE SIGNALS
Indicator | Current Value | Benchmark | Status | Meaning
Contract Change % | 2.69% | ±10% | HEALTHY | +2.69% net (8 COs)
Labor % of Revenue | 25.61% | <30% | HEALTHY | 25.6%
GL Overhead % of Revenue | 4.38% | <5% | HEALTHY | 4.4%
Vendor Concentration (Top 5) | 86.93% | <95% | HEALTHY | Top 5 = 87% of AP
Retainage % | 0% | <10% | HEALTHY | 0.0%
Gross Margin | 31.15% | >30% | HEALTHY | 31.1%
Labor Hrs Total | 7722.75 | varies | INFO | 7,723 hrs, 24 workers
Worker Concentration (top 1) | 18.96% | <25% | HEALTHY | 19.0% (Holmes, Anthony R)
Rough-in Labor Share | 68.56% | 40-65% | WATCH | 69%
Retainage Legacy | CLEARED | <90 days post-closeout | HEALTHY | $0.00
FORECAST MODELS
Forecast | Current Estimate | Confidence | Driver | Model Note
Final margin (actual) | 31.15% | Actual | Job closed | 31.1%
Retainage collection | N/A | N/A | Closed | Closed
Unit-level economics | $11,404/unit rev, $3,552/unit profit | Verified | 75 units | Mid-rise multi-family residential (urban infill): 68 standard + 7 Type A ADA units + common amenity (bike room, trash, coffee bar). Per Job Info xlsx: 75 units; per Schedule sheet: 78 (Job Ticket confirms 75 by fixture count).

## Metric Registry
Metric Registry — Cortex Data Catalog
Every metric with data_label, confidence, and source
# | Data Label | Human Label | Value | Unit | Source Tab | Confidence | Source Document(s)
1 | job_number | Job Number | 2044 | id | Benchmark KPIs | Verified | 2044 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
2 | job_name | Job Name | Blueprint Track 66 Apartments (aka Roosevelt 66th, 838 NE 66th) | text | Benchmark KPIs | Verified | 2044 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
3 | general_contractor | General Contractor | Blueprint | text | Benchmark KPIs | Verified | OWP Project List with Schedule - UPDATED 04-01-26.xlsx
4 | owner | Owner | Blueprint 836, LLC (self-build: developer, GC, and owner entity shared) | text | Benchmark KPIs | Verified | OWP Project List with Schedule - UPDATED 04-01-26.xlsx
5 | architect | Architect | TBD — per Plans: Franklin Engineering MEP; Blueprint design-build | text | Benchmark KPIs | Verified | Track 66 Apartments project info.pdf
6 | location | Location | 838 NE 66th Street, Seattle, WA 98115 | text | Benchmark KPIs | Verified | OWP Project List with Schedule - UPDATED 04-01-26.xlsx
7 | project_type | Project Type | Mid-rise multi-family residential (urban infill): 68 standard + 7 Type A ADA units + common amenity (bike room, trash, coffee bar). Per Job Info xlsx: 75 units; per Schedule sheet: 78 (Job Ticket confirms 75 by fixture count). | text | Benchmark KPIs | Verified | Scope + Submittal TOC
8 | insurance | Insurance Type | Not Wrap | text | Benchmark KPIs | Verified | OWP Project List with Schedule - UPDATED 04-01-26.xlsx
9 | gc_pm | GC PM | Andrew Withnell | text | Benchmark KPIs | Verified | 2044-Shelter Holdings subcontract SC-03-07-6505 + Boren & Spruce CO docs
10 | gc_sup | GC Sup | Scott McSpadden / Stefan Fjeldsted | text | Benchmark KPIs | Verified | 2044-Shelter Holdings subcontract SC-03-07-6505 + Boren & Spruce CO docs
11 | owp_signatory | OWP Signatory | Mike Donelson (OWP Dir Const / VP per signed subcontract) | text | Benchmark KPIs | Verified | 2044-Shelter Holdings subcontract SC-03-07-6505 + Boren & Spruce CO docs
12 | contract_signed_date | Contract Signed Date | 2017-08-03 | date | Benchmark KPIs | Verified | 2044-Shelter Holdings subcontract SC-03-07-6505 + Boren & Spruce CO docs
13 | start_date | Work Start | 2017-09 | date | Benchmark KPIs | Verified | 2044 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
14 | end_date | Work End | 2019-08 | date | Benchmark KPIs | Verified | 2044 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
15 | duration_months | Duration (months) | 24 | months | Benchmark KPIs | Verified | Derived
16 | unit_count | Unit Count | 75 | units | Benchmark KPIs | Verified | Submittal TOC
17 | total_fixtures | Total Fixtures | 634 | count | Benchmark KPIs | Verified | Submittal TOC
18 | contract_original | Contract Original | 832900 | USD | Benchmark KPIs | Verified | OWP Project List with Schedule - UPDATED 04-01-26.xlsx
19 | contract_final | Contract Final | 855264 | USD | Benchmark KPIs | Verified | OWP Project List with Schedule - UPDATED 04-01-26.xlsx
20 | co_net | Change Orders ($) | 22364 | USD | Benchmark KPIs | Verified | 2044 Job Detail Report.pdf (Sage Timberline, 04/03/2026) + CO log
21 | co_pct | CO % of Contract | 2.685% | % | Benchmark KPIs | Verified | Derived
22 | revenue | Revenue | 855264 | USD | Benchmark KPIs | Verified | 2044 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
23 | direct_cost | Direct Cost | 588885.61 | USD | Benchmark KPIs | Verified | 2044 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
24 | net_profit | Net Profit | 266378.39 | USD | Benchmark KPIs | Verified | 2044 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
25 | gross_margin | Gross Margin | 31.15% | % | Benchmark KPIs | Verified | Derived
26 | retainage | Retainage | 0 | USD | Benchmark KPIs | Verified | 2044 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
27 | retainage_pct | Retainage % of Revenue | 0% | % | Benchmark KPIs | Verified | Derived
28 | labor_cost | Labor Cost | 219024.35 | USD | Benchmark KPIs | Verified | 2044 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
29 | material_cost | Material Cost | 216377.88 | USD | Benchmark KPIs | Verified | 2044 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
30 | overhead_cost | Overhead Cost | 39065.99 | USD | Benchmark KPIs | Verified | 2044 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
31 | burden_cost | Burden Cost | 97584.65 | USD | Benchmark KPIs | Verified | 2044 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
32 | tax_cost | Tax Cost | 16832.74 | USD | Benchmark KPIs | Verified | 2044 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
33 | total_hours | Total Labor Hours | 7722.75 | hours | Benchmark KPIs | Verified | 2044 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
34 | total_workers | Total Workers | 24 | count | Benchmark KPIs | Verified | 2044 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
35 | blended_wage | Blended Gross Wage | 28.3609 | USD/hr | Benchmark KPIs | Verified | Derived
36 | loaded_wage | Fully-Loaded Wage | 58.1227 | USD/hr | Benchmark KPIs | Verified | Derived
37 | burden_mult | Burden Multiplier | 1.3421 | x | Benchmark KPIs | Verified | Derived
38 | roughin_hours | Rough-in Hours | 5294.75 | hours | Benchmark KPIs | Verified | 2044 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
39 | finish_hours | Finish Hours | 741.5 | hours | Benchmark KPIs | Verified | 2044 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
40 | rev_per_hour | Revenue per Hour | 110.746 | USD/hr | Benchmark KPIs | Verified | Derived
41 | profit_per_hour | Profit per Hour | 34.4927 | USD/hr | Benchmark KPIs | Verified | Derived
42 | rev_per_unit | Revenue per Unit | 11403.52 | USD | Benchmark KPIs | Verified | Derived
43 | cost_per_unit | Direct Cost per Unit | 7851.8081 | USD | Benchmark KPIs | Verified | Derived
44 | hours_per_unit | Hours per Unit | 102.97 | hours | Benchmark KPIs | Verified | Derived
45 | rev_per_fixture | Revenue per Fixture | 1348.9968 | USD | Benchmark KPIs | Verified | Derived
46 | labor_pct | Labor % of Revenue | 25.61% | % | Benchmark KPIs | Verified | Derived
47 | material_pct | Material % of Revenue | 25.3% | % | Benchmark KPIs | Verified | Derived
48 | total_vendors | Total Vendors | 17 | count | Benchmark KPIs | Verified | 2044 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
49 | total_invoices | Total Invoices | 18 | count | Benchmark KPIs | Verified | 2044 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
50 | top_worker_share | Top Worker Share | 18.96% | % | Benchmark KPIs | Verified | Derived
51 | top5_worker_share | Top 5 Worker Share | 62.73% | % | Benchmark KPIs | Verified | Derived
52 | cost_code_count | Cost Codes Active | 27 | count | Benchmark KPIs | Verified | 2044 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
53 | executed_co_count | Executed CO Count | 8 | count | Benchmark KPIs | Verified | CO log
54 | cor_count | COR Count | 10 | count | Benchmark KPIs | Verified | GDrive COR folder
55 | rfi_asi_count | RFI/ASI Count | 0 | count | Benchmark KPIs | Verified | GDrive ASI-RFI folder
56 | submittal_count | Submittal Count | 2 | count | Benchmark KPIs | Verified | GDrive Submittals
57 | po_count_total | PO Total (all) | 110 | count | Benchmark KPIs | Verified | GDrive POs

## Reconciliation
Reconciliation
Cross-sheet formula checks
# | Check | Value A | Value B | Delta | Status | Tabs
1 | Revenue = Contract Final | 855264 | 855264 | 0 | TIES | 1↔8
2 | Expenses = Labor+Mat+OH+Burden+Tax | 588885.61 | 588885.61 | 0 | TIES | 1↔3
3 | Net Profit = Revenue - Expenses | 266378.39 | 266378.39 | 0 | TIES | 1↔Derived
4 | Sage 999 actual = -Revenue | 855264 | 855264 | 0 | TIES | 2↔1
5 | Total Hours = Worker hours sum | 7722.75 | 7722.75 | 0 | TIES | 5↔2
6 | Contract Final - Orig = CO implied | 22364 | 22364 | 0 | TIES | 11↔Derived
7 | Worker count | 24 | 24 | 0 | TIES | 5↔1
8 | Cost code count | 27 | 27 | 0 | TIES | 2↔16